REGIONAL INNOVATION PROJECT/PROGRAMME PROPOSAL

PART I: PROJECT/PROGRAMME INFORMATION

Title of Project/Programme:	Balkan Climate Adaptation Futures: A Regional Innovation Initiative for Resilience

Country/ Countries: 	Four Countries in the Western Balkans Region: Bosnia and Herzegovina (BiH), Montenegro, North Macedonia, Serbia

Thematic Focal Area: 		           	            Innovative climate finance

Type of Implementing Entity: 			Multilateral Implementing Entity (MIE)

Implementing Entity: 				United Nations Development Programme (UNDP)

Executing Entities: 				UNDP

Amount of Financing Requested: 		US$ 5,000,000.00

Table of Contents

PART I: PROJECT INFORMATION	3

Project Background and Context	3

Problem Statement	3

The Western Balkans Region	4

Climate Risk and Climate Change Vulnerabilities in the Western Balkans Region	8

Vulnerable Populations in the Western Balkans	21

Socio-Economic Dimensions of Vulnerability	23

Innovation Context in the Western Balkans	24

Urgency of Adaptation Investments at the Local Level	29

Project Objectives	31

Project Components and Financing	34

Projected Calendar	35

PART II: PROJECT JUSTIFICATION	36

Project Components and Contribution to Climate Resilience	36

Description of the Project Components	39

Promoting New and Innovative Solutions to Climate Change Adaptation	56

Scaling Up and Rolling Out Successful Adaptation Innovations	61

Economic, Social, and Environmental Benefits and Safeguards	61

Cost-Effectiveness of the Proposed Project and Added Value of the Regional Approach	63

Alignment with National, Sub-National and Regional Adaptation and Development Strategies	65

Compliance with National Technical Standards and the Adaptation Fund’s Environmental and Social Policy	67

Maximizing Synergy: Enhancing Regional Climate Resilience through Complementary Adaptation Initiatives	68

Learning and Knowledge Management Component	70

Consultative Process and Stakeholder Engagement Approach	72

Incorporating Diverse Perspectives on Innovation from Different Stakeholders	75

Justification for Funding Requested: Addressing the Full Cost of Climate Adaptation in the Western Balkans	76

Ensuring Sustainability of Project Outcomes in the Design Process	81

Overview of Environmental and Social Impacts and Risks Relevant to the Project	82

PART III:  IMPLEMENTATION ARRANGEMENTS	82

Project Management and Coordination Arrangements	82

Measures for Financial and Project Risk Management	86

Environmental and Social Risk Management Measures 	87

Monitoring and Evaluation Arrangements and Budgeted MEL Plan	89

Evaluation Plan	91

Results Framework for the Project Proposal: Milestones, Targets, and Indicators	92

Alignment of the Project with the Adaptation Fund's Results Framework	94

Detailed Budget Breakdown	96

Disbursement Schedule with Time-Bound Milestones	96

PART IV: ENDORSEMENT BY GOVERNMENTS AND CERTIFICATION BY THE IMPLEMENTING ENTITY	97

PART V: Annexes	98

# PART I: PROJECT INFORMATION

# Project Background and Context

Problem Statement
The Western Balkans, a region rich in cultural heritage and natural resources, faces a growing climate crisis that threatens its economic, social, and environmental stability. This Regional Innovation Project focuses on four countries: Bosnia and Herzegovina, Montenegro, North Macedonia, and Serbia, all of which are already experiencing severe climate impacts, including more frequent and intense droughts, floods, wildfires, and landslides, worsened by rising temperatures and erratic rainfall patterns. These climate events undermine agriculture, water systems, and energy infrastructure, while placing vulnerable communities—particularly rural populations, women, youth, and marginalized groups—at greater risk.

Despite progress in national climate strategies through the formulation of Nationally Determined Contributions (NDCs) and National Adaptation Plans (NAPs), there remains a significant gap in implementation. Local actors—such as civil society organizations (CSOs), micro small and medium-sized enterprises (MSMEs), cooperatives, and community-based groups—often face challenges in accessing the financial and technical resources necessary to develop and scale context-relevant adaptation solutions. At the same time, the region's adaptation innovation ecosystems remain underdeveloped, with insufficient regional collaboration and limited knowledge exchange. These barriers contribute to slow progress and missed opportunities to leverage local adaptation innovation.

The Balkan Climate Adaptation Futures: A Regional Innovation Initiative for Resilience (hereafter referred to as the Regional Project) seeks to address these gaps by fostering regional collaboration, empowering local actors, and supporting the development and acceleration of locally-led, scalable adaptation innovations. By building on existing innovation capacities and enhancing coordination across the region, the project will reduce transaction costs, streamline processes, and ensure more effective implementation of adaptation solutions and focus on their replication and scalability to generate more impact. It will also promote the integration of lessons learned from previous and ongoing relevant adaptation initiatives to accelerate progress toward resilience, particularly for vulnerable communities.

### The Western Balkans Region

The Western Balkans region includes six countries and one territory - Albania, Bosnia and Herzegovina, Croatia, Montenegro, North Macedonia, Serbia and Kosovo . This proposal targets four countries in the subregion: Bosnia and Herzegovina, Montenegro, North Macedonia, and Serbia. The population of the region is declining due to factors like low birth rates and emigration. The current population numbers in the four countries involved are: Montenegro - 632,925 people, North Macedonia - 1,813,793 people, Bosnia and Herzegovina  - 3,139,803 people, and Serbia - 6,688,240 people. The real Gross Domestic Product (GDP) in the four countries grew by 3.8% (Bosnia and Herzegovina), 6.4% (Montenegro), 2.2% (North Macedonia) and 2.5% (Serbia). In the following three years, the growth rate was expected to increase. In 2025, Serbia is projected to have the highest GDP among the four countries ($92 billion), followed by Montenegro ($8.02 billion), North Macedonia ($17.27 billion), and Bosnia and Herzegovina. According to UNDP´s latest Human Development Report (2025), the four project countries present a high HDI and are included within the “very high human development” category, with the HDI index per country, presented below:

- Montenegro: the HDI is 0.862, ranking it 48th out of 193 countries.

- Serbia: the HDI is 0.883, ranking it 62th out of 193 countries.

- North Macedonia: HDI is 0.815, ranking it 68th out of 193 countries.

- Bosnia and Herzegovina: the HDI is 0.804, ranking it 74th out of 193 countries.

Geographically, the Western Balkans Region also features a rich, complex, biodiverse geography of globally important mountains, rivers, and plains, which are at the forefront in Europe of dealing with climate change and its impacts (Figure 1).

Figure 1. Topographical Map of the Western Balkans.

A defining feature of the Western Balkans, and of the four partner countries of this Regional Project, is the Dinaric Alps (Dinarides), one of the most rugged and extensive mountainous areas of Europe, which stretches northwest to southeast from the Italy-Slovenia border, across Croatia, Bosnia and Herzegovina, Serbia, Montenegro, and Kosovo to Albania. The Šar Mountains (Sharr Mountains), further south and adjacent to the Dinaric Alps, a rugged, biodiversity-rich, high mountain range in North Macedonia, Kosovo, and Albania, is among the highest in the Balkans, with many peaks exceeding 2,500 meters. The Balkan Mountains, consisting of nearly 30 distinct peaks exceeding 2,000 meters, including its highest the 2,375-meter Botev Peak, and remarkable for their flora and fauna. Mountains and the region’s complex terrain have shaped the adaptation context of the Western Balkans, creating unique adaptation challenges, strong local capacities and identities, and a complex matrix of languages, religions, and cultures, which requires a locally-led adaptation response, informed by regional and global lessons and practice. The mountains of the Western Balkans are of vital importance in providing ecosystem services to downstream, urban and regional communities, livelihoods and economies. Such mountain ecosystem services include that of “water towers”, supplying water (especially in summer) for irrigation, drinking, recreation and hydropower; as centers of both biological and cultural diversity; and as places for tourism, health and recreation. However, the Western Balkans mountain geo- and eco-systems are highly sensitive to climate change. Extreme climate events can have major consequences for both mountain, downstream, agricultural and urban areas, for which a robust adaptation response is essential.

Moreover, the Western Balkans region features some of Europe’s richest freshwater ecosystems. Referred to as “Blue Heart of Europe”, Balkan rivers are rich with freshwater biodiversity and natural habitats and contribute greatly to the region’s adaptation challenge and potential (Figure 2).

Figure 2. The “Blue Heart of Europe”: Balkans Rivers. Hydromorphological Map of the Balkan Rivers. (Color Legend: Blue: Near-natural stretch of river. Green: slightly to moderately modified stretches of river. Yellow: extensively modified stretches of river. Red: severely modified stretches of river. While the hydromorphological map of the Balkan River web shows mainly blue and green colours, a comparable map of the rest of Europe would light up in yellow and red.)

This ecologically-diverse region features more than 35,000 km of globally important rivers, notably the Sava and Danube Rivers. The Sava River Basin, comprising a catchment area of approximately 97,713 square kilometers and home to 8.2 million people, drains a significant portion of the Dinaric Alps region, through the major tributaries of the Drina, Bosna, Kupa, Una, Vrbas, Lonja, Kolubara, Bosut and Krka rivers. The Sava River’s region-wide river basin is at significant risk of climate change-induced flooding, and paradoxically water scarcity and drought resulting in damages to agriculture production, livelihoods and food security . Increasingly frequent climate-induced extreme weather and floods are putting human safety, assets and livelihoods at perpetual, increasing and unpredictable risk.  Moreover, pollution run-off from floods in the basin poses a compounding, significant and increasing threat to human health, ecosystem services, infrastructure, and livelihoods. Floodwaters carry and disperse a dangerous and often toxic mix of sediment, debris, sewage, pollution to adjacent residential, industrial and agricultural lands, including slurry, hazardous waste and pesticides,  contaminate waterways, fields and homes for years to come in climate-induced catastrophic flooding events. This endangers the environment,  communities and agricultural land throughout the flood-affected areas of the basin and requires a coordinated local and region-wide transboundary management plan and response,  of the sort the Regional Project intends to catalyze and support.

The agriculturally rich Pannonian Plain (Carpathian Basin), a large sedimentary basin in the lowlands of the Carpathian Mountains and enriched by the Danube River, invigorates agricultural productivity in northern Serbia. Otherwise, the Western Balkans region is a net food importer, at risk of climate-induced food insecurity, and a mountainous, vulnerable, and challenged region for livelihood resilience, food security and climate change. On average, the region’s total household expenditure on food is high, for example, which particularly burdens the poor, marginalized, and climate-vulnerable populations who are a priority of the Regional Project, and more than double that of the EU: 44% in North Macedonia, 32% in Montenegro, and 28% in Serbia, compared to 13% in the EU. Moreover, all of the Regional Project’s four partner countries are dependent on the import of agricultural inputs, notably energy and fertilizer, and therefore vulnerable to climate-induced and other disruptions of global trade in key commodities. Global supply shocks in commodities, such as fertilizer, are already having severe consequences on the Western Balkan’s food system, food security and livelihoods.

Today, the countries of the Western Balkans are at a climate-change adaptation turning point in the development of their economies, societies and environment. A few social, economic and other drivers will shape the region’s future. Integration with the European Union and EU accession are the principal objectives for countries in the region, in the hope that it will bring security, stability and prosperity to the people of the region. Closer integration with the EU will strongly influence environmental, climate and adaptation policies, laws and actions in the coming decades. The Western Balkans region as a whole faces similar environmental problems, which need to be tackled both locally and within the countries themselves and across borders. Legacy issues related to war, former industrial and mining sites, illegal dumping of waste, and the extraction of minerals exacerbates the adaptation challenge. Improving air quality, the protection and use of rivers and lakes, the conservation of biodiversity and the sustainable management of land, forest and water resources are all pressing priorities and shape the adaptation challenge.

## Climate change exacerbates these challenges and amplifies the risks to ecosystems, livelihoods and society.Climate Risk and Climate Change Vulnerabilities in the Western Balkans Region

The Western Balkans region experiences a variety of climates due to its diverse, mountainous and riverine geography, including Mediterranean, continental, and alpine influences (Figure 4). Northern and central areas have cold winters and warm summers with consistent rainfall. Coastal and southern areas, particularly along the Adriatic Sea, have a Mediterranean climate with hot, dry summers and mild, wet winters. Inland, the climate is generally continental, with cold winters, warm summers, and well-distributed rainfall. Alpine climates are found in higher mountain areas throughout the region. Climate change is already impacting all four partner countries of the Regional Project,- with increasing, more intense and unpredictable severity, generating more frequent and extreme weather events, including heatwaves, drought, and heavy rain, as described in the country summaries below.

Figure 4. Climate Map of the Western Balkans Region. Present day climates (1980-2016) according to the Köppen-Geiger classification on a 1km resolution according to (Beck, et al., 2018) (adapted by ClimaProof).

This section presents a summary of the climate change analysis for the sub-region, including the current status, observed change, and projected future status of climate change in the Western Balkans region. The detailed climate change analysis for the sub-region and targeted countries is presented in the Annex 10. Values for the period 1961-2015 are analyzed, drawing extensively on the Regional Cooperation Council’s (RCC) landmark study of climate change in the region (hereafter, “RCC (2018)”), which defines the period 1961-1980 as the “past” climate baseline period, and 1996-2015 as the “present” climate period. Use of 20 years for climatological period is in accordance with IPCC AR5

### Current Climate Status

##### 1) Temperature (12-19°C Average Annual)

Figure 5. Current Temperature and Precipitation (1996-2016 Average) in Western Balkans Region.

Average annual temperature for the whole region in the present climate period (since 1996) is 10.9°C.  The Northern and Central Areas of the Western Balkans typically experience cold winters, warm summers, and well-distributed rainfall throughout the year. The Southern and Coastal areas experience a Mediterranean climate, characterized by hot, dry summers and mild, relatively rainy winters. Average annual temperatures range from 12°C to 19°C, generally, with significant variations depending on location, altitude, and proximity to coast (Figure 5).

##### 2) Precipitation (Variable: 800 to 5,000 mm Average Annual)

Average annual precipitation in the Western Balkans in the present climate period (since 1996) varies significantly, depending on location, altitude, and proximity to the coast, ranging from 600 mm to 5,000 mm, which greatly emphasizes the need for locally led adaptation solutions, which is the focus of this Regional Project. The northern parts of the region generally receive around 800 mm per year. The drier, northern Pannonian Plain area, receives average annual precipitation approximately of from 600 to 1,050 mm. The southwestern coastal areas can experience up to 5,000 mm. The Dinaric Mountains form a topographic barrier that affects the precipitation pattern of the Balkan Peninsula, with the west-facing side receiving large amounts of rainfall, the mountainous areas, particularly the Dinaric Alps, receiving higher amounts of precipitation, and the east-facing, agriculturally-endowed side semi-arid and in seasonal and increasing drought, as shown in Figure 5.

Observed Climate Change

1) Temperature (+1.2°C Average Rise)

The Western Balkans region has already experienced a noticeable increase in average temperatures of 1.2°C, compared to the baseline, pre-industrial climate period of 1961-1980, with some areas experiencing a more pronounced warming trend, an increase in the number of days over 40°C, and/or an increase in the frequency and severity of heatwaves. The observed mean annual temperature increase since the pre-industrial baseline period is approximately 2-2.5°C over the region, mainly in: Bosnia and Herzegovina, Montenegro and Serbia. Moreover, the observed change in average maximum temperature increase has been far more pronounced than average minimum, with values of highest increase over 2.5°C, mostly over, in Bosnia and Herzegovina, Montenegro and some parts of Serbia (Figure 6).

Figure 6. Observed Change in Temperature and Precipitation in Western Balkans Region (1961-2015).

This warming trend region-wide is expected to disproportionately affect sectors critical for the region’s livelihoods, resilience and health, particularly agriculture, forestry, water resources, and disease, due to increased heat waves, increased cardiovascular disease, and the potential spread of vector-borne diseases. However, the spatial distribution of temperature increase is not uniform, with southern and central areas showing a smaller increase (0.5°C to 1.0°C), though higher annual averages, compared to northern areas (1.0°C to 1.5°C). The seasonal variation in observed temperature rise is also significant, with the most pronounced increases in the agriculturally critical summer months.

Significant temperature increases began in the 1980s. Moreover, the temperature over the whole region is increasing faster than the global average trend, with an especially pronounced change in the summer season and accelerated increase of maximum temperature. This highlights the alarming patterns of temperature and climate in the Western Balkans and the need for a robust, locally-led adaptation response.

##### 2) Precipitation (+0.2% to +17%).

The observed changes in precipitation patterns since the pre-industrial, baseline climate period (1961-1980), include a mix of increases and decreases, with some areas experiencing more frequent heavy precipitation events, particularly in the east, north, and west (e.g., 15% of river stations in spring and 17% in autumn, contributing to increasing severity of floods, which is discussed below), while other areas, especially in the Dinaric Alps, northern Albania and the Pannonian Plain (a significant decrease of up to 6% per decade) have experienced a decrease in heavy precipitation. The present regional annual average is 807 mm, indicating an observed change in precipitation of 0.2% relative to the baseline period. Precipitation had decreased in the 1980s and 1990s, but then began to increase and returned, at present in observed changes, to the values of the pre-industrial baseline period. This is the apparent reason for the small change of 0.2% as shown in Figure 6.

In general, the observed changes in precipitation are not as pronounced as the observed warming, because of the complex topography of the mountains. However, overall, the region has received a decreasing amount of precipitation, contributing to increasing severity of drought events, which is discussed below, with North Macedonia, among the Regional Project’s four partner countries, displaying the clearest downward trend. Bosnia and Herzegovina, Montenegro and Serbia, generally, experienced mixed or unchanging annual precipitation patterns.

Within the region, the Dinaric Alps generally receive the most precipitation. The mountains in the Western Balkans are therefore central to the flow of fresh water through rivers, farmland, communities and ecosystems, as decreasing precipitation and increasing evapotranspiration are combining to make the region, and soils in general, drier. The decrease in precipitation, particularly during the summer months, has led to increased drought conditions and reduced water availability in many parts of the region, especially in Serbia and North Macedonia.

Shifts in the seasonal distribution of precipitation has been observed, with some areas receiving more precipitation in the winter months, creating an increased risk of flooding during spring. The observed changes in precipitation also pose significant challenges for water resource management throughout the region. Atmospheric circulation patterns, such as the Arctic Oscillation (AO) and Mediterranean Oscillation (MO), significantly influence precipitation patterns in the Western Balkans.

### Projected Climate Change32

This Section presents RCC (2018)’s projected future climate change for the region for three climatological periods, in compliance with IPCC AR5 approach: 1986-2005 as the baseline period, 2016-2035 as the near future period, 2046-2065 as mid-century period, and 2081-2100 as end of the century period. Projecting the future climate in a mountainous region is notably inexact, because of the complex topography, diverse microclimates, need for high density of measurement, and need for high-resolution climate models, which are scarce. RCC (2018) analyzed two Representative Concentration Pathways (RCP) scenarios: RCP4.5 (stabilization scenario, with GHG emission peak around 2040 and afterwards declining) and RCP8.5 (continuous rise scenario, where GHG concentration continues to increase by the end of the century, otherwise known as the business-as-usual scenario). The RCP4.5 scenario is considered as best possible scenario (lower end) and RCP8.5 as extreme scenario (higher end), but current trends suggest RCP8.5 projections may be more likely (“business as usual“), for which the region should prepare and adapt.

##### Temperature (+7.5°C).

The Western Balkans region is considered a "Warming Hotspot" with projections of significant and disruptive increased heat waves and temperature increases. Mean summer temperatures could rise by as much as 7.5°C above pre-industrial times, though predicting the climate in mountainous areas is difficult because of the complex topography and hydrology. Extreme heat events are expected to become more frequent and intense, particularly in spring and autumn. Climate models predict significant future warming, with temperature increases expected to be higher than the global average. Projections indicate further warming, potentially ranging from 1.7 to 4.0°C by the end of the century, depending on global efforts to reduce greenhouse gas emissions. According to a regional model based on the medium emission scenario, the Eastern Mediterranean is expected to be 3.5–7°C warmer by the end of the 21st century, with the highest daytime increases in the Western Balkans and in the mountainous areas, in particular. A global high-emissions scenario predicts 5–8°C of warming in the Eastern Mediterranean in summer, with the Western Balkans similarly to receive the highest warming. This warming trend is expected to disproportionately affect certain sectors, including agriculture, forestry, water resources, and human health, due to increased heat waves and the potential spread of vector-borne diseases (Figure 7).

Figure 7. Projected Future Temperature and Precipitation Change in Western Balkans Region (1996-2100).

The consensus among existing models is that the Western Balkans will experience substantial warming throughout the twenty-first century, with regional warming higher than the worldwide average. In Europe, generally, warming is expected to increase with altitude and National Communications (including those of all four of the Regional Project’s partner countries) to the United Nations Framework Convention on Climate Change (UNFCCC) also indicate that the highest warming will occur within the mountainous regions of the Western Balkans countries.

Days over 35°C are expected to increase by two weeks in the Balkan Mountains and one month in the region. The same model projects winter temperatures to rise by 3°C.

Figure 7 shows a map of projected temperature change:

In the near-future period (2016-2035), relative to the baseline period (1986-2005): i) in the RCP4.5 scenario, temperature change is significant over the whole region, with average increase of 0.8°C, and seasonally significant change during JJA and SON, with more significant change in Tn than Tx.; ii) in the RCP8.5 scenario, temperature change is also significant over the whole region, with an average regional increase of 1.0°C, reaching the highest increase in JJA.

For the mid-century period (2046-2065): i) in the RCP4.5 scenario, temperature change is significant over the whole region, with average increase of 1.6°C, and seasonally significant change in JJA and in Tx, between 2.0°C and 3.0°C over most of the region. ii) in the RCP8.5 scenario, temperature change is extreme over the whole region, with an average regional increase of 2.1°C and above 2.0°C increase over most of the region most of the year.

For the end-of-the-century (2081-2100) RCC (2018) calculates that the projected temperature changes are: i) in the RCP4.5 scenario, temperature change is significant over the whole region, with average increase of 2.0°C, but stabilizes, and seasonally pronounced change in Tx in JJA and SON. ii) in the RCP8.5 scenario, temperature change will not stabilize and will continue to significantly increase to extremes, reaching a regional average increase of 4.4°C, with the most pronounced increase in JJA of over 5.0°C increase over most of the region.

Projected changes in the main climate indicators and indices for temperature in the Western Balkans, as calculated by RCC (2018), include frost days, icing days, very hot days, and heat waves. RCC (2018) also calculates valuable special climate indicators, which proxy the impacts of climate change in the region on livelihoods, ecosystems, food security, and health, including growing season, very hot dry spells (HDS), and maize yield (SHC):

|  | 2016-2035 | 2046-2065 | 2081-2100 (RCP8.5) |
| --- | --- | --- | --- |
| Frost | Decrease by 5-10 days (RCP4.5), but with a significant decrease (10-20 days) over the southern and higher altitude parts of the region. | Decrease by 10-20 days under RCP4.5 and by 20-30 days under RCP8.5. | Decrease by over 50 days over the region. |
| Icing | Decrease by 0-5 days, with a possibly higher decrease over some mountain areas in central parts of the region. | Decrease by 5-10 days under RCP4.5, and by 10-20 days under RCP8.5. | Icing days will appear only in mountain regions, but with a decrease of over 25 days |
| Very Hot Days | Increase by 5-10 days, with significantly higher increases over some parts of the region, including coastal areas of Albania, Podgorica region in Montenegro, North Macedonia, northern and central Serbia, and some parts of Bosnia and Herzegovina. | Significant increase in parts of lower altitudes (10-20 days), but most pronounced in coastal and near coastal areas and central to south-eastern part of North Macedonia (20-30 days). | Appearance of hot days in higher altitudes; an increase of 20-30 days in lower altitudes, and the most pronounced increase in coastal and near-coastal areas, and large parts of North Macedonia of over 35 days. |
| Heat Waves Frequency | Slightly increase with a highly probable significant change in southern parts of the region, especially in coastal areas of Albania, southern Bosnia and Herzegovina, Podgorica region in Montenegro and the southeast of North Macedonia. | Significantly increase over low altitudes, coastal and near-coastal areas and parts of North Macedonia, reaching values of +1 heat wave each year and with increased duration of 5 days or more. | Increases up to 2 days over the region with prolonged duration of 5-10 days. Heat waves possibly will appear in high altitudes only once in 10 years, but coastal, near-coastal areas, and large parts of North Macedonia are expected to have 2-5 more heat waves in a year, with increased duration of over 15 days and in coastal areas even over 20 days. |
| Growing Season | Increase by 10-20 days, with a more pronounced shift towards earlier dates (5-10 days) throughout the region. | Significantly increase up to 20-40 days, depending on scenario, with an earlier start date in most parts of the region of up to 20-30 days. However, in coastal areas, heating may cause the disappearance of a dormant season for plants with a biological minimum of 10°C. | Prolonged by 50-70 days, with more pronounced change in higher altitudes, and with a larger shift of the start date, reaching over 30 days throughout the region, over 40 days in southern parts, and over 50 days in south Albania. |
| Very Hot Dry Spells | Slightly increases, mainly over southern parts. | Coincide with heat waves, periods with hot temperatures will be combined with very dry periods. | Highly significant change with prolonged duration throughout the region, except the highest altitudes, of over 8 days in Serbia and over 20 days in coastal areas. |
| Maize Yield | A shift towards dry conditions mainly over agriculturally fertile Serbia and towards insufficiently humid in other parts. Over 10 years in this 20-year period (up-to 14 years in the lowest altitudes), the region will become unsuitable for maize growing without irrigation. | Wider spread of dry conditions mainly over Serbia, while in other parts of the region an insufficiently humid climate for maize is spreading, the number of years unsuitable for maize-growing without irrigation in the 20-year period is likely to be more than 14 years over the north and central Serbia. | Unsuitable conditions for maize growing, and in most productive areas almost all years during this period will not be productive. |

Precipitation (0% to -30% Decrease)

The Western Balkans will witness a decrease in annual precipitation. However, projections for precipitation are not as clear or regular as predictions of temperature. The expected precipitation decrease is more pronounced in high emission scenarios than low-emission scenarios and is particularly strong in the summer. In winter, on the contrary, precipitation will increase in the mountains and the region in general. The annual number of rainy days could decrease by 10–20 days in a medium emission scenario by the end of the twenty-first century. No increase in extreme precipitation events are expected in the region, however, flooding is predicted to become more frequent due to more precipitation in winter causing spring floods (Figure 7).

In the near-future period (2016-2035), relative to the baseline period (1986-2005), RCC (2018) calculates that projected precipitation changes are negligible, though noting that significant observed changes had already occurred prior in the Western Balkans in the 1980s: i) in the RCP4.5 scenario, no significant precipitation change in annual or seasonal values over the region. Average annual accumulation change is within a -5% and +5% interval, with decrease over most of the region in JJA.￼ ii) in the RCP8.5 scenario, also no significant precipitation change, but with somewhat different distribution. Change in the number of dry days is not significant, but is more pronounced in summer, and annually increase by 5-15 days over the region, mainly in JJA, except in northern parts of the region. Very heavy precipitation increase (in number of days and percentage of total accumulation) is not statistically significant, but is most pronounced over the northern part of Serbia (Vojvodina) according to RCP8.5, as well as an increase of very heavy rain accumulation percentage;

In the mid-century period (2046-2065), relative to the baseline period (1986-2005): i) in the RCP4.5 scenario, precipitation change still does not show statistically significant change in mean annual accumulation or in seasonal values, but the annual decrease spreads over the region, and in JJA the whole region suffers a notable decrease, which has significant implications for critical snow melt for agriculture, ecosystems, health and consumption.￼ ii) in the RCP8.5 scenario, precipitation decrease becomes significant over Albania and parts of Montenegro in JJA and, including North Macedonia, the decrease may be over -20%. However, other seasons and annual averages show no significant change.￼ Increase in the number of dry days is 5-10 days over most of the region, with significant change in southern parts (Albania and North Macedonia); change is most pronounced in JJA. The number of days with very heavy precipitation noticeably increases throughout the region, especially in the northern parts of Serbia (Vojvodina), while in regions which already have a large number of such days already, the increase is much less; very heavy rain percentage increases most over the region where such heavy-precipitation events are uncommon (north Bosnia and Herzegovina, Serbia, Kosovo (UNSC 1244/1999), parts of North Macedonia), even of around 30% in DJF and MAM, while in JJA the decrease is seen over the southern part of the region, and according to RCP8.5 the increase in Vojvodina becomes significant;

In the end-of-the-century period (2081-2100), relative to the baseline period (1986-2005): i) in the RCP4.5 scenario, precipitation change has stabilized￼ ii) ￼ In the RCP8.5 scenarios, increase in very heavy precipitation days is significant, reaching 5-10 days in some northern parts of the region and southern Serbia, especially in DJF; very heavy precipitation percentage shows the same pattern of change, however over the coastal, near-coastal and southern parts of the region (Albania), the decrease is significant in JJA, with values of over 30%.

Based on the regional analysis and baseline information presented above, Table 1 shows a summary of climate risks in Western Balkans, their vulnerabilities and potential impact.

| Summary of Climate Risks in Western Balkans Region-Related Vulnerabilities and Potential Impact |  |  |
| --- | --- | --- |
| Climate Risk | Vulnerability | Potential Impact |
| Temperature |  |  |
| Rising Temperatures | - Agriculture: high exposure of crops, crop yields and agriculture productivity to a predictable temperature range - Soil: exposure of mountain and rural soil and top cover to manage floods and wildfires - Biodiversity: loss of endemic, vulnerable and rare species and habitats that are sensitive to high temperatures - Ecosystems: exposure of mountain and rural ecosystem functions and services to heat - Disease: rise in crop disease - Net Food Importers: the countries of the Balkans Region are already net food importers, which will further strain individual, community and national food security, budgets, and spending | - Economic and livelihood losses in agriculture sector and farming communities - Decrease in ecosystem functioning - Loss of valuable species, habitats and ecosystem services - Changes and disruption to species, habitats and ecosystems, leading to loss of ecosystem services, decrease in agricultural productivity, and change in ecosystem diversity and distribution, including migration to higher altitudes - Changes and disruption to soil moisture, productivity and health - Increased fire risk - Reduced agricultural productivity |
| Heatwaves and Intense Heat | - Human Health: exposure of rural and urban populations, especially those who must work outside (farming, construction) and the elderly to heat, respiratory, kidney and cardiovascular problems - Animal Health: exposure of animals and livestock to heat-related problems | - Economic, livelihood, and asset losses - Human and animal loss of life, displacement, disease - Increased heat-related illness or death, including asthma attacks, cardiovascular disease, and lung inflammation |
| Increase in Diseases | - New Vectors: exposure to appearance of new disease vectors, such as tick-born encephalitis and dengue fever in warming temperatures - Health Systems: limited capacities and resources of rural, remote and mountainous healthcare systems and facilities | - Economic, livelihood, and asset losses - Human and animal loss of life, displacement, disease |
| Precipitation |  |  |
| Increased Heavy Rains | - Agriculture: high exposure of crops, crop yields and agriculture productivity to floods, rain patterns, and change in seasonality - Soil: exposure of mountain and rural soil and top cover to heavy rains and flooding | - Economic and livelihood losses in agriculture sector and farming communities - Loss of valuable species, habitats and ecosystem services |
| Increased Storms, Storm Intensity | - Agriculture: high exposure of crops, crop yields and agriculture productivity to floods, rain patterns, and change in seasonality - Soil: exposure of mountain and rural soil and top cover to heavy rains and flooding | - Economic and livelihood losses in agriculture sector and farming communities - Decrease in ecosystem functioning - Loss of valuable species, habitats and ecosystem services |
| Heavy Snow | - Mountain and Rural Economies: vulnerability due to poor infrastructure, housing, and access to roads and public services, especially for children and elderly - Public Services: inaccessible essential services, including emergency response | - Economic, livelihood, and asset losses - Human and animal loss of life, displacement, disease |
| Reduced Snow Cover | - Tourism: heavy reliance of winter economy on snow cover | - Economic and livelihood losses for mountain communities and national budget reliant on ski tourism |
| Drought |  |  |
| Increase in Frequency and Intensity of Wildfires | - Forests: high exposure of forests, ecosystems, ecosystem services, protected areas - Agriculture: high exposure of land, ecosystem services, water availability - Tourism: exposure of tourism operations and appeal, in coastal and inland mountain areas - Pollution: exposure to smoke, particulates, fire damage | - Loss of biodiversity, habitats, ecosystem services - Land degradation - Economic, livelihood, and asset losses - Human and animal loss of life, displacement, disease |
| Decrease in Annual River Discharge and Flow in Summer and Drought | - Agriculture: high exposure of agriculture, livestock and farms to water supply, irrigation, and groundwater - Water Infrastructure: poor water-supply infrastructure, with high system losses - Energy: exposure of hydropower and thermal power facilities to decreases in discharge, river-flow seasonality, and rising river temperatures | - Loss of crops, crop yields and livestock - Water shortages in urban areas - Inability to meet energy demand during peak summer months - Decreased energy security and supply |
| Floods |  |  |
| Increase in Frequency and Intensity of Floods | - Agriculture: high exposure of land, home, assets and property, rural and urban - Energy: energy infrastructure - Dams: risk of failure of mining tailings dams containing toxins - Landmines: risk of dislodging landmines | - Economic and livelihood losses at individual, community and national levels (budget, GDP, tax income) - Human and animal loss of life, displacement, disease - Loss of habitats, ecosystem services, clean water |

Table 1. Summary of Climate Risks in Western Balkans Region and their Vulnerabilities and Potential Impact.

### Country-Specific Climate Information and Adaptation Priorities

Please refer to Annex 10 for detailed country specific analysis of climate change trends, climate risks and adaptation priorities in four project countries: Bosnia and Herzegovina, Montenegro, North Macedonia and Serbia.

Bosnia and Herzegovina

In its National Adaptation Plan (NAP), hereafter BiH NAP (2021), Bosnia and Herzegovina analysed key drivers and impacts of climate change, and proposed 51 priority adaptation measures for the five most climate-vulnerable sectors: agriculture, water resources, biodiversity and forestry, human health and tourism. Based on previous research on climate and climate change, the biggest changes were identified in the southern, northern and north-western parts of Bosnia and Herzegovina. These include an increase in the intensity and frequency of extreme climate events (floods, droughts, violent windstorms, days with hail, prolonged heat waves, extreme temperatures, etc.). In the last two decades, some of these extremes have occurred each year, and in some places multiple extreme events have occurred. Previous research has shown increasing climate variability in all seasons in the territory of Bosnia and Herzegovina. Rapid and intense changes occur over short periods of time – from extremely cold to warm weather, or from periods of extremely heavy rainfall to very dry spells. Water systems are expected to be exposed to the impacts associated with climate change, and the projected changes in precipitation and air temperature are expected to adversely affect the current water resources management system in Bosnia and Herzegovina. In recent decades the country has seen an increase in the frequency of extreme droughts and floods. Climate change in Bosnia and Herzegovina is having an increasing impact on human health. This impact is predominantly manifested through sudden changes in extreme weather conditions. These changes are closely associated with blood pressure oscillations and cardiovascular and neurological problems, especially in vulnerable groups (chronic patients, the elderly, etc.). Moreover, extreme events such as floods may cause the spread of water-borne diseases.

Montenegro

Montenegro is increasingly vulnerable to a range of climate-related hazards that threaten its natural ecosystems, socio-economic sectors, and the well-being of its population. The country’s mountainous terrain, Mediterranean-continental climate, and high biodiversity intensify the complexity of its climate vulnerabilities. One of the most critical and rapidly intensifying risks is the increased frequency, intensity, and duration of heatwaves. Podgorica, the Montenegro capital for instance, now experiences over 70 tropical days annually, with maximum temperatures surpassing 40°C becoming increasingly common—an elevenfold increase compared to historic norms. These temperature extremes have grave implications for public health, energy systems, and labor productivity, especially affecting vulnerable groups such as the elderly, outdoor workers, and people with pre-existing health conditions. Droughts pose a chronic and expanding risk to agriculture, forestry, and water supply systems. Severe drought events in 2003, 2011, 2017, and 2020 demonstrated Montenegro’s limited capacity to absorb such shocks. These events reduced crop yields, led to livestock mortality, diminished hydropower output, and triggered significant economic losses across rural communities. Future climate patterns indicate that droughts will become more frequent, longer lasting, and spatially widespread. Flooding and flash floods, driven by erratic and intense precipitation events, increasingly damage infrastructure, disrupt transportation, and contaminate water supplies. Forest fires have become a seasonal hazard, particularly in the south and central parts of the country, driven by prolonged droughts, high temperatures, and strong winds. Sea-level rise, while more gradual, poses a critical long-term threat to Montenegro’s coastal infrastructure and tourism industry. As part of the preparation of Montenegro’s first National Adaptation Plan, which is currently in the final phase of adoption by the Government of Montenegro, key priority sectors for climate adaptation have been identified based on vulnerability assessments and national consultations. These include water resources, agriculture, health, and tourism, with cross-cutting priorities in institutional capacity building, data systems, and gender-sensitive policy integration.

North Macedonia

The last decade (2011-2020) was the warmest decade since the beginning of meteorological measurements in the country. The largest change in the annual number of frost days, icing days, summer days and tropical nights compared to the reference period is observed for the same decade. Analysis of precipitation indices shows a change in the precipitation regime with an increase in the frequency of heavy and very heavy precipitation. Climate projections also include further increase in temperature with more temperature extremes in summer months, likely increase in precipitation variability, and in frequency and intensity of droughts. These changes in climate lead to more frequent and intense extreme weather events, forest fires, droughts, and floods, all of which threaten socio-economic stability, public health, and natural ecosystems. Both urban and rural areas are affected. Urban centres face issues related to infrastructure, heatwaves, pollution, and governance. In urban centres air pollution and related public health risks pose a major adaptation challenge. Intersectional vulnerabilities are pronounced among women and vulnerable groups, including Roma women, rural women, and persons with disabilities, who face compounded exclusion due to poor housing, lack of infrastructure, and limited mobility. Flooding and stormwater management also represent a significant challenge for cities in North Macedonia. In rural areas, where a large portion of the population depends on agriculture for their livelihood, agricultural vulnerability to climate change is the most critical adaptation challenge. Recurrent droughts, record-breaking wildfires, hailstorms, and temperature extremes have reduced crop yields and affected food security. Closely linked to agriculture is the issue of water scarcity. Rural areas increasingly suffer from declining water availability, particularly during the growing season. Biodiversity and ecosystem degradation are also acute in rural landscapes, especially in forested and mountainous regions as a result of rising temperatures and human activity. Forest fires are becoming more frequent and severe, damaging ecosystems, farmland, and infrastructure, while landslides, often triggered by intense rainfall and enabled by erosion and slope instability, threaten rural settlements and transport routes.

Serbia

Serbia has a moderate, warm-humid continental climate and continental precipitation regime, influenced by the Adriatic and Mediterranean Seas. Serbia’s geographic diversity shapes its climate and local context for adaptation, including variations in elevation, proximity to the Adriatic Sea and large river basins, and exposure to winds. In the Serbian NAP (2023), the government prioritized six “climatic impact-drivers”, or climate hazards: (1) increased climate variability, (2) increase in temperature and heat waves, (3) change in the annual-precipitation distribution, (4) change in precipitation-intensity distribution, (5) change in droughts, and (6) change in climate aridity/dryness. These climatic impact-drivers contribute to one or more of four climate hazard groups, which Serbia identifies as: Too Warm; Too Wet; Too Dry; and Storms.An increase in the level of aridity of the climate in Serbia is expected, meaning increasingly drier average climate conditions. Due to the unfavorable distribution of precipitation during the year, in the largest part of the country, except in the high mountains of the western Serbia, the JJA season is “semi-dry”. In 2041-2060, on average, Serbia will have a “dry sub-humid” climate, and in RCP8.5 it will be “semi-arid” in 2081-2100. The increased climate variability means more frequent occurrence of years with drier conditions, as well as the afore-mentioned increase in droughts. Landslides in Serbia are a significant risk to life, livelihoods, and the environment , and are increasing, particularly in the central and eastern parts of the country, due to a combination of factors, including climate change, extreme weather events, particularly heavy precipitation (rain and snow) and floods, and human activities. Serbia is prone to landslides triggered by heavy rainfall, snow thaws, and earthquakes. The climate hazards that threaten human health and safety are increasing and they will continue to increase in the future in Serbia to cause worsening of health conditions and premature deaths. Serbian NAP (2023) proposes 25 priority adaptation measures in eight climate-vulnerable sectors: Cross-Cutting Measures (9), Agriculture (6), Forestry (3), Road Infrastructure (1), Urban Planning (2), Energy Sector (2), Health Sector (1), Biodiversity (1).

Socio-Economic Vulnerability of Communities in the Western Balkans to Climate-Induced Risks

The Western Balkan region is increasingly exposed to climate-induced hazards such as floods, droughts, wildfires, and heatwaves. These events are becoming more frequent and intense due to climate change, threatening lives, livelihoods, and development gains. Over the past decade, floods alone have affected more than two million people in the region, while wildfires and heatwaves have caused widespread damage and thousands of premature deaths98. These hazards are intensifying due to climate change, placing significant stress on already vulnerable populations.

## Vulnerable Populations in the Western Balkans

The people of the Western Balkans region have a high population vulnerability to climate-induced risks because of the region’s socio-economic, demographic, and employment characteristics, and this is critically the case for the region’s vulnerable and marginalized communities, who are a high priority of the Regional Project. Please refer to the Gender Assessment and Action Plan (Annex 5) for more details.

- Rural and Agricultural Communities: Rural populations, particularly those dependent on agriculture, are among the most climate-vulnerable groups in the Western Balkans. Agriculture employs a significant portion of the workforce in countries like Albania and North Macedonia, yet it remains highly sensitive to climate variability. Droughts and erratic rainfall patterns have led to crop failures, livestock losses, and reduced income, pushing many smallholder farmers into poverty. Structural issues such as fragmented land ownership, outdated irrigation systems, and limited access to credit further exacerbate vulnerability99.

- Urban Poor and Informal Settlements: Urbanization in the Western Balkans has led to the expansion of informal settlements, particularly in secondary cities and peri-urban areas. These communities often lack basic infrastructure such as drainage, waste management, and emergency services. As a result, they are disproportionately affected by urban flooding, heatwaves, and landslides. The urban poor typically live in substandard housing with limited access to cooling or healthcare, increasing their exposure to climate-related health risks.

- Women and Children: Women in the region face systemic barriers to economic participation, land ownership, and decision-making, particularly in rural areas. These gender disparities limit their ability to adapt to climate change. For example, women are more likely to be employed in informal or subsistence agriculture, which is highly climate-sensitive and lacks social protection. Additionally, caregiving responsibilities and limited mobility during disasters increase their exposure to harm100. Children, especially in poor households, are also at risk due to malnutrition, disrupted education, and health impacts from extreme weather events.

- Elderly and Persons with Disabilities: The region’s aging population is particularly vulnerable to climate-induced health risks. Elderly individuals are more susceptible to heat stress, respiratory illnesses, and mobility challenges during evacuations. Many live alone or in remote areas with limited access to healthcare and social support. Similarly, persons with disabilities face barriers to accessing early warning systems, shelters, and emergency services, making them highly vulnerable during disasters.

- Marginalized Ethnic Minorities: Significant ethnic minorities in the Western Balkans—such as Bosniaks, Albanians, Serbs, and Croats—live both in their ethnic homelands and across neighboring states due to historical shifts following the fall of the Ottoman and Austro-Hungarian Empires and the breakup of Yugoslavia. These populations often reside in ethnically mixed or contested areas. Depending on their location, these groups may face discrimination, climate-related vulnerabilities, and social or political constraints. Ethnic tensions, cultural divides, and historical grievances can further intensify their marginalization and exposure to risk.

Marginalized ethnic minorities in the region—particularly Roma, Ashkali, Egyptians, and others—face persistent and severe discrimination, exclusion, and poverty. The Roma, Europe’s largest ethnic minority, are especially affected, with limited access to education, employment, healthcare, housing, and essential services. Despite living near non-Roma communities, they experience significantly worse outcomes due to systemic barriers and a lack of reliable data to inform effective policy responses.

These communities struggle with low human and financial capital, weak labor market participation, and limited opportunities for economic advancement. For example, in Serbia, equalizing Roma employment and earnings with the general population could boost GDP by up to 3.5% annually. Youth are particularly affected, with 68% of marginalized Roma aged 15–24 in the Western Balkans classified as NEET (not in employment, education, or training), compared to 34% among non-Roma peers. Addressing these disparities is crucial for both social justice and economic development.

Roma women are among the most disadvantaged groups in Europe, facing double discrimination—both as women and as members of the Roma minority. Their access to education, employment, and essential services is significantly worse than that of both non-Roma women and Roma men. This exclusion is reflected in alarming statistics: 78% of Roma women aged 15–24 are not in employment, education, or training (NEET), compared to 59% of Roma men. Unemployment among Roma women is also higher, and their labor force participation remains extremely low.

This marginalization traps Roma women in a cycle of poverty and social exclusion, limiting their ability to contribute to or benefit from economic growth. Given the Roma population's youthfulness, investing in their human capital—especially that of women—is crucial, particularly in the context of Europe’s aging population. Economic inclusion of Roma women could unlock a large, underutilized labor force and help break intergenerational cycles of disadvantage.

The Balkan Vlach, also known as Aromanians or Wallachians, are a Romance-language-speaking ethnic minority spread across several Balkan countries, including Serbia, Albania, Greece, North Macedonia, Romania, and Bulgaria. Historically pastoral and seasonally nomadic, they lived in remote valleys and mountains and are known for their entrepreneurial and trading skills, as well as a rich oral tradition of folk tales and legends.

Despite their distinct cultural identity, the Balkan Vlach faces ongoing challenges such as cultural and linguistic subordination, limited political recognition, and socio-economic marginalization. Over time, long-term cohabitation with neighboring groups has led to increasing assimilation, further threatening the preservation of their unique heritage.

LGBTQ+ Individuals. Anti-gender movements in the region are threatening human rights and democracy, especially targeting women and LGBTQ+ individuals. These movements influence laws and policies that restrict access to basic services and fuel widespread discrimination and violence. Marginalized individuals, especially those facing multiple layers of exclusion (e.g., LGBTQ+ people in rural, low-income areas), are particularly vulnerable. In response, feminist and LGBTQ+ organizations are urged to strengthen alliances, protect inclusive education, and push for intersectional gender perspectives in EU-related processes like the Berlin Process.

## Socio-Economic Dimensions of Vulnerability

- Poverty and Economic Inequality: Poverty remains a persistent challenge in the Western Balkans, particularly in rural areas and among marginalized groups. Climate shocks such as floods and droughts disproportionately affect low-income households, who often lack savings, insurance, or diversified income sources. In Kosovo and Bosnia and Herzegovina, for example, over 20% of the population lives below the national poverty line, with rural poverty rates even higher. Economic inequality also limits access to adaptation resources, reinforcing cycles of vulnerability.

- Employment and Livelihoods: The region’s economies are heavily reliant on sectors that are highly sensitive to climate change, including agriculture, forestry, and tourism. These sectors provide employment for a large share of the population, especially in rural areas. However, climate-induced disruptions—such as droughts reducing crop yields or wildfires damaging forests—can lead to job losses and income instability. In addition, outdoor workers are heavily affected by heat waves, in particular those working in construction, transport etc. Informal employment is widespread, particularly among women and youth, and often lacks social protection, making workers more vulnerable to climate shocks.

- Health and Infrastructure: Climate change is exacerbating public health risks in the Western Balkans. Heat waves contribute to cardiovascular and respiratory illnesses, while floods increase the spread of waterborne diseases. Vulnerable populations—such as the elderly, children, and those with pre-existing conditions—are at greatest risk. At the same time, aging infrastructure and under-resourced health systems limit the region’s capacity to respond to climate-related health emergencies.

- Education and Human Capital: Climate change also threatens long-term human development in the region. Disruptions to education due to extreme weather events—such as school closures during floods or heatwaves—can have lasting impacts on children’s learning outcomes. Poor nutrition linked to agricultural shocks can impair cognitive development, particularly among young children. These effects are most pronounced among low-income and rural households, perpetuating intergenerational cycles of poverty and vulnerability.

- Migration and Demographic Change: Climate-induced stressors are contributing to demographic shifts in the Western Balkans. Rural depopulation is accelerating as young people migrate to urban areas or abroad in search of better opportunities. This out migration reduces the adaptive capacity of rural communities, leaving behind aging populations with limited resources. At the same time, urban areas are struggling to accommodate growing populations, leading to overcrowding and increased pressure on infrastructure and services.

- Governance and Institutional Capacity: Local governments in the Western Balkans often lack the financial and technical capacity to implement effective climate adaptation measures. This is particularly true in smaller municipalities, where planning systems are under developed and emergency response mechanisms are weak. Limited coordination between national and local authorities further hampers the effectiveness of adaptation efforts. Vulnerable populations are often excluded from decision-making processes, reducing the relevance and equity of climate policies.

## Innovation Context in the Western Balkans

The Western Balkans is classified as an "Emerging Innovator" region according to the 2024 European Innovation Scoreboard (EIS). The region presents strong potential for innovation, particularly in the field of climate adaptation, but faces key challenges such as low R&D investment, limited government support for business innovation, and underdeveloped innovation ecosystems. Despite these challenges, the region has a foundation upon which this project can build. By fostering regional collaboration and applying lessons learned from previous initiatives, this project will support innovation, reduce transactional costs, and strengthen the capacity of local actors.

European Innovation Scoreboard (EIS) Overview:
EIS measures innovation across four categories:

- Framework Conditions: Evaluates human resources, research systems, and digitalization capabilities.

- Innovation Investments: Measures investments made by both public and private sectors in R&D and innovation support.

- Innovation Activities: Focuses on the innovation performance of SMEs, including R&D, intellectual property, and industry linkages.

- Innovation Impacts: Assesses the outcomes of innovation, including employment impacts, sales, and environmental sustainability.

Each country has strengths in specific areas of innovation, including environment-related technologies and the activities of SMEs. However, challenges persist in areas such as R&D spending, government support for innovation, and the integration of climate adaptation solutions into broader business practices. This project will leverage the region’s existing innovation capacity and aim to overcome these barriers, creating a strong foundation for locally-led climate adaptation solutions.

#### Innovation Readiness in the Four Partner Countries

According to the EIS (2024), the four Western Balkan countries possess a strong foundation for innovation and are developing an emerging innovation ecosystem. The Regional Project can leverage and enhance this foundation, advancing and amplifying the efforts of locally-led, climate-focused innovators (Figure 8).

Figure 8. European Innovation Scorecard (EIS 2024), Highlighting the Readiness of the Four Western Balkans Partner Countries, in the Context of the Entire EU, for AF’s Investment in Innovation and Locally-Led Adaptation Acceleration.

This section provides a summary of the EIS (2024) assessment for each of the Regional Project's partner countries. Each country exhibits unique strengths, such as in the production, deployment, or use of environmental technologies, positioning them as strong candidates for investment in locally-led adaptation and innovation.

Bosnia and Herzegovina

EIS Summary. EIS (2024) categorizes Bosnia as an “Emerging Innovator”, the EIS category which comprises countries that score less than 70% of the EU average in the EIS Innovation Framework. EIS calculates an Innovation Index of 36.4 for Bosnia and Innovation Rank of 37, an impressive 2.7 improvement since 2023 and 6.4 improvement since 2017 (Figure 9). This highlights Bosnia’s readiness for an AF investment in locally-led adaptation innovation.

That said, Bosnia’s innovation performance still falls short of its potential, at 33.1% of the EU average in 2024 and lower than the Emerging Innovator category average of 48%. This underscores the potential to build on, improve and amplify adaptation innovation in Bosnia through AF’s investment and the Regional Project’s proposed technical assistance, capacity building, incubation, and adaptation acceleration support services.

EIS Assessment of Relative Strengths and Weaknesses. According to EIS (2024), Bosnia’s Innovation Relative Strengths include: environment-related technologies, SMEs introducing product innovations, and SMEs introducing business process innovations. Relative Weaknesses include: R&D spending in the public sector, venture capital (VC) spending, and direct and indirect government support of business R&D. Strong increases since 2017 include: broadband penetration, international scientific co-publications, and employment in knowledge-intensive activities. Strong decreases since 2017 include: population with tertiary education, population involved in lifelong learning, and R&D expenditure in the public sector. Strong increases since 2023 include: broadband penetration, employment in knowledge-intensive activities, and resource productivity. Strong decreases since 2023 include: scientific publications among the top 10% most cited, trademark applications, and knowledge-intensive services exports.

Montenegro

EIS Summary. EIS (2024) categorizes Montenegro as an “Emerging Innovator”, the EIS category which comprises countries that score less than 70% of the EU average in the EIS Innovation Framework. EIS calculates an Innovation Index of 36.4 for Montenegro and Innovation Rank of 37, an impressive 2.7 improvement since 2023 and 6.4 improvement since 2017 (Figure 9). This highlights Montenegro’s readiness for an AF investment in locally-led adaptation innovation.

That said, Montenegro’s innovation performance still falls short of its potential, at 33.1% of the EU average in 2024 and lower than the Emerging Innovator category average of 48%. This underscores the potential to build on, improve and amplify adaptation innovation in Montenegro through AF’s investment and the Regional Project’s proposed technical assistance, capacity building, incubation, and adaptation acceleration support services.

EIS Assessment of Relative Innovation Strengths and Weaknesses. According to EIS (2024), Montenegro’s Innovation Relative Strengths include: SMEs introducing product innovations, innovative SMEs collaborating with others, and SMEs introducing business process innovations. Relative Weaknesses include: direct and indirect government support of business R&D, design applications, and new Ph.D. graduates. Strong increases since 2017 include: broadband penetration, environment-related technologies, and international scientific co-publications. Strong decreases since 2017 include: foreign Ph.D. students as a % of all Ph.D. students, job-to-job mobility of HRST,6 and PCT7 patent applications. Strong increases since 2023 include: broadband penetration, scientific publications among the top 10% most cited, and PCT patent applications. Strong decreases since 2023 include: enterprises providing ICT training, trademark applications, and public-private co-publications.

North Macedonia

EIS Summary. EIS (2024) categorizes North Macedonia as an “Emerging Innovator”, the EIS category which comprises countries that score less than 70% of the EU average in the EIS Innovation Framework. EIS calculates an Innovation Index of 49.6 for North Macedonia and Innovation Rank of 34, an impressive 3.9 improvement since 2023 and 11.9 improvement since 2017 (Figure 10). This highlights North Macedonia’s readiness for an AF investment in locally-led adaptation innovation.

That said, North Macedonia’s innovation performance still falls short of its potential, at 45.1% of the EU average in 2024 and lower than the Emerging Innovator category average of 48%. This underscores the potential to build on, improve and amplify adaptation innovation in North Macedonia through AF’s investment and the Regional Project’s proposed technical assistance, capacity building, incubation, and adaptation acceleration support services.

EIS Assessment of Relative Strengths and Weaknesses. According to EIS (2024), North Macedonia’s Innovation Relative Strengths include: number of foreign Ph.D. students as a % of all Ph.D. students, environment-related technologies, and non-R&D innovation expenditures. Relative Weaknesses include: design applications, R&D spending in the business sector, and direct and indirect government support of business R&D. Strong increases since 2017 include: job-to-job mobility of HRST, number of foreign Ph.D. students as a % of all Ph.D. students, environment-related technologies. Strong decreases since 2017 include: R&D expenditure in the public sector, enterprises providing ICT training, population involved in lifelong learning. Strong increases since 2023 include: environment-related technologies, resource productivity, new Ph.D. graduates. Strong decreases since 2023 include: job-to-job mobility of HRST, enterprises providing ICT training, public-private co-publications.

Serbia

EIS Summary. EIS (2024) categorizes Serbia as an “Emerging Innovator”, the EIS category which comprises countries that score less than 70% of the EU average in the EIS Innovation Framework. EIS calculates an Innovation Index of 49.6 for Serbia and Innovation Rank of 34, an impressive 3.9 improvement since 2023 and 11.9 improvement since 2017 (Figure 10). This highlights Serbia’s readiness for an AF investment in innovation for adaptation.

That said, Serbia’s innovation performance still falls short of its potential, at 45.1% of the EU average in 2024 and lower than the Emerging Innovator category average of 48%. This underscores the potential to build on, improve and amplify adaptation innovation in Serbia through AF’s investment and the Regional Project’s proposed technical assistance, capacity building, incubation, and adaptation acceleration support services.

EIS Assessment of Relative Strengths and Weaknesses. According to EIS (2024), Serbia’s Innovation Relative Strengths include: non-R&D innovation expenditures, SMEs introducing product innovations, and innovation expenditures per person employed. Relative Weaknesses include: design applications, air emissions by fine particulates, and resource productivity. Strong increases since 2017 include: broadband penetration, SMEs introducing product innovations, and SMEs introducing business process innovations. Strong decreases since 2017 include: innovation expenditures per person employed, enterprises providing ICT training, and environment-related technologies. Strong increases since 2023 include: SMEs introducing product innovations, SMEs introducing business process innovations, and enterprises providing ICT training. Strong decreases since 2023 include: environment-related technologies, job-to-job mobility of HRST, and PCT patent applications.

Figure 9. European Innovation Scorecard (EIS) (2024). Bosnia and Herzegovina and Montenegro

Figure 10. European Innovation Scorecard (EIS) (2024). North Macedonia and Serbia

The EIS assessment underscores the potential to build on existing innovation ecosystems in these countries, offering a strong foundation for the Regional Project. The project aims to accelerate climate adaptation innovations by providing catalytic funding to local innovators, strengthening regional collaboration, and supporting capacity-building and incubation for local NGOs, CSOs and small businesses.

## Urgency of Adaptation Investments at the Local Level

The World Bank estimates that an initial, comprehensive adaptation investment package in the Western Balkans could reach up to US$37.2 billion, including for the Regional Project‘s four partner countries: US$6.8 billion for Bosnia and Herzegovina, or 0.6–1 percent of GDP per year until 2050; US$5.7 billion for Montenegro, or 1.5-2.3 percent of GDP per year until 2050; US$6.4 billion for North Macedonia, or 0.8-1.2 percent of GDP per year until 2050; and US$9.5 billion for Serbia, or 0.4-0.6 percent of GDP per year until 2050 Globally, UNDP highlights a significant funding gap for climate change adaptation, with costs projected to range from US$140 billion to US$300 billion per year by 2030 and as high as US￼. In the Western Balkans, each country may need to invest up to US$2 billion by 2030 alone. Front-loading and accelerating adaptation investments and innovation within the next five years will help mitigate long-term costs and the impacts of climate-related shocks. Such actions are expected to deliver substantial economic benefits, including avoided losses, accelerated economic growth, and amplified social and environmental co-benefits, with an estimated return on investment of up to 400%. However, these adaptation investments are just one part of the fiscal burden. In addition, to achieve economy-wide Net Zero, the countries of the Western Balkans would need to invest an additional US$89.4 billion, or 1.9 percent of GDP on average per year until 2050, compared to a reference scenario, most of which would be to transition the power sectors of each country and scal solar, wind, and hydro generation capacities. North Macedonia, for example, would need to invest an additional US$1.7 billion by 2030 and US$5.6 billion by 2050, equivalent to about 2.6 percent of GDP per year. Serbia would need to invest an additional US$10.4 billion by 2050, equivalent to 1.6 percent of GDP per year. Montenegro would need to invest an additional US$235 million until 2050, equivalent to 0.2 percent of GDP per year. Bosnia and Herzegovina would need to invest an additional US$0.5 billion by 2030 and US$5.8 billion by 2050, equivalent to 1.8 percent of GDP per year.

Climate adaptation innovations bring numerous benefits beyond the immediate impact on climate resilience. For example, the transition to net-zero could reduce air pollution-related mortality by 15% by 2050, potentially saving thousands of lives. Additionally, early-warning systems offer substantial benefits in terms of preventing mortality and hospitalization, with the benefits often outweighing the implementation costs by hundreds or even thousands of times. Water and flood management, along with nature-based solutions, can stimulate local economic development. However, a key missing component is locally-led adaptation and innovation at the community level, supported by national, regional, and global expertise, to scale successful climate adaptation practices, tools, and technologies. This project aims to address this critical gap.

Currently, the global and regional climate finance landscape places a heavy emphasis on mitigation efforts aimed at reducing greenhouse gas emissions. However, there has been less focus on risk reduction, adaptation, and particularly in locally-led adaptation innovation. According to the Climate Policy Initiative, only US$22 billion per year globally is allocated to climate adaptation, compared to over US$436 billion for mitigation. This underfunding is partly due to the complexity of adaptation, as it lacks a single, standardized measure like greenhouse gas emissions, making it harder to track and fund. Moreover, there is no “one size fits all” solution to adaptation challenges, further explaining why it has received less attention and funding. Locally-led adaptation innovation represents a key opportunity, particularly in the Western Balkans, where diverse and non-standard solutions can be developed to address climate risks. Entrepreneurship, whether non-profit, social, for-profit, or in partnership models, is an effective approach to generating locally-led, innovative solutions to adaptation challenges.

However, adaptation finance for NGOs, CSOs, and Micro, Small, and Medium-sized Enterprises (MSMEs) remains scarce. The finance gap between NGOs, CSOs, and Micro, Small, and MSMEs and private sector finance continues to hinder the scalability of local innovative solutions. Traditionally, small, community-based initiatives have limited access to funding, relying primarily on donations or local grants. These initiatives falling under the “missing middle” group remain largely excluded from larger, transformative funding mechanisms typically available through private finance.

As identified in a OECD/UNCDF report (2020; p.112), the Small and Medium Enterprises (SMEs) are vital to emerging economies, generating 70% of new jobs, contributing up to 40% of GDP, and act as important vehicles for innovation and community development. However, many of these SMEs fall into the “missing middle”—which means that they are too large for microfinance, yet too small or risky for traditional banks and investors. Three main barriers contribute to this financing gap according to this report are:

- High Transaction Costs – Similar effort is needed to assess SMEs as large firms, but with smaller returns.

- Risk Perception – SMEs often lack collateral, financial history, or sector familiarity, making them appear riskier.

- Investment Readiness – Many SMEs lack the skills to present strong financial models and business plans to attract formal investment.

The above is particularly evident in the Western Balkans, where high capital costs and concerns over ownership deter innovators and entrepreneurs from accessing equity, while non-profits and social enterprises face even greater challenges due to the unsuitability of traditional financing models. As a result, the capacity to scale and invest in locally-led adaptation solutions are severely constrained.

Early-stage investments in adaptation are crucial to reducing long-term costs, preventing climate-related losses, and generating substantial returns. These investments will also yield co-benefits, such as improved public health, biodiversity restoration, and the creation of sustainable local economies. By addressing these challenges, this regional project will help bridge the existing finance gaps, foster locally-led innovations, and support the broader goal of enhancing climate resilience across the Western Balkans.

# Project Objectives

The objective of the Regional Project is to accelerate locally-led climate change adaptation innovation in Bosnia and Herzegovina, Montenegro, North Macedonia, and Serbia by applying an enterprise development approach that strengthens regional collaboration, promotes gender equality, women’s empowerment and social inclusion, supports community-based innovation, and fosters learning and knowledge exchange at both regional and global levels.

This objective will be achieved through the following three interlinked outcomes:

- Outcome 1: Development, promotion, and acceleration of locally-led innovative climate adaptation solutions in four Western Balkans countries, with particular emphasis on approaches that advance gender equality and women’s empowerment, and which address priority climate risks.

- Outcome 2: Selected adaptation innovations are strengthened and positioned for scale through tailored business development support, market testing, and identification of funding and financing pathways.

- Outcome 3: Knowledge, evidence, and lessons from adaptation innovations are captured, shared, and leveraged to inform replication, scale and policy engagement across the Western Balkans through regional learning platform and global networks.

Overarching Development Outcome

The overarching goal of the project is to accelerate, develop, and promote innovation for effective, long-term, locally-led adaptation to climate change in the four Western Balkans partner countries. Special emphasis will be placed on supporting vulnerable groups and advancing gender equity and women’s empowerment. The innovative adaptation solutions will address priority climate risks which affect the four Western Balkan countries as described in the baseline information of this proposal.

Project Design and Implementation Approach

This project adopts a holistic ecosystem-building approach to strengthen climate resilience at local and regional levels. By integrating innovation, inclusion, and knowledge-sharing, the project aims to catalyze sustainable, community-driven adaptation. The main project approach is described as follows:

- Pilot Locally-Led Adaptation Technologies and Practices

Objective: Empower communities to test and scale context-specific adaptation solutions.

Could be achieved through:

- Support demonstration projects in climate-resilient agriculture, water management, and nature-based solutions.

- Facilitate participatory design processes to ensure solutions are culturally appropriate and locally owned.

- Monitor and evaluate pilot outcomes to inform broader replication.

Impact: Builds local capacity, enhances community ownership, and ensures solutions are grounded in real-world needs.

2. Incubate and Accelerate CSOs, NGOs, SMEs, and Cooperatives

Objective: Strengthen the innovation ecosystem by supporting grassroots and entrepreneurial actors.

Could be achieved through:

- Provide grant funding, mentorship, and technical assistance to early-stage climate adaptation initiatives.

- Establish innovation hubs or accelerators focused on climate-smart technologies and services.

- Foster partnerships between civil society, private sector, and academia.

Impact: Drives local economic development, creates green jobs, and scales innovative adaptation solutions.

3. Create Regional Knowledge Platforms

Objective: Facilitate peer learning and replication of successful adaptation strategies.

Could be achieved through:

- Develop digital and in-person platforms for sharing case studies, tools, and lessons learned.

- Organize regional discussions, workshops, and exchange visits.

- Promote open-access knowledge products and policy briefs.

Impact: Enhances regional cooperation, reduces duplication of efforts, and accelerates the spread of effective practices.

4. Ensure Inclusive Innovation

Objective: Prioritize equity and inclusion in all project components.

Could be achieved through:

- Design targeted approaches for women, youth, Roma, Vlachs, Vlachs, Gorani, Egyptians (in Montenegro), and other marginalized groups.

- Support leadership development and capacity-building for underrepresented stakeholders.

- Apply gender and social inclusion lenses in project design, implementation, and evaluation.

Impact: Promotes social equity, strengthens community cohesion, and ensures that adaptation benefits reach the most vulnerable.

5. Cross-Cutting Co-Benefits:

This integrated approach will generate multiple co-benefits beyond climate resilience:

- Public Health: Reduced exposure to climate-related health risks (e.g., heat stress, waterborne diseases).

- Food Security: Improved agricultural productivity and access to nutritious food.

- Gender Equality: Empowerment of women through leadership roles and economic opportunities.

- Green Economic Growth: Job creation in sustainable sectors and support for climate-resilient livelihoods.

- Energy Transition: Promotion of clean energy solutions (e.g., efficient cooking, solar-powered irrigation).

# Project Components and Financing

| Project/Programme Components | Expected Outcomes | Expected Outputs | Countries | Amount (US$) |
| --- | --- | --- | --- | --- |
| 1. Innovation Facility for Climate Adaptation | Outcome 1: Development, promotion, and acceleration of locally-led innovative climate adaptation solutions in four Balkans countries, with particular emphasis on approaches that advance gender equality and women’s empowerment, and which address priority climate risks. | Output 1.1: Innovation concepts are identified and strengthened through inclusive call for interest, innovation sprints, and tailored design support. Output 1.2: Promising pilots are financed through small-scale grants and supported to address climate risks with a focus on gender equality and social inclusion. | Bosnia and Herzegovina, Montenegro, North Macedonia, and Serbia | $ 2,767,793 |
| 2. Technical assistance and capability development for scale | Outcome 2: Selected adaptation innovations are strengthened and positioned for scale through tailored business development support, market testing, and identification of funding and financing pathways. | Output 2.1: Adaptation innovators receive tailored business development support, including incubation, acceleration, mentoring, and market testing, to strengthen implementation readiness and sustainability. Output 2.2: Scalable adaptation innovations are connected to funding and financing opportunities and supported for integration into national systems, local service delivery, or relevant markets. | Bosnia and Herzegovina, Montenegro, North Macedonia, and Serbia | $ 981,656 |
| 3. Knowledge Management and Regional Collaboration | Outcome 3: Knowledge, evidence, and lessons from adaptation innovations are captured, shared, and leveraged to inform replication, scale and policy engagement across the Western Balkans through regional learning platform and global networks. | Output 3.1: Regional knowledge exchange platforms and collaboration mechanisms are established to facilitate peer learning, cross-border dialogue, and community-of-practice engagement among adaptation actors. Output 3.2: Insights, lessons learned, and good practices from adaptation pilots are systematically documented, synthesized, and disseminated to inform future programming and policy across countries. | Bosnia and Herzegovina, Montenegro, North Macedonia, and Serbia | $ 638,246 |
| 4. Project Office/Management Execution cost (3.1%) 5. Total Project Cost |  |  |  | $157,760 |
|  |  |  |  | $4,545,455 |
| 6. Project Cycle Management Fee charged by the Implementing Entity (if applicable) (10%) |  |  |  | $454,545 |
| Amount of Financing Requested |  |  |  | $5,000,000.00 |

## Projected Calendar

Indicate the dates of the following milestones for the proposed project/programme

| Milestones | Expected Dates |
| --- | --- |
| Start of Project Implementation | 1 April 2026 |
| Mid-term Evaluation | 31 May 2028 |
| Project Closing | 30 March 2030 |
| Terminal Evaluation | 15 December 2029 |

PART II:  PROJECT JUSTIFICATION

# PART II: PROJECT JUSTIFICATION

- Describe the project / programme components, particularly focusing on the concrete adaptation activities, how these activities would contribute to climate resilience. For regional projects describe also how they would build added value through the regional approach, compared to implementing similar activities in each country individually. For the case of a programme, show how the combination of individual projects would contribute to the overall increase in resilience.

## Project Components and Contribution to Climate Resilience

Theory of Change

This Theory of Change is grounded in the belief that locally led innovation, when supported with the right resources, partnerships, and knowledge systems, can drive inclusive, scalable, replicable, and gender-responsive adaptation across the Western Balkans. It recognizes that climate adaptation innovation emerges through interconnected dynamics rather than linear cause-and-effect relationships, creating the conditions for an innovation ecosystem to flourish.

If local innovators, actors and communities in the Western Balkans, particularly women and the most vulnerable, are empowered with interconnected innovation cycles that build capabilities, credibility, and enabling networks to develop and scale adaptation solutions,

Then an ecosystem of locally led adaptation innovations will emerge, strengthen resilience across the region, and contribute to more sustainable, inclusive and gender-responsive adaptation and responses to climate change,

Because they are supported through three mutually reinforcing components that create upward spirals of innovation, learning, and scaling.

Theory of Change is supported by three key components:

- Innovation Facility for Climate Adaptation: the call for proposal and innovation sprint recognize and elevate local solutions while building context-specific adaptation technologies and practices, addressing priority climate risks identified by the four countries. This generates a “capacity-confidence-investment cycle” where successful recognition of local expertise builds confidence, attracts investment, and enables further capacity building.

- Technical assistance and capability development for scale: supports the transition from pilots to scalable solutions through targeted business support, technical assistance and acceleration. This creates a “visibility-credibility-support cycle” where successful pilots enhance the local actors credibility, attract additional support from funders and policy makers, and creates opportunities for recognition.

- Knowledge Management and Regional Collaboration: captures and amplifies learnings through peer exchange, regional platforms and systematic documentation of effective practices. This generates a “regional-local learning loop” where cross-border knowledge exchange strengthens the entire regional adaptation ecosystem.

This approach rests on several assumptions, including the willingness and capacity of local actors to drive innovation, the engagement of women-led initiatives, the existence of policy and market space to support scaling, and continued regional cooperation driven by shared climate priorities.

Figure 11-12. Regional Project Theory of Change

To achieve the programme’s objective of supporting the development and diffusion of innovative adaptation practices, tools, and technologies, the Regional Project will be established and managed by UNDP with four main functions: (1) Sourcing, screening, and selection; (2) Grant Administration and Management; (3) Aggregated technical advisory and business development support; and (4) Knowledge coordination and result aggregation. All the funding windows under the UNDP’s Adaptation Innovation Marketplace (AIM) follows a similar structure.

Figure 12. Major Functions of the Regional Project

The four major functions are described as following briefly:

- Sourcing, screening and Selection of grants. The small grant size will be grouped into two lots: (i) Between USD 15,000 USD to USD 40,000 USD (for testing, new solutions); (ii) between USD 40,000 to USD 150,000 (for scaling or replicating solutions). One regional call for proposal will be launched during the project cycle. Small grants proposals will be reviewed and screened according to the screening criteria that will comply with the Adaptation Fund´s and UNDP´s guidelines. Each grantee will have from 18 to maximum 30 months to complete the grant project.

- Aggregated Technical Support Facility. The project will leverage both in-house expertise as well as external expertise (on competitive basis) to efficiently deliver Technical and Business Development Capacity Building, Incubation, and Acceleration Support.

- Knowledge Management and sharing and Result-Based Monitoring and Evaluation. The Regional Project will coordinate with local, regional, global relevant stakeholders to share knowledge and lessons learned to further enhance the effectiveness and sustainability of the programme.

- Programme Execution and Management. This will include grant administration and management.

The Regional Project is designed to develop and diffuse innovative adaptation practices, tools, and technologies that will result in improved climate resilience of the target grantee-project beneficiaries over a baseline or business as usual scenario. UNDP’s presence in over 170 countries is a unique and underutilized asset in acceleration of ideas space. It can act as a powerful vehicle for scaling proven adaptation innovations across borders, accelerating learning loops and market entry. Furthermore, technical assistance from the network of UNDP and partners will be provided to grantees to enhance the results. The Regional Project will also provide grantees a pathway to explore to scale their solutions, leveraging both public funding opportunities and potential private funding channels, including those potential opportunities brokered by UNDP and its partners.

Furthermore, utilizing existing networks, the Regional Project also aims to share lessons learned and best practices through a knowledge-sharing open platform. Sharing best practices can help individuals and organizations from the Western Balkans to better prioritize their options based on need, capacity, and local adaptation context.

In addition to this, this Regional Project offers distinct advantages over standalone national interventions:

- Shared learning and replication: Peer-to-peer exchange enables solutions to be adapted and scaled across similar contexts, accelerating progress and reducing risk.

- Efficient delivery of technical support: A regional pool of expertise ensures consistent, high-quality assistance across countries.

- Enhanced policy alignment: The platform complements regional frameworks such as the Green Agenda for the Western Balkans and reinforces EU integration processes.

- Stronger visibility and leverage: Regional coordination amplifies grantee visibility, fosters strategic partnerships, and opens new pathways to finance and scale.

The results and learning of the Regional Project will assist the landscape for innovation in locally-led climate change adaptation with the focus on pre-seed, non-profit, as well as established organizations and social enterprises, while sharing the experience and evidence of locally-led adaptation innovations with regional Western Balkans and relevant global communities.

Strategic Fit and Partnerships

Strategically, the project will be anchored under the UNDP-led Adaptation Innovation Marketplace (AIM), an initiative born in 2021, out of a need to help countries overcome barriers to developing and implementing innovative climate adaptation solutions in line with their context and priorities, especially those related to accessing finance and technical support. AIM is a Flagship Initiative of the Climate Promise, which is the framework for UNDP’s support to developing countries to achieve their NDC priorities and deliver the Paris Agreement goals.

AIM supports local communities around the world to expand and accelerate promising adaptation solutions by providing investment, know-how and visibility. With initial funding from the Adaptation Fund, the Global Environment Facility (GEF) and the European Union, the initiative supports civil society organizations, social enterprises, women and young people to scale up innovative technologies, practices and business models that advance climate adaptation in local communities.

In addition to catalytic grant investment, AIM through it projects, offers local actors know-how on enterprise development and mentoring opportunities, leverages technical assistance, provides global visibility, and access to investors and partners who could accelerate these climate adaptation solutions.

In addition to this, the Regional Project aligns with the following frameworks and initiatives:

- National frameworks: NAPs, NDCs, green growth, and poverty reduction strategies

- Regional initiatives: Green Agenda for the Western Balkans, RCC, NALAS, SWG RRD, South-East European Climate Change Framework

- Global goals: SDGs, Paris Agreement, Sendai Framework

The Western Balkans stands at a critical juncture, where climate vulnerability and innovation potential intersect. This project will help bridge gaps in adaptation finance, strengthen innovation ecosystems, and foster regional collaboration. By supporting local actors and innovators, the project will:

- Deliver inclusive, scalable, and cost-effective adaptation solutions

- Empower communities to build resilience to climate risks

- Catalyze systemic change, improving the region's long-term climate resilience

This initiative will set a replicable precedent for climate innovation in transition economies, unlocking significant social, environmental, and economic benefits while contributing to the region’s just transition towards a low-carbon future.

## Description of the Project Components

To operationalize its Theory of Change, the regional project will be implemented through three interrelated components, corresponding to three outcomes:

#### Component 1: Innovation Facility for Climate Adaptation

Outcome 1: Development, promotion, and acceleration of locally-led innovative climate adaptation solutions in four Balkans countries, with particular emphasis on approaches that advance gender equality and women’s empowerment, and which address priority climate risks.

Locally-led adaptation innovations are developed, designed, and prepared for implementation through inclusive sourcing, technical support, and grant funding, with a focus on addressing priority climate risks and advancing gender equality and social inclusion in the Western Balkans.

Output 1.1: Innovation concepts are identified and strengthened through an inclusive call for interest, innovation sprints, and tailored design support.

The methodology for identifying and selecting locally-led innovation solutions prioritizes inclusivity and innovation quality through a deliberate two-stage approach. Rather than issuing a traditional ‘call for proposals’, the project will launch a ‘call for interest’ to cast a wider net and engage diverse local actors who may have promising ideas but lack the capacity to develop full proposals initially. During the project's inception phase (first six months), a broad outreach campaign will be undertaken across the four participating countries to ensure wide awareness and inclusive access to the upcoming call for interest. This will include targeted information sessions—online and in person if needed—tailored to reach diverse local actors such as NGOs, CSOs, cooperatives, MSMEs, and community-based innovators, particularly those from marginalized communities who may not typically engage with formal funding processes. All outreach materials and guidelines will be made available in relevant local languages.

The call for interest will be followed by rapid innovation and learning sprint designed to strengthen concept development and ensure genuine innovation before full proposal development. Selected applicants will participate in intensive, short-term collaborative workshops that combine peer learning and technical mentorship, for participants to hands-on improve their initial concepts. This sprint will specifically focus on validating the innovation potential of concepts, identifying implementation challenges early, and incorporating lessons from similar initiatives globally. This front-loaded learning approach ensures that only truly innovative, well-designed, and locally-grounded solutions advance to full proposal development and implementation, while building the capacity of local innovators throughout the process. The full design of the call for interest and the structure of innovation and learning sprints will be developed - during the outreach and initiation phase - by the project team, drawing on UNDP’s regional capabilities on innovation and peer learning practices.

The below figure (Figure13) illustrates the process from Regional call for interest to selection of initiatives to fund.

Figure 13: Regional Learning and Design Sprint

Regional call for interest

To build a strong pipeline of locally-led adaptation innovations, the project will launch a comprehensive regional 'Call for Interest' targeting local NGOs, CSOs, MSMEs, cooperatives, and grassroots innovators across the four participating Western Balkan countries. This inclusive approach deliberately moves beyond traditional proposal-based funding to ensure that promising adaptation concepts from diverse actors - including those with limited proposal-writing capacity - can enter the innovation pipeline and receive tailored support for development.

The project team will ensure robust outreach to maximize reach and ensure equitable access:

- Multi-channel outreach campaign: Leveraging UNDP's extensive networks, partner organizations, civil society networks, business associations, academic institutions, and local government contacts to disseminate information through formal and informal channels. The project team will develop a visual identity of the Call for Interest and the regional Innovation Facility for Climate Adaptation that generates attraction and interest from stakeholders.

- Targeted communication: Developing locally-adapted messaging and materials in all relevant local languages, with specific outreach efforts directed toward women-led organizations, youth groups, and marginalized communities including Roma, Vlachs, Gorani, and Egyptians.

- Information webinars and Q&A sessions: Hosting multiple information sessions in each country as needed, offered in local languages and at different times to accommodate diverse schedules, with recordings made available for wider access.

- Application support materials: Creating an application guideline and FAQ document that clearly explain the process, criteria, and expectations in accessible language.

The Call for Interest will utilize a streamlined application template (online) requiring as a minimum:

- Basic organizational information and legal status verification

- Initial concept idea description using a standardized template that guides applicants

- Preliminary alignment with selection criteria (detailed in project annex) covering innovation potential, local relevance, climate adaptation impact, and inclusion considerations

- Expression of commitment to participate in subsequent learning activities

The Call for Interest will be done at the regional level, however, translated and modified as needed by the country coordinators, including direct communication to applicants as needed.

Applications will undergo a pass/fail assessment conducted by the extended regional project team (consisting of all four UNDP country offices and Istanbul Regional Hub), ensuring consistent standards while incorporating local contextual knowledge. The assessment will focus on basic eligibility, concept viability, and innovation potential rather than detailed technical merit as this will be part of the full proposal development later.

This approach is designed to create a larger learning cohort (described in more details below) than the final number of funded innovations, allowing for peer learning, cross-pollination of ideas, and further selection through the subsequent development process. Selected applicants will advance to the innovation and learning sprint phase, where they will refine their concepts before developing full proposals for final selection by the project's Selection Committee.

The Call for Interest serves as both an inclusive entry point and a capacity-development mechanism, ensuring that the most promising locally-led adaptation innovations receive the support needed to develop into fundable, implementable solutions.

This approach of maintaining a larger cohort of concepts, while recognizing that not all will reach full maturity for selection, provides UNDP and partners with a comprehensive landscape review of current climate adaptation innovation potential across the Western Balkans region and creates a valuable 'bank of ideas' that can be further refined, promoted, and potentially connected with alternative funding sources and opportunities beyond the project's direct support.

Regional Learning and Design Sprint

Following the Call for Interest, the project will implement a regional Learning and Design for Innovation Sprint designed to further improve promising concepts into implementable adaptation solutions. This intensive capacity-development sprint serves dual purposes: strengthening individual project concepts building on a tested process and embedding experience from outside the Western Balkans while fostering peer learning among the selected cohort.

The Sprint will be co-designed and facilitated in-house by UNDP, building on similar previous examples, and will bring in global and regional expertise as needed. The program will be carried out over 6-8 weeks and utilize a blended approach featuring:

- Virtual regional workshops bringing the full cohort together for intensive collaborative sessions

- “Test & Refine Homework” enabling continuous engagement between face-to-face sessions

- Peer-to-peer learning exchanges facilitating knowledge sharing across countries and sectors

- Rapid Individual mentorship to check-in on learning and engagement of the participants

- Regional expertise integration incorporating insights from previous climate adaptation initiatives and local innovation ecosystems

The Sprint follows a proven four-stage approach tailored for climate adaptation innovation:

- Discover: Participants deepen their understanding of the specific adaptation challenge through a structured community listening exercise, stakeholder mapping, a light climate risk assessment, and vulnerability analysis. This component emphasizes participatory methods and ensures solutions are grounded in real community needs and local knowledge systems.

- Define: Teams refine their project focus and intervention pathways using strategic framing processes including systems thinking and foresight methodologies. Participants learn to articulate clear problem statements, identify leverage points for maximum impact, and integrate gender equality and social inclusion considerations from the outset.

- Develop & Deliver: Participants are given the space to (re)think their partnership base and outreach, current business model, and prepare their possible implementation plan, with continuous integration of gender and social inclusion lenses throughout the design process.

- Scale: The final sessions explore and will inspire participants to consider already upfront possible pathways for scaling and sustainability. Scaling will be unpacked as a concept and entails not only replication, but intention to attract further public funding or private finance, behavioral and cultural changes, and or regulatory and policy changes in the longer run.

Beyond individual project development, the sprint incorporates:

- Cross-regional and global inspiration examining successful adaptation innovations globally

- Failure analysis learning from challenges and setbacks in similar initiatives, including a tailored session on social and environmental risks

- Innovation ecosystem mapping identifying potential partners, funders, and scaling pathways

- Gender and inclusion ensuring projects advance equity and reach marginalized groups

- Pitch development training preparing participants for effective communication with diverse stakeholders

Following the Sprint, participants will have dedicated time to develop their comprehensive proposals if they choose to go forward in the proposal stage, incorporating learning and feedback from the sprint. This intensive collaborative process also provides UNDP with valuable opportunities to assess participants' sustained motivation, capacity to deliver on commitments, and collaborative potential, while building trust and rapport essential for effective communication, engagement, and support throughout the implementation phase. Importantly, this approach moves beyond transactional grant-making toward building genuine partnerships that leverage and strengthen existing local capabilities, facilitate strategic connections across the innovation ecosystem, and create synergies where collaborative impact exceeds individual project outcomes. Final proposals will be screened by the extended regional team and evaluated by the project's Selection Committee described below. This pre-step prior to full proposal development ensures that selected projects are not only technically sound and context-specific but also benefit from regional learning networks, peer support systems, and enhanced capability for implementation success and long-term sustainability.

Output 1.1 – Indicative Activities

- Design and Launch of Call for Expression of Interest (EOI), developing guidelines and eligibility criteria, and disseminating through regional networks, UNDP country offices, and social media. The project will identify and support locally-led adaptation innovations across the Western Balkans using inclusive outreach and simplified applications.

- Screening and Scoring for EOI submissions using a standardized scorecard to assess innovation, feasibility, and impact, including gender and social inclusion as scoring criteria.

- Innovation and Learning Sprint, conduct an innovation and learning sprint to strengthen concept development, validate innovation potential, and ensure only well-designed, locally grounded solutions move forward to the full proposal stage.

- Regional Call for Proposals, launch a regional call for proposals with a detailed application package, including templates for the results framework, budget, and gender action plan.

- Proposal Screening and Scoring, Screen and score proposals using a standardized scorecard to assess innovation, feasibility, and impact, including gender and social inclusion as scoring criteria.

- Conducted Selection and Due Diligence, including background checks, financial assessments, and risk screening, while applying Environmental and Social Safeguards (ESS) and the Gender Marker.

- Grant Agreement Finalization, review and finalize Low Value Grant Agreements (LVGAs) by reviewing and ensuring alignment with national adaptation priorities.

- Disbursement and Monitoring,  disburse funds in tranches based on milestones, with quarterly reporting and site visits (if required).

Output 1.2: Promising pilots are financed through small-scale grants and supported to address climate risks with a focus on gender equality and social inclusion.

Selection Committee establishment

As part of the inception phase of the project, a Selection Committee will be established with delegated responsibility on behalf of the projects Steering Committee, as per UNDP’s programmatic rules and regulations. The Selection Committee comprises a minimum of eight members ensuring balanced regional representation and technical expertise:

- Four country office representatives at management level (Bosnia and Herzegovina, Montenegro, North Macedonia, Serbia)

- One senior representative from UNDP Istanbul Regional Hub

- One representative from UNDP's Technical Adaptation team

- Two external experts from relevant organizations or programs with 1) climate adaptation and 2) innovation expertise

- Social and Environmental Safeguard Specialist and Gender Equality and Women’s Empowerment Specialist

Meetings will be held online, the Regional Project team serves as the Secretariat, and decisions are based on consensus. More information will be spelled out in the separate Terms of Reference of the Selection Committee endorsed upon its first meeting. Final selection recommendations require endorsement on a no-objection basis by the Steering Committee to ensure alignment with overall project objectives and strategic priorities.

Robust conflict of interest protocol governs the selection processes. Members of the Selection Committee, along with their affiliated institutions, are ineligible for funding. Any potential conflicts will be declared and managed according to UNDP standards, with affected members recusing themselves from relevant deliberations. The grant application template and criteria are found in Annex 2. While grants will be awarded through a competitive merit-based selection process, the Selection Committee will apply a balanced regional distribution principle to ensure equitable participation and capacity development across all four participating countries, while maintaining quality standards and full alignment with project objective.

Grant agreements will be executed using appropriate modalities as per UNDP’s rules and regulations, and will include Low Value Grants, Innovation Challenges, Responsible Party Agreements, and or in exceptional cases direct procurement by UNDP, to ensure maximum flexibility to adapt to changing circumstances on the ground.

Grants allocation and monitoring

The project's innovation approach deliberately employs a two-tiered funding structure designed to nurture the full spectrum of climate adaptation solutions—from early-stage experimentation to proven concept scaling. This dual approach recognizes that genuine innovation requires supporting both emerging ideas and validated solutions, helping to foster a dynamic ecosystem that generates novel approaches while accelerating proven interventions.

Lot 1 – Grants for Innovation and Experimentation (USD 15,000 - USD 40,000) These smaller grants specifically target novel approaches, emerging technologies, or innovative business models with clear potential for climate adaptation impact. Priority will be given to:

- Untested but promising concepts that address adaptation challenges through new methodologies

- Early-stage innovations from non-traditional actors or emerging organizations

- Experimental approaches that challenge conventional adaptation practices

- Solutions that demonstrate potential for breakthrough impact despite limited track records

Lot 2 - Scaling Grants for Proven Solutions (USD 40,000 - USD 150,000) These larger grants support the expansion or replication of solutions that have demonstrated early results and pathways to scale. Focus areas include:

- Validated approaches ready for geographic expansion, replication or deeper implementation

- Proven technologies or methodologies requiring support for broader adoption

- Successful pilot initiatives with documented results and scaling potential

By supporting both experimentation and scaling, the project aims to create an innovation facility for climate adaptation that can attract additional funding sources beyond the Adaptation Fund. This facility acts as a dynamic platform for generating, testing, and scaling new solutions, building a pipeline of innovations that can leverage diverse funding mechanisms and create sustained impact across the Western Balkans region.

On quality assurance and compliance, all proposals undergo rigorous screening aligned with Adaptation Fund and UNDP guidelines, including:

#### Social and environmental safeguards assessment

#### Gender analysis and inclusion impact review

#### Sustainability and scalability review

#### Technical feasibility and innovation potential review

#### Priority consideration will be given to concepts that enhance the resilience of vulnerable populations, demonstrate clear pathways to longer-term sustainability, and contribute to the broader learning agenda of the innovation facility.

Grant and funding instrument agreements will be structured using appropriate UNDP modalities tailored to recipient organizational characteristics (CSOs, NGOs, SMEs, cooperatives), ensuring compliance with UNDP rules and policies while maintaining flexibility to support diverse innovation actors. Performance-based disbursement mechanisms will be employed where appropriate, linking funding to achievement of specific milestones and learning objectives that contribute to both individual project success and broader ecosystem knowledge generation.

What types of innovative adaptation solutions to be funded by the grants/funding instruments?

Based on the development context presented in the first part of this proposal, the climate risks faced by Bosnia and Herzegovina, Montenegro, North Macedonia, and Serbia are diverse but interconnected, with common threats including extreme heat, droughts, flooding, and wildfires. These impacts threaten key sectors such as agriculture, water resources, and energy, making adaptation a crucial priority for the region. Each country’s NAP priority areas outline specific actions, such as improving water management, strengthening disaster risk reduction systems, and adapting agriculture to changing climate conditions among others. The Regional Project will build on these priorities, supporting the development and scaling of locally-led adaptation innovations solutions, enhancing regional collaboration, and ensuring that adaptation solutions are inclusive, sustainable, and resilient to future climate risks.

The following priority climate risks will be addressed through this project, as they are common to the four Western Balkan countries:

Priority climate risks:

- Droughts and rainfall variability

- Temperature rise, heatwaves and wildfires

- Floods

- Landslides

- Sea Level Rise and/or Salination (only Montenegro)

- Coastal erosion (only Montenegro)

- Climate induced health risk

Considering the above, the following types of solutions and thematic sectors would be considered for the call for proposals/grantees selection. It is important to recognize the strong interlinkages and co-benefits that exist between the targeted sectors and adaptation solutions. Many of the piloted interventions contribute to multiple outcomes across thematic areas. Leveraging these interconnections can significantly enhance the overall impact and sustainability of the financing. Ensuring the scalability of solutions and maximizing their relevance across sectors are both critical to the effectiveness and long-term value of the grant:

1. Climate-Resilient Agriculture and Food Security

The agricultural sector is not only a major driver of climate change but is also seriously affected by it, increasing the importance of the sector to climate action. As noted in the narrative section, the agriculture sector is central to the economies of the Western Balkans. Climate change increases weather variability, intensifying and increasing extreme weather events, disrupts rainfall patterns, increases temperatures, and risks the introduction of pests and diseases to regions previously unaffected.

Adaptation benefits:

- Promoting drought- and flood-tolerant crops, digital agricultural tools and services for on-farm practices like irrigation and agrochemical inputs, resilient and effective irrigation systems, among other interventions, can reduce the vulnerability of farmers to climate change, increase food security by stabilizing crop yields and prices of agricultural commodities.

- Promote sustainable and resilient livelihoods of farmers through sustainable production of agricultural commodities, higher value-added and sustainable food value chain development, and crop/plant diversification, including agroforestry.

- Supports sustainable farming practices that preserve or improve soil health, water, and biodiversity.

- Integrating farming and food traditions with context-specific technology can drive sustainable development by building on local knowledge.

- Technological and policy innovations must reshape the cost structure of the agrifood value chain to incentivize sustainable practices.

- Tapping into wasted and underutilized assets offers potential for creating sustainable food value, reducing waste while enhancing resource efficiency and economic inclusiveness.

2. Water Management

Climate change increase the intensity and frequency of droughts, and increasingly variable rainfall impacts hydrological cycles and freshwater availability, among others. Improving water management in areas experiencing an elevated level of water stress can reduce the increased pressure on water demand and improve room for allocation under increasingly scarce and constrained conditions, particularly important for reducing competition between critical water use sectors. There is a high degree of interlinkages with several other thematic priorities, including agriculture and disaster risk reduction.

Adaptation benefits:

- Rainwater harvesting and storage can reduce dependency on ground- and surface water extraction, reduce flows in drainage systems (alleviating flood risk). Risks of reduced surface flow and/or return flows would have to be determined on a case-to-case basis.

- Wastewater treatment that leads to effective water recycling can contribute to more efficient use during dry periods.

- Builds resilience in both rural and urban water systems. Due to the interconnectedness of the water sector, especially at basin, watershed, and catchment levels, adaptation measures for improved water resources management have significant co-benefits and leveraging opportunity – for example in terms of agriculture and flood protection.

3. Flood Risk Management

Reasons: Climate change increases the frequency and intensity of floods. Adaptation benefits:

- Infrastructure like levees, retention basins, and green drainage systems protect lives and property

- Flood zoning and early warning systems reduce vulnerability

- Helps maintain economic stability in flood-prone areas

4. Urban Climate Resilience

Cities are hotspots for climate risks like heatwaves, flooding, air pollution, and infrastructure stress. According to a 2024 World Bank report, the average frequency of extremely hot temperatures in Western Balkan cities, on average, relative to its own historical experience increased from 0.09 months (or 3 days a year) in the 1990s to 1.32 months (or more than 40 days a year) in 2011–20 – a fourteen-fold increase in only two decades. The average intensity of extreme heat events also gradually increased over the same period, while extreme dry and extreme wet weather events have been increasing.

Adaptation benefits:

- Resilient and risk-informed housing development, sustainable and resilient city planning, and climate resilience principles integrated in zoning regulation.

- Develop solutions focused on climate resilience of energy infrastructure to address issues of access and costs – aiming to reduce demand and use of polluting fuels, such as wood and waste, for private heating solutions.

- Innovative solutions for greening cities in a practical and walkable manner, developing urban nature-based solutions (NbS) for adapting to climate risks, e.g. permeable surfaces, tree-planting solutions for increasing canopy coverage and cleaner air, utilizing wall and roof spaces for greenery, and developing or applying green-blue solutions for better urban water management – strengthening resilience to urban flooding, promoting cool and healthy urban micro-climates, and human well-being.

4. Disaster Risk Reduction (DRR)

Climate change intensifies weather related disasters, like floods, wildfires, droughts, storms, among others, leading to increasing human, economic, and environmental losses. Aside from the direct threat to life, disasters are having increasingly stronger macroeconomic impacts, with direct losses estimated at $202 billion. When cascading and ecosystem costs are considered, escalating disaster costs now surpass $2.3 trillion annually, disproportionately affecting the most vulnerable. Even as hazards become more intense and volatile due to climate change, investments in reducing exposure and vulnerability are the cost-effective future of development. Disaster risk reduction (DRR) measures deliver some of the highest benefit-cost ratios in development investment, ranging from 2:1 to 10:1 or more. Just as total disaster costs have been underestimated, so have the benefits of DRR in both developed and developing countries alike.

Floods, drought, extreme heat, landslides, and wildfire hazards become more frequent and more intense, posing substantial and growing risks for people and the economy. There is research suggesting compounding risks through overlapping hazards, for example droughts may increase risk of floods depending on the preconditions during which the sudden increase of precipitation occurs (geography, topography, soil conditions including moisture, etc.). There is however strong evidence that drought-to-flood events cause more impacts than if the hazards would occur on their own – situations more likely to arise due to the increased frequency of these extreme weather events.

Nature-based Solutions (NbS) innovations, such as Ecosystem-based DRR (Eco-DRR), that provide natural buffers against climate impacts and work with ecosystems to provide myriad co-benefits across all categories listed in this section would be highly encouraged to increase impact of investments.

Adaptation benefits:

- Deploying or creating local adaptations of natural asset valuation tools to make a bankable business case for ecosystems, natural resources, promoting biodiversity and natural conservation.

- Addressing gaps for multi-hazard early warning systems in low-access areas to prevent disasters, enhance preparedness, increase response times, and minimize recovery costs – saving lives, protecting infrastructure, and reducing impacts on livelihoods.

- Integrating risk-informed, green (green-grey where necessary) engineering solutions in water management and flood planning.

- Restoring and protecting wetlands and forests reduces flood and erosion risks, protect biodiversity, protecting natural carbon sequestration functions, and providing opportunities for sustainable tourism.

- Enhances biodiversity and carbon sequestration and is often more cost-effective and sustainable than purely grey engineering solutions.

- Combining bio- and grey infrastructure through hybrid engineering for improving local coastal development in high-risk areas, protecting the environment and livelihoods (e.g., fisheries, tourism).

- Early warning systems save lives by enabling timely evacuations

- Spatial risk mapping informs better land-use planning

- Wildfire prevention reduces damage to ecosystems and communities

5. Nature-Based Solutions

Ecosystems provide natural buffers against climate impacts.

Adaptation benefits:

- Restoring wetlands, mangroves, and forests reduces flood and erosion risks

- Enhances biodiversity and carbon sequestration

- Often more cost-effective and sustainable than engineered solutions

6. Integrated Coastal Zone Management

Rising sea levels and storm surges threaten coastal communities and ecosystems.

Adaptation benefits:

- Combines engineering, policy, and ecosystem-based approaches

- Protects livelihoods (e.g., fisheries, tourism) and infrastructure

- Encourages sustainable development in vulnerable coastal zones

7. Climate-Health Integrated Management

Recognizes the deep interconnection between climate change and public health and ensures that adaptation strategies address both environmental and human well-being in a coordinated way.

Adaptation benefits:

- Helps prevent and manage diseases linked to climate change, such as heatstroke, respiratory illnesses, and vector-borne diseases

- Ensures health facilities and services can withstand and respond to climate shocks like floods, droughts, and extreme heat

- Combines climate forecasting with health surveillance to anticipate and respond to outbreaks and emergencies more effectively

- Targets vulnerable populations and delivers broader benefits like cleaner air, safer water, and improved nutrition

Output 1.2 – Indicative Activities

- Targeted outreach to women and marginalized groups, partner with women’s networks, youth groups, and minority associations; translate materials into local languages to ensure social inclusiveness and gender-responsiveness in selection criteria.

- Gender and inclusion training for applicants, offer webinars on how to integrate GESI into project design; provide examples of inclusive adaptation innovations.

- Gender-responsive proposal review, require gender analysis and action plans in proposals; prioritize women-led and socially inclusive initiatives.

- Monitoring GESI outcomes & capacity building for grantees, track participation of women and marginalized groups; evaluate how projects address structural barriers and promote empowerment.

#### Component 2: Technical assistance and capability development for scale

Outcome 2: Selected adaptation innovations are strengthened and positioned for scale through tailored business development support, market testing, and identification of funding and financing pathways.

Building on the foundation of locally-led adaptation innovations developed under Outcome 1, Component 2 focuses on stewarding promising climate adaptation solutions into viable, scalable solutions capable of generating effects across the Western Balkans region. This component recognizes that innovative adaptation technologies and practices require strategic business development support, market validation, and access to appropriate funding or financing to transition from pilot demonstrations to widespread implementation. This component will provide differentiated support tailored to the two distinct categories of innovators identified in Outcome 1 through a methodological approach that combines targeted capability development, mentorship, and market positioning, among other things. By connecting adaptation innovators with funding opportunities and integrating successful solutions into national systems and local service delivery mechanisms, Component 2 ensures that climate adaptation innovations can achieve the scale and sustainability necessary to meaningfully enhance regional climate resilience while generating economic opportunities for local communities and enterprises.

Output 2.1: Adaptation innovators receive tailored business development support, including incubation, acceleration, mentoring, and market testing, to strengthen implementation readiness and sustainability.

Given the nature of this project, the innovation facility will have a range of available support options to meet the diverse needs of climate adaptation innovators across the Western Balkans. Under this output, selected adaptation innovators will receive multi-layered support designed to strengthen their organizational capacity, enhance solution viability, and accelerate pathway to scale. This support ecosystem will be tailored to address the specific needs and maturity levels of the two innovator categories, ensuring that both established organizations and emerging innovators receive appropriate guidance to achieve their scaling objectives. The support framework includes hands-on practical assistance from country-based and regional project teams throughout implementation, with specialized expertise in gender equality integration and innovation development; strategic mentorship and engagement from MBA students and faculty from globally recognized universities, providing access to cutting-edge business development knowledge and international networks; and participation in BOOST, a tailored regional accelerator programme specifically designed for climate adaptation enterprises in the Western Balkans context. The detailed design and delivery mechanisms for these support interventions will be refined during the project inception phase to ensure maximum relevance and impact. The core areas of business development support are outlined below.

Overall hands-on and in-house technical support from UNDP

The project team will provide customized support to grantees, including tailored technical training, business development mentoring, and strategic partnership facilitation. The facility will offer on-demand expertise in gender equality and innovation, while actively connecting grantees with relevant national institutions and private sector actors to enhance solution development and market penetration. Additional external expertise and support can also be provided depending on the specific needs and circumstances of individual grantees. Beyond direct grantee support, the project team aims to help strengthen the broader enabling environment through policy support, hands-on advice and technical assistance, enhanced linkages with marginalized groups, and specialized support for women and youth empowerment. Drawing on proven methodologies from the global UNDP implemented AFCIA project and the Innovation Team in the Istanbul Regional Hub, the team will embed and localize training modules and assessment tools—including Value Chain Driven Viability Analysis and climate risk and scaling assessments—tailored to address specific needs identified during implementation. This integrated approach ensures that grantees receive both immediate operational support and access to systemic improvements that facilitate long-term sustainability and scale.

Please visit the two-page factsheets for all 44 grantees are now available on the UNDP AFCIA webpage, under the Solutions Catalogue. Each factsheet highlights the grantee’s key achievements, social impact, adaptation benefits, innovation characteristics, replication potential, funding snapshot, and investability.

BOOST Acceleration Programme

To support the transition from robust proposal development to effective delivery, selected grantees will receive targeted support through a structured BOOST Acceleration Programme, implemented in-house by UNDP with external expertise as needed. This will help strengthen their organizational structures, enhance financial sustainability, and build operational readiness for scaling their climate adaptation solutions.

BOOST is UNDP’s tested acceleration model designed to help local innovators, social enterprises, MSMEs, CSOs, NGOs strengthen their business models, internal capacity, and readiness for implementation. The programme has been successfully applied across Europe and Central Asia to support over 100 solutions advancing climate resilience, green recovery, and social innovation.

UNDP has so far delivered 10 BOOST acceleration programs in the region, including a dedicated Urban Future Finance edition for Western Balkan cities. These programs gave firsthand insights into what innovators in the region are missing—capital, mentors, and business development support—and how to close those gaps. Through these programs and offices, UNDP has built strong partnerships with regional governments, municipalities, private sector (including advanced technology companies and the startup ecosystem), and relevant development partner

In this project, BOOST will be tailored to support adaptation-focused initiatives in the Western Balkans with guidance from the Technical Team to ensure that the knowledge and learnings from UNDP AFCIA's capacity-building efforts are fully integrated into the design. It will complement the innovation sprint by providing structured, practical assistance during the early stages of implementation, helping grantees strengthen their organizations, improve operational readiness, and position their projects for long-term success. The programme will specifically focus on strengthening projects that address the Adaptation Fund’s priorities, including enhancing climate resilience, reducing vulnerability, promoting inclusion, and building sustainable, locally relevant solutions.

The BOOST support package will run over approximately 8-10 weeks, however can be divided up or phased out depending on the needs of the cohort(s) of grantees. Examples of well-tested and documented main modules and boosters are shared below, which can be further complemented by sub-sessions or thematics as relevant during implementation.

Example Modules of a BOOST Acceleration Programme

1. Sustainability-Focused Business Model Innovation: This module focuses on strengthening business models to enhance organizational resilience and sustainability. It emphasizes the integration of social, environmental, and economic dimensions into long-term business strategies aligned with green recovery. It will provide practical tools for building sustainable businesses.

2. Impact Measurement / Management Guidance: Grantees will be supported to integrate practical, results-oriented impact measurement into their project design. This includes developing a measurable impact strategy aligned with the Sustainable Development Goals (SDGs), essential for scaling innovative solutions and attracting strategic partners. By strengthening impact management, grantees will be better positioned to demonstrate how their work contributes to reducing vulnerability, enhancing climate resilience, and creating lasting benefits for communities.

3. Communications and Visibility Support: Grantees will receive targeted support to strengthen their communications capacity, increase visibility, and access platforms to showcase their work. This includes tailored advice on storytelling, brand positioning, and engaging partners, funders, and stakeholders. Effective communication is essential to building partnerships, securing resources, and raising the profile of adaptation solutions within local, national, and regional contexts.

Examples of Booster workshops

1. Mentorship and Expert Guidance: Through this component, grantees will have access to dedicated mentorship that addresses both organizational development and sector-specific challenges. This includes core support in areas such as business development, operational planning, and team management. Where relevant, participants will also be connected to sector experts who can provide targeted technical advice, market insights, and connections to relevant networks, supporting both technical and strategic growth.

2. Peer Learning and Ecosystem Connections: This component will foster peer learning, shared knowledge exchange, and connections to relevant networks within the adaptation and innovation space. Grantees will have opportunities to engage with the BOOST alumni network, participate in curated events, and build relationships with other actors working to advance climate resilience. This helps situate their work within a broader ecosystem, enhancing collaboration, visibility, and potential for scaling.

BOOST’s flexible design allows the support provided to be tailored to the specific needs of the selected grantees, based on their organizational type, experience level, and the nature of their proposed solution. Whether participants are NGOs, MSMEs, cooperatives, or local innovators, the programme will be adapted to ensure that the tools, mentorship, and learning opportunities are relevant and practical.

Output 2.1 – Indicative Activities

- Establish or partner with incubators/accelerators to deliver tailored support, leverage existing innovation hubs or university-based incubators.

- Organize structured training programs on business model development, financial planning, and investment readiness, include both in-person and virtual delivery formats.

- Facilitate prototype development and testing through access to technical labs or pilot communities, prioritize climate-resilient and locally appropriate technologies.

- Support development of business plans and investment pitches through coaching, MBA fellowship programme support, and peer review, use standardized templates and expert mentors.

- Host discussions for scaling or investor pitch events at the country and regional levels, invite local investors, donors, and government representatives.

- Support grantees through university students and MBA Fellowship Programme, engage university students to leverage their skills and knowledge.

Output 2.2: Scalable adaptation innovations are connected to funding and financing opportunities and supported for integration into national systems, local service delivery, or relevant markets.

This output aims to support proven adaptation innovations in their transition from grant-supported pilots to sustainable, scaled efforts through strategic financing connections and market integration support. The project will provide comprehensive investment readiness and financing facilitation through multiple complementary activities.

MBA Fellowship Programme

Building on the success and learning from the global UNDP AFCIA project's use of this modality, which has successfully integrated business expertise into locally-led climate adaptation efforts, the MBA Fellowship Programme strategically engages postgraduate students from prestigious universities from the Global Network for Advanced Management (GNAM Network), to support grantees with dedicated business development assistance for up to six months. This collaboration will be facilitated through a responsible party selected under UNDP's procurement standards, ensuring a seamless integration of top-tier students into the programme.

The programme connects academic expertise with the practical needs of climate adaptation, providing vital support in areas such as business model refinement, financial strategy, and market expansion planning. Students will assist local initiatives by applying their knowledge in business management, financial planning, and market research, ensuring alignment with locally led adaptation principles. This mutual learning platform will benefit both grantees, who gain strategic business support, and students, who acquire real-world experience in addressing complex climate adaptation challenges, particularly in the Western Balkans context.

The programme also contributes to building a repository of lessons learned, tested practices, and case studies, creating a continuous documentation and knowledge exchange mechanism. By promoting systemic learning, the programme fosters collaboration between academia, development organizations, and local innovators, contributing to the scaling of sustainable, scalable climate solutions. This collaboration strengthens the climate adaptation landscape and ensures that the lessons learned can be applied to future projects, enabling scaling across regions.

By connecting grassroots organizations with business schools, the MBA Fellowship Programme bridges the gap between local knowledge and business expertise, driving scalable, innovative climate adaptation solutions. The fellowship enhances the leadership, financial, and strategic skills of students while providing grantees with high-level business support, improving their capacity to attract investment and scale their solutions.

The programme also promotes systemic change by aligning development finance with private sector priorities, fostering collaboration between the two sectors. Business schools serve as neutral platforms for testing new concepts, promoting long-term relationships, and closing the gap between climate finance and the projects that need it most. Ultimately, the MBA Fellowship Programme contributes to scaling adaptation solutions, strengthening resilience, and building more sustainable, inclusive societies.

In addition to the global MBA fellowship programme, the project will actively seek partnerships with universities across the Western Balkans region to engage local students and faculty with climate adaptation innovators. These potential collaborations will leverage regional expertise and cultural understanding while building institutional capacity, ensuring the sustainability of knowledge and expertise developed through the project beyond its duration. This approach will help ensure that knowledge and expertise developed through the project remain embedded within regional educational institutions, creating a sustainable foundation for continued support to future climate adaptation initiatives beyond the project's duration.

Investment and Partnership Expertise

The project will maintain on-demand in-house investment and partnership expertise to support grantees in developing fundraising strategies, exploring potential financing partners, and structuring approaches for scaling. This technical support includes assistance with financial modeling, due diligence preparation, investor relations, and partnership negotiations with both public and private sector actors.

To further strengthen the investment readiness of grantees, where appropriate, the project will engage specialized venture philanthropy organizations through competitive procurement processes. These experts will provide tailored guidance on impact investment strategies, social enterprise development, and innovative financing mechanisms for climate adaptation ventures.

Additionally, the project team will leverage UNDP AFCIA’s partnership model to facilitate connections between local grantees and potential investors. This will support the refinement of business models and enhance their investment-readiness. Through the MBA Fellowship Programme, MBA students from leading global universities will work with local grantees to refine business models, strengthen financial strategies, and expand market reach. This collaboration will not only provide technical expertise but also enhance the sustainability and scalability of adaptation solutions, driving long-term impact and fostering partnerships that can accelerate adaptation efforts across the region.

Financing Pathways and Market Integration

The project will assist grantees in exploring a variety of financing pathways, including concessional and blended finance opportunities, ensuring alignment with the most appropriate and sustainable funding mechanisms. In addition, the project will leverage UNDP's extensive portfolio of climate and environmental projects as potential scaling platforms to facilitate the growth of innovative solutions.

Grantees will be introduced to government entities to explore available public funding mechanisms, creating opportunities for strategic collaborations with national institutions. This will enhance their access to both public and private sector funding, fostering market penetration and increasing sustainability potential. Additionally, the engagement of the four UNDP country offices in the Western Balkans and their extensive stakeholder networks will further support market integration, ensuring a broader and more impactful reach for adaptation solutions across the region.

Showcase and Networking Opportunities

Toward the end of grant implementation cycles, structured Pitching Events at the national level will provide grantees with platforms to present their work and explore scaling and replication opportunities with potential investors and partners. Additionally, UNDP will aim to support grantee participation in high-level national and international events to showcase innovations and build networks that may facilitate future scaling opportunities.

BOOST Acceleration Programme - Module on Fundraising and Investment Readiness

As part of the BOOST programme, selected grantees will receive specialized support to strengthen their financing capabilities and investment readiness. This module provides tailored mentorship to improve solution communication, develop compelling pitch materials, and design comprehensive fundraising strategies. Participants will explore pathways to diverse financing sources, including public, private, and blended finance mechanisms, while investigating alternative financing tools such as crowdfunding and impact lending. This component aims to help promising innovations develop operational and financial foundations that may support long-term viability and scaling opportunities.

Output 2.2 – Indicative Activities

- Map Potential Public and Private Sector Partners for Scaling and Integration, include the country office stakeholder ecosystem—ministries, local governments, cooperatives, and MSMEs.

- Facilitate Investor Brokering, organize sector-specific innovation fairs or B2B meetings.

- Conduct Policy Dialogues and Roundtables to Present Innovation Outcomes, engage policymakers early to build buy-in.

- Support Pilot Integration of Selected Innovations into Public Programs or Private Sector Supply Chains, provide technical assistance and co-financing where needed.

- Develop Case Studies and Policy Briefs Showcasing Successful Innovations, disseminate through national and regional platforms.

Component 3: Knowledge Management and Regional Collaboration

Outcome 3:  Knowledge, evidence, and lessons from adaptation innovations are captured, shared, and leveraged to inform replication, scale and policy engagement across the Western Balkans through regional learning platform and global networks.

Innovation thrives through shared learning and collaborative exchange. Recognizing that sustainable climate adaptation requires continuous knowledge sharing to scale innovative solutions, Component 3 establishes a comprehensive framework for capturing, synthesizing, and disseminating insights from locally-led adaptation innovations across the Western Balkans. This component will design and implement peer learning and cross-border collaboration, ensuring that successful adaptation practices and lessons learned are effectively shared among communities, practitioners, and policymakers throughout the region and beyond. Through both formal regional platforms and flexible, responsive learning support directly tailored to grantee needs, this outcome will maximize the visibility and replication potential of proven adaptation solutions while building lasting capacity for innovation and knowledge management across Bosnia and Herzegovina, Montenegro, North Macedonia, and Serbia.

Output 3.1: Regional knowledge exchange platforms and collaboration mechanisms are established to facilitate peer learning, cross-border dialogue, and community-of-practice engagement among adaptation actors.

A comprehensive knowledge-sharing mechanism will be established under this output, focusing on facilitating the exchange of relevant practices, lessons learned, and innovative solutions. This system will leverage existing regional knowledge and experiences from UNDP's initiatives, particularly in the Istanbul Regional Hub and Western Balkans Country Offices, UNDP Climate Promise, UNDP implemented AFCIA project, using a variety of channels such as social media, blogs, working papers, case studies, and open-source tools. Rather than developing an online platform, the focus will be on creating a flexible structure that ensures broad access to knowledge through these multiple channels, and the creation of a community of practice of practitioners and relevant stakeholders.

Community engagement will be a key element of this system, with tools like the BOOST Alumni Network, the AIM partner network (which includes AFCIA’s partnership platform), TADAMON NGO Empowernment Platform and the UNDP SGP’s Global Citizens Knowledge Platform playing important roles in expanding the reach and effects of shared knowledge. These tools will ensure the knowledge-sharing process is expansive and impactful, supporting both grassroots-level actors and policymakers. More details will be specified in the respective annual work plans.

Output 3.1 – Indicative Activities

- Establish a Regional Digital Knowledge Space for Adaptation Innovation, includes a searchable repository of case studies, tools, and policy briefs.

- Organize Annual Regional Learning and Knowledge-Sharing Events, includes innovation fairs, thematic workshops, and regional showcases.

- Launch Regional MBA Fellowship Program for Knowledge Exchange and Capacity Building. The MBA Fellowship Programme will connect local adaptation innovators with postgraduate business students from global and regional universities, providing tailored business development support while fostering mutual learning, strengthening institutional capacity, and promoting scalable, sustainable climate solutions across the Western Balkans.

- Develop and Implement a Visibility and Branding Strategy for the Adaptation Fund, includes branding guidelines, media kits, and storytelling campaigns.

- Facilitate Peer-to-Peer Learning Exchanges Between Countries, includes virtual and in-person study tours and thematic dialogues.

- Collaborate with National Entities and Global Networks (e.g., weADAPT, Global Resilience Partnership) to align with global best practices and amplify regional voices.

Output 3.2: Insights, lessons learned, and good practices from adaptation pilots are systematically documented, synthesized, and disseminated to inform future programming and policy across countries.

This output will focus on systematically documenting, synthesizing, and sharing lessons from adaptation pilots across the region. Key activities will include organizing peer learning spaces such as innovation fairs, workshops, peer to peer  knowledge exchange “Talks”, and product showcases in collaboration with grantees and the broader AIM community (e.g. partners like the International Centre for Climate Change and Development (ICCCAD), Climate and Development Knowledge Network (CDKN), the Least Developed Countries Universities Consortium on Climate Change (LUCCC), the Global Resilience Partnership (GRP), the Climate-Knowledge Innovation Community (Climate-KIC) , the UN Capital Development Fund (UNCDF) and investment networks like the Asia Venture Philanthropy Network (AVPN), African Venture Philanthropy Alliance (AVPA), Latimpacto and Impact Europe) can all offer additional networking, dissemination and knowledge brokering possibilities for the grantees under this regional project.

The stakeholder ecosystems of the four UNDP Country Offices in the Western Balkans alongside the Istanbul Regional Hub, will facilitate the exchange of ideas, foster collaboration, and support the scaling of successful solutions. To enhance the knowledge base, the project will establish virtual connections with incubators, accelerators, innovation labs, and climate adaptation practitioners. These engagements will enrich the adaptation process by integrating diverse perspectives, providing tailored support to grantees, and ensuring that solutions are scalable, impactful, and aligned with regional and global best practices.

A strategic communications and dissemination plan, developed with UNDP Communication teams and adhering to UNDP’s Communication guidelines, will ensure that key learnings, achievements, and grantee impact stories are shared across national, regional, and global platforms and appropriate social media channels. This plan will leverage UNDP’s communication channels, ensuring consistency with global messaging and alignment with organizational standards for disseminating climate adaptation insights.

The communication efforts will include:

- Digital and social media content creation

- Documentation of results and key learnings in reports like the Donor Progress Report

- Participation in relevant events and forums

These efforts will amplify the project’s impact, ensuring that lessons reach key stakeholders such as policymakers, practitioners, and the broader public, ultimately supporting the scaling of locally-led, gender-responsive adaptation solutions.

The project will also utilize existing tools like CoP platforms (e.g., Slack and Microsoft Teams) and survey tools (e.g., SurveyMonkey and Google Forms) for real-time engagement and data collection. This will ensure ongoing knowledge exchange and support the scaling and replication of innovative adaptation solutions.

The Adaptation Fund’s contribution will be prominently highlighted at key stages throughout the project, including grant sourcing, screening, and administration. UNDP will develop knowledge products that clearly demonstrate the impact of the Adaptation Fund, featuring key success stories that will be shared in broader external communications. Grantees will be encouraged to recognize the support of the Adaptation Fund and UNDP in their communications, ensuring proper acknowledgment without co-branding. Some examples of UNDP’s communication products related to adaptation for innovation solutions can be found below:

- Showcasing AIM and UNDP-AFCIA as UNDP’s Climate Promise flagship initiative.

- UNDP-AFCIA's grantee stories

- UNDP-AFCIA's catalogue factsheets

- UNDP-AFCIA's videos and Flickr

- UNDPs Innovation platform in Eurasia (landing page for all innovation related project)

The Regional Project will create a dynamic, inclusive learning environment that fosters knowledge exchange and supports the scaling and replication of successful adaptation solutions. Through a comprehensive knowledge exchange framework, the project will encourage collaboration, continuous learning, and innovation. This approach will empower grantees to strengthen their capacity to effectively tackle climate challenges across the Western Balkans.

The project's digital-first approach, incorporating online workshops, virtual collaboration platforms, and generative AI tools for innovation and knowledge co-creation, will measurably enhance participants' digital literacy and technological skills while strengthening their capacity to develop and scale locally-led climate adaptation solutions.

### Knowledge Management and Monitoring

As described in more detail in separate section, a robust results-based monitoring, evaluation and learning (MEL) framework will guide project implementation, allowing for the measurement of progress, identification of emerging challenges, and adaptive management. The MEL framework will be conducted in line with UNDP and AF requirements, ensuring accountability, learning, and adaptive management across the four participating countries. A dedicated knowledge management system will capture lessons learned, good practices, and innovations, disseminating them across regional and global adaptation platforms to support continuous learning and contribute to broader climate adaptation agendas.

The MEL system will be coordinated by the UNDP Istanbul Regional Hub as project lead, with oversight from the technical team and implementation support from the UNDP Country Offices. The framework will include:

- A web-based digital data collection system for quarterly grantee reports

- A results-based reporting template designed to meet both UNDP and AF requirements

- A project dashboard to track KPIs, measure progress, and showcase impact (as an example, please see UNDP-AFCIA dashboard).

- Consolidation of impact data generated by the Regional Project, and integration in UNDP’s Climate Change Adaptation portfolio’s dashboard ,  and in IRH’s databases and dashboards.

- Consolidation of regional data and quality assurance before submitting reports to the AF

Key performance indicators for this output will include:

- Progress measured through quarterly grantee reports

- Evaluation of grantee reports for alignment with project goals and gender/safeguard standards

- Regular participation in mid-term and terminal evaluations

- Existence a Learning Methodology to capture tangible and intangible learning from project team and grantees

Output 3.2 – Indicative Activities

- Document and publish case studies, policy briefs, and innovation profiles, focus on scalability, gender inclusion, and climate impact.

- Organize cross-border exchange visits and joint learning missions, target policymakers, innovators, and community leaders.

- Host regional webinars and podcasts on adaptation innovation, thematic focus on finance, gender, nature-based solutions, etc.

- Develop a regional knowledge dissemination toolkit, includes templates, translation support, and dissemination channels.

- Conduct impact assessments and learning reviews, feed into adaptive management and future programming.

- Support joint publications and research with academic institutions, promote evidence-based scaling and policy influence.

- Describe how the project /programme would promote new and innovative solutions to climate change adaptation, such as new approaches, technologies, and mechanisms.

## Promoting New and Innovative Solutions to Climate Change Adaptation

The Regional Project is designed to identify, support, and advance locally-led, innovative adaptation solutions that respond directly to the climate vulnerabilities of Bosnia and Herzegovina, Montenegro, North Macedonia, and Serbia. Drawing on lessons learned from the UNDP-Adaptation Fund Climate Innovation Accelerator (AFCIA), the project introduces a challenge fund model, a relatively new mechanism in the adaptation landscape that empowers non-traditional actors—such as grassroots organizations, social enterprises, cooperatives, and local innovators—to drive change.

Unlike conventional adaptation projects, innovation under this initiative is not limited to technological invention. It includes any improved or adapted solution that offers greater efficiency, effectiveness, equity, or sustainability. These principles are operationalized through a competitive grant process and structured support system, ensuring that innovations are both bold and grounded in local realities.

The project fosters innovation for adaptation considering:

- New approaches and technologies tailored to local socio-ecological realities;

- Revived and contextualized knowledge of social, economic, and political marginalized communities and traditional knowledge that supports adaptation;

- Enterprise-based solutions that integrate adaptation into sustainable business models;

- Social innovations that strengthen inclusion and climate leadership among women, youth, and marginalized groups.

All small grant proposals are screened against a rigorous set of innovation criteria, including:

- "Different or Better": The solution must represent an improvement or alternative to existing practices;

- Value-Driven: The innovation must address a specific, quantifiable adaptation problem;

- Scalability: A clear strategy must exist for replication or policy uptake;

- Feasibility: Solutions must be viable within current capacities and resources.

Additionally, proposals must outline pathways for financial, technical, and operational sustainability, including co-financing strategies, risk management, and an exit plan. All proposals are reviewed through a gender equality lens and screened for environmental and social safeguards.

### Innovation for Adaptation Approach

Through the three core technical components and dedicated project-management component, the Regional Project aims to foster, develop and accelerate locally-led adaptation innovation from local entrepreneurs and NGOs/CSOs, in each of the four partner countries, through three main avenues:

- Integration of climate change adaptation strategies with focus on vulnerable communities: Finding and implementing adaptation solutions that address priority climate risks in the Western Balkan countries, which are developed contextually and with the inclusion of the communities most vulnerable to climate change, to enable those communities to become more resilient to climate change.

- Innovate with focus on adaptation: Innovation for adaptation solutions may include approaches, technologies and mechanisms. Innovation for adaptation projects differ from concrete adaptation projects in their stakeholder engagement, including with unconventional actors, and in the emphasis on iterative deployment where change, learning, and new information is embraced and can take innovation projects in different directions (Definition of Innovation (AFB/B.36/8).

- Embed SES and Gender: Embed gender equality and social considerations into these innovative solutions, with measurable indicators and monitoring mechanisms to track progress, outcomes and impact.

The following sections elaborate on each of these three essential innovation and scaling skills.

1. Integration of climate change adaptation strategies with focus on vulnerable communities

1. Address Climate Change-induced Risks

The grantee funding proposal should be clearly linked to a sector identified at the national level (i.e. through NDCs, NAPs or National Communications) that is particularly vulnerable to climate change and specify the climate risks that the grant will be addressing. Different types of solutions that could be considered are, for example:

- Climate-resilient agriculture and food security

- Water management (harvesting, storage, recirculating water in areas or periods of drought).

- Flood risk management

- Nature-based solutions

- Urban climate resilience (e.g. resilient housing, energy efficient cooking).

- Disaster risk reduction (e.g. early warning systems, spatial risk mapping, wildfire prevention)

- Integrated coastal zone management practices

- Climate-Health Integrated Management

2. Measurable adaptation impacts

The project components will deliver measurable improvements in climate resilience by:

- Reducing exposure to climate hazards across agriculture, water, land, and urban systems;

- Enhancing the adaptive capacity of vulnerable communities and ecosystems;

- Fostering inclusive, gender-equitable innovation ecosystems that amplify the voices and leadership of women, youth, and marginalized groups;

- Building financially sustainable models for adaptation enterprises and solutions.

3. Address the Adaptive Capacity or Resilience of a Community to Climate Change, including Vulnerable and Marginalized Peoples

The project will support solutions that increase the adaptive capacity of a community and/or increase their resilience (including, for example, by increasing the resilience of the natural systems on which they depend) to climate change, including climate variability, as well as in the formation of resilient social networks. All proposed solutions will be required to address gender and vulnerability aspects of the target beneficiaries such as how to enhance adaptive capacity of women and girls, youth, peoples with disabilities, elders, ethnic minorities (e.g. Roma, Vlachs, Gorani, Egyptians in Montenegro), all of whom are particularly vulnerable to climate risks.

Proposed grantee solutions will be based on the application of the innovation-assessment methodologies and will describe the characteristics of community vulnerability and options considered to accelerate tried-and-tested and innovative solutions to climate change risks.

- Scale-up and Replicate Successful Locally-Led Adaptation-Innovation Results

With UNDP’s regional and global network and partners, successful adaptation-innovation technologies, practices and business models from the Regional Project, scaling up or replication of solutions will be explored through either public or private channels. Public channels include UNDP’s adaptation projects supported by AF, EU, GEF and GCF. Private channels include UNDP’s partners network and innovation ecosystem. These pathways will help expand the reach and impact of effective solutions, facilitating their adoption across a broader region.

While the project can play an important role in investment brokering by facilitating connections and supporting the development of a strong pipeline of investable projects, it will not engage in the extensive matchmaking process. The complexities of due diligence and the high level of engagement required to secure deals—especially between investors and grantees—are beyond the scope of the project. UNDP is positioned to provide strategic support but will not act as a dedicated intermediary to close investment deals. Instead, the focus will be on creating an enabling environment for scaling successful solutions and ensuring that projects are better positioned for future investment opportunities.

2. Innovate with focus on adaptation

The Adaptation Fund describes innovation for adaptation as:

“The creating, testing, deployment or diffusion of new, adapted or improved adaptation solutions, developed contextually and with the inclusion of the communities most vulnerable to climate change, to enable those communities to become more resilient to climate change. Innovation solutions may include approaches, technologies and mechanisms. Innovation projects and programmes differ from concrete adaptation projects and programmes in the nature of their stakeholder engagement, including with unconventional actors, and in the emphasis on iterative deployment where change, learning, and new information is embraced and can take innovation projects and programmes in different directions.”

The Regional Project will directly support the Adaptation Fund’s innovation for adaptation agenda by supporting initiatives that demonstrate strong potential to enable the most vulnerable communities to adapt to climate change impacts. Through this support, a diverse portfolio of locally appropriate, community-driven innovation activities has taken shape, each contributing uniquely to a broader ecosystem of learning, testing, replicating and/ or scaling.

The critical aspects to select strong, scalable and self-sustainable innovation for adaptation solutions are:

- Different or Better Solutions

The proposed idea must be an improvement over existing practices or solutions or a new solution that is meaningfully different than existing adaptation solutions. It must have added value over and above what the target beneficiary is currently using/practicing to address the adaptation problem that they are facing. These innovative solutions could be not only new technologies and approaches, but also building on and/or reviving and integrating traditional knowledge of social, economic, and political marginalized communities and local communities into the solutions. The grantee proposal should also show potential for systemic and sustained improvement of such practices or approaches, and even engaging with uncommon stakeholders.

- Delivers Value/Solves an Adaptation Problem

The proposed idea must address a specific and sizable adaptation problem that is incurring a cost (either in cash or in kind) to the target beneficiaries. For example, a revival of indigenous technology could be proposed to increase access to water during dry-spell resulting in reduction of multiple planting costs. It must deliver value and impact that can be quantified. Although, it is not required that the target beneficiaries have to pay (in-kind or in-cash) for such solution, it is crucial that project proponents articulate how the project would be operationally sustainable.

- Cross-scale Policy and Acceleration Potential

It is critical that replication and scale up potential are embedded in a project design from the beginning to increase the likelihood of project replicability and scalability. Therefore, all proposed grantee solutions will identify and engage tested solutions for potential replication, up-scaling, or integrating of the innovations to be supported, and describe a process to support such processes (e.g. holding knowledge fairs to promote replication, engagement of social impact investors etc.).

- Doable/Practical

Most markets value proven technologies that provide potential solutions that are also testable. Capacity, commitment, and track record of the proposal developers are also crucial in determining whether the idea can be realized and further developed into a successful venture. To support this, the project will offer targeted technical assistance to help strengthen promising ideas, ensuring they are feasible, viable, desirable, grounded in local realities, and designed for practical implementation and sustainability.

5. Evolves and Strengthens Through Innovation Practices

The proposed ideas should demonstrate the potential to evolve over time, incorporating learning, feedback, and the use of innovation tools and frameworks to improve design and delivery. This includes being open to refining solutions through testing, community engagement, and technical support.

To support this process, the project will draw on the expertise and experience of UNDP’s Istanbul Regional Hub. Through its innovation practice, IRH will provide technical assistance and design support at two key stages.
 
First, during the expression of interest stage, a broad pool of applicants will receive support to strengthen their understanding of the problem at hand and refine their proposals. This includes applying tools such as the portfolio approach, community listening, and foresight to help applicants unpack the problem, explore system dynamics, and improve the design and relevance of their ideas.

For shortlisted applicants, the project will offer more tailored, in-depth support through a structured accelerator programme. Drawing on tested initiatives such as BOOST, Tadamon NGO Empowerment Project, and other regional initiatives, this phase will provide practical tools, mentorship, and business development support to help selected grantees further develop their solutions and build the capabilities needed for effective implementation, scale, and long-term sustainability.

Together, this two-fold process not only strengthens individual proposals but also helps build a stronger, more investable pipeline of innovative, locally relevant adaptation projects for the region.

3. Embed Gender Equality and Social Considerations into Business Operations

Quantitatively (as much as possible) assess both direct and indirect costs and economic and financial, social and environmental benefits, with preference to work with women and the most vulnerable. The Regional Project´s screening criteria will address economic and financial viability criteria by describing value proposition and an economic/financial benefit and cost analysis to clearly and vulnerable communities, and vulnerable groups within communities, including gender considerations. Additionally, the proposal will have to compare the benefit/cost of its innovation against the existing baseline and/or current practices to demonstrate its innovative aspects as well as its cost effectiveness of the proposed innovation. All the projects will need to meet the GENDER Marker 2 at least, which means projects that have gender equality as a significant objective.

Potential environment and social impacts and their management will also be an essential part of the screening criteria, in alignment with the Adaptation Fund´s and UNDP´s Environmental and Social Policy. The project proponent will provide a brief environmental and social impact assessment and the corresponding management and monitoring and evaluation plan, as required according to the AF and UNDP relevant policies.

Furthermore, the small-grant proposal will integrate a simplified gender analysis to understand and meaningfully address the specific needs, priorities, structural and systemic barriers, status and roles of men and women. Proposals will detail how the project will advance gender equality and women’s empowerment, and must adhere to the Adaptation Fund´s and UNDP´s policies and requirements on gender. The proposal will demonstrate how the grantee project intends to build resilience, address their differentiated vulnerabilities and increase their capability to adapt to climate change impacts with a gender-responsive approach. The proposal will illustrate how gender equality is embedded in the project design, consultation, implementation, monitoring, reporting, and evaluation and how the project has adequate budget to deliver on these objectives. Existing gender inequalities should not be exacerbated by any activities or innovative solutions of grantee.

- Describe how the project/programme aims to roll out successful innovative adaptation practices, tools, and technologies and/or describe how the project aims to scale up viable innovative adaptation practices, tools, and technologies.

## Scaling Up and Rolling Out Successful Adaptation Innovations

A key objective of the project is to ensure that successful adaptation innovations do not remain isolated pilots but instead evolve into scalable and replicable models. To this end, the project integrates a multi-pronged strategy for scaling:

- Built-in Scalability Criteria: Proposals must demonstrate how their innovation could be scaled within or beyond their immediate context, including potential policy linkages and market channels.

- Dedicated Technical Support: A portion of the technical assistance facility is reserved specifically to support grantees in refining their scale-up strategies. This includes:

  - Technical advisory support in climate change adaptation

  - Technical advisory support in innovation processes

  - Business development and investment-readiness training;

  - Tailored incubation and acceleration services;

  - Support for implementing exit and sustainability strategies.

- Investment Brokering: The project through UNDP network of partners facilitates connections with public finance mechanisms (e.g., GEF, GCF, national funds) and private sector partners to unlock follow-on investment. Each grantee is encouraged to identify pipeline funding and partnerships from the outset.

- Knowledge Sharing and Peer Learning: Through regional innovation fairs, peer-to-peer exchanges, and learning platforms, successful innovations are showcased and shared across the four countries, enabling replication by other actors facing similar challenges.

- Global Networks and Visibility: Innovations supported by the project are integrated into UNDP’s Adaptation Innovation Marketplace (AIM) networks of partners (e.g. Adaptation Innovation Marketplace/AFCIA; BOOST programme, Tadamon programme, SGP Programme to mention few), which links grantees with international platforms for knowledge, funding, and policy engagement.

The project’s scaling framework is informed by practical experience under the UNDP-AFCIA initiative. As documented in the AFCIA Annual Reports (2022–2024), innovations such as solar-powered irrigation, fog harvesting, and community-based early warning systems have demonstrated how structured support, visibility, and ecosystem-building can lead to tangible and replicable adaptation impact.

Through its structured support model, focus on inclusive innovation, and clear pathways for scale, the Regional Project ensures that locally-led adaptation solutions are not only discovered—but strengthened, replicated, and sustained. It positions the Western Balkans as a regional hub for climate adaptation innovation, while contributing to the global knowledge base on how to enable transformational resilience at scale.

## Economic, Social, and Environmental Benefits and Safeguards

The Regional Project is designed to deliver tangible economic, social, and environmental benefits while ensuring strong alignment with the Environmental and Social Policy (ESP) and Gender Policy (GP) of the Adaptation Fund and UNDP. The project gives particular attention to the needs and priorities of vulnerable communities and groups within communities, including women, youth, communities facing social, economic, and political marginalization, persons with disabilities, and other marginalized populations.

- Describe how the project / programme would provide economic, social, and environmental benefits, with particular reference to the most vulnerable communities, and vulnerable groups within communities, including gender considerations.  Describe how the project / programme would avoid or mitigate negative impacts, in compliance with the Environmental and Social Policy and Gender Policy of the Adaptation Fund.

### Economic, Social, and Environmental Benefits

Economic Benefits

Through catalytic grant support and technical assistance, the project supports the development of inclusive and sustainable adaptation enterprises, with clear value propositions and demonstrable cost-effectiveness. Each small grant proposal must conduct a benefit-cost analysis that identifies both direct and indirect economic impacts—such as reduced loss and damage from climate hazards, improved agricultural productivity, and new or strengthened livelihood opportunities. The project also encourages innovations that lower climate-related costs for at-risk communities and foster long-term financial sustainability.

Social Benefits

The project is committed to strengthening social equity and resilience. All supported initiatives must address differentiated vulnerabilities across social groups, with a particular focus on enhancing the adaptive capacity and leadership of women and girls, while also empowering youth and underrepresented groups. Proposals are required to articulate how they will promote inclusive participation, strengthen community networks, and contribute to improved access to information, resources, and services.

Environmental Benefits

Funded innovations are expected to contribute to environmental protection and ecosystem resilience, including through nature-based solutions, improved water and land management, and the restoration of degraded ecosystems. The project promotes climate-smart practices that deliver co-benefits for biodiversity, soil and water quality, and long-term ecosystem services.

### Gender Considerations and Social Inclusion

Gender equality and women's empowerment are central to the project’s design and implementation. In alignment with the Adaptation Fund’s Gender Policy, all grantees will be required to:

- Conduct a gender analysis as part of project planning;

- Ensure inclusive participation of women and men in consultations and decision-making;

- Embed gender-responsive objectives and indicators in their results frameworks;

- Allocate sufficient resources to implement gender-focused activities.

Proposals must also show how project design and implementation will contribute to addressing structural barriers, ensuring equitable access to benefits, and strengthening the agency of women and girls, youth, peoples with disabilities, elders, ethnic minorities (e.g. Roma, Vlachs, Gorani, Egyptians in Montenegro) in local adaptation efforts. Please refer to GAAP in the Annex 5.

### Environmental and Social Safeguards

All project activities will be assessed and implemented in accordance with the Environmental and Social Policy (ESP) of the Adaptation Fund and UNDP’s Social and Environmental Standards. Environmental and social risks will be proactively identified and managed through a phased, consultative approach:

- Initial National-Level Consultations: In coordination with UNDP Country Offices, the project has initiated virtual consultations with national stakeholders—government institutions, civil society organizations, and technical experts—in each participating country. These discussions are informing the design of the project framework, principles for implementation, and early identification of environmental and social risks.

- Integration of National Priorities: In-house localized know-how of the project team as well as stakeholder input will be used to align the project with national climate adaptation priorities and contextual realities, before and throughout the specific grantee-led interventions are identified. This approach helps ensure local relevance and ownership and enhances safeguard responsiveness from the outset. Any risks will be duly recorded and brought to the attention of the regional SES specialist and Steering Committee as needed.

- Site-Specific Safeguard Measures: Once grantees are selected and specific sites/interventions are confirmed, a more detailed review by the project team in consultation with the Gender Specialist and SES Specialist as needed will be conducted and based on the review, targeted screenings and or community-level consultations will be conducted. These targeted screenings may necessitate the development:

  - Environmental and Social Management Plans (ESMPs)

  - Stakeholder Engagement Plans (SEPs)

  - Gender Action Plans (GAPs)

  - Risk mitigation frameworks, with support from a designated safeguards expert

This phased safeguards approach enables responsible expectation management, ensures compliance with AF and UNDP policies, and provides transparency throughout the project lifecycle—especially in the early stages when grantee selection and project sites are still being finalized.

More information is found in Annexes 3, Social and Environmental Screening Procedure and Annex 4, Environmental and Social Management Plan.

### Integrated Risk and Benefit Management

Through the screening and review process, all grantee proposals will be evaluated for:

- General due diligence process; including checking legal registration documents, social media accounts, and other relevant documents to ensure compliance with the minimum application pre-requisites,  including the alignment with Technology Needs Assessments (if applicable)

- Economic and financial viability, including direct and indirect benefit potential;

- Social inclusiveness and gender-responsiveness, with clear targets for vulnerable groups;

- Environmental sustainability, with impact mitigation plans where necessary.

A portion of the project’s technical assistance facility is dedicated to helping grantees implement safeguards, exit strategies, and sustainability measures, ensuring that adaptation innovations deliver long-term, transformative impact without causing harm.

- Describe or provide an analysis of the cost-effectiveness of the proposed project / programme and explain how the regional approach would support cost-effectiveness.

## Cost-Effectiveness of the Proposed Project and Added Value of the Regional Approach

The Regional Project is designed to deliver impact through a cost-effective, performance-based, and partnership-oriented model. The project maximizes the use of existing institutional infrastructure, leverages strategic partnerships, and applies a regional lens to promote efficient delivery and optimize results.

### Cost-Effectiveness of the Innovation Model

The project uses an approach to identify, test, and scale the most promising locally-led adaptation innovations. Rather than predetermining intervention sites or thematic areas, the open call of interest mechanism enables a bottom-up selection process, allowing the best ideas to emerge based on merit and contextual relevance. This method avoids inefficiencies often associated with top-down programme design and ensures that resources are allocated to interventions with the highest potential for impact.

Proposals will be selected based on clearly defined, multi-criteria screening, including:

- Adaptation relevance and innovation potential;

- Financial, technical, and operational sustainability;

- Economic, social, and environmental co-benefits;

- Alignment with the Environmental and Social Policy and Gender Policy of the Adaptation Fund and UNDP.

This approach ensures that only initiatives offering strong value for money and alignment with adaptation priorities will be supported.

### Leveraging UNDP's Institutional Capabilities

The project builds on UNDP’s proven experience in managing multi-country and innovation-focused initiatives, such as the Global Environment Facility’s Small Grants Programme (GEF SGP), the Adaptation Fund Climate Innovation Accelerator (AFCIA), the BOOST Impact Acceleration Programme, and the TADAMON NGO Empowerment Programme. It also draws on our extensive work applying systems thinking and portfolio approaches to address complex development challenges, particularly through initiatives like the City Experiment Fund and Mayors for Economic Growth.

These established programme structures, operational systems, and regional knowledge - including pre-existing insights from our work in the Western Balkans - will be adapted and applied to this project. This significantly reduces start-up costs and enables rapid, community-driven, high-quality delivery without the need to build new entities or teams from scratch. This use of existing infrastructure represents a cost-efficient model of fund administration, technical assistance, and monitoring and evaluation, while still offering sufficient flexibility to tailor support to local conditions.

This project will be supported throughout by the expertise of UNDP’s Istanbul Regional Hub, which leads the application of innovation practices, ecosystem development, and systems approaches across the region. Through this work, IRH provides practical methods to help local actors design solutions that are ambitious, strategic, and grounded in context. These capabilities, along with tools such as the portfolio approach, community listening, foresight, and innovation accelerators like BOOST and Tadamon NGO Empowerment Project, will be embedded into the project to strengthen proposals, build robust solutions, and ensure supported initiatives are well-positioned for implementation and scale.

### Economies of Scale and Efficiency through a Regional Approach

This project aligns with UNDP's Regionality Principles by promoting regional public goods through strengthened cooperation and integration, managing climate adaptation externalities that transcend borders, and generating shared development knowledge and innovation that overcomes institutional and financial barriers too high for individual countries to surmount alone.

Implementing this project as a regional initiative rather than as separate national projects creates multiple opportunities for cost-efficiency and knowledge synergies, including:

- Shared technical and advisory resources across countries, avoiding duplication of efforts and access to wide range of technical expertise and knowledge;

- Joint learning platforms and knowledge exchange events that serve multiple countries at once;

- Regional coordination mechanisms that streamline governance, reduce overhead costs, and improve implementation consistency;

- Cross-border replication of successful solutions, reducing the need to reinvent adaptation models in each national context.

These efficiencies ensure that a greater proportion of available funding directly supports innovation development and scaling, rather than administrative or transaction costs.

### Strategic Partnerships and Co-Financing Opportunities

The project’s cost-effectiveness is further enhanced by its ability to leverage additional technical and financial contributions from strategic partners. Organizations that are already working with UNDP under the UNDP-AFCIA Programme, such as the Global Resilience Partnership (GRP), Climate-KIC, impact investment and philanthropy networks, public or private funders could be potentially engaged to provide additional technical support or knowledge exchange/amplification. These partnerships will:

- Enhance the project’s reach and visibility;

- Enable resource pooling for grantee support;

- Unlock additional investment pathways for scaling successful innovations;

- Align scalability requirements and technical support with impact funder´s requirements.

Under UNDP-AFCIA´s Fellowship programme and thought leadership work stream,  three informal Collaborative Working Groups with key systemic stakeholders have been set up, including Alti Global, BNP Paribas, UNCDF, Euroclear, Fidelity, and Acumen, to explore and advance the potential of micro-bonds and blended finance as innovative mechanisms to mobilize capital for climate resilience and adaptation at the local level. A key focus of this initiative is tackling one of the most critical bottlenecks hindering climate projects in the global south: the smaller ticket sizes of these projects, coupled with their high perceived risk. The Collaborative Working Group is exploring pathways to de-risk such investments, making them more attractive to private sector players and institutional investors while ensuring financial models that enable scalability and long-term sustainability.

By aligning with partners that share a common goal of accelerating innovation for climate resilience, the project is well-positioned to amplify its impact without requiring proportionate increases in budget.

In summary, the project offers a highly cost-effective model for delivering climate adaptation results through innovation. It combines a competitive, performance-based funding mechanism with efficient use of UNDP’s infrastructure, strategic partnerships, and the collective efficiencies of a regional platform. This structure ensures that the project delivers maximum value per dollar invested, with a strong emphasis on sustainability, scalability, and inclusive impact.

- Describe how the project / programme is consistent with national or sub-national sustainable development strategies, including, where appropriate, national or sub-national development plans, poverty reduction strategies, national communications, or national adaptation programs of action, or other relevant instruments, where they exist. If applicable, please refer to relevant regional plans and strategies where they exist.

## Alignment with National, Sub-National and Regional Adaptation and Development Strategies

The Regional Project is fully aligned with the national and sub-national sustainable development strategies, climate policies, and adaptation priorities of Bosnia and Herzegovina, Montenegro, North Macedonia, and Serbia. The project is also consistent with the objectives of the Paris Agreement, 2030 Agenda for Sustainable Development, and the respective Nationally Determined Contributions (NDCs) of the participating countries. At the regional level, the project complements efforts to promote stability, resilience, and climate-smart development in Southeast Europe.

### Alignment with National Adaptation Plans (NAPs)

All four participating countries are actively engaged in advancing their National Adaptation Plans (NAPs) with support from the Green Climate Fund (GCF) and UNDP. This project is designed to complement, accelerate, and amplify these national processes by catalysing local adaptation innovations that address the priority sectors and vulnerable populations identified in each NAP.

- Bosnia and Herzegovina finalized its NAP in December 2022, identifying agriculture, water resources, biodiversity and forestry, health, and tourism as key priority sectors. The project directly supports Bosnia’s emphasis on nature-based solutions, early warning systems, resilient agriculture, and community-level capacity building.

- Montenegro is finalizing its NAP with UNDP support, with a focus on agriculture, water, health, and tourism. The project aligns with Montenegro’s efforts to integrate adaptation into national planning systems and strengthen institutional capacities for evidence-based, gender-sensitive adaptation decision-making.

- North Macedonia initiated its GCF-funded NAP process in 2024, prioritizing adaptation in water, agriculture, energy, health, biodiversity, forestry, and cultural heritage, with a nexus approach and cross-sectoral planning. The project’s multi-sectoral, locally-led innovation approach is highly complementary to North Macedonia’s integrated planning objectives.

- Serbia officially adopted NAP in December 2023 by Government’s decision, and submitted its NAP to UNFCCC in July 2024. It outlines cross-sectoral adaptation measures including in agriculture, energy, infrastructure, health, biodiversity, and urban planning. The project supports Serbia’s priorities by targeting community-level innovation in these sectors and promoting scalable adaptation practices aligned with Serbia’s institutional frameworks.

In all four countries, the project will engage closely with ministries and institutions responsible for adaptation planning, contributing to the mainstreaming of climate resilience into sectoral development policies and budgets.

### Alignment with SDGs, NDCs, and Other National Strategies

At the national level, the project also supports implementation of:

- NDC commitments, especially in adaptation-relevant sectors such as agriculture, water, ecosystems, health, and infrastructure;

- National sustainable development strategies that promote resilience, economic inclusion, and green growth;

- Poverty reduction strategies by targeting the most vulnerable populations, including women, rural communities, and marginalized groups.

Each grant proposal submitted under the project will be required to demonstrate alignment with national and sub-national policies. This includes explaining how the innovation contributes to:

- SDG 2: Zero Hunger;

- SDG 5: Gender Equality;

- SDG 6: Clean Water and Sanitation;

- SDG 13: Climate Action;

- and other context-specific SDGs and national development objectives.

This alignment will be part of the screening and selection criteria, ensuring coherence between project-supported activities and national adaptation and development priorities.

### Alignment with Technology Needs Assessments (TNAs) and Technology Action Plans (TAPs)

In addition to alignment with NAPs and NDCs, the project will also take into account the Technology Needs Assessments (TNAs) and Technology Action Plans (TAPs) where available in the participating countries, as follows:

- Bosnia and Herzegovina initiated TNA for both mitigation and adaptation in the Fourth National Communication to the UNFCCC, with a focus on sectors such as agriculture and water resources.

- North Macedonia has completed the process of TNA in energy sector in 2004.  There are no Technology Action Plans (TAPs) for North Macedonia listed on TT:CLEAR as of today. Currently the Fifth National Communication and Bi-Annual Transparency Reports are under preparation and TNA with TAPs will be developed. Both documents are expected to be completed by 2026.  National submissions and summaries consistently flag water resources, agriculture, forestry/biodiversity (incl. wildfire risk), health, and tourism & cultural heritage as priority sectors for adaptation, with cross-cutting DRR/governance and early-warning components.

- Montenegro has completed their TNA processes identifying technology priorities across key adaptation and mitigation sectors. The assessment prioritized water resources, public health, agricultural land and production, coastal zones, and forests for climate adaptation. Montenegro’s Third National Communication (TNC) to the UNFCCC, published in 2020, reinforced many of the TNA’s findings. The TNC presented projections under “without measures” and “with additional measures” scenarios, alongside sector-specific mitigation actions. It also provided a detailed assessment of climate risks, highlighting increased exposure to droughts, floods, wildfires, and heatwaves. Adaptation options were laid out for water management, forestry, agriculture, coastal protection, health, and urban resilience. For the period 2025–2035, the updated strategy and action plan will need to align the TNA’s technology priorities with the new NDC targets and NECP measures. On the adaptation side, operationalising the NAP will be critical for sequencing measures such as water balance management, flood early-warning systems, drought response, wildfire prevention, climate-resilient agriculture, and coastal protection. Key enabling actions remain consistent with the original TNA recommendations but have become more urgent. These include expanding financing instruments through the Eco-Fund and international partners, strengthening and enforcing technical standards, upgrading the monitoring, reporting, and verification (MRV) system, investing in data and information services, and ensuring effective coordination among ministries and stakeholders.

- In Serbia,  the Biennial Transparency Report recognizes the need for technological development and technology transfer to strengthen Serbia’s capacities and technologies, thus contributing to the achievement of long-term climate goals in accordance with the Paris Agreement and the commitments defined in NDC. TNA identified the need for development and transfer technologies in the context of climate change, including creating, spreading, and applying new technologies that help, not only mitigate climate change, but also adapt to its effects. TNA demonstrated that assistance is needed in promoting technological development and technology transfer in the following sectors:

  - Agriculture (improvement of technology and practices in the agricultural sector), e.g. Precision farming (PF), including Variable Rate Technology (VRT), Remote Sensing Technologies, Global Positioning Systems (GPS) and Geographic Information Systems (GIS) to support the more precise application of inputs and machinery, on 146 kha by 2030. This will contribute to a 20.44kt CO2 eq reduction compared to the WOM scenario.

  - Industry (modernization of technological processes in industrial production),

  - Energy (improvement of the use of renewable energy sources and modernization of the energy sector),

  - Transport (promotion of the production and use of advanced biofuels, as well as the development of infrastructure for alternative fuels).

Serbia’s National Climate Change Adaptation Programme envisaged the deployment of resilient infrastructure and production technologies—such as optimized irrigation systems, drought resistant crops, climate-smart livestock facilities, anti-hail and frost-protection systems, green infrastructure in urban planning, and sustainable soil management methods. Integrated climate information and monitoring technologies (high-performance computing systems, automated meteorological, hydrological, soil-moisture and agrometeorological stations, radar and satellite remote sensing, GIS-based georeferenced data portals, biodiversity and ecosystem monitoring tools) supported by data integration and early-warning platforms with advanced forecasting and dissemination capabilities; modelling and simulation tools for climate risk assessments (including agriculture, forestry, infrastructure, health, and biodiversity), and decision-support systems for public policy integration and budget tracking. In the field, specialized sensors, drones, and remote monitoring devices for damage and loss assessments.The regional project will review and incorporate the findings of these TNAs, TAPs, and equivalent instruments during implementation—particularly within the due diligence and technical support processes. This will help guide the selection and scaling of locally led innovations, ensuring their alignment with national technology priorities. Integrating these instruments will further enhance country ownership, policy coherence, and the long-term sustainability of project outcomes.

Regional and Multi-Country Value

As a regional initiative, the project adds unique value by facilitating:

- Cross-border knowledge exchange on shared climate risks;

- Replication of tested practices across similar ecological and socio-economic contexts;

- Regional collaboration mechanisms that support the diffusion of innovative solutions, alignment of policy instruments, and strengthening of collective resilience.

Rather than duplicating isolated national efforts, this regional approach allows countries to benefit from economies of scale, shared learning platforms, and coordinated support systems. It enhances regional capacity while reinforcing country ownership and leadership in climate adaptation. This alignment ensures that the project effectively addresses local vulnerabilities while also making a valuable contribution to the broader regional and global climate resilience agenda.

- Describe how the project / programme meets relevant national technical standards, where applicable, such as standards for environmental assessment, building codes, etc., and complies with the Environmental and Social Policy of the Adaptation Fund.

## Compliance with National Technical Standards and the Adaptation Fund’s Environmental and Social Policy

The Regional Project is designed to ensure full compliance with relevant national technical standards, sectoral regulations, and the Environmental and Social Policy (ESP) and Gender Policy (GP) of the Adaptation Fund (AF). Alignment with these frameworks is embedded in both the design and implementation modalities of the project.

### Integration into Grant Proposal and Selection Process

As part of the competitive grant process, all applicants will be required to:

- Demonstrate alignment with national technical regulations and standards, including but not limited to environmental assessments, building codes, agricultural practices, water management protocols, and public health standards relevant to the nature and scope of their proposed innovation;

- Describe how proposed products, services, or technologies comply with applicable national and—where relevant—international standards, especially for innovations intended for broader replication or export.

This requirement is clearly outlined in the grant application template and forms a core part of the proposal evaluation and due diligence process.

### Verification During Implementation

Once grants are awarded, grantees will be expected to:

- Report on their compliance with the national technical standards outlined in their original proposal;

- Provide supporting documentation or certificates (where applicable), such as approvals, permits, or independent verification of conformity with standards;

- Submit to compliance monitoring conducted through the project’s monitoring and evaluation framework, in collaboration with UNDP Country Offices and technical experts.

This process will ensure that innovations supported by the project are not only context-appropriate and effective, but also safe, legally compliant, and scalable.

### Environmental and Social Safeguards

Since the project includes a range of activities and sub-projects with yet unknown design parameters and uncertain social and environmental risks that cannot be fully assessed during the project appraisal, this Environmental and Social Management Framework (ESMF) has been developed to guide further assessment and management of the expected environmental and social risks of the project based on the applicable UNDP's Social and Environmental Standards (SES) and the Adaptation Fund’s ESP and GP.

In line with the ESMF:

- All grantees will undergo a preliminary environmental and social risk screening as part of the proposal assessment process;

- A qualified safeguards expert in coordination with the Performance and Data Analystexpert will provide technical support and quality assurance to grantees throughout the project lifecycle.

UNDP will ensure that no activity causes or contributes to adverse environmental or social impacts, particularly on vulnerable or marginalized groups. Local consultations and grievance mechanisms will be implemented where necessary, consistent with national requirements and AF policy.

- Describe if there is duplication of project / programme with other funding sources, if any.

## Maximizing Synergy: Enhancing Regional Climate Resilience through Complementary Adaptation Initiatives

The Regional Project has been designed to complement, rather than duplicate, existing regional adaptation initiatives, ensuring its alignment with the broader regional and global climate adaptation agenda. By addressing local vulnerabilities and supporting climate resilience, the project will build on and scale up adaptation innovations in synergy with ongoing initiatives. Efforts will be made to avoid the duplication of activities, with careful attention to leveraging existing resources, structures, infrastructures, and services from other projects to maximize efficiency and impact.

During the preparatory phase, the project will assess relevant ongoing and past initiatives to ensure proper alignment, complementarity, and compatibility. This process will occur during the concept and proposal stages, facilitating coordination with other organizations and program focal points in the project area. By prioritizing consultation and collaboration, the project will avoid redundancy and ensure that activities are well-integrated within the broader landscape of regional adaptation efforts.

Through a structured approach to coordination, the project will enhance its contributions to regional adaptation goals, driving innovation while supporting and building on existing frameworks. This proactive strategy will ensure that the project complements and strengthens existing efforts, fostering a collaborative environment where synergies can be realized and outcomes can be maximized.

The following provides a comprehensive analysis of how the proposed project aligns with and contributes to the broader spectrum of existing adaptation initiatives in the region:

- Regional Cooperation Council (RCC)

The RCC is a key regional platform that promotes cooperation, sustainable development, and integration across the Western Balkans. While it focuses on economic growth, green transformation, and reducing regional disparities, the Regional Project complements these efforts by addressing specific climate adaptation challenges through locally-driven solutions. The project will contribute to the RCC's broader objectives by focusing on the practical implementation of climate adaptation innovations, ensuring alignment with the region's sustainable development goals without overlapping with RCC's broader political, economic, and environmental initiatives.

- Biodiversity Task Force of the Western Balkans (BDTF WB)

The BDTF WB focuses on integrating biodiversity into regional environmental policy and fostering cooperation on biodiversity conservation. The Regional Project complements these efforts by incorporating biodiversity considerations into local climate adaptation strategies, promoting climate-resilient solutions that enhance ecosystem stability. By addressing local climate vulnerabilities, the Regional Project supports the region's biodiversity goals without duplicating the BDTF WB's core work, ensuring alignment with broader sustainability and resource management objectives.

- Green Agenda for the Western Balkans (GAWB)

The GAWB is a strategic framework designed to align the region with the European Green Deal and the 2030 Biodiversity Strategy, promoting sustainable economic transformation and carbon neutrality by 2050. The Regional Project supports GAWB’s goals by scaling locally-led climate adaptation solutions that address specific climate vulnerabilities. While GAWB focuses on broader sustainability objectives, the Regional Project takes a more targeted approach, accelerating innovation at the community level and complementing the Green Agenda’s vision by strengthening local capacities for climate resilience and adaptation.

- IUCN: Greening the Western Balkans Project (2024–2028)

The Greening the Western Balkans Project focuses on restoring and protecting biodiversity across the region, strengthening governance, and promoting regional cooperation. The Regional Project complements these efforts by enhancing climate resilience through locally-led adaptation innovations, addressing local climate risks, and scaling up climate adaptation solutions. While both projects share a focus on environmental sustainability, the Regional Project extends IUCN’s work by introducing new practices for climate resilience and supporting communities in adapting to climate change, without duplicating conservation activities.

- IUCN (SIDA): ADAPT 2.0: Nature-based Solutions (NbS) for Climate Change Mitigation and Adaptation

ADAPT 2.0 integrates Nature-based Solutions (NbS) into regional policies and development frameworks to address climate and biodiversity challenges in the Western Balkans. The Regional Project complements ADAPT 2.0 by extending NbS into a broader adaptation strategy that addresses a wider range of climate vulnerabilities and promotes locally-led solutions to enhance resilience across the region. While ADAPT 2.0 focuses primarily on NbS for climate mitigation and adaptation, the Regional Project incorporates NbS as a key component while introducing additional innovative adaptation practices, ensuring alignment with the broader climate adaptation agenda without duplicating ADAPT 2.0’s focus.

- EU’s Economic and Investment Plan for the Western Balkans (EIP)

The EIP focuses on driving long-term economic recovery and green transition through infrastructure and economic development. The Regional Project complements the EIP by scaling up climate adaptation solutions at the local level, addressing the specific climate vulnerabilities of communities and ecosystems. While the EIP emphasizes sustainable economic growth and green transformation, the Regional Project ensures that climate resilience is integrated into the region’s broader development strategies, filling an important gap in local adaptation efforts. This alignment allows both projects to contribute to a cohesive strategy for sustainable development without overlapping in their core activities.

- AF-UNDP: Integrated Climate-resilient Transboundary Flood Risk Management in the Drin River Basin

The AF-UNDP project focuses on transboundary flood risk management in the Drin River Basin, addressing climate-induced risks through improved coordination and resilience-building measures. The Regional Project complements this initiative by expanding its scope beyond flood risk management, addressing a wider range of climate adaptation challenges across the Western Balkans. While both projects aim to enhance climate resilience, the Regional Project introduces innovative solutions to various climate impacts and scales them beyond the Drin River Basin, ensuring a holistic approach to regional climate adaptation.

The Regional Project is strategically designed to complement the ongoing adaptation initiatives in the region, contributing to the broader climate resilience agenda without duplicating existing efforts. By focusing on locally-driven innovations, enhancing community-level resilience, and fostering regional collaboration, the project will add value to the existing adaptation framework in the Western Balkans, ensuring that adaptation solutions are scalable, inclusive, and aligned with broader regional and global goals.

- Describe the learning and knowledge management component to capture and disseminate lessons learned.

## Learning and Knowledge Management

### Empowering Grantees and Strengthening Local Adaptation through Knowledge Exchange

Knowledge exchange and peer-to-peer learning are fundamental to the Regional Project as they create opportunities for grantees to share valuable insights, best practices, and lessons learned from their own experiences. By facilitating networking and providing direct communication channels between grantees, the project fosters a collaborative environment where participants can learn from one another and collectively address common challenges. This approach promotes the cross-pollination of ideas and solutions, enhancing local adaptation efforts while scaling up successful initiatives. Peer-to-peer exchange not only strengthens the impact of the project but also empowers grantees by building valuable connections and creating opportunities for collaboration and growth across the region.

### Fostering Knowledge Exchange and Capacity Building through the MBA Internship Program

The MBA Internship Programme is a powerful tool for knowledge exchange, strategically linking academic expertise from leading business schools with the practical needs of locally-led climate adaptation initiatives. This unique partnership, which includes UNDP, a responsible party selected within UNDP’s procurement standards, and top-tier universities, fosters an environment for cross-disciplinary collaboration. By embedding MBA students with Regional Project grantees, the program facilitates the transfer of essential business knowledge, particularly in areas such as business model refinement, financial strategy, and market expansion. In turn, students gain valuable insights into the complexities of climate adaptation in the Global South, deepening their understanding of real-world challenges faced by grassroots organizations. This exchange not only bridges the gap between academic theory and practical application but also contributes to the development of a more robust, evidence-based understanding of climate adaptation and innovation.

From a knowledge management perspective, the MBA internship program serves as a platform for the continuous documentation and sharing of lessons learned from both students and grantees. Grantees benefit from the strategic support provided by students, which enhances their ability to scale successful climate solutions and strengthen their organizational capacity. For students, the program offers a rare opportunity to apply academic knowledge in real-world settings, contributing to meaningful solutions for complex climate issues. Through this continuous knowledge exchange, the program helps create a living repository of insights, best practices, and case studies, which can be leveraged to inform future adaptation strategies. By fostering a culture of mutual learning, the program ensures that innovative climate solutions are better supported and more widely replicated, strengthening the knowledge base of all stakeholders involved.

The structure of the MBA internship program also promotes systemic learning and knowledge exchange on a broader scale. Through collaboration between academia, development organizations, and the private sector, the program creates an inclusive environment for shared learning, facilitating discussions on critical issues such as blended finance and how to scale financing models to support climate adaptation projects. Students’ exposure to these innovative financial mechanisms contributes to an evolving understanding of how to effectively address funding gaps for adaptation initiatives. The program helps to build a knowledge ecosystem where students, local organizations, and global experts can collaborate and share insights. This continuous learning process not only addresses immediate challenges but also generates long-term value by fostering sustainable and scalable solutions. Ultimately, the MBA internship program contributes to building a more resilient climate adaptation landscape, ensuring that lessons learned can be applied to future projects and scaled across regions.

The results from the knowledge management component can also be fed into the work that the three Collaborative Working Groups established with support from UNDP-AFCIA, to explore and advance the potential of micro-bonds and blended finance as innovative mechanisms to mobilize capital for climate resilience and adaptation at the local level. Key partners like the Global Resilience Partnership and the MBA schools engaged in the MBA internship programme, have also expressed interest in continuing to co-developing case studies and specialized research about scaling locally led adaptation solutions, using as a base the pipeline of projects created by UNDP under this regional project.

### Creating a Knowledge Platform to Support Scaling and Replication

The regional project will establish a comprehensive knowledge-sharing and learning structure designed to facilitate the exchange, scaling, and replication of climate adaptation solutions. This approach will align with the Adaptation Fund’s Monitoring and Tracking System (AF MTS), specifically focusing on Strategic Focus 3, which emphasizes sharing lessons learned and developing guidance on adaptation finance and actions. Key outcomes will include identifying, codifying, and disseminating lessons learned while creating knowledge to support scaling efforts and strengthen adaptation capacities across the region.

The structured knowledge exchange system will facilitate the sharing of best practices, lessons learned, and innovative solutions. This system will not involve developing an online platform but will instead establish a structure that ensures effective knowledge dissemination across various channels. This structure will build on existing regional knowledge and experiences from ongoing UNDP Istanbul Regional Hub initiatives and UNDP Country Office initiatives in the Western Balkans, leveraging tools such as social media, blogs, working papers, case studies, and open-source applications to ensure broad access to key knowledge.

The knowledge exchange will be strengthened by community engagement tools such as the BOOST Alumni Network, network of AIM partners, UNDP SGP’s Global Citizens Knowledge Platform, and South-South Cooperation initiatives, which will help expand the reach and impact of the knowledge-sharing efforts.

The peer learning opportunities are facilitated among regional grantees. These events, such as hackathons, innovation fairs, and product showcases, will encourage the cross-fertilization of ideas and foster collaboration, helping to scale and replicate successful adaptation solutions across the region. These learning events will be organized in close collaboration with direct access grantees and the broader AIM community, enabling a dynamic flow of knowledge and building a foundation for scaling impactful solutions.

Additionally, the project will enhance the knowledge base through virtual connections between the knowledge exchange structure and leading incubators, accelerators, innovation labs, and climate adaptation practitioners. This collaboration will help integrate diverse perspectives and expertise, enriching the capacity-building process. A strategic communication and dissemination program will also be implemented to raise visibility and highlight the Adaptation Fund’s contribution throughout the project lifecycle, ensuring that key learnings and achievements reach relevant stakeholders at national, regional, and global levels.

Furthermore, the project will utilize several existing platforms and tools to further enhance knowledge exchange and peer learning, including Community of Practice (CoP) platforms like Slack and Microsoft Teams, surveys and polls through platforms such as SurveyMonkey and Google Forms, and the Adaptation Innovation Marketplace for showcasing and sharing innovative climate solutions. Learning platforms for webinars, virtual workshops, and training will be leveraged to deliver capacity-building content to grantees, enhancing their understanding of climate adaptation solutions and equipping them with practical tools to implement in their communities.

Through this comprehensive structure, the project will facilitate an ongoing cycle of knowledge creation, validation, and sharing, promoting collaboration across the region and fostering the scaling of locally led, gender-responsive climate adaptation solutions.

### Visibility and Branding of the Adaptation Fund

The Adaptation Fund’s support will be clearly visible at key stages of the project, including grant sourcing, screening, and administration. UNDP will produce knowledge products that showcase the impact of the Adaptation Fund, with success stories shared for broader external communication. Grantees will be encouraged to acknowledge the support of the Adaptation Fund and UNDP in their communications, ensuring proper recognition without co-branding.

By creating a dynamic and inclusive learning environment, the Regional Project will enhance knowledge exchange, facilitate scaling and replication of adaptation solutions, and empower grantees to address climate challenges more effectively across the Western Balkans.

- Describe the consultative process, including the list of stakeholders consulted, undertaken during project / programme preparation, with particular reference to vulnerable groups, including gender considerations, in compliance with the Environmental and Social Policy of the Adaptation Fund.

## Consultative Process and Stakeholder Engagement Approach

At the stage of the Regional Project´s preparation, it was not yet feasible to conduct deeper consultations at the level of specific project sites or with stakeholders that will ultimately be engaged by the grantees. This is because the specific sub-projects and implementing partners (grantees) across the three target countries will be identified through a transparent open call for proposals, which will take place at the beginning of implementation. As such, the project currently includes Unidentified Sub-Projects (USPs), consistent with the nature of the innovation process being supported and in line with guidance from the Adaptation Fund (Decision B.39/52).

Given this structure, UNDP´s approach to stakeholder consultation has been adapted accordingly. In line with the Adaptation Fund’s Environmental and Social Policy (ESP) and Gender Policy (GP), we are undertaking initial virtual consultations with key national stakeholders—coordinated through the respective UNDP Country Offices in the 4 participating countries. These consultations include representatives from government agencies, civil society organizations, research centres and other relevant institutions, and are intended to inform the overall project framework, including implementation principles and safeguards.

UNDP recognizes that national stakeholders require clarity on the project’s direction and expected outcomes. While specific grantee-led activities cannot yet be defined, UNDP is ensuring that stakeholder input shapes the overarching implementation approach and risk identification processes at the national level. This includes integrating national priorities and contextual realities now as part of the project design stage.

Once grantees are selected and specific interventions and sites are identified through the open call process, more detailed, locally grounded stakeholder consultations will be conducted. These will include consultations with vulnerable or marginalized groups, women, Indigenous Peoples, and other directly affected communities as relevant. At that stage, UNDP will also develop and disclose detailed risk assessments and management instruments—including gender action plans, stakeholder engagement plans, and environmental and social management plans—supported by gender and safeguards experts as part of project support and quality assurance.

This phased approach allows UNDP to manage stakeholder expectations responsibly and transparently, recognizing that not all organizations applying for the grants may ultimately be selected or have the capacity to implement. However, UNDP us fully committed to ensuring that, in line with Adaptation Fund guidance on USPs, risk identification, gender considerations, and stakeholder engagement are addressed at both the framework level (during proposal formulation) and the sub-project level (once grantees are known). These measures will ensure robust safeguards and inclusive engagement throughout the project lifecycle.

The Adaptation Fund was consulted about the above-mentioned phased approach to stakeholder consultations and considering the nature of the programme and the inclusion of Unidentified Sub-Projects (USPs), they informed that the strategy seemed well-justified and aligned with the Fund’s guidance.

Further to this, Annexes 4 and 5 outline the envisioned consultation processes that will further advance during implementation—to meet the requirements of the UNDP´s and the Adaptation Fund´s Environmental and Social Safeguards Policies and Gender Policies.

### Initial Consultations with Key National Stakeholders

The consultative process undertaken during the preparation of the Regional Project has been designed to ensure broad stakeholder engagement, with particular attention to vulnerable groups and gender considerations, in compliance with the Environmental and Social Policy (ESP) of the Adaptation Fund. The process has been structured in phases, enabling effective national and local input integration throughout the project’s development. Detailed information can be found in the following annexes to this proposal Annex 6 (Stakeholder Mapping Matrixes), and Annex 7 (Stakeholder Consultations and Engagement).

The first phase of the consultation process involved virtual meetings with key national stakeholders, coordinated through UNDP Country Offices in the four target countries. These consultations engaged representatives from government agencies, civil society organizations, non governmental organizations, SMEs and relevant institutions. The primary aim was to inform the overall project framework, ensuring alignment with national priorities and contextual realities. National stakeholders provided valuable input that guided the development of the project’s implementation principles, safeguards, and risk identification processes, ensuring that the project aligns with national adaptation strategies.

In Bosnia and Herzegovina, the stakeholder consultation brought together representatives from government ministries, hydrometeorological institutes, academia, development agencies, civil society, and the private sector. Participants welcomed the regional initiative and emphasized the need for clear administrative procedures and institutional support to ensure effective participation, given the country’s complex governance structure. The importance of ensuring access for development agencies and civil society organizations was underlined, along with calls for active engagement of local actors and broader community involvement. Stakeholders expressed strong interest in grant access and regional collaboration and affirmed the need for flexible, inclusive processes. Stakeholders also stressed the relevance of gender-sensitive approaches and appreciated the inclusive design of the initiative. The session reaffirmed Bosnia and Herzegovina’s interest and readiness to participate in the Regional Project. Focus on Vulnerable Groups and Gender Considerations.

In Montenegro, stakeholder consultations emphasized the importance of aligning the regional project with national policy processes, including the National Adaptation Plan (NAP), Low-Carbon Development Strategy, National Climate and Energy Plan, and NDCs. Participants highlighted significant capacity gaps among municipalities, SMEs, and NGOs in developing fundable adaptation proposals and called for the pairing of grant support with technical assistance and mentoring. Engagement with business development professionals was seen as essential, particularly in raising awareness and building skills to integrate climate considerations into investment planning. Stakeholders also identified a need to strengthen the role of local governments in embedding adaptation criteria into economic support schemes, especially in agriculture and tourism. The Environmental Protection Fund was recognized as a potential partner to leverage existing mechanisms and build capacity. Gender considerations were prioritized, with recommendations to build on UNDP’s EmpowerHer experience and align with national gender equality legislation. Finally, stakeholders stressed the importance of coordinating with existing initiatives—such as GORA and GEF-7 projects—to ensure complementarity, avoid duplication, and maximize outreach to vulnerable groups and local actors.

In North Macedonia, during the consultation stage stakeholders emphasized the need to prioritize high-impact sectors—such as agriculture, water resource management, and urban resilience—while ensuring inclusivity and innovation at even modest funding levels. It is noted that flexibility is important to allow participation from a wide range of municipalities, while still making sure that underserved and vulnerable communities receive adequate support. The consultation highlighted the importance of supporting rural women, youth, persons with disabilities, Roma communities, and small-scale farmers, who are often excluded from formal decision-making but face acute climate risks. Participants stressed the value of strong municipal leadership, gender expertise, and partnerships with academia and civil society to enhance implementation and sustainability. Geographically, the North-East region and climate-stressed urban zones like Skopje were identified as priority areas. Innovation, affordability, and scalability were key themes, with stakeholders advocating for solutions such as hydroponics and bio-waste processing, underpinned by robust monitoring frameworks and inclusive engagement mechanisms.

In Serbia, stakeholder consultations aligned with the ongoing national adaptation planning process, providing an opportunity to ensure coherence with the country’s National Adaptation Plan and related strategies. Participants expressed strong support for the project’s emphasis on locally driven action and prioritization of vulnerable populations—particularly the elderly, Roma communities, individuals with chronic illnesses, and rural residents and underlined the importance of inclusivity to address vulnerabilities and existing needs of target areas. Key thematic priorities included nature-based solutions, disaster risk reduction, and drought resilience. Stakeholders emphasized the importance of transparent and inclusive grant allocation mechanisms, recommending that informal groups be supported through structured partnerships. They also highlighted the need to build the capacities of civil society organizations and local governments. Regional cooperation was seen as a valuable dimension—both for sharing knowledge and for implementing cross-border or jurisdictionally aligned initiatives with scalable benefits across the Western Balkans.

In compliance with the ESP, particular attention was given to vulnerable groups, including women; youth; communities facing social, economic, and political marginalization; and marginalized communities. Gender considerations were incorporated into the consultation process, with the results informing the project’s design and risk management strategies. This approach ensures that the needs of vulnerable groups are central to the project’s implementation, and that gender-sensitive actions are embedded into its activities.

### Future Stakeholder Consultations and Detailed Risk Assessments

As the project progresses, further consultations will be conducted at the sub-project level, once specific grantees and interventions are identified through an open call for proposals. These consultations will focus on localized engagement, particularly with vulnerable groups, women, and marginalized and underserved populations ensuring that interventions are tailored to the specific needs of the communities they aim to serve. Detailed stakeholder meeting summaries, responses to stakeholder comments, and stakeholder engagement plans will be included in the application forms. Additionally, risk assessments, gender action plans, and environmental and social management plans will be developed and disclosed, ensuring compliance with the Adaptation Fund's policies and the safeguarding of vulnerable groups.

This consultative process ensures that the voices of all stakeholders, particularly vulnerable groups, are actively heard and incorporated into the project’s design and implementation. The phased approach allows for continuous learning, adaptation, and responsiveness, ensuring that the project remains aligned with the principles of the Adaptation Fund’s Environmental and Social Policy throughout its lifecycle.

- Describe how the project/programme draws on multiple perspectives on innovation from e.g., communities that are vulnerable to climate change, research organizations, or other partners in the innovation space, in the context in which the project/programme would take place.

## Incorporating Diverse Perspectives on Innovation from Different Stakeholders

The project draws on multiple perspectives on innovation by actively engaging a diverse range of stakeholders, including local communities, research organizations, and development partners. Communities most affected by climate change—such as local communities, marginalized groups, women, youth and rural populations—are central to the project’s innovation process, as they bring valuable lived experiences and unique insights into local adaptation challenges. Their participation ensures that the solutions developed are contextually relevant, grounded in the real-world needs of those who are most impacted by climate change.

In addition to local knowledge, the project incorporates expertise from research organizations, whose findings help shape the technical and scientific aspects of the adaptation solutions. These research entities provide evidence-based approaches, innovative methodologies, and a deeper understanding of climate trends, which are crucial for developing scalable and sustainable solutions.

The project also benefits from the MBA Internship Programme, which connects MBA students from leading global business schools with grantees in the region. These students provide valuable expertise in business strategy, financial planning, and scaling, helping to refine and strengthen the business models of local organizations. By integrating academic insights with local adaptation efforts, the MBA Internship Programme ensures that innovative solutions are not only technically feasible but also financially sustainable and scalable.

The Regional Project also collaborates with other key partners in the innovation space, including UNDP stakeholders and UNDP Country office innovation ecosystem for 4 countries, private sector partners, non-profits, and social enterprises, to foster a multi-stakeholder environment. By integrating diverse perspectives from across these sectors, the project ensures that adaptation solutions are not only innovative but also feasible, scalable, and adaptable to the changing realities of the region.

This approach encourages cross-pollination of ideas and strengthens the solutions ability to identify and implement effective, locally driven, and globally informed climate adaptation strategies. Through this inclusive process, the supported solutions not only address the immediate needs of vulnerable communities but also contributes to the broader climate resilience agenda, fostering long-term sustainability and innovation in the region.

- Provide justification for funding requested, focusing on the full cost of adaptation reasoning.

## Justification for Funding Requested: Addressing the Full Cost of Climate Adaptation in the Western Balkans

### Baseline Scenario: Insufficient Adaptation and Innovation Financing

The Western Balkans are already experiencing significant impacts from climate change, with increasing extreme weather events and long-term shifts in climate patterns. To minimize climate-related losses, reduce long-term adaptation costs, and protect vulnerable communities, these countries urgently need to adapt to the changing conditions. There is a valuable opportunity to strengthen adaptation efforts by supporting locally-led initiatives, promoting regional collaboration, and enhancing knowledge exchange between local and global networks. Innovation plays a crucial role in this process, providing context-specific solutions to address the region’s unique challenges. By leveraging local knowledge and integrating innovative technologies, practices, and business models, the region can accelerate the scaling of adaptation solutions, leading to a more resilient and sustainable future. This focus on innovation will drive the development of new tools, methodologies, and partnerships, empowering communities to adapt in a sustainable and effective manner, while closing gaps in adaptation efforts and accelerating inclusive solutions.

Adapting to climate change in the Western Balkans is urgent. The World Bank estimates that an initial, comprehensive package of investments in the Western Balkans may reach US$37 billion. There is a large gap remains in funding for climate change adaptation globally, indicating the global costs of adaptation may range from US$140 billion to US$300 billion per year by 2030 and up to US$500 billion per year by 2050 and that in the Balkans each country may need to invest as much as US$2 billion by 2030 alone.

Climate adaptation innovation and action in the Western Balkans brings many benefits, far beyond the effects on climate. For instance, early-warning systems yield extremely high benefits in terms of avoided mortality and hospitalization - hundreds or even thousands of times the implementation cost. Flood and water management, and nature-based solutions, can also benefit local economic development. However, a crucial gap exists in locally-led adaptation and innovation at the community level, which is essential for scaling successful climate adaptation practices, tools, and technologies. This project aims to bridge that gap by fostering innovative and locally led adaptation solutions and connecting them with national, regional, and global expertise to enhance their impact and scalability.

The current global and regional climate finance landscape focuses heavily on efforts to mitigate future temperature rise by removing greenhouse gas emissions. However, less attention has been paid to risk reduction, adaptation, and especially locally led adaptation innovation.  According to the Climate Policy Initiative, as little as $22 billion per year globally goes to climate change adaptation compared to more than $436 billion per year for climate change mitigation. The Western Balkans, with its increasing vulnerability to extreme weather events, rising temperatures, and water scarcity, is facing mounting challenges. Despite the urgent need for adaptation, access to climate finance remains severely constrained, limiting the region's ability to implement effective strategies that can mitigate climate impacts and build resilience.

Adaptation is a complicated challenge as there is no single common unit of measure such as greenhouse gas emissions. There is no “one size fits all” solution, which may, in part, explain why adaptation receives less attention and funding. Locally-led adaptation innovation is the key. This is especially true for the investment in adaptation innovation. The very nature of non-standard solution of adaptation is a massive opportunity for the Western Balkans region. Entrepreneurship in all forms, whether non-profit, social, for-profit and partnership, is a great approach to find potential locally-led and innovative multi-functional solutions for adaptation challenges.

As mentioned in earlier pages of this proposal, many of the entrepreneurs/ SMEs fall into the “missing middle”—which means that they are too large for microfinance, yet too small or risky for traditional banks and investors. Three main barriers contribute to this financing gap according to this OECD/UNCDF (2020) report are:

- High Transaction Costs – Similar effort is needed to assess SMEs as large firms, but with smaller returns.

- Risk Perception – SMEs often lack collateral, financial history, or sector familiarity, making them appear riskier.

- Investment Readiness – Many SMEs lack the skills to present strong financial models and business plans to attract formal investment.

The above is particularly evident in the Western Balkans, where high capital costs and concerns over ownership deter innovators and entrepreneurs from accessing equity, while non-profits and social enterprises face even greater challenges due to the unsuitability of traditional financing models. As a result, the capacity to scale and invest in locally-led adaptation solutions are severely constrained.

The Regional Project will also specifically reach out to include women, disadvantaged, remote, and marginalized communities. The proposed approach acknowledges that women-owned and minority-led enterprises often face persistent barriers in accessing adaptation finance. These businesses are more likely to operate in informal settings, smaller-scale sectors, or under less favourable lending conditions, which can limit their growth and resilience. Beyond financial constraints, non-financial barriers—such as limited access to training, unequal property rights, and institutional or legal hurdles—also restrict opportunities for formal financing. Gender norms and limited outreach from financial institutions further contribute to the financing gap.

To strengthen inclusive adaptation efforts, UNDP aims to explore targeted solutions that address both financial and systemic barriers, supporting more equitable access to finance for underserved and underrepresented innovators and entrepreneurs.

Locally-led adaptation and innovation are recognized as effective approaches to addressing climate change challenges. Public funding is proven to be extremely crucial for incubating and accelerating innovation when entrepreneurs are still operating at pre-seed stage with limited (or no) revenue potential. Building on existing experience, the proposal seeks to further strengthen and scale these locally driven solutions as a reliable pathway for climate resilience.

### Additionality of the Regional Project´s intervention

The requested funding for the Regional Project is critical to bridge the substantial adaptation finance gap in the Western Balkans, aligning with UNDP's commitment to strengthening resilience against climate change impacts. Without the project, available finance for innovations and business development in the region would likely not be directed toward climate resilience initiatives, as these are often perceived as more complex, higher-risk, and less investment-ready compared to conventional business ventures. They also typically require extensive technical assistance, readiness support, and mentoring, which are not sufficiently available or financed under current conditions.

In the baseline scenario, locally led adaptation efforts in the Western Balkans remain largely underdeveloped and insufficiently supported— particularly those led by or benefiting vulnerable communities and women. A lack of targeted technical assistance, early-stage investment, and institutional support prevents these initiatives from progressing beyond isolated pilots or informal solutions.

The Regional Project offers a transformative alternative by creating the enabling conditions—through tailored technical support, capacity building, scoping, and investment facilitation—for the identification, development, and scaling of high-impact, locally driven adaptation innovations.

Through three interlinked outcomes, the Regional Project will catalyse the development and diffusion of innovative adaptation practices, tools, and technologies, thereby strengthening the climate resilience of target communities compared to the baseline scenario:

- Outcome 1: Development, promotion, and acceleration of locally-led innovative climate adaptation solutions in four Western Balkans countries, with particular emphasis on approaches that advance gender equality and women’s empowerment, and which address priority climate risks.

- Outcome 2: Selected adaptation innovations are strengthened and positioned for scale through tailored business development support, market testing, and identification of funding and financing pathways.

- Outcome 3: Knowledge, evidence, and lessons from adaptation innovations are captured, shared, and leveraged to inform replication, scale and policy engagement across the Western Balkans through regional learning platform and global networks.

Outcome 1: Additionality

In the baseline scenario without the project, innovative adaptation initiatives led by civil society organizations, social enterprises, and SMEs in the Western Balkans face persistent barriers to financing. Traditional investors often perceive these initiatives as high-risk, with limited or no near-term revenue potential, especially during the early stages of development. Debt financing is typically less accessible, and equity investments are rare. As a result, promising ideas struggle to progress beyond the conceptual phase, leaving significant adaptation potential untapped—particularly among non-traditional actors and community-based innovators.

This project will act as an incubator for locally led adaptation innovation, accelerating the development and scaling of context-specific solutions across the Western Balkans. By providing targeted small and medium-sized grants, it addresses a critical financing gap for early-stage and high-impact initiatives that typically fall outside the scope of traditional funding. In doing so, the project introduces clear additionality by enabling public finance to de-risk innovation where private capital remains limited. Beyond funding, the project will foster a collaborative platform for sharing lessons, showcasing best practices, and building networks—contributing to a growing regional and global knowledge base on effective adaptation.

At the core of this outcome is a two-tiered funding structure that supports the entire innovation lifecycle—from early-stage experimentation to the scaling of validated solutions. This dual approach recognizes that genuine innovation requires supporting both emerging ideas and validated solutions, helping to foster a dynamic ecosystem that generates novel approaches while accelerating proven interventions:

- Lot 1 – Grant Funds for Innovation and Experimentation (USD 15,000 - USD 40,000). These smaller grants specifically target novel approaches, emerging technologies, or innovative business models with clear potential for climate adaptation impact. Priority will be given to:

  - Untested but promising concepts that address adaptation challenges through new methodologies

  - Early-stage innovations from non-traditional actors or emerging organizations

  - Experimental approaches that challenge conventional adaptation practices

  - Solutions that demonstrate potential for breakthrough impact despite limited track records

- Lot 2 - Scaling Grants for Proven Solutions (USD 40,000 - USD 150,000). These larger grants support the expansion or replication of solutions that have demonstrated early results and pathways to scale. Focus areas include:

  - Validated approaches ready for geographic expansion, replication or deeper implementation

  - Proven technologies or methodologies requiring support for broader adoption

  - Successful pilot initiatives with documented results and scaling potential

By supporting both experimentation and scaling, the project aims to create an innovation facility for climate adaptation that can attract additional funding sources beyond the Adaptation Fund. This facility will act as a dynamic platform for generating, testing, and scaling new solutions, building a pipeline of innovations that can leverage diverse funding mechanisms and create sustained impact across the Western Balkans region.

Priority will be given to initiatives that demonstrate clear benefits for vulnerable populations, especially women and marginalized communities, and that show credible pathways to sustainability and replication.

Grant agreements will be designed using fit-for-purpose UNDP modalities suited to the nature of recipient organizations (e.g., CSOs, cooperatives, SMEs), ensuring both compliance and flexibility to support diverse innovation actors. Performance-based disbursement mechanisms will be employed where appropriate, linking funding to achievement of specific milestones and learning objectives that contribute to both individual project success and broader ecosystem knowledge generation.

Outcome 2: Additionality

In the baseline scenario, early-stage adaptation innovations in the Western Balkans struggle to mature due to limited access to tailored business development support. Most locally led initiatives—particularly those led by CSOs, cooperatives, or SMEs—are perceived as high-risk, lack investment readiness, and face barriers in accessing conventional financing. Available public or private support for business development is rarely directed toward adaptation-focused ventures, which are often more complex, less profitable in the short term, and require dedicated technical assistance, mentoring, and financial planning to become viable and scalable.

The regional project introduces clear additionality by providing targeted business development support specifically designed for climate adaptation innovations. Through tailored technical assistance—including business model refinement, financial planning, and market access strategies—the project will bridge the gap between promising ideas and scalable adaptation solutions- —enabling innovators to transition from early-stage ideas to viable, investable adaptation solutions. This support will enable local actors to strengthen their operational models, enhance investment readiness, and position themselves to attract both public and private funding, which would otherwise remain out of reach. This approach is in line with UNDP's broader mission to eradicate poverty, reduce inequalities, and build resilience to climate change impacts. The project will ensure that no one is left behind in the face of climate change, fostering sustainable, scalable, and inclusive adaptation solutions across the Western Balkans.

This approach not only enhances the financial and operational sustainability of supported initiatives but also contributes to a broader shift toward systems-level resilience. By helping local actors become more attractive to both public and private funders, the project will catalyse a pipeline of inclusive, scalable adaptation solutions that would otherwise remain overlooked. The Regional Project will catalyse the growth of early-stage, innovative adaptation solutions, providing tailored business development assistance that bridges the gap between innovation and scalable financial structures, ultimately driving broader, impactful deployment of adaptation solutions.

The Regional Project will maximize impact by leveraging existing resources, structures, and partnerships. Collaborations with development partners and community of UNDP offices in the Western Balkans, who have extensive experience in working with vulnerable groups, will be integral to the project’s success. These partners have shown strong support for the project concept and bring valuable expertise in adaptation finance and innovation. Additionally, the project will align with ongoing UNDP initiatives in the region, ensuring complementarity and avoiding duplication of efforts. Close coordination and consultation with other organizations and program focal points in the region will be prioritized during the design, implementation, and monitoring phases to enhance efficiency and maximize impact.

In doing so, the project offers a tangible adaptation alternative—one that strengthens the enabling environment for inclusive, resilient innovation and ensures that locally driven solutions can progress from pilot stage to transformative impact.

Outcome 3: Additionality

In the Western Balkans, the full cost of achieving effective, inclusive, and scalable climate adaptation goes well beyond financing individual projects or technologies. A critical and often underfunded component is the knowledge infrastructure required to ensure that locally led innovations are systematically captured, shared, and scaled across borders. In the baseline scenario, community-level adaptation solutions remain fragmented and isolated. Valuable lessons from local innovation rarely move beyond their immediate context due to the absence of structured mechanisms for documentation, peer learning, and policy feedback. This severely limits the region’s ability to scale what works and build institutional memory around effective climate responses.

The regional project addresses this systemic gap by investing in the enabling conditions that are essential to unlock the full value of locally led adaptation. The requested funding is justified as it covers core costs that are not supported extensively including targeted technical assistance, capacity development, cross-border peer learning, and strategic knowledge dissemination. These are necessary for creating the ecosystem conditions in which adaptation innovations can be sustained, replicated, and integrated into broader development strategies.

Specifically, the project will establish a regional knowledge exchange and learning framework that supports continuous learning and collaboration across Bosnia and Herzegovina, Montenegro, North Macedonia, and Serbia. Through structured activities—such as peer learning events, regional workshops, innovation showcases, and facilitated exchanges—grantees and stakeholders will be empowered to share practical insights, build capacity, and adapt successful approaches to new contexts. These efforts will be complemented by systematic documentation and dissemination of lessons through diverse tools such as blogs, case studies, and working papers, leveraging UNDP’s regional expertise and platforms including BOOST, TADAMON, the AIM partner network, and the UNDP SGP Global Citizens Knowledge Platform. Importantly, the project will not invest in new digital infrastructure but will utilize a decentralized, multi-channel approach to ensure cost-efficiency while maximizing accessibility and impact. Knowledge will be shared through existing networks, creating a flexible, inclusive community of practice that reaches both grassroots actors and policymakers.

Without this intervention, the existing public and private finance available in the region would not be directed toward these enabling functions. Baseline funding mechanisms do not typically cover the costs associated with cross-country learning, knowledge exchange, or visibility for early-stage innovations—particularly those led by vulnerable or marginalized communities. These aspects are essential to achieving transformational, system-wide adaptation but remain underfunded due to their indirect and long-term return on investment.

Key activities under this component will include peer learning events, innovation showcases, regional workshops, and exchange forums designed in collaboration with grantees and local partners. These events will help surface practical insights and create opportunities for horizontal learning between communities, practitioners, and policymakers.

To further strengthen regional knowledge ecosystems, UNDP Country Offices in 4 Western Balkan countries will play a central role in coordinating stakeholder engagement, ensuring that learnings are integrated into policy processes, and supporting linkages with relevant national and regional institutions. The project will also foster virtual connections with incubators, accelerators, innovation labs, and climate adaptation experts to enrich learning and provide tailored technical input to grantees.

By addressing this critical gap, the project will ensure that locally led adaptation solutions are not only piloted but also equipped for replication and scaling. The funding requested is essential to cover the full cost of adaptation—going beyond direct implementation to include the long-term structures and capacities needed to support the sustained growth and spread of effective solutions.

This outcome directly responds to the current fragmentation of knowledge and lack of structured learning opportunities in the Western Balkans. By fostering collaboration, peer learning, and cross-border exchange, it will enable grantees and their partners to design more adaptive, resilient responses to climate risks. Through this approach, the project will cultivate a culture of continuous improvement, ensuring that successful practices are systematically sustained, scaled, and adapted to new contexts.

Ultimately, this component will lay the foundation for a more connected, inclusive, and durable adaptation ecosystem across the region—one where local innovation can thrive, inform policy, and contribute meaningfully to long-term climate resilience.

The requested amount of $5,000,000 from the Adaptation Fund is sufficient to fully achieve the project’s intended outcomes and objectives. While the project may explore opportunities for additional financing to further enhance its impact, the successful delivery of core results is not contingent upon external co-financing.

- Describe how the sustainability of the project / programme outcomes has been taken into account when designing the project / programme.

## Ensuring Sustainability of Project Outcomes in the Design Process

The sustainability of the project outcomes has been carefully considered in the design of the programme to ensure long-term impact. Proposals should demonstrate evidence of existing funding, a co-financing strategy (if applicable), and secure forthcoming funding. Additionally, a comprehensive fundraising strategy and identification of relevant partners must be included to ensure the project's long-term viability. These elements will be evaluated as part of the proposal screening criteria.

Additionally, each proposal will include a project risk assessment and management plan focused on ensuring the expected outcomes and long-term sustainability. An exit strategy for each grantee will be developed, and a portion of the technical assistance facility will be dedicated to ensuring its effective implementation.

To maintain transparency and accountability, the proposal must define clear and transparent procurement procedures, ensuring competition and efficiency. It should outline processes for (i) recording financial transactions and account balances, and (ii) managing and disbursing funds in alignment with project objectives. These procedures must adhere to established financial management best practices. Additionally, a financial and budget plan must be provided, with a possibility of an annual financial audit conducted to ensure compliance.

In accordance with UNDP Financial Regulations and Rules, the supported solutions might undergo audits, with the audit cycle and process to be discussed during the inception stage to ensure full compliance with applicable audit policies.

- Provide an overview of the environmental and social impacts and risks identified as being relevant to the project / programme.

As mentioned in section J, it was not yet feasible to conduct deeper assessment of specific sub-projects during the proposal preparation, because these will be identified through a transparent open call for proposals, which will take place at the beginning of implementation. As such, the project currently includes Unidentified Sub-Projects (USPs), consistent with the nature of the innovation process being supported and in line with guidance from the Adaptation Fund (Decision B.39/52).

In this regard, the UNDP has conducted its own generic screening of the proposed project against the UNDP’s Social and Environmental Standards (see Annex with the Social and Environmental Screening Procedure) that broadly outlined the potential impacts and risks associated with the envisaged USPs. The screening classified the projects as involving Moderate social and environmental risks based on the UNDP’s risk rating methodology and proposed further screenings of the specific USPs to ensure their full compliance with the UNDP SES and Adaptation Fund’s Environmental and Social Policy.

The UNDP’s Moderate social and environmental risk rating corresponds to the Adaptation Fund’s environmental and social risks rating Category B (few, small, not widespread, and reversible or easily mitigated risks). For sake of completeness, a detailed review of the potential risks is provided below based on the Adaptation Funds Environmental and Social Policy.

## Overview of Environmental and Social Impacts and Risks Relevant to the Project

| Checklist of environmental and social principles | No further assessment required for compliance | Potential impacts and risks – further assessment and management required for compliance |
| --- | --- | --- |
| Compliance with the Law: |  | Moderate risks The supported activities might fail to demonstrate full compliance with the applicable law. Further assessment and management required for compliance All project-supported activities shall be screened to ensure that they fully comply with all applicable national law. |
| Access and Equity: |  | Moderate risks Marginalized groups (persons with disabilities, ethnic minorities e.g. Roma populations, poor communities) may be excluded from decision-making and benefits because of limited outreach to vulnerable populations because of their insufficient capacity to engage effectively, or inadequate conflict sensitivity in project design. Risk level based on Adaptation Fund’s methodology: Moderate All project-supported activities shall be screened in order to ensure that provide fair and equitable access to benefits in a manner that is inclusive for potentially affected populations, including marginalized individuals and persons with disabilities, and not exacerbate existing inequities, particularly with respect to marginalized or vulnerable people who live in extreme poverty or face disadvantage(s) that limit their choices and opportunities relative to others in society. |
| Marginalized and Vulnerable Groups: |  | Moderate risks The supported projects might exacerbate existing inequities, particularly with respect to marginalized or vulnerable groups. Further assessment and management required for compliance All project-supported activities shall be screened to ensure that they do not to exacerbate existing inequities, particularly with respect to marginalized or vulnerable groups. Where risks of potential risks to access and equity arise, the supported actions shall be required to: - identify potential impact of the proposed activities on the potentially affected individuals and groups, including those who have lesser access to its benefits and/or marginalized or vulnerable groups, - Identify practical measures that avoid, reduce or offset such adverse impacts, and - uphold the principles of accountability, inclusion, non-discrimination, and participation and increase the inclusion of potentially affected groups in decision-making processes that may impact them (consistent with the non-discrimination and equality human rights principle). |
| Human Rights: |  | Moderate risks The project might provide support for activities that guarantee e.g. equal protection under the law; discrimination based on race, color, sex, language, religion, political or other opinion, national or social origin, property, birth or other status right; etc., defined in the national law and the core international human rights treaties (e.g. Universal Declaration of Human Rights and International Covenant on Civil and Political Rights, etc.) Further assessment and management required for compliance All project-supported activities shall be screened for potential Human Rights risks. Where the risks of Human Rights violation would rise, the project shall duly consider any such risks and assist the applicants in adequately addressing them based on standards set in international law or national law (whichever is higher). |
| Gender Equality and Women’s Empowerment: |  | Moderate risks The supported activities might not be implemented in a gender-responsive manner and discriminate against women or girls or reinforce gender-based discrimination and/or inequalities. Further assessment and management required for compliance All project-supported activities shall be screened to ensure that they are gender-responsive and not reinforce gender-based discrimination and/or inequalities. The supported actions will be expected to promote a meaningful and equitable participation of both women and men in decision-making about the supported activities, allow both genders obtain comparable social and economic benefits from the proposed actions, and support women to easily access them. The project will (where relevant) promote women-led initiatives. |
| Core Labour Rights: |  | Moderate risks The grant recipients and project contractors may not have procedures for observance of workers’ rights and may not provide contracted worker with labour and working conditions that meet the relevant national labour laws and relevant ILO conventions. Further assessment and management required for compliance All project-supported activities shall be screened for the potential labor risk violations. The supported organisations will be required to provide their workers with labour and working conditions that meet the national labour laws, including the following core labor-related requirements stipulated in the relevant key ILO conventions: - Provide project workers with clear and understandable information on terms and conditions of their employment (e.g. payment in a timely manner, written notice of termination, and payment of all wages and benefits on termination, etc.). - Prevent and address violence, harassment, intimidation, or exploitation, including any form of gender-based violence. - Ensure that workers engaged have appropriate health and social insurance. - Exclude unsafe working practices and implement relevant occupational health and safety measures, such as: - Provide workers with introductory job- focused safety trainings before starting work; training event is properly registered in the instructions’ book. - Ensure that workers’ protective equipment based on the local requirements and international good practice (e.g. hardhats, masks, safety glasses, harnesses, safety boots, etc.) - Make the first aid kits available on site and fire-extinguisher easily accessible in all sections of the site. - Introduce appropriate signposting of the sites will inform workers of key rules and regulations to follow. - Record and report health & safety incidents to UNDP. |
| Indigenous Peoples: | X | No risks The project area does not include any Indigenous Peoples. Further assessment and management required for compliance N/A |
| Involuntary Resettlement: |  | Moderate risks Project activities might cause adverse social and economic impacts from land or resource acquisition or restrictions on land or resource use. Further assessment and management required for compliance All project-supported activities shall be screened for potential displacement risks. Where such risks would arise, the actions seeking project support shall be required to conduct a dedicated due diligence of any displacement activities before they take place to: - Identify and assess any potential physical and economic displacement risks - Prohibit any forced evictions. - Include measures for avoiding, or, when avoidance is not possible, minimizing any potential displacement risks and their adverse social and economic impacts. - Consult the potentially affected stakeholders (with specific attention to poor and marginalised groups) on the proposed measures and opportunities for improving their living standards and the overall socioeconomic status through the project interventions. |
| Protection of Natural Habitats: |  | Moderate risks The supported activities might inadvertently cause a potential degradation of natural and critical habitats and adverse effects on ecosystem services. Further assessment and management required for compliance All project-supported activities shall be screened for risks related to natural Habitats. They shall be generally required to: - as far as possible, conduct the proposed activities in areas where natural habitats have already been converted to other land uses or that have low value for biodiversity and ecosystem services, and low sensitivity to the anticipated impacts, - keep interventions in natural and semi-natural habitats to minimum in order not to disturb the existing flora and fauna, degrade the habitat and resident species populations - where possible avoid interventions that would reduce ecological connectivity in the ecosystem (e.g. restricting the free movement of species between important habitats) or changes in the important ecosystem processes (e.g. hydrological regimes and nutrient flows) that support ecosystems and their services. - assess and manage the impacts of proposed interventions on critical, natural and modified habitats and their ecosystem services in accordance with the UNDP SES 1 requirements, - use cost-effective opportunities to enhance the existing habitats and ecosystem services as part of the proposed interventions. |
| Conservation of Biological Diversity: |  | Moderate risks The supported activities located in the proximity of critical ecosystems might cause reduction of recognized Vulnerable, Endangered, or Critically Endangered species, or have adverse impacts on endemic species, restricted-range species, and migratory species. Further assessment and management required for compliance All project-supported activities shall be screened for biodiversity risks. They shall be generally required to consider the presence of any endangered species and any potentially significant adverse impacts on their habitats, breeding grounds, free movement, and migration needs and will be optimised to ensure that they: - do not cause any reduction of any recognized Vulnerable, Endangered, or Critically Endangered species, - avoid adverse impacts on endemic species, restricted-range species, and migratory species, and - minimize unwarranted impacts on resident species populations. They shall also be required to: - not introduce species known to be invasive into new environments, - promote the use of native species or more resilient varieties of native species as a priority, and - use any potentially suitable alien species (e.g. climate resilient crop seed varieties) only if they were duly approved as posing no risks of potential invasive behaviour by the relevant authorities. |
| Climate Change: |  | Moderate risks Some supported activities (e.g. changes in land-uses or changes in the cooling systems) might inadvertently trigger greenhouse gas emissions. Further assessment and management required for compliance The supported actions shall be screened for any potential project-related increases in emissions that may exacerbate climate change, such as GHG emissions and black carbon emissions. Where any such risks would arise (e.g. the use of cooling systems), the action shall be asked to consider and adopt technically and financially feasible alternatives for reducing proposal-related greenhouse gas emissions. Such options may include, but are not limited to: - alternative project locations, - adoption of renewable or low-carbon energy sources, or energy efficiency measures - use of low-global-warming-potential coolants for air-conditioning and refrigeration, - promote climate-smart agricultural, forestry, and livestock management practices, and ecosystem-based adaptation and mitigation measures (including potential integration of carbon sinks). |
| Pollution Prevention and Resource Efficiency: |  | Moderate risks Grant-supported activities may fail to meet all applicable national environmental laws and standards, and applicable international agreements and good international practices or avoiding, minimizing, and mitigating environmental and related public health risks associated with the potential release of pollutants due to routine or non-routine circumstances. Further assessment and management required for compliance The supported actions shall be screened for pollution prevention and resource efficiency risks. They will be required to avoid, minimize, and mitigate environmental and related public health risks associated with the potential release of pollutants in routine and non-routine circumstances in accordance with the national law and international best practices used in the region. Where the risks of pollution release would arise, the project will: - require operators to conduct orientation training addressing relevant environmental and occupational health and safety issues prior commencement of the relevant operations, - conduct regular surveillance is conducted to avoid leaks, spills, incidents or accidents occurring during the use of equipment and during storage, - monitor, manage and remediate any chemical oil leaks or spills, and incidents/accidents occurring during the use of equipment and their effects, and undertake all necessary immediate actions to ensure they do not adversely affect water bodies/sources. Where the risks of inadequate waste management would arise, the supported actions shall be required to: - reduce the generation of any generated waste - separate waste at the source (where possible) - reuse waste in a manner that is safe for human health and the environment. - transport all waste that cannot be reused to an appropriate waste recovery-or-treatment facility that appropriately controls its emissions and residues in accordance with the national law and international best practices used in the region. |
| Public Health: |  | Moderate risks Projects may create certain health and safety risks or construction-related risks to communities and workers. Further assessment and management required for compliance The supported actions shall be screened for public health and safety risks. They will be required to be designed, implemented, and operated in accordance with the national law and will also respect the following UNDP requirements for construction process management: - have design and management plans which were: i) prepared by suitably qualified and experienced professionals who are certified for such design process, and ii) cleared by the competent authorities for construction process management. Low-risk designs will require at least a peer-review by qualified professionals. - be constructed and operated by the experienced contractor(s) having relevant certifications and permits for the relevant works, - implement preventive/protective measures to avoid/minimize the relevant health and safety risks for the construction workers and the surrounding communities based on the national law and international good practice, and - be before the beginning of their actual use/operation approved (and where needed certified) by either competent authorities or independent professionals not involved in their design and construction. Where potential impacts on public health arise, the supported actions shall be required to: - use qualified health and safety experts to assess the risks to, and potential impacts on, the safety of affected communities during the project design, construction, operation, and decommissioning, - adopt preventive measures and plans to address any identified risks in a manner commensurate with their potential impacts based on good practices and standards used by the international organizations working in the region, - prepare, implement, and monitor emergency preparedness plans in collaboration with stakeholders and relevant authorities, where relevant, and - require periodic safety inspections and monitoring, and report to UNDP should any issue be found. |
| Physical and Cultural Heritage: |  | Moderate risks Grant-supported activities may damage sites, structures, or objects with historical, cultural, or religious values; or adverse impacts on intangible cultural heritage (e.g. changes in landscapes with cultural significance). The supported actions shall be screened for risks related to cultural heritage. They will be required to: - comply with the local requirements for their protection and preservation and fully respect the requirements of the World Heritage Convention (if they might affect the World Heritage sites). - Where moderate risks arise, consult the relevant authorities and explore all viable and feasible alternatives for the reduction of these risks (including changes in the planned activities, in situ conservation and rehabilitation, etc.) to avoid, minimize, or offset such risks. - ensure that it does not lead to the destruction of unknown cultural heritage and follow national requirements and/or globally recognized good practices for field study, inventorying, and documentation of archaeological heritage. |
| Lands and Soil Conservation: |  | Moderate risks The supported activities might cause adverse impacts on productivity, organic content, structure, and water-retention capacity of soils. Further assessment and management required for compliance The supported actions shall be screened for the potential impacts on soil and required to: - avoid conversion of productive lands or lands that provide valuable ecosystem services - avoid, and where avoidance is not possible, minimize adverse impacts on soils, their biodiversity, organic content, productivity, structure, and water-retention capacity - adopt appropriate measures to ensure that the supported activities promote soil conservation - support. They will also be used as a reference during the review process of the project application. |

A detailed Social and Environmental Screening Procedure (SESP) and Environmental and Social Management Framework (ESFM) that complies with the Adaptation Fund´s Safeguards Policy and UNDP´s Social and Environmental Standards are presented in Annex 4 and 5 respectively. The ESMF chapter 5 outlines the screening of unspecified sub-projects and presents Environmental and Social Management Guidelines that will be provided to the USPs. These guidelines directly integrate the mitigation measures presented in the above screening.

.

PART III: IMPLEMENTATION ARRANGEMENTS

# PART III:  IMPLEMENTATION ARRANGEMENTS

- Describe the arrangements for project / programme management at the regional and national level, including coordination arrangements within countries and among them. Describe how the potential to partner with national institutions, and when possible, national implementing entities (NIEs), has been considered, and included in the management arrangements.

## Project Management and Coordination Arrangements

Regional Management Structure

The Regional Project will be implemented by UNDP through its Istanbul Regional Hub under the Direct Implementation Modality (DIM). This modality ensures centralized oversight, coherent governance, and accountability, while enabling efficient delivery of technical and operational support across Bosnia and Herzegovina, Montenegro, North Macedonia, and Serbia.

The Istanbul Regional Hub will serve as the Implementing Partner for this project. The Implementing Partner is responsible for executing this project. Specific tasks include:

- Project planning, coordination, management, monitoring, evaluation and reporting. This includes providing all required information and data necessary for timely, comprehensive and evidence-based project reporting, including results and financial data, as necessary. The Implementing Partner will strive to ensure project-level M&E is undertaken by national institutes and is aligned with national systems so that the data used and generated by the project supports national systems.

- Overseeing the management of project risks as included in this project document and new risks that may emerge during project implementation.

- Procurement of goods and services, including human resources.

- Financial management, including overseeing financial expenditures against project budgets.

- Approving and signing the multiyear workplan.

- Approving and signing the combined delivery report at the end of the year; and,

- Signing the financial report or the funding authorization and certificate of expenditures.

The Regional Project Governance Arrangements:

The UNDP Istanbul Regional Hub (IRH) Manager assumes full responsibility and accountability for oversight and quality assurance of this Project and ensures its timely implementation in compliance with the AF-specific requirements and UNDP’s Programme and Operations Policies and Procedures (POPP), its Financial Regulations and Rules and Internal Control Framework. A UNDP Regional Bureau representative in the Hub will assume the assurance role and will present assurance findings to the Project Board, and therefore attends Project Board meetings as a non-voting member.

UNDP’s implementation oversight role in the project – as represented in the project board and via the project assurance function – is performed by the IRH Manager and UNDP IRH RBM and QA Specialist. UNDP’s execution role in the project is performed by the Regional Project Manager, who will report to the IRH Innovations Team Leader (or Regional Programme Chief, IRH).

The Implementing Partner could engage Responsible Parties to deliver specific activities under the project in line with UNDP policies and procedures and if deemed necessary for the effective project delivery.

Regional Steering Committee

The regional project will be steered by the Regional Project Steering Committee as per UNDP procedures and requirements. The Regional Steering Committee will secure high-level oversight of the execution of the project and approval of strategic project execution decisions of the Implementing Partner. The Steering Committee’s roles and responsibilities are unpacked in the standard UNDP Terms of Reference for Project Board/Steering Committee and will be presented and endorsed upon the Steering Committee’s first meeting. The Steering Committee is the formal governance body of the project, which approves the activities in the project, reviews and clears annual workplans (AWPs) and annual progress achieved by the project through Annual Project Reviews based on the approved AWP. The Steering Committee will meet on an annual basis (more often if required) and its decisions are binding. Prior to the meetings the project team, which acts as the secretariat, will duly submit brief mid-year actions updates on the previous period and the plan for the next one. The Steering Committee will evaluate submitted documents and oversee approving plans and budgets. The Steering Committee is chaired by IRH management as per the internal control framework and regional programme Standard Operation Procedures.

Composition of the Regional Steering Committee:

- Project Executive: This is an individual who represents ownership of the project and chairs (or co-chairs) the Project Board. The Project Executive is: the IRH Manager, UNDP.

- Beneficiary Representative(s): Individuals or groups representing the interests of those groups of stakeholders who will ultimately benefit from the project. Their primary function within the board is to ensure the realization of project results from the perspective of project beneficiaries. The Beneficiary representative (s) is/are: Selected national stakeholders/CSOs (on the rotational basis) and UNDP Country Office management in the four partner countries.

- Development Partner: Individuals or groups representing the interests of the parties concerned that provide funding, strategic guidance and/or technical expertise to the project. The Development Partner is: Representative of the UNDP BPPS Climate Hub.

Project Assurance

Project Assurance is the responsibility of each Steering Committee member, however the role can be delegated.  The Project Assurance role supports the Steering Committee by carrying out objective and independent project oversight and monitoring functions. This role ensures appropriate project management milestones are managed and completed. Project Assurance has to be independent of the Programme Manager; therefore the Steering Committee cannot delegate any of its assurance responsibilities to the Regional Programme Manager. UNDP IRH RBM and QA Specialist will perform the Quality Assurance role.

At the national level, the project will be delivered in close collaboration with UNDP Country Offices and relevant national stakeholders. National coordination mechanisms will be established to align implementation with country-specific climate adaptation priorities and ensure ownership. These mechanisms will facilitate structured engagement with civil society organizations (CSOs), micro-, small- and medium-sized enterprises (MSMEs), cooperatives, and government institutions—promoting inclusive participation in the development and scaling of locally-driven adaptation solutions. The UNDP Adaptation Fund Climate Innovation Accelerator (AFCIA) Global Project Team will provide technical support and advice to the Regional Project Management Team, allowing the project to benefit from global knowledge and technical assistance.

Regional and Inter-Country Coordination

As is the practice in similar regional projects, the project team led by the Regional Project Manager acts as one consolidated team regardless of physical location. Building on IRH’s solid experience on distributed teams and implementation and the SOP for regional programming, a regional coordination mechanism will be established to foster collaboration, peer learning, and knowledge exchange across the four countries within UNDP offices and alongside partners. The distributed project team carries out regular joint activities including technical working groups, learning events, peer-to-peer exchanges, and innovation showcases and relevant as needed, in addition to the country specific/led activities. These efforts aim to facilitate the sharing of good practices, refine innovative solutions, and enable replication and scaling of successful approaches across the region.

This coordination framework will also leverage engagement with regional development partners and platforms to promote policy coherence, optimize resource use, and enhance collective impact. The model promotes cross-border collaboration while remaining responsive to national contexts and institutional frameworks.

Regional Project Team

UNDP will maintain a team of professional project personnel who will be directly involved in the implementation and monitoring of the project. The personnel time allocated to the implementation of the project will be duly recorded. The team will consist of the regional project management unit under IRH however based in one of the implementing Western Balkan countries within a UNDP Country Office, working as one project team with the personnel supporting the project from the other implementing UNDP Country Offices, and alongside. Together they make up the Secretariats of the Regional Project. UNDP personnel will ensure high quality in the development and implementation of activities, provide insight generation, maintain relationships and ensure smooth delivery of the project The UNDP Country Offices (COs) will implement in-country activities as per agreed workplans. IRH will ensure financial allocations to Country Offices as per established workplans / activities for each of the country. The assigned CO staff will support the project implementation, monitoring, and contribute to the financial and operational closure and final reporting.

Partnerships with National Institutions 
Strategic engagement with national institutions is integral to the project’s approach. Through UNDP Country Offices, the project will work closely with ministries and public agencies responsible for climate change adaptation, environment, and sustainable development to ensure strong alignment with national policy frameworks, including Nationally Determined Contributions (NDCs) and National Adaptation Plans (NAPs).

The Adaptation Fund´s website indicates that there are no National Implementing Entities (NIEs) operating in the Western Balkans region. However, the Regional Programme will map out relevant NIEs and national agencies that would benefit from knowledge sharing, build on existing innovation grant experiences, and contributing to the replication of scalable solutions, enhancing coherence between global adaptation financing and local implementation efforts.

Stakeholder Engagement
A strong emphasis will be placed on inclusive, multi-stakeholder engagement at all levels. The project will actively involve CSOs, the private sector, academia, and regional and international partners to co-create, implement, and scale solutions. This collaborative framework fosters a dynamic innovation ecosystem, reinforces social ownership, and supports systemic resilience in the Western Balkans.

Knowledge Management and Monitoring
A robust results-based monitoring and evaluation (MEL) framework will guide project implementation, allowing for the measurement of progress, identification of emerging challenges, and adaptive management. A dedicated knowledge management system will capture lessons learned, good practices, and innovations to be disseminated across regional and global adaptation platforms. This will support continuous learning and contribute to broader climate adaptation agendas, including South-South and triangular cooperation.

UNDP Execution Role: The National Designated Authorities for AF, UNDP and the AF have agreed for UNDP to fully execute the project under the DIM modality and for the cost of these services to be charged to the project budget up to the approved amount of USD 106,000.  To ensure the strict independence required by the AF and in accordance with the UNDP Internal Control Framework, these execution services will be delivered independently from the AF-specific oversight and quality assurance services.

- Describe the measures for financial and project / programme risk management.

## Measures for Financial and Project Risk Management

| Potential Risk | Risk Level | Risk Management Strategy |
| --- | --- | --- |
| Misappropriation of the grant funding | Low | Performance based disbursement will be used instead of providing the total grant amount at the grant signing stage. Grantees may be asked to get an agreement from UNDP (with advise from UNDP country office) if procurement of goods/services exceeds a certain threshold. Financial audit is required as a part of the annual progress report. |
| Lack of participation at the regional call for proposals across the four targeted Western Balkan countries | Low | During the regional call for proposals, UNDP will also actively source innovation ideas from the network of development partners who are working on innovation, incubation, and acceleration as well as climate adaptation and resilience topics. With the extensive network of UNDP Innovation team and BOOST network, Accelerator Labs in the Country Offices, Country Office ecosystem and detailed stakeholder mapping that will be developed the risk of lacking participation is relatively low. |
| Project implementation delay | Medium | To mitigate this risk, UNDP will provide ongoing technical and business development support and apply its standard Monitoring and Evaluation (MEL) processes, including: - Quarterly Reporting: Grantees will submit progress and financial reports every three months throughout the implementation period. - Ongoing Support: Continuous technical and business acceleration support will help identify and address potential implementation challenges early on. - Timely Issue Resolution: Any barriers to timely completion will be monitored and addressed through tailored mitigation strategies. This approach will ensure proactive oversight and supports effective and timely project delivery |
| Imbalanced Reporting of Success vs. Challenges and Lessons Learned | Medium | To ensure accurate and balanced reporting, grantees will be encouraged to document both successes and challenges as part of their regular progress updates. Lessons learned—particularly from challenges—are essential for continuous improvement, knowledge sharing, and the replication or scaling of effective practices. This expectation will be clearly communicated throughout the programme implementation cycle and reinforced during regular monitoring. Project implementation will also be guided by the Impact Report and documented lessons learned from UNDP-AFCIA Phase I implementation. These insights will inform best practices and support adaptive learning. All relevant lessons from the Regional Project will be similarly captured to contribute to broader institutional learning and future programme design. |
| Grantees fail in securing scale up and replication support and funding from other sources after the completion of the project | Medium/High | While it is common for only a portion of innovative or early-stage initiatives to secure follow-on funding the programme is designed to improve these odds by strengthening grantees’ capacity for long-term sustainability. Through targeted technical assistance, the project will help grantees enhance their financial planning, develop robust business models, and strengthen partnerships. This support aims to make initiatives more ‘investment-ready’, enabling them to attract additional funding and diversify income streams. By addressing core barriers such as limited access to finance, technical know-how, and strategic networks, the project aims to bridge the gap between promising community-led adaptation initiatives and the resources needed for sustained impact. Based on comparable experience, it is anticipated that approximately 20–30% of supported initiatives may successfully secure follow-on investment or replication support. |
| Environmental, social and governance risk not managed, triggering risk events | Medium | Environmental, social and governance criteria will be established in every step of the project under the guidance of UNDP teams. UNDP Social and Environmental Safeguards Procedure (SESP) will be used to ensure the controls of this risk are in place. ESG management plan will be prepared before the programme implementation. Call of proposal will highlight potential ESG risk, selection template will contain ESG risk identification questions, ESG expert will be presented in the technical panel, MEL reporting's will also contain a ESG reporting section. |

- Describe the measures for environmental and social risk management, in line with the Environmental and Social Policy of the Adaptation Fund.

# Environmental and Social Risk Management Measures

A detailed Social and Environmental Screening Procedure (SESP) and  Environmental and Social Management Framework (ESFM), that complies with the Adaptation Fund´s Safeguards Policy and UNDP´s Safeguard policy is presented in Annex 3 and 4 respectively.

The Regional Project is fully aligned with the Environmental and Social Policy (ESP) of the Adaptation Fund and UNDP’s Social and Environmental Standards (SES). It incorporates a comprehensive, phased approach to environmental and social risk management, ensuring that all activities are implemented responsibly and inclusively.

1. Preliminary Risk Screening

- Grantees will be requested to consider - with the help of using the guidance proposed in the ESMF - the main risks that their solution/project could potentially generate in the environment and the communities where they plan to operate.

- Based on this, all grantee proposals will submit their own initial environmental and social risk screening that will be reviewed during the selection process, by the Performance and Data Analyst with the help of the UNDP´s safeguard experts.

3. Integration of mitigation measures into final design of the supported actions

- If this screening identifies potential risks, the applicants will be asked to explore measures to avoid, minimize, or offset any potentially significant risks in order to comply with the minimum legal requirements in each Western Balkan country and the requirements stipulated in UNDP´s Social and Environmental Standards and the Adaptation Fund´s Environmental and Social Policy.

4. Ongoing Monitoring and Support

- Grantees will report regularly on safeguard implementation and will be required to undertake appropriate corrective actions as needed.

- The Performance and Data Analyst will, in coordination with the safeguards expert, provide technical support and quality assurance on social and environmental risk management throughout the project lifecycle.

5. Grievance Redress and Transparency

- In addition, a web-based Grievance Redress Mechanism (GRM) system will be established and made publicly known and accessible in each of the project countries. This platform will enable stakeholders to submit concerns, or complaints —anonymously if they wish— about any potential violation of environmental and social standards during the project implementation. A dedicated email address will also be provided through the project website to facilitate GRM submissions.

- The Project Management Unit (PMU) will regularly monitor and respond to submissions to ensure timely resolution and continuous improvement, in alignment with the Environmental and Social Policy of the Adaptation Fund.

6. Gender equality and social inclusion are central to the project’s safeguards approach:

- Proposals must demonstrate how they will mainstream gender, empower women, and address differentiated vulnerabilities.

- Gender equality must be embedded across all stages—design, consultation, implementation, monitoring, and evaluation.

- All projects must meet Gender Marker 2, indicating gender equality as a significant objective.

This integrated safeguards framework ensures that all supported innovations are effective, inclusive, and environmentally and socially responsible. Its structured and participatory approach proactively manages environmental and social risks, contributing to sustainable, inclusive, and equitable climate adaptation outcomes.

- Describe the monitoring and evaluation arrangements and provide a budgeted MEL plan.

## Monitoring and Evaluation Arrangements and Budgeted MEL Plan

Monitoring, evaluation and learning (MEL) will be conducted in line with UNDP and AF requirements, ensuring accountability, learning, and adaptive management across the four participating countries. The MEL system will be coordinated by the UNDP Istanbul Regional Hub, with technical support from the global team and implementation support from UNDP Country Offices.

1. MEL Framework and Responsibilities

- UNDP Istanbul Regional Hub: Leads MEL coordination including developing a web-based digital data collection system for quarterly grantee reports. Reviewing and clearing submitted reports for quality and alignment, designing a results-based reporting template (meeting both UNDP and AF requirements), and developing a project dashboard to visualize KPIs, track progress, and showcase impact. The Hub also consolidates regional data and ensures quality assurance before submitting reports to the AF.

- UNDP Global Team: Provides technical backstopping, tools, global learning integration, review of AF annual progress report.

- UNDP Country Offices: Support national-level data collection, grantee monitoring, and stakeholder engagement.

- Grantees: Submit quarterly reports, gender and safeguard data, and participate in evaluations.

- Independent Evaluators: Conduct midterm and terminal evaluation.

2. Key MEL Activities

Online Inception Workshop and Report

Held within 90 days of project start to:

- Review project strategy, results framework, and MEL plan.

- Clarify roles, reporting lines, and safeguard responsibilities.

- Finalize the first-year work plan and launch the project.

Baseline Assessment

A formal Project Baseline Report will be prepared and submitted to the Adaptation Fund Secretariat no later than the submission of the first Project Performance Report (PPR). This report will:

- Establish baseline values for all indicators in the results framework.

- Use a combination of primary data collection and reliable secondary sources.

- Be developed in collaboration with national partners and validated through stakeholder consultations.

Quarterly and Annual Monitoring

- Grantees submit quarterly technical and financial reports.

- Annual AF Project Performance Reports (PPRs) will be submitted. These reports will comprehensively cover updates on gender mainstreaming, lessons learned, key achievements, the results framework, procurement, financial status, and environmental and social safeguards.

Mid Term Review

An independent mid-term review by the end of year 2 (mid-project) will be done to assess impact, sustainability, and lessons learned. The MTR report and management response will be publicly disclosed.

Terminal Evaluation (TE)

An independent evaluation at project end to assess impact, sustainability, and lessons learned. The TE report and management response will be publicly disclosed.

Knowledge and Learning

- Annual showcasing events and peer learning workshops.

- Web-based publication of lessons learned and technical briefs.

- Integration with the Adaptation Innovation Marketplace (AIM) and regional knowledge platforms.

In addition to these activities, the project includes a dedicated Performance and Data Analyst to enhance the effectiveness of the project’s results framework. The specialist will be responsible for streamlining data collection processes from all grantees, supporting the design of impact indicators (to be included in LVGAs), and developing a database and dashboard to track progress across Western Balkans grantees. They will also consolidate impact data and, where relevant, connect it to broader dashboard and impact showcases under the global CCA portfolio and IRH. The specialist will further support overall project-level MEL and quality assurance processes, including the Mid-Term Review (MTR) and Terminal Evaluation.

## Budget Narrative and Alignment with AF Requirements

Monitoring and Evaluation (M&E) activities are embedded within the project’s implementation structure and budgeted in accordance with the Adaptation Fund’s guidance (AFB/EFC.4/7/Rev.1).

- Day-to-day monitoring activities, including tracking results, managing risks, and reporting, are budgeted under Executing Entity (EE) costs.

- Evaluation activities, including the Mid-Term Review (MTR) and Terminal Evaluation (TE), are budgeted under the Implementing Entity (IE) fee, as they fall under project oversight and completion responsibilities.

- The roles of the UNDP Istanbul Regional Hub and Global Team in quality assurance and evaluation coordination are explicitly tied to the IE fee.

- The roles of the Project Management Unit (PMU) and Project Coordinators in day-to-day monitoring and reporting are tied to EE costs.

The following table presents the reallocation of M&E activities and associated costs in alignment with Adaptation Fund guidelines:

| Monitoring Activity |  |  |  |  |
| --- | --- | --- | --- | --- |
|  | Frequency/Timeframe | Expected Action | Responsible Parties | Indicative Cost (USD) (for the 4 years) |
| Inception Workshop and Report | Inception Workshop within 2 months of the First Disbursement | As per above description | Executing Entity (EE) PMU, Regional Hub, Performance and Data Analyst | 3,000 (See Detailed Budget, Budget Note 4) |
| Project Baseline Report | Baseline report with in first year of implementation not later than submission of annual PPR | As per above Baseline assessment description | Executing Entity (EE) PMU, Regional Hub, Performance and Data Analyst | 3,000 (IE Fee) |
| Track results progress (see above Results Framework for details) | Annually and at mid-point and closure | Slower than expected progress will be addressed by project management. | Executing Entity (EE) Performance and Data Analyst, Regional PM | 20,000 (See Budget Note 1) |
| Monitor and Manage Risk | Quarterly | Risks are identified by project management and actions are taken to manage risk. The risk log is actively maintained to keep track of identified risks and actions taken. | Steering Committee, Regional Project Manager, IRH | IRH staff, PMU |
| Monitor GAAP and ESMF | ongoing |  | Executing Entity (EE) Safeguards Specialist, Gender Specialist | 16,000 (See Budget Notes 5 and 10) |
| Supervision Missions | Annually |  | Implementing Entity (IE) PMU, Performance and Data Analyst | 4,000 (EE fee - See Detailed budget, Budget Note 21) |
| Learning briefs and Learning Missions | As needed | Relevant lessons are captured by the project team and used to inform management decisions. Show and Tell Event: in-person peer networking & learning event for grantees to network and showcase their results | Executing Entity (EE) Performance and Data Analyst, KM Specialist | 50,000 (See Budget Notes 1, 4, 12, 19) |
| Annual Project Quality Assurance | Annually | Areas of strength and weakness will be reviewed by project management and used to inform decisions to improve project performance. | Executing Entity (EE) IRH | 4,000 IRH staff (See Budget Note 21) |
| Review and Make Course Corrections | At least annually | Performance data, risks, lessons and quality will be discussed by the project board and used to make course corrections. | Implementing Entity (IE) PMU, IRH | IRH staff, PMU |
| Annual AF Project Performance Report (PPR) | Annually | Mandatory contribution by Project Team, CO and RTA. Strengths and weaknesses will be reviewed by project management and used to inform decisions to improve project performance | Executing Entity (EE) PMU, Performance and Data Analyst, IRH, RTA | 4,000 (See Budget Note 21) |
| Project Review (Steering Committee) | At least annually | Any quality concerns or slower than expected progress should be discussed by the project board and management actions agreed to address the issues identified. | Implementing Entity (IE) Steering Committee |  |
| Mid-Term Review (MTR) | End of Year 2 | An independent mid-term review will assess impact, sustainability and lessons learned. | Executing Entity (EE) - IRH | 18,000 (IE Fee) |
| Terminal Evaluation (TE) | End of Year 4 | An independent evaluation at project end to assess impact, sustainability, and lessons learned. | Executing Entity (EE) - IRH | 24,000 (IE Fee) |
| TOTAL |  |  |  | 146,000 |

- Include a results framework for the project / programme proposal, including milestones, targets, and indicators.

Results Framework for the Project Proposal: Milestones, Targets, and Indicators

| Regional Project Objective: To accelerate locally-led adaptation innovation in Bosnia and Herzegovina, Montenegro, North Macedonia, and Serbia by applying an enterprise development approach that strengthens regional collaboration, promotes gender equality and women’s empowerment, supports locally-led innovation in priority and inclusion, and enables knowledge exchange at both regional and global levels. |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Project Objective | Outcome Indicators | Baseline | Target at Project Completion | Means of Verification | Risks and Assumptions |
| To accelerate locally-led adaptation innovation in Bosnia and Herzegovina, Montenegro, North Macedonia, and Serbia by applying an enterprise development approach that strengthens regional collaboration, promotes gender equality and women’s empowerment, supports locally-led innovation in priority and inclusion, and enables knowledge exchange at both regional and global levels | 01: Number of people with increased resilience to climate change as a result of locally-led adaptation innovations supported, scaled, or replicated through enterprise development and regional collaboration: - Direct beneficiaries (male and female) - Indirect beneficiaries (male and female) | 0 0 | (a) Direct Beneficiaries Total: 40,000 (estimated); Female: 20,660 Male: 19,340 40,000 (est.) (b) Indirect Beneficiaries Total: 100,000. Female: 51,650 Male: 48,350 (est.) | Project records, grantees proposal, progress reports, baseline | Assumptions Baseline data on beneficiaries will be available or collected early in the project. Risks: Grantees may have limited or no capacity to do so without technical support. |
|  | 02: Number of supported adaptation innovations/number of adaptation assets created or strengthened that contribute to: - resilience of ecosystems/ecosystem services - climate-resilient livelihoods. | 0 0 | (a) 10: contributing to the resilience of ecosystems/ ecosystem services or nature-based adaptation solutions (b) 10: contributing to climate-resilient livelihoods (Targets will be reviewed after selection of grantees.) |  |  |
| Outcome & corresponding Outputs | Output Indicators | Baseline | Target at Project Completion | Means of Verification | Risks and Assumptions |
| Outcome 1: Development, promotion, and acceleration of locally-led innovative climate adaptation solutions in four Balkans countries, with particular emphasis on approaches that advance gender equality and women’s empowerment, and which address priority climate risks. | 1.1. Number of climate adaptation, climate resilient production and consumption, and nature-based solutions piloted | 0 | 30 | Project reports, grantee reports, signed LVGAs, gender action plan, gender disaggregated indicators and data | Assumptions: Sufficient pool of local actors with innovative ideas; Local organizations have or can develop technical capacity; Innovation grant mechanism is accessible Risks: Limited capacity of grantees; Political or institutional barriers; Low participation from underrepresented groups such as women and marginalized population. |
| Output 1.1: innovation concepts are identified and strengthened through inclusive call for interest, innovation sprints, and tailored design support. | 1.1.1. Number of LVGAs led by or inclusive of women or marginalized group representatives 1.1.2. No / Percentage of LVGAs that demonstrate meaningful integration of gender equality and social inclusion (GESI) in their design, implementation, or governance. | 0 0 | 8 20/100% |  |  |
| Output 1.2: Promising pilots are financed through small-scale grants and supported to address climate risks with a focus on gender equality and social inclusion. | 1.2.1. Number of innovative adaptation solutions funded | 0 | 20 |  |  |
| Outcome 2: Selected adaptation innovations are strengthened and positioned for scale through tailored business development support, market testing, and identification of funding and financing pathways. | 2.1 No of innovations adopted/ replicated or scaled by public institutions, private sector actors or other NGOs/CSOs | 0 | At least 4 or 1 per country (to be tracked through policy uptake and replication pathways) | Incubation and acceleration program reports, integration reports, market analysis, participant feedback; business plans, investment pitches Integration reports, market analysis, policy adoption records, stakeholder interviews | Assumptions: Business development support tailored to local innovators; Growing ecosystem of investors and funders; National and regional systems open to integration Risks: Limited market readiness or demand; Insufficient follow-on funding; Regulatory or institutional barriers |
| Output 2.1: Adaptation innovators receive tailored business development support, including incubation, acceleration, mentoring, and market testing, to strengthen implementation readiness and sustainability. | 2.1.1 Number of adaptation innovators receiving business incubation and acceleration services 2.1.2. % of grantees receiving GESI integration training 2.1.3. Number of women-led or minority-led projects receiving tailored mentoring | 0 0 0 | 20 100% 8 |  |  |
| Output 2.2: Scalable adaptation innovations are connected to funding and financing opportunities and supported for integration into national systems, local service delivery, or relevant markets. | 2.2.1 No of business plans, prototypes, or investment pitches developed | 0 | 20 TBD (depends on grantee capacity and BOOST outcomes) |  |  |
| Outcome 3: Knowledge, evidence, and lessons from adaptation innovations are captured, shared, and leveraged to inform replication, scale and policy engagement across the Western Balkans through regional learning platform and global networks. | 3.1 Number of citation and/or adoption of shared lessons learned and codified knowledge | 0 | At least 10 citations / documented cases of adoption of lessons learned during the lifetime of the project | Regional collaboration platform documentation, knowledge products, dissemination reports, events | Assumptions: Regional collaboration supported by shared climate challenges; Effective documentation and dissemination of knowledge products; Stakeholders willing to engage Risks: Limited engagement in regional platforms; Inadequate documentation or communication; Contextual differences or lack of enabling policies |
| Output 3.1: Regional knowledge exchange platforms and collaboration mechanisms are established to facilitate peer learning, cross-border dialogue, and community-of-practice engagement among adaptation actors. | 3.1.1 No of regional knowledge-sharing platforms or events organized / Number of regional knowledge-sharing events with content explicitly addressing gender and social inclusion. | 0 | At least 4 (1 per year of implementation) / At least 2 (50% of total events) |  |  |
| Output 3.2: Insights, lessons learned, and good practices from adaptation pilots are systematically documented, synthesized, and disseminated to inform future programming and policy across countries. | 3.2.1 No of knowledge products developed and disseminated 3.2.2 No of case studies from the target countries, highlighting women-led adaptation innovations published 3.2.3. Number of gender and social inclusion-focused learning briefs produced | 0 0 0 | 10 5 3 |  |  |

Core Impact Indicator Summary Table

| Adaptation Fund Core Impact Indicator “Number of Beneficiaries” |  |  |
| --- | --- | --- |
|  | Baseline (absolute number) | Target at project approval (absolute number) |
| Direct beneficiaries supported by the project | 0 | 40,000 |
| Female direct beneficiaries | 0 | 20,660 |
| Youth direct beneficiaries Youth defined as ages 15–24; country shares use 2020 est. as latest consolidated public figures; will be updated in Year 1 using actual grantee data | 0 | 4,730 |
| Indirect beneficiaries supported by the project | 0 | 100,000 |
| Female indirect beneficiaries | 0 | 51,650 |
| Youth indirect beneficiaries Youth defined as ages 15–24; country shares use 2020 est. as latest consolidated public figures; will be updated in Year 1 using actual grantee data | 0 | 11,825 |

| Adaptation Fund Core Impact Indicator “Assets Produced, Developed, Improved, or Strengthened” |  |  |
| --- | --- | --- |
|  | Baseline | Target at project approval |
| Sector: Multi-sector (agriculture, coastal management, disaster risk reduction, urban development, water management, food security, health) *Target sectors to be defined upon selection of grantees |  |  |
| Targeted Asset 2) Physical asset (produced/improved/strengthened) | 0 | (a) 30 piloted; (b) 5 scaled |
| Changes in Asset (Quantitative or qualitative depending on the asset) | Not improved | Mostly improved |

| Adaptation Fund Indicator “Number of innovative adaptation practices, tools and technologies accelerated, scaled-up and/or replicated” |  |  |
| --- | --- | --- |
|  | Baseline | Target at project approval |
| No. of innovative practices/tools and technologies | 0 | 4 (at least 1 per country) |
| Sector: Multi-sector (agriculture, coastal management, disaster risk reduction, urban development, water management, food security, health) *Target sectors to be defined upon selection of grantees |  |  |
| Status | No innovative practices | Completed innovative practices |
| Effectiveness | 2. Partially effective | 4.Effective |

- Demonstrate how the project / programme aligns with the Results Framework of the Adaptation Fund

## Alignment of the Project with the Adaptation Fund's Results Framework

| Project Objective(s) | Project Objective Indicator(s) | Fund Outcome | Fund Outcome Indicator | Estimated Budget |
| --- | --- | --- | --- | --- |
| To accelerate locally-led adaptation innovation in Bosnia and Herzegovina, Montenegro, North Macedonia, and Serbia by applying an enterprise development approach that strengthens regional collaboration, promotes gender equality and women’s empowerment, supports locally-led innovation and inclusion, and enables knowledge exchange at both regional and global levels. | Number of people with increased resilience to climate change as a result of locally-led adaptation innovations supported, scaled, or replicated through enterprise development and regional collaboration. Number of supported adaptation innovations/number of adaptation assets created or strengthened that contribute to: resilience of ecosystems/ ecosystem services and climate-resilient livelihoods. | Outcome 8: Support the development and diffusion of innovative adaptation practices, tools and technologies Outcome 3: Strengthened awareness and ownership of adaptation and climate risk reduction processes at local level Outcome 5: Increased ecosystem resilience in response to climate change and variability induced stress Outcome 6: Diversified and strengthened livelihoods and sources of income for vulnerable people in targeted areas | 8. Innovative adaptation practices are rolled out, scaled up, encouraged and/or accelerated at regional, national and/or subnational level. 3.2. Percentage of targeted population applying appropriate adaptation responses 5. Ecosystem services and natural resource assets maintained or improved under climate change and variability-induced stress 6.2. Percentage of targeted population with sustained climate-resilient alternative livelihoods |  |
| Project Outcome(s) | Project Outcome Indicator(s) | Fund Output | Fund Output Indicator |  |
| AF MTS ER3, ER4 Outcome 1: Development, promotion, and acceleration of locally-led innovative climate adaptation solutions in four Balkans countries, with particular emphasis on approaches that advance gender equality and women’s empowerment, and which address priority climate risks | Number of climate adaptation, climate resilient production and consumption, and nature-based solutions piloted | Output 5: Vulnerable ecosystem services and natural resource assets strengthened in response to climate change impacts, including variability | 5.1 Number of natural resources assets created, maintained or improved to withstand conditions resulting from climate variability and change (by type and scale) | $1,381,396 |
|  |  | Output 6: Targeted individual and community livelihood strategies strengthened in relation to climate change impacts, including variability | 6.1.1. Number and type of adaptation assets (tangible and intangible) created or strengthened in support of individual or community livelihood strategies | $1,381,397 |
| AF MTS ER2, ER4 Outcome 2: Selected adaptation innovations are strengthened and positioned for scale through tailored business development support, market testing, and identification of funding and financing pathways. | No of innovations adopted/ replicated or scaled by public institutions, private sector actors or other NGOs/CSOs | Output 8: Viable innovations are rolled out, scaled up, encouraged and/or accelerated. | 8.1. No. of innovative adaptation practices, tools and technologies accelerated, scaled-up and/or replicated | $ 516,980 |
|  |  | Output 3.2: Strengthened capacity of national and subnational stakeholders and entities to capture and disseminate knowledge and learning | 3.2.2 No. of tools and guidelines developed (thematic, sectoral, institutional) and shared with relevant stakeholders | $ 464,676 |
| AF MTS ER1, ER4 Outcome 3: Knowledge, evidence, and lessons from adaptation innovations are captured, shared, and leveraged to inform replication, scale and policy engagement across the Western Balkans through regional learning platform and global networks. | Number of citation and/or adoption of shared lessons learned and codified knowledge | Output 8: Viable innovations are rolled out, scaled up, encouraged and/or accelerated. | 8.2. No. of key findings on effective, efficient adaptation practices, products and technologies generated | $ 638,246 |

- Include a detailed budget with budget notes, broken down by country as applicable, a budget on the Implementing Entity management fee use, and an explanation and a breakdown of the execution costs.

## G.1. The Detailed Budget and Execution Costs Breakdown with Budget Notes and the Implementing Entity Management Fee

## All related budget components — including the detailed budget, execution costs breakdown, budget notes, and the MIE management fee — are presented in Annex 8 as a separate file.

| Quantum Outcome (AF Component) | Quantum Output (AF Outcome) | Quantum Responsible Party | Quantum Fund ID | Quantum Donor ID | Quantum Activity (AF Output) | Quantum Budgetary Account Code | Quantum Budget Account Description | Amount Year 2026 | Amount Year 2027 | Amount Year 2028 | Amount Year 2029 | Total (USD) | Budget Note No. |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Component 1. Innovation Facility for Climate Adaptation | Outcome 1 Development, promotion, and acceleration of locally-led innovative climate adaptation solutions in four Balkans countries, with particular emphasis on approaches that advance gender equality and women’s empowerment, and which address priority climate risks | UNDP | 62000 | 011602 | Activity 1.1 (Output 1.1) | 71400 | Contractual Services-Individuals | 207,891 | 121,926 | 31,640 | 31,640 | 393,097 | 1 |
|  |  |  |  |  |  | 72500 | Supplies | 4,000 | 4,000 | 4,000 | 4,000 | 16,000 | 2 |
|  |  |  |  |  |  | 73100 | Rental and maintenance-premises | 1,455 | 1,455 | 1,455 | 1,455 | 5,820 | 3 |
|  |  |  |  |  |  | 75700 | Training, Workshops and Conference | 30,000 | 30,000 |  |  | 60,000 | 4 |
|  |  |  |  |  | Activity 1.2 (Output 1.2) | 71200 | International Consultants | 12,000 | 9,000 | 3,000 | 0 | 24,000 | 5 |
|  |  |  |  |  |  | 71400 | Contractual Services-Individuals | 34,719 | 34,719 | 34,719 | 34,719 | 138,876 | 6 |
|  |  |  |  |  |  | 71600 | Travel | 20,000 | 20,000 | 20,000 | 20,000 | 80,000 | 7 |
|  |  |  |  |  |  | 72100 | Contractual Services-Companies | 0 | 750,000 | 250,000 | 0 | 1,000,000 | 8a |
|  |  |  |  |  |  | 72600 | Grants | 0 | 750,000 | 300,000 | 0 | 1,050,000 | 8b |
| Total Component 1 |  |  |  |  |  |  |  | 310,065 | 1,721,100 | 644,814 | 91,814 | 2,767,793 |  |
| Component 2. Technical assistance and capability development for scale | Outcome 2 Selected adaptation innovations are strengthened and positioned for scale through tailored business development support, market testing, and identification of funding and financing pathways. | UNDP | 62000 | 011602 | Activity 2.1 (Output 2.1) | 71200 | International Consultants | 17,500 | 42,000 | 42,000 | 14,000 | 115,500 | 9 |
|  |  |  |  |  |  | 71400 | Contractual Services-Individuals | 7,588 | 7,588 | 0 | 0 | 15,176 | 10 |
|  |  |  |  |  |  | 71600 | Travel | 15,000 | 25,000 | 25,000 | 24,000 | 89,000 | 6 |
|  |  |  |  |  |  | 72100 | Contractual Services-Companies | 0 | 80,000 | 80,000 | 0 | 160,000 | 11 |
|  |  |  |  |  |  | 72500 | Supplies | 0 | 4,000 | 1,000 | 0 | 5,000 | 2 |
|  |  |  |  |  |  | 75700 | Training, Workshops and Conference | 0 | 40,000 | 40,000 | 0 | 80,000 | 12 |
|  |  |  |  |  | Activity 2.2 (Output 2.2) | 71200 | International Consultants | 0 | 80,000 | 80,000 | 0 | 160,000 | 13 |
|  |  |  |  |  |  | 71400 | Contractual Services-Individuals | 62,524 | 62,524 | 90,966 | 90,966 | 306,980 | 14 |
|  |  |  |  |  |  | 73100 | Rental and maintenance costs | 1,250 | 1,250 | 1,250 | 1,250 | 5,000 | 3 |
|  |  |  |  |  |  | 72100 | Contractual Services-Companies | 0 | 0 | 45,000 | 0 | 45,000 | 15 |
| Total Component 2 |  |  |  |  |  |  |  | 103,862 | 342,362 | 405,216 | 130,216 | 981,656 |  |
| Component 3.Knowledge Management and Regional Collaboration | Outcome 3: Knowledge, evidence, and lessons from adaptation innovations are captured, shared, and leveraged to inform replication, scale and policy engagement across the Western Balkans through regional learning platform and global networks | UNDP | 62000 | 011602 | Activity 3.1 (Output 3.1) | 71400 | Contractual Services-Individuals | 134,400 | 102,271 | 91,561 | 72,361 | 400,593 | 16 |
|  |  |  |  |  |  | 73100 | Rental and maintenance costs | 1,500 | 1,500 | 1,500 | 1,500 | 6,000 | 3 |
|  |  |  |  |  |  | 71600 | Travel | 20,000 | 20,000 | 20,000 | 20,000 | 80,000 | 6 |
|  |  |  |  |  | Activity 3.2 (Output 3.2) | 71200 | International Consultants | 14,000 | 9,500 | 9,500 | 9,500 | 42,500 | 17 |
|  |  |  |  |  |  | 71400 | Contractual Services-Individuals | 25,352 | 16,901 | 8,450 | 8,450 | 59,153 | 18 |
|  |  |  |  |  |  | 75700 | Training, Workshops and Confer | 0 | 0 | 0 | 50,000 | 50,000 | 19 |
| Total Component 3 |  |  |  |  |  |  |  | 195,252 | 150,172 | 131,011 | 161,811 | 638,246 |  |
| Project Execution Costs | Project Management Cost (PMC) | UNDP | 62000 | 011602 | Activity PMC | 74100 | Professional Services | 0 | 0 | 0 | 20,120 | 20,120 | 20 |
|  |  |  |  |  |  | 71400 | Contractual Services-Individuals | 7,910 | 7,910 | 7,910 | 7,910 | 31,640 | 21 |
|  |  |  |  |  |  | 64397 | Direct Project Cost-Staff | 25,000 | 35,000 | 23,000 | 23,000 | 106,000 | 22 |
| Total Project Management Cost |  |  |  |  |  |  |  | 32,910 | 42,910 | 30,910 | 51,030 | 157,760 |  |
| Total Direct cost of the action |  |  |  |  |  |  |  | 642,089 | 2,256,544 | 1,211,951 | 434,871 | 4,545,455 |  |
| Indirect Costs - GMS (10%) |  |  |  |  |  |  |  | 64,209 | 225,654 | 121,195 | 43,487 | 454,545 |  |
| Grand total (Direct cost and GMS) |  |  |  |  |  |  |  | 706,298 | 2,482,198 | 1,333,146 | 478,358 | 5,000,000 |  |

Budget Notes:

| Budget Note No. | Project Output (Description) |
| --- | --- |
| 1 | Innovation for Adaptation - Global Technical Specialist: Overall coordination of the global team and Technical Assistance (TA) to support the WB grantees (and guidance to the PMU/COs while delivering the project). Brings all the lessons learnt, partnership platform, and know how from the global project UNDP-AFCIA. Maintaining the well established relationship with Adaptation Fund counterparts and other partners. |
|  | Performance and Data analyst: Responsible to streamline the data collection process from all the grantees. Support with the design of impact indicators (to be included in LVGAs). Including track results progress in line with the Results Framework. Includes the capturing of lessons learned and the development of Learning Briefs, as per MEL budgeted plan) |
|  | Regional Project Manager: Leads the implementation of Component 1 – Innovation Facility for Climate Adaptation across the four Western Balkans countries. Oversees the identification and selection of locally-led innovative climate adaptation solutions, with a focus on approaches advancing gender equality and women’s empowerment and addressing priority climate risks. Coordinates the design and delivery of the regional learning programme, including design sprints, and manages the disbursement of grants. Ensures coherence across country-level activities, facilitates cross-country collaboration, and maintains strategic engagement with regional and national stakeholders to achieve project objectives. |
|  | Project Coordinator BIH: Manages the day-to-day implementation of Component 1 – Innovation Facility for Climate Adaptation at the country level. Coordinates with local partners and stakeholders to identify, promote, and support innovative climate adaptation solutions, ensuring integration of gender equality and women’s empowerment and addressing priority climate risks. Oversees in-country delivery of activities, monitors progress, and ensures timely reporting to the Regional Project Manager. Contributes to the regional learning programme and design sprint activities, and supports grant recipients in meeting project goals and compliance requirements. |
|  | Project Coordinator MNE: Manages the day-to-day implementation of Component 1 – Innovation Facility for Climate Adaptation at the country level. Coordinates with local partners and stakeholders to identify, promote, and support innovative climate adaptation solutions, ensuring integration of gender equality and women’s empowerment and addressing priority climate risks. Oversees in-country delivery of activities, monitors progress, and ensures timely reporting to the Regional Project Manager. Contributes to the regional learning programme and design sprint activities, and supports grant recipients in meeting project goals and compliance requirements. |
|  | Project Coordinator SRB: Manages the day-to-day implementation of Component 1 – Innovation Facility for Climate Adaptation at the country level. Coordinates with local partners and stakeholders to identify, promote, and support innovative climate adaptation solutions, ensuring integration of gender equality and women’s empowerment and addressing priority climate risks. Oversees in-country delivery of activities, monitors progress, and ensures timely reporting to the Regional Project Manager. Contributes to the regional learning programme and design sprint activities, and supports grant recipients in meeting project goals and compliance requirements. |
| 2 | Project office supplies |
| 3 | Rental and maintenance costs of project office premises |
| 4 | Training and workshops for grantees: Includes Learning and Design for Innovation Sprint including: virtual regional workshops, "test & refine homework", peer-to-peer learning exchanges, rapid individual mentorship. Including inception workshop as per M&E Budget |
| 5 | Safeguard specialist – International Consultant (IC): in coordination with the Performance and data analyst, provides technical support and quality assurance throughout the project lifecycle. Including Monitoring of the ESMF ($8,000 as per budgeted MEL plan) |
| 6 | Grants Associate: Supports the administration and management of grants, ensuring compliance with procedures, assisting in the selection and monitoring of grantees, and maintaining accurate financial and narrative reporting. |
| 7 | Travel for local and international consultants to attend workshops and trainings with grantees |
| 8a | Innovation Challenge grants to MSMEs for innovation solutions, will follow UNDP policy on Innovation Challenges |
| 8b | Low Value Grants to NGOs/CSOs for innovation solutions, will follow UNDP policy on Low Value Grants |
| 9 | "Partnerships and Investments Specialist: Brings the partnerships with the MBA schools from the Global Network for Advanced Management (GNAM) and connections with key private sector actors (e.g. BNP Paribas, Acumen, Foundations). Onboards grantees and students and ensures that each yearly TA cycle is beneficial for both students and grantees (working in their business development plans, revenue generation models, etc). Leads the research and though leadership component of this collaboration with grantees and MBA schools. Gives one on one TA to grantees around scaling, innovative finance mechanisms and investments." |
| 10 | Gender expertise: Provision of technical expertise to ensure gender-responsive and transformative project implementation, including integrating gender into activities, monitoring gender-specific indicators, and advising on stakeholder engagement and capacity building. Including Monitoring the implementation of the GAAP ($8,000 as per budgeted MEL Plan) |
| 11 | Technical assistance - business and administration |
| 12 | Training programs and workshops on business model development, financial planning, and investment readiness, include both in-person and virtual delivery formats |
| 13 | Local Consultancies for business, acceleration, and scaling technical support |
| 14 | Regional Project Associate: Provides administrative, logistical, and operational support for the implementation of the Technical Assistance and Capability Development for Scale component. Assists the Project Coordinator at the country level and the Regional Project Manager in coordinating and documenting activities related to business development support, market testing, and identification of funding and financing pathways for selected adaptation innovations. Facilitates communication and coordination between country and regional stakeholders, ensures smooth implementation of activities, and maintains accurate records to support timely delivery within scope. (based in MK) |
|  | Project Coordinator BIH: Leads the implementation of the Technical Assistance and Capability Development for Scale component at the country level, ensuring selected adaptation innovations are strengthened and positioned for scale. Provides technical guidance on business development support, oversees market testing processes, and facilitates the identification of funding and financing pathways. Coordinates closely with the Regional Project Manager, engages with national stakeholders and partners, and ensures activities are delivered on time, within scope, and in alignment with project objectives. |
|  | Project Associate BIH: Provides administrative, logistical, and operational support for the implementation of the Technical Assistance and Capability Development for Scale component. Assists the Project Coordinator in organizing and documenting activities related to business development support, market testing, and identification of funding and financing pathways for selected adaptation innovations. Ensures smooth coordination with stakeholders, maintains accurate records, and supports the delivery of activities on time and within scope. |
|  | Project Coordinator MNE: Leads the implementation of the Technical Assistance and Capability Development for Scale component at the country level, ensuring selected adaptation innovations are strengthened and positioned for scale. Provides technical guidance on business development support, oversees market testing processes, and facilitates the identification of funding and financing pathways. Coordinates closely with the Regional Project Manager, engages with national stakeholders and partners, and ensures activities are delivered on time, within scope, and in alignment with project objectives. |
|  | Project Associate MNE: Provides administrative, logistical, and operational support for the implementation of the Technical Assistance and Capability Development for Scale component. Assists the Project Coordinator in organizing and documenting activities related to business development support, market testing, and identification of funding and financing pathways for selected adaptation innovations. Ensures smooth coordination with stakeholders, maintains accurate records, and supports the delivery of activities on time and within scope. |
|  | Project Coordinator SRB: Leads the implementation of the Technical Assistance and Capability Development for Scale component at the country level, ensuring selected adaptation innovations are strengthened and positioned for scale. Provides technical guidance on business development support, oversees market testing processes, and facilitates the identification of funding and financing pathways. Coordinates closely with the Regional Project Manager, engages with national stakeholders and partners, and ensures activities are delivered on time, within scope, and in alignment with project objectives. |
|  | Project Associate SRB: Provides administrative, logistical, and operational support for the implementation of the Technical Assistance and Capability Development for Scale component. Assists the Project Coordinator in organizing and documenting activities related to business development support, market testing, and identification of funding and financing pathways for selected adaptation innovations. Ensures smooth coordination with stakeholders, maintains accurate records, and supports the delivery of activities on time and within scope. |
| 15 | Technical assistance - financing/funding: engaging specialized venture philanthropy organizations through competitive procurement processes. These experts will provide tailored guidance on impact investment strategies, social enterprise development, and innovative financing mechanisms for climate adaptation ventures. |
| 16 | Community engagement and Knowledge Management Specialist: In collaboration with the Performance and Data Analyst, produces high quality KM reports, factsheets, business cases from the WB grantees and provides inputs to KM products that are prepared by UNDP Climate teams to strengthen the visibility of the project. Maintain relationship with KM partners. Utilizing the knowledge and lessons generated, organizes peer to peer knowledge exchange sessions, prepares sessions in international conferences/webinars to showcase the grantees- impact achieved by the project, and coordinates capacity building efforts in specific matters (e.g. such as crowdfunding). Includes the capturing of lessons learned and the development of Learning Briefs and Missions, as per MEL budgeted plan) |
|  | Innovation Specialist: Responsible for bringing lessons learned and best practices from the Boost regional programme, facilitating knowledge transfer, and supporting the design and implementation of the innovation sprint to develop locally-led adaptation solutions. |
|  | Regional Project Associate: Provides administrative, logistical, and operational support for the Knowledge Management and Regional Collaboration component across participating countries. Assists the Regional Project Manager in coordinating activities within the Project Management Unit, ensuring smooth planning, implementation, and documentation of knowledge capture, sharing, and policy engagement efforts. Supports country teams in organizing and feeding inputs into the regional learning platform and global networks, facilitates cross-country communication, and maintains accurate records to ensure timely and coherent delivery of regional and national activities. (based in MK) |
|  | Project Coordinator BIH: Leads the implementation of the Knowledge Management and Regional Collaboration component at the country level, ensuring knowledge, evidence, and lessons from adaptation innovations are effectively captured, documented, and shared. Provides technical guidance to leverage these insights for replication, scale, and policy engagement. Coordinates inputs to the regional learning platform and contributes to global networks, working closely with the Regional Project Manager to promote cross-country collaboration and strengthen regional partnerships. |
|  | Project Associate BIH: Provides administrative, logistical, and operational support for the Knowledge Management and Regional Collaboration component. Assists the Project Coordinator at the country level and the Community engagement and Knowledge Management Specialist in organizing and documenting knowledge products, lessons learned, and evidence from adaptation innovations. Supports coordination with national and regional stakeholders, contributes to updates for the regional learning platform, and ensures smooth information flow to facilitate replication, scale, and policy engagement. |
|  | Project Coordinator MNE: Leads the implementation of the Knowledge Management and Regional Collaboration component at the country level, ensuring knowledge, evidence, and lessons from adaptation innovations are effectively captured, documented, and shared. Provides technical guidance to leverage these insights for replication, scale, and policy engagement. Coordinates inputs to the regional learning platform and contributes to global networks, working closely with the Regional Project Manager to promote cross-country collaboration and strengthen regional partnerships. |
|  | Project Coordinator SRB: Leads the implementation of the Knowledge Management and Regional Collaboration component at the country level, ensuring knowledge, evidence, and lessons from adaptation innovations are effectively captured, documented, and shared. Provides technical guidance to leverage these insights for replication, scale, and policy engagement. Coordinates inputs to the regional learning platform and contributes to global networks, working closely with the Regional Project Manager to promote cross-country collaboration and strengthen regional partnerships. |
|  | Project Associate MNE: Provides administrative, logistical, and operational support for the Knowledge Management and Regional Collaboration component. Assists the Project Coordinator at the country level and the Community engagement and Knowledge Management Specialist in organizing and documenting knowledge products, lessons learned, and evidence from adaptation innovations. Supports coordination with national and regional stakeholders, contributes to updates for the regional learning platform, and ensures smooth information flow to facilitate replication, scale, and policy engagement. |
|  | Project Associate SRB: Provides administrative, logistical, and operational support for the Knowledge Management and Regional Collaboration component. Assists the Project Coordinator at the country level and the Community engagement and Knowledge Management Specialist in organizing and documenting knowledge products, lessons learned, and evidence from adaptation innovations. Supports coordination with national and regional stakeholders, contributes to updates for the regional learning platform, and ensures smooth information flow to facilitate replication, scale, and policy engagement. |
| 17 | Audiovisual / graphic design |
|  | Translation and interpretation services |
| 18 | Communications Specialist: Produces high quality stories, blogs and photo stories, about the grantees in collaboration with the KM specialist. Connects the narrative with the Climate Promise website and the overall CCA team portfolio. Produces comms materials that has the quality and incorporates the guidance to use the UNDP Climate channels and give international visibility to the projects, the KM products, and the grantees. |
| 19 | Show and Tell Event: in-person peer networking & learning event for grantees to network and showcase their results |
| 20 | Audit costs |
| 21 | Regional Project Manager – PMU (20%): Responsible for overall management, monitoring and supervision of project implementation across the four countries, overseeing timely delivery of activities and results. Support in the reports development. |
| 22 | Direct Project Costs - Staff costs for the services provided by IRH and CO Staff |

IE Management fee:

| Category | Services Provided by UNDP | IE Fee (USD) |
| --- | --- | --- |
| Identification, Sourcing and Screening of Ideas | Provide information on substantive issues in adaptation and innovation associated with the purpose of the Adaptation Fund (AF). | 22,727 |
|  | Engage in upstream policy dialogue related to a potential application to the AF. |  |
|  | Verify soundness & potential eligibility of identified ideas for AF. |  |
| Feasibility Assessment / Due Diligence Review | Provide up-front guidance on converting general idea into a feasible project/programme. | 68,182 |
|  | Source technical expertise in line with the scope of the project/programme. |  |
|  | Verify technical reports and project conceptualization. |  |
|  | Provide detailed screening against technical, financial, social and risk criteria and provide statement of likely eligibility against AF requirements. |  |
|  | Determination of execution modality and local capacity assessment of the executing entity. |  |
|  | Assist in identifying technical partners. Validate partner technical abilities. Obtain clearances from AF. |  |
| Development & Preparation | Provide technical support, backstopping and troubleshooting to convert the idea into a technically feasible and operationally viable project/programme. | 90,909 |
|  | Source technical expertise in line with the scope of the project/programme needs. |  |
|  | Verify technical reports and project conceptualization. |  |
|  | Verify technical soundness, quality of preparation, and match with AF expectations. |  |
|  | Negotiate and obtain clearances by AF. Respond to information requests, arrange revisions etc. |  |
| Implementation | Technical support in preparing TORs and verifying expertise for technical positions. | 204,545 |
|  | Provide technical and operational guidance project teams. - Verification of technical validity / match with AF expectations of inception report/baseline report. |  |
|  | Provide technical information as needed to facilitate implementation of the project activities. |  |
|  | Provide advisory services as required. |  |
|  | Provide technical support, participation as necessary during project activities. |  |
|  | Provide troubleshooting support if needed. Provide support and oversight missions as necessary. |  |
|  | Provide technical monitoring, progress monitoring, validation and quality assurance throughout. |  |
|  | Allocate and monitor Annual Spending Limits based on agreed work plans. |  |
|  | Receipt, allocation and reporting to the AFB of financial resources. |  |
|  | Oversight and monitoring of AF funds. |  |
|  | Return unspent funds to AF. |  |
| Evaluation and Reporting | Provide technical support in preparing TOR and verify expertise for technical positions involving evaluation and reporting (including for the Mid-Term- and Terminal Evaluations). | 68,182 |
|  | Participate in briefing / debriefing (including for the Mid-Term and Terminal Evaluations).. |  |
|  | Verify technical validity / match with AF expectations of all evaluation and other reports (including for the Mid-Term and Terminal Evaluations). |  |
|  | Undertake technical analysis, validate results, and compile lessons |  |
|  | Disseminate technical findings |  |
| Total |  | 454,545 |

- Include a disbursement schedule with time-bound milestones.

## Disbursement Schedule with Time-Bound Milestones

|  | Upon Agreement signature | One Year after Project Start | Year 2 | Year 3 | Total |
| --- | --- | --- | --- | --- | --- |
| Scheduled Date | 4/1/2026 | 4/1/2027 | 4/1/2028 | 4/1/2029 |  |
| Project Funds | 642,089 | 2,256,544 | 1,211,951 | 434,871 | 4,545,455 |
| Implementing Entity Fees | 220,344 | 135,392 | 72,717 | 26,092 | 454,545 |
| Total | 862,433 | 2,391,936 | 1,284,668 | 460,963 | 5,000,000 |

PART IV: ENDORSEMENT BY GOVERNMENTS AND CERTIFICATION BY THE IMPLEMENTING ENTITY

# PART IV: ENDORSEMENT BY GOVERNMENTS AND CERTIFICATION BY THE IMPLEMENTING ENTITY

- Record of endorsement on behalf of the government

| Bosnia and Herzegovina H.E Srdan Admizic, Minister, Ministry of Finance and Treasury B&H trezorbih@mft.gov.ba | Date: July 16, 2025 |
| --- | --- |
| Montenegro Zoran Dabetić, State Secretary at the Ministry of Ecology, Sustainable Development and Northern Region Development zoran.dabetic@mers.gov.me | Date: July 16, 2025 |
| North Macedonia H.E. Mr. Izet Mexhiti Deputy Prime Minister and Minister Ministry of Environment and Physical Planning i.mexhiti@moepp.gov.mk | Date: July 4, 2025 |
| Serbia H.E Sara Pavkov, Minister, Ministry of Environmental Protection, Serbia | Date: June 26, 2025 |

B.   Implementing Entity certification

Provide the name and signature of the Implementing Entity Coordinator and the date of signature. Provide also the project/programme contact person’s name, telephone number and email address

| I certify that this proposal has been prepared in accordance with guidelines provided by the Adaptation Fund Board, and prevailing National Development and Adaptation Plans (including National Communications to the UNFCCC, national adaptation strategies and plans, disaster risk reduction strategies and action plans etc.) and subject to the approval by the Adaptation Fund Board, commit to implementing the project/programme in compliance with the Environmental and Social Policy of the Adaptation Fund and on the understanding that the Implementing Entity will be fully (legally and financially) responsible for the implementation of this project/programme. |  |
| --- | --- |
| Nancy Bennet Executive Coordinator, Vertical Fund Programme Support, Oversight and Compliance Unit Bureau for Policy and Programme Support United Nations Development Programme Implementing Entity Coordinator |  |
| Date: (Month, Day, Year) | Tel. and email: Nancy.Bennet@undp.org |
| Project Contact Person: Natalia Olofinskaya, Regional Technical Advisor, UNDP IRH |  |
| Tel. And Email: nataly.olofinskaya@undp.org; +90 (543) 532-3046 |  |

PART V: ANNEXES

Rectangle: Rounded Corners 110150740, ShapePART V: ANNEXES

# PART V: Annexes

Annex 1: Letters of endorsement from the governments

Included as a separate file in this proposal.

Annex 2: Grant Application Format and Evaluation Criteria

Included as a separate file in this proposal.

Annex 3: Social and Environmental Screening Procedure (SESP)

Included as a separate file in this proposal.

Annex 4. Social and Environmental Management Framework (ESFM)

Included as a separate file in this proposal.

Annex 5: Gender Assessment and Action Plan

Included as a separate file in this proposal.

Annex 6: Stakeholder Mapping Matrixes

Included as a separate file in this proposal.

Annex 7: Stakeholder Consultations and Engagement

Included as a separate file in this proposal.

Annex 8: Detailed Budget and Breakdown of the IE Management Fee

Included as a separate file in this proposal.

Annex 9: Detailed Multi Annual Workplan

Included as a separate file in this proposal.

Annex 10: Climate Change Analysis

Included as a separate file in this proposal.

Annex 11: Letter of justification for the proposed management arrangements and PMC

Included as a separate file in this proposal.

Thematic areas are: Agriculture, Coastal Zone Management, Disaster risk reduction, Food security, Forests, Human health, Innovative climate finance , Marine and Fisheries, Nature-based solutions and ecosystem based adaptation, Protection and enhancement of cultural heritage, Social innovation,  Rural development, Urban adaptation, Water management, Wildfire Management.

All references to Kosovo shall be understood to be in the context of the Security Council Resolution 1244 (1999).

Worldometer (2025, July 7). Montenegro Population Live. https://www.worldometers.info/world-population/montenegro-population/

Worldometer (2025, July 7). North Macedonia Population Live. https://www.worldometers.info/world-population/north-macedonia-population/#:~:text=The%20current%20population%20of%20the%20Republic%20of,elaboration%20of%20the%20latest%20United%20Nations%20data1.

Worldometer (2025, July 7). Bosnia and Herzegovina Population Live. https://www.worldometers.info/world-population/bosnia-and-herzegovina-population/

Worldometer (2025, July 7). Serbia Population Live. https://www.worldometers.info/world-population/serbia-population/

Statista Research Department (2024, November 22). GDP growth in the Western Balkans 2021-2026. https://www.statista.com/statistics/1337205/western-balkans-gdp-growth/

Statista Research Department (2024, November 22). Real gross domestic product (GDP) growth in the Western Balkans from 2021 to 2026, by territory. https://www.statista.com/statistics/1331455/western-balkans-gdp-growth-by-country/

The United Nations Development Programme (2025). Human Development Report. https://hdr.undp.org/content/human-development-report-2025

Encyclopædia Britannica. https://www.britannica.com/place/Dinaric-Alps

Alpinetrek (2024). “The Dinaric Alps: The Unknown Neighbour.” Available at: https://www.alpinetrek.co.uk/blog/dinaric-alps/#h-character-and-special-features

Shar Mountain National Park. (n.d.). General information. Public Institution National Park Shar Mountain. Retrieved June 29, 2025, from https://www.sarmountain.org.mk/en/park/general-information

Sar Mountain National Park. Available at: https://www.sarmountain.org.mk/en/biodiversity

Balkan Mountains (“Stara Planina”). Available at: https://bulgariawalking.com/hiking-tour/balkan-mountains-hiking-trekking-walking-bulgaria/.

Lasky, Jack (2024). Balkan Mountains. EBSCO Information Services. Available at: https://www.ebsco.com/research-starters/geology/balkan-mountains.a

Alfthan, B.; Krilasevic, E.; Venturini, S.; Bajrovic, S.; Jurek, M.; Schoolmeester, T., Sandei, P.C., Egerer, H, and Kurvits, T. 2015. Outlook on Climate Change Adaptation in the Western Balkan Mountains. United Nations Environment Programme (UNEP), GRID-Arendal, and Environmental Innovations Association (EIA). Vienna, Arendal and Sarajevo. www.grida.no., p. 11.

EuroNatur and Riverwatch, Save the Blue Heart of Europe Campaign. Available at: https://www.balkanrivers.net/en/campaign and https://riverwatch.eu/en/balkanrivers/background.

International Sava River Basin Commission (2010). Sava River Basin Analysis Summary. Available at: https://www.savacommission.org/UserDocsImages/05_documents_publications/water_management/eng/SavaRBMPlan//sava_booklet_eng.pdf.

Ibid.

International Sava River Basin Commission (ISRBC). Information on present and future trends, results of the relevant project implementation, and suggestions for adaptation and further steps are available at: https://www.savacommission.org/en/climate-change.

Such as occurred after the catastrophic May 2014 floods, as a result of toxic slurry released by the tailings-dam collapse at the discontinued Stolice antimony mine into the Kostajnik River and, in the same flood catastrophe, of hazardous and contaminated water pumped from the flooded Tamnava-West Coal Mine (Tamnava-Zapadno polje), a significant open-pit coal mine and major source of fuel for Serbia’s power plants, particularly the Nikola Tesla thermal power plants, into the Kolubara River. Source: Serbia PDNA (2014). Republic of Serbia (2014). Serbia Floods 2014: Post Disaster Needs Assessment (PDNA), Supported Jointly by UN Serbia, EU and World Bank. Available at: https://fpi.ec.europa.eu/system/files/2021-05/pdna_-_serbia_2014_-_report.pdf.

Climate-Adapt (2024). Toolbox for Transboundary Water Contingency Management in the Sava River Basin. Available at: https://climate-adapt.eea.europa.eu/en/metadata/case-studies/toolbox-for-transboundary-water-contingency-management-in-the-sava-river-basin/#_ftn1.

The contaminated tailings released in the Stolice dam collapse in the catastrophic May 2014 floods “contained high levels of antimony, arsenic, barium, zinc, and lead, contaminating the river and surrounding land. The contamination extended for 27 kilometers of riverbeds and 360 hectares of agricultural land.” Source: Republic of Serbia (2015). Ministry of Agriculture and Environment, Serbia Environmental Protection Agency, Assessment and Management of Contaminated Sites in Flood Disaster in Serbia 2014. Available at: https://contaminated-sites.sazp.sk/wp-content/uploads/2020/11/12_ICCS_2015_Dragana_Vidojevic.pdf.

Climate-Adapt (2024). Toolbox for Transboundary Water Contingency Management in the Sava River Basin.

Jámbor (2024). Jámbor, A., Varga, Á. Food security and crises: evidence from the Western Balkans. Agric & Food Security 13, 60 (2024). https://doi.org/10.1186/s40066-024-00514-z

Brankov (2022). Brankov, Tatjana; Bojan Matkovski. Is a Food Shortage Coming to the Western Balkans? Foods 2022, 11(22), 3672; https://doi.org/10.3390/foods11223672

Bogdanov (2022). Bogdanov, N.; Vaško, Ž.; Arias, P.; Pavloska Gjorgjieska, D. Assessment of the Impact of COVID-19 on Agrifood Systems in the Western Balkans—Regional Synthesis Report; FAO: Budapest, Hungary, 2022.

Matkovski (2020). Matkovski, B.; Đokić, D.; Zekić, S.; Jurjević, Ž. Determining Food Security in Crisis Conditions: A Comparative Analysis of the Western Balkans and the EU. Sustainability 2020, 12, 9924.

Božić (2020). Božić, D.; Nikolić, M. Food security and comparative analysis of situation in Serbia and neighbouring countries. Econ. Agric. 2020, 67, 1191–1204.

Brankov (2017). Brankov, T.; Lovre, I. Food security in the Former Yugoslav Republics. Econ. Agric. 2017, 64, 701–721.

World Bank (2025). Western Balkans Regular Economic Report No.21, Steering Through Crises. Available online: https://openknowledge.worldbank.org/bitstream/handle/10986/37368/P17720607706c30e90841607b7d53ee8106.pdf (accessed on 21 June 2025).

Eurostat. How Much are Households Spending on Food? Available online: https://ec.europa.eu/eurostat/web/products-eurostat-news/-/ddn-20201228-1 (accessed on 21 June 2025).

World Bank (2022). Western Balkans Regular Economic Report No. 22, Beyond the Crises, Fall 2022. Available at: https://openknowledge.worldbank.org/bitstream/handle/10986/38189/P17947818ec26c8c17fe014901194ac104a1b5d70a2a.pdf?sequence=1&isAllowed=y (accessed on 21 June 2025).

IFASTAT. Available online: https://www.ifastat.org/databases/plant-nutrition (accessed on 21 June 2025).

Brankov (2022). Brankov, Tatjana; Bojan Matkovski. Is a Food Shortage Coming to the Western Balkans? Foods 2022, 11(22), 3672; https://doi.org/10.3390/foods11223672

The Regional Project‘s four partner countries are in various stages of EU accession, of which the most advanced are Montenegro and Serbia, next North Macedonia, and, for Bosnia and Herzegovina, the European Commission granted candidate status in December 2023 and opened accession negotiations in March 2024. Source: https://enlargement.ec.europa.eu/enlargement-policy/bosnia-and-herzegovina_en.

Alfthan, B.; Krilasevic, E.; Venturini, S.; Bajrovic, S.; Jurek, M.; Schoolmeester, T., Sandei, P.C., Egerer, H, and Kurvits, T. (2015). Outlook on Climate Change Adaptation in the Western Balkan Mountains. United Nations Environment Programme (UNEP), GRID-Arendal, and Environmental Innovations Association (EIA). Vienna, Arendal and Sarajevo. www.grida.no., p. 11.

Ibid., p. 11

The Regional Cooperation Council (RCC) is an all-inclusive, regionally owned and led cooperation framework for South-Eastern Europe (SEE), with a view to promoting and advancing the European and Euro-Atlantic integration of the region. Available at: https://www.rcc.int/home.

RCC (2018). Vuković, Ana, Mirjam Vujadinović Mandić, Radovan Nikčević, Gazmend Turdiu, Study on Climate Change in the Western Balkans Region, Regional Cooperation Council (RCC) Secretariat, Bosne i Hercegovine, Sarajevo. Available at: https://www.rcc.int/download/docs/2018-05-Study-on-Climate-Change-in-WB-2a-lowres.pdf.

Ibid., p. 19.

RCC (2018), p. 19.

RCC (2018), p. 19.

For example, ”normal annual precipitation“ for Serbia is 896 mm. Source: Milosevic, Dragan; Stevan Savic (2013). “Analysis of Precipitation Quantities and Trends from Pannonian and Peripannonian Parts of Serbia”, Dela 39, 2013, 125–139.  December 2013. DOI:10.4312/dela.39.7.125-139

Ibid., p. 126, 129.

Republic of Montenegro (2015). The Second National Communication on Climate Change to the United Nations Convention on Climate Change (UNFCCC), February 2015, p. 43. ”The average annual precipitation ranges from 800 mm in the far north to around 5,000 mm in the far southwest.“ For instance, the village of Crkvice on Mount Orjen in Montenegro is known to receive over 5,000 mm of rainfall annually, and in record years, can even reach 7,000 mm, high precipitation due to orographic rainfall, where moist air is forced upwards by mountains, leading to increased rainfall on the windward slopes. Source: Pavlović, P., Kostić, N., Karadžić, B., Mitrović, M. (2017). Climate. In: The Soils of Serbia. World Soils Book Series. Springer, Dordrecht. https://doi.org/10.1007/978-94-017-8660-7_3.

Pavlović, P., Kostić, N., Karadžić, B., Mitrović, M. (2017). Climate. In: The Soils of Serbia. World Soils Book Series. Springer, Dordrecht. https://doi.org/10.1007/978-94-017-8660-7_3.

Micić Ponjiger, Tanja, Tin Lukić, Robert L. Wilby, Slobodan B. Marković, Aleksandar Valjarević, Slavoljub Dragićević, Milivoj B. Gavrilov, Igor Ponjiger, Uroš Durlević, Miško M. Milanović, and et al. (2023). "Evaluation of Rainfall Erosivity in the Western Balkans by Mapping and Clustering ERA5 Reanalysis Data" Atmosphere 14, no. 1: 104. https://doi.org/10.3390/atmos14010104

Pavlović, P., Kostić, N., Karadžić, B., Mitrović, M. (2017). Climate. In: The Soils of Serbia. World Soils Book Series. Springer, Dordrecht. https://doi.org/10.1007/978-94-017-8660-7_3.

RCC (2018), p. 6, 19.

RCC (2018), p. 19. See discussion above of RCC methodology for the Western Balkans. Also see: Intergovernmental Panel on Climate Change. (2018). Global warming of 1.5°C: An IPCC Special Report on the impacts of global warming of 1.5°C above pre-industrial levels and related global greenhouse gas emission pathways. Available at: https://www.ipcc.ch/sr15/.

Alfthan, B.; Krilasevic, E.; Venturini, S.; Bajrovic, S.; Jurek, M.; Schoolmeester, T., Sandei, P.C., Egerer, H, and Kurvits, T. (2015). Outlook on Climate Change Adaptation in the Western Balkan Mountains. United Nations Environment Programme (UNEP), GRID-Arendal, and Environmental Innovations Association (EIA). Vienna, Arendal and Sarajevo. www.grida.no., p. 16.

RCC (2018), p. 20.

Ibid., p. 20.

Ibid., p. 19-20.

Ibid., p. 20.

Ibid., p. 19.

Ibid., p. 21.

Milosevic, D., Stojsavljević, R., Szabo, S., Stankov, U., Savic, S., Mitrović, L. (2021). “Spatio-temporal variability of precipitation over the Western Balkan countries and its links with the atmospheric circulation patterns”, April 2021, Journal of the Geographical Institute Jovan Cvijic SASA 71(1):29-42. Available at: http://dx.doi.org/10.2298/IJGI2101029M, p. 29.

Ibid., p. 29.

RCC (2018), p. 19.

Ibid., p. 19.

Ibid, p. 20.

Milosevic, D., Stojsavljević, R., Szabo, S., Stankov, U., Savic, S., Mitrović, L. (2021). “Spatio-temporal variability of precipitation over the Western Balkan countries and its links with the atmospheric circulation patterns”, April 2021, Journal of the Geographical Institute Jovan Cvijic SASA 71(1):29-42. Available at: http://dx.doi.org/10.2298/IJGI2101029M, p. 29.

Alfthan, B.; Krilasevic, E.; Venturini, S.; Bajrovic, S.; Jurek, M.; Schoolmeester, T., Sandei, P.C., Egerer, H, and Kurvits, T. (2015). Outlook on Climate Change Adaptation in the Western Balkan Mountains. United Nations Environment Programme (UNEP), GRID-Arendal, and Environmental Innovations Association (EIA). Vienna, Arendal and Sarajevo. www.grida.no., p. 17.

RCC (2018), p. 7.

Ibid., p. 22.

World Bank (2014). Turn Down the Heat: Confronting the New Climate Normal, Turn Down the Heat Report No. 3, November 2014, World Bank Group, p. xix. See also: UNEP/GRID-Arendal (2015), p. 6.

Ibid., p. 4.

RCC (2018), p. 6.

Lelieveld, J., Hadjinicolaou, P., Kostopoulou, E., Giannakopoulos, C., Pozzer, A., Tanarhte, M., & Tyrlis, E. (2012). ”Climate change and impacts in the Eastern Mediterranean and the Middle East.“ Climatic Change, 114(3-4), 667–687. Available at:
https://doi.org/10.1007/s10584-012-0418-4.

Alfthan, B.; Krilasevic, E.; Venturini, S.; Bajrovic, S.; Jurek, M.; Schoolmeester, T., Sandei, P.C., Egerer, H, and Kurvits, T. (2015). Outlook on Climate Change Adaptation in the Western Balkan Mountains. United Nations Environment Programme (UNEP), GRID-Arendal, and Environmental Innovations Association (EIA). Vienna, Arendal and Sarajevo. www.grida.no., p. 17.

RCC (2018), UNEP-GRID-Arendal (2015), p. 17, World Bank (2014), p. 205.

Kotlarski, S., Keuler, K., Christensen, O. B., Déqué, M., Gobiet, A., Goergen, K., ... & van Meijgaard, E. (2014). Regional climate modeling on European scales: A joint standard evaluation of the EURO-CORDEX RCM ensemble. Geoscientific Model Development, 7(4), 1297–1333. Available at: https://doi.org/10.5194/gmd-7-1297-2014

Lelieveld, J., Hadjinicolaou, P., Kostopoulou, E., Giannakopoulos, C., Pozzer, A., Tanarhte, M., & Tyrlis, E. (2012). ”Climate change and impacts in the Eastern Mediterranean and the Middle East.“ Climatic Change, 114(3-4), 667–687. Available at:
https://doi.org/10.1007/s10584-012-0418-4 in UNEP/GRID-Arendal (2015), p. 17.

”Tn” denotes Temperature (Minimum). ”Tx” Temperature (Maximum).

RCC (2018), p. 23.

Ibid., p. 23.

Ibid., p. 24.

Ibid., p. 24.

RCC (2018), p. 25.

Ibid., p. 25.

UNEP/GRID--Arendal (2015), p. 17.

RCC (2018), p. 19, UNEP/GRID-Arendal, p. 17.

Önol, B. and Semazzi, F.H.M (2009). Regionalization of Climate Change Simulations over the Eastern Mediterranean. J. Climate, 22, 1944–1961, in UNEP/GRID-Arendal, p. 17.

Kotlarski, S., Bosshard, T., Lüthi, D., Pall, P., Schär, C. (2011). Elevation gradients of European climate change in the regional climate model COSMO-CLM, Climate Change, vol. 112, pp. 189–215. doi:10.1007/s10584-011-0195-5, in UNEP/GRID-Arendal, p. 17.

Sillmann, J., Kharin, V. V., Zwiers, F. W., Zhang, X., & Bronaugh, D. (2013). Climate extremes indices in the CMIP5 multimodel ensemble: Part 2. Future climate projections. Journal of Geophysical Research: Atmospheres, 118(6), 2473–2493. Available at: https://doi.org/10.1002/jgrd.50188.

Islami, B., Kamberi, M., Bruci, E.D., and Fida, E. (2009). Albania’s Second National Communication to the Conference of Parties under the United Nations Framework Convention on Climate Change. Ministry of Environment, Forestry, and Water Administration: Tirana, Albania, in UNEP/GRID-Arendal (2015), p. 17.

Ibid., p. 24.

RCC (2018), p. 25.

Ibid., p. 26.

Bosnia NAP (2021). Bosnia and Herzegovina National Adaptation Plan and Proposed Measures 2021.

Bosnia NAP (2021), p. 16.

Bosnia NAP (2021), p. 52.

Bosnia NAP (2021), p. 52.

Montenegro Draft NAP

https://www.worldbank.org/en/country/northmacedonia/overview

Climate Risk in North Macedonia: Country Risk Profile. USAID 2018 Report on climate change projections and changes in climate extremes for the Republic of North Macedonia. Available at: https://api.klimatskipromeni.mk/data/rest/file/download/5e8046fa4761fb1b91d41c7fa0a0f34b621b19acc537ff9f45b79af5b623255e.p

https://documents1.worldbank.org/curated/en/116521576516981237/txt/Air-Quality-Management-in-North-Macedonia.txt

Republic Hydrometeorological Service of Serbia (RHMSS). "Temperature Regime in Serbia". Available at: https://www.hidmet.gov.rs/eng/meteorologija/klimatologija_temp_rezim.php.

Serbia NAP (2023). Republic of Serbia: Climate Change Adaptation Program for the Period 2023-2030, referred to informally as the National Adaptation Plan (NAP) or “Serbia NAP 2023”.

Serbia NAP (2023), pp. 22-25.

Lukić, T.; Bjelajac, D.; Fitzsimmons, K.E.; Marković, S.B.; Basarin, B.; Mlađan, D.; Micić, T.; Schaetzl, R.J.; Gavrilov, M.B.; Milanović, M.; et al. Factors triggering landslide occurrence on the Zemun loess plateau, Belgrade area, Serbia. Environ. Earth Sci. 2018, 77, 1–15.

Serbia NAP (2023), p. 28.

Serbia NAP (2023), P. 52.

World Bank. (2024). Western Balkan Economies Need to Strengthen Climate Resilience. https://www.worldbank.org/en/news/press-release/2024/03/06/western-balkan-economies-need-to-strengthen-climate-resilience

FAO. (2021). Climate-Smart Agriculture in the Western Balkans. UN Women. (2020). Gender and Climate Change in the Western Balkans.

World Bank. (2022). Country Climate and Development Reports: Western Balkans.

World Bank. (2024). Western Balkan Economies Need to Strengthen Climate Resilience. Press Release.

World Bank. (2019). Breaking the cycle of Roma exclusion in the Western Balkans. Retrieved from https://www.worldbank.org

UNDP, World Bank, & European Commission. (2017). Regional Roma Survey. Retrieved from https://www.worldbank.org

European Union Agency for Fundamental Rights. (2014). Discrimination against and living conditions of Roma women in 11 EU Member States: Roma survey – Data in focus. Publications Office of the European Union. https://fra.europa.eu/sites/default/files/fra_uploads/fra-2014-roma-survey-dif-women-2_en.pdf

Minority Rights Group International. (2024). Aromanians in Albania. https://minorityrights.org/communities/aromanians-in-albania/

Council of Europe. (2024). Tackling the backlash against human rights. Retrieved from https://www.coe.int/en/web/inclusion-and-antidiscrimination/-/tackling-the-backlash-against-human-rights

UNDP Kosovo. 'Inclusive and Just Pathway to 2030.

International Labour Organization. 'Informal Employment in the Western Balkans.' https://www.ilo.org/global/about-the-ilo/newsroom/news/WCMS_834485/lang--en/index.htm

World Bank. 'Western Balkans Labor Market Trends.' https://www.worldbank.org/en/news/feature/2022/04/12/western-balkans-labor-market-trends-2022

World Bank. (2022). Climate Risk Profile: Western Balkans. Washington, DC.

World Bank. (2022). Climate Risk Profile: Western Balkans. Washington, DC.

Regional Cooperation Council. (2023). Western Balkans Climate Resilience Assessment. Sarajevo.

Regional Cooperation Council. (2023). Western Balkans Climate Resilience Assessment. Sarajevo

European Commission. (2024). European Innovation Scoreboard 2024. Publications Office of the European Union. Retrieved from https://research-and-innovation.ec.europa.eu/statistics/performance-indicators/european-innovation-scoreboard_en

”To counter the growing risks linked to climate change, WB6 [Western Balkans 6] countries will need to consider large investments in adaptation—investments that will come with significant benefits. An analysis of an initial, comprehensive multi-sectoral adaptation investment package was completed [by the World Bank team] based on data gathered from local documents, literature, and expert knowledge. The undiscounted costs (expressed in 2020 US$) of proposed policy actions and investments for an initial adaptation package following this approach in the six Western Balkan countries include, US$6.0 billion (Albania), US$6.8 billion (Bosnia and Herzegovina), US$2.8 billion (Kosovo), US$5.7 billion (Montenegro), US$6.4 billion (North Macedonia), and US$9.5 billion (Serbia). Multiple sources of information were used to estimate the needs of each country. The total for the region comes to $37.2 billion (in 2020 US$) undiscounted.”

Source: World Bank. (2024). Western Balkans 6 Country Climate and Development Report (CCDR). Available at: https://www.worldbank.org/en/region/eca/publication/western-balkans-6-ccdr.

Note: estimates for each country’s “percent of GDP per year until 2050” are drawn from the individual country reports of the CCDR, available at the same link.

UNDP. (2023). Why the Western Balkans Are Choosing Decarbonization. https://climatepromise.undp.org/news-and-stories/why-western-balkans-are-choosing-decarbonization-serbia-bosnia-and-herzegovina

United Nations Development Programme. (2023). Immediate action is needed to step up climate adaptation in Eastern Europe and Central Asia. https://www.undp.org/press-releases/immediate-action-needed-step-climate-adaptation-eastern-europe-and-central-asia

World Bank. (2024). Western Balkans 6 Country Climate and Development Report (CCDR). Available at: https://www.worldbank.org/en/region/eca/publication/western-balkans-6-ccdr. Note: estimates for each country’s required Net Zero investment and its estimate of “percent of GDP per year by 2050” are drawn from the individual country reports of the CCDR, available at the same link.

World Health Organization, 'Air pollution and climate change', WHO, 2021

Global Commission on Adaptation, 'Adapt Now: A Global Call for Leadership on Climate Resilience', 2019

Climate Policy Initiative. (2023). Global Landscape of Climate Finance 2023. Retrieved from https://www.climatepolicyinitiative.org/publication/global-landscape-of-climate-finance-2023/

OECD/UNCDF (2020; p.112), Blended Finance in the Least Developed Countries 2020: Supporting a Resilient COVID-19 Recovery, OECD Publishing, Paris, https://doi.org/10.1787/57620d04-en.

The Western Balkans' heavy reliance on coal-based energy necessitates integrating adaptation efforts with energy transition and decarbonization. While maintaining focus on adaptation finance, interventions should leverage co-benefits that support green skills development, alternative livelihoods, and local innovation capacity. This approach ensures just transition pathways for coal-dependent communities, providing workers and families with green technology training and livelihood alternatives essential for regional socio-economic stability during the shift toward sustainable resilience.

Similar to solutions as categorized under:  https://www.adaptation-fund.org/wp-content/uploads/2020/10/AFB.PPRC_.26.b.17-Options-for-further-defining-innovation-in-adaptation-1.pdf

https://climate.ec.europa.eu/climate-change/consequences-climate-change_en

World Bank (2024) Reshaping Cities: Readying cities in the Western Balkan for a changing climate. https://openknowledge.worldbank.org/entities/publication/2919885d-84a9-40e6-ab2a-aab21a5c1fcf

UNDRR (2025) Global Assessment Report (GAR) on Disaster Risk Reduction.

Barendrecht, M. H. et al. (2024). Exploring drought-to-flood interactions and dynamics: A global case review. WIREs Water, 11(4), e1726. https://doi.org/10.1002/wat2.1726

Under UNDP-AFCIA, 44 grantees received a first round of funding between 60,000 USD and 125,000 USD. Out of those 44, 36 received a second round of funding of 80,000 to 110,000 USD for scaling purposes. Please note that the published factsheets only contain the results of the first round of funding for the 44 grantees. In October 2025, the UNDP-AFCIA team will be updating all factsheets to reflect the final impact and scaling results considering the second round of funding. The revised versions will be made available online by the end of 2025.

Building on UNDP’s extensive experience in supporting local CSOs in their crowdfunding efforts, including under the IsDB supported Tadamon Crowdfunding Academy, https://tadamon.community/cfa. Tadamon Crowdfunding Academy was also successfully applied in the UNDP-AFCIA programme with evidence of successful crowdfunding campaigns.

https://unfccc.int/sites/default/files/resource/FNC%20BiH_ENG%20fin.pdf

https://unfccc.int/ttclear/TNA/MKD-TNA-TNA_2004.pdf

https://www.gov.me/dokumenta/caefb6fa-762c-4e3b-9b11-7f15a6944254

World Bank (2024). Western Balkans 6 Country Climate and Development Report (CCDR).

UNDP (2018). Climate Change Adaptation in Europe and Central Asia: Adapting to a Changing Climate for Resilient Development

https://www.climatepolicyinitiative.org/publication/global-landscape-of-climate-finance-2024/

OECD/UNCDF (2020; p.112), Blended Finance in the Least Developed Countries 2020: Supporting a Resilient COVID-19 Recovery, OECD Publishing, Paris, https://doi.org/10.1787/57620d04-en.

These estimates are indicative and will be refined during implementation based on the actual grant size, geographic coverage, and nature of supported innovations. Project will use a robust monitoring and evaluation (M&E) framework to track the actual reach and impact, disaggregated by gender and vulnerability status.

- 139 Each Party shall designate and communicate to the secretariat the authority that will endorse on behalf of the national government the projects and programmes proposed by the implementing entities.