ADAPTATION FUND BOARD SECRETARIAT TECHNICAL REVIEW

OF PROJECT/PROGRAMME PROPOSAL

Project/Programme Category:

_________________________________________________________________________________________________________

Countries/Region:	Cote d’ Ivoire and Ghana /Africa

Project Title: Improved Resilience of Coastal Communities in Cote d’ Ivoire and Ghana

Countries: Cote d’ Ivoire and Ghana

Thematic Focal Area: Disaster Risk Reduction and Early Warning Systems

Implementing Entity: United Nations Human Settlements Programme (UN-Habitat)

Executing Entities: Government of Ghana: Leading Ministry of Local Government and Rural Development

Supporting Ministry of Environment, Science, Technology and Innovation (MESTI); and Local planning departments

Government of Cote d’Ivoire: Leading Ministry of Urban Sanitation, Environment and Sustainable Development.

Supporting Ministry of Construction, Housing, Sanitation and Urban Planning, and Local planning departments

AF Project ID:	AFR/MIE/DRR/2017/1

IE Project ID:			            	Requested Financing from Adaptation Fund (US Dollars): USD 14,000,000

Reviewer and contact person: Saliha Dobardzic				Co-reviewer(s): Dirk Lamberts

IE Contact Person: 	Javier Torner

| Review Criteria | Questions | Comments on May 3, 2018 | UN-Habitat response 14 May, 2018 |
| --- | --- | --- | --- |
| Country Eligibility | - Are all of the participating countries party to the Kyoto Protocol? | Yes. Ghana and Ivory Coast are parties to the Kyoto protocol |  |
|  | - Are all of the participating countries developing countries particularly vulnerable to the adverse effects of climate change? | Yes. Ghana and Cote d’ Ivoire are vulnerable to coastal erosion, a projected one-meter rise in sea level by the end of the century. Furthermore, climate change impacts in the two countries are combined with unsustainable land and water management. This pressure on coastal communities is combined with severe forms of anthropogenic pollution from economic activities in settlements, especially in harbour areas, lagoons and ‘urban coastlines.’ |  |
| Project Eligibility | - Has the designated government authority for the Adaptation Fund endorsed the project/programme? | Yes. Endorsement letters by the designated authorities of Ghana (April 4, 2018) and Cote d’Ivoire (April 9, 2018) have been submitted. |  |
|  | - Does the regional project / programme support concrete adaptation actions to assist the participating countries in addressing the adverse effects of climate change and build in climate resilience, and do so providing added value through the regional approach, compared to implementing similar activities in each country individually? | Concrete adaptation interventions have been included in component 3 and 4. The project proposes the following solutions to climate change adaptation by testing and promoting low-cost alternative solutions and innovative techniques (i.e. building with nature) to protect the coast (i.e. reduce the impacts of climate change and erosion) and enhance community level income generation, which can be replicated in West Africa. Th “transformative interventions” include: - Sand bypassing: Dredging sediment from areas with surplus due to changes in erosion dynamics - Sand bypassing: Beach nourishment and foreshore nourishment (e.g. sand motor from dredging activities) - Green belt coastal buffer zone The “catalytic interventions” (i.e. at community level) include: - Introduce crops that are suited for a salty environment - Introduce aquaculture to adapt to current erosion dynamics (eg. Shrimp farm, clams or the other type of fish) - Replant and monitor forests and mangroves - Artificial barrier inland with natural elements (eg. Dune/barrier nourishment) - Planting of vegetation in existing dunes to prevent erosion - Set up early warning systems and temporary flood defenses, such as sand bags Regional rationale – This is quite clear based on the transboundary character of the existing challenges related to coastal erosion, sea level rise and pressures on coastal communities. Through a regional rationale, the transboundary aspects of the problem, namely coastal erosion, can be addressed through a coordinated approach. The project addresses the hazards causing inter-related negative impacts on the coast, including to lagoons located close to the sea. There is an intention to provide clarity on specific interventions, matched with community priorities, feasibility and Environmental and Social impacts and risks under these components at full proposal stage. At full proposal stage, the range of interventions identified with the support of technical experts should be specified. The potential environmental and social impacts and risks should be identified, based on the expert analysis combined with outcomes of the initial community consultations. CR 1 | CR 1: At the full project proposal development phase, UN-Habitat will detail each of the selected interventions and specify the environmental and social risks and impacts.This exercise is planned to take place in fall 2018, and will be supported by consultations with the local communities, stakeholders and the government, and will involve technical specialists. This assessment will also allow interventions to be prioritised. The expert analysis will be undertaken by the pertinent environmental assessment authority to ensure alignment and compliance with national regulations. |
|  | - Does the project / programme provide economic, social and environmental benefits, particularly to vulnerable communities, including gender considerations, while avoiding or mitigating negative impacts, in compliance with the Environmental and Social Policy of the Fund? | Not clear. At this time, the concrete actions are yet undecided upon, which makes it difficult to precisely evaluate economic, social, and environmental benefits. Furthermore, it is unclear what are the potential negative impacts of the potential activities proposed, as mentioned above. At full proposal stage, the specific interventions’ economic, social, and environmental benefits, and specific information on Environmental and Social Policy compliance should be provided. CR 2 At the full proposal phase, the framework for selecting and monitoring interventions should be developed and interventions responding to different needs and situations, matching community needs and priorities with innovative but feasible interventions. CR 3 At full proposal stage, please provide a clear description of the consultation techniques used specifically for each target group of stakeholders and a description of the key consultation findings for each group, including how any issues raised were addressed in the project designs. CR 4 | CR 2: At the project proposal development phase proposal, the interventions will be further specified and selected, including completion of a full social and environmental assessment. UN-Habitat will deduct the benefits resulting from the interventions. This analysis will be developed in compliance with the Fund’s Environmental and Social Policy and Gender Policy CR 3: At the project proposal development phase proposal, UN-Habitat will apply the in-house framework and methodology that has been extensively used in previous projects. This framework involves close community participation, and it has already been used by local teams in Ghana and Cote d’Ivoire to select the communities. This framework will include among others: impacted population, economic feasibility, environmental and social impacts, long-term sustainability, community needs, income generating capacity and alignment with national priorities. CR 4: At the project proposal development phase proposal, UN-Habitat will apply different tested consultative tools and methods such as planning studios, technical and consultative trainings, public exposition, plenary sessions and focus group discussions. These modalities have been extensively put into practice previously and they will be adjusted to the specific context of this project. A clear description of the used techniques for each target group will be provided. |
|  | - Is the project / programme cost-effective and does the regional approach support cost-effectiveness? | Not clear, as most interventions are not yet specified. A cost-effectiveness rationale has been presented for each of the project components, but it is not possible to assess realistically assess the cost-effectiveness of interventions that have not been specified. Refer to CR 2-4 At full proposal stage, please complete and present the cost-effectiveness assessments of the remaining proposed “relatively low-cost” interventions by comparing with alternative intervention options by considering the exact environmental and social circumstances. CR 5 | CR 5: At the project proposal development phase proposal, UN-Habitat will complete the cost-effectiveness analysis of the selected interventions, and screening of the environmental and social impacts and risks. This aims at understanding the effectiveness and efficiency of the selected interventions in relation to its costs and impacts, in order to justify their suitability. |
|  | - Is the project / programme consistent with national or sub-national sustainable development strategies, national or sub-national development plans, poverty reduction strategies, national communications and adaptation programs of action and other relevant instruments? If applicable, it is also possible to refer to regional plans and strategies where they exist. | Yes, as specified on pages 71-73 |  |
|  | - Does the project / programme meet the relevant national technical standards, where applicable, in compliance with the Environmental and Social Policy of the Fund? | Yes. The proposal identifies provisionally the key national technical standards that are relevant to the project. Full proposal stage - The full proposal will need to spell out how compliance with the national technical standards in both countries is achieved (p.73- 78), simultaneously in compliance with the Environmental and Social Policy of the Fund. CR 6 | CR 6: The fully-developed project proposal will demonstrate the compliance with the technical standards of Ghana and Cote D’Ivoire and the compliance with the Environmental and Social Policy and Gender Policy of the Adaptation Fund. Once the interventions have been selected, UN-Habitat will establish a working group with the pertinent national institutions in order to ensure compliance and alignment with national and local standards taking into account the ESP. These working teams have already been identified, and a first working meeting is foreseen endof Summer 2018, with MoUs to be signed a COP-24 in December |
|  | - Is there duplication of project / programme with other funding sources? | The table regarding non-duplication with other funding sources has been provided with relevant programmes/projects. The non-duplication is highlighted here as well as the compatibilities/synergies with this project and lessons to be learnt and applied in this proposal. (Section G) For the fully developed proposal, the linkages and synergies with all relevant potentially overlapping projects / programmes need to be clearly outlined, including areas of overlap and complementarity, drawing lessons from the earlier initiatives during the project design, learning from their problems/mistakes, and establishing a framework for coordination during implementation. CR 7 | CR 7: UN-Habitat has already conducted an exercise to identify all relevant projects with overlapping and complementary activities. In the full proposal development phase, this exercise will continue through meetings and workshops with the relevant national designated authorities and oversigh bodies, the programme and project managers and technical teams in order to work together, link projects and for knowledge transfer and sharing. This has already started for programmes such WACA and UN-Habitat is positive that at that time the working group on the National Adaptation Plan process in at least Cote d’Ivoire will help guide this exercise as well. |
|  | - Does the project / programme have a learning and knowledge management component to capture and feedback lessons? | Yes. A learning component has been included as part Component 5. |  |
|  | - Has a consultative process taken place, and has it involved all key stakeholders, and vulnerable groups, including gender considerations? | Yes, sufficiently for concept stage. The full proposal should include further information on the consultations held in compliance with the ESP and GP during full project development. CR 8 The full proposal will require further identification of marginalized and vulnerable groups, as well as a further gender assessment. CR 9 | CR 8: In the fully-developed project proposal, UN-Habitat will provide detailed reports on the consultative process, participation and outcomes. This will be undertaken in full compliance with with the ESP and the GP. CR 9: In the fully-developed project proposal, UN-Habitat will provide identify all relevant marginalized and vulnerable groups, as well as provide a further and complete gender assessment. The local project team has recently been complimented by a social expert, who will ensure full engagement with the communities, placing specific emphasis and efforts on inclusion and gender equality. |
|  | - Is the requested financing justified on the basis of full cost of adaptation reasoning? | Yes, adequate information is provided for the concept stage |  |
|  | - Is the project / program aligned with AF’s results framework? | Yes. The proposed components and project outcomes align with AF outcomes. |  |
|  | - Has the sustainability of the project/programme outcomes been taken into account when designing the project? | Not sufficiently addressed. Sustainability can only be assessed once interventions have been specified. At full proposal stage, when interventions have been clearly specified, the proposal must demonstrate sustainability, including financial sustainability. At full proposal stage, (financial) sustainability should be analysed of each intervention and a specific business model be developed for the prioritized proposals, based on former experience, experts and on ground analysis and through consultations. CR 10 | CR 10: UN-Habitat has already started discussions on specific business models for the interventions, i.e. with the help of competent private sector partners. In the fully-developed project proposal, this will be developed in detail aligned with the framework for the selection of interventions, the financial feasibility and sustainability study, and the opportunities for revenue generation. |
|  | - Does the project / programme provide an overview of environmental and social impacts / risks identified? | Consistent with the comments made above, all activities will be fully developed/designed during the full proposal preparation. This will allow adequate and comprehensive risks identification before submission in line with the ESP. During the full proposal development phase, interventions selected should be detailed and UN-Habitat by provide evidence that screening of all proposed interventions and assessments of possible impacts was completed. CR 11 | CR 11: In the fully-developed project proposal, once interventions have been indentified, UN-Habitat will develop a detailed description of the socio-economic and environmental risks screening, impacts and benefits (as per previous comments). This will be provided through evidence and mitigation measures, when necessary will respond to the risks. This will be combined in an ESMP following the ESP guidelines. |
|  | - Does the project promote new and innovative solutions to climate change adaptation, such as new approaches, technologies and mechanisms? | Yes. Additional information on shortlisted innovative solutions / interventions has been provided in table 5, section II.B and annex 3. The project aims for 1) technical innovation (low-cost building with nature solutions), and innovation through an ‘urban lab’ that involves a wide range of stakeholders in assessments, monitoring and implementation. |  |
| Resource Availability | - Is the requested project / programme funding within the funding windows of the pilot programme for regional projects/programmes? | Yes, at USD 14,000,000. A PFG of 100,000 has also been requested. |  |
|  | - Are the administrative costs (Implementing Entity Management Fee and Project/ Programme Execution Costs) at or below 20 per cent of the total project/programme budget? | Yes. Implementing entity fee is 8.5 % of total project/programme budget. Project execution costs are at 9.5% of total project/programme budget. |  |
| Eligibility of IE | - Is the project/programme submitted through an eligible Multilateral or Regional Implementing Entity that has been accredited by the Board? | Yes. UN-habitat is a multilateral implementing entity of the Fund. |  |
| Implementation Arrangements | - Is there adequate arrangement for project / programme management at the regional and national level, including coordination arrangements within countries and among them? Has the potential to partner with national institutions, and when possible, national implementing entities (NIEs), been considered, and included in the management arrangements? | n/a (Not applicable at the concept stage). |  |
|  | - Are there measures for financial and project/programme risk management? | n/a (Not applicable at the concept stage). |  |
|  | - Are there measures in place for the management of for environmental and social risks, in line with the Environmental and Social Policy of the Fund? Proponents are encouraged to refer to the Guidance document for Implementing Entities on compliance with the Adaptation Fund Environmental and Social Policy, for details. | n/a (Not applicable at the concept stage). |  |
|  | - Is a budget on the Implementing Entity Management Fee use included? | n/a (Not applicable at the concept stage). |  |
|  | - Is an explanation and a breakdown of the execution costs included? | n/a (Not applicable at the concept stage). |  |
|  | - Is a detailed budget including budget notes included? | n/a (Not applicable at the concept stage). |  |
|  | - Are arrangements for monitoring and evaluation clearly defined, including budgeted M&E plans and sex-disaggregated data, targets and indicators? | n/a (Not applicable at the concept stage). |  |
|  | - Does the M&E Framework include a break-down of how implementing entity IE fees will be utilized in the supervision of the M&E function? | n/a (Not applicable at the concept stage). |  |
|  | - Does the project/programme’s results framework align with the AF’s results framework? Does it include at least one core outcome indicator from the Fund’s results framework? | n/a (Not applicable at the concept stage). |  |
|  | - Is a disbursement schedule with time-bound milestones included? | n/a (Not applicable at the concept stage). |  |

| Technical Summary | The following clarifying requests (CRs) are expected to be reflected in the fully-developed project proposal: - The range of interventions identified with the support of technical experts should be specified. The potential environmental and social impacts and risks should be identified, based on the expert analysis combined with outcomes of the initial community consultations. CR 1 - The specific interventions’ economic, social, and environmental benefits, and specific information on Environmental and Social Policy compliance should be provided. CR 2 - The framework for selecting and monitoring interventions should be developed and interventions responding to different needs and situations, matching community needs and priorities with innovative but feasible interventions. CR 3 - A clear description of the consultation techniques used specifically for each target group of stakeholders and a description of the key consultation findings for each group, including how any issues raised were addressed in the project designs, should be provided. CR 4 - The cost-effectiveness assessments of the remaining proposed “relatively low-cost” interventions by comparing with alternative intervention options by considering the exact environmental and social circumstances should be completed. CR 5 - The compliance with the national technical standards in both countries (p.73- 78), also in compliance with the Environmental and Social Policy of the Fund, should be elaborated upon. CR 6 - The linkages and synergies with all relevant potentially overlapping projects / programmes need to be clearly outlined, including areas of overlap and complementarity, drawing lessons from the earlier initiatives during the project design, learning from their problems/mistakes, and establishing a framework for coordination during implementation. CR 7 - Further information on the consultations held in compliance with the ESP and GP during full project development should be included. CR 8 - Further identification of marginalized and vulnerable groups, as well as a further gender assessment will be required. CR 9 - Sustainability (financial) should be analysed of each intervention and a specific business model be developed for the prioritized proposals, based on former experience, experts and on ground analysis and through consultations. CR 10 - Interventions selected should be detailed and UN-Habitat should provide evidence that screening of all proposed interventions and assessments of possible impacts was completed, along with the description for the approach used. CR 11 |
| --- | --- |
| Date: | May 7, 2018 |