## Overview
Project Performance Report (PPR)
| Period of Report (Dates) | June 2018 to June 2019
| Project Title: | Adapting to Climate Change in Lake Victoria Basin
| Project Summary: | Climate change in the Lake Victoria Basin (LVB) – a water catchment in Burundi, Kenya, Rwanda, Tanzania and Uganda – has resulted in increased mean annual temperatures and increased variability in rainfall patterns. Climate change projections predict that mean annual temperatures will continue to increase and that variability in rainfall patterns will be exacerbated. Projected climate change will result in several negative effects within the LVB, including a decrease in water quality and availability for a number of uses, including inter alia: i) domestic; ii) agricultural; iii) industrial and commercial; and iv) cultural. The negative effects of climate change disproportionately affect marginalised and rural communities within the LVB by reducing the productivity of agriculture and wetlands and the abundance of fish in Lake Victoria and its tributaries. In addition, the projected effects of climate change are likely to negatively impact economic sectors within the LVB that depend on water resources, such as hydropower facilities and commercial fisheries. Therefore, to reduce the impact of climate change on local communities and water dependent economic sectors within the LVB, the Project will increase climate resilience in the LVB at both a regional and local level by implementing both regional and community-based climate change adaptation interventions. The Project objective will be achieved through five outcomes, namely: i) strengthened institutional and technical capacity to integrate climate resilience into transboundary water catchment management; ii) improved delivery of accurate and timely climate information to regional and national policy makers, technical officers and local communities; iii) climate change adaptation technologies, including water harvesting techniques, climate-smart agriculture and Ecosystem based Adaptation (EbA), transferred to communities to reduce their vulnerability to climate change; iv) regional resilience to climate change promoted through innovative, community based projects; and v) improved knowledge management frameworks for the collection and maintenance of regional knowledge in transboundary water catchment management and climate change adaptation practices.
|  |  | Countries | Project Type: |  | GEF Focal Area: | GEF 4 Focal Areas | GEF 2 / 3 Operational Programme: | Overall Rating of the project in the evaluation by the project evaluator: | GEF-4 Focal Area Strategic Program: | GEF-3 Focal Area Strategic Program:
| Database Number: | UNEP:S1-32AFB-00009 / SB-008892 AF ID: AFR/MIE/Water/2015/1 | Afghanistan | FP | Yes | Biodiversity | 1 | 1 | U | BD-SP1-PA Financing | 1: Arid & semi-arid ecosystems
Implementing Entity (IE) [name]: |  | United Nations Environment Programme (UNEP) | Albania | MSP | No | Climate Change Adaptation | 2 | 2 | S | BD-SP2-Marine PA | 2: Coastal, marine & freshwater ecosystems
| Type of IE: | Multilateral Implementing Entity (MIE) | Algeria | EA |  | Climate Change Mitigation | 3 | 3 | MU | BD-SP3-PA Networks | 3: Forest ecosystems
| Country(ies): | Burundi, Kenya, Rwanda, Tanzania and Uganda | Angola |  |  | International Waters | 5 | 5 | Good | BD-SP5-Markets | 13: Conservation and Sustainable Use of Biological Diversity Important to Agriculture
Relevant Geographic Points (i.e. cities, villages, bodies of water): |  | The LVB is contained within the southern section of the Nile River Basin (NRB), between the Eastern and Western Rift Valleys. The LVB catchment area is ~195,000 km2 and contains Lake Victoria, the world’s second largest freshwater lake, which has a surface area of ~69,000 km2, a mean depth of ~40 m and contains ~2,750 km3 of water . Lake Victoria extends into three countries, namely Kenya, Tanzania and Uganda, while the LVB extends further to include Burundi and Rwanda | Argentina |  |  | Multiple Focal Area |  |  |  | BD-SP7-Invasive Alien Species(IAS) | 6: Promoting the adoption of renewable energy by removing barriers and reducing implementation costs
[8 empty] | CC-SP2- Industrial EE | 8: Waterbody based operational program
| Project Milestones | [6 empty] | CC-SP3-RE,CC-SP4-Biomass | 9: Integrated Land and Water multiple focal area
| Milestone |  | Bahamas | [6 empty] | CC-SP5-Transport | 10: Contaminants based operational program
AFB Approval Date: |  | July, 2017
IE-AFB Agreement Signature Date: |  | 2017-10-01 | [6 empty] | CC-SP6-LULUCF | 12: Integrated Ecosystem Management
Start of Project/Programme: |  | 28th June 2018 | [6 empty] | Cross cutting capacity building | 14: Persistent Organic Pollutants
Mid-term Review Date (if planned):
| Terminal Evaluation Date: | 27th June 2021
|  | List documents/ reports/ brochures / articles that have been prepared about the project. | Cyprus
|  | 1. Monitoring and Evaluation Framework for the ACC-LVB Project; 2. Environmental and Social management Plan (ESMP) for the regional adapting to climate change in Lake Victoria Basin project; 3. Revised work plan and budget; 4. Inception workshop report; 5. National Coordination team capacity building reports; 6. Regional criterial to guide the selection of intervention site; 7. Reports of 1st and 2nd Regional Policy Steering Committee (RPSC); 8. Report of workshop held for regional and national institutions which provide climate information to regional and national policymakers, technical officers and local communities; 9. Terms of Reference for Project Manager, Financial Assistant and Chief Technical advisor to undertake the coordination of the daily project activities; 10. Terms of Reference for Ecosystem based Adaptation, Climate modeling, Water Catchment Management, baseline data collection and communication consultancies. 11. Expenditure Reports for Q1 and Q2 | Czech Republic
List the Website address (URL) of project. |  |  | Democratic People's Republic of Korea
|  | https://www.unenvironment.org/explore-topics/climate-change/what-we-do/climate-adaptation/ecosystem-based-adaptation/ecosystem-7 | Democratic Republic of the Congo
Denmark
| Project contacts: |  | Djibouti
National Project Manager/Coordinator |  |  | Dominica
| Name: | Dr. Masinde K.Bwire | Dominican Republic
| Email: | bwirejoseph@gmail.com; Bwire@lvbcom.org | Ecuador
| Date: |  | Egypt
| Government DA |  | El Salvador
| Name: |  | Equatorial Guinea
| Email: |  | Eritrea
| Date: |  | Estonia
| Implementing Entity |  | Ethiopia
| Name: | United Nations Environment Programme (UNEP) | Fiji
| Email: | essey.daniel@un.org | Finland
| Date: |  | France
| Executing Agency |  | Gambia
| Name: | Lake Victoria Basin Commission | Georgia
| Email: | mngube@lvbcom.org | Germany
| Date: |  | Ghana
| Executing Agency |  | Greece
| Name: | Dr. Masinde K.Bwire | Grenada
| Email: | bwirejoseph@gmail.com; Bwire@lvbcom.org | Guatemala
| Date: |  | Guinea
| Executing Agency |  | Guinea Bissau
| Name: |  | Guyana
| Email: |  | Haiti
| Date: |  | Honduras
Hungary
Iceland
India
Indonesia
Iran (Islamic Republic of)
Iraq
Ireland
Israel
Italy
Jamaica
Japan
Jordan
Kazakhstan
Kenya
Kiribati
Kuwait
Kyrgyzstan
Lao People’s Democratic Republic
Latvia
Lebanon
Lesotho
Liberia
Libyan Arab Jamahiriya
Liechtenstein
Lithuania
Luxembourg
Madagascar
Malawi
Malaysia
Maldives
Mali
Malta
Marshall Islands
Mauritania
Mauritius
Mexico
Micronesia, Federated States of
Monaco
Mongolia
Montenegro
Morocco
Mozambique
Myanmar
Namibia
Nauru
Nepal
Netherlands
New Zealand
Nicaragua
Niger
Nigeria
Norway
Oman
Pakistan
Palau
Panama
Papua New Guinea
Paraguay
Peru
Philippines
Poland
Portugal
Qatar
Republic of Korea
Republic of Moldova
Romania
Russian Federation
Rwanda
Saint Kitts and Nevis
Saint Lucia
Saint Vincent and the Grenadines
Samoa
San Marino
Sao Tome and Principe
Saudi Arabia
Senegal
Serbia
Seychelles
Sierra Leone
Singapore
Slovakia
Slovenia
Solomon Islands
Somalia
South Africa
Spain
Sri Lanka
Sudan
Suriname
Swaziland
Sweden
Switzerland
Syrian Arab Republic
Tajikistan
Thailand
The former Yugoslav Republic of Macedonia
Timor-Leste
Togo
Tonga
Trinidad and Tobago
Tunisia
Turkey
Turkmenistan
Tuvalu
Uganda
Ukraine
United Arab Emirates
United Kingdom of Great Britain and Northern Ireland
United Republic of Tanzania
United States of America
Uruguay
Uzbekistan
Vanuatu
Venezuela, Bolivarian Republic of
Viet Nam
Yemen
Zambia
Zimbabwe

## FinancialData
Financial information: cumulative from project start to [30th June 2019]
DISBURSEMENT OF AF GRANT FUNDS
How much of the total AF grant as noted in Project Document plus any project preparation grant has been spent to date?
Estimated cumulative total disbursement as of [30th June 2019] | 674201
Add any comments on AF Grant Funds. (word limit=200)
INVESTMENT INCOME | 29983.47
Amount of annual investment income generated from the Adaptation Fund’s grant
EXPENDITURE DATA
List outputs and corresponding amount spent for the current reporting period | ITEM / ACTIVITY / ACTION | AMOUNT
OUTPUTS | ITEM / ACTIVITY / ACTION | AMOUNT
Output 1.1: Strengthened institutional coordination mechanism to sustain a climate resilient approach to transboundary water catchment management.
| Regional Platform | 4900
Output 1.2. Training provided to government ministries and agencies, civil society and the private sector to address climate change related challenges in transboundary water catchment management | Monitoring | 19450
| National Training workshops | 69137
Output 2.1. Tailored climate information packages to guide both operational and long term strategic planning. | Regional Training Workshops | 39750
| Regional Meetings | 28347
| Regional Research Workshops | 24626
Output 2.2. Climate information dissemination mechanism strengthened to deliver climate information to national policymakers, LVBC technical officers and local communities. | Regional workshops, Materials & goods, Travel, Communication costs & Community information sharing | 0
Output 3.1. Project intervention sites and appropriate adaptation technologies identified. | Sub-Contracts-MoU | 332400
| Sub-Contracts-Commercial Purpose | 67114
3.2. Extension officers and local communities trained on climate change adaptation technologies including water conservation practices, climate-smart agricultural techniques and EbA activities. | Adaptation training experts, National community training workshops, Demonstration sites & Exchange visits | 0
3.3. Climate change adaptation technologies demonstrated at selected project intervention sites. | Climate change adaptation technologies – Burundi, Kenya, Tanzania, Rwanda & Uganda | 0
4.1. Small-scale projects funded to promote innovative approaches to climate change adaptation. | Community Workshops & Training | 0
Output 5.1. A forum established to promote the collaboration of research initiatives across the Lake Victoria Basin, with a focus on adaptation to climate change. | Research Forum | 965
Output 5.2. Awareness-raising campaign to share lessons learned with stakeholders, ranging from policy and decision makers to vulnerable communities in the Lake Victoria Basin. | Communication Materials | 4512.43
6. Project/Programme Execution cost (9.5%) | Office Supplies | 1730
| Project steering committee meetings | 63217.22
| Personnel | 4000
| Consultants Recruitment | 6825
| Telephone Printing and Internet | 7227.29
| TOTAL | 674200.94
PLANNED EXPENDITURE SCHEDULE
List outputs planned and corresponding projected cost for the upcoming reporting period | ITEM / ACTIVITY / ACTION | PROJECTED COST | Est. Completion Date
Output 1.1: Strengthened institutional coordination mechanism to sustain a climate resilient approach to transboundary water catchment management. | 1.1.2. To support 2 meetings of the CCTWG to plan and implement climate-resilient approaches to transboundary water catchment management. | 80000 | By February 2020
| 1.1.3. To undertake regional capacity building exercises in water catchment management in the context of climate change in organisations such as inter alia: i) LVBC; ii) CCTWG; iii) LVBC project Unit; and iv) ICPAC, FEWSNET, RCMRD and DHI | 10000 | By January 2020
Output 1.2. Training provided to government ministries and agencies, civil society and the private sector to address climate change related challenges in transboundary water catchment management | 1.2.2. Provide training on climate change, climate change adaptation and water management at the regional level to national government representatives from the climate change, environment, and water and local government sectors in each of the five Partner States. | 45000 | By January 2020
| 1.2.3. Provide training on climate change, climate change adaptation and water management at national workshops which will include 50 civil society, non-governmental organisation (NGOs) and the private sector. | 45000 | By January 2020
Output 2.1. Tailored climate information packages to guide both operational and long term strategic planning | 2.1.1. To train 25 representatives from the national meteorological agencies in each of the five Partner States on downscaling regional climate information on the national level. | 60000 | By September 2019
| 2.1.2. To develop 10 national tailored climate information packages for: i) policy and decision-makers; and ii) local communities. | 20000 | By September 2019
Output 2.2. Climate information dissemination mechanism strengthened to deliver climate information to national policymakers, LVBC technical officers and local communities. | 2.2.1. To identify 2 cost-effective means of strengthening existing climate information dissemination mechanisms, including ICPAC, FEWSNET, RCMRD and DHI. | 20000 | By September 2019
| 2.2.2. To strengthen existing climate information dissemination mechanisms including the LVBC information hub to develop an LVB specific platform for climate information. | 20000 | By February 2020
| 2.2.3. To deliver climate information for long term strategic planning to policy and decision makers in regional organisations, as well as technical staff in national ministries, within the LVB. | 10000 | By February 2020
| 2.2.4. To pilot innovative information-sharing mechanisms such as the provision of climate information through mobile networks to deliver climate information to communities in a locally relevant and accessible format. | 40000 | By March 2020
Output 3.1. Project intervention sites and appropriate adaptation technologies identified | 3.1.1. To apply findings/lessons learned from past and current LVBC programmes – Lake Victoria Region Water and Sanitation Initiative II (LVWATSAN), Lake Victoria Environmental Management Programme Phase II (LVEMP II) and the PREPARED Vulnerability Assessment (VIA) – to identify potential project intervention sites | 10000 | By December 2019
| 3.1.2. Conduct Climate risks assessment/stock take of adaptation interventions detailed in existing national strategies and action plans, recommendations from other regional projects and findings of scientific research in the LVB to identify appropriate adaptation technologies to be implemented regionally. | 15000 | By March 2020
Output 3.2. Extension officers and local communities trained on climate change adaptation technologies including water conservation practices, climate-smart agricultural techniques and EbA activities. | 3.2.1. To train 50 extension officers and 250 local community members at selected intervention sites on climate change adaptation technologies, including water conservation practices, climate-smart agricultural techniques and EbA activities. | 40000 | By January 2020
| 3.2.2. Establish demonstration sites to 250 households for climate change adaptation technologies at selected intervention sites | 10000 | By December 2019
| 3.2.3. Organise 5 information exchange visits where people from communities surrounding the project intervention sites are exposed to the climate change adaptation technologies | 25000 | By February 2020
Output 3.3. Climate change adaptation technologies demonstrated at selected project intervention sites | 3.3.1 to 3.3.5. Implement climate change adaptation technologies including water conservation practices, climate-smart agricultural techniques and EbA at the selected intervention sites in Burundi, Kenya, Rwanda, Tanzania and Uganda. | 500000 | By March 2020
Output 4.1. Small scale projects funded to promote innovative approaches to climate change adaptation. | 4.1.1. To host workshops with communities at intervention sites selected in Component 3 to identify specific climate change impacts and appropriate community-based adaptation interventions. | 5000 | By December 2019
| 4.1.2. To provide training to 1000 local communities or relevant local-level government sectors or NGOs on how to develop a project proposal and the necessary financial, administrative and monitoring procedures for a small-scale project. | 10000 | By January 2020
| 4.1.3.To review project proposals and select alt least 20 successful project proponents. | 5000 | By February 2020
| 4.1.4 to 4.1.8. Provide small grants to project proponents to implement small-scale, community-based adaptation projects in Burundi, Kenya, Rwanda, Tanzania and Uganda. | 500000 | By March 2020
| 4.1.9. To undertake monitoring and evaluation of small scale projects to provide information for Outcome 5. | 35000 | By December 2019
Output 5.1.A forum established to promote the collaboration of research initiatives across the Lake Victoria Basin, with a focus on adaptation to climate change. | 5.1.1.To hold regional workshops with researchers and technical experts to establish platform on climate change adaptation and water catchment management | 10000 | By April 2020
| 5.1.3.To promote knowledge sharing though the Global Adaptation Network (GAN), Africa Adaptation Knowledge Network (AAKNet) and Africa Adaptation Initiative. | 15000 | By March 2020
Output 5.2. Awareness raising campaign to share lessons learned with stakeholders, ranging from policy- and decision-makers to vulnerable communities in the Lake Victoria Basin. | 5.2.1. To develop a detailed communications strategy building on the communication and outreach strategy prepared by the CCTWG to share lessons learned from the proposed project with relevant national and regional stakeholders through appropriate media. | 20000 | By February 2020
| 5.2.3. To undertake awareness raising campaigns for vulnerable communities to share lessons on water management and climate change adaptation. | 17000 | By February 2020
| 5.2.4.To distribute awareness raising materials translated into local languages where proper – to policy- and decision-makers in national ministries and regional organisations to raise awareness on transboundary water management in the context of climate change and lessons learned from adaptation interventions demonstrated through Component 3 and 4. | 16000 | By April 2020
Project Operational costs at regional level (include paying salaries) | Project Operational costs at regional level (include paying salaries) | 200000 | By June 2020
| TOTAL | 1783000
ACTUAL CO-FINANCING (If the MTR or TE have not been undertaken this reporting period, DO NOT report on actual co-financing.)
How much of the total co-financing as committed in the Project Document has actually been realized? | N/A
Estimated cumulative actual co-financing as verified during Mid-term Review (MTR) or Terminal Evaluation (TE). | 0
Add any comments on actual co-financing in particular any issues related to the realization of in-kind, grant, credits, loans, equity, non-grant instruments and other types of co-financing. (word limit=200) | The co-financing of this project is on the salaries of the 5 National Coordinators; 5 Project Accountants; and to 50 National Coordination team members established in all Countries. This PPR figure shows zero as actual figures not yet collected from Countries. Other co-financing will be labour provided at intervention sites by partner countries. Next PRR will show actual figures contributed by countries.
Note on G61: Fredrick Mngube: is going on

## Risk Assesment
RISK ASSESMENT
IDENTIFIED RISKS
List all Risks identified in project preparation phase and what steps are being taken to mitigate them
Identified Risk | Current Status | Steps Taken to Mitigate Risk
High turnover of staff members in implementing agencies and within different countries may negatively impact on project deliverables. | Low | The Lake Victoria Basin Commission (executing entity of the project) has established strong partnership with government institutions of partner states (Burundi, Kenya, Rwanda, Tanzania and Uganda) with the aim of utilizing the capacities of relevant institutions including non-governmental organizations to support implementation of project activities. This is expected to ensure continuity of the project beyond individual staff and therefore cushion the project against high staff turnover. Among the key government institutions that the project has built partnership with include: National Focal Point ministries responsible for climate change, environment and water resources management; National meteorology directorates; as well as relevant regional institutions dealing with climate including IGAD Climate Prediction and Application Centre (ICPAC), Famine Early Warning Systems Network (FEWSNET) and Regional Centre for Mapping of Resources for Development (RCMRD).
Disagreement amongst stakeholders with regards to demonstration of site selection. | Low | Through a consultative process, selection of intervention sites has been done using an agreed upon list of criteria to ensure that the selection process was transparent and equitable. The selection process was conducted through a thorough participatory approach, with multiple meetings being held between national project coordination teams of each partner state, local authorities in the intervention areas and local communities. This approach helped to alleviate disagreement amongst stakeholders with regard to selection of intervention sites.
Loss of government support may result in lack of prioritisation of Project activities. | Medium | To ensure ownership of the project, the Lake Victoria Basin Sectoral Council of Ministers have established a Regional Policy Steering Committee-RPSC (Permanent Secretaries of responsible ministries) to provide strategic guidance of the project and promote political buy-in for the project. Additionally, project national coordinators have been appointed by their respective focal ministries in each of the partner states in consultation with Lake Victoria Basin Commission (LVBC). The national project coordinators are responsible for the implementation of on-the-ground intervention sites as well as ensuring that governments' maintain their commitments and considers the project as a support to their forestry and agriculture programmes within their respective countries.
Institutional capacities and relationships are not sufficient to provide effective solutions to climate problems that are complex and multi-sectoral. | Low | The project is supporting capacity building initiatives geared towards the development of institutional capacities thus putting in place appropriate institutional framework to effectively provide solutions to complex and multi-sectoral climate related problems. Additionally, the project is working with experts from specialized national and regional institutions that have adequate capacity to support implementation of project activities e.g. national meteorology directorates; focal ministries responsible for climate change, environment and water resources management; IGAD Climate Prediction and Application Centre (ICPAC); Famine Early Warning Systems Network (FEWSNET); and Regional Centre for Mapping of sources for Development (RCMRD) among others.
Capacity constraints of local institutions may limit the ability to undertake the research and interventions. | Low | Through the support of Lake Victoria Basin Commission (Executing Entity) and United Nations Environment Programme (UNEP), a research and technical forum has been established to support collaboration and exchange between local and international research institutes. This will ensure that capacity constraints of local institutions that limit the ability to undertake research and implementation of interventions are addressed. Furthermore, a Chief Technical Advisor, Administration Finance, Project Manager and consultants have been hired to support timely delivery of project outputs.
Priority interventions implemented are not found to be cost-effective. | Low | The selection process of priority adaptation measures to be implemented has been done with cost-effectiveness being one of the core principles guiding the process. Measures have also been put in place to ensure that detailed information regarding cost-effectiveness of implemented adaptation measures is documented, widely disseminated and used to inform future adaptation initiatives in the Lake Victoria Basin. Moreover, adaptation interventions to be implemented have been designed to ensure steady flow of water of good quality at reasonable cost, thus encouraging payment by consumers.
Lack of commitment/buy-in from local communities may result in failure of intervention sites | Low | During the inception phase, an extensive consultations and awareness campaigns have been done in order to inform stakeholders (especially local community) about the project and the benefits to be realized upon successful completion of the project. Measures have also been put in place to ensure community stakeholders are consulted through a bottom-up approach and integrated during the project’s implementation phases.
Critical Risks Affecting Progress (Not identified at project design)
Identify Risks with a 50% or > likelihood of affecting progress of project
Identified Risk | Current Status | Steps Taken to Mitigate Risk
Disagreement in recruitment processes between partner countries and executing agency leading to delays in hiring of project staff/consultants which negatively affects overall project implementation | Medium | Lake Victoria Basin Commission (Executing Entity) in consultation with United Nations Environment Programme (Implementing Entity) established an interim project team composed of Lake Victoria Basin Commission staff to spearhead the inception phase of the project until when the project team was in place. Furthermore, the issue of bureaucratic recruitment process that resulted to delays in hiring of project staff/consultants was presented to the East Africa Community Sectoral Council of Ministers in May 2019 who approved that in order to avoid delays project staff be employed as consultants after a competitive process adhering to UNEP and AF recruitment guidelines
Lengthy administrative process of formalizing partnership (development and signing of Memorandum of Understanding) between Lake Victoria basin Commission (Executing Entity) and Focal Ministries responsible for spearheading the implementation of project activities in respective partner states. | Medium | To fast-track the administrative process of putting in place Memorandum of Understanding between Lake Victoria Basin Commission and institutions responsible for the spearheading implementation of project activities in each partner state, consultative meetings were held that also tasked the national project coordinators to follow up with authorities responsible for approving and signing the MoUs in their respective countries. This contributed immensely to hasten the process of having in place the MoUs.
Disagreement among stakeholders with regard to roles in the Project. | Low | Stakeholder roles which are detailed clearly in the stakeholder involvement plan were discussed and agreed upon during the project's inception workshop that was held 28th June 2018. This has ensured that there is clarity on the roles and responsibilities of key stakeholders such as Lake Victoria Basin Commission (LVBC), United Nations Environment Programme (UNEP), National Executing Entities etc.
Current climate and seasonal variability and/or hazard events result in poor results for the EbA and conservation agriculture activities. | Medium | The project is in the process of recruiting a Climate Change Modeling Expert to develop operational climate model that will downscale regional climate information to the national and local level to ensure availability of accurately and timely climate data and information. This will ensure that current climate and seasonal variability and/or hazards events are taken into account during planning of the Ecosystem-based Adaptation (EbA) and conservation agriculture interventions. Additionally, the project is also recruiting an Adaptation Expert technical guidance on adaptation activities such as: introduction of drought- and flood-resilient species; crop diversification; conservation agriculture; ecosystem-based adaptation among others.
Trees planted by the project are cut down by the communities. | Medium | Measures have been put in place to ensure community involvement and awareness raising is undertaken to avoid this risk once trees have been planted. This measures include use of local communities to manage planted trees.
Some infrastructure put in place by the project, for instance communal dams as water harvest strategy, could lead to conflicts associated with different user access. | Medium | Plans are on course to establish and train community management structures such as village water committees in integrated water resources management and conflict resolutions. This will mitigate the risk of conflicts associated with competition for established water resources infrastructure.
Risk Measures: Were there any risk mitigation measures employed during the current reporting period? If so, were risks reduced? If not, why were these risks not reduced?
Add any comments relevant to risk mitigation (word limit = 500)
Overall the project risk rating is Medium. A number of the identified risks are within the control of the project team and can be mitigated against by timely and effective project management. Other risks are beyond the control of the project and will require the project team to monitor and plan accordingly through adaptive management and by putting in place mitigating measures to reduce the potential consequences. All risks will be regularly assessed and reported on at Regional Policy Steering Committee meetings and at Sectoral Council of Ministers meetings for guidance and direction.

## ESP Compliance
ENVIRONMENTAL AND SOCIAL POLICY COMPLIANCE
ESP-RELATED CONDITIONS AND REQUIREMENTS ATTACHED TO PROJECT/PROGRAMME APPROVAL DECISION
| Condition or requirement | Current status | Planned actions, including a detailed time schedule
List all ESP-related conditions and requirements included in the Board decision that need to be met. For each condition and requirement, list the current status. (Add lines as needed) [1]
SECTION 1: IDENTIFIED ESP RISKS MANAGEMENT
Was the ESP risks identification complete at the time of funding approval? [2]
ESP principle [3] | Are environmental or social risks present as per table II.K (II.L for REG) of the proposal? [4] | During project/programme formulation, an impact assessment was carried out for the risks identified. Have impacts been identified that require management actions to prevent unacceptable impacts? (as per II.K/II.L) [5] | List the identified impacts for which safeguard measures are required (as per II.K/II.L) | List here the safeguard measures (i.e. avoidance, management or mitigation) identified for each impact that are supposed to be (or had to be) implemented during the reporting period. Please break down the safeguard measures by activity. [6] | List the monitoring indicator(s) for each impact identified. [7] | State the baseline condition for each monitoring indicator | Describe each safeguard measure that has been implemented during the reporting period [8] | Describe the residual impact for each impact identified - if any - using the monitoring indicator(s) [8] | Describe remedial action for residual impacts that will be taken. [8]
1 - Compliance with the law |  |  | Unidentified sub-projects may require an EIA to comply with national environmental laws. | The requirement for an EIA will be verified by each National Project Team before the implementation of on-the-ground activities at the targeted intervention sites. | Project well aligned and complies with regional, national and sub-national policies, laws, plans and priorities for sustainable development and adapting to climate change. | The Project is well aligned and complies with regional, national and sub-national policies, laws, plans and priorities for sustainable development and adapting to climate change | During the development of the full project proposal, both regional and national stakeholders were consulted to ensure that all relevant legal requirements were met. National Environment Management Authorities and Community Development Officers are involved as members of the extension teams to ensure compliance. The established Regional Policy Steering Committee (RPSC) of Permanent Secretaries, National Coordination and district coordination teams are responsible to ensure laws are followed. | No
2 - Access and equity |  |  | Given that the beneficiaries are poor people who are not often integrated in the decision-making process, there could be risk of insufficient access of the project resources by these persons. | Clear and transparent criteria will be used by the National Project Teams to select sub-projects and project beneficiaries. This will include the selection of participants in the training sessions. | Vulnerable and marginalised groups have sufficient access and benefits to project activities, particularly the water conservation practices, climate smart agricultural techniques and EbA interventions under Component 2. | The World Bank funded project had criteria at the National Project Teams to select sub-projects and project beneficiaries. However it had gaps which had to be filled by this project. The selection of vulnerable areas was done through a fair and transparent process using the EAC-approved PREPARED VIA. | Transparent regional criteria developed and used to select intervention sites and beneficiaries. Second criteria for evaluation of baseline data and monitoring of the progress developed | No
3 – Marginalized and vulnerable Groups |  |  | Vulnerable and marginalised groups at project intervention sites will have insufficient access to project activities, particularly the water conservation practices, climate‑smart agricultural techniques and EbA interventions under Component 2. | Project activities have been specifically designed to take vulnerable and marginalised groups into account, particularly women. An ESMP will be followed throughout project intervention to ensure vulnerable and marginalised groups have adequate access to and benefit from project interventions. | Vulnerable and marginalised groups are involved in the selection of project beneficiaries and small scale projects; and have sufficient access and benefits to project activities, particularly the water conservation practices, climate smart agricultural techniques and EbA interventions under Component 2. | The LVBC through PREPARED has identified climate change hotspots; and marginalized and vulnerable groups. | Project is verifying/ validating the identified climate change hotspots; and marginalized and vulnerable groups. | No
4 – Human rights |  |  | No appreciable risk | No | Number of human rights reported and action taken | No | Project has included Community Development Officers as key extension officers to ensure compliance. | No
5 – Gender equality and women’s empowerment |  |  | Project interventions do not benefit men and women equally. | The Project has included a 50% proportionate gender consideration in all project interventions, with a specific focus on the ground activities (Component 3 and 4). Therefore, the Project is designed to promote gender equity. The PCU and local government authorities at the Project intervention sites will need to ensure that these gender considerations are adhered to during project implementation. Fair and equitable selection of beneficiaries will be done for capacity building and training sessions. A list of all the participants will be maintained and gender ratio will be monitored by the PCU on a quarterly basis. | Number women and men involved and benefiting from project activities and outcome | 30% women and 70% men used to participate and benefits from other projects | Project has developed a condition of involving 50% women in project activities, and beneficiaries. This condition help to create awareness that women are equally important as men | Participation women from government staff is low due to the establishment. | Condition has helped to increase participation and involvement of women from government. In the invitation letter this condition is included.
6 – Core labour rights |  |  | Local community members may be exposed to the risk of accidents while implementing the Project’s climate change adaptation interventions | During implementation, the PMU and National Project Teams will ensure compliance with national and international labour laws and will provide adequate protection equipment for workers. | Number of cases reported on international labour and action taken | No case reported | Project has included Community Development Officers as key extension officers to ensure compliance. | No
7 – Indigenous peoples |  |  | Indigenous communities at project intervention sites are not identified and are therefore not included in the relevant stakeholder consultations and decision-making processes. Inequitable access of indigenous peoples to the project's resources | Comprehensive stakeholder mapping will take place through Output 3.1 as project intervention sites are identified. This will allow for the identification of indigenous peoples. The Project will not contravene the rights of indigenous people. Indigenous peoples will be included in the participatory planning of project interventions and the design of CBAPs to ensure equitable access to project resources. | Number of indigenous communities identified action taken | No indigenous communities identified and reported | Project included criteria to safeguard indigenous communities | No
8 – Involuntary resettlement |  |  | No appreciable risk | During project development involuntary resettlement was addressed and included in selection criteria. Project intervention site selection included item of identifying involuntary resettlement | Number of involuntary resettlement issued identified action taken | No case reported | Project has included Community Development Officers as key extension officers to ensure compliance. | No
9 – Protection of natural habitats |  |  | Construction of adaptation interventions (for example boreholes or gabions) identified in the community based adaptation plans could result in the destruction of small areas of natural habitat. | Technical feasibility studies will be conducted for physical infrastructure identified as sub-projects in the community based adaptation plans to ensure that they will not result in significant adverse impacts on natural habitat. All activities will adhere to the EIA regulations of the relevant Partner State. | number of Construction of adaptation interventions identified and appropriate action taken | No case reported | District team establish to identify and to take appropriate action | No
10 – Conservation of biological diversity |  |  | Construction of adaptation interventions (for example boreholes or gabions) identified in the community‑based adaptation plans could result in negative impacts on biodiversity. | Technical feasibility studies will be conducted for physical infrastructure identified as sub-projects in the community based adaptation plans to ensure that they will not result in significant adverse impacts on biodiversity. | number of Construction of adaptation interventions identified and appropriate action taken | No case reported | District team establish to identify and to take appropriate action | No
11 – Climate change |  |  | No appreciable risk
12 – Pollution prevention and resource efficiency |  |  | No appreciable risk
13 – Public health |  |  | Water-related diseases (such as Malaria) may increase in frequency with the construction of water storage infrastructure. | The construction of water storage infrastructure will be accompanied with training and technical support to communities on how to mitigate the risks of water-related diseases. | Number of trainings conducted to avoid and treat Water-related diseases | No case reported | Health officers are involved in the district teams | No
14 – Physical and cultural heritage |  |  | Without specific site selection, it is possible that the interventions identified in sub-projects will negatively affect physical and cultural heritage. | Participatory mapping – which will include local communities and district level authorities – will be undertaken during the development of CBAPs to identify areas of physical and cultural significance and ensure that sub-projects will not negatively impact upon those. | number of physical and cultural heritage identified and appropriate action taken | No case reported | District team established to identify and to take appropriate action | No
15 – Lands and soil conservation |  |  | No appreciable risk
SECTION 2: MONITORING FOR UNANTICIPATED IMPACTS / CORRECTIVE ACTIONS REQUIRED
Has monitoring for unanticipated ESP risks been carried out? |  | Project has just started on the ground and monitoring is going on. Next PPR will provide details on the same.
Have unanticipated ESP risks been identified during the reporting period? |  | Unanticipated ESP risks will be monitored as countries report back on site selection and USPs. Next PPR will give details.
If unanticipated ESP risks have been identified, describe the safeguard measures that have been taken in response and how an ESMP has been prepared/updated |  | ESMP was developed and presented to stakeholders during Inception workshop for inputs. Inputs from inception workshop was incorporated and submitted to Partner States for adoption and implementation
SECTION 3: CATEGORISATION
Is the categorisation according to ESP standards still relevant?
If No, please describe the changes made at activity, output or outcome level, approved by the Board, that resulted in this change of categorization.
SECTION 4: IMPLEMENTATION ARRANGEMENTS
What arrangements have been put in place by the Implementing Entity during the reporting period to implement the required ESP safeguard measures? |  | The safeguard risks were identified during the project development phase and an ESMP developed. UNEP will manage and monitor and report on the ESMP and adapt/adjust the ESMP if and when needed. An ESP was developed and presented to the Regional project coordination team. United Nations Environment Programme (UNEP) held meeting with Executing Entity (LVBC) and Partner States (Burundi, Kenya, Rwanda, Tanzania and Uganda). One of agenda of the meeting was ESP safeguard measures. In the meeting UNEP, LVBC and Partner States agreed and put mechanisms to implement required ESP safeguard measures. The mechanisms includes (a) Project Management Unity has obligation to ensure ESP safeguard measures are implemented as per signed project document and revised ESP and reported (b) Project has established National Coordination teams with Coordinators. The teams include relevant project sectors such as Agriculture, Livestock, Forestry, climate/ Meteorology, Water, Environmental Management Authorities/ agencies; and particularly Community development officers whose mandate is to ensure ESP safeguard measures are implemented and adjusted accordingly and reported to project management (c) Project has established districts/county project coordination teams with the same structure in (b) and play the same role (d) UNEP has issued guidelines that for all activity LVBC has to ensure ESP measures are coordinated and reported to RPSC and Council of Ministers for actions. In the meeting it was agreed to identify issues which were not included in the ESP to ensure they are captured and addressed.
Have the implementation arrangements been effective during the reporting period? |  | Activities on the ground have not commenced yet.
What arrangements have been put in place by each Executing Entity during the reporting period to implement the required ESP safeguard measures? |  | National Environment Councils/ Authorities are regulatory bodies and are involved in the project implementation. The established RPSC and PMU at regional level; and national and Districts Coordination teams are responsible for implementation and reporting of ESP
Have the implementation arrangements at the EEs been effective during the reporting period? |  | Effective. An ESP was developed and presented to the Regional project coordination team for the Lake Victoria Basin
SECTION 5: PROJECTS/PROGRAMMES WITH UNIDENTIFIED SUB-PROJECTS (USPs) [9]
Have the arrangements for the process described in the ESMP for ESP compliance for USPs been put in place? [10]
Is the required capacity for ESMP implementation present and effective with the IE and the EE(s)? Have all roles and responsibilities adequately been assigned and positions filled? Please provide details. |  | ESP was developed for the LVB project that ESP for the ACC-LVB project includes the following components: (a) Subproject activity; (b) Potential adverse effects/impacts; (c) Proposed mitigation measures; (d) Institutional responsibility for mitigation (including enforcement and coordination); (e) Monitoring requirements; (f) Responsibility for monitoring and supervision; Implementation schedule; and (g) Cost estimates. National institutions and staff for ESMP implementation are present. The capacity of these institutions need to be improved to effectively implement the ESP as per agreed in the project document. Roles and responsibilities are adequately assigned to national, Districts and County institutions including established coordination teams.
Has the overall ESMP been updated with the findings of the USPs that have been identified in this reporting period? [11] |  | ESMP was presented in the inception workshop and input to improve were given. The Executive Entity in collaboration with national experts improved the ESMP and developed monitoring framework to ensure is implemented as agreed. USPs will be identified during the next reporting period. The ongoing exercise on identification of intervention activities include gathering information to guide in the identification of USPs as well as inform regular updates of ESMP.
List each USP that has been identified in the reporting period to the level where effective ESP compliance is possible [12] | Has the ESMP been applied to the USP that has been identified? | List all the ESP risks that have been identified for the USP | Has an impact assessment been carried out for each ESP risk that has been identified for the USP? | Has adequate consultation been held during risks and impacts identification for the USP? [13] | Have the data used to identify risks and impacts been disaggregated by gender as required? | List the environmental and social safeguard measures (avoidance, mitigation, management) that have been identified for the USP | List the monitoring indicator(s) for each impact identified
USPs will be identified during the next reporting period.
USPs will be identified during the next reporting period.
USPs will be identified during the next reporting period.
USPs will be identified during the next reporting period.
USPs will be identified during the next reporting period.
USPs will be identified during the next reporting period.
SECTION 6: GRIEVANCES
Was a grievance mechanism established capable and known to stakeholders to accept grievances and complaints related to environmental and social risks and impacts?
List all grievances received during the reporting period regarding environmental and social impacts of project/programme activities [14] |  | For each grievance, provide information on the grievance redress process used and the status/outcome
Project activities have not commenced yet |  | Project activities have not commenced yet
No, the project/programme includes Unidentified Sub-Projects (USPs) (also complete Section 5)
Yes, all project/programme activities had been formulated to the level where effective risks identification is possible
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Partially
Yes
No
Yes
No
Partially
Yes
No
Partially

## GP Compliance
GENDER POLICY COMPLIANCE
SECTION 1: QUALITY AT ENTRY
Was an initial gender assessment conducted during the preparation of the project/programme's first submission as a full proposal? |  | YES
Does the results framework include gender-responsive indictors broken down at the different levels (objective, outcome, output)? |  | YES
List the gender-responsive elements that were incorporated in the project/programme results framework
Gender-responsive element [2] | Level [3] | Indicator | Baseline | Target | Rated result for the reporting period (poor, satisfactory, good)
Recognition of gender in needs, opportunities and capacities, | Outcome, Output | Number of women received capacity building at regional, National and Community levels | Staff involved in regional institutions have been trained through the PREPARED project on climate change adaptation. | By the end of the project, at least 20 staff (of which at least 50% are women) trained on climate change adaptation and water catchment management during regional workshops. By the end of the project, at least 100 staff (of which at least 50% are women) trained on climate change adaptation and water catchment management during national workshops. | satisfactory
Equitable participation and influence by Women in decision making process | Outcome, Output | Relevant threat and hazard information generated and disseminated to stakeholders on a timely basis. | Policy- and decision-makers in the five Partner States receive regional forecasts from ICPAD, FEWSNET and RCMRD). Project has established a framework at national and community level for the execution of activities in each category and ensure women and men have equitable access. | By the end of the project, policy- and decision-makers in each pilot country receive down-scaled national climate information every quarter. By the end of the project, local communities in the project interventions sites receive tailored climate information packages. | satisfactory
Equitable access to financial resources and other benefits | Outcome, Output | Number of people practicing climate change adaptation technologies. | 0 | At least 500 (250 women) people (100 per intervention site) are practicing climate change adaptation technologies. | satisfactory
Project interventions are tailored to local requirements, benefits vulnerable groups and includes gender considerations. | Outcome, Output | Number of beneficiaries of small-scale community-based projects. | 0 | At least 1000 (500 women) people (200 per intervention site) benefit from small-scale community-based projects. | satisfactory
SECTION 2: QUALITY DURING IMPLEMENTATION AND AT EXIT [4]
List gender equality and women's empowerment issues encountered during implementation of the project/programme. For each gender equality and women's empowerment issue describe the progress that was made as well as the results. [5]
Gender equality and women's empowerment issues [6] |  | Rated result for the reporting period (poor, satisfactory, good)
Project has not started implementation on the ground but noted that during the capacity building workshops for government staff and other institutions, women participation was lower than the 50% required and stood at 20%. Main reason given by partners and stakeholders is the low number of women in the government institutions in the partner countries with some offices notifying that they did not have any women present in the relevant units. However Project has emphasised and discussed with partner countries to ensure the number of participation of women is increased. Subsequent workshops including discussions on how regional and national climate institutions can work together to ensure accurate and timely delivery of climate information women participation increased from 20 to 30%. Further discussions will be held with partner countries to ensure that gender parity target is achieved |  | Women participation increased from 20% to 30% following discussions with countries regarding poor gender balance in trainings and workshops. Overall rating: Poor
Regarding Project personnel at national level, 3 National Coordinators nominated by Countries are women out of 5 national coordinators. |  | Women are 60% ; men are 40%. Good
SECTION 3: IMPLEMENTATION ARRANGEMENTS
What arrangements have been put in place by the Implementing Entity during the reporting period to comply with the GP |  | UNEP has a comprehensive Policy and Strategy on Gender Equality and the Environment which sets in place the use of a gender marker. Essentially the gender marker serves as a monitoring tool that ensures that at the point of project development and implementation gender perspectives are integrated at all stages including the budget. The gender marker has a four point scale against which the project is assessed. Each project is required to meet a rating of 2a which means that gender is fully mainstreamed and the project will make a significant contribution to meeting gender equality. Should a project not meet the 2a rating, the project officer is required to revise the project and ensure gender perspectives are fully mainstreamed and thereafter resubmit the project for project review.
Have the implementation arrangements at the IE been effective during the reporting period? |  | UN Environment’s Climate Change Adaptation Unit (CCAU) organized a four-day training workshop (8 to 11 October 2018) for 16 national project managers who are implementing Global Environment Fund (GEF), Adaptation Fund (AF) and Green Climate Fund (GCF) funded adaptation projects. The training had two main objectives: strengthen capacities in climate change adaptation and project management best practices. The training included on how to integrate gender across adaptation approaches and tools with emphasis on gender analysis, gender mainstreaming, equity, equality and some of the pitfalls to understanding gender at the local level. Resource materials including UNEP gender toolkit were shared with all training participants. Project manager for the LVB project participated throughout the training and presented his personal gender action plan in relation to his project portfolio.
What arrangements have been put in place by each Executing Entity during the reporting period to comply with the GP? [7] |  | The proposed project has included proportionate gender consideration on all project interventions, with a specific focus on on-the-ground activities (Component 3 and 4). Provisions for equitable selection of beneficiaries have been included for all capacity building and training activities and gender ratio will be monitored by quarterly basis. The PCU and local government authorities at the proposed project intervention sites will be monitored to ensure that these gender considerations are adhered to during project implementation.
Have the implementation arrangements at the EE(s) been effective during the reporting period? [7] |  | 3 out of 5 National Project Coordinators nominated by the project are women (60%). However, more effort required to ensure equitable representation among national experts in partner countries is achieved through continuous discussions with governments as well as assistance in drafting gender responsive TORs.
Have any capacity gaps affecting GP compliance been identified during the reporting period and if so, what remediation was implemented? |  | Partner countries have lower ratio of women employed in offices and units relevant to the project which in turn affect the GP compliance in project deliverables. Project has ensured TORs and invitation letters include gender component and gender considerations and provide opportunities and ensure Community Development Officers give women equal opportunities and enable participation of women in decision making processes in intervention areas.
SECTION 4: GRIEVANCES
Was a grievance mechanism established capable and known to stakeholders to accept grievances and complaints related to gender equality and women's empowerment? [8]
List all grievances received through the grievance mechanism during the reporting period regarding gender-related matters of project/programme activities [9] |  | None to date.
No grievance received during the reporting period |  | Project has not started field activities during the current reporting period
Yes
No
Partially

## ESP and GP Guidance notes
ESP and GP Guidance Notes
ENVIRONMENTAL AND SOCIAL POLICY
Reference | Guidance
1 | ESP-related conditions and requirements refers to all those that relate directly or indirectly to compliance with the ESP. These conditions are usually included in “Schedule II of the legal agreement” with the name of “requirements and conditions for disbursements and disbursement schedule.”
2 | The ESP requires that environmental and social risks are identified for all project/programme activities prior to funding approval. When not all the project/programme activities have been sufficiently formulated at that time so that adequate risks identification is possible, then the ESP risks identification is not complete.
3 | Complete this section for all the ESP risks that have been identified, not taking into account any USPs
4 | The project proposal includes an overview table of identified environmental and social risks (Section II.K of the proposal, Section II.L for regional projects). For each of the 15 principles of the ESP, please copy here the findings on the presence or absence of risks by ticking the corresponding box.
5 | Only complete for those ESP principles for which risks were identified
6 | The safeguard measures that must be implemented during a project/programme are normally described in detail in the ESMP of the project/programme
7 | See the monitoring plan in the ESMP
8 | For the first PPR report of the project/programme, this column needs to be completed with full information. For subsequent PPR reports, an update of the information previously provided is sufficient.
9 | This section needs only to be completed if the project/programme includes USPs
10 | The case being, please include details on the planned timing to have all the USP implementation arrangements in place.
11 | Please submit the updated ESMP together with the PPR
12 | Add lines as appropriate, one line for each USP identified
13 | Clarify also if the grievance mechanism has been made widely known to identified and potentially affected parties
14 | If any grievances were received that must not be made public, please inform the AF Secretariat of such grievances, detailing the reasons for them to remain confidential. Conficential information may be redacted by the IE in the report.
GENDER POLICY
Reference | Guidance
1 | To be completed at PPR1
2 | Add lines as appropriate, one line for each gender-responsive element
3 | Objective, outcome, output
4 | To be completed at final PPR
5 | Risks related to gender equality and women's empowerment should be reported in the ESP compliance tab
6 | Add lines as appropriate, one line for each issue
7 | Add lines as appropriate, one line for each executing entity
8 | To be completed at PPR1
9 | If any grievances were received that must not be made public, please inform the AF Secretariat of such grievances, detailing the reasons for them to remain confidential. Confidential information may be redacted by the IE in the report. This section will not be published on the AF webiste.

## Project Indicators
PROJECT Indicators
Please provide all indicators being tracked for the project as outlined in the project document
Type of Indicator (indicators towards Objectives, Outcomes, etc.…)
| Type of Indicator | Indicator | Baseline | Progress since inception | Target for Project End
Outcome 1. Strengthened institutional and technical capacity to integrate climate resilience into transboundary water catchment management. | 1.1. Outcome Indicator | No. of staff trained to respond to, and mitigate impacts of, climate-related events (gender disaggregated). | Staff involved in regional institutions have been trained through the PREPARED project on climate change adaptation. | one (1) man trained | By the end of the project, at least 20 staff (of which at least 50% are women) trained on climate change adaptation and water catchment management during regional workshops; and By the end of the project, at least 100 staff (of which at least 50% are women) trained on climate change adaptation and water catchment management during national workshops.
| 1.1.1. Output indicator | Number of meetings of the CCTWG. | 2 meetings per year. | 1 meeting of regional climate and national situations held share experiences of data collection, analysis and dissemination | 6 meetings of the CCTWG are held
| 1.2.2. Output indicator | No. of staff trained to respond to, and mitigate impacts of, climate-related events (gender disaggregated). | Staff involved in regional institutions have been trained through the PREPARED project on climate change adaptation. | One LVBC (man) Trained on UN Environment training of Climate Change Adaptation; | at least 20 staff (of which at least 50% are women) trained on climate change
Outcome 2. Improved delivery of accurate and timely climate information to regional and national policymakers, technical officers and local communities. | 2.1. Outcome Indicator | Relevant threat and hazard information generated and disseminated to stakeholders on a timely basis. | Policy- and decision-makers in the five Partner States received project implementation status and provided directives. | This project was used to disseminate the identified climate threat and hazard information generated by PREPARED project to decision makers 14 (6 women and 8 men) Permanent Secretaries and 7 (3 women and 4 men) Sectoral Council of Ministers | By the end of the project, policy- and decision-makers in each pilot country receive down-scaled national climate information every quarter. By the end of the project, local communities in the project interventions sites receive tailored climate information packages.
| 2.1.1. Output indicator | Delivery of climate information to local communities at selected project intervention sites. | National hydro meteorological agencies in each of the Partner States receive regional climate information from institutions such as ICPAC and FEWSNet through regional forums such as the CIN. However, this information is not transmitted to local communities to allow them to plan seasonally. | 4 capacity building workshops were held for the established project National Coordination team in Burundi, Kenya, Rwanda and Uganda for climate, agriculture, water, community development technical experts (38 participants (12 women and 16men) to understand project management; and delivery of climate information to local communities at selected project intervention sites. | All communities at the selected project intervention sites receive relevant climate information at least twice a year.
| 2.1.2. Output Indicator | Stock take of climate risk information in the region conducted to inform adaptation measures | Project is preparing ToR to undertake stock take | Climate risks information stock take will be conducted in Q4 | Adaptation measures in all 9 intervention sites are selected based on climate risk assessment stock take
| 2.2.1. Output indicator | Number of staff members trained on downscaling regional climate information to the national level. | Staff from national meteorological agencies have been trained to produce regional climate information with GEOCLIMA software | Project has agreed with IGAD Climate Prediction and Application Centre (ICPAC), Famine Early Warning Systems Network (FEWSNET), Regional Centre for Mapping of Resources for Development (RCMRD) to conduct training at ICPAC training Centre. Training will be in August 2019 | At least 25 (5 per Partner State) staff members trained on downscaling regional climate information to the national level
Outcome 3. Climate change adaptation technologies transferred to communities to reduce their vulnerability to climate change. | 3.1. Outcome indicator | Natural assets protected or rehabilitated | Areas of forest and agricultural land and being degraded through overexploitation for fuelwood and unsustainable agricultural practices. | Project has identified and validated intervention sites. Actual activities has not started due to the delay of approved ToR for procurement of Adaption expert. It will start by October 2019 | At least 1000 hectares of agricultural land rehabilitated through climate-smart agriculture (200 ha at project intervention sites in each of the five Partner States) and at least 500 hectares of hectares of woodland rehabilitated using an EbA approach (100 ha at project intervention sites in each of the five Partner States).
| 3.1.1. Output indicator | Number of project intervention sites identified. | The VIA being finalised by PREPARED has identified vulnerability hotspots. Specific sites will be chosen within these hotspots. | 9 intervention sites have been identified using agreed regional criteria. Burundi selected Kirundo and Muyinga as intervention sites, Government of Kenya selected Busia and siaya as interventions sites, Government of Rwanda selected Kihere District within Akagera river basin and names of sites are Gahara and Musaza; Government of Tanzania selected Magu; and government of Uganda selected Masaka and Mubende as intervention sites. | At least 1 intervention site identified in each Partner State.
| 3.2. Outcome indicator | Number of people practicing climate change adaptation technologies. | 0 | Project has identified and validated intervention sites. Actual activities has not started due to the delay of approved ToR for procurement of Adaption expert. It will start by October 2019 | At least 1000 hectares of agricultural land rehabilitated through climate-smart agriculture (200 ha at project intervention sites in each of the five Partner States) and at least 500 hectares of hectares of woodland rehabilitated using an EbA approach (100 ha at project intervention sites in each of the five Partner States).
| 3.2.1. Output indicator | Number of community members at project intervention sites in each Partner State trained on climate change adaptation technologies (gender disaggregated). | 0 | Project has established district/ extension officers to be trained as trainers of communities. Training will start after extension team training done by ICPAC, FEWSNET and SERVIR at national level. | At least 100 community members in each Partner State (of which 50% are women) trained on climate change adaptation technologies (500 people in total).
| 3.3.1. Output indicator | Number of households at project intervention sites in each Partner State benefitting from water conservation practices. | 0 | Regional training on how to facilitate, approve project proposals for funding has been scheduled by September and training at community level will be starting by October 2019. Funds have been transferred to Countries to implement this activity. | At least 100 households in each Partner State benefitting from water conservation practices (500 households in total).
| 3.3.2. Output indicator | Number of hectares of climate-smart agriculture at project intervention sites in each Partner State | 0 | Regional training on how to facilitate project proposals has been scheduled by September and training at community level will be starting by October 2019. Funds have been transferred to Countries to implement this activity. | At least 200 hectares of climate-smart agriculture at project intervention sites in each Partner State (1000 hectares in total).
| 3.3.3. Output indicator | Number of hectares of land restored using an EbA approach at project intervention sites in each Partner State. | 0 | Regional training on how to facilitate, approve project proposals for funding has been scheduled by September and training at community level will be starting by October 2019. Funds have been transferred to Countries to implement this activity. | At least 100 hectares of hectares of land restored using an EbA approach at project intervention sites in each Partner State (500 hectares in total).
Outcome 4. Regional resilience to climate change promoted through innovative, community based projects. | 4.1. Outcome Indicator | Number of beneficiaries of small-scale community-based projects. | 0 | Regional training on how to facilitate, approve project proposals for funding has been scheduled by September and training at community level will be starting by October 2019. Funds will be transferred to Countries to implement this activity by December 2019. | At least 1000 people (200 per intervention site) benefit from small-scale community-based projects
| 4.1.1. Output indicator | Number of small-scale projects that promote innovative approaches to climate change sites funded at intervention in each Partner State. | 0 | Regional training on how to facilitate, approve project proposals for funding has been scheduled by September and training at community level will be starting by October 2019. Funds will be transferred to Countries to implement this activity by December 2019. | At least 4 small-scale projects Number of small-scale projects that promote innovative approaches to climate change sites funded at intervention in each Partner State.
Outcome 5. Improved knowledge management frameworks for the collection and maintenance of regional knowledge in transboundary water catchment management and climate change adaptation practices. | 5.1.Outcome Indicator | No. of news outlets in the local press and media that have covered climate change adaptation in relation to transboundary water catchment management in the LVB. | 0 | 3 regional TV stations covered project implementation (climate change adaptation) | At least 15 news outlets in the local press and media that have covered climate change adaptation in relation to transboundary water catchment management in the LVB.
| 5.1.1. Output indicator | Establishment of a research forum for the LVB. | Climate change research is not coordinated across the LVB and takes place in isolation | 1 established for regional and national climate institutions | One research forum for the LVB established.
| 5.2.1. Output indicator | Number of exhibitions to showcase the successful regional and community-based approaches to climate change adaptation demonstrated through the project. | Several projects, including PREPARED, have undertaken awareness-raising activities within the LVB. However, none of these awareness raising activities have included exhibitions to showcase regional and community-based climate change adaptation interventions. | 3 (One through International Environment day, two (2) UN and two (2) universities) exhibitions showcased regionally identified climate change issues, vulnerable areas and communities; and project intervention areas and expected activities and outcomes | At least 2 exhibitions to showcase the successful regional and community-based approaches to climate change adaptation demonstrated through the project.

## Rating
#NAME?
RATING ON IMPLEMENTATION PROGRESS
For rating definitions please see bottom of page.
|  | Progress on Key Milestones |  | Expected Progress |  | Progress to Date | Rating
Component 1: Improving regional management of a transboundary water catchment
|  | Activity 1.1.1. Establish Regional CC information platform ( NGOs, Governments, RMCMD, ICPAC, UNEP, LVBC, CCTWG, FEWSNET,, IUCN, WWF, DHI, NBI) |  | Hold workshop and prepare Terms of Reference to establish a platform |  | A workshop was held and Terms of Reference to establish a platform were developed and approved by Steering Committee and Sectoral Council of Ministers. | Satisfactory (S)
|  | Activity 1.1.2. Undertake Climate Change Technical Working Group meeting to finalize and validate the Stakeholders engagement strategy |  | One Climate Change Technical Working Group held to consider and validate stakeholders engagement strategy |  | Draft stakeholders engagement strategy has been prepared and will be presented to CCTWG. Second meeting has been organized and will be facilitated by incoming CTA. | Moderately satisfactory (MS)
|  | Activity 1.1.3. Undertake regional capacity building exercises in water catchment management in the context of climate change in organizations such as inter alia: i) LVBC; ii) CCTWG; iii) EAC Climate Change Unit; and iv) Lake Victoria Region Local Authority Cooperation |  | Undertake one training for 30 experts |  | Work in progress. Project has identified experts to be trained. The activity will be facilitated with technical guidance of the Water Catchment Management consultant/expert whose recruitment process is currently ongoing. | Moderately Unsatisfactory (MU)
|  | Activity 1.2.1. Undertake the preparation and dissemination of communication materials |  | Project awareness materials developed and disseminated at regional level |  | Project awareness materials were developed and disseminated at the United Nations Environment exhibition held in Dar Es Salaam, Tanzania; and at the 2018 National World Environment day celebration that was held in Kisumu, Kenya. During the same period, decision makers including East African Legislation Assembly members were sensitized about the Adapting to Climate Change in Lake Victoria Basin project. | Satisfactory (S)
Component 2. Climate information dissemination
|  | Organize the meeting/ workshop for the Regional CC Institutions network (ICPAC, FEWSNET, DHI, RCMRD) to develop tailored climate information packages for: i) policy- and decision makers; and ii) local communities |  | Workshop organized and ToR to develop tailored climate information packages developed in consultation with regional climate change institutions, Meteorology and regional climate information networks |  | Lake Victoria Basin Commission organized a workshop for the Regional Climate Change Institutions network (ICPAC, FEWSNET, DHI, RCMRD), National meteorology institutions and regional climate information network during which ToR to develop tailored climate information packages for: i) policy- and decision makers; and ii) local communities were developed. | Satisfactory (S)
|  | Activity 2.1.1. Train representatives from the national meteorological agencies in each of the five Partner States on downscaling regional climate information to the national level |  | Trained of representatives from the national meteorological agencies in each of the five Partner States on downscaling regional climate information to the national level |  | Work in progress . Project has agreed with IGAD Climate Prediction and Application Centre (ICPAC), Famine Early Warning Systems Network (FEWSNET), Regional Centre for Mapping of Resources for Development (RCMRD) to conduct training at ICPAC training Centre. These institutions agreed to provide the Climate Modelling expert among other required expert. Training is scheduled in September 2019 and LVBC is finalizing the development and signing of long-term collaboration with these institutions . | Moderately Unsatisfactory (MU)
|  | Activity 2.1.2. Organize a stakeholders workshop of sensitization for ( Policy makers, catchment and Climate Change technical experts) |  | Sensitization workshop held |  | Sensitization workshops were held in Burundi, Kenya, Rwanda and Uganda for technical experts. In order to ensure political buy-in of the project, a sensitization forum was also conducted targeting decision makers e.g. Permanent Secretaries and Sectoral Council of Ministers responsible for Climate Change and Environment in Kenya, Rwanda, Burundi, Tanzania and Uganda. | Satisfactory (S)
|  | Activity 2.2.2. Strengthen existing climate information dissemination mechanisms – including the Lake Victoria Basin Commission information hub – to develop an Lake Victoria Basin specific platform for climate information |  | Workshop held with climate change institutions to consider and identify appropriate climate information dissemination mechanisms |  | Workshop was held with climate change institutions (IGAD Climate Prediction and Application Centre (ICPAC), Famine Early Warning Systems Network (FEWSNET), Regional Centre for Mapping of Resources for Development (RCMRD)) and national meteorology directorate during which appropriate climate information dissemination mechanisms were identified. | Satisfactory (S)
|  | Activity 2.2.3. Deliver climate information for long term strategic planning to policy and decision makers in regional organizations as well as technical staff in national ministries within the Lake Victoria Basin |  | Workshop held and the lead institution selected to support the establishment of Lake Victoria Basin Commission climate change information hub |  | Consultative meetings were held with IGAD Climate Prediction and Application Centre (ICPAC), Famine Early Warning Systems Network (FEWSNET), Regional Centre for Mapping of Resources for Development (RCMRD). IGAD Climate Prediction and Application Centre (ICPAC) was selected to be the lead institution to support the establishment of a Climate change information hub to be hosted by Lake Victoria Basin Commission. | Satisfactory (S)
|  | Activity 2.2.4. Pilot innovative information-sharing mechanisms – such as the provision of climate information through mobile networks – to deliver climate information to communities in a locally relevant and accessible format |  | Piloted innovative information-sharing mechanisms |  | Not done . The activity is supposed to be done with technical guidance of the Climate Change Communications consultant/expert whose recruitment process is currently ongoing. | Marginally Unsatisfactory (MU)
Component 3. Regional approach to climate change adaptation in vulnerable communities
|  | Identify project sites for each of the countries |  | regional intervention site selection criteria developed, approved by Regional Policy Steering Committee and at least 5 project sites identified (one for each of the country) |  | Regional intervention site selection criteria was developed and approved by Regional Policy Steering Committee. The criteria was applied to identify and select 9 project sites across the five Partner States where project interventions will be implemented. Partner States using national coordination team have validated 7 sites. Validation of remaining two sites is ongoing. | Satisfactory (S)
|  | Activity 3.1.1. Documenting /lessons learned from past and current Lake Victoria Basin Commission programmes (LVWATSAN, LVEMP II, PREPARED Vulnerability Assessment) |  | Terms of Reference developed and approved by Regional Policy Steering Committee and Sectoral Council of Ministers. Hire a consultant to document lesson learnt from the past and current LVBC projects and programme. Conduct a stock take of adaptation interventions detailed in existing national strategies and action plans, recommendations from other regional projects and findings of scientific research in the Lake Victoria Basin to identify appropriate adaptation technologies to be implemented regionally |  | Terms of Reference developed and approved by Regional Policy Steering Committee and Sectoral Council of Ministers. The documentation of lessons learned from past and current Lake Victoria Basin Commission programmes will be spearheaded by the Chief Technical Advisor that has recently recruited. | Marginally Satisfactory (MS)
|  | Activity 3.2.1.Extension officers , District Teams and local communities trained on climate change adaptation technologies including water conservation practices, climate-smart agricultural techniques and EbA activities |  | One national training workshop held for 100 community members and staff in each country |  | Work in progress. Project has established district/ extension officers to be trained. Training will be facilitated with technical support of Climate Change Adaptation consultant/expert whose recruitment process is currently ongoing. | Marginally Unsatisfactory (MU)
|  | Activity 3.2.2.Climate change adaptation technologies demonstrated at selected project intervention sites |  | Climate change adaptation technologies demonstrated at selected project intervention sites |  | Work in progress. Project with district teams/ extension officers are identifying existing adaption initiatives with aim of identifying best practices. Climate change adaptation technologies demonstration at selected project intervention sites will be facilitated by Climate Change Adaptation consultant/expert whose recruitment process is currently ongoing. | Marginally Unsatisfactory (MU)
Component 4. Community-based approaches to climate change adaptation
|  | Activity 4.1.1. Identify communities/ Community based organizations/ NGOs to small scale projects on climate change interventions |  | at least 4 small scale projects per country benefiting about 200 people both direct and indirect |  | Work in progress. Intervention sites where interventions will be implemented have been validated. This activity has been delayed due to the lengthy administrative process of formalizing partnership (development and signing of Memorandum of Understanding) between Lake Victoria basin Commission (Executing Entity) and Focal Ministries responsible for spearheading the implementation of project activities in respective partner states. Identification of communities will be done by September 2019. | Marginally Unsatisfactory (MU)
|  | Activity 4.1.2. Provide training to local communities or relevant local-level government or NGOs on how to develop a project proposal and the necessary financial, administrative and monitoring procedures for a small-scale project |  | one training workshop held for each of the Country |  | Work in progress. Regional training on how to facilitate project proposals has been scheduled by September and training at community level will be starting by October 2019. This activity has been delayed due to the lengthy administrative process of formalizing partnership (development and signing of Memorandum of Understanding) between Lake Victoria basin Commission (Executing Entity) and Focal Ministries responsible for spearheading the implementation of project activities in respective partner states | Marginally Unsatisfactory (MU)
|  | Activity 4.1.3.Review project proposals and select successful project proponents |  | Projects proposal reviewed and selected |  | Work in progress. This activity will be spearheaded by the Chief Technical Advisor whose recruitment was finalized in June 2019. | Marginally Unsatisfactory (MU)
Component 5. Knowledge management and learning
|  | Activity 5.1.1. Identify one Research Institution in each of the Partner states |  | Identified research institutions in each of the Partner States |  | A total of 5 research institutions (one in each of the partner state) have been identified | Satisfactory (S)
|  | Activity 5.1.2 Establish a forum of researchers and technical experts working on climate change adaptation to coordinate climate change research initiatives across the LVB |  | Terms of Reference developed and approved by Regional Policy Steering Committee and Sectoral Council of Ministers |  | Terms of Reference were developed and approved by Regional Policy Steering Committee and Sectoral Council of Ministers | Satisfactory (S)
|  | Activity 5.2.1. Inception workshop |  | Inception workshop held by April 2018 |  | Inception workshop was held in June 2018 | Satisfactory (S)
| Project Manager/Coordinator: | Project staff in place to manage the project |  | Project staff in place by 23rd March 2018 |  | Project staff recruitment concluded on 15th February 2019. However, due to delay in administrative processes, the project staff did not assume office until June 2019. | Marginally Unsatisfactory (MU)
[6 empty] | Overall Rating | Marginally Satisfactory (MS)
Please Provide the Name and Contact information of person(s) responsible for completing the Rating section
|  | Name: | Fredrick Mhina Mngube
|  | Email: | mngube@lvbcom.org
Please justify your rating. Outline the positive and negative progress made by the project since it started. Provide specific recommendations for next steps. . (word limit=500)
The overall rating of the progress of project implementation is Moderately Satisfactory. The project was approved by the Adaption Fund Board in November 2017 and execution started in June 2018. Cooperation Agreement between East African Community (EAC) and United Nations Environment Programme on 20th February 2018. This paved the way for the approval of the project supplementary budget by the East African Legislative Assembly on 4th June 2018 to allow project related expenditures to be incurred. Other key milestones including completion of the inception phase (inception workshop held on 28th June 2018), planning of project interventions including work plan and budget as well as monitoring plan have been developed and operationalized. While there were long delays with the recruitment process due to EAC guidelines, a project coordination unit (Project Manager, Chief Technical Advisor and Admin & Finance) has also been established. To date, National Coordination teams have successfully been established across all 5 countries and trained to enhance their capacity to execute climate change adaptation projects. Additionally, a Regional Policy Steering Committee composed of senior government officials has been established to provide technical and strategic guidance towards implementation of the project. As part of the inception phase, a site selection project intervention sites have been selected in the Lake Victoria Basin across the five partner states while Environment and Social Safeguards have been developed in line with UNEP requirements. Recruitment process of consultants that will spearhead implementation of various project activities has been initiated as well. Moreover, engagement and stakeholder sensitization forums have been taking place in order to achieve high level political support from senior government officials of partner states that will play a critical role during the implementation of the project. Whilst the inception phase has taken longer than planned it has allowed extensive consultations and consensus that have contributed to a strong sense of ownership and engagement of various stakeholders at regional, national and subnational levels. While the inception phase has progressed well, some of the project activities have not been achieved due to lengthy administrative process of having in place Memorandum of Understanding between the executing entity (Lake Victoria Basin Commission) and National Focal Ministries of respective partner states to allow the transfer of funds to support implementation of project activities. Another major challenge has been the prolonged recruitment process that has resulted to delays in the establishment of a fully functional project coordination unit thereby affecting implementation of the project activities. To address the challenges, the Lake Victoria Basin Commission (executing agency) nominated its staff to provide project management support until the project coordination was in place. Another strategy that was used was proceeding with implementation of project activities that are to be done by the Lake Victoria Basin Commission and therefore not dependent on funds transfer to the National Focal Ministries through a Memorandum of Understanding. Moving forward, the project coordination unit will develop a strategy to address the time lag through fast tracking implementation of project activities.
|  | Progress on Key Milestones |  | Expected Progress |  | Progress to Date | Rating
| Implementing Agency | Component 1: Improving regional management of a transboundary water catchment
|  | Establish Regional CC information platform ( NGOs, Governments, RMCMD, ICPAC, UNEP, LVBC, CCTWG, FEWSNET,, IUCN, WWF, DHI, NBI) |  | Discussion on delivery of timely and accurate climate information held with main regional stakeholders and TORs for a regional CC information platform developed |  | A workshop was held in Nairobi on 1-2 October., 2018 and was attended by national meteorology Directors from partner states, IGAD ICPAC, FEWSNET, RCMRD, UNEPDHI, IUCN and WWF. Terms of Reference to establish a platform were developed and approved by Steering Committee and Sectoral Council of Ministers and draft ToR to develop training packages on water conservation practices, climate smart agricultural techniques and EbA activities developed | Satisfactory (S)
|  | Organize a stakeholders workshop of sensitization for ( Policy makers, catchment and Climate Change technical experts) |  | Capacity building workshops held for National Coordination teams and policy makers at local and regional level |  | Four in-country capacity building workshops/trainings held for National coordination teams in partner countries. Additional workshops held with regional policy steering committee | Satisfactory (S)
|  | Undertake the preparation and dissemination of communication materials |  | Project awareness materials developed and disseminated at regional level |  | Communication materials for the project were developed and dispersed in various national, regional and global events including 2019 United Nations Environment Assembly, United Nations Environment exhibition held in Dar Es Salaam, Tanzania, 2018 National World Environment day celebration that was held in Kisumu, Kenya as well as COP24. During the same period, decision makers including East African Legislation Assembly members were sensitized about the Adapting to Climate Change in Lake Victoria Basin project. | Satisfactory (S)
|  | Undertake Climate Change Technical Working Group meeting to finalize and validate the Stakeholders engagement strategy |  | One Climate Change Technical Working Group held to consider and validate stakeholders engagement strategy |  | Activity was not completed due to CTA recruitment delay. CTA is currently onboard and activity scheduled scheduled for completion in Q4 | Marginally Unsatisfactory (MU)
|  | Undertake regional capacity building exercises in water catchment management in the context of climate change in organizations such as inter alia: i) LVBC; ii) CCTWG; iii) EAC Climate Change Unit; and iv) Lake Victoria Region Local Authority Cooperation |  | Training for approximately 30 experts organized |  | Recruitment of Water Catchment Management consultant/expert was not finalized due to delays in recruitment of project CTA and project manager. Recruitment process currently ongoing and activity scheduled to start in Q4. | Marginally Unsatisfactory (MU)
Component 2. Climate information dissemination
|  | Organize the meeting/ workshop for the Regional CC Institutions network (ICPAC, FEWSNET, DHI, RCMRD) to develop tailored climate information packages for: i) policy- and decision makers; and ii) local communities |  | Discussion on development of tailored climate information packages held with regional stakeholders and draft ToR for developing packages developed and agreed |  | LVBC organized a workshop 1-2 October in Nairobi-Kenya, for the Regional Climate Change Institutions network (ICPAC, FEWSNET, DHI, RCMRD) during which ToR to develop tailored climate information packages for: i) policy- and decision makers; and ii) local communities were developed. Strategies on downscaling regional information to tailored packages for national and community level were developed and agreed. | Satisfactory (S)
|  | Train representatives from the national meteorological agencies in each of the five Partner States on downscaling regional climate information to the national level |  | Training packages developed and training held for representatives from the national meteorological agencies in each of the five Partner States on downscaling regional climate information to the national level |  | The activity is scheduled for Q4 due to recruitment delays. To be carried out with technical guidance of the Climate Modeling consultant/expert whose recruitment process is currently ongoing. | Unsatisfactory (U)
| Other | Strengthen existing climate information dissemination mechanisms – including the Lake Victoria Basin Commission information hub – to develop an Lake Victoria Basin specific platform for climate information |  | Workshop held with climate change institutions to consider and identify appropriate climate information dissemination mechanisms |  | Workshop was held with climate change institutions (IGAD Climate Prediction and Application Centre (ICPAC), Famine Early Warning Systems Network (FEWSNET), Regional Centre for Mapping of Resources for Development (RCMRD)) and national meteorology directorate during which appropriate climate information dissemination mechanisms were identified. | Satisfactory (S)
|  | Deliver climate information for long term strategic planning to policy and decision makers in regional organizations as well as technical staff in national ministries within the Lake Victoria Basin |  | Lead institution selected to support the establishment of Lake Victoria Basin Commission climate change information hub |  | Consultative meetings were held with IGAD Climate Prediction and Application Centre (ICPAC), Famine Early Warning Systems Network (FEWSNET), Regional Centre for Mapping of Resources for Development (RCMRD). IGAD Climate Prediction and Application Centre (ICPAC) was selected to be the lead institution to support the establishment of a Climate change information hub to be hosted by Lake Victoria Basin Commission. | Satisfactory (S)
|  | Pilot innovative information-sharing mechanisms – such as the provision of climate information through mobile networks – to deliver climate information to communities in a locally relevant and accessible format |  | Piloted innovative information-sharing mechanisms developed and discussed with regional climate information bodies. |  | Options for innovative information sharing mechanisms were proposed and discussed climate change institutions in the region. The activity will be executed with the assistance of the Climate Change Communications consultant/expert whose recruitment process is currently ongoing. | Marginally Satisfactory (MS)
Component 3. Regional approach to climate change adaptation in vulnerable communities
|  | Identify project sites for each of the countries |  | Intervention site selection criteria developed, approved by Regional Policy Steering Committee and latest 5 project sites identified (one for each of the country) |  | Regional intervention site selection criteria was developed and approved by Regional Policy Steering Committee. The criteria was applied to identify and select 9 project sites across the five partner states where project interventions will be implemented. | Satisfactory (S)
|  | Documenting /lessons learned from past and current Lake Victoria Basin Commission programmes (LVWATSAN, LVEMP II, PREPARED Vulnerability Assessment) |  | Terms of Reference developed and approved by Regional Policy Steering Committee and Sectoral Council of Ministers. Hire a consultant to document lesson learnt from the past and current LVBC projects and programme. Conduct a stock take of adaptation interventions detailed in existing national strategies and action plans, recommendations from other regional projects and findings of scientific research in the Lake Victoria Basin to identify appropriate adaptation technologies to be implemented regionally |  | Terms of Reference developed and approved by Regional Policy Steering Committee and Sectoral Council of Ministers. The documentation of lessons learned from past and current Lake Victoria Basin Commission programmes will be spearheaded by the Chief Technical Advisor that was recently recruited. | Marginally Satisfactory (MS)
|  | Extension officers , District Teams and local communities trained on climate change adaptation technologies including water conservation practices, climate-smart agricultural techniques and EbA activities |  | One national training workshop held for 100 community members and staff in each country |  | Work in progress. Project has established district/ extension officers to be trained. Training will be facilitated with technical support of Climate Change Adaptation consultant/expert whose recruitment process is currently ongoing | Marginally Unsatisfactory (MU)
|  | Climate change adaptation technologies demonstrated at selected project intervention sites |  | Climate change adaptation technologies demonstrated at selected project intervention sites |  | Work in progress. Project with district teams/ extension officers are identifying existing adaption initiatives with aim of identifying best practices. Climate change adaptation technologies demonstration at selected project intervention sites will be facilitated by Climate Change Adaptation consultant/expert whose recruitment process is currently ongoing. | Marginally Unsatisfactory (MU)
Component 4. Community-based approaches to climate change adaptation
|  | Identify communities/ Community based organizations/ NGOs to small scale projects on climate change interventions |  | at least 4 small scale projects per country benefiting about 200 people both direct and indirect |  | Work in progress. This activity has been delayed due to the lengthy administrative process of formalizing partnership (development and signing of Memorandum of Understanding) between Lake Victoria basin Commission (Executing Entity) and Focal Ministries responsible for spearheading the implementation of project activities in respective partner states. Activity to be implemented in Q4 | Marginally Unsatisfactory (MU)
|  | Provide training to local communities or relevant local-level government or NGOs on how to develop a project proposal and the necessary financial, administrative and monitoring procedures for a small-scale project |  | one training workshop held for each of the Country |  | Activity was delayed due to lengthy administrative process of Signing of MOU with partner countries. Regional training scheduled for Q4. | Marginally Unsatisfactory (MU)
|  | Review project proposals and select successful project proponents |  | Projects proposal reviewed and selected |  | Work in progress. This activity will be spearheaded by the Chief Technical Advisor whose recruitment was finalized in June 2019. | Marginally Unsatisfactory (MU)
Component 5. Knowledge management and learning
|  | Identify one Research Institution in each of the Partner states |  | Identified research institutions in each of the Partner States |  | A total of 5 research institutions (one in each of the partner state) have been identified | Satisfactory (S)
|  | Establish a forum of researchers and technical experts working on climate change adaptation to coordinate climate change research initiatives across the LVB |  | Terms of Reference developed and approved by Regional Policy Steering Committee and Sectoral Council of Ministers |  | Terms of Reference were developed and approved by Regional Policy Steering Committee and Sectoral Council of Ministers | Satisfactory (S)
|  | Inception workshop |  | Inception workshop held by April 2018 |  | Inception workshop was held in June 2018 | Satisfactory (S)
|  | Project staff in place to manage the project |  | Project staff in place by 23rd March 2018 |  | Project staff recruitment concluded on 15th February 2019. However, due to administrative processes, the project staff did not assume office until June 2019. | Marginally Unsatisfactory (MU)
[6 empty] | Overall Rating | Marginally Satisfactory (MS)
Please Provide the Name and Contact information of person(s) responsible for complete ling the Rating section
|  |  | Name: | Essey Daniel
|  |  | Email: | essey.daniel@un.org
|  |  | Please justify your rating and address the following points: 1. Indicate trends, both positive and negative, in achievement of outcomes as per the project indicators. 2. Detail critical risks that have affected progress. 3. Outline response to MTR undertaken this reporting period. 4. Outline action plan to address projects with a rating of HU, U or MU. Please keep your input to 1200 words |  | The project implementation experienced a number delays in it’s first year. A number of key milestones have been achieved, including completion of inception phase, development of project site selection criteria, development of ToR for developing climate information training packages and recruitment of the PCU. However, there were challenges that resulted in delays at inception stage and implementation including: i. Funds used by any EAC institutions from any source must be debated and adopted by Council of Ministers and approved by East African Community Legislative Assembly. Since the financial approval process for EAC financial year is July 2017 to June 2018 by the time the project funds were being approved and released by Adaption Fund to UNEP, the EAC Financial year for 2017/2018 budget approval process had been completed. ii. The recruitment process under the EAC including for project is a protracted process that involves TORs to be agreed by Lake Victoria basin (LVB) Sectoral Council of Ministers which meets twice a year followed by evaluation by special committee (ad hoc Commission) established with members from countries. This process resulted in over 6-month delay in setting up the PCU iii. Funds transfer from LVBC to project countries also took significant time. During inception meeting it was agreed to develop and sign a Memorandum of Understanding (MoU) between LVBC and the project countries before sending funds. Council of ministers to agree on the directive as well as signing process took 3 months delaying the start of activities in countries. The above challenges were mitigated by i. Fast tracking the start of the project implementation, LVBC requested authorization from the 37th council of Ministers (which adopted the project supplementary budget) to start spending project funds instead of waiting for EALA supplementary budget approval ii. Recognizing that the recruitment process delays UNEP and LVBC established an interim Project management team using existing LVBC staff to coordinate project implementation. The Environment and Natural Resources Officer was appointed as a project manager and a Finance Assistant also appointed to support the project. Through this interim project management team, the LVBC managed to establish a Regional Policy Steering Committee of the Project (RPSC) consisting Permanent Secretaries from all the five partner states instead of waiting for council of Ministers meetings which are held twice a year. Through this RPSC the project managed to develop and get approval of ToRs for recruiting the Project management team and the recruitment process is currently on-going. Furthermore, through RPSC LVBC managed to establish National Coordinators and National Project Coordination teams in each country which selected implementation sites using regional approved sites selection criteria. The interim Project team also developed and facilitated signing of Memorandum of Understanding between LVBC and countries in May 2019. A meeting between the National Coordinators, the PCU and the UNEP was organized to strategize on ways to FastTrack implementation of project activities to make up for the delays in the first year. Considering the above progress, challenges and solutions implemented to address bottlenecks and delays I rate the project Marginally Satisfactory
Rating Definitions
[5 empty] | Highly Satisfactory (HS) | Project actions/activities planned for current reporting period are progressing on track or exceeding expectations to achieve all major outcomes/outputs for given reporting period, without major shortcomings. The project can be presented as “good practice”.
[5 empty] | Satisfactory (S) | Project actions/activities planned for current reporting period are progressing on track to achieve most of its major outcomes/outputs with only minor shortcomings.
[5 empty] | Marginally Satisfactory (MS) | Project actions/activities planned for current reporting period are progressing on track to achieve most major relevant outcomes/outputs, but with either significant shortcomings or modest overall relevance.
[5 empty] | Marginally Unsatisfactory (MU) | Project actions/activities planned for current reporting period are not progressing on track to achieve major outcomes/outputs with major shortcomings or is expected to achieve only some of its major outcomes/outputs.
[5 empty] | Unsatisfactory (U) | Project actions/activities planned for current reporting period are not progressing on track to achieve most of its major outcomes/outputs.
[5 empty] | Highly Unsatisfactory (U) | Project actions/activities planned for current reporting period are not on track and shows that it is failing to achieve, and is not expected to achieve, any of its outcomes/outputs.

## Lessons Learned
QUALITATIVE MEASURES and LESSONS LEARNED
Please complete the following section every reporting period
Implementation and Adaptive Management | Response
What implementation issues/lessons, either positive or negative, affected progress? | 1) The project had a delay of 7 months between approval by AF and the inception meeting. According to the East African Community (EAC) financial rules and regulations, before funds are used by any EAC institutions from any source it must be debated and adopted by Council of Ministers and approved by East African Community Legislative Assembly (EALA). The financial approval process for EAC financial year July 2017 to June 2018 ended in March 2017. By the time the project funds were being approved and released by Adaption Fund to UNEP, the EAC Financial year for 2017/2018 budget approval process had been completed. To fast track the start of the project implementation, LVBC requested authorization from the 37th council of Ministers (which adopted the project supplementary budget) to start spending project funds instead of waiting for EALA supplementary budget approval which was done in October 2018. This enabled the project inception workshop to be held on 27th and 28th June 2018 just after Council of Ministers meeting held on 8th May 2018. 2) Recruitment process under the EAC including for project is a protracted process that involves TORs to be agreed by Lake Victoria basin (LVB) Sectoral Council of Ministers which meets twice a year followed by evaluation by special committee (ad hoc Commission) established with members from countries. This process resulted in over 6-month delay in setting up the PCU. Recognizing that the recruitment process takes about six months; UNEP and LVBC established an interim Project management team using existing LVBC staff to coordinate project implementation. The Environment and Natural Resources Officer was appointed as a project manager and a Finance Assistant also appointed to support the project. Through this interim project management team, the LVBC managed to establish a Regional Policy Steering Committee of the Project (RPSC). RPSC includes Permanent Secretaries from all the five partner states who make decisions on the project implementation instead of waiting for council of Ministers meetings which are held twice a year.
Were there any delays in implementation? If so, include any causes of delays. What measures have been taken to reduce delays? | Yes. The project had to establish Project Regional Policy Steering Committee (RPSC is made of Permanent Secretaries) to provide decisions. The process to establish RPSC was concluded on 26th April 2018. The RPSC in it's first meeting directed Lake Victoria Basin Commission to Establish National Project technical Coordination team in all 5 Countries. The process to establish national project coordination teams was concluded in July 2018 and capacity was built on the same team to understand project in September 2018. Other delays were due to the procurement regulations. According to procurement rules and regulations of East African Community, Terms of References (ToRs) have to be approved by Project Steering Committee (Meeting of Permanent Secretaries) and adopted by Sectoral Council of Ministers. The ToRs of Project Manager, Financial Assistant and Chief Technical advisor were approved by Project Steering Committee on 27th April 2018 and approval of contracts award to Consultants on 24th May 2019. The LVBC and UNEP to reduce the impact of the delay established interim Project Unit with LVBC staff to manage the project.
Describe any changes undertaken to improve results on the ground or any changes made to project outputs (i.e. changes to project design) | To improve results on the ground, the project established coordination team in each countries and build capacity on the same. The project also facilitated the countries to come up with strategies to project is successfully implemented. These strategies included: (a) regional criteria for site selection were developed and agreed with all countries (b) Memorandum of Understanding which stipulate how project will be implemented Between Lake Victoria Basin Commission and Countries were developed and signed before disbursing project funds (c) ToRs for Adaption, Watershed, Modeling and Communication consultants were developed and approved to ensure good quality consultants to support project activities (d) In each project site team of extension officers were identified to support project implementation. Capacity building will be provided by aforesaid Consultants; and (e) to compensate the time lost, now component three and four are implemented together.
How have gender considerations been taken into consideration during the reporting period? What have been the lessons learned as a consequence of inclusion of such considerations on project performance or impacts? | Since activities on ground have just started, project decided to included gender specialist (Community Development Officer) in the extension team who is responsible to follow the agreed criteria to select project beneficiaries.
Please complete the following section at mid-term and project completion
Lessons for Adaptation | Response
Climate Resilience Measures
What have been the lessons learned, both positive and negative, in implementing climate adaptation measures that would be relevant to the design and implementation of future projects/programmes for enhanced resilience to climate change? | N/A.
What is the potential for the climate resilience measures undertaken by the project/programme to be replicated and scaled up both within and outside the project area? | N/A
Concrete Adaptation Interventions
What have been the lessons learned, both positive and negative, in implementing concrete adaptation interventions that would be relevant to the design and implementation of future projects/programmes implementing concrete adaptation interventions? | N/A
What is the potential for the concrete adaptation interventions undertaken by the project/programme to be replicated and scaled up both within and outside the project area? | N/A
Community/National Impact
What would you consider to be the most successful aspects for the target communities? | N/A
What measures are/have been put in place to ensure sustainability of the project/program results? | N/A
What measures are being/could have been put in place to improve project/program results? | N/A
Knowledge Management
How has existing information/data/knowledge been used to inform project development and implementation? What kinds of information/data/knowledge were used? | N/A
If learning objectives have been established, have they been met? Please describe. | N/A
Describe any difficulties there have been in accessing or retrieving existing information (data or knowledge) that is relevant to the project. Please provide suggestions for improving access to the relevant data. | N/A
Has the identification of learning objectives contributed to the outcomes of the project? In what ways have they contributed? | N/A

## Results Tracker
Results Tracker for Adaptation Fund (AF) Projects
Goal: Assist developing-country Parties to the Kyoto Protocol that are particularly vulnerable to the adverse effects of climate change in meeting the costs of concrete adaptation projects and programmes in order to implement climate-resilient measures. Impact: Increased resiliency at the community, national, and regional levels to climate variability and change.
Important: Please read the following guidance document (also posted on the Adaptation Fund website) before entering your data
Link: http://www.adaptation-fund.org/sites/default/files/Results%20Framework%20and%20Baseline%20Guidance%20final.pdf
Adaptation Fund Strategic Results Framework
Project ID | S1-32AFB-00009 / SB-008892
Implementing Entity | UNEP
Type of implementing entity | MIE
Country
Region | Africa
Sector | Water management
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Impact: Increased resiliency at the community, national, and regional levels to climate variability and change | Core Indicator: No. of beneficiaries |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project
|  | Total | 0 | 0 | 0 | Total |  | 1780 |  | Total |  |  |  | Total
|  | % of female beneficiaries | 0% | 0% | 0% | % of female beneficiaries | 50% | 50% |  | % of female beneficiaries |  |  |  | % of female beneficiaries
|  | % of Youth beneficiaries | 0% | 0% | 0% | % of Youth beneficiaries |  |  |  | % of Youth beneficiaries |  |  |  | % of Youth beneficiaries
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 1: Reduced exposure to climate-related hazards and threats | Indicator 1: Relevant threat and hazard information generated and disseminated to stakeholders on a timely basis | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness
|  | Total | 0 | Drought | 2: Partially effective | Total | 25 | Drought | 5: Very effective | Total |  |  |  | Total
|  | % of female targeted | 0% |  |  | % of female targeted | 50% |  |  | % of female targeted |  |  |  | % of female targeted
Output 1.1 Risk and vulnerability assessments conducted and updated | Indicator 1.1: No. of projects/programmes that conduct and update risk and vulnerability assessments | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | 1 | Water management | Regional | 3: Risk and vulnterability assessments completed or updated | 3 | Water management | Regional | 3: Risk and vulnterability assessments completed or updated
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
Output 1.2 Targeted population groups covered by adequate risk reduction systems | Core Indicator 1.2: No. of Early Warning Systems | No. of adopted Early Warning Systems | Category targeted | Hazard | Drought | No. of adopted Early Warning Systems | Category targeted | Hazard | Drought | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  | 0 | 1: Risk knowledge | Geographical coverage | Regional | 1 | 1: Risk knowledge | Geographical coverage | Regional |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities | 0 |  |  | Number of municipalities | 9 |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | No. of adopted Early Warning Systems | Category targeted | Hazard | Drought | No. of adopted Early Warning Systems | Category targeted | Hazard | Drought | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  | 0 | 3: Dissemination and communication | Geographical coverage | Regional | 1 | 3: Dissemination and communication | Geographical coverage | Regional |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities | 0 |  |  | Number of municipalities | 9 |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | No. of adopted Early Warning Systems | Category targeted | Hazard | Drought | No. of adopted Early Warning Systems | Category targeted | Hazard | Drought | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  | 0 | 4: Response capability | Geographical coverage | Regional | 1 | 4: Response capability | Geographical coverage | Regional |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities | 0 |  |  | Number of municipalities | 9 |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | No. of adopted Early Warning Systems | Category targeted | Hazard | Inland flooding | No. of adopted Early Warning Systems | Category targeted | Hazard | Inland flooding | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  | 0 | 2: Monitoring and warning service | Geographical coverage | Regional | 1 | 2: Monitoring and warning service | Geographical coverage | Regional |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities | 0 |  |  | Number of municipalities | 9 |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 2: Strengthened institutional capacity to reduce risks associated with climate-induced socioeconomic and environmental losses | Indicator 2: Capacity of staff to respond to, and mitigate impacts of, climate-related events from targeted institutions increased | Number of staff targeted |  | Sector | Capacity level | Number of staff targeted |  | Sector | Capacity level | Number of staff targeted |  | Sector | Capacity level | Number of staff targeted |  | Sector | Capacity level
|  | Total | 20 | Water management | 2: Low capacity | Total | 125 | Water management | 4: High capacity | Total |  |  |  | Total
|  | % of female targeted | 40% |  |  | % of female targeted | 50% |  |  | % of female targeted |  |  |  | % of female targeted
Output 2.1 Strengthened capacity of national and sub-national centres and networks to respond rapidly to extreme weather events | Indicator 2.1.1: No. of staff trained to respond to, and mitigate impacts of, climate-related events | Total staff trained | % of female staff trained | Type |  | Total staff trained | % of female staff trained | Type |  | Total staff trained | % of female staff trained | Type |  | Total staff trained | % of female staff trained | Type
|  | 0 | 0% | Public |  | 25 | 50% | Public
| Indicator 2.1.2: No. of targeted institutions with increased capacity to minimize exposure to climate variability risks | Type | Scale | Sector | Capacity level | Type | Scale | Sector | Capacity level | Type | Scale | Sector | Capacity level | Type | Scale | Sector | Capacity level
|  | Public | Regional | Water management | 2: Low capacity | Public | Regional | Water management | 4: High capacity
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 3: Strengthened awareness and owernship of adaptation and climate risk reduction processes | Indicator 3.1: Increase in application of appropriate adaptation responses | Percentage of targeted population applying adaptation measures |  | Sector |  | Percentage of targeted population applying adaptation measures |  | Sector |  | Percentage of targeted population applying adaptation measures |  | Sector |  | Percentage of targeted population applying adaptation measures |  | Sector
|  | 0% |  | Water management |  | 100% |  | Water management
Output 3: Targeted population groups participating in adaptation and risk reduction awareness activities | Indicator 3.1.1: Percentage of targeted population awareness of predicted adverse impacts of climate change, and of appropriate responses | No. of targeted beneficiaries | % of female participants targeted | Level of awareness |  | No. of targeted beneficiaries | % of female participants targeted | Level of awareness |  | No. of targeted beneficiaries | % of female participants targeted | Level of awareness |  | No. of targeted beneficiaries | % of female participants targeted | Level of awareness
|  | 1500 | 50% | 2: Partially not aware |  | 1500 | 50% | 5: Fully aware
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Target performance at completion
Outcome 4: Increased adaptive capacity within relevant development sector services and infrastructure assets | Indicator 4.1: Increased responsiveness of development sector services to evolving needs from changing and variable climate | Project/programme sector | Geographical scale | Response level |  | Project/programme sector | Geographical scale | Response level |  | Project/programme sector | Geographical scale | Response level |  | Project/programme sector | Geographical scale | Response level
|  | Water management | Regional | 3: Moderately responsive (Some defined elements) |  | Water management | Regional | 4: Mostly responsive (Most defined elements)
| Core Indicator 4.2: Assets produced, developed, improved or strengthened | Sector | Targeted asset | Changes in asset (quantitative or qualitative) |  | Sector | Targeted asset | Changes in asset (quantitative or qualitative) |  | Sector | Targeted asset | Changes in asset (quantitative or qualitative) |  | Sector | Targeted asset | Changes in asset (quantitative or qualitative)
|  | Water management | 2: Physical asset (produced/improved/strenghtened) | 3: Moderately improved |  | Water management | 2: Physical asset (produced/improved/strenghtened) | 4: Mostly Improved
Output 4: Vulnerable development sector services and infrastructure assets strengthened in response to climate change impacts, including variability | Indicator 4.1.1: No. and type of development sector services to respond to new conditions resulting from climate variability and change | Number of services | Type |  | Sector | Number of services | Type |  | Sector | Number of services | Type |  | Sector | Number of services | Type |  | Sector
|  | 0 | Community |  | Water management | 3 | Community |  | Water management
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Target performance at completion
Outcome 5: Increased ecosystem resilience in response to climate change and variability-induced stress | Indicator 5: Ecosystem services and natural resource assets maintained or improved under climate change and variability-induced stress | Natural resource improvement level |  | Sector | Type | Natural resource improvement level |  | Sector | Type | Natural resource improvement level |  | Sector | Type | Natural resource improvement level |  | Sector | Type
|  | 2: Partially effective |  | Water management | land | 5: Very effective |  | Water management | land
Output 5: Vulnerable ecosystem services and natural resource assets strengthned in response to climate change impacts, including variability | Core Indicator 5.1: Natural Assets protected or rehabilitated | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Cultivated land/Agricultural land | 50 | ha rehabilitated | 2: Partially effective | Cultivated land/Agricultural land | 1000 | ha rehabilitated | 5: Very effective
|  | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Forests | 100 | ha rehabilitated | 2: Partially effective | Catchment area/Watershed/Aquifer | 500 | ha rehabilitated | 5: Very effective
|  | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Baseline information |  |  |  | Targeted performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 6: Diversified and strengthened livelihoods and sources of income for vulnerable people in targeted areas | Indicator 6.1: Increase in households and communities having more secure access to livelihood assets | No. of targeted households | % of female headed households | Improvement level |  | No. of targeted households | % of female headed households | Improvement level |  | No. of targeted households | % of female headed households | Improvement level |  | No. of targeted households | % of female headed households | Improvement level
|  | 1500 |  | 2: Limited improvement |  | 1500 | 50% | 5: Very high improvement
| Indicator 6.2: Increase in targeted population's sustained climate-resilient alternative livelihoods | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
|  | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
|  | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
|  | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
Output 6 Targeted individual and community livelihood strategies strengthened in relation to climate change impacts, including variability | Indicator 6.1.1: No. and type of adaptation assets created or strengthened in support of individual or community livelihood strategies | Number of Assets | Type of Assets | Sector | Adaptation strategy | Number of Assets | Type of Assets | Sector | Adaptation strategy | Number of Assets | Type of Assets | Sector | Adaptation strategy | Number of Assets | Type of Assets | Sector | Adaptation strategy
|  | 3 | Adaptation strategies | Water management | Capacity development | 3 | Adaptation strategies | Water management | Capacity development
| Core Indicator 6.1.2: Increased income, or avoided decrease in income | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | 1500 | Agricultural-related |  | 400 | 1500 | Agricultural-related |  | 500
|  | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 7: Improved policies and regulations that promote and enforce resilience measures | Indicator 7: Climate change priorities are integrated into national development strategy | Integration level |  |  |  | Integration level |  |  |  | Integration level |  |  |  | Integration level
Output 7:Improved integration of climate-resilience strategies into country development plans | Indicator 7.1: No. of policies introduced or adjusted to address climate change risks | No. of Policies introduced or adjusted | Sector | Scale | Type | No. of Policies introduced or adjusted | Sector | Scale | Type | No. of Policies introduced or adjusted | Sector | Scale | Type | No. of Policies introduced or adjusted | Sector | Scale | Type
| Indicator 7.2: No. of targeted development strategies with incorporated climate change priorities enforced | No. of Development strategies | Regulation |  | Effectiveness | No. of Development strategies | Regulation |  | Effectiveness | No. of Development strategies | Regulation |  | Effectiveness | No. of Development strategies | Regulation |  | Effectiveness
Glacier lake outburst flood
|  | Inland flooding | fr | biological assets |  | Company policy | 5: Fully enforced (All elements implemented)
|  | Salinization | Decrease | land |  | Communication & Information policy | 4: Enforced (Most elements implemented)
|  | Drought | Same | water areas |  | Defense policy | 3: Partially enforced (Some elements implemented)
|  | Wind |  | subsoil assets | increased adpative capacity | Domestic policy | 2: Partially not enforced (Most elements not implemented) |  | Agribusiness
|  | Coastal flooding |  | air | achieved | Economic policy | 1: Not enforced (No elements implemented) |  | Agricultural-related | Financial capital
|  | Storm surge | Please choose |  | enhanced level of protection | Education policy |  |  | Agriculture | Human capital
|  | Hurricane | Selected | [5 empty] | Aquaculture | Physical capital
|  |  | Not relevant |  |  | 5: All (Fully integrated) |  |  | Construction/repairing business | Social capital
[6 empty] | 4: Most |  |  | Cultivation | Natural capital
[6 empty] | 3: Some |  |  | Fishing | Personal capital
Select | 5: All | Select |  |  | Community | 2: Most not integrated |  | Other | Forestry | Adaptation strategies
1 | 4: Almost all | Private | Type | Yes | Multi-community | 1: None |  | Agriculture | Handicrafts
2 | 3: Half | Public | Scale | No | Departmental |  |  | Coastal management | Livestock production
3 | 2: Some | NGO | Sector |  | National |  |  | Disaster risk reduction | Manufacturing
4 | 1: None |  |  |  |  | 5: Very high improvement | Established | Food security | other
|  | National |  |  |  | 4: High improvement | Maintained | Health | Services
|  | Regional |  |  |  | 3: Moderate improvement | Improved | Urban development | Tourism-related
|  | Local |  |  |  | 2: Limited improvement |  | Water management | Trading
[6 empty] | 1: No improvement |  | Multi-sector
|  | 1 -generated information is irrelevant, and neither the stakeholders reached nor the timeframe managed were achieved | 1: No info transferred on time | 4: High capacity | 5: Fully aware | 5: Highly responsive (All defined elements ) | 5: Fully improved | Roads | 5: Very effective
Asia-Pacific | NIE | 2 -the existence of some challenge in any of the three aspects of the indicator (generation of dissemination, stakeholders reached or timeframe managed) | 2: Somewhat info transferred | 3: Medium capacity | 4: Mostly aware | 4: Mostly responsive (Most defined elements) | 4: Mostly Improved | Gov Buildings | 4: Effective
Latin America and Caribbean | RIE | 3 -relevant information is generated and disseminated to all identified stakeholders on timely basis | 3: Info transferred on time | 2: Low capacity | 3: Partially aware | 3: Moderately responsive (Some defined elements) | 3: Moderately improved | Causeways | 3: Moderately effective
Africa | MIE |  |  | 1: No capacity | 2: Partially not aware | 2: Partially responsive (Lacks most elements) | 2: Somewhat improved | Airports | 2: Partially effective
Eastern Europe |  |  |  |  | 1: Aware of neither | 1: Non responsive (Lacks all elements ) | 1: Not improved | Schools | 1: Ineffective
| ha protected | [6 empty] | Training Centres
| ha rehabilitated | [5 empty] | Monitoring/Forecasting capacity | Hospitals
Afghanistan, Islamic Rep. of | km protected | [5 empty] | Policy/regulatory reform | Drinking water systems
Angola | km rehabilitated | 1: Risk knowledge | 1: No plans conducted or updated |  |  |  | Capacity development | Other
Albania |  | 2: Monitoring and warning service | 2: Undertaking or updating of assessments in progress |  |  | Communication & Information policy | Sustainable forest management
Argentina |  | 3: Dissemination and communication | 3: Risk and vulnterability assessments completed or updated |  |  | Domestic policy | Strengthening infrastructure | 1: Health and Social Infrastructure (developed/improved)
Armenia | Forests | 4: Response capability |  |  |  | Economic policy | Supporting livelihoods | 2: Physical asset (produced/improved/strenghtened)
Antigua and Barbuda | Mangroves |  |  |  |  | Education policy | Mangrove reforestation
Azerbaijan | Coasts |  | From 0 to 0.5% |  |  | Energy policy | Coastal drainage and infrastructure
Burundi | Rangelands |  | From 0.5 to 1% |  |  | Environmental policy | Irrigation system
Benin | Cultivated land/Agricultural land |  | From 1% to 5% |  |  | Foreign policy | Community-based adaptation
Burkina Faso | Catchment area/Watershed/Aquifer |  | From 5% to 10% |  |  | Health policy | Erosion control
Bangladesh | Protected areas/National parks |  | From 10% to 20% |  |  | Housing policy | Soil water conservation
Bulgaria | Other |  | From 20% to 30% |  |  | Human resource policies | Microfinance
Bahrain |  |  | From 30% to 40% |  |  | Information policy | Special Program for women
Bahamas, The |  |  | From 40% to 50% |  |  | Macroeconomic policy | Livelihoods
Bosnia and Herzegovina |  |  | Above 50% |  |  | Monetary policy | Water storage
Belarus | [5 empty] | Population policy | ICT and information dissemination
Belize | [5 empty] | Private policy
Bolivia | [5 empty] | Public policy
Brazil | [5 empty] | Science policy
Barbados | [5 empty] | Social policy
Bhutan |  | 3- relevant information is generated and disseminated to all identified stakeholders on timely basis |  |  |  | Transportation policy
Botswana |  | describe |  |  |  | Urban policy
Central African Republic |  | 2- the existence of some challenge in any of the three aspects of the indicator |  |  |  | Water policy
Chile |  | describe |  |  |  | Other policy
China, People's Republic of |  | 1- generated information is irrelevant and neither the stakeholders reached nor the timeframe managed were achieved
Cote d'Ivoire |  | describe
Cameroon
Congo, Dem. Rep. of
Congo, Republic of
Cook Islands
Colombia
Comoros
Cape Verde
Costa Rica
Cuba
Czech Republic
Djibouti
Dominica
Dominican Republic
Algeria
Ecuador
Egypt
Eritrea
Estonia
Ethiopia
Fiji
Micronesia, Fed. States of
Gabon
Georgia
Ghana
Guinea
Gambia, The
Guinea-Bissau
Equatorial Guinea
Grenada
Guatemala
Guyana
Honduras
Croatia
Haiti
Hungary
Indonesia
India
Iran, Islamic Republic of
Jamaica
Jordan
Kazakhstan
Kenya
Kyrgyz Republic
Cambodia
Kiribati
Saint Kitts and Nevis
Korea, Republic of
Lao People's Democratic Republic
Lebanon
Liberia
Libya
Saint Lucia
Sri Lanka
Lesotho
Lithuania
Latvia
Morocco
Moldova
Madagascar
Maldives
Mexico
Marshall Islands
Macedonia, former Yugoslav Republic of
Mali
Malta
Myanmar
Montenegro
Mongolia
Mozambique
Mauritania
Mauritius
Malawi
Malaysia
Namibia
Niger
Nigeria
Nicaragua
Niue
Nepal
Nauru
Oman
Pakistan
Panama
Peru
Philippines
Palau
Papua New Guinea
Poland
Korea, Dem. People's Rep. of
Paraguay
Romania
Russian Federation
Rwanda
Saudi Arabia
Sudan
Senegal
Solomon Islands
Sierra Leone
El Salvador
San Marino
Serbia
Sao Tome and Principe
Suriname
Slovak Republic
Slovenia
Swaziland
Seychelles
Syrian Arab Republic
Chad
Togo
Thailand
Tajikistan
Turkmenistan
Tonga
Trinidad and Tobago
Tunisia
Turkey
Tuvalu
Tanzania
Uganda
Ukraine
Uruguay
Uzbekistan
Saint Vincent and the Grenadines
Venezuela
Vietnam
Vanuatu
Samoa
Yemen, Republic of
South Africa
Zambia
Zimbabwe
Timor-Leste
Note on I21: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Value to be updated once baseline assessment complete
Note on K21: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Value to be updated once baseline assessment complete

## Units for Indicators
Fund Outcome Indicator Units
Ecosystem services and natural assets maintained or improved under climate change and variability-induced stress
Fund Output Indicator Units
Component 1: . Number of staff trained to respond to, and mitigate impacts of, climate-related events Component 2: Relevant threat and hazard information generated and disseminated to stakeholders on a timely basis Component 3: Number and type of natural resource assets created, maintained or improved to withstand conditions resulting from climate variability and change Component 4: Number and type of natural resource assets created, maintained or improved to withstand conditions resulting from climate variability and change Component 5: Number of news outlets in the local press and media that have covered the topic
1. Strengthened institutional and technical capacity to integrate climate resilience into transboundary water catchment management. Outcome 1. Strengthened institutional and technical capacity to integrate climate resilience into transboundary water catchment management.
2. Improved delivery of accurate and timely climate information to regional and national policymakers, technical officers and local communities. Outcome 2. Improved delivery of accurate and timely climate information to regional and national policymakers, technical officers and local communities.
3. Climate change adaptation technologies transferred to communities to reduce their vulnerability to climate change. Outcome 3. Climate change adaptation technologies transferred to communities to reduce their vulnerability to climate change.
4. Regional resilience to climate change promoted through innovative, community‑based projects. Outcome 4. Regional resilience to climate change promoted through innovative, community based projects.
5. Improved knowledge management frameworks for the collection and maintenance of regional knowledge in transboundary water catchment management and climate change adaptation practices. Outcome 5. Improved knowledge management frameworks for the collection and maintenance of regional knowledge in transboundary water catchment management and climate change adaptation practices.