## Overview
Project Performance Report (PPR)
| Period of Report (Dates) | August 2014 to August 2015
| Project Title: | Addressing Climate Change Impacts on Marginalized Agricultural Communities Living in the Mahaweli River Basin of Sri Lanka
| Project Summary: | This is a resilience building project against natural hazards. The objective of this project is to secure community livelihoods and food security against climate change-induced rainfall variability leading to longer droughts and more intense rainfall. The project has two Components i) "Develop household food security and build resilient livelihoods for rain-fed farming households" and ii) "Build institutional capacity in village, local, regional service delivery to reduce risks associated with climate-induced rainfall variability"
|  |  | Countries | Project Type: |  | GEF Focal Area: | GEF 4 Focal Areas | GEF 2 / 3 Operational Programme: | Overall Rating of the project in the evaluation by the project evaluator: | GEF-4 Focal Area Strategic Program: | GEF-3 Focal Area Strategic Program:
| Database Number: |  | Afghanistan | FP | Yes | Biodiversity | 1 | 1 | U | BD-SP1-PA Financing | 1: Arid & semi-arid ecosystems
Implementing Entity (IE) [name]: |  | United Nations Word Food Programme (WFP) | Albania | MSP | No | Climate Change Adaptation | 2 | 2 | S | BD-SP2-Marine PA | 2: Coastal, marine & freshwater ecosystems
| Type of IE: | Multilateral | Algeria | EA |  | Climate Change Mitigation | 3 | 3 | MU | BD-SP3-PA Networks | 3: Forest ecosystems
| Country(ies): | Sri Lanka | Angola |  |  | International Waters | 5 | 5 | Good | BD-SP5-Markets | 13: Conservation and Sustainable Use of Biological Diversity Important to Agriculture
Relevant Geographic Points (i.e. cities, villages, bodies of water): |  | Nuwara Eliya and Polonnaruwa districts (Walapane, Medirigiriya and Lankapura Divisions ) | Argentina |  |  | Multiple Focal Area |  |  |  | BD-SP7-Invasive Alien Species(IAS) | 6: Promoting the adoption of renewable energy by removing barriers and reducing implementation costs
[8 empty] | CC-SP2- Industrial EE | 8: Water body based operational program
| Project Milestones | [6 empty] | CC-SP3-RE,CC-SP4-Biomass | 9: Integrated Land and Water multiple focal area
| Milestone |  | Bahamas | [6 empty] | CC-SP5-Transport | 10: Contaminants based operational program
AFB Approval Date:
14 -Dec-2012
IE-AFB Agreement Signature Date: |  | 2012-12-21 | [6 empty] | CC-SP6-LULUCF | 12: Integrated Ecosystem Management
Start of Project/Programme: |  | 2014-08-11 | [6 empty] | Cross cutting capacity building | 14: Persistent Organic Pollutants
Mid-term Review Date (if planned): |  | N/A
| Terminal Evaluation Date: | 2017-09-11
|  | List documents/ reports/ brochures / articles that have been prepared about the project. | Cyprus
|  | Inception workshop report. Agreement signed by World Food Programme and Government of Sri Lanka. Addendum to Agreement signed by World Food Programme and Government of Sri Lanka. Standard Operating Procedures of the project signed by World Food Programme and Government of Sri Lanka. | Czech Republic
List the Website address (URL) of project. |  |  | Democratic People's Republic of Korea
Democratic Republic of the Congo
Denmark
| Project contacts: |  | Djibouti
National Project Manager |  |  | Dominica
| Name: | Mr. Lakshan Fernando | Dominican Republic
| Email: | lakshanlsf@gmail.com | Ecuador
| Date: | 11th Aug 2015 | Egypt
| Government DA |  | El Salvador
| Name: | Mr. Udaya R. Seneviratne | Equatorial Guinea
| Email: | secretary@environmentmin.gov.lk | Eritrea
| Date: | 11th Aug 2015 | Estonia
| Implementing Entity |  | Ethiopia
| Name: | Mr. P. Vijendran | Fiji
| Email: | vijendran.paramasamy@wfp.org | Finland
| Date: | 11th Aug 2015 | France
| Executing Agency |  | Gambia
| Name: | Dr. Sunimal Jayathunga | Georgia
| Email: | dirccsd@environmentmin.gov.lk | Germany
| Date: | 11th Aug 2015 | Ghana
| Executing Agency |  | Greece
| Name: |  | Grenada
| Email: |  | Guatemala
| Date: |  | Guinea
| Executing Agency |  | Guinea Bissau
| Name: |  | Guyana
| Email: |  | Haiti
| Date: |  | Honduras
Hungary
Iceland
India
Indonesia
Iran (Islamic Republic of)
Iraq
Ireland
Israel
Italy
Jamaica
Japan
Jordan
Kazakhstan
Kenya
Kiribati
Kuwait
Kyrgyzstan
Lao People’s Democratic Republic
Latvia
Lebanon
Lesotho
Liberia
Libyan Arab Jamahiriya
Liechtenstein
Lithuania
Luxembourg
Madagascar
Malawi
Malaysia
Maldives
Mali
Malta
Marshall Islands
Mauritania
Mauritius
Mexico
Micronesia, Federated States of
Monaco
Mongolia
Montenegro
Morocco
Mozambique
Myanmar
Namibia
Nauru
Nepal
Netherlands
New Zealand
Nicaragua
Niger
Nigeria
Norway
Oman
Pakistan
Palau
Panama
Papua New Guinea
Paraguay
Peru
Philippines
Poland
Portugal
Qatar
Republic of Korea
Republic of Moldova
Romania
Russian Federation
Rwanda
Saint Kitts and Nevis
Saint Lucia
Saint Vincent and the Grenadines
Samoa
San Marino
Sao Tome and Principe
Saudi Arabia
Senegal
Serbia
Seychelles
Sierra Leone
Singapore
Slovakia
Slovenia
Solomon Islands
Somalia
South Africa
Spain
Sri Lanka
Sudan
Suriname
Swaziland
Sweden
Switzerland
Syrian Arab Republic
Tajikistan
Thailand
The former Yugoslav Republic of Macedonia
Timor-Leste
Togo
Tonga
Trinidad and Tobago
Tunisia
Turkey
Turkmenistan
Tuvalu
Uganda
Ukraine
United Arab Emirates
United Kingdom of Great Britain and Northern Ireland
United Republic of Tanzania
United States of America
Uruguay
Uzbekistan
Vanuatu
Venezuela, Bolivarian Republic of
Viet Nam
Yemen
Zambia
Zimbabwe

## FinancialData
Financial information: cumulative from project start to [11th Aug 2015]
DISBURSEMENT OF AF GRANT FUNDS
How much of the total AF grant as noted in Project Document plus any project preparation grant has been spent to date?
Estimated cumulative total disbursement as of [11th Aug 2015] | 309231
Add any comments on AF Grant Funds. (word limit=200) | After signing the SOP and distributing the first instalment by the MIE to the EE, presidential elections were announced in the country - two years ahead of schedule. As per government regulations, all government recruitments (including project staff) were paused until the elections had taken place in January 2015. After election of the new President, an interim government was formed and had revised the priorities of government ministries. As a result, it took a while before the newly assigned officials became familiar with the project and its objectives. Pending Parliamentary elections in August, 2015, the interim government was dissolved in June, 2015. Subsequently, a new Parliament was formed and new ministry portfolios were once again established, resulting in further administrative delays. However, key staff of the Project Support Unit (PSU) were recruited and a fully functional PSU was established by the end of July 2015. Due to multiple changes in administrations coinciding with the commencement of the project, progress in implementation was very slow during the reporting period. As a result, the funds disbursed to the EE were not utilized as originally planned and the results under components 1&2 were also not produced as programmed. As of reporting date, the EE has settled the account until 30th June 2015 with the supporting documents.
INVESTMENT INCOME | 0
Amount of annual investment income generated from the Adaptation Fund’s grant
EXPENDITURE DATA
List output and corresponding amount spent for the current reporting period | ITEM / ACTIVITY / ACTION | AMOUNT in US $ | In LKR
| 1.1.5 Provide drought tolerant seeds equipment planting material, organic farming tool kit to farming households in a concessionary rate/prices and provide financial assistance for carrying out such activities | 7559.9929 | 1065959 |  | 0
| Execution Cost | 26790.2477 | 3777424.92 | 26790.2411
| TOTAL | 34350.2406 | 4843383.92
PLANNED EXPENDITURE SCHEDULE
List outputs planned and corresponding projected cost for the upcoming reporting period | ITEM / ACTIVITY / ACTION | PROJECTED COST | Est. Completion Date
| 1.1 Develop diversified home garden based agro forestry in target DSDs to build household adaptive capacity to climate change | 354609.9291 | 2016-08-01
| 1.2 Introduce and promote drought tolerant cop varieties and agronomic practices to counter effects of rainfall variability | 141843.9716 | 2016-08-01
| 1.3 Identify and promote climate-resilient alternative income sources among rural farm household dependent on rain fed agriculture | 248226.9504 | 2016-08-01
| 1.4 Promote improved post-harvest technologies as viable climate-resilient livelihood sources for fare women | 212765.9574 | 2016-08-01
| 1.5 Build community assets and livelihood resources through case-for-work to support climate risk reduction measures | 283687.9433 | 2016-08-01
| 2.1 Train and mobilize officers at village, division and provincial level to design, and monitor local adaptation strategies | 127659.5745 | 2016-08-01
| 2.2 Strengthen farmer organizations with information, training and equipment to implement adaptation strategies | 177304.9645 | 2016-08-01
| 2.3 Pilot integrated watershed management models in micro watersheds to safeguard climate sensitive livelihood assets such as land and water | 425531.9149 | 2016-08-01
| 2.4 Risk Assessment and Adaptation planning conducted with target communities | 21276.5957 | 2016-08-01
| 2.5 Document and disseminate lessons of climate resilient livelihood development and watershed management approaches and best practices | 56737.5887 | 2016-08-01
| 2.6 Design and implement early warning systems for climate induced risk of landslide and drought in Mahaweli Basin | 78014.1844 | 2016-08-01
| Total Activity Cost | 2127659.5745
| Execution Cost | 202127.6596
| TOTAL | 2329787.234
ACTUAL CO-FINANCING (If the MTR or TE have not been undertaken this reporting period, DO NOT report on actual co-financing.)
How much of the total co-financing as committed in the Project Document has actually been realized? | N/A
Estimated cumulative actual co-financing as verified during Mid-term Review (MTR) or Terminal Evaluation (TE).
Add any comments on actual co-financing in particular any issues related to the realization of in-kind, grant, credits, loans, equity, non-grant instruments and other types of co-financing. (word limit=200) | N/A
Note on E9: vijendran.paramasamy:This amount was disbursed to EE by MIE during the reporting period. It does not include MIE fee.
Note on F18: vijendran.paramasamy: Exchange rate 1$ equal to Sri Lankan Rupees 141

## Risk Assesment
RISK ASSESMENT
IDENTIFIED RISKS
List all Risks identified in project preparation phase and what steps are being taken to mitigate them
Identified Risk | Current Status | Steps Taken to Mitigate Risk
Scientific & technical information in relation to climate change & its effects on the Basin remain incomplete and uncertain | Low | During the inception process National technical expertise interacted with each other to establish and ensure the availability of required technical information related to the project implementation.
Lack of awareness among participating communities and local officials on CC and potential impacts | Medium | The inception process paid attention on comprehensive community consultation and sensitization. The community representatives and local officials actively participated in the inception process. During the inception process, ground level awareness workshops were conducted to raise the awareness of community representatives and the local officials. Following this, pre-inception workshops were held to accommodate the inputs of community as well as the local officials. In the final inception workshop the national technical experts were also involved in validating inputs gathered from the field. This comprehensive inception process helped to raise awareness at various levels and mitigate the risk.
Local government in project implementation areas fails to prioritize climate change policies in their strategies and plans | Low | During the inception process special attention was paid to engage local government staff especially divisional and district staff working on environment, disaster management and agriculture. These officials are strongly networked into the project, so that local development and planning in project areas will henceforth incorporate climate risk and responses.
Policy makers and politicians prioritize economic benefits over sustainable and resilient ecosystems | Low | Action will be strategized during the implementation of activities. Identified issues will be discussed at project steering/ technical committee meetings
Additional development support for alternative livelihoods and crops are unavailable in the target DSD at the required time | Low | Action will be strategized during the implementation of activities. Identified issues will be discussed at project steering/ technical committee meetings
Critical Risks Affecting Progress (Not identified at project design)
Identify Risks with a 50% or > likelihood of affecting progress of project
Identified Risk | Current Status | Steps Taken to Mitigate Risk
Because of the Political changes, EE went through number of structural changes with the deployment of new officials time to time. The newly appointed officials required time to study and understand the project. This situation delayed the implementation of the project. | High | Each time when there was a turnover of high ranking EE officials, in order to avoid possible delay, IE took significant effort to build the relationship with the newly appointed officials and keep them engaged with the project as fast as possible .
Options to conform with AF guidelines were available under national administrative regulations. However, those implemented by EE were not in line with AF requirements and raised additional concerns regarding compliance. | Medium | The identified issues (seconded staff) were brought to the attention of the AF Secretariat.
Risk Measures: Were there any risk mitigation measures employed during the current reporting period? If so, were risks reduced? If not, why were these risks not reduced?
Add any comments relevant to risk mitigation (word limit = 500)
Yes. Delay in executing the project even after the disbursement of fund was experienced as a risk factor during the reporting period. IE took all the possible measures to raise the concern with all the relevant government entities and high ranking officials formally and informally. IE raised the concern in the project steering committee meeting and explained the consequences of delaying the project. Despite the political instability, the continuous advocacy of IE at various level made some improvement in the situation.

## Rating
RATING ON IMPLEMENTATION PROGRESS
For rating definitions please see bottom of page.
| Progress on Key Milestones |  | Expected Progress |  | Progress to Date | Rating
Project Manager/Coordinator: | Establishment of fully functional Project Support unit and availability of project staff |  | The establishment of PSU was expected in January 2015. |  | The establishment of PSU was completed only in Aug 2015 | MS
| 1.1 Develop home garden-based agro forestry systems in target DSDs to diversify livelihoods and build adaptive capacity of households to climate change |  | 30% |  | Procurement of drought tolerant seeds equipment planting material, organic farming tool kit to farming households in a concessionary rate/prices and provide financial assistance for carrying out such activities | MS
| 1.2 Introduce and promote drought tolerant crop varieties and agronomic practices to counter effects of rainfall variability |  | 25% |  | ***Activity not implemented*** | U
| 1.3 Identify and promote climate-resilient alternate income sources such as livestock, perennial cash crops and inland fisheries |  | 25% |  | ***Activity not implemented*** | U
| 1.4 Promote improved post-harvest technologies as viable climate-resilient livelihood sources for farm women |  | 25% |  | ***Activity not implemented*** | U
| 1.5 Build community incentives/ Payment for Ecosystem Services for natural resources management to implement climate risk reduction measures. |  | 30% |  | ***Activity not implemented*** | U
| 2.1 Train and mobilize officers at village, division and provincial level to design, and monitor local adaptation strategies |  | 50% |  | ***Activity not implemented*** | U
| 2.2 Strengthen Farmer Organizations with information, training and equipment to implement adaptation strategies |  | 30% |  | ***Activity not implemented*** | U
| 2.3 Pilot integrated watershed management models in micro watersheds to safeguard climate sensitive livelihood assets such as land and water |  | 25% |  | ***Activity not implemented*** | U
| 2.4 Conduct periodic assessment of project results and lessons learnt at community, divisional and national levels |  | 45% |  | ***Activity not implemented*** | U
| 2.5 Document and disseminate lessons of climate resilient livelihood development and watershed management approaches and best practices |  | 45% |  | ***Activity not implemented*** | U
| 2.6 Design and implement early warning systems for climate induced risk of landslide and drought in Mahaweli Basin |  | 25% |  | ***Activity not implemented*** | U
[5 empty] | Overall Rating | MU
Please Provide the Name and Contact information of person(s) responsible for completing the Rating section
| Name: | Lakshan Fernando
| Email: | lakshanlsf@gmail.com
Please justify your rating. Outline the positive and negative progress made by the project since it started. Provide specific recommendations for next steps. . (word limit=500)
It was originally intended to complete the recruitment of project staff and establish the Project Support Unit (PSU) and the divisional level project support units by January 2015. However Sri Lanka's political situation was not stable. The country faced two major elections namely presidential and parliamentary elections and went through changes. As a result, the EE went through several structural changes and the Designated Authority of project was also changed three times. Further, recruitment freeze due to the election and turn over/transfer of officials at various level also caused delays. However since August, 2015 a functional PSU was established and is expected to implement the project according to the action plan. With regards to project activities, as explained in the financial data tab, due to a constantly changing administration, all government recruitments (including project staff) were paused and only completed in August 2015. In absence of project staff, procurements as well as implementation of planned activities was affected.
| Progress on Key Milestones |  | Expected Progress |  | Progress to Date | Rating
Implementing Agency | During the reporting period of time WFP intended to develop an addendum to agreement with the government and develop an SOP to ensure the compliance of with AF guidelines before disburse the fund. |  | It was expected complete this in Aug 2014 |  | Task completed within the reporting period. | MS
[5 empty] | Overall Rating | MS
Please Provide the Name and Contact information of person(s) responsible for completing the Rating section
| Name: | P. Vijendran
| Email: | Vijendran.Paramasamy@wfp.org
| Progress on Key Milestones |  | Expected Progress |  | Progress to Date | Rating
Other
Overall Rating
Please Provide the Name and Contact information of person(s) responsible for completing the Rating section
Name:
Email:
| Please justify your rating and address the following points: 1. Indicate trends, both positive and negative, in achievement of outcomes as per the project indicators. 2. Detail critical risks that have affected progress. 3. Outline response to MTR undertaken this reporting period. 4. Outline action plan to address projects with a rating of HU, U or MU. Please keep your input to 1200 words |  | The agreements and SOP created a common platform and it helped to ensure the AF guidelines are articulated. However in the operational aspect, as previously mentioned, multiple changes in government administration meant constant rotation of focal points. Familiarization of government officials with the project was time consuming and had temporarily paused project activities due to elections. With regards to project activities, as explained in the financial data tab, due to a constantly changing administration, all government recruitments (including project staff) were paused and only completed in August 2015. In absence of project staff, procurements as well as implementation of planned activities was affected.
Rating Definitions
|  |  | Highly Satisfactory (HS) | Project actions/activities planned for current reporting period are progressing on track or exceeding expectations to achieve all major outcomes/outputs for given reporting period, without major shortcomings. The project can be presented as “good practice”.
|  |  | Satisfactory (S) | Project actions/activities planned for current reporting period are progressing on track to achieve most of its major outcomes/outputs with only minor shortcomings.
|  |  | Marginally Satisfactory (MS) | Project actions/activities planned for current reporting period are progressing on track to achieve most major relevant outcomes/outputs, but with either significant shortcomings or modest overall relevance.
|  |  | Marginally Unsatisfactory (MU) | Project actions/activities planned for current reporting period are not progressing on track to achieve major outcomes/outputs with major shortcomings or is expected to achieve only some of its major outcomes/outputs.
|  |  | Unsatisfactory (U) | Project actions/activities planned for current reporting period are not progressing on track to achieve most of its major outcomes/outputs.
|  |  | Highly Unsatisfactory (U) | Project actions/activities planned for current reporting period are not on track and shows that it is failing to achieve, and is not expected to achieve, any of its outcomes/outputs.

## Project Indicators
PROJECT Indicators
Please provide all indicators being tracked for the project as outlined in the project document
Type of Indicator (indicators towards Objectives, Outcomes, etc…)
Type of Indicator | Indicator | Baseline | Progress since inception | Target for Project End
Objective: To mitigate effects of climate change induced rainfall variability and its impacts on livelihood and food security in rainfed farming communities in three sub watersheds of the Mahaweli River Basin | Percentage of target population adopting risk reduction measures | Less than 10% of target population practice climate risk reduction measures |  | 75% of target population practice at least one climate risk reduction measure introduced through project interventions such as Responding to early warning and forecasting House hold level No-farm income sources Home garden food production improved water management Post harvest technologies Resistant crop varieties knowledge of climate risks and adaptation strategies
| Household consumption score | Both DSDs indicate food insecurity in VAM (Vulnerability Analysis and Mapping Data) Walapane- Very High Medirigiriya- Moderate A more sensitive index similar to household consumption score will be developed through the project’s initial household consumption surveying |  | 14039 farming households indicate improved levels of food security compared to the initial consumption survey
Outcome 1 | Percentage of target households with sustained climate resilient livelihoods | Farm families under minor irrigation/rain fed conditions highly exposed to climate change related livelihood insecurity treat level : very high |  | 14039 target households have developed at least one climate resilient livelihood strategy of alternative source of income
Diversified and strengthened livelihoods and sources of income for vulnerable farm families in minor irrigated and rain fed areas | No. of women with new source of income | Women in target areas practice tradition rain fed farming |  | Home gardens generate income in 50% of target population, women's contribution to household income increased by 50% in target households
Output 1.1 | No. of diversified home gardens created through project intervention, Value of food and income generated through diversified home gardens | Home garden diversity low-medium Low->10 species of food and multi -purpose tree species,medium-10-25 High-<25 species | Drought tolerant seeds, hand tools, planting material, organic farming tool kit purchased and distributed to farming households at concessionary rates. | 14039 rain fed farming families benefit from home garden improvement- Diversity in home gardens improved - Household income from home gardens increased
Develop home garden based agro forestry systems in target DSDs to diversify livelihoods and build adaptive capacity of households to climate change
Output 1.2
Introduce and promote drought tolerant crop varieties and agronomic practices to counter effects of rainfall variability | No. and type of drought mitigation practices introduced | Low awareness and adoption of drought tolerant agronomic practices |  | All FO s trained to engage in drought tolerant agriculture, Farmer field trials conducted with national technical agencies for 500 farm families selected by FO s, Seed banks and seed distribution established in each ASC
Output 1.3 | No. and type of alternate livelihood assets created | Low level of access to non-farm livelihood assets including information Training/skills Market linkage Finance |  | 6 technical assessments for climate resilience and market chain analysis conducted
Identify and promote climate resilient alternate income sources such as livestock, perennial cash crops and inland fisheries | No of women participated in livelihood training |  |  | Training provided to all FO s on selected livelihood options per DSD by specialized state agencies, Livelihood support equipment provided to six viable livelihood proposals from every FO
Output 1.4 |  | Non availability of information and training on post-harvest technologies at ASCs |  | Post harvest centers established in 8 ASCs in the 3 project DSDs, One post harvest village established in each ASC area 760 farm women in 08 villages linked with local livelihood incentive programs
Promote improved post harvest technologies as viable climate- resilient livelihood sources for farm women | No. of farm women engaged in project-introduced post harvest livelihoods
Output 1.5 | Percentage and level of community participation cash for work system | 0% participation in PES schemes in target area |  | 1500 households benefit from cash for work schemes in two micro catchments in target DSDs
Build community Assets and livelihood resources through cash for work to support climate risk reduction measures | Number of women participating in cash for work programme
Outcome 2
Strengthened ownership of climate risk reduction processes and increased replication potential of adaptation strategies at local level and basin/sub national level | Percentage of target population aware of predicted impacts of climate change and appropriate responsive adaptive actions to safeguard livelihood assets. | Lack of awareness of climate impacts and adaptive actions at household and community level, Extension officers and CBO officials have no training on climate proofing local community development |  | All 14039 households participate in climate risk assessment in target area receive climate change awareness, At least 50% of community risk assessment meetings consist of women, All FO s in target area receive information and tools to develop local adaptive strategies to safeguard livelihood assets, All local and divisional-level officials engaged in agriculture, fisheries, forestry and disaster management receive at least one training on supporting adaptive strategies
Output2.1 | No. of village, divisional and provincial officers trained to address climate risks | Training programmes on climate risk management are not available at regional and local level |  | One training module developed, 6 TOTs developed and conducted, 250 officials trained at provincial, divisional, and village engaged in rural development, All Agrarian Service centers in project DSDs receive climate risk management tools
Train and mobilize officers at village, division and provincial level to design, and monitor local adaptation strategies
Output 2.2
Strengthen FO s with information, training and equipment to implement adaptation strategies | Capacity of FO s to respond to climate risk | FO s lack information on risks, and lack planning capacity t o address them, Some villages do not formalized FO s |  | All FO s in target DSDs have developed management plans for local irrigation management and catchment conservation, Management plans are funded through community & government input, All FO s in the target divisions are registered with Agrarian Services and have elected representatives, At least 6 members each FO trained to conduct vulnerability reduction assessments as input 2.4
Output 2.3 | Availability of watershed-level irrigation management plans, Increased extent cultivated under pilot minor irrigation scheme | No cluster/cascade level watershed management plans exist, CI in village tanks in lower catchment<90%, CI in anicut systems in middle catchment<70% |  | Management plans for two micro watersheds developed and implemented FO s, Increase cropping intensity in both systems to over 100%
Pilot integrated watershed management plans to safeguard climate sensitive livelihood assets such as land and water
Output 2.4 | Level of awareness among awareness among target group of climate risk | Target population unaware of climate risks and adaptive measure |  | VRA s conducted in all FO s targeting 14039 households at three month, 18 month and end of project, >45% female participation
Conduct Risk Assessment and Adaptation Planning with target communities
Output 2.5 Document and disseminate lessons of climate resilient livelihood development and watershed management approaches and best practices | No. of news outlets in the local press and media reported on project lessons, No. of new project proposals,/ new community based adaptation initiatives generated within and outside the DSDs | Reporting on climate adaptation in national media poor, No such project proposals exist |  | 10 case studies generated, 5 policy briefs produced and shared with NPSC, 50 media reports on project outcomes, 2 provincial workshops to share project learning, 20 CBA proposals from other vulnerable communities generated through exchange visits
Output 2.6 | Development and functioning of early warning systems | No community based landslide warning in project DSDs, No drought/seasonal forecasting systems in place |  | Developed and implemented drought forecasting and timely dissemination model for Mahaweli basin, 15 community based landslide early warning systems with telemetric rain gauges are operationalized in Walapane DSD
Design and implement early warning systems for climate induced risk of landslide and drought in Mahaweli Basin
Note on G7: The initial household survey (baseline) and the follow up survey were not conducted during the reporting period as originally planned. Due to this situation marking the progress was not possible.

## Lessons Learned
QUALITATIVE MEASURES and LESSONS LEARNED
Please complete the following section every reporting period
Implementation and Adaptive Management | Response
What implementation issues/lessons, either positive or negative, affected progress? | It was initially unclear whether AF regulations allowed recruitment of government seconded staff for the project. The EE contacted AF Secretariat directly causing confusion between MIE and EE. The matter has been clarified and addressed by the AF Secretariat in September 2015.
Were there any delays in implementation? If so, include any causes of delays. What measures have been taken to reduce delays? | During the reporting period of time the political situation of the country was a challenge. The country faced two major elections namely presidential election and the parliamentary election. The EE went through several structural changes and the designated authority was changed three times. Further, recruitment freeze due to the election and turn over/transfer of officials at various level also experienced during the reporting period of time. All the above contributed to the project implementation delays during the reporting period of time.
Describe any changes undertaken to improve results on the ground or any changes made to project outputs (i.e. changes to project design) | Project design not changed.
How have gender considerations been taken into consideration during the reporting period? What have been the lessons learned as a consequence of inclusion of such considerations on project performance or impacts? | Not applicable for the reporting period.
Please complete the following section at mid-term and project completion
Lessons for Adaptation | Response
Climate Resilience Measures
What have been the lessons learned, both positive and negative, in implementing climate adaptation measures that would be relevant to the design and implementation of future projects/programmes for enhanced resilience to climate change? | N/A
What is the potential for the climate resilience measures undertaken by the project/programme to be replicated and scaled up both within and outside the project area? | N/A
Concrete Adaptation Interventions
What have been the lessons learned, both positive and negative, in implementing concrete adaptation interventions that would be relevant to the design and implementation of future projects/programmes implementing concrete adaptation interventions? | N/A
What is the potential for the concrete adaptation interventions undertaken by the project/programme to be replicated and scaled up both within and outside the project area? | N/A
What would you consider to be the most successful aspects for the target communities? | N/A
What measures are/have been put in place to ensure sustainability of the project/program results? | N/A
What measures are being/could have been put in place to improve project/program results? | N/A
Knowledge Management
How has existing information/data/knowledge been used to inform project development and implementation? What kinds of information/data/knowledge were used? | N/A
If learning objectives have been established, have they been met? Please describe. | N/A
Describe any difficulties there have been in accessing or retrieving existing information (data or knowledge) that is relevant to the project. Please provide suggestions for improving access to the relevant data. | N/A
Has the identification of learning objectives contributed to the outcomes of the project? In what ways have they contributed? | N/A

## Results Tracker
Results Tracker for Adaptation Fund (AF) Projects - Numbers will be available after baseline survey is completed
Goal: Assist developing-country Parties to the Kyoto Protocol that are particularly vulnerable to the adverse effects of climate change in meeting the costs of concrete adaptation projects and programmes in order to implement climate-resilient measures. Impact: Increased resiliency at the community, national, and regional levels to climate variability and change.
Important: Please read the following guidance document (also posted on the Adaptation Fund website) before entering your data
Link: http://www.adaptation-fund.org/sites/default/files/Results%20Framework%20and%20Baseline%20Guidance%20final.pdf
Adaptation Fund Strategic Results Framework
Project ID | LKA/MIE/Rural/2011/1
Implementing Entity | World Food Programme
Type of implementing entity | MIE
Country | SRI LANKA
Region | Asia-Pacific
Sector | Food security
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Impact: Increased resiliency at the community, national, and regional levels to climate variability and change | Core Indicator: No. of beneficiaries |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project
|  | Total |  |  |  | Total | 14309 |  |  | Total |  |  |  | Total
|  | % of female beneficiaries |  |  |  | % of female beneficiaries |  |  |  | % of female beneficiaries |  |  |  | % of female beneficiaries
|  | % of Youth beneficiaries |  |  |  | % of Youth beneficiaries |  |  |  | % of Youth beneficiaries |  |  |  | % of Youth beneficiaries
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 1: Reduced exposure to climate-related hazards and threats | Indicator 1: Relevant threat and hazard information generated and disseminated to stakeholders on a timely basis | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness
|  | Total |  |  |  | Total |  |  |  | Total |  |  |  | Total
|  | % of female targeted |  |  |  | % of female targeted |  |  |  | % of female targeted |  |  |  | % of female targeted
Output 1.1 Risk and vulnerability assessments conducted and updated | Indicator 1.1: No. of projects/programmes that conduct and update risk and vulnerability assessments | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
Output 1.2 Targeted population groups covered by adequate risk reduction systems | Core Indicator 1.2: No. of Early Warning Systems | No. of adopted Early Warning Systems | Category targeted | Hazard | Drought | No. of adopted Early Warning Systems | Category targeted | Hazard | Drought | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  | 0 | 2: Monitoring and warning service | Geographical coverage | Regional | 15 | 2: Monitoring and warning service | Geographical coverage | Local |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities |  |  |  | Number of municipalities | 1 |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 2: Strengthened institutional capacity to reduce risks associated with climate-induced socioeconomic and environmental losses | Indicator 2: Capacity of staff to respond to, and mitigate impacts of, climate-related events from targeted institutions increased | Number of staff targeted |  | Sector | Capacity level | Number of staff targeted |  | Sector | Capacity level | Number of staff targeted |  | Sector | Capacity level | Number of staff targeted |  | Sector | Capacity level
|  | Total |  | Food security | 2: Low capacity | Total | 250 | Food security | 3: Medium capacity | Total |  |  |  | Total
|  | % of female targeted |  |  |  | % of female targeted |  |  |  | % of female targeted |  |  |  | % of female targeted
Output 2.1 Strengthened capacity of national and sub-national centres and networks to respond rapidly to extreme weather events | Indicator 2.1.1: No. of staff trained to respond to, and mitigate impacts of, climate-related events | Total staff trained | % of female staff trained | Type |  | Total staff trained | % of female staff trained | Type |  | Total staff trained | % of female staff trained | Type |  | Total staff trained | % of female staff trained | Type
| Indicator 2.1.2: No. of targeted institutions with increased capacity to minimize exposure to climate variability risks | Type | Scale | Sector | Capacity level | Type | Scale | Sector | Capacity level | Type | Scale | Sector | Capacity level | Type | Scale | Sector | Capacity level
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 3: Strengthened awareness and ownership of adaptation and climate risk reduction processes | Indicator 3.1: Increase in application of appropriate adaptation responses | Percentage of targeted population applying adaptation measures |  | Sector |  | Percentage of targeted population applying adaptation measures |  | Sector |  | Percentage of targeted population applying adaptation measures |  | Sector |  | Percentage of targeted population applying adaptation measures |  | Sector
Output 3: Targeted population groups participating in adaptation and risk reduction awareness activities | Indicator 3.1.1: Percentage in targeted population awareness of predicted adverse impacts of climate change, and of appropriate responses | No. of targeted beneficiaries | % of female participants targeted | Level of awareness |  | No. of targeted beneficiaries | % of female participants targeted | Level of awareness |  | No. of targeted beneficiaries | % of female participants targeted | Level of awareness |  | No. of targeted beneficiaries | % of female participants targeted | Level of awareness
[6 empty] | 14309 | 50%
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Target performance at completion |  |  |  | Target performance at completion
Outcome 4: Increased adaptive capacity within relevant development sector services and infrastructure assets | Indicator 4.1: Increased responsiveness of development sector services to evolving needs from changing and variable climate | Project/programme sector | Geographical scale | Response level |  | Project/programme sector | Geographical scale | Response level |  | Project/programme sector | Geographical scale | Response level |  | Project/programme sector | Geographical scale | Response level
| Core Indicator 4.2: Assets produced, developed, improved or strengthened | Sector | Targeted asset | Changes in asset (quantitative or qualitative) |  | Sector | Targeted asset | Changes in asset (quantitative or qualitative) |  | Sector | Targeted asset | Changes in asset (quantitative or qualitative) |  | Sector | Targeted asset | Changes in asset (quantitative or qualitative)
Output 4: Vulnerable development sector services and infrastructure assets strengthened in response to climate change impacts, including variability | Indicator 4.1.1: No. and type of development sector services to respond to new conditions resulting from climate variability and change | Number of services | Type |  | Sector | Number of services | Type |  | Sector | Number of services | Type |  | Sector | Number of services | Type |  | Sector
|  | Baseline information |  |  |  | Baseline information |  |  |  | Baseline information |  |  |  | Baseline information
Outcome 5: Increased ecosystem resilience in response to climate change and variability-induced stress | Indicator 5: Ecosystem services and natural resource assets maintained or improved under climate change and variability-induced stress | Natural resource improvement level |  | Sector | Type | Natural resource improvement level |  | Sector | Type | Natural resource improvement level |  | Sector | Type | Natural resource improvement level |  | Sector | Type
Output 5: Vulnerable ecosystem services and natural resource assets strengthened in response to climate change impacts, including variability | Core Indicator 5.1: Natural Assets protected or rehabilitated | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Baseline information |  |  |  | Targeted performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 6: Diversified and strengthened livelihoods and sources of income for vulnerable people in targeted areas | Indicator 6.1: Increase in households and communities having more secure access to livelihood assets | No. of targeted households | % of female headed households | Improvement level |  | No. of targeted households | % of female headed households | Improvement level |  | No. of targeted households | % of female headed households | Improvement level |  | No. of targeted households | % of female headed households | Improvement level
| Indicator 6.2: Increase in targeted population's sustained climate-resilient alternative livelihoods | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
|  | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
|  | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
|  | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
Output 6 Targeted individual and community livelihood strategies strengthened in relation to climate change impacts, including variability | Indicator 6.1.1: No. and type of adaptation assets created or strengthened in support of individual or community livelihood strategies | Number of Assets | Type of Assets | Sector | Adaptation strategy | Number of Assets | Type of Assets | Sector | Adaptation strategy | Number of Assets | Type of Assets | Sector | Adaptation strategy | Number of Assets | Type of Assets | Sector | Adaptation strategy
| Core Indicator 6.1.2: Increased income, or avoided decrease in income | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 7: Improved policies and regulations that promote and enforce resilience measures | Indicator 7: Climate change priorities are integrated into national development strategy | Integration level |  |  |  | Integration level |  |  |  | Integration level |  |  |  | Integration level
Output 7:Improved integration of climate-resilience strategies into country development plans | Indicator 7.1: No. of policies introduced or adjusted to address climate change risks | No. of Policies introduced or adjusted | Sector | Scale | Type | No. of Policies introduced or adjusted | Sector | Scale | Type | No. of Policies introduced or adjusted | Sector | Scale | Type | No. of Policies introduced or adjusted | Sector | Scale | Type
|  | 0 | Water management | Local | Water policy | 2 | Water management | Local | Water policy
| Indicator 7.2: No. of targeted development strategies with incorporated climate change priorities enforced | No. of Development strategies | Regulation |  | Effectiveness | No. of Development strategies | Regulation |  | Effectiveness | No. of Development strategies | Regulation |  | Effectiveness | No. of Development strategies | Regulation |  | Effectiveness
Glacier lake outburst flood
|  | Inland flooding | fr | biological assets |  | Company policy | 5: Fully enforced (All elements implemented)
|  | Salinization | Decrease | land |  | Communication & Information policy | 4: Enforced (Most elements implemented)
|  | Drought | Same | water areas |  | Defense policy | 3: Partially enforced (Some elements implemented)
|  | Wind |  | subsoil assets | increased adaptive capacity | Domestic policy | 2: Partially not enforced (Most elements not implemented) |  | Agribusiness
|  | Coastal flooding |  | air | achieved | Economic policy | 1: Not enforced (No elements implemented) |  | Agricultural-related | Financial capital
|  | Storm surge | Please choose |  | enhanced level of protection | Education policy |  |  | Agriculture | Human capital
|  | Hurricane | Selected | [5 empty] | Aquaculture | Physical capital
|  |  | Not relevant |  |  | 5: All (Fully integrated) |  |  | Construction/repairing business | Social capital
[6 empty] | 4: Most |  |  | Cultivation | Natural capital
[6 empty] | 3: Some |  |  | Fishing | Personal capital
Select | 5: All | Select |  |  | Community | 2: Most not integrated |  | Other | Forestry | Adaptation strategies
1 | 4: Almost all | Private | Type | Yes | Multi-community | 1: None |  | Agriculture | Handicrafts
2 | 3: Half | Public | Scale | No | Departmental |  |  | Coastal management | Livestock production
3 | 2: Some | NGO | Sector |  | National |  |  | Disaster risk reduction | Manufacturing
4 | 1: None |  |  |  |  | 5: Very high improvement | Established | Food security | other
|  | National |  |  |  | 4: High improvement | Maintained | Health | Services
|  | Regional |  |  |  | 3: Moderate improvement | Improved | Urban development | Tourism-related
|  | Local |  |  |  | 2: Limited improvement |  | Water management | Trading
[6 empty] | 1: No improvement |  | Multi-sector
|  | 1 -generated information is irrelevant, and neither the stakeholders reached nor the timeframe managed were achieved | 1: No info transferred on time | 4: High capacity | 5: Fully aware | 5: Highly responsive (All defined elements ) | 5: Fully improved | Roads | 5: Very effective
Asia-Pacific | NIE | 2 -the existence of some challenge in any of the three aspects of the indicator (generation of dissemination, stakeholders reached or timeframe managed) | 2: Somewhat info transferred | 3: Medium capacity | 4: Mostly aware | 4: Mostly responsive (Most defined elements) | 4: Mostly Improved | Gov Buildings | 4: Effective
Latin America and Caribbean | RIE | 3 -relevant information is generated and disseminated to all identified stakeholders on timely basis | 3: Info transferred on time | 2: Low capacity | 3: Partially aware | 3: Moderately responsive (Some defined elements) | 3: Moderately improved | Causeways | 3: Moderately effective
Africa | MIE |  |  | 1: No capacity | 2: Partially not aware | 2: Partially responsive (Lacks most elements) | 2: Somewhat improved | Airports | 2: Partially effective
Eastern Europe |  |  |  |  | 1: Aware of neither | 1: Non responsive (Lacks all elements ) | 1: Not improved | Schools | 1: Ineffective
| ha protected | [6 empty] | Training Centres
| ha rehabilitated | [5 empty] | Monitoring/Forecasting capacity | Hospitals
Afghanistan, Islamic Rep. of | km protected | [5 empty] | Policy/regulatory reform | Drinking water systems
Angola | km rehabilitated | 1: Risk knowledge | 1: No plans conducted or updated |  |  |  | Capacity development | Other
Albania |  | 2: Monitoring and warning service | 2: Undertaking or updating of assessments in progress |  |  | Communication & Information policy | Sustainable forest management
Argentina |  | 3: Dissemination and communication | 3: Risk and vulnerability assessments completed or updated |  |  | Domestic policy | Strengthening infrastructure | 1: Health and Social Infrastructure (developed/improved)
Armenia | Forests | 4: Response capability |  |  |  | Economic policy | Supporting livelihoods | 2: Physical asset (produced/improved/strengthened)
Antigua and Barbuda | Mangroves |  |  |  |  | Education policy | Mangrove reforestation
Azerbaijan | Coasts |  | From 0 to 0.5% |  |  | Energy policy | Coastal drainage and infrastructure
Burundi | Rangelands |  | From 0.5 to 1% |  |  | Environmental policy | Irrigation system
Benin | Cultivated land/Agricultural land |  | From 1% to 5% |  |  | Foreign policy | Community-based adaptation
Burkina Faso | Catchment area/Watershed/Aquifer |  | From 5% to 10% |  |  | Health policy | Erosion control
Bangladesh | Protected areas/National parks |  | From 10% to 20% |  |  | Housing policy | Soil water conservation
Bulgaria | Other |  | From 20% to 30% |  |  | Human resource policies | Microfinance
Bahrain |  |  | From 30% to 40% |  |  | Information policy | Special Program for women
Bahamas, The |  |  | From 40% to 50% |  |  | Macroeconomic policy | Livelihoods
Bosnia and Herzegovina |  |  | Above 50% |  |  | Monetary policy | Water storage
Belarus | [5 empty] | Population policy | ICT and information dissemination
Belize | [5 empty] | Private policy
Bolivia | [5 empty] | Public policy
Brazil | [5 empty] | Science policy
Barbados | [5 empty] | Social policy
Bhutan |  | 3- relevant information is generated and disseminated to all identified stakeholders on timely basis |  |  |  | Transportation policy
Botswana |  | describe |  |  |  | Urban policy
Central African Republic |  | 2- the existence of some challenge in any of the three aspects of the indicator |  |  |  | Water policy
Chile |  | describe |  |  |  | Other policy
China, People's Republic of |  | 1- generated information is irrelevant and neither the stakeholders reached nor the timeframe managed were achieved
Cote d'Ivoire |  | describe
Cameroon
Congo, Dem. Rep. of
Congo, Republic of
Cook Islands
Colombia
Comoros
Cape Verde
Costa Rica
Cuba
Czech Republic
Djibouti
Dominica
Dominican Republic
Algeria
Ecuador
Egypt
Eritrea
Estonia
Ethiopia
Fiji
Micronesia, Fed. States of
Gabon
Georgia
Ghana
Guinea
Gambia, The
Guinea-Bissau
Equatorial Guinea
Grenada
Guatemala
Guyana
Honduras
Croatia
Haiti
Hungary
Indonesia
India
Iran, Islamic Republic of
Jamaica
Jordan
Kazakhstan
Kenya
Kyrgyz Republic
Cambodia
Kiribati
Saint Kitts and Nevis
Korea, Republic of
Lao People's Democratic Republic
Lebanon
Liberia
Libya
Saint Lucia
Sri Lanka
Lesotho
Lithuania
Latvia
Morocco
Moldova
Madagascar
Maldives
Mexico
Marshall Islands
Macedonia, former Yugoslav Republic of
Mali
Malta
Myanmar
Montenegro
Mongolia
Mozambique
Mauritania
Mauritius
Malawi
Malaysia
Namibia
Niger
Nigeria
Nicaragua
Niue
Nepal
Nauru
Oman
Pakistan
Panama
Peru
Philippines
Palau
Papua New Guinea
Poland
Korea, Dem. People's Rep. of
Paraguay
Romania
Russian Federation
Rwanda
Saudi Arabia
Sudan
Senegal
Solomon Islands
Sierra Leone
El Salvador
San Marino
Serbia
Sao Tome and Principe
Suriname
Slovak Republic
Slovenia
Swaziland
Seychelles
Syrian Arab Republic
Chad
Togo
Thailand
Tajikistan
Turkmenistan
Tonga
Trinidad and Tobago
Tunisia
Turkey
Tuvalu
Tanzania
Uganda
Ukraine
Uruguay
Uzbekistan
Saint Vincent and the Grenadines
Venezuela
Vietnam
Vanuatu
Samoa
Yemen, Republic of
South Africa
Zambia
Zimbabwe
Timor-Leste
Note on I21: Rupak Manvatkar: No. of Families
Note on G39: Rupak Manvatkar: Drought and Landslide
Note on K39: Rupak Manvatkar: Drought and Landslide
Note on H65: Rupak Manvatkar: No of households

## Units for Indicators
Fund Outcome Indicator Units
1. Generation of relevant data, Stakeholders, and Timeliness 2.1. Include both qualitative and quantitative measures of capacity level within targeted institutions 2.2. Number (men and women and other vulnerable groups) 3.1. Use scale from 1 to 5: 5: Fully aware 4: Mostly aware 3: Partially aware 2: Partially not aware 1: Aware of neither predicted adverse impacts of climate change nor of appropriate responses 3.2. Use scale from 1 to 5: 5: All 4: Almost all 3: Half 2: Some 1: None 4.1. Summarize in an overall scale (1-5): 5: Highly responsive (All defined elements ) 4: Mostly responsive (Most defined elements) 3: Moderately responsive (Some defined elements) 2: Partially responsive (Lacks most elements) 1: Non responsive (Lacks all elements ) 4.2. Summarize in an overall scale (1-5): 5: Fully improved 4: Mostly Improved 3: Moderately improved 2: Somewhat improved 1: Not improved 5. Depends on the targeted natural asset: Biological (species): measure through changes in population numbers (dynamics, structure, etc.) Land: measure changes in hectares. Baseline data will be necessary to estimate the change. Supporting indicators baseline and target (as well as contextual information) are needed such as the following: Farmers adopting recommended technologies, Ha. of land improved, Average deforestation rate Etc. Use scale from 1 to 5. 5: Very effective (All elements are present) 4: Effective (Most elements are present) 3: Moderately effective (Some elements are present) 2: Partially effective (Most elements are not present) 1: Ineffective (No elements are present) 6.1. Summarize in an overall scale (1-5): 5: Very high improvement 4: High improvement 3: Moderate improvement 2: Limited improvement 1: No improvement 6.2. Household income by source of livelihood in project area (USD) prior and post project intervention 7. Summarize in an overall scale (1-5). 5: All (Fully integrated) 4: Most 3: Some 2: Most not integrated 1: None
Fund Output Indicator Units
1.1. Number, sector(s) and level(s) of projects or interventions in separate fields of monitoring plan 1.2. Number 2.1.1. Number of staff (male/female) of targeted institutions: a. Obtain baseline information: total number of staff from targeted institutions b. Define target 2.1.2. Number of staff (male/female) of targeted institutions: a. Obtain baseline information: total number of staff from targeted institutions b. Define target: needs to be defined by project proponents 2.2.1. Quantitative: Percentage (includes women – and other vulnerable groups – and men). Qualitative: Adequacy: include direct analysis of major areas; adequacy/effectiveness of systems or analysis of perceptions of populations and institutions. 2.2.2. Number (broken down by gender and, if possible, by vulnerable groups defined in the area of intervention) of people 3.1. Number and type (in separate columns) at local level. 3.2. Number 4.1. Number and type 4. 2. Number and type (entered in separate columns) 5. Number of interventions by type of natural asset and intervention 6.1. Number and type (in separate columns of monitoring plan) 6.2. Income sources per household; description of income source and number of households. 7.1. Number/Sector 7.2. Number; Effectiveness (see previous indicator) through enforcement level.

## Financial annex
Addressing Climate Change Impacts on Marginalized Agricultural Communities Living in the Mahaweli River Basin
Explanatory notes on variancies between planned and actual expenditures of outputs during the reporting period
ITEM / ACTIVITY / ACTION | AMOUNT spent (US$) | Projected for 1st year | Difference (positive amount indicates amount overspent) | Reason for underspending
Component 01
Activity 1.1. | 7559.99 | 454397.16 | -446837.17 | Due to the Political situation of the country the project was not timely implemented as originally programmed. For further detail please refer to financial tab comments on AF Grant Funds
Activity 1.2. | 0 | 118936.17 | -118936.17 | ***Activity not implemented***
Activity 1.3. | 0 | 127517.73 | -127517.73 | ***Activity not implemented***
Activity 1.4. | 0 | 96666.66 | -96666.66 | ***Activity not implemented***
Activity 1.5. | 0 | 122411.34 | -122411.34 | ***Activity not implemented***
Component 02
Activity 2.1. | 0 | 128226.95 | -128226.95 | ***Activity not implemented***
Activity 2.2. | 0 | 206609.92 | -206609.92 | ***Activity not implemented***
Activity 2.3. | 0 | - |  | Activity not planned for the reporting year
Activity 2.4. | 0 | 70283.68 | -70283.68 | ***Activity not implemented***
Activity 2.5. | 0 | 10638.29 | -10638.29 | ***Activity not implemented***
Activity 2.6. | 0 | 43262.41 | -43262.41 | ***Activity not implemented***
Execution cost | 19230.25 | 88297.87 | -69067.62 | Due to the Political situation of the country the project was not timely implemented as originally programmed. For further detail please refer to financial tab comments on AF Grant Funds