## Reliquats-au-31-déc (hidden)
9.6446
| Composantes |  | Intitule | Montant délégué (1) | Montant redéployé (1i) | TYPE | Montants engagés (2) |  | Reliquat (1)-(2) | Montant payé | % Paie. | Reste à payer
[7 empty] | Mnt marchés | int. moratoires | [6 empty] | 1466635.14 | 152067.887
| Fonds du projet | C1+C4 | Convention de partenariat ABH GZR | 9270000 |  | Convention | 9270000 |  | 0 | 9270000 | 100% | 0
270000 |  |  | Convention de partenariat ORMVAO | 2750000 |  | Convention | 2750000 |  | 0 | 2750000 | 100% | 0 | Marché 10/15 | STE AS2T INGENIERIE | 1452114 | 150562.2644
22290000 |  |  | Convention de partenariat ORMVAT |  | 2000000 | Convention | 2000000 |  | -2000000 | 2000000 | 100% | 0 |  | STE ECTA2E | 1494000 | 154905.2092
|  | C2 | Contribution aux projets de partenariat | 1700000 |  | 11 Conventions | 1500000 |  | 200000 | 1500000 | 100% | 0
|  | C5 | Formations | 1600000 |  | Marché 10/15 | 1452114 | 14521.14 | 133364.86 | 733116 | 50.49% | 733519.14 | Marché 11/15 | STE NEGOVERT | 394344 | 40887.5099
|  | C5 | Activité 5.1.1.2 (Particip. rencontres & forums) | 100000 |  |  | 0 |  | 100000 |  | - - | 0 |  | STE WINZIZ | 304800 | 31603.1511
| Assistance technique (ANDZOA) |  |  | 6000000 |  | Marché 05/16 | 4881600 | 48816 | 1069584 |  | 0% | 4930416
| Etude EIES/PGES |  |  | 1800000 |  | Marché 06/16 | 960000 | 9600 | 830400 |  | 0% | 969600 | Marché 05/15 | STE NOVEC | 9313920 | 965712.6681
[14 empty] | GPT CLINIQUE PLANTES & CADINOV | 4881600 | 506148.1053
| Frais d'exécution | Equipement | Acquisition de matériel de transport | 1040000 |  | Dérogation PG | 1040000 |  | 0 | 1040000 | 100% | 0 |  | STE H2S INGENIEURIE | 4982400 | 516599.5411
|  |  | Frais d’acquisition de matériel informatique | 200000 |  | BC N°22/15 | 143340 |  | 56660 | 143340 | 100% | 0
|  |  | Frais d’acquisition photocopieurs, multimédia et fourniture de bureau | 370000 |  | Marché 11/15 | 223752 |  | -22916.62 | 208089.32 | 93% | 15662.68
[6 empty] | BC N°19/15 | 97800 |  |  | 97800 | 100% | 0 | Marché 6/16 | STE YOURI CONSULTING | 840000 | 87095.2984
[6 empty] | BC N°20/15 | 22141.06 |  |  | 22141.06 | 100% | 0 |  | STE 3 ANGLES ETUDES | 1301520 | 134947.9437
[5 empty] | 22072.36 | BC N°12/16 | 22072.36 |  |  | 0 | 0% | 22072.36 |  | GPT ID GREEN LAND & ALPHA | 1380000 | 143085.133
[5 empty] | 27251.2 | BC N°13/16 | 27151.2 |  |  | 27151.2 | 100% | 0 |  | STE DMIC | 1164000 | 120689.1991
|  |  | Frais de publication et communication | 151500 |  | BC N°17/15 | 143088 |  | 8412 | 143088 | 100% | 0 |  | STE CAPITAL RH | 1197996 | 124214.0703
|  | Travel expenses | Frais de déplacements | 100000 |  |  | 87600 |  | 12400 | 87600 | 100% | 0 |  | STE NOVEC | 960000 | 99537.4838
|  |  | Frais de transport à l’intérieur du royaume | 100000 |  | CV 1729/15 | 100000 |  | 0 | 100000 | 100% | 0 |  | STE TEAM MAROC | 1149960 | 119233.4634
|  |  | Frais d’entretien et carburant | 100000 |  | CV 3905/15 | 100000 |  | 0 | 100000 | 100% | 0 |  | STE CID | 1198740 | 124291.2118
|  |  | Restauration, et hébergement | 150000 |  | CV 05/15 | 100100 |  | 158 | 100100 | 100% | 0 |  | GPT STE SELF & STE AREMO | 1152000 | 119444.9806
[5 empty] | 49742 | CV 04/16 | 49742 |  |  | 0 | 0% | 49742
| Total |  |  | 25431500 | 2099065.56 | -- | 24970500.62 | 72937.14 | 388062.24 | 18322425.58 | 73.38% | 6721012.18
25043437.76
[13 empty] | BC 13/15 | STE ETERCOS | 32767.2 | 3397.4632
[14 empty] | STE LIBRAIRIE IQRAE | 28230 | 2927.0241
[14 empty] | STE AMANOUN DAOUD | 50712 | 5258.0676
[14 empty] | STE NEGOVERT | 27151 | 2815.1481
[13 empty] | BC 12/15 | STE ETERCOS | 22072.36 | 2288.57
[14 empty] | STE ERRACHIDIA GRAPHIQUE | 24451.8 | 2535.2819
[14 empty] | STE OMEGA SUD | 23016.6 | 2386.4734
[13 empty] | BC 17/15 | STE ARCO PRINT | 144840 | 15017.7179
[14 empty] | STE IMPREMERIE ALJBOUN | 148680 | 15415.8678
[14 empty] | STE MEDAGRAPH PUB | 143088 | 14836.062
[13 empty] | BC 22/15 | STE ETERCOS | 265075.2 | 27484.29 | 169315.2 | 434390.4
[14 empty] | STE AXANET SERVICES | 219772.8 | 22787.1162 | 147028.8 | 366801.6
[14 empty] | STE NSIB | 143340 | 14862.1906 | 216780 | 360120
[14 empty] | STE RESO2DAY SERVICES | 280674 | 29101.6497 | 177024 | 457698
[13 empty] | BC 19/15 | STE AYOU ALI ELEC | 97800 | 10140.3812 | 222000 | 319800
[14 empty] | STE RESO2DAY SERVICES | 101460 | 10519.8678 | 223680 | 325140
[14 empty] | STE NEGOVERT | 106800 | 11073.5451 | 223800 | 330600
[13 empty] | BC 20/15 | STE ETERCOS | 22141.06 | 2295.6931
[14 empty] | STE WINZIZ | 23568 | 2443.6452
[14 empty] | STE OMEGA SUD | 22240.2 | 2305.9724
[14 empty] | STE TAFILALET BUREAU | 25843.2 | 2679.5491
[14 empty] | STE NEGOVERT | 38419.02 | 3983.4714
[14 empty] | STE DOUSDATE | 25926 | 2688.1342
[13 empty] | CV 05/15 | STE OISIS MIR | 100100 | 10378.8564
[14 empty] | STE WINZIZ | 114906 | 11914.0147
[14 empty] | STE OMEGA SUD | 123849 | 12841.2686
[13 empty] | CV 04/15 | STE OISIS MIR | 49742 | 5157.4933
[14 empty] | STE TRIOMUS | 52283 | 5420.9565
[14 empty] | STE ALAOUI NAJIB | 58674 | 6083.6066
[13 empty] | CV 1729/15 | SNTL | 100000 | 10368.4879
[13 empty] | CV 3905/15 | SNTL | 100000 | 10368.4879

## Reliquats-au-31-déc USD (hidden)
9.6446
Composantes |  | Intitule | Montant délégué (1) | Montant redéployé (1i) | TYPE | Montants engagés (2) |  | Reliquat (1)-(2) | Montant payé | % Paie. | Reste à payer
[6 empty] | Mnt marchés | int. moratoires
Fonds du projet | C1+C4 | Convention de partenariat ABH GZR | #REF! |  | Convention | #REF! |  | #REF! | #REF! | #REF! | #REF!
|  | Convention de partenariat ORMVAO | #REF! |  | Convention | #REF! |  | #REF! | #REF! | #REF! | #REF!
|  | Convention de partenariat ORMVAT | #REF! | 207369.758 | Convention | #REF! |  | #REF! | #REF! | #REF! | #REF!
| C2 | Contribution aux projets de partenariat | #REF! |  | 11 Conventions | #REF! |  | #REF! | #REF! | #REF! | #REF!
| C5 | Training | #REF! |  | Marché 10/15 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
| C5 | Activité 5.1.1.2 (Particip. rencontres & forums) | #REF! |  |  | #REF! |  | #REF! |  | - - | #REF!
Technical Assitance for ANDZOA |  |  | #REF! |  | Marché 05/16 | #REF! | #REF! | #REF! |  | #REF! | #REF!
EIES/PGES |  |  | #REF! |  | Marché 06/16 | #REF! | #REF! | #REF! |  | #REF! | #REF!
Frais d'exécution | Equipement | Acquisition of transport equipment (vehicles) | #REF! |  | Dérogation PG | #REF! |  | #REF! | 93316 | #REF! | #REF!
|  | Acquisition of computer hardware | #REF! |  | BC N°22/15 | #REF! |  | #REF! | #REF! | #REF! | #REF!
|  | Acquisition of photocopiers, multimedia and office supplies | #REF! |  | Marché 11/15 | #REF! |  | #REF! | #REF! | #REF! | #REF!
[5 empty] | BC N°19/15 | #REF! |  |  | #REF! | #REF! | #REF!
[5 empty] | BC N°20/15 | #REF! |  |  | #REF! | #REF! | #REF!
|  |  |  | 2288.57 | BC N°12/16 | #REF! |  |  | #REF! | #REF! | #REF!
|  |  |  | 2825.5374 | BC N°13/16 | #REF! |  |  | #REF! | #REF! | #REF!
|  | Publication and communication costs | #REF! |  | BC N°17/15 | #REF! |  | #REF! | #REF! | #REF! | #REF!
| Travel expenses | Travel expenses | #REF! |  |  | #REF! |  | #REF! | 10368 | #REF! | #REF!
|  | Transportation within the Morocco | #REF! |  | CV 1729/15 | #REF! |  | #REF! | #REF! | #REF! | #REF!
|  | Maintenance and fuel costs | #REF! |  | CV 3905/15 | #REF! |  | #REF! | #REF! | #REF! | #REF!
|  | Catering and accommodation | #REF! |  | CV 05/15 | #REF! |  | #REF! | #REF! | #REF! | #REF!
|  |  |  | 5157.4933 | CV 04/16 | #REF! |  |  | #REF! | #REF! | #REF!
Total |  |  | #REF! | 217641.3586 | -- | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!

## Crédits_Engagements_2019 (hidden)
Situation des engagements des crédits « Exécution du projet » au 31-dec-2019 | [13 empty] | 9.6446
Composantes |  | Intitule | Montant délégué (1) | Contrats | Montants engagés (2) |  | Reliquat (1)-(2) | Paiements 2018 | Paiements 2019 | Paiements 2020 | Repport de 2018 | % Paie. | Reste à payer
[5 empty] | Montants | int. moratoires
Fonds du projet | C1+C2 | Convention de partenariat ORMVAO | 7452000 | Convention | 3000000 |  | -313600 |  | 3000000 |  | 3000000 | 100% | 0 | 311054.637
| C1+C2+C3 | Convention de partenariat ORMVAT |  | Convention | 4765600 |  |  |  | 4765600 |  | 4765600 | 100% | 0 | 494120.6593
| C2 + C3 | Contribution aux projets de partenariat (A2.2.2.1 + A 3.1.2.3) | 4935353 | Conventions / 24 projets | 4821650 |  | 113703 |  | 4821650 |  | 4821650 | 100% | 0 | 499932.1968
| C2 | 2.1.2.2 Promouvoir les produits agricoles des oasis (Ste FOOD AGRO) | 938700 | M 16/2019 | 929400 | 9294 | 6 |  | 0 |  | 929400 | 0% | 929400 | 96364.7265
| C4 | 4.1.1.1 : Mise en place d’un Fonds Documentaire (ANZAR) | 443000 | M 21/2019 | 438000 | 4380 | 620 |  | 0 |  | 438000 | 0% | 438000 | 45413.977
| C4 | 4.2.2.2 Gestion des appels à projets de sensibilisation (EDIC) | 251000 | M 20/2019 | 248160 | 2481.6 | 358.4 |  | 0 |  | 248160 | 0% | 248160 | 25730.4396
| C4 + C5 | 4.1.2.2 : Organisation des conférences thématiques | 150000 | M 18/2019 (MONDE CON) | 339720 | 3397.2 | 6882.8 |  | 339720 |  | 339720 | 100% | 0 | 35223.8271
|  | 4.2.1.2 : Campagne de communication | 100000 | [11 empty] | 0
|  | 5.1.1.2 : Participation aux rencontres scientifiques et aux forums de sensibilisation | 100000
| C5 | 5.1.2.2 : Organisation de voyages et de stages d’étude | 867000 | M 17/2019 (VULGARISM) | 191520 | 1915.2 | 904.8 |  | 0 |  | 191520 | 0% | 191520 | 19857.728
|  |  |  | M 19/2019 (MONDE CON) | 666000 | 6660 |  |  | 0 |  | 666000 | 0% | 666000 | 69054.1294 | 0
0
Etude EIES/PGES |  |  | 243000 | M 15/2019 (TTOBA) | 240000 | 2400 | 600 |  | 0 |  | 240000 | 0% | 240000 | 24884.371
0
Frais d'exécution |  | Frais de publication et communication | 400000 | M 14/2019 SIPAMA | 289200 | 2892 | 11966.08 |  | 0 | 289200 | 289200 | 100% | 0 | 29985.667
|  |  |  | BC 23/2019 Nigovert | 94992 | 949.92 |  |  | 94992 |  | 94992 | 100% | 0 | 9849.234
| Travel expenses | Frais de déplacements | 100000 |  | 100000 |  |  |  | 96800 |  | 100000 | 96.8% | 3200 | 10368.4879
|  | Frais de transport | 100000 | SNTL | [6 empty] | 0 |  | 0 | 0
|  | Restauration, et hébergement | [8 empty] | 0 |  | 0 | 0
0
Total |  |  | 16080053 | -- | 16124242 | 34369.92 | -178558.92 | 0 | 13118762 |  | 16124242 | 81.36% | 16124242 | 1671840.0806 | 0
[7 empty] | 0 | [6 empty] | 0
Note on K10: user: Paiement fin 2019 / Appaition 2020
Note on K19: user: Paiement fin 2019 / Appaition 2020

## PTBA-ANDZOA (hidden)
9.6446 |  |  |  | 9.6446 |  | 16270000
[6 empty] | 16270000 | PTBA-1 (2016) | [5 empty] | PTBA-2 (2017) | [5 empty] | PTBA 3 (2018-2019) | [5 empty] | PTBA % (16+17+18)/ PACCZO | PTBA 4 (2020-2021) | [8 empty] | PTBA Total ($US) | PTBA Total (MAD)
| Composantes | Outputs | Résultats | Produits | Outputs | Activités | PTBA 2016 (MAD) | PTBA 2016 (USD) | % PTBA 2016 / PACZO | Réalis. 2016 (MAD) | Réalis. 2016 (USD) | % Réal 2016 | PTBA 2017 (MAD) | PTBA 2017 (USD) | % PTBA 2017 / PACZO | Réalis. 2017 (MAD) | Réalis. 2017 (USD) | % Réal 2017 | PTBA 2018 (MAD) | PTBA 2018 (USD) | % PTBA 2018 | Réalis. 2018 (MAD) | Réalis. 2018 (USD) | % Réal 2018 |  | PTBA 2018 (MAD) | PTBA 2018 (USD) | % PTBA 2018 | Réalis. 2018 (MAD) | Réalis. 2018 (USD) | % Réal 2018 |  | partenaires |  |  |  |  | Couts (US$)
| 1. Amélioration des capacités d’adaptation du secteur de l’eau / Outcome 4 | Output 4: Vulnerable development sector services and infrastructure assets strengthened in response to climate change impacts, including variability | 1.1 La régulation conjointe des eaux souterraines et superficielles est améliorée grace à de nouveaux aménagements durables d'ouvrages hydrauliques et de protection | (1.1.1) Construction des ouvrages de recharge des nappes | Replenishment structures for groundwater are built | 1.1.1.1 Réaliser les études complémentaires des ouvrages de recharge des nappes dans les sites potentiels identifié (Conv ABH) | 1000000 | 103684.879 | 103.7% | 1000000 | 103684.879 | 100% |  | 0 |  |  |  | 0 | 0 | 0 |  | 0 | 0 |  | 103.7% | [6 empty] | 103684.879 |  |  | 100000 | 964460.7871 |  | 100000
[6 empty] | 1.1.1.2 Construire les ouvrages ayant les potentialités les plus élevées (Conv ABH) + ABH | 4470000 | 463471.4091 | 46.35% | 4470000 | 463471.4091 | 100% | 5100000 | 528792.8828 | 52.88% | 5100000 | 528792.8828 | 100% | 0 | 0 | 0% | 0 | 0 |  | 99.23% | [6 empty] | 992264.2919 | 228210.4187 |  | 1000000 | 9644607.871 | 9.6446 | 1000000
[6 empty] | 1.1.1.3 Acquérir les équipements de suivi (piézomètres) - (Conv ABH) + ABH-2017 | 400000 | 41473.9516 | 82.95% | 400000 | 41473.9516 | 100% | 76000 | 7880.0508 | 15.76% | 76000 | 7880.0508 | 100% | 0 | 0 | 0% | 0 | 0 |  | 98.71% | [6 empty] | 49354.0024 | 72579.4153 |  | 50000 | 482230.3936 |  | 50000
[6 empty] | 1.1.1.4 Assurer le suivi évaluation. | -- | -- | -- | -- | -- | -- |  | 0 | -- | -- | -- | -- | 0 | 0 | -- | 0 | 0 |  | -- | [9 empty] | pm | -- |  | pm
[6 empty] | 1.1.1.5 Établir une convention d'entretien et de maintenance des ouvrages de recharge des nappes. | -- | -- | -- | -- | -- | -- |  | 0 | -- | -- | -- | -- | 0 | 0 | -- | 0 | 0 |  | -- | [9 empty] | pm | -- |  | pm
|  |  |  | (1.1.2) Construction des ouvrages de protection des périmètres | Structures for perimeters protection are built | 1.1.2.1 : Réaliser les études techniques complètes des ouvrages de protection dans les sites prioritaires identifiés (Conv ORMVAO) + ORMVAT+ORMVAO-2017 | 300000 | 31105.4637 | 31.11% | 300000 | 31105.4637 | 100% | 650000 | 67395.1713 | 67.4% | 650000 | 67395.1713 | 100% | 0 | 0 | 0% | 0 | 0 |  | 98.5% | [6 empty] | 98500.635 |  |  | 100000 | 964460.7871 |  | 100000
[6 empty] | 1.1.2.2 : Construire les ouvrages prioritaires ( Conv ORMVAO) + ORMVAT+O |  | 0 | 0% | 210000 | 21773.8246 | -- | 4760000 | 493540.024 | 82.26% | 4760000 | 493540.024 | 100% | 1024000 | 106173.3161 | 17.7% | 1024000 | 106173.3161 |  | 99.95% | [6 empty] | 515313.8486 | 51842.4395 | 397009.4016 | 600000 | 5786764.7226 |  | 600000
[6 empty] | 1.1.2.3 : Établir une convention d'entretien et de maintenance des ouvrages de protection des périmètres | -- | -- | -- | -- | -- | -- |  | -- | -- | -- | -- | -- | 0 | 0 | -- | 0 | 0 |  | -- | [9 empty] | pm | -- |  | pm
|  |  |  | (1.1.3) Réalisation des études de faisabilité pour l'exploitation des ressources en eau profonde (palmeraies asséchées/Maïder) | Feasibility studies on the exploitation of deepwater resources intended for the dried up palm groves of the Maïder basin are carried out. | 1.1.3.1 : Réaliser une étude d'exploration/reconnaissance par forage des ressources en eau profonde (Conv ABH) + ABH-2017 | 2000000 | 207369.758 | 34.56% | 2000000 | 207369.758 | 100% | 3750000 | 388818.2962 | 64.8% | 3750000 | 388818.2962 | 100% | 0 | 0 | 0% | 0 | 0 |  | 99.36% | [6 empty] | 596188.0542 |  |  | 600000 | 5786764.7226 |  | 600000
[6 empty] | 1.1.3.2 : Réaliser les études de faisabilité pour l'identification des sites prioritaires et le montage financier (Conv ABH) + ABH-2017 | 800000 | 82947.9032 | 41.47% | 800000 | 82947.9032 | 100% | 1110000 | 115090.2157 | 57.55% | 1110000 | 115090.2157 | 100% | 0 | 0 | 0% | 0 | 0 |  | 99.02% | [6 empty] | 198038.1189 |  |  | 200000 | 1928921.5742 |  | 200000
|  |  | 1.2 Les ouvrages vulnirales permettant d'améliorer l'efficience de distribution de l'eau sont réhabilités | (1.2.1) Réhabilitation des khettaras | Khettaras are restored | 1.2.1.1 Formaliser l’engagement des bénéficiaires dans l’opération de réhabilitation | -- | -- | -- | -- | -- | -- |  | -- | -- | -- | -- | -- | 0 | 0 | -- | 0 | 0 |  | -- | [9 empty] | pm | -- |  | pm
[6 empty] | 1.2.1.2 Mener les travaux de réhabilitation des khettaras (Conv ORMVAO) + (Conv ORMVAT) + ORMVAT+O-2017 | 2170000 | 224996.1874 | 25% | 3470000 | 359786.5301 | 159.9% | 6470000 | 670841.1671 | 74.54% | 6470000 | 670841.1671 | 100% | 0 | 0 | 0% | 0 | 0 |  | 99.54% | [6 empty] | 1030627.6971 | 383634.0523 | 206955.0185 | 900000 | 8680147.0839 |  | 900000
|  |  |  | (1.2.2) Réhabilitation des séguias | Seguias are restored | 1.2.2.1 Formaliser l’engagement des bénéficiaires dans l’opération de réhabilitation | -- | -- | -- | -- | -- | -- |  | -- | -- | -- | -- | -- | 0 | 0 | -- | 0 | 0 |  | -- | [9 empty] | pm | -- |  | pm
[6 empty] | 1.2.2.2 Réaliser les travaux de réhabilitation des réseaux de distribution des eaux d’irrigation (Conv ORMVAT)+ ORMVAT+O |  | 0 | 0% | 340000 | 35252.8589 | -- | 2890000 | 299649.3003 | 99.88% | 2890000 | 299649.3003 | 100% | 0 | 0 | 0% | 0 | 0 |  | 99.88% | [6 empty] | 334902.1591 | 394002.5402 | 216079.2878 | 300000 | 2893382.3613 |  | 300000
1346866.5781 | Total de la composante 1 | [5 empty] | 11140000 | 1155049.5519 | 30% | 12990000 | 1346866.5781 | 116.6% | 24806000 | 2572007.1082 | 66.81% | 24806000 | 2572007.1082 | 100% | 1024000 | 106173.3161 | 2.758% | 1024000 | 106173.3161 | 0 | 99.56% | [6 empty] | 3918873.6863 |  |  | 3850000 | 37131740.3034 |  | 3850000
| 2. Diversification des sources de revenus et amélioration des conditions de vie des populations vulnérables au changement climatique dans les zones cibles / Oucome 6 | Output 6: Targeted individual and community livelihood strategies strengthened in relation to climate change impacts, including variability | 2.1 Les moyens d'existence des familles sont améliorés grace au développement d'une petite agriculture oasienne résiliente | (2.1.1) Diffusion et adoption des techniques conservatoires |  | 2.1.1.1 Réaliser une étude sur les expériences déjà menées dans la zone ou dans des zones similaires à l’international. |  | 0 | 0% |  | 0 | -- | 480000 | 49768.7419 | 99.54% | 363600 | 37699.822 | 75.75% | 0 | 0 | 0% | 0 | 0 |  | 99.54% | [9 empty] | 50000 | 482230.3936 |  | 50000
[6 empty] | 2.1.1.2 Former de nouveaux agriculteurs aux techniques conservatoires et favoriser leur diffusion |  | 0 | 0% |  | 0 | -- | 700000 | 72579.4153 | 36.29% | 0 | 0 | 0% | 0 | 0 | 0% | 0 | 0 |  | 36.29% | [9 empty] | 200000 | 1928921.5742 |  | 200000
|  |  |  | (2.1.2) Développement et valorisation des produits agricoles oasiens. |  | 2.1.2.1 Accompagner les producteurs dans le processus de certification de leurs produits. (Conv ORMVAT + ORMVAO) |  | 0 | 0% |  | 0 | -- | 1000000 | 103684.879 | 51.84% | 1000000 | 103684.879 | 100% | 928000 | 96219.5677 | 48.11% | 928000 | 96219.5677 |  | 99.95% | [9 empty] | 200000 | 1928921.5742 |  | 200000
[6 empty] | 2.1.2.2 Promouvoir les produits agricoles des oasis. |  | 0 | 0% |  | 0 | -- | 450000 | 46658.1955 | 23.33% | 437077.5 | 45318.3277 | 97.13% | 938700 | 97328.9959 | 48.66% | 0 | 0 |  | 71.99% | [9 empty] | 200000 | 1928921.5742 |  | 200000
[6 empty] | 2.1.2.3 Encourager la recherche sur les espèces endémiques et leurs usages |  | 0 | 0% |  | 0 | -- | 960000 | 99537.4838 | 99.54% | 613272 | 63587.0331 | 63.88% | 0 | 0 | 0% | 0 | 0 |  | 99.54% | [9 empty] | 100000 | 964460.7871 |  | 100000
|  |  | 2.2 Des activités économiques non agricoles sont développés afin d'acroitre la résilience de la population oasienne | (2.2.1) Développement du tourisme durable et responsable face à l’impact du CC |  | 2.2.1.1 : Soutenir les acteurs du secteur touristique dans la responsabilisation de l’activité. |  | 0 | 0% |  | 0 | -- | 250000 | 25921.2197 | 35.03% | 0 | 0 | 0% | 0 | 0 | 0% | 0 | 0 |  | 35.03% | [9 empty] | 74000 | 713700.9825 |  | 74000
[6 empty] | 2.2.1.2 : Réaliser une étude sur les produits touristiques de niche à développer |  | 0 | 0% |  | 0 | -- | 960000 | 99537.4838 | 99.54% | 644784 | 66854.351 | 67.16% | 0 | 0 | 0% | 0 | 0 |  | 99.54% | [9 empty] | 100000 | 964460.7871 |  | 100000
|  |  |  | (2.2.2) Développement et soutien des activités économiques (les jeunes adultes et les femmes) |  | 2.2.2.1 : Soutenir les petits projets économiques locaux (Appels aux projets) | 1700000 | 176264.2943 | 44.07% | 1500000 | 155527.3185 | 88.24% | 1000000 | 103684.879 | 25.92% | 1000000 | 103684.879 | 100% | 3864153 | 400654.2362 | 100.2% | 3571130.2207 | 370272.2048 |  | 170.2% | [9 empty] | 400000 | 3857843.1484 | 44.07% | 400000
[6 empty] | 2.2.2.2 : Proposer des formations adaptées au contexte et aux besoins des oasis. |  | 0 | 0% |  | 0 | -- | 500000 | 51842.4395 | 12.79% | 1500000 | 155527.3185 | 300% | 0 | 0 | 0% | 0 | 0 |  | 12.79% | [9 empty] | 405400 | 3909924.0309 | 17626.4294 | 405400
155527.3185 | Total de la composante 2 | [5 empty] | 1700000 | 176264.2943 | 10.19% | 1500000 | 155527.3185 | 88.24% | 6300000 | 653214.7376 | 37.77% | 5558733.5 | 576356.6103 | 88.23% | 5730853 | 594202.7998 | 34.36% | 4499130.2207 | 466491.7725 |  | 82.32% | [9 empty] | 1729400 | 16679384.8521 |  | 1729400
| 3. Amélioration de la résilience des écosystèmes en réponse au changement climatique et à la variabilité / Oucome 5 | Output 5: Vulnerable ecosystem services and natural resource assets strengthened in response to climate change impacts, including variability | 3.1 Les menaces réduisant la valeur des écosystèmes oasiens sont prises en compte par les communes | 3.1.1 Organisation de lutte contre l’ensablement |  | 3.1.1.1 Réaliser une étude d’identification des sites prioritaires. |  | 0 |  |  |  | -- |  | 0 | -- |  |  | -- | 0 | 0 | -- | 0 | 0 |  | -- | [9 empty] | pm | -- | 3300 | pm
[6 empty] | 3.1.1.2 Soutenir financièrement l’action de lutte mécanique et biologique des Eaux et Forêts (ORMVAT ) |  | 0 |  |  |  | -- | 500000 | 51842.4395 | 17.28% | 500000 | 51842.4395 | 100% | 5500000 | 570266.8344 | 190.1% | 5813600 | 602782.4125 |  | 207.4% | [9 empty] | 300000 | 2893382.3613 |  | 300000
[6 empty] | 3.1.1.3 Mobiliser les populations pour la lutte contre l’ensablement des habitats et des parcelles. |  | 0 |  |  |  | -- |  | 0 | -- |  |  | -- | 0 | 0 | -- | 0 | 0 |  | -- | [9 empty] | pm | -- |  | pm
|  |  |  | 3.1.2 Développement des techniques de dépollution |  | 3.1.2.1 Étudier les impacts des activités économiques des oasis |  | 0 |  |  |  | -- | 190000 | 19700.127 | 98.5% | 124472.4 | 12905.9057 | 65.51% | 0 | 0 | 0% | 0 | 0 |  | 98.5% | [9 empty] | 20000 | 192892.1574 |  | 20000
[6 empty] | 3.1.2.2 : Former les acteurs concernés aux techniques de dépollution. |  | 0 |  |  |  | -- | 1000000 | 103684.879 | 51.84% | 906091.2 | 93947.9564 | 90.61% | 0 | 0 | 0% | 0 | 0 |  | 51.84% | [9 empty] | 200000 | 1928921.5742 |  | 200000
[6 empty] | 3.1.2.3 : Soutenir les services communautaires visant à protéger les ressources naturelles. |  | 0 |  |  |  | -- | 200000 | 20736.9758 | 25.92% | 200000 | 20736.9758 | 100% | 1071200 | 111067.2424 | 138.8% | 989969.7793 | 102644.8968 |  | 164.8% | [9 empty] | 80000 | 771568.6297 |  | 80000
|  |  | 3.2 Le patrimoine est préservé et valorisé | 3.2.1 Réhabilitation des anciennes constructions sont réhabilitées pour une nouvelle utilisation |  | 3.2.1.1 : Réaliser une étude afin d’identifier les constructions à réhabiliter. |  | 0 |  |  |  | -- |  | 0 |  |  |  | -- | 0 | 0 |  | 0 | 0 |  | -- | [9 empty] | pm | -- |  | pm
[6 empty] | 3.2.1.2 : Réhabiliter et aménager les constructions identifiées. |  | 0 |  |  |  | -- |  | 0 |  |  |  | -- | 0 | 0 |  | 0 | 0 |  | 0% | [9 empty] | 360000 | 3472058.8336 |  | 360000
|  |  |  | 3.2.2 Réutilisation des techniques et des matériaux traditionnels pour de nouvelles constructions |  | 3.2.2.1 : Etudier d’un point de vue de l’urbanisme la construction publique la plus pertinente à construire en pisé. |  | 0 |  |  |  | -- |  | 0 |  |  |  | -- | 0 | 0 |  | 0 | 0 |  | -- | [9 empty] | pm | -- |  | pm
[6 empty] | 3.2.2.2 : Construire le dit bâtiment. |  | 0 |  |  |  | -- |  | 0 |  |  | 0 | -- | 0 | 0 |  | 0 | 0 |  | 0% | [9 empty] | 50600 | 488017.1583 |  | 50600
|  |  |  | 3.2.3 des accès et des espaces d’interprétation sont réhabilités pour une meilleure accessibilité et attractivité des palmeraies |  | 3.2.3.1 : Aménager des accès et pistes au sein des palmeraies (réhabilitation, éclairage solaire…) y compris assistance technique. | [19 empty] | 4494593.4504 | 466021.378
[6 empty] | 3.2.3.2 : Aménager des espaces d’interprétations touristiques. | [19 empty] | 1000000 | 103684.879
|  |  |  | 3.2.4 des points d’eau et des équipements sont acquis pour une meilleure intervention contre les incendies |  | 3.2.4.1 : Aménager des points d’eau pour la lutte contre les incendies. | [19 empty] | 650000 | 67395.1713
[6 empty] | 3.2.4.2 : Acquérir de matériels de lutte contre les incendies | [19 empty] | 600000 | 62210.9274
| Total de la composante 3 | [5 empty] | 0 | 0 | 0% | 0 | 0 | -- | 1890000 | 195964.4213 | 19.39% | 1730563.6 | 179433.2774 | 91.56% | 6571200 | 681334.0768 | 67.42% | 6803569.7793 | 705427.3093 |  | 86.81% | 6744593.4504 | 699312.3557 | [7 empty] | 1010600 | 9746840.7145 |  | 1010600
| 4. Amélioration de la prise de conscience de tous les acteurs par la gestion et le partage des connaissances / Oucome 3 | Output 3: Targeted population groups participating in adaptation and risk reduction awareness activities | 4.1 Le débat public sur l'eau et le CC est organisé | 4.1.1 Réalisation d’un bilan des ressources en eau dans le sbassins (Gheris & Maïder) |  | 4.1.1.1 : Mise en place d’un Fonds Documentaire |  | 0 |  |  | 0 | -- | 535000 | 55471.4103 | 184.9% | 406020 | 42098.1346 | 75.89% | 443000 | 45932.4014 | 153.1% | 0 | 0 |  | 338% | [9 empty] | 30000 | 289338.2361 |  | 30000
[6 empty] | 4.1.1.2 : Renforcement du système de suivi des ressources en eau dans les zones du projet (Conv ABH) | 400000 | 41473.9516 | 138.2% | 400000 | 41473.9516 | 100% |  | 0 | 0% |  | 0 | -- | 0 | 0 | 0% | 0 | 0 |  | 138.2% | [9 empty] | 30000 | 289338.2361 |  | 30000
|  |  |  | 4.1.2 Opérationnalisation du Conseil local de dialogue sur l'eau |  | 4.1.2.1 : Elaboration d’un projet de charte sur l’eau et le changement climatique en milieu oasien |  | 0 |  |  | 0 | -- | 285000 | 29550.1905 | 98.5% | 218160 | 22619.8932 | 76.55% | 0 | 0 | 0% | 0 | 0 |  | 98.5% | [9 empty] | 30000 | 289338.2361 |  | 30000
[6 empty] | 4.1.2.2 : Organisation des conférences thématiques |  | 0 |  |  | 0 | -- | 150000 | 15552.7318 | 31.11% | 160180.0588 | 16608.25 | 106.8% | 150000 | 15552.7318 | 31.11% | 145594.2857 | 15095.9259 |  | 62.21% | [9 empty] | 50000 | 482230.3936 |  | 50000
|  |  | 4.2 | 4.2.1 Définition d’une stratégie de sensibilisation et de communication |  | 4.2.1.1 : Elaboration d’une stratégie de communication |  | 0 |  |  | 0 | -- | 285000 | 29550.1905 | 98.5% | 399960 | 41469.8042 | 91.94% | 0 | 0 |  | 0 | 0 |  | 98.5% | [9 empty] | 30000 | 289338.2361 | 835000 | 30000
[6 empty] | 4.2.1.2 : Campagne de communication | 150000 | 15552.7318 |  | 149842 | 15536.3496 | 99.89% | 150000 | 15552.7318 | 31.11% |  |  |  | 100000 | 10368.4879 | 20.74% | 97062.8571 | 10063.9506 |  | 82.95% | [9 empty] | 50000 | 482230.3936 |  | 50000
[6 empty] | 4.2.1.3 : Organisation du séminaire de clôture |  | 0 |  |  | 0 | -- |  | 0 |  |  |  | -- | 0 | 0 |  | 0 | 0 |  | 0% | 450000 | 46658.1955 | [7 empty] | 46590 | 449342.2807 |  | 46590
|  |  |  | 4.2.2 Mise en place d’un mécanisme de financement |  | 4.2.2.1 Etablissement de la liste des organisations partenaires des actions de sensibilisation | -- | -- |  | -- | -- | -- |  | -- |  |  |  | -- | 0 | 0 |  | 0 | 0 |  | -- | [9 empty] | pm | -- |  | pm
[6 empty] | 4.2.2.2 Gestion des appels à projets de sensibilisation |  | 0 |  |  | 0 | -- | 350000 | 36289.7076 | 36.29% | 278275.2 | 28852.9304 | 79.51% | 251000 | 26024.9046 | 26.02% | 0 | 0 |  | 62.31% | [9 empty] | 100000 | 964460.7871 |  | 100000
57010.3012 | Total de la composante 4 | [5 empty] | 550000 | 57026.6834 | 15.56% | 549842 | 57010.3012 | 99.97% | 1755000 | 181966.9626 | 49.64% | 1462595.2588 | 151649.0124 | 83.34% | 944000 | 97878.5258 | 26.7% | 242657.1429 | 25159.8765 |  | 91.89% | 450000 | 46658.1955 | [7 empty] | 366590 | 3535616.7994 |  | 366590
| 5. Renforcement des capacités des participants à la conception et mise en œuvre des mesures d’adaptation / Oucome 2 | Output 2: Strengthened capacity of national and subnational centres and networks to respond rapidly to extreme weather events | 5.1 Les capacité d'adaptation au CC sont consolidées et développées |  |  | 5.1.1.2 : Participation aux rencontres scientifiques et aux forums de sensibilisation | 100000 | 10368.4879 | 20.74% |  | 0 | 0% | 190000 | 19700.127 | 39.4% | 202894.7412 | 21037.1167 | 106.8% | 100000 | 10368.4879 | 20.74% | 97062.8571 | 10063.9506 |  | 80.87% | [9 empty] | 50000 | 482230.3936 |  | 50000
[6 empty] | 5.1.1.1 : Réalisation de modules de formation relatifs au changement climatique | 200000 | 165895.8064 | 51.84% | 1466635.14 | 152067.887 | 91.66% | 270000 | 27994.9173 | 42.68% | 0 | 0 | 12.84% | 0 | 0 | 0% | 0 | 0 |  | 121.8% | [9 empty] | 40000 | 385784.3148 |  | 40000
|  |  |  | 5.1.2 Formation des bénéficiaires oasiens aux MA innovantes |  | 5.1.2.1 : Réalisation de modules de formation relatifs à l’adaptation | 200000 | 20736.9758 | 51.84% |  | 0 |  | 260000 | 26958.0685 |  | 0 | 0 |  | 0 | 0 | 0% | 0 | 0 |  | 119.2% | [9 empty] | 40000 | 385784.3148 |  | 40000
[6 empty] | 5.1.2.2 : Organisation de voyages et de stages d’étude |  | 0 | 0% |  | 0 |  | 300000 | 31105.4637 |  | 227250 | 23562.3888 |  | 867000 | 89894.7901 | 81.72% | 0 | 0 |  | 110% | [9 empty] | 110000 | 1060906.8658 |  | 110000
|  |  | 5.2 Les capacitées en gestion concertées de projets de CC sont renforcées | 5.2.1 Formation des participants en conception et financement des projets |  | 5.2.1.1 : Réalisation de modules de formation en cycle du projet | 300000 | 31105.4637 | 51.84% |  | 0 |  | 200000 | 20736.9758 |  | 0 | 0 |  | 0 | 0 | 0% | 0 | 0 |  | 86.4% | [9 empty] | 60000 | 578676.4723 |  | 60000
[6 empty] | 5.2.1.2 : Réalisation de modules de formation en financement des projets | 300000 | 31105.4637 | 51.84% |  | 0 |  | 200000 | 20736.9758 |  | 0 | 0 |  | 0 | 0 | 0% | 0 | 0 |  | 86.4% | [9 empty] | 60000 | 578676.4723 |  | 60000
|  |  |  | 5.2.2 : Formation des participants en mise en œuvre et en gestion concertée des projets |  | 5.2.2.1 : Réalisation de modules de formation à l’approche participative appliquée aux mesures d’adaptation | 300000 | 31105.4637 | 51.84% |  | 0 |  | 270000 | 27994.9173 |  | 0 | 0 |  | 0 | 0 | 0% | 0 | 0 |  | 98.5% | [9 empty] | 60000 | 578676.4723 |  | 60000
[6 empty] | 5.2.2.2 : Réalisation de modules de formation en gestion des conflits et médiation | 300000 | 31105.4637 | 51.84% |  | 0 |  | 270000 | 27994.9173 |  | 0 | 0 |  | 0 | 0 | 0% | 0 | 0 |  | 98.5% | [9 empty] | 60000 | 578676.4723 |  | 60000
152067.887 | Total de la composante 5 | [5 empty] | 1700000 | 321423.1249 | 36.72% | 1466635.14 | 152067.887 | 86.27% | 1960000 | 203222.3628 | 42.34% | 430144.7412 | 44599.5054 | 21.95% | 967000 | 100263.278 | 20.89% | 97062.8571 | 10063.9506 |  | 99.95% | 0 | 0 | 0% | 0 | 0 |  |  |  |  | 480000 | 4629411.7781 | 2480000 | 480000
1711472.0848 | AT ABH | [5 empty] | 6480000 | 671878.0158 | 94.02% | 200000 | 20736.9758 | 85.81% | 1000000 | 103684.879 | 14.51% | 1000000 | 103684.879 | 100% | 0 | 0 | 0% | 0 | 0 |  | 108.5% | [9 empty] | 714577 | 6891814.9587 | 520000 | 714577
| AT ORMVAO | [8 empty] | 280000 | 29031.7661 | #DIV/0! |  |  |  |  | 0 | #REF! | 0 | 0 |  | 0 | 0 | [11 empty] | 0
| AT ORMVAT | [8 empty] | 150000 | 15552.7318 | [5 empty] | 0 |  | 0 | 0 |  | 0 | 0
| AT PACCZO | [8 empty] | 4930416 | 511209.5863 | #DIV/0! | [5 empty] | #REF! | 0 | 0 |  | 0 | 0 | [11 empty] | 0
| PGES | [5 empty] | 1800000 | 186632.7822 | 41.47% | 969600 | 100532.8587 | 53.87% | 849000 | 88028.4623 | 19.56% | 484800 | 50266.4293 | 57.1% | 243000 | 25195.4256 | 5.599% | 0 | 0 |  | 62.7% | [9 empty] | 450000 | 4340073.542 |  | 450000
[39 empty] | 2016 - PTBA1 | 2017 - PTBA2 | 2019 - PTBA3 | Composantes
2388536.0035 | Total Investissement | [5 empty] | 23370000 | 2568274.4525 | 28.17% | 23036493.14 | 2388536.0035 | 98.57% | 38560000 | 3998088.9338 | 46.48% | 35472837.1 | 3677996.8221 | 91.99% | 15480053 | 1605047.422 | 18.66% | 12666420 | 1313316.2249 |  | #REF! | 7194593.4504 | 745970.5513 | 8.673% | 0 | 0 |  |  |  |  | 8601167 | 82954882.9482 |  | 8601167 | 1695935.7352 | 3524045.5138 | 1313316.2249 | C1 | Convention - ABH GZR | 10436000
[42 empty] | C1+C2 | Convention - ORMVAO | 4070000
| Staff | [5 empty] | 0 | 0 |  | 0 | 0 |  |  | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 | [11 empty] | 0 | 0 |  | 0 |  |  |  | C1+C2+C3 | Convention - ORMVAT | 12800000
| Travel expenses |  |  | Frais de déplacement |  |  | 100000 | 10368.4879 | 22.17% | 100000 | 10368.4879 | 100% | 100000 | 10368.4879 | 14.78% | 100000 | 10368.4879 | 100% | 100000 | 10368.4879 | 14.78% | 96800 | 10036.6963 |  | 51.73% | 850000 | 88132.1471 | [7 empty] | 140298 | 1353119.1951 |  | 140298 |  |  |  | C2 | Convention - IAV | 1500000
|  |  |  | Frais de transport + carburant |  |  | 200000 | 20736.9758 |  | 200000 | 20736.9758 |  | 100000 | 10368.4879 |  | 100000 | 10368.4879 |  | 100000 | 10368.4879 |  | 0 | 0 | [11 empty] | 0 | [6 empty] | Total au 31/12/2017 en MAD |  | 28806000
| Restauration et hébergeent (Atelier de démarrage) | [5 empty] | 0 | 0 |  | 0 | 0 |  |  | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 | [11 empty] | 0 | [6 empty] | Total au 31/12/2017 ( - AT ) en MAD |  | 27806000
| Equipement |  |  | Equipement : Vehicules |  |  | 1040000 | 107832.2741 | 76.91% | 899997.71 | 93316.1537 | 89.66% |  | 0 | 4.366% |  |  | 99.6% | 0 | 0 | 17.46% | 0 | 0 |  | 98.74% | [9 empty] | 237475 | 2290353.2542 |  | 237475 |  |  |  | Total au 31/12/2017 ( - AT ) en USD |  | 2883061.7452
|  |  |  | Equipement : Matériel info + Photoc. + Fourniture de bureau |  |  | 570000 | 59100.381 |  | 536256 | 55601.6385 | #DIV/0! |  | 0 |  |  |  |  | 0 | 0 |  | 0 | 0 | [11 empty] | 0
|  |  |  | Fourniture de communication |  |  | 151500 | 15708.2592 |  | 143088 | 14836.062 | #DIV/0! | 100000 | 10368.4879 |  | 99600 | 10327.0139 |  | 400000 | 41473.9516 |  | 94992 | 9849.234 | [11 empty] | 0
| Suivi et évaluation / Montoring-Evaluation | [6 empty] | 0 |  |  | 0 |  | 1050000 | 108869.1229 | 51.84% | 531704.4 | 55129.7064 | 50.64% | 0 | 0 | 0% | 0 | 0 |  | 51.84% | [9 empty] | 210000 | 2025367.6529 |  | 210000
| Charges d'exécution | [5 empty] | 2061500 | 213746.378 | 36.37% | 1879341.71 | 194859.3178 | 91.16% | 1350000 | 139974.5866 | 23.81% | 831304.4 | 86193.6961 | 61.58% | 600000 | 62210.9274 | 10.58% | 191792 | 19885.9303 |  | #REF! | 850000 | 88132.1471 | 14.99% | 0 | 0 |  |  |  |  | 587773 | 5668840.1022 |  | 587773
| Staff | [7 empty] | 0% |  | 0 |  |  |  | 0% | 0 | 0 | 0% |  |  | 0% |  |  |  | 0% | [9 empty] | 240000 | 2314705.889 |  | 240000
| Monitoring and evaluation | [7 empty] | 0% |  | 0 |  |  |  | 0% | 0 | 0 | 0% |  |  | 0% |  |  |  | 0% | [9 empty] | 200000 | 1928921.5742 |  | 200000
| Travel expenses | [7 empty] | 0% |  | 0 |  |  |  | 0% | 0 | 0 | 0% |  |  | 0% |  |  |  | 0% | [9 empty] | 150000 | 1446691.1807 |  | 150000
| Equipment and materials | [7 empty] | 0% |  | 0 |  |  |  | 0% | 0 | 0 | 0% |  |  | 0% |  |  |  | 0% | [9 empty] | 24000 | 231470.5889 |  | 24000
| Audit | [7 empty] | 0% |  | 0 |  |  |  | 0% | 0 | 0 | 0% |  |  | 0% |  |  |  | 0% | [9 empty] | 110000 | 1060906.8658 |  | 110000
| Skill building | [7 empty] | 0% |  | 0 |  |  |  | 0% | 0 | 0 | 0% |  |  | 0% |  |  |  | 0% | [9 empty] | 57060 | 550321.3251 |  | 57060
| Charges de mise en œuvre | [5 empty] | 0 | 0 | 0% | 0 | 0 |  | 0 |  | 0% | 0 | 0 | 0% | 0 | 0 | 0% | 0 | 0 |  | #REF! | 0 | 0 | 0% | 0 | 0 |  |  |  |  | 781060 | 7533017.4237 |  | 781060
| Total Général : | [5 empty] | 25431500 | 2782020.8306 | 26.45% | 24915834.85 | 2583395.3213 | 97.97% | 39910000 |  | 41.51% | 36304141.5 | 3764190.5182 | 90.97% | 16080053 | 1667258.3494 | 16.72% | 12858212 | 1333202.1552 |  | #REF! | 8044593.4504 | 834102.6984 | 8.366% | 0 | 0 |  |  |  |  | 9970000 | 96156740.4741 |  | 9970000
[19 empty] | 16080053 |  |  | 12858212 | 1333202.1552 |  |  |  | 745970.5513
[7 empty] | 21570000 | 2381641.6704 |  |  |  |  | 39910000 | [21 empty] | 9188940 | 88623723.0504
781.06

## PTBA 4 (hidden)
9.6446
42371.4504
Composante | Résultat | Produits | Activités | Coûts | Coûts
|  |  |  | en Dirhams | en USD
Composante 3 : Amélioration de la résilience des écosystèmes en réponse au changement climatique et à la variabilité. | 3.2 Le patrimoine oasien est préservé et valorisé | 3.2.3 des accès et des espaces d’interprétation sont réhabilités pour une meilleure accessibilité et attractivité des palmeraies | 3.2.3.1 : Aménager des accès et pistes au sein des palmeraies (réhabilitation, éclairage solaire…) y compris assistance technique. | 4494593.4504 | 466021.378 | 0
|  |  | 3.2.3.2 : Aménager des espaces d’interprétations touristiques. | 1000000 | 103684.879
|  | 3.2.4 des points d’eau et des équipements sont acquis pour une meilleure intervention contre les incendies | 3.2.4.1 : Aménager des points d’eau pour la lutte contre les incendies. | 650000 | 67395.1713
|  |  | 3.2.4.2 : Acquérir de matériels de lutte contre les incendies. | 600000 | 62210.9274
Total composante 3 |  |  |  | 6744593.4504 | 699312.3557
Comosanse 4 | Séminaire de cloture |  |  | 450000 | 46658.1955
Total investissement |  |  |  | 7194593.4504 | 745970.5513 | 7194593.4504
|  | Mise en peuvre |  | 850000 | 88132.1471
Total PTBA 4 |  |  |  | 8044593.4504 | 834102.6984

## Versements (hidden)
Vessements | DATE OPERATION | DATE VALEUR | LIBELLE OPERATION | DEBIT | CREDIT | Solde
V1 | 2015-05-22 | 2015-05-21 | VRT O/ INTL BANK FOR RECONSTR.+DEVE |  | 25669937.1 | 25669937.1
V1 | 2015-05-22 | 2015-05-21 | VRT O/ INTL BANK RECONST.+ DEVELOPM |  | 2638618.05 | 28308555.15 |  |  | ADA | 5088189.79 | 527568.3426
V1 | 2015-10-28 | 2015-10-28 | VIREMENT EMIS N 34 | 25431530 |  | 28308555.15 |  |  | ANDZOA | 83081381.62 | 8614282.9995
V2 | 2017-06-15 | 2017-06-14 | VRT O/ IBRD - TRUST FUNDS |  | 41331390.92 | 69639946.07
V2 | 2017-06-16 | 2017-06-15 | VRT O/ IBRD TRUST FUNDS |  | 1358326.42 | 70998272.49
V2 | 2017-09-15 | 2017-09-15 | OV N 25 | 39594335 |  | 70998272.49
V3 | 2019-02-04 | 2019-02-01 | O/ IBRD TRUST FUNDS |  | 16080053.6 | 87078326.09
V3 | 2019-02-04 | 2019-02-01 | O/ IBRD TRUST FUNDS |  | 1091245.32 | 88169571.41
V3 | 2019-08-02 | 2019-08-02 | VIREMENT EMIS N°238 | 16080053.6 |  | 88169571.41
|  |  |  | Versement à l'ANDZOA | Versement de l'FA |  | Taux | 9.6446
|  |  | MAD | 81105918.6 | 88169571.41
|  |  | USD | 8409457.3553 | 9141851.3421
|  | Demande PTBA 4 |  |  | 745970.5513
9887821.8934

## Overview
Project Performance Report (PPR)
| Period of Report (Dates) | 2019
| Project Title: | Projet d’Adaptation au Changements Climatiques dans les Zones Oasiennes au Maroc PACCZO
| Project Summary: | PACCZO Project aims to help reduce the vulnerability of people and oasis agro ecosystems in Morocco to climate change by increasing the adaptive capacity of local actors, increasing the resilience of the target ecosystem and by disseminating knowledge management. Actions will include improved management of soil and water resources, as well as the use of resistant varieties of palm trees and training sessions for the stakeholders. The project objectives will be achieved through five components: - Component 1: Improving adaptive capacities of the water sector. - Component 2: Diversifying income sources and improving the living conditions of populations vulnerable to climate change. - Component 3: Improving the ecosystems’ resilience in response to climate change and variability. - Component 4: Improving stakeholder awareness though the management and exchange of knowledge. - Component 5: Strengthening the capacities of participants in the design and implementation of adaptation measures.
|  |  | Countries | Project Type: |  | GEF Focal Area: | GEF 4 Focal Areas | GEF 2 / 3 Operational Programme: | Overall Rating of the project in the evaluation by the project evaluator: | GEF-4 Focal Area Strategic Program: | GEF-3 Focal Area Strategic Program:
| Database Number: |  | Afghanistan | FP | Yes | Biodiversity | 1 | 1 | U | BD-SP1-PA Financing | 1: Arid & semi-arid ecosystems
Implementing Entity (IE) [name]: |  | Agence pour Développement Agricole (ADA) | Albania | MSP | No | Climate Change Adaptation | 2 | 2 | S | BD-SP2-Marine PA | 2: Coastal, marine & freshwater ecosystems
| Type of IE: |  | Algeria | EA |  | Climate Change Mitigation | 3 | 3 | MU | BD-SP3-PA Networks | 3: Forest ecosystems
| Country(ies): | Morocco | Angola |  |  | International Waters | 5 | 5 | Good | BD-SP5-Markets | 13: Conservation and Sustainable Use of Biological Diversity Important to Agriculture
Relevant Geographic Points (i.e. cities, villages, bodies of water): |  | Bassin Maider "area located downstream of a catchment where the availability of water resources must be protected to ensure the preservation of the drinking water supply" (Regions : Alnif, Hssia, Mssissi, Tazarine, Taghbalte, Ait Oualal, Ait Boudaoud, Nkob) Bassin Gheris "area located in the intermediary part of a catchment where water resources can still be mobilized for saving the palm groves with a potential for agricultural production" (Regions : Ferkla, Gheris, Tinjdad, Mellaab) | Argentina |  |  | Multiple Focal Area |  |  |  | BD-SP7-Invasive Alien Species(IAS) | 6: Promoting the adoption of renewable energy by removing barriers and reducing implementation costs
[8 empty] | CC-SP2- Industrial EE | 8: Waterbody based operational program
| Project Milestones | [6 empty] | CC-SP3-RE,CC-SP4-Biomass | 9: Integrated Land and Water multiple focal area
| Milestone |  | Bahamas | [6 empty] | CC-SP5-Transport | 10: Contaminants based operational program
AFB Approval Date:
2015-04-09
IE-AFB Agreement Signature Date: |  | 2015-05-14 | [6 empty] | CC-SP6-LULUCF | 12: Integrated Ecosystem Management
Start of Project/Programme: |  | 2015-12-14 | [6 empty] | Cross cutting capacity building | 14: Persistent Organic Pollutants
Mid-term Review Date (if planned): |  | 2018-06-30
| Terminal Evaluation Date: | 2020-12-14
|  | List documents/ reports/ brochures / articles that have been prepared about the project. | Cyprus
|  | AWPB (Annual Work Plan and Budget) 2016, 2017, 2019, Manual and the management procedures of the project, Project Brochure, Environmental and Social Management Plans, Training Reports (Strengthening capacities), First semi-annual report 2016, 2017, 2018 & 2019 (Prepared by EE), Second half-yearly report 2016, 2017, 2018, 2019 (Prepared by EE), EE's Technical Assistance Reports, Project Monitoring Report n° 01 (Prepared by NIE), Project Monitoring Report n° 02 (Prepared by NIE), Audit report for the year 2015, 2016, 2017 (Prepared by NIE). | Czech Republic
List the Website address (URL) of project. |  |  | Democratic People's Republic of Korea
|  | http://andzoa.ma/fr/2016/01/26/atelier-de-demarrage-du-pacczo/ | Democratic Republic of the Congo
Denmark
| Project contacts: |  | Djibouti
National Project Manager/Coordinator |  |  | Dominica
| Name: |  | Dominican Republic
| Email: |  | Ecuador
| Date: |  | Egypt
| Government DA |  | El Salvador
| Name: | Mr Rachid Firadi | Equatoral Guinea
| Email: | firadienvironnement@gmail.com | Eritrea
| Date: |  | Estonia
| Implementing Entity |  | Ethiopia
| Name: | Ms Meryem ANDALOUSSI | Fiji
| Email: | m.andaloussi@ada.gov.ma / meryem.andaloussi@gmail.com | Finland
| Date: |  | France
| Executing Agency |  | Gambia
| Name: | Mr Ali OUBRHOU | Georgia
| Email: | oubrhou@gmail.com | Germany
| Date: |  | Ghana
| Executing Agency |  | Greece
| Name: |  | Grenada
| Email: |  | Guatemala
| Date: |  | Guinea
| Executing Agency |  | Guinea Bissau
| Name: |  | Guyana
| Email: |  | Haiti
| Date: |  | Honduras
Hungary
Iceland
India
Indonesia
Iran (Islamic Republic of)
Iraq
Ireland
Israel
Italy
Jamaica
Japan
Jordan
Kazakhstan
Kenya
Kiribati
Kuwait
Kyrgyzstan
Lao People’s Democratic Republic
Latvia
Lebanon
Lesotho
Liberia
Libyan Arab Jamahiriya
Liechtenstein
Lithuania
Luxembourg
Madagascar
Malawi
Malaysia
Maldives
Mali
Malta
Marshall Islands
Mauritania
Mauritius
Mexico
Micronesia, Federated States of
Monaco
Mongolia
Montenegro
Morocco
Mozambique
Myanmar
Namibia
Nauru
Nepal
Netherlands
New Zealand
Nicaragua
Niger
Nigeria
Norway
Oman
Pakistan
Palau
Panama
Papua New Guinea
Paraguay
Peru
Philippines
Poland
Portugal
Qatar
Republic of Korea
Republic of Moldova
Romania
Russian Federation
Rwanda
Saint Kitts and Nevis
Saint Lucia
Saint Vincent and the Grenadines
Samoa
San Marino
Sao Tome and Principe
Saudi Arabia
Senegal
Serbia
Seychelles
Sierra Leone
Singapore
Slovakia
Slovenia
Solomon Islands
Somalia
South Africa
Spain
Sri Lanka
Sudan
Suriname
Swaziland
Sweden
Switzerland
Syrian Arab Republic
Tajikistan
Thailand
The former Yugoslav Republic of Macedonia
Timor-Leste
Togo
Tonga
Trinidad and Tobago
Tunisia
Turkey
Turkmenistan
Tuvalu
Uganda
Ukraine
United Arab Emirates
United Kingdom of Great Britain and Northern Ireland
United Republic of Tanzania
United States of America
Uruguay
Uzbekistan
Vanuatu
Venezuela, Bolivarian Republic of
Viet Nam
Yemen
Zambia
Zimbabwe

## FinancialData-to-Dec-31-2019
3524045.5138
Financial information: cumulative from project start to [Dec-31-2019]
DISBURSEMENT OF AF GRANT FUNDS
How much of the total AF grant as noted in Project Document plus any project preparation grant has been spent to date?
Estimated cumulative total disbursement as of [Dec-31-2019] | 9141851.3421
Estimated cumulative total disbursement as of [Mar-31-2020] | 6533298
Add any comments on AF Grant Funds. (word limit=200)
INVESTMENT INCOME | 45907.7337
Amount of annual investment income generated from the Adaptation Fund’s grant
EXPENDITURE DATA
List ouput and corresponding amount spent for the current reporting period | Compenent / Outcome | Outputs | Expected Outcomes | Products | Activities | AMOUNT
| 1. Improving adaptive capacities of the water sector / Outcome 4 | Output 4: Vulnerable development sector services and infrastructure assets strengthened in response to climate change impacts, including variability | 1.1 Improved joint regulation of ground and surface water through new sustainable hydraulic and protective structure management | (1.1.1) Replenishment structures for groundwater are built | 1.1.1.1 Carry out complementary studies of groundwater recharge structures on the potential sites identified | 0
[5 empty] | 1.1.1.2 Build infrastructure with the greatest potential | 0
[5 empty] | 1.1.1.3 Purchase of the follow-up equipment (piezometers). | 0
[5 empty] | 1.1.1.4 Ensure the follow-up evaluation in coordination with the HBA | 0
[5 empty] | 1.1.1.5 Establish a maintenance agreement for the groundwater recharges structures. | 0
|  |  |  | (1.1.2) Structures for perimeters protection are built | 1.1.2.1 : Carry out complete technical studies of protective infrastructure in the priority sites identified | 0
[5 empty] | 1.1.2.2 : Build priority infrastructure. | 106173.3161
[5 empty] | 1.1.2.3 : Establish a maintenance agreement for perimeter protection structures | 0
|  |  |  | (1.1.3) Feasibility studies on the exploitation of deep-water resources intended for the dried up palm groves of the Maïder basin are carried out. | 1.1.3.1 : Carry out an exploration/reconnaissance study through drilling for deepwater resources. | 0
[5 empty] | 1.1.3.2 : Carry out feasibility studies to identify priority sites and their financing. (Conv ABH) | 0
|  |  | 1.2 Vulnerable infrastructure allowing the improvement of water distribution efficiency are restored | (1.2.1) Khettaras are restored | 1.2.1.1 Formalize the commitment of the beneficiaries in the restoration of the khettaras | 0
[5 empty] | 1.2.1.2 Lead the works on the restoration of the khettaras | 0
|  |  |  | (1.2.2) Seguias are restored | 1.2.2.1 Formalize the commitment of the beneficiaries in the restoration work | 0
[5 empty] | 1.2.2.2 Carry out the restoration works on the irrigation water distribution networks: irrigation channels | 0
| Total of Component 1 |  |  |  |  | 106173.3161
| 2. Diversifying income sources and improving the living conditions of populations vulnerable to climate change in the targeted areas / Oucome 6 | Output 6: Targeted individual and community livelihood strategies strengthened in relation to climate change impacts, including variability | 2.1 Improved livelihoods of families due to the development of more resilient small scale agriculture | (2.1.1) Conservation technics are circulated and adopted | 2.1.1.1 Carry out a study on the experiences already undertaken in the zone or in similar zones abroad. | 0
[5 empty] | 2.1.1.2 Train new farmers on the conservation techniques and promote their circulation | 0
|  |  |  | (2.1.2) Oasis agriculture products are developed and promoted | 2.1.2.1 Support the producers in the certification process for their products. | 96219.5677
[5 empty] | 2.1.2.2 Promotion of oasis agricultural products. | 0
[5 empty] | 2.1.2.3 Encourage research on endemic species and their uses. usages | 0
|  |  | 2.2 Developed non-agricultural economic activities help increase the resilience of the Oasis population | (2.2.1) Sustainable and responsible tourism, which faces up to climate change is developed | 2.2.1.1: Support the Tourism stakeholders to make the sector more accountable | 0
[5 empty] | 2.2.1.2: Carry out a study on niche tourism products to develop. | 0
|  |  |  | (2.2.2) Other economic activities, particularly for youths and women, are supported and developed | 2.2.2.1: Support small-scale local economic projects | 370272.2048
[5 empty] | 2.2.2.2: Offer training adapted to the context and needs of the oasis | 0
| Total of Component 2 |  |  |  |  | 466491.7725
| 3. Improving the ecosystems’ resilience in response to climate change and variability / Oucome 5 | Output 5: Vulnerable ecosystem services and natural resource assets strengthened in response to climate change impacts, including variability | 3.1 Threats reducing the value of Oasis ecosystems are taken into account by municipalities | 3.1.1 The fight against desertification is organized | 3.1.1.1 Carry out a study to identify the priority sites | 0
[5 empty] | 3.1.1.2 Financial support for the Water and Forests Commission man-made and biological efforts | 602782.4125
[5 empty] | 3.1.1.3 Populations will be mobilized in the fight against desertification of housing and parcels of land. | 0
|  |  |  | 3.1.2 Techniques for environmental cleanup are developed | 3.1.2.1 Study the impact of the oasis economic activities | 0
[5 empty] | 3.1.2.2: Train the stakeholders concerned on environmental cleanup techniques | 0
[5 empty] | 3.1.2.3: Support community services, which aim to protect natural resources | 102644.8968
|  |  | 3.2. Preserved and Promoted Heritage | 3.2.1 Historic constructions are restored for new uses | 3.2.1.1: Carry out a study in order to identify the mud brick buildings to restore | 0
[5 empty] | 3.2.1.2: Restore and fix up the buildings with a heritage interest | 0
|  |  |  | 3.2.2 Traditional techniques and materials are reused for new constructions | 3.2.2.1: Study, bearing in mind town planning, the most pertinent public building to be done in mud brick | 0
[5 empty] | 3.2.2.2: Construct said building | 0
| Total of Component 3 |  |  |  |  | 705427.3093
| 4. Improving stakeholder awareness through the management and exchange of knowledge / Oucome 3 | Output 3: Targeted population groups participating in adaptation and risk reduction awareness activities | 4.1 Organized public debate on water and climate change | 4.1.1 An assessment of resources in the intermediary Gheris basin and Maider is carried out | 4.1.1.1: Implementation of a Documentation library | 0
[5 empty] | 4.1.1.2: Strengthening of the monitoring system for water resources in the project zones. (Conv ABH) | 0
|  |  |  | 4.1.2 local council for water dialogue is operational | 4.1.2.1: Writing of a draft Charter on water and climate change in the Oases | 0
[5 empty] | 4.1.2.2: Organization of conferences on the themes of water and climate change | 15095.9259
|  |  | 4.2. Supported and developed local initiatives for communication | 4.2.1 An awareness and communication strategy is developed | 4.2.1.1: Writing of a communication strategy | 0
[5 empty] | 4.2.1.2: « Mass » communication campaign | 10063.9506
[5 empty] | 4.2.1.3: Organization of a close out seminar | 0
|  |  |  | 4.2.2 A financing mechanism is implemented | 4.2.2.1 Establishing of a list of Partner-organizations for awareness actions | 0
[5 empty] | 4.2.2.2 Management of call for projects on awareness. | 0
| Total of Component 4 |  |  |  |  | 25159.8765
| 5. Strengthening the capacities of participants in the design and implementation of adaptation measures / Oucome 2 | Output 2: Strengthened capacity of national and subnational centres and networks to respond rapidly to extreme weather events | 5.1 Consolidated and developed adaptive capacities for climate change | 5.1.1 the managers of public service are informed on the issues of climate change and introduced to adaptability measures for the main sectors | 5.1.1.2: Participation in scientific meetings and forums | 10063.9506
[5 empty] | 5.1.1.1: Conduct climate change training modules | 0
|  |  |  | 5.1.2 Oasis beneficiaries are trained on innovative adaptability measures | 5.1.2.1: Conduct adaptation training modules | 0
[5 empty] | 5.1.2.2: Organizing trips and internships | 0
|  |  | 5.2 Strengthened coordinated management capacities for climate change projects | 5.2.1 The participants (operators and beneficiaries) are trained in the designing and financing of projects | 5.2.1.1: Conduct modules on the project cycle | 0
[5 empty] | 5.2.1.2: Conduct training modules on project financing | 0
|  |  |  | 5.2.2 : The participants (operators and beneficiaries) are trained on the implementation and joint management of projects. | 5.2.2.1: Conduct training modules on the participatory approach | 0
[5 empty] | 5.2.2.2: Conduct training modules in conflict management and mediation | 0
| Total of Component 5 |  |  |  |  | 10063.9506
| TOTAL |  |  |  |  | 1313316.2249
PLANNED EXPENDITURE SCHEDULE | [6 empty] | Est. Completion Date
List outputs planned and corresponding projected cost for the upcoming (2020-2021) reporting period | Compenent / Outcome | Outputs | Expected Outcomes | Products | Activities | AMOUNT $US | 2020 |  | 2021
[7 empty] | S1 | S2 | S1 | S2
| 1. Improving adaptive capacities of the water sector / Outcome 4 | Output 4: Vulnerable development sector services and infrastructure assets strengthened in response to climate change impacts, including variability | 1.1 Improved joint regulation of ground and surface water through new sustainable hydraulic and protective structure management | (1.1.1) Replenishment structures for groundwater are built | 1.1.1.1 Carry out complementary studies of groundwater recharge structures on the potential sites identified | 0
[5 empty] | 1.1.1.2 Build infrastructure with the greatest potential | 0
[5 empty] | 1.1.1.3 Purchase of the follow-up equipment (piezometers). | 0
[5 empty] | 1.1.1.4 Ensure the follow-up evaluation in coordination with the HBA | 0
[5 empty] | 1.1.1.5 Establish a maintenance agreement for the groundwater recharges structures. | 0
|  |  |  | (1.1.2) Structures for perimeters protection are built | 1.1.2.1 : Carry out complete technical studies of protective infrastructure in the priority sites identified | 0
[5 empty] | 1.1.2.2 : Build priority infrastructure. | 0
[5 empty] | 1.1.2.3 : Establish a maintenance agreement for perimeter protection structures | 0
|  |  |  | (1.1.3) Feasibility studies on the exploitation of deep-water resources intended for the dried up palm groves of the Maïder basin are carried out. | 1.1.3.1 : Carry out an exploration/reconnaissance study through drilling for deepwater resources. | 0
[5 empty] | 1.1.3.2 : Carry out feasibility studies to identify priority sites and their financing. | 0
|  |  | 1.2 Vulnerable infrastructure allowing the improvement of water distribution efficiency are restored | (1.2.1) Khettaras are restored | 1.2.1.1 Formalize the commitment of the beneficiaries in the restoration of the khettaras | 0
[5 empty] | 1.2.1.2 Lead the works on the restoration of the khettaras | 0
|  |  |  | (1.2.2) Seguias are restored | 1.2.2.1 Formalize the commitment of the beneficiaries in the restoration work | 0
[5 empty] | 1.2.2.2 Carry out the restoration works on the irrigation water distribution networks: irrigation channels | 0
| Total of Component 1 |  |  |  |  | 0
| 2. Diversifying income sources and improving the living conditions of populations vulnerable to climate change in the targeted areas / Oucome 6 | Output 6: Targeted individual and community livelihood strategies strengthened in relation to climate change impacts, including variability | 2.1 Improved livelihoods of families due to the development of more resilient small scale agriculture | (2.1.1) Conservation technics are circulated and adopted | 2.1.1.1 Carry out a study on the experiences already undertaken in the zone or in similar zones abroad. | 0
[5 empty] | 2.1.1.2 Train new farmers on the conservation techniques and promote their circulation | 0
|  |  |  | (2.1.2) Oasis agriculture products are developed and promoted | 2.1.2.1 Support the producers in the certification process for their products. | 0
[5 empty] | 2.1.2.2 Promotion of oasis agricultural products. | 0
[5 empty] | 2.1.2.3 Encourage research on endemic species and their uses. usages | 0
|  |  | 2.2 Developed non-agricultural economic activities help increase the resilience of the Oasis population | (2.2.1) Sustainable and responsible tourism, which faces up to climate change is developed | 2.2.1.1: Support the Tourism stakeholders to make the sector more accountable | 0
[5 empty] | 2.2.1.2: Carry out a study on niche tourism products to develop. | 0
|  |  |  | (2.2.2) Other economic activities, particularly for youths and women, are supported and developed | 2.2.2.1: Support small-scale local economic projects | 0
[5 empty] | 2.2.2.2: Offer training adapted to the context and needs of the oasis | 0
| Total of Component 2 |  |  |  |  | 0
| 3. Improving the ecosystems’ resilience in response to climate change and variability / Oucome 5 | Output 5: Vulnerable ecosystem services and natural resource assets strengthened in response to climate change impacts, including variability | 3.1 Threats reducing the value of Oasis ecosystems are taken into account by municipalities | 3.1.1 The fight against desertification is organized | 3.1.1.1 Carry out a study to identify the priority sites | 0
[5 empty] | 3.1.1.2 Financial support for the Water and Forests Commission man-made and biological efforts | 0
[5 empty] | 3.1.1.3 Populations will be mobilized in the fight against desertification of housing and parcels of land. | 0
|  |  |  | 3.1.2 Techniques for environmental cleanup are developed | 3.1.2.1 Study the impact of the oasis economic activities | 0
[5 empty] | 3.1.2.2: Train the stakeholders concerned on environmental cleanup techniques | 0
[5 empty] | 3.1.2.3: Support community services, which aim to protect natural resources | 0
|  |  | 3.2. Preserved and Promoted Heritage | 3.2.1 Historic constructions are restored for new uses | 3.2.1.1: Carry out a study in order to identify the mud brick buildings to restore | 0
[5 empty] | 3.2.1.2: Restore and fix up the buildings with a heritage interest | 0
|  |  |  | 3.2.2 Traditional techniques and materials are reused for new constructions | 3.2.2.1: Study, bearing in mind town planning, the most pertinent public building to be done in mud brick | 0
[5 empty] | 3.2.2.2: Construct said building | 0
|  |  |  | 3.2.3 Access and interpretation spaces are rehabilitated for better accessibility and attractiveness of palm groves | 3.2.3.1 : Fix up access and tracks in palm groves (rehabilitation, solar lighting, etc.) including technical assistance. | 466021.378
[5 empty] | 3.2.3.2 : Fix up spaces for tourist interpretations. | 103684.879
|  |  |  | 3.2.4 Water points and equipment are acquired for a better response to fires | 3.2.4.1 : Fix up water's points for fire fighting | 67395.1713
[5 empty] | 3.2.4.2 : Acquire fire fighting equipment | 62210.9274
| Total of Component 3 |  |  |  |  | 699312.3557
| 4. Improving stakeholder awareness through the management and exchange of knowledge / Oucome 3 | Output 3: Targeted population groups participating in adaptation and risk reduction awareness activities | 4.1 Organized public debate on water and climate change | 4.1.1 An assessment of resources in the intermediary Gheris basin and Maider is carried out | 4.1.1.1: Implementation of a Documentation library | 0
[5 empty] | 4.1.1.2: Strengthening of the monitoring system for water resources in the project zones. | 0
|  |  |  | 4.1.2 local council for water dialogue is operational | 4.1.2.1: Writing of a draft Charter on water and climate change in the Oases | 0
[5 empty] | 4.1.2.2: Organization of conferences on the themes of water and climate change | 0
|  |  | 4.2. Supported and developed local initiatives for communication | 4.2.1 An awareness and communication strategy is developed | 4.2.1.1: Writing of a communication strategy | 0
[5 empty] | 4.2.1.2: « Mass » communication campaign | 0
[5 empty] | 4.2.1.3: Organization of a close out seminar | 46658.1955
|  |  |  | 4.2.2 A financing mechanism is implemented | 4.2.2.1 Establishing of a list of Partner-organizations for awareness actions | 0
[5 empty] | 4.2.2.2 Management of call for projects on awareness. | 0
| Total of Component 4 |  |  |  |  | 46658.1955
| 5. Strengthening the capacities of participants in the design and implementation of adaptation measures / Oucome 2 | Output 2: Strengthened capacity of national and subnational centres and networks to respond rapidly to extreme weather events | 5.1 Consolidated and developed adaptive capacities for climate change | 5.1.1 the managers of public service are informed on the issues of climate change and introduced to adaptability measures for the main sectors | 5.1.1.2: Participation in scientific meetings and forums | 0
[5 empty] | 5.1.1.1: Conduct climate change training modules | 0
|  |  |  | 5.1.2 Oasis beneficiaries are trained on innovative adaptability measures | 5.1.2.1: Conduct adaptation training modules | 0
[5 empty] | 5.1.2.2: Organizing trips and internships | 0
|  |  | 5.2 Strengthened coordinated management capacities for climate change projects | 5.2.1 The participants (operators and beneficiaries) are trained in the designing and financing of projects | 5.2.1.1: Conduct modules on the project cycle | 0
[5 empty] | 5.2.1.2: Conduct training modules on project financing | 0
|  |  |  | 5.2.2 : The participants (operators and beneficiaries) are trained on the implementation and joint management of projects. | 5.2.2.1: Conduct training modules on the participatory approach | 0
[5 empty] | 5.2.2.2: Conduct training modules in conflict management and mediation | 0
| Total of Component 5 |  |  |  |  | 0
| TOTAL |  |  |  |  | 745970.5513
ACTUAL CO-FINANCING (If the MTR or TE have not been undertaken this reporting period, DO NOT report on actual co-financing.)
How much of the total co-financing as committed in the Project Document has actually been realized?
Estimated cumulative actual co-financing as verified during Mid-term Review (MTR) or Terminal Evaluation (TE).
Add any comments on actual co-financing in particular any issues related to the realization of in-kind, grant, credits, loans, equity, non-grant instruments and other types of co-financing. (word limit=200)

## FinancialData-to-Mar-31-2020 (hidden)
3524045.5138
Financial information: cumulative from project start to [Jun-30-2018]
DISBURSEMENT OF AF GRANT FUNDS
How much of the total AF grant as noted in Project Document plus any project preparation grant has been spent to date?
Estimated cumulative total disbursement as of [Dec-31-2017] | 4578998
Estimated cumulative total disbursement as of [Jun-30-2018] | 5219982
Add any comments on AF Grant Funds. (word limit=200)
INVESTMENT INCOME | 58662.1009
Amount of annual investment income generated from the Adaptation Fund’s grant
EXPENDITURE DATA
List ouput and corresponding amount spent for the current reporting period | Compenent / Outcome | Outputs | Products | Activities | AMOUNT
| 1. Improving adaptive capacities of the water sector / Outcome 4 | Output 4: Vulnerable development sector services and infrastructure assets strengthened in response to climate change impacts, including variability | (1.1.1) Replenishment structures for groundwater are built | 1.1.1.1 Carry out complementary studies of groundwater recharge structures on the potential sites identified | 0
|  |  |  | 1.1.1.2 Build infrastructure with the greatest potential | 528792.8828
|  |  |  | 1.1.1.3 Purchase of the follow-up equipment (piezometers). | 7880.0508
|  |  |  | 1.1.1.4 Ensure the follow-up evaluation in coordination with the HBA | --
|  |  |  | 1.1.1.5 Establish a maintenance agreement for the groundwater recharges structures. | --
|  |  | (1.1.2) Structures for perimeters protection are built | 1.1.2.1 : Carry out complete technical studies of protective infrastructure in the priority sites identified | 67395.1713
|  |  |  | 1.1.2.2 : Build priority infrastructure. | 493540.024
|  |  |  | 1.1.2.3 : Establish a maintenance agreement for perimeter protection structures | --
|  |  | (1.1.3) Feasibility studies on the exploitation of deep-water resources intended for the dried up palm groves of the Maïder basin are carried out. | 1.1.3.1 : Carry out an exploration/reconnaissance study through drilling for deepwater resources. | 388818.2962
|  |  |  | 1.1.3.2 : Carry out feasibility studies to identify priority sites and their financing. (Conv ABH) | 115090.2157
|  |  | (1.2.1) Khettaras are restored | 1.2.1.1 Formalize the commitment of the beneficiaries in the restoration of the khettaras | --
|  |  |  | 1.2.1.2 Lead the works on the restoration of the khettaras | 670841.1671
|  |  | (1.2.2) Seguias are restored | 1.2.2.1 Formalize the commitment of the beneficiaries in the restoration work | --
|  |  |  | 1.2.2.2 Carry out the restoration works on the irrigation water distribution networks: irrigation channels | 299649.3003
| Total of Component 1 |  |  |  | 2572007.1082
| 2. Diversifying income sources and improving the living conditions of populations vulnerable to climate change in the targeted areas / Oucome 6 | Output 6: Targeted individual and community livelihood strategies strengthened in relation to climate change impacts, including variability | (2.1.1) Conservation technics are circulated and adopted | 2.1.1.1 Carry out a study on the experiences already undertaken in the zone or in similar zones abroad. | 37699.822
|  |  |  | 2.1.1.2 Train new farmers on the conservation techniques and promote their circulation | 0
|  |  | (2.1.2) Oasis agriculture products are developed and promoted | 2.1.2.1 Support the producers in the certification process for their products. | 103684.879
|  |  |  | 2.1.2.2 Promotion of oasis agricultural products. | 45318.3277
|  |  |  | 2.1.2.3 Encourage research on endemic species and their uses. usages | 63587.0331
|  |  | (2.2.1) Sustainable and responsible tourism, which faces up to climate change is developed | 2.2.1.1: Support the Tourism stakeholders to make the sector more accountable | 0
|  |  |  | 2.2.1.2: Carry out a study on niche tourism products to develop. | 66854.351
|  |  | (2.2.2) Other economic activities, particularly for youths and women, are supported and developed | 2.2.2.1: Support small-scale local economic projects | 103684.879
|  |  |  | 2.2.2.2: Offer training adapted to the context and needs of the oasis | 155527.3185
| Total of Component 2 |  |  |  | 576356.6103
| 3. Improving the ecosystems’ resilience in response to climate change and variability / Oucome 5 | Output 5: Vulnerable ecosystem services and natural resource assets strengthened in response to climate change impacts, including variability | 3.1.1 The fight against desertification is organized | 3.1.1.1 Carry out a study to identify the priority sites | 0
|  |  |  | 3.1.1.2 Financial support for the Water and Forests Commission man-made and biological efforts | 51842.4395
|  |  |  | 3.1.1.3 Populations will be mobilized in the fight against desertification of housing and parcels of land. | 0
|  |  | 3.1.2 Techniques for environmental cleanup are developed | 3.1.2.1 Study the impact of the oasis economic activities | 12905.9057
|  |  |  | 3.1.2.2: Train the stakeholders concerned on environmental cleanup techniques | 93947.9564
|  |  |  | 3.1.2.3: Support community services, which aim to protect natural resources | 20736.9758
|  |  | 3.2.1 Historic constructions are restored for new uses | 3.2.1.1: Carry out a study in order to identify the mud brick buildings to restore | 0
|  |  |  | 3.2.1.2: Restore and fix up the buildings with a heritage interest | 0
|  |  | 3.2.2 Traditional techniques and materials are reused for new constructions | 3.2.2.1: Study, bearing in mind town planning, the most pertinent public building to be done in mud brick | 0
|  |  |  | 3.2.2.2: Construct said building | 0
| Total of Component 3 |  |  |  | 179433.2774
| 4. Improving stakeholder awareness through the management and exchange of knowledge / Oucome 3 | Output 3: Targeted population groups participating in adaptation and risk reduction awareness activities | 4.1.1 An assessment of resources in the intermediary Gheris basin and Maider is carried out | 4.1.1.1: Implementation of a Documentation library | 42098.1346
|  |  |  | 4.1.1.2: Strengthening of the monitoring system for water resources in the project zones. (Conv ABH) | 0
|  |  | 4.1.2 local council for water dialogue is operational | 4.1.2.1: Writing of a draft Charter on water and climate change in the Oases | 22619.8932
|  |  |  | 4.1.2.2: Organization of conferences on the themes of water and climate change | 16608.25
|  |  | 4.2.1 An awareness and communication strategy is developed | 4.2.1.1: Writing of a communication strategy | 41469.8042
|  |  |  | 4.2.1.2: « Mass » communication campaign | 0
|  |  |  | 4.2.1.3: Organization of a close out seminar | 0
|  |  | 4.2.2 A financing mechanism is implemented | 4.2.2.1 Establishing of a list of Partner-organizations for awareness actions | 0
|  |  |  | 4.2.2.2 Management of call for projects on awareness. | 28852.9304
| Total of Component 4 |  |  |  | 151649.0124
| 5. Strengthening the capacities of participants in the design and implementation of adaptation measures / Oucome 2 | Output 2: Strengthened capacity of national and subnational centres and networks to respond rapidly to extreme weather events | 5.1.1 the managers of public service are informed on the issues of climate change and introduced to adaptability measures for the main sectors | 5.1.1.2: Participation in scientific meetings and forums | 21037.1167
|  |  |  | 5.1.1.1: Conduct climate change training modules (AO 14/2015) | 0
|  |  | 5.1.2 Oasis beneficiaries are trained on innovative adaptability measures | 5.1.2.1: Conduct adaptation training modules (AO 14/2015) | 0
|  |  |  | 5.1.2.2: Organizing trips and internships | 23562.3888
|  |  | 5.2.1 The participants (operators and beneficiaries) are trained in the designing and financing of projects | 5.2.1.1: Conduct modules on the project cycle (AO 14/2015) | 0
|  |  |  | 5.2.1.2: Conduct training modules on project financing (AO 14/2015) | 0
|  |  | 5.2.2 : The participants (operators and beneficiaries) are trained on the implementation and joint management of projects. | 5.2.2.1: Conduct training modules on the participatory approach (AO 14/2015) | 0
|  |  |  | 5.2.2.2: Conduct training modules in conflict management and mediation (AO 14/2015) | 0
| Total of Component 5 |  |  |  | 44599.5054
| TOTAL |  |  |  | 3524045.5138
PLANNED EXPENDITURE SCHEDULE
List outputs planned and corresponding projected cost for the upcoming (2018) reporting period | Compenent / Outcome | Outputs | Products | Activities | AMOUNT $US | Durée en mois | Est. Completion Date
| 1. Improving adaptive capacities of the water sector / Outcome 4 | Output 4: Vulnerable development sector services and infrastructure assets strengthened in response to climate change impacts, including variability | (1.1.1) Replenishment structures for groundwater are built | 1.1.1.1 Carry out complementary studies of groundwater recharge structures on the potential sites identified | 0
|  |  |  | 1.1.1.2 Build infrastructure with the greatest potential | 0
|  |  |  | 1.1.1.3 Purchase of the follow-up equipment (piezometers). | 0
|  |  |  | 1.1.1.4 Ensure the follow-up evaluation in coordination with the HBA | 0
|  |  |  | 1.1.1.5 Establish a maintenance agreement for the groundwater recharges structures. | 0
|  |  | (1.1.2) Structures for perimeters protection are built | 1.1.2.1 : Carry out complete technical studies of protective infrastructure in the priority sites identified | 0
|  |  |  | 1.1.2.2 : Build priority infrastructure. | 106173.3161 | 12 months | 2019-12-01
|  |  |  | 1.1.2.3 : Establish a maintenance agreement for perimeter protection structures | 0
|  |  | (1.1.3) Feasibility studies on the exploitation of deep-water resources intended for the dried up palm groves of the Maïder basin are carried out. | 1.1.3.1 : Carry out an exploration/reconnaissance study through drilling for deepwater resources. | 0
|  |  |  | 1.1.3.2 : Carry out feasibility studies to identify priority sites and their financing. | 0
|  |  | (1.2.1) Khettaras are restored | 1.2.1.1 Formalize the commitment of the beneficiaries in the restoration of the khettaras | 0
|  |  |  | 1.2.1.2 Lead the works on the restoration of the khettaras | 0
|  |  | (1.2.2) Seguias are restored | 1.2.2.1 Formalize the commitment of the beneficiaries in the restoration work | 0
|  |  |  | 1.2.2.2 Carry out the restoration works on the irrigation water distribution networks: irrigation channels | 0
| Total of Component 1 |  |  |  | 106173.3161
| 2. Diversifying income sources and improving the living conditions of populations vulnerable to climate change in the targeted areas / Oucome 6 | Output 6: Targeted individual and community livelihood strategies strengthened in relation to climate change impacts, including variability | (2.1.1) Conservation technics are circulated and adopted | 2.1.1.1 Carry out a study on the experiences already undertaken in the zone or in similar zones abroad. | 0
|  |  |  | 2.1.1.2 Train new farmers on the conservation techniques and promote their circulation | 0 | 10 months | 2019-10-01
|  |  | (2.1.2) Oasis agriculture products are developed and promoted | 2.1.2.1 Support the producers in the certification process for their products. | 96219.5677 | 12 months | 2019-12-01
|  |  |  | 2.1.2.2 Promotion of oasis agricultural products. | 97328.9959 | 03 months | 2019-04-01
|  |  |  | 2.1.2.3 Encourage research on endemic species and their uses. usages | 0
|  |  | (2.2.1) Sustainable and responsible tourism, which faces up to climate change is developed | 2.2.1.1: Support the Tourism stakeholders to make the sector more accountable | 0 | 4 months | 2019-05-01
|  |  |  | 2.2.1.2: Carry out a study on niche tourism products to develop. | 0
|  |  | (2.2.2) Other economic activities, particularly for youths and women, are supported and developed | 2.2.2.1: Support small-scale local economic projects | 400654.2362 | 12 months | 2019-12-01
|  |  |  | 2.2.2.2: Offer training adapted to the context and needs of the oasis | 0 | 10 months | 2019-10-01
| Total of Component 2 |  |  |  | 594202.7998
| 3. Improving the ecosystems’ resilience in response to climate change and variability / Oucome 5 | Output 5: Vulnerable ecosystem services and natural resource assets strengthened in response to climate change impacts, including variability | 3.1.1 The fight against desertification is organized | 3.1.1.1 Carry out a study to identify the priority sites | 0
|  |  |  | 3.1.1.2 Financial support for the Water and Forests Commission man-made and biological efforts | 570266.8344 | 12 months | 2019-12-01
|  |  |  | 3.1.1.3 Populations will be mobilized in the fight against desertification of housing and parcels of land. | 0
|  |  | 3.1.2 Techniques for environmental cleanup are developed | 3.1.2.1 Study the impact of the oasis economic activities | 0
|  |  |  | 3.1.2.2: Train the stakeholders concerned on environmental cleanup techniques | 0
|  |  |  | 3.1.2.3: Support community services, which aim to protect natural resources | 111067.2424 | 12 months | 2019-12-01
|  |  | 3.2.1 Historic constructions are restored for new uses | 3.2.1.1: Carry out a study in order to identify the mud brick buildings to restore | 0
|  |  |  | 3.2.1.2: Restore and fix up the buildings with a heritage interest | 0
|  |  | 3.2.2 Traditional techniques and materials are reused for new constructions | 3.2.2.1: Study, bearing in mind town planning, the most pertinent public building to be done in mud brick | 0
|  |  |  | 3.2.2.2: Construct said building | 0
| Total of Component 3 |  |  |  | 681334.0768
| 4. Improving stakeholder awareness through the management and exchange of knowledge / Oucome 3 | Output 3: Targeted population groups participating in adaptation and risk reduction awareness activities | 4.1.1 An assessment of resources in the intermediary Gheris basin and Maider is carried out | 4.1.1.1: Implementation of a Documentation library | 45932.4014 | 4 months
|  |  |  | 4.1.1.2: Strengthening of the monitoring system for water resources in the project zones. | 0
|  |  | 4.1.2 local council for water dialogue is operational | 4.1.2.1: Writing of a draft Charter on water and climate change in the Oases | 0
|  |  |  | 4.1.2.2: Organization of conferences on the themes of water and climate change | 15552.7318 | 12 months | 2019-12-01
|  |  | 4.2.1 An awareness and communication strategy is developed | 4.2.1.1: Writing of a communication strategy | 0
|  |  |  | 4.2.1.2: « Mass » communication campaign | 10368.4879 | 06 months
|  |  |  | 4.2.1.3: Organization of a close out seminar | 0
|  |  | 4.2.2 A financing mechanism is implemented | 4.2.2.1 Establishing of a list of Partner-organizations for awareness actions | 0
|  |  |  | 4.2.2.2 Management of call for projects on awareness. | 26024.9046 | 12 months | 2019-12-01
| Total of Component 4 |  |  |  | 97878.5258
| 5. Strengthening the capacities of participants in the design and implementation of adaptation measures / Oucome 2 | Output 2: Strengthened capacity of national and subnational centres and networks to respond rapidly to extreme weather events | 5.1.1 the managers of public service are informed on the issues of climate change and introduced to adaptability measures for the main sectors | 5.1.1.2: Participation in scientific meetings and forums | 10368.4879 | 12 months | 2019-12-01
|  |  |  | 5.1.1.1: Conduct climate change training modules | 0
|  |  | 5.1.2 Oasis beneficiaries are trained on innovative adaptability measures | 5.1.2.1: Conduct adaptation training modules | 0
|  |  |  | 5.1.2.2: Organizing trips and internships | 89894.7901 | 06 months | 2019-06-01
|  |  | 5.2.1 The participants (operators and beneficiaries) are trained in the designing and financing of projects | 5.2.1.1: Conduct modules on the project cycle | 0
|  |  |  | 5.2.1.2: Conduct training modules on project financing | 0
|  |  | 5.2.2 : The participants (operators and beneficiaries) are trained on the implementation and joint management of projects. | 5.2.2.1: Conduct training modules on the participatory approach | 0
|  |  |  | 5.2.2.2: Conduct training modules in conflict management and mediation | 0
| Total of Component 5 |  |  |  | 100263.278
| TOTAL |  |  |  | 1579851.9964
ACTUAL CO-FINANCING (If the MTR or TE have not been undertaken this reporting period, DO NOT report on actual co-financing.)
How much of the total co-financing as committed in the Project Document has actually been realized?
Estimated cumulative actual co-financing as verified during Mid-term Review (MTR) or Terminal Evaluation (TE).
Add any comments on actual co-financing in particular any issues related to the realization of in-kind, grant, credits, loans, equity, non-grant instruments and other types of co-financing. (word limit=200)

## Project Indicators
PROJECT Indicators
Type of Indicator (indicators towards Objectives, Outcomes, etc…)
Type of Indicator |  |  | Indicator | Baseline | Progress since inception | Target for Project End
Project Objective: Improve the adaptability of the Oasis populations to the impacts of climate change |  |  | Number of oases inhabitants vulnerable to the adverse effects of climate variability and change | There are no concrete adaptation measures currently being implemented in the project areas | 0 | By the end of the project, at least 4000 of the most vulnerable inhabitants in the project area will benefit from the proposed activities to cope with their vulnerability to climate change
Outcome 4: Increased adaptive capacity within relevant development sector services and infrastructure assets | Output 4 : Vulnerable developement sector services and infrastructure assets strenthned in response to climate impacts, inculding variability | Ccomponent 1. Improving adaptive capacities of the water sector | Development of water sectors' services responsive to evolving needs from changing and variable climate. | There is evidence on the shortages by basin being updated | 0 | At least 10% of households secure their access to water for drinking and irrigation.
|  | (1.1) Improved joint regulation of ground and surface water through new sustainable hydraulic and protective structure management | Efficiency of mobilization | Available studies indicate the rate water mobilization by basin | 0 | Approximately 2 million m3
|  | (1.1.1) Replenishment structures for groundwater are built | Number of recharge structures | In the intervention sites, structures for exclusively recharging groundwater do not exist. | 7 achieved | 4 structures
|  | (1.1.2) Structures for perimeters protection are built | Number of irrigated perimeters | Flooding reduces the rate of floodwater mobilization | 6 perimeters | 6 perimeters
|  | (1.1.3) Feasibility studies on the exploitation of deep-water resources intended for the dried up palm groves of the Maïder basin are carried out. | Feasibility studies by site | No deep borehole is used in the project zone to reduce the shortage of drinkable water | 4 Feasability studies (2 Sites) | 2 sites
|  | (1.2) Vulnerable infrastructure allowing the improvement of water distribution efficiency are restored | Agricultural irrigation efficiency (%) | Efficiency ratios of the traditional networks are below 50% according to APP (Agency for the Partnership for Progress) |  | 70% efficiency
|  | (1.2.1) Khettaras are restored | Area irrigated (hectares) | Khettaras to be restored are identified. According to the 2005 PDRT, the restoration will allow the khettaras to pass from 2 to 5 L/s. | 200 ha (23 Khettaras restored : 4414 linear meter) | 200 Ha
|  | (1.2.2) Seguias are restored | Area irrigated (hectares) | SMH networks to be renovated are identified | 200 ha (18 SMH networks renovated : 6096 linear meter) | 200 Ha
Outcome 6: Diversified and strengthened livelihoods and sources of income for vulnerable people in targeted areas | Output 6: targeted individual and community livelihood strategies strenthened in relation to climate change impacts, includin variability | Component 2. Diversifying income sources and improving the living conditions of populations vulnerable to climate change in the targeted areas | Percentage of households with diversified income sources and sustained climate-resilient alternative livelihoods. | The poverty rate in the zone remains especially high | 0 | At least 20% of families have diversified and improved their livelihoods through more resilient activities.
|  | (2.1) Improved livelihoods of families due to the development of more resilient small scale agriculture | VA/ha | 37000dh/ha (according to APP) | 0 | 20% increase for an objective of MAD 45000 per ha
|  | (2.1.1) Conservation technics are circulated and adopted | Number of trained farmers | The project’s target areas have not received significant training | 616 farmers (women : 19%) (32 good practices and agro-ecological and conservation studies presented in the form of technical sheets) | 800 farmers. At least 400 women.
|  | (2.1.2) Oasis agriculture products are developed and promoted | Number of products that are certified and are represented in fairs/trade shows | Experiments near the project zones have successfully developed attractive local agricultural sectors (argan, saffron, cheese, olive oil, and cactus). | 2 achived : (27 professional organizations have benefited from: - 35,325 cumin packages - 60,625 packages of henna - 600 Roll up - 250,000 Flyers - 50,000 Business cards) | 4
|  | (2.2) Developed non-agricultural economic activities help increase the resilience of the Oasis population | Number and type of economic units (existing or new) that develop in a manner adapted to climate change. | Experiments near the project zones have successfully developed high value non-agricultural sectors | 21 units | At least 20 economic units
|  | (2.2.1) Sustainable and responsible tourism, which faces up to climate change is developed | Number of tourism units that develop in a manner adapted to climate change. | The potential of responsible tourism is under-valued in the project’s implementation zones (compared to the Dadès and Draa valleys). | * 5 tourism units * Identification of: (- 10 circuits for niche tourism inherent in culture - 03 circuits for niche tourism for ecotourism - 14 circuits for religious niche tourism and Sufism - 05 circuits for tourism for archeology, memory and history. - 03 circuits for sports) | At least 5 tourism units
|  | (2.2.2) Other economic activities, particularly for youths and women, are supported and developed | Projects financed Trainings exist | The existing VSE support programs do not particularly support innovative adaptation projects. | 45 projects (women projets - about 25%) • PACCZO Contribution : 684,211 USD • Main areas of funded projects: Agriculture, Environment, Handicrafts and Tourism. | 20 projects, at least 50% managed by women 2 trainings
Outcome 5: Increased ecosystem resilience in response to climate change and variability-induced stress | Output 5 : Vulnerable developement sector services and infrastructure assets strenthned in response to climate impacts, inculding variability | Component 3. Improving the ecosystems’ resilience in response to climate change and variability | Number of oases that have reduced the threats to their ecosystem and preserved their heritage | The MEA/FAO/UNESCO/PACO studies have sounded the alarm |  | At least 4 oases
|  | (3.1) Threats reducing the value of Oasis ecosystems are taken into account by municipalities | Number of oases that have reduced the threats to their ecosystem. | Consultation workshops have stressed the importance of the degradation of ecosystems | 4 Oases | At least 4 oases participate in a dynamic for protecting the ecosystems.
|  | 3.1.1 The fight against desertification is organized | Protected hectares | The fight against desertification is already well underway by the Water and Forests Commission, which has however reached a maximum given their current means. | 120 ha | 40 ha
|  | 3.1.2 Techniques for environmental cleanup are developed | Number of stakeholders trained | Techniques for cleanup are nearly inexistent in the oasis zones. | 396 pepole (12% : women) ; Themes : - Techniques for limiting pollution and treating water. - Phyto-purification techniques. - Recycling techniques. - Trip : Guided tours in wastewater treatment stations (Ouarzazate, Agadir, Tinjdad and Fès). | 400 trained individuals (at least 50% women) with a treatment device installed.
|  | (3.2) Preserved and Promoted Heritage | Number of solicitations for restoring post-project | Few landowners are currently interested in restoration or construction because they fear that their home will become a museum. |  | There are solicitations.
|  | 3.2.1 Historic constructions are restored for new uses | Restored and used buildings | Restored buildings have a low-valued museum function (empty kasbah) | 2 restored buildings - Environmental upgrading of the Nkob Central School (province of Zagora) - Contribution to projects to restore buildings and prevent fire | 2 restored buildings used for a new purpose
|  | 3.2.2 Traditional techniques and materials are reused for new constructions | New buildings using traditional materials | Currently, only high-end tourism structures use these techniques for new constructions. | 2 new constructions - Interior design of the Abderrahmane Eddakhil school in Ferkla EL oulia; - Project to rehabilitate an environmental and ecological space at the Saghro 01 school in Alnif. | 2 new constructions
Outcome 3: Strengthened awareness and owernship of adaptation and climate risk reduction processes | Output 3 : Targeted population groups participating in adaptation and risk reduction awarness activities | Component 4. Improving stakeholder awareness though the management and exchange of knowledge | Part of the targeted municipal populations are educated on climate change issues | The population has heard of climate change but it remains an abstract concept that has yet to be connected to changes in the area. | 0 | 60% of households in the project zones
|  | (4.1) Organized public debate on water and climate change | The importance of communicating on the issue of climate change | Informal debates exist but there is a lack of data and areas for expression needed to reinforce the message. | 0 | Media coverage
|  | 4.1.1 An assessment of resources in the intermediary Gheris basin and Maider is carried out | Access to documentation | Several studies and documentation are unavailable | Establishment of a database on water ressources : 2915 documents | The existence of a documentation library Study on accessible water resources
|  | 4.1.2 local council for water dialogue is operational | Number of thematic conferences organized by the Local Council on water | Debates on climate change issues remain national and centralized | 6 regional tehmatics carried out - Organization of the international conference "The contribution of new technologies (GIS and Remote Sensing) in monitoring the dynamics of the oasis ecosystem in the face of climate changes - Thematic conference on the development of cumin in Bouarfa - Thematic conference on Tourism in Zagora - Thematic conference on local products in Zagora - Organization of the "International date fair" theme: "The date palm, lever of employment and pillar of the oasis economy" - Organization of the rose festival; theme "the fragrant rose, a strong lever for employment and the dynamics of the local economy" | 6 regional thematic conferences
|  | (4.2) Supported and developed local initiatives for communication | Population of targeted groups are educated on the overall issues relating to climate change | Communication/awareness campaigns are not targeted | 0 | Targeted content of communication/awareness campaigns
|  | 4.2.1 An awareness and communication strategy is developed | Number of mass communication campaigns | The project intervention zones have not had any mass communication activities | More than 20 press releases | 4 mass campaigns
|  | 4.2.2 A financing mechanism is implemented | Number of funded initiatives for raising the awareness of educated children, emigrants, and tourists | The project intervention zones have not had any targeted awareness activities | 50 awareness projects have been funded Awareness actions : - Climate changes - Preservation and economy of water resources - Environmental aspects. | 50 funded awareness projects
Outcome 2: Strengthened institutional capacity to reduce risks associated with climate-induced socioeconomic and environmental losses | Output 2 : Strengthened of national and sub-national centers and networks to respond rapidly to extreme weater events | Component 5 Strengthening the capacities of participants in the design and implementation of adaptation measures | No. of Officials and beneficiaries trained with reinforced capacities in adaptation project management. | The project intervention zones have not had any capacity building activities | 984 people (640 framrs + 344 public services) | 240 officials 400 oasis beneficiaries, at least 50% women
|  | (5.1) Consolidated and developed adaptive capacities for climate change | Number of officials and beneficiaries whose adaptability to climate change has been strengthened. | There are major knowledge disparities between stakeholders | 1744 participants (women 15%) | 240 public service officials 400 oasis beneficiaries, at least 50% women
|  | 5.1.1 the managers of public service are informed on the issues of climate change and introduced to adaptability measures for the main sectors | Number of training workshops and participants | Local and public officials have sectorial knowledge and are not well versed in the multi-sectoral effects of climate change. | 87 workshops (1744 participant : 15% are women). | 12 training workshops (20 people/workshop) 50 participants for scientific conferences and beneficiary awareness forums
|  | 5.1.2 Oasis beneficiaries are trained on innovative adaptability measures | Number of training workshops and travel/internships | The oasis beneficiaries are up to date on adaptation techniques and experiments conducted in neighboring countries. | - Organization of 10 trips (11% : women) - Organization of 8 workshops (9% : women) - 53 participants | 20 workshops, (20 people/workshop) 15 trips (at least 50% women)
|  | (5.2) Strengthened coordinated management capacities for climate change projects | Number of officials and beneficiaries whose ability to collectively manage climate change adaptation projects has been strengthened | The stakeholders are not familiar with the dialogue process in managing development projects | 790 participants (women 15%) | 240 public service officials 400 oasis beneficiaries (at least 50% women)
|  | 5.2.1 The participants (operators and beneficiaries) are trained in the designing and financing of projects | Number of training workshops being designed and funding of projects | The stakeholders are not aware of financing and monitoring-evaluation mechanisms for adaptation projects | 13 workshops (772 people - 15% women) | 12 workshops on the project cycle (20 people/workshop) 12 workshops on project financing (40 people/workshop) (at least 50% women)
|  | 5.2.2 : The participants (operators and beneficiaries) are trained on the implementation and joint management of projects. | Number of training workshops on the implementation and the coordinated management of projects and the number of participants | The stakeholders are not familiar with coordinated management mechanisms | 13 workshops (790 people - 14% women) | 12 workshops on the participatory approach (20 people/workshop) 12 workshops in conflict management and mediation (12 people/workshop) (at least 50% women)

## Risk Assesment
RISK ASSESMENT
IDENTIFIED RISKS
List all Risks identified in project preparation phase and what steps are being taken to mitigate them
Identified Risk | Current Status | Steps Taken to Mitigate Risk
Institutionnal risk / The project is likely to suffer the consequences of inadequate staffing and a lack of qualified personnel, which affects some of the project stakeholders, particularly certain rural local authorities. | Level: Moderate ; State : No longer relevant | State : No longer relevant Thanks to the great experience of ANDZOA in the management of similar projects, this risk is well controlled. At present, the project is carried out in a good institutional conditions thanks to the externnal "Technical Assitance" and the EE Team.
Institutionnal risk / The participatory approach promoted by the project runs the risk of being reduced or even diverted by local interest groups. | Level: Moderate ; State : Low | State : No longer relevant The project is managed in a participatory approach which avoids any kind of intercations of interests or resistance to the actions of the project
Technical risk / In light of past experiences showing the difficulties faced by similar projects covering geographically remote and disadvantaged areas, risks relating to the sustainability of actions still remain | Level: Moderate to substantial State : Medium | State : Low * The terms of reference of the projects clearly specify the difficulties associated with the work and the services requested. * The Technical Assitance and the EE teams and staff conduct field visits to monitor achievements.
Technical risk / The groundwater refill structures could affect the access to resources in certain downstream sites | Level: Moderate ; State : Low | State : Low * Coordination and consultation are done regularly with the ABH (Hydraulic Basin Agency) in order to avoid affecting the access to resources in downstream sites. * The actions of the project are programmed according to the recommendations of the ESMP (Environmental and Social Management Plan).
Environomental risk / Adverse climate conditions could have a negative effect on the success of the project. | Level: Moderate to substantial State : Medium | State : Low The project area has experienced significant adaptation to climate change in the past. The project aims to improve resilience to climate change
Financial risk / The project activities risk being delayed by the circuits for transferring funds. | Level: Moderate State : Medium | State : Medium Both NIE and EE intervened to the Paymaster to accelerate payments
Critical Risks Affecting Progress (Not identified at project design)
Identify Risks with a 50% or > likelihood of affecting progress of project
Identified Risk | Current Status | Steps Taken to Mitigate Risk
Risk Measures: Were there any risk mitigation measures employed during the current reporting period? If so, were risks reduced? If not, why were these risks not reduced?
Add any comments relevant to risk mitigation (word limit = 500)

## Rating
RATING ON IMPLEMENTATION PROGRESS
For rating definitions please see bottom of page.
| Progress on Key Milestones |  | Expected Progress |  | Progress to Date | Rating
Project Manager/Coordinator: | Project Objective: Help reduce the vulnerability of people and oasis agro ecosystems in Morocco to climate change by increasing the adaptive capacity of local actors, increasing the resilience of the target ecosystem and by disseminating knowledge management.
| Inception Phase of the Project completed |  | Inception Phase activities commenced on 14, December 2015. Within this phase, recruitment of the Technical Assistance for both NIE & EE, the inception workshop were held. The various activities of the project components have been started |  | Inception Phase commenced on 14 December 2015. - Technical assistance was recruited for both NIE & EE. - Regional Coordinating Committee (CRC) and Steering Committee (COPIL) were regularly held. - Agreements were concretized with the project partners. - Works were completed in accordance with the AWPB | S
C5 | Outcome 2: Strengthened institutional capacity to reduce risks associated with climate-induced socioeconomic and environmental losses
| Strengthening the capacities of participants in the design and implementation of adaptation measures |  | About 2600 of Officials and Oasis beneficiaries (whose ability to collectively manage climate change adaptation project) has been strengthened. |  | More than 1700 people (oasis beneficiaries) plus officials (from different services) have benefited from trainings related to adaptation to climate change. * More than 15 Workshops (Governance of water and sanitation services in the oasis environment face of CC / Integrated management of water resources face to CC). * 21% : Cooperatives & Agricultural water management associations * Organization of 10 trips * 12% : Women * 109% : Attendance rate - Managers of public services and beneficiaries have been trained on : * Governance of water and sanitation services in the oasis in the face of CC * Integrated management of water resources against CC * Management of project cycles * Project financing * Participatory approach applied to adaptation measures * Conflict Management and Mediation | S
C4 | Outcome 3: Strengthened awareness and owernship of adaptation and climate risk reduction processes
| Improving stakeholder awareness though the management and exchange of knowledge |  | The population has awarned of climate change. |  | In accordance with the specific agreement signed between the NIE and the EE on the execution of the PACCZO project, the ADZOA has performed : - Establishment of a database on water ressources : 2915 documents - 6 regional tehmatics carried out * Organization of the international conference "The contribution of new technologies (GIS and Remote Sensing) in monitoring the dynamics of the oasis ecosystem in the face of climate changes * Thematic conference on the development of cumin in Bouarfa * Thematic conference on Tourism in Zagora * Thematic conference on local products in Zagora * Organization of the "International date fair" theme: "The date palm, lever of employment and pillar of the oasis economy" * Organization of the rose festival; theme "the fragrant rose, a strong lever for employment and the dynamics of the local economy" - More than 20 press releases - 50 awareness projects have been funded | S
C1 | Outcome 4: Increased adaptive capacity within relevant development sector services and infrastructure asset
| Improving adaptive capacities of the water sector |  | Development of water sectors' services responsive to evolving needs from changing and variable climate. |  | Both 1) works on "regulation of ground and surface water" and 2) "vulnirabel infrastrastructure allowing the improvement of water efficiency - Khettara & Saguia" has been started : * Restoration of khettaras : 23 Khettaras restored (4414 linear meter) on an objective of 18 khettaras * Works on irrigation water distribution networks: 18 SMH networks renovated : 6096 linear meter * Build priority infrastructure : 4 structures * Groundwater recharge structures : 2 structures has been finished for 10000 people & 1400 hoslods * 4 Feasability studies * Structures for perimeters protection are built : 14 protective wall (2398 linear meter) | S
C3 | Outcome 5: Increased ecosystem resilience in response to climate change and variability-induced stress
| Improving the ecosystems’ resilience in response to climate change and variability |  | Number of oases that have reduced the threats to their ecosystem and preserved their heritage |  | * The fight against desertification : 120 ha (objective 40 ha) * Techniques for cleanup in the oasis zones - Techniques for limiting pollution and treating water. - Phyto-purification techniques. - Recycling techniques. - Trip : Guided tours in wastewater treatment stations (Ouarzazate, Agadir, Tinjdad and Fès). * 2 restored buildings * 2 new constructions | S
C2 | Outcome 6: Diversified and strengthened livelihoods and sources of income for vulnerable people in targeted areas
| Diversifying income sources and improving the living conditions of populations vulnerable to climate change in the targeted areas |  | Percentage of households with diversified income sources and sustained climate-resilient alternative livelihoods. |  | * Economic activities, particularly for youths and women, are supported and developed - 45 projects (women projets - about 25%) - PACCZO Contribution : 6,598,950 - Main areas of funded projects: Agriculture, Environment, Handicrafts and Tourism. * Conservation technics are circulated and adopted : 616 farmers * Oasis agriculture products are developed and promoted : 27 professional organizations have benefited. | S
[5 empty] | Overall Rating | S
Please Provide the Name and Contact information of person(s) reponsible for completeling the Rating section
| Name: | ALI OUBARHOU
| Email: | oubrhou@gmail.com
Please justify your rating. Outline the positive and negative progress made by the project since it started. Provide specific recommendations for next steps. . (word limit=500)
About 2600 of Officials and Oasis beneficiaries (whose ability to collectively manage climate change adaptation project) has been strengthened and the population has awarned of climate change. Good progress of works : 1) "to increase adaptive capacity within relevant development and natural resource sectors", 2) "to increase ecosystem resilience in response to climate change and variability-induced stress" and "to trength awareness and ownership of adaptation". 45 projects were selected (of populations vulnerable to climate change) and funded in order to diversify income resources and living conditions of this population.
| Progress on Key Milestones |  | Expected Progress |  | Progress to Date | Rating
Implementing Agency | Project Objective: Improve the adaptability of the Oasis populations to the impacts of climate change
| Inception Phase of the Project completed |  | Inception Phase activities commenced in December 2015. Within this phase, recruitment of the Technical Assistance (for NIE & EIE), the inception workshop and partnership agreements were held. |  | Inception Phase commenced on 14 December 2015. - Technical assistance was recruited for both NIE & EE. - Regional Coordinating Committee (CRC) were regularly held. - 7 Agreements were concretized with the project partners. - Works were completed in accordance with the AWPB | S
Outcome 2: Strengthened institutional capacity to reduce risks associated with climate-induced socioeconomic and environmental losses
| Strengthening the capacities of participants in the design and implementation of adaptation measures |  | About 2600 of Officials and beneficiaries trained with reinforced capacities in adaptation project management. |  | - More than 1700 people (oasis beneficiaries) plus officials (from different services) have benefited from trainings related to climate change adaptation. - More than 15 Workshops (Governance of water and sanitation services in the oasis environment face of CC / Integrated management of water resources face to CC). - 21% : Cooperatives & Agricultural water management associations - Organization of 10 trips - Women participation : 12% - 109% : Attendance rate - Managers of public services and beneficiaries have been trained | S
Outcome 3: Strengthened awareness and owernship of adaptation and climate risk reduction processes
| Improving stakeholder awareness though the management and exchange of knowledge |  | The population has awarned of climate change. |  | - Establishment of a database on water ressources : 2915 documents - 6 regional tehmatics carried out - More than 20 press releases - 50 awareness projects have been funded | S
Outcome 4: Increased adaptive capacity within relevant development sector services and infrastructure asset
| Improving adaptive capacities of the water sector |  | Development of water sectors' services responsive to evolving needs from changing and variable climate. |  | - 23 Khettaras restored (4414 linear meter) on an objective of 18 khettaras - 18 SMH networks renovated : 6096 linear meter - Build priority infrastructure : 4 structures - Groundwater recharge structures : 2 structures has been finished (for 10000 people & 1400 hoslods) - 4 Feasability studies - Structures for perimeters protection are built : 14 protective wall (2398 linear meter) | S
Outcome 5: Increased ecosystem resilience in response to climate change and variability-induced stress
| Improving the ecosystems’ resilience in response to climate change and variability |  | Number of oases that have reduced the threats to their ecosystem and preserved their heritage |  | - The fight against desertification : 120 ha (objective 40 ha) - Training in techniques for cleanup in the oasis zones - 2 restored buildings - 2 new constructions | S
Outcome 6: Diversified and strengthened livelihoods and sources of income for vulnerable people in targeted areas
| Diversifying income sources and improving the living conditions of populations vulnerable to climate change in the targeted areas |  | Percentage of households with diversified income sources and sustained climate-resilient alternative livelihoods. |  | 45 production units (project holder) receives funding (a total of 684,211 USD). | S
[5 empty] | Overall Rating | S
Please Provide the Name and Contact information of person(s) reponsible for completeling the Rating section
| Name: | MERYEM ANDALOUSSI
| Email: | m.andaloussi@ada.gov.ma / meryem.andaloussi@gmail.com
Please justify your rating. Outline the positive and negative progress made by the project since it started. Provide specific recommendations for next steps. . (word limit=500)
Project execution was carried out in accordance with 1) Annual Work Plan and 2) Budget and the Project Procurement Plan pre-established. Despite the delay in the start of the project, all the components of the project were started. The project partners are all aware of the problems of climate change and are actively involved in the success of the project. 7 agreements were signed with partners (ABH, ORMVAO, ORMVATF and IAV). The rate of participation in trainings was significant. Stakeholders are very aware of the project's objectives. The project is well publicized and the works have achieved their objectives
| Progress on Key Milestones |  | Expected Progress |  | Progress to Date | Rating
Other
Overall Rating
Please Provide the Name and Contact information of person(s) reponsible for completeling the Rating section
Name:
Email:
Please justify your rating and address the following points: 1. Indicate trends, both positive and negative, in achievement of outcomes as per the project indicators. 2. Detail critical risks that have affected progress. 3. Outline response to MTR undertaken this reporting period. 4. Outline action plan to address projects with a rating of HU, U or MU. Please keep your input to 1200 words
Rating Definitions
|  |  | Highly Satisfactory (HS) | Project actions/activities planned for current reporting period are progressing on track or exceeding expectations to acheive all major outcomes/outputs for given reporting period, without major shortcomings. The project can be presented as “good practice”.
|  |  | Satisfactory (S) | Project actions/activities planned for current reporting period are progressing on track to achieve most of its major outcomes/outputs with only minor shortcomings.
|  |  | Marginally Satisfactory (MS) | Project actions/activities planned for current reporting period are progressing on track to achieve most major relevant outcomes/outputs, but with either significant shortcomings or modest overall relevance.
|  |  | Marginally Unsatisfactory (MU) | Project actions/activities planned for current reporting period are not progressing on track to achieve major outcomes/outputs with major shortcomings or is expected to achieve only some of its major outcomes/outputs.
|  |  | Unsatisfactory (U) | Project actions/activities planned for current reporting period are not progressing on track to achieve most of its major outcomes/outputs.
|  |  | Highly Unsatisfactory (U) | Project actions/activities planned for current reporting period are not on track and shows that it is failing to achieve, and is not expected to achieve, any of its outcomes/outputs.

## Lessons Learned
QUALITATIVE MEASURES and LESSONS LEARNED
Please complete the following section every reporting period
Implementation and Adaptive Management | Response
What implementation issues/lessons, either positive or negative, affected progress? | * The PACCZO Project has created a synergy and complementarity between institutional organizations responsible for the territorial development of fragile and vulnerable ecosystems. * The commitment of professional organizations (beneficiaries) especially in the maintenance of irrigation structures which is inevitably a guarantee of sustainability of achievements.
Were there any delays in implementation? If so, include any causes of delays. What measures have been taken to reduce delays? | * Delay in large-value payment (agreement with partners) Measures : Intervention direcet at paymasters * Delays in Activity A1.1.1.1 : Carry out complementary studies of groundwater recharge structures on the potential sites identified. Reason : The scarcity of the providers making prospection of the deep waters (more than 800 meters). Tenders were tree times unsuccessful. Mesures : Redeployment of funds in groundwater recharge activities to achieve the same result.
Describe any changes undertaken to improve results on the ground or any changes made to project outputs (i.e. changes to project design) | No changes were made to project outputs
How have gender considerations been taken into consideration during the reporting period? What have been the lessons learned as a consequence of inclusion of such considerations on project performance or impacts? | * Women showed great interest toward project's objectives. * Women were present during all the training sessions. * More than 50% of the projects proposed for funding were reserved for vulnerable social categories (women and young) which allowed creation of jobs in rural areas and a significant complementary income. * Projects proposed for funding (to improve sources of income) all include women.
Please complete the following section at mid-term and project completion
Lessons for Adaptation | Response
Climate Resilience Measures
What have been the lessons learned, both positive and negative, in implementing climate adaptation measures that would be relevant to the design and implementation of future projects/programmes for enhanced resilience to climate change? | * The participatory approach framework integrating the direct beneficiaries and all administrative bodies related to water, agriculture and the environment * Support community services (aims to protect natural resources)
What is the potential for the climate resilience measures undertaken by the project/programme to be replicated and scaled up both within and outside the project area? | * Reinforce actions of diversifying income sources and improving the living conditions of populations vulnerable to CC : 1) Triggering income generation microprojects (or projets); 2) Helping women's economic independence *A great synergy between capacity building and promotion of agricultural products
Concrete Adaptation Interventions
What have been the lessons learned, both positive and negative, in implementing concrete adaptation interventions that would be relevant to the design and implementation of future projects/programmes implementing concrete adaptation interventions? | * Integration of institutional partners (administration related to water, agriculture, environment) in all project implementing processes * A great synergy was shown by the integration of the ABH and the ORMVA's concerning the work and infrastructure achievements
What is the potential for the concrete adaptation interventions undertaken by the project/programme to be replicated and scaled up both within and outside the project area? | * Immediate positive effects of the actions of underground dams on water resources and then on adaptation to Climate Change * Actions related to water (Khettaras, irrigation channels, groundwater recharge structures) have accelerated positive effects on adaptation to climate change
Community/National Impact
What would you consider to be the most successful aspects for the target communities? | * Improvement of income and living conditions of the target population * Limit the exodus and revitalization of palm groves * Promotion of Oasis products (most vulnerable to CC)
What measures are/have been put in place to ensure sustainability of the project/program results? | * Provision of technical assistance to ensure the quality of the work * Participation of the target population during implementing * Integrating the target population to ensure the maintenance of structures after completion of works
What measures are being/could have been put in place to improve project/program results?
Knowledge Management
How has existing information/data/knowledge been used to inform project development and implementation? What kinds of information/data/knowledge were used? | * Des données détaillées sur la population, l'activité économique, les statistiques agricoles (rapports, statistiques, documents, bases de données, expériences) ont été très utiles pour la préparation de l'AWP et le suivi
If learning objectives have been established, have they been met? Please describe. | *Very good results and effects of workshops, training, visits and trips: 1) good understanding of the issues and 2) adoption of actions proposed by the target population
Describe any difficulties there have been in accessing or retrieving existing information (data or knowledge) that is relevant to the project. Please provide suggestions for improving access to the relevant data. | * No difficulty was encountered
Has the identification of learning objectives contributed to the outcomes of the project? In what ways have they contributed? | * Direct commitment of partners and adoption of achievements

## Results Tracker-exemple (hidden)
Results Tracker for Adaptation Fund (AF) Projects
Goal: Assist developing-country Parties to the Kyoto Protocol that are particularly vulnerable to the adverse effects of climate change in meeting the costs of concrete adaptation projects and programmes in order to implement climate-resilient measures. Impact: Increased resiliency at the community, national, and regional levels to climate variability and change.
Important: Please read the following guidance document (also posted on the Adaptation Fund website) before entering your data
Link: http://www.adaptation-fund.org/sites/default/files/Results%20Framework%20and%20Baseline%20Guidance%20final.pdf
Adaptation Fund Strategic Results Framework
Project ID
Implementing Entity
Type of implementing entity
Country | Morocco
Region
Sector
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Impact: Increased resiliency at the community, national, and regional levels to climate variability and change | Core Indicator: No. of beneficiaries |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project
|  | Total |  |  |  | Total |  |  |  | Total |  |  |  | Total
|  | % of female beneficiaries |  |  |  | % of female beneficiaries |  |  |  | % of female beneficiaries |  |  |  | % of female beneficiaries
|  | % of Youth beneficiaries |  |  |  | % of Youth beneficiaries |  |  |  | % of Youth beneficiaries |  |  |  | % of Youth beneficiaries
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 1: Reduced exposure to climate-related hazards and threats | Indicator 1: Relevant threat and hazard information generated and disseminated to stakeholders on a timely basis | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness
|  | Total |  |  |  | Total |  |  |  | Total |  |  |  | Total
|  | % of female targeted |  |  |  | % of female targeted |  |  |  | % of female targeted |  |  |  | % of female targeted
Output 1.1 Risk and vulnerability assessments conducted and updated | Indicator 1.1: No. of projects/programmes that conduct and update risk and vulnerability assessments | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
Output 1.2 Targeted population groups covered by adequate risk reduction systems | Core Indicator 1.2: No. of Early Warning Systems | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 2: Strengthened institutional capacity to reduce risks associated with climate-induced socioeconomic and environmental losses | Indicator 2: Capacity of staff to respond to, and mitigate impacts of, climate-related events from targeted institutions increased | Number of staff targeted |  | Sector | Capacity level | Number of staff targeted |  | Sector | Capacity level | Number of staff targeted |  | Sector | Capacity level | Number of staff targeted |  | Sector | Capacity level
|  | Total |  |  |  | Total |  |  |  | Total |  |  |  | Total
|  | % of female targeted |  |  |  | % of female targeted |  |  |  | % of female targeted |  |  |  | % of female targeted
Output 2.1 Strengthened capacity of national and sub-national centres and networks to respond rapidly to extreme weather events | Indicator 2.1.1: No. of staff trained to respond to, and mitigate impacts of, climate-related events | Total staff trained | % of female staff trained | Type |  | Total staff trained | % of female staff trained | Type |  | Total staff trained | % of female staff trained | Type |  | Total staff trained | % of female staff trained | Type
| Indicator 2.1.2: No. of targeted institutions with increased capacity to minimize exposure to climate variability risks | Type | Scale | Sector | Capacity level | Type | Scale | Sector | Capacity level | Type | Scale | Sector | Capacity level | Type | Scale | Sector | Capacity level
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 3: Strengthened awareness and owernship of adaptation and climate risk reduction processes | Indicator 3.1: Increase in application of appropriate adaptation responses | Percentage of targeted population applying adaptation measures |  | Sector |  | Percentage of targeted population applying adaptation measures |  | Sector |  | Percentage of targeted population applying adaptation measures |  | Sector |  | Percentage of targeted population applying adaptation measures |  | Sector
Output 3: Targeted population groups participating in adaptation and risk reduction awareness activities | Indicator 3.1.1: Percentage in targeted population awareness of predicted adverse impacts of climate change, and of appropriate responses | No. of targeted beneficiaries | % of female participants targeted | Level of awareness |  | No. of targeted beneficiaries | % of female participants targeted | Level of awareness |  | No. of targeted beneficiaries | % of female participants targeted | Level of awareness |  | No. of targeted beneficiaries | % of female participants targeted | Level of awareness
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Target performance at completion |  |  |  | Target performance at completion
Outcome 4: Increased adaptive capacity within relevant development sector services and infrastructure assets | Indicator 4.1: Increased responsiveness of development sector services to evolving needs from changing and variable climate | Project/programme sector | Geographical scale | Response level |  | Project/programme sector | Geographical scale | Response level |  | Project/programme sector | Geographical scale | Response level |  | Project/programme sector | Geographical scale | Response level
| Core Indicator 4.2: Assets produced, developed, improved or strengthened | Sector | Targeted asset | Changes in asset (quantitative or qualitative) |  | Sector | Targeted asset | Changes in asset (quantitative or qualitative) |  | Sector | Targeted asset | Changes in asset (quantitative or qualitative) |  | Sector | Targeted asset | Changes in asset (quantitative or qualitative)
Output 4: Vulnerable development sector services and infrastructure assets strengthened in response to climate change impacts, including variability | Indicator 4.1.1: No. and type of development sector services to respond to new conditions resulting from climate variability and change | Number of services | Type |  | Sector | Number of services | Type |  | Sector | Number of services | Type |  | Sector | Number of services | Type |  | Sector
|  | Baseline information |  |  |  | Baseline information |  |  |  | Baseline information |  |  |  | Baseline information
Outcome 5: Increased ecosystem resilience in response to climate change and variability-induced stress | Indicator 5: Ecosystem services and natural resource assets maintained or improved under climate change and variability-induced stress | Natural resource improvement level |  | Sector | Type | Natural resource improvement level |  | Sector | Type | Natural resource improvement level |  | Sector | Type | Natural resource improvement level |  | Sector | Type
Output 5: Vulnerable ecosystem services and natural resource assets strengthned in response to climate change impacts, including variability | Core Indicator 5.1: Natural Assets protected or rehabilitated | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Baseline information |  |  |  | Targeted performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 6: Diversified and strengthened livelihoods and sources of income for vulnerable people in targeted areas | Indicator 6.1: Increase in households and communities having more secure access to livelihood assets | No. of targeted households | % of female headed households | Improvement level |  | No. of targeted households | % of female headed households | Improvement level |  | No. of targeted households | % of female headed households | Improvement level |  | No. of targeted households | % of female headed households | Improvement level
| Indicator 6.2: Increase in targeted population's sustained climate-resilient alternative livelihoods | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
|  | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
|  | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
|  | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
Output 6 Targeted individual and community livelihood strategies strengthened in relation to climate change impacts, including variability | Indicator 6.1.1: No. and type of adaptation assets created or strengthened in support of individual or community livelihood strategies | Number of Assets | Type of Assets | Sector | Adaptation strategy | Number of Assets | Type of Assets | Sector | Adaptation strategy | Number of Assets | Type of Assets | Sector | Adaptation strategy | Number of Assets | Type of Assets | Sector | Adaptation strategy
| Core Indicator 6.1.2: Increased income, or avoided decrease in income | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 7: Improved policies and regulations that promote and enforce resilience measures | Indicator 7: Climate change priorities are integrated into national development strategy | Integration level |  |  |  | Integration level |  |  |  | Integration level |  |  |  | Integration level
Output 7:Improved integration of climate-resilience strategies into country development plans | Indicator 7.1: No. of policies introduced or adjusted to address climate change risks | No. of Policies introduced or adjusted | Sector | Scale | Type | No. of Policies introduced or adjusted | Sector | Scale | Type | No. of Policies introduced or adjusted | Sector | Scale | Type | No. of Policies introduced or adjusted | Sector | Scale | Type
| Indicator 7.2: No. of targeted development strategies with incorporated climate change priorities enforced | No. of Development strategies | Regulation |  | Effectiveness | No. of Development strategies | Regulation |  | Effectiveness | No. of Development strategies | Regulation |  | Effectiveness | No. of Development strategies | Regulation |  | Effectiveness
Glacier lake outburst flood
|  | Inland flooding | fr | biological assets |  | Company policy | 5: Fully enforced (All elements implemented)
|  | Salinization | Decrease | land |  | Communication & Information policy | 4: Enforced (Most elements implemented)
|  | Drought | Same | water areas |  | Defense policy | 3: Partially enforced (Some elements implemented)
|  | Wind |  | subsoil assets | increased adpative capacity | Domestic policy | 2: Partially not enforced (Most elements not implemented) |  | Agribusiness
|  | Coastal flooding |  | air | achieved | Economic policy | 1: Not enforced (No elements implemented) |  | Agricultural-related | Financial capital
|  | Storm surge | Please choose |  | enhanced level of protection | Education policy |  |  | Agriculture | Human capital
|  | Hurricane | Selected | [5 empty] | Aquaculture | Physical capital
|  |  | Not relevant |  |  | 5: All (Fully integrated) |  |  | Construction/repairing business | Social capital
[6 empty] | 4: Most |  |  | Cultivation | Natural capital
[6 empty] | 3: Some |  |  | Fishing | Personal capital
Select | 5: All | Select |  |  | Community | 2: Most not integrated |  | Other | Forestry | Adaptation strategies
1 | 4: Almost all | Private | Type | Yes | Multi-community | 1: None |  | Agriculture | Handicrafts
2 | 3: Half | Public | Scale | No | Departmental |  |  | Coastal management | Livestock production
3 | 2: Some | NGO | Sector |  | National |  |  | Disaster risk reduction | Manufacturing
4 | 1: None |  |  |  |  | 5: Very high improvement | Established | Food security | other
|  | National |  |  |  | 4: High improvement | Maintained | Health | Services
|  | Regional |  |  |  | 3: Moderate improvement | Improved | Urban development | Tourism-related
|  | Local |  |  |  | 2: Limited improvement |  | Water management | Trading
[6 empty] | 1: No improvement |  | Multi-sector
|  | 1 -generated information is irrelevant, and neither the stakeholders reached nor the timeframe managed were achieved | 1: No info transferred on time | 4: High capacity | 5: Fully aware | 5: Highly responsive (All defined elements ) | 5: Fully improved | Roads | 5: Very effective
Asia-Pacific | NIE | 2 -the existence of some challenge in any of the three aspects of the indicator (generation of dissemination, stakeholders reached or timeframe managed) | 2: Somewhat info transferred | 3: Medium capacity | 4: Mostly aware | 4: Mostly responsive (Most defined elements) | 4: Mostly Improved | Gov Buildings | 4: Effective
Latin America and Caribbean | RIE | 3 -relevant information is generated and disseminated to all identified stakeholders on timely basis | 3: Info transferred on time | 2: Low capacity | 3: Partially aware | 3: Moderately responsive (Some defined elements) | 3: Moderately improved | Causeways | 3: Moderately effective
Africa | MIE |  |  | 1: No capacity | 2: Partially not aware | 2: Partially responsive (Lacks most elements) | 2: Somewhat improved | Airports | 2: Partially effective
Eastern Europe |  |  |  |  | 1: Aware of neither | 1: Non responsive (Lacks all elements ) | 1: Not improved | Schools | 1: Ineffective
| ha protected | [6 empty] | Training Centres
| ha rehabilitated | [5 empty] | Monitoring/Forecasting capacity | Hospitals
Afghanistan, Islamic Rep. of | km protected | [5 empty] | Policy/regulatory reform | Drinking water systems
Angola | km rehabilitated | 1: Risk knowledge | 1: No plans conducted or updated |  |  |  | Capacity development | Other
Albania |  | 2: Monitoring and warning service | 2: Undertaking or updating of assessments in progress |  |  | Communication & Information policy | Sustainable forest management
Argentina |  | 3: Dissemination and communication | 3: Risk and vulnterability assessments completed or updated |  |  | Domestic policy | Strengthening infrastructure | 1: Health and Social Infrastructure (developed/improved)
Armenia | Forests | 4: Response capability |  |  |  | Economic policy | Supporting livelihoods | 2: Physical asset (produced/improved/strenghtened)
Antigua and Barbuda | Mangroves |  |  |  |  | Education policy | Mangrove reforestation
Azerbaijan | Coasts |  | From 0 to 0.5% |  |  | Energy policy | Coastal drainage and infrastructure
Burundi | Rangelands |  | From 0.5 to 1% |  |  | Environmental policy | Irrigation system
Benin | Cultivated land/Agricultural land |  | From 1% to 5% |  |  | Foreign policy | Community-based adaptation
Burkina Faso | Catchment area/Watershed/Aquifer |  | From 5% to 10% |  |  | Health policy | Erosion control
Bangladesh | Protected areas/National parks |  | From 10% to 20% |  |  | Housing policy | Soil water conservation
Bulgaria | Other |  | From 20% to 30% |  |  | Human resource policies | Microfinance
Bahrain |  |  | From 30% to 40% |  |  | Information policy | Special Program for women
Bahamas, The |  |  | From 40% to 50% |  |  | Macroeconomic policy | Livelihoods
Bosnia and Herzegovina |  |  | Above 50% |  |  | Monetary policy | Water storage
Belarus | [5 empty] | Population policy | ICT and information dissemination
Belize | [5 empty] | Private policy
Bolivia | [5 empty] | Public policy
Brazil | [5 empty] | Science policy
Barbados | [5 empty] | Social policy
Bhutan |  | 3- relevant information is generated and disseminated to all identified stakeholders on timely basis |  |  |  | Transportation policy
Botswana |  | describe |  |  |  | Urban policy
Central African Republic |  | 2- the existence of some challenge in any of the three aspects of the indicator |  |  |  | Water policy
Chile |  | describe |  |  |  | Other policy
China, People's Republic of |  | 1- generated information is irrelevant and neither the stakeholders reached nor the timeframe managed were achieved
Cote d'Ivoire |  | describe
Cameroon
Congo, Dem. Rep. of
Congo, Republic of
Cook Islands
Colombia
Comoros
Cape Verde
Costa Rica
Cuba
Czech Republic
Djibouti
Dominica
Dominican Republic
Algeria
Ecuador
Egypt
Eritrea
Estonia
Ethiopia
Fiji
Micronesia, Fed. States of
Gabon
Georgia
Ghana
Guinea
Gambia, The
Guinea-Bissau
Equatorial Guinea
Grenada
Guatemala
Guyana
Honduras
Croatia
Haiti
Hungary
Indonesia
India
Iran, Islamic Republic of
Jamaica
Jordan
Kazakhstan
Kenya
Kyrgyz Republic
Cambodia
Kiribati
Saint Kitts and Nevis
Korea, Republic of
Lao People's Democratic Republic
Lebanon
Liberia
Libya
Saint Lucia
Sri Lanka
Lesotho
Lithuania
Latvia
Morocco
Moldova
Madagascar
Maldives
Mexico
Marshall Islands
Macedonia, former Yugoslav Republic of
Mali
Malta
Myanmar
Montenegro
Mongolia
Mozambique
Mauritania
Mauritius
Malawi
Malaysia
Namibia
Niger
Nigeria
Nicaragua
Niue
Nepal
Nauru
Oman
Pakistan
Panama
Peru
Philippines
Palau
Papua New Guinea
Poland
Korea, Dem. People's Rep. of
Paraguay
Romania
Russian Federation
Rwanda
Saudi Arabia
Sudan
Senegal
Solomon Islands
Sierra Leone
El Salvador
San Marino
Serbia
Sao Tome and Principe
Suriname
Slovak Republic
Slovenia
Swaziland
Seychelles
Syrian Arab Republic
Chad
Togo
Thailand
Tajikistan
Turkmenistan
Tonga
Trinidad and Tobago
Tunisia
Turkey
Tuvalu
Tanzania
Uganda
Ukraine
Uruguay
Uzbekistan
Saint Vincent and the Grenadines
Venezuela
Vietnam
Vanuatu
Samoa
Yemen, Republic of
South Africa
Zambia
Zimbabwe
Timor-Leste

## Results Tracker
Results Tracker for Adaptation Fund (AF) Projects
Goal: Assist developing-country Parties to the Kyoto Protocol that are particularly vulnerable to the adverse effects of climate change in meeting the costs of concrete adaptation projects and programmes in order to implement climate-resilient measures. Impact: Increased resiliency at the community, national, and regional levels to climate variability and change.
Important: Please read the following guidance document (also posted on the Adaptation Fund website) before entering your data
Link: http://www.adaptation-fund.org/sites/default/files/Results%20Framework%20and%20Baseline%20Guidance%20final.pdf
Adaptation Fund Strategic Results Framework
Project ID
Implementing Entity | ADA
Type of implementing entity | NIE
Country | Morocco
Region | Africa
Sector | Agriculture
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Impact: Increased resiliency at the community, national, and regional levels to climate variability and change | Core Indicator: No. of beneficiaries |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project
|  | Total | 0 |  |  | Total | 40000 |  |  | Total |  |  |  | Total
|  | % of female beneficiaries |  |  |  | % of female beneficiaries | 50% |  |  | % of female beneficiaries |  |  |  | % of female beneficiaries
|  | % of Youth beneficiaries |  |  |  | % of Youth beneficiaries |  |  |  | % of Youth beneficiaries |  |  |  | % of Youth beneficiaries
Outcome 1: Reduced exposure to climate-related hazards and threats | Indicator 1: Relevant threat and hazard information generated and disseminated to stakeholders on a timely basis | Indicator 1: Relevant threat and hazard information generated and disseminated to stakeholders on a timely basis | Indicator 1: Relevant threat and hazard information generated and disseminated to stakeholders on a timely basis | Indicator 1: Relevant threat and hazard information generated and disseminated to stakeholders on a timely basis | Indicator 1: Relevant threat and hazard information generated and disseminated to stakeholders on a timely basis | Indicator 1: Relevant threat and hazard information generated and disseminated to stakeholders on a timely basis | Indicator 1: Relevant threat and hazard information generated and disseminated to stakeholders on a timely basis | Indicator 1: Relevant threat and hazard information generated and disseminated to stakeholders on a timely basis | Indicator 1: Relevant threat and hazard information generated and disseminated to stakeholders on a timely basis | Indicator 1: Relevant threat and hazard information generated and disseminated to stakeholders on a timely basis | Indicator 1: Relevant threat and hazard information generated and disseminated to stakeholders on a timely basis | Indicator 1: Relevant threat and hazard information generated and disseminated to stakeholders on a timely basis | Indicator 1: Relevant threat and hazard information generated and disseminated to stakeholders on a timely basis | Indicator 1: Relevant threat and hazard information generated and disseminated to stakeholders on a timely basis | Indicator 1: Relevant threat and hazard information generated and disseminated to stakeholders on a timely basis | Indicator 1: Relevant threat and hazard information generated and disseminated to stakeholders on a timely basis | Indicator 1: Relevant threat and hazard information generated and disseminated to stakeholders on a timely basis | Indicator 1: Relevant threat and hazard information generated and disseminated to stakeholders on a timely basis | Indicator 1: Relevant threat and hazard information generated and disseminated to stakeholders on a timely basis | Indicator 1: Relevant threat and hazard information generated and disseminated to stakeholders on a timely basis | Indicator 1: Relevant threat and hazard information generated and disseminated to stakeholders on a timely basis | Indicator 1: Relevant threat and hazard information generated and disseminated to stakeholders on a timely basis
Output 1.1 Risk and vulnerability assessments conducted and updated | Indicator 1.1: No. of projects/programmes that conduct and update risk and vulnerability assessments | Indicator 1.1: No. of projects/programmes that conduct and update risk and vulnerability assessments | Indicator 1.1: No. of projects/programmes that conduct and update risk and vulnerability assessments | Indicator 1.1: No. of projects/programmes that conduct and update risk and vulnerability assessments | Indicator 1.1: No. of projects/programmes that conduct and update risk and vulnerability assessments | Indicator 1.1: No. of projects/programmes that conduct and update risk and vulnerability assessments | Indicator 1.1: No. of projects/programmes that conduct and update risk and vulnerability assessments | Indicator 1.1: No. of projects/programmes that conduct and update risk and vulnerability assessments | Indicator 1.1: No. of projects/programmes that conduct and update risk and vulnerability assessments | Indicator 1.1: No. of projects/programmes that conduct and update risk and vulnerability assessments | Indicator 1.1: No. of projects/programmes that conduct and update risk and vulnerability assessments | Indicator 1.1: No. of projects/programmes that conduct and update risk and vulnerability assessments | Indicator 1.1: No. of projects/programmes that conduct and update risk and vulnerability assessments | Indicator 1.1: No. of projects/programmes that conduct and update risk and vulnerability assessments | Indicator 1.1: No. of projects/programmes that conduct and update risk and vulnerability assessments | Indicator 1.1: No. of projects/programmes that conduct and update risk and vulnerability assessments | Indicator 1.1: No. of projects/programmes that conduct and update risk and vulnerability assessments | Indicator 1.1: No. of projects/programmes that conduct and update risk and vulnerability assessments | Indicator 1.1: No. of projects/programmes that conduct and update risk and vulnerability assessments | Indicator 1.1: No. of projects/programmes that conduct and update risk and vulnerability assessments | Indicator 1.1: No. of projects/programmes that conduct and update risk and vulnerability assessments | Indicator 1.1: No. of projects/programmes that conduct and update risk and vulnerability assessments
Output 1.2 Targeted population groups covered by adequate risk reduction systems | Core Indicator 1.2: No. of Early Warning Systems | Core Indicator 1.2: No. of Early Warning Systems | Core Indicator 1.2: No. of Early Warning Systems | Core Indicator 1.2: No. of Early Warning Systems | Core Indicator 1.2: No. of Early Warning Systems | Core Indicator 1.2: No. of Early Warning Systems | Core Indicator 1.2: No. of Early Warning Systems | Core Indicator 1.2: No. of Early Warning Systems | Core Indicator 1.2: No. of Early Warning Systems | Core Indicator 1.2: No. of Early Warning Systems | Core Indicator 1.2: No. of Early Warning Systems | Core Indicator 1.2: No. of Early Warning Systems | Core Indicator 1.2: No. of Early Warning Systems | Core Indicator 1.2: No. of Early Warning Systems | Core Indicator 1.2: No. of Early Warning Systems | Core Indicator 1.2: No. of Early Warning Systems | Core Indicator 1.2: No. of Early Warning Systems | Core Indicator 1.2: No. of Early Warning Systems | Core Indicator 1.2: No. of Early Warning Systems | Core Indicator 1.2: No. of Early Warning Systems | Core Indicator 1.2: No. of Early Warning Systems | Core Indicator 1.2: No. of Early Warning Systems
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 2: Strengthened institutional capacity to reduce risks associated with climate-induced socioeconomic and environmental losses | Indicator 2: Capacity of staff to respond to, and mitigate impacts of, climate-related events from targeted institutions increased | Number of staff targeted |  | Sector | Capacity level | Number of staff targeted |  | Sector | Capacity level | Number of staff targeted |  | Sector | Capacity level | Number of staff targeted |  | Sector | Capacity level
|  | Total | 82 | Multi-sector | 3: Medium capacity | Total | 1794 | Multi-sector | 4: High capacity | Total | 1831 | Multi-sector | 4: High capacity | Total
|  | % of female targeted | 12% |  |  | % of female targeted | 50% |  |  | % of female targeted | 15% |  |  | % of female targeted
Output 2.1 Strengthened capacity of national and sub-national centres and networks to respond rapidly to extreme weather events | Indicator 2.1.1: No. of staff trained to respond to, and mitigate impacts of, climate-related events | Total staff trained | % of female staff trained | Type |  | Total staff trained | % of female staff trained | Type |  | Total staff trained | % of female staff trained | Type |  | Total staff trained | % of female staff trained | Type
|  |  | 12% | Private |  |  | 50% | Private |  | 1744 | 15% | Private
| Indicator 2.1.2: No. of targeted institutions with increased capacity to minimize exposure to climate variability risks | Type | Scale | Sector | Capacity level | Type | Scale | Sector | Capacity level | Type | Scale | Sector | Capacity level | Type | Scale | Sector | Capacity level
|  | Public | Local | Multi-sector | 3: Medium capacity | Public | Local | Multi-sector | 4: High capacity | Public | Local | Multi-sector | 4: High capacity
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 3: Strengthened awareness and owernship of adaptation and climate risk reduction processes | Indicator 3.1: Increase in application of appropriate adaptation responses | Percentage of targeted population applying adaptation measures |  | Sector |  | Percentage of targeted population applying adaptation measures |  | Sector |  | Percentage of targeted population applying adaptation measures |  | Sector |  | Percentage of targeted population applying adaptation measures |  | Sector
|  | 30% |  | Multi-sector |  | 60% |  | Multi-sector |  | 60% |  | Multi-sector
Output 3: Targeted population groups participating in adaptation and risk reduction awareness activities | Indicator 3.1.1: Percentage in targeted population awareness of predicted adverse impacts of climate change, and of appropriate responses | No. of targeted beneficiaries | % of female participants targeted | Level of awareness |  | No. of targeted beneficiaries | % of female participants targeted | Level of awareness |  | No. of targeted beneficiaries | % of female participants targeted | Level of awareness |  | No. of targeted beneficiaries | % of female participants targeted | Level of awareness
|  | 0 | 0% | 3: Partially aware |  | 40000 | 50% | 4: Mostly aware |  | 137202 | 50% | 4: Mostly aware
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 4: Increased adaptive capacity within relevant development sector services and infrastructure assets | Indicator 4.1: Increased responsiveness of development sector services to evolving needs from changing and variable climate | Project/programme sector | Geographical scale | Response level |  | Project/programme sector | Geographical scale | Response level |  | Project/programme sector | Geographical scale | Response level |  | Project/programme sector | Geographical scale | Response level
|  | Water management | Local | 3: Moderately responsive (Some defined elements) |  | Water management | Local | 5: Highly responsive (All defined elements ) |  | Water management | Local | 5: Highly responsive (All defined elements )
| Core Indicator 4.2: Assets produced, developed, improved or strengthened | Sector | Targeted asset | Changes in asset (quantitative or qualitative) |  | Sector | Targeted asset | Changes in asset (quantitative or qualitative) |  | Sector | Targeted asset | Changes in asset (quantitative or qualitative) |  | Sector | Targeted asset | Changes in asset (quantitative or qualitative)
|  | Agriculture | 2: Physical asset (produced/improved/strenghtened) | 2: Somewhat improved |  | Agriculture | 2: Physical asset (produced/improved/strenghtened) | 4: Mostly Improved |  | Agriculture | 2: Physical asset (produced/improved/strenghtened) | 4: Mostly Improved
|  | Water management | 2: Physical asset (produced/improved/strenghtened) | 2: Somewhat improved |  | Water management | 2: Physical asset (produced/improved/strenghtened) | 4: Mostly Improved |  | Water management | 2: Physical asset (produced/improved/strenghtened) | 4: Mostly Improved
Output 4: Vulnerable development sector services and infrastructure assets strengthened in response to climate change impacts, including variability | Indicator 4.1.1: No. and type of development sector services to respond to new conditions resulting from climate variability and change | Number of services | Type |  | Sector | Number of services | Type |  | Sector | Number of services | Type |  | Sector | Number of services | Type |  | Sector
|  |  | Departmental |  | Agriculture |  | Departmental |  | Agriculture | 3 | Departmental |  | Agriculture
|  |  | Departmental |  | Water management |  | Departmental |  | Water management | 1 | Departmental |  | Water management
|  |  | Departmental |  | Food security |  | Departmental |  | Food security | 2 | Departmental |  | Food security
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 5: Increased ecosystem resilience in response to climate change and variability-induced stress | Indicator 5: Ecosystem services and natural resource assets maintained or improved under climate change and variability-induced stress | Natural resource improvement level |  | Sector | Type | Natural resource improvement level |  | Sector | Type | Natural resource improvement level |  | Sector | Type | Natural resource improvement level |  | Sector | Type
|  | 3: Moderately effective |  | Water management |  | 4: Effective |  |  |  | 4: Effective |  | Agriculture | water areas
Output 5: Vulnerable ecosystem services and natural resource assets strengthned in response to climate change impacts, including variability | Core Indicator 5.1: Natural Assets protected or rehabilitated | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Forests | 1 | ha protected | 3: Moderately effective | Forests | 1 | ha protected | 4: Effective | Forests | 2 | ha protected | 5: Very effective
|  | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Protected areas/National parks | 1 | ha rehabilitated | 3: Moderately effective | Protected areas/National parks | 1 | ha rehabilitated | 4: Effective | Protected areas/National parks | 1 | ha rehabilitated | 5: Very effective
|  | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Protected areas/National parks | 4 | km protected | 3: Moderately effective | Protected areas/National parks | 4 | km protected | 4: Effective | Protected areas/National parks | 4 | km protected | 5: Very effective
|  | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Other | 7 | ha protected | 3: Moderately effective | Other | 7 | ha protected | 4: Effective | Other | 7 | ha protected | 5: Very effective
|  | Baseline information |  |  |  | Targeted performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 6: Diversified and strengthened livelihoods and sources of income for vulnerable people in targeted areas | Indicator 6.1: Increase in households and communities having more secure access to livelihood assets | No. of targeted households | % of female headed households | Improvement level |  | No. of targeted households | % of female headed households | Improvement level |  | No. of targeted households | % of female headed households | Improvement level |  | No. of targeted households | % of female headed households | Improvement level
|  | 0 | 0% |  |  | 1140 | 50% |  |  | 22867 | 50% | 4: High improvement
| Indicator 6.2: Increase in targeted population's sustained climate-resilient alternative livelihoods | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
[9 empty] | Agriculture | 25154 | 50% | From 40% to 50% | Agriculture
|  | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
[9 empty] | Tourism-related |  |  |  | Tourism-related
|  | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
[9 empty] | Handicrafts |  |  |  | Handicrafts
|  | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
[9 empty] | other |  |  |  | other
Output 6 Targeted individual and community livelihood strategies strengthened in relation to climate change impacts, including variability | Indicator 6.1.1: No. and type of adaptation assets created or strengthened in support of individual or community livelihood strategies | Number of Assets | Type of Assets | Sector | Adaptation strategy | Number of Assets | Type of Assets | Sector | Adaptation strategy | Number of Assets | Type of Assets | Sector | Adaptation strategy | Number of Assets | Type of Assets | Sector | Adaptation strategy
|  | 3 | Adaptation strategies | Water management | Supporting livelihoods | 3 | Adaptation strategies | Water management | Supporting livelihoods | 3 | Adaptation strategies | Water management | Supporting livelihoods
| Core Indicator 6.1.2: Increased income, or avoided decrease in income | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  |  | Agricultural-related |  |  |  | Agricultural-related |  |  |  | Agricultural-related
|  | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  |  | Tourism-related |  |  |  | Tourism-related |  |  |  | Tourism-related
|  | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  |  | Handicrafts |  |  |  | Handicrafts |  |  |  | Handicrafts
|  | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  |  | other |  |  |  | other |  |  |  | other
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 7: Improved policies and regulations that promote and enforce resilience measures | Indicator 7: Climate change priorities are integrated into national development strategy | Integration level |  |  |  | Integration level |  |  |  | Integration level |  |  |  | Integration level
Output 7:Improved integration of climate-resilience strategies into country development plans | Indicator 7.1: No. of policies introduced or adjusted to address climate change risks | No. of Policies introduced or adjusted | Sector | Scale | Type | No. of Policies introduced or adjusted | Sector | Scale | Type | No. of Policies introduced or adjusted | Sector | Scale | Type | No. of Policies introduced or adjusted | Sector | Scale | Type
| Indicator 7.2: No. of targeted development strategies with incorporated climate change priorities enforced | No. of Development strategies | Regulation |  | Effectiveness | No. of Development strategies | Regulation |  | Effectiveness | No. of Development strategies | Regulation |  | Effectiveness | No. of Development strategies | Regulation |  | Effectiveness
Glacier lake outburst flood
|  | Inland flooding | fr | biological assets |  | Company policy | 5: Fully enforced (All elements implemented)
|  | Salinization | Decrease | land |  | Communication & Information policy | 4: Enforced (Most elements implemented)
|  | Drought | Same | water areas |  | Defense policy | 3: Partially enforced (Some elements implemented)
|  | Wind |  | subsoil assets | increased adpative capacity | Domestic policy | 2: Partially not enforced (Most elements not implemented) |  | Agribusiness
|  | Coastal flooding |  | air | achieved | Economic policy | 1: Not enforced (No elements implemented) |  | Agricultural-related | Financial capital
|  | Storm surge | Please choose |  | enhanced level of protection | Education policy |  |  | Agriculture | Human capital
|  | Hurricane | Selected | [5 empty] | Aquaculture | Physical capital
|  |  | Not relevant |  |  | 5: All (Fully integrated) |  |  | Construction/repairing business | Social capital
[6 empty] | 4: Most |  |  | Cultivation | Natural capital
[6 empty] | 3: Some |  |  | Fishing | Personal capital
Select | 5: All | Select |  |  | Community | 2: Most not integrated |  | Other | Forestry | Adaptation strategies
1 | 4: Almost all | Private | Type | Yes | Multi-community | 1: None |  | Agriculture | Handicrafts
2 | 3: Half | Public | Scale | No | Departmental |  |  | Coastal management | Livestock production
3 | 2: Some | NGO | Sector |  | National |  |  | Disaster risk reduction | Manufacturing
4 | 1: None |  |  |  |  | 5: Very high improvement | Established | Food security | other
|  | National |  |  |  | 4: High improvement | Maintained | Health | Services
|  | Regional |  |  |  | 3: Moderate improvement | Improved | Urban development | Tourism-related
|  | Local |  |  |  | 2: Limited improvement |  | Water management | Trading
[6 empty] | 1: No improvement |  | Multi-sector
|  | 1 -generated information is irrelevant, and neither the stakeholders reached nor the timeframe managed were achieved | 1: No info transferred on time | 4: High capacity | 5: Fully aware | 5: Highly responsive (All defined elements ) | 5: Fully improved | Roads | 5: Very effective
Asia-Pacific | NIE | 2 -the existence of some challenge in any of the three aspects of the indicator (generation of dissemination, stakeholders reached or timeframe managed) | 2: Somewhat info transferred | 3: Medium capacity | 4: Mostly aware | 4: Mostly responsive (Most defined elements) | 4: Mostly Improved | Gov Buildings | 4: Effective
Latin America and Caribbean | RIE | 3 -relevant information is generated and disseminated to all identified stakeholders on timely basis | 3: Info transferred on time | 2: Low capacity | 3: Partially aware | 3: Moderately responsive (Some defined elements) | 3: Moderately improved | Causeways | 3: Moderately effective
Africa | MIE |  |  | 1: No capacity | 2: Partially not aware | 2: Partially responsive (Lacks most elements) | 2: Somewhat improved | Airports | 2: Partially effective
Eastern Europe |  |  |  |  | 1: Aware of neither | 1: Non responsive (Lacks all elements ) | 1: Not improved | Schools | 1: Ineffective
| ha protected | [6 empty] | Training Centres
| ha rehabilitated | [5 empty] | Monitoring/Forecasting capacity | Hospitals
Afghanistan, Islamic Rep. of | km protected | [5 empty] | Policy/regulatory reform | Drinking water systems
Angola | km rehabilitated | 1: Risk knowledge | 1: No plans conducted or updated |  |  |  | Capacity development | Other
Albania |  | 2: Monitoring and warning service | 2: Undertaking or updating of assessments in progress |  |  | Communication & Information policy | Sustainable forest management
Argentina |  | 3: Dissemination and communication | 3: Risk and vulnterability assessments completed or updated |  |  | Domestic policy | Strengthening infrastructure | 1: Health and Social Infrastructure (developed/improved)
Armenia | Forests | 4: Response capability |  |  |  | Economic policy | Supporting livelihoods | 2: Physical asset (produced/improved/strenghtened)
Antigua and Barbuda | Mangroves |  |  |  |  | Education policy | Mangrove reforestation
Azerbaijan | Coasts |  | From 0 to 0.5% |  |  | Energy policy | Coastal drainage and infrastructure
Burundi | Rangelands |  | From 0.5 to 1% |  |  | Environmental policy | Irrigation system
Benin | Cultivated land/Agricultural land |  | From 1% to 5% |  |  | Foreign policy | Community-based adaptation
Burkina Faso | Catchment area/Watershed/Aquifer |  | From 5% to 10% |  |  | Health policy | Erosion control
Bangladesh | Protected areas/National parks |  | From 10% to 20% |  |  | Housing policy | Soil water conservation
Bulgaria | Other |  | From 20% to 30% |  |  | Human resource policies | Microfinance
Bahrain |  |  | From 30% to 40% |  |  | Information policy | Special Program for women
Bahamas, The |  |  | From 40% to 50% |  |  | Macroeconomic policy | Livelihoods
Bosnia and Herzegovina |  |  | Above 50% |  |  | Monetary policy | Water storage
Belarus | [5 empty] | Population policy | ICT and information dissemination
Belize | [5 empty] | Private policy
Bolivia | [5 empty] | Public policy
Brazil | [5 empty] | Science policy
Barbados | [5 empty] | Social policy
Bhutan |  | 3- relevant information is generated and disseminated to all identified stakeholders on timely basis |  |  |  | Transportation policy
Botswana |  | describe |  |  |  | Urban policy
Central African Republic |  | 2- the existence of some challenge in any of the three aspects of the indicator |  |  |  | Water policy
Chile |  | describe |  |  |  | Other policy
China, People's Republic of |  | 1- generated information is irrelevant and neither the stakeholders reached nor the timeframe managed were achieved
Cote d'Ivoire |  | describe
Cameroon
Congo, Dem. Rep. of
Congo, Republic of
Cook Islands
Colombia
Comoros
Cape Verde
Costa Rica
Cuba
Czech Republic
Djibouti
Dominica
Dominican Republic
Algeria
Ecuador
Egypt
Eritrea
Estonia
Ethiopia
Fiji
Micronesia, Fed. States of
Gabon
Georgia
Ghana
Guinea
Gambia, The
Guinea-Bissau
Equatorial Guinea
Grenada
Guatemala
Guyana
Honduras
Croatia
Haiti
Hungary
Indonesia
India
Iran, Islamic Republic of
Jamaica
Jordan
Kazakhstan
Kenya
Kyrgyz Republic
Cambodia
Kiribati
Saint Kitts and Nevis
Korea, Republic of
Lao People's Democratic Republic
Lebanon
Liberia
Libya
Saint Lucia
Sri Lanka
Lesotho
Lithuania
Latvia
Morocco
Moldova
Madagascar
Maldives
Mexico
Marshall Islands
Macedonia, former Yugoslav Republic of
Mali
Malta
Myanmar
Montenegro
Mongolia
Mozambique
Mauritania
Mauritius
Malawi
Malaysia
Namibia
Niger
Nigeria
Nicaragua
Niue
Nepal
Nauru
Oman
Pakistan
Panama
Peru
Philippines
Palau
Papua New Guinea
Poland
Korea, Dem. People's Rep. of
Paraguay
Romania
Russian Federation
Rwanda
Saudi Arabia
Sudan
Senegal
Solomon Islands
Sierra Leone
El Salvador
San Marino
Serbia
Sao Tome and Principe
Suriname
Slovak Republic
Slovenia
Swaziland
Seychelles
Syrian Arab Republic
Chad
Togo
Thailand
Tajikistan
Turkmenistan
Tonga
Trinidad and Tobago
Tunisia
Turkey
Tuvalu
Tanzania
Uganda
Ukraine
Uruguay
Uzbekistan
Saint Vincent and the Grenadines
Venezuela
Vietnam
Vanuatu
Samoa
Yemen, Republic of
South Africa
Zambia
Zimbabwe
Timor-Leste