{"text_format":"2","workbook":"xls","n_sheets":8,"sheets":["Overview","FinancialData","Risk Assesment","Rating","Project Indicators","Lessons Learned","Results Tracker","Units for Indicators"],"not_rendered":{"charts":0,"images":2,"macros":0,"external_links":2,"defined_names":23,"comments":0,"pivot_tables":0},"unopened":[],"bounds":{"document_bytes":16777216,"sheet_cells":100000,"run_cost":"one","rows_first":2000,"rows_last":500,"rows_between":2000,"halvings":0,"cell_chars":16384,"cell_head_chars":4096},"cells_cut":0,"cells_raw":0,"read":"whole","date_system":"1900","formulas":"cached_only"}

{"sheet":"Overview","index":0,"n_rows":177,"n_cols":16,"rows_kept":177,"cut":false,"hidden":false,"merged":[[15,1,15,2],[26,1,26,2],[35,1,35,2],[25,1,25,2],[18,1,18,2],[22,1,23,2],[24,1,24,2],[31,1,31,2],[52,3,54,3],[56,3,58,3],[22,3,23,3]],"flags":["formulas_cached_only"]}
[]
[]
[null,null,null,"Project Performance Report (PPR)"]
[]
[null,null,"Period of Report (Dates)","  01/05/17 - 30/04/18"]
[]
[null,null,"Project Title: ","Conservation and Management of Coastal Resources as a Potential Adaptation Strategy for Sea Level Rise"]
[]
[]
[]
[]
[]
[null,null,"Project Summary: ","In India nearly 100 million people living along the coastline are reliant on climate-dependent activities such as agriculture, fishing and aquaculture. The livelihood security of these coastal communities and ecological security of the coastal areas are already under stress due to high population density, urbanization, industrial development, high rate of environmental degradation and frequent occurrence of cyclones and storms. Sea level changes and occurrence of extreme events such as cyclones and storm surges will be aggravating this problem. The predicated sea level rise would lead to inundation of seawater in about 5,700 km2 of land along the coastal states of India and nearly 7 million coastal families could be directly affected if the sea level increases by 1 m by 2100. \n\nFarming families, fishermen, aqua farmers and others will bear the brunt of these impacts through less stable livelihoods and rising risks to their health, safety and homes. Many fisheries-dependent communities already live a precarious and vulnerable existence because of poverty, lack of access to social services and lack of essential infrastructure. As indicated above the coastal area of India is highly vulnerable to climate change and the present project is designed to link ecological rehabilitation of degraded mangroves, utilization of saline lands for livelihood development and preparing the communities for facing the climate change challenges through adaptation measures."]
[{"$nulls":7},"Countries","Project Type:  ",null,"GEF Focal Area: ","GEF 4 Focal Areas","GEF 2 / 3 Operational Programme: ","Overall Rating of the project in the evaluation by the project evaluator: ","GEF-4 Focal Area Strategic Program: ","GEF-3 Focal Area Strategic Program: "]
[null,null,"Database Number: ","IND/NIE/Coastal/2014/1",null,null,null,"Afghanistan","FP","Yes","Biodiversity",1,1,"U","BD-SP1-PA Financing","1: Arid & semi-arid ecosystems"]
[null,"Implementing Entity (IE) [name]:",null,"National Bank for Agriculture and Rural Development (NABARD)",null,null,null,"Albania","MSP","No","Climate Change Adaptation",2,2,"S","BD-SP2-Marine PA","2: Coastal, marine & freshwater ecosystems"]
[null,null,"Type of IE:","Developmental Bank",null,null,null,"Algeria","EA",null,"Climate Change Mitigation",3,3,"MU","BD-SP3-PA Networks","3: Forest ecosystems"]
[null,null,"Country(ies): ","India",null,null,null,"Angola",null,null,"International Waters",5,5,"Good","BD-SP5-Markets","13: Conservation and Sustainable Use of Biological Diversity Important to Agriculture"]
[null,"Relevant Geographic Points (i.e. cities, villages, bodies of water):",null,"Project Location:\n\nThe project is being implemented in the Krishna delta (lat. 15°44′–16°40′N and long. 80°20′–81°30′E) in the state of Andhra Pradesh on the southeast coast of India. The soil of the coastal tract is sandy, coarse, deep and occasionally saline. About 4.5 million people, depending on agriculture, fisheries and aquaculture, live within the delta. About 5,40,000 ha are irrigated with river water within the delta. In the project area, nearly 17% of the population are poorest of the poor and 37% are poor. The land use pattern indicates that nearly 55% of the land area is under agriculture, 8.7% of the area is under forest. Brackish water aquaculture is practiced in about 4,000 ha. \n\nProject Villages:\n\nProject is being implemented in three villages namely, Sorlagondi, Nali and Basavanipalem, located in the Krishna deltaic region of Andhra Pradesh. The main occupation of the community in all the three villages is Agriculture, Fishing and aquaculture. The total population of the three villages is about 3,905. There are about 1,104 households in these three villages. \n\n",null,null,null,"Argentina",null,null,"Multiple Focal Area",null,null,null,"BD-SP7-Invasive Alien Species(IAS)","6: Promoting the adoption of renewable energy by removing barriers and reducing implementation costs"]
[{"$nulls":12},"CC-SP2- Industrial EE","8: Waterbody based operational program"]
[null,null,"Project Milestones",{"$nulls":9},"CC-SP3-RE,CC-SP4-Biomass","9: Integrated Land and Water multiple focal area"]
[null,null,"Milestone","S.No          Major Activity                                                                                               Time line\n1      Community mobilization and organization                                                       0-6 months\n2      Participatory Rural Appraisal                                                                                 0-6 months\n3      Implementing entry point activities                                                                     0-6 months\n4      Identification and demarcation of site for mangroves and IMFFS           0-6 months\n5      Restoration of mangrove areas for coastal protection                                  7-24 months \n8      Land preparation and development of integrated mangrove fishery                                                   farming system (IMFFS) and cage and pen culture for fish culture                   7-24 months                                      9    Planting of mangroves and halophytes in the IMFFS farm and                                                                            participatory monitoring                                                                                                    7-24 months\n",null,null,null,"Bahamas",{"$nulls":6},"CC-SP5-Transport","10: Contaminants based operational program"]
[null,"AFB Approval Date:",null,"2014-10-10"]
[]
[null,"IE-AFB Agreement Signature Date:",null,"2014-11-25",{"$nulls":9},"CC-SP6-LULUCF","12: Integrated Ecosystem Management"]
[null,"Start of Project/Programme:",null,"2015-06-23",{"$nulls":9},"Cross cutting capacity building","14: Persistent Organic Pollutants"]
[null,"Mid-term Review Date (if planned):",null,"2017-06-23"]
[null,null,"Terminal Evaluation Date:","2019-06-19"]
[]
[null,null,null,"List documents/ reports/ brochures / articles that have been prepared about the project.",null,null,null,"Cyprus"]
[null,null,null,"Reports:                                                                                                                                                                                           1. Inception Report  2. Participatory Rural Appraisal 3. Socio-economic survey 4. Micro plan 5. Village Level Institutions 6. Exposure visit to Coringa mangroves  7.   Exposure visit to Brahmavar, Karnataka on cage culture 8. Mangrove Nursery 9. Mangrove restoration 10. Entry Point activities of the project.\n \nBrochures:                                                                                                                                                                                                                                                                                 1. Overview of the project 2. Climate change Sea level rise and  3. Mangrove conservation and management. ",null,null,null,"Czech Republic"]
[null,"List the Website address (URL) of project.",{"$nulls":5},"Democratic People's Republic of Korea"]
[null,null,null,"NA",null,null,null,"Democratic Republic of the Congo"]
[{"$nulls":7},"Denmark"]
[null,null,"Project contacts:  ",{"$nulls":4},"Djibouti"]
[null,"National Project Manager/Coordinator",{"$nulls":5},"Dominica"]
[null,null,"Name: ","R.Ramasubramanian, Principal Co-ordinator- Coastal Systems Research \nM S Swaminathan Research Foundation (MSSRF)",null,null,null,"Dominican Republic"]
[null,null,"Email: ","rramasubramani@rediffmail.com; ramasubramanian@mssrf.res.in ",null,null,null,"Ecuador"]
[null,null,"Date: ","2018-08-02",null,null,null,"Egypt"]
[null,null,"Government DA",{"$nulls":4},"El Salvador"]
[null,null,"Name: ","Ravi S. Prasad, IAS (Joint Secretary)\nMinistry of Environment, Forests & Climate Change, Govt. of India",null,null,null,"Equatorial Guinea"]
[null,null,"Email: ","ravis.prasad@nic.in",null,null,null,"Eritrea"]
[null,null,"Date: ","2018-08-02",null,null,null,"Estonia"]
[null,null,"Implementing Entity",{"$nulls":4},"Ethiopia"]
[null,null,"Name: ","Shankar A. Pande (CGM-FSPD)\nNational Bank for Agriculture and Rural Development",null,null,null,"Fiji"]
[null,null,"Email: ","shankar.pandey@nabard.org",null,null,null,"Finland"]
[null,null,"Date: ","2018-08-02",null,null,null,"France"]
[null,null,"Executing Agency",{"$nulls":4},"Gambia"]
[null,null,"Name: ","M S Swaminathan Research Foundation",null,null,null,"Georgia"]
[null,null,"Email: ","rramasubramani@rediffmail.com; ramasubramanian@mssrf.res.in ",null,null,null,"Germany"]
[null,null,"Date: ","2018-08-02",null,null,null,"Ghana"]
[null,null,"Executing Agency",{"$nulls":4},"Greece"]
[null,null,"Name: ","Same as Above",null,null,null,"Grenada"]
[null,null,"Email: ",{"$nulls":4},"Guatemala"]
[null,null,"Date: ",{"$nulls":4},"Guinea"]
[null,null,"Executing Agency",{"$nulls":4},"Guinea Bissau"]
[null,null,"Name: ","Same as Above",null,null,null,"Guyana"]
[null,null,"Email: ",{"$nulls":4},"Haiti"]
[null,null,"Date: ",{"$nulls":4},"Honduras"]
[{"$nulls":7},"Hungary"]
[{"$nulls":7},"Iceland"]
[{"$nulls":7},"India"]
[{"$nulls":7},"Indonesia"]
[{"$nulls":7},"Iran (Islamic Republic of)"]
[{"$nulls":7},"Iraq"]
[{"$nulls":7},"Ireland"]
[{"$nulls":7},"Israel"]
[{"$nulls":7},"Italy"]
[{"$nulls":7},"Jamaica"]
[{"$nulls":7},"Japan"]
[{"$nulls":7},"Jordan"]
[{"$nulls":7},"Kazakhstan"]
[{"$nulls":7},"Kenya"]
[{"$nulls":7},"Kiribati"]
[{"$nulls":7},"Kuwait"]
[{"$nulls":7},"Kyrgyzstan"]
[{"$nulls":7},"Lao People’s Democratic Republic"]
[{"$nulls":7},"Latvia"]
[{"$nulls":7},"Lebanon"]
[{"$nulls":7},"Lesotho"]
[{"$nulls":7},"Liberia"]
[{"$nulls":7},"Libyan Arab Jamahiriya"]
[{"$nulls":7},"Liechtenstein"]
[{"$nulls":7},"Lithuania"]
[{"$nulls":7},"Luxembourg"]
[{"$nulls":7},"Madagascar"]
[{"$nulls":7},"Malawi"]
[{"$nulls":7},"Malaysia"]
[{"$nulls":7},"Maldives"]
[{"$nulls":7},"Mali"]
[{"$nulls":7},"Malta"]
[{"$nulls":7},"Marshall Islands"]
[{"$nulls":7},"Mauritania"]
[{"$nulls":7},"Mauritius"]
[{"$nulls":7},"Mexico"]
[{"$nulls":7},"Micronesia, Federated States of"]
[{"$nulls":7},"Monaco"]
[{"$nulls":7},"Mongolia"]
[{"$nulls":7},"Montenegro"]
[{"$nulls":7},"Morocco"]
[{"$nulls":7},"Mozambique"]
[{"$nulls":7},"Myanmar"]
[{"$nulls":7},"Namibia"]
[{"$nulls":7},"Nauru"]
[{"$nulls":7},"Nepal"]
[{"$nulls":7},"Netherlands"]
[{"$nulls":7},"New Zealand"]
[{"$nulls":7},"Nicaragua"]
[{"$nulls":7},"Niger"]
[{"$nulls":7},"Nigeria"]
[{"$nulls":7},"Norway"]
[{"$nulls":7},"Oman"]
[{"$nulls":7},"Pakistan"]
[{"$nulls":7},"Palau"]
[{"$nulls":7},"Panama"]
[{"$nulls":7},"Papua New Guinea"]
[{"$nulls":7},"Paraguay"]
[{"$nulls":7},"Peru"]
[{"$nulls":7},"Philippines"]
[{"$nulls":7},"Poland"]
[{"$nulls":7},"Portugal"]
[{"$nulls":7},"Qatar"]
[{"$nulls":7},"Republic of Korea"]
[{"$nulls":7},"Republic of Moldova"]
[{"$nulls":7},"Romania"]
[{"$nulls":7},"Russian Federation"]
[{"$nulls":7},"Rwanda"]
[{"$nulls":7},"Saint Kitts and Nevis"]
[{"$nulls":7},"Saint Lucia"]
[{"$nulls":7},"Saint Vincent and the Grenadines"]
[{"$nulls":7},"Samoa"]
[{"$nulls":7},"San Marino"]
[{"$nulls":7},"Sao Tome and Principe"]
[{"$nulls":7},"Saudi Arabia"]
[{"$nulls":7},"Senegal"]
[{"$nulls":7},"Serbia"]
[{"$nulls":7},"Seychelles"]
[{"$nulls":7},"Sierra Leone"]
[{"$nulls":7},"Singapore"]
[{"$nulls":7},"Slovakia"]
[{"$nulls":7},"Slovenia"]
[{"$nulls":7},"Solomon Islands"]
[{"$nulls":7},"Somalia"]
[{"$nulls":7},"South Africa"]
[{"$nulls":7},"Spain"]
[{"$nulls":7},"Sri Lanka"]
[{"$nulls":7},"Sudan"]
[{"$nulls":7},"Suriname"]
[{"$nulls":7},"Swaziland"]
[{"$nulls":7},"Sweden"]
[{"$nulls":7},"Switzerland"]
[{"$nulls":7},"Syrian Arab Republic"]
[{"$nulls":7},"Tajikistan"]
[{"$nulls":7},"Thailand"]
[{"$nulls":7},"The former Yugoslav Republic of Macedonia"]
[{"$nulls":7},"Timor-Leste"]
[{"$nulls":7},"Togo"]
[{"$nulls":7},"Tonga"]
[{"$nulls":7},"Trinidad and Tobago"]
[{"$nulls":7},"Tunisia"]
[{"$nulls":7},"Turkey"]
[{"$nulls":7},"Turkmenistan"]
[{"$nulls":7},"Tuvalu"]
[{"$nulls":7},"Uganda"]
[{"$nulls":7},"Ukraine"]
[{"$nulls":7},"United Arab Emirates"]
[{"$nulls":7},"United Kingdom of Great Britain and Northern Ireland"]
[{"$nulls":7},"United Republic of Tanzania"]
[{"$nulls":7},"United States of America"]
[{"$nulls":7},"Uruguay"]
[{"$nulls":7},"Uzbekistan"]
[{"$nulls":7},"Vanuatu"]
[{"$nulls":7},"Venezuela, Bolivarian Republic of"]
[{"$nulls":7},"Viet Nam"]
[{"$nulls":7},"Yemen"]
[{"$nulls":7},"Zambia"]
[{"$nulls":7},"Zimbabwe"]

{"sheet":"FinancialData","index":1,"n_rows":99,"n_cols":19,"rows_kept":99,"cut":false,"hidden":false,"merged":[[94,2,94,8],[8,6,8,8],[10,6,10,8],[108,2,108,3],[107,6,107,8],[108,6,108,8],[104,6,104,8],[103,6,103,8],[103,2,103,3],[9,6,9,8],[95,6,95,8],[16,6,16,7],[2,2,2,9],[96,2,96,8],[8,2,8,3],[10,2,10,3],[64,2,64,3],[65,2,65,3],[95,2,95,3],[17,6,17,7],[104,2,104,3],[107,2,107,3],[106,2,106,3],[100,2,100,3],[101,2,101,3],[101,6,101,8],[4,2,4,8],[3,1,3,8],[16,2,16,3],[6,2,6,3],[15,2,15,3],[13,2,13,8],[17,5,27,5],[17,4,27,4],[7,2,7,8],[27,6,27,7],[23,6,23,7],[12,2,12,3],[18,6,18,7],[19,6,19,7],[20,6,20,7],[21,6,21,7],[98,2,98,3],[97,2,97,3],[98,6,98,8],[97,6,97,8],[12,6,12,8],[34,6,34,7],[35,6,35,7],[37,6,37,7],[39,6,39,7],[40,6,40,7],[34,4,39,4],[34,5,39,5],[59,6,59,7],[61,6,61,7],[60,6,60,7],[38,6,38,7],[41,6,41,7],[42,6,42,7],[49,6,49,7],[50,6,50,7],[62,6,62,7],[40,4,49,4],[40,5,49,5],[50,4,57,4],[50,5,57,5],[58,6,58,7],[54,6,54,7],[57,6,57,7],[51,6,51,7],[43,6,43,7],[28,4,33,4],[28,5,33,5],[28,6,28,7],[29,6,29,7],[30,6,30,7],[31,6,31,7],[33,6,33,7],[69,5,72,5],[69,4,72,4],[74,4,80,4],[74,5,80,5],[82,4,84,4],[82,5,84,5],[22,6,22,7],[24,6,24,7],[25,6,25,7],[26,6,26,7],[36,6,36,7],[44,6,44,7],[55,6,55,7],[56,6,56,7],[45,6,45,7],[46,6,46,7],[47,6,47,7],[52,6,52,7],[53,6,53,7]],"flags":["formulas_cached_only"]}
[]
[]
[null,null,"Financial Information:  Cumulative from project start to [23/06/15 - 30/04/18]"]
[]
[]
[]
[null,null,"DISBURSEMENT OF AF GRANT FUNDS "]
[null,null,"How much of the total AF grant as noted in Project Document plus any project preparation grant has been spent to date?"]
[null,null,"Estimated cumulative total disbursement as of [30-06-2018]",null,null,null,290754,null,null,"In USD"]
[{"$nulls":6},17445220,null,null,"In Indian Rupees at the exchange rate of 1 USD = INR 60"]
[null,null,"Add any comments on AF Grant Funds. (word limit=200)",null,null,null,"No Comments"]
[]
[null,null,"INVESTMENT INCOME ",null,null,null,"NABARD maintains one RBI account where all the funds are credited and pooled. In view of this, project wise investment income may not be ascertained. The Investment Income is reported separately to AF for all the 06 projects sanctioned for India worth USD 9.85 Million"]
[null,null,"Amount of annual investment income generated from the Adaptation Fund’s grant"]
[]
[null,null,"EXPENDITURE DATA"]
[null,null,"List output and corresponding amount spent for the current reporting period",null,"Project Components","Expected Outcomes","ITEM / ACTIVITY / ACTION",null,"AMOUNT in USD","AMOUNT in INR"]
[{"$nulls":4},"1. Community mobilization and organization","Improved community\norganization to undertake\nclimate change\nadaptation measures","Community mobilization and organization"]
[{"$nulls":6},"Activity 1.1.1.Organizing project orientation meetings to    community ",null,0,0]
[{"$nulls":6}," Activity 1.1.2.Sensitizing the community on gender",null,0,0]
[{"$nulls":6},"Activity 1.1.3.Organizing exposure visits to successful participatory mangrove, IMFFS and coastal resources mgmt projects",null,0,0]
[{"$nulls":6},"Activity 1.1.4.Conducting Participatory Rural Appraisal (PRA)",null,0,0]
[{"$nulls":6},"Activity 1.1.5.Forming village level institutions",null,0,0]
[{"$nulls":6},"Activity 1.1.6.Implementing entry point activities",null,2000,120000]
[{"$nulls":6},"Activity 1.2.1.Organizing orientation meetings on CC, SLR and adaptive capacity",null,0,0]
[{"$nulls":6},"Activity 1.3.1.Preparing annual micro plan:",null,0,0]
[{"$nulls":6},"Activity 1.3.2.Implementing micro plan and monitoring",null,0,0]
[{"$nulls":6},"Sub Total",null,2000,120000]
[{"$nulls":4},"2.Capacity building for coastal protection and livelihoods","Trained stakeholders on\ncoastal protection and\nlivelihoods","Capacity building for coastal protection and livelihoods"]
[{"$nulls":6},"Activity 2.1.2.Organizing training on mangrove restoration techniques to VLI members",null,0,0]
[{"$nulls":6},"Activity 2.1.3.Organizing training on mangrove restoration to NGOs and Self government",null,0,0]
[{"$nulls":6},"Activity 2.1.4.Organizing training on mangrove restoration to Government officials",null,0,0]
[{"$nulls":6},"Activity 2.2.2.Organizing training on IMFFS",null,0,0]
[{"$nulls":6},"Sub Total",null,0,0]
[{"$nulls":4},"3. Restoration of\nmangrove areas\nfor coastal\nprotection","Restored and healthy\nmangrove replanted area\ncontributing to protection\nof coastal erosion sea\nlevel rise","Restoring mangroves for coastal protection"]
[{"$nulls":6},"Activity 3.1.4.Preparing land for mangrove restoration (Canal digging)",null,23319.283333333333,1399157]
[{"$nulls":6},"Activity 3.1.5.Planting mangrove saplings ",null,0,0]
[{"$nulls":6},"Activity 3.2.2.Establishing mangrove nursery",null,3333.5,200010]
[{"$nulls":6},"Activity 3.1.6.Monitoring and after care",null,1000,60000]
[{"$nulls":6},"Sub Total",null,27652.783333333333,1659167]
[{"$nulls":4},"4. Demonstration\nof Integrated\nmangrove based\nfishery livelihoods","Demonstrated fishery\nrelated sustainable\nlivelihoods integrated with\nmangroves","Demonstration of mangrove dependent fishery"]
[{"$nulls":6},"Activity 4.1.2 a.Constructing two types of IMFFS farms (Pond preparation)",null,65000,3900000]
[{"$nulls":6},"Activity 4.1.2 b.Construction of sluice gates",null,7291.333333333333,437480]
[{"$nulls":6},"Activity 4.3.2.Construction of cages and pens",null,38888.55,2333313]
[{"$nulls":6},"Activity 4.1.3.Raising mangrove plantation in the IMFFS farms",null,0,0]
[{"$nulls":6},"Activity 4.2.2.Stocking of fishes/shrimps/crabs",null,0,0]
[{"$nulls":6},"Activity 4.2.3.Monitoring of IMFFS ponds",null,0,0]
[{"$nulls":6},"Activity 4.3.3.Stocking of fish crab juveniles",null,0,0]
[{"$nulls":6},"Activity 4.3.4 b.Feed cost",null,0,0]
[{"$nulls":6},"Sub Total",null,111179.88333333333,6670793]
[{"$nulls":4},"5. Knowledge\nManagement for\nImproved Coastal\nProtection","Prepared and published\nmaterials on ways to\nupscale coastal protection\nand livelihood systems in\nmangrove areas","Knowledge Management for improve coastal Protection"]
[{"$nulls":6},"Activity 5.1.1.Preparation of resource materials in local language",null,333.33,20000]
[{"$nulls":6},"Activity 5.1.2.Preparation of Brochure and Pamphlets",null,0,0]
[{"$nulls":6},"Activity 5.2.1.Documenting processes",null,0,0]
[{"$nulls":6},"Activity 5.2.1 b.Monitoring of Project activities along with community",null,833.3333333333334,50000]
[{"$nulls":6},"Activity 5.2.3.Organizing workshop at district level",null,0,0]
[{"$nulls":6},"Activity 5.2.4.Organizing workshop at national level",null,0,0]
[{"$nulls":6},"Sub Total",null,1166.6633333333334,70000,null,null,null,"`"]
[{"$nulls":6},"Total of all the Project Components(1-5)",null,141999.33,8519960]
[{"$nulls":6},"Project Execution cost",null,6725,403500]
[]
[]
[{"$nulls":6},"TOTAL",null,148724.33,8923460]
[]
[null,null,"PLANNED EXPENDITURE SCHEDULE"]
[null,null,"List outputs planned and corresponding projected cost for the upcoming reporting period [01/05/2018 to 30/04/2019]",null,"Project Components","Expected Outcomes","ITEM / ACTIVITY / ACTION","PROJECTED COST (In USD)","PROJECTED COST (In INR)","Est. Completion Date",{"$nulls":5},"Amt already Released (Agreement Signing Amt)","Requested by EE (1st Year)","As per DPR (Agreement Signing + \n1st Year of Project Implementation) in USD","As per DPR (Agreement Signing + \n1st Year of Project Implementation) in  INR"]
[{"$nulls":4},"Community mobilization and organization",null,null,0,0,"2018-12-18",{"$nulls":5},680000,866645,13333,799980]
[{"$nulls":4},"2.Capacity building for coastal protection and livelihoods","Trained stakeholders on\ncoastal protection and\nlivelihoods","Activity 2.2.2.Organizing training on IMFFS ",3333.3,199998,"2018-12-18",{"$nulls":5},300000,216710,5000,300000]
[{"$nulls":4},"Sub-Total",null,null,3333.3,199998,"2018-12-18"]
[{"$nulls":4},"3. Restoring mangroves for coastal protection","Restored and healthy\nmangrove replanted area\ncontributing to protection\nof coastal erosion sea\nlevel rise"," Activity 3.1.4.Preparing degraded mangroves for restoration",37916.5,2274990,"2018-12-18"]
[{"$nulls":6},"Activity 3.1.5.Planting mangrove saplings",3333.5,200010,"2018-12-18"]
[{"$nulls":6}," Activity 3.1.6.Monitoring and after care",3167,190020,"2018-12-18"]
[{"$nulls":6},"Activity 3.2.2.Establishing mangrove nursery",3200,192000,"2018-12-18"]
[{"$nulls":4},"Sub-Total",null,null,47617,2857020,"2018-12-18",{"$nulls":5},1195833,3095105,47583,2854980]
[{"$nulls":4},"Demonstration of mangrove dependent fishery","Demonstrated fishery\nrelated sustainable\nlivelihoods integrated with\nmangroves","Activity 4.1.2 a.Pond preparation ",130000,7800000,"2018-12-18"]
[{"$nulls":6},"Activity 4.1.2 b.Construction of sluice gates",14583,874980,"2018-12-18"]
[{"$nulls":6},"Activity 4.1.3.Raising mangrove plantation in the IMFFS farms",867,52020,"2018-12-18"]
[{"$nulls":6},"Activity 4.2.2.Stocking of fishes/shrimps/crabs",4166.5,249990,"2018-12-18"]
[{"$nulls":6},"Activity 4.2.3.Monitoring of IMFFS ponds",1800,108000,"2018-12-18",{"$nulls":5},5914167,10383750,209749.5,12584970]
[{"$nulls":6},"Activity 4.3.3.Stocking of fish crab juveniles ",5000,300000,"2018-12-18"]
[{"$nulls":6},"Activity 4.3.4b.Feed cost",3333,199980,"2018-12-18"]
[{"$nulls":4},"Sub-Total",null,null,159749.5,9584970,"2018-12-18"]
[{"$nulls":4},"5. Knowledge Management for improve coastal Protection","Prepared and published\nmaterials on ways to\nupscale coastal protection\nand livelihood systems in\nmangrove areas","Activity 5.1.1 b.Preparation of Brochure and Pamphlets ",1666.5,99990,"2018-12-18",{"$nulls":5},430000,541710,8334,500040]
[{"$nulls":6},"Activity 5.2.1.Documenting processes",5000,300000,"2018-12-18"]
[{"$nulls":6},"Activity 5.2.1b.Monitoring of Project activities along with   community",1666.5,99990,"2018-12-18"]
[{"$nulls":4},"Sub-Total",null,null,8333,499980]
[{"$nulls":4},"Project Execution cost",null,"Research fellows 2 nos.",8000,480000,"2018-12-18",{"$nulls":5},8520000,15103920,283999.5,17039970]
[{"$nulls":6},"Field Asst. - 1 no",2000,120000,"2018-12-18"]
[{"$nulls":6},"Travel",700,42000,"2018-12-18"]
[{"$nulls":6},"Contingency and other office expenses ",1400,84000,"2018-12-18",{"$nulls":8},{"$error":"#REF!"}]
[{"$nulls":6},"Monitoring and Evaluation",933,55980,"2018-12-18"]
[{"$nulls":4},"Sub-Total",null,null,13033,781980,"2018-12-18"]
[{"$nulls":6},"TOTAL",232065.8,13923948,{"$nulls":7},41355840]
[]
[null,null,"ACTUAL CO-FINANCING (If the MTR or TE have not been undertaken this reporting period, DO NOT report on actual co-financing.) "]
[null,null,"How much of the total co-financing as committed in the Project Document has actually been realized?",null,null,null,0]
[]
[null,null,"Estimated cumulative actual co-financing as verified during Mid-term Review (MTR) or Terminal Evaluation (TE). ",null,null,null,"NA"]
[null,null,"Add any comments on actual co-financing in particular any issues related to the realization of in-kind, grant, credits, loans, equity, non-grant instruments and other types of co-financing. (word limit=200)",null,null,null,"NA"]

{"sheet":"Risk Assesment","index":2,"n_rows":29,"n_cols":5,"rows_kept":29,"cut":false,"hidden":false,"merged":[[12,4,12,5],[13,4,13,5],[26,2,26,5],[17,2,17,5],[18,2,18,5],[15,4,15,5],[14,4,14,5],[20,2,23,5],[2,2,2,5],[3,1,3,5],[4,2,4,5],[6,2,6,3],[7,2,7,5],[8,4,8,5],[52,2,52,3],[52,4,52,5],[46,2,46,3],[46,4,46,5],[48,2,48,3],[48,4,48,5],[28,2,28,5],[27,2,27,3],[9,4,9,5],[10,4,10,5],[11,4,11,5],[42,4,42,5],[41,2,41,5],[42,2,42,3],[27,4,27,5],[19,4,19,5],[43,2,43,3],[53,2,53,3],[53,4,53,5],[49,2,49,3],[49,4,49,5],[39,2,39,3],[40,2,40,3],[43,4,43,5],[45,2,45,3],[51,2,51,3]],"flags":["formulas_cached_only"]}
[]
[]
[null,null,"RISK ASSESMENT"]
[]
[]
[]
[null,null,"IDENTIFIED RISKS"]
[null,null,"List all Risks identified in project preparation phase and what  steps are being taken to mitigate them"]
[null,null,"Identified Risk","Current Status","Steps Taken to Mitigate Risk"]
[null,null,"Failure in Community Mobilization to undertake the activities of mangrove-fishery - inertia against change","Low","Community was involved in mangrove restoration trainings and also in the mangrove restoration work which helped them earn livelihood and at the same time to own the given project.\n\nCommunity ownership has been promoted through\ndevelopment of the village committees."]
[null,null,"Not all necessary stakeholders may take part in the process with the capacity and commitment required. Afterwards, there can be resistance from some stakeholders in adopting the proposed measures. ","Low","All the major stakeholders viz., Community, Government departments and NGOs have been oriented about the project. The organisation of stakeholders workshop and the village level meetings have reduced the risk.  \n\nThe initiation of entry point activities in the respective villages have built the confidence and also rapport with the stakeholders. The government department i.e. the forest department has permitted to restore 200 ha. of the degraded area.  The forest department is also part of monitoring the work. MSSRF is also  periodically  updating  the progress and also submitting  the annual reports to the department."]
[null,null,"Financial miss-management ","Low","Periodic on-site and off-site Monitoring has been conducted for verification of expenditures both by EE and NIE"]
[null,null,"Slow progress of the work due to climatic unfavourable factors","Low","Though there was delay in getting permission for mangrove restoration from the forest department, the work has been completed sucessfully."]
[null,null,"Extreme weather events during the project lifetime undermine confidence of local communities in adaptation measures promoted by the project ","Medium","The IMFFS fishers and community-based institutions are sensitized on disaster risk reduction and on early warning communication operated by Government Agencies. This in turn is observed to improve the coping capacity of the local communities to overcome the disasters.\n\n"]
[null,null,"Limited capacity of partner organisations to deliver project outputs","Low","The EE has been implementing Joint Mangrove Management for the last 20 years.  It has been working with the local communities and implementing community centric projects with adequate training and capacity building initiatives. "]
[null,null,"Failure to create ownership of the project at the local level","Low","The project components were evolved after having series of consultations with the community members during the project planning stage. The adaptation strategies are simple,  increasing community ownership  and building in sustainability to project interventions."]
[]
[null,null,"Critical Risks Affecting Progress (Not identified at project design)"]
[null,null,"Identify Risks with a 50% or > likelihood of affecting progress of project"]
[null,null,"Identified Risk","Current Status","Steps Taken to Mitigate Risk"]
[null,null,"NA"]
[]
[]
[]
[]
[]
[null,null,"Risk Measures: Were there any risk mitigation measures employed during the current reporting period?  If so, were risks reduced?  If not, why were these risks not reduced?"]
[null,null,"Add any comments relevant to risk mitigation (word limit = 500)"]
[null,null,"NA"]

{"sheet":"Rating","index":3,"n_rows":57,"n_cols":9,"rows_kept":57,"cut":false,"hidden":false,"merged":[[2,2,2,8],[3,2,3,8],[20,2,20,7],[7,3,7,4],[8,3,8,4],[13,3,13,4],[11,3,11,4],[9,5,9,6],[10,5,10,6],[6,3,6,4],[29,3,29,4],[30,3,30,4],[31,3,31,4],[16,3,16,8],[30,5,30,6],[31,5,31,6],[26,3,26,4],[26,5,26,6],[27,5,27,6],[27,3,27,4],[32,3,32,4],[33,3,33,4],[28,3,28,4],[33,5,33,6],[12,5,12,6],[13,5,13,6],[29,5,29,6],[32,5,32,6],[28,5,28,6],[21,3,24,8],[6,5,6,6],[8,5,8,6],[7,5,7,6],[17,4,17,7],[18,4,18,7],[12,3,12,4],[9,3,9,4],[10,3,10,4],[11,5,11,6],[56,6,56,8],[51,6,51,8],[52,6,52,8],[53,6,53,8],[54,6,54,8],[55,6,55,8],[48,3,48,4],[48,5,48,8],[36,4,36,7],[37,4,37,7],[39,3,39,4],[39,5,39,6],[46,4,46,7],[45,4,45,7],[40,3,42,8]],"flags":["formulas_cached_only"]}
[]
[]
[null,null,"RATING ON IMPLEMENTATION PROGRESS "]
[null,null,"For rating definitions please see bottom of page."]
[]
[]
[null,null,null,"Progress on Key Milestones",null,"Expected Progress",null,"Progress to Date","Rating"]
[null,null,"Project Manager/Coordinator (MSSRF): ","Community mobilized and organized in 3 villages - Village level institutions formed in each village ",null,"Development of 3 Village level institutions ",null,"Gender balanced village level institutions formed in all the 3 project villages viz., in Sorlagondi, Nali and Basavanipalem.\n\nCommunity members including women participating in the VLI meetings, planning and implementation of project activities","HS"]
[null,null,null,"Orientation of the stakeholders in Climate change, Sea level rise and Adaptation strategies ",null,"Orientation of the 500 members of the community ",null,"All the 500 members of the community were Oriented in Climate Change, Sea Level Rise and Adaptation strategies \n\nLocal community members are channelized for the preparation of the annual micro plans for the optimal utilization of resources","S"]
[null,null,null,"200 stakeholders to be trained on mangrove restoration ",null,"120 members of the community would be trained in  mangrove restoration ",null,"64 members from Basavanipalem were trained in mangrove restoration activities such as mangrove nursery development, canal alignment, digging and planting of saplings. \n\nNumber of women, men and youth would be trained in designing\nand establishing IMFFS farms","MS"]
[null,null,null,"Replanted mangrove area close to 3 villages for future coastal protection",null,"90 ha of mangroves replanted",null,"Completed planting in 90 ha and another 110 ha is under progress ","MS"]
[null,null,null,"Established central mangrove nursery serving the needs of the 3  project villages",null,"1.3 lakhs saplings were to be raised in the central mangrove nursery",null,"About 130000 saplings were planted in the first year and another 50,000 saplings were raised  ","S"]
[null,null,null,"Two models of IMFFS demonstrated with the participation of local community and stakeholders",null,"25 ha area to be demonstrated under two models of IMFFS ",null,"The IMMFS model demonstrated in 15 ha with the participation of local community and stakeholders","S"]
[null,null,null,"Resource materials prepared for dissemination among various stakeholders",null,"Development of 4 pamphlets as resource material ",null,"3 pamphlets as resource material developed and published ","HS"]
[{"$nulls":7},"Overall Rating","S"]
[]
[null,null,null,"Please Provide the Name and Contact information of person(s) responsible for completing the Rating section"]
[null,null,null,"Name: ","R Ramasubramanian"]
[null,null,null,"Email: ","rramasubramani@rediffmail.com"]
[]
[null,null,"Please justify your rating.  Outline the positive and negative progress made by the project since it started.  Provide specific recommendations for next steps. . (word limit=500)"]
[null,null,null,"The activities are being implemented as per the plan. The community members were oriented on the climate change vulnerabilities.  Participatory vulnerability assessment was carried out and the coping capacity of the community is mapped. The mobilized community was organized into village level institution to plan, implement and monitor the project. During the first year the mangrove restoration work was not started due to delay in getting the permission from the forest department. Mangrove saplings (1.3 lakhs) were raised in the nursery. Field visits were organized to the degraded area to identify the suitability of the area to restore mangroves. Integrated Mangrove Fishery Farming (IMFFS) activity was completed in 15 ha. Three resource materials were prepared and given to the community."]
[]
[]
[]
[]
[null,null,null,"Progress on Key Milestones",null,"Expected Progress",null,"Progress to Date","Rating"]
[null,null,"Implementing Agency (NABARD)  ","Community mobilized and organized in 3 villages - Village level institutions formed in each village ",null,"Development of 3 Village level institutions ",null,"Gender balanced village level institutions formed in all the 3 project villages viz., in Sorlagondi, Nali and Basavanipalem.\n\n\n\n\n\n","S"]
[null,null,null,"Orientation of the stakeholders in Climate change, Sea level rise and Adaptation strategies ",null,"Orientation of the 500 members of the community ",null,"All the 500 members of the community were Oriented in Climate Change, Sea Level Rise and Adaptation strategies \n\n","S"]
[null,null,null,"200 stakeholders trained on mangrove restoration ",null,"120 members of the community would be trained in  mangrove restoration ",null,"64 community members were trained in mangrove restoration work during June 2017.\n\n","MS"]
[null,null,null,"Replanted mangrove area close to 3 villages for future coastal protection",null,"200 ha of mangroves replanted",null,"During 2017 about 90 ha of degraded mangroves have been restored and another 110 ha canal digging work has been completed.","S"]
[null,null,null,"Established central mangrove nursery serving 3 villages",null,"1.3 lakh saplings to be raised in the central mangrove nursery",null,"About 1.3 lakh saplings raised during last year was planted and another 50,000 saplings were raised. ","S"]
[null,null,null,"Two models of IMFFS demonstrated with the participation of local community and stakeholders",null,"25 ha area to be demonstrated under two models of IMFFS ",null,"The IMMFS model demonstrated in 15 ha with the participation of local community and stakeholders","S"]
[null,null,null,"Resource materials prepared for dissemination among various stakeholders",null,"Development of 4 pamphlets as resource material ",null,"3 pamphlets as resource material are developed and published ","S"]
[{"$nulls":7},"Overall Rating","S"]
[null,null,null,"Please Provide the Name and Contact information of person(s) responsible for completing the Rating section"]
[null,null,null,"Name: ","Kuldeep Singh "]
[null,null,null,"Email: ","kuldeep.singh@nabard.org"]
[]
[null,null,null,"Progress on Key Milestones",null,"Expected Progress",null,"Progress to Date","Rating"]
[null,null,"Other","NA"]
[]
[]
[{"$nulls":7},"Overall Rating"]
[null,null,null,"Please Provide the Name and Contact information of person(s) responsible for completing the Rating section"]
[null,null,null,"Name: "]
[null,null,null,"Email: "]
[]
[null,null,null,"Please justify your rating and address the following points:\n1. Indicate trends, both positive and negative, in achievement of outcomes as per the project indicators.  \n2.  Detail critical risks that have affected progress.  \n3.  Outline response to MTR undertaken this reporting period.  \n4.  Outline action plan to address projects with a rating of HU, U or MU. Please keep your input to 1200 words",null,"The village level meetings were organised regularly. Discussions were held with the community about the progress of the work and other project related activities in the meeting.  The training on mangrove restoration has helped the community to involve better in the mangrove restoration works. They also earned their livelihood in the the work. The mangrove plantation work was completed in 90 ha area and another 110 ha area is under progress. The survival of saplings in about 60% which is due to erosion of seedlings and also due to extreme summer months.  However, all the dead saplings will be replaced in September - October 2018. Multiple species is being planted to have rich biodiversity. "]
[]
[{"$nulls":6},"Rating Definitions"]
[{"$nulls":5},"Highly Satisfactory (HS)","Project actions/activities planned for current reporting period are progressing on track or exceeding expectations to achieve all  major outcomes/outputs for given reporting period, without major shortcomings. The project can be presented as “good practice”."]
[{"$nulls":5},"Satisfactory (S)","Project actions/activities planned for current reporting period  are progressing on track to achieve most of its major outcomes/outputs with only minor shortcomings."]
[{"$nulls":5},"Marginally Satisfactory (MS)","Project actions/activities planned for current reporting period  are progressing on track to achieve most   major relevant outcomes/outputs, but with either significant shortcomings or modest overall relevance. "]
[{"$nulls":5},"Marginally Unsatisfactory (MU)","Project actions/activities planned for current reporting period  are not progressing on track to achieve  major outcomes/outputs with major shortcomings or is expected to achieve only some of its major outcomes/outputs."]
[{"$nulls":5},"Unsatisfactory (U)","Project actions/activities planned for current reporting period  are not progressing on track to achieve most of its major outcomes/outputs."]
[{"$nulls":5},"Highly Unsatisfactory (U)","Project actions/activities planned for current reporting period  are not on track and shows that it is failing to achieve, and is not expected to achieve, any of its outcomes/outputs."]

{"sheet":"Project Indicators","index":4,"n_rows":24,"n_cols":9,"rows_kept":24,"cut":false,"hidden":false,"merged":[[6,4,6,5],[11,4,11,5],[2,2,5,2],[7,2,10,2],[11,2,13,2],[10,4,10,5],[7,4,7,5],[8,4,8,5],[2,3,2,8],[3,3,3,8],[4,3,4,8],[12,4,12,5],[5,3,5,4],[9,4,9,5],[24,7,24,8],[22,4,22,5],[16,4,16,5],[18,4,18,5],[13,4,13,5],[15,4,15,5],[23,4,23,5],[14,2,16,2],[17,2,20,2],[21,2,23,2],[14,4,14,5],[17,4,17,5],[19,4,19,5],[20,4,20,5],[21,4,21,5]],"flags":["formulas_cached_only"]}
[]
[]
[null,null,null,"Project Indicators"]
[null,null,null,"Please provide all indicators being tracked for the project as outlined in the project document"]
[]
[null,null,null,"Type of Indicator (indicators towards Objectives, Outcomes, etc.…)"]
[null,null,"Component(s)","Type of Indicator","Indicator",null,"Baseline","Progress since Inception","Target for Project End"]
[null,null,"Component 1: Community mobilization and organization","Outcome 1: Improved community organization to undertake climate change adaptation measures","Number of men and women in 3 villages trained in participatory approaches and micro planning and implementing project activities. Number of stakeholders participating in the VLI meetings, planning and implementation of activities",null,"Very limited awareness about climate change and its impact and possible adaptive measures to reduce vulnerability in the project villages","Almost 40% of the community are aware of Climate Change issues in the coastal area. 15 members of the community directly benefit from the IMFFS ponds","At least 60% people (of which nearly 50% of women) living in the project villages directly benefited from reduced vulnerability to climate change related impacts"]
[null,null,null,"Output 1.1: Gender balanced village level institutions formed in Sorlagondi, Nali and Basavanipalem villages","Frequency of VLI meetings organized with quorum ",null,"No VLI institutions in place","3 gender balanced VLI institutions formed for 3 participating villages","3 gender balanced VLI institutions formed for 3 participating villages"]
[null,null,null,"Output 1.2: 1,500 people oriented to Climate Change (CC), Sea Level Rise (SLR) and adaptive capacity concepts and measures involving mangroves","Number of orientation meetings organized in the three villages",null,"No orientation on CC, SLR and adaptive capacity","300 members of the community were oriented in Climate Change concepts ","1,500 people including 50% women would be orientated on CC, SLR and adaptive capacity"]
[null,null,null,"Output 1.3: Annual micro plans prepared for optimal utilization of resources ","Number of micro plans with detailed activities",null,"No micro plan is available","3 village level annual micro plans are available","12 micro plans (3 annual micro plans for each village for 4 years) would be developed"]
[null,null,"Component 2: Capacity building for coastal protection and livelihoods","Outcome 2: Trained stakeholders on coastal protection and livelihoods","Number of women, men and youth trained on mangrove restoration technique\n\nNumber of women, men and youth trained in designing and establishing IMFFS farms\n\nNumber of members of local self-government, government institutions and local NGOs trained on mangrove restoration and IMFFS establishment\n",null,"No Community members  trained in mangrove restoration and IMFFS in 2 villages  (Nali and Basavanipalayam)                                                                                        \n\n5% of the stakeholder groups know mangrove restoration techniques","64 community members were trained in mangrove restoration. Other stakeholders will be trained during this phase.","At least 50% marginalized and vulnerable members of the community and youth trained.\n\n At least 20% members of stakeholders organizations working in coastal resource management and improving adaptive capacity of community to climate change in the project region trained."]
[null,null,null,"Output 2.1:\n 200 stakeholders trained on mangrove restoration ","Number of training programmes organized with equal women and men trainees",null,"0 Nos.of  community members trained in mangrove restoration","64 members were trained in mangrove restoration ","200 members would be trained on mangrove restoration"]
[null,null,null,"Output 2.2: 50 farmers trained in IMFSS","Number of training organized with equal women and men trainees",null,"0 Nos. of  trained farmers on IMFFs","Beneficiaries have been identified and capacity building trainings are in progress","50 farmers including at least 20 women trained in IMFFS"]
[null,null,"Component 3: Restoration of mangrove areas for coastal protection","Outcome 3: Restored and healthy mangrove replanted area, contributing to protection of coastal erosion and sea -level rise ","VLI plan for mangrove restoration and protection in each of 3 villages\n\nMangrove restored with 300,000 mangrove saplings\n\nConditions of mangrove plantation:  80% survival of planted saplings and growth rate.\n",null,"0 community plan is available for mangrove management\n\n800 ha of degraded mangroves present nearby project villages\n","Restoration of degraded mangrove forest has commenced","Mangrove restoration would be conducted  in 200 ha area"]
[null,null,null,"Output 3.1: Replanted mangrove area close to 3 villages for future coastal protection","Area of mangrove restored with multispecies of mangroves",null,"800 ha of degraded mangrove near project villages was restored under  certain other  project implemented by the executing entity","90 ha of mangroves were restored and another 110 ha is under progress","Mangrove replantation would be conducted in 200 ha area."]
[null,null,null,"Output 3.2:Established central mangrove nursery serving 3 villages","Number of saplings of different mangrove species raised",null,"No nursery present ","1,30,000 saplings were raised during 2017 and another 50,000 during 2017-18 for planting ","One centralized nursery. About 300,000 saplings  would be raised."]
[null,null,"Component 4: Demonstration of Integrated mangrove based fishery livelihood","Outcome 4: \nDemonstrated fishery related sustainable livelihoods integrated with mangroves \n","Village Level Institution (VLI) plan for IMFFS establishment  and management\n\nReduction in input costs of shrimp and fish farming compared to conventional aqua farms\n",null,"100 ha abandoned shrimp farms present near project villages","15 ha area of IMFFS  and another 10 ha area under progress                         0 cages for fish culture","IMFFS established in 50 ha in abandoned shrimp farms by participating farmers with a minimum of 600 mangroves plants per ha and 300 kg of prawn per year per ha of IMFFS"]
[null,null,null,"Output 4.1: Two models of IMFFS demonstrated with the participation of local community and stakeholders","Number of IMFFS ponds",null,"No IMFFS farm","Demonstration of IMFFS model for 15 ha area and another 10 ha is under progress","Demonstration of IMFFS model for 50 ha area"]
[null,null,null,"Output 4.2: \nTwo culture of fish or prawn or both undertaken in the IMFFS farms per year\n","Number of culture by IMFFS farmers",null,"No culture (Abandoned farms)","First culture completed. Crabs were cultivated and the same were harvested ","100 culture in 50 ha of IMFFS farms per year"]
[null,null,null,"Output 4.3:\nCage and pen culture established for culture of crabs, fish, clams and cockles\n","Number of cages and pens established for culture of fishes",null,"No cages ","Preliminary assessment is made. Community members and MSSRF trained in cage culture ","10 cages would be established for culture of fishes"]
[null,null,"Component 5: Knowledge Management for Improved Coastal Protection","Prepared and published material on ways to up-scale coastal protection and livelihood systems in mangrove areas","Awareness materials on CC, SLR, Vulnerability and Adaptive capacity prepared in local language and distributed to community and other stakeholders\n\nNumber of meetings and workshops held\n\nNumber of brochures and pamphlets prepared and distributed\n",null,"No awareness materials were available ","Three brochures prepared and distributed to the community living in 3 villages ","4 brochures and 2 workshops (one district level and the other at national level)"]
[null,null,null,"Output 5.1: Resource materials prepared for dissemination among various stakeholders","No of pamphlets distributed to various stakeholders",null," No pamphlets available ","3 brochures were distributed to the stakeholders","4 brochures would be  distributed to the stakeholders"]
[null,null,null,"Output 5.2:\nStakeholders brought together and knowledge on CC, SLR, Vulnerability and measures to improve adaptive capacity shared\n","Number of workshops organised \n\nNumber of stakeholders participated \n",null,"N0 workshops organised on CC, Sea Level Rise  and vulnerability to CC adaptive capacity","Planned in the last year","  2 workshops - one district level and the other at national level"]

{"sheet":"Lessons Learned","index":5,"n_rows":28,"n_cols":4,"rows_kept":28,"cut":false,"hidden":false,"merged":[[23,2,23,3],[2,2,2,3],[11,2,11,3],[13,2,13,3],[16,2,16,3],[19,2,19,3]],"flags":["formulas_cached_only"]}
[]
[]
[null,null,"QUALITATIVE MEASURES and LESSONS LEARNED"]
[]
[null,null,"Please complete the following section every reporting period"]
[null,null,"Implementation and Adaptive Management","Response"]
[null,null,"What implementation issues/lessons, either positive or negative, affected progress?","Positive factor: One of the Climate Change adaptation strategy, viz., mangrove conservation and management is not new to the local community. The community are experiencing coastal erosion and they want mangroves to be planted to arrest erosion. Communities are also aware that the mangrove restoration activities would increase the fishery production. "]
[null,null,"Were there any delays in implementation?  If so, include any causes of delays. What measures have been taken to reduce delays?","Nil for the given PPR reporting period. \n\nDuring the PPR 1 reporing period (  23/06/15 - 30/04/17), The mangrove restoration work was delayed due to delay in getting permission from the forest department. Request letters and the required documents were submitted to get permission from the Forest Department. Based on the above documents, the department has allotted permission to bring 200 ha of project area under mangrove plantation on 08 March 2017."]
[null,null,"Describe any changes undertaken to improve results on the ground or any changes made to project outputs (i.e. changes to project design)","No changes have been made."]
[null,null,"How have gender considerations been taken into consideration during the reporting period? What have been the lessons learned as a consequence of inclusion of such considerations on project performance or impacts?","Yes. M. S. Swaminathan Research Foundation right from the beginning had involved women and other marginalized communities in all its projects.  In all the project villages women are part of the village level institutions and equal opportunity has  been given to them in general body and executive body. Drinking water concern identified by women during PRA was addressed in 2 villages as the entry point activity. Large number of women were involved in mangrove nursery development and its management. "]
[]
[null,null,"Please complete the following section at mid-term and project completion"]
[null,null,"Lessons for Adaptation","Response"]
[null,null,"Climate Resilience Measures"]
[null,null,"What have been the lessons learned, both positive and negative, in implementing climate adaptation measures that would be relevant to the design and implementation of future projects/programmes for enhanced resilience to climate change?","In mangrove restoration activity, mangrove saplings were raised in the nursery close to the sea.  The saplings have better adaptaion as they were grown in  the same saline environment and become accustomed to saltwater environments thereby increasing their overall survival rate. The local community realised that the mangroves will mitigate the sea shore erosion and also help in protecting the village from cyclones as well as sea level rise. \n"]
[null,null,"What is the potential for the climate resilience measures undertaken by the project/programme to be replicated and scaled up both within and outside the project area?","Participatory mangrove restoration through involvement of local communities members, forest departments and other stakeholders helps greatly in achieveing the project goals."]
[null,null,"Concrete Adaptation Interventions"]
[null,null,"What have been the lessons learned, both positive and negative, in implementing concrete adaptation interventions that would be relevant to the design and implementation of future projects/programmes implementing concrete adaptation interventions?","Community trainings in mangrove restoration have been held to share techniques for seed collection and storage, canal digging, and planting, managing and monitoring mangroves thereby contributing immensely towards achievemment of project objectives."]
[null,null,"What is the potential for the concrete adaptation interventions undertaken by the project/programme to be replicated and scaled up both within and outside the project area?","Raising and planting mangroves helps to reestablish the natural systems  to improve protection from floods and erosion."]
[null,null,"Community/National Impact"]
[null,null,"What would you consider to be the most successful aspects for the target communities?","Successful participatory resources management with active involvememt of Women has been serving as a model to manage the large area of unprotected mangroves located along the other coastal areas of the Krishna district."]
[null,null,"What measures are/have been put in place to ensure sustainability of the project/program results?","The participating farmers in mangrove restoration have given an undertaking indicating that they would carry on aqua farming in the IMFFS farm and protect the mangrove plantations in the IMFFS beyond the project period thereby reflecting the project sustainability in the future. "]
[null,null,"What measures are being/could have been put in place to improve project/program results?","During the course of the project, location specific management protocol has been developed jointly by the project aqua farmers, MSSRF, and National Centre for Sustainable Aquaculture, Government of India to improve the project outcomes."]
[null,null,"Knowledge Management "]
[null,null,"How has existing information/data/knowledge been used to inform project development and implementation? What kinds of information/data/knowledge were used?","The information on sea level rise and role of mangroves and IMFFS in increasing community adaptive capacity towards Climate Change."]
[null,null,"If learning objectives have been established, have they been met? Please describe.","Yes. Learning objectives are met through organization of farmers to farmer learning programme under the project to provide exposure to IMFFS to other aqua farmers in the region of project implementation."]
[null,null,"Describe any difficulties there have been in  accessing or retrieving existing information (data or knowledge) that is relevant to the project. Please provide suggestions for improving access to the relevant data.","NA"]
[null,null,"Has the identification of learning objectives contributed to the outcomes of the project? In what ways have they contributed?","Yes.  Learning among aqua farmers has helped in replication of IMFFS through Fisherman Associations, Self Help Groups (SHGs), Individuals, etc. "]

{"sheet":"Results Tracker","index":6,"n_rows":320,"n_cols":19,"rows_kept":320,"cut":false,"hidden":false,"merged":[[9,1,9,2],[18,3,18,6],[18,7,18,10],[18,11,18,14],[18,15,18,18],[19,1,22,1],[19,2,22,2],[24,3,24,6],[24,7,24,10],[24,11,24,14],[24,15,24,18],[25,11,25,12],[25,15,25,16],[26,17,27,17],[26,18,27,18],[28,1,37,1],[28,2,37,2],[26,10,27,10],[26,13,27,13],[26,14,27,14],[26,5,27,5],[26,6,27,6],[26,9,27,9],[39,7,40,7],[39,8,40,8],[45,3,46,3],[45,4,46,4],[45,7,46,7],[45,8,46,8],[25,1,27,1],[25,2,27,2],[25,3,25,4],[25,7,25,8],[39,11,40,11],[39,12,40,12],[38,1,49,1],[38,2,49,2],[39,3,40,3],[39,4,40,4],[39,15,40,15],[39,16,40,16],[42,3,43,3],[42,4,43,4],[42,7,43,7],[42,8,43,8],[42,11,43,11],[42,12,43,12],[42,15,43,15],[42,16,43,16],[45,11,46,11],[45,12,46,12],[45,15,46,15],[45,16,46,16],[48,15,49,15],[48,16,49,16],[51,3,51,6],[51,7,51,10],[51,11,51,14],[51,15,51,18],[48,3,49,3],[48,4,49,4],[48,7,49,7],[48,8,49,8],[48,11,49,11],[48,12,49,12],[53,13,54,13],[53,14,54,14],[53,17,54,17],[53,18,54,18],[55,1,58,1],[55,2,56,2],[55,5,55,6],[55,9,55,10],[55,13,55,14],[55,17,55,18],[52,1,54,1],[52,2,54,2],[52,3,52,4],[52,7,52,8],[52,11,52,12],[52,15,52,16],[53,5,54,5],[53,6,54,6],[53,9,54,9],[53,10,54,10],[56,5,56,6],[56,9,56,10],[56,13,56,14],[56,17,56,18],[61,3,61,4],[61,5,61,6],[61,7,61,8],[61,9,61,10],[57,2,58,2],[60,3,60,6],[60,7,60,10],[60,11,60,14],[60,15,60,18],[61,11,61,12],[61,13,61,14],[61,15,61,16],[61,17,61,18],[64,13,64,14],[64,17,64,18],[66,3,66,6],[66,7,66,10],[66,11,66,14],[66,15,66,18],[62,15,62,16],[62,17,62,18],[63,1,64,1],[63,2,64,2],[63,5,63,6],[63,9,63,10],[63,13,63,14],[63,17,63,18],[64,5,64,6],[64,9,64,10],[61,1,62,1],[61,2,62,2],[62,3,62,4],[62,5,62,6],[62,7,62,8],[62,9,62,10],[62,11,62,12],[62,13,62,14],[69,9,69,10],[69,13,69,14],[69,17,69,18],[70,5,70,6],[70,9,70,10],[70,13,70,14],[70,17,70,18],[67,17,67,18],[67,1,75,1],[67,2,68,2],[67,5,67,6],[68,5,68,6],[69,2,75,2],[69,5,69,6],[71,5,71,6],[73,5,73,6],[75,5,75,6],[73,9,73,10],[73,13,73,14],[73,17,73,18],[74,5,74,6],[74,9,74,10],[74,13,74,14],[74,17,74,18],[71,9,71,10],[71,13,71,14],[71,17,71,18],[72,5,72,6],[72,9,72,10],[72,13,72,14],[72,17,72,18],[75,9,75,10],[75,13,75,14],[75,17,75,18],[79,8,79,9],[79,12,79,13],[79,16,79,17],[78,16,78,17],[80,4,80,5],[80,8,80,9],[80,12,80,13],[80,16,80,17],[77,8,77,9],[77,12,77,13],[77,16,77,17],[78,4,78,5],[78,8,78,9],[78,12,78,13],[84,15,84,18],[85,1,86,1],[85,2,86,2],[85,3,85,4],[85,7,85,8],[85,11,85,12],[85,15,85,16],[86,3,86,4],[84,7,84,10],[84,11,84,14],[81,12,81,13],[81,16,81,17],[82,4,82,5],[82,8,82,9],[82,12,82,13],[82,16,82,17],[76,1,82,1],[76,2,82,2],[76,4,76,5],[76,8,76,9],[76,12,76,13],[76,16,76,17],[77,4,77,5],[79,4,79,5],[81,4,81,5],[81,8,81,9],[87,1,98,1],[87,2,98,2],[88,3,89,3],[88,4,89,4],[88,5,89,5],[84,3,84,6],[88,6,89,6],[94,3,95,3],[94,4,95,4],[94,5,95,5],[88,18,89,18],[91,3,92,3],[91,4,92,4],[91,5,92,5],[91,6,92,6],[91,7,92,7],[91,8,92,8],[91,9,92,9],[91,10,92,10],[91,11,92,11],[88,12,89,12],[88,13,89,13],[88,14,89,14],[88,15,89,15],[88,16,89,16],[88,17,89,17],[88,7,89,7],[88,8,89,8],[88,9,89,9],[88,10,89,10],[88,11,89,11],[91,18,92,18],[91,12,92,12],[91,13,92,13],[91,14,92,14],[91,15,92,15],[94,6,95,6],[94,7,95,7],[94,8,95,8],[94,9,95,9],[94,10,95,10],[94,11,95,11],[91,16,92,16],[91,17,92,17],[94,18,95,18],[94,12,95,12],[101,1,110,1],[101,2,102,2],[101,5,101,6],[101,9,101,10],[101,13,101,14],[97,12,98,12],[97,14,98,14],[97,15,98,15],[102,5,102,6],[102,9,102,10],[102,13,102,14],[97,9,98,9],[97,10,98,10],[103,2,110,2],[100,3,100,6],[100,7,100,10],[100,11,100,14],[97,3,98,3],[97,4,98,4],[97,5,98,5],[97,6,98,6],[97,7,98,7],[97,8,98,8],[122,15,122,18],[118,12,118,13],[119,12,119,13],[120,12,120,13],[115,17,115,18],[116,17,116,18],[117,17,117,18],[118,17,118,18],[119,17,119,18],[123,7,123,10],[123,11,123,14],[111,1,120,1],[111,2,112,2],[113,2,120,2],[113,4,113,5],[114,4,114,5],[115,4,115,5],[116,4,116,5],[122,11,122,14],[115,8,115,9],[116,8,116,9],[117,8,117,9],[118,8,118,9],[119,8,119,9],[120,17,120,18],[120,8,120,9],[115,12,115,13],[116,12,116,13],[117,12,117,13],[120,4,120,5],[122,3,122,6],[122,7,122,10],[117,4,117,5],[118,4,118,5],[119,4,119,5],[1,2,1,6],[5,1,5,6],[6,1,6,6],[7,1,7,6],[2,2,2,6],[128,12,128,13],[67,9,67,10],[68,9,68,10],[67,13,67,14],[68,13,68,14],[128,16,128,17],[127,2,128,2],[127,4,127,5],[127,8,127,9],[127,12,127,13],[127,16,127,17],[128,4,128,5],[128,8,128,9],[123,15,123,18],[124,3,124,6],[124,7,124,10],[124,11,124,14],[124,15,124,18],[125,1,128,1],[125,2,126,2],[123,1,124,1],[123,2,124,2],[123,3,123,6],[68,17,68,18],[113,8,113,9],[114,8,114,9],[113,12,113,13],[114,12,114,13],[114,17,114,18],[113,17,113,18],[100,15,100,18],[97,16,98,16],[97,17,98,17],[102,17,102,18],[97,18,98,18],[97,11,98,11],[94,13,95,13],[94,14,95,14],[94,15,95,15],[94,16,95,16],[94,17,95,17],[101,17,101,18],[97,13,98,13]],"flags":["formulas_cached_only"]}
[]
[]
[null,null,"Results Tracker for Adaptation Fund (AF)  Projects    "]
[]
[]
[null,"Goal: Assist developing-country Parties to the Kyoto Protocol that are particularly vulnerable to the adverse effects of climate change in meeting the costs of concrete adaptation projects and programmes in order to implement climate-resilient measures. \nImpact: Increased resiliency at the community, national, and regional levels to climate variability and change. "]
[null,"Important: Please read the following guidance document (also posted on the Adaptation Fund website) before entering your data "]
[null,"Link: http://www.adaptation-fund.org/sites/default/files/Results%20Framework%20and%20Baseline%20Guidance%20final.pdf"]
[]
[null,"Adaptation Fund Strategic Results Framework"]
[]
[null,"Project ID","IND/NIE/Coastal/2014/1"]
[null,"Implementing Entity","National Bank for Agriculture and Rural Development (NABARD) "]
[null,"Type of implementing entity","NIE"]
[null,"Country","India"]
[null,"Region","Asia-Pacific"]
[null,"Sector","Coastal Management"]
[]
[null,null,null,"Baseline information",null,null,null,"Target performance at completion",null,null,null,"Performance at mid-term",null,null,null,"Performance at completion"]
[null,"Impact: Increased resiliency at the community, national, and regional levels to climate variability and change","Core Indicator: No. of beneficiaries",null,"Total (direct + indirect beneficiaries)","Direct beneficiaries supported by the project","Indirect beneficiaries supported by the project",null,"Total (direct + indirect beneficiaries)","Direct beneficiaries supported by the project","Indirect beneficiaries supported by the project",null,"Total (direct + indirect beneficiaries)","Direct beneficiaries supported by the project","Indirect beneficiaries supported by the project",null,"Total (direct + indirect beneficiaries)","Direct beneficiaries supported by the project","Indirect beneficiaries supported by the project"]
[null,null,null,"Total",0,0,0,"Total",1000,800,200,"Total",800,600,200,"Total"]
[null,null,null,"% of female beneficiaries",0,0,0,"% of female beneficiaries",0.5,0.4,0.1,"% of female beneficiaries",0.3,0.25,0.1,"% of female beneficiaries"]
[null,null,null,"% of Youth beneficiaries",0,0,0,"% of Youth beneficiaries",0.15,0.1,0.05,"% of Youth beneficiaries",0.1,0.08,0.02,"% of Youth beneficiaries"]
[]
[null,null,null,"Baseline information",null,null,null,"Target performance at completion",null,null,null,"Performance at mid-term",null,null,null,"Performance at completion"]
[null,"Outcome 1: Reduced exposure to climate-related hazards and threats","Indicator 1: Relevant threat and hazard information generated and disseminated to stakeholders on a timely basis","Number of targeted stakeholders",null,"Hazards information generated and disseminated","Overall effectiveness","Number of targeted stakeholders",null,"Hazards information generated and disseminated","Overall effectiveness","Number of targeted stakeholders",null,"Hazards information generated and disseminated","Overall effectiveness","Number of targeted stakeholders",null,"Hazards information generated and disseminated","Overall effectiveness"]
[null,null,null,"Total",0,"Salinization","3: Moderately effective","Total",500,"Salinization","4: Effective","Total",300,"Salinization","4: Effective"]
[null,null,null,"% of female targeted",0,null,null,"% of female targeted",0.5,null,null,"% of female targeted",0.3]
[null,"Output 1.1 Risk and vulnerability assessments conducted and updated","Indicator 1.1: No. of projects/programmes that conduct and update risk and vulnerability assessments","No. of projects/programmes that conduct and update risk and vulnerability assessments","Sector","Scale","Status","No. of projects/programmes that conduct and update risk and vulnerability assessments","Sector","Scale","Status","No. of projects/programmes that conduct and update risk and vulnerability assessments","Sector","Scale","Status","No. of projects/programmes that conduct and update risk and vulnerability assessments","Sector","Scale","Status"]
[null,null,null,1,"Disaster risk reduction","Local","3: Risk and vulnerability assessments completed or updated",1,"Disaster risk reduction","Local","3: Risk and vulnerability assessments completed or updated",1,"Disaster risk reduction","Local","3: Risk and vulnerability assessments completed or updated"]
[null,null,null,"No. of projects/programmes that conduct and update risk and vulnerability assessments","Sector","Scale","Status","No. of projects/programmes that conduct and update risk and vulnerability assessments","Sector","Scale","Status","No. of projects/programmes that conduct and update risk and vulnerability assessments","Sector","Scale","Status","No. of projects/programmes that conduct and update risk and vulnerability assessments","Sector","Scale","Status"]
[]
[null,null,null,"No. of projects/programmes that conduct and update risk and vulnerability assessments","Sector","Scale","Status","No. of projects/programmes that conduct and update risk and vulnerability assessments","Sector","Scale","Status","No. of projects/programmes that conduct and update risk and vulnerability assessments","Sector","Scale","Status","No. of projects/programmes that conduct and update risk and vulnerability assessments","Sector","Scale","Status"]
[]
[null,null,null,"No. of projects/programmes that conduct and update risk and vulnerability assessments","Sector","Scale","Status","No. of projects/programmes that conduct and update risk and vulnerability assessments","Sector","Scale","Status","No. of projects/programmes that conduct and update risk and vulnerability assessments","Sector","Scale","Status","No. of projects/programmes that conduct and update risk and vulnerability assessments","Sector","Scale","Status"]
[]
[null,null,null,"No. of projects/programmes that conduct and update risk and vulnerability assessments","Sector","Scale","Status","No. of projects/programmes that conduct and update risk and vulnerability assessments","Sector","Scale","Status","No. of projects/programmes that conduct and update risk and vulnerability assessments","Sector","Scale","Status","No. of projects/programmes that conduct and update risk and vulnerability assessments","Sector","Scale","Status"]
[]
[null,"Output 1.2 Targeted population groups covered by adequate risk reduction systems","Core Indicator 1.2: No. of Early Warning Systems","No. of adopted Early Warning Systems","Category targeted","Hazard","Storm surge","No. of adopted Early Warning Systems","Category targeted","Hazard","Storm surge","No. of adopted Early Warning Systems","Category targeted","Hazard",null,"No. of adopted Early Warning Systems","Category targeted","Hazard"]
[null,null,null,1,"3: Dissemination and communication","Geographical coverage","Local",1,"3: Dissemination and communication","Geographical coverage","Local",1,"3: Dissemination and communication","Geographical coverage","Local",null,null,"Geographical coverage"]
[{"$nulls":5},"Number of municipalities",0,null,null,"Number of municipalities",0,null,null,"Number of municipalities",0,null,null,"Number of municipalities"]
[null,null,null,"No. of adopted Early Warning Systems","Category targeted","Hazard","Storm surge","No. of adopted Early Warning Systems","Category targeted","Hazard","Storm surge","No. of adopted Early Warning Systems","Category targeted","Hazard","Storm surge","No. of adopted Early Warning Systems","Category targeted","Hazard"]
[null,null,null,2,"4: Response capability","Geographical coverage","Local",2,"4: Response capability","Geographical coverage","Local",1,"4: Response capability","Geographical coverage","Local",null,null,"Geographical coverage"]
[{"$nulls":5},"Number of municipalities",0,null,null,"Number of municipalities",0,null,null,"Number of municipalities",0,null,null,"Number of municipalities"]
[null,null,null,"No. of adopted Early Warning Systems","Category targeted","Hazard",null,"No. of adopted Early Warning Systems","Category targeted","Hazard",null,"No. of adopted Early Warning Systems","Category targeted","Hazard",null,"No. of adopted Early Warning Systems","Category targeted","Hazard"]
[{"$nulls":5},"Geographical coverage",null,null,null,"Geographical coverage",null,null,null,"Geographical coverage",null,null,null,"Geographical coverage"]
[{"$nulls":5},"Number of municipalities",null,null,null,"Number of municipalities",null,null,null,"Number of municipalities",null,null,null,"Number of municipalities"]
[null,null,null,"No. of adopted Early Warning Systems","Category targeted","Hazard",null,"No. of adopted Early Warning Systems","Category targeted","Hazard",null,"No. of adopted Early Warning Systems","Category targeted","Hazard",null,"No. of adopted Early Warning Systems","Category targeted","Hazard"]
[{"$nulls":5},"Geographical coverage",null,null,null,"Geographical coverage",null,null,null,"Geographical coverage",null,null,null,"Geographical coverage"]
[{"$nulls":5},"Number of municipalities",null,null,null,"Number of municipalities",null,null,null,"Number of municipalities",null,null,null,"Number of municipalities"]
[]
[null,null,null,"Baseline information",null,null,null,"Target performance at completion",null,null,null,"Performance at mid-term",null,null,null,"Performance at completion"]
[null,"Outcome 2: Strengthened institutional capacity to reduce risks associated with climate-induced socioeconomic and environmental losses","Indicator 2: Capacity of staff to respond to, and mitigate impacts of, climate-related events from targeted institutions increased","Number of staff targeted",null,"Sector","Capacity level","Number of staff targeted",null,"Sector","Capacity level","Number of staff targeted",null,"Sector","Capacity level","Number of staff targeted",null,"Sector","Capacity level"]
[null,null,null,"Total",0,"Coastal management","2: Low capacity","Total",20,"Coastal management","4: High capacity","Total",15,"Coastal management","4: High capacity","Total"]
[null,null,null,"% of female targeted",0,null,null,"% of female targeted",0.3,null,null,"% of female targeted",0.3,null,null,"% of female targeted"]
[null,"Output 2.1 Strengthened capacity of national and sub-national centres and networks to respond rapidly to extreme weather events","Indicator 2.1.1: No. of staff trained to respond to, and mitigate impacts of, climate-related events","Total staff trained","% of female staff trained","Type",null,"Total staff trained","% of female staff trained","Type",null,"Total staff trained","% of female staff trained","Type",null,"Total staff trained","% of female staff trained","Type"]
[null,null,null,0,0,"Public",null,20,0.3,null,null,15,0.3,"Public"]
[null,null,"Indicator 2.1.2: No. of targeted institutions with increased capacity to minimize exposure to climate variability risks","Type","Scale","Sector","Capacity level","Type","Scale","Sector","Capacity level","Type","Scale","Sector","Capacity level","Type","Scale","Sector","Capacity level"]
[null,null,null,"Public","Local","Coastal management","2: Low capacity","Public","Local","Coastal management","4: High capacity","Public","Local","Coastal management","3: Medium capacity"]
[]
[null,null,null,"Baseline information",null,null,null,"Target performance at completion",null,null,null,"Performance at mid-term",null,null,null,"Performance at completion"]
[null,"Outcome 3: Strengthened awareness and ownership of adaptation and climate risk reduction processes","Indicator 3.1: Increase in application of appropriate adaptation responses","Percentage of targeted population applying adaptation measures",null,"Sector",null,"Percentage of targeted population applying adaptation measures",null,"Sector",null,"Percentage of targeted population applying adaptation measures",null,"Sector",null,"Percentage of targeted population applying adaptation measures",null,"Sector"]
[null,null,null,0,null,"Coastal management",null,0.5,null,"Coastal management",null,0.4,null,"Coastal management"]
[null,"Output 3: Targeted population groups participating in adaptation and risk reduction awareness activities ","Indicator 3.1.1: Percentage of targeted population awareness of predicted adverse impacts of climate change, and of appropriate responses","No. of targeted beneficiaries","% of female participants targeted","Level of awareness",null,"No. of targeted beneficiaries","% of female participants targeted","Level of awareness",null,"No. of targeted beneficiaries","% of female participants targeted","Level of awareness",null,"No. of targeted beneficiaries","% of female participants targeted","Level of awareness"]
[null,null,null,0,0,"1: Aware of neither",null,50,0.4,"4: Mostly aware",null,15,0.5,"4: Mostly aware"]
[]
[null,null,null,"Baseline information",null,null,null,"Target performance at completion",null,null,null,"Performance at mid-term",null,null,null,"Target performance at completion"]
[null,"Outcome 4: Increased adaptive capacity within relevant development sector services and infrastructure assets","Indicator 4.1: Increased responsiveness of development sector services to evolving needs from changing and variable climate","Project/programme sector","Geographical scale","Response level",null,"Project/programme sector","Geographical scale","Response level",null,"Project/programme sector","Geographical scale","Response level",null,"Project/programme sector","Geographical scale","Response level"]
[null,null,null,"Coastal management","Local","2: Partially responsive (Lacks most elements)",null,"Coastal management","Local","4: Mostly responsive (Most defined elements)",null,"Coastal management","Local","4: Mostly responsive (Most defined elements)"]
[null,null,"Core Indicator 4.2: Assets produced, developed, improved or strengthened","Sector","Targeted asset","Changes in asset (quantitative or qualitative)",null,"Sector","Targeted asset","Changes in asset (quantitative or qualitative)",null,"Sector","Targeted asset","Changes in asset (quantitative or qualitative)",null,"Sector","Targeted asset","Changes in asset (quantitative or qualitative)"]
[null,null,null,"Coastal management","2: Physical asset (produced/improved/strengthened)","2: Somewhat improved",null,"Coastal management","2: Physical asset (produced/improved/strengthened)","4: Mostly Improved",null,"Coastal management","2: Physical asset (produced/improved/strengthened)","3: Moderately improved"]
[null,null,null,"Disaster risk reduction","2: Physical asset (produced/improved/strengthened)","2: Somewhat improved",null,"Disaster risk reduction","2: Physical asset (produced/improved/strengthened)","4: Mostly Improved",null,"Disaster risk reduction","2: Physical asset (produced/improved/strengthened)","3: Moderately improved"]
[]
[]
[]
[]
[null,"Output 4: Vulnerable development sector services and infrastructure assets strengthened in response to climate change impacts, including variability","Indicator 4.1.1: No. and type of development sector services to respond to new conditions resulting from climate variability and change","Number of services","Type",null,"Sector","Number of services","Type",null,"Sector","Number of services","Type",null,"Sector","Number of services","Type",null,"Sector"]
[null,null,null,3,"Community",null,"Coastal management",3,"Community",null,"Coastal management",2,"Community",null,"Coastal management"]
[]
[]
[]
[]
[]
[]
[null,null,null,"Baseline information",null,null,null,"Baseline information",null,null,null,"Performance at mid-term",null,null,null,"Target performance at completion"]
[null,"Outcome 5: Increased ecosystem resilience in response to climate change and variability-induced stress","Indicator 5: Ecosystem services and natural resource assets maintained or improved under climate change and variability-induced stress","Natural resource improvement level",null,"Sector","Type","Natural resource improvement level",null,"Sector","Type","Natural resource improvement level",null,"Sector","Type","Natural resource improvement level",null,"Sector","Type"]
[null,null,null,"2: Partially effective",null,"Disaster risk reduction","biological assets","4: Effective",null,"Disaster risk reduction","biological assets","4: Effective",null,"Disaster risk reduction","biological assets"]
[null,"Output 5: Vulnerable ecosystem services and natural resource assets strengthened in response to climate change impacts, including variability","Core Indicator 5.1: Natural Assets protected or rehabilitated","Natural asset or Ecosystem (type)","Total number of natural assets or ecosystems protected/rehabilitated","Unit","Effectiveness of protection/rehabilitation","Natural asset or Ecosystem (type)","Total number of natural assets or ecosystems protected/rehabilitated","Unit","Effectiveness of protection/rehabilitation","Natural asset or Ecosystem (type)","Total number of natural assets or ecosystems protected/rehabilitated","Unit","Effectiveness of protection/rehabilitation","Natural asset or Ecosystem (type)","Total number of natural assets or ecosystems protected/rehabilitated","Unit","Effectiveness of protection/rehabilitation"]
[null,null,null,"Mangroves",200,"ha rehabilitated","1: Ineffective","Mangroves",200,"ha rehabilitated","1: Ineffective","Mangroves",90,"ha rehabilitated","2: Partially effective"]
[]
[null,null,null,"Natural asset or Ecosystem (type)","Total number of natural assets or ecosystems protected/rehabilitated","Unit","Effectiveness of protection/rehabilitation","Natural asset or Ecosystem (type)","Total number of natural assets or ecosystems protected/rehabilitated","Unit","Effectiveness of protection/rehabilitation","Natural asset or Ecosystem (type)","Total number of natural assets or ecosystems protected/rehabilitated","Unit","Effectiveness of protection/rehabilitation","Natural asset or Ecosystem (type)","Total number of natural assets or ecosystems protected/rehabilitated","Unit","Effectiveness of protection/rehabilitation"]
[]
[]
[null,null,null,"Natural asset or Ecosystem (type)","Total number of natural assets or ecosystems protected/rehabilitated","Unit","Effectiveness of protection/rehabilitation","Natural asset or Ecosystem (type)","Total number of natural assets or ecosystems protected/rehabilitated","Unit","Effectiveness of protection/rehabilitation","Natural asset or Ecosystem (type)","Total number of natural assets or ecosystems protected/rehabilitated","Unit","Effectiveness of protection/rehabilitation","Natural asset or Ecosystem (type)","Total number of natural assets or ecosystems protected/rehabilitated","Unit","Effectiveness of protection/rehabilitation"]
[]
[]
[null,null,null,"Natural asset or Ecosystem (type)","Total number of natural assets or ecosystems protected/rehabilitated","Unit","Effectiveness of protection/rehabilitation","Natural asset or Ecosystem (type)","Total number of natural assets or ecosystems protected/rehabilitated","Unit","Effectiveness of protection/rehabilitation","Natural asset or Ecosystem (type)","Total number of natural assets or ecosystems protected/rehabilitated","Unit","Effectiveness of protection/rehabilitation","Natural asset or Ecosystem (type)","Total number of natural assets or ecosystems protected/rehabilitated","Unit","Effectiveness of protection/rehabilitation"]
[]
[]
[]
[null,null,null,"Baseline information",null,null,null,"Targeted performance at completion",null,null,null,"Performance at mid-term",null,null,null,"Performance at completion"]
[null,"Outcome 6: Diversified and strengthened livelihoods and sources of income for vulnerable people in targeted areas","Indicator 6.1: Increase in households and communities having more secure access to livelihood assets","No. of targeted households","% of female headed households","Improvement level",null,"No. of targeted households","% of female headed households","Improvement level",null,"No. of targeted households","% of female headed households","Improvement level",null,"No. of targeted households","% of female headed households","Improvement level"]
[null,null,null,840,0.15,"2: Limited improvement",null,840,0.15,"3: Moderate improvement",null,600,0.15,"3: Moderate improvement"]
[null,null,"Indicator 6.2: Increase in targeted population's sustained climate-resilient alternative livelihoods","No. of targeted households","% of female headed households","% increase in income level vis-à-vis baseline","Alternate Source","No. of targeted households","% of female headed households","% increase in income level vis-à-vis baseline","Alternate Source","No. of targeted households","% of female headed households","% increase in income level vis-à-vis baseline","Alternate Source","No. of targeted households","% of female headed households","% increase in income level vis-à-vis baseline","Alternate Source"]
[null,null,null,840,0.15,"From 1% to 5%","Fishing",840,0.15,"From 20% to 30%","Fishing",600,0.15,"From 10% to 20%","Fishing"]
[null,null,null,"No. of targeted households","% of female headed households","% increase in income level vis-à-vis baseline","Alternate Source","No. of targeted households","% of female headed households","% increase in income level vis-à-vis baseline","Alternate Source","No. of targeted households","% of female headed households","% increase in income level vis-à-vis baseline","Alternate Source","No. of targeted households","% of female headed households","% increase in income level vis-à-vis baseline","Alternate Source"]
[]
[null,null,null,"No. of targeted households","% of female headed households","% increase in income level vis-à-vis baseline","Alternate Source","No. of targeted households","% of female headed households","% increase in income level vis-à-vis baseline","Alternate Source","No. of targeted households","% of female headed households","% increase in income level vis-à-vis baseline","Alternate Source","No. of targeted households","% of female headed households","% increase in income level vis-à-vis baseline","Alternate Source"]
[]
[null,null,null,"No. of targeted households","% of female headed households","% increase in income level vis-à-vis baseline","Alternate Source","No. of targeted households","% of female headed households","% increase in income level vis-à-vis baseline","Alternate Source","No. of targeted households","% of female headed households","% increase in income level vis-à-vis baseline","Alternate Source","No. of targeted households","% of female headed households","% increase in income level vis-à-vis baseline","Alternate Source"]
[]
[null,"Output 6 Targeted individual and community livelihood strategies strengthened in relation to climate change impacts, including variability","Indicator 6.1.1: No. and type of adaptation assets created or strengthened in support of individual or community livelihood strategies","Number of Assets","Type of Assets","Sector","Adaptation strategy","Number of Assets","Type of Assets","Sector","Adaptation strategy","Number of Assets","Type of Assets","Sector","Adaptation strategy","Number of Assets","Type of Assets","Sector","Adaptation strategy"]
[null,null,null,3,"Natural capital","Coastal management","Supporting livelihoods",3,"Natural capital","Coastal management","Supporting livelihoods",3,"Natural capital","Coastal management","Supporting livelihoods"]
[null,null,"Core Indicator 6.1.2: Increased income, or avoided decrease in income","Number of households (total number in the project area)","Income source",null,"Income level (USD)","Number of households (total number in the project area)","Income source",null,"Income level (USD)","Number of households (total number in the project area)","Income source",null,"Income level (USD)","Number of households (total number in the project area)","Income source","Income source"]
[null,null,null,690,"Fishing",null,90,690,"Fishing",null,150,600,"Fishing",null,120]
[null,null,null,"Number of households (total number in the project area)","Income source",null,"Income level (USD)","Number of households (total number in the project area)","Income source",null,"Income level (USD)","Number of households (total number in the project area)","Income source",null,"Income level (USD)","Number of households (total number in the project area)","Income source","Income source"]
[null,null,null,50,"Aquaculture",null,0,50,"Aquaculture",null,200,15,"Aquaculture",null,200]
[null,null,null,"Number of households (total number in the project area)","Income source",null,"Income level (USD)","Number of households (total number in the project area)","Income source",null,"Income level (USD)","Number of households (total number in the project area)","Income source",null,"Income level (USD)","Number of households (total number in the project area)","Income source","Income source"]
[]
[null,null,null,"Number of households (total number in the project area)","Income source",null,"Income level (USD)","Number of households (total number in the project area)","Income source",null,"Income level (USD)","Number of households (total number in the project area)","Income source",null,"Income level (USD)","Number of households (total number in the project area)","Income source","Income source"]
[]
[]
[null,null,null,"Baseline information",null,null,null,"Target performance at completion",null,null,null,"Performance at mid-term",null,null,null,"Performance at completion"]
[null,"Outcome 7: Improved policies and regulations that promote and enforce resilience measures","Indicator 7: Climate change priorities are integrated into national development strategy","Integration level",null,null,null,"Integration level",null,null,null,"Integration level",null,null,null,"Integration level"]
[null,null,null,"3: Some",null,null,null,"4: Most",null,null,null,"4: Most"]
[null,"Output 7:Improved integration of climate-resilience strategies into country development plans","Indicator 7.1: No. of policies introduced or adjusted to address climate change risks","No. of Policies introduced or adjusted","Sector","Scale","Type","No. of Policies introduced or adjusted","Sector","Scale","Type","No. of Policies introduced or adjusted","Sector","Scale","Type","No. of Policies introduced or adjusted","Sector","Scale","Type"]
[null,null,null,1,"Coastal management","National","Environmental policy",2,"Coastal management","National","Environmental policy",1,"Coastal management","Regional","Environmental policy"]
[null,null,"Indicator 7.2: No. of targeted development strategies with incorporated climate change priorities enforced","No. of Development strategies","Regulation",null,"Effectiveness","No. of Development strategies","Regulation",null,"Effectiveness","No. of Development strategies","Regulation",null,"Effectiveness","No. of Development strategies","Regulation",null,"Effectiveness"]
[null,null,null,1,"2: Partially not enforced (Most elements not implemented)",null,"2: Partially effective",1,"4: Enforced (Most elements implemented)",null,"4: Effective",1,"4: Enforced (Most elements implemented)",null,"3: Moderately effective"]
[]
[]
[]
[]
[]
[null,null,null,"Glacier lake outburst flood"]
[null,null,null,"Inland flooding","for","biological assets",null,"Company policy","5: Fully enforced (All elements implemented)"]
[null,null,null,"Salinization","Decrease","land",null,"Communication & Information policy","4: Enforced (Most elements implemented)"]
[null,null,null,"Drought","Same","water areas",null,"Defence policy","3: Partially enforced (Some elements implemented)"]
[null,null,null,"Wind",null,"subsoil assets","increased adaptive capacity","Domestic policy","2: Partially not enforced (Most elements not implemented)",null,"Agribusiness"]
[null,null,null,"Coastal flooding",null,"air","achieved","Economic policy","1: Not enforced (No elements implemented)",null,"Agricultural-related","Financial capital"]
[null,null,null,"Storm surge","Please choose",null,"enhanced level of protection","Education policy",null,null,"Agriculture","Human capital"]
[null,null,null,"Hurricane","Selected",{"$nulls":5},"Aquaculture","Physical capital"]
[{"$nulls":4},"Not relevant",null,null,"5: All (Fully integrated)",null,null,"Construction/repairing business","Social capital"]
[{"$nulls":7},"4: Most",null,null,"Cultivation","Natural capital"]
[{"$nulls":7},"3: Some",null,null,"Fishing","Personal capital"]
[null,"Select","5: All","Select",null,null,"Community","2: Most not integrated",null,"Other","Forestry","Adaptation strategies"]
[null,1,"4: Almost all","Private","Type","Yes","Multi-community","1: None",null,"Agriculture","Handicrafts"]
[null,2,"3: Half","Public","Scale","No","Departmental",null,null,"Coastal management","Livestock production"]
[null,3,"2: Some","NGO","Sector",null,"National",null,null,"Disaster risk reduction","Manufacturing"]
[null,4,"1: None",{"$nulls":4},"5: Very high improvement","Established","Food security","other"]
[null,null,null,"National",null,null,null,"4: High improvement","Maintained","Health ","Services"]
[null,null,null,"Regional",null,null,null,"3: Moderate improvement","Improved","Urban development","Tourism-related"]
[null,null,null,"Local",null,null,null,"2: Limited improvement",null,"Water management","Trading"]
[{"$nulls":7},"1: No improvement",null,"Multi-sector"]
[null,null,null,"1 -generated information is irrelevant, and neither the stakeholders reached nor the timeframe managed were achieved","1: No info transferred on time","4: High capacity","5: Fully aware","5: Highly responsive (All defined elements )","5: Fully improved","Roads","5: Very effective"]
[null,"Asia-Pacific","NIE","2 -the existence of some challenge in any of the three aspects of the indicator (generation of dissemination, stakeholders reached or timeframe managed)","2: Somewhat info transferred","3: Medium capacity","4: Mostly aware","4: Mostly responsive (Most defined elements)","4: Mostly Improved","Go Buildings","4: Effective"]
[null,"Latin America and Caribbean","RIE","3 -relevant information is generated and disseminated to all identified stakeholders on timely basis","3: Info transferred on time","2: Low capacity","3: Partially aware","3: Moderately responsive (Some defined elements)","3: Moderately improved","Causeways","3: Moderately effective"]
[null,"Africa","MIE",null,null,"1: No capacity","2: Partially not aware","2: Partially responsive (Lacks most elements)","2: Somewhat improved","Airports","2: Partially effective"]
[null,"Eastern Europe",{"$nulls":4},"1: Aware of neither","1: Non responsive (Lacks all elements )","1: Not improved","Schools","1: Ineffective"]
[null,null,"ha protected",{"$nulls":6},"Training Centres"]
[null,null,"ha rehabilitated",{"$nulls":5},"Monitoring/Forecasting capacity","Hospitals"]
[null,"Afghanistan, Islamic Rep. of","km protected",{"$nulls":5},"Policy/regulatory reform","Drinking water systems"]
[null,"Angola","km rehabilitated","1: Risk knowledge","1: No plans conducted or updated",null,null,null,"Capacity development","Other"]
[null,"Albania",null,"2: Monitoring and warning service","2: Undertaking or updating of assessments in progress",null,null,"Communication & Information policy","Sustainable forest management"]
[null,"Argentina",null,"3: Dissemination and communication","3: Risk and vulnerability assessments completed or updated",null,null,"Domestic policy","Strengthening infrastructure","1: Health and Social Infrastructure (developed/improved)"]
[null,"Armenia","Forests","4: Response capability",null,null,null,"Economic policy","Supporting livelihoods","2: Physical asset (produced/improved/strengthened)"]
[null,"Antigua and Barbuda","Mangroves",{"$nulls":4},"Education policy","Mangrove reforestation"]
[null,"Azerbaijan","Coasts",null,"From 0 to 0.5%",null,null,"Energy policy","Coastal drainage and infrastructure"]
[null,"Burundi","Rangelands",null,"From 0.5 to 1%",null,null,"Environmental policy","Irrigation system"]
[null,"Benin","Cultivated land/Agricultural land",null,"From 1% to 5%",null,null,"Foreign policy","Community-based adaptation"]
[null,"Burkina Faso","Catchment area/Watershed/Aquifer",null,"From 5% to 10%",null,null,"Health policy","Erosion control"]
[null,"Bangladesh","Protected areas/National parks",null,"From 10% to 20%",null,null,"Housing policy","Soil water conservation"]
[null,"Bulgaria","Other",null,"From 20% to 30%",null,null,"Human resource policies","Microfinance"]
[null,"Bahrain",null,null,"From 30% to 40%",null,null,"Information policy","Special Program for women"]
[null,"Bahamas, The",null,null,"From 40% to 50%",null,null,"Macroeconomic policy","Livelihoods"]
[null,"Bosnia and Herzegovina",null,null,"Above 50%",null,null,"Monetary policy","Water storage"]
[null,"Belarus",{"$nulls":5},"Population policy","ICT and information dissemination"]
[null,"Belize",{"$nulls":5},"Private policy"]
[null,"Bolivia",{"$nulls":5},"Public policy"]
[null,"Brazil",{"$nulls":5},"Science policy"]
[null,"Barbados",{"$nulls":5},"Social policy"]
[null,"Bhutan",null,"3- relevant information is generated and disseminated to all identified stakeholders on timely basis",null,null,null,"Transportation policy"]
[null,"Botswana",null,"describe",null,null,null,"Urban policy"]
[null,"Central African Republic",null,"2- the existence of some challenge in any of the three aspects of the indicator",null,null,null,"Water policy"]
[null,"Chile",null,"describe",null,null,null,"Other policy"]
[null,"China, People's Republic of",null,"1- generated information is irrelevant and neither the stakeholders reached nor the timeframe managed were achieved"]
[null,"Cote d'Ivoire",null,"describe"]
[null,"Cameroon"]
[null,"Congo, Dem. Rep. of"]
[null,"Congo, Republic of"]
[null,"Cook Islands"]
[null,"Colombia"]
[null,"Comoros"]
[null,"Cape Verde"]
[null,"Costa Rica"]
[null,"Cuba"]
[null,"Czech Republic"]
[null,"Djibouti"]
[null,"Dominica"]
[null,"Dominican Republic"]
[null,"Algeria"]
[null,"Ecuador"]
[null,"Egypt"]
[null,"Eritrea"]
[null,"Estonia"]
[null,"Ethiopia"]
[null,"Fiji"]
[null,"Micronesia, Fed. States of"]
[null,"Gabon"]
[null,"Georgia"]
[null,"Ghana"]
[null,"Guinea"]
[null,"Gambia, The"]
[null,"Guinea-Bissau"]
[null,"Equatorial Guinea"]
[null,"Grenada"]
[null,"Guatemala"]
[null,"Guyana"]
[null,"Honduras"]
[null,"Croatia"]
[null,"Haiti"]
[null,"Hungary"]
[null,"Indonesia"]
[null,"India"]
[null,"Iran, Islamic Republic of"]
[null,"Jamaica"]
[null,"Jordan"]
[null,"Kazakhstan"]
[null,"Kenya"]
[null,"Kyrgyz Republic"]
[null,"Cambodia"]
[null,"Kiribati"]
[null,"Saint Kitts and Nevis"]
[null,"Korea, Republic of"]
[null,"Lao People's Democratic Republic"]
[null,"Lebanon"]
[null,"Liberia"]
[null,"Libya"]
[null,"Saint Lucia"]
[null,"Sri Lanka"]
[null,"Lesotho"]
[null,"Lithuania"]
[null,"Latvia"]
[null,"Morocco"]
[null,"Moldova"]
[null,"Madagascar"]
[null,"Maldives"]
[null,"Mexico"]
[null,"Marshall Islands"]
[null,"Macedonia, former Yugoslav Republic of"]
[null,"Mali"]
[null,"Malta"]
[null,"Myanmar"]
[null,"Montenegro"]
[null,"Mongolia"]
[null,"Mozambique"]
[null,"Mauritania"]
[null,"Mauritius"]
[null,"Malawi"]
[null,"Malaysia"]
[null,"Namibia"]
[null,"Niger"]
[null,"Nigeria"]
[null,"Nicaragua"]
[null,"Niue"]
[null,"Nepal"]
[null,"Nauru"]
[null,"Oman"]
[null,"Pakistan"]
[null,"Panama"]
[null,"Peru"]
[null,"Philippines"]
[null,"Palau"]
[null,"Papua New Guinea"]
[null,"Poland"]
[null,"Korea, Dem. People's Rep. of"]
[null,"Paraguay"]
[null,"Romania"]
[null,"Russian Federation"]
[null,"Rwanda"]
[null,"Saudi Arabia"]
[null,"Sudan"]
[null,"Senegal"]
[null,"Solomon Islands"]
[null,"Sierra Leone"]
[null,"El Salvador"]
[null,"San Marino"]
[null,"Serbia"]
[null,"Sao Tome and Principe"]
[null,"Suriname"]
[null,"Slovak Republic"]
[null,"Slovenia"]
[null,"Swaziland"]
[null,"Seychelles"]
[null,"Syrian Arab Republic"]
[null,"Chad"]
[null,"Togo"]
[null,"Thailand"]
[null,"Tajikistan"]
[null,"Turkmenistan"]
[null,"Tonga"]
[null,"Trinidad and Tobago"]
[null,"Tunisia"]
[null,"Turkey"]
[null,"Tuvalu"]
[null,"Tanzania"]
[null,"Uganda"]
[null,"Ukraine"]
[null,"Uruguay"]
[null,"Uzbekistan"]
[null,"Saint Vincent and the Grenadines"]
[null,"Venezuela"]
[null,"Vietnam"]
[null,"Vanuatu"]
[null,"Samoa"]
[null,"Yemen, Republic of"]
[null,"South Africa"]
[null,"Zambia"]
[null,"Zimbabwe"]
[null,"Timor-Leste"]

{"sheet":"Units for Indicators","index":7,"n_rows":4,"n_cols":2,"rows_kept":4,"cut":false,"hidden":false,"merged":[],"flags":["formulas_cached_only"]}
[null," Fund Outcome Indicator Units"]
[null,"1. Generation of relevant data, Stakeholders, and Timeliness \n2.1. Include both qualitative and quantitative measures of capacity level within targeted institutions\n2.2. Number (men and women and other vulnerable groups)\n3.1. Use scale from 1 to 5: 5: Fully aware 4: Mostly aware 3: Partially aware 2: Partially not aware 1: Aware of neither predicted adverse impacts of climate change nor of appropriate responses\n3.2. Use scale from 1 to 5:  5: All 4: Almost all 3: Half 2: Some 1: None\n4.1. Summarize in an overall scale (1-5): 5: Highly responsive (All defined elements ) 4: Mostly responsive (Most defined elements) 3: Moderately responsive (Some defined elements) 2: Partially responsive (Lacks most elements) 1: Non responsive (Lacks all elements )                                                                                                                                                                                                                    4.2.  Summarize in an overall scale (1-5):  5: Fully improved 4: Mostly Improved 3: Moderately improved 2: Somewhat improved\n1: Not improved                                                                                                                                                                                                                           5.  Depends on the targeted natural asset: \nBiological (species): measure through changes in population numbers (dynamics, structure, etc.)\nLand: measure changes in hectares. Baseline data will be necessary to estimate the change. Supporting indicators baseline and target (as well as contextual information) are needed such as the following: Farmers adopting recommended technologies, Ha. of land improved, Average deforestation rate Etc.\nUse scale from 1 to 5.  5: Very effective (All elements are present) 4: Effective (Most elements are present) 3: Moderately effective (Some elements are present) 2: Partially effective (Most elements are not present) 1: Ineffective (No elements are present)\n6.1.  Summarize in an overall scale (1-5):  5: Very high improvement 4: High improvement 3: Moderate improvement 2: Limited improvement 1: No improvement                                                                                                                                                                                                                                                         6.2.  Household income by source of livelihood in project area (USD) prior and post project intervention                                                                                                                                                                                                                                                      7. Summarize in an overall scale (1-5).  5: All (Fully integrated) 4: Most 3: Some 2: Most not integrated 1: None"]
[null,"Fund Output Indicator Units"]
[null,"1.1.  Number, sector(s) and level(s) of projects or interventions in separate fields of monitoring plan                                                                                  1.2. Number\n2.1.1. Number of staff (male/female) of targeted institutions: a. Obtain baseline information: total number of staff from targeted institutions b. Define target\n2.1.2. Number of staff (male/female) of targeted institutions: a. Obtain baseline information: total number of staff from targeted institutions b. Define target: needs to be defined by project proponents\n2.2.1. Quantitative: Percentage (includes women – and other vulnerable groups – and men).\nQualitative: Adequacy: include direct analysis of major areas; adequacy/effectiveness of systems or analysis of perceptions of populations and institutions.\n2.2.2. Number (broken down by gender and, if possible, by vulnerable groups defined in the area of intervention) of people                                                                                                        3.1. Number and type (in separate columns) at local level.                                                                                                                                    3.2. Number                                                                                                                                                                                                                                     4.1. Number and type                                                                                                                                                                                                               4. 2.  Number and type (entered in separate columns)                                                                                                                                                     5.  Number of interventions by type of natural asset and intervention                                                                                                                    6.1.  Number and type (in separate columns of monitoring plan)                                                                                                                                                                                                                                                    6.2. Income sources per household; description of income source and number of households.                                                                                                                                                                                                                                                     7.1.  Number/Sector                                                                                                                                                                                                                                                   7.2. Number; Effectiveness (see previous indicator) through enforcement level."]