## Overview
Project Performance Report (PPR)
| Project Title: | Adaptation to coastal erosion in vulnerable areas
| Project Summary: | “Adaptation to coastal erosion in vulnerable areas” is a 2 years (2011 / 2012) project financed with 8 619 000 USD by the Adaptation Fund through a one-step approval process. The project document was approved during the 11th meeting of the AF Board (16-17 September 2010) in Bonn and the MOU was signed in 11th November 2010. The main focus of the project is the development of adaptation capacities of communities the most vulnerable to coastal erosion and sea level rising in 3 regions of Senegal, located along the coastline. The principal promoter of the project is the Directorate of Environment, with a strong involvement of CSO (GREEN Senegal and Dynamique Femme) The main components of the project are: - Training and awareness rising - Building up of coastal protection facilities in the areas of Rufisque and Saly - Building an anti-salt dike in Joal - Strengthening of the protection and development of the littoral: beach, fish processing areas - Development, strengthening, and implementation of the regulation on coastal protection and the adaptation to climate change - Communication - Follow-up/Evaluation/Monitoring
|  |  | Countries | Project Type: |  | GEF Focal Area: | GEF 4 Focal Areas | GEF 2 / 3 Operational Programme: | Overall Rating of the project in the evaluation by the project evaluator: | GEF-4 Focal Area Strategic Program: | GEF-3 Focal Area Strategic Program:
| Database Number: |  | Afghanistan | FP | Yes | Biodiversity | 1 | 1 | U | BD-SP1-PA Financing | 1: Arid & semi-arid ecosystems
| Implementing Entity (name): | Centre de Suivi Ecologique (CSE) | Albania | MSP | No | Climate Change Adaptation | 2 | 2 | S | BD-SP2-Marine PA | 2: Coastal, marine & freshwater ecosystems
| Type of IE: | National | Algeria | EA |  | Climate Change Mitigation | 3 | 3 | MU | BD-SP3-PA Networks | 3: Forest ecosystems
| Country(ies): | Senegal | Angola |  |  | International Waters | 5 | 5 | Good | BD-SP5-Markets | 13: Conservation and Sustainable Use of Biological Diversity Important to Agriculture
Relevant Geographic Points (i.e. cities, villages, bodies of water): |  | Senegal | Argentina |  |  | Multiple Focal Area |  |  |  | BD-SP7-Invasive Alien Species(IAS) | 6: Promoting the adoption of renewable energy by removing barriers and reducing implementation costs
[8 empty] | CC-SP2- Industrial EE | 8: Waterbody based operational program
| Project Milestones | [6 empty] | CC-SP3-RE,CC-SP4-Biomass | 9: Integrated Land and Water multiple focal area
| Milestone |  | Bahamas | [6 empty] | CC-SP5-Transport | 10: Contaminants based operational program
| AFB Approval Date: | 17th September 2010 | [6 empty] | CC-SP6-LULUCF | 12: Integrated Ecosystem Management
| Start of Project/Programme: | 21st January 2011 | [6 empty] | Cross cutting capacity building | 14: Persistent Organic Pollutants
Mid-term Review (if planned):
| Terminal Evaluation: | February 2013
|  | List documents/ reports/ brochures / articles that have been prepared about the project. | Cyprus
Czech Republic
| List the Website address (URL) of project. |  | Democratic People's Republic of Korea
Democratic Republic of the Congo
Denmark
| Project contacts: |  | Djibouti
| National Project Manager/Coordinator |  | Dominica
| Name: |  | Dominican Republic
| Email: |  | Ecuador
| Date: |  | Egypt
| Government DA |  | El Salvador
| Name: | Ndèye Fatou Guène | Equatoral Guinea
| Email: | mactarguen@yahoo.fr | Eritrea
| Date: | 2010-07-29 | Estonia
| Executing Agency |  | Ethiopia
| Name: | Directorate of the Environment | Fiji
| Email: | cheikh.syllan@gmail.com | Finland
| Date: | 2011-01-04 | France
| Executing Agency |  | Gambia
| Name: | GREEN Senegal | Georgia
| Email: | greensenegal@orange.sn | Germany
| Date: | 2011-01-05 | Ghana
| Executing Agency |  | Greece
| Name: | Dynamique Femme | Grenada
| Email: | dynfemme@yahoo.fr | Guatemala
| Date: | 2011-01-10 | Guinea
| Executing Agency |  | Guinea Bissau
| Name: |  | Guyana
| Email: |  | Haiti
| Date: |  | Honduras
Hungary
Iceland
India
Indonesia
Iran (Islamic Republic of)
Iraq
Ireland
Israel
Italy
Jamaica
Japan
Jordan
Kazakhstan
Kenya
Kiribati
Kuwait
Kyrgyzstan
Lao People’s Democratic Republic
Latvia
Lebanon
Lesotho
Liberia
Libyan Arab Jamahiriya
Liechtenstein
Lithuania
Luxembourg
Madagascar
Malawi
Malaysia
Maldives
Mali
Malta
Marshall Islands
Mauritania
Mauritius
Mexico
Micronesia, Federated States of
Monaco
Mongolia
Montenegro
Morocco
Mozambique
Myanmar
Namibia
Nauru
Nepal
Netherlands
New Zealand
Nicaragua
Niger
Nigeria
Norway
Oman
Pakistan
Palau
Panama
Papua New Guinea
Paraguay
Peru
Philippines
Poland
Portugal
Qatar
Republic of Korea
Republic of Moldova
Romania
Russian Federation
Rwanda
Saint Kitts and Nevis
Saint Lucia
Saint Vincent and the Grenadines
Samoa
San Marino
Sao Tome and Principe
Saudi Arabia
Senegal
Serbia
Seychelles
Sierra Leone
Singapore
Slovakia
Slovenia
Solomon Islands
Somalia
South Africa
Spain
Sri Lanka
Sudan
Suriname
Swaziland
Sweden
Switzerland
Syrian Arab Republic
Tajikistan
Thailand
The former Yugoslav Republic of Macedonia
Timor-Leste
Togo
Tonga
Trinidad and Tobago
Tunisia
Turkey
Turkmenistan
Tuvalu
Uganda
Ukraine
United Arab Emirates
United Kingdom of Great Britain and Northern Ireland
United Republic of Tanzania
United States of America
Uruguay
Uzbekistan
Vanuatu
Venezuela, Bolivarian Republic of
Viet Nam
Yemen
Zambia
Zimbabwe
Note on D13: Daouda Ndiaye: It was a two-step approval process.

## FinancialData
Financial information: cumulative from project start to [insert date]
DISBURSEMENT OF AF GRANT FUNDS
How much of the total AF grant as noted in Project Document plus any project preparation grant has been spent to date?
Estimated cumulative total disbursement as of 10th February 2012 | 2971622
Add any comments on AF Grant Funds. (word limit=200) | Most of the works having been initiated, the pace of calls for funds is set to get even quicker during the 3rd semester. Therefore, it's important to mobilize all budgeted resources in order to avoid delays and to support a good rythm of implementation.
EXPENDITURE DATA
List item / activity / action and corresponding amount spent for the current reporting period | ITEM / ACTIVITY / ACTION | AMOUNT
| Action 1.1 : Environmental Impâct Assessment for the design of the coastal protection facilities in the area of Rufisque-Est (Thiawlene) | 19802.6
| Action 1.2: Building up of the coastal protection facilities in the areas of Rufisque. The target areas host houses, economic and cultural infrastructure (Fish processing areas, fishing docks, cemeteries, etc.) | 1412714.4299
| Action 2.1: Carry out and validate the detailed technical feasibility studies for the design of the protection facilities of the coastal areas of Saly | 32902.4258
| Action 2.2 : Set up the protection facilities of the vulnerable areas covering hotels, people, poor villages, as well as the fishing docks | 160636.7104
| Action 2.3: Assistance in the development of the fishing dock and the fish processing area | 105177.7397
| Action 3.1: Study and achieve the anti-salt barriers in the rice-growing areas of Joal and the other agricultural crops. | 214052.8799
| Action 3.2: Protect and develop beaches and fish processing areas. | 94384.9284
| Action 3.3: Restore the cleanliness of the beaches | 15671.04
| Action 3.4: awarness and training programme | 21990.92
| Action 4.1: Design, fine tune, and strengthen the regulation pertaining to the management of the littoral, by taking into account the CC dimension: Environment Code, other codes and regulations | 1547.93
| Action 5.1: Design and implement the awareness and training programme | 16924.62
| Action 5.2: Fine tune and share the suitable communication tools | 39258.32
| Action 5.3: Inform, sensitize, and train people on the adaptation techniques to climate change in coastal areas | 16901.7154
| Action 6.1: Monitoring/ Follow up | 37961.65
| Action 6.2: External Evaluation and audit | 0
| Action 6.3: Controle of realisation | 30575.1766
| N.I.E. fees | 50000
2270503.0861
PLANNED DISBURSEMENT SCHEDULE
List item / activity / action planned and corresponding projected cost for the upcoming reporting period | ITEM / ACTIVITY / ACTION | PROJECTED COST | Est. Completion Date
| Action 1.1: Public hearing ofr the Environmental Impact Assessment report (coastal protection facilities in Rufisque-Est) | 197.4 | March 2012
| Action 1.2: Building up of the coastal protection facilities in the areas of Rufisque. | 687285.57 | December 2012
| Action 1.3 :Cleaning-up of channels (Thiawlene) | 19000 | July-August 2012
| Action 1.3 : Awareness raisin (Rufisque) | 16000 | December 2012
| Action 1.3 : Trainings on NAPA, organizational dynamics, climate change and fisheries (Rufisque) | 15000 | March 2012
| Action 2.1: Rehabilitation of the fishing dock at Saly Coulang | 67097.5742 | February 2012
| Action 2.2: Building the protection facilities of the vulnerable areas in Saly | 1039363.2896 | November 2012
| Action 2.3: Training (NAPA, climate change and fisheries) and exchange visits (Saly) | 31032.44 | March 2012
| Action 2.3: Awareness raising in Saly (in-home visit, radio programs, meetings with neighbourhood committees, focus-group and social mobilization, communications media) | 36570.17 | End of August
| Action 2.3: Developing the drying area (Saly) | 53115.48 | Early March
| Action 2.3: Documenting and building on good practices in adaptation to climate change | 26524.3 | End of May
| Action 2.3: Monitoring and coordination | 44690.53 | End of August
| Action 3.1: Building the anti-salt dike in Joal | 485947.1201 | August 2012
| Action 3.2: Consolidation of the fishing dock in Joal | 165874.96 | Mid July 2012
| Action 3.2: Feasibility study and reconstituion of the fish processing area in Joal | 14069.17 | End of February
| Action 3.2: Works on the fish processing area in Joal | 325670.9416 | End of September
| Action 3.3: Restore the cleanliness of the beaches | 117863.98 | End of Project
| Action 3.4: awarness and training programme | 36240.12 | March 2012
| Action 4.1: Review of the Environmental code | 17573.71 | April 2012
| Action 4.2: Dissemination of the elaborated texts | 50000 | December 2012
| Action 5.1: Information and training workshops on climate change | 79288.52 | July 2012
| Action 5.2: Fine tune and share the suitable communication tools | 35858.84 | End of project
| Action 5.3: Inform, sensitize, and train people on the adaptation techniques to climate change in coastal areas | 15523.07 | August 2012
| Action 5.4: Train the different target groups on the new regulations on adaptation | 30000 | March 2012
| Action 6.1: Monitoring/ Follow up | 30000 | End of Project
| Action 6.2: External Evaluation and audit | 45000 | March 2012
| Action 6.3: Controle of realisation | 13722.62 | End of Project
| N.I.E. fees | 50000 | End of Project
3548509.8055
ACTUAL CO-FINANCING
How much of the total co-financing as committed in the Project Document has actually been realized?
If the MTR or TE have not been undertaken this reporting period, DO NOT report on actual co-financing.
Estimated cumulative actual co-financing as verified during Mid-term Review (MTR) or Terminal Evaluation (TE).
Add any comments on actual co-financing in particular any issues related to the realization of in-kind, grant, credits, loans, equity, non-grant instruments and other types of co-financing. (word limit=200)
Note on F65: Daouda Ndiaye: The next reporting period is June-July 2012. Therefore the disbursement schedule by item should be limited to that period.

## Risk Assesment
RISK ASSESMENT
IDENTIFIED RISKS
List all Risks identified in project preparation phase and what steps are being taken to elivate them (word limit = 200)
Identified Risk | Current Status | Steps Taken to Elivate Risk
Efficiency of technical measures adopted to fight coastal erosion | Low | Freasibility studies were realized prior to each contract, clear technical specifications were given in the tender and a stringent control is performed during the realization, both from executing agencies and from the implementing entity.
Management of the project heavily dependent on subcontracting | Low | It was decided that contract award processes are subject to the procedures of the CSE, and no to the ones of the Public Procurement Regulation Agency which is more time consuming. To this end, the manual of procedures of the CSE was updated with the inclusion of an annex on “contracting procedures”. In addition, delegate project managers were hired to assist the project owner (the excuting entities) in the procurement.
Conflict over the management and maintenance of the built infrastructures between local communities, private companies, extension services | Low | Many information and sensitization activities were undertaken toward the different stakeholders, a database on households and their assets is also under elaboration. In addition, many meetings were organized between neighboring local government units in the area of impact of the anti-salt dike to discuss the management of the land resources.
Local communities do not fully participate to the project | No longer relevant | The information, sentitization and mobilization activities were very successfull and local communities are highly committed an involved
Low impact/application of the Coastal Act | Medium | It is planned to disseminate the new regulations and the Coastal Act provide for the setting up of a national body for the management of the littoral. One of the mandates of this body will be to ensure the application of the law
Lack of coordination among the executing entities | Low | Regular technical committee meetings are organized to coordinate the interventions, as well as national and local steering committee meetings.
Low consciousness of the populations and decision makers with regards to climate change | Low | Many awarness raising activites were and conitnue to be realized
Critical Risks Affecting Progress (Not identified at project design)
Identify Risks with a 50% or > likelihood of affecting progress of project
Identified Risk | Current Status | Steps Taken to Elivate Risk
Building of the protection facility and related works dependent on the synergy of interventions with the West African Economic and Monetary Union (WAEMU) | Low | Regular meetings with WAEMU staff, DNA and implementing entities
Difficulties to mobilize populations because of elections scheduled for February 2012 | Medium | Schedule most of the mobilization activities out of the critical period
Conflict between the executing entity and a portion of the population about the site of implantation of the structures in Joal | Low | Sensitization activities and advocacy in the relevant areas
Risks associated with the complexity of maritime works | Low | Take fullest advantage of the dry season and of the calm sea period
Risk Measures: Were there any risk mitigation measures employed during the current reporting period? If so, were risks reduced? If not, why were these risks not reduced?
Add any comments relevant to risk elevation (word limit = 500)

## Rating
RATING ON IMPLEMENTATION PROGRESS
For rating definitions please see bottom of page.
| Progress on Key Milestones | Expected Progress |  | Progress to Date | Rating
Project Manager/Coordinator:
Overall Rating
Please justify your rating. Outline the positive and negative progress made by the project since it started. Provide specific recommendations for next steps. . (word limit=500)
| Progress on Key Milestones | Expected Progress |  | Progress to Date | Rating
Implementing Agency | Building coastal protection facility in Thiawlene (Rufisque-Est) | Works were supposed to be launched since September 2011 for the fishing dock, since July 2011 for the fish processing area ( |  | No objection opinion obtained from UEMOA, financial resources mobilized and works start-up meeting held | S
| Building coastal protection facility in Saly | Works were supposed to be launched since December 2011 |  | Studies completed, tender was initiated for hiring the company in charge of works | S
| Rehabilitation of fish processing areas in Saly Coulang | Works were supposed to start by august 2011 |  | Works on its final stage | S
| Building anti-salt-dike in Joal | Works were supposed to start in december 2011 |  | Works launched in January 2012 | S
| Developement of the fish processing area and fishing dock in Joal | Works were supposed to be launched since September 2011 for the fishing dock, since July 2011 for the fish processing area |  | Studies compelted, the company in charge of works hired and the works are about to start for the fishing dock; Technical study underway for the fish processing area | S
| Formulation of the law on littoral and revision of the Environmental Code | Was supposed to be completed in the first year |  | The littoral law and the Environmental Code already passed the stage of the Supreme Court and will be submitted to the vote of the Parliament very soon | S
| Awareness raising | Good knowledge of the project, its objectives and its activities in the areas of intervention |  | Good level of implementation | HS
|  |  |  | Overall Rating | S
| Please justify your rating and address the following points: 1. Indicate trends, both positive and negative, in achievement of outcomes as per the project indicators. 2. Detail critical risks that have affected progress. 3. Outline response to MTR undertaken this reporting period. 4. Outline action plan to address projects with a rating of HU, U or MU. Please keep your input to 1200 words | To date, the awareness raising activities have been implemented with a good rhythm. However, the launch of construction work took some time due to delays in procurements. Nevertheless, most of the realizations are now started and the pace of implementation should be very high during the 3rd semester. For the protection facility of Rufisque-Est, it took a long time to get the no objection opinion from the West African Economic and Monetary Union (WAEMU) , precondition for the signing of the agreement between the Executing entity (the Directorate of the Environment) and the project owner agent called AGETIP (public works execution agency). Despite this delay, the prescribed period for the realization (up to ten months) respects the project deadlines. The protection facility in Saly, a tender was already initiated for hiring the company in charge of works and the construction should start very soon. The reconstitution of the fish processing areas, the work is in its final stage in Saly, while the technical studies are underway in Joal. Regarding the elaboration of the littoral law and the review and update of the Environmental Code, the activities are progressing on track. In general, most of major objectives should be achieved at due time.
Rating Definitions
|  |  | Highly Satisfactory (HS) | Project actions/activities planned for current reporting period are progressing on track or exceeding expectations to acheive all major objectives/outcomes for given reporting period, without major shortcomings. The project can be presented as “good practice”.
|  |  | Satisfactory (S) | Project actions/activities planned for current reporting period are progressing on track to achieve most of its major objectives/outcomes with only minor shortcomings.
|  |  | Marginally Satisfactory (MS) | Project actions/activities planned for current reporting period are progressing on track to achieve most major relevant objectives/outcomes, but with either significant shortcomings or modest overall relevance.
|  |  | Marginally Unsatisfactory (MU) | Project actions/activities planned for current reporting period are not progressing on track to achieve major objectives/outcomes with major shortcomings or is expected to achieve only some of its major objectives/outcomes.
|  |  | Unsatisfactory (U) | Project actions/activities planned for current reporting period are not progressing on track to achieve most of its major objectives/outcomes.
|  |  | Highly Unsatisfactory (U) | Project actions/activities planned for current reporting period are not on track and shows that it is failing to achieve, and is not expected to achieve, any of its objectives/outcomes.
Note on C8: Daouda Ndiaye: The representative from the DEEC in charge of coordinating the project should complete this part. Unless it is clearly stated that CSE plays that role.
Note on F30: Daouda Ndiaye: For the protection facility in Saly, please elaborate on the findings of the studies, explain which technique was finally chosen.

## Project Indicators
PROJECT Indicators
Please provide all indicators being tracked for the project as outlined in the project document
Type of Indicator (indicators towards Objectives, Outcomes, etc…)
Type of Indicator | Indicator | Baseline | Progress to date | Target
| Indicator 1.1: number of study report | One study report validated for Rufisque | Completed | The detailed technical feasibility studies for the protection of the coastal areas of Rufisque are updated
| Indicator 1.2: Length of protected coast (in linear meter) | 6,000 square kilometres of areas threatened by flood | The company in charge of the works was hired | The protection works of the coastal areas of Rufisque are built (381 linear meter of wall built through the Adaptation Fund )
| indicator.1. 3: Linear number of cleaned up channels | Coastal facilities and human settlements facing high threats | Not started yet | The waste ways of rainwater are cleaned up and connected to the sea
| Indicator 2.1: Study Reports | No study made | Completed | The detailed technical feasibility studies for the protection of the coastal areas of Saly are completed and validated
| Indicator: 2.2. Length of the coast protected (in linear metre) | 3 square kilometres of areas threatened by flood | A tender was initiated for hiring the company in charge of works | The protection works of the coastal areas of Saly are completed
| Indicator 2. 3 Existence of a sound fishing dock and a good fish processing area | Destruction of fishing docks and fish processing areas due to sea-level rise | Works on its final stage | The development of the fishing dock and the fish processing area in Saly is done
| Indicator 3.1. Study reports, number of curbs and dikes built | Rice-growing activities affected by intrusion of saline waters; drainage of rice growing areas difficult | Works launched | The technical studies and the dikes to prevent salt intrusion into the rice-growing areas of Joal are done
| Indicator: 3.2.1. The curbs for protected beaches and the fish processing areas are developed | The beach is used as lavatory and the waste management system is very poor | A collecting system was estabilished, along with salubrity committees. About sixty cleaning operations were organized | The protection and development of beaches and fish processing areas are completed
Indicator 3.2.2. The setting up of a rational and effective waste management programme in the beach is completed
| Indicator 4.1. Number and nature of the legal materials drawn up and in force | No (or inadequate) legal materials dealing with the management of the littoral and taking into account the CC | The littoral law and the Environmental Code already passed the stage of the Supreme Court | The legal materials dealing with the management of the littoral and taking into account the CC dimension are drawn up
| Indicator 4.2. Number of popularization sessions and participants | Peoples in these areas have very few information about the legal materials | Not started yet | The texts drawn up are popularized
| Indicator 5.1. Study Report | Education on adaptation is still a national priority | Regional committees for adaptation to climate change (COMREC) were estabilished by Oredre of the Governors and the capacity building neeeds were identified | A training and sensitization programme is designed and carried out
| Indicator 5.2. Number and nature of the communication tools developed | Adaptation programmes/projects are still devoided of adequate tools for taking up and disseminating learned lessons on community adaptation | A draft of communication strategy was elaborated | Adequate communication tools are developed and shared
| Indicator 5. 3. Number of sensitization sessions/workshops held or participants | Cross learning mechanisms are little_known | 1313 sensitization sessions (in-home visits, focus-group, social mibilization, radio programs, advocacy, traditional wrestling), 16 information panels installed | People are informed, sensitized and trained on the adaptation techniques to climate change en coastal areas
| Indicator 5. 4. Number of training sessions/workshops or participants | Cross learning mechanisms are little_known | 3 training sessions organized | The different target groups are trained in the new regulations on the adaptation

## AF Tracking Tool
Tracking Tool for Adaptation Fund (AF) Projects
Goal: Assist developing-country Parties to the Kyoto Protocol that are particularly vulnerable to the adverse effects of climate change in meeting the costs of concrete adaptation projects and programmes in order to implement climate-resilient measures. Impact: Increased resiliency at the community, national, and regional levels to climate variability and change.
Important: Please read the following Results Framework and Baseline Guidance (also posted on the Adaptation Fund website) before entering your data
Link: http://www.adaptation-fund.org/sites/default/files/Results%20Framework%20and%20Baseline%20Guidance%20final.pdf
Please select the relevant Fund level Outcome and Output indicators that allign with the project objectives and outcomes
OBJECTIVE 1: Implement the actions to protect the coastal areas of Rufisque, Saly, and Joal against erosion, with the aim to protect houses and the economic infrastructures threatened by the erosion including fish processing areas, fishing docks, tourism or cultural infrastructures, and restore lost or threatened activities
Fund Outcome | Please select from dropdown menu below | Fund Outcome Indicator | Please select from dropdown menu below | Target at CEO Endorsement (see Units in next sheet) | Baseline (see Units in next sheet) | Mid-term Results | Terminal Results
Outcome 1: Reduced exposure at national level to climate-related hazards and threats Outcome 2: Strengthened institutional capacity to reduce risks associated with climate-induced socioeconomic and environmental losses Outcome 3: Strengthened awareness and ownership of adaptation and climate risk reduction processes at local level Outcome 4: Increased adaptive capacity within relevant development and natural resource sectors Outcome 5: Increased ecosystem resilience in response to climate change and variability-induced stress Outcome 6: Diversified and strengthened livelihoods and sources of income for vulnerable people in targeted areas Outcome 7: Improved policies and regulations that promote and enforce resilience measures | 4 | 1. Relevant threat and hazard information generated and disseminated to stakeholders on a timely basis 2.1. No. and type of targeted institutions with increased capacity to minimize exposure to climate variability risks 2.2. Number of people with reduced risk to extreme weather events 3.1. Percentage of targeted population aware of predicted adverse impacts of climate change, and of appropriate responses 3.2. Modification in behavior of targeted population 4.1. Development sectors' services responsive to evolving needs from changing and variable climate 4.2. Physical infrastructure improved to withstand climate change and variability-induced stress 5. Ecosystem services and natural assets maintained or improved under climate change and variability-induced stress 6.1. Percentage of households and communities having more secure (increased) access to livelihood assets 6.2. Percentage of targeted population with sustained climate-resilient livelihoods 7. Climate change priorities are integrated into national development strategy | 4.2 | 5 | 1 (Nothing in Saly and a very rudimentary stone dyke in Rufisque)
Fund Output | Please select from dropdown menu below | Fund Output Indicator | Please select from dropdown menu below | Target at CEO Endorsement (see Units in next sheet) | Baseline (see Units in next sheet) | Mid-term Results | Terminal Results
Output 1: Risk and vulnerability assessments conducted and updated at a national level Output 2.1: Strengthened capacity of national and regional centres and networks to respond rapidly to extreme weather events Output 2.2: Targeted population groups covered by adequate risk reduction systems Output 3: Targeted population groups participating in adaptation and risk reduction awareness activities Output 4: Vulnerable physical, natural, and social assets strengthened in response to climate change impacts, including variability Output 5: Vulnerable physical, natural, and social assets strengthened in response to climate change impacts, including variability Output 6: Targeted individual and community livelihood strategies strengthened in relation to climate change impacts, including variability Output 7: Improved integration of climate-resilience strategies into country development plans | 4 | 1.1. No. and type of projects that conduct and update risk and vulnerability assessments 1.2. Development of early warning systems 2.1.1. No. of staff trained to respond to, and mitigate impacts of, climate-related events 2.1.2. Capacity of staff to respond to, and mitigate impacts of, climate-related events from targeted institutions increased 2.2.1. Percentage of population covered by adequate risk-reduction systems 2.2.2. No. of people affected by climate variability 3.1 No. and type of risk reduction actions or strategies introduced at local level 3.2 No. of news outlets in the local press and media that have covered the topic 4.1. No. and type of health or social infrastructure developed or modified to respond to new conditions resulting from climate variability and change (by type) 4. 2. No. of physical assets strengthened or constructed to withstand conditions resulting from climate variability and change (by asset types) 5. No. and type of natural resource assets created, maintained or improved to withstand conditions resulting from climate variability and change (by type of assets) 6.1. No. and type of adaptation assets (physical as well as knowledge) created in support of individualor community-livelihood strategies 6.2. Type of income sources for households generated under climate change scenario 7.1. No., type, and sector of policies introduced or adjusted to address climate change risks 7.2. No. or targeted development strategies with incorporated climate change priorities enforced | 4.2 | 2 coastal protection facilities | 0 protection facility in Saly, 1 rudimentary stone dyke in Rufisque-Est
OBJECTIVE 2: Implement the actions to fight the salinization of agricultural lands used to grow rice in Joal, with the construction of anti-salt dikes
Fund Outcome | Please select from dropdown menu below | Fund Outcome Indicator | Please select from dropdown menu below | Target at CEO Endorsement | Baseline | Mid-term Results | Terminal Results
Outcome 1: Reduced exposure at national level to climate-related hazards and threats Outcome 2: Strengthened institutional capacity to reduce risks associated with climate-induced socioeconomic and environmental losses Outcome 3: Strengthened awareness and ownership of adaptation and climate risk reduction processes at local level Outcome 4: Increased adaptive capacity within relevant development and natural resource sectors Outcome 5: Increased ecosystem resilience in response to climate change and variability-induced stress Outcome 6: Diversified and strengthened livelihoods and sources of income for vulnerable people in targeted areas Outcome 7: Improved policies and regulations that promote and enforce resilience measures | 4 | 1. Relevant threat and hazard information generated and disseminated to stakeholders on a timely basis 2.1. No. and type of targeted institutions with increased capacity to minimize exposure to climate variability risks 2.2. Number of people with reduced risk to extreme weather events 3.1. Percentage of targeted population aware of predicted adverse impacts of climate change, and of appropriate responses 3.2. Modification in behavior of targeted population 4.1. Development sectors' services responsive to evolving needs from changing and variable climate 4.2. Physical infrastructure improved to withstand climate change and variability-induced stress 5. Ecosystem services and natural assets maintained or improved under climate change and variability-induced stress 6.1. Percentage of households and communities having more secure (increased) access to livelihood assets 6.2. Percentage of targeted population with sustained climate-resilient livelihoods 7. Climate change priorities are integrated into national development strategy | 4.2 | 5 | 1 (Rice-growing araes abandoned due to salinization)
Fund Output | Please select from dropdown menu below | Fund Output Indicator | Please select from dropdown menu below | Target at CEO Endorsement | Baseline | Mid-term Results | Terminal Results
Output 1: Risk and vulnerability assessments conducted and updated at a national level Output 2.1: Strengthened capacity of national and regional centres and networks to respond rapidly to extreme weather events Output 2.2: Targeted population groups covered by adequate risk reduction systems Output 3: Targeted population groups participating in adaptation and risk reduction awareness activities Output 4: Vulnerable physical, natural, and social assets strengthened in response to climate change impacts, including variability Output 5: Vulnerable physical, natural, and social assets strengthened in response to climate change impacts, including variability Output 6: Targeted individual and community livelihood strategies strengthened in relation to climate change impacts, including variability Output 7: Improved integration of climate-resilience strategies into country development plans | 4 | 1.1. No. and type of projects that conduct and update risk and vulnerability assessments 1.2. Development of early warning systems 2.1.1. No. of staff trained to respond to, and mitigate impacts of, climate-related events 2.1.2. Capacity of staff to respond to, and mitigate impacts of, climate-related events from targeted institutions increased 2.2.1. Percentage of population covered by adequate risk-reduction systems 2.2.2. No. of people affected by climate variability 3.1 No. and type of risk reduction actions or strategies introduced at local level 3.2 No. of news outlets in the local press and media that have covered the topic 4.1. No. and type of health or social infrastructure developed or modified to respond to new conditions resulting from climate variability and change (by type) 4. 2. No. of physical assets strengthened or constructed to withstand conditions resulting from climate variability and change (by asset types) 5. No. and type of natural resource assets created, maintained or improved to withstand conditions resulting from climate variability and change (by type of assets) 6.1. No. and type of adaptation assets (physical as well as knowledge) created in support of individualor community-livelihood strategies 6.2. Type of income sources for households generated under climate change scenario 7.1. No., type, and sector of policies introduced or adjusted to address climate change risks 7.2. No. or targeted development strategies with incorporated climate change priorities enforced | 4.2 | 5 | No salinity control works
OBJECTIVE 3: Assist local communities of the coastal area of Joal, especially women, in handling fish processing areas of the districts located along the littoral and to conduct awareness programme and training related to adaptation and its adverse effects
Fund Outcome | Please select from dropdown menu below | Fund Outcome Indicator | Please select from dropdown menu below | Target at CEO Endorsement | Baseline | Mid-term Results | Terminal Results
Outcome 1: Reduced exposure at national level to climate-related hazards and threats Outcome 2: Strengthened institutional capacity to reduce risks associated with climate-induced socioeconomic and environmental losses Outcome 3: Strengthened awareness and ownership of adaptation and climate risk reduction processes at local level Outcome 4: Increased adaptive capacity within relevant development and natural resource sectors Outcome 5: Increased ecosystem resilience in response to climate change and variability-induced stress Outcome 6: Diversified and strengthened livelihoods and sources of income for vulnerable people in targeted areas Outcome 7: Improved policies and regulations that promote and enforce resilience measures | 6 | 1. Relevant threat and hazard information generated and disseminated to stakeholders on a timely basis 2.1. No. and type of targeted institutions with increased capacity to minimize exposure to climate variability risks 2.2. Number of people with reduced risk to extreme weather events 3.1. Percentage of targeted population aware of predicted adverse impacts of climate change, and of appropriate responses 3.2. Modification in behavior of targeted population 4.1. Development sectors' services responsive to evolving needs from changing and variable climate 4.2. Physical infrastructure improved to withstand climate change and variability-induced stress 5. Ecosystem services and natural assets maintained or improved under climate change and variability-induced stress 6.1. Percentage of households and communities having more secure (increased) access to livelihood assets 6.2. Percentage of targeted population with sustained climate-resilient livelihoods 7. Climate change priorities are integrated into national development strategy | 6.1 | 4 | 1
Fund Output | Please select from dropdown menu below | Fund Output Indicator | Please select from dropdown menu below | Target at CEO Endorsement | Baseline | Mid-term Results | Terminal Results
Output 1: Risk and vulnerability assessments conducted and updated at a national level Output 2.1: Strengthened capacity of national and regional centres and networks to respond rapidly to extreme weather events Output 2.2: Targeted population groups covered by adequate risk reduction systems Output 3: Targeted population groups participating in adaptation and risk reduction awareness activities Output 4: Vulnerable physical, natural, and social assets strengthened in response to climate change impacts, including variability Output 5: Vulnerable physical, natural, and social assets strengthened in response to climate change impacts, including variability Output 6: Targeted individual and community livelihood strategies strengthened in relation to climate change impacts, including variability Output 7: Improved integration of climate-resilience strategies into country development plans | 6 | 1.1. No. and type of projects that conduct and update risk and vulnerability assessments 1.2. Development of early warning systems 2.1.1. No. of staff trained to respond to, and mitigate impacts of, climate-related events 2.1.2. Capacity of staff to respond to, and mitigate impacts of, climate-related events from targeted institutions increased 2.2.1. Percentage of population covered by adequate risk-reduction systems 2.2.2. No. of people affected by climate variability 3.1 No. and type of risk reduction actions or strategies introduced at local level 3.2 No. of news outlets in the local press and media that have covered the topic 4.1. No. and type of health or social infrastructure developed or modified to respond to new conditions resulting from climate variability and change (by type) 4. 2. No. of physical assets strengthened or constructed to withstand conditions resulting from climate variability and change (by asset types) 5. No. and type of natural resource assets created, maintained or improved to withstand conditions resulting from climate variability and change (by type of assets) 6.1. No. and type of adaptation assets (physical as well as knowledge) created in support of individualor community-livelihood strategies 6.2. Type of income sources for households generated under climate change scenario 7.1. No., type, and sector of policies introduced or adjusted to address climate change risks 7.2. No. or targeted development strategies with incorporated climate change priorities enforced | 6.1 | 2 fish processing areas developed, one fishing dock restored, several awareness raising sessions held | 1 artisanal fish processing area, 1 fish processing area and 1 fishing dock in poor condition, low awareness of climate change effects and adapattaion strategies
OBJECTIVE 4: Communicate on the adaptation, sensitize and train local people on climate change adaptation techniques in coastal areas and on good practices, to avoid an aggravation of the various situations encountered
Fund Outcome | Please select from dropdown menu below | Fund Outcome Indicator | Please select from dropdown menu below | Target at CEO Endorsement | Baseline | Mid-term Results | Terminal Results
Outcome 1: Reduced exposure at national level to climate-related hazards and threats Outcome 2: Strengthened institutional capacity to reduce risks associated with climate-induced socioeconomic and environmental losses Outcome 3: Strengthened awareness and ownership of adaptation and climate risk reduction processes at local level Outcome 4: Increased adaptive capacity within relevant development and natural resource sectors Outcome 5: Increased ecosystem resilience in response to climate change and variability-induced stress Outcome 6: Diversified and strengthened livelihoods and sources of income for vulnerable people in targeted areas Outcome 7: Improved policies and regulations that promote and enforce resilience measures | 3 | 1. Relevant threat and hazard information generated and disseminated to stakeholders on a timely basis 2.1. No. and type of targeted institutions with increased capacity to minimize exposure to climate variability risks 2.2. Number of people with reduced risk to extreme weather events 3.1. Percentage of targeted population aware of predicted adverse impacts of climate change, and of appropriate responses 3.2. Modification in behavior of targeted population 4.1. Development sectors' services responsive to evolving needs from changing and variable climate 4.2. Physical infrastructure improved to withstand climate change and variability-induced stress 5. Ecosystem services and natural assets maintained or improved under climate change and variability-induced stress 6.1. Percentage of households and communities having more secure (increased) access to livelihood assets 6.2. Percentage of targeted population with sustained climate-resilient livelihoods 7. Climate change priorities are integrated into national development strategy | 3.1 | 4 | 2
Fund Output | Please select from dropdown menu below | Fund Output Indicator | Please select from dropdown menu below | Target at CEO Endorsement | Baseline | Mid-term Results | Terminal Results
Output 1: Risk and vulnerability assessments conducted and updated at a national level Output 2.1: Strengthened capacity of national and regional centres and networks to respond rapidly to extreme weather events Output 2.2: Targeted population groups covered by adequate risk reduction systems Output 3: Targeted population groups participating in adaptation and risk reduction awareness activities Output 4: Vulnerable physical, natural, and social assets strengthened in response to climate change impacts, including variability Output 5: Vulnerable physical, natural, and social assets strengthened in response to climate change impacts, including variability Output 6: Targeted individual and community livelihood strategies strengthened in relation to climate change impacts, including variability Output 7: Improved integration of climate-resilience strategies into country development plans | 3 | 1.1. No. and type of projects that conduct and update risk and vulnerability assessments 1.2. Development of early warning systems 2.1.1. No. of staff trained to respond to, and mitigate impacts of, climate-related events 2.1.2. Capacity of staff to respond to, and mitigate impacts of, climate-related events from targeted institutions increased 2.2.1. Percentage of population covered by adequate risk-reduction systems 2.2.2. No. of people affected by climate variability 3.1 No. and type of risk reduction actions or strategies introduced at local level 3.2 No. of news outlets in the local press and media that have covered the topic 4.1. No. and type of health or social infrastructure developed or modified to respond to new conditions resulting from climate variability and change (by type) 4. 2. No. of physical assets strengthened or constructed to withstand conditions resulting from climate variability and change (by asset types) 5. No. and type of natural resource assets created, maintained or improved to withstand conditions resulting from climate variability and change (by type of assets) 6.1. No. and type of adaptation assets (physical as well as knowledge) created in support of individualor community-livelihood strategies 6.2. Type of income sources for households generated under climate change scenario 7.1. No., type, and sector of policies introduced or adjusted to address climate change risks 7.2. No. or targeted development strategies with incorporated climate change priorities enforced | 3.1 | A training and sensitization programme is designed and carried out Adequate communication tools are developed and shared. People are informed, sensitized and trained on the adaptation techniques to climate change en coastal areas The different target groups are trained in the new regulations on the adaptation. | Education on adaptation is still a national priority Adaptation programmes/projects are still devoided of adequate tools for taking up and disseminating learned lessons on community adaptation Cross learning mechanisms are little_known
OBJECTIVE 5: Develop and implement the appropriate regulations for the management of coastal areas
Fund Outcome | Please select from dropdown menu below | Fund Outcome Indicator | Please select from dropdown menu below | Target at CEO Endorsement | Baseline | Mid-term Results | Terminal Results
Outcome 1: Reduced exposure at national level to climate-related hazards and threats Outcome 2: Strengthened institutional capacity to reduce risks associated with climate-induced socioeconomic and environmental losses Outcome 3: Strengthened awareness and ownership of adaptation and climate risk reduction processes at local level Outcome 4: Increased adaptive capacity within relevant development and natural resource sectors Outcome 5: Increased ecosystem resilience in response to climate change and variability-induced stress Outcome 6: Diversified and strengthened livelihoods and sources of income for vulnerable people in targeted areas Outcome 7: Improved policies and regulations that promote and enforce resilience measures | 7 | 1. Relevant threat and hazard information generated and disseminated to stakeholders on a timely basis 2.1. No. and type of targeted institutions with increased capacity to minimize exposure to climate variability risks 2.2. Number of people with reduced risk to extreme weather events 3.1. Percentage of targeted population aware of predicted adverse impacts of climate change, and of appropriate responses 3.2. Modification in behavior of targeted population 4.1. Development sectors' services responsive to evolving needs from changing and variable climate 4.2. Physical infrastructure improved to withstand climate change and variability-induced stress 5. Ecosystem services and natural assets maintained or improved under climate change and variability-induced stress 6.1. Percentage of households and communities having more secure (increased) access to livelihood assets 6.2. Percentage of targeted population with sustained climate-resilient livelihoods 7. Climate change priorities are integrated into national development strategy | 7 | 4 | 2
Fund Output | Please select from dropdown menu below | Fund Output Indicator | Please select from dropdown menu below | Target at CEO Endorsement | Baseline | Mid-term Results | Terminal Results
Output 1: Risk and vulnerability assessments conducted and updated at a national level Output 2.1: Strengthened capacity of national and regional centres and networks to respond rapidly to extreme weather events Output 2.2: Targeted population groups covered by adequate risk reduction systems Output 3: Targeted population groups participating in adaptation and risk reduction awareness activities Output 4: Vulnerable physical, natural, and social assets strengthened in response to climate change impacts, including variability Output 5: Vulnerable physical, natural, and social assets strengthened in response to climate change impacts, including variability Output 6: Targeted individual and community livelihood strategies strengthened in relation to climate change impacts, including variability Output 7: Improved integration of climate-resilience strategies into country development plans | 7 | 1.1. No. and type of projects that conduct and update risk and vulnerability assessments 1.2. Development of early warning systems 2.1.1. No. of staff trained to respond to, and mitigate impacts of, climate-related events 2.1.2. Capacity of staff to respond to, and mitigate impacts of, climate-related events from targeted institutions increased 2.2.1. Percentage of population covered by adequate risk-reduction systems 2.2.2. No. of people affected by climate variability 3.1 No. and type of risk reduction actions or strategies introduced at local level 3.2 No. of news outlets in the local press and media that have covered the topic 4.1. No. and type of health or social infrastructure developed or modified to respond to new conditions resulting from climate variability and change (by type) 4. 2. No. of physical assets strengthened or constructed to withstand conditions resulting from climate variability and change (by asset types) 5. No. and type of natural resource assets created, maintained or improved to withstand conditions resulting from climate variability and change (by type of assets) 6.1. No. and type of adaptation assets (physical as well as knowledge) created in support of individualor community-livelihood strategies 6.2. Type of income sources for households generated under climate change scenario 7.1. No., type, and sector of policies introduced or adjusted to address climate change risks 7.2. No. or targeted development strategies with incorporated climate change priorities enforced | 7.1 | The Environmental Code updated; the littoral law elaborated; the texts are popularized | No (or inadequate) legal materials dealing with the management of the littoral and taking into account the CC Peoples in these areas have very few information about the legal materials

## Units for Indicators
Fund Outcome Indicator Units
1. Generation of relevant data, Stakeholders, and Timeliness 2.1. Include both qualitative and quantitative measures of capacity level within targeted institutions 2.2. Number (men and women and other vulnerable groups) 3.1. Use scale from 1 to 5: 5: Fully aware 4: Mostly aware 3: Partially aware 2: Partially not aware 1: Aware of neither predicted adverse impacts of climate change nor of appropriate responses 3.2. Use scale from 1 to 5: 5: All 4: Almost all 3: Half 2: Some 1: None 4.1. Summarize in an overall scale (1-5): 5: Highly responsive (All defined elements ) 4: Mostly responsive (Most defined elements) 3: Moderately responsive (Some defined elements) 2: Partially responsive (Lacks most elements) 1: Non responsive (Lacks all elements ) 4.2. Summarize in an overall scale (1-5): 5: Fully improved 4: Mostly Improved 3: Moderately improved 2: Somewhat improved 1: Not improved 5. Depends on the targeted natural asset: Biological (species): measure through changes in population numbers (dynamics, structure, etc.) Land: measure changes in hectares. Baseline data will be necessary to estimate the change. Supporting indicators baseline and target (as well as contextual information) are needed such as the following: Farmers adopting recommended technologies, Ha. of land improved, Average deforestation rate Etc. Use scale from 1 to 5. 5: Very effective (All elements are present) 4: Effective (Most elements are present) 3: Moderately effective (Some elements are present) 2: Partially effective (Most elements are not present) 1: Ineffective (No elements are present) 6.1. Summarize in an overall scale (1-5): 5: Very high improvement 4: High improvement 3: Moderate improvement 2: Limited improvement 1: No improvement 6.2. Household income by source of livelihood in project area (USD) prior and post project intervention 7. Summarize in an overall scale (1-5). 5: All (Fully integrated) 4: Most 3: Some 2: Most not integrated 1: None
Fund Output Indicator Units
1.1. Number, sector(s) and level(s) of projects or interventions in separate fields of monitoring plan 1.2. Number 2.1.1. Number of staff (male/female) of targeted institutions: a. Obtain baseline information: total number of staff from targeted institutions b. Define target 2.1.2. Number of staff (male/female) of targeted institutions: a. Obtain baseline information: total number of staff from targeted institutions b. Define target: needs to be defined by project proponents 2.2.1. Quantitative: Percentage (includes women – and other vulnerable groups – and men). Qualitative: Adequacy: include direct analysis of major areas; adequacy/effectiveness of systems or analysis of perceptions of populations and institutions. 2.2.2. Number (broken down by gender and, if possible, by vulnerable groups defined in the area of intervention) of people 3.1. Number and type (in separate columns) at local level. 3.2. Number 4.1. Number and type 4. 2. Number and type (entered in separate columns) 5. Number of interventions by type of natural asset and intervention 6.1. Number and type (in separate columns of monitoring plan) 6.2. Income sources per household; description of income source and number of households. 7.1. Number/Sector 7.2. Number; Effectiveness (see previous indicator) through enforcement level.

## Lessons Learned
QUALITATIVE MEASURES and LESSONS LEARNED
Please Complete the following section every reporting period
Implementation and Adaptive Management | Response
Describe any implementation issues/lessons affecting progress (positive and negative) | Synergy with other projects can be beneficial, but it can also be source of difficulties in implementing with different procedures
Were there any delays in implementation? If so, what are the measures taken to reduce delays? | There were delays in the realization of the protection facility in Rufisque due to slowness in obtaining the no objection from the UEMOA, one of the major partners.
Describe any changes undertaken to improve results on the ground or any changes made to project outputs (i.e. changes to project design)
How have gender considerations been taken into consideration during the reporting period?
Please Complete the following section at mid-term and project completion
Lessons for Adaptation | Response
Climate Resilent Measures
Please Describe the Climate Resilent measures being undertaken by the project/programme.
Which of these masures has been most effective and why?
Which have been least effective and why?
Concrete Adaptaiton Interventions
Please desribe the concrete adaptation measures being undertaken by the project/programme
What are/were the most difficult aspects of implementing such measures?
What are/were the most successful aspects of the implementation of the interventions?
Community/National Impact
What would you consider to be the most successful aspects for the target communities?
What measures are/have been put in place to ensure sustainability of the project/program results?
What measures are being/could have been put in place to improve project/program results?
Knowledge Management
Describe what kind and how existing information/data/knowledge has been used to inform the development and the implementation of the project.
Describe any difficulties there have been in accessing or retrieving existing information (data or knowledge) that is relevant to the project. Please provide suggestions for improving access to the relevant data.
Have the Project Learning Objectives been met? Please describe.
Has the identification of learning objectives contributed to the outcomes of the project? In what why have they contributed?
Note on D10: Daouda Ndiaye: not completed.