## Overview
Project Performance Report (PPR)
| Period of Report (Dates) | February - July 2012
| Project Title: | Adaptation to coastal erosion in vulnerable areas
| Project Summary: | “Adaptation to coastal erosion in vulnerable areas” is a 2 years (2011 / 2012) project financed with 8 619 000 USD by the Adaptation Fund through a one-step approval process. The project document was approved during the 11th meeting of the AF Board (16-17 September 2010) in Bonn and the MOU was signed in 11th November 2010. The main focus of the project is the development of adaptation capacities of communities the most vulnerable to coastal erosion and sea level rising in 3 regions of Senegal, located along the coastline. The principal promoter of the project is the Directorate of Environment, with a strong involvement of CSO (GREEN Senegal and Dynamique Femme) The main components of the project are: - Training and awareness rising - Building up of coastal protection facilities in the areas of Rufisque and Saly - Building an anti-salt dike in Joal - Strengthening of the protection and development of the littoral: beach, fish processing areas - Development, strengthening, and implementation of the regulation on coastal protection and the adaptation to climate change - Communication - Follow-up/Evaluation/Monitoring
|  |  | Countries | Project Type: |  | GEF Focal Area: | GEF 4 Focal Areas | GEF 2 / 3 Operational Programme: | Overall Rating of the project in the evaluation by the project evaluator: | GEF-4 Focal Area Strategic Program: | GEF-3 Focal Area Strategic Program:
| Database Number: |  | Afghanistan | FP | Yes | Biodiversity | 1 | 1 | U | BD-SP1-PA Financing | 1: Arid & semi-arid ecosystems
Implementing Entity (IE) [name]: |  | Centre de Suivi Ecologique (CSE) | Albania | MSP | No | Climate Change Adaptation | 2 | 2 | S | BD-SP2-Marine PA | 2: Coastal, marine & freshwater ecosystems
| Type of IE: | National | Algeria | EA |  | Climate Change Mitigation | 3 | 3 | MU | BD-SP3-PA Networks | 3: Forest ecosystems
| Country(ies): | Senegal | Angola |  |  | International Waters | 5 | 5 | Good | BD-SP5-Markets | 13: Conservation and Sustainable Use of Biological Diversity Important to Agriculture
Relevant Geographic Points (i.e. cities, villages, bodies of water): |  | Senegal | Argentina |  |  | Multiple Focal Area |  |  |  | BD-SP7-Invasive Alien Species(IAS) | 6: Promoting the adoption of renewable energy by removing barriers and reducing implementation costs
[8 empty] | CC-SP2- Industrial EE | 8: Waterbody based operational program
| Project Milestones | [6 empty] | CC-SP3-RE,CC-SP4-Biomass | 9: Integrated Land and Water multiple focal area
| Milestone |  | Bahamas | [6 empty] | CC-SP5-Transport | 10: Contaminants based operational program
AFB Approval Date: |  | 17th September 2010
IE-AFB Agreement Signature Date: |  | 11th November 2010 | [6 empty] | CC-SP6-LULUCF | 12: Integrated Ecosystem Management
Start of Project/Programme: |  | 21st January 2011 | [6 empty] | Cross cutting capacity building | 14: Persistent Organic Pollutants
Mid-term Review Date (if planned): |  | October 2012
| Terminal Evaluation Date: | End of project
|  | List documents/ reports/ brochures / articles that have been prepared about the project. | Cyprus
Czech Republic
List the Website address (URL) of project. |  |  | Democratic People's Republic of Korea
Democratic Republic of the Congo
Denmark
| Project contacts: |  | Djibouti
National Project Manager/Coordinator |  |  | Dominica
| Name: |  | Dominican Republic
| Email: |  | Ecuador
| Date: |  | Egypt
| Government DA |  | El Salvador
| Name: | Ndèye Fatou Guène | Equatoral Guinea
| Email: | mactarguen@yahoo.fr | Eritrea
| Date: | 2010-07-29 | Estonia
| Implementing Entity |  | Ethiopia
| Name: | Directorate of the Environment | Fiji
| Email: | cheikh.syllan@gmail.com | Finland
| Date: | 2011-01-04 | France
| Executing Agency |  | Gambia
| Name: | GREEN Senegal | Georgia
| Email: | greensenegal@orange.sn | Germany
| Date: | 2011-01-05 | Ghana
| Executing Agency |  | Greece
| Name: | Dynamique Femme | Grenada
| Email: | dynfemme@yahoo.fr | Guatemala
| Date: | 2011-01-10 | Guinea
| Executing Agency |  | Guinea Bissau
| Name: |  | Guyana
| Email: |  | Haiti
| Date: |  | Honduras
Hungary
Iceland
India
Indonesia
Iran (Islamic Republic of)
Iraq
Ireland
Israel
Italy
Jamaica
Japan
Jordan
Kazakhstan
Kenya
Kiribati
Kuwait
Kyrgyzstan
Lao People’s Democratic Republic
Latvia
Lebanon
Lesotho
Liberia
Libyan Arab Jamahiriya
Liechtenstein
Lithuania
Luxembourg
Madagascar
Malawi
Malaysia
Maldives
Mali
Malta
Marshall Islands
Mauritania
Mauritius
Mexico
Micronesia, Federated States of
Monaco
Mongolia
Montenegro
Morocco
Mozambique
Myanmar
Namibia
Nauru
Nepal
Netherlands
New Zealand
Nicaragua
Niger
Nigeria
Norway
Oman
Pakistan
Palau
Panama
Papua New Guinea
Paraguay
Peru
Philippines
Poland
Portugal
Qatar
Republic of Korea
Republic of Moldova
Romania
Russian Federation
Rwanda
Saint Kitts and Nevis
Saint Lucia
Saint Vincent and the Grenadines
Samoa
San Marino
Sao Tome and Principe
Saudi Arabia
Senegal
Serbia
Seychelles
Sierra Leone
Singapore
Slovakia
Slovenia
Solomon Islands
Somalia
South Africa
Spain
Sri Lanka
Sudan
Suriname
Swaziland
Sweden
Switzerland
Syrian Arab Republic
Tajikistan
Thailand
The former Yugoslav Republic of Macedonia
Timor-Leste
Togo
Tonga
Trinidad and Tobago
Tunisia
Turkey
Turkmenistan
Tuvalu
Uganda
Ukraine
United Arab Emirates
United Kingdom of Great Britain and Northern Ireland
United Republic of Tanzania
United States of America
Uruguay
Uzbekistan
Vanuatu
Venezuela, Bolivarian Republic of
Viet Nam
Yemen
Zambia
Zimbabwe

## FinancialData
Financial information: cumulative from project start to 22nd August 2012
DISBURSEMENT OF AF GRANT FUNDS
How much of the total AF grant as noted in Project Document plus any project preparation grant has been spent to date?
Estimated cumulative total disbursement as of 22 August 2012 | 3627425.5997
Add any comments on AF Grant Funds. (word limit=200)
EXPENDITURE DATA
List ouput and corresponding amount spent for the current reporting period | ITEM / ACTIVITY / ACTION | AMOUNT
| Action 1.1 : Environmental Impact Assessment for the design of the coastal protection facilities in the area of Rufisque-Est (Thiawlene) | 518.3926
| Action 1.2: Building up of the coastal protection facilities in the areas of Rufisque. The target areas host houses, economic and cultural infrastructure (Fish processing areas, fishing docks, cemeteries, etc.) | 0
| Action 1.3 :Cleaning-up of channels, including awareness raising and training activities (Thiawlene) | 23710.4881
| Action 2.1: Carry out and validate the detailed technical feasibility studies for the design of the protection facilities of the coastal areas of Saly | 30005.6691
| Action 2.2 : Set up the protection facilities of the vulnerable areas covering hotels, people, poor villages, as well as the fishing docks | 29973.4583
| Action 2.3: Assistance in the development of the fishing dock and the fich processing area in Saly | 110213.3496
| Action 3.1: Study and achieve the anti-salt barriers in the rice-growing areas of Joal and the other agricultural crops. | 149704.5536
| Action 3.2: Protect and develop beaches and fish processing areas. | 138275.2395
| Action 3.3: Restore the cleanliness of the beaches | 66667.7622
| Action 3.4: awarness and training programme | 9690.3538
| Action 4.1: Design, fine tune, and strengthen the regulation pertaining to the management of the littoral, by taking into account the CC dimension: Environment Code, other codes and regulations | 17872.1022
| Action 4.2: Dissemination of the elaborated texts | 0
| Action 5.1: Design and implement the awareness and training programme | 12486.2108
| Action 5.2: Fine tune and share the suitable communication tools | 18662.1325
| Action 5.3: Inform, sensitize, and train people on the adaptation techniques to climate change in coastal areas | 2674.9057
| Action 5.4: Train the different target groups on the new regulations on adaptation | 1555.1777
| Action 6.1: Monitoring/ Follow up | 30341.517
| Action 6.2: External Evaluation and audit | 0
| Action 6.3: Controle of realisation | 13452.2871
| TOTAL | 655803.5997
PLANNED EXPENDITURE SCHEDULE
List outputs planned and corresponding projected cost for the upcoming reporting period | ITEM / ACTIVITY / ACTION | PROJECTED COST | Est. Completion Date
| Action 1.2: Building up of the coastal protection facilities in the area of Rufisque. | 967285.57 | January 2013
| Action 1.3 :Cleaning-up of channels (Thiawlene) | 48359.82 | January 2013
| Action 1.3 : Awareness raising (Rufisque) | 17748.09 | January 2013
| Action 1.3 : Trainings on NAPA, organizational dynamics, climate change and fisheries (Rufisque) | 10448.49 | October 2012
| Action 2.1: Rehabilitation of the fishing dock at Saly Coulang | 27035 | Completed
| Action 2.2: Building the protection facilities of the vulnerable areas in Saly | 1609389.83 | January 2013
| Action 2.3: Training (NAPA, climate change and fisheries) and exchange visits (Saly) | 21654.08 | October 2012
| Action 2.3: Awareness raising in Saly (in-home visit, radio programs, meetings with neighbourhood committees, focus-group and social mobilization, communications media) | 8227.62 | January 2013
| Action 2.3: Developing the drying area (Saly) | 2780.91 | September 2012
| Action 2.3: Documenting and building on good practices in adaptation to climate change | 26322.43 | November 2012
| Action 2.3: Monitoring and coordination | 25697.6 | January 2013
| Action 3.1: Building the anti-salt dike in Joal | 306024.43 | August 2012
| Action 3.2: Consolidation of the fishing dock in Joal | 24879.2913 | August 2012
| Action 3.2: Works on the fish processing area in Joal | 543987.401 | January 2013
| Action 3.3: Restore the cleanliness of the beaches | 91196.22 | End of Project
| Action 3.4: awarness and training programme | 26549.77 | October 2012
| Action 4.1: Design, fine tune and strenghten the regulation pertaining to the management of the littoral (Littoral law and environment Code) | 0 | December 2012
| Action 4.2: Dissemination of the elaborated texts | 90000 | January 2013
| Action 5.1: Information and training workshops on climate change | 121802.3 | October 2012
| Action 5.2: Fine tune and share the suitable communication tools | 17196.7 | End of Project
| Action 5.3: Inform, sensitize, and train people on the adaptation techniques to climate change in coastal areas | 27848.17 | January 2013
| Action 5.4: Train the different target groups on the new regulations on adaptation | 58444.82 | January 2013
| Action 6.1: Monitoring/ Follow up | 25000 | End of Project
| Action 6.2: External Evaluation and audit | 45000 | End of project
| Action 6.3: Controle of realisation | 15000 | End of Project
| TOTAL | 4157878.5422
ACTUAL CO-FINANCING (If the MTR or TE have not been undertaken this reporting period, DO NOT report on actual co-financing.)
How much of the total co-financing as committed in the Project Document has actually been realized? | 1338000
Estimated cumulative actual co-financing as verified during Mid-term Review (MTR) or Terminal Evaluation (TE).
Add any comments on actual co-financing in particular any issues related to the realization of in-kind, grant, credits, loans, equity, non-grant instruments and other types of co-financing. (word limit=200)
Note on F41: Déthié Soumaré Ndiaye: this balance wil be used in line 6.3

## Risk Assesment
RISK ASSESMENT
IDENTIFIED RISKS
List all Risks identified in project preparation phase and what steps are being taken to mitigate them
Identified Risk | Current Status | Steps Taken to Mitigate Risk
Efficiency of technical measures adopted to fight coastal erosion | Low | Feasibility studies were realized prior to each contract, clear technical specifications were given in the tender and a stringent control is performed during the realization, both from executing agencies and from the implementing entity.
Management of the project heavily dependent on subcontracting | Low | It was decided that contract award processes are subject to the procedures of the CSE, and no to the ones of the Public Procurement Regulation Agency which is more time consuming. To this end, the manual of procedures of the CSE was updated with the inclusion of an annex on “contracting procedures”. In addition, delegate project managers were hired to assist the project owner (the excuting entities) in the procurement.
Conflict over the management and maintenance of the built infrastructures between local communities, private companies, extension services | Low | Many information and sensitization activities were undertaken toward the different stakeholders, a database on households and their assets is also under elaboration. In addition, many meetings were organized between neighboring local government units in the area of impact of the anti-salt dike to discuss the management of the land resources.
Local communities do not fully participate to the project | No longer relevant | The information, sentitization and mobilization activities were very successfull and local communities are highly committed an involved
Local governments do not accept the project | Low | The local governments are fully associated to the implementation of the activities. They play an imoportant role in mobilising populations and taking decision a bout the location of the facilities. They will aslo be involved in the monitoring and the maintenance of these facilities
Low consciousness of the populations and decision makers with regards to climate change | No longer relevant | The project has implemented an intense comunication and awareness raising programme, targeting all categories of stakeloders and addressing all issues relating to climate change and its impacts
Low impact/application of the Coastal Act |  | It is planned to disseminate the new regulations and the Coastal Act provide for the setting up of a national body for the management of the littoral. One of the mandates of this body will be to ensure the application of the law
Lack of coordination among the executing entities | Low | Regular technical committee meetings are organized to coordinate the interventions, as well as national and local steering committee meetings.
Budget forecasts not adequate, under estimation of the projected line items allocations | medium | A financial component called ‘Divers’ (Miscellaneous) will be integrated and will concentrate 5 per cent of the budget for possible readjustments
Delays in the disbursement of founds, due to length of the chain | Low | There is a good collaboration framework established with the AF Secretariat and a good follow-up after reports are sent, to give any requested clarifications and make sure the disbusrements are done at due time
Critical Risks Affecting Progress (Not identified at project design)
Identify Risks with a 50% or > likelihood of affecting progress of project
Identified Risk | Current Status | Steps Taken to Mitigate Risk
Building of the protection facility and related works dependent on the synergy of interventions with the West African Economic and Monetary Union (WAEMU) | Low | Regular meetings with WAEMU staff, DNA and implementing entities
Difficulties to mobilize populations because of elections scheduled for February 2012 | Medium | Schedule most of the mobilization activities out of the critical period
Conflict between the executing entity and a portion of the population about the site of implantation of the structures in Joal | Low | Sensitization activities and advocacy in the relevant areas
Risks associated with the complexity of maritime works | Low | Take fullest advantage of the dry season and of the calm sea period
The installation of the new Parliament could generate some delays for the adoption of the Littoral law and Environment code, resulting in delays in the training and dissemination programme | Low | The necessary steps will be taken towards the public authorities put priority on these texts at the beginning of the parliamentary session
Risk Measures: Were there any risk mitigation measures employed during the current reporting period? If so, were risks reduced? If not, why were these risks not reduced?
Add any comments relevant to risk mitigation (word limit = 500)

## Rating
RATING ON IMPLEMENTATION PROGRESS
For rating definitions please see bottom of page.
| Progress on Key Milestones |  | Expected Progress |  | Progress to Date | Rating
Project Manager/Coordinator:
Overall Rating
Please Provide the Name and Contact information of person(s) reponsible for completeling the Rating section
Name:
Email:
Please justify your rating. Outline the positive and negative progress made by the project since it started. Provide specific recommendations for next steps. . (word limit=500)
| Progress on Key Milestones |  | Expected Progress |  | Progress to Date | Rating
Implementing Agency | Building coastal protection facility in Thiawlene (Rufisque-Est) |  | Works were supposed to be in adanced stage |  | Works started with the extraction of the blocks of basalt which will be used to realize the facility | S
| Building coastal protection facility in Saly |  | Works were supposed to be launched since December 2011 |  | Studies completed, tender initiated for hiring the company in charge of works was unsuccessfull. A new tender was iniated under urgent procedures | MS
| Rehabilitation of fish processing areas in Saly Coulang |  | Completed |  | Completed | S
| Building anti-salt-dike in Joal |  | Works were supposed to be in a final stage |  | Works in a final stage | S
| Developement of the fish processing area and fishing dock in Joal |  | Works were supposed to be completed |  | Works in a final stage | S
| Formulation of the law on littoral and revision of the Environmental Code |  | Was supposed to be completed in the first year |  | The littoral law and the Environmental Code already passed the stage of the Supreme Court. It is awaiting adoption by the Council of Ministers and the examination before the Parliament. The Environment Code was already discussed by the relevant authorities and is awaiting and examination in plenary at the Secretariat of the Government and consideration by the Supreme Court | MS
| Awareness raising |  | Good knowledge of the project, its objectives and its activities in the areas of intervention |  | Good level of implementation | HS
[5 empty] | Overall Rating | S
Please Provide the Name and Contact information of person(s) reponsible for completing the Rating section
| Name: | Assize Toure
| Email: | assize@cse.sn
| Progress on Key Milestones |  | Expected Progress |  | Progress to Date | Rating
Other
Overall Rating
Please Provide the Name and Contact information of person(s) reponsible for completeling the Rating section
Name:
Email:
| Please justify your rating and address the following points: 1. Indicate trends, both positive and negative, in achievement of outcomes as per the project indicators. 2. Detail critical risks that have affected progress. 3. Outline response to MTR undertaken this reporting period. 4. Outline action plan to address projects with a rating of HU, U or MU. Please keep your input to 1200 words |  | To date, the awareness raising activities have been implemented with a good rhythm. The construction work were launched in the 3 areas of intervention and most of them are completed or in a final stage (rehabilitation and protection of the fishing dock in Joal, building the anti-salt dike in Joal, rehabilitation of the fish processinh area in Saly). Regarding the fish processing area of Khelcom (Joal), a prototype of improved stove was realized and approved and a tender was initiated for the rehabilitation of the site. Nevertheless, there could be some delays (about 3 months) for the adoption and dissemination of the new regulations and for the completion of the protection works in Saly.The first call for tender for the protection facility in Saly has been unsccessfull (due to technical inadequacy in the specifications, shown by a complementary study) and was relaunched under urgent procedure. By the time it was relaunched, we received a letter from the Central Directorate for public procurement complaining that the normal 30-days deadline was not observed and thatthe tender was not posted on their web portal. So it took us some additional days to have a mmeting with them and then, prepare an answer explaining that it was an urgent procedure(they did not read carefuly) and that referring to the CSE procedures handobook, we do not have necessarily to post it on their web portal. The tender is being relaunched now.
Rating Definitions
|  |  | Highly Satisfactory (HS) | Project actions/activities planned for current reporting period are progressing on track or exceeding expectations to acheive all major outcomes/outputs for given reporting period, without major shortcomings. The project can be presented as “good practice”.
|  |  | Satisfactory (S) | Project actions/activities planned for current reporting period are progressing on track to achieve most of its major outcomes/outputs with only minor shortcomings.
|  |  | Marginally Satisfactory (MS) | Project actions/activities planned for current reporting period are progressing on track to achieve most major relevant outcomes/outputs, but with either significant shortcomings or modest overall relevance.
|  |  | Marginally Unsatisfactory (MU) | Project actions/activities planned for current reporting period are not progressing on track to achieve major outcomes/outputs with major shortcomings or is expected to achieve only some of its major outcomes/outputs.
|  |  | Unsatisfactory (U) | Project actions/activities planned for current reporting period are not progressing on track to achieve most of its major outcomes/outputs.
|  |  | Highly Unsatisfactory (U) | Project actions/activities planned for current reporting period are not on track and shows that it is failing to achieve, and is not expected to achieve, any of its outcomes/outputs.

## Project Indicators
PROJECT Indicators
Please provide all indicators being tracked for the project as outlined in the project document
Type of Indicator (indicators towards Objectives, Outcomes, etc…)
Type of Indicator | Indicator | Baseline | Progress since inception | Target for Project End
| Indicator 1.1: number of study report | One study report validated for Rufisque | Completed | The detailed technical feasibility studies for the protection of the coastal areas of Rufisque are updated
| Indicator 1.2: Length of protected coast (in linear meter) | 6,000 square kilometres of areas threatened by flood | The company in charge of the works was hired and has received instructions to begin works, field was opened, detailed planning completed, the plan of the facility was elaborated, extracting raw materials in preparation, the geotextilewas oredred and already delivered | The protection works of the coastal areas of Rufisque are built (381 linear meter of wall built through the Adaptation Fund )
| indicator.1. 3: Linear number of cleaned up channels | Coastal facilities and human settlements facing high threats | Cleaning of the shoreline, clearing of conduits (400 linear meters), removing waste materials | The waste ways of rainwater are cleaned up and connected to the sea
| Indicator 2.1: Study Reports | No study made | Completed | The detailed technical feasibility studies for the protection of the coastal areas of Saly are completed and validated
| Indicator: 2.2. Length of the coast protected (in linear metre) | 3 square kilometres of areas threatened by flood | The first call for tender for hiring the company in charge of works was fruitless. Another call for tender is to be launched very soon | The protection works of the coastal areas of Saly are completed
| Indicator 2. 3 Existence of a sound fishing dock and a good fish processing area | Destruction of fishing docks and fish processing areas due to sea-level rise | Works completed | The development of the fishing dock and the fish processing area in Saly is done
| Indicator 3.1. Study reports, number of curbs and dikes built | Rice-growing activities affected by intrusion of saline waters; drainage of rice growing areas difficult | Works in its final stage (completed at 85%) | The technical studies and the dikes to prevent salt intrusion into the rice-growing areas of Joal are done
| Indicator: 3.2.1. The curbs for protected beaches and the fish processing areas are developed | The beach is used as lavatory and the waste management system is very poor | A collecting system was estabilished, along with salubrity committees. About seventy five cleaning operations were organized, a prototype of improved stove as realized and validated, a call for the submission of proposals was issued and the proposals are under evaluation | The protection and development of beaches and fish processing areas are completed
Indicator 3.2.2. The setting up of a rational and effective waste management programme in the beach is completed
| Indicator 4.1. Number and nature of the legal materials drawn up and in force | No (or inadequate) legal materials dealing with the management of the littoral and taking into account the CC | The littoral law and the Environmental Code already passed the stage of the Supreme Court. It is awaiting adoption by the Council of Ministers and the examination before the Parliament. The Environment Code was already discussed by the relevant authorities and is awaiting and examination in plenary at the Secretariat of the Government and consideration by the Supreme Court | The legal materials dealing with the management of the littoral and taking into account the CC dimension are drawn up
| Indicator 4.2. Number of popularization sessions and participants | Peoples in these areas have very few information about the legal materials | Not started yet | The texts drawn up are popularized
| Indicator 5.1. Study Report | Education on adaptation is still a national priority | Regional committees for adaptation to climate change (COMREC) were estabilished by Order of the Governors and the capacity building neeeds were identified. The TORs for the training session are already elaborated. | A training and sensitization programme is designed and carried out
| Indicator 5.2. Number and nature of the communication tools developed | Adaptation programmes/projects are still devoided of adequate tools for taking up and disseminating learned lessons on community adaptation | A draft of communication strategy was elaborated, a web site developed and 1 film produced. A press visit was organized on the project's sites. | Adequate communication tools are developed and shared
| Indicator 5. 3. Number of sensitization sessions/workshops held or participants | Cross learning mechanisms are little_known | 1313 sensitization sessions (in-home visits, focus-group, social mibilization, 104 radio programs, advocacy, traditional wrestling), 16 information panels installed | People are informed, sensitized and trained on the adaptation techniques to climate change en coastal areas
| Indicator 5. 4. Number of training sessions/workshops or participants | Cross learning mechanisms are little_known | 5 training sessions organized, followed by 10 restitutions | The different target groups are trained in the new regulations on the adaptation

## Lessons Learned
QUALITATIVE MEASURES and LESSONS LEARNED
Please complete the following section every reporting period
Implementation and Adaptive Management | Response
What implementation issues/lessons, either positive or negative, affected progress? | Synergy with other projects can be beneficial, but it can also be source of difficulties in implementing with different procedures. The other actors in Rufisque have fundings from donors with different procedures and different requirements. During critical times, theses specificities could generate some blockages
Were there any delays in implementation? If so, include any causes of delays. What measures have been taken to reduce delays? | It is expected some delays for the protection works in Saly. After the first call for tender was unsuccessful, the seond one was initiated using an urgent procedure.
Describe any changes undertaken to improve results on the ground or any changes made to project outputs (i.e. changes to project design)
How have gender considerations been taken into consideration during the reporting period? What have been the lessons learned as a consequence of inclusion of such considerations on project performance or impacts?
Please complete the following section at mid-term and project completion
Lessons for Adaptation | Response
Climate Resilience Measures
What have been the lessons learned, both positive and negative, in implementing climate adaptation measures that would be relevant to the design and implementation of future projects/programmes for enhanced resilience to climate change?
What is the potential for the climate resilience measures undertaken by the project/programme to be replicated and scaled up both within and outside the project area?
Concrete Adaptation Interventions
What have been the lessons learned, both positive and negative, in implementing concrete adaptation interventions that would be relevant to the design and implementation of future projects/programmes implementing concrete adaptation interventions?
What is the potential for the concrete adaptation interventions undertaken by the project/programme to be replicated and scaled up both within and outside the project area?
Community/National Impact
What would you consider to be the most successful aspects for the target communities?
What measures are/have been put in place to ensure sustainability of the project/program results?
What measures are being/could have been put in place to improve project/program results?
Knowledge Management
How has existing information/data/knowledge been used to inform project development and implementation? What kinds of information/data/knowledge were used?
If learning objectives have been established, have they been met? Please describe.
Describe any difficulties there have been in accessing or retrieving existing information (data or knowledge) that is relevant to the project. Please provide suggestions for improving access to the relevant data.
Has the identification of learning objectives contributed to the outcomes of the project? In what ways have they contributed?

## Results Tracker
Results Tracker for Adaptation Fund (AF) Projects
Goal: Assist developing-country Parties to the Kyoto Protocol that are particularly vulnerable to the adverse effects of climate change in meeting the costs of concrete adaptation projects and programmes in order to implement climate-resilient measures. Impact: Increased resiliency at the community, national, and regional levels to climate variability and change.
Important: Please read the following Results Framework and Baseline Guidance (also posted on the Adaptation Fund website) before entering your data
Link: http://www.adaptation-fund.org/sites/default/files/Results%20Framework%20and%20Baseline%20Guidance%20final.pdf
Please select the relevant Fund level Outcome and Output indicators that allign with the project objectives and outcomes
OBJECTIVE 1: Implement the actions to protect the coastal areas of Rufisque, Saly, and Joal against erosion, with the aim to protect houses and the economic infrastructures threatened by the erosion including fish processing areas, fishing docks, tourism or cultural infrastructures, and restore lost or threatened activities
Fund Outcome | Please select from dropdown menu below | Fund Outcome Indicator | Please select from dropdown menu below | Target at CEO Endorsement (see Units in next sheet) | Baseline (see Units in next sheet) | Mid-term Results | Terminal Results
Outcome 1: Reduced exposure at national level to climate-related hazards and threats Outcome 2: Strengthened institutional capacity to reduce risks associated with climate-induced socioeconomic and environmental losses Outcome 3: Strengthened awareness and ownership of adaptation and climate risk reduction processes at local level Outcome 4: Increased adaptive capacity within relevant development and natural resource sectors Outcome 5: Increased ecosystem resilience in response to climate change and variability-induced stress Outcome 6: Diversified and strengthened livelihoods and sources of income for vulnerable people in targeted areas Outcome 7: Improved policies and regulations that promote and enforce resilience measures | 4 | 1. Relevant threat and hazard information generated and disseminated to stakeholders on a timely basis 2.1. No. and type of targeted institutions with increased capacity to minimize exposure to climate variability risks 2.2. Number of people with reduced risk to extreme weather events 3.1. Percentage of targeted population aware of predicted adverse impacts of climate change, and of appropriate responses 3.2. Modification in behavior of targeted population 4.1. Development sectors' services responsive to evolving needs from changing and variable climate 4.2. Physical infrastructure improved to withstand climate change and variability-induced stress 5. Ecosystem services and natural assets maintained or improved under climate change and variability-induced stress 6.1. Percentage of households and communities having more secure (increased) access to livelihood assets 6.2. Percentage of targeted population with sustained climate-resilient livelihoods 7. Climate change priorities are integrated into national development strategy | 4.2 | 5 | 1 (Nothing in Saly and a very rudimentary stone dyke in Rufisque)
Fund Output | Please select from dropdown menu below | Fund Output Indicator | Please select from dropdown menu below | Target at CEO Endorsement (see Units in next sheet) | Baseline (see Units in next sheet) | Mid-term Results | Terminal Results
Output 1: Risk and vulnerability assessments conducted and updated at a national level Output 2.1: Strengthened capacity of national and regional centres and networks to respond rapidly to extreme weather events Output 2.2: Targeted population groups covered by adequate risk reduction systems Output 3: Targeted population groups participating in adaptation and risk reduction awareness activities Output 4: Vulnerable physical, natural, and social assets strengthened in response to climate change impacts, including variability Output 5: Vulnerable physical, natural, and social assets strengthened in response to climate change impacts, including variability Output 6: Targeted individual and community livelihood strategies strengthened in relation to climate change impacts, including variability Output 7: Improved integration of climate-resilience strategies into country development plans | 4 | 1.1. No. and type of projects that conduct and update risk and vulnerability assessments 1.2. Development of early warning systems 2.1.1. No. of staff trained to respond to, and mitigate impacts of, climate-related events 2.1.2. Capacity of staff to respond to, and mitigate impacts of, climate-related events from targeted institutions increased 2.2.1. Percentage of population covered by adequate risk-reduction systems 2.2.2. No. of people affected by climate variability 3.1 No. and type of risk reduction actions or strategies introduced at local level 3.2 No. of news outlets in the local press and media that have covered the topic 4.1. No. and type of health or social infrastructure developed or modified to respond to new conditions resulting from climate variability and change (by type) 4. 2. No. of physical assets strengthened or constructed to withstand conditions resulting from climate variability and change (by asset types) 5. No. and type of natural resource assets created, maintained or improved to withstand conditions resulting from climate variability and change (by type of assets) 6.1. No. and type of adaptation assets (physical as well as knowledge) created in support of individualor community-livelihood strategies 6.2. Type of income sources for households generated under climate change scenario 7.1. No., type, and sector of policies introduced or adjusted to address climate change risks 7.2. No. or targeted development strategies with incorporated climate change priorities enforced | 4.2 | 2 coastal protection facilities | 0 protection facility in Saly, 1 rudimentary stone dyke in Rufisque-Est
OBJECTIVE 2: Implement the actions to fight the salinization of agricultural lands used to grow rice in Joal, with the construction of anti-salt dikes
Fund Outcome | Please select from dropdown menu below | Fund Outcome Indicator | Please select from dropdown menu below | Target at CEO Endorsement | Baseline | Mid-term Results | Terminal Results
Outcome 1: Reduced exposure at national level to climate-related hazards and threats Outcome 2: Strengthened institutional capacity to reduce risks associated with climate-induced socioeconomic and environmental losses Outcome 3: Strengthened awareness and ownership of adaptation and climate risk reduction processes at local level Outcome 4: Increased adaptive capacity within relevant development and natural resource sectors Outcome 5: Increased ecosystem resilience in response to climate change and variability-induced stress Outcome 6: Diversified and strengthened livelihoods and sources of income for vulnerable people in targeted areas Outcome 7: Improved policies and regulations that promote and enforce resilience measures | 4 | 1. Relevant threat and hazard information generated and disseminated to stakeholders on a timely basis 2.1. No. and type of targeted institutions with increased capacity to minimize exposure to climate variability risks 2.2. Number of people with reduced risk to extreme weather events 3.1. Percentage of targeted population aware of predicted adverse impacts of climate change, and of appropriate responses 3.2. Modification in behavior of targeted population 4.1. Development sectors' services responsive to evolving needs from changing and variable climate 4.2. Physical infrastructure improved to withstand climate change and variability-induced stress 5. Ecosystem services and natural assets maintained or improved under climate change and variability-induced stress 6.1. Percentage of households and communities having more secure (increased) access to livelihood assets 6.2. Percentage of targeted population with sustained climate-resilient livelihoods 7. Climate change priorities are integrated into national development strategy | 4.2 | 5 | 1 (Rice-growing araes abandoned due to salinization)
Fund Output | Please select from dropdown menu below | Fund Output Indicator | Please select from dropdown menu below | Target at CEO Endorsement | Baseline | Mid-term Results | Terminal Results
Output 1: Risk and vulnerability assessments conducted and updated at a national level Output 2.1: Strengthened capacity of national and regional centres and networks to respond rapidly to extreme weather events Output 2.2: Targeted population groups covered by adequate risk reduction systems Output 3: Targeted population groups participating in adaptation and risk reduction awareness activities Output 4: Vulnerable physical, natural, and social assets strengthened in response to climate change impacts, including variability Output 5: Vulnerable physical, natural, and social assets strengthened in response to climate change impacts, including variability Output 6: Targeted individual and community livelihood strategies strengthened in relation to climate change impacts, including variability Output 7: Improved integration of climate-resilience strategies into country development plans | 4 | 1.1. No. and type of projects that conduct and update risk and vulnerability assessments 1.2. Development of early warning systems 2.1.1. No. of staff trained to respond to, and mitigate impacts of, climate-related events 2.1.2. Capacity of staff to respond to, and mitigate impacts of, climate-related events from targeted institutions increased 2.2.1. Percentage of population covered by adequate risk-reduction systems 2.2.2. No. of people affected by climate variability 3.1 No. and type of risk reduction actions or strategies introduced at local level 3.2 No. of news outlets in the local press and media that have covered the topic 4.1. No. and type of health or social infrastructure developed or modified to respond to new conditions resulting from climate variability and change (by type) 4. 2. No. of physical assets strengthened or constructed to withstand conditions resulting from climate variability and change (by asset types) 5. No. and type of natural resource assets created, maintained or improved to withstand conditions resulting from climate variability and change (by type of assets) 6.1. No. and type of adaptation assets (physical as well as knowledge) created in support of individualor community-livelihood strategies 6.2. Type of income sources for households generated under climate change scenario 7.1. No., type, and sector of policies introduced or adjusted to address climate change risks 7.2. No. or targeted development strategies with incorporated climate change priorities enforced | 4.2 | 5 | No salinity control works
OBJECTIVE 3: Assist local communities of the coastal area of Joal, especially women, in handling fish processing areas of the districts located along the littoral and to conduct awareness programme and training related to adaptation and its adverse effects
Fund Outcome | Please select from dropdown menu below | Fund Outcome Indicator | Please select from dropdown menu below | Target at CEO Endorsement | Baseline | Mid-term Results | Terminal Results
Outcome 1: Reduced exposure at national level to climate-related hazards and threats Outcome 2: Strengthened institutional capacity to reduce risks associated with climate-induced socioeconomic and environmental losses Outcome 3: Strengthened awareness and ownership of adaptation and climate risk reduction processes at local level Outcome 4: Increased adaptive capacity within relevant development and natural resource sectors Outcome 5: Increased ecosystem resilience in response to climate change and variability-induced stress Outcome 6: Diversified and strengthened livelihoods and sources of income for vulnerable people in targeted areas Outcome 7: Improved policies and regulations that promote and enforce resilience measures | 6 | 1. Relevant threat and hazard information generated and disseminated to stakeholders on a timely basis 2.1. No. and type of targeted institutions with increased capacity to minimize exposure to climate variability risks 2.2. Number of people with reduced risk to extreme weather events 3.1. Percentage of targeted population aware of predicted adverse impacts of climate change, and of appropriate responses 3.2. Modification in behavior of targeted population 4.1. Development sectors' services responsive to evolving needs from changing and variable climate 4.2. Physical infrastructure improved to withstand climate change and variability-induced stress 5. Ecosystem services and natural assets maintained or improved under climate change and variability-induced stress 6.1. Percentage of households and communities having more secure (increased) access to livelihood assets 6.2. Percentage of targeted population with sustained climate-resilient livelihoods 7. Climate change priorities are integrated into national development strategy | 6.1 | 4 | 1
Fund Output | Please select from dropdown menu below | Fund Output Indicator | Please select from dropdown menu below | Target at CEO Endorsement | Baseline | Mid-term Results | Terminal Results
Output 1: Risk and vulnerability assessments conducted and updated at a national level Output 2.1: Strengthened capacity of national and regional centres and networks to respond rapidly to extreme weather events Output 2.2: Targeted population groups covered by adequate risk reduction systems Output 3: Targeted population groups participating in adaptation and risk reduction awareness activities Output 4: Vulnerable physical, natural, and social assets strengthened in response to climate change impacts, including variability Output 5: Vulnerable physical, natural, and social assets strengthened in response to climate change impacts, including variability Output 6: Targeted individual and community livelihood strategies strengthened in relation to climate change impacts, including variability Output 7: Improved integration of climate-resilience strategies into country development plans | 6 | 1.1. No. and type of projects that conduct and update risk and vulnerability assessments 1.2. Development of early warning systems 2.1.1. No. of staff trained to respond to, and mitigate impacts of, climate-related events 2.1.2. Capacity of staff to respond to, and mitigate impacts of, climate-related events from targeted institutions increased 2.2.1. Percentage of population covered by adequate risk-reduction systems 2.2.2. No. of people affected by climate variability 3.1 No. and type of risk reduction actions or strategies introduced at local level 3.2 No. of news outlets in the local press and media that have covered the topic 4.1. No. and type of health or social infrastructure developed or modified to respond to new conditions resulting from climate variability and change (by type) 4. 2. No. of physical assets strengthened or constructed to withstand conditions resulting from climate variability and change (by asset types) 5. No. and type of natural resource assets created, maintained or improved to withstand conditions resulting from climate variability and change (by type of assets) 6.1. No. and type of adaptation assets (physical as well as knowledge) created in support of individualor community-livelihood strategies 6.2. Type of income sources for households generated under climate change scenario 7.1. No., type, and sector of policies introduced or adjusted to address climate change risks 7.2. No. or targeted development strategies with incorporated climate change priorities enforced | 6.1 | 2 fish processing areas developed, one fishing dock restored, several awareness raising sessions held | 1 artisanal fish processing area, 1 fish processing area and 1 fishing dock in poor condition, low awareness of climate change effects and adapattaion strategies
OBJECTIVE 4: Communicate on the adaptation, sensitize and train local people on climate change adaptation techniques in coastal areas and on good practices, to avoid an aggravation of the various situations encountered
Fund Outcome | Please select from dropdown menu below | Fund Outcome Indicator | Please select from dropdown menu below | Target at CEO Endorsement | Baseline | Mid-term Results | Terminal Results
Outcome 1: Reduced exposure at national level to climate-related hazards and threats Outcome 2: Strengthened institutional capacity to reduce risks associated with climate-induced socioeconomic and environmental losses Outcome 3: Strengthened awareness and ownership of adaptation and climate risk reduction processes at local level Outcome 4: Increased adaptive capacity within relevant development and natural resource sectors Outcome 5: Increased ecosystem resilience in response to climate change and variability-induced stress Outcome 6: Diversified and strengthened livelihoods and sources of income for vulnerable people in targeted areas Outcome 7: Improved policies and regulations that promote and enforce resilience measures | 3 | 1. Relevant threat and hazard information generated and disseminated to stakeholders on a timely basis 2.1. No. and type of targeted institutions with increased capacity to minimize exposure to climate variability risks 2.2. Number of people with reduced risk to extreme weather events 3.1. Percentage of targeted population aware of predicted adverse impacts of climate change, and of appropriate responses 3.2. Modification in behavior of targeted population 4.1. Development sectors' services responsive to evolving needs from changing and variable climate 4.2. Physical infrastructure improved to withstand climate change and variability-induced stress 5. Ecosystem services and natural assets maintained or improved under climate change and variability-induced stress 6.1. Percentage of households and communities having more secure (increased) access to livelihood assets 6.2. Percentage of targeted population with sustained climate-resilient livelihoods 7. Climate change priorities are integrated into national development strategy | 3.1 | 4 | 2
Fund Output | Please select from dropdown menu below | Fund Output Indicator | Please select from dropdown menu below | Target at CEO Endorsement | Baseline | Mid-term Results | Terminal Results
Output 1: Risk and vulnerability assessments conducted and updated at a national level Output 2.1: Strengthened capacity of national and regional centres and networks to respond rapidly to extreme weather events Output 2.2: Targeted population groups covered by adequate risk reduction systems Output 3: Targeted population groups participating in adaptation and risk reduction awareness activities Output 4: Vulnerable physical, natural, and social assets strengthened in response to climate change impacts, including variability Output 5: Vulnerable physical, natural, and social assets strengthened in response to climate change impacts, including variability Output 6: Targeted individual and community livelihood strategies strengthened in relation to climate change impacts, including variability Output 7: Improved integration of climate-resilience strategies into country development plans | 3 | 1.1. No. and type of projects that conduct and update risk and vulnerability assessments 1.2. Development of early warning systems 2.1.1. No. of staff trained to respond to, and mitigate impacts of, climate-related events 2.1.2. Capacity of staff to respond to, and mitigate impacts of, climate-related events from targeted institutions increased 2.2.1. Percentage of population covered by adequate risk-reduction systems 2.2.2. No. of people affected by climate variability 3.1 No. and type of risk reduction actions or strategies introduced at local level 3.2 No. of news outlets in the local press and media that have covered the topic 4.1. No. and type of health or social infrastructure developed or modified to respond to new conditions resulting from climate variability and change (by type) 4. 2. No. of physical assets strengthened or constructed to withstand conditions resulting from climate variability and change (by asset types) 5. No. and type of natural resource assets created, maintained or improved to withstand conditions resulting from climate variability and change (by type of assets) 6.1. No. and type of adaptation assets (physical as well as knowledge) created in support of individualor community-livelihood strategies 6.2. Type of income sources for households generated under climate change scenario 7.1. No., type, and sector of policies introduced or adjusted to address climate change risks 7.2. No. or targeted development strategies with incorporated climate change priorities enforced | 3.1 | A training and sensitization programme is designed and carried out Adequate communication tools are developed and shared. People are informed, sensitized and trained on the adaptation techniques to climate change en coastal areas The different target groups are trained in the new regulations on the adaptation. | Education on adaptation is still a national priority Adaptation programmes/projects are still devoided of adequate tools for taking up and disseminating learned lessons on community adaptation Cross learning mechanisms are little_known
OBJECTIVE 5: Develop and implement the appropriate regulations for the management of coastal areas
Fund Outcome | Please select from dropdown menu below | Fund Outcome Indicator | Please select from dropdown menu below | Target at CEO Endorsement | Baseline | Mid-term Results | Terminal Results
Outcome 1: Reduced exposure at national level to climate-related hazards and threats Outcome 2: Strengthened institutional capacity to reduce risks associated with climate-induced socioeconomic and environmental losses Outcome 3: Strengthened awareness and ownership of adaptation and climate risk reduction processes at local level Outcome 4: Increased adaptive capacity within relevant development and natural resource sectors Outcome 5: Increased ecosystem resilience in response to climate change and variability-induced stress Outcome 6: Diversified and strengthened livelihoods and sources of income for vulnerable people in targeted areas Outcome 7: Improved policies and regulations that promote and enforce resilience measures | 7 | 1. Relevant threat and hazard information generated and disseminated to stakeholders on a timely basis 2.1. No. and type of targeted institutions with increased capacity to minimize exposure to climate variability risks 2.2. Number of people with reduced risk to extreme weather events 3.1. Percentage of targeted population aware of predicted adverse impacts of climate change, and of appropriate responses 3.2. Modification in behavior of targeted population 4.1. Development sectors' services responsive to evolving needs from changing and variable climate 4.2. Physical infrastructure improved to withstand climate change and variability-induced stress 5. Ecosystem services and natural assets maintained or improved under climate change and variability-induced stress 6.1. Percentage of households and communities having more secure (increased) access to livelihood assets 6.2. Percentage of targeted population with sustained climate-resilient livelihoods 7. Climate change priorities are integrated into national development strategy | 7 | 4 | 2
Fund Output | Please select from dropdown menu below | Fund Output Indicator | Please select from dropdown menu below | Target at CEO Endorsement | Baseline | Mid-term Results | Terminal Results
Output 1: Risk and vulnerability assessments conducted and updated at a national level Output 2.1: Strengthened capacity of national and regional centres and networks to respond rapidly to extreme weather events Output 2.2: Targeted population groups covered by adequate risk reduction systems Output 3: Targeted population groups participating in adaptation and risk reduction awareness activities Output 4: Vulnerable physical, natural, and social assets strengthened in response to climate change impacts, including variability Output 5: Vulnerable physical, natural, and social assets strengthened in response to climate change impacts, including variability Output 6: Targeted individual and community livelihood strategies strengthened in relation to climate change impacts, including variability Output 7: Improved integration of climate-resilience strategies into country development plans | 7 | 1.1. No. and type of projects that conduct and update risk and vulnerability assessments 1.2. Development of early warning systems 2.1.1. No. of staff trained to respond to, and mitigate impacts of, climate-related events 2.1.2. Capacity of staff to respond to, and mitigate impacts of, climate-related events from targeted institutions increased 2.2.1. Percentage of population covered by adequate risk-reduction systems 2.2.2. No. of people affected by climate variability 3.1 No. and type of risk reduction actions or strategies introduced at local level 3.2 No. of news outlets in the local press and media that have covered the topic 4.1. No. and type of health or social infrastructure developed or modified to respond to new conditions resulting from climate variability and change (by type) 4. 2. No. of physical assets strengthened or constructed to withstand conditions resulting from climate variability and change (by asset types) 5. No. and type of natural resource assets created, maintained or improved to withstand conditions resulting from climate variability and change (by type of assets) 6.1. No. and type of adaptation assets (physical as well as knowledge) created in support of individualor community-livelihood strategies 6.2. Type of income sources for households generated under climate change scenario 7.1. No., type, and sector of policies introduced or adjusted to address climate change risks 7.2. No. or targeted development strategies with incorporated climate change priorities enforced | 7.1 | The Environmental Code updated; the littoral law elaborated; the texts are popularized | No (or inadequate) legal materials dealing with the management of the littoral and taking into account the CC Peoples in these areas have very few information about the legal materials

## Units for Indicators
Fund Outcome Indicator Units
1. Generation of relevant data, Stakeholders, and Timeliness 2.1. Include both qualitative and quantitative measures of capacity level within targeted institutions 2.2. Number (men and women and other vulnerable groups) 3.1. Use scale from 1 to 5: 5: Fully aware 4: Mostly aware 3: Partially aware 2: Partially not aware 1: Aware of neither predicted adverse impacts of climate change nor of appropriate responses 3.2. Use scale from 1 to 5: 5: All 4: Almost all 3: Half 2: Some 1: None 4.1. Summarize in an overall scale (1-5): 5: Highly responsive (All defined elements ) 4: Mostly responsive (Most defined elements) 3: Moderately responsive (Some defined elements) 2: Partially responsive (Lacks most elements) 1: Non responsive (Lacks all elements ) 4.2. Summarize in an overall scale (1-5): 5: Fully improved 4: Mostly Improved 3: Moderately improved 2: Somewhat improved 1: Not improved 5. Depends on the targeted natural asset: Biological (species): measure through changes in population numbers (dynamics, structure, etc.) Land: measure changes in hectares. Baseline data will be necessary to estimate the change. Supporting indicators baseline and target (as well as contextual information) are needed such as the following: Farmers adopting recommended technologies, Ha. of land improved, Average deforestation rate Etc. Use scale from 1 to 5. 5: Very effective (All elements are present) 4: Effective (Most elements are present) 3: Moderately effective (Some elements are present) 2: Partially effective (Most elements are not present) 1: Ineffective (No elements are present) 6.1. Summarize in an overall scale (1-5): 5: Very high improvement 4: High improvement 3: Moderate improvement 2: Limited improvement 1: No improvement 6.2. Household income by source of livelihood in project area (USD) prior and post project intervention 7. Summarize in an overall scale (1-5). 5: All (Fully integrated) 4: Most 3: Some 2: Most not integrated 1: None
Fund Output Indicator Units
1.1. Number, sector(s) and level(s) of projects or interventions in separate fields of monitoring plan 1.2. Number 2.1.1. Number of staff (male/female) of targeted institutions: a. Obtain baseline information: total number of staff from targeted institutions b. Define target 2.1.2. Number of staff (male/female) of targeted institutions: a. Obtain baseline information: total number of staff from targeted institutions b. Define target: needs to be defined by project proponents 2.2.1. Quantitative: Percentage (includes women – and other vulnerable groups – and men). Qualitative: Adequacy: include direct analysis of major areas; adequacy/effectiveness of systems or analysis of perceptions of populations and institutions. 2.2.2. Number (broken down by gender and, if possible, by vulnerable groups defined in the area of intervention) of people 3.1. Number and type (in separate columns) at local level. 3.2. Number 4.1. Number and type 4. 2. Number and type (entered in separate columns) 5. Number of interventions by type of natural asset and intervention 6.1. Number and type (in separate columns of monitoring plan) 6.2. Income sources per household; description of income source and number of households. 7.1. Number/Sector 7.2. Number; Effectiveness (see previous indicator) through enforcement level.