## Overview
Project Performance Report (PPR)
| Period of Report (Dates) | 1/1/2015- 31/12/2015
| Project Title: | Climate Change Adaptation Programme in Water and Agriculture in Anseba Region, Eritrea.
| Project Summary: | The objective of the project is to: ''to increase community resilience and adaptive capacity to climate change through an integrated water management and agricultural development approach in the Sub-zoba Hamelmalo and Habero, Anseba region, Eritrea.'' The Hamelmalo and Hebero sub zobas are bisected by the Anseba River. Large part of these areas has been deforested and the rugged topography is exposed to severe soil erosions reducing the top soil and making the forest and woodland regeneration difficult. The two sub regions have been identified as having vulnerable livelihood system, low agricultural productivity and ranked among the most top five zobas affected by food insecurity due increased impact of climate change and rainfall variability. This project is designed to enhance the availability of water for increased productivity and to develop the adaptive capacity of vulnerable communities by expanding small scale irrigation to increase agricultural production and to conserve water and soil through rangeland development. The project comprises of four key outcomes as follows: 1. Increased water availability and erosion control through groundwater recharge, rainwater harvesting, irrigation and soil and water conservation measures. It comprises Construction of sub-surface dam associated with pumping and irrigation water distribution facilities, construction of two micro dams to retain and store rainfall runoff and soil and water conservation measures implemented to improve runoff management and infiltration. 2. Climate resilient agricultural and livestock production enhanced. This focus on a range of climate resilient agricultural technologies and methods developed and transferred to farmers like drought and disease resistant varieties, integrated crop-livestock production system, conservation agriculture, agroforestry, rangeland management; and traditional improved fuel efficient stove. Seasonal forecast used a farmer-led collaborative action learning process to enhance adaptive capacity and climate proof production system. 3. Improved climate risk information and climate monitoring used to raise awareness and enhance community preparedness to climate change. This mainly emphasis on the improved climate risk information generated and capacity developed for climate monitoring and analysis. Awareness raised at different levels on climate change risks facing zoba Anseba 4. Knowledge management system established and knowledge management activities implemented. This component consists of establishment of knowledge management system and implementation of knowledge management activities, and implementation of policy advocacy activities.
|  |  | Countries | Project Type: |  | GEF Focal Area: | GEF 4 Focal Areas | GEF 2 / 3 Operational Programme: | Overall Rating of the project in the evaluation by the project evaluator: | GEF-4 Focal Area Strategic Program: | GEF-3 Focal Area Strategic Program:
| Database Number: |  | Afghanistan | FP | Yes | Biodiversity | 1 | 1 | U | BD-SP1-PA Financing | 1: Arid & semi-arid ecosystems
Implementing Entity (IE) [name]: |  | UNDP | Albania | MSP | No | Climate Change Adaptation | 2 | 2 | S | BD-SP2-Marine PA | 2: Coastal, marine & freshwater ecosystems
| Type of IE: | MIE | Algeria | EA |  | Climate Change Mitigation | 3 | 3 | MU | BD-SP3-PA Networks | 3: Forest ecosystems
| Country(ies): | Eritrea | Angola |  |  | International Waters | 5 | 5 | Good | BD-SP5-Markets | 13: Conservation and Sustainable Use of Biological Diversity Important to Agriculture
Relevant Geographic Points (i.e. cities, villages, bodies of water): |  | Hamelmalo and Habero | Argentina |  |  | Multiple Focal Area |  |  |  | BD-SP7-Invasive Alien Species(IAS) | 6: Promoting the adoption of renewable energy by removing barriers and reducing implementation costs
[8 empty] | CC-SP2- Industrial EE | 8: Waterbody based operational program
| Project Milestones | [6 empty] | CC-SP3-RE,CC-SP4-Biomass | 9: Integrated Land and Water multiple focal area
| Milestone |  | Bahamas | [6 empty] | CC-SP5-Transport | 10: Contaminants based operational program
AFB Approval Date: |  | 2011-03-18
IE-AFB Agreement Signature Date: |  | 2011-04-26 | [6 empty] | CC-SP6-LULUCF | 12: Integrated Ecosystem Management
Start of Project/Programme: |  | 2012-11-06 | [6 empty] | Cross cutting capacity building | 14: Persistent Organic Pollutants
Mid-term Review Date (if planned): |  | 2016-03-06
| Terminal Evaluation Date: | 2018-06-06
|  | List documents/ reports/ brochures / articles that have been prepared about the project. | Cyprus
|  | Inception report Enviromental Impact Assesment Field report Eritrean Journal Progress Report ERITV (Eritrean Television) UNDP50Microsite Africa Page HAN@Geeskaafrika.com | Czech Republic
List the Website address (URL) of project. |  |  | Democratic People's Republic of Korea
|  | www.adaptation-fund.org | Democratic Republic of the Congo
Denmark
| Project contacts: |  | Djibouti
National Project Manager/Coordinator |  |  | Dominica
| Name: | Mr. Ghebremeskel Tewolde ( Ministry of Agriculture) | Dominican Republic
| Email: | anejigna@yahoo.com | Ecuador
| Date: | 2013-08-01 | Egypt
| Government DA |  | El Salvador
| Name: | Mr Mogos Woldeyohannes Bairu, DG Dept of Environment; Ministry of Land, Water and Environment | Equatoral Guinea
| Email: | m.bairu@gmail.com | Eritrea
| Date: | 2013-08-01 | Estonia
| Implementing Entity |  | Ethiopia
| Name: | Adam Habteab | Fiji
| Email: | adam.habteab@undp.org | Finland
| Date: | 2013-08-01 | France
| Executing Agency |  | Gambia
| Name: | Ali Mohammed (Governor-Anseba Regional Administration) | Georgia
| Email: | Tel 401003 amohammed@yahoo.com | Germany
| Date: | 2013-08-01 | Ghana
| Executing Agency |  | Greece
| Name: |  | Grenada
| Email: |  | Guatemala
| Date: |  | Guinea
| Executing Agency |  | Guinea Bissau
| Name: |  | Guyana
| Email: |  | Haiti
| Date: |  | Honduras
Hungary
Iceland
India
Indonesia
Iran (Islamic Republic of)
Iraq
Ireland
Israel
Italy
Jamaica
Japan
Jordan
Kazakhstan
Kenya
Kiribati
Kuwait
Kyrgyzstan
Lao People’s Democratic Republic
Latvia
Lebanon
Lesotho
Liberia
Libyan Arab Jamahiriya
Liechtenstein
Lithuania
Luxembourg
Madagascar
Malawi
Malaysia
Maldives
Mali
Malta
Marshall Islands
Mauritania
Mauritius
Mexico
Micronesia, Federated States of
Monaco
Mongolia
Montenegro
Morocco
Mozambique
Myanmar
Namibia
Nauru
Nepal
Netherlands
New Zealand
Nicaragua
Niger
Nigeria
Norway
Oman
Pakistan
Palau
Panama
Papua New Guinea
Paraguay
Peru
Philippines
Poland
Portugal
Qatar
Republic of Korea
Republic of Moldova
Romania
Russian Federation
Rwanda
Saint Kitts and Nevis
Saint Lucia
Saint Vincent and the Grenadines
Samoa
San Marino
Sao Tome and Principe
Saudi Arabia
Senegal
Serbia
Seychelles
Sierra Leone
Singapore
Slovakia
Slovenia
Solomon Islands
Somalia
South Africa
Spain
Sri Lanka
Sudan
Suriname
Swaziland
Sweden
Switzerland
Syrian Arab Republic
Tajikistan
Thailand
The former Yugoslav Republic of Macedonia
Timor-Leste
Togo
Tonga
Trinidad and Tobago
Tunisia
Turkey
Turkmenistan
Tuvalu
Uganda
Ukraine
United Arab Emirates
United Kingdom of Great Britain and Northern Ireland
United Republic of Tanzania
United States of America
Uruguay
Uzbekistan
Vanuatu
Venezuela, Bolivarian Republic of
Viet Nam
Yemen
Zambia
Zimbabwe

## FinancialData
Financial information: cumulative from project start to [insert date]
DISBURSEMENT OF AF GRANT FUNDS
How much of the total AF grant as noted in Project Document plus any project preparation grant has been spent to date?
Estimated cumulative total disbursement as of [31/12/2015] | 3536103.67
Add any comments on AF Grant Funds. (word limit=200) | This disbursement is relatively high as at 31 December, 2015 (98% of the total allocated budget for the reporting period USD 861,624.75 out of 877,145.00 has been utilised).
INVESTMENT INCOME | So far no significant Return on Investment has been achieved. However, it is anticipated that such return on investment will be attained in the coming years when the ongoing project investment is fully implemented and get matured (in the mid-to long term project impact).
Amount of annual investment income generated from the Adaptation Fund’s grant
EXPENDITURE DATA
List ouput and corresponding amount spent for the current reporting period | ITEM / ACTIVITY / ACTION | AMOUNT
| Output: 1:1 | 358781.24
| out put 1.2 | 120982
| out put 1.4 (COA 72115,72305) | 140000
Output 1.3 (COA 72105)
| Outcome 1 subtotal | 619763.24
Outcome 2
| out put 2:1 | 129125.6
| Output 3.1 (COA 72220) $55000 Effected,25000 Encumbered) | 35979.4
| Output 4.1 | 35568.15
| Execution Costs | 41188.36
| TOTAL | 861624.75
PLANNED EXPENDITURE SCHEDULE
List outputs planned and corresponding projected cost for the upcoming reporting period | ITEM / ACTIVITY / ACTION | PROJECTED COST | Est. Completion Date
| 1.1: Groundwater recharged and irrigation technologies implemented for crop and forage production by developing a sub-surface dam within the Anseba River | 40,000.00 Preparation technical design of for sub surface dan and associated facilities and irrigation technology in Hamelmalo. | 2016
| 1.3: One micro dam will be constructed to retain and store rainfall run-off and to enable higher cereal and forage production levels as well as supply of water for livestock | 535,000.00 Construction of micro dam and sb surface dam in Habero. | 2016
| 1.4: Soil and water conservation measures implemented to improve runoff management and infiltration for improved rangeland management and enhanced cereal production | 165,000.00 Construct hillside terraces along contours in identified locations, using stone-faced hillside terrace in Sub Zoba Habero and Hamelmalo to establish woodlots. . | 2016
| 1.4.3 Construct check dams to slow down the speed of stream flow and check further gully formation, using appropriate materials depending upon the severity of the damage and gully formation in the catchment area. Check dam construction will be carried out by beneficiary communities through Cash for Work (CFW) | 665,000.00 Construct Sub surface dams to slow down the speed of stream flow ( through communities cash for work scheme) in Hamelmalo | 2016
| 1.4.7 Establishement of one new nursery station in Habero an rehabilitate the existing one in Hamelmalo | 100000 Establish one new tree seedling and forage legumes nursery in Habero and rehabilitate the existing one in Hamelmalo | 2016
| 2.1 A range of climate-resilient agricultural technologies and methods developed and transferred to farmers | 55,000.00 Enhance capacity and effectiveness of agricultural extension agents through training,Develop and provide a range of options to farmers on climate-resilient technologies for enhanced and sustainable crop productivity, including agroforestry, In 2016 we will continue on provision training and support for construction and installation of improve energy-efficient stoves. | 2016
| 2.1.3 provide a range of options to agro-pastoralists specifically targeting women-headed households on climate resilient technologies for enhanced livestock and range land management | 115,000.00 provide a range of options to agro-pastoralists specifically targeting women-headed households on climate resilient technologies for enhanced livestock and range land management | 2016
| 2.1.4 Provide training and support for the construction and installation of traditional improved energy-efficient stoves | 280,000.00 Procurement and installation of solar home lighting in Sub Zoba Hamelmalo and Habero | 2016
| 3.1 Improved climate risk information generated and capacity developed for climate monitoring and analysis | 25,000.00 Staff trained on taking meteorological readings, standardised recording and reporting at zoba and sub zoba level User-friendly knowledge dissemination products developed and disseminated using improved climate risk information | 2016
| 3.2 Awareness raised at different levels on climate change risks facing Zoba Anseba | 10,000.00 Train community members in data collection, carry out institutional strengthening to establish community-based early warning | 2016
| Project Management | 26,500.00 Operating expenses | 2016
| TOTAL |  | 2016500
ACTUAL CO-FINANCING (If the MTR or TE have not been undertaken this reporting period, DO NOT report on actual co-financing.)
How much of the total co-financing as committed in the Project Document has actually been realized?
Estimated cumulative actual co-financing as verified during Mid-term Review (MTR) or Terminal Evaluation (TE).
Add any comments on actual co-financing in particular any issues related to the realization of in-kind, grant, credits, loans, equity, non-grant instruments and other types of co-financing. (word limit=200)

## Risk Assesment
RISK ASSESMENT
IDENTIFIED RISKS
List all Risks identified in project preparation phase and what steps are being taken to mitigate them
Identified Risk | Current Status | Steps Taken to Mitigate Risk
Severe drought or other extreme weather events (HIGH) | Eritrea already has an extreme climate and adaptation project intervensions are geared towards these extremes. (MODERATE) | Metrological equipment procured from international and local market and installed in November. Climate information is essential to managing risks especially in the agricultural and smallholder sector. Climate data interpretation and modelling using additional meteorological equipment is crucial to provide daily agromet products, early warning for extreme weather events such as floods and storms, and longer term projections for the trends in the country. This will have a bearing on decisions made on infrastructure and policies. Weather Stations and additional meteorological equipment allow ground truthing of satellite data and improves accuracy of forecasting which in turn will inform the programme activities on crop diversification, adapted seed choices, and guide activities such as rainwater harvesting, climate smart agricultural practices.
Low human and institutional capacity for the implementation of CC-related interventions. ( MODERATE) | Capacity is low for Outcome 3 of the project: climate risk information and community preparedness systems. For all other Outcomes there is sufficient expertise to implement the project. ( LOW) | Carry out an international procurement to bring in expertise to help develop capacity in GoE to design climate risk information systems for use by local communities.
Failure of zoba administration to institutionalise early warning system and meterological/climate observation components. (MODERATE) | Activities to implement the climate monitoring and risk information aspects of the project have not yet begun. However, capacities in GoE would benefit from support. ( MODERATE) | Carry out an international procurement to bring in expertise to help develop capacity in GoE to design climate risk information systems for use by local communities.
Migration of human and livestock population under conditions of extreme severity to localities with a better natural resource base. ( LOW) | Project is intended to provide resilient livelihood opportunities for local communities which will help stem migration. ( LOW) | Even though two micro dams were constructed to mitigate the human migration in search water for livestock, with the population growth the demand is high and a design is completed to construct extra dams. The project shows a tremendous result in mitigation of human migration by promoting irrigation and diversion scheme development; therefore, currently 75 farmers are practicing sedentary farming/irrigation farming.
Accessibility and communications in the programme ( LOW) | For extension agents once Outcome 3 begins implementation: Off road motorbikes for extension agents and mobile phones/radio for communities (MODERATE) | Since the project sites are in a very remote area with no proper road, line for electricity, telephone …. Purchase of motorbikes and mobile phones/radio communication is required.
Potential conflict with neighbouring Ethiopia. ( LOW) | No war no peace' situation still prevails. (Low) | Beyond the project scope.
Critical Risks Affecting Progress (Not identified at project design)
Identify Risks with a 50% or > likelihood of affecting progress of project
Identified Risk | Current Status | Steps Taken to Mitigate Risk
Shortage of feed, water and health of the dairy cows (Low) | hybride dairy cows which are adaptive to existing climate condition of the area, were distributed to farmers (Low) | In order to mitigate the feed shoratge a diversion structure and wells constructed and the flood conveyed to the farm to irrigate animal feed & improve the water point for livestock. On the health issue a veterinary expert assigned in the project area, moreover, farmers were also given training and awareness programme on livestck management (Destocking & restocking)
Delays in programme implementation, particularly for infrastructure. - Unavailability of cement is a bottleneck for preceding the construction works. - Lack of machinery - Unavailability of climate expert at zoba level has influenced hitting the objective of the project. As it’s already mentioned in the project objective the main task of the climate expert is to support the community in upgrading their resilience and adaptive capacity to climate change. (Low) | The budget of the project was released during the rainy season which was not convenient to implement the proposed dam construction. It's opted to transfer the budget allocated for 2015 to 2016 (Low) | Some delays in programme implementation were experienced during the reporting year which were largely attributed to the delays in AWP approval and lengthy cash transfer system in place. A letter was sent to the Ministry of National Development and the Ministry of Land Water and Environment to request them to help mitigate these problems. Moreover, to try to find better ways and means towards expeditious implementation of the project, consultations were conducted between the ministry of National Development, Ministry of Land, Water & Environment, UNDP, Bank of Eritrea and the Commercial Bank of Eritrea. These efforts are showing some signs of improvement through the problem has yet to be solved fundamentally.
Groundwater level dropping and salinisation of wells leading to potential scarcity and competition, possibly leading to conflict (Low) | Ground water rechargeed and salinization of the wells reduced (Low) | Two micro dams and one diversion structure has been constructed and soil and water conservation structures constructed on the upper catchment of the dams and wells to slow down the run off and allows the flood to perculate.
Price escalation and unavailability of commodities and materials (Moderate) | Inflation is extremely high prices esclate by almost 40% for all construction materials and goods. The reason for inflation particularly on goods, construction materials, equipment , fuel etc is due to the import limitation set by the government and shortage thereof of items readily available in the market. (Moderate) | The implementing partner has already submiitted BoQ for all required materials to the concerned Ministries and Government agencies. Discussions has been going on to resolve the problem and speed up implementation.
Risk Measures: Were there any risk mitigation measures employed during the current reporting period? If so, were risks reduced? If not, why were these risks not reduced?
Add any comments relevant to risk mitigation (word limit = 500)
As such so far no mitigation measures has been employed, however, in the management of the project, at each stage of the procurement/implementation cycle the potential risks are being foreseen and proactive actions are being adopted towards the achievement of the overall goal.

## Rating
RATING ON IMPLEMENTATION PROGRESS
For rating definitions please see bottom of page.
| Progress on Key Milestones |  | Expected Progress |  | Progress to Date |  | Rating
Project Manager/Coordinator: | 1.1: Groundwater recharged and irrigation technologies implemented for crop and forage production by developing a sub-surface dam within the Anseba River |  | Sub-surface dam with pumping and irrigation water distribution facilities completed. Forage production per ha on irrigated land increased. |  | As part of groundwater recharge and irrigation development, a reservoir with a capacity of 314 M3 was constructed, 2.25 Km of 90mm pipe and 1.5Km of 75mm pipe were installed in the farms. Moreover, in order to mitigate water loss during distribution a hydrant was applied to the water pipes at 30 meter intervals. Integration of irrigation and climate smart agricultural production technologies was introduced as part of the Integrated Minimum Agricultural Package (IMAP) scheme of the project. Improved crop varieties were distributed to farmers which included maize, sorghum, millet, fruits (mangoes, lemon and banana), vegetables (tomatoes and onions) and forage crops (alfalfa). The farmers have been able to develop 75ha of farm land. Agricultural production and productivity have significantly increased contributing to improved livelihood of many households in the local community. To ensure long term sustainability of the development work, farmers are organizing themselves and establishing associations mandated with coordination of equitable and efficient irrigation water management and use and to oversee other agricultural activities such as pest surveillance and control. |  | HS
| 1.2.: Floodwater harvested to enable irrigation of rain-fed cereal production and rangelands. |  | Diversion weir location identified. Topographic map prepared and diversion structures constructed. |  | As a continuation of diversion structures construction of the project area, a secondary canal that helps to distribute floodwater to the farms was constructed. Construction of this canal helped to increase the area under agricultural development by 50% bringing the figure to 75ha. Most of the planted crops which include field crops, fruits and vegetables are in good condition. Many of the farmers have already started selling their agricultural products (onion, okra, maize, pumpkin, lemon, tomato, milk and animal fodder) to the local market generating significant household cash income. |  | HS
| Output 1.4: Soil and water conservation measures implemented to improve runoff management and infiltration for improved rangeland management and enhanced cereal production. |  | Tree nursery daily workers recruited and seedlings production materials supplied. Site for soil and water conservation identified and consevation structure designed. |  | The nursery site located at Zeron in sub zoba Hamelmalo was renovated to reinstate and enhance its tree seedlings production capacity. The nursery site has a potential of propagating half a million of different types of seedlings. 13 nursery site workers were recruited to manage and produce seedlings to be distributed to the local communities. The nursery maintenance and operational costs are covered by the project. During the reporting year, around 44,000 seedlings of different species have been distributed to the surrounding farmers. As part and parcel of the restoration and conservation of the local natural resources soil and water conservation structures have been constructed with active participation of the local communities. Apart from these physical works, biological measures were also implemented by sisal tree species which have high economic value to the local communities. The specific conservation activities carried out are outlined as follows: 1. Terraces: 175.02km 2. Check dam: 3061.9m3 3. Pitting: 19,740 pits 4. Tree planting: 26,004 tree seedlings 5. A total of 28,819 community members have participated in this soil and water conservation activities out of which 37% were women. |  | S
| 2.1 A range of climate-resilient agricultural technologies and methods developed and transferred to farmers |  | Farmlands for the implementation of climate-resilient agricultura technologies and methods assessed and selected. Beneficiaries of this scheme identified. Livestock breed and seeds adaptation survey conducted. |  | The Minimum Integrated Agricultural package which is being implemented in the project area, as part and parcel of the wider project programme, is aimed at promoting household food security through provision of essential agricultural inputs to the project beneficiaries. The package includes provision of 1dairy cow, 2beehives, 25chicks, some citrus and vegetable seeds, some forage seeds, moringa tree and fuel woods tree species for each individual beneficiary. Farmers of the sub zoba Habero planted around 100ha of farmland with improved variety of pearl millet during the last cropping (HAC) season. Assessment conducted by the HAC in collaboration with the farmers clearly indicated that the crop performed very well under the highly scarce and small amount of rainfall prevalent in the area. Witnessing this very good results, farmers of the area are embracing and adopting the improved pearl millet variety as one mechanism of adaption to climate change and ensuring food security. In order to enhance awareness on the benefits of the technology and share experience a one-day farmers’ field day was conducted bringing together different key stakeholder. 42 farmers from sub-zoba Habero, and 30 experts and extension agents representing MoA, MoLWE, HAC and NARI participated in the event. There is great interest among the farmers to adopt the technology in a more scale and have also recommended that the adoption of crop variety also be replicated and adopted in other areas with similar climatological condition. |  | S
| 3.2 Awareness raised at different levels on climate change risks facing Zoba Anseba |  | Trainees on climate change risks selected in consultation with Adminstration of Anseba Region. TOR for trainers developed. |  | A 10-days training workshop on GIS projection and mapping was given to technical experts from Departments of Agriculture and land, finance and infrastructure and mapping of Anseba Region. 20 experts undergone the training which will help them to enhance their capacity to do land use planning and natural resources management. |  | S
| 3.3 Community preparedness enhanced through development of a community-based early warning system in sub-zobas Hamelmalo and Habero |  |  |  | Not included in the signed AWP of 2015
| 4.1 Knowledge management system established and knowledge management activities implemented |  | Training modules identified and designed with technical support from Hamelemalo Agricultural College. |  | In order to enhance farmers awareness and knowledge about partnership development and understand the rationale for extension service, and how this system work linking the farmers and the research communities, a five-day training workshop was given to farmers representing each kebebis/districts within the sub-zoba Habero and Hamelmalo. The training was given by the Hamelmalo Agricultural College (HAC). |  | s
| 4.2 Policy advocacy activities implemented |  |  |  | Not included in the signed AWP of 2015
[5 empty] | Overall Rating | S | S
Please Provide the Name and Contact information of person(s) reponsible for completeling the Rating section
| Name: | Gebremeskel Tewolde (National Project Coordinator)
| Email: | anejigna@yahoo.com
It can be assessed that the project has been able to achieve good results. The dams and diversion structures were constructed before rain season, and this helped to harvest the rain and diverted the flood to the farm. Consequently, enough water has been conserved/stored, and crop production and productivity in the diversion fed farms increased. A total of 98ha of land that has been previously abandoned land has been put under irrigated agriculture. The crops that have been cropped included: maize, sorghum, millet, fruits (mangoes, lemon and banana), vegetables (tomatoes and onions) and forage for animals (alfalfa). Under the minimum integrated agricultural package, 50 women headed households were provided with a package of 1 dairy cow, 25 chickens and 2 beehives to each of them. Moreover, it is assessed that the ongoing soil and water conservation and natural resource management work have significantly contributed to increased local ground water resources. The local communities are increasingly benefiting from the enrichment of the groundwater in the form of water supply for domestic use, livestock and irrigation water. Overall the project has been able to execute 90% of the activities of the annual work plan for the reporting period (2015).
Please justify your rating. Outline the positive and negative progress made by the project since it started. Provide specific recommendations for next steps. . (word limit=500)
| Progress on Key Milestones |  | Expected Progress |  | Progress to Date | Rating
| according the annual work plan, the project has achieved much physical work activities. |  | In 2015, the project will have a varity of activities from all its planned outputs and much more tangible results are expected to be achieved by timely implementation and active collaboration of key stakeholders. |  | I have visited the project area and observed that the project has been able to accomplish impressive work during the reporting period. Moreover, it is assessed that the project has executed about 90% of the annual work plan development activities. To mention some of the major activities accomplished: 1. Two micro-dams have been constructed in Wazentet and Gebsie villages which are providing all year round water supply for domestic use, and livestock. 2. A diversion structure with a capacity of 314m3 has also been constructed. Villages of Fiza, Lemayte and Aretay are benefiting from this diversion structure where about 400 to 500 households are now engaged in crop and livestock farming with the support of solar powered irrigation. 3. A total of 98ha of land that has previously been abandoned is now under irrigation scheme. Farmers are producing different types of crops including maize, sorghum, millet, fruits, vegetables and forage for animals (alfalfa and elephant grass). 4. Local assessments and farmers report indicate that crop production and productivity have significantly increased that the communities are no longer receiving food rations from the government. 5. Moreover, many farmers have also been able to produce surplus and sell this in the local market. | S
Implementing Agency
S
Please Provide the Name and Contact information of person(s) reponsible for completeling the Rating section
| Name: | Adam Habteab (UNDP)
| Email: | adam.habteab@undp.org
| Progress on Key Milestones |  | Expected Progress |  | Progress to Date | Rating
| I have been closely monitoring its implementation. I have found out that the project has done well and achieved its intended results. |  | Selected outcomes as per the AWP of the project will be realized and the project will hit its goals. |  | 1. Design and construction of micro dams, diversion structures, well renovations and installation of solar pumps for irrigation, 2. Dissemination of drought tolerant, heat tolerant and early matured crops, establishment of meteorological station, 3. Dissemination of improved stoves, baseline survey, Rehabilitation of nursery, 4. Soil and water conservation, afforestation activities, enclosure protection activities, etc. were undertaken. | S
Other
[5 empty] | Overall Rating | S
Please Provide the Name and Contact information of person(s) reponsible for completeling the Rating section
| Name: | Ali Mohammed (Governor-Anseba Regional Administration)
Email:
| Please justify your rating and address the following points: 1. Indicate trends, both positive and negative, in achievement of outcomes as per the project indicators. 2. Detail critical risks that have affected progress. 3. Outline response to MTR undertaken this reporting period. 4. Outline action plan to address projects with a rating of HU, U or MU. Please keep your input to 1200 words |  | My assessment of the project is very positive. Though the project had started late in July, the progress made to date is very satisfactory. I observe high dedication on the part of the project implementers including project staff and other key stakeholders. In my view, the project has already demonstrated that it can be a model that can potentially be replicated and up-scaled. I am confident that the project will be able to accomplish all its outcome objectives in the coming two years. (Governor’ letter was translated from Tigrigna/local language)
Rating Definitions
|  |  | Highly Satisfactory (HS) | Project actions/activities planned for current reporting period are progressing on track or exceeding expectations to acheive all major outcomes/outputs for given reporting period, without major shortcomings. The project can be presented as “good practice”.
|  |  | Satisfactory (S) | Project actions/activities planned for current reporting period are progressing on track to achieve most of its major outcomes/outputs with only minor shortcomings.
|  |  | Marginally Satisfactory (MS) | Project actions/activities planned for current reporting period are progressing on track to achieve most major relevant outcomes/outputs, but with either significant shortcomings or modest overall relevance.
|  |  | Marginally Unsatisfactory (MU) | Project actions/activities planned for current reporting period are not progressing on track to achieve major outcomes/outputs with major shortcomings or is expected to achieve only some of its major outcomes/outputs.
|  |  | Unsatisfactory (U) | Project actions/activities planned for current reporting period are not progressing on track to achieve most of its major outcomes/outputs.
|  |  | Highly Unsatisfactory (U) | Project actions/activities planned for current reporting period are not on track and shows that it is failing to achieve, and is not expected to achieve, any of its outcomes/outputs.

## Project Indicators
PROJECT Indicators
Please provide all indicators being tracked for the project as outlined in the project document
Type of Indicator (indicators towards Objectives, Outcomes, etc…)
Type of Indicator | Indicator | Baseline | Progress since inception | Target for Project End
Outcome 1 | Outcome indicator: Change in level of renewable water resources used in programme area Indicator 1.1.1: Sub-surface dam with associated pumping and irrigation water distribution facilities completed Indicator 1.1.2: Number of households of agropastoralists using the water supply to increase their agricultural and rangeland productivity by twenty-fold Indicator 1.2.1: Number of hectares of rangeland that become fully under supplementary irrigation and have an increased productivity of 40% Indicator 1.2.2: Number of hectares of cereal production that are converted to be fully under supplementary irrigation Indicator 1.2.3: Number of hectares of the dominant cereal crops (sorghum and pearl millet) that have an increased production of from 0.36 (baseline) tons per hectare to 0.7 tons per hectare Indicator 1.3.1: Number of hectares of cereal production that is converted to be fully under supplementary irrigation and in which the production of the dominant cereal crops (sorghum and pearl millet) is increased from 0.36 tons per hectare (baseline) to 1.0 tons per hectare Indicator 1.3.2 Increase in forage production per ha of irrigated land. Indicator 1.3.3: Amount of time spent in search of water and forage for livestock. Indicator 1.4.1: Livestock carrying capacity of rangelands under this protection and rehabilitation programme Indicator 1.4.2: Agricultural production of farm lands under the on farm soil and water conservation programme Indicator 1.4.3: Percentage of households migrating to other areas due to climatic shock | Only about 1 Million cubic meters is put in use. 1)Integrated water/agriculture adaptation actions are not implemented, Eritrea’s rural areas will continue to experience increasing vulnerability and growing insecurity, due to decreased availability of water and conflicts between crop and livestock uses. This will damage the social fabric in rural areas. 2)Communities in the two zobas have serious shortage of water supply. | 2015 - As continuation of solar installation diversion extension works completed to irrigate aadditional 25ha (Total 75ha)of land which is situated in sub zoba Habero particularly in fiza, a reservoir with a capacity of 314 M3 is constructed and HDPE pipe with all accessories purchased. Around 2.25 Km of 90mm pipe has been lied in the main canal of the farm. By the end of 2015, the project had constructed 2 micro-dams and 1 diversion structure to enhance renewable water resources used in programme area. This year, additional 1 micro-dam and one sub-surface dam will be built. These water harvesting structures are believed to significantly contribute towards enriching the renewable water resources in the area and meeting the project target by the end of the project cycle. 2014 - Enviromental Impact Assesment and social/Economic/ Enviromental baseline study (BLS) conducted and final report submitted. Workshop organised on 04/11/2014 to review , discuss and finalised the report. Stakeholders from Min of Land, Water and Environment, Min of Agriculture, Sub Region Adminstration, UNDP and Hamelmalo Agricultural College participated in the workshop. Construction of Diversion Structure: In two sites of sub zoba Habero (Fiza and Lemayeta) started, 90% of the proposed activities completed. A diversion weir completed ( Weir dimension 132M lomg, 5.7M wall height, 3.2M depth, 3.15M width). Besides 306 Meters of canal constructed in two diversion area 136 Lemayeta and 170M Fiza) 8 diversion gates with a dimension of 2M*1.5M and pointing of structure underway. This diversion structure serve to supply water for irrigating 124ha (200HH). | 5.3 million cubic meters of renewable water resources used in programme area (an increase of 4.3 million m3). Achieved by building two micro dams constructed to retain and store rainfall run-off and to enable higher cereal and forage production levels as well as supply of water for livestock.
2014- As part of promoting irrigation scheme a full set of solar irrigation is installed to irrigate 50ha of land. Two solar pumps with a capacity of 7.5kw each 48 modules of 180 watt capacity with all accessories are fixed to generate power.10rolls of HDPE pipe with 90mm, 100m length a total of 1000M pipe . Gil pipe total length of 300M , 10 rolls ,33mm ,700M cable with 35M3 and 1000M is buried in order to protect the solar array from any damage and human interference.this system will minimise the farm expenses for purchasing fuel.
Technical Design and bill of quantity completed. A bid document is prepared and submitted to bidders.
Two microdams with a capacity of 320,000m3 have been constructed . The dam served to provide an access of water for livestock and human and for the enriching of the ground water.
Outcome2 | Outcome indicator: Change in food security in the programme area as a result of using climate resilient agricultural and livestock production methods, measured as# of months per year additionally covered by local production Indicator 2.1.1 Number of project beneficiaries involved in capacity development for implementation of specific agricultural and/or livestock adaptation measures, disaggregated according to gender Indicator 2.1.2: Number of professionals involved in capacity development to enable rolling out of climate-resilient agricultural production technologies and methods, disaggregated according to gender Indicator 2.1.3: Percent change in beneficiaries’ capacities to make resource management decisions based on climate information Indicator 2.1.4: Increased agricultural and livestock production as a result of implementing climate-resilient technologies and methods Indicator 2.1.5: Number of improved traditional energy-efficient stoves distributed and in regular use Indicator 2.2.1: Number of farmers using seasonal forecasts to develop on-farm adaptive strategies Indicator 2.2.2: Increased production and farm income as a result of using seasonal forecasts to guide on-farm activities | Sub Zoba Hamelmalo and Habero ranked the top five (out of 11) most affected zobas by food insecurity due to increased impact of climate change. | 2015- As part of household income and nutrition empowerment and to practice minimum integrated agricultural package, 50 dairy cows & 50 milking cans ,25 chickens, 2 bee hives, citru, vegetable seeds, moringa tree and other forage trees were distributed to 50 households in Habero and Hamelmalo. As continuation of diversion constrcution, a secondary canal which divides the flood to the farms were execavted and finishing of the previously constructed diversion structure was executed. This extensions has incresed the total # of hectars by 50% and currently 75 Ha land have been irrigated both by solar and diversion. Most of the crops ,fruits, vegetables.....grown in the area are in good condition. Farmers have started selling surplus production in the market to neighborin communities; Onion, Okra, Maize, Pumpkin, Lemon, Tomato, milk, and animal forage 2014- 339.32 quintals of improved seeds procured ( 134.97 pearl millet and 204.35 Sorghum)and distributed to benficiaries in sub-zoba Hamelmalo and Habero. From improved seed distribution it's expected the yield to increase by 15% to 20%. Ultimately, this supports the farmers to improve their livelihood and attain food security and increase livestock production by harvesting the stalks/stovers. . Improved stoves introduced in vulnerable sub zoba Hamelmalo and Habero to mitigate deforestation and fuel wood defeciency.All the necessary materials for the construction of 400 improved energy-efficient stoves procured, 63 women from the community trained and as of todate 79 stoves of the total 400 (79HH) has been constructed | 70% of programme beneficiaries have sufficient food for at least an additional three months per year
Outcome 3 | Percentage of programme beneficiaries making use of improved climate risk information and climate monitoring processes, disaggregated according gender Indicator 3.1.1: Downscaled climate change projections at the sub-national scale from multiple GCMs for Zoba Anseba Indicator 3.1.2: Number of gender-sensitive knowledge products developed and disseminated using improved climate risk information Indicator 3.1.3: Class 1 meteorological station installed in sub-zoba Habero and six Class 3 meteorological stations installed, three in each sub-zoba Indicator 3.1.4: Number of staff trained on meteorological observation and analysis, disaggregated according to gender Indicator 3.2.1: Number of stakeholders participating in awareness raising events, disaggregated according to gender and age where possible Indicator 3.2.2: Perceived change in decision making as a result of participation in awareness raising activities Indicator 3.3.1: Number of community members trained on EWS Indicator 3.3.2: Number of stakeholders served by community-based EWS Indicator 3.3.3: Losses resulting from climate-related disasters (e.g. mortality, injury, property or infrastructure lost or damaged) compared with recent historical experience or projected baseline, in the area served by the community-based EWS | No improved climate risk information available yet. | Installation of six meteorological station completed. With the help of Met. Experts from WRD and civil aviation. The two sites Hamelmalo Agricultural College and Hagaz Agro-technical School were identified for Manual and 4 sub zobas (Habero, Keren, Aditekelizan and Geleb) for Automatic manual; accordingly, the installation of the station is completed; and they start recording. Temporary observers for the manual station are assigned; Construction works for metrological offices completed, | 70% of the communities will make use of improved climate risk information
Outcome 4 | Number of lessons learned and natural resource management in the context of climate change as a result of the programme. Indicator 4.1.1: Number of ‘lessons learned’ codified Indicator 4.1.2: Number of relevant networks or communities through which lessons learned are disseminated Indicator 4.2.1: Number of knowledge products developed for use in policy advocacy activities Indicator 4.2.2: Number of policies/plans/strategies/programmes revised or developed as a result of policy advocacy activities | No relevant lessons learned are being captured or disseminated. | To promote the capapcity of the experts from Department of Agriculture & land, Department of infrastrucutre, Dep. Information and mapping of anseba region & Dap. Of finance and Administration, 10 days training of GIS projection and mapping was given in collapration with Hamelmalo Agriculture college. 20 Experts were participated in the training. The training was arranged both in therotical and practical way. To share the experience of the farmers , extensionist & researchers, farmers day was conducted. The field days was conducted in collabration with NARI, HAC, MoA of Anseba region. 42 farmers from the sub zoba Habero and 30 experts from NARI,HAC, MoA zoba & Sub zoba& MoLWE – Dept. of enviroment participated. Geremenation and purity test conducted by Mamelmalo Aagricultural College laboratory and from the analysis a good result is obtained (96% purity and 95% germenation for sorghum and 90% purity and 92% germenation for pearl millet). This will reduce future crop failure in the sub-zoba's.A seed committee comprised of from Hamelmalo college of Agriculture, Min of Agriculture, Agronomists, representative of regional Adminstration established to undertake assesment. | At least five lessons learned codified and disseminated

## Lessons Learned
QUALITATIVE MEASURES and LESSONS LEARNED
Please complete the following section every reporting period
Implementation and Adaptive Management | Response
What implementation issues/lessons, either positive or negative, affected progress? | 1. As no climate expert has so far been deployed at zoba level to serve the project, the meteorological data collected are not being utilized to the fullest possible. This has put limitation in terms of analysing the climate change impact vis-à-vis the technologies that are being implemented in the project area to support the local farming communities towards robust adaptation to climate change. 2. Delays in approval of AWP as well as cash transfer from the bank to the project account have been identified as major obstacles for project implementation as scheduled. To try to mitigate these problems, several negotiations were conducted with the ministry of National Development, and ministry of Land water and Environment. Nevertheless, though there are some positive signs, the problems still persist and will require extra effort to solve these constraints.
Were there any delays in implementation? If so, include any causes of delays. What measures have been taken to reduce delays? | There were delays in implementation are largely attributed to: late approval/signing of AWP (May 2015) and excessive delays in cash transfer (long cash transfer procedure). MND and other key ministries and the banks were made aware of these problems and efforts were made to engage them to mitigate the problem. Very limited availability of cement and machinery were also other bottlenecks for the implementation particularly related to activities that involve construction. Due to shortage of supply of machinery service some of the excavation work had to be executed manually slowing the pace of some of the activities. Government institutions and reginal government decision makers were approached to help solve these limitations. These engagements have been able to solve the problem partially. As no climate expert has so far been deployed at zoba level to serve the project, the meteorological data collected are not being utilized to the fullest possible. This has put limitation in terms of analysing the climate change impact vis-à-vis the technologies that are being implemented in the project area to support the local farming communities towards robust adaptation to climate change. This problem has been explained to the Ministry of Land Water and Environment and the project is continually requesting for a deployment of climate expert.
Describe any changes undertaken to improve results on the ground or any changes made to project outputs (i.e. changes to project design) | 1. Establishment of farmers association for each project sites/villages. 2. Coordination mechanism with national research institutions developed for promotion of new agricultural innovations which contributes to increase agricultural production and improve the livelihood of the community.
How have gender considerations been taken into consideration during the reporting period? What have been the lessons learned as a consequence of inclusion of such considerations on project performance or impacts? | Compliance of the project with Equal Opportunity Act is mandatory as per Government legal framework. Focus on Gender has been fully integrated into project activities through involvement of women in the project activities like construction of energy-saving stoves as an opportunity for the women to generate income and save money and time. In order to provide quality nutrition to the local communities, the project has been implementing Minimum Integrated Agricultural Package which comprises provision of dairy cows, chickens, bee hives, and seeds to grow fruit crops, vegetables. About 37% of the beneficiaries are women headed households. Local women's associations have been actively involved in the implementation of the project.
Please complete the following section at mid-term and project completion
Lessons for Adaptation | Response
Climate Resilience Measures
What have been the lessons learned, both positive and negative, in implementing climate adaptation measures that would be relevant to the design and implementation of future projects/programmes for enhanced resilience to climate change?
What is the potential for the climate resilience measures undertaken by the project/programme to be replicated and scaled up both within and outside the project area?
Concrete Adaptation Interventions
What have been the lessons learned, both positive and negative, in implementing concrete adaptation interventions that would be relevant to the design and implementation of future projects/programmes implementing concrete adaptation interventions? | Mid-term evaluation is going to be carried out in June 2016 that will establish the lessons to be learnt. However, the few lessons learnt are as follows: 1. Community based projects is very crucial for successful implementation and sustainability of projects. 2. The country needs to train and have adequate number of qualified MET/climate experts to respond to the existing gap in this field. This makes even important as the impact of climate change is emerging as an important development challenge in the country. 3. To ensure sustainability of improved/drought tolerant seed supply establishment of village based seed multiplication and seed bank is very crucial and this can be done in collaboration with national agricultural research institute, Hamelmallo Agricultural College, Ministry of Agriculture and other relevant institutions.
What is the potential for the concrete adaptation interventions undertaken by the project/programme to be replicated and scaled up both within and outside the project area? | The project interventions were unique and have resulted to admirable progress in the project area. The pilot project is refered as the UNDP model. It has been already asked by the regional adminstration that technical teams to familiarize themselves with the project for upscaling and replication throughout the region.
Community/National Impact
What would you consider to be the most successful aspects for the target communities?
What measures are/have been put in place to ensure sustainability of the project/program results?
What measures are being/could have been put in place to improve project/program results?
Knowledge Management
How has existing information/data/knowledge been used to inform project development and implementation? What kinds of information/data/knowledge were used?
If learning objectives have been established, have they been met? Please describe.
Describe any difficulties there have been in accessing or retrieving existing information (data or knowledge) that is relevant to the project. Please provide suggestions for improving access to the relevant data.
Has the identification of learning objectives contributed to the outcomes of the project? In what ways have they contributed?

## Results Tracker
Results Tracker for Adaptation Fund (AF) Projects
Goal: Assist developing-country Parties to the Kyoto Protocol that are particularly vulnerable to the adverse effects of climate change in meeting the costs of concrete adaptation projects and programmes in order to implement climate-resilient measures. Impact: Increased resiliency at the community, national, and regional levels to climate variability and change.
Important: Please read the following guidance document (also posted on the Adaptation Fund website) before entering your data
Link: http://www.adaptation-fund.org/sites/default/files/Results%20Framework%20and%20Baseline%20Guidance%20final.pdf
Adaptation Fund Strategic Results Framework
Project ID | 00061576 (PIMS 4540)
Implementing Entity | UNDP
Type of implementing entity | MIE
Country | Eritrea
Region | Africa
Sector | Multi-sector
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Impact: Increased resiliency at the community, national, and regional levels to climate variability and change | Core Indicator: No. of beneficiaries |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project
|  | Total | 67500 | 27000 | 40500 | Total | 45500 | 12595 | 32905 | Total | 18000 | 4983 | 13017 | Total
|  | % of female beneficiaries | 48% | 22.2% | 25.8% | % of female beneficiaries | 40% | 24% | 16% | % of female beneficiaries | 40% | 11% | 29% | % of female beneficiaries
|  | % of Youth beneficiaries | 47% | 18.6% | 28.4% | % of Youth beneficiaries | 56% | 15.5% | 40.5% | % of Youth beneficiaries | 56% | 15.5% | 40.5% | % of Youth beneficiaries
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 1: Reduced exposure to climate-related hazards and threats | Indicator 1: Relevant threat and hazard information generated and disseminated to stakeholders on a timely basis | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness
|  | Total | 200 | Drought | 2: Partially effective | Total | 1200 | Drought | 3: Moderately effective | Total | 534 | Drought | 4: Effective | Total
|  | % of female targeted | 32% |  |  | % of female targeted | 38% |  |  | % of female targeted | 34% |  |  | % of female targeted
Output 1.1 Risk and vulnerability assessments conducted and updated | Indicator 1.1: No. of projects/programmes that conduct and update risk and vulnerability assessments | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
Output 1.2 Targeted population groups covered by adequate risk reduction systems | Core Indicator 1.2: No. of Early Warning Systems | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard | Drought | No. of adopted Early Warning Systems | Category targeted | Hazard | Drought | No. of adopted Early Warning Systems | Category targeted | Hazard
|  | 1 | 3: Dissemination and communication | Geographical coverage | Regional | 5 | 3: Dissemination and communication | Geographical coverage | Regional | 5 | 3: Dissemination and communication | Geographical coverage | Regional |  |  | Geographical coverage
|  |  |  | Number of municipalities | 6 |  |  | Number of municipalities |  |  |  | Number of municipalities | 4 |  |  | Number of municipalities
|  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard | Drought | No. of adopted Early Warning Systems | Category targeted | Hazard | Drought | No. of adopted Early Warning Systems | Category targeted | Hazard
|  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 2: Strengthened institutional capacity to reduce risks associated with climate-induced socioeconomic and environmental losses | Indicator 2: Capacity of staff to respond to, and mitigate impacts of, climate-related events from targeted institutions increased | Number of staff targeted |  | Sector | Capacity level | Number of staff targeted |  | Sector | Capacity level | Number of staff targeted |  | Sector | Capacity level | Number of staff targeted |  | Sector | Capacity level
|  | Total | 0 | Multi-sector | 2: Low capacity | Total | 100 | Multi-sector | 2: Low capacity | Total | 72 | Multi-sector | 3: Medium capacity | Total
|  | % of female targeted | 0% |  |  | % of female targeted | 30% |  |  | % of female targeted | 20% |  |  | % of female targeted
Output 2.1 Strengthened capacity of national and sub-national centres and networks to respond rapidly to extreme weather events | Indicator 2.1.1: No. of staff trained to respond to, and mitigate impacts of, climate-related events | Total staff trained | % of female staff trained | Type |  | Total staff trained | % of female staff trained | Type |  | Total staff trained | % of female staff trained | Type |  | Total staff trained | % of female staff trained | Type
|  | 25 | 25% | Public |  | 50 | 30% | Public |  | 15 | 33% | Public
| Indicator 2.1.2: No. of targeted institutions with increased capacity to minimize exposure to climate variability risks | Type | Scale | Sector | Capacity level | Type | Scale | Sector | Capacity level | Type | Scale | Sector | Capacity level | Type | Scale | Sector | Capacity level
|  | Public | Regional | Multi-sector | 2: Low capacity | Public | National | Agriculture | 2: Low capacity | Public | National | Agriculture | 3: Medium capacity
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 3: Strengthened awareness and owernship of adaptation and climate risk reduction processes | Indicator 3.1: Increase in application of appropriate adaptation responses | Percentage of targeted population applying adaptation measures |  | Sector |  | Percentage of targeted population applying adaptation measures |  | Sector |  | Percentage of targeted population applying adaptation measures |  | Sector |  | Percentage of targeted population applying adaptation measures |  | Sector
|  | 6% |  | Multi-sector |  | 38 |  | Multi-sector |  | 14 |  | Multi-sector
Output 3: Targeted population groups participating in adaptation and risk reduction awareness activities | Indicator 3.1.1: Percentage of targeted population awareness of predicted adverse impacts of climate change, and of appropriate responses | No. of targeted beneficiaries | % of female participants targeted | Level of awareness |  | No. of targeted beneficiaries | % of female participants targeted | Level of awareness |  | No. of targeted beneficiaries | % of female participants targeted | Level of awareness |  | No. of targeted beneficiaries | % of female participants targeted | Level of awareness
|  | 0 | 0% | 2: Partially not aware |  | 3000 | 40% | 2: Partially not aware |  | 800 | 26% | 3: Partially aware
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Target performance at completion |  |  |  | Target performance at completion
Outcome 4: Increased adaptive capacity within relevant development sector services and infrastructure assets | Indicator 4.1: Increased responsiveness of development sector services to evolving needs from changing and variable climate | Project/programme sector | Geographical scale | Response level |  | Project/programme sector | Geographical scale | Response level |  | Project/programme sector | Geographical scale | Response level |  | Project/programme sector | Geographical scale | Response level
|  | Multi-sector | Regional | 2: Partially responsive (Lacks most elements) |  | Multi-sector | Regional | 4: Mostly responsive (Most defined elements) |  | Multi-sector | Regional | 3: Moderately responsive (Some defined elements)
| Core Indicator 4.2: Assets produced, developed, improved or strengthened | Sector | Targeted asset | Changes in asset (quantitative or qualitative) |  | Sector | Targeted asset | Changes in asset (quantitative or qualitative) |  | Sector | Targeted asset | Changes in asset (quantitative or qualitative) |  | Sector | Targeted asset | Changes in asset (quantitative or qualitative)
|  | Multi-sector | 2: Physical asset (produced/improved/strenghtened) | 1: Not improved |  | Multi-sector | 2: Physical asset (produced/improved/strenghtened) | 4: Mostly Improved |  | Multi-sector | 2: Physical asset (produced/improved/strenghtened) | 2: Somewhat improved
Output 4: Vulnerable development sector services and infrastructure assets strengthened in response to climate change impacts, including variability | Indicator 4.1.1: No. and type of development sector services to respond to new conditions resulting from climate variability and change | Number of services | Type |  | Sector | Number of services | Type |  | Sector | Number of services | Type |  | Sector | Number of services | Type |  | Sector
|  | 0 | Irrigation |  | Agriculture | 1 | Irrigation |  | Agriculture
|  | 0 | Dam/Subsurface/Diversions |  | Water management | 3 | Dam/Subsurface/Diversions |  | Water management
|  | Baseline information |  |  |  | Baseline information |  |  |  | Baseline information |  |  |  | Baseline information
Outcome 5: Increased ecosystem resilience in response to climate change and variability-induced stress | Indicator 5: Ecosystem services and natural resource assets maintained or improved under climate change and variability-induced stress | Natural resource improvement level |  | Sector | Type | Natural resource improvement level |  | Sector | Type | Natural resource improvement level |  | Sector | Type | Natural resource improvement level |  | Sector | Type
|  | 2: Partially effective |  | Other | land | 1: Ineffective
Output 5: Vulnerable ecosystem services and natural resource assets strengthned in response to climate change impacts, including variability | Core Indicator 5.1: Natural Assets protected or rehabilitated | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Cultivated land/Agricultural land | 6 | ha rehabilitated | 2: Partially effective | Cultivated land/Agricultural land
|  | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Catchment area/Watershed/Aquifer | 300 | ha protected | 2: Partially effective
|  | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Baseline information |  |  |  | Targeted performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 6: Diversified and strengthened livelihoods and sources of income for vulnerable people in targeted areas | Indicator 6.1: Increase in households and communities having more secure access to livelihood assets | No. of targeted households | % of female headed households | Improvement level |  | No. of targeted households | % of female headed households | Improvement level |  | No. of targeted households | % of female headed households | Improvement level |  | No. of targeted households | % of female headed households | Improvement level
|  | 9000 | 30% | 2: Limited improvement |  | 13250 | 30% | 4: High improvement |  | 11250 | 30% | 2: Limited improvement
| Indicator 6.2: Increase in targeted population's sustained climate-resilient alternative livelihoods | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
|  | 0 | 0% | From 0 to 0.5% | Agricultural-related | 800 | 40% | From 30% to 40% | Agricultural-related | 350 | 25% | From 20% to 30% | Agricultural-related
|  | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
|  | 0 | 0% | From 0 to 0.5% | Livestock production | 100 | 30% | From 40% to 50% | Livestock production | 50 | 10% | From 30% to 40% | Livestock production
|  | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
|  | 3180 | 40% | From 40% to 50% | Forestry | 4380 | 40% | Above 50% | Forestry | 3980 | 18% | From 20% to 30% | Forestry
|  | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
Output 6 Targeted individual and community livelihood strategies strengthened in relation to climate change impacts, including variability | Indicator 6.1.1: No. and type of adaptation assets created or strengthened in support of individual or community livelihood strategies | Number of Assets | Type of Assets | Sector | Adaptation strategy | Number of Assets | Type of Assets | Sector | Adaptation strategy | Number of Assets | Type of Assets | Sector | Adaptation strategy | Number of Assets | Type of Assets | Sector | Adaptation strategy
|  | 0 | Physical capital | Multi-sector | Strengthening infrastructure | 5 | Physical capital | Multi-sector | Strengthening infrastructure | 2 | Physical capital | Multi-sector | Strengthening infrastructure
| Core Indicator 6.1.2: Increased income, or avoided decrease in income | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income | income source
|  | 5 | Agricultural-related |  | 20000 | 150 | Agricultural-related |  | 230000 | 100 | Agricultural-related |  | 140000
|  | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 7: Improved policies and regulations that promote and enforce resilience measures | Indicator 7: Climate change priorities are integrated into national development strategy | Integration level |  |  |  | Integration level |  |  |  | Integration level |  |  |  | Integration level
|  | 4: Most |  |  |  | 5: All (Fully integrated) |  |  |  | 4: Most
Output 7:Improved integration of climate-resilience strategies into country development plans | Indicator 7.1: No. of policies introduced or adjusted to address climate change risks | No. of Policies introduced or adjusted | Sector | Scale | Type | No. of Policies introduced or adjusted | Sector | Scale | Type | No. of Policies introduced or adjusted | Sector | Scale | Type | No. of Policies introduced or adjusted | Sector | Scale | Type
| Indicator 7.2: No. of targeted development strategies with incorporated climate change priorities enforced | No. of Development strategies | Regulation |  | Effectiveness | No. of Development strategies | Regulation |  | Effectiveness | No. of Development strategies | Regulation |  | Effectiveness | No. of Development strategies | Regulation |  | Effectiveness
Glacier lake outburst flood
|  | Inland flooding | fr | biological assets |  | Company policy | 5: Fully enforced (All elements implemented)
|  | Salinization | Decrease | land |  | Communication & Information policy | 4: Enforced (Most elements implemented)
|  | Drought | Same | water areas |  | Defense policy | 3: Partially enforced (Some elements implemented)
|  | Wind |  | subsoil assets | increased adpative capacity | Domestic policy | 2: Partially not enforced (Most elements not implemented) |  | Agribusiness
|  | Coastal flooding |  | air | achieved | Economic policy | 1: Not enforced (No elements implemented) |  | Agricultural-related | Financial capital
|  | Storm surge | Please choose |  | enhanced level of protection | Education policy |  |  | Agriculture | Human capital
|  | Hurricane | Selected | [5 empty] | Aquaculture | Physical capital
|  |  | Not relevant |  |  | 5: All (Fully integrated) |  |  | Construction/repairing business | Social capital
[6 empty] | 4: Most |  |  | Cultivation | Natural capital
[6 empty] | 3: Some |  |  | Fishing | Personal capital
Select | 5: All | Select |  |  | Community | 2: Most not integrated |  | Other | Forestry | Adaptation strategies
1 | 4: Almost all | Private | Type | Yes | Multi-community | 1: None |  | Agriculture | Handicrafts
2 | 3: Half | Public | Scale | No | Departmental |  |  | Coastal management | Livestock production
3 | 2: Some | NGO | Sector |  | National |  |  | Disaster risk reduction | Manufacturing
4 | 1: None |  |  |  |  | 5: Very high improvement | Established | Food security | other
|  | National |  |  |  | 4: High improvement | Maintained | Health | Services
|  | Regional |  |  |  | 3: Moderate improvement | Improved | Urban development | Tourism-related
|  | Local |  |  |  | 2: Limited improvement |  | Water management | Trading
[6 empty] | 1: No improvement |  | Multi-sector
|  | 1 -generated information is irrelevant, and neither the stakeholders reached nor the timeframe managed were achieved | 1: No info transferred on time | 4: High capacity | 5: Fully aware | 5: Highly responsive (All defined elements ) | 5: Fully improved | Roads | 5: Very effective
Asia-Pacific | NIE | 2 -the existence of some challenge in any of the three aspects of the indicator (generation of dissemination, stakeholders reached or timeframe managed) | 2: Somewhat info transferred | 3: Medium capacity | 4: Mostly aware | 4: Mostly responsive (Most defined elements) | 4: Mostly Improved | Gov Buildings | 4: Effective
Latin America and Caribbean | RIE | 3 -relevant information is generated and disseminated to all identified stakeholders on timely basis | 3: Info transferred on time | 2: Low capacity | 3: Partially aware | 3: Moderately responsive (Some defined elements) | 3: Moderately improved | Causeways | 3: Moderately effective
Africa | MIE |  |  | 1: No capacity | 2: Partially not aware | 2: Partially responsive (Lacks most elements) | 2: Somewhat improved | Airports | 2: Partially effective
Eastern Europe |  |  |  |  | 1: Aware of neither | 1: Non responsive (Lacks all elements ) | 1: Not improved | Schools | 1: Ineffective
| ha protected | [6 empty] | Training Centres
| ha rehabilitated | [5 empty] | Monitoring/Forecasting capacity | Hospitals
Afghanistan, Islamic Rep. of | km protected | [5 empty] | Policy/regulatory reform | Drinking water systems
Angola | km rehabilitated | 1: Risk knowledge | 1: No plans conducted or updated |  |  |  | Capacity development | Other
Albania |  | 2: Monitoring and warning service | 2: Undertaking or updating of assessments in progress |  |  | Communication & Information policy | Sustainable forest management
Argentina |  | 3: Dissemination and communication | 3: Risk and vulnterability assessments completed or updated |  |  | Domestic policy | Strengthening infrastructure | 1: Health and Social Infrastructure (developed/improved)
Armenia | Forests | 4: Response capability |  |  |  | Economic policy | Supporting livelihoods | 2: Physical asset (produced/improved/strenghtened)
Antigua and Barbuda | Mangroves |  |  |  |  | Education policy | Mangrove reforestation
Azerbaijan | Coasts |  | From 0 to 0.5% |  |  | Energy policy | Coastal drainage and infrastructure
Burundi | Rangelands |  | From 0.5 to 1% |  |  | Environmental policy | Irrigation system
Benin | Cultivated land/Agricultural land |  | From 1% to 5% |  |  | Foreign policy | Community-based adaptation
Burkina Faso | Catchment area/Watershed/Aquifer |  | From 5% to 10% |  |  | Health policy | Erosion control
Bangladesh | Protected areas/National parks |  | From 10% to 20% |  |  | Housing policy | Soil water conservation
Bulgaria | Other |  | From 20% to 30% |  |  | Human resource policies | Microfinance
Bahrain |  |  | From 30% to 40% |  |  | Information policy | Special Program for women
Bahamas, The |  |  | From 40% to 50% |  |  | Macroeconomic policy | Livelihoods
Bosnia and Herzegovina |  |  | Above 50% |  |  | Monetary policy | Water storage
Belarus | [5 empty] | Population policy | ICT and information dissemination
Belize | [5 empty] | Private policy
Bolivia | [5 empty] | Public policy
Brazil | [5 empty] | Science policy
Barbados | [5 empty] | Social policy
Bhutan |  | 3- relevant information is generated and disseminated to all identified stakeholders on timely basis |  |  |  | Transportation policy
Botswana |  | describe |  |  |  | Urban policy
Central African Republic |  | 2- the existence of some challenge in any of the three aspects of the indicator |  |  |  | Water policy
Chile |  | describe |  |  |  | Other policy
China, People's Republic of |  | 1- generated information is irrelevant and neither the stakeholders reached nor the timeframe managed were achieved
Cote d'Ivoire |  | describe
Cameroon
Congo, Dem. Rep. of
Congo, Republic of
Cook Islands
Colombia
Comoros
Cape Verde
Costa Rica
Cuba
Czech Republic
Djibouti
Dominica
Dominican Republic
Algeria
Ecuador
Egypt
Eritrea
Estonia
Ethiopia
Fiji
Micronesia, Fed. States of
Gabon
Georgia
Ghana
Guinea
Gambia, The
Guinea-Bissau
Equatorial Guinea
Grenada
Guatemala
Guyana
Honduras
Croatia
Haiti
Hungary
Indonesia
India
Iran, Islamic Republic of
Jamaica
Jordan
Kazakhstan
Kenya
Kyrgyz Republic
Cambodia
Kiribati
Saint Kitts and Nevis
Korea, Republic of
Lao People's Democratic Republic
Lebanon
Liberia
Libya
Saint Lucia
Sri Lanka
Lesotho
Lithuania
Latvia
Morocco
Moldova
Madagascar
Maldives
Mexico
Marshall Islands
Macedonia, former Yugoslav Republic of
Mali
Malta
Myanmar
Montenegro
Mongolia
Mozambique
Mauritania
Mauritius
Malawi
Malaysia
Namibia
Niger
Nigeria
Nicaragua
Niue
Nepal
Nauru
Oman
Pakistan
Panama
Peru
Philippines
Palau
Papua New Guinea
Poland
Korea, Dem. People's Rep. of
Paraguay
Romania
Russian Federation
Rwanda
Saudi Arabia
Sudan
Senegal
Solomon Islands
Sierra Leone
El Salvador
San Marino
Serbia
Sao Tome and Principe
Suriname
Slovak Republic
Slovenia
Swaziland
Seychelles
Syrian Arab Republic
Chad
Togo
Thailand
Tajikistan
Turkmenistan
Tonga
Trinidad and Tobago
Tunisia
Turkey
Tuvalu
Tanzania
Uganda
Ukraine
Uruguay
Uzbekistan
Saint Vincent and the Grenadines
Venezuela
Vietnam
Vanuatu
Samoa
Yemen, Republic of
South Africa
Zambia
Zimbabwe
Timor-Leste

## Units for Indicators
Fund Outcome Indicator Units
1. Generation of relevant data, Stakeholders, and Timeliness 2.1. Include both qualitative and quantitative measures of capacity level within targeted institutions 2.2. Number (men and women and other vulnerable groups) 3.1. Use scale from 1 to 5: 5: Fully aware 4: Mostly aware 3: Partially aware 2: Partially not aware 1: Aware of neither predicted adverse impacts of climate change nor of appropriate responses 3.2. Use scale from 1 to 5: 5: All 4: Almost all 3: Half 2: Some 1: None 4.1. Summarize in an overall scale (1-5): 5: Highly responsive (All defined elements ) 4: Mostly responsive (Most defined elements) 3: Moderately responsive (Some defined elements) 2: Partially responsive (Lacks most elements) 1: Non responsive (Lacks all elements ) 4.2. Summarize in an overall scale (1-5): 5: Fully improved 4: Mostly Improved 3: Moderately improved 2: Somewhat improved 1: Not improved 5. Depends on the targeted natural asset: Biological (species): measure through changes in population numbers (dynamics, structure, etc.) Land: measure changes in hectares. Baseline data will be necessary to estimate the change. Supporting indicators baseline and target (as well as contextual information) are needed such as the following: Farmers adopting recommended technologies, Ha. of land improved, Average deforestation rate Etc. Use scale from 1 to 5. 5: Very effective (All elements are present) 4: Effective (Most elements are present) 3: Moderately effective (Some elements are present) 2: Partially effective (Most elements are not present) 1: Ineffective (No elements are present) 6.1. Summarize in an overall scale (1-5): 5: Very high improvement 4: High improvement 3: Moderate improvement 2: Limited improvement 1: No improvement 6.2. Household income by source of livelihood in project area (USD) prior and post project intervention 7. Summarize in an overall scale (1-5). 5: All (Fully integrated) 4: Most 3: Some 2: Most not integrated 1: None
Fund Output Indicator Units
1.1. Number, sector(s) and level(s) of projects or interventions in separate fields of monitoring plan 1.2. Number 2.1.1. Number of staff (male/female) of targeted institutions: a. Obtain baseline information: total number of staff from targeted institutions b. Define target 2.1.2. Number of staff (male/female) of targeted institutions: a. Obtain baseline information: total number of staff from targeted institutions b. Define target: needs to be defined by project proponents 2.2.1. Quantitative: Percentage (includes women – and other vulnerable groups – and men). Qualitative: Adequacy: include direct analysis of major areas; adequacy/effectiveness of systems or analysis of perceptions of populations and institutions. 2.2.2. Number (broken down by gender and, if possible, by vulnerable groups defined in the area of intervention) of people 3.1. Number and type (in separate columns) at local level. 3.2. Number 4.1. Number and type 4. 2. Number and type (entered in separate columns) 5. Number of interventions by type of natural asset and intervention 6.1. Number and type (in separate columns of monitoring plan) 6.2. Income sources per household; description of income source and number of households. 7.1. Number/Sector 7.2. Number; Effectiveness (see previous indicator) through enforcement level.