## Overview
Project Performance Report (PPR)
| Period of Report (Dates) | 1 July 2014 - 30 June 2015
| Project Title: | Enhancing Resilience of Communities in Solomon Islands to the Adverse Effects of Climate Change on Agriculture and Food Security - Strogem Waka lo Community fo Kaikai (SWoCK)
| Project Summary: | The Solomon Islands National Adaptation Programme of Action (NAPA) identified agriculture and food security as one of the most vulnerable sectors requiring urgent attention. The project addresses the NAPA priority and will contribute to enhance resilience of the agriculture sector to maintain and improve food security in the country. In particular, the project will lead to the following key results (outcomes) 1) Promote and pilot community-adaptation activities enhancing food security and livelihood resilience in pilot communities in at least 3 selected regions; 2) Strengthen institutions and adjusted national and sub-national policies related to governing agriculture in the context of a range of climate change futures; and 3) Foster the generation and spread of relevant knowledge for assisting decision-making at the community and policy-formulation level.
|  |  | Countries | Project Type: |  | GEF Focal Area: | GEF 4 Focal Areas | GEF 2 / 3 Operational Programme: | Overall Rating of the project in the evaluation by the project evaluator: | GEF-4 Focal Area Strategic Program: | GEF-3 Focal Area Strategic Program:
| Database Number: | PIMS 4451 - AFB/MIE/Food/2010/1 | Afghanistan | FP | Yes | Biodiversity | 1 | 1 | U | BD-SP1-PA Financing | 1: Arid & semi-arid ecosystems
Implementing Entity (IE) [name]: |  | United Nations Development Programme | Albania | MSP | No | Climate Change Adaptation | 2 | 2 | S | BD-SP2-Marine PA | 2: Coastal, marine & freshwater ecosystems
| Type of IE: | MIE | Algeria | EA |  | Climate Change Mitigation | 3 | 3 | MU | BD-SP3-PA Networks | 3: Forest ecosystems
| Country(ies): | Solomon Islands | Angola |  |  | International Waters | 5 | 5 | Good | BD-SP5-Markets | 13: Conservation and Sustainable Use of Biological Diversity Important to Agriculture
Relevant Geographic Points (i.e. cities, villages, bodies of water): |  | Weather Coast of Guadalcanal, South Makira, South Choiseul, North Malaita, Central Maringe in Isabel, Honiara City, Lau and Langa Langa lagoons in Malaita | Argentina |  |  | Multiple Focal Area |  |  |  | BD-SP7-Invasive Alien Species(IAS) | 6: Promoting the adoption of renewable energy by removing barriers and reducing implementation costs
[8 empty] | CC-SP2- Industrial EE | 8: Waterbody based operational program
| Project Milestones | [6 empty] | CC-SP3-RE,CC-SP4-Biomass | 9: Integrated Land and Water multiple focal area
| Milestone |  | Bahamas | [6 empty] | CC-SP5-Transport | 10: Contaminants based operational program
AFB Approval Date: |  | March 18, 2011
IE-AFB Agreement Signature Date: |  | 2011-04-01 | [6 empty] | CC-SP6-LULUCF | 12: Integrated Ecosystem Management
Start of Project/Programme: |  | July 1, 2011 | [6 empty] | Cross cutting capacity building | 14: Persistent Organic Pollutants
Mid-term Review Date (if planned): |  | 2013-12-01
| Terminal Evaluation Date: | 2016-07-01
|  | List documents/ reports/ brochures / articles that have been prepared about the project. | Cyprus
|  | Inception Report Multi-year Work plan and Activity Schedule Mission Reports Quarterly Reports Mid-term Evaluation Report Project Board meeting minutes Success story (published in UNDP Adaptation Bulletin issue 13, July 2013: http://www.undp-alm.org/resources/adaptation-bulletin-13 Press Releases http://www.aljazeera.com/indepth/features/2014/09/solomon-women-carry-climate-change-burden-201492374735560628. html http://thediplomat.com/2014/09/food-security-and-solomon-islands/ Solomon Islands highlighting how Adaptation Fund resources are invested in an early warning system and automated whether stations. http://www.trust.org/item/20140918120924-nz3d6 Sea Level Rise Article:https://undp.exposure.co/af-solomon-islands | Czech Republic
List the Website address (URL) of project. |  |  | Democratic People's Republic of Korea
|  | http://www.undp-adaptation.org/project/af_solomonislands | Democratic Republic of the Congo
Denmark
| Project contacts: |  | Djibouti
National Project Manager/Coordinator |  |  | Dominica
| Name: | Kristina.Fidali | Dominican Republic
| Email: | kristina.fidali@undp.org | Ecuador
| Date: | 2015-05-30 | Egypt
| Government DA |  | El Salvador
| Name: | Dr. Melchior Mataki , Permanent Secretary (a.g.), Ministry of Environment, Climate Change, Disaster Management and Meteorology (MECDM) | Equatoral Guinea
| Email: | psmataki@mecm.gov.sb | Eritrea
| Date: | 2015-05-30 | Estonia
| Implementing Entity |  | Ethiopia
| Name: | Lynelle Popot and Yusuke Taishi | Fiji
| Email: | lynelle.popot@undp.org; yusuke.taishi@undp.org | Finland
| Date: | 2015-05-30 | France
| Executing Agency |  | Gambia
| Name: | Dr. Melchior Mataki , Permanent Secretary (a.g.), Ministry of Environment, Climate Change, Disaster Management and Meteorology (MECDM) | Georgia
| Email: | ‎psmataki@mecm.gov.sb | Germany
| Date: | 2015-05-30 | Ghana
| Executing Agency |  | Greece
| Name: | Jimmy Saelea, Permanent Secretary, Ministry of Agriculture and Livestock (MAL) | Grenada
| Email: | j_saelea@yahoo.com | Guatemala
| Date: | 2015-05-30 | Guinea
| Executing Agency |  | Guinea Bissau
| Name: |  | Guyana
| Email: |  | Haiti
| Date: |  | Honduras
Hungary
Iceland
India
Indonesia
Iran (Islamic Republic of)
Iraq
Ireland
Israel
Italy
Jamaica
Japan
Jordan
Kazakhstan
Kenya
Kiribati
Kuwait
Kyrgyzstan
Lao People’s Democratic Republic
Latvia
Lebanon
Lesotho
Liberia
Libyan Arab Jamahiriya
Liechtenstein
Lithuania
Luxembourg
Madagascar
Malawi
Malaysia
Maldives
Mali
Malta
Marshall Islands
Mauritania
Mauritius
Mexico
Micronesia, Federated States of
Monaco
Mongolia
Montenegro
Morocco
Mozambique
Myanmar
Namibia
Nauru
Nepal
Netherlands
New Zealand
Nicaragua
Niger
Nigeria
Norway
Oman
Pakistan
Palau
Panama
Papua New Guinea
Paraguay
Peru
Philippines
Poland
Portugal
Qatar
Republic of Korea
Republic of Moldova
Romania
Russian Federation
Rwanda
Saint Kitts and Nevis
Saint Lucia
Saint Vincent and the Grenadines
Samoa
San Marino
Sao Tome and Principe
Saudi Arabia
Senegal
Serbia
Seychelles
Sierra Leone
Singapore
Slovakia
Slovenia
Solomon Islands
Somalia
South Africa
Spain
Sri Lanka
Sudan
Suriname
Swaziland
Sweden
Switzerland
Syrian Arab Republic
Tajikistan
Thailand
The former Yugoslav Republic of Macedonia
Timor-Leste
Togo
Tonga
Trinidad and Tobago
Tunisia
Turkey
Turkmenistan
Tuvalu
Uganda
Ukraine
United Arab Emirates
United Kingdom of Great Britain and Northern Ireland
United Republic of Tanzania
United States of America
Uruguay
Uzbekistan
Vanuatu
Venezuela, Bolivarian Republic of
Viet Nam
Yemen
Zambia
Zimbabwe

## FinancialData
Financial information: cumulative from project start to 30 June 2015
DISBURSEMENT OF AF GRANT FUNDS
How much of the total AF grant as noted in Project Document plus any project preparation grant has been spent to date?
Estimated cumulative total disbursement as of 30 June 2015 | 3979746.66
Add any comments on AF Grant Funds. (word limit=200) | So far, US$4,699,536 AF grants have been received in three tranches, of which US$3,979,746.66 has been disbursed or committed with the total delivery of 84.7%. Compared to previous reporting period this period has seen robust improvement in the delivery on the ground, which also results in improved utilisation of AF funds.
INVESTMENT INCOME | N/A
Amount of annual investment income generated from the Adaptation Fund’s grant
EXPENDITURE DATA
List ouput and corresponding amount spent for the current reporting period | ITEM / ACTIVITY / ACTION | AMOUNT
| Output1.1Develop and implement integrated land use plans at community level targeting communities | 165451.28
| 1.2 Climate change resilient farming and aquaculture production techniques and systems introduced at community level | 410000
| 1.3 Establishment of provincial and community level food banks | 119000
| 1.4 Strengthening capacity for processing and storage of root crops | 98451.28
| 1.5 Government and NGO field staff and communities trained in use of climate information | 88570
| 2.1 Integration of climate and disaster risks into national and provincial agriculture and livestock sector policy, other relevant policies and strategies and related instruments and coordination mechanisms | 110000
| 2.2 Capacity of Solomon Islands Meteorological Services (SIMS) Strengthened to produce enhanced weather and climate Information services tailored to agriculture sector and land resources management | 87733.37
| 2.3 Capacity of Climate change division within MECDM, MAL and SNR enhanced to support integration of climate Change risks into land use planning and field operations | 67570
| 3.1 Lessons learned and best practices generated (case studies, photo stories, short videos, posters etc) and distributed to other communities, civil society, policy makers in government and to global community through appropriate mechanisms | 29765.67
| 3.2 Training materials developed incorporating climate change issues and used for training of field staff and students | 32000
| 4.1 Project Management Unit established and operational | 243354
| 4.2 Project monitoring and evaluation | 56940
| TOTAL | 1508835.6
PLANNED EXPENDITURE SCHEDULE
List outputs planned and corresponding projected cost for the upcoming reporting period | ITEM / ACTIVITY / ACTION | PROJECTED COST | Est. Completion Date
| Output1.1Develop and implement integrated land use plans at community level targeting communities | 125000 | 2016-06-01
| 1.2 Climate change resilient farming and aquaculture production techniques and systems introduced at community level | 122000 | 2016-06-01
| 1.3 Establishment of provincial and community level food banks | 30000 | 2016-06-01
| 1.4 Strengthening capacity for processing and storage of root crops | 50000 | 2016-06-01
| 1.5 Government and NGO field staff and communities trained in use of climate information | 22000 | 2016-06-01
| 2.1 Integration of climate and disaster risks into national and provincial agriculture and livestock sector policy, other relevant policies and strategies and related instruments and coordination mechanisms | 55000 | 2016-06-01
| 2.2 Capacity of Solomon Islands Meteorological Services (SIMS) Strengthened to produce enhanced weather and climate Information services tailored to agriculture sector and land resources management | 191232.34 | 2016-06-01
| 2.3 Capacity of Climate change division within MECDM, MAL and SNR enhanced to support integration of climate Change risks into land use planning and field operations | 108000 | 2016-06-01
| 3.1 Lessons learned and best practices generated (case studies, photo stories, short videos, posters etc) and distributed to other communities, civil society, policy makers in government and to global community through appropriate mechanisms | 183021 | 2016-06-01
| 3.2 Training materials developed incorporating climate change issues and used for training of field staff and students | 55000 | 2016-06-01
| 4.1 Project Management Unit established and operational | 120000 | 2016-06-01
| 4.2 Project monitoring and evaluation | 59000 | 2016-06-01
| TOTAL | 1120253.34
ACTUAL CO-FINANCING (If the MTR or TE have not been undertaken this reporting period, DO NOT report on actual co-financing.)
How much of the total co-financing as committed in the Project Document has actually been realized? | N/A
Estimated cumulative actual co-financing as verified during Mid-term Review (MTR) or Terminal Evaluation (TE). | N/A
Add any comments on actual co-financing in particular any issues related to the realization of in-kind, grant, credits, loans, equity, non-grant instruments and other types of co-financing. (word limit=200) | Government inkind co-financing has been through office space for two farming system officer within MAL and two Climate Change Adaptation Officer in MECDM and the technical daily support of the Permanent Secretaries (2) Directors (7), principle level technical staff (12) and Technical Provincial Extension staff (7) of the Ministry of Environment, Climate Change, Disaster Management and Meteorology and the Ministry of Agriculture and Livestock. The co-financing value for this reporting period from the government is estimated to be USD52,783. Of this, the contributions in terms of the government staffing is as follows: PS =USD$3287.67; Directors=USD$8630.14; Principle Level technical staff=USD$14,793.85: Office Space=USD$26,301; Provincial Extension Staff= USD$8400

## Procurement
PROCUREMENT DATA
Please provide information for all contracts over $2,500 USD
Please provide the number of contracts under $2,500, signed during this reporting period: |  |  |  | July 2014 to June 2015
LIST OF CONTRACTS
List all contracts related to the project/program with signature dates
Contract Type | Agency / Contracted party | Contract Value/Amount (USD) | Signiture Date | Payment to Date | Remaining Balance
Individual Contract (Consultancy) |  | 14501.5 | 28th November 2014 | 31st January 2014 | 0
Individual Contract (Consultancy) |  | 7784.08 | 28th October 2015 | 31st January 2014 | 0
Individual Contract (Consultancy) |  | 71964.8 | 28th November 2014 | 27th November 2015 | 71964.8
Individual Contract (Consultancy) |  | 4305 | 25th July 2014 | 30th August 2015 | 0
Individual Contract (Consultancy) |  | 4667.01 | 29th October 2014 | 15th November 2015 | 0
Individual Contract (Consultancy) |  | 19939.85 | 4th December 2014 | 31st December 2014 | 0
Individual Contract (Consultancy) |  | 25140 | 21st May 2015 | 3rd July 2015 | 25140
Service Contract (Project Staff) |  | 19847.2 | 2015-02-02 | 6615.72 | 13231.48
Service Contract (Project Staff) |  | 10347.68 | 27th April 2015 | 912.77 | 9434.91
Service Contract (Project Staff) |  | 10347.68 | 24th September 2014 | 7731.93 | 2615.75
Service Contract (Project Staff) |  | 10347.68 | 10th July 2014 | 7198.07 | 0
Service Contract (Project Staff) |  | 10347.68 | 10th May 2015 | 792.93 | 9554.75
Service Contract (Project Staff) |  | 10347.68 | 1st May 2014 | 7249.92 | 0
Service Contract (Project Staff) |  | 14684.71 | 11th Sept 2014 | 10577.4923 | 4107.2177
Service Contract (Project Staff) |  | 10347.68 | 23rd March 2015 | 2002.14 | 8345.54
Service Contract (Project Staff) |  | 13333.3333 | 12th November 2014 | 5042.2 | 0
Service Contract (Project Staff) |  | 25954.65 | 1st July 2014 | 23791.2 | 2163.45
Service Contract (Project Staff) |  | 14758.2 | 23rd March 2015 | 2855.5 | 11902.7
Service Contract (Project Staff) |  | 10347.68 | 2nd Feb 2015 | 3449.23 | 6898.45
Service Contract (Project Staff) |  | 8395.0617 | 12th November 2013 | 4615.6757 | 0
Service Contract (Project Staff) |  | 10347.68 | 12th November 2014 | 5990.65 | 4357.03
Service Contract (Project Staff) |  | 10347.68 | 12th November 2014 | 5990.65 | 4357.03
Service Contract (Project Staff) |  | 10347.68 | 12th November 2014 | 5990.65 | 4357.03
Service Contract (Project Staff) |  | 14684.71 | 2nd Feb 2015 | 4919.4 | 9765.31
Service Contract (Project Staff) |  | 10347.68 | 22nd Sept 2014 | 7731.93 | 2615.75
Service Contract (Project Staff) |  | 8395.0617 | 4th February 2013 | 2798.3539 | 0
Service Contract (Project Staff) |  | 10347.68 | 2nd Feb 2015 | 3200.63 | 7147.05
Service Contract (Project Staff) |  | 8395.0617 | 3rd December 2013 | 4197.5309 | 0
Service Contract (Project Staff) |  | 10347.68 | 22nd Sept 2015 | 7731.93 | 2615.75
Service Contract (Project Staff) |  | 10347.68 | 2nd Feb 2015 | 3200.63 | 7147.05
Service Contract (Project Staff) |  | 8395.0617 | 13th May 2013 |  | 0
BIDS
List all bids for each contact signed with date of open call and winning bid
CONTRACT & Procurement Method | Submitted Bids | Bid Amount (USD) | Winning Bid Amount (USD) | Selection Justification for the Winner
Venue Hire & Catering services during SWoCK Project partners Climate Services Workshop on the 15th - 17th July 2014. |  | 6929.46 | 6929.46 | The lowest-priced offer among the technically compliant / responsive offer was awarded.
|  | 8800.25 | 8800.25
7500.06
XXX: Sea Level Rise (SLR) equipment hire at 1000/day*21 days to be used during SLR mapping training in South Makira Province on the 5th - 26th July 2014. |  | 2904.56 | 2904.56 | Direct Payment since there is no other Sea Level Rise Mapping Equipment in Country for Hire.
XXX: Payment of printing of T-shirt for the World Meteorology Day 21st |  | 3042.88 |  | A direct Payment was made by the projecgt upon a Letter from Permmanent Secretary after a soliciatation process was made by project partner (MECDM).
Payment to XXX; Advertisement of SWoCK vacancies (LUP officier & 2 PPCs officer [GP & cp]) on the 25th, 26th, 30 July and 1st, 2nd August 2014 |  | 2756.23 |  | A direct payment was made for advertisement of Vanancanies within the Project. Solomon Star Company was selected because of LTA with UNDP and the wider coverage they have in the country.
Reprinting of SWoCK Brochure for promotion or education purposes 9/11/14. |  | 3181.1895 | 3181.19 | The lowest-priced offer among the technically compliant/responsive offer was awarded.
3251.7
3265.3
Printing of 1054 A4 posters for SWoCK Project.03/10/14 |  | 23076.92 |  | The lowest-priced offer among the technically compliant/responsive offer was awarded.
|  | 22857.14 | 22857.14
26394.56
Printing for 100 SWoCK designed round neck T-Shirts for promotion purposes during the World Food Day celebration on the 16th October 2014 |  | 3296.7 | 3296.7 | The lowest-priced offer among the technically compliant/responsive offer was awarded.
3872
3423.62
Life jackets for staff' saftey during SWoCK missions to sites. |  | 4653.7088 | 3484.225 | The lowest-priced offer among the technically compliant/responsive offer was awarded.
4823.32
4775.12
First Aid Kits for staff safety during SWoCK missions to sites. |  | 2780.24 | 2696.15 | The lowest-priced offer among the technically compliant/responsive offer was awarded.
2696.15
2864.2
Purchase 18 handheld GPS units for Minitry of Lands and livestock, Land Use Department. |  | 4103.6936 |  | The Lowest-priced offer among the technically compliant/responsive offer was awarded, due to providing all the required specifications.
|  | 3815.3215 | 4103.6936
2685.2804
Survival kits & Rain coat for staffs' safety during SWoCK mission to sites |  | 3334.46 | 3334.46 | The lowest-priced offer among the technically compliant/responsive offer was awarded.
3423.52
3532.68
Venue Hire for SWoCK V & A training, 27th - 29th October 2014. |  | 4309.52 | 5497.25 | The lowest-priced offer among the technically compliant/responsive offer was awarded.
6922.0246
5526.6758
Venue Hire and Catering during Project retreat, 28th - 30th November 2014 |  | 5497.25 | 5497.25 | The lowest-priced offer among the technically compliant/responsive offer was awarded
12837.8
11808.2
Catering and Venue Hire for the National CBLUP workshop on the 24th - 26th November 2014 |  | 7478.98 |  | xx offer the cheapest price but their conference room cannot cater for 45 participants. So xxx provide the service as the second cheapest.
5904.08
|  | 6824.49 | 6824.49
Live radio broadcast in Honiara during world Food Day on the 16th October 2014. |  | 3548.08 | 3548.08 | xx is the sole and technically qualified supplier of broadcasting on the medium (MW) and shortwave (SW) frequencies that reach all provinces in Solomon Islands, therefore they were awarded.
2 laptops (14th April, 2015) |  | 2723.68 | 2723.68 | The lowest-priced offer among the technically compliant/responsive offer was awarded.
$2, 941.84
3382.63
Communication equipment (26th March, 2015) |  | 5026.11 | 5026.11 | xxx appeared cheaper but they do not have in stock most of the required items, therefore not included in the quote. yyy is the next cheapest, however, the external drive do not meet all the criteria and most of the key equipment are not in stock at the moment, it will take 2-3 weeks to arrive in country. Advance was selected though quote higher, they met all specifications and all equipment are currently in stock.
4700
2139.87
HF Radio for Makira SWoCK Office, Request for Quotation, (8th May, 2015) |  | 2608.94 | 2608.94 | Since XXX is the sole suppliers of HF Radios in Solomon Islands and the quotation received is compliant and responsive to our requirements, the evaluation panel award the contract to supply one complete unit of HF Radio to XXX
Purchase of materials for building Zaina Tina Men's accommadation at Burnscreek for Centre for Organic Systems (ZNT) and Organic Demonstration and Research Farm |  | 5250.78 |  | The lowest-priced product offer among the technically compliant/responsive offer was awarded.
|  | 3433.16 | 3433.16
4975.54
Food processing and preservation equipment for MAL (28th March 2014) |  | 76300 |  | The lowest-priced and quality product offer among the technically compliant/responsive offer was awarded.
|  | $59, 217.97 | $59, 217.97

## Risk Assesment
RISK ASSESMENT
IDENTIFIED RISKS
List all Risks identified in project preparation phase and what steps are being taken to mitigate them
Identified Risk | Current Status | Steps Taken to Mitigate Risk
Poor collaboration between project partners | Medium | Roles and responsibility of project partners discussed and clarified during Technical Advisory Group Meeting. The project board agreed the need for additional oversight function and revised reporting lines since Q3 2014 whereby the Project Management Unit (PMU) now reports directly to the line Ministry's directors' to ensure they are fully informed about the project activities. Regarding NGO partners such as Kastom Gaden Association and SNR which have been slow in their implementation of project activities, the project has taken measures as follows; Requested Kastom Gaden to come up with a strategic plan to showcase to the project that they have the capacity to implement their outstanding activities or else return the funds. Based on this Kastom Gaden acknowledge their limit capacity and signed an MOU with Zainatina which is a member NGO or Kastom Gaden to carry out their activities. To date Zainatina has been carrying out activities in Choisuel and Maliata. Also, certain activities planned for Kastom gaden is mainstreamed into MAL’s activities which is currently being implemented in parallel with the help of technical agricultural staff regarding soil improvement and farming system techniques. NGASI The second half of this reporting period, the project has ceased the MOU with NGASI as progress intended was not acceptable. As way of addressing NGASI’s activities the project is working closely with MAL extension staff and research to have germplasim hubs within research sites were fruits, nuts and tubers are collected and grown for distribution to the MAL research sites Nationally ,Provincially and to SWoCK Communities.
Land disputes amongst community members affect land use planning exercise | low | The initial baseline data and survey including the V&A assessment conducted by the project in target communities identified existing community mechanisms (modern or traditional) that can be used to manage land dispute. Land Use Policy has been drafted and community presentations of the draft have started in the previous reporting period where land disputes were amongst the topics being discussed. In this reporting period,the project has worked well with communities and have produced 15 community based land used plans which indicates the current risk has been reduced.
Limited human resources in SIG agencies to contribute to the activities | low | Participation of SIG officers were secured during the project inception phase. The project board discussed this issue and revised the project organization structure by adding additional human resources supported by the project. Futhermore, on need bases, the project will contract additional technical expertise to help with the implementation of the project activities. During this reporting period the project has recruited a Senior Technical Advisor to provide oversight to PMU and technical guidance to project partners to assist with the project implementation. Also the project has created an additional sennior project officer post to support SIG agencies in implementing project activties.
A series of unusually adverse climatic conditions does not damage adaptation measures being implemented, or weaken the interest of key stakeholders to addressing adaptation issues | low | To anticipate this risks, project activities will be scheduled to avoid and/or respond to such occurrences. A key partner to this project is SIMS which provides timely and accurate weather data to inform implementation of activities with targeted communities. The phase two of procurement of extra parts of Automated Weather Stations and additional training support to related data base management is expected to enhance observational capacity of SIMS towards better climate early warning and information services. In April 2014, flashfloods hit parts of Guadalcanal and Malaita provinces where SWoCK is operational. The project team's response has been swift in coordinating with MECDM and MAL in the attempt to fasttrack the provision of livelihood support. Within the original outcome framework of the project, the project is contributing to the concept of "building back better (or more resilient)".
Weak cooperation by communities at proposed sites | Medium | Managing community expectation to ensure ownership has been difficult which resulted in some setbacks in project activties. A rapid assessment in December 2014 on the uptake by community members of climate resilient agricultural practices showed that the performance of the demonstration plots was less than satisfactory. An adaptive management response was considered necessary as it is impractical to gauge the impact of the project if the slow take-up continues to prevail on the ground. Hence, in response, PMU with the advice of Senior Technical Advisor and Project Partners agreed to change the community demonstration approach to lead farmers approach. The lead farmer approach uses existing gardens to showcase important farming systems approaches relevant to the community context. For example, in Langalanga, lead farmer John Thomas’ garden was profiled and accredited by PMU for demonstration. This way, the SWoCK project does not create any new demonstration sites but only builds on existing successful models in the community. SWoCK will use the local successful farmers to guide SWoCK Project to provide local advice and guidance to interested farmers in the project sites.
The techniques and technologies developed are not gender sensitive - i. e. they increase inequity between men and women or change the social roles of men and women in a way that reduces self reliance | low | The project had identified several entry points of women's networks to work with at the community levels. Gender considerations has been considered in focus group discussions during the V&A assessments carried out in four of the five provinces. Gender inclusion is considered in the establishment of village committees for management of food banks and bulking sites (nurseries) and demonstration plots. Gender balanced / sensitive tools will be developed by the gender consultant under the project to be used by implementing partners to plan, implement and monitor project activities in communities. A gender gap analysis has been produced which looks at roles or men and women in SWoCK communities and partner ministries. Based on this report's recommendation it was highlighted that there is a need for a gender tool for line ministries to utilise. Given other climate change initiatives are also trying to mainstream gender into climate project activties, it has been discussed with key partners to formulate a gender tool which will be complimented by the UNDP PRRP's risk screening tool that would be used at all government tiers as well as on CBLUPs.
NGO's capacity of financial management is weak, prompting the need to find alternative operational arrangements, and causing delays in the formalization of engagements (MoUs) as responsible parties | Medium | Grant Agreement has been signed with Kastom Garden Association, but still needs the financial progress reports to be of substantive standard. PMU is working with Kastom Garden to ensure the financial expenses are captured and reported appropriately. Currently, the PMU assisted by UNDP is carrying out an assessment of the delivery of KGA with an option of terminating the contract and transferring the responsibility of soil assessment to MAL. KGA has sub-contracted Zaina Tina (a local organic farming NGO) to carry out implementation of its activities under the MoU to address the problem of slow delivery.
NGO's capacity to deliver activities on time may be limited which affects the project's outcome results. | Medium | Based on this Kastom Gaden acknowledge their limit capacity and signed an MOU with Zainatina which is a member NGO or Kastom Gaden to carry out their activities. To date Zainatina has been carrying out activities in Choisuel and Maliata. Also, certain activities planned for Kastom garden is mainstreamed into MAL’s activities which is currently being implemented in parallel with the help of technical agricultural staff regarding soil improvement and farming system techniques. NGASI The second half of this reporting period, the project has ceased the MOU with NGASI as progress intended was not acceptable. As way of addressing NGASI’s activities the project is working closely with MAL extension staff and research to have germplasim hubs within research sites were fruits, nuts and tubers are collected and grown for distribution to the MAL research sites Nationally ,Provincially and to SWoCK Communities.
Critical Risks Affecting Progress (Not identified at project design)
Identify Risks with a 50% or > likelihood of affecting progress of project
Identified Risk | Current Status | Steps Taken to Mitigate Risk
Turn over of project staff | medium | During this implementation period due to performance issue four staff's contract were not renewed and two resigned for greener pastures. This affected project's delivery. However, once the new project manager and the full team were recruited with an additional senior post filled, the project picked up momentum. Through proper induction and directives the new project team is progressing well under the current circumstances.
Project coordination between national partners, as well as towards and within provincial and community levels remains a challenge. | medium | To overcome this, the project is establishing and strengthening project coordination mechanisms, such as creating new reporting lines under the Project Board where the Director Climate Change (MECDM) and Director Research (MAL) provide the daily oversight to the PMU, the formalization of a Technical Advisory Committee encompassing all key national partners, the establishment of Provincial and Community Steering Committees, institutionalizing support mechanisms from CROP agencies (e.g. Choiseul partnership, SPC support), clarifying reporting lines of project staff involving relevant line ministry superiors.
Risk Measures: Were there any risk mitigation measures employed during the current reporting period? If so, were risks reduced? If not, why were these risks not reduced?
Add any comments relevant to risk mitigation (word limit = 500)
Risks identified have been managed soundly which resulted in some risks been reduced. For example, the risk of land use conflicts have been managed well continuously through community dialogues. The risk of implementation delays due to government capacity has been addressed through strengthening the PMU staffing to assist SIG agencies. Coordination risks still exist, but the new reporting arrangement which was officially put in place duirng this reporting period is expected to bring the risks to manageable level.

## Rating
RATING ON IMPLEMENTATION PROGRESS
For rating definitions please see bottom of page.
| Progress on Key Milestones |  | Expected Progress |  | Progress to Date | Rating
Project Manager/Coordinator: | 1.1a Guideline for land use planning integrating climate change completed |  | Guideline completed by the beginning of the second year of the project. |  | The draft National Rural Land Use Policy (NRLUP) was completed in March 2014. While the plan was to review and approve the draft by cabinet by June 2014, due to the flash flood that affected many parts of the country in April 2014, this process has been put on hold until now. However, in the meanwhile, MAL has conducted two review workshops in March and May 2015 to finalize the draft and present the document in the SIG prescribed format for cabinet submission. MAL confirmed the launch of the NRLUP on the 12th June 2015. Linking to the NRLUP is the guideline for land use planning integrating climate change considerations. One of the policy goals is to ensure that critical forces of change such as climate change impacts, disaster risk reduction, population increases and so on are holistically addressed in land use planning. One of the policy commitments by the government is to ensure rigorous assessments including vulnerability and adaptation assessment, cost benefit analysis, impact assessments and risk screening be carried out before any land use development plan is carried out. The government shall support sector level bugetary allocation for implementation of key sector adaptation programmes. Climate Change, Disaster Risk Reduction and Disaster Management within the NRLUP identifies areas the ministry is to integrate risk reduction activities to enhance sustainability and resilience of the ministry and the farmers through developing community-based approaches to climate change adaptation and disaster risk reduction, promote agro-forestry with the use of intercropping to reduce vulnerability to natural disaster, soil degradation and erosion and improve farm productivity etc. Most of the focused activities identified are currently being implemented by SWoCK such as the Community plans and agro-forestry awareness. In terms of mainstreaming risk SWoCK is working closely with the Pacific Risk Resilience Programme a regional UNDP programme that looking into mainstreaming risks into the planning processes of Ministry of Agriculture. | HS
| 1.1b Land use planning with communities completed |  | Land use plan should be made available by the end of the third year of the project |  | Community Based Land Use Planning was conducted for a total of 18 communities (15 communities in 2014 and 3 communities in 2015). The outcome of the planning process is the establishment of the Community Based Land Use Plan of Actions (CBLUPoA). CBLUPoA are village plans, small-scale, community driven and somewhat autonomous development plans targeted at specific land use problems (e.g soil infertility, poor water resource management) and resulting in the formulation of community micro-projects. The process of CBLUPoA is highly participatory by which communities fully participate, interact and lead discussions to ascertain their development goals, assess the status of their environment, landform, biodiversity, resource base, prioritize key actions and identify possible threats and risks to achieving their development plans against the backdrop of increasing climate change threats. Climate change is reflected in the vulnerability and adaptation assessments and sea level rise mapping where relevant for coastal communities to inform communities of vulnerable areas for gardening, development and construction of infrastructure. Sea level rise mapping concerns with current and projected sea level rise; vulnerabilities of local natural systems and communities to current and projected climate change impacts; possible adaptation measures and communicating risks and vulnerability to communities. Currently the project team is working closly with the Provincial government and the UNDP PPRP programme to mobilize resources for the implementation of CBLUPoA through the Provincial Budget Allocation for individual Provinces. | HS
| 1.1c Communities receive land use plans |  |  |  | A total of 18 communities received CBLUPoA. Some of the specific activities include; establishment of buffer zone around water catchment areas; establishment of disaster preparedness plans, replanting of mangrove on degraded coastline areas, soil improvement trainings, introduce resilient crops, establishment of protected areas, establishment of coastal zone management plans. Implementation of some community plans are currently done under the SWoCK project and others incorporated into the provincial Agriculture Extension Services workplan and relevant provincial authorities for their support in implementation. | HS
| 1.2a V&A completed for all project areas |  | V&A training completed for all sites by the end of the third year. |  | V&A was completed for all project areas by March 2015. Assessments for Malaita, Makira and Isabel Provinces completed between 2012-2013 led by Ministry of Agriculture and Livestock (MAL). The Government agreed not to repeat V&A for Choiseul but use the V&A report compiled by SPC/GIZ Project which was conducted in 2012. V&A reports for Malaita, Makira and Isabel Provinces have been reviewed by external UNDP Officials to make improvement of the V&A report quality. The most recent V&A assessment for the project was conducted for Guadalcanal Province from 13-24th April 2015. V&A Profile for each of the communities will be produced and resource material for SNRAS curriculum. Using participatory V&A approach, participating communities built capacity and enhance their understanding and awareness of key attributes of climate change vulnerability impacting their food security and agriculture and how community can build their adaptive capacity to response most effectively. The results of the V&As inform the type of interventions prioritised for each community. | S
| 1.2b All on-farm demos on soil management and crop diversification completed |  | At least one demo site is established in all target provinces and areas by the fourth year of the project |  | 30 communities in 5 Provinces (Makira, Choiseul, Isabel, Malaita, Guadalcanal) have established on-farm demonstrations using lead farmer approach. A lead farmers garden is used as demonstration garden. The lead farmer is responsible for the management of the garden and is expected to become a conduit of skills to other interested farmers in the community. By March 2015, the project has registered a total of 123 lead farmers that the project is working with in the 30 communities. Soil improvement, management trainings with their communities and diversification of crop base have already taken place in most of the lead farmers gardens. A number of bulking sites have been established (4 in Guadalcanal, 2 in Makira, 1 in Choiseul and 1 in Isabel) in preparation for this activity. Bulking sites are used as nurseries to grow crops to be used in demonstration sites. Some of these crops include yam, pana, taro, cassava and sweetpotatoe varieties. | S
| 1.2c All aquaculture demonstrations completed |  | Demonstration completed by the beginning of the fourth year of the project |  | The aquaculture demonstration is an integrated set-up. Intergration in this set-up means crop-livestock-fish farming co-existing and using the pond ecosystem to stabalize nutrient use in the ponds. A feasibility study on the establishment of the integrated aquaculture demonstration at School of Natural Resource & Applied Science (SNRAS) was completed by the Ministry of Fisheries and Marine Resources (MFMR), WorldFish and SNRAS. The design inputs was supported by 6 SNRAS staff that participated in the Look and Learn trip to Cook Islands and Fiji. Project also supported a full time staff (Aquaculture Technician) for the next 12 months to manage and provide technical reports to the project on the establishment and replicate the design for interested communities. A Letter of Agreement was signed by UNDP and SNRAS for the support provided to the latter for the position of the Aquaculture Technician. Statement of Works for the excavation was prepared by Aquaculture Technician. Although the work was expected to be completed by July 2015, it is currently facing delay due to the technicality of the excavation work. | MS
| 1.2d All 200 target farmers supplied with improved germplasm and planting materials |  | 200 farmers receiving germplasm and planting materials by the beginning of the fourth year of the project |  | A total of 123 interested farmers from five provinces have registered with the project to receive improved planting materials that are either selected based on local criteria’s for crop resilience or MAL tested varieties. From the 123 farmers, about 40 farmers will be selected to attend the agro-biodiversity and Plant Genetic Resources for Food and Agriculture (PGRFA) workshop that will be organized by the Germplasm Consultant to ascertain the status of PGRFA in Solomon Islands. So far, 30 farmers in Isabel have received sweetpotatoe varieties that have shown strong resistence to pest and disease. The PGRFA workshop was conducted successfully and farmers from Makira, Malaita, Isabel, Choiseul, Guadalcanal, Temotu attended the workshop. A staus report for PGRFA for provinces highlighted the priority crops for the provinces. Priority crops for Makira are banana, sweet potato and taro and yam. Those for Isabel are sweet potato, wild yam, taro, banana. Those for Choiseul Province are taro, sweet potato, banana, cassava, leafy vegetables. Those for Malaita Province are taro, yam, sweet potato, breadfruit, lesser yam, and banana. Those for Guadalcanal Province are taro, wild yam, lesser yam, and giant swamp taro. The priority crops are considered by farmers to be essential for food security based on use, they need to be resistant to pests and diseases, they require long storage in the ground and quick maturity for some crops. The SWoCK project is using the PGRFA report to guide germplasm collections and bulking and supply to farmers in doing so the project is likely to see adjustments on demonstration sites. | S
| 1.2e Market outlet for nut growers established |  | Outlet established by the end of third years of project |  | NGASI was recruited during the last reporting period. They have established three nurseries (nuts and other fruit trees) in three provinces (Choiseul, Isabel and Makira). A market outlet (Maraghoto Holdings) is in place but supply of nuts is low to meet desired demand.TOR to engage a local consultant is under preparation for local consultant to investigate the viability of local markets supporting Indigenouse Fruit and Nut growers (IFN). NGASI will only concentrate on collection and distribution of IFN for 2015. Since the departure of the NGASI project coordinator, there is lack of human resources for NGASI to contribute its mandated responsibility under the project. To date the mirco-grant agreement with NGASI is yet to be finalized awaiting the progress report for the last quarter which has not been produced by the outgoing coordinator. Given the current level of progress, the Government and UNDP are in discussion to reassess and possibliy change the scope of this milestone. | MU
| 1.3a Review of the staus of germplasm collection and agro-biodiversity |  | Food banks and germplasm collections established by the end of the third year |  | After two rounds of unsuccesful RFPs for the germplasm consultancy in previous reporting periods, this reporting period, a successful candidate was identied internationally. The purpose of the germplasm consultancy is to produce a status report on Plant Genetic Resources for Food and Agriculture (PGRFA) in Solomon Islands and develop a training programme for gene collection and plant material utilization. Specifically, the status report must identify what exists, what has been lost, what is the capacity, what are the needs now and in the future taking into account climate change projections and nutrition needs, where are the gaps, and where should PGRFA research should focus and how best Solomon Islands PGRFA can be conserved and utilized. For future farmer owned gene banks are encouraged to promote crop diversity. The findings of the PGRFA report points to a general decline in plant genetic diversity in crops and leafy vegetables nationally, and a germplasm framework for collection, utilization and management was proposed, using a three tier approach for communities, provinces and national level. Since the PGRFA report was made available in July 2015, the SWoCK project has now adopted the framework for Makira and Isabel Provinces which are ready to start activities in this regard. A short, medium and long term training programme for genetic resources collection, utilization and management for farmers was also developed. Short term training areas include; database use, climate change impact on food production, farmer information collection, use of descriptors and genebank management. Medium term training needs include participatory plant breeding and tissue culture. Long term training needs will most likely include scale-up trainings on the medium and short term training needs. | S
| 1.3b All food banks and germplasm collections established |  |  |  | Food banks are defined as "reserved food crops", stored in the ground for longer period with the intention to use during disaster times, for example, during cyclone seasons, flood events and or drought periods. Reserved food crops include giant swamp taro (kakake), yam, lesser yam, taro, breadfruit, indigeous nuts. Some food banks exist as monocropping establsihments whilst others in groves. Food bank awareness for all provinces was reported. As with developing a strategic approach to promoting food banks, provincial differences exist, and must be considered in establsihing food banks. Total of 123 farmers involved in planting reserved food crops such as kakake, yam, taro, breadfruit and breadfruit from planting material distributions made by the project to communities of Makira, Isabel, Guadalcanal, Choiseul and Malaita. A video documentary on how to prepapare a kakake pudding was done with Ataa community, in Malaita Province. Germplasm collections have been initiated in all provinces in the past. Now that the PGRFA report has been made available since July 2015, the project is adjusting germplasm collections and bulking as per each province's need and in doing so the project is likely to see adjustments on demonstration sites especially with selection of priority crops given that report cited some crops such as "sweetpotato" as highly likely to be vulnerable under future climate scenarios whilst banana and other crops like cassava and taro may strive better. However given the completion of the PGRFA was towards the later end of project implementation, in terms of timing, it is likely that activities are not going to be scaled-up. | S
| 1.4 One-off assistance to women’s group to procure simple technologies or equipment for food processing and preservation |  | One-off assistance provided to women in communities to promote simple local techniques of food preservation and processing by the 3rd year. |  | Food processing machines for demonstration purpose to be based in Honiara are being procured. In April Board meeting, it was suggested that knowledge exchange be facilitated between the Pacific Adaptation to Climate Change Project (SCCF-financed) and SWoCK projects on solar driers, grinders and chips making. However, there have been little discussions about appropriate ways for food processing (both utilizing traditional techniques as well as introduction of new simple techniques). The School of Natural Resources & Applied Science (SNRAS) food processing procurement is earmarked to focus strongly on local, simple tools and techniques. However, due to lack of storage capacity at the SNRAS, the procurement is indefinitely on hold. As a result, the role of SNRAS to provide food processing training for women who receive assiatnce for root crop processing may not happen in this format. The assistance that is going to women's group will be facilitated by the SWoCK project as a one-off assistance to women's groups to support simple food processing and preservation equipment or techniques. Consultation with urban women in Honiara was conducted on the 21st March for a stock take on the different types of food processing activities, equipment and products urban women use in food processing. A rapid consultation was also done with Keamami Community of GPPOL 1 and Rade Aekoa and Lilisiana of Lanagalanga, Malaita Province to represent the peri-urban communities and rural community respectively. These consultation outcomes will guide the determination of the range of tools and equipment that can be supported under the women’s grant facility for urban, peri-urban and rural dwelling women. A one-off grant assistance is envisaged to support women in food processing to the amount of USD$50,000 for 2015. | MS
| 1.5a All training activities on climate information conducted |  | Soil suitability and crop selection manual completed by the middle of the second year of the project |  | A discussion with SIMS about the production of seasonal calendar has taken place, but no concrete ways forward has been agreed. Follow up discussions with SIMS and MECDM are planned to identify capacity gaps, if any, within SIMS to produce seasonal calendar. Seasonal calenders are also identified as a climate product to be developed by SIMS and agriculture for specific traditional crops. The first training is specific to the climate information collected and stored by the AWS’s. The first planned training for development of agriculture drought information and disaster flood information is to be conducted as soon as the NIWA contract for Phase 2 is ready. The training on climate information was itemised as one of the key milestones in the NIWA Phase 2 contract. Discussion was facilitated with MAL LUP for a mini-crop selection manual based on Research Bulletin No.1 by L.D.C Chase. MAL agreed and the mini-soil suitability and crop selection manual is under review and will be completed before the end of the year. | MS
| 1.5b Soil suitability and crop selection manual completed |  |  |  |  | MS
| 2.1a Climate change mainstreaming guideline completed |  | By the end of the second year of the project, sub-national level mainstreaming is complete; by the end of the third year of the project, a mainstreaming guideline is produced. |  | Mainstreaming climate change adaptation is an iterative process of integrating climate change adaptation considerations into policy making, policy reviews and coordination mechanisms at national, sector and sub-national level. At the national level, the project procured an international land use specialist who drafted the National Rural Land Use Policy (NRLUP) (See Progress 1.1a above). The NRLUP recognised the issues of climate change confronting sustainable development in the form of proper land use planning and integrated robust vulnerability and adaptation assessments and risk screening as pre-requisites for development approval. The project also supported the review and adjustment of the Agriculture and Livestock Sector Policy (2009-2014) to integrate climate change considerations. A local consultant was procured to facilitate the review which is now underway with national consultation carried out in July. The details of the review in terms of the specifics of climate change considerations integrated into the revised policy will become known when the draft version of the review is made available for comments in September 2015. At the sub-national level, the Provincial Climate Change Steering Committees (PCCSC) estabished for Malaita, Makira and Isabel Province. In tandem with efforts to mainstream climate change into policy processes, the overall objective of the establishment of the PCCSC as a coordination mechanism is for the long term strengthening of sub-national institution and capacities. PCCSC is envisioned to be a standard practice, pivotal to establishing climate change adaptation mainstreaming as a standard practice in government, administrative procedures, systems and tools at all levels of government. Apart from the provincial-national coordination role of PCCSC, it will also assist in advisory role for provincial planners who work with divisional workplans to incorporate climate change risks in the screening criteria used to assess project proposals before inclusion into provincial development plans/programmes. The PCCSC will also encourage action on adaptation by promoting relevant budgetary support mechanisms for sector level budget support and promote performance budgeting as part of adaptation mainstreaming efforts to encourage climate change conscious decision making by planners. The project experiences in mainstreaming climate change at the national level (policy making, policy review) and provincial level (PCCSC) will be documented into a "climate change adaptation manistreaming guideline for Solomon Islands". The development of the mainstreaming guideline will be prioritised for the 4th quarter of 2015. | MS
| 2.1b Gender mainstreaming guideline completed |  |  |  | Development of the gender mainstreaming guideline is a milestone that has to be changed due to limited time to complete the particular milestone. The SWoCK Project will however look at the gender baseline study recommendations completed in February 2015 which pointed to a number of issues including lack of monitoring of policy implementation for gender indicators, lack of capacity development for project implementers on gender tools and resources, weak collaboration and coordination between gender agencies implementing gender related projects. Based on the study recommendations, the SWoCK Project intends to contribute to the development of resource material for sensitive and inclusive gender participation at community level consultations, workshops and or decision making meetings. Based on project experiences, a consultant is intended to be procured to produce the resource material. | MS
| 2.1c All four provinces mainstream climate change |  |  |  | There are other projects also working in the area of mainstreaming climate change at the provincial level such as the Pacific Risk Resilience Project (PRRP) and Climate Risilience Integration Project (CRISP) concurrently with SWoCK Project. In discussion with these initiatives to avoid duplication and promote complementarity, the SWoCK Project will focus on the PCCSC mechanism and support the integration of climate change into budget planning for any fiscal year, risk screening for provincial development plans including community based land use planning projects and coordination of provincial-nation climate change projects at the provincial level. | S
| 2.2a National agro-meteorological services strategy completed |  | All AWS and manual voluntary weather stations established by the end of the third year of the project |  | SIMS has completed the national agro-meteorological strategy under their corporate plan supported by the UNDP SIMCAP Project. Since this milestone was already completed by another project, the SWoCK Project contributed towards capacity building as another element of mainstreaming climate services into agriculture sector through the recommendations of both Permanent Secretaries of Ministry of Environment Climate Change Disaster Management & Meteorlogy (MECDM) and Agriculture and Livestock (MAL) who are kep implementing partners of the SWoCK Project. The SWoCK Project in turn supported a Senior Farming Systems Research Officer to undergo training in China on agrometeorological forecasting, agrometeorological analysis and stimulate crop growing systems, operate agriculture remote sensing and operate and use agroclimatic resources. The outcome of the training will further strengthen dialogue and partnership between the Solomon Islands Meterological Services (SIMS) and Agriculture Sector in addressing food security through the climate change adaptation and resilience lens. | S
| 2.2b All AWS and manual voluntary weather stations established |  |  |  | All AWS (4) and VRG (12) already procured. 1 AWS and 1 VRG already installed at Avuavu in 2014. A new contract has been awarded to National Institute of Water & Atmospheric Research Ltd (NIWA) to procure spare parts for the AWSs and VRGs and complete the installation. Two additional AWSs will be installed at Mono in the Shortland Islands and at Tikopia in the far esatern side of Solomon Islands. The two areas are cyclone-prone areas and the installation will complete a national coverage of meteorlogical forcast for highly vulnerable, disaster proned areas. Climate Early Warning System for agricultural drought and fire will be developed for specific agricultural crops in the pahsee 2 of the NIWA contract. | S
| 2.3a GIS laboratory completed and 1st training course offered |  | GIS laboratory completed and 1st training course offered by the beginning of the third year of the project |  | 12 computers have been purchased and now at SNR. A consultant was procured to provide the architectural design for a GIS laboratory to house 40 computers, a reprograhic room and a server along with the bill of quantity for the construction of the laboratory. Currently, an approval is pending from the Honiara City Council to start the construction of the GIS laboratory. It is expected to be completed before the end of the year. GIS software was already installed for the 12 computers. A basic GIS training was also conducted for 12 teaching staff of School of Natural Resources & Applied Science many of whom have no previous GIS knowledge which was concluded in August. In addition, a consultant to design a curriculum course for applied GIS to land use planning for agriculture to be taught at the certificate level was sought nationally. Unfortunately, there was no response to the procurement notice and so the plan is to re-advertise internationally. | MS
| 3.1a Project communication strategy |  | Project communication strategy completed during the first year of the project |  | Communication Strategy has been complete in March 2014. So far, the following communication materials have been produced: - 1,000 Brochure (English/Pidn) on climate change - 1,000 Brochure (250 for each disease) on common pests and diseases for potatoes, taro, cabbage and casava (2 languages) - A factsheet on the project (replica of SWoCK brochure) - 24 programmes (Monthly 15-minute each) on national public radio. A video footage of giant swamp taro pudding preparation was captured at Ataa Community, Malaita Province but is still to complete post-production stage. An international consultant was procured to produce 5 video documentaries for SWoCK Project impact areas and the production will be officially completed by 16th of October. The five documentary thematic areas include; backyard farming on artificial islands, women and climate change adaptation, bulking and germplasm collections, improving climate forcasting through automatic weather stations and community based land use planning for better adaptation. | S
| 3.1b Compilation of first case studies completed and ready for distribution within the country and internationally |  |  |  | A consultant was sought for the development of four case studies. The consultant shall lead and mentor a team of four project staff to write four case studies based on four project impact areas as approved by PMU, to edit manuscripts, compile case studies into publishable formats ready to share with national and international audiences. The consultancy is planned to begin on 7th of September and conclude on 30th October. | MS
| 3.2 First resource material completed and ready for distribution to SNR students and extension staff |  | First resource materials to be completed by the beginning of the third year of the project |  | Participatory V&A tool, Community Based Land Use Planning Toolkit; Community Based Land Use Planning Modules and Sea Level Rise Mapping and Beach Profiling resource materials currently under development | S
[5 empty] | Overall Rating | S
Please Provide the Name and Contact information of person(s) reponsible for completeling the Rating section
| Name: | Kristina Fidali
| Email: | kristina.fidali@undp.org
Please justify your rating. Outline the positive and negative progress made by the project since it started. Provide specific recommendations for next steps. . (word limit=500)
The overall rating for the project since the last reporting period has improved from Marginally Satisfactory (MS) to Satisfactory (S). The marked improvement is a result of a number of adaptive responses within the project but the key adaptive changes include clearer strategic direction for the project, strong support and collaboration between key implementing partners, strong team work from project staff and improved access to technical advise through the inclusion of a Senior Technical Advisor to support PMU. For future, further improvement can be achieved if procurement of key goods and services identified in our procurement plan is delivered in a timely manner. To improve progress, project staff are encouraged to improve their competence on procurement by sitting for procurement tests to improve their understanding of UNDP processes and guidelines to improve on procurement planning and, more importantly, overall efficiency in procurement support needs to improve.
| Progress on Key Milestones |  | Expected Progress |  | Progress to Date | Rating
Implementing Agency | 1.1a Guideline for land use planning integrating climate change completed |  | Guideline completed by the beginning of the second year of the project. |  | The draft National Rural Land Use Policy (NRLUP) was completed in March 2014. While the plan was to review and approve the draft by cabinet by June 2014, due to the flash flood that affected many parts of the country in April 2014, this process has been put on hold until now. However, in the meanwhile, MAL has conducted two review workshops in March and May 2015 to finalize the draft and present the document in the SIG prescribed format for cabinet submission. MAL confirmed the launch of the NRLUP on the 12th June 2015. Linking to the NRLUP is the guideline for land use planning integrating climate change considerations. One of the policy goals is to ensure that critical forces of change such as climate change impacts, disaster risk reduction, population increases and so on are holistically addressed in land use planning. One of the policy commitments by the government is to ensure rigorous assessments including vulnerability and adaptation assessment, cost benefit analysis, impact assessments and risk screening be carried out before any land use development plan is carried out. The government shall support sector level bugetary allocation for implementation of key sector adaptation programmes. Climate Change, Disaster Risk Reduction and Disaster Management within the NRLUP identifies areas the ministry is to integrate risk reduction activities to enhance sustainability and resilience of the ministry and the farmers through developing community-based approaches to climate change adaptation and disaster risk reduction, promote agro-forestry with the use of intercropping to reduce vulnerability to natural disaster, soil degradation and erosion and improve farm productivity etc. Most of the focused activities identified are currently being implemented by SWoCK such as the Community plans and agro-forestry awareness. In terms of mainstreaming risk SWoCK is working closely with the Pacific Risk Resilience Programme a regional UNDP programme that looking into mainstreaming risks into the planning processes of Ministry of Agriculture. | HS
| 1.1b Land use planning with communities completed |  | Land use plan should be made available by the end of the third year of the project |  | Community Based Land Use Planning was conducted for a total of 18 communities (15 communities in 2014 and 3 communities in 2015). The outcome of the planning process is the establishment of the Community Based Land Use Plan of Actions (CBLUPoA). CBLUPoA are village plans, small-scale, community driven and somewhat autonomous development plans targeted at specific land use problems (e.g soil infertility, poor water resource management) and resulting in the formulation of community micro-projects. The process of CBLUPoA is highly participatory by which communities fully participate, interact and lead discussions to ascertain their development goals, assess the status of their environment, landform, biodiversity, resource base, prioritize key actions and identify possible threats and risks to achieving their development plans against the backdrop of increasing climate change threats. Climate change is reflected in the vulnerability and adaptation assessments and sea level rise mapping where relevant for coastal communities to inform communities of vulnerable areas for gardening, development and construction of infrastructure. Sea level rise mapping concerns with current and projected sea level rise; vulnerabilities of local natural systems and communities to current and projected climate change impacts; possible adaptation measures and communicating risks and vulnerability to communities. Currently the project team is working closly with the Provincial government and the UNDP PPRP programme to mobilize resources for the implementation of CBLUPoA through the Provincial Budget Allocation for individual Provinces.
| 1.1c Communities receive land use plans |  |  |  | A total of 18 communities received CBLUPoA. Some of the specific activities include; establishment of buffer zone around water catchment areas; establishment of disaster preparedness plans, replanting of mangrove on degraded coastline areas, soil improvement trainings, introduce resilient crops, establishment of protected areas, establishment of coastal zone management plans. Implementation of some community plans are currently done under the SWoCK project and others incorporated into the provincial Agriculture Extension Services workplan and relevant provincial authorities for their support in implementation.
| 1.2a V&A completed for all project areas |  | V&A training completed for all sites by the end of the third year |  | V&A was completed for all project areas by March 2015. Assessments for Malaita, Makira and Isabel Provinces completed between 2012-2013 led by Ministry of Agriculture and Livestock (MAL). The Government agreed not to repeat V&A for Choiseul but use the V&A report compiled by SPC/GIZ Project which was conducted in 2012. V&A reports for Malaita, Makira and Isabel Provinces have been reviewed by external UNDP Officials to make improvement of the V&A report quality. The most recent V&A assessment for the project was conducted for Guadalcanal Province from 13-24th April 2015. V&A Profile for each of the communities will be produced and resource material for SNRAS curriculum. Using participatory V&A approach, participating communities built capacity and enhance their understanding and awareness of key attributes of climate change vulnerability impacting their food security and agriculture and how community can build their adaptive capacity to response most effectively. The results of the V&As inform the type of interventions prioritised for each community. | S
| 1.2b All on-farm demos on soil management and crop diversification completed |  | At least one demo sites are established in all target provinces and areas by the fourth year of the project |  | 30 communities in 5 Provinces (Makira, Choiseul, Isabel, Malaita, Guadalcanal) have established on-farm demonstrations using lead farmer approach. A lead farmers garden is used as demonstration garden. The lead farmer is responsible for the management of the garden and is expected to become a conduit of skills to other interested farmers in the community. By March 2015, the project has registered a total of 123 lead farmers that the project is working with in the 30 communities. Soil improvement, management trainings with their communities and diversification of crop base have already taken place in most of the lead farmers gardens. A number of bulking sites have been established (4 in Guadalcanal, 2 in Makira, 1 in Choiseul and 1 in Isabel) in preparation for this activity. Bulking sites are used as nurseries to grow crops to be used in demonstration sites. Some of these crops include yam, pana, taro, cassava and sweetpotatoe varieties. | S
| 1.2c All aquaculture demonstrations completed |  | Demonstration completed by the beginning of the fourth year of the project |  | The aquaculture demonstration is an integrated set-up. Intergration in this set-up means crop-livestock-fish farming co-existing and using the pond ecosystem to stabalize nutrient use in the ponds. A feasibility study on the establishment of the integrated aquaculture demonstration at School of Natural Resource & Applied Science (SNRAS) was completed by the Ministry of Fisheries and Marine Resources (MFMR), WorldFish and SNRAS. The design inputs was supported by 6 SNRAS staff that participated in the Look and Learn trip to Cook Islands and Fiji. Project also supported a full time staff (Aquaculture Technician) for the next 12 months to manage and provide technical reports to the project on the establishment and replicate the design for interested communities. A Letter of Agreement was signed by UNDP and SNRAS for the support provided to the latter for the position of the Aquaculture Technician. Statement of Works for the excavation was prepared by Aquaculture Technician. Although the work was expected to be completed by July 2015, it is currently facing delay due to the technicality of the excavation work. | MS
| 1.2d All 200 target farmers supplied with improved germplasm and planting materials |  | 200 farmers receiving germplasm and planting materials by the beginning of the fourth year of the project |  | A total of 123 interested farmers from five provinces have registered with the project to receive improved planting materials that are either selected based on local criteria’s for crop resilience or MAL tested varieties. From the 123 farmers, about 40 farmers will be selected to attend the agro-biodiversity and Plant Genetic Resources for Food and Agriculture (PGRFA) workshop that will be organized by the Germplasm Consultant to ascertain the status of PGRFA in Solomon Islands. So far, 30 farmers in Isabel have received sweetpotatoe varieties that have shown strong resistence to pest and disease. The PGRFA workshop was conducted successfully and farmers from Makira, Malaita, Isabel, Choiseul, Guadalcanal, Temotu attended the workshop. A staus report for PGRFA for provinces highlighted the priority crops for the provinces. Priority crops for Makira are banana, sweet potato and taro and yam. Those for Isabel are sweet potato, wild yam, taro, banana. Those for Choiseul Province are taro, sweet potato, banana, cassava, leafy vegetables. Those for Malaita Province are taro, yam, sweet potato, breadfruit, lesser yam, and banana. Those for Guadalcanal Province are taro, wild yam, lesser yam, and giant swamp taro. The priority crops are considered by farmers to be essential for food security based on use, they need to be resistant to pests and diseases, they require long storage in the ground and quick maturity for some crops. The SWoCK project is using the PGRFA report to guide germplasm collections and bulking and supply to farmers in doing so the project is likely to see adjustments on demonstration sites. | MS
| 1.2e Market outlet for nut growers established |  | Outlet established by the end of third years of project |  | NGASI was recruited during the last reporting period. They have established three nurseries (nuts and other fruit trees) in three provinces (Choiseul, Isabel and Makira). A market outlet (Maraghoto Holdings) is in place but supply of nuts is low to meet desired demand.TOR to engage a local consultant is under preparation for local consultant to investigate the viability of local markets supporting Indigenouse Fruit and Nut growers (IFN). NGASI will only concentrate on collection and distribution of IFN for 2015. Since the departure of the NGASI project coordinator, there is lack of human resources for NGASI to contribute its mandated responsibility under the project. To date the mirco-grant agreement with NGASI is yet to be finalized awaiting the progress report for the last quarter which has not been produced by the outgoing coordinator. Given the current level of progress, the Government and UNDP are in discussion to reassess and possibliy change the scope of this milestone. | MU
| 1.3a Review of the staus of germplasm collection and agro-biodiversity |  | Food banks and germplasm collections established by the end of the third year |  | After two rounds of unsuccesful RFPs for the germplasm consultancy in previous reporting periods, this reporting period, a successful candidate was identied internationally. The purpose of the germplasm consultancy is to produce a status report on Plant Genetic Resources for Food and Agriculture (PGRFA) in Solomon Islands and develop a training programme for gene collection and plant material utilization. Specifically, the status report must identify what exists, what has been lost, what is the capacity, what are the needs now and in the future taking into account climate change projections and nutrition needs, where are the gaps, and where should PGRFA research should focus and how best Solomon Islands PGRFA can be conserved and utilized. For future farmer owned gene banks are encouraged to promote crop diversity. The findings of the PGRFA report points to a general decline in plant genetic diversity in crops and leafy vegetables nationally, and a germplasm framework for collection, utilization and management was proposed, using a three tier approach for communities, provinces and national level. Since the PGRFA report was made available in July 2015, the SWoCK project has now adopted the framework for Makira and Isabel Provinces which are ready to start activities in this regard. A short, medium and long term training programme for genetic resources collection, utilization and management for farmers was also developed. Short term training areas include; database use, climate change impact on food production, farmer information collection, use of descriptors and genebank management. Medium term training needs include participatory plant breeding and tissue culture. Long term training needs will most likely include scale-up trainings on the medium and short term training needs. | MS
| 1.3b All food banks and germplasm collections established |  |  |  | Food banks are defined as "reserved food crops", stored in the ground for longer period with the intention to use during disaster times, for example, during cyclone seasons, flood events and or drought periods. Reserved food crops include giant swamp taro (kakake), yam, lesser yam, taro, breadfruit, indigeous nuts. Some food banks exist as monocropping establsihments whilst others in groves. Food bank awareness for all provinces was reported. As with developing a strategic approach to promoting food banks, provincial differences exist, and must be considered in establsihing food banks. Total of 123 farmers involved in planting reserved food crops such as kakake, yam, taro, breadfruit and breadfruit from planting material distributions made by the project to communities of Makira, Isabel, Guadalcanal, Choiseul and Malaita. A video documentary on how to prepapare a kakake pudding was done with Ataa community, in Malaita Province. Germplasm collections have been initiated in all provinces in the past. Now that the PGRFA report has been made available since July 2015, the project is adjusting germplasm collections and bulking as per each province's need and in doing so the project is likely to see adjustments on demonstration sites especially with selection of priority crops given that report cited some crops such as "sweetpotato" as highly likely to be vulnerable under future climate scenarios whilst banana and other crops like cassava and taro may strive better. However given the completion of the PGRFA was towards the later end of project implementation, in terms of timing, it is likely that activities are not going to be scaled-up.
| 1.4 1st tranche of root crop processing grant disbursed for women’s group |  | Grant disbursed by the end of the second year. |  | Food processing machines for demonstration purpose to be based in Honiara are being procured. In April Board meeting, it was suggested that knowledge exchange be facilitated between the Pacific Adaptation to Climate Change Project (SCCF-financed) and SWoCK projects on solar driers, grinders and chips making. However, there have been little discussions about appropriate ways for food processing (both utilizing traditional techniques as well as introduction of new simple techniques). The School of Natural Resources & Applied Science (SNRAS) food processing procurement is earmarked to focus strongly on local, simple tools and techniques. However, due to lack of storage capacity at the SNRAS, the procurement is indefinitely on hold. As a result, the role of SNRAS to provide food processing training for women who receive assiatnce for root crop processing may not happen in this format. The assistance that is going to women's group will be facilitated by the SWoCK project as a one-off assistance to women's groups to support simple food processing and preservation equipment or techniques. Consultation with urban women in Honiara was conducted on the 21st March for a stock take on the different types of food processing activities, equipment and products urban women use in food processing. A rapid consultation was also done with Keamami Community of GPPOL 1 and Rade Aekoa and Lilisiana of Lanagalanga, Malaita Province to represent the peri-urban communities and rural community respectively. These consultation outcomes will guide the determination of the range of tools and equipment that can be supported under the women’s grant facility for urban, peri-urban and rural dwelling women. A one-off grant assistance is envisaged to support women in food processing to the amount of USD$50,000 for 2015. | MS
| 1.5 All training activities on climate information conducted |  | Soil suitability and crop selection manual completed by the middle of the second year of the project |  | A discussion with SIMS about the production of seasonal calendar has taken place, but no concrete ways forward has been agreed. Follow up discussions with SIMS and MECDM are planned to identify capacity gaps, if any, within SIMS to produce seasonal calendar. Seasonal calenders are also identified as a climate product to be developed by SIMS and agriculture for specific traditional crops. The first training is specific to the climate information collected and stored by the AWS’s. The first planned training for development of agriculture drought information and disaster flood information is to be conducted as soon as the NIWA contract for Phase 2 is ready. The training on climate information was itemised as one of the key milestones in the NIWA Phase 2 contract. Discussion was facilitated with MAL LUP for a mini-crop selection manual based on Research Bulletin No.1 by L.D.C Chase. MAL agreed and the mini-soil suitability and crop selection manual is under review and will be completed before the end of the year. | MS
1.5 Soil suitability and crop selection manual completed
| 2.1a Mainstreaming guideline completed |  | By the end of the second year of the project, sub-national level mainstreaming is complete; by the end of the third year of the project, a mainstreaming guideline is produced. |  | Mainstreaming climate change adaptation is an iterative process of integrating climate change adaptation considerations into policy making, policy reviews and coordination mechanisms at national, sector and sub-national level. At the national level, the project procured an international land use specialist who drafted the National Rural Land Use Policy (NRLUP) (See Progress 1.1a above). The NRLUP recognised the issues of climate change confronting sustainable development in the form of proper land use planning and integrated robust vulnerability and adaptation assessments and risk screening as pre-requisites for development approval. The project also supported the review and adjustment of the Agriculture and Livestock Sector Policy (2009-2014) to integrate climate change considerations. A local consultant was procured to facilitate the review which is now underway with national consultation carried out in July. The details of the review in terms of the specifics of climate change considerations integrated into the revised policy will become known when the draft version of the review is made available for comments in September 2015. At the sub-national level, the Provincial Climate Change Steering Committees (PCCSC) estabished for Malaita, Makira and Isabel Province. In tandem with efforts to mainstream climate change into policy processes, the overall objective of the establishment of the PCCSC as a coordination mechanism is for the long term strengthening of sub-national institution and capacities. PCCSC is envisioned to be a standard practice, pivotal to establishing climate change adaptation mainstreaming as a standard practice in government, administrative procedures, systems and tools at all levels of government. Apart from the provincial-national coordination role of PCCSC, it will also assist in advisory role for provincial planners who work with divisional workplans to incorporate climate change risks in the screening criteria used to assess project proposals before inclusion into provincial development plans/programmes. The PCCSC will also encourage action on adaptation by promoting relevant budgetary support mechanisms for sector level budget support and promote performance budgeting as part of adaptation mainstreaming efforts to encourage climate change conscious decision making by planners. The project experiences in mainstreaming climate change at the national level (policy making, policy review) and provincial level (PCCSC) will be documented into a "climate change adaptation manistreaming guideline for Solomon Islands". The development of the mainstreaming guideline will be prioritised for the 4th quarter of 2015. | MS
| 2.1b Gender guideline completed (30/6/2012) |  |  |  | Development of the gender mainstreaming guideline is a milestone that has to be changed due to limited time to complete the particular milestone. The SWoCK Project will however look at the gender baseline study recommendations completed in February 2015 which pointed to a number of issues including lack of monitoring of policy implementation for gender indicators, lack of capacity development for project implementers on gender tools and resources, weak collaboration and coordination between gender agencies implementing gender related projects. Based on the study recommendations, the SWoCK Project intends to contribute to the development of resource material for sensitive and inclusive gender participation at community level consultations, workshops and or decision making meetings. Based on project experiences, a consultant is intended to be procured to produce the resource material.
| 2.1c All four provinces mainstreaming climate change |  |  |  | There are other projects also working in the area of mainstreaming climate change at the provincial level such as the Pacific Risk Resilience Project (PRRP) and Climate Risilience Integration Project (CRISP) concurrently with SWoCK Project. In discussion with these initiatives to avoid duplication and promote complementarity, the SWoCK Project will focus on the PCCSC mechanism and support the integration of climate change into budget planning for any fiscal year, risk screening for provincial development plans including community based land use planning projects and coordination of provincial-nation climate change projects at the provincial level.
| 2.2a National agro-meteorological services strategy completed |  | All AWS and manual voluntary weather stations established by the end of the third year of the project |  | SIMS has completed the national agro-meteorological strategy under their corporate plan supported by the UNDP SIMCAP Project. Since this milestone was already completed by another project, the SWoCK Project contributed towards capacity building as another element of mainstreaming climate services into agriculture sector through the recommendations of both Permanent Secretaries of Ministry of Environment Climate Change Disaster Management & Meteorlogy (MECDM) and Agriculture and Livestock (MAL) who are kep implementing partners of the SWoCK Project. The SWoCK Project in turn supported a Senior Farming Systems Research Officer to undergo training in China on agrometeorological forecasting, agrometeorological analysis and stimulate crop growing systems, operate agriculture remote sensing and operate and use agroclimatic resources. The outcome of the training will further strengthen dialogue and partnership between the Solomon Islands Meterological Services (SIMS) and Agriculture Sector in addressing food security through the climate change adaptation and resilience lens. | S
2.2b All AWS and manual voluntary weather stations established
| 2.3 GIS laboratory completed and 1st training course offered |  | GIS laboratory completed and 1st training course offered by the beginning of the third year of the project |  | 12 computers have been purchased and now at SNR. A consultant was procured to provide the architectural design for a GIS laboratory to house 40 computers, a reprograhic room and a server along with the bill of quantity for the construction of the laboratory. Currently, an approval is pending from the Honiara City Council to start the construction of the GIS laboratory. It is expected to be completed before the end of the year. GIS software was already installed for the 12 computers. A basic GIS training was also conducted for 12 teaching staff of School of Natural Resources & Applied Science many of whom have no previous GIS knowledge which was concluded in August. In addition, a consultant to design a curriculum course for applied GIS to land use planning for agriculture to be taught at the certificate level was sought nationally. Unfortunately, there was no response to the procurement notice and so the plan is to re-advertise internationally. | MS
| 3.1 Project communication strategy |  | Project communication strategy completed during the first year of the project |  | Communication Strategy has been complete in March 2014. So far, the following communication materials have been produced: - 1,000 Brochure (English/Pidn) on climate change - 1,000 Brochure (250 for each disease) on common pests and diseases for potatoes, taro, cabbage and casava (2 languages) - A factsheet on the project (replica of SWoCK brochure) - 24 programmes (Monthly 15-minute each) on national public radio. A video footage of giant swamp taro pudding preparation was captured at Ataa Community, Malaita Province but is still to complete post-production stage. An international consultant was procured to produce 5 video documentaries for SWoCK Project impact areas and the production will be officially completed by 16th of October. The five documentary thematic areas include; backyard farming on artificial islands, women and climate change adaptation, bulking and germplasm collections, improving climate forcasting through automatic weather stations and community based land use planning for better adaptation. | MS
3.1 Compilation of first case studies completed and ready for distribution within the country and internationally
| 3.2 First resource material completed and ready for distribution to SNR students and extension staff |  | By the beginning of the third year of the project |  | Participatory V&A tool, Community Based Land Use Planning Toolkit; Community Based Land Use Planning Modules and Sea Level Rise Mapping and Beach Profiling resource materials currently under development | S
[5 empty] | Overall Rating | S
Please Provide the Name and Contact information of person(s) reponsible for completeling the Rating section
| Name: | Lynelle Popot, Yusuke Taishi
| Email: | lynelle.popot@undp.org; yusuke.taishi@undp.org
| Please justify your rating and address the following points: 1. Indicate trends, both positive and negative, in achievement of outcomes as per the project indicators. 2. Detail critical risks that have affected progress. 3. Outline response to MTR undertaken this reporting period. 4. Outline action plan to address projects with a rating of HU, U or MU. Please keep your input to 1200 words |  | The April flash floods in 2014 caused significant damage to food gardens (mostly on kumara, cassava, taro, pana and vegetables), export crops (cocoa, copra, palm oil) as well as fruit trees (banana). In total, 1,225 households in Honiara City and 7,335 households in Guadalcanal province were directly affected. The floods directly impacted the livestock sub-sector, with significant losses of animals, mostly pigs and poultry along with damage to fences, chicken sheds (41 and 13 totally or partially damaged respectively in Guadalcanal and Honiara), and pig structures (64 and 4 totally or partially damaged in Guadalcanal and Honiara respectively). The SWoCK project supported 160 farmers (45% were woman and 55% men) who lost crops and livestock. Areas of support were targeted based on the MAL recovery plan which focused on: a. Crops I. Vegetable rehabilitation II. Root cops rehabilitation III. Cocoa rehabilitation IV. Cocoa driers and fermentries V. Coconut driers VI. Floriculture b. Livestock I. Broiler restocking II. Local poultry breeding III. Piggery restocking IV. Piggery infrastructure The project supported these activities through a grant of USD$196,244. Initially the plan was to support the farmers to do integrated farming systems for crops and livestock. However due to HR capacity within the Ministry of Agriculture it was not possible. The CBLUP is a success activity of the project to date. The process itself is attuned with the current government’s bottom up approach and restructuring within the Ministry of Provincial Government and Institutional strengthening (MPGIS) to give more ownership for direct funding to Ward members for community development. It is seen as a complimentary process to the Provincial Climate Change Steering Committee. Working alongside the Pacific Risk Resilience Programme that also looks at strengthening the governance systems at all tiers of the government, both project/programmes with line Ministries are discussing how CBLUP Action Plans can be funded through an active PCCSC or directly though the Ward grants. This activity is an activity that once the project ends, needs scaling up. An output that is of concern is the community grants for food processing. As the School of Industrial Arts does not have the capacity as stipulated in the project document, it is difficult for us to procure simple food processing from them to assist with the grants to women at pilot communities. However, given the timeframe and based on current situation the project has taken the approach to support community women with a One-off assistance to procure simple technologies or equipment for food processing and preservation. For example in the case of langalanga lagoon, the SWoCK project is in touch with PACC project to discuss the possibility of purchasing food dryers to ensure women in the lagoon can dry sea food for their livelihood as they do not have any soil to garden but live off the sea as the island is manmade or artificial. As this project is coming to a close soon, UNDP, the Government and the Project Team need to start stocktaking of project progress and drafting an exit strategy. Secondly with regards to agro-meteorological activities, it is difficult to achieve this output in the original form envisioned in the project document. However the project still see this output as relevant and thus will support a Senior Farming Systems Research Officer to undergo training in China on agrometeorological forecasting, agrometeorological analysis and stimulate crop growing systems, operate agriculture remote sensing and operate and use agroclimatic resources. Through the training the officer will be the focal point within MAL to work with the Solomon Islands Meteorological Services (SIMS) to address food security. As for the market outlet, based on NGASI’s activities the project has taken a different approach to address this by working closely with MAL extension staff and research to have germplasm hubs and foodbanks within research sites. Food items such as fruits, nuts and tubers have been collected and grown for distribution to the MAL research sites nationally, provincially and to SWoCK Communities. This would be a collective outlet for foodbank, germplasm and fruit and nut outlet. With that, taking into consideration the progress to date, the project has performed satisfactory well. It has strategically looked into its outputs and have targeted enabling activities under each outputs to pick up the implementation phase.
Rating Definitions
|  |  | Highly Satisfactory (HS) | Project actions/activities planned for current reporting period are progressing on track or exceeding expectations to acheive all major outcomes/outputs for given reporting period, without major shortcomings. The project can be presented as “good practice”.
|  |  | Satisfactory (S) | Project actions/activities planned for current reporting period are progressing on track to achieve most of its major outcomes/outputs with only minor shortcomings.
|  |  | Marginally Satisfactory (MS) | Project actions/activities planned for current reporting period are progressing on track to achieve most major relevant outcomes/outputs, but with either significant shortcomings or modest overall relevance.
|  |  | Marginally Unsatisfactory (MU) | Project actions/activities planned for current reporting period are not progressing on track to achieve major outcomes/outputs with major shortcomings or is expected to achieve only some of its major outcomes/outputs.
|  |  | Unsatisfactory (U) | Project actions/activities planned for current reporting period are not progressing on track to achieve most of its major outcomes/outputs.
|  |  | Highly Unsatisfactory (U) | Project actions/activities planned for current reporting period are not on track and shows that it is failing to achieve, and is not expected to achieve, any of its outcomes/outputs.
Note on F70: Phatthamon Jantalae: revised inputs provided

## Project Indicators
PROJECT Indicators
Please provide all indicators being tracked for the project as outlined in the project document
Type of Indicator (indicators towards Objectives, Outcomes, etc…)
Type of Indicator | Indicator | Baseline | Progress since inception | Target for Project End
Objective | No. of enabling policy instruments and coordination mechanisms in the agriculture and food security sector reviewed to integrate climate change hazards and risks. | National policy instruments, coordination mechanisms and institutions in the agriculture and food security sector do not address climate related risks and hazards. | In this reporting period, the National Rural Land Use Policy which was expected to be launched in June 2015 was now recsheduled for September. The delay was due to the recent change of the relevant Minister. The review of the Agriculture and Livestock Policy (2009-2014) and the first draft will be circulated for comments as of the first week of September. In this reporting quarter, the PCCSC for Isabel has completed its consultantion and development of TOR for PCCSC. | At least four national and provincial level policy instruments, and coordination mechanisms (MAL, CCD, SIMS, SNR) addressing the agriculture sector and food security have integrated climate change risks and hazards.
| No. of farming systems to be introduced, communities and households in coastal areas and highlands in Solomon Islands able to maintain or increase food production and food security and cope with climate variability and change. | Communities and agriculture food production systems in coastal areas and highlands of Solomon Islands are exposed to future climate related risks and hazards, have weak coping capacity and have not started building resilience. | 123 lead farmers from 18 communities in 15 Wards and 5 provinces have been introduced to a portfolio of farming systems (mixed cropping, intercropping, agro-forestry) with conservation agriculture practices to help maintain and or increase food production and cope with climate variability and change. | By the end of the project at least 18 wards in 3 climatic and geographic cluster areas (windward side, leeward side and artificial) have integrated climate change risks into their land use plans and farming systems.
Outcome 1 | No. of wards where climate risks are integrated into land use and agriculture production aspects | No of integrated land use planning undertaken and climate change consideration are yet to be factored into land use plans across the different geographic regions in Solomon Islands especially those that are more vulnerable to climate risks | 18 Communities in 15 Wards in 3 climate and geographical areas have established community based land use plan of actions. This year the focus is on implementation of the land use action plans. Discussion to integrate the land use planning at the Ward level will be discussed with two provinces (Isabel and Makira) that have shown inerest and already have structural platform to absorb the roles and functions for land use planning. Some of the specific activities include; establishment of buffer zone around water catchment areas; establishment of disaster preparedness plans, replanting of mangrove on degraded coastline areas, soil improvement trainings, introduce resilient crops, establishment of protected areas, establishment of coastal zone management plans. Implementation of some community plans are currently done under the SWoCK project and others incorporated into the provincial Agriculture Extension Services workplan and relevant provincial authorities for their support in implementation. | By the end of the year 1 detailed land use and climate risk assessments are carried out, and by the end of the project climate-resilient land use planning and agriculture production considerations are integrated into ward development plans in at least 18 wards in 3 climatic and geographic cluster areas.
| No. of wards developing climate-resilient farming and aqua-culture production techniques and systems | Small holder farming systems are not able to cope with declining soil fertility and limited agriculture, processing and food security adaption options and strategies available in the country. | All five provinces have bulking sites established. Sites typically have local crop varieties (root crops, fruites, leaf vegetables). Trial of SPC and MAL local potatoes varieties was conducted in Isabel Province with 5 local varieties identified to be performing well. A feasibility study on the establishment of the integrated aquaculture demonstration at SNRAS was completed by the Ministry of Fisheries and Marine Resources (MFMR), WorldFish and SNRAS personnels. The aquaculture demonstration is an integrated set-up. Intergrated in this set-up means crop-livestock-fish farming co-existing and using the pond ecosystem to stabalize nutrient use in the ponds. The design inputs was supported by 6 School of Natural Resource & Applied Science staff that participated in the Look and Learn trip to Cook Islands and Fiji. Project also supported a full time staff (Aquaculture Technician) for the next 12 months to manage and provide technical reports to the project on the establishment and replicate the design for interested communities. A Letter of Agreement was signed by UNDP and School of Natural Resource & Applied Science for the support provided to School of Natural Resource & Applied Science for the position of the Aquaculture Technician. Statement of Works for the excavation was prepared by Aquaculture Technician. Work was expected to be completed by July 2015 however due to the technicality of the excavation work expected for the drainage system and water pipings for the 5 ponds, it took longer than expected for officers to complete the statement of works for the RFQ. RFQ was used for solicitation and 6 company bids were received and evaluated. A contract is expected to be awarded to the most compliant and responsive bidder by first week of September. Lead farmers in 15 Wards from 5 provinces involved in project farming system activities to date. Lead farmers have undergone series of training in a number of conservation/organic farming practices including contours for hilly garden areas, mulching to retain water moisture, soil improvement by using legumous plants and intercropping, terracing, composting, use of natural pesticides, expansion of food banks, bulking. The germplasm consultant will be onboard by 21st May and will make assessment of the gene bank for agricultural food crops and propose a training program for MAL to promote germplasm with local farmers. Backyard farming is encouraged in areas that face problem with access to good agricultural land, insufficient time for gardening, saltwater intrusion and high rainfall and distant gardens to increase in production for sale and consumption. Food Processing Equipments have been procured for MAL to promote food processing with women to empower women to contribute to food security reslience by improving longer storage time and preservation. | By the end of the project at least 18 pilot wards develop climate resilient farming and aqua-culture production techniques and systems.
Outcome 2 | No. of national and provincial level policies, strategies, plans and coordinating mechanisms reviewed and incorporate climate change risks | Very few national policies taking climate risks into consideration, no policy instruments in place to guide and support communities and households address climate variability and change and coordinating mechanisms not addressing climate change considerations. | Provincial Climate Change Steering Committee was established in Malaita, Makira and consultations for the establishment of PCCSC was completed for Isabel Province. The composition: Chiefs of communities (one chief for Malaita), NGOs, women leaders, youth leaders, representatives from provincial govt (agri, env't, disaster, water), religeous groups. Last years PPR, it was reported "Agriculture Act will be amended to incorporate climate risks. This will be done once Steering Committees are established". Upon advice from the Permanent Secretary of Ministry of Agriculture and Livestock (MAL) through his Undersecretary (Technical), the SWoCK project was encouraged to support the MAL to review the Agriculture and Livestock Policy (2009-2014) instead as it is very urgent. SWoCK Project helped organize a pre-review presentation whereby relevant stakeholders were invited to have a broad base discussion on areas important to mainstreaming climate change into the agriculture sector. Some of the key stakeholders include climate change department, Solomon Islands Meteorological Services, Ministry of Development Planning & Aid Coordination (MDPAC), Ministry of Finance and Treasury (MoFT), National Disaster Management Office and Export Companies. The project is supporting capacity building, and institutional strengthening and coordination and assessments as elements of mainstreaming of climate change adaptation. | By the end of project climate change considerations are incorporated into the national long term development plan, at least three policy and legislative frameworks (new Food Security Policy, Land Use Policy, and Agriculture Act), development planning processes and development plans of at least 4 provincial governments.
| No. of weather stations established in the country, meeting WMO standards and contributing data to national weather service and early warning system | Only five manual weather stations in operation in the country with none located in the windward side of the main islands and in areas more prone to cyclones | Four AWS and 12 voluntary weather stations have been procured. The installation of equipment was also assisted by NIWA. Trainings on maintenance was completed in February 2015. One AWS has been installed in Guadalcanal, one rain gauge in eastern Guadalcanal. Two Met Officers sent to New Zealand for training on instrumentation (caliberation, installation, configuration etc) and to familiarize with the equipment. Upon return, they are now responsible for the installation of the AWS. However, given the newness of the operation for the installation, it is recommended that staff be given opportunity to be guided in the process and not put under pressure to handle costly instruments by themselves, that NIWA technicians will have to be present to supervise. Phase 2 of NIWA support will include development of CLEWS and training for SIMS and MAL, NGOs, Farmers on how to use the products | At least 3 AWS and at least 12 voluntary weather stations established at strategic locations, meet WMO standards and contributing to nationwide monitoring and early warning system.
| Agriculture-tailored climate early warning and information products established and communicated to users. | Historic and new weather data not analysed nor information generated and tailored for distribution to the agriculture sector and other related sectors. | Training on the Automatic Weather Stations and climate service products was completed in June 2014 for about 40 staff of Ministry of Agriculture Livestock (MAL) based at the provincial extension offices and Solomon Islands Meteorological Services fromt he provincial centres. All AWS (4) and VRG (12) already procured. 1 AWS and 1 VRG already installed at Avuavu in 2014. A new contract has been awarded to National Institute of Water & Atmospheric Research Ltd (NIWA) to procure spare parts for the AWS and VRGs and complete the installation of the AWS and VRG. Two additional AWS will be installed at Mono in the Shortland Islands and at Tikopia in the far esatern side of Solomon Islands procured under National Disaster Management Office (NDMO). The NDMO sites are cycloneーprone areas and the installation will complete a national coverage of meteorlogical forcast for highly vulnerable, disaster proned areas. Climate Early Warning System for agricultural drought and fire will be developed for specific agricultural crops in the pahsee 2 of the NIWA contract. | By year 3 agriculture tailored CLEWS and info products are established, and by the end of the project this information is being used by at least 200 personnel from government and NGOs (50 provincial Gov., 70 MAL extensions/research/land use officers, 30 SIMS field staff, 20 KGA staff and 140 contact farmers, NGASI 50 contact farmers) and village constituencies (church leaders, women's group, farmers, CBOs).
| No. of officers within MAL, MECDM, NGOs and SNR trained in methods to support communities integrate climate considerations into agriculture production and land-use planning. | Climate change division of MECDM has only three staff who already have heavy workloads and not able to support V&A and climate change mainstreaming into agriculture and other sectors. | 12 computers have been procured for School of Natural Resources & Applied Science. Sea Level Rise Equipments have been procured also for MECDM to do SLR mapping of vulnerable coastal communities to inform their land use planning. GIS application for land use planning training will be conducted for SNR in June 2015. A GIS laboratory is under planning for construction for teaching of GIS application to land use planning for agriculture. A consultant was procured to provide the architectural design for a GIS laboratory to house 40 computers, a reprograhic room and a server along with the bill of quantity for the construction of the laboratory. The plans was approached by the Pro-Vice Chancellor of the Solomon Islands National University (SINU) for the School of Natural Resources & Applied Science (SNRAS) whom are recepient of the GIS laboratory. A building approval from the Honiara City Council is now sought and once approval is received, a builder will be contracted to construct the building. The GIS laboratory is expected to be completed before the end of the year. GIS software was already installed for the 12 computers. A basic GIS training was also conducted for 12 teaching staff of School of Natural Resources & Applied Science many of whom have no previous GIS knowledge which was concluded in August. In addition, a consultant to design a curriculum course for applied GIS to land use planning for agriculture to be taught at the certificate level was sought nationally. Unfortunately, there was no response to the procurement notice and so the plan is to re-advertise internationally. 12 land use planning modules have been developed as a trainers guide to implement climate-sensitive land use planning for field staff and community representatives | At least 200 officers at the policy and field officer level within MAL, MECDM, NGOs and SNR trained in methods to support communities with integration of climate change risks into land use planning and agriculture production By the end of year 2, a GIS laboratory is established, a GIS based agriculture and climate information system is established, and by the year 3, 16 MAL MECDM and SNR staff trained on its management and application, and by the end of the project at least 12 training courses developed and implemented on climate-sensitive land-use planning for policy makers, field staff and community representatives
Outcome 3 | No. of knowledge products developed and disseminated | Absence of a communication strategy and lack of information management system to support adaptation of the agriculture sector and food security to climate change risks. | Communication Strategy has been completed in March 2014. It entails different components of communication, aims, audience setting, and budgeted activities. Communication Implementation workshop was completed in March 2015 and Communication Implementation Plan was developed for partners. An International Consultant is sought for development of 5 case studies. Additionally an international consultant was procured to produce 5 video documentaries for SWoCK Project impact areas and the production will be officially completed by 16th of October. The five documentary thematic areas include; backyard farming on artificial islands, women and climate change adaptation, bulking and germplasm collections, improving climate forcasting through automatic weather stations and community based land use planning for better adaptation. A project websie is also under development and is expected to be completed by September 2015. 1,000 Brochure (English/Pidn) on climate change 1,000 Brochure (250 for each disease) on common pests and diseases for potatoes, taro, cabbage and casava (2 languages) A factsheet on the project (replica of SWoCK brochure) - PDF is already posted in UNDP Fiji website 24 programmes (Monthly 15-minute each) on national public radio. A video footage of giant swamp taro pudding preparation was captured at Ataa Community , Malaita Province but is still to complete post-production stage. | In each project year at least 5 knowledge products (case study, experience note, photo story, video, technical reports, etc.) developed and disseminated to local, national and regional stakeholders.
| No. of exchange programs and activities designed to share lessons learnt and raise awareness on climate change impacts on agriculture and food production | There is no existing nationwide program and there is a lack of expertise to integrate climate and agriculture information for dissemination to public. | A national exchange program is drafted for the month of July 2015 in Choiseul Province to include farmers from other provinces and promotional events will be hosted. The departure of the Provincial Project Coordinator (PPC) for Choiseul Province for another job left the position vacant so the plan was dropped. Three national workshops for communities that have establsihed their CBLUPoA have been conducted to provide them the avenue to share with other communities their experience in the process of planning. | Exchange site visits organized between participating pilot communities and a national forum held by year 2 and by the end of the year. By the end of the project, Solomon Islands is able to share its experiences on adaptation to climate change in the agriculture and food security sector with other countries within the country, the Pacific and globally by exchange of site visits, organizing a forum and disseminating information through the social media.
| No. of documented case studies and lessons learnt used in the teaching of short courses as well as certificate and diploma courses in agriculture, forestry and environmental studies in the School of Natural Resources (SNR). | SNR do not have local case studies on climate change adaptation and agriculture for use in the range of courses on offer. | A consultant was sought for the development of four case studies. The consultant shall lead and mentor a team of four project staff to write four case studies based on four project impact areas as approved by PMU, to edit manuscripts, compile case studies into publishable formats ready to share with national and international audiences. The consultancy is planned to begin on 7th of September and conclude on 30th October. | At least four case studies generated by the project are incorporated and used in SNR training courses to promote and raise knowledge and understanding of young Solomon Islanders on climate change adaptation in the agriculture sector.

## Lessons Learned
QUALITATIVE MEASURES and LESSONS LEARNED
Please complete the following section every reporting period
Implementation and Adaptive Management | Response
What implementation issues/lessons, either positive or negative, affected progress? | Due to geographical location of the sites, monitoring is not carried out effectively as required on the sites. Monitoring activities must be promoted more proactively to closely monitor community progress. This is important for timely intervention and to give confidence to communities on their own progress in implementation at the community and household level. Also there has been delay in the procurement of SWoCK goods and services which has affected greatly the progress of implementation. Both UNDP and the Government acknowledge that there is room for improvement for the UNDP Honiara Office procurement. Moving forward the project has had many conversation with procurement and operations colleagues of UNDP to seek realistic solutions.
Were there any delays in implementation? If so, include any causes of delays. What measures have been taken to reduce delays? | Unfavourable weather conditions and unrealiable dometic airlines services are disruptive to project implementation. The process for development of TORs can also be lengthy and require sound planning to maximise opportunity for impact on the ground, hence, 5 senior project officers are allocated in pairs to oversee sound planning of TORs to maximise opportunity for effective M&E in the next 12 months.
Describe any changes undertaken to improve results on the ground or any changes made to project outputs (i.e. changes to project design) | Due to geographical spread of project sites for effective monitoring by project staff, lead farmers are engaged as community resource personnel with a specified TOR to carry out monitoring and evaluation and documentation of results based on agreed indicators. This change is encouraging communities to measure their own success and report to each other on their progress through community meetings. This strategy is trialled in Malaita and Choiseul Province.
How have gender considerations been taken into consideration during the reporting period? What have been the lessons learned as a consequence of inclusion of such considerations on project performance or impacts? | For greater impact on the ground and efficiency in the implementation, the project has forged a partnership with Small Grant Program (SGP) to extend technical training to women who have received funding to agriculture related project and need training. This is a case for Sasamunga in Choiseul Province where the project is working with a network of women to support the completion of their seed bank and extension of their kakae food patch and contribute to the distribution of emergency food crop to other women in the community.
Please complete the following section at mid-term and project completion
Lessons for Adaptation | Response
Climate Resilience Measures
What have been the lessons learned, both positive and negative, in implementing climate adaptation measures that would be relevant to the design and implementation of future projects/programmes for enhanced resilience to climate change? | The geographical spread of communities widens the scope of adaptation responses to communities further stretching the capacity of partners to respond effectively on timely manner to communities adaptation plan of actions. For future, it is imperative that capacity building be prioritised for the provincial administration level as implementers of government policies at the sub-national level, who are one level closer to the people. It is costly to administer projects from Honiara as it is far from the communities and it should be moved closer to the people. An ecosystem-based approach to safeguarding the food security of a community is exhibited in some communities to be a strong indicator of food security. The community of Loloko community in South Choiseul, Choiseul Province is surrounded by different ecosystems including the wetland, sea, mangrove forest, riverine, streams, virgin forest and secondary forest. The different ecosystems provide for different food types and because the ecosystems are by and large, intact, the produce of food is very abundant in the community.
What is the potential for the climate resilience measures undertaken by the project/programme to be replicated and scaled up both within and outside the project area? | The chances of replication and upsacling of climate adaptation measures such as food banks, nurseries of plant tolerant species and land use planning in cognisant of climate change impacts reamins high. This is because the process is simple and capacity building for communities is central part of the activities. However, we have also learned various barriers that affect the scale-up potential of the project. For example, support for nut growers for providing access to market outlets was part of the project design, but unsteady supplies and capacity limitation in the NGO that was supporting this activity are leading us to reconsider the viability of this support. The awareness must also create the demand for farming and consumption of resilient crops nationally. Technical and administrative capacities of sub-national government are also critical for sustainability of climate resilience measures. While the project is working toward improving all of these areas, the progress is sometimes slow. In the next reporting period, the formulation of a realistic exit strategy will be one of the important activities for the project and the potential for scale-up will also be discussed.
Concrete Adaptation Interventions
What have been the lessons learned, both positive and negative, in implementing concrete adaptation interventions that would be relevant to the design and implementation of future projects/programmes implementing concrete adaptation interventions? | Same as above
What is the potential for the concrete adaptation interventions undertaken by the project/programme to be replicated and scaled up both within and outside the project area? | Same as above
Community/National Impact
What would you consider to be the most successful aspects for the target communities? | For this reporting period, 15 communities have produced theri CBLUP in which would be implemented in the 3&4th quarter of 2015. This is a vital step forward in linkinng their plans up to the sub national government through their ward level.
What measures are/have been put in place to ensure sustainability of the project/program results? | In terms of sustainability of project results once the project ends, the project has collaborated with the ZainaTina NGO which trains lead farmers on adaptative and organic farming techniques and systems. Organic farming utilizes techniques like crop rotation, cover crops, agro-forestry and leguminous plants. Organic soil has higher carbon content since techniques used will keep photosynthesized carbon dioxide in the soil instead of returning it into the atmosphere. This is a sustainable way of farming into the future and is less costly for village farmers to take up. Futher to that, the project will support lead farmers within communnities who are interested to tap the GEF SGP funding for continuity.
What measures are being/could have been put in place to improve project/program results? | Senior technical adviser was recruited during this reporting period to work closely with PMU to provide the technical backstop. This is based on a recommendation from the MTE report and it has been profoundly helpful in moving the project forward in the right direction. Futher to that by adding another reporting line to the directors of key partner ministries to ensure they are aware about project implementation has aluded to PMU having their support to carry out various activties.
Knowledge Management
How has existing information/data/knowledge been used to inform project development and implementation? What kinds of information/data/knowledge were used? | The information gained and developed by MAL and MECDM has been used to inform project development. MAL, with its expertise especially on pests and diseases, has re-printed an inforemation sheet and translated into a more readable document that can be accepted by the rural people. MECDM information and data in relation to the causes and effects of climate change has been printed and translated into the local common language with the aim of making sure people in rural areas understand the information and take appropriate adaptation action where needed. Futhermore, both Ministries have technical projects with other donors which are complimentary to the project (PACC, PRRP). Through the lead Ministries, informations on lessons learned from similar projects are shared as well as synergies identified to collaborate on some national activites (WED,WFD etc)
If learning objectives have been established, have they been met? Please describe. | During this reporting period, some learning objectives have been established under component 2 in the context of capacity building for implementing partners and are satisfactorily met. One of the successful outcomes of such learning initiatives is the capacity building provided for the CCD staff to use the survey equipment procured under the project for environment impact assessment. The IP is now using the equipment and the knowledge gained to carry out their planned assessments.
Describe any difficulties there have been in accessing or retrieving existing information (data or knowledge) that is relevant to the project. Please provide suggestions for improving access to the relevant data. | There have been some difficulty in gathering usable documents from MET and Climate Change Division to develop easy-to-read brochures or pamphlets. Closer collaboration is needed between MET and CCD Communication officer to develop information sheets that are more accessible and understandable by the rural populace. The information sheets/brochures/pamphlets should be translated into pijin or local dialect. The same can also be said with the Ministry of Agriculture. In this reporting period, retrieval of GIS data needed for advancing GIS based Land Use Planning is difficult due to the unavailability of the data in-country. Efforts have been made for MAL to liaise with SOPAC to source the data for project training purposes. Progress has been made through the help of Permanent Secretary for MAL.
Has the identification of learning objectives contributed to the outcomes of the project? In what ways have they contributed? | The learning objectives include dissemination of information of good practices encountered during the course of the project, lessons learnt, and be knowledgeable about Climate Change, its effects and what can be done to withstand varying weather conditions. The various printed materials, radio programs to be aired soon, brochures, factsheets, and other communication tools that will bedeveloped and delivered now that some sucesses have been identified during the course of the past years will help contribute to the learning objectives. Having the learning objectives in place, it helps with equiping the Project replicate best practices to project sites with the same context but are slow in implementation. For example, in Langalanga, lead farmer John Thomas’ garden was profiled and accredited by PMU for demonstration. As accredited lead farmer, SWoCK use John and his garden as demonstration for interested community farmers to learn from. In this way SWoCK does not create any new demonstration but only builds on existing successful models in the community. SWoCK has used the local successful farmers to guide SWoCK Project to provide local advice and guidance to interested farmers in the project sites. Also, using a capacity building approach in the assessments that project carry out with communities; Participatory Vulnerability Assessment; Community Based Land Use Planning, and Community Based Monitoring and Evaluation, the project is making reputable progress whilst gaining the trust of the community.

## Results Tracker
Results Tracker for Adaptation Fund (AF) Projects
Goal: Assist developing-country Parties to the Kyoto Protocol that are particularly vulnerable to the adverse effects of climate change in meeting the costs of concrete adaptation projects and programmes in order to implement climate-resilient measures. Impact: Increased resiliency at the community, national, and regional levels to climate variability and change.
Important: Please read the following guidance document (also posted on the Adaptation Fund website) before entering your data
Link: http://www.adaptation-fund.org/sites/default/files/Results%20Framework%20and%20Baseline%20Guidance%20final.pdf
Adaptation Fund Strategic Results Framework
Project ID | 00078069
Implementing Entity | UNDP
Type of implementing entity | MIE
Country | Solomon Islands
Region | Asia-Pacific
Sector | Agriculture
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Impact: Increased resiliency at the community, national, and regional levels to climate variability and change | Core Indicator: No. of beneficiaries |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project
|  | Total | 0 | 0 | 0 | Total | 20000 | 3025 | 26975 | Total | 20000 | 335 | 9160 | Total
|  | % of female beneficiaries | 0% | 0% | 0% | % of female beneficiaries | 40% | 30% | 10% | % of female beneficiaries | 40% | 10% | 10% | % of female beneficiaries
|  | % of Youth beneficiaries | 0% | 0% | 0% | % of Youth beneficiaries | 30% | 20% | 10% | % of Youth beneficiaries | 30% | 5% | 10% | % of Youth beneficiaries
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 1: Reduced exposure to climate-related hazards and threats | Indicator 1: Relevant threat and hazard information generated and disseminated to stakeholders on a timely basis | Number of stakeholders |  | Hazards information generated and disseminated | Overall effectiveness | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness
|  | Total | 2 | Drought | 1: Ineffective | Total | 36 | Drought | 5: Very effective | Total | 6 | Drought | 1: Ineffective | Total
|  | % of female targeted | 0% |  |  | % of female targeted | 50% |  |  | % of female targeted | 5% |  |  | % of female targeted
Output 1.1 Risk and vulnerability assessments conducted and updated | Indicator 1.1: No. of projects/programmes that conduct and update risk and vulnerability assessments | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
Output 1.2 Targeted population groups covered by adequate risk reduction systems | Core Indicator 1.2: No. of Early Warning Systems | No. of adopted Early Warning Systems | Category targeted | Hazard | Drought | No. of adopted Early Warning Systems | Category targeted | Hazard | Drought | No. of adopted Early Warning Systems | Category targeted | Hazard | Drought | No. of adopted Early Warning Systems | Category targeted | Hazard
|  | 0 | 1: Risk knowledge |  | National | 3 | 1: Risk knowledge | Geographical coverage | National | 0 | 1: Risk knowledge | Geographical coverage | National |  |  | Geographical coverage
[5 empty] | 0 |  |  | Number of municipalities | 9 |  |  | Number of municipalities | 9 |  |  | Number of municipalities
|  | No. of adopted Early Warning Systems | Category targeted | Hazard | Hurricane | No. of adopted Early Warning Systems | Category targeted | Hazard | Hurricane | No. of adopted Early Warning Systems | Category targeted | Hazard | Hurricane | No. of adopted Early Warning Systems | Category targeted | Hazard
|  | 0 | 2: Monitoring and warning service | Geographical coverage | Local | 3 | 2: Monitoring and warning service | Geographical coverage | National | 0 | 2: Monitoring and warning service | Geographical coverage | National |  |  | Geographical coverage
|  |  |  | Number of municipalities | 4 |  |  | Number of municipalities | 9 |  |  | Number of municipalities | 9 |  |  | Number of municipalities
|  | No. of adopted Early Warning Systems | Category targeted | Hazard | Hurricane | No. of adopted Early Warning Systems | Category targeted | Hazard | Hurricane | No. of adopted Early Warning Systems | Category targeted | Hazard | Hurricane | No. of adopted Early Warning Systems | Category targeted | Hazard
|  | 0 | 3: Dissemination and communication | Geographical coverage | Local | 3 | 3: Dissemination and communication | Geographical coverage | National | 0 | 3: Dissemination and communication | Geographical coverage | National |  |  | Geographical coverage
|  |  |  | Number of municipalities | 4 |  |  | Number of municipalities | 9 |  |  | Number of municipalities | 9 |  |  | Number of municipalities
|  | No. of adopted Early Warning Systems | Category targeted | Hazard | Drought | No. of adopted Early Warning Systems | Category targeted | Hazard | Drought | No. of adopted Early Warning Systems | Category targeted | Hazard | Drought | No. of adopted Early Warning Systems | Category targeted | Hazard
|  | 0 | 4: Response capability | Geographical coverage | Local | 3 | 4: Response capability | Geographical coverage | National | 0 | 4: Response capability | Geographical coverage | National |  |  | Geographical coverage
|  |  |  | Number of municipalities | 0 |  |  | Number of municipalities | 9 |  |  | Number of municipalities | 9 |  |  | Number of municipalities
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 2: Strengthened institutional capacity to reduce risks associated with climate-induced socioeconomic and environmental losses | Indicator 2: Capacity of staff to respond to, and mitigate impacts of, climate-related events from targeted institutions increased | Number of staff targeted |  | Sector | Capacity level | Number of staff targeted |  | Sector | Capacity level | Number of staff targeted |  | Sector | Capacity level | Number of staff targeted |  | Sector | Capacity level
|  | Total | 2000 | Multi-sector | 2: Low capacity | Total | 500 | Multi-sector | 4: High capacity | Total | 500 | Agriculture | 3: Medium capacity | Total
|  | % of female targeted | 50% |  |  | % of female targeted | 50% |  |  | % of female targeted | 50% |  |  | % of female targeted
Output 2.1 Strengthened capacity of national and sub-national centres and networks to respond rapidly to extreme weather events | Indicator 2.1.1: No. of staff trained to respond to, and mitigate impacts of, climate-related events | Total staff trained | % of female staff trained | Type |  | Total staff trained | % of female staff trained | Type |  | Total staff trained | % of female staff trained | Type |  | Total staff trained | % of female staff trained | Type
|  | 4 | 0% | Public |  | 2000 | 50% | Public |  | 335 | 37.6% | Public
| Indicator 2.1.2: No. of targeted institutions with increased capacity to minimize exposure to climate variability risks | Type | Scale | Sector | Capacity level | Type | Scale | Sector | Capacity level | Type | Scale | Sector | Capacity level | Type | Scale | Sector | Capacity level
|  | Public | National | Multi-sector | 2: Low capacity | Public | National | Multi-sector | 4: High capacity | Public | National | Multi-sector | 3: Medium capacity
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 3: Strengthened awareness and owernship of adaptation and climate risk reduction processes | Indicator 3.1: Increase in application of appropriate adaptation responses | Percentage of targeted population applying adaptation measures |  | Sector |  | Percentage of targeted population applying adaptation measures |  | Sector |  | Percentage of targeted population applying adaptation measures |  | Sector |  | Percentage of targeted population applying adaptation measures |  | Sector
|  | 0% |  | Agriculture |  | 20 |  | Agriculture |  | 20 |  | Agriculture
Output 3: Targeted population groups participating in adaptation and risk reduction awareness activities | Indicator 3.1.1: Percentage in targeted population awareness of predicted adverse impacts of climate change, and of appropriate responses | No. of targeted beneficiaries | % of female participants targeted | Level of awareness |  | No. of targeted beneficiaries | % of female participants targeted | Level of awareness |  | No. of targeted beneficiaries | % of female participants targeted | Level of awareness |  | No. of targeted beneficiaries | % of female participants targeted | Level of awareness
|  | 0 | 0% | 2: Partially not aware |  | 4000 | 40% | 5: Fully aware |  | 335 | 30% | 3: Partially aware
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Target performance at completion
Outcome 4: Increased adaptive capacity within relevant development sector services and infrastructure assets | Indicator 4.1: Increased responsiveness of development sector services to evolving needs from changing and variable climate | Project/programme sector | Geographical scale | Response level |  | Project/programme sector | Geographical scale | Response level |  | Project/programme sector | Geographical scale | Response level |  | Project/programme sector | Geographical scale | Response level
| Core Indicator 4.2: Assets produced, developed, improved or strengthened | Sector | Targeted asset | Changes in asset (quantitative or qualitative) |  | Sector | Targeted asset | Changes in asset (quantitative or qualitative) |  | Sector | Targeted asset | Changes in asset (quantitative or qualitative) |  | Sector | Targeted asset | Changes in asset (quantitative or qualitative)
Output 4: Vulnerable development sector services and infrastructure assets strengthened in response to climate change impacts, including variability | Indicator 4.1.1: No. and type of development sector services to respond to new conditions resulting from climate variability and change | Number of services | Type |  | Sector | Number of services | Type |  | Sector | Number of services | Type |  | Sector | Number of services | Type |  | Sector
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid term |  |  |  | Target performance at completion
Outcome 5: Increased ecosystem resilience in response to climate change and variability-induced stress | Indicator 5: Ecosystem services and natural resource assets maintained or improved under climate change and variability-induced stress | Natural resource improvement level |  | Sector | Type | Natural resource improvement level |  | Sector | Type | Natural resource improvement level |  | Sector | Type | Natural resource improvement level |  | Sector | Type
Output 5: Vulnerable ecosystem services and natural resource assets strengthned in response to climate change impacts, including variability | Core Indicator 5.1: Natural Assets protected or rehabilitated | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Baseline information |  |  |  | Targeted performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 6: Diversified and strengthened livelihoods and sources of income for vulnerable people in targeted areas | Indicator 6.1: Increase in households and communities having more secure access to livelihood assets | No. of targeted households | % of female headed households | Improvement level |  | No. of targeted households | % of female headed households | Improvement level |  | No. of targeted households | % of female headed households | Improvement level |  | No. of targeted households | % of female headed households | Improvement level
| Indicator 6.2: Increase in targeted population's sustained climate-resilient alternative livelihoods | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
|  | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
|  | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
|  | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
Output 6 Targeted individual and community livelihood strategies strengthened in relation to climate change impacts, including variability | Indicator 6.1.1: No. and type of adaptation assets created or strengthened in support of individual or community livelihood strategies | Number of Assets | Type of Assets | Sector | Adaptation strategy | Number of Assets | Type of Assets | Sector | Adaptation strategy | Number of Assets | Type of Assets | Sector | Adaptation strategy | Number of Assets | Type of Assets | Sector | Adaptation strategy
| Core Indicator 6.1.2: Increased income, or avoided decrease in income | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 7: Improved policies and regulations that promote and enforce resilience measures | Indicator 7: Climate change priorities are integrated into national development strategy | Integration level |  |  |  | Integration level |  |  |  | Integration level |  |  |  | Integration level
|  | 2: Most not integrated |  |  |  | 4: Most |  |  |  | 3: Some
Output 7:Improved integration of climate-resilience strategies into country development plans | Indicator 7.1: No. of policies introduced or adjusted to address climate change risks | No. of Policies introduced or adjusted | Sector | Scale | Type | No. of Policies introduced or adjusted | Sector | Scale | Type | No. of Policies introduced or adjusted | Sector | Scale | Type | No. of Policies introduced or adjusted | Sector | Scale | Type
|  | 0 | Multi-sector | National |  | 2 | Multi-sector | National |  | 1 | Agriculture | National
| Indicator 7.2: No. of targeted development strategies with incorporated climate change priorities enforced | No. of Development strategies | Regulation |  | Effectiveness | No. of Development strategies | Regulation |  | Effectiveness | No. of Development strategies | Regulation |  | Effectiveness | No. of Development strategies | Regulation |  | Effectiveness
Glacier lake outburst flood
|  | Inland flooding | fr | biological assets |  | Company policy | 5: Fully enforced (All elements implemented)
|  | Salinization | Decrease | land |  | Communication & Information policy | 4: Enforced (Most elements implemented)
|  | Drought | Same | water areas |  | Defense policy | 3: Partially enforced (Some elements implemented)
|  | Wind |  | subsoil assets | increased adpative capacity | Domestic policy | 2: Partially not enforced (Most elements not implemented) |  | Agribusiness
|  | Coastal flooding |  | air | achieved | Economic policy | 1: Not enforced (No elements implemented) |  | Agricultural-related | Financial capital
|  | Storm surge | Please choose |  | enhanced level of protection | Education policy |  |  | Agriculture | Human capital
|  | Hurricane | Selected | [5 empty] | Aquaculture | Physical capital
|  |  | Not relevant |  |  | 5: All (Fully integrated) |  |  | Construction/repairing business | Social capital
[6 empty] | 4: Most |  |  | Cultivation | Natural capital
[6 empty] | 3: Some |  |  | Fishing | Personal capital
Select | 5: All | Select |  |  | Community | 2: Most not integrated |  | Other | Forestry | Adaptation strategies
1 | 4: Almost all | Private | Type | Yes | Multi-community | 1: None |  | Agriculture | Handicrafts
2 | 3: Half | Public | Scale | No | Departmental |  |  | Coastal management | Livestock production
3 | 2: Some | NGO | Sector |  | National |  |  | Disaster risk reduction | Manufacturing
4 | 1: None |  |  |  |  | 5: Very high improvement | Established | Food security | other
|  | National |  |  |  | 4: High improvement | Maintained | Health | Services
|  | Regional |  |  |  | 3: Moderate improvement | Improved | Urban development | Tourism-related
|  | Local |  |  |  | 2: Limited improvement |  | Water management | Trading
[6 empty] | 1: No improvement |  | Multi-sector
|  | 1 -generated information is irrelevant, and neither the stakeholders reached nor the timeframe managed were achieved | 1: No info transferred on time | 4: High capacity | 5: Fully aware | 5: Highly responsive (All defined elements ) | 5: Fully improved | Roads | 5: Very effective
Asia-Pacific | NIE | 2 -the existence of some challenge in any of the three aspects of the indicator (generation of dissemination, stakeholders reached or timeframe managed) | 2: Somewhat info transferred | 3: Medium capacity | 4: Mostly aware | 4: Mostly responsive (Most defined elements) | 4: Mostly Improved | Gov Buildings | 4: Effective
Latin America and Caribbean | RIE | 3 -relevant information is generated and disseminated to all identified stakeholders on timely basis | 3: Info transferred on time | 2: Low capacity | 3: Partially aware | 3: Moderately responsive (Some defined elements) | 3: Moderately improved | Causeways | 3: Moderately effective
Africa | MIE |  |  | 1: No capacity | 2: Partially not aware | 2: Partially responsive (Lacks most elements) | 2: Somewhat improved | Airports | 2: Partially effective
Eastern Europe |  |  |  |  | 1: Aware of neither | 1: Non responsive (Lacks all elements ) | 1: Not improved | Schools | 1: Ineffective
| ha protected | [6 empty] | Training Centres
| ha rehabilitated | [5 empty] | Monitoring/Forecasting capacity | Hospitals
Afghanistan, Islamic Rep. of | km protected | [5 empty] | Policy/regulatory reform | Drinking water systems
Angola | km rehabilitated | 1: Risk knowledge | 1: No plans conducted or updated |  |  |  | Capacity development | Other
Albania |  | 2: Monitoring and warning service | 2: Undertaking or updating of assessments in progress |  |  | Communication & Information policy | Sustainable forest management
Argentina |  | 3: Dissemination and communication | 3: Risk and vulnterability assessments completed or updated |  |  | Domestic policy | Strengthening infrastructure | 1: Health and Social Infrastructure (developed/improved)
Armenia | Forests | 4: Response capability |  |  |  | Economic policy | Supporting livelihoods | 2: Physical asset (produced/improved/strenghtened)
Antigua and Barbuda | Mangroves |  |  |  |  | Education policy | Mangrove reforestation
Azerbaijan | Coasts |  | From 0 to 0.5% |  |  | Energy policy | Coastal drainage and infrastructure
Burundi | Rangelands |  | From 0.5 to 1% |  |  | Environmental policy | Irrigation system
Benin | Cultivated land/Agricultural land |  | From 1% to 5% |  |  | Foreign policy | Community-based adaptation
Burkina Faso | Catchment area/Watershed/Aquifer |  | From 5% to 10% |  |  | Health policy | Erosion control
Bangladesh | Protected areas/National parks |  | From 10% to 20% |  |  | Housing policy | Soil water conservation
Bulgaria | Other |  | From 20% to 30% |  |  | Human resource policies | Microfinance
Bahrain |  |  | From 30% to 40% |  |  | Information policy | Special Program for women
Bahamas, The |  |  | From 40% to 50% |  |  | Macroeconomic policy | Livelihoods
Bosnia and Herzegovina |  |  | Above 50% |  |  | Monetary policy | Water storage
Belarus | [5 empty] | Population policy | ICT and information dissemination
Belize | [5 empty] | Private policy
Bolivia | [5 empty] | Public policy
Brazil | [5 empty] | Science policy
Barbados | [5 empty] | Social policy
Bhutan |  | 3- relevant information is generated and disseminated to all identified stakeholders on timely basis |  |  |  | Transportation policy
Botswana |  | describe |  |  |  | Urban policy
Central African Republic |  | 2- the existence of some challenge in any of the three aspects of the indicator |  |  |  | Water policy
Chile |  | describe |  |  |  | Other policy
China, People's Republic of |  | 1- generated information is irrelevant and neither the stakeholders reached nor the timeframe managed were achieved
Cote d'Ivoire |  | describe
Cameroon
Congo, Dem. Rep. of
Congo, Republic of
Cook Islands
Colombia
Comoros
Cape Verde
Costa Rica
Cuba
Czech Republic
Djibouti
Dominica
Dominican Republic
Algeria
Ecuador
Egypt
Eritrea
Estonia
Ethiopia
Fiji
Micronesia, Fed. States of
Gabon
Georgia
Ghana
Guinea
Gambia, The
Guinea-Bissau
Equatorial Guinea
Grenada
Guatemala
Guyana
Honduras
Croatia
Haiti
Hungary
Indonesia
India
Iran, Islamic Republic of
Jamaica
Jordan
Kazakhstan
Kenya
Kyrgyz Republic
Cambodia
Kiribati
Saint Kitts and Nevis
Korea, Republic of
Lao People's Democratic Republic
Lebanon
Liberia
Libya
Saint Lucia
Sri Lanka
Lesotho
Lithuania
Latvia
Morocco
Moldova
Madagascar
Maldives
Mexico
Marshall Islands
Macedonia, former Yugoslav Republic of
Mali
Malta
Myanmar
Montenegro
Mongolia
Mozambique
Mauritania
Mauritius
Malawi
Malaysia
Namibia
Niger
Nigeria
Nicaragua
Niue
Nepal
Nauru
Oman
Pakistan
Panama
Peru
Philippines
Palau
Papua New Guinea
Poland
Korea, Dem. People's Rep. of
Paraguay
Romania
Russian Federation
Rwanda
Saudi Arabia
Sudan
Senegal
Solomon Islands
Sierra Leone
El Salvador
San Marino
Serbia
Sao Tome and Principe
Suriname
Slovak Republic
Slovenia
Swaziland
Seychelles
Syrian Arab Republic
Chad
Togo
Thailand
Tajikistan
Turkmenistan
Tonga
Trinidad and Tobago
Tunisia
Turkey
Tuvalu
Tanzania
Uganda
Ukraine
Uruguay
Uzbekistan
Saint Vincent and the Grenadines
Venezuela
Vietnam
Vanuatu
Samoa
Yemen, Republic of
South Africa
Zambia
Zimbabwe
Timor-Leste
Note on M54: - 261 Provincial level government staff (107 women and 164 men) trained on community engagement, sea level rise mapping exercise,and development of a land use planning module - 22 Community members and provincial government staff (7 women and 15 men) are actively participating as a Provincial Climate Change Coordination Committee member in Malaita - 2 Met Officers (both men) and 36 officers from line ministries (8 women and 28 men) trained on the use of climate data and early warning system - 14 Provincial level government officers (4 women and 10 men) have been trained and administered a V&A

## Units for Indicators
Fund Outcome Indicator Units
1. Generation of relevant data, Stakeholders, and Timeliness 2.1. Include both qualitative and quantitative measures of capacity level within targeted institutions 2.2. Number (men and women and other vulnerable groups) 3.1. Use scale from 1 to 5: 5: Fully aware 4: Mostly aware 3: Partially aware 2: Partially not aware 1: Aware of neither predicted adverse impacts of climate change nor of appropriate responses 3.2. Use scale from 1 to 5: 5: All 4: Almost all 3: Half 2: Some 1: None 4.1. Summarize in an overall scale (1-5): 5: Highly responsive (All defined elements ) 4: Mostly responsive (Most defined elements) 3: Moderately responsive (Some defined elements) 2: Partially responsive (Lacks most elements) 1: Non responsive (Lacks all elements ) 4.2. Summarize in an overall scale (1-5): 5: Fully improved 4: Mostly Improved 3: Moderately improved 2: Somewhat improved 1: Not improved 5. Depends on the targeted natural asset: Biological (species): measure through changes in population numbers (dynamics, structure, etc.) Land: measure changes in hectares. Baseline data will be necessary to estimate the change. Supporting indicators baseline and target (as well as contextual information) are needed such as the following: Farmers adopting recommended technologies, Ha. of land improved, Average deforestation rate Etc. Use scale from 1 to 5. 5: Very effective (All elements are present) 4: Effective (Most elements are present) 3: Moderately effective (Some elements are present) 2: Partially effective (Most elements are not present) 1: Ineffective (No elements are present) 6.1. Summarize in an overall scale (1-5): 5: Very high improvement 4: High improvement 3: Moderate improvement 2: Limited improvement 1: No improvement 6.2. Household income by source of livelihood in project area (USD) prior and post project intervention 7. Summarize in an overall scale (1-5). 5: All (Fully integrated) 4: Most 3: Some 2: Most not integrated 1: None
Fund Output Indicator Units
1.1. Number, sector(s) and level(s) of projects or interventions in separate fields of monitoring plan 1.2. Number 2.1.1. Number of staff (male/female) of targeted institutions: a. Obtain baseline information: total number of staff from targeted institutions b. Define target 2.1.2. Number of staff (male/female) of targeted institutions: a. Obtain baseline information: total number of staff from targeted institutions b. Define target: needs to be defined by project proponents 2.2.1. Quantitative: Percentage (includes women – and other vulnerable groups – and men). Qualitative: Adequacy: include direct analysis of major areas; adequacy/effectiveness of systems or analysis of perceptions of populations and institutions. 2.2.2. Number (broken down by gender and, if possible, by vulnerable groups defined in the area of intervention) of people 3.1. Number and type (in separate columns) at local level. 3.2. Number 4.1. Number and type 4. 2. Number and type (entered in separate columns) 5. Number of interventions by type of natural asset and intervention 6.1. Number and type (in separate columns of monitoring plan) 6.2. Income sources per household; description of income source and number of households. 7.1. Number/Sector 7.2. Number; Effectiveness (see previous indicator) through enforcement level.