## Overview
Project Performance Report (PPR)
| Period of Report (Dates) | 01 July 2011 - 01 July 2012
| Project Title: | Enhancing Resilience of Communities in Solomon Islands to the Adverse Effects of Climate Change on Agriculture and Food Security - Strogem Waka lo Community fo Kaikai (SWoCK)
| Project Summary: | The Solomon Islands National Adaptation Programme of Action (NAPA) identified agriculture and food security as one of the most vulnerable sectors requiring urgent attention. The project addresses the NAPA priority and will contribute to enhance resilience of the agriculture sector to maintain and improve food security in the country. In particular, the project will lead to the following key results (outcomes) 1) Promote and pilot community-adaptation activities enhancing food security and livelihood resilience in pilot communities in at least 3 selected regions; 2) Strengthen institutions and adjusted national and sub-national policies related to governing agriculture in the context of a range of climate change futures; and 3) Foster the generation and spread of relevant knowledge for assisting decision-making at the community and policy-formulation level.
| Database Number: | AFB/MIE/Food/2010/1
Implementing Entity (IE) [name]: |  | United Nations Development Programme
| Type of IE: | MIE
| Country(ies): | Solomon Islands
Relevant Geographic Points (i.e. cities, villages, bodies of water): |  | Weather Coast of Guadalcanal, South Makira, South Choiseul, North Malaita, Central Maringe in Isabel, Honiara City, Lau and Langa Langa lagoons in Malaita
Project Milestones
Milestone
AFB Approval Date: |  | March 18, 2011
IE-AFB Agreement Signature Date: |  | 2011-04-01
Start of Project/Programme: |  | July 1, 2011
Mid-term Review Date (if planned): |  | 2013-12-01
| Terminal Evaluation Date: | 2016-07-01
List documents/ reports/ brochures / articles that have been prepared about the project.
Inception Report Press Release on inception workshop Multi-year Work plan and Activity Schedule Mission Reports Quarterly Reports Notes from Project Board meetings
List the Website address (URL) of project.
http://www.undp-adaptation.org/project/af_solomonislands
Project contacts:
National Project Manager/Coordinator
| Name: | currently vacant
Email:
Date:
Government DA
| Name: | Chanel Iroi, Permanent Secretary (a.g.), Ministry of Environment, Climate Change, Disaster Management and Meteorology (MECDM)
| Email: | c.iroi@met.gov.sb
| Date: | 2012-03-01
Implementing Entity
| Name: | Yoko Ebisawa and Gabor Vereczi
| Email: | yoko.ebisawa@undp.org; gabor.vereczi@undp.org
| Date: | 2011-05-01
Executing Agency
| Name: | Chanel Iroi, Permanent Secretary (a.g.), Ministry of Environment, Climate Change, Disaster Management and Meteorology (MECDM)
| Email: | c.iroi@met.gov.sb
| Date: | 2012-03-01
Executing Agency
| Name: | Frank Wickham, Permanent Secretary, Ministry of Agriculture and Livestock (MAL)
| Email: | wickham.frank@gmail.com
| Date: | 2012-03-01
Executing Agency
Name:
Email:
Date:

## FinancialData
Financial information: cumulative from project start to June 2012
DISBURSEMENT OF AF GRANT FUNDS
How much of the total AF grant as noted in Project Document plus any project preparation grant has been spent to date?
Estimated cumulative total disbursement as of 30 June 2012 | 305728 |  | The estimated cumulative total disbursement as of 30 June 2012 was based on recent reconciliation of financial information.
Add any comments on AF Grant Funds. (word limit=200) | Although original amount requested to AF for the first year was USD715,915, actual expenditure was USD305,728. Major reasons of this gap of approx USD 400,000 were caused by the delay of procurement of equipments (approx USD 350,000 for procurement of land use related equipments, automatic weather stations, and GIS laboratory related equipments) which took time to discuss with the government counterparts on detailed specification and justification. The gap of approx USD20,000 was caused by delay of concluding the agreement with NGO, which required additional time to assess the capacity of NGO's financial management. Activities of policy review was not conducted within the first year due to the limited human resources available in the country to conduct such task which added approx USD25,000 to the gap. These procurements and activities will be implemented in the second year. Based on the first year disbursement result, the multi-year budget has been revised as follows; Second Year (Jul 2012-Jun 2013): USD1,372,000 Third Year (Jul 2013-Jun 2014): USD2,208,000 Forth Year (Jul 2014-Jun 2015): USD1,215,000
EXPENDITURE DATA
List item / activity / action and corresponding amount spent for the current reporting period | ITEM / ACTIVITY / ACTION | AMOUNT
| 1. Community based adaptation initiatives implemented in at least 30 communities across at least 3 regions in Solomon Islands | 126384
| 2. Institutional strengthening to support climate resilient policy frameworks for the agriculture sector | 40555
| 3. Climate change adaptation specific knowledge production, sharing and dissemination | 19481
| Project execution | 119308
| TOTAL | 305728
PLANNED DISBURSEMENT SCHEDULE
List item / activity / action planned and corresponding projected cost for the upcoming reporting period | ITEM / ACTIVITY / ACTION | PROJECTED COST | Est. Completion Date
| 1. Community based adaptation initiatives implemented in at least 30 communities across at least 3 regions in Solomon Islands | 785000 | 2013-06-01 | While this is the estimated disbursements for the next reporting period, we concern that the disbursement amount would be optimistic due to the capacity constraint of the government. UNDP is willing to provide additional support if requested.
| 2. Institutional strengthening to support climate resilient policy frameworks for the agriculture sector | 395000 | 2013-06-01
| 3. Climate change adaptation specific knowledge production, sharing and dissemination | 82000 | 2013-06-01
| Project execution | 110000 | 2013-06-01
| TOTAL | 1372000
ACTUAL CO-FINANCING
How much of the total co-financing as committed in the Project Document has actually been realized? | Co-financing is non-applicable to the project. However, during the first year the project has managed to leverage other initiatives and carried out collaborations and co-organized several events, including Premiers Environment Round Table with MECDM, (total approx. USD110,000), Climate Change Policy Consultation and Launch (with the other UNDP-supported projects (total approx USD45,000), Participatory 3D Modelling workshop with CTA, The Nature Conservancy, Partners with Melanesians and other UNDP-supported project (total approx USD100,000), and the project awareness activities in the targeted sites with the other UNDP-supported project (total approx USD35,000).
If the MTR or TE have not been undertaken this reporting period, DO NOT report on actual co-financing.
Estimated cumulative actual co-financing as verified during Mid-term Review (MTR) or Terminal Evaluation (TE).
Add any comments on actual co-financing in particular any issues related to the realization of in-kind, grant, credits, loans, equity, non-grant instruments and other types of co-financing. (word limit=200)

## Procurement
PROCUREMENT DATA
LIST OF CONTRACTS
List all contracts related to the project/program with signature dates
| Contract Type | Agency / Contracted party | Signature Date | Payment to Date | Remaining Balance
| Individual Contract (Consultancy) |  | June 17, 2011 | USD 3,240.49 | None
| Service Contract (Project Staff) |  | July 8, 2011 | USD 13,488.27 | None
| Service Contract (Project Staff) |  | July 8, 2011 | USD 7,881.58 | USD 4,158.43
| Service Contract (Project Staff) |  | January 23, 2012 | USD 3,652.49 | USD 4,664.38
| Service Contract (Project Staff) |  | May 1, 2012 | USD 1,460.45 | USD 6,856.42
BIDS
List all bids for each contact signed with date of open call and winning bid
CONTRACT | Submitted Bids |  | Winning Bid | Selection justification for the winner | Procurement Method
IT equipments (Laptop, projector, camera, video camera and hard disks) for PMU (Jul 12, 2011) |  |  | SBD 142,580 | The lowest-priced offer among the technically compliant/responsive offers was awarded. | Request for Quotation
Project Vehicle (Jul 20, 2011) |  |  | SBD 205,000 | The lowest-priced offer among the technically compliant/responsive offers was awarded. | Request for Quotation
Office Furniture for PMU (Oct 4, 2011) |  |  | SBD45,470 | The lowest-priced offer among the technically compliant/responsive offers was awarded. Applicant 2 and 3 were not responsive. | Request for Quotation
Printer for MAL GIS (Sep 17, 2011) |  |  |  | The lowest-priced offer among the technically compliant/responsive offers was awarded. | Request for Quotation
SBD 60,000
Computer for MAL GIS (Sep 17, 2011) |  |  | SBD 80,100 | The applicant No1 was awarded as the offered computer received less virus and the best solution to protect the GIS database from the virus in the future. Although it was not specified in the Request for Quotation, procurement of Macintosh computer was recommended by IT, which was the better solution to protect GIS data from the virus. Applicant No1 supplied Macintosh computer. | Request for Quotation

## Risk Assesment
RISK ASSESMENT
IDENTIFIED RISKS
List all Risks identified in project preparation phase and what steps are being taken to mitigate them (word limit = 200)
Identified Risk | Current Status | Steps Taken to Mitigate Risk
Delays in project inception impact on achieving project outputs and outcomes and reduce scope to deliver program as outlined in proposal | low | Inception phase has been carried out without delay, through scheduling the Inception Workshop and a set of follow up meeting with national project partners and provincial stakeholders.
Poor collaboration between project partners | low | Roles and responsibility of project partners discussed and clarify during initial inception workshop. Initial planning and provincial travelling in provincial target sites for baseline data collection and activities took place with the involvement of responsible implementing partners. Regular Project Board meetings and technical team meetings partners meetings and planning being coordinated and supported by SWoCK PMU to encourage partners’ collaboration in implementation. PMU is facilitating process to resource and staffing project partners for an effective coordination and collaboration between partners.
Weak cooperation by communities at proposed sites | low | Communities' understanding and appreciation of the project was obtained during the initial baseline data and project awareness by project partners. Key people were identified and established as focal persons to link between the project and communities.
Land disputes amongst community members affect land use planning exercise | low | The initial baseline data and survey conducted by the project in target communities identified existing community mechanisms (modern or traditional) that can be used to manage land dispute. The existing mechanisms will be part of the land use planning exercise.
Limited human resources in SIG agencies to contribute to the activities | medium | Participation of SIG officers were secured during the project inception phase. The project board discussed this issue and revised the project organization structure by adding additional human resources supported by the project.
A series of unusually adverse climatic conditions does not damage adaptation measures being implemented, or weaken the interest of key stakeholders to addressing adaptation issues | low | To anticipate this risks, project activities will be scheduled to avoid and/or respond to such occurrences. SIMS weather information and production will be used to inform partners and communities to make decision on project activities implementation plans and schedule.
The techniques and technologies developed are not gender sensitive - i. e. they increase inequity between men and women or change the social roles of men and women in a way that reduces self reliance | low | The project had identified several entry points of women's networks to work with at the community levels. Gender considerations will be addressed during the upcoming V&A assessments. Gender balanced / sensitive tools will be developed and used by implementing partners to plan and monitor project activities in communities.
The selection of pilot sites do not follow the established criteria and are derailed due to political processes and influences | low | The selection of pilot sites is ongoing based on the initial consultations and engagements carried out in the target provinces. The pilot sites will be confirmed in accordance to the criteria specified in the project proposal and will be agreed by the Project Board.
The government is not supportive, politically and financially, to a cross-sectoral and integrated approach to the management of climate risks and opportunities | low | Participation of SIG officers were secured during the project inception phase and throughout the implementation. Regular Project Board meetings are held with key project partners involved. The project team composed by national partners is being formalized through a Technical Working Group.
Critical Risks Affecting Progress (Not identified at project design)
Identify Risks with a 50% or > likelihood of affecting progress of project
Identified Risk | Current Status | Steps Taken to Mitigate Risk
Limited market of human resources available to project requirements which has resulted in the delay of staff recruitment in almost all posts, affecting project implementation. Despite the various rounds of announcements and recruitment processes initiated, only a few of the envisaged project support staff could be recruited. | medium | Through a joint monitoring exercise carried out by PMU, national partners, UNDP CO and RTA, in May 2012 the entire project support organigrame has been readjusted with support staff and expert ToRs modified or newly developed and post levels reclassified in order to attract more qualified candidates. In addition to the advertisement in local newspapers, the network of the ministries and various project partners has been also engaged to identify suitable candidates. Collaboration has been initiated with the regional agencies such as SPC to source further technical support. Various recruitments are currently under way, including a new Project Manager.
NGO's capacity of financial management is weak, prompting the need to find alternative operational arrangements, and causing delays in the formalization of engagements (MoUs) as responsible parties | medium | Instead of transferring the cash, the Project Board decided that direct payment would be made by UNDP in order to minimize the risk, in addition to initiate the development of NGO capacities to address this operational matter.
Risk Measures: Were there any risk mitigation measures employed during the current reporting period? If so, were risks reduced? If not, why were these risks not reduced?
Add any comments relevant to risk mitigation (word limit = 500)
Most critical risk was the limited human resources available to recruit needed staff for the project. Risk mitigation mentioned above was employed and some posts were filled while others are being filled. However some technical positions were still difficult to fill based on available expertise nationally, thus collaboration has been initiated with regional agencies (SPC).

## Rating
RATING ON IMPLEMENTATION PROGRESS
For rating definitions please see bottom of page.
| Progress on Key Milestones |  | Expected Progress |  | Progress to Date | Rating
Project Manager/Coordinator: | National Climate Change Policy is completed and high level awareness raising activity is delivered |  | National Climate Change Policy is completed and high level awareness raising activity is delivered |  | NCCP Launched in June and policy implementation in progress | S
| Guideline for land use planning integrating climate change completed by 30/12/2012 |  | Guideline for land use planning integrating climate change completed by 30/12/2012 |  | There has been some delay in moving forward with this particular activity | MU
| V&A training completed for all sites (31/12/2012) |  | V&A training completed for all sites (31/12/2012) |  | There has been some delay in moving forward with this particular activity | MU
| Soil suitability and crop selection manual completed (30/12/2012) |  | Soil suitability and crop selection manual completed (30/12/2012) |  | There has been some delay in moving forward with this particular activity | MU
| Gender guideline completed (30/6/2012) |  | Gender guideline completed (30/6/2012) |  | No guideline developed by the date specified. Progress has been slow | U
| All AWS and manual voluntary weather stations established |  | All AWS and manual voluntary weather stations established |  | Contract to start installing only finalised in August 2012 | MS
| GIS laboratory completed and 1st training course offered |  | GIS laboratory completed and 1st training course offered |  | Progress in erecting a new building for the GIS lab has been slow | MS
| Project communication strategy completed (30/6/2012) |  | Project communication strategy completed (30/6/2012) |  | No progress made and as a result no strategy developed by the end of given period | U
| PMU fully staffed and operational (30/12/2011) |  | PMU fully staffed and operational (30/12/2011) |  | Rest of the vacant posts filled only in 2012 | MU
[5 empty] | Overall Rating | MU
Please Provide the Name and Contact information of person(s) reponsible for completeling the Rating section
| Name: | Joe Horokou (a.g. PS) and Douglas Yee (Director of Climate Change), Ministry of Environment, Climate Change, Disaster Management and Meteorology (MECDM)
| Email: | horokoujoe@gmail.com, d.yee@met.gov.sb
Please justify your rating. Outline the positive and negative progress made by the project since it started. Provide specific recommendations for next steps. . (word limit=500)
Overall, the progress is not on track to achieve many of the outcomes during the reporting year. The achieved outcomes were launching of the National Climate Change Policy, and there are some progress regarding the establishment AWS and rainfall stations and establishment of GIS laboratory. However, outcomes regarding land use planning, V&A training, Soil suitability and crop selection manual, gender guideline, project communication strategy and PMU staffing were either delayed or no progress made during the reporting period, mainly due to the lack of human resources in the market as well as in the ministries. The ministry recommends to prioritize to secure the human resources so as any of the delayed activities are able to fully implement as well as enhance the partnership with the other development partners.
| Progress on Key Milestones |  | Expected Progress |  | Progress to Date | Rating
Implementing Agency | National Climate Change Policy is completed and high level awareness raising activity is delivered |  | National Climate Change Policy is completed and high level awareness raising activity is delivered |  | A National Climate Change Policy was endorsed in March 2012 and launched in June 2012, supported by the SWoCk initiative. The project co-hosted in Sep 2011 the Premiers Environment Round Table to address climate change issues and engage high level officials at the provincial level. This was the first opportunity to gather all provincial leaders to discuss environment and climate change issues. | HS
| Guideline for land use planning integrating climate change completed by 30/12/2012 |  | Guideline for land use planning integrating climate change completed by 30/12/2012 |  | The draft guideline was not developed yet due to the capacity constraint of the country to undertake this task although UNDP is supporting the government by facilitating the recruitment with various rounds of call. Further support is being sought from SPC and the Fiji Government (Land Resources Department) as South-South collaboration for this component. The SWoCK project team (PMU, UNDP MCO) played a crucial part in facilitating the organization of an international workshop on the 3D Participatory Modelling in May in Honiara. One of the targeted communities in SWoCK had a demonstration role in the workshop through building an example model. This technique will be used as a tool for community engagement in land-use processes and the implementation of alternative farming practices integrating climate risks and resilience. | MU
| V&A training completed for all sites (31/12/2012) |  | V&A training completed for all sites (31/12/2012) |  | V&A tools was not finalized yet due to the capacity constraint of the country to undertake this task although UNDP is supporting the government by facilitating the recruitment with various rounds of call. However, the Ministry of Agriculture took a lead to draft V&A tool during the reporting year, which was further discussed and elaborated at a technical team meeting supported by UNDP CO and RTA in May. The project is planning to conduct V&A training and exercises in all provinces within the year. The initial baseline surveys conducted at targeted communities will also feed to the V&A process. | MS
| Soil suitability and crop selection manual completed (30/12/2012) |  | Soil suitability and crop selection manual completed (30/12/2012) |  | This activity was planned to be implemented through the NGO project partner. However, the response from the NGO has delayed due to the limitation of implementation capacity within the NGO, which is being addressed currently (training, hiring of additional project tech staff) | U
| Gender guideline completed (30/6/2012) |  | Gender guideline completed (30/6/2012) |  | The draft guideline was not developed yet due to the capacity constraint of the country to undertake this task although UNDP is supporting the government by facilitating the recruitment with various rounds of call. Gender aspects are being integrated into the V&A method and process to be rolled out during the year. | MU
| All AWS and manual voluntary weather stations established |  | All AWS and manual voluntary weather stations established |  | Series of field surveys were conducted to identify the potential locations for installing AWSs and rain fall stations. The contract document is under preparation in order to procure relevant equipments. | MS
| GIS laboratory completed and 1st training course offered |  | GIS laboratory completed and 1st training course offered |  | There is a constraint for the space available to establish GIS laboratory. However, the temporary spaces was allocated within the School of Natural Resources, Solomon Islands College of Higher Education (SICHE). The procurement of necessary equipments are being finalized. | MS
| Project communication strategy completed (30/6/2012) |  | Project communication strategy completed (30/6/2012) |  | The draft strategy was not developed yet due to the capacity constraint of the country to undertake this task although UNDP is supporting the government by facilitating the recruitment with various rounds of calls. Support is being sought from the UNDP Pacific Centre and Fiji MCO joint Communication unit, while the communication officer is being recruited. A number of communication means and products have been established, including a project website was established, logo along with a local language project title and acronym, T-shirts and brochures. | MU
| PMU fully staffed and operational (30/12/2011) |  | PMU fully staffed and operational (30/12/2011) |  | Most of the PMU posts was filled within the reporting period. However, the contract of the Project Manager was not extended due to the poor performance, and recruitment process is under way for a new one. | MU
[5 empty] | Overall Rating | MS
Please Provide the Name and Contact information of person(s) responsible for completeling the Rating section
| Name: | Yoko Ebisawa and Gabor Vereczi
| Email: | yoko.ebisawa@undp.org; gabor.vereczi@undp.org
| Progress on Key Milestones |  | Expected Progress |  | Progress to Date | Rating
Other
Overall Rating
Please Provide the Name and Contact information of person(s) reponsible for completeling the Rating section
Name:
Email:
| Please justify your rating and address the following points: 1. Indicate trends, both positive and negative, in achievement of outcomes as per the project indicators. 2. Detail critical risks that have affected progress. 3. Outline response to MTR undertaken this reporting period. 4. Outline action plan to address projects with a rating of HU, U or MU. Please keep your input to 1200 words |  | In its first years of implementation the project has been successful in strengthening inter-agency coordination mechanisms (through PB, technical team, coordination with NGOs), engage provincial stakeholders in target areas (Premiers' Roundtable, initial consultations and surveys in target communities), and initiate technical processes (e.g. methodology and training development for V&A, planning for equipment and training activities for climate early warning system engaging regional expertise - NIWA). The following are the main factors have been affecting implementation, with remedial actions facilitated by UNDP: Capacity constraint of the country to undertake the various project positions to support the government – the lack of qualified staff and associated technical capacity at government counterparts is the most significant factor. In spite of 2 rounds of calls for various posts, only a finance, a procurement officer and one (out 6) Provincial Coordinators could be recruited given the lack of sufficient and qualified candidates available in the labour market locally. UNDP and PMU revised the entire project management and technical support setup, including revising and crafting 8 ToRs for technical support staff. These have been presented and discussed by the Project Board. A new organigram and action table has been crafted with PMU for the revised setup, main aspects: - More balanced staffing setup considering support needs of MECDM and MAL at both national and provincial levels (new MAL PS has been very engaged and helpful) - Technical tasks are more streamlined, complementary and aligned with project outcomes and outputs - Post level and contract forms readjusted (higher grade, or switching from service contract to individual contract mode) in an attempt to attract more qualified candidates - Next round of calls to be pursued in a more targeted way, engaging networks of partner government and NGO institutions, as well as provincial governments for the Provincial Project Coordinator posts (previous rounds of calls used mainly ads in Solomon Star newspaper) - Outlining options for bringing in regional/international expertise (e.g. SPC Land Resources Division collaboration, Fiji Gov Land use Department as South-South collaboration, engaging a high quality regional food security and CC specialist as visiting expert with STA type mentoring functions) Procurement delays, esp. the big ticket item MET equipment, due to a combination of tech aspects being fixed with provider, and the need for gov to get more familiar with UNDP operational procedures to better feed info to the process). NPMU and UNDP has been providing ongoing guidance, meetings has been hold with SIMS Director to finetune pending details on the bid document, NIWA is being engaged through direct contract. Delay with finalizing NGO MoUs due to their lack of fiduciary capacities and the need for UNDP and PMU to find alternative modalities (ongoing discussions with NGASI and Kastom garden Association) Partner coordination amongst national partner: in spite of ongoing and significant efforts of PMU to supported by UNDP, it has been difficult to bring together partners for various project processes. Remedial actions: - Following a suggestion of the Director of MECDM CC Division, partners group is being formalized as Technical Advisory Committee, through crafting a ToR and get PB approve and request partner agencies to formally nominate members. - Further harmonize field visit scheduling and conduct between the various partners in order to avoid duplication and community consultation fatigue. - Further pursue the setting up of Provincial CC Steering Committees – to ToR and determine process to establish them
Rating Definitions
|  |  |  | Highly Satisfactory (HS) | Project actions/activities planned for current reporting period are progressing on track or exceeding expectations to acheive all major objectives/outcomes for given reporting period, without major shortcomings. The project can be presented as “good practice”.
|  |  |  | Satisfactory (S) | Project actions/activities planned for current reporting period are progressing on track to achieve most of its major objectives/outcomes with only minor shortcomings.
|  |  |  | Marginally Satisfactory (MS) | Project actions/activities planned for current reporting period are progressing on track to achieve most major relevant objectives/outcomes, but with either significant shortcomings or modest overall relevance.
|  |  |  | Marginally Unsatisfactory (MU) | Project actions/activities planned for current reporting period are not progressing on track to achieve major objectives/outcomes with major shortcomings or is expected to achieve only some of its major objectives/outcomes.
|  |  |  | Unsatisfactory (U) | Project actions/activities planned for current reporting period are not progressing on track to achieve most of its major objectives/outcomes.
|  |  |  | Highly Unsatisfactory (U) | Project actions/activities planned for current reporting period are not on track and shows that it is failing to achieve, and is not expected to achieve, any of its objectives/outcomes.

## Project Indicators
PROJECT Indicators
Please provide all indicators being tracked for the project as outlined in the project document
Type of Indicator (indicators towards Objectives, Outcomes, etc…)
Type of Indicator | Indicator | Baseline | Progress since inception | Target for Project End
Objective | No. of enabling policy instruments and coordination mechanisms in the agriculture and food security sector reviewed to integrate climate change hazards and risks. | National policy instruments, coordination mechanisms and institutions in the agriculture and food security sector do not address climate related risks and hazards. | One policy was endorsed and one coordination mechanisms was established. A National Climate Change Policy was endorsed in March 2012 and launched in June 2012, supported by the SWoCK initiative. The policy addresses agriculture and food security issue as one of the priority sectors and stipulates the necessity of effective institutional arrangement to plan, implement and coordinate and integrated and multi-stakeholder participatory approach to addressing climate change. The project also supported to establish coordination mechanisms in provincial level by co-hosting in Premiers Environment Round Table in Sep 2011 to address climate change issues and engage high level officials at the provincial level. This was the first opportunity to gather all provincial leaders to discuss environment and climate change issues. Currently Provincial level project coordination mechanisms (steering committees) are being explored and established. | At least four national and provincial level policy instruments, and coordination mechanisms (MAL, CCD, SIMS, SNR) addressing the agriculture sector and food security have integrated climate change risks and hazards.
| No. of farming systems to be introduced, communities and households in coastal areas and highlands in Solomon Islands able to maintain or increase food production and food security and cope with climate variability and change. | Communities and agriculture food production systems in coastal areas and highlands of Solomon Islands are exposed to future climate related risks and hazards, have weak coping capacity and have not started building resilience. | Farming systems was not introduced yet. Initial site visits and baseline surveys has been conducted in various target areas to identify the type of integrated farming systems to be promoted. The national NGO NGASI (Nut Growers Association) has been engaged to promote crop diversification through growing nuts and fruits. | By the end of the project at least 18 wards in 3 climatic and geographic cluster areas (windward side, leeward side and artificial) have integrated climate change risks into their land use plans and farming systems.
Outcome 1 | No. of wards where climate risks are integrated into land use and agriculture production aspects | No of integrated land use planning undertaken and climate change consideration are yet to be factored into land use plans across the different geographic regions in Solomon Islands especially those that are more vulnerable to climate risks | No integrated land use planning was undertaken yet. However, a range of initial consultations, baseline data gathering and engagement meetings has been held in target provinces and communities that has served for awareness raising on the need to integrate climate risk aspects in land use planning. A V & A tool has been prepared and will be rolled out in 2012 in target communities for climate risk assessment, in order to support land use processes in a climate resilient way. Participatory 3D Modelling was introduced during the workshop in May 2012 as a method of community based land use planning. | By the end of the year 1 detailed land use and climate risk assessments are carried out, and by the end of the project climate-resilient land use planning and agriculture production considerations are integrated into ward development plans in at least 18 wards in 3 climatic and geographic cluster areas.
| No. of wards developing climate-resilient farming and aqua-culture production techniques and systems | Small holder farming systems are not able to cope with declining soil fertility and limited agriculture, processing and food security adaption options and strategies available in the country. | Climate-resilient farming and aqua-culture production techniques and systems was not developed yet in ward level. However, the project conducted a look-and-learn visit to observe and obtain lessons learnt from the existing aqua-culture production techniques and systems in Western province. | By the end of the project at least 18 pilot wards develop climate resilient farming and aqua-culture production techniques and systems. At least four demonstrations planned and established on efficient use of water in agriculture and aquaculture production systems. A national, provincial and local agro-biodiversity and food bank strategy established and implemented in at least one site per target climatic and geographic cluster area. At least four small scale pilot root crop processing facilities established and operated by women At least 20 families on man-made artificial islands provided with water storage tanks, roofing iron and low-cost bucket drip irrigation systems to support small scale vegetable production.
| No. of national provincial and field staff across government, NGO, village constituencies trained to utilize climate information to guide decision making in agricultural production, and climate resilient farming and aquaculture techniques | Officials, technical experts and field staff of government, NGOs, private sector and training institutions have limited capacity and not been trained to plan, design and facilitate V&A assessments in the agriculture food production sector. | No training conducted yet. A training plan is being established through a planned initial sector-focus workshop | By the end of the 2nd year, at least 200 personnel from government and NGOs (50 provincial gov., 70 MAL extension/research/land use officers, 30 SIMS field staff, 20 KGA staff and 140 contact farmers, NGASI 50 contact farmers), YEP volunteers, and village constituencies (church leaders, women, groups, farmers, CBOs) are trained in the use of climate information.
Outcome 2 | No. of national and provincial level policies, strategies, plans and coordinating mechanisms reviewed and incorporate climate change risks | Very few national policies taking climate risks into consideration, no policy instruments in place to guide and support communities and households address climate variability and change and coordinating mechanisms not addressing climate change considerations. | One policy was endorsed. A National Climate Change Policy was endorsed in March 2012 and launched in June 2012, supported by the SWoCK initiative. The policy addresses agriculture and food security issue as one of the priority sectors and stipulates the necessity of effective institutional arrangement to plan, implement and coordinate and integrated and multi-stakeholder participatory approach to addressing climate change. | By the end of project climate change considerations are incorporated into the national long term development plan, at least three policy and legislative frameworks (new Food Security Policy, Land Use Policy, and Agriculture Act), development planning processes and development plans of at least 4 provincial governments.
| No. of weather stations established in the country, meeting WMO standards and contributing data to national weather service and early warning system | Only five manual weather stations in operation in the country with none located in the windward side of the main islands and in areas more prone to cyclones | Weather stations was not established yet. However, location of 4 AWS and 12 automatic rain stations were identified and initial contact to the community were made. The contract document for procurement of the equipments is underway. | At least 3 AWS and at least 12 voluntary weather stations established at strategic locations, meet WMO standards and contributing to nationwide monitoring and early warning system.
| Agriculture-tailored climate early warning and information products established and communicated to users. | Historic and new weather data not analysed nor information generated and tailored for distribution to the agriculture sector and other related sectors. | Agriculture-tailored climate early warning and information products was not established yet. A partnership support arrangement is being developed to support SIMS and national partners to this end, based on ongoing engagement in various countries through UNDP-supported projects. Currently contractual arrangements are being set up. | By year 2 agriculture tailored CLEWS and info products are established, and by the end of the project this information is being used by at least 200 personnel from government and NGOs (50 provincial gov, 70 MAL extensions/research/land use officers, 30 SIMS field staff, 20 KGA staff and 140 contact farmers, NGASI 50 contact farmers) and village constituencies (church leaders, women's group, farmers, CBOs).
| No. of officers within MAL, MECDM, NGOs and SNR trained in methods to support communities integrate climate considerations into agriculture production and land-use planning. GIS-based agriculture information system integrating climate info, and related institutional capacities for climate risk management in agriculture. | Climate change division of MECDM has only three staff who already have heavy workloads and not able to support V&A and climate change mainstreaming into agriculture and other sectors. | 20 officers from MAL, MECDM, NGOs and SNR were trained on participatory 3D modelling method as a tool to support communities to integrate climate considerations into land-use planning. SNR is implementing to construct the GIS laboratory to provide training facilities. On the job training at SPC-SOPAC is under discussion to provide intensive training to MAL GIS officer. | At least 200 officers at the policy and field officer level within MAL, MECDM, NGOs and SNR trained in methods to support communities with integration of climate change risks into land use planning and agriculture production By the end of year 2, a GIS laboratory is established, a GIS based agriculture and climate information system is established, and by the year 3, 16 MAL MECDM and SNR staff trained on its management and application, and by the end of the project at least 12 training courses developed and implemented on climate-sensitive land-use planning for policy makers, field staff and community representatives
Outcome3 | No. of knowledge products developed and disseminated | Absence of a communication strategy and lack of information management system to support adaptation of the agriculture sector and food security to climate change risks. | Knowledge product was not yet developed. Project website was established. A project logo along with a project title, acronym and slogan in local language has been created, T-shorts and brochures have been produced to facilitate communication and awareness raising activities targeted to national audience and communities. | In each project year at least 5 knowledge products (case study, experience note, photo story, video, technical reports, etc.) developed and disseminated to local, national and regional stakeholders.
| No. of exchange programs and activities designed to share lessons learnt and raise awareness on climate change impacts on agriculture and food production | There is no existing nationwide program and there is a lack of expertise to integrate climate and agriculture information for dissemination to public. | One activity was conducted. The international workshop on the participatory 3D modelling was organized in which SWoCK partners from MECDM, MAL, SNR and NGOs participated. The event was an important opportunity to exchange experiences in participatory planning techniques and community empowerment for climate change adaptation amongst a range of countries in the Pacific, the Caribbean and international organizations. | Exchange site visits organized between participating pilot communities and a national forum held by year 2 and by the end of the year. Bu the end of the project, Solomon Islands is able to share its experiences on adaptation to climate change in the agriculture and food security sector with other countries within the country, the Pacific and globally by exchange of site visits, organizing a forum and disseminating information through the social media.
| No. of documented case studies and lessons learnt used in the teaching of short courses as well as certificate and diploma courses in agriculture, forestry and environmental studies in the School of Natural Resources (SNR). | SNR do not have local case studies on climate change adaptation and agriculture for use in the range of courses on offer. | No case studies and lessons learnt was included in courses provided by SNR. However, 39 students from environment certificate course participated in conducting awareness activity of the project in six pilot sites in Dec. 2011. | At least four case studies generated by the project are incorporated and used in SNR training courses to promote and raise knowledge and understanding of young Solomon Islanders on climate change adaptation in the agriculture sector.

## Lessons Learned
QUALITATIVE MEASURES and LESSONS LEARNED
Please Complete the following section every reporting period
Implementation and Adaptive Management | Response
Describe any implementation issues/lessons affecting progress (positive and negative) | Implementation is slow mainly due to the capacity constraint of the country to undertake most of the project tasks. Limited market of human resources available to project requirements has resulted in the delay of staff recruitment in almost all posts. Limited human resources in SIG agencies and limited capacity of financial management also affected the slow implementation of the activities. Despite the slow implementation, there is a strong ownership from the government to implement the project. The project maintains good relationship with the key counterparts including Permanent Secretaries from both MECDM and MAL, with frequent discussions to tackle the obstacles mentioned above. Various climate change adaptation initiatives have been started by the other development partners and CO has participated in a joint donor mission to one of the targeted site in Choiseul province, with GIZ/SPC, USAID, and SPREP. Information of each project was shared among these development partners and future collaboration was discussed to synergize the project results.
Were there any delays in implementation? If so, include any causes of delays. What are the measures taken to reduce delays? | There was delay in implementation mainly due to the capacity constraint of the country to undertake most of the project tasks. Limited market of human resources available to project requirements has resulted in the delay of staff recruitment in almost all posts. Limited human resources in SIG agencies and limited capacity of financial management also affected the slow implementation of the activities. The entire project support organigram has been readjusted with support staff and expert ToRs modified or newly developed and post levels reclassified in order to attract more qualified candidates. In addition to the advertisement in local newspapers, the network of the ministries and various project partners has been also engaged to identify suitable candidates in addition to cooperation with CROP agencies and other development partners. There were also delays in implementation for activities which was assigned to national NGOs due to the limited capacity of financial management. The project required additional time to assess the capacity of NGO's financial management to conclude the agreement. In order to minimize the risk, the project agreed not to transfer the fund to the NGO but make a direct payment which is required to implement relevant activities.
Describe any changes undertaken to improve results on the ground or any changes made to project outputs (i.e. changes to project design) | There are some modification in the Results Framework although these changes do not affect fundamentally the original project results. Indicators and targets of Outcome 1 have been refined and wording of "community" was replaced by "ward". For clarity, the wording of "3 targeted regions" which address windward, leeward sides and artificial islands was replaced by "3 climatic and geographic cluster areas". Wording of indicators and target of Outcome 2 and 3 were also refined and quantified.
How have gender considerations been taken into consideration during the reporting period? What have been the lessons learned as a consequence of inclusion of such considerations on project performance or impacts? | The project had identified several entry points of women's networks to work with at the community levels. It is important to keep reminding the project staff and counterparts. Gender considerations will be addressed during the upcoming V&A assessments. Gender balanced / sensitive tools will be developed and used by implementing partners to plan and monitor project activities in communities.
Please Complete the following section at mid-term and project completion
Lessons for Adaptation | Response
Climate Resilent Measures
Please Describe the Climate Resilent measures being undertaken by the project/programme.
Which of these masures has been most effective and why?
Which have been least effective and why?
Concrete Adaptaiton Interventions
Please desribe the concrete adaptation measures being undertaken by the project/programme
What are/were the most difficult aspects of implementing such measures?
What are/were the most successful aspects of the implementation of the interventions?
Community/National Impact
What would you consider to be the most successful aspects for the target communities?
What measures are/have been put in place to ensure sustainability of the project/program results?
What measures are being/could have been put in place to improve project/program results?
Knowledge Management
Describe what kind and how existing information/data/knowledge has been used to inform the development and the implementation of the project.
If Learning Objectives have been established, have they been met? Please describe.
Describe any difficulties there have been in accessing or retrieving existing information (data or knowledge) that is relevant to the project. Please provide suggestions for improving access to the relevant data.
Has the identification of learning objectives contributed to the outcomes of the project? In what why have they contributed?
What have been the major lessons learned that would add to the knowledge base for dissemination within and beyond the project area?

## AF Tracking Tool
Tracking Tool for Adaptation Fund (AF) Projects
Goal: Assist developing-country Parties to the Kyoto Protocol that are particularly vulnerable to the adverse effects of climate change in meeting the costs of concrete adaptation projects and programmes in order to implement climate-resilient measures. Impact: Increased resiliency at the community, national, and regional levels to climate variability and change.
Important: Please read the following Results Framework and Baseline Guidance (also posted on the Adaptation Fund website) before entering your data
Link: http://www.adaptation-fund.org/sites/default/files/Results%20Framework%20and%20Baseline%20Guidance%20final.pdf
Please select the relevant Fund level Outcome and Output indicators that allign with the project objectives and outcomes
OBJECTIVE 1
Fund Outcome | Please select from dropdown menu below | Fund Outcome Indicator | Please select from dropdown menu below | Target at CEO Endorsement (see Units in next sheet) | Baseline (see Units in next sheet) | Mid-term Results | Terminal Results
Outcome 1: Reduced exposure at national level to climate-related hazards and threats Outcome 2: Strengthened institutional capacity to reduce risks associated with climate-induced socioeconomic and environmental losses Outcome 3: Strengthened awareness and ownership of adaptation and climate risk reduction processes at local level Outcome 4: Increased adaptive capacity within relevant development and natural resource sectors Outcome 5: Increased ecosystem resilience in response to climate change and variability-induced stress Outcome 6: Diversified and strengthened livelihoods and sources of income for vulnerable people in targeted areas Outcome 7: Improved policies and regulations that promote and enforce resilience measures | 6 | 1. Relevant threat and hazard information generated and disseminated to stakeholders on a timely basis 2.1. No. and type of targeted institutions with increased capacity to minimize exposure to climate variability risks 2.2. Number of people with reduced risk to extreme weather events 3.1. Percentage of targeted population aware of predicted adverse impacts of climate change, and of appropriate responses 3.2. Modification in behavior of targeted population 4.1. Development sectors' services responsive to evolving needs from changing and variable climate 4.2. Physical infrastructure improved to withstand climate change and variability-induced stress 5. Ecosystem services and natural assets maintained or improved under climate change and variability-induced stress 6.1. Percentage of households and communities having more secure (increased) access to livelihood assets 6.2. Percentage of targeted population with sustained climate-resilient livelihoods 7. Climate change priorities are integrated into national development strategy | 1 | By the end of the project climate early warning and agromet information is being regularly disseminated to at least 200 personnel from government and NGOs | Tailored climate information is not available and not being regularly disseminated to agricultural users in the public and civil sectors.
Fund Output | Please select from dropdown menu below | Fund Output Indicator | Please select from dropdown menu below | Target at CEO Endorsement (see Units in next sheet) | Baseline (see Units in next sheet) | Mid-term Results | Terminal Results
Output 1: Risk and vulnerability assessments conducted and updated at a national level Output 2.1: Strengthened capacity of national and regional centres and networks to respond rapidly to extreme weather events Output 2.2: Targeted population groups covered by adequate risk reduction systems Output 3: Targeted population groups participating in adaptation and risk reduction awareness activities Output 4: Vulnerable physical, natural, and social assets strengthened in response to climate change impacts, including variability Output 5: Vulnerable physical, natural, and social assets strengthened in response to climate change impacts, including variability Output 6: Targeted individual and community livelihood strategies strengthened in relation to climate change impacts, including variability Output 7: Improved integration of climate-resilience strategies into country development plans | 6 | 1.1. No. and type of projects that conduct and update risk and vulnerability assessments 1.2. Development of early warning systems 2.1.1. No. of staff trained to respond to, and mitigate impacts of, climate-related events 2.1.2. Capacity of staff to respond to, and mitigate impacts of, climate-related events from targeted institutions increased 2.2.1. Percentage of population covered by adequate risk-reduction systems 2.2.2. No. of people affected by climate variability 3.1 No. and type of risk reduction actions or strategies introduced at local level 3.2 No. of news outlets in the local press and media that have covered the topic 4.1. No. and type of health or social infrastructure developed or modified to respond to new conditions resulting from climate variability and change (by type) 4. 2. No. of physical assets strengthened or constructed to withstand conditions resulting from climate variability and change (by asset types) 5. No. and type of natural resource assets created, maintained or improved to withstand conditions resulting from climate variability and change (by type of assets) 6.1. No. and type of adaptation assets (physical as well as knowledge) created in support of individualor community-livelihood strategies 6.2. Type of income sources for households generated under climate change scenario 7.1. No., type, and sector of policies introduced or adjusted to address climate change risks 7.2. No. or targeted development strategies with incorporated climate change priorities enforced | 1.2 | At least 3 AWS and at least 12 voluntary weather stations established at strategic locations, meet WMO standards and contributing to nationwide monitoring and early warning system. At least 3 agriculture tailored climate early warning and information products are established | Only five manual weather stations in operation in the country with none located in the windward side of the main islands and in areas more prone to cyclones. Currently only rainfall seasonal outlooks are produced by SIMS but not being tailored to agricultural users.
OBJECTIVE 2
Fund Outcome | Please select from dropdown menu below | Fund Outcome Indicator | Please select from dropdown menu below | Target at CEO Endorsement | Baseline | Mid-term Results | Terminal Results
Outcome 1: Reduced exposure at national level to climate-related hazards and threats Outcome 2: Strengthened institutional capacity to reduce risks associated with climate-induced socioeconomic and environmental losses Outcome 3: Strengthened awareness and ownership of adaptation and climate risk reduction processes at local level Outcome 4: Increased adaptive capacity within relevant development and natural resource sectors Outcome 5: Increased ecosystem resilience in response to climate change and variability-induced stress Outcome 6: Diversified and strengthened livelihoods and sources of income for vulnerable people in targeted areas Outcome 7: Improved policies and regulations that promote and enforce resilience measures | 2 | 1. Relevant threat and hazard information generated and disseminated to stakeholders on a timely basis 2.1. No. and type of targeted institutions with increased capacity to minimize exposure to climate variability risks 2.2. Number of people with reduced risk to extreme weather events 3.1. Percentage of targeted population aware of predicted adverse impacts of climate change, and of appropriate responses 3.2. Modification in behavior of targeted population 4.1. Development sectors' services responsive to evolving needs from changing and variable climate 4.2. Physical infrastructure improved to withstand climate change and variability-induced stress 5. Ecosystem services and natural assets maintained or improved under climate change and variability-induced stress 6.1. Percentage of households and communities having more secure (increased) access to livelihood assets 6.2. Percentage of targeted population with sustained climate-resilient livelihoods 7. Climate change priorities are integrated into national development strategy | 2.1 | At least 5 institutions (provincial government , MAL, MECDM, NGOs and CBOs) develop capacity in the use of climate information for the agriculture sector and climate-resilient farming and aquaculture techniques and | Public and civil sociaety instituions have limited capacity and not been trained to plan, design and facilitate for the implementaiton of climate change adaptation measures agriculture food production sector.
Fund Output | Please select from dropdown menu below | Fund Output Indicator | Please select from dropdown menu below | Target at CEO Endorsement | Baseline | Mid-term Results | Terminal Results
Output 1: Risk and vulnerability assessments conducted and updated at a national level Output 2.1: Strengthened capacity of national and regional centres and networks to respond rapidly to extreme weather events Output 2.2: Targeted population groups covered by adequate risk reduction systems Output 3: Targeted population groups participating in adaptation and risk reduction awareness activities Output 4: Vulnerable physical, natural, and social assets strengthened in response to climate change impacts, including variability Output 5: Vulnerable physical, natural, and social assets strengthened in response to climate change impacts, including variability Output 6: Targeted individual and community livelihood strategies strengthened in relation to climate change impacts, including variability Output 7: Improved integration of climate-resilience strategies into country development plans | 2.1 | 1.1. No. and type of projects that conduct and update risk and vulnerability assessments 1.2. Development of early warning systems 2.1.1. No. of staff trained to respond to, and mitigate impacts of, climate-related events 2.1.2. Capacity of staff to respond to, and mitigate impacts of, climate-related events from targeted institutions increased 2.2.1. Percentage of population covered by adequate risk-reduction systems 2.2.2. No. of people affected by climate variability 3.1 No. and type of risk reduction actions or strategies introduced at local level 3.2 No. of news outlets in the local press and media that have covered the topic 4.1. No. and type of health or social infrastructure developed or modified to respond to new conditions resulting from climate variability and change (by type) 4. 2. No. of physical assets strengthened or constructed to withstand conditions resulting from climate variability and change (by asset types) 5. No. and type of natural resource assets created, maintained or improved to withstand conditions resulting from climate variability and change (by type of assets) 6.1. No. and type of adaptation assets (physical as well as knowledge) created in support of individualor community-livelihood strategies 6.2. Type of income sources for households generated under climate change scenario 7.1. No., type, and sector of policies introduced or adjusted to address climate change risks 7.2. No. or targeted development strategies with incorporated climate change priorities enforced | 2.1.1 | At least 200 personnel are trained in the use of climate information and climate resilient farming and aquaculture techniques in the government and NGOs (50 Provincial Gov., 70 MAL extension/research/land use officers, 30 SIMS field staff, 20 KGA staff and 140 contact farmers, NGASI – 50 contact farmers), YEP volunteers, and village constituencies | Officials, technical experts and field staff of Government, NGOs, private sector and training institutions have limited capacity and not been trained to plan, design and facilitate for the implementaiton of climate change adaptation measures agriculture food production sector.
OBJECTIVE 3
Fund Outcome | Please select from dropdown menu below | Fund Outcome Indicator | Please select from dropdown menu below | Target at CEO Endorsement | Baseline | Mid-term Results | Terminal Results
Outcome 1: Reduced exposure at national level to climate-related hazards and threats Outcome 2: Strengthened institutional capacity to reduce risks associated with climate-induced socioeconomic and environmental losses Outcome 3: Strengthened awareness and ownership of adaptation and climate risk reduction processes at local level Outcome 4: Increased adaptive capacity within relevant development and natural resource sectors Outcome 5: Increased ecosystem resilience in response to climate change and variability-induced stress Outcome 6: Diversified and strengthened livelihoods and sources of income for vulnerable people in targeted areas Outcome 7: Improved policies and regulations that promote and enforce resilience measures | 3 | 1. Relevant threat and hazard information generated and disseminated to stakeholders on a timely basis 2.1. No. and type of targeted institutions with increased capacity to minimize exposure to climate variability risks 2.2. Number of people with reduced risk to extreme weather events 3.1. Percentage of targeted population aware of predicted adverse impacts of climate change, and of appropriate responses 3.2. Modification in behavior of targeted population 4.1. Development sectors' services responsive to evolving needs from changing and variable climate 4.2. Physical infrastructure improved to withstand climate change and variability-induced stress 5. Ecosystem services and natural assets maintained or improved under climate change and variability-induced stress 6.1. Percentage of households and communities having more secure (increased) access to livelihood assets 6.2. Percentage of targeted population with sustained climate-resilient livelihoods 7. Climate change priorities are integrated into national development strategy | 3.1 | By the end of the project at least 18 target wards develop climate resilient farming and aqua-culture production techniques and systems. | Smallholder farming systems do not integrate climate information and risks, and communities in the target wards lack capacity to apply climate resilient farming and aqua-culture production techniques
Fund Output | Please select from dropdown menu below | Fund Output Indicator | Please select from dropdown menu below | Target at CEO Endorsement | Baseline | Mid-term Results | Terminal Results
Output 1: Risk and vulnerability assessments conducted and updated at a national level Output 2.1: Strengthened capacity of national and regional centres and networks to respond rapidly to extreme weather events Output 2.2: Targeted population groups covered by adequate risk reduction systems Output 3: Targeted population groups participating in adaptation and risk reduction awareness activities Output 4: Vulnerable physical, natural, and social assets strengthened in response to climate change impacts, including variability Output 5: Vulnerable physical, natural, and social assets strengthened in response to climate change impacts, including variability Output 6: Targeted individual and community livelihood strategies strengthened in relation to climate change impacts, including variability Output 7: Improved integration of climate-resilience strategies into country development plans | 3 | 1.1. No. and type of projects that conduct and update risk and vulnerability assessments 1.2. Development of early warning systems 2.1.1. No. of staff trained to respond to, and mitigate impacts of, climate-related events 2.1.2. Capacity of staff to respond to, and mitigate impacts of, climate-related events from targeted institutions increased 2.2.1. Percentage of population covered by adequate risk-reduction systems 2.2.2. No. of people affected by climate variability 3.1 No. and type of risk reduction actions or strategies introduced at local level 3.2 No. of news outlets in the local press and media that have covered the topic 4.1. No. and type of health or social infrastructure developed or modified to respond to new conditions resulting from climate variability and change (by type) 4. 2. No. of physical assets strengthened or constructed to withstand conditions resulting from climate variability and change (by asset types) 5. No. and type of natural resource assets created, maintained or improved to withstand conditions resulting from climate variability and change (by type of assets) 6.1. No. and type of adaptation assets (physical as well as knowledge) created in support of individualor community-livelihood strategies 6.2. Type of income sources for households generated under climate change scenario 7.1. No., type, and sector of policies introduced or adjusted to address climate change risks 7.2. No. or targeted development strategies with incorporated climate change priorities enforced | 3.1 | By the end of the project climate-resilient land use planning and agriculture production considerations are integrated into Ward Development Plans in at least 18 Wards in 3 climatic and geographic cluster areas. | Integrated land use approaches and climate change considerations are yet to be factored into land use plans across the different geographic regions in Solomon Islands especially those that are more vulnerable to climate risks
OBJECTIVE 4
Fund Outcome | Please select from dropdown menu below | Fund Outcome Indicator | Please select from dropdown menu below | Target at CEO Endorsement | Baseline | Mid-term Results | Terminal Results
Outcome 1: Reduced exposure at national level to climate-related hazards and threats Outcome 2: Strengthened institutional capacity to reduce risks associated with climate-induced socioeconomic and environmental losses Outcome 3: Strengthened awareness and ownership of adaptation and climate risk reduction processes at local level Outcome 4: Increased adaptive capacity within relevant development and natural resource sectors Outcome 5: Increased ecosystem resilience in response to climate change and variability-induced stress Outcome 6: Diversified and strengthened livelihoods and sources of income for vulnerable people in targeted areas Outcome 7: Improved policies and regulations that promote and enforce resilience measures |  | 1. Relevant threat and hazard information generated and disseminated to stakeholders on a timely basis 2.1. No. and type of targeted institutions with increased capacity to minimize exposure to climate variability risks 2.2. Number of people with reduced risk to extreme weather events 3.1. Percentage of targeted population aware of predicted adverse impacts of climate change, and of appropriate responses 3.2. Modification in behavior of targeted population 4.1. Development sectors' services responsive to evolving needs from changing and variable climate 4.2. Physical infrastructure improved to withstand climate change and variability-induced stress 5. Ecosystem services and natural assets maintained or improved under climate change and variability-induced stress 6.1. Percentage of households and communities having more secure (increased) access to livelihood assets 6.2. Percentage of targeted population with sustained climate-resilient livelihoods 7. Climate change priorities are integrated into national development strategy | 7 | By the end of project climate change considerations are incorporated into at least three policy and legislative frameworks, development planning processes and plans of at least 4 provincial governments | There is no national policy on climate change to guide development processes, agriculture policies and related plans and instruments at the national and provincial levels do not integrate cimate risks
Fund Output | Please select from dropdown menu below | Fund Output Indicator | Please select from dropdown menu below | Target at CEO Endorsement | Baseline | Mid-term Results | Terminal Results
Output 1: Risk and vulnerability assessments conducted and updated at a national level Output 2.1: Strengthened capacity of national and regional centres and networks to respond rapidly to extreme weather events Output 2.2: Targeted population groups covered by adequate risk reduction systems Output 3: Targeted population groups participating in adaptation and risk reduction awareness activities Output 4: Vulnerable physical, natural, and social assets strengthened in response to climate change impacts, including variability Output 5: Vulnerable physical, natural, and social assets strengthened in response to climate change impacts, including variability Output 6: Targeted individual and community livelihood strategies strengthened in relation to climate change impacts, including variability Output 7: Improved integration of climate-resilience strategies into country development plans |  | 1.1. No. and type of projects that conduct and update risk and vulnerability assessments 1.2. Development of early warning systems 2.1.1. No. of staff trained to respond to, and mitigate impacts of, climate-related events 2.1.2. Capacity of staff to respond to, and mitigate impacts of, climate-related events from targeted institutions increased 2.2.1. Percentage of population covered by adequate risk-reduction systems 2.2.2. No. of people affected by climate variability 3.1 No. and type of risk reduction actions or strategies introduced at local level 3.2 No. of news outlets in the local press and media that have covered the topic 4.1. No. and type of health or social infrastructure developed or modified to respond to new conditions resulting from climate variability and change (by type) 4. 2. No. of physical assets strengthened or constructed to withstand conditions resulting from climate variability and change (by asset types) 5. No. and type of natural resource assets created, maintained or improved to withstand conditions resulting from climate variability and change (by type of assets) 6.1. No. and type of adaptation assets (physical as well as knowledge) created in support of individualor community-livelihood strategies 6.2. Type of income sources for households generated under climate change scenario 7.1. No., type, and sector of policies introduced or adjusted to address climate change risks 7.2. No. or targeted development strategies with incorporated climate change priorities enforced | 7.1 | By the end of project climate change considerations are incorporated into at least three policy and legislative frameworks, development planning processes and plans of at least 4 provincial governments | There is no national policy on climate change to guide development processes, agriculture policies and related plans and instruments at the national and provincial levels do not integrate cimate risks

## Units for Indicators
Fund Outcome Indicator Units
1. Generation of relevant data, Stakeholders, and Timeliness 2.1. Include both qualitative and quantitative measures of capacity level within targeted institutions 2.2. Number (men and women and other vulnerable groups) 3.1. Use scale from 1 to 5: 5: Fully aware 4: Mostly aware 3: Partially aware 2: Partially not aware 1: Aware of neither predicted adverse impacts of climate change nor of appropriate responses 3.2. Use scale from 1 to 5: 5: All 4: Almost all 3: Half 2: Some 1: None 4.1. Summarize in an overall scale (1-5): 5: Highly responsive (All defined elements ) 4: Mostly responsive (Most defined elements) 3: Moderately responsive (Some defined elements) 2: Partially responsive (Lacks most elements) 1: Non responsive (Lacks all elements ) 4.2. Summarize in an overall scale (1-5): 5: Fully improved 4: Mostly Improved 3: Moderately improved 2: Somewhat improved 1: Not improved 5. Depends on the targeted natural asset: Biological (species): measure through changes in population numbers (dynamics, structure, etc.) Land: measure changes in hectares. Baseline data will be necessary to estimate the change. Supporting indicators baseline and target (as well as contextual information) are needed such as the following: Farmers adopting recommended technologies, Ha. of land improved, Average deforestation rate Etc. Use scale from 1 to 5. 5: Very effective (All elements are present) 4: Effective (Most elements are present) 3: Moderately effective (Some elements are present) 2: Partially effective (Most elements are not present) 1: Ineffective (No elements are present) 6.1. Summarize in an overall scale (1-5): 5: Very high improvement 4: High improvement 3: Moderate improvement 2: Limited improvement 1: No improvement 6.2. Household income by source of livelihood in project area (USD) prior and post project intervention 7. Summarize in an overall scale (1-5). 5: All (Fully integrated) 4: Most 3: Some 2: Most not integrated 1: None
Fund Output Indicator Units
1.1. Number, sector(s) and level(s) of projects or interventions in separate fields of monitoring plan 1.2. Number 2.1.1. Number of staff (male/female) of targeted institutions: a. Obtain baseline information: total number of staff from targeted institutions b. Define target 2.1.2. Number of staff (male/female) of targeted institutions: a. Obtain baseline information: total number of staff from targeted institutions b. Define target: needs to be defined by project proponents 2.2.1. Quantitative: Percentage (includes women – and other vulnerable groups – and men). Qualitative: Adequacy: include direct analysis of major areas; adequacy/effectiveness of systems or analysis of perceptions of populations and institutions. 2.2.2. Number (broken down by gender and, if possible, by vulnerable groups defined in the area of intervention) of people 3.1. Number and type (in separate columns) at local level. 3.2. Number 4.1. Number and type 4. 2. Number and type (entered in separate columns) 5. Number of interventions by type of natural asset and intervention 6.1. Number and type (in separate columns of monitoring plan) 6.2. Income sources per household; description of income source and number of households. 7.1. Number/Sector 7.2. Number; Effectiveness (see previous indicator) through enforcement level.