## Overview
Project Performance Report (PPR)
| Period of Report (Dates) | December,2013
| Project Title: | Climate Change Adaptation Programme in Water and Agriculture in Anseba Region,Eritrea.
Project Summary:
|  | The objective of the project is to: ''to increase community resilence and adaptive capacity to climate change through an integrated water management and agricultural developmemnt approach in the Sub-zoba Hamelmalo and Habero, Anseba region,Eritrea.'' The Hamelmalo and Hebero sub zobas are bisected by the Anseba River. Large part of these areas has been deforested and the rugged topography is exposed to severe soil erosions reducing the top soil and making the forest and woodland regeneration difficult. The two sub regions have been identified as having vulnerable livelihood system, low agricultural productivity and ranked among the most top five zobas affected by food insecurity due increased impact of climate change and rainfall variability. This project is designed to enhance the availability of water for increased productivity and to develop the adaptive capacity of vulnerable communities by expanding small scale irrigation to increase agricultural production and to conserve water and soil through rangeland development. The project comprises of five key outcomes as follows: 1. Increased water availability and erosion control through groundwater recharge,rainwater harvesting,irrigation and soil and water conservation measures. It comprises Construction of sub-surface dam associated with pumping and irrigation water distribution facilities, construction of two microdams to retain and store rainfall runoff and soil and water conservation measures implemented to improve runoff management and infiltration. 2.Climate resilient agricultural and livestock production enhanced . This focus on a range of climate resilient agricultural technologies and methods developed and transfered to farmers like drought and disease resistant varieties, integrated crop-livestock production system, conservation agriculture, agroforestry, rangeland management; and traditional improved fuel efficient stove. Seasonal forecast used a farmer-led collaborative action learing process to enhanceadaptive capacity and climate proof production system. 3. Improved climate risk information and climate monitoring used to raise awareness and enhance community prepaedness to climate change. This mainly emphasis on the improved climate risk information generated and capacity developed for climate monitoring and analysis. awareness raised at different levels on climate change risks facing zoba Anseba 4. Knoweledge management system established and knoweledge managemnt activities implemented. This component consists of establishment of knoweledge management system and implementation of knweledge management actiovites, and implementation of policy advocacy activities. | Countries | Project Type: |  | GEF Focal Area: | GEF 4 Focal Areas | GEF 2 / 3 Operational Programme: | Overall Rating of the project in the evaluation by the project evaluator: | GEF-4 Focal Area Strategic Program: | GEF-3 Focal Area Strategic Program:
| Database Number: |  | Afghanistan | FP | Yes | Biodiversity | 1 | 1 | U | BD-SP1-PA Financing | 1: Arid & semi-arid ecosystems
Implementing Entity (IE) [name]: |  | Ministry of Land Water and Environment | Albania | MSP | No | Climate Change Adaptation | 2 | 2 | S | BD-SP2-Marine PA | 2: Coastal, marine & freshwater ecosystems
| Type of IE: | Governmemnt | Algeria | EA |  | Climate Change Mitigation | 3 | 3 | MU | BD-SP3-PA Networks | 3: Forest ecosystems
| Country(ies): | Eritrea | Angola |  |  | International Waters | 5 | 5 | Good | BD-SP5-Markets | 13: Conservation and Sustainable Use of Biological Diversity Important to Agriculture
Relevant Geographic Points (i.e. cities, villages, bodies of water): |  | Hamelmalo and Habero | Argentina |  |  | Multiple Focal Area |  |  |  | BD-SP7-Invasive Alien Species(IAS) | 6: Promoting the adoption of renewable energy by removing barriers and reducing implementation costs
[8 empty] | CC-SP2- Industrial EE | 8: Waterbody based operational program
| Project Milestones | [6 empty] | CC-SP3-RE,CC-SP4-Biomass | 9: Integrated Land and Water multiple focal area
| Milestone |  | Bahamas | [6 empty] | CC-SP5-Transport | 10: Contaminants based operational program
AFB Approval Date: |  | 2012-10-09
IE-AFB Agreement Signature Date: |  | 2012-06-09 | [6 empty] | CC-SP6-LULUCF | 12: Integrated Ecosystem Management
Start of Project/Programme: |  | 2013-01-06 | [6 empty] | Cross cutting capacity building | 14: Persistent Organic Pollutants
Mid-term Review Date (if planned): |  | 2015-01-10
| Terminal Evaluation Date: | 2015-01-10
|  | List documents/ reports/ brochures / articles that have been prepared about the project. | Cyprus
|  | Inception report Field report Progress Report | Czech Republic
List the Website address (URL) of project. |  |  | Democratic People's Republic of Korea
Democratic Republic of the Congo
Denmark
| Project contacts: |  | Djibouti
National Project Manager/Coordinator |  |  | Dominica
| Name: | Mr. Ghebremeskel Tewolde | Dominican Republic
| Email: | anejigna@yahoo.com | Ecuador
| Date: | 2013-08-01 | Egypt
| Government DA |  | El Salvador
| Name: | Ministry of National Development | Equatoral Guinea
| Email: |  | Eritrea
| Date: |  | Estonia
| Implementing Entity |  | Ethiopia
| Name: | Yoseph Admekom | Fiji
| Email: | yoseph.admekom@undp.org | Finland
| Date: | 2013-08-01 | France
| Executing Agency |  | Gambia
| Name: | Minnistry of Land, Water and Enviroment | Georgia
| Email: | m.bairu@gmail.com | Germany
| Date: | 2013-08-01 | Ghana
| Executing Agency |  | Greece
| Name: |  | Grenada
| Email: |  | Guatemala
| Date: |  | Guinea
| Executing Agency |  | Guinea Bissau
| Name: |  | Guyana
| Email: |  | Haiti
| Date: |  | Honduras
Hungary
Iceland
India
Indonesia
Iran (Islamic Republic of)
Iraq
Ireland
Israel
Italy
Jamaica
Japan
Jordan
Kazakhstan
Kenya
Kiribati
Kuwait
Kyrgyzstan
Lao People’s Democratic Republic
Latvia
Lebanon
Lesotho
Liberia
Libyan Arab Jamahiriya
Liechtenstein
Lithuania
Luxembourg
Madagascar
Malawi
Malaysia
Maldives
Mali
Malta
Marshall Islands
Mauritania
Mauritius
Mexico
Micronesia, Federated States of
Monaco
Mongolia
Montenegro
Morocco
Mozambique
Myanmar
Namibia
Nauru
Nepal
Netherlands
New Zealand
Nicaragua
Niger
Nigeria
Norway
Oman
Pakistan
Palau
Panama
Papua New Guinea
Paraguay
Peru
Philippines
Poland
Portugal
Qatar
Republic of Korea
Republic of Moldova
Romania
Russian Federation
Rwanda
Saint Kitts and Nevis
Saint Lucia
Saint Vincent and the Grenadines
Samoa
San Marino
Sao Tome and Principe
Saudi Arabia
Senegal
Serbia
Seychelles
Sierra Leone
Singapore
Slovakia
Slovenia
Solomon Islands
Somalia
South Africa
Spain
Sri Lanka
Sudan
Suriname
Swaziland
Sweden
Switzerland
Syrian Arab Republic
Tajikistan
Thailand
The former Yugoslav Republic of Macedonia
Timor-Leste
Togo
Tonga
Trinidad and Tobago
Tunisia
Turkey
Turkmenistan
Tuvalu
Uganda
Ukraine
United Arab Emirates
United Kingdom of Great Britain and Northern Ireland
United Republic of Tanzania
United States of America
Uruguay
Uzbekistan
Vanuatu
Venezuela, Bolivarian Republic of
Viet Nam
Yemen
Zambia
Zimbabwe

## FinancialData
Financial information: cumulative from project start to [insert date]
DISBURSEMENT OF AF GRANT FUNDS
How much of the total AF grant as noted in Project Document plus any project preparation grant has been spent to date?
Estimated cumulative total disbursement as of [05/12/31] | 621750
Add any comments on AF Grant Funds. (word limit=200)
EXPENDITURE DATA
List ouput and corresponding amount spent for the current reporting period | ITEM / ACTIVITY / ACTION | AMOUNT
| Output 1.2 | 202119
| out put 1.4 | 162256.7
| Output 1.3 | 163591.75
| Outcome 1 subtotal | 527967.45
| Output 3.1 | 80000
| Execution Costs | 23782.21
PLANNED EXPENDITURE SCHEDULE | TOTAL | 621749.99
List outputs planned and corresponding projected cost for the upcoming reporting period | ITEM / ACTIVITY / ACTION | PROJECTED COST: 2014 budget | Est. Completion Date
| 1.1: Groundwater recharged and irrigation technologies implemented for crop and forage production by developing a sub-surface dam within the Anseba River | 460700 | 2015
| 1.2.: Floodwater harvested to enable irrigation of rain-fed cereal production and rangelands. | 245000 | 2015 | ,
| 1.3: Two micro dams constructed to retain and store rainfall run-off and to enable higher cereal and forage production levels as well as supply of water for livestock | 306000 | 2015
| 1.4: Soil and water conservation measures implemented to improve runoff management and infiltration for improved rangeland management and enhanced cereal production | 144500 | 2015
| 2.1 A range of climate-resilient agricultural technologies and methods developed and transferred to farmers | 296250 | 2015 |  | 0 | 0
| 2.2: Seasonal forecasts used in a farmer-led collaborative action learning process to enhance adaptive capacity and climate-proof production systems | 58000 | 2016 |  | 0 | 0
| 3.1 Improved climate risk information generated and capacity developed for climate monitoring and analysis | 172500 | 2015 |  | 0
| 3.2 Awareness raised at different levels on climate change risks facing Zoba Anseba | 56500 | 2015 |  |  | 0
| 3.3 Community preparedness enhanced through development of a community-based early warning system in sub-zobas Hamelmalo and Habero | 77000 | 2016
| 4.1 Knowledge management system established and knowledge management activities implemented | 58750 | 2015
| 4.2 Policy advocacy activities implemented | 58300 | 2016
| Project Management | 93400
ACTUAL CO-FINANCING (If the MTR or TE have not been undertaken this reporting period, DO NOT report on actual co-financing.) | TOTAL | 2026900
How much of the total co-financing as committed in the Project Document has actually been realized?
Estimated cumulative actual co-financing as verified during Mid-term Review (MTR) or Terminal Evaluation (TE).
Add any comments on actual co-financing in particular any issues related to the realization of in-kind, grant, credits, loans, equity, non-grant instruments and other types of co-financing. (word limit=200)

## Risk Assesment
RISK ASSESMENT
IDENTIFIED RISKS
List all Risks identified in project preparation phase and what steps are being taken to mitigate them
Identified Risk | Current Status | Steps Taken to Mitigate Risk
Severe drought or other extreme weather events | Eritrea already has an extreme climate and adaptation project intervensions are geared towards these extremes. | Project implementation.
Groundwater level dropping and salinisation of wells leading to potential scarcity and competition, possibly leading to conflict. | Micro-dams are intended to re-charge groundwater levels. A monitoring plan is in process of being developed by Hamelmalo college to measure recharge rates (as well as other impacts from project activities). | All necessary environmental assessment procedures will be followed to ensure that the design of the investments follows best practice. A monitoring plan to measure re-charge rates will be put into place in 2014.
Low human and institutional capacity for the implementation of CC-related interventions. | Capacity is low for Outcome 3 of the project: climate risk information and community preparedness systems. For all other Outcomes there is sufficient expertise to implement the project. | Carry out an international procurement to bring in expertise to help develop capacity in GoE to design climate risk information systems for use by by local communities.
Delays in programme implementation, particularly for infrastructure. | The budget of the project was released during the rainy season which was not convenient to implement the proposed action of diversion schemes. Infrastructure will be built in 2014. | Design and BoQ of the activities were prepared. 3000 quintal of cement was purchased for the construction of diversion structure. Continous negotiation and consultation was done with ministry of National Development and ministry of Land water and Enviroment. A serious of letter were written to these ministry to speed up the implementation process.
Price escalation and unavailability of commodities and materials. | none | n/a
Failure of zoba administration to institutionalise early warning system and meterological/climate observation components. | Activities to implement the climate monitoring and risk information aspects of the project have not yet begun. However, capacities in GoE would benefit from support. | Carry out an international procurement to bring in expertise to help develop capacity in GoE to design climate risk information systems for use by by local communities.
Migration of human and livestock population under conditions of extreme severity to localities with a better natural resource base. | Project is intended to provide resilient livelihood opportunities for local communities which will help stem migration. | Project implementation.
Accessibility and communications in the programme | For extension agents once Outcome 3 begins implementation: Off road motorbikes for extension agents and mobile phones/radio for communities | Purchase of motorbikes and mobile phones/radio communication
Critical Risks Affecting Progress (Not identified at project design)
Identify Risks with a 50% or > likelihood of affecting progress of project
Identified Risk | Current Status | Steps Taken to Mitigate Risk
Delays in programme implementation, particularly for infrastructure. | The budget of the project was released during the rainy season which was not convenient to implement the proposed action of diversion schemes. Infrastructure will be built in 2014. | Design and BoQ of the activities were prepared. 3000 quintal of cement was purchased for the construction of diversion structure. Continous negotiation and consultation was done with ministry of National Development and ministry of Land water and Enviroment. A serious of letter were written to these ministry to speed up the implementation process.
Potential conflict with neighbouring Ethiopia. | None | n/a
Risk Measures: Were there any risk mitigation measures employed during the current reporting period? If so, were risks reduced? If not, why were these risks not reduced?
Add any comments relevant to risk mitigation (word limit = 500)

## Rating
RATING ON IMPLEMENTATION PROGRESS
For rating definitions please see bottom of page.
| Progress on Key Milestones |  | Expected Progress |  | Progress to Date | Rating
Project Manager/Coordinator: | 1.1: Groundwater recharged and irrigation technologies implemented for crop and forage production by developing a sub-surface dam within the Anseba River |  | Sub-surface dam with associated pumping and irrigation water distribution facilities completed.Increase in forage production per ha of irrigated land |  | Specification for solar installation prepared and sent to potential supplier. A quotation for the construction of sub surface dam collected and the winner of the bid identified. Construction will be started 1st week of December |  | S
| 1.2.: Floodwater harvested to enable irrigation of rain-fed cereal production and rangelands. |  | Select the location for the proposed diversion weir,Prepare topographic map and constrcution of diversion structure |  | A site for flood water diversion was identified, a design has been prepared. 3000 quintal of cement for construction has been procured. Provision construction materials like stone and sand collected at the project site area and construction is ongoing. |  | S
| 1.3: Two micro dams constructed to retain and store rainfall run-off and to enable higher cereal and forage production levels as well as supply of water for livestock |  | Identify suitable locations for the two micro dams based on vulnerable communities, streamflow characteristics and irrigable potential of land,Prepare construction level drawings with accurate costing for the construction of the micro dams and their appurtenant structures (spillway and outlet work),Complete construction of the micro dams ,maintenance of the irrigation structures and pumps |  | Site for for micro dams identified, technical Design of the two micro dams completed and bill of quantity prepared for all construction materials . A bid document prepared and distributed/submitted to bidders. 2nd week of December Contract award will be issued and construction activities will commence. |  | S
| 1.4: Soil and water conservation measures implemented to improve runoff management and infiltration for improved rangeland management and enhanced cereal production |  | Construct hillside terracing along contours in identified locations using stone faced hillside terracing,: Construct check dams,Implement planned enclosure and afforestation activities, using multipurpose trees |  | A site for construction of soil and water conservation structure identified and enclosed. Soil and water conservation structures constructed (232 km hill terracing, 7307.23m3 capacity check dams), 143,000 economical trees like a.senegal(130,000) and (13000) sisal planted, 6 guards to protect enclosures recruited, temporary nursery site selected and site is enclosed for natural regenaration. |  | S
| 2.1 A range of climate-resilient agricultural technologies and methods developed and transferred to farmers |  | Enhance capacity and effectiveness of agricultural extension agents through training and enhanced mobility and communications |  | Not included in the signed AWP of 2013
| 2.2: Seasonal forecasts used in a farmer-led collaborative action learning process to enhance adaptive capacity and climate-proof production systems |  | programme sites for the collaborative action learning process and hold introductory meetings at each locality, attended by farmers, research professionals and extension agents |  | Not included in the signed AWP of 2013
| 3.1 Improved climate risk information generated and capacity developed for climate monitoring and analysis |  | Sites selected,equipment purchased and installed for one Class 1 meteorological station in sub-zoba Habero and Hamelmalo |  | Site for metrological stations identified in two zobas, specification in consultation with MET committee from different institutes prepared, quotations distributed to potential suppliers. |  | S | COMPLIANCE WITH SAFEGUARDS?
| 3.2 Awareness raised at different levels on climate change risks facing Zoba Anseba |  | Develop a detailed strategy for the climate change awareness raising campaign for the programme, spelling out a workplan, target audiences and modes of communication,CC awareness raising campaign to capture public imagination and secure initial political commitment, |  | Not included in the signed AWP of 2013
| 3.3 Community preparedness enhanced through development of a community-based early warning system in sub-zobas Hamelmalo and Habero |  | Train community members in data collection, carry out institutional strengthening of relevant community institutions and establish community-based early warning system in the two programme sub-zobas |  | Not included in the signed AWP of 2013
Please justify your rating. Outline the positive and negative progress made by the project since it started. Provide specific recommendations for next steps. . (word limit=500) | 4.1 Knowledge management system established and knowledge management activities implemented |  | Design and establish a knowledge management system for the programme, based on existing processes in the Zoba Anseba administration, to be institutionalised within the administration. This will include identifying a lead agency for this purpose, as well as a coordination mechanism between relevant departments for sharing lessons, and developing a standardised system for capturing lessons learned, Conduct a study tour |  | Not included in the signed AWP of 2013
| 4.2 Policy advocacy activities implemented |  | Conduct regular policy advocacy activities throughout the life of the programme, including at relevant national and regional events. Develop appropriate knowledge products, including photo stories, presentations and briefing notes, for use in policy advocacy activities |  | Not included in the signed AWP of 2013
[6 empty] | Overall Rating | S
Please Provide the Name and Contact information of person(s) reponsible for completeling the Rating section
| Name: | Gebremeskel Tewolde (NPC)
Implementing Agency | Email: | anejigna@yahoo.com
There has been a very high amount of work done in a very short period of time (effective date of start – July 2013). The progress of the project implementation is highly affected by the delay of disbursement of advances. The six month delay was due to the introduction of new working procedures and norms established by the government to be applied by a UN system in Eritrea. Then funds were released during the rainy season which made it difficult to conduct any construction activities. In addition, the rough road was worsened by the rainy season hampering smooth and and speedy implementation. To avoid unsatisfactory result new activities were taken up by the project to compensate for delayed activities. Procurements were made. And soil and water conservation activities have been accomplished in the project sites by the 800 members of the community through a cash for work mechanism. This covers 456 hectares (about 50% of planned treatment area) of one of the two Districts - Hamelmalo. After construction, the community have shown initiatives to protect interventions such as the treated enclosures which the local government is also committed to support.
| Progress on Key Milestones |  | Expected Progress |  | Progress to Date | Rating
Other | Despite the late start of the project, the project has achieved much physical work activities. |  | In 2014, the project will have a varity of activities from all its planned outputs and much more tangible results are expected to be achieved by timely implementation and active collaboration of key stakeholders. |  | Much physical work and identification of sites for future interventions as well as purchases of equipment, supplies and construction materials have been undertaken. | S
Overall Rating
Please Provide the Name and Contact information of person(s) reponsible for completeling the Rating section
| Name: | Yoseph Admekom (UNDP)
| Email: | yoseph.admekom@undp.org
| Progress on Key Milestones |  | Expected Progress |  | Progress to Date | Rating
| I have visited the project and have been closely monitoring its implementation. I have found out that the project has done well and achieved its intended results with some changes made in accommodating other activities brought forward that were not in the AWP due to necessary action taken to mitigate impacts of delay in the start up. |  | Strongly believe that all outcomes of the project will be realized and the project will hit its goals. |  | Soil and water conservation, afforestation activities, design of micro dams, dicersion structure, well renovations, enclosure protection activities, etc. were undertaken. The has also prepared itself much in terms of design and materials of work to be achieved in for 2014. | S
Overall Rating
Please Provide the Name and Contact information of person(s) reponsible for completeling the Rating section
| Name: | Mogos Woldeyohannes (Director Geenral and National Environment Focal Point)
| Email: | m.bairu@gmail.com
| Please justify your rating and address the following points: 1. Indicate trends, both positive and negative, in achievement of outcomes as per the project indicators. 2. Detail critical risks that have affected progress. 3. Outline response to MTR undertaken this reporting period. 4. Outline action plan to address projects with a rating of HU, U or MU. Please keep your input to 1200 words |  | The project has just started and has a long way to implement its activities and measure its output and outcomes.At this moment, one can oly state that the so-fare accomplished is within a veryshort period of tim. With the dedication of staff and stakeholders as well the support the rpoject recieves from highest government officials, including the Governor of Anseba, theproject has much chance of accomplishing all its outcomes in the coming 4-5 years.
Rating Definitions
|  |  | Highly Satisfactory (HS) | Project actions/activities planned for current reporting period are progressing on track or exceeding expectations to acheive all major outcomes/outputs for given reporting period, without major shortcomings. The project can be presented as “good practice”.
|  |  | Satisfactory (S) | Project actions/activities planned for current reporting period are progressing on track to achieve most of its major outcomes/outputs with only minor shortcomings.
|  |  | Marginally Satisfactory (MS) | Project actions/activities planned for current reporting period are progressing on track to achieve most major relevant outcomes/outputs, but with either significant shortcomings or modest overall relevance.
|  |  | Marginally Unsatisfactory (MU) | Project actions/activities planned for current reporting period are not progressing on track to achieve major outcomes/outputs with major shortcomings or is expected to achieve only some of its major outcomes/outputs.
|  |  | Unsatisfactory (U) | Project actions/activities planned for current reporting period are not progressing on track to achieve most of its major outcomes/outputs.
|  |  | Highly Unsatisfactory (U) | Project actions/activities planned for current reporting period are not on track and shows that it is failing to achieve, and is not expected to achieve, any of its outcomes/outputs.

## Project Indicators
PROJECT Indicators
Please provide all indicators being tracked for the project as outlined in the project document
Type of Indicator (indicators towards Objectives, Outcomes, etc…)
Type of Indicator | Indicator | Baseline | Progress since inception | Target for Project End
Outcome 1 | Change in level of renewable water resources used in programme area | Only about 1 Million cubic meters is put in use. 1)Integrated water/agriculture adaptation actions are not implemented, Eritrea’s rural areas will continue to experience increasing vulnerability and growing insecurity, due to decreased availability of water and conflicts between crop and livestock uses. This will damage the social fabric in rural areas. 2)Communities in the two zobas have serious shortage of water supply. | 3000 quintal of cement for the construction of diversion structure is procured -7,307.25M3 of checkdam and 233.84 Km of terracin is constructed -143,000 trees are planted | 5.3 million cubic meters of renewable water resources used in programme area (an increase of 4.3 million m3). Achieved by building two micro dams constructed to retain and store rainfall run-off and to enable higher cereal and forage production levels as well as supply of water for livestock.
specification for solar instalation prepared and sent to potential supplier. A quotation of the spulliers collected and the winner of the bid identified
Technical Design and bill of quantity is done. A bid document is prepared and submitted to bidders.
A site for construction of soil and water conservation structure identified and enclosed. Soil and water conservation structures constructed, economical trees like a.senegal and sisal planted and site is enclosed for natural regenaration.
Outcome2 | Change in food security in the programme area as a result of using climate resilient agricultural and livestock production methods, measured as# of months per year additionally covered by local production | Sub Zoba Hamelmalo and Habero ranked the top five (out of 11) most affected zobas by food insecurity due to increased impact of climate change. |  | 70% of programme beneficiaries have sufficient food for at least an additional three months per year
Outcome 3 | Percentage of programme beneficiaries making use of improved climate risk information and climate monitoring processes, disaggregated according gender | No improved climate risk information available yet. | Site identified, specification prepared, quotationss distributed to potential suppliers | 70% of programme beneficiaries make use of improved climate risk information
Outcome 4 | Number of lessons learned and natural resource management in the context of climate change as a result of the programme. | No relevant lessons learned are being captured or disseminatd. |  | At least five lessons learned codified ad disseminated

## Lessons Learned
QUALITATIVE MEASURES and LESSONS LEARNED
Please complete the following section every reporting period
Implementation and Adaptive Management | Response
What implementation issues/lessons, either positive or negative, affected progress? | The budget of the project was released during the rainy season which was not convenient to implement the proposed action of diversion schemes. Infrastructure will be built in 2014. Design and BoQ of the activities were prepared. 3000 quintal of cement was purchased for the construction of diversion structure. Continous negotiation and consultation was done with ministry of National Development and ministry of Land water and Enviroment. A serious of letter were written to these ministry to speed up the implementation process.
Were there any delays in implementation? If so, include any causes of delays. What measures have been taken to reduce delays? | Yes, There was budget delay in implementation. Revising the proposed plan of action and a series of consultation with the stakeholder and community was done to mitigate the delay.
Describe any changes undertaken to improve results on the ground or any changes made to project outputs (i.e. changes to project design) | - Due to the rainy season construction couldn't be executed as planned, to save time and expedite implementation after the rainy season cement for construction was procured. - Construction of soil and water -conservation measures, and afforestation were implemented prior to the proposed schedule
How have gender considerations been taken into consideration during the reporting period? What have been the lessons learned as a consequence of inclusion of such considerations on project performance or impacts? | The compliance of the project with Equal Opportunity Act is mandatory as per Government legal framework. Focus on Gender has been fully integrated into project activities through involvement of women in activities (Women's association have been actively involved in the adaption project: plantation of selected trees like seasal, acacia.... and women participation in soil and water conservation (terracing, check dams ....... was very high.
Please complete the following section at mid-term and project completion
Lessons for Adaptation | Response
Climate Resilience Measures
What have been the lessons learned, both positive and negative, in implementing climate adaptation measures that would be relevant to the design and implementation of future projects/programmes for enhanced resilience to climate change?
What is the potential for the climate resilience measures undertaken by the project/programme to be replicated and scaled up both within and outside the project area?
Concrete Adaptation Interventions
What have been the lessons learned, both positive and negative, in implementing concrete adaptation interventions that would be relevant to the design and implementation of future projects/programmes implementing concrete adaptation interventions?
What is the potential for the concrete adaptation interventions undertaken by the project/programme to be replicated and scaled up both within and outside the project area?
Community/National Impact
What would you consider to be the most successful aspects for the target communities?
What measures are/have been put in place to ensure sustainability of the project/program results?
What measures are being/could have been put in place to improve project/program results?
Knowledge Management
How has existing information/data/knowledge been used to inform project development and implementation? What kinds of information/data/knowledge were used?
If learning objectives have been established, have they been met? Please describe.
Describe any difficulties there have been in accessing or retrieving existing information (data or knowledge) that is relevant to the project. Please provide suggestions for improving access to the relevant data.
Has the identification of learning objectives contributed to the outcomes of the project? In what ways have they contributed?

## Results Tracker
Results Tracker for Adaptation Fund (AF) Projects
Goal: Assist developing-country Parties to the Kyoto Protocol that are particularly vulnerable to the adverse effects of climate change in meeting the costs of concrete adaptation projects and programmes in order to implement climate-resilient measures. Impact: Increased resiliency at the community, national, and regional levels to climate variability and change.
Important: Please read the following Results Framework and Baseline Guidance (also posted on the Adaptation Fund website) before entering your data
Link: http://www.adaptation-fund.org/sites/default/files/Results%20Framework%20and%20Baseline%20Guidance%20final.pdf
Please select the relevant Fund level Outcome and Output indicators that allign with the project objectives and outcomes
OBJECTIVE 1
Fund Outcome | Please select from dropdown menu below | Fund Outcome Indicator | Please select from dropdown menu below | Target at CEO Endorsement (see Units in next sheet) | Baseline (see Units in next sheet) | Mid-term Results | Terminal Results
Outcome 1: Reduced exposure at national level to climate-related hazards and threats Outcome 2: Strengthened institutional capacity to reduce risks associated with climate-induced socioeconomic and environmental losses Outcome 3: Strengthened awareness and ownership of adaptation and climate risk reduction processes at local level Outcome 4: Increased adaptive capacity within relevant development and natural resource sectors Outcome 5: Increased ecosystem resilience in response to climate change and variability-induced stress Outcome 6: Diversified and strengthened livelihoods and sources of income for vulnerable people in targeted areas Outcome 7: Improved policies and regulations that promote and enforce resilience measures | 4 | 1. Relevant threat and hazard information generated and disseminated to stakeholders on a timely basis 2.1. No. and type of targeted institutions with increased capacity to minimize exposure to climate variability risks 2.2. Number of people with reduced risk to extreme weather events 3.1. Percentage of targeted population aware of predicted adverse impacts of climate change, and of appropriate responses 3.2. Modification in behavior of targeted population 4.1. Development sectors' services responsive to evolving needs from changing and variable climate 4.2. Physical infrastructure improved to withstand climate change and variability-induced stress 5. Ecosystem services and natural assets maintained or improved under climate change and variability-induced stress 6.1. Percentage of households and communities having more secure (increased) access to livelihood assets 6.2. Percentage of targeted population with sustained climate-resilient livelihoods 7. Climate change priorities are integrated into national development strategy | 4.2
Fund Output | Please select from dropdown menu below | Fund Output Indicator | Please select from dropdown menu below | Target at CEO Endorsement (see Units in next sheet) | Baseline (see Units in next sheet) | Mid-term Results | Terminal Results
Output 1: Risk and vulnerability assessments conducted and updated at a national level Output 2.1: Strengthened capacity of national and regional centres and networks to respond rapidly to extreme weather events Output 2.2: Targeted population groups covered by adequate risk reduction systems Output 3: Targeted population groups participating in adaptation and risk reduction awareness activities Output 4: Vulnerable physical, natural, and social assets strengthened in response to climate change impacts, including variability Output 5: Vulnerable physical, natural, and social assets strengthened in response to climate change impacts, including variability Output 6: Targeted individual and community livelihood strategies strengthened in relation to climate change impacts, including variability Output 7: Improved integration of climate-resilience strategies into country development plans | 4 | 1.1. No. and type of projects that conduct and update risk and vulnerability assessments 1.2. Development of early warning systems 2.1.1. No. of staff trained to respond to, and mitigate impacts of, climate-related events 2.1.2. Capacity of staff to respond to, and mitigate impacts of, climate-related events from targeted institutions increased 2.2.1. Percentage of population covered by adequate risk-reduction systems 2.2.2. No. of people affected by climate variability 3.1 No. and type of risk reduction actions or strategies introduced at local level 3.2 No. of news outlets in the local press and media that have covered the topic 4.1. No. and type of health or social infrastructure developed or modified to respond to new conditions resulting from climate variability and change (by type) 4. 2. No. of physical assets strengthened or constructed to withstand conditions resulting from climate variability and change (by asset types) 5. No. and type of natural resource assets created, maintained or improved to withstand conditions resulting from climate variability and change (by type of assets) 6.1. No. and type of adaptation assets (physical as well as knowledge) created in support of individualor community-livelihood strategies 6.2. Type of income sources for households generated under climate change scenario 7.1. No., type, and sector of policies introduced or adjusted to address climate change risks 7.2. No. or targeted development strategies with incorporated climate change priorities enforced | 4.2
OBJECTIVE 2
Fund Outcome | Please select from dropdown menu below | Fund Outcome Indicator | Please select from dropdown menu below | Target at CEO Endorsement | Baseline | Mid-term Results | Terminal Results
Outcome 1: Reduced exposure at national level to climate-related hazards and threats Outcome 2: Strengthened institutional capacity to reduce risks associated with climate-induced socioeconomic and environmental losses Outcome 3: Strengthened awareness and ownership of adaptation and climate risk reduction processes at local level Outcome 4: Increased adaptive capacity within relevant development and natural resource sectors Outcome 5: Increased ecosystem resilience in response to climate change and variability-induced stress Outcome 6: Diversified and strengthened livelihoods and sources of income for vulnerable people in targeted areas Outcome 7: Improved policies and regulations that promote and enforce resilience measures | 6 | 1. Relevant threat and hazard information generated and disseminated to stakeholders on a timely basis 2.1. No. and type of targeted institutions with increased capacity to minimize exposure to climate variability risks 2.2. Number of people with reduced risk to extreme weather events 3.1. Percentage of targeted population aware of predicted adverse impacts of climate change, and of appropriate responses 3.2. Modification in behavior of targeted population 4.1. Development sectors' services responsive to evolving needs from changing and variable climate 4.2. Physical infrastructure improved to withstand climate change and variability-induced stress 5. Ecosystem services and natural assets maintained or improved under climate change and variability-induced stress 6.1. Percentage of households and communities having more secure (increased) access to livelihood assets 6.2. Percentage of targeted population with sustained climate-resilient livelihoods 7. Climate change priorities are integrated into national development strategy | 6.2
Fund Output | Please select from dropdown menu below | Fund Output Indicator | Please select from dropdown menu below | Target at CEO Endorsement | Baseline | Mid-term Results | Terminal Results
Output 1: Risk and vulnerability assessments conducted and updated at a national level Output 2.1: Strengthened capacity of national and regional centres and networks to respond rapidly to extreme weather events Output 2.2: Targeted population groups covered by adequate risk reduction systems Output 3: Targeted population groups participating in adaptation and risk reduction awareness activities Output 4: Vulnerable physical, natural, and social assets strengthened in response to climate change impacts, including variability Output 5: Vulnerable physical, natural, and social assets strengthened in response to climate change impacts, including variability Output 6: Targeted individual and community livelihood strategies strengthened in relation to climate change impacts, including variability Output 7: Improved integration of climate-resilience strategies into country development plans | 6 | 1.1. No. and type of projects that conduct and update risk and vulnerability assessments 1.2. Development of early warning systems 2.1.1. No. of staff trained to respond to, and mitigate impacts of, climate-related events 2.1.2. Capacity of staff to respond to, and mitigate impacts of, climate-related events from targeted institutions increased 2.2.1. Percentage of population covered by adequate risk-reduction systems 2.2.2. No. of people affected by climate variability 3.1 No. and type of risk reduction actions or strategies introduced at local level 3.2 No. of news outlets in the local press and media that have covered the topic 4.1. No. and type of health or social infrastructure developed or modified to respond to new conditions resulting from climate variability and change (by type) 4. 2. No. of physical assets strengthened or constructed to withstand conditions resulting from climate variability and change (by asset types) 5. No. and type of natural resource assets created, maintained or improved to withstand conditions resulting from climate variability and change (by type of assets) 6.1. No. and type of adaptation assets (physical as well as knowledge) created in support of individualor community-livelihood strategies 6.2. Type of income sources for households generated under climate change scenario 7.1. No., type, and sector of policies introduced or adjusted to address climate change risks 7.2. No. or targeted development strategies with incorporated climate change priorities enforced | 6.1
OBJECTIVE 3
Fund Outcome | Please select from dropdown menu below | Fund Outcome Indicator | Please select from dropdown menu below | Target at CEO Endorsement | Baseline | Mid-term Results | Terminal Results
Outcome 1: Reduced exposure at national level to climate-related hazards and threats Outcome 2: Strengthened institutional capacity to reduce risks associated with climate-induced socioeconomic and environmental losses Outcome 3: Strengthened awareness and ownership of adaptation and climate risk reduction processes at local level Outcome 4: Increased adaptive capacity within relevant development and natural resource sectors Outcome 5: Increased ecosystem resilience in response to climate change and variability-induced stress Outcome 6: Diversified and strengthened livelihoods and sources of income for vulnerable people in targeted areas Outcome 7: Improved policies and regulations that promote and enforce resilience measures | 1 | 1. Relevant threat and hazard information generated and disseminated to stakeholders on a timely basis 2.1. No. and type of targeted institutions with increased capacity to minimize exposure to climate variability risks 2.2. Number of people with reduced risk to extreme weather events 3.1. Percentage of targeted population aware of predicted adverse impacts of climate change, and of appropriate responses 3.2. Modification in behavior of targeted population 4.1. Development sectors' services responsive to evolving needs from changing and variable climate 4.2. Physical infrastructure improved to withstand climate change and variability-induced stress 5. Ecosystem services and natural assets maintained or improved under climate change and variability-induced stress 6.1. Percentage of households and communities having more secure (increased) access to livelihood assets 6.2. Percentage of targeted population with sustained climate-resilient livelihoods 7. Climate change priorities are integrated into national development strategy | 1
Fund Output | Please select from dropdown menu below | Fund Output Indicator | Please select from dropdown menu below | Target at CEO Endorsement | Baseline | Mid-term Results | Terminal Results
Output 1: Risk and vulnerability assessments conducted and updated at a national level Output 2.1: Strengthened capacity of national and regional centres and networks to respond rapidly to extreme weather events Output 2.2: Targeted population groups covered by adequate risk reduction systems Output 3: Targeted population groups participating in adaptation and risk reduction awareness activities Output 4: Vulnerable physical, natural, and social assets strengthened in response to climate change impacts, including variability Output 5: Vulnerable physical, natural, and social assets strengthened in response to climate change impacts, including variability Output 6: Targeted individual and community livelihood strategies strengthened in relation to climate change impacts, including variability Output 7: Improved integration of climate-resilience strategies into country development plans | 1 | 1.1. No. and type of projects that conduct and update risk and vulnerability assessments 1.2. Development of early warning systems 2.1.1. No. of staff trained to respond to, and mitigate impacts of, climate-related events 2.1.2. Capacity of staff to respond to, and mitigate impacts of, climate-related events from targeted institutions increased 2.2.1. Percentage of population covered by adequate risk-reduction systems 2.2.2. No. of people affected by climate variability 3.1 No. and type of risk reduction actions or strategies introduced at local level 3.2 No. of news outlets in the local press and media that have covered the topic 4.1. No. and type of health or social infrastructure developed or modified to respond to new conditions resulting from climate variability and change (by type) 4. 2. No. of physical assets strengthened or constructed to withstand conditions resulting from climate variability and change (by asset types) 5. No. and type of natural resource assets created, maintained or improved to withstand conditions resulting from climate variability and change (by type of assets) 6.1. No. and type of adaptation assets (physical as well as knowledge) created in support of individualor community-livelihood strategies 6.2. Type of income sources for households generated under climate change scenario 7.1. No., type, and sector of policies introduced or adjusted to address climate change risks 7.2. No. or targeted development strategies with incorporated climate change priorities enforced | 1.2
OBJECTIVE 4
Fund Outcome | Please select from dropdown menu below | Fund Outcome Indicator | Please select from dropdown menu below | Target at CEO Endorsement | Baseline | Mid-term Results | Terminal Results
Outcome 1: Reduced exposure at national level to climate-related hazards and threats Outcome 2: Strengthened institutional capacity to reduce risks associated with climate-induced socioeconomic and environmental losses Outcome 3: Strengthened awareness and ownership of adaptation and climate risk reduction processes at local level Outcome 4: Increased adaptive capacity within relevant development and natural resource sectors Outcome 5: Increased ecosystem resilience in response to climate change and variability-induced stress Outcome 6: Diversified and strengthened livelihoods and sources of income for vulnerable people in targeted areas Outcome 7: Improved policies and regulations that promote and enforce resilience measures | 7 | 1. Relevant threat and hazard information generated and disseminated to stakeholders on a timely basis 2.1. No. and type of targeted institutions with increased capacity to minimize exposure to climate variability risks 2.2. Number of people with reduced risk to extreme weather events 3.1. Percentage of targeted population aware of predicted adverse impacts of climate change, and of appropriate responses 3.2. Modification in behavior of targeted population 4.1. Development sectors' services responsive to evolving needs from changing and variable climate 4.2. Physical infrastructure improved to withstand climate change and variability-induced stress 5. Ecosystem services and natural assets maintained or improved under climate change and variability-induced stress 6.1. Percentage of households and communities having more secure (increased) access to livelihood assets 6.2. Percentage of targeted population with sustained climate-resilient livelihoods 7. Climate change priorities are integrated into national development strategy | 7
Fund Output | Please select from dropdown menu below | Fund Output Indicator | Please select from dropdown menu below | Target at CEO Endorsement | Baseline | Mid-term Results | Terminal Results
Output 1: Risk and vulnerability assessments conducted and updated at a national level Output 2.1: Strengthened capacity of national and regional centres and networks to respond rapidly to extreme weather events Output 2.2: Targeted population groups covered by adequate risk reduction systems Output 3: Targeted population groups participating in adaptation and risk reduction awareness activities Output 4: Vulnerable physical, natural, and social assets strengthened in response to climate change impacts, including variability Output 5: Vulnerable physical, natural, and social assets strengthened in response to climate change impacts, including variability Output 6: Targeted individual and community livelihood strategies strengthened in relation to climate change impacts, including variability Output 7: Improved integration of climate-resilience strategies into country development plans | 7 | 1.1. No. and type of projects that conduct and update risk and vulnerability assessments 1.2. Development of early warning systems 2.1.1. No. of staff trained to respond to, and mitigate impacts of, climate-related events 2.1.2. Capacity of staff to respond to, and mitigate impacts of, climate-related events from targeted institutions increased 2.2.1. Percentage of population covered by adequate risk-reduction systems 2.2.2. No. of people affected by climate variability 3.1 No. and type of risk reduction actions or strategies introduced at local level 3.2 No. of news outlets in the local press and media that have covered the topic 4.1. No. and type of health or social infrastructure developed or modified to respond to new conditions resulting from climate variability and change (by type) 4. 2. No. of physical assets strengthened or constructed to withstand conditions resulting from climate variability and change (by asset types) 5. No. and type of natural resource assets created, maintained or improved to withstand conditions resulting from climate variability and change (by type of assets) 6.1. No. and type of adaptation assets (physical as well as knowledge) created in support of individualor community-livelihood strategies 6.2. Type of income sources for households generated under climate change scenario 7.1. No., type, and sector of policies introduced or adjusted to address climate change risks 7.2. No. or targeted development strategies with incorporated climate change priorities enforced | 7.2

## Units for Indicators
Fund Outcome Indicator Units
1. Generation of relevant data, Stakeholders, and Timeliness 2.1. Include both qualitative and quantitative measures of capacity level within targeted institutions 2.2. Number (men and women and other vulnerable groups) 3.1. Use scale from 1 to 5: 5: Fully aware 4: Mostly aware 3: Partially aware 2: Partially not aware 1: Aware of neither predicted adverse impacts of climate change nor of appropriate responses 3.2. Use scale from 1 to 5: 5: All 4: Almost all 3: Half 2: Some 1: None 4.1. Summarize in an overall scale (1-5): 5: Highly responsive (All defined elements ) 4: Mostly responsive (Most defined elements) 3: Moderately responsive (Some defined elements) 2: Partially responsive (Lacks most elements) 1: Non responsive (Lacks all elements ) 4.2. Summarize in an overall scale (1-5): 5: Fully improved 4: Mostly Improved 3: Moderately improved 2: Somewhat improved 1: Not improved 5. Depends on the targeted natural asset: Biological (species): measure through changes in population numbers (dynamics, structure, etc.) Land: measure changes in hectares. Baseline data will be necessary to estimate the change. Supporting indicators baseline and target (as well as contextual information) are needed such as the following: Farmers adopting recommended technologies, Ha. of land improved, Average deforestation rate Etc. Use scale from 1 to 5. 5: Very effective (All elements are present) 4: Effective (Most elements are present) 3: Moderately effective (Some elements are present) 2: Partially effective (Most elements are not present) 1: Ineffective (No elements are present) 6.1. Summarize in an overall scale (1-5): 5: Very high improvement 4: High improvement 3: Moderate improvement 2: Limited improvement 1: No improvement 6.2. Household income by source of livelihood in project area (USD) prior and post project intervention 7. Summarize in an overall scale (1-5). 5: All (Fully integrated) 4: Most 3: Some 2: Most not integrated 1: None
Fund Output Indicator Units
1.1. Number, sector(s) and level(s) of projects or interventions in separate fields of monitoring plan 1.2. Number 2.1.1. Number of staff (male/female) of targeted institutions: a. Obtain baseline information: total number of staff from targeted institutions b. Define target 2.1.2. Number of staff (male/female) of targeted institutions: a. Obtain baseline information: total number of staff from targeted institutions b. Define target: needs to be defined by project proponents 2.2.1. Quantitative: Percentage (includes women – and other vulnerable groups – and men). Qualitative: Adequacy: include direct analysis of major areas; adequacy/effectiveness of systems or analysis of perceptions of populations and institutions. 2.2.2. Number (broken down by gender and, if possible, by vulnerable groups defined in the area of intervention) of people 3.1. Number and type (in separate columns) at local level. 3.2. Number 4.1. Number and type 4. 2. Number and type (entered in separate columns) 5. Number of interventions by type of natural asset and intervention 6.1. Number and type (in separate columns of monitoring plan) 6.2. Income sources per household; description of income source and number of households. 7.1. Number/Sector 7.2. Number; Effectiveness (see previous indicator) through enforcement level.