## Overview
Project Performance Report (PPR)
| Period of Report (Dates) | July 2016-June 2017
| Project Title: | Climate Change Adaptation Programme in Water and Agriculture in Anseba Region, Eritrea.
| Project Summary: | The objective of the project is to: ''to increase community resilience and adaptive capacity to climate change through an integrated water management and agricultural development approach in the Sub-zoba Hamelmalo and Habero, Anseba region, Eritrea.'' The Hamelmalo and Hebero sub zobas are bisected by the Anseba River. Large part of these areas has been deforested and the rugged topography is exposed to severe soil erosions reducing the top soil and making the forest and woodland regeneration difficult. The two sub regions have been identified as having vulnerable livelihood system, low agricultural productivity and ranked among the most top five zobas affected by food insecurity due increased impact of climate change and rainfall variability. This project is designed to enhance the availability of water for increased productivity and to develop the adaptive capacity of vulnerable communities by expanding small scale irrigation to increase agricultural production and to conserve water and soil through rangeland development. The project comprises of four key outcomes as follows: 1. Increased water availability and erosion control through groundwater recharge, rainwater harvesting, irrigation and soil and water conservation measures. It comprises Construction of sub-surface dam associated with pumping and irrigation water distribution facilities, construction of two micro dams to retain and store rainfall runoff and soil and water conservation measures implemented to improve runoff management and infiltration. 2. Climate resilient agricultural and livestock production enhanced. This focus on a range of climate resilient agricultural technologies and methods developed and transferred to farmers like drought and disease resistant varieties, integrated crop-livestock production system, conservation agriculture, agroforestry, rangeland management; and traditional improved fuel efficient stove. Seasonal forecast used a farmer-led collaborative action learning process to enhance adaptive capacity and climate proof production system. 3. Improved climate risk information and climate monitoring used to raise awareness and enhance community preparedness to climate change. This mainly emphasis on the improved climate risk information generated and capacity developed for climate monitoring and analysis. Awareness raised at different levels on climate change risks facing zoba Anseba 4. Knowledge management system established and knowledge management activities implemented. This component consists of establishment of knowledge management system and implementation of knowledge management activities, and implementation of policy advocacy activities.
Database Number:
Implementing Entity (IE) [name]: |  | UNDP
| Type of IE: | MIE
| Country(ies): | Eritrea
Relevant Geographic Points (i.e. cities, villages, bodies of water): |  | Hamelmalo and Habero
Project Milestones
Milestone
AFB Approval Date: |  | 2011-03-18
IE-AFB Agreement Signature Date: |  | 2011-04-26
Start of Project/Programme: |  | 2012-11-06
Mid-term Review Date (if planned): |  | 2016-03-06
| Terminal Evaluation Date: | 2018-06-06
List documents/ reports/ brochures / articles that have been prepared about the project.
Inception report Environmental Impact Assessment Field report Eritrean Journal MTR Progress Report ERITV (Eritrean Television) UNDP50Microsite Africa Page HAN@Geeskaafrika.com
List the Website address (URL) of project.
www.adaptation-fund.org
Project contacts:
National Project Manager/Coordinator
| Name: | Mr. Ghebremeskel Tewolde ( Ministry of Agriculture)
| Email: | gmt74yr@gmail.com
| Date: | 2017-08-14
Government DA
| Name: | Mr. Mogos Woldeyohannes Bairu, DG Dept. of Environment; Ministry of Land, Water and Environment
| Email: | m.bairu@gmail.com
| Date: | 2017-08-14
Implementing Entity
| Name: | Adam Habteab
| Email: | adam.habteab@undp.org
| Date: | 2017-08-14
Executing Agency
| Name: | Ali Mohammed (Governor-Anseba Regional Administration)
| Email: | Tel 401003 gmt74yr@gmail.com
| Date: | 2017-08-14
Executing Agency
Name:
Email:
Date:
Executing Agency
Name:
Email:
Date:

## FinancialData
Financial information: cumulative from project start to [insert date]
DISBURSEMENT OF AF GRANT FUNDS
How much of the total AF grant as noted in Project Document plus any project preparation grant has been spent to date?
Estimated cumulative total disbursement as of [31/06/2017] | 5315899.96
Add any comments on AF Grant Funds. (word limit=200) | As of 30 August, 2017 ,out of 881,400.00 the total allocated budget for the reporting period USD 710,147.37 (2nd quarter Expenditure 343,392.46 and 3rd quarte advance $366,754.87) has been disbursed. (81%) IP will request next advance once ASL for the remaining balance 428,350.00 (5th Tranche) established.
INVESTMENT INCOME | 8,373.48
Amount of annual investment income generated from the Adaptation Fund’s grant
EXPENDITURE DATA
List output and corresponding amount spent for the current reporting period | ITEM / ACTIVITY / ACTION | AMOUNT
| Output: 1:1 Groundwater recharged and irrigation technologies implemented for crop and forage production by developing a sub-surface dam within the Anseba River | 206667
| Out put 1.2 Floodwater harvested to enable irrigation of rain-fed cereal production and rangelands. | 12822.65
| Out Put 1.3 : Two micro dams constructed to retain and store rainfall run-off and to enable higher cereal and forage production levels as well as water supply for livestock. | 341550
| Out Put 1.4: Soil and water conservation measures implemented to improve runoff management and infiltration for improved rangeland management and enhanced cereal production. | 421666
| Out put 2:1 A range of climate-resilient agricultural technologies and methods developed and transferred to farmers | 81835
| Output 3.1 Community preparedness enhanced through development of a community-based early warning system in sub-zobas Hamelmalo and Habero | 12000
| Output 4.1Knowledge management system established and knowledge management activities implemented | 8000
| Execution Costs | 17366.65
| TOTAL | 1101907.3
PLANNED EXPENDITURE SCHEDULE
List outputs planned and corresponding projected cost for the upcoming reporting period | ITEM / ACTIVITY / ACTION | PROJECTED COST | Est. Completion Date
| Output 1.1: Groundwater recharged and irrigation technologies implemented for crop and forage production by developing a sub-surface dam within the Anseba River | 13,334.00 Preparation technical design, specification for solar irrigation technology and associated facilities in Habero and Hamelmalo. | 2018-06-01
| Output 1.2: Floodwater harvested to enable irrigation of rain-fed cereal production and rangelands. | 90,000.00 Construct small diversion systems and develop irrigation system | 2018-03-01
| Output 1.3: One micro dam will be constructed to retain and store rainfall run-off and to enable higher cereal and forage production levels as well as supply of water for livestock | 73,334.00 Construction of micro dam in Mezeret village Sub Zoba Habero, Site identification, Design and Bill of quantity completed. Mobilization of material for the construction will start end of August and Construction will start mid of September. | 2017-05-01
| Output 1.4: Soil and water conservation measures implemented to improve runoff management and infiltration for improved rangeland management and enhanced cereal production | 103,334.00 Construct hillside terraces along contours in identified locations, using stone-faced hillside terrace in Sub Zoba Habero and Hamelmalo to establish woodlots. . | 2018-06-01
| Output 2.1 Provide training and support for the construction and installation of traditional improved energy-efficient stoves | 232,396.04 Procurement of raw materials and construction of improved energy efficient stoves for 2000HH in Sub Zoba Hamelmalo and Habero | 2018-05-01
| Output 3.1: Improved climate risk information generated and capacity developed for climate monitoring and analysis | 20,000.00 Staff trained on taking meteorological readings, standardized recording and reporting at zoba and sub zoba level User-friendly knowledge dissemination products developed and disseminated using improved climate risk information. Provision of IT equipment for data collection. | 2017-05-01
| Output 3.2 Awareness raised at different levels on climate change risks facing Zoba Anseba | 20,001.00 Train community members in data collection, carry out institutional strengthening to establish community-based early warning | 2017-05-01
| Output 3.3: Community preparedness enhanced through development of a community-based early warning system in sub- | 26,668.00 Carry out a stocktaking assessment of former and existing initiatives and structures for community preparedness to climate risks and early warning systems, such as the structures established under the National Food Information System (NFIS) | 2018-05-01
| Output 4.1: Knowledge management system established and knowledge management activities implemented | 45,000.00 Design and establish a knowledge management system for the programme, based on existing processes in the Zoba Anseba administration, to be institutionalized within the administration. | 2018-05-01
| Output 4.2: Policy advocacy activities implemented | 13,333.00 Develop appropriate knowledge products, including photo stories, presentations and briefing notes, for use in policy advocacy activities | 2018-05-01
| Terminal Evaluation | 30000 | 2018-10-01
| Project Management | 26,500.00 (Operating expenses) | 2018-10-01
| TOTAL | 693900.04
ACTUAL CO-FINANCING (If the MTR or TE have not been undertaken this reporting period, DO NOT report on actual co-financing.)
How much of the total co-financing as committed in the Project Document has actually been realized?
Estimated cumulative actual co-financing as verified during Mid-term Review (MTR) or Terminal Evaluation (TE).
Add any comments on actual co-financing in particular any issues related to the realization of in-kind, grant, credits, loans, equity, non-grant instruments and other types of co-financing. (word limit=200)

## Risk Assesment
RISK ASSESMENT
IDENTIFIED RISKS
List all Risks identified in project preparation phase and what steps are being taken to mitigate them
Identified Risk | Current Status | Steps Taken to Mitigate Risk
Severe drought or other extreme weather events (HIGH) | Eritrea already has an extreme climate and adaptation project interventions are geared towards these extremes. (MODERATE) | Metrological equipment procured from both international and local market have been installed in November 2015. This infrastructure has been providing essential Climate information for managing risks especially in the agricultural and smallholder sector. Climate data interpretation and modelling using additional meteorological equipment is crucial to provide daily agromet products, early warning for extreme weather events such as floods and storms, and longer term projections for the trends in the country. Because of the weather stations and additional meteorological equipment, accuracy of forecasting has improved informing the programme activities on crop diversification, adapted seed choices, and guide activities such as rainwater harvesting, climate smart agricultural practices.
Low human and institutional capacity for the implementation of CC-related interventions. ( MODERATE) | Capacity is low for Outcome 3 of the project: climate risk information and community preparedness systems. For all other Outcomes there is sufficient expertise to implement the project. ( LOW) | Since September 2016, UNDP CO has employed an International Disaster Risk Management and Resilience Building advisor to enhance the capacity of all projects including the Adaptation Fund Programme with regards to climate risk management and Community preparedness. Through this support training was provided to eighty (80) development practitioners drawn from regional and sub-regional local governments. These trainees are in turn organizing training and capacity building programmes to their respective communities on disaster risk preparedness and management.
Failure of zoba administration to institutionalize early warning system and meteorological/climate observation components. (MODERATE) | Activities to implement the climate monitoring and risk information aspects of the project have not yet begun. However, capacities in GoE would benefit from support. ( MODERATE) | Training was provided on to government staffs 10 October 2016 at Regional level on data collection, collating and analyzing climate information. Consultation with water resource department and Ministry of Agriculture is in progress for the establishment of metrological resource center at regional level to gather climate data from the different existing weather stations.
Migration of human and livestock population under conditions of extreme severity to localities with a better natural resource base. ( LOW) | Project is intended to provide resilient livelihood opportunities for local communities which will help stem migration. ( LOW) | In addition to the two micro dams that were constructed in the preceding reporting periods, two additional micro dams were constructed during the current reporting period (November 2016--March 2017) to reduce seasonal migration of the beneficiary farming communities in search of water and pasture. The programme has continued to yield tremendous results in mitigating human and livestock seasonal outmigration by promoting irrigation and diversion scheme development. Currently, 275 farmers are practicing sedentary farming/irrigation farming with an increment of 200 farming households as compared with the preceding reporting period.
Accessibility and communications in the programme ( LOW) | For extension agents once Outcome 3 begins implementation: Off road motorbikes for extension agents and mobile phones/radio for communities (MODERATE) | The most direct road to the programme area is not convenient for motorbikes. It is highly broken and rugged. To mitigate the challenges faced by the nature of the existing road, a better alternative but a little longer road that takes to the project site is being used by deploying a 4-wheel drive vehicle.
Potential conflict with neighboring Ethiopia. ( LOW) | No war no peace' situation still prevails. (Low) | Though the issue has had repercussion on the performance of the project, the solution is beyond the scope of the project.
Shortage of feed, water and health of the dairy cows (Low) | hybrid dairy cows which are adaptive to existing climate condition of the area, were distributed to farmers (Low) | Before and after distribution of the hybrid dairy cows, beneficiary farming households were given orientation and training on the behavior of the dairy cows in terms of feeding habit, feed and shelter requirement and overall management requirement. To cope with their feed and water demand, more diversion canals and wells were constructed. A veterinary expert was assigned to support the farming communities to deal with the protective and curative health activities of the dairy cows.
Price escalation and unavailability of commodities and materials (Low) | Inflation is extremely high prices escalate by almost 40% for all construction materials and goods. The reason for inflation particularly on goods, construction materials, equipment , fuel etc. is due to the import limitation set by the government and shortage thereof of items readily available in the market. (Low) | Shortage of supply cement which constitutes a major input in construction of the irrigation facilities has been solved that the project has now secured enough cement for completion of all micro-dams and downstream canal development. The cement was supplied by the Red Sea Corporation (a parastatal procurement agency) and the price of the cement was very low than what is in the open market. Moreover, to avoid high prices for all other items to be procured, the project has made all necessary preparation in terms of identifying items to be procured for the year and preparing exhaustive Bill of Quantity for proper sourcing and competitive price.
Delays in programme implementation, particularly for infrastructure. - Unavailability of cement is a bottleneck for preceding the construction works. - Lack of machinery - (Low) | The budget of the project was released during the rainy season which was not convenient to implement the proposed dam construction. It's opted to transfer the budget allocated for 2015 to 2016 (Low) | AWP for this year (2017) was approved and signed in April which led to delayed start of project activities for the year. However, there has been significant improvement in terms of cash transfer that the duration has been shortened to maximum of two weeks to reach the project. Moreover, cement supply problem was solved and the project managed to secure 1,500 ton of cement which is being used for the planned micro-dam infrastructures. Some of the cements will also be used next year for similar irrigation infrastructure related construction activities.
Critical Risks Affecting Progress (Not identified at project design)
Identify Risks with a 50% or > likelihood of affecting progress of project
Identified Risk | Current Status | Steps Taken to Mitigate Risk
Groundwater level dropping and salinization of wells leading to potential scarcity and competition, possibly leading to conflict (Low) | Ground water recharged and salinization of the wells reduced (Low) | In order to further increase the groundwater recharge, additional two new micro dams were constructed during this reporting year (November 2016--March 2017) . Moreover, renovation of old wells and construction of additional diversion structures have been accomplished. Significant soil and water conservation activities on the upper catchment of the dams and wells have been done to protect soil erosion, and to allow improved percolation of the run offs by slowing down its velocity.
Risk Measures: Were there any risk mitigation measures employed during the current reporting period? If so, were risks reduced? If not, why were these risks not reduced?
Add any comments relevant to risk mitigation (word limit = 500)
Several mitigation measures have been employed related to mitigating price escalation, and reducing the duration (delay) of cash transfer to the project site. For instance, the project was able to secure enough cement supplies from government cement factory through Red Sea Corporation at highly reasonable price. Cash transfer delays have been significantly reduced thanks to the proactive negotiation of the project holders with concerned decision makers and the bank.

## Rating
RATING ON IMPLEMENTATION PROGRESS
For rating definitions please see bottom of page.
| Progress on Key Milestones |  | Expected Progress |  | Progress to Date |  | Rating
Project Manager/Coordinator: | 1.1: Groundwater recharged and irrigation technologies implemented for crop and forage production by developing a sub-surface dam within the Anseba River |  | Sub-surface dam with pumping and irrigation water distribution facilities completed. Forage production per ha on irrigated land increased. |  | As per the Prodoc, a sub-surface dam was planned to be constructed in the Anseba River in sub zoba Hamelmalo. However, this output is now modified based on the beneficiaries request to be changed from sub-surface to micro-dam structure. The beneficiaries argued that a sub-surface dam would serve only a limited number of farmers who already have wells and pumps and are engaged in horticultural production. Accepting the demand of the local communities, the project is doing preparation for construction of one micro-dam in Sub Region Habero with a capacity of 250,000 cubic meter is also underway. Pre-construction activities such as site identification, technical design and bill of quantity have been completed. Mobilization of construction materials for the planned micro-dam is set to start by end of August and the construction works will start in mid of September 2017. The dam will be completed between December 2017 and January 2018. |  | HS
| Output 1.3: Two micro dams constructed to retain and store rainfall run-off and to enable higher cereal and forage production levels as well as water supply for livestock. |  | 1.3.4: Complete construction of the micro dams and develop manual on operation and maintenance of the irrigation structures and pumps (two micro dams and one check dam) |  | As continuation of the preceding years to improve water retention systems and thereby to further enhance adaptation to climate change of the beneficiary communities within the project area two-micro-dams with a total capacity of 1.0 million cubic meter have been constructed in Bashari village sub zoba Hamelmalo during the reporting year. These micro-dams will help to slow down runoff and recharge the aquifers within the local water resources system. Moreover, they will serve as an importunate investment in a watershed protection that produces benefits to the local communities. The micro-dams will retain rainwater/runoff, providing water for agricultural/irrigation and domestic usages; while recharging groundwater resources and creating a cooler local micro climate. The micro-dams will support farmers to use the critical water and soil resources to intensify their production, earn greater incomes, and increase the likelihood that they can remain on their land rather than move in search of water and forage elsewhere. Construction of the micro-dams apart from adapting to climate change is a strategy to increase agricultural productivity and manage watersheds to benefit the local communities. These two reservoirs have a capacity to irrigate more than 100ha of agricultural land and to provide water for both households and livestock. The micro -dams are expected to further boost groundwater recharge and irrigation development in the programme area and benefit at least additional 200 faming households within the programme area. Climate smart agricultural production technologies like solar irrigation and IMAP will be installed in the two micro-dam infrastructures. Design, specification and bill of quantity for the procurement of solar pumps and accessories is completed. To ensure long term sustainability of the development work and to enhance communities’ adaptation and resilience to climate change, farmers have established water users’ association to manage and coordinate equitable and efficient irrigation water use. Preparation for construction of one micro-dam in Sub Region Habero with a capacity of 250,000 cubic meter is also underway. Pre-construction activities such as site identification, technical design and bill of quantity have been completed. Mobilization of construction materials for the planned micro-dam is set to start by end of August and the construction works will start in mid of September 2017. The dam will be completed between December 2017 and January 2018. |  | HS
| Output 1.4: Soil and water conservation measures implemented to improve runoff management and infiltration for improved rangeland management and enhanced cereal production. |  | Tree nursery daily workers recruited and seedlings production materials supplied. Site for soil and water conservation identified and conservation structure designed. |  | As part of the ongoing endeavor to protect and conserve the local environment, 13Km of terraces, 1125 cubic meter of check-dams and 90,000 pits have been prepared. Construction of these soil and water conservation will help to restore degraded soils by slowing or preventing the rapid surface runoff. Moreover, by reducing the speed of water ﬂow, it retains sediments and provide a supply of good quality, well-filtered water. As part and parcel of the physical measures, 50,000 seedlings of Acacia species were planted to restore and conserve the upper catchment of the newly built micro-dam in Hamelmalo area (Bashari). Likewise, 40,000 sisal tree species were planted in Habero area to restore and conserve the degraded landscape. Apart from conservation value, sisal tree species have high economic value to the local communities. These biophysical measures will ultimately contribute towards enhancing communities’ adaptation and resilience to climate change. The local communities actively participated in the planning and implementation of this soil and water conservation activities. A total of 214 community members have participated in this soil and water conservation activities out of which 30% were women. |  | S
| 2.1 A range of climate-resilient agricultural technologies and methods developed and transferred to farmers |  | Farmlands for the implementation of climate-resilient agriculture technologies and methods assessed and selected. Beneficiaries of this scheme identified. Livestock breed and seeds adaptation survey conducted. |  | To enhance adaptation capacity and resilience to climate change of the local communities some agricultural and renewable energy source technologies were distributed during the reporting period. As part of this climate resilience building, 100 beehives have been distributed to 50 farmers in sub zoba Habero and Hamelmalo. This provision will support beneficiaries to improve their food and nutrition security and provide additional income to the households. 750 Solar powered home lighting apparatus have also been delivered to the project site. These home lighting systems will benefit 750 households in Sub Zoba Habero and Hamelmalo areas. Installation of these apparatus has already begun and will be completed by end of October 2017. The home lighting technologies are intended to improve the living condition of the farming communities and contribute towards combating climate change. In collaboration with research department of the Hamelmalo Agricultural College, about 20 tones of climate-resilient seeds (improved heat tolerant seeds) have been distributed to farmers in the project area. This is aimed at improving livelihood and resilience of the local communities. Improved crop varieties which includes maize, sorghum, millet, fruits (mangoes, lemon and banana), vegetables (tomatoes and onions) and forage crops (alfalfa) have been distributed to 100 farmers. |  | S
|  |  | 2.1.4 Provide training and support for the construction and installation of traditional improved energy efficient stove and renewable energy |  | As part of the project’s effort to expand improved energy access by the local communities, 2000 energy efficient stoves are planned to be distributed to 2000 households. Specification and bill of quantity (BoQ) for the procurement of raw materials for the construction of these stoves is underway.
| 3.3 Community preparedness enhanced through development of a community-based early warning system in sub-zobas Hamelmalo and Habero |  |  |  | Metrological stations have been installed in the preceding years of development of the project aimed at strengthening communities’ awareness on the knowledge base of climate risk and the early warning chain of climate change trends, seasonal forecasts and weather alerts Nevertheless, the data collection, management and analysis are not robust enough as project climate expert is not yet on the ground. To try to fill this gap to some extent, a Five-days Training on data collection and other meteorological subjects were provided to government staffs in collaboration with water resource department of the Ministry of Land, Water and Environment.
| 4.1 Knowledge management system established and knowledge management activities implemented |  | Training modules identified and designed with technical support from Hamelemalo Agricultural College. |  | In order to build farmers’ knowledge, enhance their adaptation and resilience capacity to climate change and improved production practices, a five-day training workshop was provided to 100 farmers drawn from each kebebis/districts of sub-zobas Habero and Hamelmalo. The training focused on agricultural constraints in general and climate change related challenges faced by the local farming communities. Moreover, the focus was also seeking possible solutions, adopting climate smart agricultural practices and the relationship between farming communities and the research objectives and activities of Hamelmalo Agricultural College. 25 extension agents were also part of the aforementioned training, experience sharing and discussion the training workshop. |  | s
| 4.2 Policy advocacy activities implemented |  |  |  | Not included in the signed AWP of 2016
[5 empty] | Overall Rating | S | S
Please Provide the Name and Contact information of person(s) responsible for completing the Rating section
| Name: | Gebremeskel Tewolde (National Project Coordinator)
| Email: | anejigna@yahoo.com
My assessment is that the project has been able to achieve very good results particularly in mitigating the adverse effect of water stress within the programme/project area that is characterized by arid- and semi-arid climatic conditions. To date three dams and one diversion structures have been constructed which helped local communities to conserve/harvest flood water and use it for their agricultural activities. The local farming communities have been able to conserve and store adequate water for crop production and livestock. Productivity per hectare has increased from 5 -10 tons. Likewise, animal productivity has shown significant improvement. A total of 98ha of land that had been previously abandoned land has been put back under irrigated agriculture. The crops are grown included: maize, sorghum, millet, fruits (mangoes, lemon and banana), vegetables (tomatoes and onions) and forage for animals (alfalfa, elephant grass). Under the minimum integrated agricultural package, 50 women headed households were provided with a package of 1 dairy cow, 25 chickens and 2 beehives to each of them. About 18.8 tons of improved drought tolerant seeds have been distributed to farmers in the project area. Moreover, the ongoing soil and water conservation and natural resource management work have significantly contributed to enrichment of local groundwater resources. Consequently, the local communities are increasingly benefiting from the enrichment of the groundwater in the form of water supply for domestic use, livestock and irrigation water. 750 Solar powered home lighting apparatus have been procured and delivered to the project site. These home lighting systems will benefit 750 households in Sub Zoba Habero and Hamelmalo areas. Installation of these apparatus will be completed by end of October 2017. Moreover, as part of the project’s effort to expand improved energy access by the local communities, 2000 energy efficient stoves are planned to be distributed to 2000 households. Specification and bill of quantity (BoQ) for the procurement of raw materials for the construction of these stoves is underway. Overall the project has been able to execute 90% of the activities of the annual work plan for the reporting period (2016/17).
Please justify your rating. Outline the positive and negative progress made by the project since it started. Provide specific recommendations for next steps. . (word limit=500)
| Progress on Key Milestones |  | Expected Progress |  | Progress to Date | Rating
| According the annual work plan, the project has achieved much physical work activities. |  | In 2015, the project will have a variety of activities from all its planned outputs and much more tangible results are expected to be achieved by timely implementation and active collaboration of key stakeholders. |  | In 2017/18, the programme is implementing and will continue to execute different development activities based on its objectives and activities. As the project is progressing towards its ending of operational activities, efforts by the key stakeholders and local communities will be further enhanced and more coordinated for a smooth completion of the project. I have visited the project area and observed that the project has been able to accomplish impressive work during the reporting period. Moreover, it is assessed that the project has executed about 90% of the annual work plan development activities. To mention some of the major activities accomplished: 1. Two micro-dams with a total capacity of 1,000,000M3 have been constructed in Bashari village Sub Zoba Hamelmalo. These dams are expected to irrigate more than 100ha of new agricultural land and provide all year-round water supply to 200HH for domestic and livestock use. The dam has a capacity to irrigate more than 100ha of agricultural land and water for both households and livestock. The dams are expected to further boost groundwater recharge and irrigation development in the programme area. Improved crop varieties which includes maize, sorghum, millet, fruits (mangoes, lemon and banana), vegetables (tomatoes and onions) and forage crops (alfalfa) have been distributed to 100 farmers. 2. Moreover, activities related to site identification, technical design and bill of quantity for the construction of another new micro dam with a capacity of 250,000M3 in Sub Region Habero have been completed. Mobilization of construction materials for the planned micro-dam is set to start by end of August and the construction works will start in mid of September 2017. The dam will be completed between December 2017 and January 2018. 3. During the reporting period, around 90,000 Acacia and Sisal tree species were planted to restore and conserve the upper catchment of the newly built micro-dam in Hamelmalo area (Bashari). The local communities actively participated in the planning and in this soil and water conservation activities. A total of 214 community members have participated in this soil and water conservation activities out of which 30% were women. 4. As part of the ongoing Minimum Integrated Agricultural package component of the programme, 100 beehives have been distributed to 50 farmers in sub zoba Habero and Hamelmalo during this reporting period. This provision is aimed at promoting household food security of the beneficiaries. 5. 750 Solar powered home lighting apparatus have been procured and delivered to the project site. These home lighting systems will benefit 750 households in Sub Zoba Habero and Hamelmalo areas. Installation of these apparatus will be completed by end of October 2017. 6. Moreover, as part of the project’s effort to expand improved energy access by the local communities, 2000 energy efficient stoves are planned to be distributed to 2000 households. Specification and bill of quantity (BoQ) for the procurement of raw materials for the construction of these stoves is underway. | S
Implementing Agency
S
Please Provide the Name and Contact information of person(s) responsible for completing the Rating section
| Name: | Adam Habteab (UNDP)
| Email: | adam.habteab@undp.org
| Progress on Key Milestones |  | Expected Progress |  | Progress to Date | Rating
| I have been closely monitoring its implementation. I have found out that the project has done well and achieved its intended results. |  | Selected outcomes as per the AWP of the project will be realized and the project will hit its goals. |  | 1. Design and construction of Dams, micro dams, diversion structures, well renovations and installation of solar pumps for irrigation, 2. Installation of home lighting for 750 households will be accomplished by end of October 2017 3. Dissemination of improved energy efficient stoves, 4. Soil and water conservation, afforestation activities, enclosure protection activities, etc. were undertaken. 5. Implementation of minimum integrated agricultural package and its modality in the project sites in the sub zoba Hamelmalo and Habero. | S
Other
[5 empty] | Overall Rating | S
Please Provide the Name and Contact information of person(s) responsible for completing the Rating section
| Name: | Ali Mohammed (Governor-Anseba Regional Administration)
Email:
| Please justify your rating and address the following points: 1. Indicate trends, both positive and negative, in achievement of outcomes as per the project indicators. 2. Detail critical risks that have affected progress. 3. Outline response to MTR undertaken this reporting period. 4. Outline action plan to address projects with a rating of HU, U or MU. Please keep your input to 1200 words |  | My assessment of the project is very positive. Though the project had started late in July 2012, the progress made to date is very satisfactory. I observe high dedication on the part of the project implementers including project staff and other key stakeholders. In my view, the project has already demonstrated that it can be a model that can potentially be replicated and up-scaled. I am confident that the project will be able to accomplish all its outcome objectives in the coming year.(Governor’ letter was translated from Tigrigna/local language)
Rating Definitions
|  |  | Highly Satisfactory (HS) | Project actions/activities planned for current reporting period are progressing on track or exceeding expectations to achieve all major outcomes/outputs for given reporting period, without major shortcomings. The project can be presented as “good practice”.
|  |  | Satisfactory (S) | Project actions/activities planned for current reporting period are progressing on track to achieve most of its major outcomes/outputs with only minor shortcomings.
|  |  | Marginally Satisfactory (MS) | Project actions/activities planned for current reporting period are progressing on track to achieve most major relevant outcomes/outputs, but with either significant shortcomings or modest overall relevance.
|  |  | Marginally Unsatisfactory (MU) | Project actions/activities planned for current reporting period are not progressing on track to achieve major outcomes/outputs with major shortcomings or is expected to achieve only some of its major outcomes/outputs.
|  |  | Unsatisfactory (U) | Project actions/activities planned for current reporting period are not progressing on track to achieve most of its major outcomes/outputs.
|  |  | Highly Unsatisfactory (U) | Project actions/activities planned for current reporting period are not on track and shows that it is failing to achieve, and is not expected to achieve, any of its outcomes/outputs.

## Project Indicators
PROJECT Indicators
Please provide all indicators being tracked for the project as outlined in the project document
Type of Indicator (indicators towards Objectives, Outcomes, etc.…)
Type of Indicator | Indicator | Baseline | Progress since inception | Target for Project End
Outcome 1 | Outcome indicator: Change in level of renewable water resources used in programme area Indicator 1.1.1: Sub-surface dam with associated pumping and irrigation water distribution facilities completed Indicator 1.1.2: Number of households of agropastoralists using the water supply to increase their agricultural and rangeland productivity by twenty-fold Indicator 1.2.1: Number of hectares of rangeland that become fully under supplementary irrigation and have an increased productivity of 40% Indicator 1.2.2: Number of hectares of cereal production that are converted to be fully under supplementary irrigation Indicator 1.2.3: Number of hectares of the dominant cereal crops (sorghum and pearl millet) that have an increased production of from 0.36 (baseline) tons per hectare to 0.7 tons per hectare Indicator 1.3.1: Number of hectares of cereal production that is converted to be fully under supplementary irrigation and in which the production of the dominant cereal crops (sorghum and pearl millet) is increased from 0.36 tons per hectare (baseline) to 1.0 tons per hectare Indicator 1.3.2 Increase in forage production per ha of irrigated land. Indicator 1.3.3: Amount of time spent in search of water and forage for livestock. Indicator 1.4.1: Livestock carrying capacity of rangelands under this protection and rehabilitation programme Indicator 1.4.2: Agricultural production of farm lands under the on farm soil and water conservation programme Indicator 1.4.3: Percentage of households migrating to other areas due to climatic shock | Only about 1 Million cubic meters is put in use. 1)Integrated water/agriculture adaptation actions are not implemented, Eritrea’s rural areas will continue to experience increasing vulnerability and growing insecurity, due to decreased availability of water and conflicts between crop and livestock uses. This will damage the social fabric in rural areas. 2)Communities in the two zobas have serious shortage of water supply. | 2016--One micro-dam with a total capacity of 1,000,000M3 has been constructed in Bashari village Sub Zoba Hamelmalo ( Out put Indicator 1.1.1). The dam is expected to irrigate more than 100ha of new agricultural land and provide all year-round water supply to 200HH for domestic and livestock use. The dam has a capacity to irrigate more than 100ha of agricultural land and water for both households and livestock (Out put Indicator 1.2.1). The dam is expected to further boost groundwater recharge and irrigation development in the programme area. Through the ongoing expansion of irrigation facilities including construction of a new micro-dam, additional 100 ha of new farmlands are expected to made available for irrigation development that would benefit at least 200 faming households. Improved crop varieties which includes maize, sorghum, millet, fruits (mangoes, lemon and banana), vegetables (tomatoes and onions) and forage crops (alfalfa) have been distributed to 100 farmers ( Out put Indicator 1.3.1). *Moreover, activities related to site identification, technical design and bill of quantity for the construction of another new micro dam with a capacity of 250,000M3 in Sub Region Habero have been completed. Mobilization of construction materials for the planned micro-dam is set to start by end of August and the construction works will start in mid of September 2017 (Output Indicator 1.1.1). The dam will be completed between December 2017 and January 2018. *During the reporting period, around 90,000 Acacia and Sisal tree species were planted to restore and conserve the upper catchment of the newly built micro-dam in Hamelmalo area (Bashari). The local communities actively participated in the planning and in this soil and water conservation activities. A total of 214 community members have participated in this soil and water conservation activities out of which 30% were women. *As part of the ongoing Minimum Integrated Agricultural package component of the programme, 100 beehives have been distributed to 50 farmers in sub zoba Habero and Hamelmalo during this reporting period. This provision is aimed at promoting household food security of the beneficiaries. *750 Solar powered home lighting apparatus have been procured and delivered to the project site. These home lighting systems will benefit 750 households in Sub Zoba Habero and Hamelmalo areas. Installation of these apparatus will be completed by end of October 2017. 2015 - As continuation of solar installation diversion extension works completed to irrigate additional 25ha (Total 75ha)of land which is situated in sub zoba Habero particularly in fiza, a reservoir with a capacity of 314 M3 is constructed and HDPE pipe with all accessories purchased. Around 2.25 Km of 90mm pipe has been lied in the main canal of the farm. By the end of 2015, the project had constructed 2 micro-dams and 1 diversion structure to enhance renewable water resources used in programme area. This year, additional 1 micro-dam and one sub-surface dam will be built. These water harvesting structures are believed to significantly contribute towards enriching the renewable water resources in the area and meeting the project target by the end of the project cycle. 2014 - Environmental Impact Assessment and social/Economic/ Environmental baseline study (BLS) conducted and final report submitted. Workshop organized on 04/11/2014 to review , discuss and finalized the report. Stakeholders from Min of Land, Water and Environment, Min of Agriculture, Sub Region Administration, UNDP and Hamelmalo Agricultural College participated in the workshop. Construction of Diversion Structure: In two sites of sub zoba Habero (Fiza and Lemayeta) started, 90% of the proposed activities completed. A diversion weir completed ( Weir dimension 132M long, 5.7M wall height, 3.2M depth, 3.15M width). Besides 306 Meters of canal constructed in two diversion area 136 Lemayeta and 170M Fiza) 8 diversion gates with a dimension of 2M*1.5M and pointing of structure underway. This diversion structure serve to supply water for irrigating 124ha (200HH). | 5.3 million cubic meters of renewable water resources used in programme area (an increase of 4.3 million m3). Achieved by building two micro dams constructed to retain and store rainfall run-off and to enable higher cereal and forage production levels as well as supply of water for livestock.
2014- As part of promoting irrigation scheme a full set of solar irrigation has been installed to irrigate 50ha of land. Two solar pumps with a capacity of 7.5kw each 48 modules of 180-watt capacity with all accessories were installed to generate power.10rolls of HDPE pipe with 90mm, 100m length a total of 1000M pipe. Gil pipe total length of 300M, 10 rolls ,33mm ,700M cable with 35M3 and 1000M is buried in order to protect the solar array from any damage and human interference. This system has significantly contributed to reduce farm expenses in terms of fuel cost and consumption.
Technical Design and bill of quantity completed. A bid document is prepared and submitted to bidders.
Two micro dams with a capacity of 320,000m3 have been constructed . The dams provided access of water for livestock and human and enrichment of the ground water ( Output Indicator 1.1.1).
Outcome2 | Outcome indicator: Change in food security in the programme area as a result of using climate resilient agricultural and livestock production methods, measured as# of months per year additionally covered by local production Indicator 2.1.1 Number of project beneficiaries involved in capacity development for implementation of specific agricultural and/or livestock adaptation measures, disaggregated according to gender Indicator 2.1.2: Number of professionals involved in capacity development to enable rolling out of climate-resilient agricultural production technologies and methods, disaggregated according to gender Indicator 2.1.3: Percent change in beneficiaries’ capacities to make resource management decisions based on climate information Indicator 2.1.4: Increased agricultural and livestock production as a result of implementing climate-resilient technologies and methods Indicator 2.1.5: Number of improved traditional energy-efficient stoves distributed and in regular use Indicator 2.2.1: Number of farmers using seasonal forecasts to develop on-farm adaptive strategies Indicator 2.2.2: Increased production and farm income as a result of using seasonal forecasts to guide on-farm activities | Sub Zoba Hamelmalo and Habero ranked the top five (out of 11) most affected zobas by food insecurity due to increased impact of climate change. | 2016- a water well which serves as water source for irrigation in fiza was renovated and desilted to improve the water capacity of the well. Under the minimum integrated agricultural package, 10 dairy cows in Habero and 9 dairy cows in Hamelmalo were distributed to new round of beneficiaries bring the number of beneficiaries of this scheme to 69 households (Output Indicator 2.1.4). As part of household income and nutrition enhancement through the minimum integrated agricultural package, 50 dairy cows and 50 milking cans, 25 chickens, 2 beehives, citrus, vegetable seeds, moringa tree and other forage trees were distributed to 50 households in Habero and Hamelmalo (Output Indicator 2.1.4). A secondary canal within existing diversion canals was constructed that helped to increase the total # of hectares by 50%. Most of the crops, fruits, vegetables grown in the area are in good condition. Farmers have continued to sell surplus production in the local market. Improved seeds of onion, okra, maize, pumpkin, lemon, tomato, were distributed to the local farmers. Moreover, 33.9 tons of improved seeds of pearl millet and sorghum were distributed to the local farmers in sub-zoba Hamelmalo and Habero. It is estimated that the productivity of crops to have increased by at least 20%. | 70% of programme beneficiaries have sufficient food for at least an additional three months per year
Outcome 3 | Percentage of programme beneficiaries making use of improved climate risk information and climate monitoring processes, disaggregated according gender Indicator 3.1.1: Downscaled climate change projections at the sub-national scale from multiple GCMs for Zoba Anseba Indicator 3.1.2: Number of gender-sensitive knowledge products developed and disseminated using improved climate risk information Indicator 3.1.3: Class 1 meteorological station installed in sub-zoba Habero and six Class 3 meteorological stations installed, three in each sub-zoba Indicator 3.1.4: Number of staff trained on meteorological observation and analysis, disaggregated according to gender Indicator 3.2.1: Number of stakeholders participating in awareness raising events, disaggregated according to gender and age where possible Indicator 3.2.2: Perceived change in decision making as a result of participation in awareness raising activities Indicator 3.3.1: Number of community members trained on EWS Indicator 3.3.2: Number of stakeholders served by community-based EWS Indicator 3.3.3: Losses resulting from climate-related disasters (e.g. mortality, injury, property or infrastructure lost or damaged) compared with recent historical experience or projected baseline, in the area served by the community-based EWS | No improved climate risk information available yet. | Installation of six meteorological station completed with the help of Met. Experts from WRD and civil aviation. Two manual meteorological station were installed in Hamelmalo Agricultural College and Hagaz Agro-technical School. While four Automatic manuals were installed in 4 sub zobas (Habero, Keren, Aditekelizan and Geleb). Observers for the manual station have been assigned and data are regularly collected (Output Indicator 3.1.3). | 70% of the communities will make use of improved climate risk information
Outcome 4 | Number of lessons learned and natural resource management in the context of climate change as a result of the programme. Indicator 4.1.1: Number of ‘lessons learned’ codified Indicator 4.1.2: Number of relevant networks or communities through which lessons learned are disseminated Indicator 4.2.1: Number of knowledge products developed for use in policy advocacy activities Indicator 4.2.2: Number of policies/plans/strategies/programmes revised or developed as a result of policy advocacy activities | No relevant lessons learned are being captured or disseminated. | 10 days training of GIS projection and mapping was given in collaboration with Hamelmalo Agriculture college for 20 Experts. The trainees were drawn from Department of Agriculture & land, Department of infrastructure, Dep. Information and mapping of Annseba region & Dap. of finance and Administration. The training was a mixture of theoretical and practical activities (Output Indicator 4.1.2). To share the experience of the farmers, extension agents & researchers, farmer’s day was conducted. The field day was conducted in collaboration with NARI, HAC, MoA of Anseba region. 42 farmers from the sub zoba Habero and 30 experts from NARI, HAC, MoA zoba & Sub zoba& MoLWE – Dept. of environment participated. Germination and purity test conducted by Hamelmalo Agricultural College laboratory and from the analysis a good result is obtained (96% purity and 95% germination for sorghum and 90% purity and 92% germination for pearl millet). This will reduce future crop failure in the sub-zoba's. A seed committee comprised of from Hamelmalo college of Agriculture, Min of Agriculture, Agronomists, representative of regional Administration established to undertake assessment (Output Indicator 4.1.1). | At least five lessons learned codified and disseminated

## Lessons Learned
QUALITATIVE MEASURES and LESSONS LEARNED
Please complete the following section every reporting period
Implementation and Adaptive Management | Response
What implementation issues/lessons, either positive or negative, affected progress? | 1. As no climate expert has so far been deployed at zoba level to serve the project, the meteorological data collected are not being utilized to the fullest possible. This has put limitation in terms of analyzing the climate change impact vis-à-vis the technologies that are being implemented in the project area to support the local farming communities towards robust adaptation to climate change. 2. Delays in approval of AWP as well as cash transfer from the bank to the project account have been identified as major obstacles for project implementation as scheduled. To try to mitigate these problems, negotiations are being carried out with the ministry of National Development, and ministry of Land water and Environment. to find out ways and means on how the Department of Water Resources can provide meteorological related technical support through providing training and continuous advisory to the project.
Were there any delays in implementation? If so, include any causes of delays. What measures have been taken to reduce delays? | There were delays in implementation which are largely attributed to: late approval/signing of AWP (May 2015) and excessive delays in cash transfer (long cash transfer procedure). MND and other key ministries and the banks were made aware of these problems and efforts were made to engage them to mitigate the problem. Very limited availability of cement and machinery were also other bottlenecks for the implementation particularly related to activities that involve construction. Due to shortage of supply of machinery service some of the excavation work had to be executed manually slowing the pace of some of the activities. Government institutions and reginal government decision makers were approached to help solve these limitations. These engagements have helped to solve the problem to great extent. As no climate expert, has so far been deployed at zoba level to serve the project, the meteorological data collected are not being utilized to the fullest possible. This has put limitation in terms of analyzing the climate change impact vis-à-vis the technologies that are being implemented in the project area to support the local farming communities towards robust adaptation to climate change. This problem has been explained to the Ministry of Land Water and Environment and the project is continually requesting for a deployment of climate expert.
Describe any changes undertaken to improve results on the ground or any changes made to project outputs (i.e. changes to project design) | 1. Establishment of farmers association for each project sites/villages. 2. Coordination mechanism with national research institutions developed for promotion of new agricultural innovations which contributes to increase agricultural production and improve the livelihood of the community.
How have gender considerations been taken into consideration during the reporting period? What have been the lessons learned as a consequence of inclusion of such considerations on project performance or impacts? | Compliance of the project with Equal Opportunity Act is mandatory as per Government legal framework. Focus on Gender has been fully integrated into project activities through involvement of women in the project activities like construction of energy-saving stoves as an opportunity for the women to generate income and save money and time. In order to provide quality nutrition to the local communities, the project has been implementing Minimum Integrated Agricultural Package which comprises provision of dairy cows, chickens, bee hives, and seeds to grow fruit crops, vegetables. About 37% of the beneficiaries are women headed households. Local women's associations have been actively involved in the implementation of the project.
Please complete the following section at mid-term and project completion
Lessons for Adaptation | Response
Climate Resilience Measures
What have been the lessons learned, both positive and negative, in implementing climate adaptation measures that would be relevant to the design and implementation of future projects/programmes for enhanced resilience to climate change?
What is the potential for the climate resilience measures undertaken by the project/programme to be replicated and scaled up both within and outside the project area?
Concrete Adaptation Interventions
What have been the lessons learned, both positive and negative, in implementing concrete adaptation interventions that would be relevant to the design and implementation of future projects/programmes implementing concrete adaptation interventions? | Mid-term evaluation has been carried out in July 2017 that established the lessons to be learnt. However, the few lessons learnt are as follows: 1. Community based projects is very crucial for successful implementation and sustainability of projects. 2. The country needs to train and have adequate number of qualified MET/climate experts to respond to the existing gap in this field. This makes even important as the impact of climate change is emerging as an important development challenge in the country. 3. To ensure sustainability of improved/drought tolerant seed supply establishment of village based seed multiplication and seed bank is very crucial and this can be done in collaboration with national agricultural research institute, Hamelmallo Agricultural College, Ministry of Agriculture and other relevant institutions. 4. Minimum Integrated Agricultural package is one of the core strategies for the implementation of intensive agricultural development to improve the livelihood of the community. the modality of the package is pass on system which promotes the sustainability of the project.
What is the potential for the concrete adaptation interventions undertaken by the project/programme to be replicated and scaled up both within and outside the project area? | The project interventions were unique and have resulted to admirable progress in the project area. The pilot project is referred as the UNDP model. It has been already asked by the regional administration that technical teams to familiarize themselves with the project for upscaling and replication throughout the region.
Community/National Impact
What would you consider to be the most successful aspects for the target communities? | Creation of strong sense of ownership among the communities. Minimum integrated Agricultural package is the most successful aspect of the project as it ensures food and nutrition security by providing a dairy cow, fruit trees, forage, vegetables, fuel wood, improved stoves for one household with in half hectare.
What measures are/have been put in place to ensure sustainability of the project/program results? | Establishment of development committees and full participation/ownership of beneficiaries community. Presence of trained agricultural extension agents in the project area.
What measures are being/could have been put in place to improve project/program results? | Capacity development in early warning system and strengthening extension system.
Knowledge Management
How has existing information/data/knowledge been used to inform project development and implementation? What kinds of information/data/knowledge were used? | Through Farmer to Farmer and community champions, sharing experience meetings were conducted to raise awareness on the importance of the adaptation programme, to create a strong sense of ownership among communities and to build appropriate technologies to increase productivity at farm level.
If learning objectives have been established, have they been met? Please describe. | No learning management system or coordination mechanism has been established
Describe any difficulties there have been in accessing or retrieving existing information (data or knowledge) that is relevant to the project. Please provide suggestions for improving access to the relevant data. | Unavailability of climate expert at zoba level to collect data from MET stations has influenced hitting the objective of the project. Consultation is underway with water department of the Ministry of Land Water and Environment to provide training to regional administration and concerned ministry staffs. The climate expert is to support the community in upgrading their resilience and adaptive capacity to climate change and sustainability of the project.
Has the identification of learning objectives contributed to the outcomes of the project? In what ways have they contributed? | Trainigs on climate resilient provided to farmers/ extension agents and research support by Hamelmalo Agricultural College has contributed to ensure sustainablity and increase productivity.

## Results Tracker
Results Tracker for Adaptation Fund (AF) Projects
Goal: Assist developing-country Parties to the Kyoto Protocol that are particularly vulnerable to the adverse effects of climate change in meeting the costs of concrete adaptation projects and programmes in order to implement climate-resilient measures. Impact: Increased resiliency at the community, national, and regional levels to climate variability and change.
Important: Please read the following guidance document (also posted on the Adaptation Fund website) before entering your data
Link: http://www.adaptation-fund.org/sites/default/files/Results%20Framework%20and%20Baseline%20Guidance%20final.pdf
Adaptation Fund Strategic Results Framework
Project ID | 00061576 (PIMS 4540)
Implementing Entity | UNDP
Type of implementing entity | MIE
Country | Eritrea
Region | Africa
Sector | Multi-sector
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Impact: Increased resiliency at the community, national, and regional levels to climate variability and change | Core Indicator: No. of beneficiaries |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project
|  | Total | 67500 | 27000 | 40500 | Total | 45500 | 12595 | 32905 | Total | 35000 | 10000 | 25000 | Total
|  | % of female beneficiaries | 48% | 22.2% | 25.8% | % of female beneficiaries | 40% | 24% | 16% | % of female beneficiaries | 76% | 22% | 54% | % of female beneficiaries
|  | % of Youth beneficiaries | 47% | 18.6% | 28.4% | % of Youth beneficiaries | 56% | 15.5% | 40.5% | % of Youth beneficiaries | 56% | 15.5% | 40.5% | % of Youth beneficiaries
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 1: Reduced exposure to climate-related hazards and threats | Indicator 1: Relevant threat and hazard information generated and disseminated to stakeholders on a timely basis | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness
|  | Total | 200 | Drought | 2: Partially effective | Total | 1200 | Drought | 3: Moderately effective | Total | 748 | Drought | 4: Effective | Total
|  | % of female targeted | 32% |  |  | % of female targeted | 38% |  |  | % of female targeted | 34% |  |  | % of female targeted
Output 1.1 Risk and vulnerability assessments conducted and updated | Indicator 1.1: No. of projects/programmes that conduct and update risk and vulnerability assessments | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
Output 1.2 Targeted population groups covered by adequate risk reduction systems | Core Indicator 1.2: No. of Early Warning Systems | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard | Drought | No. of adopted Early Warning Systems | Category targeted | Hazard | Drought | No. of adopted Early Warning Systems | Category targeted | Hazard
|  | 1 | 3: Dissemination and communication | Geographical coverage | Regional | 5 | 3: Dissemination and communication | Geographical coverage | National | 6 | 3: Dissemination and communication | Geographical coverage | National |  |  | Geographical coverage
|  |  |  | Number of municipalities | 6 |  |  | Number of municipalities | 6 |  |  | Number of municipalities | 6 |  |  | Number of municipalities
|  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard | Drought | No. of adopted Early Warning Systems | Category targeted | Hazard | Drought | No. of adopted Early Warning Systems | Category targeted | Hazard
|  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 2: Strengthened institutional capacity to reduce risks associated with climate-induced socioeconomic and environmental losses | Indicator 2: Capacity of staff to respond to, and mitigate impacts of, climate-related events from targeted institutions increased | Number of staff targeted |  | Sector | Capacity level | Number of staff targeted |  | Sector | Capacity level | Number of staff targeted |  | Sector | Capacity level | Number of staff targeted |  | Sector | Capacity level
|  | Total | 0 | Multi-sector | 2: Low capacity | Total | 100 | Multi-sector | 2: Low capacity | Total | 72 | Multi-sector | 3: Medium capacity | Total
|  | % of female targeted | 0% |  |  | % of female targeted | 30% |  |  | % of female targeted | 20% |  |  | % of female targeted
Output 2.1 Strengthened capacity of national and sub-national centers and networks to respond rapidly to extreme weather events | Indicator 2.1.1: No. of staff trained to respond to, and mitigate impacts of, climate-related events | Total staff trained | % of female staff trained | Type |  | Total staff trained | % of female staff trained | Type |  | Total staff trained | % of female staff trained | Type |  | Total staff trained | % of female staff trained | Type
|  | 40 | 30% | Public |  | 65 | 30% | Public |  | 45 | 36% | Public
| Indicator 2.1.2: No. of targeted institutions with increased capacity to minimize exposure to climate variability risks | Type | Scale | Sector | Capacity level | Type | Scale | Sector | Capacity level | Type | Scale | Sector | Capacity level | Type | Scale | Sector | Capacity level
|  | Public | Regional | Multi-sector | 2: Low capacity | Public | National | Agriculture | 2: Low capacity | Public | National | Multi-sector | 3: Medium capacity
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 3: Strengthened awareness and ownership of adaptation and climate risk reduction processes | Indicator 3.1: Increase in application of appropriate adaptation responses | Percentage of targeted population applying adaptation measures |  | Sector |  | Percentage of targeted population applying adaptation measures |  | Sector |  | Percentage of targeted population applying adaptation measures |  | Sector |  | Percentage of targeted population applying adaptation measures |  | Sector
|  | 6% |  | Multi-sector |  | 38 |  | Multi-sector |  | 24 |  | Multi-sector
Output 3: Targeted population groups participating in adaptation and risk reduction awareness activities | Indicator 3.1.1: Percentage of targeted population awareness of predicted adverse impacts of climate change, and of appropriate responses | No. of targeted beneficiaries | % of female participants targeted | Level of awareness |  | No. of targeted beneficiaries | % of female participants targeted | Level of awareness |  | No. of targeted beneficiaries | % of female participants targeted | Level of awareness |  | No. of targeted beneficiaries | % of female participants targeted | Level of awareness
|  | 0 | 0% | 2: Partially not aware |  | 3000 | 40% | 2: Partially not aware |  | 1600 | 40% | 3: Partially aware
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Target performance at completion |  |  |  | Target performance at completion
Outcome 4: Increased adaptive capacity within relevant development sector services and infrastructure assets | Indicator 4.1: Increased responsiveness of development sector services to evolving needs from changing and variable climate | Project/programme sector | Geographical scale | Response level |  | Project/programme sector | Geographical scale | Response level |  | Project/programme sector | Geographical scale | Response level |  | Project/programme sector | Geographical scale | Response level
|  | Multi-sector | Regional | 2: Partially responsive (Lacks most elements) |  | Multi-sector | Regional | 4: Mostly responsive (Most defined elements) |  | Multi-sector | Regional | 3: Moderately responsive (Some defined elements)
| Core Indicator 4.2: Assets produced, developed, improved or strengthened | Sector | Targeted asset | Changes in asset (quantitative or qualitative) |  | Sector | Targeted asset | Changes in asset (quantitative or qualitative) |  | Sector | Targeted asset | Changes in asset (quantitative or qualitative) |  | Sector | Targeted asset | Changes in asset (quantitative or qualitative)
|  | Multi-sector | 2: Physical asset (produced/improved/strengthened) | 1: Not improved |  | Multi-sector | 2: Physical asset (produced/improved/strengthened) | 4: Mostly Improved |  | Multi-sector | 2: Physical asset (produced/improved/strengthened) | 3: Moderately improved
Output 4: Vulnerable development sector services and infrastructure assets strengthened in response to climate change impacts, including variability | Indicator 4.1.1: No. and type of development sector services to respond to new conditions resulting from climate variability and change | Number of services | Type |  | Sector | Number of services | Type |  | Sector | Number of services | Type |  | Sector | Number of services | Type |  | Sector
|  | 0 | Irrigation |  | Agriculture | 1 | Irrigation |  | Agriculture | 3 | irrigation and water supply, livestock |  | Multi-sector
|  | 0 | Dam/Subsurface/Diversions |  | Water management | 3 | Dam/Subsurface/Diversions |  | Water management | 3 | Agriculture/energy/meteorology |  | Multi-sector
|  | Baseline information |  |  |  | Baseline information |  |  |  | Baseline information |  |  |  | Baseline information
Outcome 5: Increased ecosystem resilience in response to climate change and variability-induced stress | Indicator 5: Ecosystem services and natural resource assets maintained or improved under climate change and variability-induced stress | Natural resource improvement level |  | Sector | Type | Natural resource improvement level |  | Sector | Type | Natural resource improvement level |  | Sector | Type | Natural resource improvement level |  | Sector | Type
|  | 2: Partially effective |  | Other | land | 1: Ineffective
Output 5: Vulnerable ecosystem services and natural resource assets strengthened in response to climate change impacts, including variability | Core Indicator 5.1: Natural Assets protected or rehabilitated | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Cultivated land/Agricultural land | 6 | ha rehabilitated | 2: Partially effective | Cultivated land/Agricultural land
|  | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Catchment area/Watershed/Aquifer | 300 | ha protected | 2: Partially effective
|  | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Baseline information |  |  |  | Targeted performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 6: Diversified and strengthened livelihoods and sources of income for vulnerable people in targeted areas | Indicator 6.1: Increase in households and communities having more secure access to livelihood assets | No. of targeted households | % of female headed households | Improvement level |  | No. of targeted households | % of female headed households | Improvement level |  | No. of targeted households | % of female headed households | Improvement level |  | No. of targeted households | % of female headed households | Improvement level
|  | 9000 | 30% | 2: Limited improvement |  | 13250 | 30% | 4: High improvement |  | 13030 | 30% | 3: Moderate improvement
| Indicator 6.2: Increase in targeted population's sustained climate-resilient alternative livelihoods | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
|  | 0 | 0% | From 0 to 0.5% | Agricultural-related | 800 | 40% | From 30% to 40% | Agricultural-related | 500 | 32% | From 20% to 30% | Agricultural-related
|  | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
|  | 0 | 0% | From 0 to 0.5% | Livestock production | 100 | 30% | From 40% to 50% | Livestock production | 69 | 30% | From 30% to 40% | Livestock production
|  | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
|  | 3180 | 40% | From 40% to 50% | Forestry | 4380 | 40% | Above 50% | Forestry | 4194 | 30% | From 20% to 30% | Forestry
|  | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
Output 6 Targeted individual and community livelihood strategies strengthened in relation to climate change impacts, including variability | Indicator 6.1.1: No. and type of adaptation assets created or strengthened in support of individual or community livelihood strategies | Number of Assets | Type of Assets | Sector | Adaptation strategy | Number of Assets | Type of Assets | Sector | Adaptation strategy | Number of Assets | Type of Assets | Sector | Adaptation strategy | Number of Assets | Type of Assets | Sector | Adaptation strategy
|  | 0 | Physical capital | Multi-sector | Strengthening infrastructure | 5 | Physical capital | Multi-sector | Strengthening infrastructure | 4 | Physical capital | Multi-sector | Strengthening infrastructure
| Core Indicator 6.1.2: Increased income, or avoided decrease in income | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income | income source
|  | 5 | Agricultural-related |  | 20000 | 350 | Agricultural-related |  | 230000 | 100 | Agricultural-related |  | 190000 | 300
|  | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 7: Improved policies and regulations that promote and enforce resilience measures | Indicator 7: Climate change priorities are integrated into national development strategy | Integration level |  |  |  | Integration level |  |  |  | Integration level |  |  |  | Integration level
|  | 4: Most |  |  |  | 5: All (Fully integrated) |  |  |  | 4: Most
Output 7:Improved integration of climate-resilience strategies into country development plans | Indicator 7.1: No. of policies introduced or adjusted to address climate change risks | No. of Policies introduced or adjusted | Sector | Scale | Type | No. of Policies introduced or adjusted | Sector | Scale | Type | No. of Policies introduced or adjusted | Sector | Scale | Type | No. of Policies introduced or adjusted | Sector | Scale | Type
| Indicator 7.2: No. of targeted development strategies with incorporated climate change priorities enforced | No. of Development strategies | Regulation |  | Effectiveness | No. of Development strategies | Regulation |  | Effectiveness | No. of Development strategies | Regulation |  | Effectiveness | No. of Development strategies | Regulation |  | Effectiveness
Glacier lake outburst flood
|  | Inland flooding | fr | biological assets |  | Company policy | 5: Fully enforced (All elements implemented)
|  | Salinization | Decrease | land |  | Communication & Information policy | 4: Enforced (Most elements implemented)
|  | Drought | Same | water areas |  | Defense policy | 3: Partially enforced (Some elements implemented)
|  | Wind |  | subsoil assets | increased adaptive capacity | Domestic policy | 2: Partially not enforced (Most elements not implemented) |  | Agribusiness
|  | Coastal flooding |  | air | achieved | Economic policy | 1: Not enforced (No elements implemented) |  | Agricultural-related | Financial capital
|  | Storm surge | Please choose |  | enhanced level of protection | Education policy |  |  | Agriculture | Human capital
|  | Hurricane | Selected | [5 empty] | Aquaculture | Physical capital
|  |  | Not relevant |  |  | 5: All (Fully integrated) |  |  | Construction/repairing business | Social capital
[6 empty] | 4: Most |  |  | Cultivation | Natural capital
[6 empty] | 3: Some |  |  | Fishing | Personal capital
Select | 5: All | Select |  |  | Community | 2: Most not integrated |  | Other | Forestry | Adaptation strategies
1 | 4: Almost all | Private | Type | Yes | Multi-community | 1: None |  | Agriculture | Handicrafts
2 | 3: Half | Public | Scale | No | Departmental |  |  | Coastal management | Livestock production
3 | 2: Some | NGO | Sector |  | National |  |  | Disaster risk reduction | Manufacturing
4 | 1: None |  |  |  |  | 5: Very high improvement | Established | Food security | other
|  | National |  |  |  | 4: High improvement | Maintained | Health | Services
|  | Regional |  |  |  | 3: Moderate improvement | Improved | Urban development | Tourism-related
|  | Local |  |  |  | 2: Limited improvement |  | Water management | Trading
[6 empty] | 1: No improvement |  | Multi-sector
|  | 1 -generated information is irrelevant, and neither the stakeholders reached nor the timeframe managed were achieved | 1: No info transferred on time | 4: High capacity | 5: Fully aware | 5: Highly responsive (All defined elements ) | 5: Fully improved | Roads | 5: Very effective
Asia-Pacific | NIE | 2 -the existence of some challenge in any of the three aspects of the indicator (generation of dissemination, stakeholders reached or timeframe managed) | 2: Somewhat info transferred | 3: Medium capacity | 4: Mostly aware | 4: Mostly responsive (Most defined elements) | 4: Mostly Improved | Gov Buildings | 4: Effective
Latin America and Caribbean | RIE | 3 -relevant information is generated and disseminated to all identified stakeholders on timely basis | 3: Info transferred on time | 2: Low capacity | 3: Partially aware | 3: Moderately responsive (Some defined elements) | 3: Moderately improved | Causeways | 3: Moderately effective
Africa | MIE |  |  | 1: No capacity | 2: Partially not aware | 2: Partially responsive (Lacks most elements) | 2: Somewhat improved | Airports | 2: Partially effective
Eastern Europe |  |  |  |  | 1: Aware of neither | 1: Non responsive (Lacks all elements ) | 1: Not improved | Schools | 1: Ineffective
| ha protected | [6 empty] | Training Centers
| ha rehabilitated | [5 empty] | Monitoring/Forecasting capacity | Hospitals
Afghanistan, Islamic Rep. of | km protected | [5 empty] | Policy/regulatory reform | Drinking water systems
Angola | km rehabilitated | 1: Risk knowledge | 1: No plans conducted or updated |  |  |  | Capacity development | Other
Albania |  | 2: Monitoring and warning service | 2: Undertaking or updating of assessments in progress |  |  | Communication & Information policy | Sustainable forest management
Argentina |  | 3: Dissemination and communication | 3: Risk and vulnerability assessments completed or updated |  |  | Domestic policy | Strengthening infrastructure | 1: Health and Social Infrastructure (developed/improved)
Armenia | Forests | 4: Response capability |  |  |  | Economic policy | Supporting livelihoods | 2: Physical asset (produced/improved/strengthened)
Antigua and Barbuda | Mangroves |  |  |  |  | Education policy | Mangrove reforestation
Azerbaijan | Coasts |  | From 0 to 0.5% |  |  | Energy policy | Coastal drainage and infrastructure
Burundi | Rangelands |  | From 0.5 to 1% |  |  | Environmental policy | Irrigation system
Benin | Cultivated land/Agricultural land |  | From 1% to 5% |  |  | Foreign policy | Community-based adaptation
Burkina Faso | Catchment area/Watershed/Aquifer |  | From 5% to 10% |  |  | Health policy | Erosion control
Bangladesh | Protected areas/National parks |  | From 10% to 20% |  |  | Housing policy | Soil water conservation
Bulgaria | Other |  | From 20% to 30% |  |  | Human resource policies | Microfinance
Bahrain |  |  | From 30% to 40% |  |  | Information policy | Special Program for women
Bahamas, The |  |  | From 40% to 50% |  |  | Macroeconomic policy | Livelihoods
Bosnia and Herzegovina |  |  | Above 50% |  |  | Monetary policy | Water storage
Belarus | [5 empty] | Population policy | ICT and information dissemination
Belize | [5 empty] | Private policy
Bolivia | [5 empty] | Public policy
Brazil | [5 empty] | Science policy
Barbados | [5 empty] | Social policy
Bhutan |  | 3- relevant information is generated and disseminated to all identified stakeholders on timely basis |  |  |  | Transportation policy
Botswana |  | describe |  |  |  | Urban policy
Central African Republic |  | 2- the existence of some challenge in any of the three aspects of the indicator |  |  |  | Water policy
Chile |  | describe |  |  |  | Other policy
China, People's Republic of |  | 1- generated information is irrelevant and neither the stakeholders reached nor the timeframe managed were achieved
Cote d'Ivoire |  | describe
Cameroon
Congo, Dem. Rep. of
Congo, Republic of
Cook Islands
Colombia
Comoros
Cape Verde
Costa Rica
Cuba
Czech Republic
Djibouti
Dominica
Dominican Republic
Algeria
Ecuador
Egypt
Eritrea
Estonia
Ethiopia
Fiji
Micronesia, Fed. States of
Gabon
Georgia
Ghana
Guinea
Gambia, The
Guinea-Bissau
Equatorial Guinea
Grenada
Guatemala
Guyana
Honduras
Croatia
Haiti
Hungary
Indonesia
India
Iran, Islamic Republic of
Jamaica
Jordan
Kazakhstan
Kenya
Kyrgyz Republic
Cambodia
Kiribati
Saint Kitts and Nevis
Korea, Republic of
Lao People's Democratic Republic
Lebanon
Liberia
Libya
Saint Lucia
Sri Lanka
Lesotho
Lithuania
Latvia
Morocco
Moldova
Madagascar
Maldives
Mexico
Marshall Islands
Macedonia, former Yugoslav Republic of
Mali
Malta
Myanmar
Montenegro
Mongolia
Mozambique
Mauritania
Mauritius
Malawi
Malaysia
Namibia
Niger
Nigeria
Nicaragua
Niue
Nepal
Nauru
Oman
Pakistan
Panama
Peru
Philippines
Palau
Papua New Guinea
Poland
Korea, Dem. People's Rep. of
Paraguay
Romania
Russian Federation
Rwanda
Saudi Arabia
Sudan
Senegal
Solomon Islands
Sierra Leone
El Salvador
San Marino
Serbia
Sao Tome and Principe
Suriname
Slovak Republic
Slovenia
Swaziland
Seychelles
Syrian Arab Republic
Chad
Togo
Thailand
Tajikistan
Turkmenistan
Tonga
Trinidad and Tobago
Tunisia
Turkey
Tuvalu
Tanzania
Uganda
Ukraine
Uruguay
Uzbekistan
Saint Vincent and the Grenadines
Venezuela
Vietnam
Vanuatu
Samoa
Yemen, Republic of
South Africa
Zambia
Zimbabwe
Timor-Leste

## Units for Indicators
Fund Outcome Indicator Units
1. Generation of relevant data, Stakeholders, and Timeliness 2.1. Include both qualitative and quantitative measures of capacity level within targeted institutions 2.2. Number (men and women and other vulnerable groups) 3.1. Use scale from 1 to 5: 5: Fully aware 4: Mostly aware 3: Partially aware 2: Partially not aware 1: Aware of neither predicted adverse impacts of climate change nor of appropriate responses 3.2. Use scale from 1 to 5: 5: All 4: Almost all 3: Half 2: Some 1: None 4.1. Summarize in an overall scale (1-5): 5: Highly responsive (All defined elements ) 4: Mostly responsive (Most defined elements) 3: Moderately responsive (Some defined elements) 2: Partially responsive (Lacks most elements) 1: Non responsive (Lacks all elements ) 4.2. Summarize in an overall scale (1-5): 5: Fully improved 4: Mostly Improved 3: Moderately improved 2: Somewhat improved 1: Not improved 5. Depends on the targeted natural asset: Biological (species): measure through changes in population numbers (dynamics, structure, etc.) Land: measure changes in hectares. Baseline data will be necessary to estimate the change. Supporting indicators baseline and target (as well as contextual information) are needed such as the following: Farmers adopting recommended technologies, Ha. of land improved, Average deforestation rate Etc. Use scale from 1 to 5. 5: Very effective (All elements are present) 4: Effective (Most elements are present) 3: Moderately effective (Some elements are present) 2: Partially effective (Most elements are not present) 1: Ineffective (No elements are present) 6.1. Summarize in an overall scale (1-5): 5: Very high improvement 4: High improvement 3: Moderate improvement 2: Limited improvement 1: No improvement 6.2. Household income by source of livelihood in project area (USD) prior and post project intervention 7. Summarize in an overall scale (1-5). 5: All (Fully integrated) 4: Most 3: Some 2: Most not integrated 1: None
Fund Output Indicator Units
1.1. Number, sector(s) and level(s) of projects or interventions in separate fields of monitoring plan 1.2. Number 2.1.1. Number of staff (male/female) of targeted institutions: a. Obtain baseline information: total number of staff from targeted institutions b. Define target 2.1.2. Number of staff (male/female) of targeted institutions: a. Obtain baseline information: total number of staff from targeted institutions b. Define target: needs to be defined by project proponents 2.2.1. Quantitative: Percentage (includes women – and other vulnerable groups – and men). Qualitative: Adequacy: include direct analysis of major areas; adequacy/effectiveness of systems or analysis of perceptions of populations and institutions. 2.2.2. Number (broken down by gender and, if possible, by vulnerable groups defined in the area of intervention) of people 3.1. Number and type (in separate columns) at local level. 3.2. Number 4.1. Number and type 4. 2. Number and type (entered in separate columns) 5. Number of interventions by type of natural asset and intervention 6.1. Number and type (in separate columns of monitoring plan) 6.2. Income sources per household; description of income source and number of households. 7.1. Number/Sector 7.2. Number; Effectiveness (see previous indicator) through enforcement level.