## Overview
Project Performance Report (PPR)
| Period of Report (Dates) | November 2011 to November 2012
| Project Title: | Enhancing resilience of communities to the adverse effects of climate change on food security, in Pichincha Province and the Jubones River Basin
| Project Summary: | Ecuador's Ministry of Environment and the United Nations World Food Programme initiated a five-year project to strengthen resilience and food security in 12 cantons, for approximately 120 communities and 15,000 families located in the Pichincha Province and the Jubones River Basin. The overall goal of the project is to reduce food insecurity and vulnerability of communities and ecosystems, related to the adverse effects of climate change, in the most vulnerable cantons of Pichincha Province and the basin of the Jubones River. The project includes two components with the following objectives: Component 1: Develop awareness and knowledge capacity at the community level on climate change and food insecurity related risks. Objective 1: Increase knowledge to manage climate change risks affecting food security in targeted cantons in Pichincha Province and in the Basin of the Jubones River. Component 2: Increase adaptive capacity and reduce recurrent risks of climate variability at the community level. Objective 2: Strengthen adaptive capacity of highly food insecure communities to respond to the impacts of climate change, including variability in targeted cantons in the Pichincha Province and Public Consortium of the Jubones River Basin ("Consorcio Público de la Cuenca del Río Jubones - CCRJ"). The project approach recognizes the importance of critical ecosystems and agricultural production systems in support of food security and the most vulnerable segments of the population. The project targets those cantons with high levels of chronic malnutrition and high risk of precipitation fluctuations and water availability due to climate variability and change. It also targets communities that will be most severely affected by climate related events and are least able to cope with increased climate variability. These components are being be implemented at community level under the leadership of Ministry of Environment (MAE), and in coordination with the Ministry of Agriculture (MAGAP) and WFP, through two management authorities: under direct management of the Public Consortium of the Jubones River Basin and the Pichincha Provincial Government ("Gobierno Autónomo Descentralizado de Pichincha - GADPP").
|  |  | Countries | Project Type: |  | GEF Focal Area: | GEF 4 Focal Areas | GEF 2 / 3 Operational Programme: | Overall Rating of the project in the evaluation by the project evaluator: | GEF-4 Focal Area Strategic Program: | GEF-3 Focal Area Strategic Program:
| Database Number: |  | Afghanistan | FP | Yes | Biodiversity | 1 | 1 | U | BD-SP1-PA Financing | 1: Arid & semi-arid ecosystems
Implementing Entity (IE) [name]: |  | United Nations Word Food Programme (WFP) | Albania | MSP | No | Climate Change Adaptation | 2 | 2 | S | BD-SP2-Marine PA | 2: Coastal, marine & freshwater ecosystems
| Type of IE: | Multilateral | Algeria | EA |  | Climate Change Mitigation | 3 | 3 | MU | BD-SP3-PA Networks | 3: Forest ecosystems
| Country(ies): | Ecuador | Angola |  |  | International Waters | 5 | 5 | Good | BD-SP5-Markets | 13: Conservation and Sustainable Use of Biological Diversity Important to Agriculture
Relevant Geographic Points (i.e. cities, villages, bodies of water): |  | Jubones River Basin (covering 3 Provinces, 12 Cantons and 39 Parishes) Pichincha Province (covering 1 Province, 2 Cantons and 11 Parishes) | Argentina |  |  | Multiple Focal Area |  |  |  | BD-SP7-Invasive Alien Species(IAS) | 6: Promoting the adoption of renewable energy by removing barriers and reducing implementation costs
[8 empty] | CC-SP2- Industrial EE | 8: Waterbody based operational program
| Project Milestones | [6 empty] | CC-SP3-RE,CC-SP4-Biomass | 9: Integrated Land and Water multiple focal area
| Milestone |  | Bahamas | [6 empty] | CC-SP5-Transport | 10: Contaminants based operational program
AFB Approval Date: |  | March 18, 2011
IE-AFB Agreement Signature Date: |  | July 2011 | [6 empty] | CC-SP6-LULUCF | 12: Integrated Ecosystem Management
Start of Project/Programme: |  | November 29, 2011 | [6 empty] | Cross cutting capacity building | 14: Persistent Organic Pollutants
Mid-term Review Date (if planned): |  | December 2013
| Terminal Evaluation Date: | August 2016
|  | List documents/ reports/ brochures / articles that have been prepared about the project. | Cyprus
|  | - Inception Report, delivered to the AF in May 2012 - Building Resilience: Bridging Food Security, Climate Change Adaptation and Disaster Risk Reduction, WFP paper, November 2011 (http://reliefweb.int/sites/reliefweb.int/files/resources/Workshop%20Building%20Resilience%20-%20Case%20Studies%20Overview%20-%20final%20draft.pdf) - Landscapes for People, Food and Nature Initiative (http://blog.ecoagriculture.org/2012/03/02/community-action-for-food-security-and-resilience-2/), March 2012 - WFP Annual Report 2011, May 2012 - SETECI report, October 2012 - Methodology for the Vulnerability Study, edited on October 2012 - El Comercio (Ecuadorian daily newspaper) news article. July 2012 - MAE webpage (http://web.ambiente.gob.ec/?q=node/878&page=0,3) - WFP webpage (http://www.wfp.org/countries/ecuador/operations) and monthly executive brief - MAE, CCRJ, GAD PP and WFP press releases during project execution | Czech Republic
List the Website address (URL) of project. |  |  | Democratic People's Republic of Korea
|  | n/a | Democratic Republic of the Congo
Denmark
| Project contacts: |  | Djibouti
National Project Manager/Coordinator |  |  | Dominica
| Name: | Juan Bravo | Dominican Republic
| Email: | jbravom@ambiente.gob.ec | Ecuador
| Date: | 2012-11-30 | Egypt
| Government DA |  | El Salvador
| Name: | María Victoria Chiriboga | Equatoral Guinea
| Email: | mchiriboga@ambiente.gob.ec | Eritrea
| Date: | 2012-11-30 | Estonia
| Implementing Entity |  | Ethiopia
| Name: | Deborah Hines | Fiji
| Email: | deborah.hines@wfp.org | Finland
| Date: | 2012-11-30 | France
| Executing Agency |  | Gambia
| Name: | Lorena Tapia, Ministra de Ambiente (e) | Georgia
| Email: | ltapia@ambiente.gob.ec | Germany
| Date: | 2012-11-30 | Ghana
| Executing Agency |  | Greece
| Name: | Javier Ponce, Ministro de Agricultura, Ganadería, Acuacultura y Pesca | Grenada
| Email: | jponce@magap.gob.ec | Guatemala
| Date: | 2012-11-30 | Guinea
| Executing Agency |  | Guinea Bissau
| Name: | Gustavo Baroja, Prefecto del Gobierno Autonomo de la Provincia de Pichincha | Guyana
| Email: | gbaroja@pichincha.gob.ec | Haiti
| Date: | 2012-11-30 | Honduras
| Executing Agency |  | Guinea Bissau
| Name: | John Franco, Presidente del Consorcio Público de la Cuenca del Río Jubones | Guyana
| Email: | st@cuencadeljubones.gob.ec | Haiti
| Date: | 2012-11-30 | Honduras
Hungary
Ireland
Israel
Italy
Jamaica
Japan
Jordan
Kazakhstan
Kenya
Kiribati
Kuwait
Kyrgyzstan
Lao People’s Democratic Republic
Latvia
Lebanon
Lesotho
Liberia
Libyan Arab Jamahiriya
Liechtenstein
Lithuania
Luxembourg
Madagascar
Malawi
Malaysia
Maldives
Mali
Malta
Marshall Islands
Mauritania
Mauritius
Mexico
Micronesia, Federated States of
Monaco
Mongolia
Montenegro
Morocco
Mozambique
Myanmar
Namibia
Nauru
Nepal
Netherlands
New Zealand
Nicaragua
Niger
Nigeria
Norway
Oman
Pakistan
Palau
Panama
Papua New Guinea
Paraguay
Peru
Philippines
Poland
Portugal
Qatar
Republic of Korea
Republic of Moldova
Romania
Russian Federation
Rwanda
Saint Kitts and Nevis
Saint Lucia
Saint Vincent and the Grenadines
Samoa
San Marino
Sao Tome and Principe
Saudi Arabia
Senegal
Serbia
Seychelles
Sierra Leone
Singapore
Slovakia
Slovenia
Solomon Islands
Somalia
South Africa
Spain
Sri Lanka
Sudan
Suriname
Swaziland
Sweden
Switzerland
Syrian Arab Republic
Tajikistan
Thailand
The former Yugoslav Republic of Macedonia
Timor-Leste
Togo
Tonga
Trinidad and Tobago
Tunisia
Turkey
Turkmenistan
Tuvalu
Uganda
Ukraine
United Arab Emirates
United Kingdom of Great Britain and Northern Ireland
United Republic of Tanzania
United States of America
Uruguay
Uzbekistan
Vanuatu
Venezuela, Bolivarian Republic of
Viet Nam
Yemen
Zambia
Zimbabwe

## FinancialData
Financial information: cumulative from project start to November 2012
DISBURSEMENT OF AF GRANT FUNDS | 2473859
How much of the total AF grant as noted in Project Document plus any project preparation grant has been spent to date?
Estimated cumulative total disbursement as of November 15, 2012 | 298808.25 |  |  | 12.08%
Add any comments on AF Grant Funds. (word limit=200) | Under harmonized approach to cash transfer (HACT), this amount includes all expenses made by WFP on behalf of MAE - executing agency, the first and second transfers made to MAE and WFP´s execution cost. It does not include commitments up to date. While 66% of the total budget is going to be invested in concrete adaptation measures which will start in 2013, this low rate of execution for the first year is understandable. During this first period, a sound environment for implementation was created by registering the project under national procedures. After an extensive process, on 07 August 2012, the Government of Ecuador declared that the project is a priority, and on 16 October the financial execution became possible. Meanwhile, the Project conducted an exhaustive orientation process with national institutions, hired project staff, defined implementation arrangements among national institutions with a strong leadership of MAE and full support and involvement on the part of WFP.
EXPENDITURE DATA
List output and corresponding amount spent for the current reporting period | ITEM / ACTIVITY / ACTION | AMOUNT
| 1.1.1. Parishes in targeted cantons trained in climate change threats and adaptation measures which reduce vulnerability, in particular related to food security | 38243.46
| 1.1.3. Food security and gender considerations integrated in all adaptation training programs | 3378.93
| 1.2.1. Canton and community adaptation plans developed to reduce vulnerabilities to climate change induced food insecurity in targeted areas | 134531.94
| 1.2.2. Community participation in processes to develop adaptation plans in targeted cantons | 13733.95
| 1.2.3. Agreements developed and signed among targeted cantons, GPP or MCRJ, MAE and WFP to implement adaptation actions | 23993.86
| Execution Cost | 84926.11
| TOTAL | 298808.25
PLANNED EXPENDITURE SCHEDULE
List outputs planned and corresponding projected cost for the upcoming reporting period | ITEM / ACTIVITY / ACTION | PROJECTED COST | Est. Completion Date
| 1.1.1. Parishes in targeted cantons trained in climate change threats and adaptation measures which reduce vulnerability, in particular related to food security | 25357.41 | 2013-12-01
| 1.1.2. Targeted parishes participate in adaptation and risk reduction awareness activities | 25107.41 | 2013-10-01
| 1.1.3. Food security and gender considerations integrated in all adaptation training programs | 25107.41 | 2013-11-01
| 1.2.1. Canton and community adaptation plans developed to reduce vulnerabilities to climate change induced food insecurity in targeted areas | 59647.79 | 2013-06-01
| 1.2.2. Community participation in processes to develop adaptation plans in targeted cantons | 40189.79 | 2013-07-01
| 1.2.3. Agreements developed and signed among targeted cantons, GPP or MCRJ, MAE and WFP to implement adaptation actions | 40139.79 | 2013-06-01
| 1.2.4. Women participated in processes and decision making to develop adaptation plans | 40139.79 | 2013-11-01
| 1.3.1. Community early warning system designed, implemented and maintained | 200094.11 | 2013-08-01
| 1.3.2. Monitoring system in place to track climate events in targeted cantons | 37661.11 | 2013-08-01
| 1.3.3. Monitoring system to track project results and lessons learned | 65000 | 2013-10-01
| 2.1.1. Concrete adaptation measures based on community adaptation plans are designed | 1378776 | 2013-12-01
2.1.2. Physical assets created, improved or maintained
2.1.3. Natural resources assets created, improved or maintained
2.1.4. Identification of adaptation technology requirements
2.1.5. Implementation strategy includes approach for the use of incentives
2.2.1. Community participation, in particular of women, guide decision making processes for project execution
2.2.2. Parishes share success stories and lessons learned
| Execution Cost | 130868.97 | 2013-12-01
| TOTAL | 2068089.58 | 2013-12-01
ACTUAL CO-FINANCING (If the MTR or TE have not been undertaken this reporting period, DO NOT report on actual co-financing.)
How much of the total co-financing as committed in the Project Document has actually been realized? | The Project document has not established co-financing or this project. However, MAE, GADPP and CCRJ committed in kind resources for project execution such as: office and communica-tion facilities, ground transportation, staff time, etc. This project has raised government’s commitment to ensure the replication of the project measures in communities where the project cannot reach, and continued sustainability of the project’s interventions.
Estimated cumulative actual co-financing as verified during Mid-term Review (MTR) or Terminal Evaluation (TE). | 0
Add any comments on actual co-financing in particular any issues related to the realization of in-kind, grant, credits, loans, equity, non-grant instruments and other types of co-financing. (word limit=200) | n/a
Note on E7: Amount does not consider MIE Fee 7%

## Risk Assesment
RISK ASSESMENT
IDENTIFIED RISKS
List all Risks identified in project preparation phase and what steps are being taken to mitigate them
Identified Risk | Current Status | Steps Taken to Mitigate Risk
Changes in responsible actors in the Ecuadorian Government may determine possible changes in the national strategy for climate change. | Medium | The Ministry of Environment is the Governmental institution responsible for climate change policies and strategies. The National Strategy on Climate Change (NSCC) proposes to strengthen capacities in sectorial ministries and local governments to ensure sustainable activities. In order to avoid possible delays due to 2013 Government Elections, the project promoted full participation of all government authorities in planning and execution. Most products are being developed with local authorities which will help to maintain continuity of actions.
Climate change adaptation has not been incorporated in policies, strategies, and plans of local governments. | Low | Territorial plans (PDOTs) have been designed in each local government. In order to incorporate adaptation to climate change at local level, MAE is developing the National Adaptation and Mitigation Climate Change Plans and the National Plan of Creation and Strengthening Conditions to Climate Change. Plans are designed through a participatory process and will be discussed with local stakeholders.
MCRJ is going through a re-organization process to become a local governmental consortium. During this period of change the leadership may redirect its priorities towards different objectives. | Overcome | The Public Consortium of the Jubones River Basin (CCRJ) is the local executing partner for the project, fully involved in all aspects of planning and execution. The CCRJ, formerly Association of the Jubones River Basin ("Mancomunidad de la Cuenca del Río Jubones" MCRJ) carried out a process to be legally qualified to execute the project at local level.
Scientific and technical information in relation to climate change in Ecuador is insufficient, incomplete, and uncertain. | Medium | MAE is implementing other adaptation to climate change projects (PRAA, PACC GACC) which have produced scientific and technical information regarding climate change. Climate models have been developed such as: as FClindex to identify climate variability, CRISTAL methodology to prioritize adaptation measures within communities, as well as a methodologies for climate change vulnerability studies that can be applied in any site or context, and strengthening of agro-climatic network with INAHMI in order to produce climatic information for early warning systems. These activities will continue to be partially strengthened through the project.
There is little local specialized management and technical capacity related to climate change, particularly in the entities that are responsible for the project. MAE identified among one of the major problems regarding adaptation to climate change, the lack of human technical resources. | Medium | MAE is working to assist local governments in climate change mainstreaming. Under project implementation there is a close coordination among institutions at national and local levels to incorporate climate change priorities. The project is working on the baseline study in 50 parishes to determine the knowledge level on climate change, food security and gender. Also the project is assessing the technical resources, equipment and infrastructure available at local level. The project is designing a local capacity building strategy and training modules on climate change, food and nutrition security and gender to improve community resilience.
Regulatory setting is in discussion by Ecuador National Assembly, including a new law that regulates the use of hydro resources. | Medium | The Ecuadorian National Assembly has not enacted the new law for water management as yet. Nevertheless, during the past months of the project implementation, it was visible that the project is able to promote adaptation measures focused on water management at a local level with the support of Local Governments, which have new competences stated in the COOTAD legislation. A clear example of this fact is the CCRJ, the project local partner, which is working at a local level on water management projects in coordination with the National Secretariat of Water. The approval of this law can not be influenced by the MAE because it is being discussed at the National Assembly (Congress), therefore, the level of involvement is minimum.
Weak local organizational structures, which may raise conflicts within and among local communities. | Low | Throughout the capacity building plan, the project will identify community priorities, strengthens and weaknesses. The Steering Committee is proposing some actions to prevent conflicts and improve local organization structures.
MAE has pointed out the lack of local level information on many aspects of climate change. | Medium | The project is undertaking a vulnerability study on targeted areas to determine baseline indicators related to climate change threats in food and nutrition security and gender empowerment.
Critical Risks Affecting Progress (Not identified at project design)
Identify Risks with a 50% or > likelihood of affecting progress of project
Identified Risk | Current Status | Steps Taken to Mitigate Risk
National start up processes for cooperation project in Ecuador take an extensive amount of time. | Overcome (mostly) | MAE played a leadership role in this process. The technical staff of MAE counted with political allies to support the process. MAE took the initiative at the highest authority level for the completion of the process in the least amount of time possible.
The decision making process for this project is delayed due to the many stakeholders that are involved in the implementation. | Medium | The project has now a Steering Committee Policy and an Operational Manual to guide all the implementation processes; both documents define clearly stakeholder roles and responsibilities. These processes should mitigate communication-related risks shortly.
Local Stakeholders lack project implementation experience and understanding of adaptation to climate change processes delay the achievement of project objectives. | Medium | Project local staff has been facing some difficulties in its interaction with the communities through the CCRJ. MAE relocated the local staff to its office (originally at CCRJ offices) in order to strengthen the relationships and better support the project team with other local actors such as MAGAP, universities, local governments. The Ministry of Environment, has proved the commitment of its authorities, by seeking to build a lasting and working relationship with the local partners and other local actors, focused on the main aim which is to continue with the activities planned and recover lost time in the project start. The MAE has ensured a participatory approach in decision-making times. The Steering Committe must find consensus to approve strategic documents that are going to reinforce activities execution, such as the The Operational Manual, the Steering Committe Policy, and the Annual Operation Plan.
Risk Measures: Were there any risk mitigation measures employed during the current reporting period? If so, were risks reduced? If not, why were these risks not reduced?
Add any comments relevant to risk mitigation (word limit = 500)
Yes. A risk mitigation measure was employed for setting up expanding the role of Project Steering Committee, including WFP participation at Representative level in the Steering Committee and redefining participation level of CCRJ. The unplanned risk of timespan of “National start up processes for cooperation project in Ecuador" has received high level attention in both MAE and WFP. Both institutions, communicated their concerns to national entities in charge of approving the different steps of the processes. Regarding project execution, all stakeholders agreed on concrete deadlines to overcome delays.

## Rating
RATING ON IMPLEMENTATION PROGRESS
For rating definitions please see bottom of page.
| Progress on Key Milestones |  | Expected Progress |  | Progress to Date | Rating
National Executing Entity (Ministry of Environment) | Output 1.1.1. Communities in targeted cantons trained in climate change threats and adaptation measures which reduce vulnerability, in particular related to food security |  | All communities participated in initial training sessions |  | By the end of the year the capacity building training modules will be completed. The capacity building plan will be implemented during 2013-2014-2015 | MS
| Output 1.2.2. Community participation in process to develop adaptation plan in targeted cantons |  | 50 % of cantons reached |  | Vulnerability study undertaking for all parishes targeted (50) in the project. | MS
| Output 1.2.3. Agreements developed and signed among targeted cantons, GPP or CCRJ, MAE and WFP to implement adaptation actions |  | 50% of agreements reached to implement adaptation plans |  | In the Jubones River Basin, 39 parishes signed agreements with CCRJ for project implementation in May 2012. The identification of local execution modalities is pending. | S
| Output 1.3.1. Community early warning system designated, implements and maintained |  | 15% of early warning systems in place |  | In order to determine details on the early warning systems for agro meteorological purposes contacts with INAMHI, MAGAP and SNGR have been taking place. | MS
| Output 1.3.2. Monitoring system in place to track climate events in targeted cantons |  | Monitoring systems in place |  | In order to determine details of the early warning systems so as to gain agro meteorological information contacts the project has made contact and held initial meetings with INAMHI, MAGAP and SNGR. | MS
| Output 1.3.3. Monitoring system to track project results and lessons learned |  | Monitoring system in place |  | Mechanism to implement the monitoring plan and system is been analyzed between MAE and WFP. | MU
| Output 2.1.1. Concrete adaptation measures based on community adaptation plans are designed |  | 40% of adaptation measures planned |  | The vulnerability study on targeted parishes is underway by technical staff, who were hired for the project in September 2012. The results of this study will provide the best options for adaptation measures to be implemented. | MU
| Output 2.1.5.1. Implementation strategy includes approach for the use of incentives |  | Strategy developed |  | As soon as the adaptation plans for targeted parishes are ready, the project will define the most suitable incentives to be used. | U
[5 empty] | Overall Rating | MS
Please Provide the Name and Contact information of person(s) responsible for completing the Rating section
| Name: | María Victoria Chiriboga, National Director of Climate Change Adaptation
| Email: | mchiriboga@ambiente.gob.ec
Please justify your rating. Outline the positive and negative progress made by the project since it started. Provide specific recommendations for next steps. . (word limit=500)
The Project started in November 2011 when the Inception Workshop took place. The extensive process of prioritization, which was ended on August 7th 2012, allowed to active the financial operation under the MAE procedures and norms on October 16th. It is important to mention that the project manager was hired in April 2012 and the administrative and financial assistant in September 2012. It was possible to hire all the staff required; they were trained in different technical topics, including how to implement the vulnerability and mainstreaming gender in all project activities with the support of MAE, MAGAP, GAD PP, CCRJ, WFP, UN Women and others. The delay in the project execution was mainly due to the prioritization process, the lack of clarity in the role of each stakeholder, which affected the implementation of field activities, the definition of the orientation in food security/sovereignty in climate change process (this is the first initiative of this kind in Ecuador and Latin America), and the gender approach and tools and methodologies to be applied to ensure achievement of long term sustainability for the adaptation measures. At present, the project developed the Steering Committee Regulation and the Operational Manual. The vulnerability study, local adaptation plans, capacity building plan and the capacity training modules have been developed among other documents and tools needed. It is recommended to develop long term agreements among MAE and other local partners to force the project to meet milestones for implementation at local levels. Additionally, it is important to consider and work within the framework and time required of the execution modalities covered by HACT (harmonized approach to cash transfer) which allows mixed financial execution between the MAE TE account and the WFP. Finally, the vulnerability study will clarify the project indicators to be used and monitored; therefore it is recommended to review the project log frame to adjust indicators without affecting project outcomes.
| Progress on Key Milestones |  | Expected Progress |  | Progress to Date | Rating
Implementing Agency | Output 1.1.1. Communities in targeted cantons trained in climate change threats and adaptation measures which reduce vulnerability, in particular related to food security |  | All communities participated in initial training sessions |  | By the end of the year the capacity building training modules will be completed. The capacity building plan will be implemented during 2013-2014-2015 | MS
| Output 1.2.2. Community participation in process to develop adaptation plan in targeted cantons |  | 50 % of cantons reached |  | Vulnerability study undertaking for all parishes targeted (50) in the project. | MU
| Output 1.2.3. Agreements developed and signed among targeted cantons, GPP or CCRJ, MAE and WFP to implement adaptation actions |  | 50% of agreements reached to implement adaptation plans |  | In the Jubones River Basin, 39 parishes signed agreements with CCRJ for project implementation in May 2012. The identification of local execution modalities is pending. | MU
| Output 1.3.1. Community early warning system designated, implements and maintained |  | 15% of early warning systems in place |  | In order to determine details on the early warning systems for agro meteorological purposes contacts with INAMHI, MAGAP and SNGR have been taking place. | MU
| Output 1.3.2. Monitoring system in place to track climate events in targeted cantons |  | Monitoring systems in place |  | In order to determine details of the early warning systems so as to gain agro meteorological information contacts the project has made contact and held initial meetings with INAMHI, MAGAP and SNGR. | U
| Output 1.3.3. Monitoring system to track project results and lessons learned |  | Monitoring system in place |  | Mechanism to implement the monitoring plan and system is been analyzed between MAE and WFP. | U
| Output 2.1.1. Concrete adaptation measures based on community adaptation plans are designed |  | 40% of adaptation measures planned |  | The vulnerability study on targeted parishes is underway by technical staff, who were hired for the project in September 2012. The results of this study will provide the best options for adaptation measures to be implemented. | MU
| Output 2.1.5.1. Implementation strategy includes approach for the use of incentives |  | Strategy developed |  | As soon as the adaptation plans for targeted parishes are ready, the project will define the most suitable incentives to be used. | U
[5 empty] | Overall Rating | MU
Please Provide the Name and Contact information of person(s) responsible for completing the Rating section
| Name: | Veronica Alvarado, WFP´s Programme Office and Project Administrator
| Email: | veronica.alvarado@wfp.org
| Progress on Key Milestones |  | Expected Progress |  | Progress to Date | Rating
Other
Overall Rating
Please Provide the Name and Contact information of person(s) responsible for completing the Rating section
Name:
Email:
| Please justify your rating and address the following points: 1. Indicate trends, both positive and negative, in achievement of outcomes as per the project indicators. 2. Detail critical risks that have affected progress. 3. Outline response to MTR undertaken this reporting period. 4. Outline action plan to address projects with a rating of HU, U or MU. Please keep your input to 1200 words |  | Leading by WFP, the Inception Workshop took place in November 2011. Eventhough, concrete measures of the project have not yet begun, the project has made important progress on defining the implementation arrangements at local execution level and has established coordination mechanisms among local, regional, and national partners. The Project Steering Committee was established in November 2011 to guide project implementation. In August 2011, the Ministry of Environment initiated an exhaustive process of consultation and orientation with national institutions such as the Coordinating Ministry of Heritage, the National Secretariat for Planning and Development (SENPLADES), the Technical Secretariat for International Cooperation (SETECI), the Ministry of Economy and the National Central Bank to demonstrate that the project is aligned with national priorities. This is an Ecuadorian request to allow implementation to any project. WFP supported and worked together with MAE during this process for almost one year. In August 2012 the Government of Ecuador declared that the project fits within national priorities and can therefore be executed with international funds in Ecuador. After that point, MAE was able to open a bank account on the Ecuadorian Central Bank (TE Account) to manage resources from this project under the United Nations harmonized approach to cash transfer (HACT) modality. During the first semester of 2012, at MAE´s request due to lack of the TE account, WFP was in charge of the acquisition of office equipment for project activities through competitive processes; and, the selection processes to hire the National Project Manager, Project Assistant and 12 technical project staff. The Project Manager was hired in April 2012 and the rest of the project team in September 2012. The project team was trained on climate change, food security and gender topics. The technical staff was trained to conduct the vulnerability and base line study – designed by MAE, which is underway on the targeted areas to determine the base line and design the adaptation plans at parish level within a participatory process. From the plans, the adaptation measures will be defined with targeted communities. The project had been integrated within existing climate change programmes with a strong feedback mechanism to learn from and contribute to other projects. A value added of this project is viewing gender as a critical component linked to ensuring project sustainability, through systematic capacity building and integration of women into decision-making structures. During the last semester of the year all stakeholders and project team have been working to create a sound environment for implementation, and design the main tools for investigation and management. The project team has developed a detailed work plan to accelerate implementation and rapidly advance project results in 2013. A strong commitment from all project stakeholders is setting and enforcing deadlines for remaining on track in 2013.
Rating Definitions
|  |  | Highly Satisfactory (HS) | Project actions/activities planned for current reporting period are progressing on track or exceeding expectations to achieve all major outcomes/outputs for given reporting period, without major shortcomings. The project can be presented as “good practice”.
|  |  | Satisfactory (S) | Project actions/activities planned for current reporting period are progressing on track to achieve most of its major outcomes/outputs with only minor shortcomings.
|  |  | Marginally Satisfactory (MS) | Project actions/activities planned for current reporting period are progressing on track to achieve most major relevant outcomes/outputs, but with either significant shortcomings or modest overall relevance.
|  |  | Marginally Unsatisfactory (MU) | Project actions/activities planned for current reporting period are not progressing on track to achieve major outcomes/outputs with major shortcomings or is expected to achieve only some of its major outcomes/outputs.
|  |  | Unsatisfactory (U) | Project actions/activities planned for current reporting period are not progressing on track to achieve most of its major outcomes/outputs.
|  |  | Highly Unsatisfactory (HU) | Project actions/activities planned for current reporting period are not on track and shows that it is failing to achieve, and is not expected to achieve, any of its outcomes/outputs.

## Project Indicators
PROJECT Indicators
Please provide all indicators being tracked for the project as outlined in the project document
Type of Indicator (indicators towards Objectives, Outcomes, etc…)
Type of Indicator | Indicator | Baseline | Progress since inception | Target for Project End
Impact | Threat level to ecosystems, related to climate change effects | Ecosystems rated as high vulnerability | During the design of the methodology for the vulnerability study, an ecosystem approach was considered. To strengthen food provision to vulnerable communities. | The vulnerability level of ecosystems in the project area, are rated as medium
Impact | Household consumption score | Food consumption less than 30 for 80% of population | The project is conducting the vulnerability study which will establish the base line. | Food consumption score improves (> 35/40) for all targeted participants
Outcome 1.1. | Number of adaptation plans implemented at the community level, and incorporated in the district development plan | No community adaptation plans under development | The first step to design adaptation plans is to determine the base line and the necessities of the communities. After the study is finished the plans will be developed during 2013. | 50 parishes (39 parishes for the CCRJ and 11 for the GPP ) develop adaptation plans to climate change risk, in a participatory process
Output 1.1.1 | Number of targeted population aware of climate change impacts and appropriate responses to threats | Limited knowledge by vulnerable parishes in the adaptation measures to reduce food insecurity | During 2013 the capacity building plan will be implemented on climate change, food and nutrition security and gender. The plan is under design. | At least one family member out of 15,000 households have knowledge of climate threats and adaptation measures
Output 1.1.2 | Awareness raised at community level of climate change threats | Limited awareness by parishes of climate threats and local responses | During 2013 the capacity building plan will be implemented on climate change, food and nutrition security and gender. The plan is under design. | Two 4 year awareness campaigns (one for the CCRJ and one for GPP) have been established and implemented
Output 1.1.3 | Food security training plan integrated within the adaptation training programs, with gender considerations. | Neither adaptation plans have integrated food security component, nor any development plans | During 2013 the adaptation plans will be finalized and will consider elements from the gender mainstreaming strategy, capacity building strategy and plan on climate change, food and nutrition security and gender. | All the developed adaptation plans, include a food security training plan. At least 40% of the participants in the training programs are women
Outcome 1.2 | Number of planning frameworks at provincial and canton level include change adaptation considerations | Each of the targeted cantons has a development plan, that includes environmental issues, but it does not include adaptation measures | During 2013 the project will interact more closely with local governments to incorporate climate change, food and nutrition security and gender in local planning. | All the targeted cantons and provinces have incorporated climate change variability and adaptation considerations
Outcome 1.2 | Number of parishes with adaptation plans aligned with local and provincial priorities | Each district by law must have a development plan developed by March 2011. These plans include environmental issues |  | 50 parishes have developed their adaptation plans, aligned with local and provincial priorities, are used as a decision making tool
Outcome 1.2 | Number of adaptation plans, developed with community participation. | There are no climate change adaptation plans developed with active community participation | The vulnerability study is carried out with local participation, laying the groundwork for community participation in adaptation plan design process. | 50 parishes have participated in the adaptation plan development, with 50% of women in parishes participating
Output 1.2.1. | Number of adaptation plans with a vulnerability reduction and food security approach | There are no adaptation plans for targeted cantons and parishes with this focus | With the results from the vulnerability study, the adaptation plans will be developed through a participatory process in targeted parishes. | All targeted canton and community adaptation plans incorporate vulnerability reduction and food security solutions
Output 1.2.2. | Number of parishes and community leaders that participate in the process to develop adaptation plans | There are no adaptation plans developed with community participation. |  | 50 parishes, including leaders and citizens have actively participated in the adaptation plans development
Output 1.2.3. | Number of institutions with increased capacity to manage adverse climate change events | No agreements in the targeted project area. | CCRJ has signed local agreements with communities from the Jubones River Basin. The operational structure for partnerships has not yet been determined. | 50 parishes sign agreements with required stakeholders
Output 1.2.4. | Number of women that are community leaders with an actively participation in adaptation plans development, and decision making processes. | Limited participation of women and limited decision making roles | The capacity development strategy considers the training of local women leaders in targeted areas, such as mechanisms to promote the participation and empowerment of women. | Women involved in decision making in all parishes
Outcome 1.3. | Disaster preparedness score. | Limited disaster preparedness knowledge in local governments of targeted parishes | The project is gathering the information needed to implement the activities regarding this indicator | Disaster preparedness score equal to or greater than 7, indicating local government capacity in disaster preparedness ad food security information with WFP support
Outcome 1.3. | Percentage of early warning systems that meet national meteorological standards that are used on place | No early warning systems to cope with main disasters on place | During 2013, in close collaboration between MAE, INAHMI, SNGR and MAGAP a methodology to design community early warning and monitoring systems will be developed. The methodology will help to determine the type of warning to be implemented as well as the agro climatic information needed by communities and the strategy to incorporate them in local governments. | 50 systems in place and parishes able to take appropriate response actions following protocols
Output 1.3.1. | Number of vulnerable cantons with a designed early warning system and protocols | No early warning systems to cope with main disasters on place |  | 50 parishes have designed their early warning systems and protocols
Output 1.3.2. | A basic community based system for risk monitoring | No community monitoring system on place |  | 30 parishes have a monitoring system to track climate events
Output 1.3.3. | A project results and lessons learned monitoring system | No monitoring system |  | Document with project lesson learned and validated models to be replicated
Outcome 2.1. | Community adaptation asset score (natural and physical) | No adaptive capacity is implemented in the targeted rural parishes | The vulnerability study will provide the information to calculate this score in 2013. | 50 parishes have reduced their risk and implemented adaptation measures Asset score threshold set to capture increase (created or restored) in community adaptation assets over base level communities
Outcome 2.1. | Percentage of households in targeted parishes with increased capacity to manage climate risk desegregated by gender | Initial survey of targeted households | The vulnerability study includes community surveys. The data will be completed in 2013. | At least one member of each targeted household has received training and increased their understanding of climate risk and management 50% of the household participants are women
Output 2.1.1. | Number of parishes that have implemented concrete adaptation measures | No community activities implemented in the targeted rural parishes | No adaptation measures have been implemented, the project is working on the Vulnerability Study. The Project has planned to implement some measures in 14 parishes next year | 50 parishes have implemented at least 3 concrete adaptation measures
Output 2.1.2. | Physical assets implemented | Limited number of physical assets in place | No physical assets have been implemented, the project is working on the Vulnerability Study. The Project has planned to implement some measures in 14 parishes next year. | Assets created according to community plans
Output 2.1.3. | Natural resources assets implemented | Limited number of natural assets in place to withstand or adapt to climate change events | No natural resourses assets have been implemented, the project is working on the Vulnerability Study. The Project has planned to implement some measures in 14 parishes next year. | Activities implemented according to community plans
Output 2.1.4. | Number of technological instruments to address climate threats identified | No technologies related to adaptation to climate change in place | The vulnerability study includes community surveys. The data will be completed in 2013. | The GPP and the CCRJ have identified the adaptation technologies needed to address climate change on each of the targeted parishes
Output 2.1.5. | Number of parishes that receive incentives to implement physical/natural resources assets | Payment for ecosystem services has not been implemented before in the targeted project area | No incentives have been given, the project is working on the Vulnerability Study. The Project has planned to implement activities regarding this indicator next year. | To be determined according to community plans
Outcome 2.2. | Coordination mechanisms among parishes, local governments, provincial governments in place | Limited coordination among the main involved institutions to implement the adaptation measures | The Project has signed memorandum of understandings with local implementing partners. When the adaptation measures are identified, other agreements with local actors will be signed. | There is a letter of interest among all the involved entities to manage jointly climate change risks in the targeted cantons
Outcome 2.2. | Percentage of local governments and key stakeholders at national, provincial and local level that access to climate change relevant information | Climate change and variability information is insufficient and not up-dated Access is limited | Project strategy considers information, lessons learn and best practice dissemination. | Project stakeholders are able to access to up-dated information
Output 2.2.1. | Parishes agree and support with decisions taken | Limited community participation on decision making processes | Project strategy considers community participation and empowers women's participation in decision making. | All of the proposed activities in the project have a participatory implementation strategy 50% of the participants are women.
Output 2.2.2. | Number of workshops to disseminate de information | No documented information available | The Project does not have yet documented information about the parishes experiences because the project is just starting | Each of the targeted parishes has by the end of the project documented their experience
Output 2.2.2. | Number of visits to other parishes, not targeted in this project, to disseminate the information | No visits have been carried out | The Project does not have yet documented information about the parishes experiences because the project is just starting | The most successful experiences, as well as the worst ones are documented

## Lessons Learned
QUALITATIVE MEASURES and LESSONS LEARNED
Please complete the following section every reporting period
Implementation and Adaptive Management | Response
What implementation issues/lessons, either positive or negative, affected progress? | The project produces continuous lessons learned, as it is the first initiative in Ecuador addressing climate change, food security and gender. The project has raised strong commitment of national institutions, working together to reach project outcomes. All results and best practices will be taken into consideration by the Government of Ecuador in new initiatives. The project strongly involves expertise at the local level and therefore has strong country and community ownership. A positive element of implementation is that the project has been well received at local level because the communities recognize the importance of food security as a fundamental necessity, and value the approach to face climate change threats. The main concern of the project to ensure accountability and project outcomes was the implementation mechanisms, roles and responsibilities of stakeholders. HACT modality was chosen to execute project funds which means that disbursements are made directly by WFP to the executing entity (MAE), for which MAE is accountable for applying national procedures, or the national entity relies on the WFP’s procurement and other systems.
Were there any delays in implementation? If so, include any causes of delays. What measures have been taken to reduce delays? | Yes, the project faces delays in implementation. The delays have been explained in the rating section. Project implementation faced important challenges to set up clear stakeholders roles and responsibilities and to have in place all mechanisms required to manage resources. Project start up required flexibility in roles, with WFP assuming hiring and procurement due to constrains in MAE processes and to assure accountability. Another important measure implemented was the establishment of a Project Steering Committed to guide project implementation and set deadlines to achieve results.
Describe any changes undertaken to improve results on the ground or any changes made to project outputs (i.e. changes to project design) | n/a
How have gender considerations been taken into consideration during the reporting period? What have been the lessons learned as a consequence of inclusion of such considerations on project performance or impacts? | A value added of this project is viewing gender as a critical component linked to ensuring project sustainability, through systematic capacity building and integration of women into decision-making structures. This project has a very strong potential to demonstrate the concrete ways in which women can be effectively integrated into decision-making structures to ensure resilience to the impacts of climate change. During this period a very close relationship with UN Women has helped to deepen the consideration for the interaction of women and climate change. A consultancy to design a strategy for gender mainstreaming in the project is underway. Another consultancy to determine gender baseline in targeted parishes is been contracted.
Please complete the following section at mid-term and project completion
Lessons for Adaptation | Response
Climate Resilience Measures
What have been the lessons learned, both positive and negative, in implementing climate adaptation measures that would be relevant to the design and implementation of future projects/programmes for enhanced resilience to climate change? | n/a
What is the potential for the climate resilience measures undertaken by the project/programme to be replicated and scaled up both within and outside the project area? | n/a
Concrete Adaptation Interventions
What have been the lessons learned, both positive and negative, in implementing concrete adaptation interventions that would be relevant to the design and implementation of future projects/programmes implementing concrete adaptation interventions? | Planning with communities is very positive to design concrete adaptation measures because them raised from their own needs, but this planning needs time during project implementation.
What is the potential for the concrete adaptation interventions undertaken by the project/programme to be replicated and scaled up both within and outside the project area? | n/a
Community/National Impact
What would you consider to be the most successful aspects for the target communities? | n/a
What measures are/have been put in place to ensure sustainability of the project/program results? | n/a
What measures are being/could have been put in place to improve project/program results? | n/a
Knowledge Management
How has existing information/data/knowledge been used to inform project development and implementation? What kinds of information/data/knowledge were used? | MAE within another project has designed a methodology for vulnerability studies on climate change. This methodology was adapted to this project incorporating food and nutrition security and gender dimensions. This project also used information produced by a study carried out by WFP and CIFFEN which assessed climate change threats on food and nutrition security in Ecuador. The Ecuador´s Nutrition Survey carried out by WFP has also contributed to this project.
If learning objectives have been established, have they been met? Please describe. | n/a
Describe any difficulties there have been in accessing or retrieving existing information (data or knowledge) that is relevant to the project. Please provide suggestions for improving access to the relevant data. | n/a
Has the identification of learning objectives contributed to the outcomes of the project? In what ways have they contributed? | Yes, They have helped to focus discussion on food security as it is very broad with respect to climate change. Also help to identify clear gender empowerment related objectives. They also kept the discussion on track when identifying indicators for the vulnerability study.

## Results Tracker
Results Tracker for Adaptation Fund (AF) Projects
Goal: Assist developing-country Parties to the Kyoto Protocol that are particularly vulnerable to the adverse effects of climate change in meeting the costs of concrete adaptation projects and programmes in order to implement climate-resilient measures. Impact: Increased resiliency at the community, national, and regional levels to climate variability and change.
Important: Please read the following Results Framework and Baseline Guidance (also posted on the Adaptation Fund website) before entering your data
Link: http://www.adaptation-fund.org/sites/default/files/Results%20Framework%20and%20Baseline%20Guidance%20final.pdf
Please select the relevant Fund level Outcome and Output indicators that allign with the project objectives and outcomes
OBJECTIVE 1
Fund Outcome | Please select from dropdown menu below | Fund Outcome Indicator | Please select from dropdown menu below | Target at project approval (see Units in next sheet) | Baseline (see Units in next sheet) | Mid-term Results | Terminal Results
Outcome 1: Reduced exposure at national level to climate-related hazards and threats Outcome 2: Strengthened institutional capacity to reduce risks associated with climate-induced socioeconomic and environmental losses Outcome 3: Strengthened awareness and ownership of adaptation and climate risk reduction processes at local level Outcome 4: Increased adaptive capacity within relevant development and natural resource sectors Outcome 5: Increased ecosystem resilience in response to climate change and variability-induced stress Outcome 6: Diversified and strengthened livelihoods and sources of income for vulnerable people in targeted areas Outcome 7: Improved policies and regulations that promote and enforce resilience measures | 3 | 1. Relevant threat and hazard information generated and disseminated to stakeholders on a timely basis 2.1. No. and type of targeted institutions with increased capacity to minimize exposure to climate variability risks 2.2. Number of people with reduced risk to extreme weather events 3.1. Percentage of targeted population aware of predicted adverse impacts of climate change, and of appropriate responses 3.2. Modification in behavior of targeted population 4.1. Development sectors' services responsive to evolving needs from changing and variable climate 4.2. Physical infrastructure improved to withstand climate change and variability-induced stress 5. Ecosystem services and natural assets maintained or improved under climate change and variability-induced stress 6.1. Percentage of households and communities having more secure (increased) access to livelihood assets 6.2. Percentage of targeted population with sustained climate-resilient livelihoods 7. Climate change priorities are integrated into national development strategy | 3.1 | 1 | 1
Fund Output | Please select from dropdown menu below | Fund Output Indicator | Please select from dropdown menu below | Target at project approval (see Units in next sheet) | Baseline (see Units in next sheet) | Mid-term Results | Terminal Results
Output 1: Risk and vulnerability assessments conducted and updated at a national level Output 2.1: Strengthened capacity of national and regional centres and networks to respond rapidly to extreme weather events Output 2.2: Targeted population groups covered by adequate risk reduction systems Output 3: Targeted population groups participating in adaptation and risk reduction awareness activities Output 4: Vulnerable physical, natural, and social assets strengthened in response to climate change impacts, including variability Output 5: Vulnerable physical, natural, and social assets strengthened in response to climate change impacts, including variability Output 6: Targeted individual and community livelihood strategies strengthened in relation to climate change impacts, including variability Output 7: Improved integration of climate-resilience strategies into country development plans | 3 | 1.1. No. and type of projects that conduct and update risk and vulnerability assessments 1.2. Development of early warning systems 2.1.1. No. of staff trained to respond to, and mitigate impacts of, climate-related events 2.1.2. Capacity of staff to respond to, and mitigate impacts of, climate-related events from targeted institutions increased 2.2.1. Percentage of population covered by adequate risk-reduction systems 2.2.2. No. of people affected by climate variability 3.1 No. and type of risk reduction actions or strategies introduced at local level 3.2 No. of news outlets in the local press and media that have covered the topic 4.1. No. and type of health or social infrastructure developed or modified to respond to new conditions resulting from climate variability and change (by type) 4. 2. No. of physical assets strengthened or constructed to withstand conditions resulting from climate variability and change (by asset types) 5. No. and type of natural resource assets created, maintained or improved to withstand conditions resulting from climate variability and change (by type of assets) 6.1. No. and type of adaptation assets (physical as well as knowledge) created in support of individualor community-livelihood strategies 6.2. Type of income sources for households generated under climate change scenario 7.1. No., type, and sector of policies introduced or adjusted to address climate change risks 7.2. No. or targeted development strategies with incorporated climate change priorities enforced | 3.1
OBJECTIVE 2
Fund Outcome | Please select from dropdown menu below | Fund Outcome Indicator | Please select from dropdown menu below | Target at project approval (see Units in next sheet) | Baseline | Mid-term Results | Terminal Results
Outcome 1: Reduced exposure at national level to climate-related hazards and threats Outcome 2: Strengthened institutional capacity to reduce risks associated with climate-induced socioeconomic and environmental losses Outcome 3: Strengthened awareness and ownership of adaptation and climate risk reduction processes at local level Outcome 4: Increased adaptive capacity within relevant development and natural resource sectors Outcome 5: Increased ecosystem resilience in response to climate change and variability-induced stress Outcome 6: Diversified and strengthened livelihoods and sources of income for vulnerable people in targeted areas Outcome 7: Improved policies and regulations that promote and enforce resilience measures | 5 | 1. Relevant threat and hazard information generated and disseminated to stakeholders on a timely basis 2.1. No. and type of targeted institutions with increased capacity to minimize exposure to climate variability risks 2.2. Number of people with reduced risk to extreme weather events 3.1. Percentage of targeted population aware of predicted adverse impacts of climate change, and of appropriate responses 3.2. Modification in behavior of targeted population 4.1. Development sectors' services responsive to evolving needs from changing and variable climate 4.2. Physical infrastructure improved to withstand climate change and variability-induced stress 5. Ecosystem services and natural assets maintained or improved under climate change and variability-induced stress 6.1. Percentage of households and communities having more secure (increased) access to livelihood assets 6.2. Percentage of targeted population with sustained climate-resilient livelihoods 7. Climate change priorities are integrated into national development strategy | 5
Fund Output | Please select from dropdown menu below | Fund Output Indicator | Please select from dropdown menu below | Target at project approval (see Units in next sheet) | Baseline | Mid-term Results | Terminal Results
Output 1: Risk and vulnerability assessments conducted and updated at a national level Output 2.1: Strengthened capacity of national and regional centres and networks to respond rapidly to extreme weather events Output 2.2: Targeted population groups covered by adequate risk reduction systems Output 3: Targeted population groups participating in adaptation and risk reduction awareness activities Output 4: Vulnerable physical, natural, and social assets strengthened in response to climate change impacts, including variability Output 5: Vulnerable physical, natural, and social assets strengthened in response to climate change impacts, including variability Output 6: Targeted individual and community livelihood strategies strengthened in relation to climate change impacts, including variability Output 7: Improved integration of climate-resilience strategies into country development plans | 5 | 1.1. No. and type of projects that conduct and update risk and vulnerability assessments 1.2. Development of early warning systems 2.1.1. No. of staff trained to respond to, and mitigate impacts of, climate-related events 2.1.2. Capacity of staff to respond to, and mitigate impacts of, climate-related events from targeted institutions increased 2.2.1. Percentage of population covered by adequate risk-reduction systems 2.2.2. No. of people affected by climate variability 3.1 No. and type of risk reduction actions or strategies introduced at local level 3.2 No. of news outlets in the local press and media that have covered the topic 4.1. No. and type of health or social infrastructure developed or modified to respond to new conditions resulting from climate variability and change (by type) 4. 2. No. of physical assets strengthened or constructed to withstand conditions resulting from climate variability and change (by asset types) 5. No. and type of natural resource assets created, maintained or improved to withstand conditions resulting from climate variability and change (by type of assets) 6.1. No. and type of adaptation assets (physical as well as knowledge) created in support of individualor community-livelihood strategies 6.2. Type of income sources for households generated under climate change scenario 7.1. No., type, and sector of policies introduced or adjusted to address climate change risks 7.2. No. or targeted development strategies with incorporated climate change priorities enforced | 5
OBJECTIVE 3
Fund Outcome | Please select from dropdown menu below | Fund Outcome Indicator | Please select from dropdown menu below | Target at project approval (see Units in next sheet) | Baseline | Mid-term Results | Terminal Results
Outcome 1: Reduced exposure at national level to climate-related hazards and threats Outcome 2: Strengthened institutional capacity to reduce risks associated with climate-induced socioeconomic and environmental losses Outcome 3: Strengthened awareness and ownership of adaptation and climate risk reduction processes at local level Outcome 4: Increased adaptive capacity within relevant development and natural resource sectors Outcome 5: Increased ecosystem resilience in response to climate change and variability-induced stress Outcome 6: Diversified and strengthened livelihoods and sources of income for vulnerable people in targeted areas Outcome 7: Improved policies and regulations that promote and enforce resilience measures |  | 1. Relevant threat and hazard information generated and disseminated to stakeholders on a timely basis 2.1. No. and type of targeted institutions with increased capacity to minimize exposure to climate variability risks 2.2. Number of people with reduced risk to extreme weather events 3.1. Percentage of targeted population aware of predicted adverse impacts of climate change, and of appropriate responses 3.2. Modification in behavior of targeted population 4.1. Development sectors' services responsive to evolving needs from changing and variable climate 4.2. Physical infrastructure improved to withstand climate change and variability-induced stress 5. Ecosystem services and natural assets maintained or improved under climate change and variability-induced stress 6.1. Percentage of households and communities having more secure (increased) access to livelihood assets 6.2. Percentage of targeted population with sustained climate-resilient livelihoods 7. Climate change priorities are integrated into national development strategy
Fund Output | Please select from dropdown menu below | Fund Output Indicator | Please select from dropdown menu below | Target at project approval (see Units in next sheet) | Baseline | Mid-term Results | Terminal Results
Output 1: Risk and vulnerability assessments conducted and updated at a national level Output 2.1: Strengthened capacity of national and regional centres and networks to respond rapidly to extreme weather events Output 2.2: Targeted population groups covered by adequate risk reduction systems Output 3: Targeted population groups participating in adaptation and risk reduction awareness activities Output 4: Vulnerable physical, natural, and social assets strengthened in response to climate change impacts, including variability Output 5: Vulnerable physical, natural, and social assets strengthened in response to climate change impacts, including variability Output 6: Targeted individual and community livelihood strategies strengthened in relation to climate change impacts, including variability Output 7: Improved integration of climate-resilience strategies into country development plans |  | 1.1. No. and type of projects that conduct and update risk and vulnerability assessments 1.2. Development of early warning systems 2.1.1. No. of staff trained to respond to, and mitigate impacts of, climate-related events 2.1.2. Capacity of staff to respond to, and mitigate impacts of, climate-related events from targeted institutions increased 2.2.1. Percentage of population covered by adequate risk-reduction systems 2.2.2. No. of people affected by climate variability 3.1 No. and type of risk reduction actions or strategies introduced at local level 3.2 No. of news outlets in the local press and media that have covered the topic 4.1. No. and type of health or social infrastructure developed or modified to respond to new conditions resulting from climate variability and change (by type) 4. 2. No. of physical assets strengthened or constructed to withstand conditions resulting from climate variability and change (by asset types) 5. No. and type of natural resource assets created, maintained or improved to withstand conditions resulting from climate variability and change (by type of assets) 6.1. No. and type of adaptation assets (physical as well as knowledge) created in support of individualor community-livelihood strategies 6.2. Type of income sources for households generated under climate change scenario 7.1. No., type, and sector of policies introduced or adjusted to address climate change risks 7.2. No. or targeted development strategies with incorporated climate change priorities enforced
OBJECTIVE 4
Fund Outcome | Please select from dropdown menu below | Fund Outcome Indicator | Please select from dropdown menu below | Target at project approval (see Units in next sheet) | Baseline | Mid-term Results | Terminal Results
Outcome 1: Reduced exposure at national level to climate-related hazards and threats Outcome 2: Strengthened institutional capacity to reduce risks associated with climate-induced socioeconomic and environmental losses Outcome 3: Strengthened awareness and ownership of adaptation and climate risk reduction processes at local level Outcome 4: Increased adaptive capacity within relevant development and natural resource sectors Outcome 5: Increased ecosystem resilience in response to climate change and variability-induced stress Outcome 6: Diversified and strengthened livelihoods and sources of income for vulnerable people in targeted areas Outcome 7: Improved policies and regulations that promote and enforce resilience measures |  | 1. Relevant threat and hazard information generated and disseminated to stakeholders on a timely basis 2.1. No. and type of targeted institutions with increased capacity to minimize exposure to climate variability risks 2.2. Number of people with reduced risk to extreme weather events 3.1. Percentage of targeted population aware of predicted adverse impacts of climate change, and of appropriate responses 3.2. Modification in behavior of targeted population 4.1. Development sectors' services responsive to evolving needs from changing and variable climate 4.2. Physical infrastructure improved to withstand climate change and variability-induced stress 5. Ecosystem services and natural assets maintained or improved under climate change and variability-induced stress 6.1. Percentage of households and communities having more secure (increased) access to livelihood assets 6.2. Percentage of targeted population with sustained climate-resilient livelihoods 7. Climate change priorities are integrated into national development strategy
Fund Output | Please select from dropdown menu below | Fund Output Indicator | Please select from dropdown menu below | Target at project approval (see Units in next sheet) | Baseline | Mid-term Results | Terminal Results
Output 1: Risk and vulnerability assessments conducted and updated at a national level Output 2.1: Strengthened capacity of national and regional centres and networks to respond rapidly to extreme weather events Output 2.2: Targeted population groups covered by adequate risk reduction systems Output 3: Targeted population groups participating in adaptation and risk reduction awareness activities Output 4: Vulnerable physical, natural, and social assets strengthened in response to climate change impacts, including variability Output 5: Vulnerable physical, natural, and social assets strengthened in response to climate change impacts, including variability Output 6: Targeted individual and community livelihood strategies strengthened in relation to climate change impacts, including variability Output 7: Improved integration of climate-resilience strategies into country development plans |  | 1.1. No. and type of projects that conduct and update risk and vulnerability assessments 1.2. Development of early warning systems 2.1.1. No. of staff trained to respond to, and mitigate impacts of, climate-related events 2.1.2. Capacity of staff to respond to, and mitigate impacts of, climate-related events from targeted institutions increased 2.2.1. Percentage of population covered by adequate risk-reduction systems 2.2.2. No. of people affected by climate variability 3.1 No. and type of risk reduction actions or strategies introduced at local level 3.2 No. of news outlets in the local press and media that have covered the topic 4.1. No. and type of health or social infrastructure developed or modified to respond to new conditions resulting from climate variability and change (by type) 4. 2. No. of physical assets strengthened or constructed to withstand conditions resulting from climate variability and change (by asset types) 5. No. and type of natural resource assets created, maintained or improved to withstand conditions resulting from climate variability and change (by type of assets) 6.1. No. and type of adaptation assets (physical as well as knowledge) created in support of individualor community-livelihood strategies 6.2. Type of income sources for households generated under climate change scenario 7.1. No., type, and sector of policies introduced or adjusted to address climate change risks 7.2. No. or targeted development strategies with incorporated climate change priorities enforced

## Units for Indicators
Fund Outcome Indicator Units
1. Generation of relevant data, Stakeholders, and Timeliness 2.1. Include both qualitative and quantitative measures of capacity level within targeted institutions 2.2. Number (men and women and other vulnerable groups) 3.1. Use scale from 1 to 5: 5: Fully aware 4: Mostly aware 3: Partially aware 2: Partially not aware 1: Aware of neither predicted adverse impacts of climate change nor of appropriate responses 3.2. Use scale from 1 to 5: 5: All 4: Almost all 3: Half 2: Some 1: None 4.1. Summarize in an overall scale (1-5): 5: Highly responsive (All defined elements ) 4: Mostly responsive (Most defined elements) 3: Moderately responsive (Some defined elements) 2: Partially responsive (Lacks most elements) 1: Non responsive (Lacks all elements ) 4.2. Summarize in an overall scale (1-5): 5: Fully improved 4: Mostly Improved 3: Moderately improved 2: Somewhat improved 1: Not improved 5. Depends on the targeted natural asset: Biological (species): measure through changes in population numbers (dynamics, structure, etc.) Land: measure changes in hectares. Baseline data will be necessary to estimate the change. Supporting indicators baseline and target (as well as contextual information) are needed such as the following: Farmers adopting recommended technologies, Ha. of land improved, Average deforestation rate Etc. Use scale from 1 to 5. 5: Very effective (All elements are present) 4: Effective (Most elements are present) 3: Moderately effective (Some elements are present) 2: Partially effective (Most elements are not present) 1: Ineffective (No elements are present) 6.1. Summarize in an overall scale (1-5): 5: Very high improvement 4: High improvement 3: Moderate improvement 2: Limited improvement 1: No improvement 6.2. Household income by source of livelihood in project area (USD) prior and post project intervention 7. Summarize in an overall scale (1-5). 5: All (Fully integrated) 4: Most 3: Some 2: Most not integrated 1: None
Fund Output Indicator Units
1.1. Number, sector(s) and level(s) of projects or interventions in separate fields of monitoring plan 1.2. Number 2.1.1. Number of staff (male/female) of targeted institutions: a. Obtain baseline information: total number of staff from targeted institutions b. Define target 2.1.2. Number of staff (male/female) of targeted institutions: a. Obtain baseline information: total number of staff from targeted institutions b. Define target: needs to be defined by project proponents 2.2.1. Quantitative: Percentage (includes women – and other vulnerable groups – and men). Qualitative: Adequacy: include direct analysis of major areas; adequacy/effectiveness of systems or analysis of perceptions of populations and institutions. 2.2.2. Number (broken down by gender and, if possible, by vulnerable groups defined in the area of intervention) of people 3.1. Number and type (in separate columns) at local level. 3.2. Number 4.1. Number and type 4. 2. Number and type (entered in separate columns) 5. Number of interventions by type of natural asset and intervention 6.1. Number and type (in separate columns of monitoring plan) 6.2. Income sources per household; description of income source and number of households. 7.1. Number/Sector 7.2. Number; Effectiveness (see previous indicator) through enforcement level.