## Overview
Project Performance Report (PPR)
| Period of Report (Dates) | July 2014 - June 2015
| Project Title: | Reduction of Risks and Vulnerability Based on Flooding and Droughts in the Estero Real River Watershed.
| Project Summary: | The Program's objective is to reduce the risks of droughts and flooding caused by climate change and variability in the Estero Real River Watershed in the Departments of Leon and Chinandega, the Estero River (3,690 km2), and especially the sub-watershed of the Villanueva River (1,290 km2), also known as the Rio Grande or Aquespalapa - typical of the combined effects of poor development models and strong climate variability. It will be carried out by investing in water collection, the use of agro-ecological best practices in farms for more effective use of existing resources, capacity building in local communities, municipalities and government institutions by formulating and implementing policies, plans and programs that reduce enviornmental variability and promote the sustainable management of natural resources, the recuperation of the ecosystems and the population's access to a healthy environment, thus promoting climate change adaptation and also providing the means to apply the national Climate Change strategy.
|  |  | Countries | Project Type: |  | GEF Focal Area: | GEF 4 Focal Areas | GEF 2 / 3 Operational Programme: | Overall Rating of the project in the evaluation by the project evaluator: | GEF-4 Focal Area Strategic Program: | GEF-3 Focal Area Strategic Program:
| Database Number: | PIMS # 4448 | Afghanistan | FP | Yes | Biodiversity | 1 | 1 | U | BD-SP1-PA Financing | 1: Arid & semi-arid ecosystems
Implementing Entity (IE) [name]: |  | United Nations Development Program | Albania | MSP | No | Climate Change Adaptation | 2 | 2 | S | BD-SP2-Marine PA | 2: Coastal, marine & freshwater ecosystems
| Type of IE: | Multilateral | Algeria | EA |  | Climate Change Mitigation | 3 | 3 | MU | BD-SP3-PA Networks | 3: Forest ecosystems
| Country(ies): | Nicaragua | Angola |  |  | International Waters | 5 | 5 | Good | BD-SP5-Markets | 13: Conservation and Sustainable Use of Biological Diversity Important to Agriculture
Relevant Geographic Points (i.e. cities, villages, bodies of water): |  | Watershed of the Estero Real River, sub watershed of Villanueva River. | Argentina |  |  | Multiple Focal Area |  |  |  | BD-SP7-Invasive Alien Species(IAS) | 6: Promoting the adoption of renewable energy by removing barriers and reducing implementation costs
[8 empty] | CC-SP2- Industrial EE | 8: Waterbody based operational program
| Project Milestones | [6 empty] | CC-SP3-RE,CC-SP4-Biomass | 9: Integrated Land and Water multiple focal area
| Milestone |  | Bahamas | [6 empty] | CC-SP5-Transport | 10: Contaminants based operational program
AFB Approval Date: |  | December, 2010
IE-AFB Agreement Signature Date: |  | March, 2011 | [6 empty] | CC-SP6-LULUCF | 12: Integrated Ecosystem Management
Start of Project/Programme: |  | 40718 | [6 empty] | Cross cutting capacity building | 14: Persistent Organic Pollutants
Mid-term Review Date (if planned): |  | April, 2014
| Terminal Evaluation Date: | October, 2015
|  | List documents/ reports/ brochures / articles that have been prepared about the project. | Cyprus
|  | M&E Documents: - Informes Trimestrales (PNUD), Informe de Gestión Ano 2011, 2012, 2013, 2014 y primer semestre 2015 (Gobierno) - Auditoria Social del Proyecto. - Informe de Evaluación de Medio termino Policy and planning documents - Reglamento Operativo del Programa Reducción de riesgos y vulnerabilidad ante inundaciones y sequías en la cuenca del Río Estero Real - ocho Planes Municipales de Proteccion Ambiental de las familias ante el Cambio Climático, ocho Planes de Manejo de Microcuencas y uno de la Subcuenca del Río Villanueva - Desarrollo de Indicadores Socio - ambientales de adaptación al cambio climatico para el monitoreo de la subcuenca del Río Grande / Río Villanueva de la cuenca del Río Estero Real - Informe de Seguimiento y Monitoreo a los Planes de Transformación Agroecologica 2012 - 2013, - Diagnostico de Género, Estrategia de Género Programa Estero Real, Estrategia para la compensación ambiental por manejo de regeneración natural en zonas de recarga hídrica y riparias, Technical studies, guides and reports: -Guía Metodológica para la Elaboración de Planes de Transformación Agroecológica de Fincas; Informes de Seguimiento Mensual (Gobierno) - Estudio de Delimitación de Zonas Riparias y Recargas Hídricas - Estudio de amenazas por inundación en el área urbana de Villanueva y Poblados adyacentes - Estudio Hidrológico de la parte alta, media y baja de la subcuenca del río Villanueva, - Mapa de suelo, uso potencial y conflictos de uso de la tierra en el marco del Convenio MARENA - INETER. - mapas de incidencia de las ocho microcuencas en referencia a cambio de uso del suelo, monitoreo de puntos de calor, análisis de riesgo, sistemas de riego, sistema de inversión, informe de monitoreo de puntos de calor - Estudio de calidad y disponibiliad del agua de los Recuros Hidricos en las 08 microcuencas de la Cuenca del Estero Real - Informe de evolución de las áras bajo riego - Sistema de Riego Comunal Las Mercedes - Guía de Protección de fuentes de Agua y Rehabilitación de Bosques Riparios para la adaptación al cambio climático - Estudio base de datos sobre situación de género en las ocho microcuencas, mapeo de actores locales de las ocho microcuencas. Communication and media products: Boletines informativos en 2011 (1); 2012 (3), 2013 (4) en: http://www.sinia.net.ni/multisites/EsteroReal/ Pagina Web Programa Estero Real, 2012 al 2014 Videos: https://www.youtube.com/watch?v=OYsgt4kiM7E https://www.youtube.com/watch?v=EV0nyvci_GI https://www.youtube.com/watch?v=Ss3OIHMvIIA https://www.youtube.com/watch?v=E3q0iSz5U7A https://www.youtube.com/watch?v=y5SvEMh9vdk | Czech Republic
List the Website address (URL) of project. |  |  | Democratic People's Republic of Korea
|  | www.sinia.net.ni/multisites/EsteroReal | Democratic Republic of the Congo
Denmark
| Project contacts: |  | Djibouti
National Project Manager/Coordinator |  |  | Dominica
| Name: | Luis Humberto Picado | Dominican Republic
| Email: | lpicado2014@yahoo.com | Ecuador
| Date: | 2015-06-30 | Egypt
| Government DA |  | El Salvador
| Name: | Denis Fuentes | Equatoral Guinea
| Email: | dfuentes@marena.gob.ni | Eritrea
| Date: | 2015-06-30 | Estonia
| Implementing Entity |  | Ethiopia
| Name: | Maria Fernanda Sanchez | Fiji
| Email: | fernanda.sanchez@undp.org | Finland
| Date: | 2015-06-30 | France
| Executing Agency |  | Gambia
| Name: | Teresita Sequeira | Georgia
| Email: | tsequeira@marena.gob.ni | Germany
| Date: | 2015-06-30 | Ghana
| Executing Agency |  | Greece
| Name: |  | Grenada
| Email: |  | Guatemala
| Date: |  | Guinea
| Executing Agency |  | Guinea Bissau
| Name: |  | Guyana
| Email: |  | Haiti
| Date: |  | Honduras
Hungary
Iceland
India
Indonesia
Iran (Islamic Republic of)
Iraq
Ireland
Israel
Italy
Jamaica
Japan
Jordan
Kazakhstan
Kenya
Kiribati
Kuwait
Kyrgyzstan
Lao People’s Democratic Republic
Latvia
Lebanon
Lesotho
Liberia
Libyan Arab Jamahiriya
Liechtenstein
Lithuania
Luxembourg
Madagascar
Malawi
Malaysia
Maldives
Mali
Malta
Marshall Islands
Mauritania
Mauritius
Mexico
Micronesia, Federated States of
Monaco
Mongolia
Montenegro
Morocco
Mozambique
Myanmar
Namibia
Nauru
Nepal
Netherlands
New Zealand
Nicaragua
Niger
Nigeria
Norway
Oman
Pakistan
Palau
Panama
Papua New Guinea
Paraguay
Peru
Philippines
Poland
Portugal
Qatar
Republic of Korea
Republic of Moldova
Romania
Russian Federation
Rwanda
Saint Kitts and Nevis
Saint Lucia
Saint Vincent and the Grenadines
Samoa
San Marino
Sao Tome and Principe
Saudi Arabia
Senegal
Serbia
Seychelles
Sierra Leone
Singapore
Slovakia
Slovenia
Solomon Islands
Somalia
South Africa
Spain
Sri Lanka
Sudan
Suriname
Swaziland
Sweden
Switzerland
Syrian Arab Republic
Tajikistan
Thailand
The former Yugoslav Republic of Macedonia
Timor-Leste
Togo
Tonga
Trinidad and Tobago
Tunisia
Turkey
Turkmenistan
Tuvalu
Uganda
Ukraine
United Arab Emirates
United Kingdom of Great Britain and Northern Ireland
United Republic of Tanzania
United States of America
Uruguay
Uzbekistan
Vanuatu
Venezuela, Bolivarian Republic of
Viet Nam
Yemen
Zambia
Zimbabwe

## FinancialData
Financial information: cumulative from project start to [insert date]
DISBURSEMENT OF AF GRANT FUNDS
How much of the total AF grant as noted in Project Document plus any project preparation grant has been spent to date?
Estimated cumulative total disbursement as of June 2015 | 4926894
Add any comments on AF Grant Funds. (word limit=200)
INVESTMENT INCOME | De acuerdo al informe final del porgrama, considerando los beneficios promedios aumentados en los sistemas agroforestales equivalentes a la producción de una cosecha asegurada de una hectárea de Maíz asociada con Frijol, el valor monetario de este aumento es de US$ 1,400.00 por año. Si consideramos las 1005 fincas bajo planes de manejo esto sería un monto anual de U$1,407,000.00.
Amount of annual investment income generated from the Adaptation Fund’s grant
EXPENDITURE DATA
List ouput and corresponding amount spent for the current reporting period JULY 2014 - JUNE 2015 | ITEM / ACTIVITY / ACTION | AMOUNT
| 1. Investments in infrastructure for storing and using rain and surface water in eight micro-watersheds in the upper watershed of the Estero Real River. | 426095.62
| 2. Introduction of climate resilient agro-ecological practices to make effective use of available water. | 189931.49
| 3. Institutional development and capacity building in micro-watersheds, municipalities, and participating national institutions | 248600.82
| 4. Ongoing monitoring and analysis of climatic conditions and changes in land use, water flows and soil quality | 299105.4
| 5. Project Execution | 58403.95
| TOTAL | 1222137.28
PLANNED EXPENDITURE SCHEDULE
List outputs planned and corresponding projected cost for the upcoming reporting period | ITEM / ACTIVITY / ACTION | PROJECTED COST
| 1. Investments in infrastructure for storing and using rain and surface water in eight micro-watersheds in the upper watershed of the Estero Real River. | 16684.38 | 2015-12-31
| 2. Introduction of climate resilient agro-ecological practices to make effective use of available water. | 13674.95 | 2015-12-31
| 3. Institutional development and capacity building in micro-watersheds, municipalities, and participating national institutions | 54133.88 | 2015-12-31
| 4. Ongoing monitoring and analysis of climatic conditions and changes in land use, water flows and soil quality | 58612.79 | 2015-12-31
| TOTAL | 143106
ACTUAL CO-FINANCING (If the MTR or TE have not been undertaken this reporting period, DO NOT report on actual co-financing.)
How much of the total co-financing as committed in the Project Document has actually been realized?
Estimated cumulative actual co-financing as verified during Mid-term Review (MTR) or Terminal Evaluation (TE).
Add any comments on actual co-financing in particular any issues related to the realization of in-kind, grant, credits, loans, equity, non-grant instruments and other types of co-financing. (word limit=200)

## Procurement
PROCUREMENT DATA
Please provide information for all contracts over $2,500 USD
Please provide the number of contracts under $2,500, signed during this reporting period:
LIST OF CONTRACTS
List all contracts related to the project/program with signature dates
Contract Type | Agency / Contracted party | Contract Value/Amount (USD) | Signiture Date | Payment to Date | Remaining Balance
1. Investments in infrastructure for storing and using rain and surface water in eight micro-watersheds in the upper watershed of the Estero Real River.
SC |  | 3743.8236 | 2014-09-01 | 3743.8236 | 0
SC |  | 8232.4535 | 2014-10-08 | 8232.4535 | 0
SC |  | 5000 | 2014-11-24 | 5000 | 0
SC |  | 4898.2668 | 2014-12-19 | 4898.2668 | 0
Consultancy Contract (Individual Contract) |  | 26133.54 | 2015-06-30 | 6327.75 | 19805.79
2. Introduction of climate resilient agro-ecological practices to make effective use of available water.
Consultancy Contract (Individual Contract) |  | 2100 | 2014-09-30 | 2100 | 0
Consultancy Contract (Individual Contract) |  | 2100 | 2014-09-30 | 2100 | 0
Consultancy Contract (Individual Contract) |  | 2100 | 2014-09-30 | 2100 | 0
Consultancy Contract (Individual Contract) |  | 2100 | 2014-09-30 | 2100 | 0
SC |  | 5000 | 2014-11-24 | 5000 | 0
SC |  | 5000 | 2015-05-07 | 5000 | 0
SC |  | 10000 | 2015-06-30 | 0 | 10000
3. Training and capacity development in micro-watersheds, municipalities and participating national institutions.
SC |  | 5000 | 2014-11-24 | 5000 | 0
SC |  | 4991.598 | 2014-12-10 | 4991.598 | 0
SC |  | 4991.598 | 2014-12-10 | 4991.598 | 0
SC |  | 5000 | 2015-05-07 | 5000 | 0
SC |  | 18000 | 2015-06-30 | 0 | 18000
4. Ongoing monitoring and analysis of climatic conditions and changes in land use, water flows and soil quality
SC |  | 5000 | 2015-05-07 | 5000 | 0
Consultancy Contract (Individual Contract) |  | 5000 | 2014-05-04 | 5000 | 0
SC |  | 2500 | 2015-06-30 | 0 | 2500
BIDS
List all bids for each contact signed with date of open call and winning bid
CONTRACT & Procurement Method | Submitted Bids | Bid Amount (USD) | Winning Bid | Winning Bid Amount (USD) | Selection Justification for the Winner
1. Investments in infrastructure for storing and using rain and surface water in eight micro-watersheds in the upper watershed of the Estero Real River.
Purchase of hardware store materials for the reparation of water collection and storage facilities in the micro-watersheds of the municipalities of El Sauce, Achuapa and Villanueva. |  | 12641.6689 |  | 1472.9 | Partial awarding, for the best economic offer and for meeting the technical specifications.
8498.5481
|  | 8205.5105 |  | 5229.9475
6021.6606
Purchase of cement, for the construction of water collection and storage facilities. |  | 8779.9355 |  | 7759.4687 | For the best economic offer and for meeting the technical specifications.
10998.1025
11220.2087
Ampos purchase two carries for receipt of documents |  | 304.63 |  | 264.8956 | For the best economic offer and for meeting the technical specifications.
196.3947
Purchase of computer equipment |  | 18779.9962 |  | 1052.8302 | Partial awarding, for the best economic offer and for meeting the technical specifications.
18236.0283
|  | 8592.4528 |  | 2831.8581
20998.5396
|  | 20698.1985 |  | 13848.1155
5238.3181
Reproduction of 500 copies on Water Act |  | 546.3451 |  | 546.3451 | For the best economic offer and for meeting the technical specifications.
834.1183
Purchase office furniture |  | 19458.4789 |  | 30141.624 | For the best economic offer and for meeting the technical specifications.
12026.4695
US$ 12,512.00
34662.8674
8276.1869
11978.4371
Purchase air conditioners |  | 23987.4126 |  | 2837.3203 | Partial awarding, for the best economic offer and for meeting the technical specifications.
20481.26
19736.4503
|  | 22819.8794 |  | 17258.5682
23817.7566
Purchase of three sets of tires |  | 1928.1825 |  | 377.3939 | Partial awarding, for the best economic offer and for meeting the technical specifications.
|  | 2138.0631 |  | 541.837
|  | 2134.7803 |  | 1119.7567
Purchase cleaning products |  | 395.4792 |  | 201.3113 | Partial awarding, for the best economic offer and for meeting the technical specifications.
|  | 332.5847 |  | 174.2347
Purchase of several café |  | 649.7255 |  | 649.7255 | Unique offer
Purchase of materials and equipment of office |  | 1133.089 |  | 393.4412 | Partial awarding, for the best economic offer and for meeting the technical specifications.
|  | 1063.5212 |  | 672.1142
Purchase bond paper |  | 874.4837 |  | 1018.7758 | For the best economic offer and for meeting the technical specifications.
1342.8701
1171.5922
Purchase and toner cartridges for printers and photocopiers |  | 1285.9523 |  | 1061.2148 | Partial awarding, for the best economic offer and for meeting the technical specifications.
|  | 1220.3969 |  | 577.4578
877.5066
2. Introduction of climate resilient agro-ecological practices to make effective use of available water.
Purchase of 140 Kg of foot californian worms baby |  | 2555.2261 |  | 2607.3736 | For the best economic offer and for meeting the technical specifications.
5214.7472
Purchase plastic bags to nursery |  | 324.1933 |  | 2562.7244 | For the best economic offer and for meeting the technical specifications.
2931.8348
2986.3065
Direct purchase of building materials strategy for collecting and sowing seeds |  | 4997.4707 |  | 349.9897 | Partial awarding, for the best economic offer and for meeting the technical specifications.
|  | 874 |  | 811.2913
Purchase barbed wire and galvanized staples |  | 40569.6456 |  | 42056.6133 | For the best economic offer and for meeting the technical specifications.
48668.7468
64053.428
42056.6133
56472.1885
3. Training and capacity development in micro-watersheds, municipalities and participating national institutions.
Design and digital printing full color folders executive type |  | 993.8479 |  | 709.1723 | For the best economic offer and for meeting the technical specifications.
870.7069
951.9016
1023.723
1108.8367
1157.7181
899.1611
1162.8635
1144.8546
815.5481
856.7114
1041.9463
Elaboration of style polo shirts with embroidered logos and screen printed shirts and caps round neck |  | 9862.0433 |  | 3467.5615 | Partial awarding, for the best economic offer and for meeting the technical specifications.
|  | 13888.3296 |  | 5779.2692
6646.1596
Elaboration round neck shirts silkscreened |  | 4881.7124 |  | 5613.9692 | For the best economic offer and for meeting the technical specifications.
3379.647
3191.8888
3051.0702
5829.8911
3191.8888
4966.2035
4232.0691

## Risk Assesment
RISK ASSESMENT
IDENTIFIED RISKS
List all Risks identified in project preparation phase and what steps are being taken to mitigate them
Identified Risk | Current Status | Steps Taken to Mitigate Risk
Actores nacionales y municipales claves no se ponen de acuerdo para una estrategia de adaptación al nivel de la cuenca. | Bajo | En el periodo de Julio 2014 a Junio 2015, se finalizó la formulación de cinco (5) Planes de Protección Ambiental de las Familias ante el cambio climático en los Municipios de Chinandega, El Viejo, Puerto Morazán y Somotillo en el Departamento de Chinandega y en Larreynaga-Malpaisillo en el departamento de León, con el apoyo de Instituciones de Gobierno como el Ministerio de Salud (MINSA), Ministerio de Educación (MED) , Policía Nacional, Instituto Nicaragüense de Tecnología Agropecuaria (INTA), Ministerio Agropecuario y Forestal (MAGFOR), Ministerio de la Familia, así como el Movimiento de Jóvenes Ambientalista Guardabarranco y Poder Ciudadano y el Instituto Nicaraguense de Fomento Municipal ( INIFON).
En Diciembre del 2014 se conformó Comité de la Subcuenca del Río Villanueva, donde participaron los miembros de los comités de las 8 microcuencas de los municipios de los municioios de Achuap y El Sauce departamento de León y Villanueva departamento de Chinandega quedando Inscrito en el Registro Público del Derecho del Agua en la Autoridad Nacional del Agua (ANA). Con la participación de actores nacionales y municipales claves (INIFOM, MAG,, INAFOR, INTA, MARENA, INAFOR y Gobiernos Municipales) se elaboraron 08 Planes de Manejo de Microcuencas en los munipios de Achuapa, El Sauce y Villanuevai; En base a las experiencias de los planes de microcuencas se formulo el Plan de Manejo para la Subcuenca del Río Villanueva.
Sucesos naturales atrasen la ejecución del programa. | Bajo | Durante el período julio 2014 a junio 2015, el riesgo de atraso en la ejecución del programa fue bajo, debido a que la mayoria de las actividades se realizaron en el primer semestre del año 2014 lo que permitio que no fueron afectadas por las amenazas de la presencia del fenomeno del Niño; posteriormente el Programa entró a su etapa de cierre final.
Critical Risks Affecting Progress (Not identified at project design)
Identify Risks with a 50% or > likelihood of affecting progress of project
Identified Risk | Current Status | Steps Taken to Mitigate Risk
Risk Measures: Were there any risk mitigation measures employed during the current reporting period? If so, were risks reduced? If not, why were these risks not reduced?
Add any comments relevant to risk mitigation (word limit = 500)

## Rating
RATING ON IMPLEMENTATION PROGRESS
For rating definitions please see bottom of page.
| Progress on Key Milestones |  | Expected Progress |  | Progress to Date | Rating
Project Manager/Coordinator: | Outcome 1: Aumentar la Disponibilidad de agua para uso domestico y productivos de pequenos escala y reducido el riesgo de estres acuatico y sequia
| Output. 1.1 The construction of 2 communal irrigation systems to supply water to 85 farming families in 2 micro-watersheds, which increases water viability for domestic use and small scale production and reduces the risk of water shortage and drought. |  | Asistencia Técnica para el buen funcionamiento y mantenimeinto a los sistemas de riego comunales suministran granjas familiares en dos micro-cuencas. |  | En el periodo de Julio 2014 a Junio 2015 se brindó asistencia técnica para que las familias portagonistas continuen dandoles un adeacuado mantenimiento para el buen funcionamiento de los Sistemas de Riego de Salale y Las Mercedes en el municipio El Sauce - León, para la sostenibilidad de los mismos. | Satisfactory (S)
| Output 1.2 At least 880 rainwater collection and storage structure |  | Seguimiento y manetenimiento para el buen funcionamiento de las obas de captación y almacenamiento de aguas pluviales. |  | Realizado manteniendo y seguimiento al buen funcionamiento de 16 lagunetas en 5 comunidades de los municipios de Villanueva – Chinandega y El Sauce – León. Los Protagonistas dijeron sentirse satisfechos con las obras ya que se encuentran funcionando bien, utilizando esa agua para darle de beber a su ganado en esta época seca. | Satisfactory (S)
| Output 1.3 A At least 1000 farm families organized and trained in management, efficient use and maintenance of their communal and individual irrigation systems and water storage facilities. |  | Familias protagonistas organizadas y entrenadas en el manejo, uso eficiente y el mantenimiento de sus sistemas de riego comunales e individuales y las instalaciones de almacenamiento de agua |  | Se ha motivado un cambio de actitud positiva, fortaleciendo a las familias productoras para garantizar el cuido, manejo y mantenimiento de los dos sistemas comunitario de riego y las pequeñas infraestructuras de captación de aguas pluviales a traves de eventos de capacitación, dada la importancia que estas tiene para ellos y sus futuras generaciones. como parte de la motivación a las familias protagonistas se han elaborados y publicados viedeos donde se muestran los resultados y satisfacción de los protagonistas. | Satisfactory (S)
Outcome 2: Introduccion de practicas agro-ecologicas climaticamente resilientes para hacer uso efectivo del agua disponible
| Output 2.1 At least 1000 farm families with agro-ecological farm transformation plans and using their own resources and available credit for their ongoing implementation. |  | Seguimiento y Asistencia Técnica a 1005 Familias Protagonistas que implementan planes de transformación granja agro-ecológicos de fincas. |  | Se brindó Asistencia Técnica a las familias protagonistas que implementaron Planes de Finca en el área de incidencia del programa, asi como tambien se realizaron firmas y entrega de 280 Convenios Solidarios a protagonistas de los tres Municipios de Incidencia del Programa MARENA Estero Real. | Satisfactory (S)
| Output 2.2 At least 140 hectares converted to water-conscious and climate resilient agro-ecological production in each micro-watershed. |  | Recolección de semilla para siembra directa. |  | Se firmaron un total 320 Actas de compromisos de recolección de semilla forestal de diferentes especies, lo que generó un total de 1,307 kg de semillas (equivalente a 28.75 qq), las familias protagonistas, entregaron en los puntos de copio de cada comunidad contribuyendo al incremento de la vegetación con lo cual se logrará el amarre de los suelos, fluctuaciones de los vientos, recarga acuíferas, recuperación de la biodiversidad y reducción de las tolvaneras en los municipios de incidencia del programa. Elaborada Cartilla de Recolección y Siembra Directa de Semillas Forestales para su implementación en los municipios de Achuapa, El Sauce y Villanueva | Satisfactory (S)
| Output 2.3 At least 50 protected hectares in water system recharge areas and riparian zones in each micro-watershed. |  | Fortalecimiento a las familias protagonistas para la protección de las áreas de recarga del sistema de agua y las zonas ribereñas en cada microcuenca. |  | Se desarrallaron 06 conversatorios con la participación de 333 familias protagonistas (90 mujeres y 243 varones), donde se les presentó el Plan de acción para la recolección y siembra directa de semillas forestales con el objetivo de impulsar la regeneración natural del bosque en zonas de recarga hídricas y riparias en las ocho Micro-cuencas de incidencia del Programa de los municipios de Achuapa, El Sauce. Elaborada Cartilla de Recolección y Siembra Directa de Semillas Forestales con la participación del Coordinador, Especialistas y Facilitador técnico del Programa MARENA Estero Real. Elaborada Guía para la Protección de zonas de recarga riparias, en coordinación con los GFCV, Movimiento Ambientalistas Guardabarranco, y los Gobiernos Locales de los municipios de Achuapa, El Sauce y Villanueva. Como parte del fortalecomiento y motivación a las familias protagonistas se han elaborados y publicados viedeos donde se muestran los resultados y satisfacción de los protagonistas. | Satisfactory (S)
Outcome 3: Capacitacion y desarrollo institucional en micro-cuencas, municipalidades e instituciones nacionales participantes.
| Output 3.1. Design and development of a fire prevention and control campaign for forest, agricultural and cattle farming areas, in coordination with the Civil Defense. |  | Desarrollada campaña de prevención y control de incendios agricolas y forestales con la participación de los actores locales de las 8 micro-cuencas en los 3 municipios. |  | Realizada una campañas de sensibilización para la prenvención y control de incendios forestales y agricolas en las 29 comunidades de incidencia del programa en los municipios de El Sauce, Achuapa y Villanueva a través de cuñas radiales y televisivas, con mensajes alusivos a protección del bosque, protección de fuentes de agua y prevención de incendios forestales y quemas agrícolas, la estrategia de Vivir Sano, Vivir bonito para Vivir bien. | Satisfactory (S)
|  |  | Elaborados 5 Planes Municipales en coordinación con los gobiernos locales, instituciones de gobierno y ONG . |  | En el periodo julio 2014 al junio del 2015, se formularon 05 Planes de Adaptación de la Familia ante el Cambio Climatico de los municipios de Chinandega, El Viejo, Puerto Morazán Somotillo en el departamento de Chinandega y Larreynaga - Malpaisillo en el departamento de León, a traves de 15 talleres participativos . . | Satisfactory (S)
| Output 3.2 Inter-institutional coordinating bodies in El Sauce, Achuapa and Villanueva coordinate governmental and non-governmental agency work plans in the micro-watershed in the Villanueva River basin. |  | Órganos de coordinación interinstitucionales en El Sauce, Achuapa y Villanueva coordinar planes de trabajo agencia gubernamentales y no gubernamentales en la microcuenca de la cuenca del Río Villanueva. |  | Se conformó el Comité de la Subcuenca del Río Villanueva, en coordinación con Gobiernos Locales, la Autoridad Nacional del Agua (ANA), INTA, MAG, INAFOR, INIFOM, y representantes de los 08 comité de microcuencas, quedando debidamente constituido y funcionando. | Satisfactory (S)
Outcome 4: Monitoreo y análisis continuo de condiciones climáticas y cambios en el uso de la tierra, los caudales y calidad de los suelos.
| Output . 4.1 Hydrological study of the lower watershed of the Villanueva River, identifying the required hydraulic works to reduce flooding caused by sediment from the upper watershed. |  | Documento Final sobre Estudio hidrológico. |  | Elaborado y presentado documento final del Estudio hidrogeológico de la parte alta, media y baja de la subcuenca del Río Villanueva, lo que permite a los gobiernos locales y comunitarios conocer los puntos criticos y los escenarios climaticos futuros, asi como las medidas de mitigación y de restauración ambiental. Este estudio se realizó en el marco de un convenio de colaboración entre el Ministerio de Medio Ambiente y Recursos Naturales (MARENA) y el Instituto Nicaragüense de Estudios Territoriales (INETER). | Satisfactory (S)
| Output. 4.2 Ongoing participatory monitoring of water flows and quality, soil conditions, and land use changes. |  | Finalizado de Estudio de calidad y disponibilidad del recurso hídrico en las ocho microcuencas de incidencia del Programa Estero Real |  | Realizados comentarios e incorporadas observaciones al docuemento final por parte del CIRA - UNAN - Managua, asi como también realizó presentación final al MARENA. | Satisfactory (S)
| Output. 4.3 Electronic information posts in each targeted micro-watershed present relevant national and global climate information, digitalize local monitoring data, and prepare maps of land use, waer flow and soil quality changes for farm families, local organizations and users of the National Environmental Information System (SINIA). |  | Documento Final de Lecciones Aprendidas. |  | Elaborado documentos sobre Lecciones aprendidas de las experiencias y resultados del Proyecto Estero Real. | Satisfactory (S)
[5 empty] | Overall Rating | Satisfactory (S)
Please Provide the Name and Contact information of person(s) reponsible for completeling the Rating section
| Name: | Luis Humberto Picado
| Email: | lpicado14@yahoo.com
Please justify your rating. Outline the positive and negative progress made by the project since it started. Provide specific recommendations for next steps. . (word limit=500)
Durante el periodo de ejecución de junio del 2011 al 30 de junio del 2015, con este Proyecto se implementaron diferentes combinaciones de medidas de adaptación: conservación, protección de fuentes de agua y cosechas de agua; implementación de sistemas de restauración ambiental para proteger zonas de recarga hídrica; planificación comunitaria, municipal y de cuencas hidrográficas; educación ambiental, desarrollo de estudios y fortalecimiento de los sistemas de información ambiental y de cambio climático. Se considera que al finalizar su ejecución, el programa es considerado Satisfactorio, logrando llevar beneficios a 1005 familias de los municipios de El Sauce, Achuapa y Villanueva ubicados en la Cuenca del Río Estero Real, mediante el aumento de la disponibilidad del agua en 251,154 m3, incremento en la cobertura del bosque en 2008 hectáreas, protección de 958 fuentes de agua y desarrollo de capacidades de 1005 familias productoras. El desembolso total desde el inicio del proyecto hasta junio de 2015 ha sido de USD $ 4,926,894.00 (el 97.18 % del importe total del proyecto).
| Progress on Key Milestones |  | Expected Progress |  | Progress to Date | Rating
Implementing Agency | OUTCOME 1: Increased availability of water for small scale domestic and productive uses and reduced risk of water stress and drought. | [5 empty] | Falta la información por parte de la oficina de país.
Output. 1.1 The construction of 2 communal irrigation systems to supply water to 85 farming families in 2 micro-watersheds, which increases water viability for domestic use and small scale production and reduces the risk of water shortage and drought.
Output 1.2 At least 880 rainwater collection and storage structure
Output 1.3 A At least 1000 farm families organized and trained in management, efficient use and maintenance of their communal and individual irrigation systems and water storage facilities.
OUTCOME 2: Enhance resilience through agro-ecological practices and effective use of available water in the eight targeted micro-watersheds
Output 2.1 At least 1000 farm families with agro-ecological farm transformation plans and using their own resources and available credit for their ongoing implementation.
Output 2.2 At least 140 hectares converted to water-conscious and climate resilient agro-ecological production in each micro-watershed.
Output 2.3 At least 50 protected hectares in water system recharge areas and riparian zones in each micro-watershed.
Outcome 3: Capacitacion y desarrollo institucional en micro-cuencas, municipalidades e instituciones nacionales participantes.
Output 3.1. Design and development of a fire prevention and control campaign for forest, agricultural and cattle farming areas, in coordination with the Civil Defense.
Output 3.2 Inter-institutional coordinating bodies in El Sauce, Achuapa and Villanueva coordinate governmental and non-governmental agency work plans in the micro-watershed in the Villanueva River basin.
OUTCOME 4: Continuous monitoring and analysis of climate conditions and land use changes, water volume and soil quality.
Output . 4.1 Hydrological study of the lower watershed of the Villanueva River, identifying the required hydraulic works to reduce flooding caused by sediment from the upper watershed.
Output. 4.2 Ongoing participatory monitoring of water flows and quality, soil conditions, and land use changes.
Output. 4.3 Electronic information posts in each targeted micro-watershed present relevant national and global climate information, digitalize local monitoring data, and prepare maps of land use, waer flow and soil quality changes for farm families, local organizations and users of the National Environmental Information System (SINIA).
Overall Rating
Please Provide the Name and Contact information of person(s) reponsible for completeling the Rating section
Name:
Email:
| Progress on Key Milestones |  | Expected Progress |  | Progress to Date | Rating
Other
Overall Rating
Please Provide the Name and Contact information of person(s) reponsible for completeling the Rating section
Name:
Email:
| Please justify your rating and address the following points: 1. Indicate trends, both positive and negative, in achievement of outcomes as per the project indicators. 2. Detail critical risks that have affected progress. 3. Outline response to MTR undertaken this reporting period. 4. Outline action plan to address projects with a rating of HU, U or MU. Please keep your input to 1200 words |  | explicar porque es satisfacctorio
Rating Definitions
|  |  | Highly Satisfactory (HS) | Project actions/activities planned for current reporting period are progressing on track or exceeding expectations to acheive all major outcomes/outputs for given reporting period, without major shortcomings. The project can be presented as “good practice”.
|  |  | Satisfactory (S) | Project actions/activities planned for current reporting period are progressing on track to achieve most of its major outcomes/outputs with only minor shortcomings.
|  |  | Marginally Satisfactory (MS) | Project actions/activities planned for current reporting period are progressing on track to achieve most major relevant outcomes/outputs, but with either significant shortcomings or modest overall relevance.
|  |  | Marginally Unsatisfactory (MU) | Project actions/activities planned for current reporting period are not progressing on track to achieve major outcomes/outputs with major shortcomings or is expected to achieve only some of its major outcomes/outputs.
|  |  | Unsatisfactory (U) | Project actions/activities planned for current reporting period are not progressing on track to achieve most of its major outcomes/outputs.
|  |  | Highly Unsatisfactory (U) | Project actions/activities planned for current reporting period are not on track and shows that it is failing to achieve, and is not expected to achieve, any of its outcomes/outputs.

## Project Indicators
PROJECT Indicators
Please provide all indicators being tracked for the project as outlined in the project document
Type of Indicator (indicators towards Objectives, Outcomes, etc…)
Type of Indicator | Indicator | Baseline | Progress since inception | Target for Project End
Objective: Reducir los riesgos de sequías e inundaciones generados por el cambio climático y la variabilidad en la Cuenca del Río Estero Real. | Número de familias productoras en las micro cuencas enfocadas con por lo menos una cosecha anual, debido a las medidad de adaptacion | 400 | 1005 Productores con Planes de Transformación Agro-ecológicas en Fincas, lo que representan el 100% del total de los productores beneficiarios, implementando sus planes de transformación agroecologicas en sus fincas, garantizando dos cosechas anuales, debido a las tecnologias agroecologicas de adaptaciòn al cambio climatico. | 1005
| Número de familias productoras incluidas en la propuesta de manejo de la Sub-cuenca. | 0 | 7,174 familias protagonistas incluidas en las propuestas de los 8 planes de manejo de 8 microcuencas y el Plan de Manejo de la Subcuenca del Rio Villanueva. | 7120
Outcome 1 | Aumentar la Disponibilidad de agua para uso domestico y productivos de pequenos escala y reducido el riesgo de estres acuatico y sequia
| Porcentaje de fincas en cada micro-cuenca con riego por obras hidráulicas construidas con fondos del programa. | 0 | Al finalizar el Proyecto se sobre cumplió la meta del 90% de fincas (85 fincas en las Mercedes y 32 fincas en Salale ), donde se construyeron obras hidráulicas. En La microcuenca de Las Mercedes; inicialmente de manera artesanal, solamente 28 familias aprovechaban el agua para riego a través de mangueras, con el proyecto se tecnificó el sistema de riego se fortaleció la organización y se sumaron al sistema 57 familias protagonistas para un total de 85 familias (510 habitantes), incrementándose el beneficio a un 204% más de la población demandante de riego. En la Microcuenca de Salale;inicialmente de manera artesanal a solamente a 20 familias aprovechaban el agua para riego a través de mangueras, con el proyecto se tecnificó el sistema de riego, se fortaleció la organización y se sumaron al sistema comunal de riego 12 familias protagonistas, para un total de 32 familias protagonistas (192 habitantes), incrementándose el beneficio a un 60% más de la población demandante de riego. | 90%
| Superficie en Hectáreas a incrementar bajo riego. | 67.55 has | El proyecto la final de sus ejecucion alcanzó un incremento de 96.95 has de áreas a regar, al total del 164.5 Has. Este incremento en hectáreas, se debe a que hubo mayor participación de los protagonistas en regar sus áreas de cultivo utilizando los nuevos sistemas de riego. | 164.5 has
Outcome 2 | Introduccion de practicas agro-ecologicas climaticamente resilientes para hacer uso efectivo del agua disponible
| Percentage of farms in each micro-watershed whose water usage qualifies as Satisfactory in relation to the corresponding technical indications. | 5% | El 100% de las familias protagonistas con obras de captación de aguas pluviales construidas en las comunidades de las 08 microcuencas de incidencia del programa, califican como "satisfactoria" la oferta de cantidad y calidad de agua captada, la que es utilizada para aguar el ganado y riego a pequeña escala en época de verano, garantizando de esta forma la seguridad alimentaria de las familias protagonistas. | 90%
| Cantidad de obras de cosecha de agua instaladas y funcionando a nivel de micro cuencas. | 0 | Construidas y funcionando 908 obras de captación y almacenamiento de aguas pluviales (93 lagunetas; 467 pilas de captación, 146 Cisternas, 185 abrevaderos y 17 diques), con capacidad para captar 251,154 m3 de agua durante todo el invierno, beneficiando a 792 familias protagonistas en los municipios de El Sauce, Achuapa y Villanueva: El Sauce: 33 Lagunetas, 88 pilas, 22 cisternas, 57 Abrevaderos y 03 Dique en las de comunidades Las Mercedes, El Borbollón, Cooperativa Ismael Castillo, Salale, Petaquilla, Campañento, La Montaña, La Montañita, El ojochal, Nacascolo Norte, Coyol placa. Achuapa: 19 Lagunetas, 216 Pilas, 56 Cisternas,70 Abrevaderos y 11 Diques, en las comunidades de San Nicolás, Lagartillo, Las Brisas, San Antonio, Varela, El Guaylo, Guanacaste, Las Lajas, Rio Arriba, Las Tablas y Rodeíto. Villanueva: 41 Lagunetas; 163 Pilas, 68 Cisternas, 58 Abrevaderos y 03 Diques, en las comunidades de Los Genizaros, Los Tololos, San Ramón, Las Pilas, El Tule y Chupaderos. | 880
| Percentage of producer families in each micro-watershed implementing agro-ecological farm transformation plans | 5% | 100% de las familias protagonistas cuentan con planes de transformación agroecológicas de fincas (PTAF), distribuidos de la siguiente manera: - Achuapa: 375 familias protagonistas. - El Sauce: 350 familias protagonistas. - Villanueva: 280 familias protagonistas. | 80%
| Surface in hectares in agro-ecological farming transformation plans. | 0 | Al finalizar el Programa 2,235 hectáreas se encuentran bajo manejo agroecologico a través de 1005 planes de transformación agroecologica elaborados en los municipios de Achuapas, en la microcuencas Varela y El Coyolar, en el muncipio El Sauce en las microcrocuencas Campamento - Petaquilla; Las Mercedes y Salale y en el municipio de Villanueva en las microcuencas de El Pilón, El Genizaros y Las Pilas. La meta se sobrecumplio en 200%. | 1120 has
| Increase in the percentage of land in each micro-watershed with permanent vegetation coverage. | 25% | Se ha logrado incrementar en un 61% la cobertura vegetal en las 08 microcuencas, alcanzando un 11% más de lo programado (50%), pasando de 100 has a 223 has en zonas de bosque ripario. Paralelamente se ha logrado la regeneracón natural de 1,785 has de bosque en zanas de recarga hídrica, que se suman a la protección del bosque ripario incrementado. | 50% (al menos 200 has en zonas de bosque ripario)
| Number of families benefitting from home and land investments through the Farming Transformations Plans (PTAF). | 0 | 1005 familias protagonistas en las 29 comunidades se benefician con las inversiones del hogar y la tierra (758 fogones mejorados; 721 gallineros y 331 chiqueros). | 1005 Familias
Outcome 3 | Capacitacion y desarrollo institucional en micro-cuencas, municipalidades e instituciones nacionales participantes.
| A proposal validated and endorsed by three municipal governments for the operation of a Committee for the Rio Villanueva Sub-watershed. | 0 | Elaborado y Validado Plan de Manejo de la Subcuenca del Río Villanueva el que orienta el funcionamiento y operación del Comité de la subcuenca del Río Villanueva | 1
| Number Municipalities in the watershed with climate change adaptive measures included in their official plans or related normative instruments. | 0 | 08 municipalidades (Achuapa, El Sauce , Villanueva,Chinandega, El Viejo, Puerto Morazán, Somotillo y Larreynaga - Malpaisillo), cuentan con sus Planes Municipales de Proteccion Ambiental de las familias ante el Cambio Climatico, integrando sus estrategias y lienas de accion en sus planes de trabajo y normativas relacionadas. | 9
Outcome 4 | Monitoreo y análisis continuo de condiciones climáticas y cambios en el uso de la tierra, los caudales y calidad de los suelos.
| Hydrological study and number of informative bulletins disclosing the participatory monitoring of water quantity and quality, soils conditions, and the changes in its use. | 0 | En este Periodo se concluyó el Estudio hidrogeológico en la parte alta, media y baja de la subcuenca del Río Villanueva, lo que permite a los gobiernos locales y comunidades conocer los puntos criticos y los escenarios climaticos futuros, asi como las medidas de mitigación y de restauración ambiental. 09 boletines informativos elaborados con el objetivo de dar a conocer información generada sobre el monitoreo ambiental de las condiciones climaticas, las condiciones de suelo, cantidad y calidad de agua y lecciones aprendidas sobre practicas agroecologicas y cosechas de agua desarrollada por los protagonistas de las 29 comunidades que atiende el programa. | 1
| Lessons learned in the eight micro-watersheds and the Rio Villanueva sub-watershed available at SINIA and other websites (ALM) and distributed through exchange workshops. | 0 | Disponible Pagina Web interactiva (www.sinia.net.ni/multisites/EsteroReal) , Documento de lecciones aprendidas e informes anuales del proyecto. | Feed AF and MARENA website; 4 annual reports and 12 quarterly reports.

## Lessons Learned
QUALITATIVE MEASURES and LESSONS LEARNED
Please Complete the following section every reporting period
Implementation and Adaptive Management | Response
Describe any implementation issues/lessons affecting progress (positive and negative) | El manejo de la regeneración natural es mucho más efectivo para el restablecimiento de los bosques y el manejo de cuencas que la reforestación mediante otros métodos, para apoyar el desarrollo de la regeneración natural la siembra directa de semillas forestales nativas de la zona es un método efectivo Con pequeños incentivos dirigido hacia los productores la recolección y la siembra directa de semillas forestales es un método que permite lograr impacto considerable en el incremento de la regeneración natural para la protección de las zonas de recarga hídrica y riparias
Were there any delays in implementation? If so, include any causes of delays. What are the measures taken to reduce delays? | Aunque hubo retrasos en las mediciones de caudales en la elaboración del estudio de calidad y cantidad de agua al finalizarlo cumplió con su objetivo. La coordinación inter-institucional y las alianzas para la prosperidad realizadas en el marco de la formulación de los planes municipales de protección ambiental de las familias ante el cambio climático fueron muy importantes para identificar estrategias locales claves de adaptación al cambio climático. El Plan de manejo de la subcuenca elaborado de manera participativa partiendo de la experiencia y el conocimiento de las comunidades permite la apropiación de las estrategias por parte de los actores de la subcuenca y estas se ejecuten.
Describe any changes undertaken to improve results on the ground or any changes made to project outputs (i.e. changes to project design) | Los métodos de reforestación tradicionales con plantas provenientes de viveros, son métodos que en zonas secas presentan desventajas relacionados a costos altos y al bajo porcentaje de prendimiento; para contrarestar, lo anterior el Programa impulso la recolección y siembra directa de semillas forestales siendo este un método silvicultural de gran impacto, mas barato, menos costoso y de fácil adopción por parte de los protagonistas que desarrollan reforestación en zonas de recargas hídricas y riparias.
How have gender considerations been taken into consideration during the reporting period? What have been the lessons learned as a consequence of inclusion of such considerations on project performance or impacts? | El programa contribuyó a disminuir las brechas de genero e incidió positivamente en las necesidades estratégicas cuando fueron convocados todos los protagonistas con sus parejas a participar en las asambleas y talleres y es desde allí es que se integró la participación de la mujer en igualdad de condiciones para la toma de decisiones, dandole un enfoque de genero a los procesos de conformación de los Comités de Microcuencas, mujeres con titulos de propiedad, con recursos hidricos accesibles a sus vivienda (pilas de captacion de agua), mujeres generando ingresos económicos con actividades de patio (gallineros, chiqueros, frutales); formando parte de la Red de promotoras ambientales, asi como también promoviendo el desarrollo de sus Planes de Transformación Agroecologica de fincas. El programa con los diferente eventos de capacitcación que se desarrollaron, incidió en reducir o eliminar la inequidades entre hombres y mujeres; ampliar el reconocimiento de sus derechos y oportunidades, aumentado el empoderamiento de las mujeres; pero se deben tomar en cuenta los intereses y necesidades de hombres y mujeres, y asegurar la participación equitativa; también los horarios de las actividades promovidas por el proyecto los cuales deben ajustarse a las posibilidades de las mujeres de tal manera que no implique recarga de trabajo. Para finalizar es fundamental desde el inicio del programa contar con una línea base sobre la situación de género con el grupo meta lo que permite conocer las necesidades propias de mujeres y hombres para definir acciones afirmativas de intervención pertinentes que garanticen la sostenibilidad de las mismas. En términos generales, la participación de las mujeres en los eventos promovidos por el proyecto ha sido aproximadamente del 35%.
Please Complete the following section at mid-term and project completion
Lessons for Adaptation | Response
Climate Resilent Measures
Please Describe the Climate Resilent measures being undertaken by the project/programme. | Sistemas de restauración ambiental (Agroforestal, Silvo-pastoril) importantes para reducir los riesgos de sequia o déficit de agua en los cultivos ya que crean un microclima que mantiene la humedad del suelo y el ambiente permitiendo cosechas aunque estas sean reducidas. Los sistemas silvo-pastoriles contribuyen a frenar la erosión y facilita la infiltración del agua en el suelo. -Manejo de regeneración natural en zonas de recarga hídrica y riparias: La repoblación forestal a través de plantaciones con fenómenos de sequia presenta baja sobrevivencia de plantas, siendo mas importante las plantas que nacen adaptada a la zona lo que asegura la repoblación en menor tiempo, con menos costo y esfuerzo. -La recolección y siembra directa de semillas forestales: es un método silvicultura de gran impacto, mas barato, menos costoso y de fácil adopción por parte de los protagonistas que desarrollan reforestación en zonas de recargas hídricas y riparias.
Which of these masures has been most effective and why? | Los Sistemas de restauracion ambiental (Agroforestal, silvopastoril ) porque garantizan la seguridad alimentaria aun en epocas de sequia. La regeneracion natural en zonas de recarga hidrica porque garantizan la repoblacion forestal ; La siembra directa de semillas forestales porque garantizan mayor sobrevivencia de plantas, es mas barato y de facil adopcion por los protagonistas.
Which have been least effective and why? | La introduccion de lombricultura no fue muy efectiva, pues no todos los productores y productoras se apropiaron de su manejo en el campo.
Concrete Adaptaiton Interventions
Please desribe the concrete adaptation measures being undertaken by the project/programme | Una de las mejores soluciones para enfrentar la sequía y el cambio climático es la ubicación, diseño y construcción de pequeñas obras individuales y comunales para cosechar y almacenar el agua de lluvia (Pilas, cisternas, abrevaderos, diques). Este proceso debe ir acompañado con la correspondiente generación de capacidades para el manejo efectivo y adecuado del agua. Los Sistemas de restauración ambiental (Agroforestal, Silvopastoril) son importantes para reducir los riesgos de sequia o déficit de agua en los cultivos ya que crean un microclima que mantiene la humedad del suelo y el ambiente permitiendo cosechas aunque estas sean reducidas. El manejo de la regeneración natural es mucho más efectivo para el restablecimiento de los bosques y el manejo de cuencas que la reforestación mediante otros métodos, para apoyar el desarrollo de la regeneración natural la siembra directa de semillas forestales nativas de la zona es un método efectivo.
What are/were the most difficult aspects of implementing such measures? | El proceso de formulacion del plan de manejo de la subcuenca del Rio Grande o Villanueva, por que depende de una metodologia integrando los aspectos claves del manejo de cuencas y los aspectos adaptativos asi como la participacion de todos los actores claves para su formulacion.
What are/were the most successful aspects of the implementation of the interventions? | La apropiacion de las prácticas y tecnologias para la adaptacion al cambio climatico por parte de protagonistas ,gabinetes de la familia comunidad y vida, gobiernos locales e instituciones de gobierno .
Community/National Impact
What would you consider to be the most successful aspects for the target communities? | El desarrollo de capacidades que se implementó con los protagonistas, el proceso de transformacion agroecologica de fincas hacia un sistema resiliente y responsable del agua, la planificacion y el manejo del territorio para la adaptacion al cambio climatico.
What measures are/have been put in place to ensure sustainability of the project/program results? | La apropiacion del proceso de transformacion agroecologica de fincas con practicas resilientes por parte de los protagonistas, la apropiacion de los proceso de planificación y manejo del territorio para la adaptacion al cambio climatico por parte de gobiernos locales, comites de microcuencas y subcuenca, gabienetes de la familia comunidad y vida , movimiento ambientalista guardabarranco y de instituciones de gobierno. Las alianzas para la prosperidad que se ha logrado entre diferentes instituciones a traves de la cual se replican las experiencias del proyecto.
What measures are being/could have been put in place to improve project/program results? | Acciones para la investigacion en temas relevantes de los proceso de transformacion agroecologica mediante las practicas adaptativas
Knowledge Management
Describe what kind and how existing information/data/knowledge has been used to inform the development and the implementation of the project. | Los talleres, asambleas de consulta y consenso y reuniones, han permitido informar a los protagonistas y aliados del programa sobre el desarrollo e implementación efectiva de las acciones ejecutadas por el Proyecto. La base de datos de georeferenciación de fincas bajo manejo agroecológico permite elaborar mapas comparativos a través de los cuales se puede conocer e informar sobre el cambio de uso del suelo. El Monitoreo ambiental participativo en las 8 microcuencas (pluviometría, medición de la erosión, medición de caudales) permiten la toma de decisiones de las comunidades ante fenómenos de sequia e inundación para la alerta temprana.
If Learning Objectives have been established, have they been met? Please describe. | El principal objetivo de aprendizaje del Proyecto fue el bagaje de conocimientos generados en los grupos metas sobre la adaptacion al cambio climatico.
Describe any difficulties there have been in accessing or retrieving existing information (data or knowledge) that is relevant to the project. Please provide suggestions for improving access to the relevant data. | El programa no presenta dificultad para recuperación de la informacion existente hay una especialidad encargada de mantener la información.
Has the identification of learning objectives contributed to the outcomes of the project? In what why have they contributed? | El aprendizaje sobre la adaptacion al cambio climatico ha permitido que los protagonistas y otros grupos se hayan apropiado de las practicas, metodologias y estrategias del Proyecto poniendolas en practica en sus fincas, con lo que se ha mejorado la capacidad adaptativa de estos.
What have been the major lessons learned that would add to the knowledge base for dissemination within and beyond the project area? | Los sistemas de riego comunales son fundamentales para represar agua y mejorar su distribución lo cual permite regar mayor área durante todo el año y que los protagonistas aseguren al menos 3 cosechas al año . Las lagunetas son mas adecuadas para implementarse con productores silvopastoriles que con productores agroforestales ya que restan area productiva al sistema por el espacio que ocupan. . Los Sistemas de restauración ambiental (Agroforestal, Silvo-pastoril) son importantes para reducir los riesgos de sequia o deficit de agua en los cultivos ya que crean un microclima que mantiene la humedad del suelo y el ambiente permitiendo cosechas aunque estas sean reducidas. Los sistemas silvo-pastoriles contribuyen mas que los sistemas agroforestales a frenar la erosión y facilitan la infiltración del agua en el suelo contribuyendo a reducir grandemente las inundaciones en la parte baja de las cuencas. -El Manejo de la regeneracion natural en zonas de recarga hídrica y riparias aun con presencia de fenomenos de sequia presenta sobrevivencia adecuada de plantas, siendo muy importante para la repoblacion forestal en menor tiempo, con menos costo y menos esfuerzo. -La recoleccion y siembra drecta de semillas forestales: es un metodo silvicultural de gran impacto, mas barato, menos costoso y de facil adopcion por parte de los protagonistas que desarrollan reforestacion en zonas de recargas hidricas y riparias. - Monitoreo ambiental a través de nodos de información: Mantiene informados a las comunidades sirviendo como alerta temprana

## Results Tracker
Results Tracker for Adaptation Fund (AF) Projects
Goal: Assist developing-country Parties to the Kyoto Protocol that are particularly vulnerable to the adverse effects of climate change in meeting the costs of concrete adaptation projects and programmes in order to implement climate-resilient measures. Impact: Increased resiliency at the community, national, and regional levels to climate variability and change.
Important: Please read the following guidance document (also posted on the Adaptation Fund website) before entering your data
Link: http://www.adaptation-fund.org/sites/default/files/Results%20Framework%20and%20Baseline%20Guidance%20final.pdf
Adaptation Fund Strategic Results Framework
Project ID
Implementing Entity
Type of implementing entity
Country
Region
Sector
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Impact: Increased resiliency at the community, national, and regional levels to climate variability and change | Core Indicator: No. of beneficiaries |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project
|  | Total |  |  |  | Total |  |  |  | Total |  |  |  | Total
|  | % of female beneficiaries |  |  |  | % of female beneficiaries |  |  |  | % of female beneficiaries |  |  |  | % of female beneficiaries
|  | % of Youth beneficiaries |  |  |  | % of Youth beneficiaries |  |  |  | % of Youth beneficiaries |  |  |  | % of Youth beneficiaries
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 1: Reduced exposure to climate-related hazards and threats | Indicator 1: Relevant threat and hazard information generated and disseminated to stakeholders on a timely basis | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness
|  | Total |  |  |  | Total |  |  |  | Total |  |  |  | Total
|  | % of female targeted |  |  |  | % of female targeted |  |  |  | % of female targeted |  |  |  | % of female targeted
Output 1.1 Risk and vulnerability assessments conducted and updated | Indicator 1.1: No. of projects/programmes that conduct and update risk and vulnerability assessments | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
Output 1.2 Targeted population groups covered by adequate risk reduction systems | Core Indicator 1.2: No. of Early Warning Systems | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 2: Strengthened institutional capacity to reduce risks associated with climate-induced socioeconomic and environmental losses | Indicator 2: Capacity of staff to respond to, and mitigate impacts of, climate-related events from targeted institutions increased | Number of staff targeted |  | Sector | Capacity level | Number of staff targeted |  | Sector | Capacity level | Number of staff targeted |  | Sector | Capacity level | Number of staff targeted |  | Sector | Capacity level
|  | Total |  |  |  | Total |  |  |  | Total |  |  |  | Total
|  | % of female targeted |  |  |  | % of female targeted |  |  |  | % of female targeted |  |  |  | % of female targeted
Output 2.1 Strengthened capacity of national and sub-national centres and networks to respond rapidly to extreme weather events | Indicator 2.1.1: No. of staff trained to respond to, and mitigate impacts of, climate-related events | Total staff trained | % of female staff trained | Type |  | Total staff trained | % of female staff trained | Type |  | Total staff trained | % of female staff trained | Type |  | Total staff trained | % of female staff trained | Type
| Indicator 2.1.2: No. of targeted institutions with increased capacity to minimize exposure to climate variability risks | Type | Scale | Sector | Capacity level | Type | Scale | Sector | Capacity level | Type | Scale | Sector | Capacity level | Type | Scale | Sector | Capacity level
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 3: Strengthened awareness and owernship of adaptation and climate risk reduction processes | Indicator 3.1: Increase in application of appropriate adaptation responses | Percentage of targeted population applying adaptation measures |  | Sector |  | Percentage of targeted population applying adaptation measures |  | Sector |  | Percentage of targeted population applying adaptation measures |  | Sector |  | Percentage of targeted population applying adaptation measures |  | Sector
Output 3: Targeted population groups participating in adaptation and risk reduction awareness activities | Indicator 3.1.1: Percentage in targeted population awareness of predicted adverse impacts of climate change, and of appropriate responses | No. of targeted beneficiaries | % of female participants targeted | Level of awareness |  | No. of targeted beneficiaries | % of female participants targeted | Level of awareness |  | No. of targeted beneficiaries | % of female participants targeted | Level of awareness |  | No. of targeted beneficiaries | % of female participants targeted | Level of awareness
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Target performance at completion |  |  |  | Target performance at completion
Outcome 4: Increased adaptive capacity within relevant development sector services and infrastructure assets | Indicator 4.1: Increased responsiveness of development sector services to evolving needs from changing and variable climate | Project/programme sector | Geographical scale | Response level |  | Project/programme sector | Geographical scale | Response level |  | Project/programme sector | Geographical scale | Response level |  | Project/programme sector | Geographical scale | Response level
| Core Indicator 4.2: Assets produced, developed, improved or strengthened | Sector | Targeted asset | Changes in asset (quantitative or qualitative) |  | Sector | Targeted asset | Changes in asset (quantitative or qualitative) |  | Sector | Targeted asset | Changes in asset (quantitative or qualitative) |  | Sector | Targeted asset | Changes in asset (quantitative or qualitative)
Output 4: Vulnerable development sector services and infrastructure assets strengthened in response to climate change impacts, including variability | Indicator 4.1.1: No. and type of development sector services to respond to new conditions resulting from climate variability and change | Number of services | Type |  | Sector | Number of services | Type |  | Sector | Number of services | Type |  | Sector | Number of services | Type |  | Sector
|  | Baseline information |  |  |  | Baseline information |  |  |  | Baseline information |  |  |  | Baseline information
Outcome 5: Increased ecosystem resilience in response to climate change and variability-induced stress | Indicator 5: Ecosystem services and natural resource assets maintained or improved under climate change and variability-induced stress | Natural resource improvement level |  | Sector | Type | Natural resource improvement level |  | Sector | Type | Natural resource improvement level |  | Sector | Type | Natural resource improvement level |  | Sector | Type
Output 5: Vulnerable ecosystem services and natural resource assets strengthned in response to climate change impacts, including variability | Core Indicator 5.1: Natural Assets protected or rehabilitated | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Baseline information |  |  |  | Targeted performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 6: Diversified and strengthened livelihoods and sources of income for vulnerable people in targeted areas | Indicator 6.1: Increase in households and communities having more secure access to livelihood assets | No. of targeted households | % of female headed households | Improvement level |  | No. of targeted households | % of female headed households | Improvement level |  | No. of targeted households | % of female headed households | Improvement level |  | No. of targeted households | % of female headed households | Improvement level
| Indicator 6.2: Increase in targeted population's sustained climate-resilient alternative livelihoods | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
|  | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
|  | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
|  | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
Output 6 Targeted individual and community livelihood strategies strengthened in relation to climate change impacts, including variability | Indicator 6.1.1: No. and type of adaptation assets created or strengthened in support of individual or community livelihood strategies | Number of Assets | Type of Assets | Sector | Adaptation strategy | Number of Assets | Type of Assets | Sector | Adaptation strategy | Number of Assets | Type of Assets | Sector | Adaptation strategy | Number of Assets | Type of Assets | Sector | Adaptation strategy
| Core Indicator 6.1.2: Increased income, or avoided decrease in income | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 7: Improved policies and regulations that promote and enforce resilience measures | Indicator 7: Climate change priorities are integrated into national development strategy | Integration level |  |  |  | Integration level |  |  |  | Integration level |  |  |  | Integration level
Output 7:Improved integration of climate-resilience strategies into country development plans | Indicator 7.1: No. of policies introduced or adjusted to address climate change risks | No. of Policies introduced or adjusted | Sector | Scale | Type | No. of Policies introduced or adjusted | Sector | Scale | Type | No. of Policies introduced or adjusted | Sector | Scale | Type | No. of Policies introduced or adjusted | Sector | Scale | Type
| Indicator 7.2: No. of targeted development strategies with incorporated climate change priorities enforced | No. of Development strategies | Regulation |  | Effectiveness | No. of Development strategies | Regulation |  | Effectiveness | No. of Development strategies | Regulation |  | Effectiveness | No. of Development strategies | Regulation |  | Effectiveness
Glacier lake outburst flood
|  | Inland flooding | fr | biological assets |  | Company policy | 5: Fully enforced (All elements implemented)
|  | Salinization | Decrease | land |  | Communication & Information policy | 4: Enforced (Most elements implemented)
|  | Drought | Same | water areas |  | Defense policy | 3: Partially enforced (Some elements implemented)
|  | Wind |  | subsoil assets | increased adpative capacity | Domestic policy | 2: Partially not enforced (Most elements not implemented) |  | Agribusiness
|  | Coastal flooding |  | air | achieved | Economic policy | 1: Not enforced (No elements implemented) |  | Agricultural-related | Financial capital
|  | Storm surge | Please choose |  | enhanced level of protection | Education policy |  |  | Agriculture | Human capital
|  | Hurricane | Selected | [5 empty] | Aquaculture | Physical capital
|  |  | Not relevant |  |  | 5: All (Fully integrated) |  |  | Construction/repairing business | Social capital
[6 empty] | 4: Most |  |  | Cultivation | Natural capital
[6 empty] | 3: Some |  |  | Fishing | Personal capital
Select | 5: All | Select |  |  | Community | 2: Most not integrated |  | Other | Forestry | Adaptation strategies
1 | 4: Almost all | Private | Type | Yes | Multi-community | 1: None |  | Agriculture | Handicrafts
2 | 3: Half | Public | Scale | No | Departmental |  |  | Coastal management | Livestock production
3 | 2: Some | NGO | Sector |  | National |  |  | Disaster risk reduction | Manufacturing
4 | 1: None |  |  |  |  | 5: Very high improvement | Established | Food security | other
|  | National |  |  |  | 4: High improvement | Maintained | Health | Services
|  | Regional |  |  |  | 3: Moderate improvement | Improved | Urban development | Tourism-related
|  | Local |  |  |  | 2: Limited improvement |  | Water management | Trading
[6 empty] | 1: No improvement |  | Multi-sector
|  | 1 -generated information is irrelevant, and neither the stakeholders reached nor the timeframe managed were achieved | 1: No info transferred on time | 4: High capacity | 5: Fully aware | 5: Highly responsive (All defined elements ) | 5: Fully improved | Roads | 5: Very effective
Asia-Pacific | NIE | 2 -the existence of some challenge in any of the three aspects of the indicator (generation of dissemination, stakeholders reached or timeframe managed) | 2: Somewhat info transferred | 3: Medium capacity | 4: Mostly aware | 4: Mostly responsive (Most defined elements) | 4: Mostly Improved | Gov Buildings | 4: Effective
Latin America and Caribbean | RIE | 3 -relevant information is generated and disseminated to all identified stakeholders on timely basis | 3: Info transferred on time | 2: Low capacity | 3: Partially aware | 3: Moderately responsive (Some defined elements) | 3: Moderately improved | Causeways | 3: Moderately effective
Africa | MIE |  |  | 1: No capacity | 2: Partially not aware | 2: Partially responsive (Lacks most elements) | 2: Somewhat improved | Airports | 2: Partially effective
Eastern Europe |  |  |  |  | 1: Aware of neither | 1: Non responsive (Lacks all elements ) | 1: Not improved | Schools | 1: Ineffective
| ha protected | [6 empty] | Training Centres
| ha rehabilitated | [5 empty] | Monitoring/Forecasting capacity | Hospitals
Afghanistan, Islamic Rep. of | km protected | [5 empty] | Policy/regulatory reform | Drinking water systems
Angola | km rehabilitated | 1: Risk knowledge | 1: No plans conducted or updated |  |  |  | Capacity development | Other
Albania |  | 2: Monitoring and warning service | 2: Undertaking or updating of assessments in progress |  |  | Communication & Information policy | Sustainable forest management
Argentina |  | 3: Dissemination and communication | 3: Risk and vulnterability assessments completed or updated |  |  | Domestic policy | Strengthening infrastructure | 1: Health and Social Infrastructure (developed/improved)
Armenia | Forests | 4: Response capability |  |  |  | Economic policy | Supporting livelihoods | 2: Physical asset (produced/improved/strenghtened)
Antigua and Barbuda | Mangroves |  |  |  |  | Education policy | Mangrove reforestation
Azerbaijan | Coasts |  | From 0 to 0.5% |  |  | Energy policy | Coastal drainage and infrastructure
Burundi | Rangelands |  | From 0.5 to 1% |  |  | Environmental policy | Irrigation system
Benin | Cultivated land/Agricultural land |  | From 1% to 5% |  |  | Foreign policy | Community-based adaptation
Burkina Faso | Catchment area/Watershed/Aquifer |  | From 5% to 10% |  |  | Health policy | Erosion control
Bangladesh | Protected areas/National parks |  | From 10% to 20% |  |  | Housing policy | Soil water conservation
Bulgaria | Other |  | From 20% to 30% |  |  | Human resource policies | Microfinance
Bahrain |  |  | From 30% to 40% |  |  | Information policy | Special Program for women
Bahamas, The |  |  | From 40% to 50% |  |  | Macroeconomic policy | Livelihoods
Bosnia and Herzegovina |  |  | Above 50% |  |  | Monetary policy | Water storage
Belarus | [5 empty] | Population policy | ICT and information dissemination
Belize | [5 empty] | Private policy
Bolivia | [5 empty] | Public policy
Brazil | [5 empty] | Science policy
Barbados | [5 empty] | Social policy
Bhutan |  | 3- relevant information is generated and disseminated to all identified stakeholders on timely basis |  |  |  | Transportation policy
Botswana |  | describe |  |  |  | Urban policy
Central African Republic |  | 2- the existence of some challenge in any of the three aspects of the indicator |  |  |  | Water policy
Chile |  | describe |  |  |  | Other policy
China, People's Republic of |  | 1- generated information is irrelevant and neither the stakeholders reached nor the timeframe managed were achieved
Cote d'Ivoire |  | describe
Cameroon
Congo, Dem. Rep. of
Congo, Republic of
Cook Islands
Colombia
Comoros
Cape Verde
Costa Rica
Cuba
Czech Republic
Djibouti
Dominica
Dominican Republic
Algeria
Ecuador
Egypt
Eritrea
Estonia
Ethiopia
Fiji
Micronesia, Fed. States of
Gabon
Georgia
Ghana
Guinea
Gambia, The
Guinea-Bissau
Equatorial Guinea
Grenada
Guatemala
Guyana
Honduras
Croatia
Haiti
Hungary
Indonesia
India
Iran, Islamic Republic of
Jamaica
Jordan
Kazakhstan
Kenya
Kyrgyz Republic
Cambodia
Kiribati
Saint Kitts and Nevis
Korea, Republic of
Lao People's Democratic Republic
Lebanon
Liberia
Libya
Saint Lucia
Sri Lanka
Lesotho
Lithuania
Latvia
Morocco
Moldova
Madagascar
Maldives
Mexico
Marshall Islands
Macedonia, former Yugoslav Republic of
Mali
Malta
Myanmar
Montenegro
Mongolia
Mozambique
Mauritania
Mauritius
Malawi
Malaysia
Namibia
Niger
Nigeria
Nicaragua
Niue
Nepal
Nauru
Oman
Pakistan
Panama
Peru
Philippines
Palau
Papua New Guinea
Poland
Korea, Dem. People's Rep. of
Paraguay
Romania
Russian Federation
Rwanda
Saudi Arabia
Sudan
Senegal
Solomon Islands
Sierra Leone
El Salvador
San Marino
Serbia
Sao Tome and Principe
Suriname
Slovak Republic
Slovenia
Swaziland
Seychelles
Syrian Arab Republic
Chad
Togo
Thailand
Tajikistan
Turkmenistan
Tonga
Trinidad and Tobago
Tunisia
Turkey
Tuvalu
Tanzania
Uganda
Ukraine
Uruguay
Uzbekistan
Saint Vincent and the Grenadines
Venezuela
Vietnam
Vanuatu
Samoa
Yemen, Republic of
South Africa
Zambia
Zimbabwe
Timor-Leste

## Units for Indicators
Fund Outcome Indicator Units
1. Generation of relevant data, Stakeholders, and Timeliness 2.1. Include both qualitative and quantitative measures of capacity level within targeted institutions 2.2. Number (men and women and other vulnerable groups) 3.1. Use scale from 1 to 5: 5: Fully aware 4: Mostly aware 3: Partially aware 2: Partially not aware 1: Aware of neither predicted adverse impacts of climate change nor of appropriate responses 3.2. Use scale from 1 to 5: 5: All 4: Almost all 3: Half 2: Some 1: None 4.1. Summarize in an overall scale (1-5): 5: Highly responsive (All defined elements ) 4: Mostly responsive (Most defined elements) 3: Moderately responsive (Some defined elements) 2: Partially responsive (Lacks most elements) 1: Non responsive (Lacks all elements ) 4.2. Summarize in an overall scale (1-5): 5: Fully improved 4: Mostly Improved 3: Moderately improved 2: Somewhat improved 1: Not improved 5. Depends on the targeted natural asset: Biological (species): measure through changes in population numbers (dynamics, structure, etc.) Land: measure changes in hectares. Baseline data will be necessary to estimate the change. Supporting indicators baseline and target (as well as contextual information) are needed such as the following: Farmers adopting recommended technologies, Ha. of land improved, Average deforestation rate Etc. Use scale from 1 to 5. 5: Very effective (All elements are present) 4: Effective (Most elements are present) 3: Moderately effective (Some elements are present) 2: Partially effective (Most elements are not present) 1: Ineffective (No elements are present) 6.1. Summarize in an overall scale (1-5): 5: Very high improvement 4: High improvement 3: Moderate improvement 2: Limited improvement 1: No improvement 6.2. Household income by source of livelihood in project area (USD) prior and post project intervention 7. Summarize in an overall scale (1-5). 5: All (Fully integrated) 4: Most 3: Some 2: Most not integrated 1: None
Fund Output Indicator Units
1.1. Number, sector(s) and level(s) of projects or interventions in separate fields of monitoring plan 1.2. Number 2.1.1. Number of staff (male/female) of targeted institutions: a. Obtain baseline information: total number of staff from targeted institutions b. Define target 2.1.2. Number of staff (male/female) of targeted institutions: a. Obtain baseline information: total number of staff from targeted institutions b. Define target: needs to be defined by project proponents 2.2.1. Quantitative: Percentage (includes women – and other vulnerable groups – and men). Qualitative: Adequacy: include direct analysis of major areas; adequacy/effectiveness of systems or analysis of perceptions of populations and institutions. 2.2.2. Number (broken down by gender and, if possible, by vulnerable groups defined in the area of intervention) of people 3.1. Number and type (in separate columns) at local level. 3.2. Number 4.1. Number and type 4. 2. Number and type (entered in separate columns) 5. Number of interventions by type of natural asset and intervention 6.1. Number and type (in separate columns of monitoring plan) 6.2. Income sources per household; description of income source and number of households. 7.1. Number/Sector 7.2. Number; Effectiveness (see previous indicator) through enforcement level.