## Overview
Project Performance Report (PPR)
| Period of Report (Dates) | March 2011 - Junio 2012
| Project Title: | Reduction of Risks and Vulnerability Based on Flooding and Droughts in the Estero Real River Watershed.
| Project Summary: | The programme is aimed to reduce risks from droughts and flooding generated by climate change and variability in the watershed of the Estero Real River. In Chinandega and León, the Estero Real River Watershed (3.690 km2), and in particular the sub watershed of the Villanueva River (1,550 km2)—also known as Rio Grande or Aquespalapa—is emblematic of the combined impacts of poor development models and strong climate variability. The programme will rely upon a coordinated set of interventions designed to implement new public policies for addressing climate change by introducing agro-ecological practices and participatory watershed management in highly vulnerable rural communities. Through targeted investments in water retention, long-term farm planning, and institutional capacity building in local communities, municipalities and government agencies, the Programme will validate an adaptation scheme as a vehicle for implementation of the national climate change strategy.
|  |  | Countries | Project Type: |  | GEF Focal Area: | GEF 4 Focal Areas | GEF 2 / 3 Operational Programme: | Overall Rating of the project in the evaluation by the project evaluator: | GEF-4 Focal Area Strategic Program: | GEF-3 Focal Area Strategic Program:
| Database Number: | AFB/MIE/Water/2010/1 | Afghanistan | FP | Yes | Biodiversity | 1 | 1 | U | BD-SP1-PA Financing | 1: Arid & semi-arid ecosystems
Implementing Entity (IE) [name]: |  | United Nations Development Programme | Albania | MSP | No | Climate Change Adaptation | 2 | 2 | S | BD-SP2-Marine PA | 2: Coastal, marine & freshwater ecosystems
| Type of IE: | Multilateral | Algeria | EA |  | Climate Change Mitigation | 3 | 3 | MU | BD-SP3-PA Networks | 3: Forest ecosystems
| Country(ies): | Nicaragua | Angola |  |  | International Waters | 5 | 5 | Good | BD-SP5-Markets | 13: Conservation and Sustainable Use of Biological Diversity Important to Agriculture
Relevant Geographic Points (i.e. cities, villages, bodies of water): |  | Watershed of the Estero Real River, sub watershed of Villanueva River. | Argentina |  |  | Multiple Focal Area |  |  |  | BD-SP7-Invasive Alien Species(IAS) | 6: Promoting the adoption of renewable energy by removing barriers and reducing implementation costs
[8 empty] | CC-SP2- Industrial EE | 8: Waterbody based operational program
| Project Milestones | [6 empty] | CC-SP3-RE,CC-SP4-Biomass | 9: Integrated Land and Water multiple focal area
| Milestone |  | Bahamas | [6 empty] | CC-SP5-Transport | 10: Contaminants based operational program
AFB Approval Date: |  | December, 2010
IE-AFB Agreement Signature Date: |  | March, 2011 | [6 empty] | CC-SP6-LULUCF | 12: Integrated Ecosystem Management
Start of Project/Programme: |  | June, 2011 | [6 empty] | Cross cutting capacity building | 14: Persistent Organic Pollutants
Mid-term Review Date (if planned): |  | February, 2013
| Terminal Evaluation Date: | February, 2015
|  | List documents/ reports/ brochures / articles that have been prepared about the project. | Cyprus
|  | Operations Manual for the Reduction of Risks and Vulnerability based on Flooding and Droughts in the Estero Real River Watershed Programme, Methodological Guidelines to Formulate Agroecological Farm Transformation Plans; Monthly Follow-up Reports (Government); Quarterly Reports (UNDP); Management Report Year 2011 (Government) | Czech Republic
| List the Website address (URL) of project. |  | Democratic People's Republic of Korea
|  | http://www.undp-alm.org/projects/af-nicaragua | Democratic Republic of the Congo
Denmark
| Project contacts: |  | Djibouti
National Project Manager/Coordinator |  |  | Dominica
| Name: | Orlando Caceres | Dominican Republic
| Email: | hocaceres@yahoo.com.ar | Ecuador
| Date: | 2012-05-07 | Egypt
| Government DA |  | El Salvador
| Name: | Denis Fuentes | Equatoral Guinea
| Email: | dfuentes@marena.gob.ni | Eritrea
| Date: | 2012-05-07 | Estonia
| Implementing Entity |  | Ethiopia
| Name: | Maria Fernanda Sanchez / Reis Lopez Rello | Fiji
| Email: | fernanda.sanchez@undp.org / reis.lopez.rello@undp.org | Finland
| Date: | 2012-05-07 | France
| Executing Agency |  | Gambia
| Name: | Martha Elena Ruiz | Georgia
| Email: | mruiz@marena.gob.ni | Germany
| Date: | 2012-05-07 | Ghana
| Executing Agency |  | Greece
| Name: |  | Grenada
| Email: |  | Guatemala
| Date: |  | Guinea
| Executing Agency |  | Guinea Bissau
| Name: |  | Guyana
| Email: |  | Haiti
| Date: |  | Honduras
Hungary
Iceland
India
Indonesia
Iran (Islamic Republic of)
Iraq
Ireland
Israel
Italy
Jamaica
Japan
Jordan
Kazakhstan
Kenya
Kiribati
Kuwait
Kyrgyzstan
Lao People’s Democratic Republic
Latvia
Lebanon
Lesotho
Liberia
Libyan Arab Jamahiriya
Liechtenstein
Lithuania
Luxembourg
Madagascar
Malawi
Malaysia
Maldives
Mali
Malta
Marshall Islands
Mauritania
Mauritius
Mexico
Micronesia, Federated States of
Monaco
Mongolia
Montenegro
Morocco
Mozambique
Myanmar
Namibia
Nauru
Nepal
Netherlands
New Zealand
Nicaragua
Niger
Nigeria
Norway
Oman
Pakistan
Palau
Panama
Papua New Guinea
Paraguay
Peru
Philippines
Poland
Portugal
Qatar
Republic of Korea
Republic of Moldova
Romania
Russian Federation
Rwanda
Saint Kitts and Nevis
Saint Lucia
Saint Vincent and the Grenadines
Samoa
San Marino
Sao Tome and Principe
Saudi Arabia
Senegal
Serbia
Seychelles
Sierra Leone
Singapore
Slovakia
Slovenia
Solomon Islands
Somalia
South Africa
Spain
Sri Lanka
Sudan
Suriname
Swaziland
Sweden
Switzerland
Syrian Arab Republic
Tajikistan
Thailand
The former Yugoslav Republic of Macedonia
Timor-Leste
Togo
Tonga
Trinidad and Tobago
Tunisia
Turkey
Turkmenistan
Tuvalu
Uganda
Ukraine
United Arab Emirates
United Kingdom of Great Britain and Northern Ireland
United Republic of Tanzania
United States of America
Uruguay
Uzbekistan
Vanuatu
Venezuela, Bolivarian Republic of
Viet Nam
Yemen
Zambia
Zimbabwe

## FinancialData
Financial information: cumulative from project start to 30 - Jun - 2012
DISBURSEMENT OF AF GRANT FUNDS
How much of the total AF grant as noted in Project Document plus any project preparation grant has been spent to date?
Estimated cumulative total disbursement as of JUNE, 2012 | 403654
Add any comments on AF Grant Funds. (word limit=200) | According to the project document, $1,990,000 should be executed during the first year, however the budget was modified at the inception workshop.
EXPENDITURE DATA
List item / activity / action and corresponding amount spent for the current reporting period | ITEM / ACTIVITY / ACTION | AMOUNT
| 1. Investments in infrastructure for storing and using rain and surface water in eight micro-watersheds in the upper watershed of the Estero Real River. | 66184
| 2. Introduction of climate resilient agro-ecological practices to make effective use of available water. | 81052
| 3. Institutional development and capacity building in micro-watersheds, municipalities, and participating national institutions | 19568
| 4. Ongoing monitoring and analysis of climatic conditions and changes in land use, water flows and soil quality | 48229
| Project Execution | 188621
| TOTAL | 403654
PLANNED DISBURSEMENT SCHEDULE
List item / activity / action planned and corresponding projected cost for the upcoming reporting period | ITEM / ACTIVITY / ACTION | PROJECTED COST | Est. Completion Date
| 1. Investments in infrastructure for storing and using rain and surface water in eight micro-watersheds in the upper watershed of the Estero Real River. | 685643 | 2013-06-01
| 2. Introduction of climate resilient agro-ecological practices to make effective use of available water. | 472290 | 2013-06-01
| 3. Institutional development and capacity building in micro-watersheds, municipalities, and participating national institutions | 20183 | 2013-06-01
| 4. Ongoing monitoring and analysis of climatic conditions and changes in land use, water flows and soil quality | 195710 | 2013-06-01
| TOTAL | 1373826
ACTUAL CO-FINANCING
How much of the total co-financing as committed in the Project Document has actually been realized?
If the MTR or TE have not been undertaken this reporting period, DO NOT report on actual co-financing.
Estimated cumulative actual co-financing as verified during Mid-term Review (MTR) or Terminal Evaluation (TE).
Add any comments on actual co-financing in particular any issues related to the realization of in-kind, grant, credits, loans, equity, non-grant instruments and other types of co-financing. (word limit=200)

## Risk Assesment
RISK ASSESMENT
IDENTIFIED RISKS
List all Risks identified in project preparation phase and what steps are being taken to mitigate them (word limit = 200)
Identified Risk | Current Status | Steps Taken to Mitigate Risk
Farmers and households have limited understanding of the importance and/or the possibility of responding and planning for current and future climate change impacts | Low | 35 community assemblies have been carried out to raise awareness among farmers and households of the risks possed by climate change impacts, the importance of participating in the AF project - led by MARENA - and applying adaptation measures in their farms. Likewise, the 280 families visited to gather baseline information for the agro-ecological transformation plans have been receptive about implementing silvopastoral systems.
Limited access to credit can limit adopting new technologies | Low | Up to now there has been no action to mitigate this risk, since the implementation of the investment plans in the farms will begin during the second semester of 2012.
Key national and municipal stakeholders do not agree on a common watershed adaptation strategy | Low | MARENA has initiated the process to formalize alliances among local and national stakeholders by signing formal interinstitutional agreements between MARENA-INETER, MARENA-ANA, MARENA-MAGFOR-IDR-INTA and MARENA-Municipality of El Sauce. MARENA is formulating Municipal Adaptation Plans for three targeted municipalities - Achuapa, El Sauce and Villanueva - involving local stakeholders such as producer's organizations: National Agricultural and Stockbreeders Union (UNAG), Agricultural and Livestock Cooperatives Union for El Sauce (UCASA), Juan Francisco Paz Silva Producers' Cooperative. Government institutions: Ministry of Health (MINSA), Ministry of Education (MED), National Police, Nicaraguan Institute of Agricultural Technology (INTA), Ministry of Agriculture, Livestock and Forestry (MAGFOR), Ministry of Family, as well as Movimiento de Jovenes Ambientalista Guardabarranco (Guardabarranco Environmental Youth Movement), Poder Ciudadano en Achuapa, El Sauce and Villanueva, and the Associations of the Municipalities of Chinandega Norte and Leon Norte, through the implementation of 18 workshops with the participation of 963 people (522 men and 441 women).
Extreme weather events could delay project's execution. | Medium | In September and October 2011, tropical storms caused rockfall, landslides, and flooding in the municipalities of Achuapa, El Sauce and Villanueva, which caused the proliferation of the leptospira bacteria which causes leptospirosis. Moreover, storms destroyed road infrastructures, limiting access to the communities. In light of this situation, the Government of Nicaragua decreed a National State of Emergency as a consequence of extreme weather impacts.
Critical Risks Affecting Progress (Not identified at project design)
Identify Risks with a 50% or > likelihood of affecting progress of project
Identified Risk | Current Status | Steps Taken to Mitigate Risk
Works design had weaknesses | This risk has decreased | A new design was formulated for the communal irrigation system for the community of Salale.
Risk Measures: Were there any risk mitigation measures employed during the current reporting period? If so, were risks reduced? If not, why were these risks not reduced?
Add any comments relevant to risk mitigation (word limit = 500)
The Salale communal irrigation system had to be redesigned and relocated in order to reduce the environmental impact on the site; the water will be carried through a pipeline instead of an open channel, avoiding sanitary risks and allowing a greater number of families to be incorporated (from 20 original families planned to 32 families). Additionally, the document anticipated carrying out a "hydrological study of the Villanueva River lower watershed, that would allow identifying the hydraulic works required to reduce flooding caused by sediment from the higher watershed". An Interinstitutional Commission was formed in the framework of the Project Coordination Committee which carried out field visits and gathered existing information to define the study's scope, identifying the need to widen the study's scope in order to be able to determine the zone's vulnerability and risks. In addition, MARENA is completing the study with available information that other stakeholders have already provided.

## Rating
RATING ON IMPLEMENTATION PROGRESS
For rating definitions please see bottom of page.
| Progress on Key Milestones |  | Expected Progress |  | Progress to Date | Rating
Project Manager/Coordinator: | The construction of 2 communal irrigation systems to supply water to 85 farming families in 2 micro watersheds, which increases the availabitlity of water for small scale domestic and productive use and reduces the risk of water stress and drought. |  | That construction gets underway to be completed during the second semester of 2012, especially the Salale communal irrigation system. |  | The construction of the communal irrigation system in Las Mercedes micro-watershed has started, which will directly benefit 65 farming families to carry out irrigation activities. Additionlly, the communal irrigation system for the Salale micro-watershed was redesigned, with construction starting in October 2012, to directly benefit 32 farming families. In addition, at the territorial level the municipal governments are strengthening partnership strategies to address the water crises, especially during the critical 6 months when there is a shortage of water, to support initiatives to implement local water management plans. | Satisfactory (S)
|  |  | At least 880 rain water collection and storage structures supply water to family farms in 8 micro-watersheds. |  | In the framework of agro-ecological transformation plans construction sites have been identified for 177 water harvesting systems (collection and storage), with construction beginning in August 2012. | Satisfactory (S)
| Preparation of the hydrological study for the higher, middle and lower micro-watershed of the Villanueva River. |  | To have carried out the hydrological study in the second semester of 2012. |  | A consultation process was carried out with the municipalities of Somotillo, Villanueva, Representatives of the National Assembly and Government institutions such as the Ministry of the Environment and Natural Resources, the Nicaraguan Institute of Territorial Studies, the Executive Secretariat of the National System for Prevention, Mitigation and Attention to Disasters, and the Ministry of Transportation and Infrastructures to know in situ the problems generated by flooding in the middle and lower part of the Villanueva River micro-watershed, specifically in the stretch of 7.2 km in the community of Las Pozas. A topographical survey is being carried out which will allow to have updated information to develop vulnerability and risks to flooding maps for the municipalities of Villanueva and Somotillo, which will allow identifying the critical flooding points and complete the information necessary to have the hydrological study ready in the first semester of 2013. All this process is being carried out in the framework of a cooperation agreement between the Ministry of the Environment and Natural Resources and the Nicaraguan Institute of Territorial Studies. | Satisfactory (S)
| At least 1005 farming families have agro-ecological transformation plans in their farms, which will allow introducing climate resilient agro-ecological practices to use the available water effectively, using their own resources and available credit for their implementation. |  | The preparation of 1005 agro-ecological transformation plans in family farms as an essential instrument to guide investments in productive systems. |  | The preparation of 280 agro-ecological transformation plans in family farms has become an essential instrument to guide investments in productive systems and to identify gender relationships that allow focusing MARENA's efforts in strengthening equal participation of family members in productive system tasks. In this regard, the implementation of the organization model through the community has facilitated the data collection process and the formulation of transformation plans and other actions to be implemented in the communities and municipalities. | Satisfactory (S)
| Identification and prioritization for 400 ha of riparian and recharge zones of drinking water systems in state of degradation. |  | Start the identification process of water riparian and recharge zones in order to carry out the demarcation and preparation of territorial management plans during the second semester of 2012 |  | Field visits were carried out to identify water riparian and recharge zones in the 8 micro-watersheds for a total of 2000 ha which are located in strategic places in order to supply water to the neighboring communities. | Satisfactory (S)
| Design and development of a campaign to control and prevent forest, agricultural and livestock fires in coordination with Civil Defense. |  | Develop a fire prevention and control campaign with the participation of local stakeholders of the micro-watersheds in the 3 municipalities. |  | The campaign was focused in raising awareness in the communities in the micro-watersheds where meetings and sessions with students and the general population took placerelated to forest fires. The participation of the Civil Defense was key, as well as that of the municipalities with their local disaster prevention committees. | Satisfactory (S)
| Support households and farmers in 3 municipalitites to cope with climate change impacts by developing 3 tailored municipal climate change adaptation plans in the municipalities of Villanueva, El Sauce and Achuapa. |  | Develop the methodology for the development of the adaptation plans for each municipality and have them agreed by the municipal councils in the second semester of 2012, to be used a planning tool for each municipality. |  | Households and farmers were trianed during 18 workshops at each municipality to generate information and input from MARENA to develop the adaptation plans, with specific strategic lines per municipality. | Satisfactory (S)
| Establish electronic information posts to gather information of each of the 8 micro-watersheds with support from SINIA-MARENA and the governmental institutions. |  | To hire technical support responsible for the implementation of electronic information posts and their technical strengthening in the second semester of 2012. |  | Technicians responsible for the electronic information posts were hired to start collecting baseline information on the environmental and productive indicators in each of the micro-watershed communities. A training course is been developed on SIG and ARWIS tools to gather and process cartographical information. | Satisfactory (S)
[5 empty] | Overall Rating | Satisfactory (S)
Please Provide the Name and Contact information of person(s) reponsible for completeling the Rating section
| Name: | Orlando Cáceres
| Email: | horlandocaceres@yahoo.com.ar
Please justify your rating. Outline the positive and negative progress made by the project since it started. Provide specific recommendations for next steps. . (word limit=500)
Since the project has been only implemented for a year, strong progress had been made by MARENA towards generating agreements and coordinating with other Ministries and institutions to carry out activities as planned in the annual work plan. Positive progress has been made in relation to construction of communal irrigation systems and rain water collection and storage structures. Moreover, MARENA is developing agro-ecological transformation plans for family farm in the targeted municipalities and has secured support for establishing electronic information posts in the 8 micro-watersheds to generate and compile climate-related data. Although integrating adaptation into development plans will be a major task, MARENA facilitated 18 workshops to train local stakeholders which input will be analyzed and included per municipality. Overall, the project has generated an important momentum internally in MARENA, where working groups have been created and externally where alliances have been institutionalized among government institutions and relevant stakeholders.
| Progress on Key Milestones |  | Expected Progress |  | Progress to Date | Rating
Implementing Agency | Component 1: As established in the yearly annual work plan, MARENA initiate the construction of two communal irrigation systems that will benefit 85 households in two micro-basins to increase water availability for domestic and productive use. |  | Works to establish communal irrigation systems have started and expected to be finalized in late 2012. |  | The construction of the communal irrigation system in Las Mercedes micro-basin started, and it´s expected to benefit 65 households while communal irrigation system in Salale micro-basin has been already designed and its construction is expected to start by October 2012 to benefit 32 households. | S
| Component 2: At least 1005 households have been provided with plans to introduce silvopastoral systems that promote climate resilient agro-ecological practices. In addition, MARENA has identified and prioritized 400 ha of riparian and water system recharge zones to be protected. |  | Development of 1005 plans of agro-ecological transformation plans to introduce silvopastoral systems in family farms. Identification of areas of riparian and water system recharge zones to be protected and develop territorial management plans. |  | 1005 farmers and households will be provided with plans of agro-ecological transformation to introduce silvopastoral systems which are currently under development. Currently MARENA is integrating data and sub-national officer and communities’ feedback. Field visits were carried out to identify water riparian and recharge zones in the prioritized 8 micro-watersheds. In addition, demarcation of riparian and recharge zones and development of management plans will be finalized late 2012. | S
| Component 3: Support households and farmers in 3 municipalitites to cope with climate change impacts by developing climate change adaptation plans for the Villanueva, El Sauce and Achuapa municipalities. |  | Develop a methodology to integrate adaptation to climate change under micro-basin management plans for the selected municipalities. |  | 963 people (522 men and 441 women) were trained on adaptation-related risks and opportunitites during the implementation of 18 workshops. Currently all input provided by the communities at each workshop is been analyzed by MARENA which will develop a tailored methodology to integrate adaptation under management plans focusing in detailing strategic lines per municipality. | S
| Component 4: Commission a hydro geologic study for the upper, middle and lower lever of the Villanueva River basin. In addition, electronic information posts are being installed in each targeted micro-watershed, to provide geo-referenced information to MARENA and SINIA. |  | To commission the hydro geologic study for the Villanueva River basin and to ensure technical support for the implementation of electronic information posts. |  | The hydro geologic study will provide current information data on dynamics of the Villanueva River basin to identify the causes of the flooding, which is currently been carried out based on a topographic survey to elaborate vulnerability and flood hazard maps in Villanueva and Somotillo Municipalities. In addition, MARENA, using AF resources, has secured technical support for the implementation of electronic information posts to start collecting baseline information on indicators of selected micro-watersheds. | S
[5 empty] | Overall Rating | S
Please Provide the Name and Contact information of person(s) reponsible for completeling the Rating section
| Name: | Maria Fernanda Sanchez / Reis Lopez Rello
| Email: | fernanda.sanchez@undp.org / reis.lopez.rello@undp.org
| Progress on Key Milestones |  | Expected Progress |  | Progress to Date | Rating
Other
Overall Rating
Please Provide the Name and Contact information of person(s) reponsible for completeling the Rating section
Name:
Email:
| Please justify your rating and address the following points: 1. Indicate trends, both positive and negative, in achievement of outcomes as per the project indicators. 2. Detail critical risks that have affected progress. 3. Outline response to MTR undertaken this reporting period. 4. Outline action plan to address projects with a rating of HU, U or MU. Please keep your input to 1200 words |  | During 1st year of implementation, MARENA established agreements with Ministries and government institutions in each micro-watershed in accordance with its respective areas of competence. Similarly, MARENA integrated municipal technical teams in El Sauce, Achuapa, and Villanueva municipalities to optimize coordination among sub-national governments, cooperatives, farmers’ organizations and NGOs that are active in the area. MARENA, using AF resources, has initiated construction works for two communal irrigation systems that will increase water availability for domestic and productive use. Around 85 households - 65 households in Las Mercedes micro-watershed and 32 households in Salale micro-watershed– will benefit from the construction of two communal irrigation systems. In addition, 1005 family farms will be provided with plans for agro-ecological transformation to introduce silvopastoral systems which are under development by MARENA. To participate effectively in the preparation of micro-watershed and sub-watershed plans, MARENA trained 963 people (522 men and 441 women) on adaptation-related risks and opportunities during the implementation of 18 workshops. These forums served as open spaces to examine and discuss information, share own experiences, debate its implications, examine options for action and consequences of each option, and build agreements. All input provided by households and sub-national governments is being analyzed by MARENA to develop micro-watershed management plans with strategic lines per municipality. Finally, MARENA, using AF funds, has secured technical support for the implementation of electronic information posts to start collecting baseline information on indicators of selected micro-watersheds. Electronic information post established in each targeted micro-watershed will feed in the National Environmental Information System (SINIA) to develop geo-referenced information to be used for local stakeholders and as monitoring tools for activities carried out by MARENA in El Sauce, Achuapa, and Villanueva municipalities. Total disbursement as of June 2012 has been equal to USD$403,654. First tranche amounting for USD$1,990,000 was modified at the Inception workshop and set at USD$400,000. The Inception Workshop was carried out from 21st to 24th June 2011, officially starting the project. The 2nd tranche of USD$1,440,000 was disbursed in July 2011. As of June 2012, USD$403,654 have been executed, leaving a balance of USD$1,436,346. The expenses from June to December 2011 were USD$126,544 and from January to June 2012 were USD$277,110 totaling USD$403,654. It´s been estimated that at the end of 2012 USD$1,711,406 will be executed, which means a cumulative expenditure of USD$2,115,058 representing 42% of the entire budget of the project. During first semester of 2012 it was planned the construction of the two communal irrigation systems in watersheds of Salale and Las Mercedes, totaling USD$730,000. It was decided that communal irrigation systems construction works will be carried out in the 2nd semester of 2012 for various reasons: As indicated in the project document, there were designs for works that had been prepared by an earlier international cooperation project (2008). However, during the process of preparing technical documents to start the bidding process, it was detected the need to review designs to update and tailor technical elements, especially those related to reducing the environmental impact of preparing the site where the works would be built. The review process of communal irrigation systems construction works culminated in the development of a new design and relocation of one irrigation system (Salale) that will benefit more families while reducing the environmental impact on the site. In May 2012 the company that will build the communal irrigation system in the watershed of Las Mercedes was hired and it is expected to finalized construction works in October 2012. The redesign of communal irrigation system of Salale began in March and ended in July 2012. In August, the tender for communal irrigation system of Salale was opened, and it is expected to finalize contract and start works in October. In addition, the design of small-scale works to capture and store water at the farm level was subject to the development of agroecological farms plans. From June to December 2011, MARENA focused on developing the Methodological Guide for Agroecological Transformation at Farm Level, aiming to generate and capture field information with the support from students of the School of Agro-Ecology, however it was not possible as the period of field practice did not coincide with the project. Local consultants were hired to generate and analyzed field information to support the development of agroecological transformation plans. At the end of 2012, the project will be benefiting 307 families by constructing small-scale works to capture and store water at the farm level. To date, 462 transformation agroecological plans at farms level have been designed, aiming to have 500 in December. Finally, at the end of 2012, MARENA will have begun the process of implementing transformation agroecological plans in which 50% of the total budget is expected to be executed.
Rating Definitions
|  |  |  | Highly Satisfactory (HS) | Project actions/activities planned for current reporting period are progressing on track or exceeding expectations to acheive all major objectives/outcomes for given reporting period, without major shortcomings. The project can be presented as “good practice”.
|  |  |  | Satisfactory (S) | Project actions/activities planned for current reporting period are progressing on track to achieve most of its major objectives/outcomes with only minor shortcomings.
|  |  |  | Marginally Satisfactory (MS) | Project actions/activities planned for current reporting period are progressing on track to achieve most major relevant objectives/outcomes, but with either significant shortcomings or modest overall relevance.
|  |  |  | Marginally Unsatisfactory (MU) | Project actions/activities planned for current reporting period are not progressing on track to achieve major objectives/outcomes with major shortcomings or is expected to achieve only some of its major objectives/outcomes.
|  |  |  | Unsatisfactory (U) | Project actions/activities planned for current reporting period are not progressing on track to achieve most of its major objectives/outcomes.
|  |  |  | Highly Unsatisfactory (U) | Project actions/activities planned for current reporting period are not on track and shows that it is failing to achieve, and is not expected to achieve, any of its objectives/outcomes.

## Project Indicators
PROJECT Indicators
Please provide all indicators being tracked for the project as outlined in the project document
Type of Indicator (indicators towards Objectives, Outcomes, etc…)
Type of Indicator | Indicator | Baseline | Progress since inception | Target for Project End
Indicador de Programa | Number of farm families in the targeted micro-watersheds with at least one annual harvest. | 400 | Progress has only be made on the development of 120 agro-ecological farm transformation plans; this indicator will show progress in the next PPR | 1005
Indicador de Programa | Number of farm families included in Sub-Watershed management proposal. | 0 | Preparation of the Micro-Watershed Management Plans has not yet started | 7120
Indicador de Resultado | Percentage of farms in each micro-watershed with access to irrigation by means of hydraulic works built with programme funds. | 0 | One hundred seventeen water harvesting works have been identified which will benefit 120 families of the municipality of Achuapa (41 basins, 4 ponds, 25 drinking troughs, 21 lined springs of water, 12 water tanks to collect rain water, 8 lined wells, and 6 rope pumps) in the micro-watersheds of San Antonio, Varela and El Cacao-Coyolar. The identificationof 190 works in the municipalities of El Sauce and Villanueva will be completed in September for a total of 307 water related works that will be installed by December 2012. | 90%
Indicador de Resultado | Surface in hectares to increase low risk | 67.55 has | The irrigation systems are still not working; at this time they have only been designed and identified. | 161.5 has
Indicador de Resultado | Amount of water (lts/sec) carried through the communal irrigation system infrastructures. | 0 lts/seg | At the beginning of the project the original designs for the work were reviewed and consulted with the communities. The communal irrigation system in the micro-watershed of Las Mercedes was tendered in May 2012 and construction started in June 2012. This system will directly benefit 65 farming families and it is estimated that the flow will be 30 lts/sec. Construction is expected to be completed in November 2012. On the other hand, the communal irrigation system of the Salale micro-watershed had to be redesigned and relocated, its construction is expected to begin in October 2012 - this system will directly benefit 32 farming families. | 50 lts/seg
Indicador de Resultado | Percentage of farmers in each micro-watershed, the water use of which is rated as satisfactory in relation to the relevant technical guidelines. | 5% | The irrigation systems are not working yet; at this time they have only been designed and identified | 90%
Indicador de Resultado | Number of water harvesting works installed and working at the micro-watershed level | 0 | Through the information gathering process for the preparation of agro-ecological farm transformation plans, 117 water harvesting works have been identified that will benefit 120 families of the municipality of Achuapa (41 basins, 4 ponds, 25 drinking troughs, 21 lined springs of water, 12 water tanks for rain water collection, 8 lined wells and 6 rope pumps) in the micro watersheds of San Antonio, Varela and El Cacao-Cayolar. In September, the identification process of 190 works will be completed in the municipalities of El Sauce and Villanueva for a total of 307 water works that will be installed in December 2012. | 880
Indicador de Resultado | Percentage of farm families in each micro-watershed implementing agro-ecological farm transformation plans. | 5% | 32% of the total of agro-ecological farm transformation plans of the municipality of Achuapa have been delivered. The implementation of these plans will begin in August 2012. | 80%
Indicador de Resultado | Number of farming families with agro-ecological farm transformation plans | 0 | Baseline information has been collected to formulate 280 agro-ecological farm transformation plans. Out of these, 120 have been completed and delivered to the same number of farming families in the municipality of Achuapa, in the micro-watershed of San Antonio, Varela and El Cacao-Coyolar. In October, MARENA will complete the delivery process of 380 agro-ecological farm transformation plans in the municipalities of El Sauce and Villanueva for a total of 500 plans. | 1005
Indicador de Resultado | Area (ha) of agro-ecological transformation plans developed in farms | 0 | Three hundred twelve hectares have been identified through 120 agro-ecological transformation plans developed in the municipality of Achuapa, in the micro watershed of San Antonio, Varela and El Cacao-Cayolar. | 1120 has
Indicador de Resultado | Increase in percentage of land in each micro-watershed with vegetation coverage. | 25% | This indicator will show progress in the next PPR | 50%
Indicador de Resultado | Surface in hectares of protected forest water recharge and riparian zones | 0 | One hundred twenty hectares were identified through field work in the water recharge zones in the municipality of Achuapa, in the higher part of the micro-watershed. Currently, a consulting firm was hired to demarcate and develop the Water Recharge and Riparian Zone Management Plan prioritized in the 8 micro-watersheds of the Villanueva River sub watershed. | 400 has
Indicador de Resultado | An experientially-based proposal endorsed by three municipal governments for the operation of a Sub-Watershed Committee for the Villanueva River basin. | 0 | The coordination process started with the National Water Authority to conform the Sub-watershed Management Committee based on the General National Water Law. During the second semester of 2012, MARENA will identify stakeholders that will integrate the Sub-watershed Management Committee and share with them the legal instruments that the National Water Authority is generating regarding the organization processes at the micro-watershed, sub-watershed and watershed levels. | 1
Indicador de Resultado | Municipalities in watershed with climate change adaptation measures included with their official plans and related normative instruments. | 0 | Based on the official methodology of the Ministry of the Environment and Natural Resources to develop the Municipal Climate Change Adaptation Plans, 18 workshops were held in the municipalities of Achuapa, El Sauce and Villanueva to generate information to allows communitites to share experiences of climate-related effects and to identify adaptation measures in these municipalities. These plans will be approved by the three municipalities in September and will be reproduced for their dissemination. | 9
Indicador de Resultado | Hydrological study and number of news bulletins to disseminate the participatory monitoring of water quality and amount, soil conditions and use changes. | 0 | A consultation process was carried out with the municipalities of Somotillo and Villanueva, Representatives of the National Assembly and Government Institutions such as the Ministry of the Environment and Natural Resources, the Nicaraguan Institute of Territorial Studies, the Executive Secretariat of the National System for the Prevention, Mitigation and Attention to Disasters, and the Ministry of Transportation and Infrastructure, to identify in situ the problems generated by flooding in the middle and low part of the Villanueva River Sub-watershed, specifically in a stretch of 7.2 km in the community of Las Pozas. A topographical survey is being carried out that will allow having updated information to develop flodding vulnerability maps to the municipalities of Villanueva and Somotillo, and to identify critical flooding points and complete the information necessary to have the hydrological study ready in the first semester of 2013. All this process is operating in the framework of a collaboration agreement between the Ministry of the Environment and Natural Resources and the Nicaraguan Institute of Territorial Studies. | 1
Indicador de Resultado | Lessons learnt in eight micro-watersheds and the Villanueva River Sub-Watershed available in SINIA. | 0 | Eight nodes have been installed, one in each micro-watershed. The personnel in charge of the nodes is being trained to facilitate the management of the information. | Feed the AF and MARENA website; 4 annual reports and 12 quarterly reports.

## Lessons Learned
QUALITATIVE MEASURES and LESSONS LEARNED
Please Complete the following section every reporting period
Implementation and Adaptive Management | Response
Describe any implementation issues/lessons affecting progress (positive and negative) | The communal irrigation system for Salale had to be redesigned and relocated. In order to reduce the environmental impact on the site, for example, the water will be carried through pipelines instead of an open channel, avoiding sanitary risks and allowing the incorporation of a greater number of families (from 20 families originally planned to 32 families). To develop an Operations Manual for the implementation of the Agro-ecological Transformation Plans (Output 2.2), based on the elegibility criteria stipulated in the PRODOC. To direct around US$50,000 for investment in smaller works for efficient water use identified through the agro-ecological farm transformation plans to directly benefit women and their households. The accurate definition of indicators in the logical framework allows better follow-up and monitoring of AF project's activitites, especially to show the incorporation of the gender perspective. Implementation of government strategies that further incorporate and disseminate the regulatory instruments that promote the active participation of women; among them are the Equal Rights and Opportunity Law, the Gender Policy, and the Joint Gender Programme.
Were there any delays in implementation? If so, include any causes of delays. What are the measures taken to reduce delays? | The largest project investments are in the construction of two communal irrigation systems in the micro watersheds of Las Mercedes and Salale. These were delayed during the design revision because they were incomplete, resulting in the development of a new design and relocation of one of them (Salale), which allowed more families to benefit and also reduce the environmental impact on the site. Additionally, there were delays in the formulation of the Methodological Guidelines for the Development of Farm Plans and it was not possible to incorporate the students of the Agro-ecological School in the information gathering process, since the strudents' practice period did not coincide with the project's needs and local technicians had to be hired to gather the baseline information and overcome the delays. The delays at the beginning of the Hydrological Study were due to the need to develop a secondary information gathering process, generated by other institutions in the area of the sub-watershed of the Villanueva River. Currently, this work is being carried out in a coordinated manner in the framework of a Collaboration Agreement between the Ministry of the Environment and Natural Resources and the Nicaraguan Institute of Territorial Studies (INRTER), where a work plan has been developed to gather information that will serve as input to generate the first maps for flooding and landslide susceptibility and threat in the sub-watershed of the Villanueva River.
Describe any changes undertaken to improve results on the ground or any changes made to project outputs (i.e. changes to project design) | In order to strengthen local capacities in following-up investments in the communal irrigation systems in the micro-watersheds of Las Mercedes and Salale, a collaboration agreement was signed between MAREN-Municipality of El Sauce, to transfer resources to hire two resident engineers who will follow-up on the construction and maintainance of the communal irrigation systems. Originally, the baseline information to develop the agro-ecological farm transformation plans would be collected by agro-ecology students from UNAN Leon, however the need to hire qualified technicians with more experience to guarantee the quality of the information generated was identified; In addition, students had limited time to dedicate to the field work due to their academic work and the project was in urgent need to start the information gathering process. The project document anticipated that a "Hydrological study be carried out in the lower watershed of the Villanueva River, identifying the hydraulic works required to reduce flooding caused by sediment of the higher watershed", but recently, in the framework of the Project Coordination Committee, an interinstitutional committee was formed that carried out field visits and gathered information to define the scope of the study, identifying the need to widen its scope to determine the zone's vulnerability and risks, in addition to analyzing project impact in this zone.
How have gender considerations been taken into consideration during the reporting period? What have been the lessons learned as a consequence of inclusion of such considerations on project performance or impacts? | In the agro-ecological transformation plans family has been considered in an integral manner focusing in including gender perspective aiming to improve the implementation of these plans. The Project Operations Manual contemplates the Implementation of the Agro-ecological Farm Transformation Plan with investments managed directly by women in each of the eight micro-watersheds in the project's area of influence in the amount of around US$50,000.
Please Complete the following section at mid-term and project completion
Lessons for Adaptation | Response
Climate Resilent Measures
Please Describe the Climate Resilent measures being undertaken by the project/programme.
Which of these masures has been most effective and why?
Which have been least effective and why?
Concrete Adaptaiton Interventions
Please desribe the concrete adaptation measures being undertaken by the project/programme
What are/were the most difficult aspects of implementing such measures?
What are/were the most successful aspects of the implementation of the interventions?
Community/National Impact
What would you consider to be the most successful aspects for the target communities?
What measures are/have been put in place to ensure sustainability of the project/program results?
What measures are being/could have been put in place to improve project/program results?
Knowledge Management
Describe what kind and how existing information/data/knowledge has been used to inform the development and the implementation of the project.
If Learning Objectives have been established, have they been met? Please describe.
Describe any difficulties there have been in accessing or retrieving existing information (data or knowledge) that is relevant to the project. Please provide suggestions for improving access to the relevant data.
Has the identification of learning objectives contributed to the outcomes of the project? In what why have they contributed?
What have been the major lessons learned that would add to the knowledge base for dissemination within and beyond the project area?

## AF Tracking Tool
Tracking Tool for Adaptation Fund (AF) Projects
Goal: Assist developing-country Parties to the Kyoto Protocol that are particularly vulnerable to the adverse effects of climate change in meeting the costs of concrete adaptation projects and programmes in order to implement climate-resilient measures. Impact: Increased resiliency at the community, national, and regional levels to climate variability and change.
Important: Please read the following Results Framework and Baseline Guidance (also posted on the Adaptation Fund website) before entering your data
Link: http://www.adaptation-fund.org/sites/default/files/Results%20Framework%20and%20Baseline%20Guidance%20final.pdf
Please select the relevant Fund level Outcome and Output indicators that align with the project objectives and outcomes
OBJECTIVE 1
Fund Outcome | Please select from dropdown menu below | Fund Outcome Indicator | Please select from dropdown menu below | Target at CEO Endorsement (see Units in next sheet) | Baseline (see Units in next sheet) | Mid-term Results | Terminal Results
Outcome 1: Reduced exposure at national level to climate-related hazards and threats Outcome 2: Strengthened institutional capacity to reduce risks associated with climate-induced socioeconomic and environmental losses Outcome 3: Strengthened awareness and ownership of adaptation and climate risk reduction processes at local level Outcome 4: Increased adaptive capacity within relevant development and natural resource sectors Outcome 5: Increased ecosystem resilience in response to climate change and variability-induced stress Outcome 6: Diversified and strengthened livelihoods and sources of income for vulnerable people in targeted areas Outcome 7: Improved policies and regulations that promote and enforce resilience measures | 6 | 1. Relevant threat and hazard information generated and disseminated to stakeholders on a timely basis 2.1. No. and type of targeted institutions with increased capacity to minimize exposure to climate variability risks 2.2. Number of people with reduced risk to extreme weather events 3.1. Percentage of targeted population aware of predicted adverse impacts of climate change, and of appropriate responses 3.2. Modification in behavior of targeted population 4.1. Development sectors' services responsive to evolving needs from changing and variable climate 4.2. Physical infrastructure improved to withstand climate change and variability-induced stress 5. Ecosystem services and natural assets maintained or improved under climate change and variability-induced stress 6.1. Percentage of households and communities having more secure (increased) access to livelihood assets 6.2. Percentage of targeted population with sustained climate-resilient livelihoods 7. Climate change priorities are integrated into national development strategy | 6.1 | 90% of communities in each micro-watershed have access to communal irrigation systems. | To date, communities in Villanueva, El Sauce and Achuapa municipalities lack access to irrigation systems.
Fund Output | Please select from dropdown menu below | Fund Output Indicator | Please select from dropdown menu below | Target at CEO Endorsement (see Units in next sheet) | Baseline (see Units in next sheet) | Mid-term Results | Terminal Results
Output 1: Risk and vulnerability assessments conducted and updated at a national level Output 2.1: Strengthened capacity of national and regional centres and networks to respond rapidly to extreme weather events Output 2.2: Targeted population groups covered by adequate risk reduction systems Output 3: Targeted population groups participating in adaptation and risk reduction awareness activities Output 4: Vulnerable physical, natural, and social assets strengthened in response to climate change impacts, including variability Output 5: Vulnerable physical, natural, and social assets strengthened in response to climate change impacts, including variability Output 6: Targeted individual and community livelihood strategies strengthened in relation to climate change impacts, including variability Output 7: Improved integration of climate-resilience strategies into country development plans |  | 1.1. No. and type of projects that conduct and update risk and vulnerability assessments 1.2. Development of early warning systems 2.1.1. No. of staff trained to respond to, and mitigate impacts of, climate-related events 2.1.2. Capacity of staff to respond to, and mitigate impacts of, climate-related events from targeted institutions increased 2.2.1. Percentage of population covered by adequate risk-reduction systems 2.2.2. No. of people affected by climate variability 3.1 No. and type of risk reduction actions or strategies introduced at local level 3.2 No. of news outlets in the local press and media that have covered the topic 4.1. No. and type of health or social infrastructure developed or modified to respond to new conditions resulting from climate variability and change (by type) 4. 2. No. of physical assets strengthened or constructed to withstand conditions resulting from climate variability and change (by asset types) 5. No. and type of natural resource assets created, maintained or improved to withstand conditions resulting from climate variability and change (by type of assets) 6.1. No. and type of adaptation assets (physical as well as knowledge) created in support of individualor community-livelihood strategies 6.2. Type of income sources for households generated under climate change scenario 7.1. No., type, and sector of policies introduced or adjusted to address climate change risks 7.2. No. or targeted development strategies with incorporated climate change priorities enforced
OBJECTIVE 2
Fund Outcome | Please select from dropdown menu below | Fund Outcome Indicator | Please select from dropdown menu below | Target at CEO Endorsement | Baseline | Mid-term Results | Terminal Results
Outcome 1: Reduced exposure at national level to climate-related hazards and threats Outcome 2: Strengthened institutional capacity to reduce risks associated with climate-induced socioeconomic and environmental losses Outcome 3: Strengthened awareness and ownership of adaptation and climate risk reduction processes at local level Outcome 4: Increased adaptive capacity within relevant development and natural resource sectors Outcome 5: Increased ecosystem resilience in response to climate change and variability-induced stress Outcome 6: Diversified and strengthened livelihoods and sources of income for vulnerable people in targeted areas Outcome 7: Improved policies and regulations that promote and enforce resilience measures | 6 | 1. Relevant threat and hazard information generated and disseminated to stakeholders on a timely basis 2.1. No. and type of targeted institutions with increased capacity to minimize exposure to climate variability risks 2.2. Number of people with reduced risk to extreme weather events 3.1. Percentage of targeted population aware of predicted adverse impacts of climate change, and of appropriate responses 3.2. Modification in behavior of targeted population 4.1. Development sectors' services responsive to evolving needs from changing and variable climate 4.2. Physical infrastructure improved to withstand climate change and variability-induced stress 5. Ecosystem services and natural assets maintained or improved under climate change and variability-induced stress 6.1. Percentage of households and communities having more secure (increased) access to livelihood assets 6.2. Percentage of targeted population with sustained climate-resilient livelihoods 7. Climate change priorities are integrated into national development strategy | 6.1 | 80% of farm families in each micro-watershed implementing agro-ecological farm transformation plans. | Few family farms (5%) in targeted municipalities are implementing silvopastoral systems.
Fund Output | Please select from dropdown menu below | Fund Output Indicator | Please select from dropdown menu below | Target at CEO Endorsement | Baseline | Mid-term Results | Terminal Results
Output 1: Risk and vulnerability assessments conducted and updated at a national level Output 2.1: Strengthened capacity of national and regional centres and networks to respond rapidly to extreme weather events Output 2.2: Targeted population groups covered by adequate risk reduction systems Output 3: Targeted population groups participating in adaptation and risk reduction awareness activities Output 4: Vulnerable physical, natural, and social assets strengthened in response to climate change impacts, including variability Output 5: Vulnerable physical, natural, and social assets strengthened in response to climate change impacts, including variability Output 6: Targeted individual and community livelihood strategies strengthened in relation to climate change impacts, including variability Output 7: Improved integration of climate-resilience strategies into country development plans | 7 | 1.1. No. and type of projects that conduct and update risk and vulnerability assessments 1.2. Development of early warning systems 2.1.1. No. of staff trained to respond to, and mitigate impacts of, climate-related events 2.1.2. Capacity of staff to respond to, and mitigate impacts of, climate-related events from targeted institutions increased 2.2.1. Percentage of population covered by adequate risk-reduction systems 2.2.2. No. of people affected by climate variability 3.1 No. and type of risk reduction actions or strategies introduced at local level 3.2 No. of news outlets in the local press and media that have covered the topic 4.1. No. and type of health or social infrastructure developed or modified to respond to new conditions resulting from climate variability and change (by type) 4. 2. No. of physical assets strengthened or constructed to withstand conditions resulting from climate variability and change (by asset types) 5. No. and type of natural resource assets created, maintained or improved to withstand conditions resulting from climate variability and change (by type of assets) 6.1. No. and type of adaptation assets (physical as well as knowledge) created in support of individualor community-livelihood strategies 6.2. Type of income sources for households generated under climate change scenario 7.1. No., type, and sector of policies introduced or adjusted to address climate change risks 7.2. No. or targeted development strategies with incorporated climate change priorities enforced | 7.2 | 3 targeted municipalities have included climate change adaptation measures under their development plans. | In Nicaragua, municipalities are not integrating climate change adaptation under their development plans. (Zero Municipalities)
OBJECTIVE 3
Fund Outcome | Please select from dropdown menu below | Fund Outcome Indicator | Please select from dropdown menu below | Target at CEO Endorsement | Baseline | Mid-term Results | Terminal Results
Outcome 1: Reduced exposure at national level to climate-related hazards and threats Outcome 2: Strengthened institutional capacity to reduce risks associated with climate-induced socioeconomic and environmental losses Outcome 3: Strengthened awareness and ownership of adaptation and climate risk reduction processes at local level Outcome 4: Increased adaptive capacity within relevant development and natural resource sectors Outcome 5: Increased ecosystem resilience in response to climate change and variability-induced stress Outcome 6: Diversified and strengthened livelihoods and sources of income for vulnerable people in targeted areas Outcome 7: Improved policies and regulations that promote and enforce resilience measures | 1 | 1. Relevant threat and hazard information generated and disseminated to stakeholders on a timely basis 2.1. No. and type of targeted institutions with increased capacity to minimize exposure to climate variability risks 2.2. Number of people with reduced risk to extreme weather events 3.1. Percentage of targeted population aware of predicted adverse impacts of climate change, and of appropriate responses 3.2. Modification in behavior of targeted population 4.1. Development sectors' services responsive to evolving needs from changing and variable climate 4.2. Physical infrastructure improved to withstand climate change and variability-induced stress 5. Ecosystem services and natural assets maintained or improved under climate change and variability-induced stress 6.1. Percentage of households and communities having more secure (increased) access to livelihood assets 6.2. Percentage of targeted population with sustained climate-resilient livelihoods 7. Climate change priorities are integrated into national development strategy | 1 | 8 electronic information posts installed in each targeted micro-watershed to provide geo-referenced information | Targeted micro-watershed lack infrastructure to record and disseminate climate-related data.
Fund Output | Please select from dropdown menu below | Fund Output Indicator | Please select from dropdown menu below | Target at CEO Endorsement | Baseline | Mid-term Results | Terminal Results
Output 1: Risk and vulnerability assessments conducted and updated at a national level Output 2.1: Strengthened capacity of national and regional centres and networks to respond rapidly to extreme weather events Output 2.2: Targeted population groups covered by adequate risk reduction systems Output 3: Targeted population groups participating in adaptation and risk reduction awareness activities Output 4: Vulnerable physical, natural, and social assets strengthened in response to climate change impacts, including variability Output 5: Vulnerable physical, natural, and social assets strengthened in response to climate change impacts, including variability Output 6: Targeted individual and community livelihood strategies strengthened in relation to climate change impacts, including variability Output 7: Improved integration of climate-resilience strategies into country development plans |  | 1.1. No. and type of projects that conduct and update risk and vulnerability assessments 1.2. Development of early warning systems 2.1.1. No. of staff trained to respond to, and mitigate impacts of, climate-related events 2.1.2. Capacity of staff to respond to, and mitigate impacts of, climate-related events from targeted institutions increased 2.2.1. Percentage of population covered by adequate risk-reduction systems 2.2.2. No. of people affected by climate variability 3.1 No. and type of risk reduction actions or strategies introduced at local level 3.2 No. of news outlets in the local press and media that have covered the topic 4.1. No. and type of health or social infrastructure developed or modified to respond to new conditions resulting from climate variability and change (by type) 4. 2. No. of physical assets strengthened or constructed to withstand conditions resulting from climate variability and change (by asset types) 5. No. and type of natural resource assets created, maintained or improved to withstand conditions resulting from climate variability and change (by type of assets) 6.1. No. and type of adaptation assets (physical as well as knowledge) created in support of individualor community-livelihood strategies 6.2. Type of income sources for households generated under climate change scenario 7.1. No., type, and sector of policies introduced or adjusted to address climate change risks 7.2. No. or targeted development strategies with incorporated climate change priorities enforced
OBJECTIVE 4
Fund Outcome | Please select from dropdown menu below | Fund Outcome Indicator | Please select from dropdown menu below | Target at CEO Endorsement | Baseline | Mid-term Results | Terminal Results
Outcome 1: Reduced exposure at national level to climate-related hazards and threats Outcome 2: Strengthened institutional capacity to reduce risks associated with climate-induced socioeconomic and environmental losses Outcome 3: Strengthened awareness and ownership of adaptation and climate risk reduction processes at local level Outcome 4: Increased adaptive capacity within relevant development and natural resource sectors Outcome 5: Increased ecosystem resilience in response to climate change and variability-induced stress Outcome 6: Diversified and strengthened livelihoods and sources of income for vulnerable people in targeted areas Outcome 7: Improved policies and regulations that promote and enforce resilience measures |  | 1. Relevant threat and hazard information generated and disseminated to stakeholders on a timely basis 2.1. No. and type of targeted institutions with increased capacity to minimize exposure to climate variability risks 2.2. Number of people with reduced risk to extreme weather events 3.1. Percentage of targeted population aware of predicted adverse impacts of climate change, and of appropriate responses 3.2. Modification in behavior of targeted population 4.1. Development sectors' services responsive to evolving needs from changing and variable climate 4.2. Physical infrastructure improved to withstand climate change and variability-induced stress 5. Ecosystem services and natural assets maintained or improved under climate change and variability-induced stress 6.1. Percentage of households and communities having more secure (increased) access to livelihood assets 6.2. Percentage of targeted population with sustained climate-resilient livelihoods 7. Climate change priorities are integrated into national development strategy
Fund Output | Please select from dropdown menu below | Fund Output Indicator | Please select from dropdown menu below | Target at CEO Endorsement | Baseline | Mid-term Results | Terminal Results
Output 1: Risk and vulnerability assessments conducted and updated at a national level Output 2.1: Strengthened capacity of national and regional centres and networks to respond rapidly to extreme weather events Output 2.2: Targeted population groups covered by adequate risk reduction systems Output 3: Targeted population groups participating in adaptation and risk reduction awareness activities Output 4: Vulnerable physical, natural, and social assets strengthened in response to climate change impacts, including variability Output 5: Vulnerable physical, natural, and social assets strengthened in response to climate change impacts, including variability Output 6: Targeted individual and community livelihood strategies strengthened in relation to climate change impacts, including variability Output 7: Improved integration of climate-resilience strategies into country development plans |  | 1.1. No. and type of projects that conduct and update risk and vulnerability assessments 1.2. Development of early warning systems 2.1.1. No. of staff trained to respond to, and mitigate impacts of, climate-related events 2.1.2. Capacity of staff to respond to, and mitigate impacts of, climate-related events from targeted institutions increased 2.2.1. Percentage of population covered by adequate risk-reduction systems 2.2.2. No. of people affected by climate variability 3.1 No. and type of risk reduction actions or strategies introduced at local level 3.2 No. of news outlets in the local press and media that have covered the topic 4.1. No. and type of health or social infrastructure developed or modified to respond to new conditions resulting from climate variability and change (by type) 4. 2. No. of physical assets strengthened or constructed to withstand conditions resulting from climate variability and change (by asset types) 5. No. and type of natural resource assets created, maintained or improved to withstand conditions resulting from climate variability and change (by type of assets) 6.1. No. and type of adaptation assets (physical as well as knowledge) created in support of individualor community-livelihood strategies 6.2. Type of income sources for households generated under climate change scenario 7.1. No., type, and sector of policies introduced or adjusted to address climate change risks 7.2. No. or targeted development strategies with incorporated climate change priorities enforced

## Units for Indicators
Fund Outcome Indicator Units
1. Generation of relevant data, Stakeholders, and Timeliness 2.1. Include both qualitative and quantitative measures of capacity level within targeted institutions 2.2. Number (men and women and other vulnerable groups) 3.1. Use scale from 1 to 5: 5: Fully aware 4: Mostly aware 3: Partially aware 2: Partially not aware 1: Aware of neither predicted adverse impacts of climate change nor of appropriate responses 3.2. Use scale from 1 to 5: 5: All 4: Almost all 3: Half 2: Some 1: None 4.1. Summarize in an overall scale (1-5): 5: Highly responsive (All defined elements ) 4: Mostly responsive (Most defined elements) 3: Moderately responsive (Some defined elements) 2: Partially responsive (Lacks most elements) 1: Non responsive (Lacks all elements ) 4.2. Summarize in an overall scale (1-5): 5: Fully improved 4: Mostly Improved 3: Moderately improved 2: Somewhat improved 1: Not improved 5. Depends on the targeted natural asset: Biological (species): measure through changes in population numbers (dynamics, structure, etc.) Land: measure changes in hectares. Baseline data will be necessary to estimate the change. Supporting indicators baseline and target (as well as contextual information) are needed such as the following: Farmers adopting recommended technologies, Ha. of land improved, Average deforestation rate Etc. Use scale from 1 to 5. 5: Very effective (All elements are present) 4: Effective (Most elements are present) 3: Moderately effective (Some elements are present) 2: Partially effective (Most elements are not present) 1: Ineffective (No elements are present) 6.1. Summarize in an overall scale (1-5): 5: Very high improvement 4: High improvement 3: Moderate improvement 2: Limited improvement 1: No improvement 6.2. Household income by source of livelihood in project area (USD) prior and post project intervention 7. Summarize in an overall scale (1-5). 5: All (Fully integrated) 4: Most 3: Some 2: Most not integrated 1: None
Fund Output Indicator Units
1.1. Number, sector(s) and level(s) of projects or interventions in separate fields of monitoring plan 1.2. Number 2.1.1. Number of staff (male/female) of targeted institutions: a. Obtain baseline information: total number of staff from targeted institutions b. Define target 2.1.2. Number of staff (male/female) of targeted institutions: a. Obtain baseline information: total number of staff from targeted institutions b. Define target: needs to be defined by project proponents 2.2.1. Quantitative: Percentage (includes women – and other vulnerable groups – and men). Qualitative: Adequacy: include direct analysis of major areas; adequacy/effectiveness of systems or analysis of perceptions of populations and institutions. 2.2.2. Number (broken down by gender and, if possible, by vulnerable groups defined in the area of intervention) of people 3.1. Number and type (in separate columns) at local level. 3.2. Number 4.1. Number and type 4. 2. Number and type (entered in separate columns) 5. Number of interventions by type of natural asset and intervention 6.1. Number and type (in separate columns of monitoring plan) 6.2. Income sources per household; description of income source and number of households. 7.1. Number/Sector 7.2. Number; Effectiveness (see previous indicator) through enforcement level.