## Overview
Project Performance Report (PPR)
| Period of Report (Dates) | 30 June 2013 to 30 June 2014 (data only up to 30 April 2014)
| Project Title: | Increasing climate resilience through an Integrated Water Resource Management Programme in HA. Ihavandhoo, ADh. Mahibadhoo and GDh. Gadhdhoo Island
| Project Summary: | The primary problem addressed by this project is a significant, climate change-induced decline of freshwater security that is affecting vulnerable communities in Maldives. As surface freshwater is generally lacking throughout the country, the key problems pertaining to long-term freshwater security relate to the management of increasingly variable rainwater resources and increasingly saline and polluted groundwater. The proposed project will demonstrate climate-smart freshwater management in the Maldivian context and establish integrated and resilient water supply systems on the densely populated islands of HA. Ihavandhoo, ADh. Mahibadhoo and GDh. Gadhdhoo, with a view on country-wide replication and up scaling. The project will increase total freshwater storage capacity on all target islands to buffer the effects of less reliable rainfall and freshwater shortages during longer dry periods, and improve the quality of harvested rainwater through adjustments in rainwater collection, filtration and storage. The robustness and connectivity of communal rainwater storage schemes will be strengthened, and additional production capacity for desalinated freshwater will be installed to provide backup capacity in times of water stress. Artificial groundwater recharge will be enhanced to improve the quality and quantity of water stored in the natural aquifer, and contamination of household effluents will be reduced to prevent damages to the sensitive reef ecosystem. In their integration, these elements provide a compound solution to a number of critical climate and non-climate-related problems and a suitable model for replication on other islands with similar vulnerabilities. Experiences from this project will be used to inform capacity development of public and private sector stakeholders at national, provincial, atoll and island level.
|  |  |  | GEF Focal Area: | GEF 4 Focal Areas | GEF 2 / 3 Operational Programme: | Overall Rating of the project in the evaluation by the project evaluator: | GEF-4 Focal Area Strategic Program: | GEF-3 Focal Area Strategic Program:
| Database Number: | PIMS 4582 | Yes | Biodiversity | 1 | 1 | U | BD-SP1-PA Financing | 1: Arid & semi-arid ecosystems
Implementing Entity (IE) [name]: |  | UNDP Maldives | No | Climate Change Adaptation | 2 | 2 | S | BD-SP2-Marine PA | 2: Coastal, marine & freshwater ecosystems
| Type of IE: | Multilateral Implementing Entity |  | Climate Change Mitigation | 3 | 3 | MU | BD-SP3-PA Networks | 3: Forest ecosystems
| Country(ies): | Maldives |  | International Waters | 5 | 5 | Good | BD-SP5-Markets | 13: Conservation and Sustainable Use of Biological Diversity Important to Agriculture
Relevant Geographic Points (i.e. cities, villages, bodies of water): |  | HA. Ihavandhoo, ADh. Mahibadhoo and GDh. Gadhdhoo Island |  | Multiple Focal Area |  |  |  | BD-SP7-Invasive Alien Species(IAS) | 6: Promoting the adoption of renewable energy by removing barriers and reducing implementation costs
[6 empty] | CC-SP2- Industrial EE | 8: Waterbody based operational program
| Project Milestones |  |  |  |  | CC-SP3-RE,CC-SP4-Biomass | 9: Integrated Land and Water multiple focal area
| Milestone | [6 empty] | CC-SP5-Transport | 10: Contaminants based operational program
AFB Approval Date: |  | June 22, 2011
IE-AFB Agreement Signature Date: |  | November 3, 2011 |  |  |  |  | CC-SP6-LULUCF | 12: Integrated Ecosystem Management
Start of Project/Programme: |  | December 15, 2011 |  |  |  |  | Cross cutting capacity building | 14: Persistent Organic Pollutants
Mid-term Review Date (if planned):
Terminal Evaluation Date:
List documents/ reports/ brochures / articles that have been prepared about the project.
Inception Report Press Release for Project Initiation Seminar for Stakeholders Annual Work plan 2012 Quarterly Reports for Q1-4 2012, Q1-4 2313, Q1 2014 Funding Authorization and Certificate of Expenditure Q3-4 2012 Reports Project Board meeting minutes Initial Assessments and Engineering Reports Concept Design Report Detailed Design Report Annual Work Plan 2013 Procurement Plan 2013 / UNOPS Environment Impact Assessment Reports Willingness to Pay Survey for 3 project islands, Report Willingness to Pay Survey basic training on tools used Awareness Strategy Press Release for Project Initiation at Island levels with high-level monitoring visits One day Seminar on Integrated Water Resource Management Presentations Project Board meeting minutes 22 September and 24 December 2013. Mid-term review report
List the Website address (URL) of project.
http://www.environment.gov.mv http://www.unops.org http://www.undp-alm.org/projects/af-maldives http://www.mv.undp.org/
Project contacts:
National Project Manager/Coordinator
| Name: | Najfa Shaheem Razee
| Email: | najfa.razee@environment.gov.mv
Date:
Government DA
| Name: | Shaheeda Adam Ibrahim
| Email: | shaheeda.adam@environment.gov.mv
Date:
Implementing Entity
| Name: | Mohamed Inaz
| Email: | mohamed.inaz@undp.org
Date:
Executing Agency
Name:
Email:
Date:
Executing Agency
Name:
Email:
Date:
Executing Agency
Name:
Email:
Date:

## FinancialData
Financial information: cumulative from project start to 30 Apr 2014
DISBURSEMENT OF AF GRANT FUNDS
How much of the total AF grant as noted in Project Document plus any project preparation grant has been spent to date?
Estimated cumulative total disbursement as of 30th April 2015 | 1817789
Add any comments on AF Grant Funds. (word limit=200) | Outcome 1 - 7.3 million total The Annual Workplan signed in April 2012 was USD 4.6 million. Revised in July 2012 down to USD 0.6 million. Delays were a result of following factors: (i) Challenges in finding space and location for such large pieces of infrastructure on such small islands (e.g. multiple discussions with community representatives on relocation of facilities from originally expected sites); (ii) Multiple changes requested to the technical design by local stakeholders and by government stakeholders (e.g. extensive discussion about collection of rainwater from only community buildings, from households, groundwater recharge pits, etc.), including Environmental and Social Implact Assessment; (iii) Some significantly erroneous assumptions in the project design phase about the technical aspects of the project (e.g. that groundwater recharge pit examples from Malé could be replicated; the size of the rainwater collection and storage tanks feasible to be constructed on the islands); (iv) Turnover in both government and UNOPS staff; and (v) poor technical capacity of experts and engineers. The detailed design phase of the project was completed in March 2013, with final sign-off of the detailed design by the MEE and EPA. The Annual Workplan 2013 was agreed at USD 6,206,362. This target was adjusted downward 4 times during the year, starting from 58% reduction in June, 77% reduction in September and 83% reduction by November 2013. Delays were due to lack of standard practices in preparation of the bill of quantities missing out important preliminaries such as planning and costing for site clearance (e.g.. removal of coconut trees and existing structures), delays were cause due to site relocation as a result of lack of planning and stakeholder consultation. Delays also were caused by prolonged procurement process and contracting of major components. The reverse osmosis plant contract took 7 months from advertisement to contract award. Annual Workplan for 2014 was approved 24 December 2013 and signed on 19.01.2014. Procurement process for solar panels, pipe laying contracts was not initiated till end of February (27.02.2014). Evaluation and approval of the RO plant bids received in September 2013 delayed until 20 March 2014. Contract for RO plant was only signed on 20 April 2014. Initial issues related to MoU with UNOPS and perceptions about transparency and accountability have all been raised, discussed and resolved through rounds of tripartide discussions and at a Project Board meeting on 22 September, 2013 where the revised PID was approved. The current asymetry in expenditure under the components, compared to PMU relates to prolonged works on design and preparations. Such ration is expected to considerably reverse towards fourth quarter of 2014 when all awareded contracts and actual construction will commence.
EXPENDITURE DATA
List ouput and corresponding amount spent for the current reporting period | ITEM / ACTIVITY / ACTION | AMOUNT
| 1.1 Artificial groundwater recharge systems established to protect groundwater resources from salinization and improve aquifer yields in dry seasons | 13369
| 1.2 Rainwater harvesting schemes redesigned, interconnected and structurally improved to buffer climatic extremes and ensure equal water supply for all households during dry periods | 349856.24
| 1.3 Production and distribution system for desalinated water supply established | 661946.01
| 1.4. Existing wastewater management systems redesigned and improved to ensure sufficient quantities of safe groundwater during dry periods | 6903.72
| UNOPS Project Management Unit cost | 162462.15
| 2.1 Community consultations on each target island ensure participative design, sustainability and continued maintenance of integrated water resource management schemes | 31832.77
| 2.2 Targeted training events conducted in each region to strengthen water user participation and skills in adaptive, integrated water resource management | 0
| 3.1Training of technicians in the design, operation and management of Integrated Water Resource Management systems | 0
| 3.2 Institutional mechanisms created to integrate adaptive management of freshwater resources into the design and rollout of new water management projects and schemes | 0
| 3.3 Action plan developed and financing mobilized to replicate integrated, climate-resilient freshwater management on at least 4 additional islands | 0
| OUTCOME 4: M&E | 13903.18
| OUTCOME 5: PMU | 88187.76
| TOTAL | 1328460.83
PLANNED EXPENDITURE SCHEDULE
List outputs planned and corresponding projected cost for the upcoming reporting period | ITEM / ACTIVITY / ACTION | PROJECTED COST | Est. Completion Date
| 1.1 Artificial groundwater recharge systems established to protect groundwater resources from salinization and improve aquifer yields in dry seasons | 121506.72 | 2014-09-01
| 1.2 Rainwater harvesting schemes redesigned, interconnected and structurally improved to buffer climatic extremes and ensure equal water supply for all households during dry periods | 815878.71 | 2014-09-01
| 1.3 Production and distribution system for desalinated water supply established | 4037009.62 | 2014-09-01
| 1.4. Existing wastewater management systems redesigned and improved to ensure sufficient quantities of safe groundwater during dry periods | 87819.97 | 2014-09-01
| UNOPS Project Management Unit cost | 383835.25 | 2014-09-01
| OUTCOME 2: Strengthened local awareness and ownership of integrated climate resilient freshwater management systems | 76500 | 2014-12-01
| outcome 3: Improved institutional Capacity to promote and enforce climate reslient freshwater management on all inhabited islands | 30000 | 2014-12-01
| Monitoring and Evaluation | 45000 | 2014-12-01
| Outcome 5: Project Management Ministry of Environment & Energy | 101000 | 2014-12-01
| TOTAL | 5698550.27
ACTUAL CO-FINANCING (If the MTR or TE have not been undertaken this reporting period, DO NOT report on actual co-financing.)
How much of the total co-financing as committed in the Project Document has actually been realized?
Estimated cumulative actual co-financing as verified during Mid-term Review (MTR) or Terminal Evaluation (TE).
Add any comments on actual co-financing in particular any issues related to the realization of in-kind, grant, credits, loans, equity, non-grant instruments and other types of co-financing. (word limit=200)

## Risk Assesment
RISK ASSESMENT
IDENTIFIED RISKS
List all Risks identified in project preparation phase and what steps are being taken to mitigate them
Identified Risk | Current Status | Steps Taken to Mitigate Risk
Effective engagement and consensus building by different water users, public and private stakeholders to agree on an integrated approach to freshwater and wastewater management | Low | Community level stakeholders such as the Island Council and general public, regional stakeholder - Atoll Council and Utility company's for water and electricity are engaged systematically. Engagement was undertaken during surveys, consultation seminars, workshops and meetings.
Human resources capacity issues (e.g. staff turnover) in different government offices preclude effective engagement of particular stakeholders in the project | Medium | Engage as many personnel from relevant departments, especially technical personnel. Turnover at that level is lower and will ensure continuity.
Extreme weather events during project implementation may damage construction works; | Medium | Planned to give attention to weather predictions in the construction plan
Delays in recruitment of qualified project staff may affect the timeframe and quality of various project activities. | Low | Regional and international recruitment were done to fill in the gap in required qualification.
Community acceptance of technical design options proposed by project | Medium | Survey "willingness to pay" and ongoing development of awareness tools will help addressthe risk
Construction material shortage | High | Communicate and co-ordination of the selected contractors and suppliers. Resources have been arranged from different countries.
Ihavandhoo Island Tree Clearance | Mitigated with some delay to construction. | The tree clearance is already completed by the intervention of island council
Low Island Staff recruitment response | Mitigated | Island staff recruitment process were completed. Island staff were selected though competitive in interview process with involvement of MEE and Feneka
Critical Risks Affecting Progress (Not identified at project design)
Identify Risks with a 50% or > likelihood of affecting progress of project
Identified Risk | Current Status | Steps Taken to Mitigate Risk
Ad-hoc issues arising due to poor planning by UNOPS (responsible party) that result in changes to and/or additional costs due to amendment of existing contracts. | Medium | MEE requested UNOPS (responsible party) to obtain endorsement on any amendments to designs and subsequently to existing contracts to ensure that the project remains within budget to minimize the risk of falling short of funds to implement the project in accordance with the approved and agreed design.
Contractors set with unrealistic schedules | Medium | Closely monitor progress
Delays adding up and pushing up costs for execution and operation | High | Closely monitor contracts and manage scheduling of works to avoid delays to the overall project agreed timeline.
Human remains found at the location where the rainwater storage tank is to be constructed in the island of Gadhdhoo may affect the work progress schedule on the contract for costruction of 3 rainwater harvesting tanks in the island. | Medium | Discuss with the Island Council on alternative means of transferring the human remains to the cemetary that is accepted. Explain to the Island Council that changing site location at this stage will result in re-designing additional costs which the Project will not be able to sustain and that reduced capacity of rainwater storage on the island would result in higher costs of production of water leading to higher prices.
Challenges in supply of pipe materials and customs clearance has caused delay in overall work progress | Medium | Avoid miscommunication with supplier to ensure that the supply is brought with UNDP as consignee. Since UNOPS does not have a license to import. Provide support to the suppliers in to clear material from customs. Apply charges to suppliers as per contract for delayed supply.
The project may not be able to demonstrate quantifiably improvements to; groundwater quality the only source of water during the dry season and drinking water quality. | Medium | A monitoring plan for groundwater quality, distribution water quality will need to be implemented for component 1 activities to assess progress on quantifiable indicators and suitability for replication
Delays in awarding of the contract for the reverse osmosis plant may affect the water tight test of the glass reinforced plastic (GRP) storage tanks. | Low | Negotiate with the GRP tank supplier. Consider alternate testing with harvested rainwater if available prior to the installation and commissioning of the reverse osmosis plant.
Risk Measures: Were there any risk mitigation measures employed during the current reporting period? If so, were risks reduced? If not, why were these risks not reduced?
Add any comments relevant to risk mitigation (word limit = 500)
Most of the risk mitigation actions given under "the Steps Taken to Mitigate Risk" were undertaken during period.

## Rating
RATING ON IMPLEMENTATION PROGRESS
For rating definitions please see bottom of page.
| Progress on Key Milestones |  | Expected Progress |  | Progress to Date | Rating
Project Manager/Coordinator: | A
| Objective: To ensure reliable and safe freshwater supply for Maldivian communities in a changing climate |  | 100% of populations in 3 project islands will have access to safe and affordable water |  | UNOPS (responsible party for component 1) completed preliminary field surveys in February 2012 and May 2012. Based on survey information, the distribution networks, location of the central water supply plant and estimates of rainwater harvesting were prepared along with a concept design. The concept design was presented at the inception workshops held in June 2012. The first draft of the detailed design for the system for each of the 3 islands was submitted by UNOPS(responsible party for component 1) to MEE in August 2012. Analysis of the data presented by UNOPS was carried out by MEE with the assistance of EPA (the regulatory authority). This process identified that the amount of rainwater that was collected when supplemented with desalinated water would only comprise of 3% of the final mix. This limitation was due to consideration of only public or community buildings in the catchment area in the design submitted by UNOPS. Discussions were carried between MEE and UNOPS to consider recommendation to increase the rainwater collection catchment areas and storage so that a significant proportion of the water delivered to households would comprise of rainwater. MEE also identified that the desalination plant capacity was too big since the aim of the project is to demonstrate optimal utilization of all water resources i.e. rainwater and desalinated water. The rational for including and increasing the use of treated rainwater as part of the mix of the water supply is to reduce the production costs and thereby cost-effectiveness of the completed system. EPA (the regulatory authority) encouraged the project to increase the composition of rainwater to at least 20-30% of the projected demand to justify the investments (collection network, rainwater storage tanks). Furthermore, EPA advised to reduce the capacities of the RO plants in the proposed designs prepared by UNOPS noting that by installing RO plants to cater to the full demands the incentives for the operators to utilize rainwater would be diminished. This directive was based on local knowledge and experience of the regulator. Noting that for an operator it was far easier to assure quality of water supplied in an entirely closed system with only desalinated water. EPA noted that the huge risk of provided full capacity RO plants as it increased the likelihood that the operator would cease utilization of rainwater and simply increase the tariff to supply desalinated water only. Which would result in loss of the project's objective to provide affordable water supply in the 3 islands. The design revisions were undertaken by UNOPS based on the EPAs and MEE's recommendations during the period October 2012 through March 2013. The designs were approved by EPA in March 2013. The procurement process was initiated in April 2013 for the major work packages which includes the civil works for the RO plant building and Rainwater Harvesting and Storage tanks. On all three islands the major construction activities such as the rainwater harvesting tanks, glass reinforced plastic tanks and the reverse osmosis plant building are more than 50 percent complete. Delays described in the justification below, have meant that critical components such as the reverse osmosis plant installation and pipe laying will not be completed during the reporting period. The project will not be able to deliver the complete system by July 2013 as agreed in the Project Board meeting held in December 2013. Two thirds of the supply of pipes have been delivered. Pipe laying implementation delayed by 2 months due to delayed procurement initiation. However, UNOPS (responsible party for outcome 1) anticipates that by September 2014, with the supply of the reverse osmosis plant by August, that the entire water system will be completed. FENAKA Corporation has been engaged since the start of the project with an agreement that staff recruited by the Project will be absorbed into their corporate structure. Staff training on operation and maintenance is planned for July/August 2014. The tariff structure produced by the Project through the Willingness to Pay Survey was shared with FENAKA for review of their Board and they are expected to initiate the approval process from EPA within May 2014. | MU
Component 1 Ground water aquifer protected and freshwater supply ensured in HA. Ihavandhoo, ADh. Mahibadhoo and GDh. Gadhdhoo to provide reliable, equitable and cost-effective access to safe freshwater in a changing climate
| Artificial groundwater recharge systems established to protect groundwater resources from salinization and improve aquifer yields in dry seasons. |  | Detailed design. |  | Design proposed but not verified if effective. This was confirmed by the Environmental Impact Assessment (EIA) undertaken as part of the regulatory requirements to implement the project. Further hydrogeological study is required to understand the unique aquifer of the project islands, soil permeability and horizontal movement of water in the aquifer for optimal location and design to be used. The EIA has suggested the use of skimming wells as an alternative approach to reduce the drawn down effect caused by traditional wells in households. Feasibility will need to be assessed with a study of the actual capacity and use of the current aquifer. A desk review was undertaken through UNOPS (responsible party for Outcome 1) partner Ove Arup. The follow up proposal was exceptionally high in cost. MEE initiated discussions with the International Water Management Institute. A preliminary site visit was carried out in February 2014. A proposal for managed aquifer recharge study and implementation has been submitted This proposal is being negotiated by UNOPS (responsible party) on time frame proposed and available budget. This activity will lag behind the installation of the water supply system. MEE will continue to work with UNOPS(responsible party)to ensure that the activity is implemented. It is important to note and promote that ground water is the primary resource of water available in an island in a changing climate. | MU
| Rainwater harvesting schemes redesigned, interconnected and structurally improved to buffer climatic extremes and ensure equal water supply for all households during dry periods. |  | Completed detail design, procurement completed and construction activities to have completed. |  | Design initially proposed utilized only the catchment area of public and community buildings and did not meet the targets of the project. Additional catchment area has been explored in the revised design which includes private households that discharge excess rainwater. The current design allows for future expansion of the system to integrate more households that are willing to contribute. Disinfection and safeguards have been included at the central water supply plant for the rainwater to be treated prior to it being pumped into the distribution network. Inclusion of Ultraviolet treatment in addition to chlorination has been recommended by MEE and UNOPS (responsible party) is working on the procurement of this. Design process delayed taking over one year to complete primarily due to a lack of adherence by UNOPS (responsible party) to Government guidelines and regulations on Water Supply provisions as mandated by EPA (regulatory authority) and lack of technical capacity on climate resilience and IWRM. Designs proposed were reiterated over various discussions. Environment Impact Assessment was not undertaken until after finalizing the detail design. Design approved March 2013. Construction incomplete on all rainwater harvesting tanks due to delays faced in procurement, lack of proper assessment and costing of site clearing preliminaries in the contracts awarded and tank location resulting due to a lack of engaging all stakeholders by UNOPS (responsible party) during the design planning phase. MEE has questioned the appropriateness of the construction methodology used for the rainwater tanks as a masonry wall has been erected instead of a formwork. This means that the actual tank walls are hidden behind a masonry wall. Despite assurances by UNOPS (responsible party) of a water tight test to be carried out upon completion. The masonry wall poses a problem in terms of locating leaks in the future and costly investigative work since the wall will need to be demolished to reach the concrete which forms the sides of the tanks. The project is designed for a 35 year horizon and the sustainability of these tanks needs to be addressed by UNOPS (responsible party). | MU
| Production and distribution system for desalinated water supply established |  | Completed detail design, procurement completed and supply installation to be completed by July 31. |  | Plant capacity is too large paving the way for the operator to utilize only desalinated water. Design revision was undertaken and has been approved. Design process delayed taking over one year to complete primarily due to a lack of adherence by UNOPS (responsible party) to Government guidelines and regulations on Water Supply provisions as mandated by EPA (regulatory authority) and lack of technical capacity on climate resilience and IWRM. Designs proposed were reiterated over various discussions. Environment Impact Assessment was not undertaken until after finalizing the detail design. Designs revised for optimal storage of rainwater and optimal capacity of reverse osmosis plants. Procurement on the supply and installation of reverse osmosis plant delayed. Initial evaluation by UNOPS (responsible party) of bids for technical compliance was carried out by an civil engineer with no experience in operation and maintenance of reverse osmosis plants and 3 managers. MEE recommended that an expert be hired to evaluate the technical compliance. 4 months delay was faced thereafter in the approval process within UNOPS (responsible party). The system installation is scheduled for September 2014 which is a delay of 2 months to the agreed schedule at the December 2013 project board meeting endorsing the annual workplan for 2014. | MU
| Existing wastewater management systems redesigned and improved to ensure sufficient quantities of safe groundwater during dry periods. |  | Completed concept design, detail design and completion of procurement. |  | UNOPS (responsible party) is to undertake an assessment of the current projects in the pipeline and established system in Mahibadhoo island to prepare a plan that will integrate measures to reduce groundwater pollution. Negotiations are underway with the International Water Resource Management Institute and expected to be completed by May 2014. | U
Component 2 Strengthened local awareness and ownership of integrated, climate-resilient freshwater management systems
| Output 2.1: Community consultations on each target island ensure participative design, sustainability and continued maintenance of integrated water resource management schemes |  | Community consultations completed. Willingness to pay survey completed. |  | Consultations have taken place in May/June 2012. In addition a project initiation seminar was launched at high level with the participation of representatives from 2 of 3 islands and all 3 regions. The concept designs were shared with the community during field visits and during the aforementioned formal consultations. Willingness to Pay Survey has been completed for all 3 islands. A tariff structure proposed based on the survey results. Prior to depreciation and based on projected demand/population increase financial analysis of the proposed system assures breakeven operation of the system is possible with the tariff structure that people are willing to pay in the next 10 years. When depreciation is accounted for the system will be operating at a loss. The Ministry has conveyed to Fenaka (the Govt. Utility Corporation which will take over operation) the survey results and requested that they initiate approval of the tariff structure from the EPA (regulator). | S
| Output 2.2: Targeted training events conducted in each region to strengthen water user participation and skills in adaptive, integrated water resource management |  | Awareness strategy formulated. National awareness campaign on IWRM. Training of participants on IWRM. |  | An awareness strategy and campaign for national awareness and capacity building on IWRM has been completed. Delays in procurement due to lack of interest from local bidders and procurement processes have delayed the contract award for the national campaign launching by 8 months since the procurement process was initiated. The contract is expected to be awarded by the end of May 2014. A seminar on integrated water resource management was held in February 2014. Due travel difficulties participants from one of the target islands were not able to attend. Participants from two project islands as well as two additional islands where the Government is replicating the project joined in the seminar in addition to national stakeholders, non-governmental organizations, private companies and government utility companies as well as EPA (regulatory authority) and the MEE. | MU
Component 3: Training of technicians in the design, operation and management of Integrated Water Resource Management systems
| Output 3.1: Training of technicians in the design, operation and management of integrated water resource management systems |  | Training on RO plant operation and maintenance to be completed. |  | Regional utility companies have been dismantled since the change in Government in February 2012. The Project will now target the Government's utility corporation Fenaka for this training. The project is recruiting staff at island level for monitoring of project implementation and will train these staff. Once commissioned the staff will be absorbed by Fenaka. On site training to be carried out during the installation of the reverse osmosis plants. Once commissioned and handed over, the project will further strengthen the training of staff hired through the project utilizing local capacities such as the Male Water and Sewerage Company (40 years plus experience) for the training on operation and maintenance. The training has been delayed to the delay in contracting the supply and installation of the Reverse Osmosis plant. | MU
| Output 3.2: Institutional mechanisms created to integrate adaptive management of freshwater resources into the design and rollout of new water management projects and schemes |  | Not planned during reporting period. |  | Not planned for implementation in the current reporting period. Discussions have been held on developing a set of guidelines for the review of future projects inclusive of assessments such as willingness to pay.
| Output 3.3 Action plan developed and financing mobilized to replicate integrated, climate-resilient freshwater management on at least 4 additional islands |  | The government approves at least 4 new, fully financed freshwater and/or wastewater management projects on the basis of lessons learned and design principles replicated from the proposed project |  | All new water and projects are subject to technical reviews on the basis of IWRM and climate resilience principles similar to this project. 3 projects have been handed over to contractors and 13 more projects are being designed similar to this project. MEE has raised finance through the public sector investment (Government Budget) for the provision of safe water through an IWRM approach in 3 islands of Mulah, Dhiggaru and Maamigili serving a cumulative population of 3,709 (Census 2006, Statistical Yearbook of Maldives 2013). The 3 projects have been approved and handed over to the contractors. The work has started on all 3 islands. Government is planning to implement two donor funded projects in Hinnavaru and Thoddoo that follow a similar model to provide cost effective and safe water supply using the IWRM approach of this Project. MEE has raised funding through Government budget to design safe water supply systems using the low cost IWRM approach in 13 islands. The target is achieved as the Government has since project inception approved 6 projects on the basis of the lessons learnt during the design phase of this Project. | HS
[5 empty] | Overall Rating | MU
Please Provide the Name and Contact information of person(s) responsible for completing the Rating section
| Name: | Najfa Shaheem Razee
| Email: | najfa.razee@environment.gov.mv
Please justify your rating. Outline the positive and negative progress made by the project since it started. Provide specific recommendations for next steps. . (word limit=500)
Several delays were encountered during the reporting period which could have been avoided had standardized methods been followed during the preparation of bills of quantities(BOQ). These include the lack of inclusion into the bids the requirement to clear and dispose from the project sites coconut trees and the demolition of a shed. MEE recommended that UNOPS (responsible party) follow Standard Method of Measurement published by the Royal Institute of Chartered Surveyors or bring UNOPS global support to ensure that important items in the preliminaries of a BOQ were not missed. Site re-location on Ihavandhoo of all 3 rainwater tanks and design changes occurred due to lack of land on Mahibadhoo. MEE recommended that UNOPS (responsible party) identify stakeholders and provide full information such as conveying the actual size of the tank by comparison to existing structures. These actions should have been taken prior to initiating procurement to avoid delays and contract variations. Inaccurate cost estimates for Gadhdhoo island has been recurring and resulting in bids being 30 percent (laying of pipes) to 40 percent higher (Reverse Osmosis plant building) than engineers estimates. MEE has recommended UNOPS (responsible party) ensure that cost estimates are accurate and up to date prior to bidding. Delays were also encountered in the procurement of the reverse osmosis plant. The Ministry recommended that UNOPS hire a local expert to speed up the process since the bids had been evaluated by a team of 4 personnel comprising of one civil engineer - with no experience operation and maintenance of reverse osmosis plants, and three managers. Soon after which financial opening of the technically compliant bids were carried out. It still took an additional 4 months, in total 7 months, to reach contract award. To facilitate project progress the Ministry has worked closely with UNOPS (responsible party) to address the shortcomings identified above which has impacted the timeline for the completion of physical work. The project remains at risk of not fulfilling the objectives should further delays occur. The project management costs will be fully exhausted by the end of July for UNOPS (responsible party). The Government has informed UNOPS during two board meetings held in September 2013, and December 2013 that the Government will not be able to provide additional funds to for UNOPS (responsible party) project management through the project or from other sources. In addition, MEE will require the services of an engineer for the project to assess quality prior to project handover. However, the Project has been highlyl successful in advocating a integrated water supply system. The inception, design phase and willingness to pay survey conducted by this Project has contributed to the Government's policy of utilizing an IWRM approach to delivery a cost effective and safe water supply in all projects water supply projects. All projects are subjected to technical review on this basis. 1 project on Ukulhas island is ongoing. 3 projects have started on 3 seperate islands during this reporting period. Another two have been approved with donor finance. As concluded by the MTE " The project has faced slow-going in the initial two years of the project, but there has been significant progress in the past six months, and there are indications that the project could be considered successful by the anticipated time of completion, in late 2015. A number of benchmarks will have to be met however with regard to completion and operation of the water systems in the three islands, and the likely sustainability of the systems will have to be demonstrated. At the same time, the significant delays faced thus far mean that there must be zero tolerance for further slippage. In the second half of the project, activities must be completed as planned, and activities not yet started must commence immediately. With any further delays in core project results the project risks losing prospects for sustainability, and as such, risks failure. The project team and partners must take all possible measures to ensure the project remains on track from this point forward".
| Progress on Key Milestones |  | Expected Progress |  | Progress to Date | Rating
Implimenting Agency | 1. 1 Artificial groundwater recharge systems established to protect groundwater resources from salinization and improve aquifer yields in dry seasons. |  |  |  | After discussions held between MEE, UNOPS and UNDP officials it was decided that the groundwater recharge system proposed in the project document was not feasible for the three islands. Construction of recharge wells throughout the island was agreed as ineffective and inefficient ground water recharge systems unsuitable for the Maldivian islands for two main reasons: 1. The network connecting the recharge wells is likely to be clogged by silt similar to what happens in the drainage system in Male'. 2. Unavailability of land for construction of the wells. In the revised design, UNOPS proposed to install three ground water recharge pits that collect over flow from the rainwater storage tanks. This was approved with the larger design of the system proposed by UNOPS but UNOPS has been instructed to develop a more comprehensive groundwater recharge system that is based on a geo-hydrological study. Currently, the plan is to capacitate EPA to conduct the study and findings of this geo-hydrological study will be used by UNOPS to develop an enhanced ground water recharge system. MEE found the proposal for ground water recharge study through UNOPS too costly and during the reporting period, the Ministry has been in touch with a firm "Integrated Water Management Institute" (IWMI) to conduct this study. There has been an initial stakeholder meeting and a site visit. Based on this a proposal has been developed and submitted to the UNOPS which is now under negotiation. Considering that this activity was initially a considerable portion of the allocation, it has not moved repidly enough. While the rainwater harvesting and RO water generation components are underway, this need to have gone in parrallel. | U
| 1. 2 Rainwater harvesting schemes redesigned, interconnected and structurally improved to buffer climatic extremes and ensure equal water supply for all households during dry periods. |  |  |  | The initial design described in project document and submitted by UNOPS to MEE described harvesting of rainwater from all public buildings and connecting them to the main storage tank which stores the desalinated water. However, based on rainfall pattern of past 10 years, it was understood that the storage tank to be built at the public buildings would not get full with just water collected from the buildings. Also, to get cost savings from integration of rainwater with desalinated water, a higher ratio of rainwater is needed. In the project document it was proposed to redesign the rainwater harvesting systems in the households but all the stakeholders agreed that all past projects that focused on improving and encouraging rainwater harvesting at households have failed. Hence, based on these two points, the system was redesigned to collect rainwater from households in the vicinity of the storage tank at the public building. In concept, this ensured that enough rainwater is collected to fill the storage tanks in the public buildings and would give a higher rainwater ratio in the water that is piped to households. Currently, procurement of materials and civil works for implementing the design is underway. Civil works are underway since late 2013, after designs were approved in March 2013. There have been delays in implementation due to delays in in contractor procurement, delays in reaching agreements on placements of tanks, inadequate inspection and re-planning. | MU
| 1.3 Production and distribution system for desalinated water supply established |  |  |  | The distribution system and production capacity of the desalination plant had been designed by UNOPS and approved by MEE and EPA. It took a long time for approvals as there were lots of back and forth among MEE, EPA and the UNOPS designers. Procurement, although ongoing, has been delayed on different occations and the PMU/MEE has stepped up its role in monitoring the Responsible Party. It is expected that a 2 month delay (till Sept 2014) will occur against the 2014 workplan. | MU
| 1.4 Existing wastewater management systems redesigned and improved to ensure sufficient quantities of safe groundwater during dry periods. |  |  |  | An assessment of current projects in the pipeline and the established system in one target island (Mahibadhoo) on preparing a plan for integartion of measures to reduce groundwater pollution is under discussion with the Responsible Party and the MEE for the party in milestone 1.1, IWMI, to undertake. This is not complete although it was envisaged it would be done by end of May 2014. | U
| Output 2.1: Community consultations on each target island ensure participative design, sustainability and continued maintenance of integrated water resource management schemes |  |  |  | In June 2012, a team from MEE, UNOPS and UNDP visited the target islands and discussed the proposed water management system with more than 30 people from each community. The communities provided their input on using the public buildings for rainwater harvesting and their opinion on mixing rainwater with desalinated water. Their concerns about cleaning the roof of the public buildings and who is to be responsible for it were noted and shared with FENAKA (the state owned company who will manage the system). This was followed up by a willingness to pay survey in which 171 households from Ihavandhoo, 134 households from Mahibadhoo and 178 from Gadhdhoo were surveyed. 77 percent of respondents from Mahibadhoo and Ihavandhoo were female. , 73 percent from Gadhdhoo were female. The survey found out the willingness and affordability of the community to pay for water that will be supplied by the system. Using the findings of the survey a tariff system was designed for the islands and operational sustainability of the systems has been conceptually ensured. The tariff for Ihavandhoo and Gadhdhoo are same as Male. In other islands where desalination plants have been installed without integration of rainwater harvesting, the tariff is higher than Male. This proves high economical benefits of the current design for these two islands. During communication of these results from the MEE to Government utility company, Fenaka (the Govt. Utiliy Corporation which will take over operation,) MEE has requested that they intiate approval of the tariff structure from the EPA (regulator). Further consultations have taken place with the commity on infrastructure locations and on the designs of the water management setup. However, more engagement is needed with the communities to keep them constantly upbeat on the developments so that the sustainability of the system after the project can be ensured. | U
| Output 2.2: Targeted training events conducted in each region to strengthen water user participation and skills in adaptive, integrated water resource management |  |  |  | A survey was conducted in the target islands and other Maldivian islands to understand the level of awareness among the communities on good practices of water usage, water harvesting and management. 71 percent of the surveyed population was female. Based on the findings of this survey a communications strategy that focuses on informing the communities and changing their behavior has been formulated. An awareness strategy and campaign for national awareness and capacity building on IWRM has now been developed. There has been extreme delays in contracting out the awareness component which was due in end of Q3 / early Q4 in 2013. The PMU expects to have this taking off in Q2 of 2014. | U
| Output 3.1: Training of technicians in the design, operation and management of integrated water resource management systems |  |  |  | The project is targeting the utility company (Fenaka) staff for capacity building trainings. The trainings have been delayed as setup of the system, largely the RO plant, has been delayed. | MU
| Output 3.2: Institutional mechanisms created to integrate adaptive management of freshwater resources into the design and rollout of new water management projects and schemes |  |  |  | not planned for the reporting period. | S
| Output 3.3 Action plan developed and financing mobilized to replicate integrated, climate-resilient freshwater management on at least 4 additional islands |  |  |  | Government now considered IWRM in all other water management projects. An action plan has not been developed as in the milestone. However, based on recommendations of this project, government is now piloting a water management setup in a different island. | MU
[5 empty] | Overall Rating | MU
Please Provide the Name and Contact information of person(s) responsible for completing the Rating section
| Name: | Mohamed Inaz
| Email: | mohamed.inaz@undp.org
| Progress on Key Milestones |  | Expected Progress |  | Progress to Date | Rating
Other
Overall Rating
Please Provide the Name and Contact information of person(s) responsible for completing the Rating section
Name:
Email:
Please justify your rating and address the following points: 1. Indicate trends, both positive and negative, in achievement of outcomes as per the project indicators. 2. Detail critical risks that have affected progress. 3. Outline response to MTR undertaken this reporting period. 4. Outline action plan to address projects with a rating of HU, U or MU. Please keep your input to 1200 words
Rating Definitions
|  |  | Highly Satisfactory (HS) | Project actions/activities planned for current reporting period are progressing on track or exceeding expectations to achieve all major outcomes/outputs for given reporting period, without major shortcomings. The project can be presented as “good practice”.
|  |  | Satisfactory (S) | Project actions/activities planned for current reporting period are progressing on track to achieve most of its major outcomes/outputs with only minor shortcomings.
|  |  | Marginally Satisfactory (MS) | Project actions/activities planned for current reporting period are progressing on track to achieve most major relevant outcomes/outputs, but with either significant shortcomings or modest overall relevance.
|  |  | Marginally Unsatisfactory (MU) | Project actions/activities planned for current reporting period are not progressing on track to achieve major outcomes/outputs with major shortcomings or is expected to achieve only some of its major outcomes/outputs.
|  |  | Unsatisfactory (U) | Project actions/activities planned for current reporting period are not progressing on track to achieve most of its major outcomes/outputs.
|  |  | Highly Unsatisfactory (U) | Project actions/activities planned for current reporting period are not on track and shows that it is failing to achieve, and is not expected to achieve, any of its outcomes/outputs.

## Project Indicators
PROJECT Indicators
Please provide all indicators being tracked for the project as outlined in the project document
Type of Indicator (indicators towards Objectives, Outcomes, etc…)
Type of Indicator | Indicator | Baseline | Progress since inception | Target for Project End
Ground water aquifer protected and freshwater supply ensured in HA. Ihavandhoo, ADh. Mahibadhoo and GDh. Gadhdhoo to provide reliable, equitable and cost-effective access to safe freshwater in a changing climate | Number of people living on HA. Ihavandhoo, ADh. Mahibadhoo, and GDh. Gadhdhoo who have uninterrupted access to reliable and safe freshwater supply in extreme climatic conditions | 6701 people living on HA. Ihavandhoo, ADh. Mahibadhoo, and GDh. Gadhdhoo are not able to meet their freshwater needs in a highly variable and changing climate. Water needs are met through unreliable supply of rainwater, which is frequently contaminated through insufficiently protected collection and storage systems. Total freshwater collection and storage capacity on each island is insufficient to address water needs during the dry season. Groundwater is highly saline and polluted and unfit for domestic use. Backup desalination systems do not supply the minimum humanitarian water requirements during climatic extremes and disaster events. | Technical constraints resulted in a prolonged design period of 13 months since the signing of the project to reach an approved detail design. The detail design was approved at the end of March 2013. Procurement processes has been initiated in April 2013 by UNOPS (responsible party) for the delivery of the water supply plant, rainwater harvesting network, storage tanks and distribution networks. Construction of rainwater harvesting tanks, installation of glass reinforced plastic storage tanks and reverse osmosis plant building are above 50 percent complete on all three islands except for Gadhdhoo where one of three rainwater tank is delayed due to human remains unearthed during construction. | 100% of the population living on HA. Ihavandhoo, ADh. Mahibadhoo, and GDh. Gadhdhoo will have uninterrupted access to reliable and safe freshwater supply of at least 15 liters per person per day at all times, including during extreme climate events
| Groundwater quality on each target island | Perception with target population of all islands that due to salinity and pollution, groundwater is unfit for consumption and most household uses. No current data available on the quality of groundwater in target islands Existing groundwater recharge capacity: Ihavandhoo: 0 m3 Mahibadhoo: 0 m3. Gadhdhoo: 0 m3 | Past experience on the use of groundwater recharge pits in the Maldives have not been successful. These have quickly accumulated silt and become redundant as is seen in the capital island Male'. UNOPS (party responsible for outcome 1) contracted their global partner Ove Arup who carried out a desk study. The Project was not able to carry forward due to the high cost of the proposal. MEE initiated discussions with the International Water Management Institute (IWMI). Preliminary site visits were carried out to all three islands by IWMI and a proposal for assessing and implementing a suitable option for groundwater recharge has been presented and is being negotiated based on the budget constraints of the project. It is expected that the proposal will be finalized during May 2014. The proposal involves a managed aquifer recharge assessment and implementation of an suitable technology for recharge. | By the end of the project, the quality of groundwater in each target island has improved to levels that are safe for hygiene and agricultural purposes The outcomes and implementation scope will be depend on the proposal of MAR study
| Volume of rainwater collected and stored to supply safe and clean freshwater during dry periods | Existing rainwater harvesting capacity: Ihavandhoo: 1,289m3 (households) + 105m3 (communal) Gadhdhoo: no data (individual systems only) Mahibadhoo: no data (individual systems only) Most existing rainwater harvesting systems have insufficient capacities of 2,5 m3 per household and lack proper disinfection safeguards | The design has been modified to include collection of rainwater from public, community and private households. Communal rainwater tanks connected to the central plant will be installed. Rainwater will then be treated and circulated in combination with desalinated water. This will reduce costs and allow for the desalination plant to be operated throughout the year. Desalinated plants cannot be left more than 24 hours without operation as it can result in deterioration of the membranes. Construction of rain water tanks were awarded and construction works 80% completed on two islands, Mahibadhoo and Ihavandhoo. On Gadhdhoo one of three tanks is yet to be constructed due to the discovery of human remains on site and objection by the community on the relocation of remains as advised by the Ministry of Islamic Affairs. The other two tanks in Gadhdhoo are nearing 50% completion. | Improved rainwater harvesting and storage capacity will be installed as follows: Ihavandhoo: 550 m3 Mahibadhoo: 500 m3. Gadhdhoo: 550 m3 All new rainwater harvesting systems will be equipped with disinfection safeguards to ensure safety of water supply
| Capacity of desalinated freshwater supply available during dry spells, drought and flooding | Existing capacity to generate freshwater supply from desalination: Ihavandhoo: 0m3 / day Gadhdhoo: 10m3 / day Mahibadhoo: 10m3 / day | The design proposed for all three islands includes installation of a desalinated plant. Plant capacity initially proposed was considered to be too big since the project was attempting to demonstrate cost effective supply through a hybrid rainwater + desalinated water model. The distribution network layout for all three islands was completed. The contract for the supply of pipes has been awarded. Due to shipment delays only 2 thirds of the pipe supply has reached Maldives during the reporting period. Contracts for supply of RO plant was awarded in April 2014. On Mahibadhoo and Gadhdhoo the existing reverse osmosis plants have been assessed for rehabilitation and inclusion in the system. The contractor for the supply and installation of the reverse osmosis plants has recommended that these plants are beyond repair and instead has proposed an increase in the plant capacity that will be supplied. The original design required the supply of a total capacity of Mahibadhoo 50m3,Gaddhoo 60m3 and Ihavandhoo 70m3. The contractor is proposed to supply 70m3 for all three islands at no cost instead of rehabilitating the existing reverse osmosis plants. RO building works are more than 75% completed on all three islands. The pipe laying contracts are yet to be awarded. On two islands the budgets are insufficient with Gadhdhoo bid being 30 percent above the engineers estimate. | The following minimum amounts of desalination capacity will be installed on each target island: Ihavandhoo: 70 m3 Mahibadhoo: 50 m3. Gadhdhoo: 60 m3 Potable water quality levels will be in conformity with WHO standard at all times
| Number of planned wastewater management and sewage systems which integrate targeted measures to reduce groundwater pollution | 1 sewage treatment plant under construction by a contractor in ADh. Mahibadhoo 1 sewage treatment plant in design phase in HA. Ihavandhoo; 1 sewage treatment plant in design phase in GDh. Gadhdhoo Sea level rise and unsecured septic tanks pollute groundwater and render it unsafe for household uses | With the assistance of MEE, UNOPS (party responsible for outcome 1) has engaged the International Water Management Institute (IWMI) who have proposed an assessment and study on management aquifer recharge. The proposed implementation duration is 2 years and the cost is above the available budget. UNOPS (party responsible for Outcome 1) is negotiating with IWMI on achievable targets during the project duration. UNOPS expects to finalize the negotiations by end of May 2014. | All sewage and wastewater management systems which are planned and/or constructed on the 3 target islands integrate targeted measures to reduce groundwater pollution The outcomes and implementation scope will be depend on the proposal of MAR study
Strengthened local awareness and ownership of integrated, climate-resilient freshwater management systems | Number of integrated water management systems which are based on participatory planning between water users and water providers and can be sustained in line with actual willingness to pay for operation and maintenance | Willingness to pay for integrated water management services is unknown No participatory planning and design process for water supply and management schemes | The project inception, conceptual designs and detailed designs have been through a participatory approach with sharing of information during the reporting period. Community consultations have been undertaken to gauge the perception on the project and expectations. Ministry has completed a willingness to pay survey on all 3 islands. The results have produced a tariff structure which has been recommended to the future operator Fenaka - Government Utility corporation. The financial analysis shows that the provided depreciation is not accounted for, the system can be sustainably operated at the tariff rates that the communities are willing to pay. FENAKA - Government Utility corporation is reviewing the tariff structure developed through the project and is expected to submit the tariff structure for approval by EPA (regulatory authority) by end of May 2014. | Integrated water management systems on all target islands are designed and installed based on community participation, and their operation and maintenance is based on actual willingness to pay
| Communal willingness to pay for continued operations and maintenance of freshwater supply on each target island | Willingness to pay for integrated water management services is unknown No participatory planning and design process for water supply and management schemes | same as above. | Integrated water resources management systems on each target island are designed and installed on the basis of community input, and their continued operation is aligned with actual willingness to pay for the operation and maintenance of the installed infrastructure
| Number of Maldivians which are aware about their rights, roles and responsibilities in the management of freshwater resources in a changing climate | Limited awareness across all islands and atolls about the value of water as both an economic as well as social good, which is sensitive to climate-related shocks and stresses and therefore needs to be managed responsibly. | Awareness strategy and national campaign has been formulated. Delays in procurement meant that the campaign rollout was not initiated as planned during Quarter 4 of 2013. A bidder was selected for the national campaign brand identity and specification development in May 2014. A one day seminar on integrated water resource management was held in February 2014. The objective of the seminar was to increase awareness on the principles of IWRM applied in the context of the Maldives islands. The seminar included a session to focus on the importance of Ground Water, since it is the only water resource available to islands during the dry season as well as impacts of climate change on water resources, its management and water security. During the discussion sessions, local experiences in different types of water projects including those that focused on groundwater recharge were shared amongst the participants. The participants included FENAKA (government utility company), other Government utility companies, participants from 2 of the project islands and participants from project islands where MEE is actively implementing IWRM projects in addition to national stakeholders in key sectors such as the Environment Protection Agency(regulator), the Health Ministry among others, community based organizations and private companies engaged in the water sector. The seminar was conducted by the International Water Management Institute (IWMI). | At least 1 IWRM training campaign is conducted in each administrative region (7 total) to strengthen dialogue between water users and providers and increase sensitization about the economic, social and environmental role of water in a changing climate
Improved institutional capacity to promote and enforce climate-resilient freshwater management on all inhabited islands | Number of fully financed follow-up projects which adopt the climate resilient, integrated water resources management approach demonstrated by the project | Maldives has no integrated water resources management project in place that is suitable for replication and up scaling | The Government has already taken on board the cost effectiveness of combining the utilization of community rainwater harvesting with desalination and is the process of formulating a new project in the island of Ukulhas based on the design processes of this project. Ukulhas has 96 households and population of 615 (Census 2006, Statistical Yearbook of Maldives 2013). The Male Water and Sewerage Company (private sector) has initiated and is piloting a project in Dhuvaafaru utilizing concepts of integrating rainwater and desalinated water as proposed by this project in 2011. MEE has raised finance through the public sector investment (Government Budget) for the provision of safe water through an IWRM approach in 3 islands of Mulah, Dhiggaru and Maamigili serving a cumulative population of 3,709 (Census 2006, Statistical Yearbook of Maldives 2013). The Government's policy following this project, is to ensure that all new water projects follow the principles of IWRM for low cost safe water provision. Two new donor funded projects are in the pipeline for Hinnavaru island, population 3,017 and Thoddoo island, population 1,199. MEE has raised funding through Government budget to design safe water supply systems using the low cost IWRM appraoch in 13 islands. | Project approach is replicated on at least 4 islands
| Number of staff from water and sewage utility companies trained in the technical principles and skills required to design, implement and maintain climate-resilient and integrated water management systems | No staff of public or private utility companies in Maldives has received targeted training on IWRM | Targeted training. Since project formulation the provincial utility companies has been dismantled and in place Fenaka Corporation has been established with the mandate to provide utility services in these islands. Fenaka has been brought on board and is part of the project coordination team and will be a targeted recipient of training initiatives. Staff recruited during the project implementation and funded by the Project will absorbed into FENAKA (government utility) upon handover the project in September 2014. These staff number 3 per project island, one supervisor and two technicians, will be given hands on training by the supplier of the reverse osmosis plant. | At least 5 staff from each water and sewage utility company currently active in Maldives are trained in the technical principles of integrated water resource management and recognize basic design principles which make water supply and sewage systems adaptive to a changing climate
| Number of new water and sewage management projects which are reviewed and improved on the basis of lessons learned from the project | Maldives has no adaptive and integrated water resources management project in place that is suitable for replication and up scaling The government is not able to draw on best practices in the adaptive management of freshwater resources | All new water and projects are subject to technical reviews on the basis of IWRM and climate resilience principles similar to this project. 3 projects have been handed over to contractors and 13 more projects are being designed similar to this project. | Each new water and wastewater management project that is approved by the Government of Maldives is subject to technical reviews on the basis of IWRM and climate resilience principles
| Financing allocated to new water management projects which integrate climate resilient and integrated design and are approved by the government for implementation | The government is not able to draw on best practices in the adaptive management of freshwater resources to enable systematic planning and financing of additional projects | MEE has raised finance through the public sector investment (Government Budget) for the provision of safe water through an IWRM approach in 3 islands of Mulah, Dhiggaru and Maamigili serving a cumulative population of 3,709 (Census 2006, Statistical Yearbook of Maldives 2013). The 3 projects have been approved and handed over to the contractors. The work has started on all 3 islands. Government is planning to implement two donor funded projects in Hinnavaru and Thoddoo that follow a similar model to provide cost effective and safe water supply using the IWRM approach of this Project. MEE has raised funding through Government budget to design safe water supply systems using the low cost IWRM approach in 13 islands. The target is achieved as the Government has since project inception approved 6 projects on the basis of the lessons learnt during the design phase of this Project. | The government approves at least 4 new, fully financed freshwater and/or wastewater management projects on the basis of lessons learned and design principles replicated from the proposed project

## Lessons Learned
QUALITATIVE MEASURES and LESSONS LEARNED
Please complete the following section every reporting period
Implementation and Adaptive Management | Response
What implementation issues/lessons, either positive or negative, affected progress? | (1) human resources for project: The Ministry notes the lack of technical capacity of involved UNOPS (responsible party for outcome 1) experts in areas of climate resilience, IWRM, sustainable development or similar water projects involving reverse osmosis plants and project management (4 managers have been part of the project). Ensure that future projects engage human resources with the required skills and experience. (2) lack of planning and anticipation of possible delays/risks linked to point 1 to take into account national policies, guidelines, regulations and community needs. Creative problem solving is not apparent, when a suggestion is given only that suggestion is explored and no other options for addressing a problem are sought. E.g.. the delay in recruiting certified Island Engineers. Only when one approach fails was another looked into. Effective adaptive management requires identification of multiple project scenarios and problem solution options and anticipatory risk management. (3) reacting to delays instead of predicting and taking preventive measures. Example: The annual workplan for 2014 was endorsed on 24 December 2013 and signed on 19 January 2014. Procurement scheduling should have taken place as soon as the Board approved the budgets for 2014. However, the bidding processes were not initiated until the end of February 2014 nearly 2 months after budget approval. Planning and procurement scheduling would have reduced the risk of delays that could result in the procurement process. In the case of the supply and installation of solar panels for the operation of the reverse osmosis plant the bidding process was unsuccessful in the first round due to very high prices and only two parties competing. Therefore, UNOPS (responsible party for outcome 1) had to cancel the first round and begin a new round of the procurement process. Had the process been initiated at the beginning of 2014 (bid documents were ready at the end of 2013) the risk of further delays to the project could have been minimized. (4) comparatively higher prices on tenders issued by UNOPS (responsible party for outcome 1) as opposed to Government bids. For example solar PV cheapest price is USD 3 per KW installed in second round of bidding whereas MEE bids achieve a price of USD 1.8 per KW including inverters and installation of the same quality. The same is observed in construction bids. (5) strengthen planning processes in budgeting to include contingency rather than calculating contingency based upon the winning bid prices. (6) applying best practices in Environment Impact Assessment to guide the design process and following standards in civil works would have prevented much of the delays being faced in the implementation of Outcome 1 by UNOPS (responsible party) (7) Adhere to financial and procurement policies to avoid delays, anticipate, forecast and plan to ensure that policies are followed and no delays are caused as a result of known processes that need to be followed. (8) Coordination meetings have proven to be a very useful mechanism to update MEE, UNDP and UNOPS, and troubleshoot. It is a good mechanism to continue and take up in projects. (9) It should be noted that their should be more frequent visits to project sites by the Project Manager as a lot of community engagement is mostly at the infrastructure level through UNOPS. The IWRM specialist of the PMU has been on field missions but it is vital to maintain a strong relationship with the communities and the PMU, esp the PM, to ensure smooth integration of the infrastructure and the soft systems that the project brings in into the community. The community engagement components remain a low priority with the PMU and the government and needs to be picked up now. The workplan is designed to take some of the community engagement up this year, and UNDP is pushing for this component to be more strongly taken up.
Were there any delays in implementation? If so, include any causes of delays. What measures have been taken to reduce delays? | Supplies of pipes, water meters and fittings: FENAKA(government utility) raised concerns (7.12.2013) on the specifications of the water meters offered by the winning bidder showing a starting flow rate of 4-5l/h which is higher than the meters installed in Male’ by MWSC. The KENT class D meters installed by MWSC has a starting flow rate of 3l/h. The expected water consumption will be very low in these islands and FENAKA cannot afford to have unaccounted water usage through the meters. Any unregistered flow of water through dripping will have a huge impact financially on the revenue side. “minimum registration flow rate” - rate below which the meter will not register a reading. Supply of meters changed to meet requirements of a registering flow rate of around 3 l/h. Supply and installation of reverse osmosis plants: UNOPS (responsible party) carried out the technical evaluation of bids by a civil engineer with no experience in the operation and maintenance of reverse osmosis plants and 3 managers. MEE recommended that technical compliance of bids be evaluated by a local expert or company. Once endorsed by FENAKA and the third party expert the technically compliant bids were approved for financial opening. Financial bids for Supply and Installation of Reverse Osmosis Plants: two parties with the highest points are approximately 24% higher than the engineers estimate and that there was a budget shortfall of approximately USD 250,000 in the component. UNOPS had negotiated with Male Water and Sewerage Company for a price revision and they were able to give a 4% discount only. Discussion also took place on cancelling components such as backup generators and fire hydrant components to fit the project budget. These negotiations violated UNOPS (responsible party) procurement policies and it resulted in an additional 3 month delay in obtaining approval for contracting. Recommendation: Follow financial and procurement policies to avoid delays. This contract stands to delay the entire project delivery. Ihavandhoo island: contract variations on civil works contracts were required. Site clearance was not included in the original bid. Rainwater harvesting tanks 1) one tank moved to children’s park, youth objected on proximity of tank to football grounds. 2) move tank to the corner of the mosque’s plot. 3) demolition of a shed was not included and approval for demolition of shed that belongs to Ministry of Health 4) The floor height of the building had to be raised as the area is prone to flooding. 5) Refusal by some owners to accept the compensation for coconut tree felling. Mitigation measures proposed by MEE: consult all relevant parties/stakeholders on designs before initiating procurement. Follow Standard Method of Measurement (SMM) published by the Royal Institute of Chartered Surveyors (RICS) or bring UNOPS global support in the preparation of bills of quantities so that important items under preliminaries are not missed. This is industry wide practice and used by Government. Mahibadhoo: Contract variation on civil works contracts were required. Community requested design change due to lack of land. 2 rainwater harvesting tanks were combined with a net loss of 50 tonnes in storage capacity. Design changes meant obtaining clearance from EPA prior to MEE approval on contract variation. Mitigation measure proposed by MEE: Design team with UNDP & MEE Consult all relevant parties/stakeholders on design Gadhdhoo: Civil works bids were excessively high during the first two rounds at over 40% and 12%. In the third round budget and BOQ was revised. Pipe laying bids are 30% higher than engineers estimate. Mitigation measures Ensure BOQs/Cost estimates are up to date and include contingency. Outcome 2 – delays in procurement in the preparation of the campaign identity have meant that this activity has not moved forward. 8 months delay as a result of lack of interest resulting in 3 rounds of advertisement. Evaluation process was carried out 3 times based on advise of the MEE tender committee due to the huge price difference. Outcome 2 / Outcome 3 / M&E / PMU – disbursement against the Annual Workplan is almost zero due to the lack of funds advanced to the Ministry. The Fund Advance request was initiated on 6 February 2014. UNDP was not able to complete shaded areas without negative figures and therefore they were in discussion with their HQ until 16 February 2014. This negative figure is being brough in as there were expenditure from budget lines that did not have authorised budget advanced. At this point UNDP decided to proceed anyway and process the FACE form. The next issue that was raised was that the figures in the FACE form were not tallying with the Quarter Workplan. This discussion and explanation took another 2 weeks. Finally a revised FACE form that was accepted by the Executing Agency UNDP was submitted on 27 March 2014. By the end of the quarter no funds were received. Trainings have been conducted for both PMU staff and UNDP staff of FACE forms and there is now a common understanding on how FACE forms are done. UNDP has had issues with identifying which activities on the workplan correcponds to the expenditure on the FACE forms as there were occassions where Ministry had reported expenditure from budget lines that did not have an initial allocation (which had led to the initial negative figures on the FACE form.) UNDP has also devised a new Quarterly Reporting format which will clarify how the expenditure on the FACE form translates to actual workplan level activity, which will help better align the expenditure against the results. It should also be noted that the funds meant for the first quarter will not be deposited until end of April and therefore, the balance shown in FACE form for Quarter 1 reporting is virtual and not available at the time. The potential for the Environment Impact Assessment (EIA) to contribute towards a sustainable design was not fully exploited by the project. The EIA was completed in 1 month for all 3 island after the completion of the detailed design. Future such projects should rely more on the EIA to guide the design process with thorough analysis of climate change projections, socio-economic impacts and options analysis rather than treat the EIA as meeting a regulatory requirement to assure that adaptation projects are sustainable in the longer run and that the most optimal solution is deployed within the constraints of the available resources. To avoid risks in the future Ministry is suggesting that contract variation require the endorsement of MEE to ensure that we remain within budget. We otherwise risk falling short of funds and more importantly not implementing a system as per the approved designs The regular coordination meetings among MEE, UNDP and UNOPS had helped to a great extend in maintinging momentun as much as possible and troubleshooting issues.
Describe any changes undertaken to improve results on the ground or any changes made to project outputs (i.e. changes to project design)
How have gender considerations been taken into consideration during the reporting period? What have been the lessons learned as a consequence of inclusion of such considerations on project performance or impacts? | The project will benefit both genders through the provision of safe potable water. Women are invited to join the community level consultations and will be a target group for awareness initiatives under the project, particularly the social and economic values of water in a changing climate. | Delays will add up and slow delivery pushing up costs to for execution and operation of the project.
A monitoring plan for groundwater quality, distribution water quality will need to be implemented for component 1 activities to assess progress on indicators and suitability for replication.
Please complete the following section at mid-term and project completion
Lessons for Adaptation | Response
Climate Resilience Measures
What have been the lessons learned, both positive and negative, in implementing climate adaptation measures that would be relevant to the design and implementation of future projects/programmes for enhanced resilience to climate change? | 1) Consider the limitation of land in small islands such as those in the Maldives and look for options that can be a work-around. 2) Avoid putting in concrete structures such as huge rainwater storage tanks which will be costly to repair in the event of failure and costly to remove. Given the shortage of land, incorporate underground tanks into buildings for example, the reverse osmosis plant building.
What is the potential for the climate resilience measures undertaken by the project/programme to be replicated and scaled up both within and outside the project area? | Hybrid system being developed to maximize water resources. Climatic change causes an increased uncertainty on rainfall patterns resulting in long dry periods and intense showers. The project will demonstrate artificial recharge of groundwater and ensure that targeted measures are undertaken to prevent groundwater pollution in the new sanitation projects to be deployed in the project islands. In addition, the awareness campaign will be geared towards preservation and protection of groundwater the primary resource of water on islands which can increase resilience of islands in a changing climate and is also essential to buffer away the sea water intrusion.
Concrete Adaptation Interventions
What have been the lessons learned, both positive and negative, in implementing concrete adaptation interventions that would be relevant to the design and implementation of future projects/programmes implementing concrete adaptation interventions?
What is the potential for the concrete adaptation interventions undertaken by the project/programme to be replicated and scaled up both within and outside the project area? | Ensuring water security in 3 islands by implementing a water management system that integrates rainwater and desalinated water as well as introduces a good practice of ground water recharge and management.
Community/National Impact
What would you consider to be the most successful aspects for the target communities? | Isolated island communities will be able to be self reliant in water supply. Furthermore, the it is anticipated that once the plant is operational the beneficiary islands would be able to supply water to nearby islands during the dry season reducing the cost to the central government.
What measures are/have been put in place to ensure sustainability of the project/program results? | 1) MEE ensured that UNOPS (responsible party) jointly recruit with FENAKA for each island, one supervisor and two technicians, during project implementation. These staff will be absorbed into FENAKA corporation upon completion of the project. Project knowledge and technical skills in operation and maintenance will be transferred. 2) The project is being designed to incorporate elements of renewable energy so that future operation and maintenance will be more cost effective.
What measures are being/could have been put in place to improve project/program results? | IWMI has been engaged in developing GWR options with infrastructure design
Knowledge Management
How has existing information/data/knowledge been used to inform project development and implementation? What kinds of information/data/knowledge were used? | A more thorough discussion with various stakeholders to learn about water supply provisions that the Government or private sector has undertaken in the past. The project has not produced enough knowledge products and there should be a stronger focus on knowledge management including at island, atoll, national and SIDS level.
If learning objectives have been established, have they been met? Please describe. | 1) UNOPS developed a training schedule for the island based site staff in civil works.One training session was held in Male, briefings have been carried out via Skype and on site. The staff are reporting based on the training they received. No material has been produced as yet for archiving and use by staff. It is expected that suppliers will provide manuals for specific components however UNOPS (responsible party) needs to provide a complete manual on preventive maintenance along with specific manuals provided by suppliers. 2) Supplier's of equipment will be providing hands on training to project field staff and facilitate capacity building in operation and maintenace once the equipment is delivered.
Describe any difficulties there have been in accessing or retrieving existing information (data or knowledge) that is relevant to the project. Please provide suggestions for improving access to the relevant data.
Has the identification of learning objectives contributed to the outcomes of the project? In what ways have they contributed?

## Results Tracker
Results Tracker for Adaptation Fund (AF) Projects
Goal: Assist developing-country Parties to the Kyoto Protocol that are particularly vulnerable to the adverse effects of climate change in meeting the costs of concrete adaptation projects and programmes in order to implement climate-resilient measures. Impact: Increased resiliency at the community, national, and regional levels to climate variability and change.
Important: Please read the following Results Framework and Baseline Guidance (also posted on the Adaptation Fund website) before entering your data
Link: http://www.adaptation-fund.org/sites/default/files/Results%20Framework%20and%20Baseline%20Guidance%20final.pdf
Please select the relevant Fund level Outcome and Output indicators that allign with the project objectives and outcomes
OBJECTIVE 1
Fund Outcome | Please select from dropdown menu below | Fund Outcome Indicator | Please select from dropdown menu below | Target at project/programme approval (see Units in next sheet) | Baseline (see Units in next sheet) | Mid-term Results | Terminal Results
Outcome 1: Reduced exposure at national level to climate-related hazards and threats Outcome 2: Strengthened institutional capacity to reduce risks associated with climate-induced socioeconomic and environmental losses Outcome 3: Strengthened awareness and ownership of adaptation and climate risk reduction processes at local level Outcome 4: Increased adaptive capacity within relevant development and natural resource sectors Outcome 5: Increased ecosystem resilience in response to climate change and variability-induced stress Outcome 6: Diversified and strengthened livelihoods and sources of income for vulnerable people in targeted areas Outcome 7: Improved policies and regulations that promote and enforce resilience measures | 1 | 1. Relevant threat and hazard information generated and disseminated to stakeholders on a timely basis 2.1. No. and type of targeted institutions with increased capacity to minimize exposure to climate variability risks 2.2. Number of people with reduced risk to extreme weather events 3.1. Percentage of targeted population aware of predicted adverse impacts of climate change, and of appropriate responses 3.2. Modification in behavior of targeted population 4.1. Development sectors' services responsive to evolving needs from changing and variable climate 4.2. Physical infrastructure improved to withstand climate change and variability-induced stress 5. Ecosystem services and natural assets maintained or improved under climate change and variability-induced stress 6.1. Percentage of households and communities having more secure (increased) access to livelihood assets 6.2. Percentage of targeted population with sustained climate-resilient livelihoods 7. Climate change priorities are integrated into national development strategy | 4.2 | 5 | 1 | 1
Fund Output | Please select from dropdown menu below | Fund Output Indicator | Please select from dropdown menu below | Target at project/programme approval | Baseline | Mid-term Results | Terminal Results
Output 1: Risk and vulnerability assessments conducted and updated at a national level Output 2.1: Strengthened capacity of national and regional centres and networks to respond rapidly to extreme weather events Output 2.2: Targeted population groups covered by adequate risk reduction systems Output 3: Targeted population groups participating in adaptation and risk reduction awareness activities Output 4: Vulnerable physical, natural, and social assets strengthened in response to climate change impacts, including variability Output 5: Vulnerable physical, natural, and social assets strengthened in response to climate change impacts, including variability Output 6: Targeted individual and community livelihood strategies strengthened in relation to climate change impacts, including variability Output 7: Improved integration of climate-resilience strategies into country development plans | 2.2 | 1.1. No. and type of projects that conduct and update risk and vulnerability assessments 1.2. Development of early warning systems 2.1.1. No. of staff trained to respond to, and mitigate impacts of, climate-related events 2.1.2. Capacity of staff to respond to, and mitigate impacts of, climate-related events from targeted institutions increased 2.2.1. Percentage of population covered by adequate risk-reduction systems 2.2.2. No. of people affected by climate variability 3.1 No. and type of risk reduction actions or strategies introduced at local level 3.2 No. of news outlets in the local press and media that have covered the topic 4.1. No. and type of health or social infrastructure developed or modified to respond to new conditions resulting from climate variability and change (by type) 4. 2. No. of physical assets strengthened or constructed to withstand conditions resulting from climate variability and change (by asset types) 5. No. and type of natural resource assets created, maintained or improved to withstand conditions resulting from climate variability and change (by type of assets) 6.1. No. and type of adaptation assets (physical as well as knowledge) created in support of individualor community-livelihood strategies 6.2. Type of income sources for households generated under climate change scenario 7.1. No., type, and sector of policies introduced or adjusted to address climate change risks 7.2. No. or targeted development strategies with incorporated climate change priorities enforced | 2.2.1 | 3 | 0 | 0
OBJECTIVE 2
Fund Outcome | Please select from dropdown menu below | Fund Outcome Indicator | Please select from dropdown menu below | Target at project/programme approval (see Units in next sheet) | Baseline | Mid-term Results | Terminal Results
Outcome 1: Reduced exposure at national level to climate-related hazards and threats Outcome 2: Strengthened institutional capacity to reduce risks associated with climate-induced socioeconomic and environmental losses Outcome 3: Strengthened awareness and ownership of adaptation and climate risk reduction processes at local level Outcome 4: Increased adaptive capacity within relevant development and natural resource sectors Outcome 5: Increased ecosystem resilience in response to climate change and variability-induced stress Outcome 6: Diversified and strengthened livelihoods and sources of income for vulnerable people in targeted areas Outcome 7: Improved policies and regulations that promote and enforce resilience measures | 4 | 1. Relevant threat and hazard information generated and disseminated to stakeholders on a timely basis 2.1. No. and type of targeted institutions with increased capacity to minimize exposure to climate variability risks 2.2. Number of people with reduced risk to extreme weather events 3.1. Percentage of targeted population aware of predicted adverse impacts of climate change, and of appropriate responses 3.2. Modification in behavior of targeted population 4.1. Development sectors' services responsive to evolving needs from changing and variable climate 4.2. Physical infrastructure improved to withstand climate change and variability-induced stress 5. Ecosystem services and natural assets maintained or improved under climate change and variability-induced stress 6.1. Percentage of households and communities having more secure (increased) access to livelihood assets 6.2. Percentage of targeted population with sustained climate-resilient livelihoods 7. Climate change priorities are integrated into national development strategy | 4.2 |  |  | 1
Fund Output | Please select from dropdown menu below | Fund Output Indicator | Please select from dropdown menu below | Target at project/programme approval | Baseline | Mid-term Results | Terminal Results
Output 1: Risk and vulnerability assessments conducted and updated at a national level Output 2.1: Strengthened capacity of national and regional centres and networks to respond rapidly to extreme weather events Output 2.2: Targeted population groups covered by adequate risk reduction systems Output 3: Targeted population groups participating in adaptation and risk reduction awareness activities Output 4: Vulnerable physical, natural, and social assets strengthened in response to climate change impacts, including variability Output 5: Vulnerable physical, natural, and social assets strengthened in response to climate change impacts, including variability Output 6: Targeted individual and community livelihood strategies strengthened in relation to climate change impacts, including variability Output 7: Improved integration of climate-resilience strategies into country development plans | 4 | 1.1. No. and type of projects that conduct and update risk and vulnerability assessments 1.2. Development of early warning systems 2.1.1. No. of staff trained to respond to, and mitigate impacts of, climate-related events 2.1.2. Capacity of staff to respond to, and mitigate impacts of, climate-related events from targeted institutions increased 2.2.1. Percentage of population covered by adequate risk-reduction systems 2.2.2. No. of people affected by climate variability 3.1 No. and type of risk reduction actions or strategies introduced at local level 3.2 No. of news outlets in the local press and media that have covered the topic 4.1. No. and type of health or social infrastructure developed or modified to respond to new conditions resulting from climate variability and change (by type) 4. 2. No. of physical assets strengthened or constructed to withstand conditions resulting from climate variability and change (by asset types) 5. No. and type of natural resource assets created, maintained or improved to withstand conditions resulting from climate variability and change (by type of assets) 6.1. No. and type of adaptation assets (physical as well as knowledge) created in support of individualor community-livelihood strategies 6.2. Type of income sources for households generated under climate change scenario 7.1. No., type, and sector of policies introduced or adjusted to address climate change risks 7.2. No. or targeted development strategies with incorporated climate change priorities enforced | 4.2 | 3 | 0 | 0 (desing stage completed)
OBJECTIVE 3
Fund Outcome | Please select from dropdown menu below | Fund Outcome Indicator | Please select from dropdown menu below | Target at project/programme approval | Baseline | Mid-term Results | Terminal Results
Outcome 1: Reduced exposure at national level to climate-related hazards and threats Outcome 2: Strengthened institutional capacity to reduce risks associated with climate-induced socioeconomic and environmental losses Outcome 3: Strengthened awareness and ownership of adaptation and climate risk reduction processes at local level Outcome 4: Increased adaptive capacity within relevant development and natural resource sectors Outcome 5: Increased ecosystem resilience in response to climate change and variability-induced stress Outcome 6: Diversified and strengthened livelihoods and sources of income for vulnerable people in targeted areas Outcome 7: Improved policies and regulations that promote and enforce resilience measures | 3 | 1. Relevant threat and hazard information generated and disseminated to stakeholders on a timely basis 2.1. No. and type of targeted institutions with increased capacity to minimize exposure to climate variability risks 2.2. Number of people with reduced risk to extreme weather events 3.1. Percentage of targeted population aware of predicted adverse impacts of climate change, and of appropriate responses 3.2. Modification in behavior of targeted population 4.1. Development sectors' services responsive to evolving needs from changing and variable climate 4.2. Physical infrastructure improved to withstand climate change and variability-induced stress 5. Ecosystem services and natural assets maintained or improved under climate change and variability-induced stress 6.1. Percentage of households and communities having more secure (increased) access to livelihood assets 6.2. Percentage of targeted population with sustained climate-resilient livelihoods 7. Climate change priorities are integrated into national development strategy | 3.1 | 100 | 30 | 50
Fund Output | Please select from dropdown menu below | Fund Output Indicator | Please select from dropdown menu below | Target at project/programme approval | Baseline | Mid-term Results | Terminal Results
Output 1: Risk and vulnerability assessments conducted and updated at a national level Output 2.1: Strengthened capacity of national and regional centres and networks to respond rapidly to extreme weather events Output 2.2: Targeted population groups covered by adequate risk reduction systems Output 3: Targeted population groups participating in adaptation and risk reduction awareness activities Output 4: Vulnerable physical, natural, and social assets strengthened in response to climate change impacts, including variability Output 5: Vulnerable physical, natural, and social assets strengthened in response to climate change impacts, including variability Output 6: Targeted individual and community livelihood strategies strengthened in relation to climate change impacts, including variability Output 7: Improved integration of climate-resilience strategies into country development plans | 3 | 1.1. No. and type of projects that conduct and update risk and vulnerability assessments 1.2. Development of early warning systems 2.1.1. No. of staff trained to respond to, and mitigate impacts of, climate-related events 2.1.2. Capacity of staff to respond to, and mitigate impacts of, climate-related events from targeted institutions increased 2.2.1. Percentage of population covered by adequate risk-reduction systems 2.2.2. No. of people affected by climate variability 3.1 No. and type of risk reduction actions or strategies introduced at local level 3.2 No. of news outlets in the local press and media that have covered the topic 4.1. No. and type of health or social infrastructure developed or modified to respond to new conditions resulting from climate variability and change (by type) 4. 2. No. of physical assets strengthened or constructed to withstand conditions resulting from climate variability and change (by asset types) 5. No. and type of natural resource assets created, maintained or improved to withstand conditions resulting from climate variability and change (by type of assets) 6.1. No. and type of adaptation assets (physical as well as knowledge) created in support of individualor community-livelihood strategies 6.2. Type of income sources for households generated under climate change scenario 7.1. No., type, and sector of policies introduced or adjusted to address climate change risks 7.2. No. or targeted development strategies with incorporated climate change priorities enforced | 3.2 | 5 | 1 | 5
OBJECTIVE 4
Fund Outcome | Please select from dropdown menu below | Fund Outcome Indicator | Please select from dropdown menu below | Target at project/programme approval | Baseline | Mid-term Results | Terminal Results
Outcome 1: Reduced exposure at national level to climate-related hazards and threats Outcome 2: Strengthened institutional capacity to reduce risks associated with climate-induced socioeconomic and environmental losses Outcome 3: Strengthened awareness and ownership of adaptation and climate risk reduction processes at local level Outcome 4: Increased adaptive capacity within relevant development and natural resource sectors Outcome 5: Increased ecosystem resilience in response to climate change and variability-induced stress Outcome 6: Diversified and strengthened livelihoods and sources of income for vulnerable people in targeted areas Outcome 7: Improved policies and regulations that promote and enforce resilience measures |  | 1. Relevant threat and hazard information generated and disseminated to stakeholders on a timely basis 2.1. No. and type of targeted institutions with increased capacity to minimize exposure to climate variability risks 2.2. Number of people with reduced risk to extreme weather events 3.1. Percentage of targeted population aware of predicted adverse impacts of climate change, and of appropriate responses 3.2. Modification in behavior of targeted population 4.1. Development sectors' services responsive to evolving needs from changing and variable climate 4.2. Physical infrastructure improved to withstand climate change and variability-induced stress 5. Ecosystem services and natural assets maintained or improved under climate change and variability-induced stress 6.1. Percentage of households and communities having more secure (increased) access to livelihood assets 6.2. Percentage of targeted population with sustained climate-resilient livelihoods 7. Climate change priorities are integrated into national development strategy
Fund Output | Please select from dropdown menu below | Fund Output Indicator | Please select from dropdown menu below | Target at project/programme approval | Baseline | Mid-term Results | Terminal Results
Output 1: Risk and vulnerability assessments conducted and updated at a national level Output 2.1: Strengthened capacity of national and regional centres and networks to respond rapidly to extreme weather events Output 2.2: Targeted population groups covered by adequate risk reduction systems Output 3: Targeted population groups participating in adaptation and risk reduction awareness activities Output 4: Vulnerable physical, natural, and social assets strengthened in response to climate change impacts, including variability Output 5: Vulnerable physical, natural, and social assets strengthened in response to climate change impacts, including variability Output 6: Targeted individual and community livelihood strategies strengthened in relation to climate change impacts, including variability Output 7: Improved integration of climate-resilience strategies into country development plans |  | 1.1. No. and type of projects that conduct and update risk and vulnerability assessments 1.2. Development of early warning systems 2.1.1. No. of staff trained to respond to, and mitigate impacts of, climate-related events 2.1.2. Capacity of staff to respond to, and mitigate impacts of, climate-related events from targeted institutions increased 2.2.1. Percentage of population covered by adequate risk-reduction systems 2.2.2. No. of people affected by climate variability 3.1 No. and type of risk reduction actions or strategies introduced at local level 3.2 No. of news outlets in the local press and media that have covered the topic 4.1. No. and type of health or social infrastructure developed or modified to respond to new conditions resulting from climate variability and change (by type) 4. 2. No. of physical assets strengthened or constructed to withstand conditions resulting from climate variability and change (by asset types) 5. No. and type of natural resource assets created, maintained or improved to withstand conditions resulting from climate variability and change (by type of assets) 6.1. No. and type of adaptation assets (physical as well as knowledge) created in support of individualor community-livelihood strategies 6.2. Type of income sources for households generated under climate change scenario 7.1. No., type, and sector of policies introduced or adjusted to address climate change risks 7.2. No. or targeted development strategies with incorporated climate change priorities enforced

## Units for Indicators
Fund Outcome Indicator Units
1. Generation of relevant data, Stakeholders, and Timeliness 2.1. Include both qualitative and quantitative measures of capacity level within targeted institutions 2.2. Number (men and women and other vulnerable groups) 3.1. Use scale from 1 to 5: 5: Fully aware 4: Mostly aware 3: Partially aware 2: Partially not aware 1: Aware of neither predicted adverse impacts of climate change nor of appropriate responses 3.2. Use scale from 1 to 5: 5: All 4: Almost all 3: Half 2: Some 1: None 4.1. Summarize in an overall scale (1-5): 5: Highly responsive (All defined elements ) 4: Mostly responsive (Most defined elements) 3: Moderately responsive (Some defined elements) 2: Partially responsive (Lacks most elements) 1: Non responsive (Lacks all elements ) 4.2. Summarize in an overall scale (1-5): 5: Fully improved 4: Mostly Improved 3: Moderately improved 2: Somewhat improved 1: Not improved 5. Depends on the targeted natural asset: Biological (species): measure through changes in population numbers (dynamics, structure, etc.) Land: measure changes in hectares. Baseline data will be necessary to estimate the change. Supporting indicators baseline and target (as well as contextual information) are needed such as the following: Farmers adopting recommended technologies, Ha. of land improved, Average deforestation rate Etc. Use scale from 1 to 5. 5: Very effective (All elements are present) 4: Effective (Most elements are present) 3: Moderately effective (Some elements are present) 2: Partially effective (Most elements are not present) 1: Ineffective (No elements are present) 6.1. Summarize in an overall scale (1-5): 5: Very high improvement 4: High improvement 3: Moderate improvement 2: Limited improvement 1: No improvement 6.2. Household income by source of livelihood in project area (USD) prior and post project intervention 7. Summarize in an overall scale (1-5). 5: All (Fully integrated) 4: Most 3: Some 2: Most not integrated 1: None
Fund Output Indicator Units
1.1. Number, sector(s) and level(s) of projects or interventions in separate fields of monitoring plan 1.2. Number 2.1.1. Number of staff (male/female) of targeted institutions: a. Obtain baseline information: total number of staff from targeted institutions b. Define target 2.1.2. Number of staff (male/female) of targeted institutions: a. Obtain baseline information: total number of staff from targeted institutions b. Define target: needs to be defined by project proponents 2.2.1. Quantitative: Percentage (includes women – and other vulnerable groups – and men). Qualitative: Adequacy: include direct analysis of major areas; adequacy/effectiveness of systems or analysis of perceptions of populations and institutions. 2.2.2. Number (broken down by gender and, if possible, by vulnerable groups defined in the area of intervention) of people 3.1. Number and type (in separate columns) at local level. 3.2. Number 4.1. Number and type 4. 2. Number and type (entered in separate columns) 5. Number of interventions by type of natural asset and intervention 6.1. Number and type (in separate columns of monitoring plan) 6.2. Income sources per household; description of income source and number of households. 7.1. Number/Sector 7.2. Number; Effectiveness (see previous indicator) through enforcement level.