## Overview
Project Performance Report (PPR)
| Period of Report (Dates) | 22.05.2014 - 22.05.2015
| Project Title: | Addressing climate change risks to farming systems in Turkmenistan at national and community level
| Project Summary: | The proposed project aims to overcome barriers to addressing immediate and long term adaptation needs in the water sector in Turkmenistan in order to achieve greater water efficiency and productivity under climate change induced aridification. The project will therefore aim to strengthen water management practices at national and local levels in response to climate change induced water scarcity risks to local farming systems in Turkmenistan. The project takes a comprehensive approach towards achieving this objective by encompassing national level water policy and local community level action to improve water efficiency and supply services.
|  |  | Countries | Project Type: |  | GEF Focal Area: | GEF 4 Focal Areas | GEF 2 / 3 Operational Programme: | Overall Rating of the project in the evaluation by the project evaluator: | GEF-4 Focal Area Strategic Program: | GEF-3 Focal Area Strategic Program:
| Database Number: | PIMS #: 4450; Project Number: 00074953 | Afghanistan | FP | Yes | Biodiversity | 1 | 1 | U | BD-SP1-PA Financing | 1: Arid & semi-arid ecosystems
Implementing Entity (IE) [name]: |  | UNDP | Albania | MSP | No | Climate Change Adaptation | 2 | 2 | S | BD-SP2-Marine PA | 2: Coastal, marine & freshwater ecosystems
| Type of IE: | Multilateral Implementing Entity | Algeria | EA |  | Climate Change Mitigation | 3 | 3 | MU | BD-SP3-PA Networks | 3: Forest ecosystems
| Country(ies): | Turkmenistan | Angola |  |  | International Waters | 5 | 5 | Good | BD-SP5-Markets | 13: Conservation and Sustainable Use of Biological Diversity Important to Agriculture
Relevant Geographic Points (i.e. cities, villages, bodies of water): |  | The project is implemented in regions that represent typical conditions of three major agro-ecological zones in Turkmenistan—that is, mountain (south-western part of Central Kopetdag Mountains, closer to the border with Iran), desert (Karakum region that is located in the Central Karakum Desert), and oasis (Sakar-chaga is located in the north-western part of Mary Velayat in the delta of Murgab River) systems. | Argentina |  |  | Multiple Focal Area |  |  |  | BD-SP7-Invasive Alien Species(IAS) | 6: Promoting the adoption of renewable energy by removing barriers and reducing implementation costs
[8 empty] | CC-SP2- Industrial EE | 8: Waterbody based operational program
| Project Milestones | [6 empty] | CC-SP3-RE,CC-SP4-Biomass | 9: Integrated Land and Water multiple focal area
| Milestone |  | Bahamas | [6 empty] | CC-SP5-Transport | 10: Contaminants based operational program
AFB Approval Date: |  | 2011-11-03
IE-AFB Agreement Signature Date: |  | 2011-12-08 | [6 empty] | CC-SP6-LULUCF | 12: Integrated Ecosystem Management
Start of Project/Programme: |  | 2011-10-01 | [6 empty] | Cross cutting capacity building | 14: Persistent Organic Pollutants
Mid-term Review Date (if planned): |  | MTE Mission, September 29 – October 3rd, 2014
| Terminal Evaluation Date: | 2016-07-01
|  | List documents/ reports/ brochures / articles that have been prepared about the project. | Cyprus
|  | 1. Articles published on UNDP Country Office website - Building a water user partnership for better water management, 10 Jan 2014 (www.tm.undp.org; http://www.undp-alm.org/projects/af-turkmenistan); - UNDP projects boosts efforts in the field of climate change and water management in Turkmenistan, 14 Apr 2014 (www.tm.undp.org; http://www.undp-alm.org/projects/af-turkmenistan); - Water management by water users, 24 Apr 2014 (www.tm.undp.org; http://www.undp-alm.org/projects/af-turkmenistan) - Locals discuss findings of the assessment of socio-economic impacts of climate change, 07 May 2014 (www.tm.undp.org; http://www.undp-alm.org/projects/af-turkmenistan); - Local communities mobilized to achieve greater water use efficiency and increase resilience against climate change impacts, 16 Jun 2014 (www.tm.undp.org; http://www.undp-alm.org/projects/af-turkmenistan) - Innovative methodology of calculating tariffs for irrigation water supply services to local farmers introduced to save water use, 03 Jul 2014 (www.tm.undp.org; http://www.undp-alm.org/projects/af-turkmenistan) - Turkmenistan introduced innovative technologies for sustainable water management in the farming system, 04 Jul 2014 (www.tm.undp.org; http://www.undp-alm.org/projects/af-turkmenistan) - Strengthening legal framework for rational use of water resources and community-level water management, 14 Jul 2014 (www.tm.undp.org; http://www.undp-alm.org/projects/af-turkmenistan) - Boosting traditional water-saving techniques for resilience of local communities in the Karakum desert, 13 Aug 2014 (www.tm.undp.org; http://www.undp-alm.org/projects/af-turkmenistan) - Local farmers design adaptation strategies for sustainable water use, 11 Nov 2014 (www.tm.undp.org; http://www.undp-alm.org/projects/af-turkmenistan) - Coordination of joint plans for sustainable water management, 08 Apr 2015 (www.tm.undp.org; http://www.undp-alm.org/projects/af-turkmenistan) - Adaptation Technologies 101: Intro to climate resilient use of water resources by local communities in Turkmenistan (http://www.undp-alm.org/projects/af-turkmenistan) - Creating shelterbelts - basis for stable yields of agricultural crops, 28 April, 2015 (www.tm.undp.org, http://www.undp-alm.org/projects/af-turkmenistan) - UNDP facilitates cooperation between experts from Turkmenistan and Kazakhstan on sustainable land and water management in the context of climate change, 28-29 April, 2015 (www.tm.undp.org) - Seminar on socio-economic assessment of the climate change impacts on agriculture and water management in Turkmenistan, 23 Jun 2015 (www.tm.undp.org, http://www.undp-alm.org/projects/af-turkmenistan) - Dissemination of knowledge in the field of resource-saving technologies for the rational use of water, 23 Jun 2015 (www.tm.undp.org, http://www.undp-alm.org/projects/af-turkmenistan) 2. Book on "Natural pastures and development of distant pastures in Turkmenistan" 3. Mid-term Evaluation Report, December 8, 2014 4. AF Financial Audit report. 5. International Water Forum in Turkmenistan, 2-3 April, 2014 - Collection of scientific thesises (3 thesises); | Czech Republic
List the Website address (URL) of project. |  |  | Democratic People's Republic of Korea
|  | http://www.undp-alm.org/projects/af-turkmenistan; http://www.tm.undp.org/content/turkmenistan/en/home/operations/projects/environment_and_energy/addressing-climate-change-risks-to-farming-systems-in-turkmenist.html | Democratic Republic of the Congo
Denmark
| Project contacts: |  | Djibouti
National Project Manager/Coordinator |  |  | Dominica
| Name: | Ahmet Shadurdiev | Dominican Republic
| Email: | ahmed.shadurdyev@undp.org | Ecuador
| Date: | 2015-04-21 | Egypt
| Government DA |  | El Salvador
| Name: | Mr. Muhammet Durikov, Director of the National Institute of Deserts, Flora and Fauna of Turkmenistan under the Ministry of Nature Protection of Turkmenistan | Equatoral Guinea
| Email: | durikov@mail.ru | Eritrea
| Date: | 2015-04-21 | Estonia
| Implementing Entity |  | Ethiopia
| Name: | Mr. Rovshen Nurmuhamedov, UNDP Programme Officer; Mr. Yusuke Taishi, UNDP Regional Technical Advisor | Fiji
| Email: | rovshen.nurmuhamedov@undp.org; yusuke.taishi@undp.org | Finland
| Date: | 2015-04-21 | France
| Executing Agency |  | Gambia
| Name: | Mr. Muhammet Durikov, Director of the National Institute of Deserts, Flora and Fauna of Turkmenistan under the Ministry of Nature Protection of Turkmenistan | Georgia
| Email: | durikov@mail.ru | Germany
| Date: | 2015-04-21 | Ghana
| Executing Agency |  | Greece
| Name: |  | Grenada
| Email: |  | Guatemala
| Date: |  | Guinea
| Executing Agency |  | Guinea Bissau
| Name: |  | Guyana
| Email: |  | Haiti
| Date: |  | Honduras
Hungary
Iceland
India
Indonesia
Iran (Islamic Republic of)
Iraq
Ireland
Israel
Italy
Jamaica
Japan
Jordan
Kazakhstan
Kenya
Kiribati
Kuwait
Kyrgyzstan
Lao People’s Democratic Republic
Latvia
Lebanon
Lesotho
Liberia
Libyan Arab Jamahiriya
Liechtenstein
Lithuania
Luxembourg
Madagascar
Malawi
Malaysia
Maldives
Mali
Malta
Marshall Islands
Mauritania
Mauritius
Mexico
Micronesia, Federated States of
Monaco
Mongolia
Montenegro
Morocco
Mozambique
Myanmar
Namibia
Nauru
Nepal
Netherlands
New Zealand
Nicaragua
Niger
Nigeria
Norway
Oman
Pakistan
Palau
Panama
Papua New Guinea
Paraguay
Peru
Philippines
Poland
Portugal
Qatar
Republic of Korea
Republic of Moldova
Romania
Russian Federation
Rwanda
Saint Kitts and Nevis
Saint Lucia
Saint Vincent and the Grenadines
Samoa
San Marino
Sao Tome and Principe
Saudi Arabia
Senegal
Serbia
Seychelles
Sierra Leone
Singapore
Slovakia
Slovenia
Solomon Islands
Somalia
South Africa
Spain
Sri Lanka
Sudan
Suriname
Swaziland
Sweden
Switzerland
Syrian Arab Republic
Tajikistan
Thailand
The former Yugoslav Republic of Macedonia
Timor-Leste
Togo
Tonga
Trinidad and Tobago
Tunisia
Turkey
Turkmenistan
Tuvalu
Uganda
Ukraine
United Arab Emirates
United Kingdom of Great Britain and Northern Ireland
United Republic of Tanzania
United States of America
Uruguay
Uzbekistan
Vanuatu
Venezuela, Bolivarian Republic of
Viet Nam
Yemen
Zambia
Zimbabwe

## FinancialData
Financial information: cumulative from project start to [May 2015]
DISBURSEMENT OF AF GRANT FUNDS
How much of the total AF grant as noted in Project Document plus any project preparation grant has been spent to date?
Estimated cumulative total disbursement as of [30 May 2015] | 1368317
Add any comments on AF Grant Funds. (word limit=200) | The Project has received received $1,855,000 from the AF so far in 3 tranches. The cumulative expenditures so far is $1,368,317. Total cash to be disburses till 31-Dec-2015: $2,160,256. Expected cash deficit for 2015: $-305,256. Additional cash needed from AF in 2-3 months: $635,000. This amount is TRANCHE-4, which was due to be transferred in Oct.2013. After receiving the Tranche-4, the total received amount will comprise in USD: $2,490,000. There will be only TRANCHE-5 left ($210,000), which will be requested to be transferred in May 2016.
EXPENDITURE DATA
List ouput and corresponding amount spent for the current reporting period | ITEM / ACTIVITY / ACTION | AMOUNT
| Output 1.1. Socio-economic impact of climate change on water availability costed and documented, including cost-benefit analysis of adaptation measures | 27649
| Output 1.2: A package of modifications in the water code, with particular focus on communal water management; and financial incentives for water efficiency (eg differentiated and progressive tariff) developed; | 65465
| Output 2.1: At least 4,000 agri-pastoralists of the Nohur mountainous region develop and implement water harvesting and saving techniques (such as slope terracing, small rainwater collection dams, contour and stone bunds, planting pits, tillage, mulching) to improve soil moisture levels; | 205804
| Output 2.2: At least 8,000 farmers implement community-based well and watering point management measures, including sand fixation and introduction of drought resistant traditional grain varieties in the Karakum desert region | 203296
| Output 2.3. At least 20,000 farmers in the Sakarchaga area benefit from improved irrigation services through the introduction of canal level, localized management practice. | 193333.31
| Output 3.1. Mandates and institutional functions of local associations strengthened to improve local water services that are more resilient to increasing water stress and benefit for at least 40% of farmers and pastoralists | 141612
| Output 3.2: Based on VCA assessments, community-based adaptation plans with particular focus on water delivery services designed and implemented through the government's social development programmes with direct engagement of at least 40% of farmers and pastoralists | 10011
| Output 3.3: Investment in at least four water management projects led by Water User Associations on the basis of the above VCA assessment, resulting in improved quality of agricultural water supply and strengthened WUA mandate and profile | 6014
| Output 3.4. Lessons learned on community-based adaptation options in various agro-climatic conditions of Turkmenistan codified and disseminated (eg through ALM and other networks. | 27787
| Output 4 (May 2014 - May 2015) / Project Management | 144809.58
| TOTAL | 1025780.89
PLANNED EXPENDITURE SCHEDULE
List outputs planned and corresponding projected cost for the upcoming reporting period | ITEM / ACTIVITY / ACTION | PROJECTED COST | Est. Completion Date
| Output 1.1. Socio-economic impact of climate change on water availability costed and documented, including cost-benefit analysis of adaptation measures | 2536.5 | 2016-05-31
| Output 1.2: A package of modifications in the water code, with particular focus on communal water management; and financial incentives for water efficiency (eg differentiated and progressive tariff) developed; | 29816 | 2016-05-31
| Output 2.1: At least 4,000 agri-pastoralists of the Nohur mountainous region develop and implement water harvesting and saving techniques (such as slope terracing, small rainwater collection dams, contour and stone bunds, planting pits, tillage, mulching) to improve soil moisture levels; | 124723 | 2016-05-31
| Output 2.2: At least 8,000 farmers implement community-based well and watering point management measures, including sand fixation and introduction of drought resistant traditional grain varieties in the Karakum desert region | 109786 | 2016-05-31
| Output 2.3. At least 20,000 farmers in the Sakarchaga area benefit from improved irrigation services through the introduction of canal level, localized management practice. | 81944.5 | 2016-05-31
| Output 3.1. Mandates and institutional functions of local associations strengthened to improve local water services that are more resilient to increasing water stress and benefit for at least 40% of farmers and pastoralists | 27481.5 | 2016-05-31
| Output 3.2: Based on VCA assessments, community-based adaptation plans with particular focus on water delivery services designed and implemented through the government's social development programmes with direct engagement of at least 40% of farmers and pastoralists | 2814 | 2016-05-31
| Output 3.3: Investment in at least four water management projects led by Water User Associations on the basis of the above VCA assessment, resulting in improved quality of agricultural water supply and strengthened WUA mandate and profile | 3506 | 2016-05-31
| Output 3.4. Lessons learned on community-based adaptation options in various agro-climatic conditions of Turkmenistan codified and disseminated (eg through ALM and other networks. | 16544.5 | 2016-05-31
| Output 4 (May 2014 - May 2015) / Project Management | 28562.5 | 2016-05-31
| TOTAL | 427714.5
ACTUAL CO-FINANCING (If the MTR or TE have not been undertaken this reporting period, DO NOT report on actual co-financing.)
How much of the total co-financing as committed in the Project Document has actually been realized? | In the reporting period the project team mobilized in total US$ 311,718. This includes US$ 140,000 from Water Design Institute, which agreed to cover costs of design and reconstruction of 35 km Inter-Farm Collector Canal in Sakarchaga Project Region, which was part of the planned Project community investment activities; co-financing from the UNDP supported Climate Risk Management in Turkmenistan project in the amount of US$ 85,718.42 for implementation of adaptation measures in pilot regions (laser leveler equipment with scrapper, pre-works before laser planning, soil-lab and trainings, water regulating devices for proper distribution of scarce irrigation water); Co-financing from beneficiary communities in the form of labor amounted at US$80,000, including US$ 33,000 in Nohur region, US$ 10,000 in Sakarchaga region and US$ 37,000 in Karakum project region.
Estimated cumulative actual co-financing as verified during Mid-term Review (MTR) or Terminal Evaluation (TE). | 346000
Add any comments on actual co-financing in particular any issues related to the realization of in-kind, grant, credits, loans, equity, non-grant instruments and other types of co-financing. (word limit=200) | The MTR (as of December 2014) attests that US$346,000 co-financing has been contributed by the government and beneficiaries at the community-level although no specific commitments were included in the original project document. The breakdown of the co-financing is presented below: - UNDP-funded Climate Risk Management Project: $28,000 - Community in-kind co-financing: $178,000 - Ministry of Water Economy: $140,000

## Procurement
PROCUREMENT DATA
Please provide information for all contracts over $2,500 USD
Please provide the number of contracts under $2,500, signed during this reporting period: |  |  |  | 5
LIST OF CONTRACTS
List all contracts related to the project/program with signature dates
Contract Type | Agency / Contracted party | Contract Value/Amount (USD) | Signiture Date | Payment to Date (USD) | Remaining Balance (USD) | Pposition/ brief description | Comments
IC 2013-068-01 (PO7958) |  | 26000 | 2013-07-29 | 31/10/2013 - 15,600 05/12/2013 - 10,400 | 0 | International adviser on water and economic instrument. The role of the consultant -to bring best international practice on instruments to stimulate water efficiency.
IC 2013-070-01 (PO7960) |  | 29750 | 2013-07-31 | 31/10/2013 - 5,950 27/11/2013 - 11,900 07/12/2013 - 11,900 | 0 | International adviser on soci-economic assessment of climatechange impact. The role of the consultant -to provide evidence and analysis on the economics of climate change in water sector in Turkmenistan.
IC 2013_033_01 (PO7925) |  | 7000 | 2013-05-27 | 10/09//2013 - 2,800 27/11/2013 - 4,200 | 0 | National consultant on strategic and institutional issues
IC 2013-036-01 (PO 7916) |  | 7000 | 2013-05-29 | 10/09//2013 - 2,800 27/11/2013 - 4,200 | 0 | National consultant on water management and agriculture
SC 2014-115-03 |  | 25752 | 2014-06-05 | 28 date of each month - 2,074 28 date of each month - 2,146 | 2146 | Project Manager. Leads the project team in the day-to-day implementation of the project. | Current contract 08 May 2014 - 7 May 2015
SC 2013-025-03 SC 2014-124-04 |  | 19272 | 2014-07-01 | 28 date of each month - 1,606 | 1606 | National Technical Adviser. Provides technical recommendations on strategic and technical issues and coordinates the project with national partners. | xxx passed away in April 2015
SC 2012-091-01 SC 2013 -050-02 SC 2014-008-03 SC 2014-100-04 SC 2015-002-06 |  | 1648 | 29/11/2012 29/11/2013 31/01/2014 01/05/2014 27/02/2015 | 28 date of each month- 824 | 0 | Local Project Coordinator in Nohur region. Provides day-to-day support and assistance to the project in the implementation and administration of activities in the project area, coordinates with local administration and is responsible for community mobilization.
SC 2012-092-01 SC 2013-051-02 SC 2014-007-03 SC 2014-101-04 SC 2015-001-06 |  | 1648 | 29/11/2012 29/11/2013 31/01/2014 01/05/2014 27/02/2015 | 28 date of each month - 824 | 0 | Local Project Coordinator in Karakum region. responsibilities as above
SC 2012-093-01 SC 2013-052-02 SC 2014-005-03 SC 2015-003-06 |  | 1716 | 29/11/2012 29/11/2013 31/01/2014 27/02/2015 | 28 date of each month - 858 | 0 | Local Project Coordinator in Sakarchaga region. responsibilities as above
SC 2012-106-04 SC 2013-022-05 SC2013-033-06 SC 2013-097-07 SC 2014-004-08 SC 2014-106-09 SC 2014-153-10 |  | 10716 | 24/12/2012 26/06/2013 31/07/2013 30/12/2013 31/01/2014 30/04/2014 01/01/2015 | 28 date of each month - 893 | 0 | Finance Assistant. Provides Admin/Finance assistance. | The contract SC 2012-106-04 for the period of Jan - June 2013. xxxx resigned from the job on 24-Feb-2015. Her replacement - new Finance Assistant is being recruited.
SC 2013-037-01 SC2013-078-02 SC 2014-010-03 SC 2014-098-04 SC 2014-155-05 |  | 5781.6 | 26/08/2013 27/12/2013 30/01/2014 30/04/2014 01/01/2015 | 28 date of each month - 481.8 | 3854.4 | Head of Project Implementation Unit. Responsible for procurement processes for the project and ensures that the project receives quality support services (HR, admin) from the project implementation unit | 30% of salary is financed by the AF project as the Head of PIU salary is proportionately shared by Env.Portfolio projects
SC 2013-003-03 SC 203-074-04 SC 2014-005-05 SC 2014-103-06 SC 2014-156-07 |  | 5964 | 04/02/2013 27/12/2013 30/01/2014 30/04/2014 | 28 date of each month - 491.30 SC 2014-103-06: 28 date of each month - 710.00 | 3976 | Driver-clerk. Provides driving services | 70% of salary is financed by AF project 30% of salary is financed by another project
IC 2013-017-01 |  | 4968 | 26/03/2013 | 01/07/2013 - 670 14/08/2013 - 1,814 27/11/2013 - 2,484 | 0 | Additional driver provided transportation services to Nohur and Karakum for project staff
IC 2013-076-01 (PO 7970) |  | 15000 | 21/08/2013 | 12/09/2013 - 1,500 27/11/2013- 4,500 28/11/2013 -3,000 | 6000 | National expert on sustainable land manageemnt in the context of climate change.
|  | 18000 | 2015-05-04 | 0 | 18000 | National expert on sustainable land manageemnt in the context of climate change.
IC 2013-072-01 (PO 7976) |  | 3600 | 2013-08-06 | 30/10/2013 - 1,440 29/04/2014 - 2,160 | 0 | Gardener in Karakum project region
|  | 4000 | 2015-05-04 | 0 | 4000 | Gardener in Karakum project region
IC 2013-071-01 (PO 7978) |  | 3600 | 2013-08-12 | 30/10/2013 - 1,440 29/04/2014 - 2,160 | 0 | Gardener in Sakarchaga project region
|  | 4000 | 2015-05-04 | 0 | 4000 | Gardener in Sakarchaga project region
IC 2013-073-01 (PO 7977) |  | 3600 | 2013-08-12 | 30/10/2013 - 1,440 29/04/2014 - 2,160 | 0 | Gardener in Nohur project region
|  | 4500 | 2015-05-04 | 0 | 4500 | Gardener in Nohur project region
IC 2013-079-01 |  | 1700 | 29/08/2013 | 30/10/2013 - 1,360 27/11/2013 - 340 | 0 | Engineer on calculation of repairs works provided define work overload and compile cost sheet on selection of nessecary materials and methods of construction works for 3 project regions. Compose work schedule on timeframe for repair work
IC 2013-086-01 |  | 2704.44 | 12/09/2013 | 21/10/2013 - 2,704.44 | 0 | Translation/Editing
IC 2015-013-01 |  | 5000 | 11-Mar-2015 | 0 | 5000 | Translation/Editing
IC 2013-030-03 |  | 1105.82 | 16/05/2013 | 11/10/2013 - 450.00 06/09/2013 - 308.39 05/06/2013 - 347.43 | 0 | Translation/Editing
IC 2013-026-01 |  | 1000 | 16/02/2013 | 05/06/2013 - 1000.00 | 0 | Designer, including the following duties and responsibilities: a). Preparation of design, layout, and any other designs for the publication in accordance with the UNDP Graphic Standards; b). Edition of photo materials provided c). Ensure all corrections have been inserted; d). Create PDF and/or in other related graphical formats, from final electronic file; f). Submit all final files to Programme Specialist on CD or any other data bearer.
IC 2013-019-01 |  | 1064.8 | 27/03/2013 | 25/04/2013 - 96.80 23/05/2013 - 96.80 28/06/2013 - 96.80 23/07/2013 - 96.80 23/08/2013 - 96.80 26/09/2013 - 96.80 08/12/2013 - 96.80 09/12/2013 - 96.80 28/02/2014 - 193.60 26/03/2014 - 96.80 | 0 | Office Cleaner | Monthly Salary of 242.00 USD was covered by three Projects in the following breakdown: IC 2013-019-01: PAS 30% - 72.60 USD AF 40% - 96.80 USD BSAP 30% - 72.60 USD
IC 2014-063-01 |  | 1377.6 | 14/05/2014 | June 2014 - 114.80 July 2014 - 114.80 Aug 2014 - 114.80 Sep 2014 - 114.80 Oct 2014 - 114.80 Nov 2014 - 114.80 Dec 2014 - 114.80 Jan 2015 - 114.80 Feb 2015 - 114.80 Mar 2015 - 114.80 | 229.6 | Office Cleaner | Monthly Salary of 287.00 AF 40% - 114.80 USD
IC2013_059_01 (PO 7936) |  | 2043 | 20/06/2013 | 22/08/2013 - 817 05/09/2013 - 1,226 | 0 | Trainer on community mobilization
IC 2013-103-02 (PO 8106) |  | 12183 | 29/11/2013 | 28/03/2014 - 2,436 22/04/2014 - 2,436 | 7311 | Trainer on community mobilizaion provide the adapting trainer modules for each pilot region
|  | 11500 | 2015-05-04 | 0 | 0 | Trainer on community mobilizaion provide the adapting trainer modules for each pilot region
RLA/TKM003-2013 (PO-7927) |  | 80000 | 23/05/2013 | 12/05/2013 - 40,033 12/07/2013 - 11,765 | 28202 | One Expert working for Oxford Consulting Services was hired with RLA. This Expert rendered CTA Services, including providing suport in strengthening policy and institutional capacity; commuity-based adaptation initiatives; community system for water delivery; operational functions; assistance in planning, monitoring and evaluation.
IC 2014-048-01 |  | 12630 | 21/04/2014 | 0 | 12630 | National expert on valuation of socio economic efficiency of investment activities for pilot regions and determining economic factors for functionning of the Water Users Association.
|  | 18000 | 2015-05-04 | 0 | 18000 | National expert on valuation of socio economic efficiency of investment activities for pilot regions and determining economic factors for functionning of the Water Users Association.
IC 2014-047-01 |  | 22170 | 31/03/2014 | 0 | 22170 | Irrigation specialist
IC 2014-043-02 PO 8108 |  | 10700 | 28/03/2014 | 0 | 10700 | National expert on determining legal basis for functioning of Association of water users
|  | 14000 | 2015-05-04 | 0 | 14000 | National expert on determining legal basis for functioning of Association of water users
IC 2014-046-01 |  | 21620 | 2014-01-04 | 0 | 21620 | Water infsrastructure engineer (Agriculture sector)
IC 2014-067-01 |  | 29500 | 2014-04-15 | 0 | 29500 | International adviser on water and economic instrument. The role of the consultant -to bring best international practice on instruments to stimulate water efficiency.
SC 2014-117-01 |  | 10296 | 2014-05-22 | 0 | 10296 | Field Technical Assistant. Under the Project Manager key focus will be on supporting activities implemented with local communities under Component 2 and 3.
BIDS
List all bids for each contact signed with date of open call and winning bid
CONTRACT & Procurement Method | Submitted Bids | Bid Amount (USD) | Winning Bid Amount (USD) | Selection Justification for the Winner
Tender RFQ-TKM-006-2013 Procurement of water regulation device 16 pcs PO 7999 |  | 16210.53 | 16210.53 | Procurement was made for water regulation device 16 pcs with delivery to Sakarchaga District. Selection was based on lowest price with timely delivery.
24070.18
Tender RFQ-TKM-008-2013 Procurement of construction materials PO 8000 |  | 44441.02 | 29989.12 | Procurement was made for construction materials. Selection was based on lowest price with timely delivery.
31115.44
29989.12
Tender Micropurchasing/ Canvassing Procurement of construction materials for Sakarchaga project office PO 8047 |  | 4784.74 | 4784.74 | Construction materials were purchased for lowest price and timely delivery.
5518.53
Tender Micropurchasing/ Canvassing Procurement of construction materials for Karakum project office PO 8048 |  | 3781.23 | 3781.23 | The offered equipment meets requester’s requirements. The price is competitive and lowest; the vendor provides 1-year warranty on parts and services.
4500.386
Tender RFQ-TKM-004-2013 Procurement of Archa 627pcs for Nohur project region PO 8014 |  | Unit Price $14.91 USD Total: 9,350.00 | 9350 | Selection was based on lowest price with timely delivery, good stand (color, plant health) and packing, no damages and good root system, plant height.
Unit Price $15.30 USD
Tender RFQ-TKM-004-2013 Procurement of Archa 623pcs for Nohur project region PO 8013 |  | Unit Price $14.04 USD Total: $8,743.86 | 8743.86 | Selection was based on lowest price with timely delivery, good stand (color, plant health) and packing, no damages and good root system, plant height The reason for purchasing only 623 pcs was that available quantity was only 623 pcs. Total quantity needed as per RFQ-TKM-004-2013 was 1250 pcs, and remaining was bought from the Entrepreneur xxx as per PO#8014 for a bit higher unit price.
Unit Price $15.30 USD
Tender Micropurchasing/ Canvassing Procurement of winter tires and discs PO8037 (03.12.2013) |  | 3415.78 | 3415.78 | Procurement of winter tires and discs for project vehicle
3587.72
3589.47
Tender RFQ-TKM-006-2014 PO8153 (07.05.2014) |  | 23638.9263 | 23638.9263 | Procurement of Company Service for Construction of 5 dams with water reservoirs and Repairment of 2 dams with water reservoirs (RFQ-TKM-006-2014)
26116.84
82100
Repair of the existing drip irrigation system in Nohur (RFQ-TKM-011-2014, PO-8165) |  | 4978.95 | 4978.95 | Procurement of Company Service for Repair of the existing drip irrigation system by procurement of 33000pcs of drippers, Nohur
5775
6892.98
8900
11115.79
12421.05
18526.32
22578.95
25473.68
27720
31378.95
32421.05
Grant Agreement for Adaptation Initiatives in Karakum |  | 79744.43 | 79744.43 | Procurement of Services of Farmers Union for Construction of 7 new wells, Construction of 11 new sardobs, Repair the existing 6 wells, Repair the existing 5 Kaks, repair of 4 sardobs, Works on sand dune fixation, Karakum
Repair of the existing drip irrigation system in Nohur (RFQ-TKM-010-2014, PO-8188) |  | 23454.63 | 23454.63 | Procurement of Company Service for materials supply for a basin 400m3 and springs constructions in Nohur
25976.67
25102.37
34187.72
Materials supply for construction of 15 pits for vermicomposting in Nohur (RFQ-TKM-012-2014, PO-8186) |  | 17684.21 | 19923.68 | Procurement of Company Service for materials supply for construction of 15 pits for vermicomposting (biohumus) in Nohur Project Region NOTE: The Vendor Mr. xxx provided a partial quote, by quoting only for the Lot-1
19923.68
Water regulating 5 devices installation in Sakarchage (RFQ-TKM-013-2014, PO-8177) |  | 16438.6 | 16438.6 | Procurement of Company Service for installation works of 5 water regulating devices (check-gates) in Sakarchaga Project Region
18101.75
Construction materials supply for Grant Activities in Karakum (RFQ-TKM-018-2014, PO-8200) |  | 90762.11 | 90762.11 | Procurement of construction materials supply for wells and sardobs construction in Karakum Project Region
122896.14
96835.58
Construction materials supply for sand dune fixation in Karakum (RFQ-TKM-019-2014, PO-8203) |  | 39312.28 | 39312.28 | Procurement of construction materials supply for sand dune fixation in Karakum Project Region
45333.33
71549.12
170455.44
406814.04
Buldozer Service for 3 Reservoirs in Nohur - by the Company Galkan Gala (RFQ-TKM-024-2014, PO-8219) |  | 7752.2982 | 7752.2982 | Direct Contracting modality was applied.
Installation of 7 water regulating devices in Sakarchaga - by the Company Galkan Gala (RFQ-TKM-027-2014, PO-8249) |  | 21898.2456 | 21898.2456 | Direct Contracting modality was applied.
Water regulating 3 devices Q = 0,8 м3/с installation in Sakarchage (RFQ-TKM-028-2014, PO-8251) |  | 14200 | 14200 | Procurement of Company Service for installation works of 3 water regulating devices (check-gates) Q = 0,8 м3/с in Sakarchaga Project Region
14900
Company service for 6 km drainage collector cleaning in Sakarchaga (RFQ-TKM-029-2014, PO-8274) |  | 81600 | 15157.8947 | Company service for 6 km drainage collector cleaning in Sakarchaga Project Region
17017.5439
15157.8947
37894.7368
15700
20 ha land reclamation in Sakarchaga - by the Company Galkan Gala (RFQ-TKM-004-2015) |  | 19964.74 | 19964.74 | Direct Contracting modality was applied.
6.8 km drainage collector cleaning in Sakarchaga - by the State Company "Mary yer-suw gurlushyk" (RFQ-TKM-006-2015) |  | 17178.9474 | 17178.9474 | Direct Contracting modality was applied.

## Risk Assesment
RISK ASSESMENT
IDENTIFIED RISKS
List all Risks identified in project preparation phase and what steps are being taken to mitigate them
Identified Risk | Current Status | Steps Taken to Mitigate Risk
The special law on “Water Users Association”, which is a part of Water Code, has not been approved by the Parliament. This weakens WUA's legal status and its authority for water resources management. | Medium | Until the law is enacted, the project is continuing its support to WUA as a voluntary organization which is permitted under the Dayhan farm structure. In addition, the project National expert on legal issues is regularly in contact with the head of the Mejlis (Parliament) of the Environment department. These issues were discussed in detail during the seminar conducted on June 9, 2015, where they promised to convey their comments and amendments to the UNDP Turkmenistan for further analysis. Some laws are under consideration in the Mejlis (Parliament) of Turkmenistan in the working group.
Weak interdepartmental interaction and coordination create obstacles for joint management of water and land resources | Low | The Project Board was established that consists of representatives of the Ministry of Nature Protection, Ministry of Agriculture, Ministry of Water Economy, Ministry of Finance, Parlament, the National Institute of Deserts, Flora and Fauna, Ministry of Economy and etc. – interested ministries and departments, local authorities and local communities. The Project Board meetings contribute to better interdepartmental interaction and coordination. During the reporting period, communication and coordination on issues of communication and connections/relations with the above mentioned ministries and departments has improved significantly thanks to the efforts and friendly AF project team
No awareness of water users about climate change and its impacts on water resources | Low | A series of seminars, round tables, workshops with local communities and government officials were conducted, which increased awareness of water users about climate change and its impacts on water resources. The knowledge capacity of local communities in all three project regions was significantly strengthened thanks to series of seminars and trainings organized on general topics related to climate change and concepts of Water Users Associations (WUAs), and etc. Over the past period thanks to the efforts of AF team and conducting of trainings, seminars and meetings with local communities and local authorities the project team succeeded to strengthen their capacity of knowledge in the field of sustainable water and land management in the context of climate change.
Poor motivation of water users to participate in decision making | Low | The adaptation measures plan (investment plan) for each project region increased the interest of local communities. In addition, a series of training events also contributed to increasing the motivation of water users to participate in decision making process. They expressed interest in providing contribution to the project in each pilot region in a form of labor. In the Nohur project region the estimated contribution is $34,500; in Sakarchaga project region - $31,580; in Karakum project region - $111,920. Local communities formed groups of water users that will participate in decision making. A significant part of the adaptation measures developed on basis of local communities needs have already been implemented in 2014 for all three pilot regions. In addition, during the implementation of adaptation measures representatives of local communities both men and women (60% and 40%, respectively) active participated. Thanks to the introduction of adaptation measures and regular meetings with local communities in three pilot regions their motivation in decision-making and participation in the implementation of project activities has increased substantially. After the implementation of adaptation measures and income of local communities have increased by an average of 15-20%. As an example you can see 1) the reconstruction of drip irrigation systems, i.e. income received from yields of vegetables and fruits. 2) The use of laser leveling in the pilot region Sakarchaga increased wheat yield by 20-30%.
Water users skepticism towards the new technologies and innovations, reluctance to give up unsustainable practices | Low | The seminars and workshops included the issues related to the introduction and explanation of advantages of new technologies compared to the traditional /conventional technologies. The representatives of all three project regions were directly acquainted with the modern/innovative technologies (for instance: the use of drip irrigation systems, laser leveling, etc.). The investment plans for each project region were developed according to the identified local needs of communities, which included the modern/innovative investment technologies and projects. To ensure wider outreach, UNDP Turkmenistan website, ALM website and national center newspaper regularly published articles on effective implementation of new innovative technologies. Two local project coordinators had a study tour to Israel "Innovation in agriculture - Israel technologies". They have conducted the trainings for local communities in each project region. Moreover, representatives of four communities from other regions participated in Nohur trainings. The local coordinators are now better able to promote best available international practices among local population. Received a positive and effective results of implemented adaptation measures in all three pilot regions has significantly expanded the number of participating and supporting the continuation of performing of the developed investment plan based on the local needs of population. In addition, the introduction of innovative technologies (such as drip irrigation systems, laser leveling, etc.) allowed to increase the income of the local population, and accordingly their level of life has been improved.
The imperfections of the water infrastructure for the implementation of sustainable water management | Medium | To improve the infrastructure of the water sector the project activities included the activities such as construction and repair of water regulating devices, construction and reconstruction of collector drainage systems, construction and reconstruction of dams to collect surface runoff water etc. The received efficiency of the implemented adaptation measures (please see the project indicators sheet, where indicated the whole list of implemented adaptation measures). That greatly strengthened institutional linkages between ministries and agencies on the sustainable management of water and land resources. In addition, an exchange of the experience with the Central Asian countries in particular, the visit of a delegation of experts and specialists from Kazakhstan in the framework of development of cooperation "South-South" on Climate Change has allowed to familiriazed and to aim the prospects for the introduction of new technologies.
Lack of services and soil and water surveillance | Low | The prepared documents by WUA and WUG envisaged to assign their responsibilities on improvement of services. In the project region Sakarchaga the soil lab was procured by the UNDP CRM in Turkmenistan project. The risk is not relevant and will be recommended to be removed following the Mid-term evaluation. Mid-term evaluation conducted by the international auditor Mr. Josh Brann showed, that the success of the project work in this area that allows us to delete this risk.
Lack or low level of agricultural consulting services | Low | Leading national and international experts conducted seminars, trainings and workshops including field practical trips where they gave consultations related to agricultural issues. Over the past period a large number of trainings to increase knowledge of local communities in the field of provision of consulting services were carried out. As a result of effective work of the project team awareness and consulting services to local farmers, tenants and land owners has strengthened.
Due to staff turnover at the target Ministries the trained staff may leave for other job opportunities undermining installed technical capacity | Low | This risk realized in 2013 when the National Project Coordinator left the Ministry of Nature Protection (MNP) of Turkmenistan. The project had to make an extra effort to bring up-to-date the new contact point in the MNP. Due to the transition of the National Project Coordinator Durikov M. to the position of Director of the Institute of Deserts Flora and Fauna of Turkmenistan risks associated with staff turnover were eliminated.
Reluctance of decision makers to introduce progressive and differentiated water tariff and policy within project lifetime | Low | This risk is still relevant. To address it, six consultations/round tables were organized in the reporting period to discuss developed by the AF project proposal on introdcution of a new tarif system. Another consultation is planned for early June. The proposal will also be shared with key involved ministries for comments and methodological guidance for tariff implementation will be developed. Developed by experts of the project a package of documents for the implementation of tariffs for water delivery was transferred in the beginning of January 2015 to relevant stakeholders for review and further use.
Failure to include water in land use master plan or to establish basin level water management within current regulatory frameworks, and subsequent take up by Ministries within strategic frameworks | Low | The proposed by the project amendments to Water Code include introduction of the basin level water management. The President has stated that there is a need to review the Land Use Code and the project will engage when the process of revision will start. Developed by experts of the project a package of documents with additions and amendments to the Water and Land Code of Turkmenistan was transferred in January 2015 to stakeholders for review and further use.
During the inception phase of the project, it was noted that there are significant demographic fluctuations in the target regions, including due to internal migration. Therefore, as population may decrease, it may be challenging to achieve targets on the number of people to benefit from the project in the three focus regions (Output 2.1, Output 2.2., Output 2.3., Output 3.1., Output 3.2). | Low | This risk is reduced as based on investment plans in each project region, planned number of beneficiaries will be covered. In addition, there will be a significant number of indirect beneficiaries.Effective implementation of adaptation measures increases the sustainability of the beneficiaries inhabited in each pilot region.
Critical Risks Affecting Progress (Not identified at project design)
Identify Risks with a 50% or > likelihood of affecting progress of project
Identified Risk | Current Status | Steps Taken to Mitigate Risk
Changes in project management and national team of experts can lead to delays in project implementation and reduce the effectiveness of the project. | Low | The project manager was able to prove the need to maintain a highly skilled and experienced team, which is confirmed by Mid-term evaluation audit and international experts. Taking this into account contracts with the national experts was concluded. After conclusion of contracts with national experts a working meeting to address difficulties and challenges was conducted. It was prepared a clear working plan. Taking into account these, there is no any challenges in project management.
Risk Measures: Were there any risk mitigation measures employed during the current reporting period? If so, were risks reduced? If not, why were these risks not reduced?
Add any comments relevant to risk mitigation (word limit = 500)
The key project risk is related to delays in tendering process, at the moment the risk is slightly reduced but will be closely monitored in the next reporting period. In particular, the Country Office developed a Procurement Plan, according to which every tender should be initiated at least four months in advance of the starting date of planned activity.

## Rating
RATING ON IMPLEMENTATION PROGRESS
For rating definitions please see bottom of page.
| Progress on Key Milestones |  | Expected Progress |  | Progress to Date | Rating
Project Manager/Coordinator: | Outcome 1: institutional capacity to develop climate resilient water policies in agriculture strengthened |  | Revision of the Water Code for a clear understanding of climate change impacts on water resources availability of targeted ministries and departments of agriculture sector and farmer associations, private land owners, tenants and farmers. Local communities in 3 project regions have a clear understanding about findings of the Assessment of Socio-Economic Impacts of Climate Change. A method of calculating the differentiated water tariffs for water supply services for local communities in 3 project regions |  | The underlying premise of this Outcome is that a community-level organization (Water User Association and Water User Group) needs to be established and empowered in order to maintain the water infrastructures, including those put in place with AF resources. A revision of Water Code is an essential step towards this. During the reporting period, IP prepared and submitted a package of legal documents to the relevant authorities on amendments and supplements to the Code of Turkmenistan "On Water" in the context of Climate Change including: - Amendments and additions to the draft Water Code; - Draft law on the WUA / WUG and dissemination among all interested parties; - Regulations on public administration (WUA /WUG) of water management at the local level - Participation in the discussion of the draft documents with the Ministry of Water Resources and other key stakeholders - Amendments and additions to the Law of Turkmenistan “On Farmers' Associations”; - Regulations on financial incentives - Taking into account the effect and impact of the Climate Change on water resources and their submission to the state authorities for review. Several seminars and working meetings were conducted to raise general awareness among policy makers and beaurocrats about the need for a legislation change in light of climate change. The target participants include key ministries and agencies, such as the Mejlis of Turkmenistan, the Ministry of Water Resources of Turkmenistan, the Ministry of Agriculture, Ministry of Nature Protection, Ministry of economy and development of Turkmenustan, SA “Turkmenmallary”, Hydro-meteorological Center under the Cabinet of Ministers of Turkmenistan as well as representatives of local self-government bodies and local communities, and the Institute of Deserts, Flora and Fauna Turkmenistan. The topics of discussion include general overview and justification of the draft of the Water Code and the preparation of a draft law on the WUA / WUG, proposed changes to the Law of Turkmenistan “On Farmers' Associations”, the method of calculation of the tariff for water supply services, and socio-economic impact of climate change on water availability, economic impacts, identification of possible adaptation measures, and cost-benefit of various adaptation measures. Documents capturing the outcomes from this discussion are currently being prepared to be distributed to the state authorities. | Satisfactory (S)
| Outcome 2: Resilience to climate change enhanced in targeted communities through the introduction of community-based adaptation approaches |  | At least one water harvesting technique and saving measures implemented in Nohur region to benefit 4,000 agri-pastoralists by end of 2014 At least two watering points established in Karakum region to benefit 8,000 farmers and pastoralists by end of 2014 Set of at least three agronomic measures implemented in at least 3 communities by end of 2014 Canal level irrigation improvement measures implemented in the Sakar-Chaga region to benefit 20,000 people by end of the project |  | Outcome 2.1. Adaptation measures implemented and agreed in the project region of Nohur: 1. The construction of 7 dams and reservoirs; 2. Full repair of 3 dams and reservoirs; 3. Full repair of 4 springs; 4. Construction of a concrete pool (volume capacity - 400 m3); 5. Full repair and reconstruction of the existing system of drip irrigation on 20 hectares (10 hectares of gardens, 10 hectares of vegetables); 6. Designing a new drip irrigation system in the village of Konegumbez (10 ha); 7. Local control center established; 8. Created a local seedlings nursery; 9. Production of compost and organic-compost cycle completed -14 pits. A cost-benefit analysis of these adaptation activities was undertaken in the process according to the project 2014 Work Pan. A Study Tour of the local project coordinators aimed at their capacity building was conducted. Regular inspections, technical control and support for the implementation of the agreed investment activities have been performed. Output 2.2. The following adaptation activities in the project area Karakum were achieved: 1. In the north-eastern part of the village Bokurdak the work on the stabilizing the sand in the area of 10 hectares. The row materials to secure 10 hectares of sand were delivered. The works associated with fixing and afforestation of sands on 10 hectares have been completed; 2. Designing drip irrigation system in the village of Chalysh (3.02 ha) is completed; 3. Full repair works of 4 dew mounds for livestock farms No. 1 (500 m3) and No. 2 (500 m3) - completed; 4. Construction of new 7 wells using the traditional way for cattle farms No. 1 and No. 2 - completed; 5. Repair of existing 6 wells 6 for cattle farms No. 1 and No. 2 - completed; 6. Cleaning of 8 takyrs and kaks - rain wells for livestock farms No. 1 and No. 2; 7. The construction of the new 11 dew mounds (60 m3) for livestock farm No. 1 and No. 2; 8. Local control center established; 9. Local nursery created. A cost-benefit analysis of these adaptation activities was undertaken in the process according to the project 2014 Work Pan. Ensure regular inspection, technical control and support for the implementation of the implementation of the implementation of the agreed investment activities. Output 2.3. The following adaptation activities in the project region Sakarchaga were implemented: 1. All 16 planned water counting structures were constructed. 2. The works were undertaken through the production association "Marysuvhozhalyk" that serves the region. A mechanized cleaning of farm reservoir with a total length of 31.5 km has been completed in the "Zakhmet" of Sakarçäge District. The first phase of renovation and cleaning 6 km farm collector have also been completed. 3. Local control center was established; 4. Local nursery created; 5. Reclamation of 20 hectares of abandoned lands were successfully completed, located in the territory of the Farmers Union Zahmet of Sakarchaga District. | Highly Satisfactory (HS)
| Outcome 3: Community-managed water delivery services introduced to benefit over 30,000 farmer and pastoralist communities in the three target agro-ecological zones. |  | Increased number of associations with improved institutional capacity to deliver water services to target communities. |  | Indicator 3.1. The number of associations with improved institutional capacity to provide water services to targeted communities. Outcome 3.1. Mandates and institutional functions of local associations strengthened to improve local water services that are more resilient to increasing water stress and benefit for at least 40% of farmers and pastoralists. The organization of water user groups which have clear objectives, institutional capacity and skills of management. The supply of water resources based the local communities. As part of the 3 components there were 3 trainings conducted in each pilot area directed on organizational development and management of water user groups (20 participants, 2 training 2 days, 1 training 3 days, 1 training for 4 days). There were identified a structure of the group of water users and the development of the draft statute. 3.3 Investment in at least 4 water management projects led by Water User Associations on the basis of the above VCA assessment, resulting in improved quality of agricultural water supply and strengthened WUA mandate and profile. One training on capacity building of water user groups in the development of investment projects, effective management of water resources, monitoring and evaluation through the use of modern technologies, as well as preparation of investment projects, all were held in the project region of Sakarchaga (two-day training in each pilot region for 20 people). Meetings aimed at the collection and dissemination of practical experience and lessons learned. There is also a regular and systematic publication of project news and its achieved results posted on the website of UNDP (among them, corresponding reports, documents and conclusions for submission to interested parties). Wide dissemination of project results in UNDP ALM and other networks. The participation and cooperation with other project initiatives and participation in their activities (e.g. UNDP Climate Risk Management in Turkmenistan). The Project Steering Committee meeting was held, and project management and support was provided for a national seminar dedicated to the International Environment Day - June 5, 2014. | Satisfactory (S)
[5 empty] | Overall Rating | Satisfactory (S)
Please Provide the Name and Contact information of person(s) reponsible for completeling the Rating section
| Name: | Ahmet Shadurdiev
| Email: | ahmed.shadurdyev@undp.org
Please justify your rating. Outline the positive and negative progress made by the project since it started. Provide specific recommendations for next steps. . (word limit=500)
Material and technical basis for sustainable functioning of the project was established. Established highly qualified and experienced team of international and national experts for the project, united by a common strategy and objectives of the project. On the basis of the master plan/investment plans developed for each project region, all adaptation measures planned for 2014-2015 have been implemented, which was agreed and responds to the identified local needs in the context of climate change. Taking into account the provisions of the new Law on Nature Protection of Turkmenistan (2014), national experts of the project developed a package of amendments, additions and changes to the draft Water Code of Turkmenistan and submitted to the Ministry of Water Economy. In addition the provisions on Water User Groups (WUG) formed on the basis of farmers' associations brigades were developed. Recommendations for amendments and additions to the draft Water Code of Turkmenistan were developed and submitted to the Ministry of Water Economy of Turkmenistan (14.01.2014). These proposals provide basis for establishment of WUA in Turkmenistan and gave an entry point for development of normative legal documents related to WUA. A package of documents was submitted in the begining 2015. In addition, within the framefork of the current legislation the national experts with the participation of international experts have developed the methodology for calculation of tariffs for water supply. Also recommendations on modifications and additions to the Law of Turkmenistan "On Farmers' Associations" (2007); Draft of the Law of Turkmenistan "On Water Users Associations"; Recommendations for introducing amendments and changes to the national water legislation regarding tariffs for water supply services; Methodology for calculating tariffs for water supply services were submitted to the Mejlis of Turkmenistan, the Ministry of Water Economy of Turkmenistan and the Ministry of Agriculture of Turkmenistan for further discussion and use. In order to implement the planned measures tender bids/offers (technical, financial and project planning documents) were fully prepared. Through a series of training modules and seminars the institutional capacity of all key stakeholders, local authorities and local communities was increased/strengthed.
| Progress on Key Milestones |  | Expected Progress |  | Progress to Date | Rating
Implementing Agency | Outcome 1: institutional capacity to develop climate resilient water policies in agriculture strengthened |  | Revision of the Water Code for a clear understanding of climate change impacts on water resources availability of targeted ministries and departments of agriculture sector and farmer associations, private land owners, tenants and farmers. Local communities in 3 project regions have a clear understanding about findings of the Assessment of Socio-Economic Impacts of Climate Change. A method of calculating the differentiated water tariffs for water supply services for local communities in 3 project regions |  | Within the framework of the first component a seminar was organized to facilitate a discussion on the socio-economic impact of climate change on water availability, economic impacts, identification of possible adaptation measures, and cost-benefit of various adaptation measures. Documents capturing the outcomes from this discussion are currently being prepared to be distributed to the state authorities. During the reporting period, IP also prepared and submitted a package of legal documents to the relevant authorities on amendments and supplements to the Code of Turkmenistan "On Water" in the context of Climate Change. Within the framework of this output, the IP with assistance from the Project Management Team has prepared, discussed and agreed on the following draft documents: - Amendments and additions to the draft Water Code; - Draft law on the WUA / WUG and dissemination among all interested parties; - Regulations on public administration (WUA /WUG) of water management at the local level - Participation in the discussion of the draft documents with the Ministry of Water Resources and other key stakeholders - Amendments and additions to the Law of Turkmenistan “On Farmers' Associations”; - Regulations on financial incentives - Taking into account the effect and impact of the Climate Change on water resources and their submission to the state authorities for review. A seminar was conducted for the consultation and discussion of amendments to the draft of the Water Code and the preparation of a draft law on the WUA / WUG. In addition, a working meeting was conducted for the consultation and discussion of proposed changes to the Law of Turkmenistan “On Farmers' Associations”; A seminar to discuss the method of calculation of the tariff for water supply services was organized jointly with the Ministry of Water Resources, Ministry of Economy and Development and the Ministry of Nature Protection of Turkmenistan and other concerned ministries. The final documents were submitted to the state authorities for review. A package of documents was submitted in the beginning of January, 2015. Recommendations for amendments and additions to the draft WaterCide of Turkmenistan. In addition, within the framefork of the current legislation the national experts with the participation of international experts have developed the methodology for calculation of tariffs for water supply. Also recommendations on modifications and additions to the Law of Turkmenistan "On Farmers' Associations" (2007); Draft of the Law of Turkmenistan "On Water Users Associations"; Recommendations for introducing amendments and changes to the national water legislation regarding tariffs for water supply services; Methodology for calculating tariffs for water supply services were submitted to the Mejlis of Turkmenistan, the Ministry of Water Economy of Turkmenistan and the Ministry of Agriculture of Turkmenistan for further discussion and use. | Moderately Satisfactory (MS)
| Outcome 2: Resilience to climate change enhanced in targeted communities through the introduction of community-based adaptation approaches |  | At least one water harvesting technique and saving measures implemented in Nohur region to benefit 4,000 agri-pastoralists by end of 2014 At least two watering points established in Karakum region to benefit 8,000 farmers and pastoralists by end of 2014 Set of at least three agronomic measures implemented in at least 3 communities by end of 2014 Canal level irrigation improvement measures implemented in the Sakar-Chaga region to benefit 20,000 people by end of the project |  | Outcome 2.1. Adaptation measures implemented and agreed in the project region of Nohur: 1. The construction of 7 dams and reservoirs; 2. Full repair of 3 dams and reservoirs; 3. Full repair of 4 springs; 4. Construction of a concrete pool (volume capacity - 400 m3); 5. Full repair and reconstruction of the existing system of drip irrigation on 20 hectares (10 hectares of gardens, 10 hectares of vegetables); 6. Designing a new drip irrigation system in the village of Konegumbez (10 ha); 7. Local control center established; 8. Created a local seedlings nursery; 9. Production of compost and organic-compost cycle completed. A cost-benefit analysis of these adaptation activities was undertaken in the process according to the project 2014 Work Pan. A Study Tour of the local project coordinators aimed at their capacity building was conducted. Regular inspections, technical control and support for the implementation of the agreed investment activities have been performed. Output 2.2. The following adaptation activities in the project area Karakum were achieved: 1. In the north-eastern part of the village Bokurdak the work on the stabilizing the sand in the area of 10 hectares. The row materials to secure 10 hectares of sand were delivered. The works associated with fixing and afforestation of sands on 10 hectares have been completed; 2. Designing drip irrigation system in the village of Chalysh (3.02 ha) is completed; 3. Full repair works of 4 dew mounds for livestock farms No. 1 (500 m3) and No. 2 (500 m3) - completed; 4. Construction of new 7 wells using the traditional way for cattle farms No. 1 and No. 2 - completed; 5. Repair of existing 6 wells 6 for cattle farms No. 1 and No. 2 - completed; 6. Cleaning of 8 takyrs and kaks - rain wells for livestock farms No. 1 and No. 2; 7. The construction of the new 11 dew mounds (60 m3) for livestock farm No. 1 and No. 2; 8. Local control center established; 9. Local nursery created. A cost-benefit analysis of these adaptation activities was undertaken in the process according to the project 2014 Work Pan. Ensure regular inspection, technical control and support for the implementation of the implementation of the implementation of the agreed investment activities. Output 2.3. The following adaptation activities in the project region Sakarchaga were implemented: 1. All 16 planned water counting structures were constructed. 2. The works were undertaken through the production association "Marysuvhozhalyk" that serves the region. A mechanized cleaning of farm reservoir with a total length of 31.5 km has been completed in the "Zakhmet" of Sakarçäge District. The first phase of renovation and cleaning 6 km farm collector have also been completed. 3. Local control center was established; 4. Local nursery created. | Satisfactory (S)
| Outcome 3: Community-managed water delivery services introduced to benefit over 30,000 farmer and pastoralist communities in the three target agro-ecological zones. |  | Increased number of associations with improved institutional capacity to deliver water services to target communities. |  | Indicator 3.1. The number of associations with improved institutional capacity to provide water services to targeted communities. Outcome 3.1. Mandates and institutional functions of local associations strengthened to improve local water services that are more resilient to increasing water stress and benefit for at least 40% of farmers and pastoralists. The organization of water user groups which have clear objectives, institutional capacity and skills of management. The supply of water resources based the local communities. As part of the 3 components there were 3 trainings conducted in each pilot area directed on organizational development and management of water user groups (20 participants, 2 training 2 days, 1 training 3 days, 1 training for 4 days). There were identified a structure of the group of water users and the development of the draft statute. 3.3 Investment in at least 4 water management projects led by Water User Associations on the basis of the above VCA assessment, resulting in improved quality of agricultural water supply and strengthened WUA mandate and profile. One training on capacity building of water user groups in the development of investment projects, effective management of water resources, monitoring and evaluation through the use of modern technologies, as well as preparation of investment projects, all were held in the project region of Sakarchaga (two-day training in each pilot region for 20 people). Meetings aimed at the collection and dissemination of practical experience and lessons learned. There is also a regular and systematic publication of project news and its achieved results posted on the website of UNDP (among them, corresponding reports, documents and conclusions for submission to interested parties). Wide dissemination of project results in UNDP ALM and other networks. The participation and cooperation with other project initiatives and participation in their activities (e.g. UNDP Climate Risk Management in Turkmenistan). The Project Steering Committee meeting was held, and project management and support was provided for a national seminar dedicated to the International Environment Day - June 5, 2014. | Moderately Satisfactory (MS)
[5 empty] | Overall Rating | MS
Please Provide the Name and Contact information of person(s) reponsible for completeling the Rating section
| Name: | Rovshen Nurmuhamedov; Yusuke Taishi
| Email: | rovshen.nurmuhamedov@undp.org; yusuke.taishi@undp.org
Please justify your rating. Outline the positive and negative progress made by the project since it started. Provide specific recommendations for next steps. . (word limit=500)
The project is making solid progress towards the achievement of the project objective and supporting outcomes. Progress towards Outcome 2 is particularly positive as a number of concrete adaptation measures have been delivered on the ground. For example, the introduction of a greenhouse on a pilot-basis (with the capital investment of US$4,000 plus community labour contributions) was completed during this reporting period and community members saw the first harvest of cucumbers amounting to nearly 1.5 tonnes. This is about US$850 in market value. This means that the investment would be paid back in less than two years even if private sector financing was directed (although the construction of a well, which was also financed by AF resources, is a necessary condition for a successful greenhouse. So the return on investment needs to be adjusted taking this into considerations). Constructions of communal wells for livestock have been proven to be very successful as well. The challenge for the project is that these successes have not led to the passage of the draft Water Code, which would empower Water User Groups as custodians of communal water infrastructures and enable them to collect fees for O&M based on a standard formula for computing water tariffs. Furthermore, the main results and findings from the work under Component 1 such as the socio-economic study are not grounded within relevant ministries and institutions. Thus, the impact of the project's strategic work is not yet visible in the institutional planning. The project needs to do more work wtih the national counterparts to ensure their ownership of the project outcomes and results. Moreover, it is still unclear whether these successful demonstrations of adaptation measures would lead to, for example, integration of these measures into regular government development programmes and plans. While this is outside the control of the project to a certain extent, adaptive management in terms of the project implementation strategy may be warranted especially as the project passes the halfway point of the implementation. Moving forward, several recommendations are presented below: First, the project team could strengthen awareness raising activities and disseminations of project lessons towards internal audience (policy makers, legislatures, senior government officers). The project team has produced a number of press releases, articles, web stories, etc, but they often appear to be targeting external audiences (such as donors) and at times too technical. A much more targeted approach specifically for policy/legislation change may be necessary. Second, related to the first point, increasing government ownership of the project needs to be one of the priorities for the project team for the reminder of the project. While it is apparent that the government views very positively about the project, there is still a risk that all successes demonstrated in this project remains to be "pilot-tests carried out in an externally-financed project" and once the project is over, business-as-usual prevails (this is especially true if the draft Water Code is not passed). In the context of Turkmenistan, there is a limited window through which to influence government policies and strategies; nonetheless, improvement in communications strategy and targeted awareness raising among senior level politicians may be effective. Under Component 3, the project needs to be more proactive in identifying recommendations and solutions that would create local demand for services of the pilot water user associations. Furthermore, funding is a key prerequisite for WUA sustainability, and the project needs to focus more on devising and instituting workable financina mechanisms.
| Progress on Key Milestones |  | Expected Progress |  | Progress to Date | Rating
Other | Outcome 1: institutional capacity to develop climate resilient water policies in agriculture strengthened |  | Revision of the Water Code for a clear understanding of climate change impacts on water resources availability of targeted ministries and departments of agriculture sector and farmer associations, private land owners, tenants and farmers. Local communities in 3 project regions have a clear understanding about findings of the Assessment of Socio-Economic Impacts of Climate Change. A method of calculating the differentiated water tariffs for water supply services for local communities in 3 project regions |  | Within the framework of the first component a seminar was organized to facilitate a discussion on the socio-economic impact of climate change on water availability, economic impacts, identification of possible adaptation measures, and cost-benefit of various adaptation measures. Documents capturing the outcomes from this discussion are currently being prepared to be distributed to the state authorities. The underlying premise of this Outcome is that a community-level organization (Water User Association and Water User Group) needs to be established and empowered in order to maintain the water infrastructures, including those put in place with AF resources. A revision of Water Code is an essential step towards this. During the reporting period, IP also prepared and submitted a package of legal documents to the relevant authorities on amendments and supplements to the Code of Turkmenistan "On Water" in the context of Climate Change. Within the framework of this output, the IP with assistance from the Project Management Team has prepared, discussed and agreed on the following draft documents: - Amendments and additions to the draft Water Code; - Draft law on the WUA / WUG and dissemination among all interested parties; - Regulations on public administration (WUA /WUG) of water management at the local level - Participation in the discussion of the draft documents with the Ministry of Water Resources and other key stakeholders - Amendments and additions to the Law of Turkmenistan “On Farmers' Associations”; - Regulations on financial incentives - Taking into account the effect and impact of the Climate Change on water resources and their submission to the state authorities for review. A seminar was conducted for the consultation and discussion of amendments to the draft of the Water Code and the preparation of a draft law on the WUA / WUG. In addition, a working meeting was conducted for the consultation and discussion of proposed changes to the Law of Turkmenistan “On Farmers' Associations”; A seminar to discuss the method of calculation of the tariff for water supply services was organized jointly with the Ministry of Water Resources, Ministry of Economy and Development and the Ministry of Nature Protection of Turkmenistan and other concerned ministries. The final documents were submitted to the state authorities for review. A package of documents was submitted in the beginning of January, 2015. Recommendations for amendments and additions to the draft WaterCide of Turkmenistan. In addition, within the framefork of the current legislation the national experts with the participation of international experts have developed the methodology for calculation of tariffs for water supply. Also recommendations on modifications and additions to the Law of Turkmenistan "On Farmers' Associations" (2007); Draft of the Law of Turkmenistan "On Water Users Associations"; Recommendations for introducing amendments and changes to the national water legislation regarding tariffs for water supply services; Methodology for calculating tariffs for water supply services were submitted to the Mejlis of Turkmenistan, the Ministry of Water Economy of Turkmenistan and the Ministry of Agriculture of Turkmenistan for further discussion and use. | Satisfactory (S)
| Outcome 2: Resilience to climate change enhanced in targeted communities through the introduction of community-based adaptation approaches |  | At least one water harvesting technique and saving measures implemented in Nohur region to benefit 4,000 agri-pastoralists by end of 2014 At least two watering points established in Karakum region to benefit 8,000 farmers and pastoralists by end of 2014 Set of at least three agronomic measures implemented in at least 3 communities by end of 2014 Canal level irrigation improvement measures implemented in the Sakar-Chaga region to benefit 20,000 people by end of the project |  | Outcome 2.1. Adaptation measures implemented and agreed in the project region of Nohur: 1. The construction of 7 dams and reservoirs; 2. Full repair of 3 dams and reservoirs; 3. Full repair of 4 springs; 4. Construction of a concrete pool (volume capacity - 400 m3); 5. Full repair and reconstruction of the existing system of drip irrigation on 20 hectares (10 hectares of gardens, 10 hectares of vegetables); 6. Designing a new drip irrigation system in the village of Konegumbez (10 ha); 7. Local control center established; 8. Created a local seedlings nursery; 9. Production of compost and organic-compost cycle completed. A cost-benefit analysis of these adaptation activities was undertaken in the process according to the project 2014 Work Pan. A Study Tour of the local project coordinators aimed at their capacity building was conducted. Regular inspections, technical control and support for the implementation of the agreed investment activities have been performed. Output 2.2. The following adaptation activities in the project area Karakum were achieved: 1. In the north-eastern part of the village Bokurdak the work on the stabilizing the sand in the area of 10 hectares. The row materials to secure 10 hectares of sand were delivered. The works associated with fixing and afforestation of sands on 10 hectares have been completed; 2. Designing drip irrigation system in the village of Chalysh (3.02 ha) is completed; 3. Full repair works of 4 dew mounds for livestock farms No. 1 (500 m3) and No. 2 (500 m3) - completed; 4. Construction of new 7 wells using the traditional way for cattle farms No. 1 and No. 2 - completed; 5. Repair of existing 6 wells 6 for cattle farms No. 1 and No. 2 - completed; 6. Cleaning of 8 takyrs and kaks - rain wells for livestock farms No. 1 and No. 2; 7. The construction of the new 11 dew mounds (60 m3) for livestock farm No. 1 and No. 2; 8. Local control center established; 9. Local nursery created. A cost-benefit analysis of these adaptation activities was undertaken in the process according to the project 2014 Work Pan. Ensure regular inspection, technical control and support for the implementation of the implementation of the implementation of the agreed investment activities. Output 2.3. The following adaptation activities in the project region Sakarchaga were implemented: 1. All 16 planned water counting structures were constructed. 2. The works were undertaken through the production association "Marysuvhozhalyk" that serves the region. A mechanized cleaning of farm reservoir with a total length of 31.5 km has been completed in the "Zakhmet" of Sakarçäge District. The first phase of renovation and cleaning 6 km farm collector have also been completed. 3. Local control center was established; 4. Local nursery created. | Highly Satisfactory (HS)
| Outcome 3: Community-managed water delivery services introduced to benefit over 30,000 farmer and pastoralist communities in the three target agro-ecological zones. |  | Increased number of associations with improved institutional capacity to deliver water services to target communities. |  | Indicator 3.1. The number of associations with improved institutional capacity to provide water services to targeted communities. Outcome 3.1. Mandates and institutional functions of local associations strengthened to improve local water services that are more resilient to increasing water stress and benefit for at least 40% of farmers and pastoralists. The organization of water user groups which have clear objectives, institutional capacity and skills of management. The supply of water resources based the local communities. As part of the 3 components there were 3 trainings conducted in each pilot area directed on organizational development and management of water user groups (20 participants, 2 training 2 days, 1 training 3 days, 1 training for 4 days). There were identified a structure of the group of water users and the development of the draft statute. 3.3 Investment in at least 4 water management projects led by Water User Associations on the basis of the above VCA assessment, resulting in improved quality of agricultural water supply and strengthened WUA mandate and profile. One training on capacity building of water user groups in the development of investment projects, effective management of water resources, monitoring and evaluation through the use of modern technologies, as well as preparation of investment projects, all were held in the project region of Sakarchaga (two-day training in each pilot region for 20 people). Meetings aimed at the collection and dissemination of practical experience and lessons learned. There is also a regular and systematic publication of project news and its achieved results posted on the website of UNDP (among them, corresponding reports, documents and conclusions for submission to interested parties). Wide dissemination of project results in UNDP ALM and other networks. The participation and cooperation with other project initiatives and participation in their activities (e.g. UNDP Climate Risk Management in Turkmenistan). The Project Steering Committee meeting was held, and project management and support was provided for a national seminar dedicated to the International Environment Day - June 5, 2014. | Satisfactory (S)
[5 empty] | Overall Rating | Satisfactory (S)
Please Provide the Name and Contact information of person(s) reponsible for completeling the Rating section
| Name: | Mr. Muhammet Durikov, Director of the National Institute of Deserts, Flora and Fauna of Turkmenistan under the Ministry of Nature Protection of Turkmenistan
| Email: | durikov@mail.ru
| Please justify your rating and address the following points: 1. Indicate trends, both positive and negative, in achievement of outcomes as per the project indicators. 2. Detail critical risks that have affected progress. 3. Outline response to MTR undertaken this reporting period. 4. Outline action plan to address projects with a rating of HU, U or MU. Please keep your input to 1200 words |  | The project successfully performed and implemented its objectives for the period 2014-2015. The implementation of all activities according to all components has been successfully implemented. Particularly according to component 2 in 2014 adaptation measures in three pilot regions were implemented in order to reduce the negative impact of climate change on sustainable water use. However, I consider that it is necessary to speed up/accelerate announcement of tenders for further implementation of the remaining adaptation measures. Regarding, the Karakum pilot region consider the need to sign a Grant Agreement with the Farmers association "Karakum". The project defined the methodological and organizational levers of active mobilization of local communities in the work of the project. As an example, it is possible to indicate that the majority of costs are not material in the implementation of adaptation measures takes local communities on themselves in three pilot regions. In addition, capacity of local communities was increased in the field of new technologies and methods for obtaining sustainable yield and water efficiency in the context of climate change. From year to year, the involvement of local communities (leaseholders, farmers) increases. In addition, recommendations were prepared and submitted to relevant stakeholders for additions and amendments to the normative-regulatory legal framework for the management of water-land and pasture resources. Moreover, methodology of calculating the differentiated water tariffs for water supply services has been developed for calculating tariffs for the services of water supply. It is necessary to note that in the framework of the project it was prepared a report on the impact of implemented adaptation measures on socio-economic conditions of local communities in three pilot regions. In addition, the project is actively replicating new technologies, best practices in the field of sustainable water management in various natural and ecological conditions of Turkmenistan.
Rating Definitions
|  |  | Highly Satisfactory (HS) | Project actions/activities planned for current reporting period are progressing on track or exceeding expectations to acheive all major outcomes/outputs for given reporting period, without major shortcomings. The project can be presented as “good practice”.
|  |  | Satisfactory (S) | Project actions/activities planned for current reporting period are progressing on track to achieve most of its major outcomes/outputs with only minor shortcomings.
|  |  | Marginally Satisfactory (MS) | Project actions/activities planned for current reporting period are progressing on track to achieve most major relevant outcomes/outputs, but with either significant shortcomings or modest overall relevance.
|  |  | Marginally Unsatisfactory (MU) | Project actions/activities planned for current reporting period are not progressing on track to achieve major outcomes/outputs with major shortcomings or is expected to achieve only some of its major outcomes/outputs.
|  |  | Unsatisfactory (U) | Project actions/activities planned for current reporting period are not progressing on track to achieve most of its major outcomes/outputs.
|  |  | Highly Unsatisfactory (U) | Project actions/activities planned for current reporting period are not on track and shows that it is failing to achieve, and is not expected to achieve, any of its outcomes/outputs.

## Project Indicators
PROJECT Indicators
Please provide all indicators being tracked for the project as outlined in the project document
Type of Indicator (indicators towards Objectives, Outcomes, etc…)
Type of Indicator | Indicator | Baseline | Progress since inception | Target for Project End
Outcome 1: Institutional capacity to develop climate resilient water policies in agriculture strengthened | Indicator 1.1: Water code subsidiary laws and regulations that introduce progressive pricing policies and communal management for local water services are in place and operational. | Government has made progressive steps towards improving water management systems. It invests heavily in the improvement and upgrade of water infrastructure and looks out for more advanced technologies. However, water policies remain outdated as well as poorly enforced due to underdeveloped regulations and subsidiary legislation. Tools and methods are missing to indentify the most cost-effective adaptation options in the water policies. Water pricing is largely inadequate. | Taking into account the provisions of the new Law on Nature Protection of Turkmenistan (2014) National experts of the project developed a package of amendments to the draft Water Code of Turkmenistan and submitted to the Ministry of Water Economy in January 2014. The amendments aim at improving water resources management in the context of climate change. More specifically, they include the introduction of water tariffs to be collected from users, which are to be used for the maintenance of rural water infrastrucutre; and formally recognizing the Water User Groups to oversee the operations and maintenance of the water systems. These amendment documents were submitted to the Ministry of Water Economy of Turkmenistan, Ministry of Agriculture of Turkmenistan and to the Mejlis (Parliament) of Turkmenistan in January, 2015. An analysis of the socio-economic conditions in all three pilot regions was performed and a report prepared. In addition, a clear methodology of calculating the differentiated water tariffs for water supply services was developed as an input to the draft amendment document. A seminar was conducted for the consultation and discussion of amendments to the draft of the Water Code and the preparation of a draft law on the WUA / WUG. In addition, a working meeting was conducted for the consultation and discussion of proposed changes to the Law of Turkmenistan “On Farmers' Associations”; a seminar to discuss the method of calculation of the tariff for water supply services was organized jointly with the Ministry of Water Resources, Ministry of Economy and Development and the Ministry of Nature Protection of Turkmenistan and other concerned ministries. The final documents were submitted to the state authorities for review. Also a workshop (including participants from velayats) on discussion of recommendations to the darft laws "on Pastures" and Code "On Land" with Parliament, Ministry of Agriculture, Ministry of Water economy, MNP and other interested ministries, experts and specialists from Kazakhstan in the framework of development of cooperation South-South Cooperation on Climate Change was conducted. These recommendations are under consideration in the working group of the Mejlis (Parliament) of Turkmenistan. Preliminary comments on our recommendations are expected to receive in the near future. | A package of amendments to water code with proposed water tariff and other economic instruments developed and submitted for adoption by end of 2012. Update of the water code to ensure explicit recognition of climate impacts on water resource availability by end of 2013. At least 2 sets of sub- regulations developed under the Water Code to implement a) progressive and differentiated tariffs, b) support for water delivery services under communal management
Output 1.1. Socio-economic impact of climate change on water availability costed and documented, including cost-benefit analysis of adaptation measures | Indicator 1.1.1: Study on socio-economic impacts of climate change on water availability, including cost-benefit analysis of adaptation measures conducted | 0 | 1. At the local level: Based on the VCA assessment, a socio-economic report on impacts of climate change risks onto local economies of three project regions was prepared at the national level with the participation of all relevant stakeholders. A preliminary cost-benefit analysis was conducted which will be completed at the end of the implementation of all adaptation measures/investment activities. 2 consultation workshops were organized to discuss the findings of the recently conducted studies on the socio-economic impacts of climate change risks on local economies of three project regions – Sakarchaga in Mary velayat (irrigation area), Karakum (desert area) and Nohur (mountainous area) in Ahal velayat. 2. At the National level: Within the framework of the first component during a seminar jointly with the Ministry of Water Resources, Ministry of Economy and Development and the Ministry of Nature Protection of Turkmenistan and other concerned ministries held negotiation and discussion of research on the socio-economic impact of climate change on water availability, including the assessment of the effectiveness of adaptation measures: 1. Social Assessment; 2. Economic evaluation; 3. Identification of adaptation measures; 4. Cost-benefit analysis of adaptation measures and submission to the relevant state authorities. A seminar was organized to discuss the study of socio-economic impact. A package of draft amendment documentsfor the Water Code of Turkmenistan was prepared and submitted to the state authority. | Study on socio-economic impacts of climate change on water availability, including cost-benefit analysis of adaptation measures conducted
| Indicator 1.1.2: Number of water legislative acts amended based on climate change cost estimations | 0 | 1. Several amendments for inclusion to the Water Code of Turkmenistan developed. They are: a) Amendments to the Water Code on the concept of "association of water users and water users groups WUA"; b) Amendments to the Water Code related to rights of water users on the establishment of WUAs / WUGs; c) Amendments to the Water Code of related to the transition of water management to the basin principle; d) Establishment of basins’ councils; e) Amendments to the Water Code related to the provision of the Cabinet of Ministers the right to transfer on the balance or for the use of the interfarm collector and collector-drainage networks of WUA/WUG; f) Amendments to the Water Code regarding the distribution of competence of state bodies in the water sector; g) The extension of the competence of local authorities in the field of water resources management; h) Amendments to the Water Code related to fixing the norms of the differentiated approach in determining the tariffs for water supply services; i) On the determination of the legal regime of water protection zones; 2. Several draft sub-laws have been prepared. They are: a) Rules of water used by WUGs in the area of irrigated agriculture, mountainous areas, and desert zones; b)Law on WUAs; c) Law on Amendments, additions and changes to the Law about the farmers' associations; d) Regulation on the introduction of differentiated tariffs for the water supply services. The Law of Turkmenistan "On amendments and additions to the Code of Turkmenistan" On the Water "(2004), adopted by the Mejlis of Turkmenistan, March 1, 2014 was taking into account some recommendations and suggestions made by the project team. The above mentioned normative legal documents are the main results, which are recorded in the project document. All these documents will lead and contribute to the achievement of outputs and outcomes. | At least 2
Output 1.2. A package of modifications in the water code, with particular focus on communal water management; and financial incentives for water efficiency (e.g. differentiated and progressive tariff) developed | Indicator 1.2.1: Number of water regulations to introduce progressive and differentiated tariff and water delivery services under communal management | 0 | A methodology of differentiated tariffs for water supply services was developed and will be tested by established WUG with results expected at the final stage of the project. A seminar to discuss the method of calculation of the tariff for water supply services was organized jointly with the Ministry of Water Resources, Ministry of Economy and Development and the Ministry of Nature Protection of Turkmenistan and other concerned ministries. The final documents were submitted to the state authorities for review. Currently, comments are expected from the Ministry of Water Resources of Turkmenistan and the Mejlis (Parliament) of Turkmenistan on developed recommendations on the methodology for calculation of tariffs for the supply of water and the effect of adaptation measures implemented in the framework of the project on the socio-economic situation of local communities. | At least 2
Outcome 2: Resilience to climate change enhanced in targeted communities through the introduction of community-based adaptation approaches | Indicator 2.1: Number of community based adaptation solutions implemented at the local level upon project closure. | Some of the coping mechanisms employed by farmers, agri-pastoralists and pastoralists in the main agro-ecological systems are increasingly strained due to mounting water deficits. A combination of innovative and traditional measures hasn’t been tested to improve water capture, optimize water demand and improve water efficient applications. Over 2,000,000 people live in the target regions with the majority engaged in agriculture, mainly in marginal lands and having very limited access to stable water delivery services. | At the present moment the adaptation measures are being implemented according to the elaborated plan on 2015. By end of the project all planned adaptation measures will be completed and will benefit the local communities in 3 project regions. More than one water harvesting technique (dams with water reservoirs -10) and saving measure (basins, drip irrigations systems) implemented in Nohur project region which benefit at least 4,000 agri-pastoralists. More than two watering points (7 wells, 11 sardobs - 60 m3, 4 sardobs - 500 m3, kaks, sand dune fixation works on 10 ha and etc.) established in Karakum region, which benefit 8,000 farmers and pastoralists. Collector drainage irrigation improvement measures implemented in the Sakar-Chaga project region (17 water regulating devices, cleaning of 31.5 km farm collector will be completed by the end of 2015, reclamation of 20 hectares of abandoned lands were successfully completed, located in the territory of the Farmers Union Zahmet of Sakarchaga District. These adaptation measures will benefit benefit 20,000 people by end of the project. | At least one water harvesting technique and saving measure implemented in Nohur region to benefit 4,000 agri-pastoralists by end of 2014 At least two watering points established in Karakum region to benefit 8,000 farmers and pastoralists by end of 2014 Set of at least three agronomic measures (terracing, intercropping, saksaul planting) implemented in at least 3 communities by end of 2014 Canal level irrigation improvement measures implemented in the Sakar-Chaga region to benefit 20,000 people by end of the project
| Indicator 2.2: % of population with improved water management practices resilient to climate change impacts in the targeted regions. |  | The implementation of adaptation measures/activities according to the developed investment plans for the three pilot regions is being implemented. In 2014 all the tender bids were prepared and potential performers for their implementation were selected. All expected for the implementation of all adaptaion measures according to AWP 2014 in all 3 project regions were implemented. For implementation of adaptation measures in the Karakum pilot region a Grant Agreement between UNDP and farmer association was signed. The implementation of all planned projects are covering all beneficiaries of all three pilot regions: 1. At least 70% agri-pastoralists of the Nohur; 2. At least 50% farmers in the Karakum desert region; 3. At least 50% farmers in the Sakarchaga area have been assisted so far. | At least 70% agri-pastoralists of the Nohur At least 50% farmers in the Karakum desert region At least 50% farmers in the Sakarchaga area
Output 2.1:At least 4,000 agri-pastoralists of the Nohur mountainous region develop and implement water harvesting and saving techniques (such as slope terracing, small rainwater collection dams, contour and stone bunds, planting pits, tillage, mulching) to improve soil moisture levels | Indicator 2.1.1: water harvesting and saving techniques demonstrated/tested in targeted Nohur area | 0 | Based on VCA assessment and investment plan for the Nohur pilot region, almost all planned adaptation measures have been implemented. The implemented measures include the following: 1. The construction of 7 dams and reservoirs - direct beneficiaries - 320 people; Indirect beneficiaries - 5000 people; 2. Full repair of 3 dams and reservoirs - direct beneficiaries- 40 people; 3. Full repair of 4 springs - direct beneficiaries- 1000 people; 4. The construction of a concrete pool (volume capacity - 400 m3) - direct beneficiaries - 230 people; 5. Full repair and reconstruction of the existing system of drip irrigation on 20 hectares (10 hectares of gardens, 10 hectares of vegetables) - direct beneficiaries - 750 people; 6. Designing a new drip irrigation system in the village of Konegumbez (10 ha) - direct beneficiaries - 100 people; 7. Local control center established - local office; 8. Created a local seedlings nursery; 9. Production of compost and organic- compost cycle completed -14 pits - direct beneficiaries - 750 people; 10. Afforestation measures on 10 ha - direct beneficiaries- 1000 people. The analysis of "cost-benefit" concerning adaptation activities is in process. A Study Tour of the local project coordinators aimed at their capacity building was conducted. Regular inspections, technical control and support for the implementation of the agreed investment activities have also been performed. At the end of 2015 it is expected that the following additioal adaptation measures will be implemented: Repair of the main irrigation pipe in villages Nohur for efficient use of available water resources; Procurement of construction materials and equipment for drip irrigation systems on an area of 5-10 hectares; Construction of drip irrigation systems on an area of 5-10 hectares; Production of information materials for these technologies; and Trainings targeting farmers for the use and maintenance of these systems. | At least one water harvesting technique and saving measure
Output 2.2: At least 8,000 farmers implement community-based well and watering point management measures, including sand fixation and introduction of drought resistant traditional grain varieties in the Karakum desert region | Indicator 2.2.1: Community based well and watering point management measures tested and demonstrated in targeted Karakum area | 0 | Based on VCA assessment and investment plan for the Karakum pilot region, almost all planned adaptation measures have been implemented. The implemented measures include the following: 1. Sand stabilization work was carried out in the area of 10 hectares in Bokurdak village. The row materials to secure 10 hectares of sand were delivered. The works associated with fixing and afforestation of sands on 10 hectares have been completed - direct beneficiaries - more than 5000 people; 2. Designing drip irrigation system in the village of Chalysh (3.02 ha) is completed direct beneficiaries - 40 people; 3. Full repair work of 4 sardobs for livestock farms No. 1 (500 m3) and No. 2 (500 m3) was completed - direct beneficiaries - 1000 people; 4. Construction of new 7 wells for cattle farms No. 1 and No. 2 was completed - direct beneficiaries - 320 people; 5. Repair of existing 6 wells for cattle farms No. 1 and No. 2 was completed - direct beneficiaries - 1000 people; 6. Cleaning of 8 takyrs and kaks - rain wells for livestock farms No. 1 and No. 2 - direct beneficiaries - 200 people; 7. The construction of 11 new sardobs (60 m3) for livestock farm No. 1 and No. 2 - direct beneficiaries - 1000 people; 8. Local control center established - local office; 9. Local nursery created. Analysis of "cost-benefit" of adaptation activities is in the process. By the end of 2015 it is expected that the following adaptation measures will be implemented: Installation of drip irrigation systems in Chalysh area (3.02 ha); and Trainings targeting farmers for the use and maintenance of these systems | At least two watering points
Output 2.3. At least 20,000 farmers in the Sakarchaga area benefit from improved irrigation services through the introduction of canal level, localized management practice | Indicator 2.3.1: Canal level management tested and demonstrated in targeted Sakarchaga area | 0 | Based on VCA assessment and investment plan for the Sakarchaga pilot region, nearly all planned adaptation measures have been implemented. The implemented measures include the following: 1. All 16 planned water regulating deveices were constructed - direct beneficiaries - 1850 people; 2. The works were undertaken through the production association "Marysuvhozhalyk" that serves the region. A mechanized cleaning of farm reservoir with a total length of 31.5 km has been completed in the "Zakhmet" of Sakarçäge District. The first phase of renovation and cleaning 6 km farm collector have also been completed - direct beneficiaries - 5542 people; 3. Local control center was established; 4. Local nursery created. 5. Reclamation of 20 hectares of abandoned lands were successfully completed, located in the territory of the Farmers Union Zahmet of Sakarchaga District - direct beneficiaries 85 people. 6. Equipement was procured and a study of the waterflow of the irrigation water will be conducted - direct beneficiaries - 85 people; At the end of 2015 it is expected to implement the following adaptation measures: Cleaning of on-farm collector (25.5 km), Design and construction: 1. Preparation works on reconstruction and cleaning of the interfarm collector (5 km); 2. series of brochure and booklets according to AWP 2015 will be published; trainings on increasing of capacity will be continued. | At least one measure
Outcome 3: Community-managed water delivery services introduced to benefit over 30,000 farmer and pastoralist communities in the three target agro-ecological zones. | Indicator 3.1 Number of associations with improved institutional capacity to deliver water services to target communities. | The State continues to play a far-reaching and predominant role in the economy and acts as the main provider in ensuring adequate living standards of the population, with subsidies, price controls and the free provision of utilities underpinning the system. This has been possible largely due to revenues from the hydrocarbons sector. However, it poses large budgetary burden and results in unsustainable and ineffective water delivery services to farmer and pastoralists communities. Self-functioning and maintained services with the direct engagement of communities are not practiced. Despite existence of water user and farmer associations their role and capacities are limited to improve the water management and delivery options. | As described under Outcome 1, project support for amending the Water Code is in progress. Once the Code is amended, it will provide stronger underpinnings for improving the functions of community-level water user and farmer asssociations. In the meanwhile, Project team developed a number of training modules targeting local communities to prepare investment proposals while taking into account good practices of adaptation technologies tested in the project. In 2013-2014, 15 training sessions were conducted to local water users, covering the following topics: adaptation to climate change, organizational development of local water users, organization of water user groups and building partnerships, assessment of local needs and needs of water users in planning for local adaptation measures, and development of adaptation projects. On average 375 people participated in each training consisting of leaseholders and team leaders of brigades of F/O, shepherds chekene, bayars, local mirabs, Archins of gengeshes, heads of livestock farms, private farmers, agronomists, hydraulic engineers and other water users participated in these trainings. Several key results ensued: 1. Increased general awareness of water users about climate change and water 2. Participants of the trainings conducted further meetings with local population to distribute knowledge gained in the trainings 3. Identification of local leaders and activists who are willing to participate directly in project activities 4. Composition of the Executive Committee of water users groups, and the total number of 32 people have been identified and approved by the Farmers’ associations in three pilot regions 5. Jointly with the AF national expert on strategic and institutional issues, members of the Executive Committee of water users group have identified and developed goals, objectives and functions of water user groups and the rules of water user groups in the irrigated area of agriculture, in conditions of the desert and mountainous areas, which was approved by the chairmen of F/A of the pilot regions (except for Sakarchaga) translated into the Turkmen language as well 6. Members of the Executive Committee worked out approaches and methods of establishing partnership between water users groups and other Government agencies in the field of water use 7. Members of the Executive Committees were trained on methods of conducting a joint assessment of local community/local water users’ needs. Based on these identified needs, members of water user groups at the first general meetings developed and approved a short term plans for further implementation of adaptation measures in settlements. In order to implement these plans, members of the executive committees of water user groups were trained to methods of writing of investment grant projects. At the end of the training drafts of 12 investments project proposals have been developed. With the active participation of Archins and heads of F/A in the pilot regions during the second general meeting local water users have discussed and voted to approve the final project proposals. | At least 6 associations have clear mandates, institutional capacities and skills to manage and deliver water services to the target communities by end of 2013 At least 6 community plans on water adaptation have been designed and budgeted through the government’s social development programmes by end of the project At least 6 local water adaptation investment projects have been funded through WUA and associated community organizations At least three lessons learned notes per targeted agro-ecological system, developed and widely disseminated through knowledge networks for further replication by end of project
| Indicator 3.2: % of targeted population with more secure access to water services in the face of climate change where communal management systems adopted. |  | Progress is expected after implementation of all planned activities. Implemented adaptation measures will allow to assess their impact on the socio-economic conditions of local communities. In addition, a cost-benefit analysis for each pilot region will be conducted. | By end of the project at least 80% of targeted population of approximately 30,000 people has access to improved water services that are resilient to drought and climate aridification
Output 3.1: Mandates and institutional functions of local associations strengthened to improve local water services that are more resilient to increasing water stress and benefit at least 30,000 farmers and pastoralists | Indicator 3.1.1: Number of associations with modified mandates strengthening their institutional roles to manage and deliver water services to the target communities | 0 | After agreement and approval of establishment WUG by local authorities and farmer associations, a number of WUGs have been established. The project has already established of 6 WUGs (4 on the basis of 4 brigades of farmer association "Zahmet", one in Karakum and one in Nohur). The project will also work to ‘upgrade’ the WUGs into proper WUAs. There is also an ambition to pilot new water tariff through WUG(s). It has been observed that the presence of WUGs have improved community-based water management principles at the local level. They introduce joint planning, management, decision-making and management of hydraulic structures (inter-farm collectors, local dams with water reservoirs, wells, sardobs, kaks and etc.) | At least 6 associations
Output 3.2: Based on VCA assessments, community-based adaptation plans with particular focus on water delivery services designed and implemented through the government’s social development programmes with direct engagement of at least 30,000 farmers and pastoralists | Indicator 3.2.1: Number of community plans has been budgeted through the government’s social development programmes | 0 | With assistance from the project team, investment projects were developed with the active participation of Archins and heads of F/A in the pilot regions during the general meeting, where local water users have discussed and voted to approve the final project proposals. Key findings of the VCA assessment were translated into 11 indicators of climate risks and degrees of change in the last 20 years and 9 indicators of the impact of climatic factors on economic activity of local communities. On this basis, an action plan was developed to reduce the impact of climate risks on the life of local communities in three pilot regions. 10 investment projects have been developed. The best investment project will be implemented. | At least 6 community plans on water adaptation
Output 3.3: At least 6 projects funded up to a total of $400,000 through WUAs and associated community groups | Indicator 3.3.1: Number and value of projects through the WUAs | 0 | The following community projects have been developed in close consultations with local water users. ACTIVITIES: Karakum (AF/UNDP funding): 1. Water supply – Village-1: $35,237 2. Water supply – Village-2: $38,739 3. Water supply – Schools No.7 & No.9: $18,103 4. Water supply – Schools No.15: $16,778 Nohur (AF/UNDP funding): 1. Water supply – 2 basins constr.: $18,914 2. Milk Processing 1 ton/day: $35,500 Sakarchaga (AF/UNDP funding): 1. Water supply – 3000m ditch, 9 water regulating devices: $36,000 2. Water saving – Drip irrigation 0.5 ha demo plot, water basin: $21,659 3. Field rest house (women, children, men) & water reg. dev. 8ea: $23,718 4. Water pump 150kWt and power transformer: $19,700 The total financing expected from UNDP/AF: $264,348; Local contribution: $99,989; TOTAL investment: $364,337 Total direct beneficiaries of the AF Project 2015 year investment activities: KARAKUM: Children - 2425; Women - 3877; Men - 4243; NOHUR: Children - 373; Women - 843; Men - 870; SAKARCHAGA: Children - 5190; Women - 3880; Men - 5380; TOTAL: Children - 8675; Women - 8600; Men - 9806 | At least 6 projects of a total budget of $400,000
Output 3.4: Lessons learned on community-based adaptation options under various agro-climatic conditions of Turkmenistan disseminated through ALM and other networks | Indicator 3.4.1: Number of lessons learned notes formulated | 0 | Lessons learned were formulated in the form of articles, press releases on the UNDP and ALM website. For reporting period 18 articles, press releases in local newspapers and UNDP website. In addition, the experience from the AF-financed project was shared with a group of experts and specialists from Kazakhstan (topics included improvement of legal framework on sustainable pasture management and land resources and discussion of recommendations on additions to the national legislation of Turkmenistan). | At least three lessons learned
| Indicator: 3.4.2: Number of lessons learned included in the ALM and other knowledge networks | 0 | A regular and systematic publication of project news and its achieved results posted on the website of UNDP (among them, corresponding reports, documents and conclusions for submission to interested parties). The wide-spread dissemination of project results in the training mechanisms of ALM adaptation and in other networks. The participation and cooperation with other project initiatives and participation in their activities (e.g. UNDP Climate Risk Management in Turkmenistan). The Project Steering Committee meeting was held, and project management and support was provided for a national seminar dedicated to the International Environment Day - June 5, 2014. | At least three lessons learned

## Lessons Learned
QUALITATIVE MEASURES and LESSONS LEARNED
Please complete the following section every reporting period
Implementation and Adaptive Management | Response
What implementation issues/lessons, either positive or negative, affected progress? | Positive lessons: - Local community did not accept the most advanced technologies such as the introduction of solar panels for water exctraction from wells and the use of wind energy, and asked to place more emphasis on traditional folk technologies. Consultative approach adopted in the project resulted in the use of technologies that are more acceptable by end-users. However, it also indicates the need for longer term awareness raising if modern technologies are proven to be more cost-effective; - Introduction of the investment plan on the implementation of methods and technologies in the context of climate change was carried out from the bottom-up i.e. taking into account the needs of local communities. As a result, after the implementation of adaptation measures, it is expected that the maintenance of water supply systems will be strengthened; - Solution of project issues accelerated and the efficiency of project tasks increased after establishment of highly qualified project team of national and international experts with scientific and practical experience in implementing similar projects. - It was important to spend time and resources to obtain buy-ins from local authorities and local communities in 3 pilot regions to ensure smooth implementation of the project. - Cooperation with other donor programmes was very useful, allowing to pool resources (work with CRM in Turkmenistan project, including joint workshops, shared VRA work). UNDP has been providing policy and technical support to the government’s endeavors for improving water management through the AF project and the UNDP Regional project on "Climate Risk Management in Central Asia" (CRM project). The two projects adopted the approach to combine the demonstration of community-based water efficiency measures and providing policy advisory of improving national water legislation, in order to ensure the sustainability of the project results. - International best practice is important for agricultural system (israel study tour, drip irrigation, WUA structures) Challenges: The GoT procedure of the adoption of draft of legal documents developed by the project team takes a long time (the project developed a package of amendments, additions and changes to the draft Water Code of Turkmenistan and submitted to the Ministry of Water Economy). An important lesson documented in the annual PPR for 2014 (“Changing the legislative basis to recognize climate impacts is a multi-year process, and dependent upon national timetables and processes, rather than the project”) remains valid.
Were there any delays in implementation? If so, include any causes of delays. What measures have been taken to reduce delays? | Project Manager started to meet regularly with the Senior Management of UNDP. Meetings with them helped promptly to solve a lot of issues.
Describe any changes undertaken to improve results on the ground or any changes made to project outputs (i.e. changes to project design) | No significant changes in the reporting period.
How have gender considerations been taken into consideration during the reporting period? What have been the lessons learned as a consequence of inclusion of such considerations on project performance or impacts? | During the reporting period (implementation of investment plans, seminars, trainings, round tables and etc.) women, land owners, doctors and teacher were actively engaged in the implementation of all project activities. As a result, the project team noticed during meetings with them that women continue to concentrate their attention on improving the social conditions of life (construction of kindergartens, construction of enterprises related to locl crafts (carpet weaving , embroidery, wool processing etc.)
Please complete the following section at mid-term and project completion
Lessons for Adaptation | Response
Climate Resilience Measures
What have been the lessons learned, both positive and negative, in implementing climate adaptation measures that would be relevant to the design and implementation of future projects/programmes for enhanced resilience to climate change? | - Local communities in three pilot regions began to receive benefits from the introduction of all implemented investment projects (interest of representative of local communities in the implementation of innovative technologies in the context of climate change increased). People feel the real results of the implemented adaptation projects and express their gratitude and hope that this work will be continued in the future. - Changing the legislative basis to recognise climate impacts is a multi-year process, and dependent upon national timetables and processes, rather than project - Book on "Natural pastures and development of distant pastures in Turkmenistan" in the framework of the project "Addressing Climate Change Risks to Farming Systems in Turkmenistan at the national and local levels" was distributed among stakeholders and it is widely used by scientists and specialists and higher education institutions. At the present time, book (monography) on Sustainable management of water resources in Turkmenistan in the context of climate change with active participation of all national experts and specialist is being prepared.
What is the potential for the climate resilience measures undertaken by the project/programme to be replicated and scaled up both within and outside the project area? | Medium - High: This is currently promoted in the following ways: - High level discussions with government over linking project and national investment plans, field trips, investment plans - The gained project experience has attracted attentions not only from local community but also international specialists and experts. Within the framework of "South-South" cooperation representatives of Kazakhstan want to learn our experience and implement following technologies: sand dune fixation, construction of wells, sardobs, drip irrigation systems and methods of implementation of adaptation activities on the ground.
Concrete Adaptation Interventions
What have been the lessons learned, both positive and negative, in implementing concrete adaptation interventions that would be relevant to the design and implementation of future projects/programmes implementing concrete adaptation interventions? | Lessons include: - Measures requiring state involvement in design and permitting have long lead times for development - Community level adaptation measures (pasture wells, sustainable agriculture, soil fixation) are better pursued through grant arrangements than through commercial tender - Direct personal contribution of local communities in the implementation of adaptation measures. - Local communities are aware of the strengths and opportunities in the implementation of a particular adaptation measures - Achieved results of this project can be used as a model for buildings relationships with the local community, development of plans and jointly their implementation.
What is the potential for the concrete adaptation interventions undertaken by the project/programme to be replicated and scaled up both within and outside the project area? | High: - Many activities are reflected in national plans. Many innovative activities will be replicated on similar conditions in different regions of Turkmenistan and also in Central Asia, in particular in the Republic of Kazakhstan. . - Innovative approaches, such as drip irrigation, laser levelling were positive assessed and recommend by the national ministries
Community/National Impact
What would you consider to be the most successful aspects for the target communities? | - Benefits of increased water availability and improved economic returns from agriculture. As an example of the above is the introduction of drip irrigation systems and laser leveling systems. - Involvement in adaptation planning and investment processes - Training on risks and climate vulnerability - Increase the capacity of knowledge of local communities in the context of climate change - Relationship between local communities and local authorities in place strengthened
What measures are/have been put in place to ensure sustainability of the project/program results? | Measures include: - Training of farming communities in climate resilient planning approaches - Establishment of water user groups (WUG) to maintain and develop farm level water mangaement practices and infrastructure post project - Proposals to develop more progressive water tariffs and water user associations in law - Hydro engineering devices in various pilot regions (water regulating devices, wells, sardobs, dams with water reservoirs, springs, etc.) constructed
What measures are being/could have been put in place to improve project/program results? | Measures include: - Accelerated procurement processes for goods and services - Better quality of technical parameters and specifications to be provided by the project team for tender organization
Knowledge Management
How has existing information/data/knowledge been used to inform project development and implementation? What kinds of information/data/knowledge were used? | Information used includes: - Agriculture sector and national cliamte data has fed into the analysis of the national level socio-economic impact of climate change - Regional vulnerability and socio-economic data has been used as part of the Vulnerability Risk Analysis (VRA) for pilot sites - Over the past period Book on "Natural pastures and development of distant pastures in Turkmenistan" in the framework of the project "Addressing Climate Change Risks to Farming Systems in Turkmenistan at the national and local levels" was distributed among stakeholders and it is widely used by scientists and specialists and higher education institutions (2 languages) was printed out.
If learning objectives have been established, have they been met? Please describe. | Learning objectives focus primarily around the Annual Work Plan 2014-15. Trainign modules for local communities were developed by AF National Trainer on community mobilization and have been implemented by International and National team of experts.
Describe any difficulties there have been in accessing or retrieving existing information (data or knowledge) that is relevant to the project. Please provide suggestions for improving access to the relevant data. | Difficulties are still relevant and include: - Access to government socio-economic and climate data is restricted, which has been a challenge for the national socio-economic analysis of climate change - Access to detailed agriculture and water sector investment plans and budgets is restricted, making it challenging to assess the existing level of adaptation mainstreaming - Access to local socio-economic and other local government data is restricted Options include direct contact with national inistries and local government, and the conducting of project specific surveys where data is required. Data for VCA assessment were collected by national and international experts from the local population of the three project regions.
Has the identification of learning objectives contributed to the outcomes of the project? In what ways have they contributed? | Learning objectives contributed to the outcomes of the project, in partciular local communities increased awareness about the sustainable and efficient use of water resources

## Results Tracker
Results Tracker for Adaptation Fund (AF) Projects
Goal: Assist developing-country Parties to the Kyoto Protocol that are particularly vulnerable to the adverse effects of climate change in meeting the costs of concrete adaptation projects and programmes in order to implement climate-resilient measures. Impact: Increased resiliency at the community, national, and regional levels to climate variability and change.
Important: Please read the following Results Framework and Baseline Guidance (also posted on the Adaptation Fund website) before entering your data
Link: http://www.adaptation-fund.org/sites/default/files/Results%20Framework%20and%20Baseline%20Guidance%20final.pdf
Objective: To strengthen water management practices at national and local levels in the context of climate change risks induced water scarcity to farming systems in Turkmenistan
OBJECTIVE 1
Fund Outcome | Please select from dropdown menu below | Fund Outcome Indicator | Please select from dropdown menu below | Target at CEO Endorsement (see Units in next sheet) | Baseline (see Units in next sheet) | Mid-term Results | Terminal Results
Outcome 1: Reduced exposure at national level to climate-related hazards and threats Outcome 2: Strengthened institutional capacity to reduce risks associated with climate-induced socioeconomic and environmental losses Outcome 3: Strengthened awareness and ownership of adaptation and climate risk reduction processes at local level Outcome 4: Increased adaptive capacity within relevant development and natural resource sectors Outcome 5: Increased ecosystem resilience in response to climate change and variability-induced stress Outcome 6: Diversified and strengthened livelihoods and sources of income for vulnerable people in targeted areas Outcome 7: Improved policies and regulations that promote and enforce resilience measures | 7 | 1. Relevant threat and hazard information generated and disseminated to stakeholders on a timely basis 2.1. No. and type of targeted institutions with increased capacity to minimize exposure to climate variability risks 2.2. Number of people with reduced risk to extreme weather events 3.1. Percentage of targeted population aware of predicted adverse impacts of climate change, and of appropriate responses 3.2. Modification in behavior of targeted population 4.1. Development sectors' services responsive to evolving needs from changing and variable climate 4.2. Physical infrastructure improved to withstand climate change and variability-induced stress 5. Ecosystem services and natural assets maintained or improved under climate change and variability-induced stress 6.1. Percentage of households and communities having more secure (increased) access to livelihood assets 6.2. Percentage of targeted population with sustained climate-resilient livelihoods 7. Climate change priorities are integrated into national development strategy | 7 | 7.3: Some (integrated) in Water code of Turkmenistan, (2004) A package of amendments to water code with proposed water tariff and other economic instruments developed and submitted for adoption by end of 2012 Update of the water code to ensure explicit recognition of on climate impacts on water resource availability by end of 2013 At least 2 sets of sub- regulations developed under the Water Code to implement a) progressive and differentiated tariffs, b) support for water delivery services under communal management | 7.2: Most not integrated in Water code of Turkmenistan, (2004). The National Strategy on Climate Change was adopted. There is sections on the use of adaptive techniques in agriculture. Government has made progressive steps towards improving water management systems. It invests heavily in the improvement and upgrade of water infrastructure and looks out for more advanced technologies. However, water policies remain outdated as well as poorly enforced due to underdeveloped regulations and subsidiary legislation. Tools and methods are missing to indentify the most cost-effective adaptation options in the water policies. Water pricing is largely inadequate. The current water policies burden the state budget and do not free resources for service improvement to farmers, especially local small holders. At the same time, farmers involved in large scale productions of water thirsty crop varieties do not receive adequate price signals to use water more efficiently. Given the increasing water shortages and priorities assigned to cash crop production the small holder subsistence farmers bear a disproportionate burden of exacerbating water deficits. | 1 (None) as of today. As reported elsewhere in this PPR, recommendations and ammendments have been put forward for integration in a revised Water Code. However, the new revision has not been approved as of today
OBJECTIVE 2
Fund Output | Please select from dropdown menu below | Fund Output Indicator | Please select from dropdown menu below | Target at CEO Endorsement (see Units in next sheet) | Baseline (see Units in next sheet) | Mid-term Results | Terminal Results
Output 1: Risk and vulnerability assessments conducted and updated at a national level Output 2.1: Strengthened capacity of national and regional centres and networks to respond rapidly to extreme weather events Output 2.2: Targeted population groups covered by adequate risk reduction systems Output 3: Targeted population groups participating in adaptation and risk reduction awareness activities Output 4: Vulnerable physical, natural, and social assets strengthened in response to climate change impacts, including variability Output 5: Vulnerable physical, natural, and social assets strengthened in response to climate change impacts, including variability Output 6: Targeted individual and community livelihood strategies strengthened in relation to climate change impacts, including variability Output 7: Improved integration of climate-resilience strategies into country development plans | 3 | 1. Relevant threat and hazard information generated and disseminated to stakeholders on a timely basis 2.1. No. and type of targeted institutions with increased capacity to minimize exposure to climate variability risks 2.2. Number of people with reduced risk to extreme weather events 3.1. Percentage of targeted population aware of predicted adverse impacts of climate change, and of appropriate responses 3.2. Modification in behavior of targeted population 4.1. Development sectors' services responsive to evolving needs from changing and variable climate 4.2. Physical infrastructure improved to withstand climate change and variability-induced stress 5. Ecosystem services and natural assets maintained or improved under climate change and variability-induced stress 6.1. Percentage of households and communities having more secure (increased) access to livelihood assets 6.2. Percentage of targeted population with sustained climate-resilient livelihoods 7. Climate change priorities are integrated into national development strategy | 03.янв | 3.4: Mostly aware At least 70% of agri-pastoralists and farmers of the Nohur mountainous region trained, develop and implement water harvesting and saving techniques. At least one water harvesting technique and saving measures implemented in Nohur region to benefit 70% agri-pastoralists At least 50% of farmers implement community-based well and watering point management measures, including sand fixation. At least two watering points established for at least 50%. Set of at least three agronomic measures implemented in at least 3 communities At least 50% farmers in Sakarchaga area to benefit from improved irrigation services through the introduction of canal level, localized management practice. | 3. 1: Aware of neither predicted adverse impacts of climate change nor of appropriate responses. Some of the coping mechanisms employed by farmers, agri-pastoralists and pastoralists in the main agro-ecological systems are increasingly strained due to mounting water deficits. A combination of innovative and traditional measures hasn’t been tested to improve water capture, optimize water demand and improve water efficient applications. Over 2,000,000 people live in the target regions with the majority engaged in agriculture, mainly in marginal lands and having very limited access to stable water delivery services. | 65-70 % of populations that were aware of the adverse impact of climate change in the target regions
OBJECTIVE 3
Fund Outcome | Please select from dropdown menu below | Fund Outcome Indicator | Please select from dropdown menu below | Target at CEO Endorsement | Baseline | Mid-term Results | Terminal Results
Outcome 1: Reduced exposure at national level to climate-related hazards and threats Outcome 2: Strengthened institutional capacity to reduce risks associated with climate-induced socioeconomic and environmental losses Outcome 3: Strengthened awareness and ownership of adaptation and climate risk reduction processes at local level Outcome 4: Increased adaptive capacity within relevant development and natural resource sectors Outcome 5: Increased ecosystem resilience in response to climate change and variability-induced stress Outcome 6: Diversified and strengthened livelihoods and sources of income for vulnerable people in targeted areas Outcome 7: Improved policies and regulations that promote and enforce resilience measures | 2 | 1. Relevant threat and hazard information generated and disseminated to stakeholders on a timely basis 2.1. No. and type of targeted institutions with increased capacity to minimize exposure to climate variability risks 2.2. Number of people with reduced risk to extreme weather events 3.1. Percentage of targeted population aware of predicted adverse impacts of climate change, and of appropriate responses 3.2. Modification in behavior of targeted population 4.1. Development sectors' services responsive to evolving needs from changing and variable climate 4.2. Physical infrastructure improved to withstand climate change and variability-induced stress 5. Ecosystem services and natural assets maintained or improved under climate change and variability-induced stress 6.1. Percentage of households and communities having more secure (increased) access to livelihood assets 6.2. Percentage of targeted population with sustained climate-resilient livelihoods 7. Climate change priorities are integrated into national development strategy | 02.янв | 2. 1: WUAs established/strengthened in local communities in three pilot regions. Mandates and institutional functions of local associations strengthened to improve local water services that are more resilient to increasing water stress and benefit at least 40% farmers and pastoralists. At least 6 associations have clear mandates, institutional capacities and skills to manage and deliver water services to the target communities by end of 2013 At least 6 community plans on water adaptation have been designed and budgeted through the government’s social development programmes by end of the project At least 4 local water adaptation investment projects have been funded through WUA and associated community organizations By end of the project at least 80% of targeted population of approximately 50% has access to improved water services that are resilient to drought and climate aridification. At least three lessons learned notes per targeted agro-ecological system, developed and widely disseminated through knowledge networks for further replication by end of project | 2.1 The State continues to play a far-reaching and predominant role in the economy and acts as the main provider in ensuring adequate living standards of the population, with subsidies, price controls and the free provision of utilities underpinning the system. This has been possible largely due to revenues from the hydrocarbons sector. However, it poses large budgetary burden and results in unsustainable and ineffective water delivery services to farmer and pastoralists communities. Self-functioning and maintained services with the direct engagement of communities are not practiced. Despite existence of water user and farmer associations their role and capacities are limited to improve the water management and delivery options. | 6 local institutions that become responsible for local water management have been established with assistance from the AF resources. Several capacity building trainings and exercises have been delivered to date to strenghten their institutional functions.

## Units for Indicators
Fund Outcome Indicator Units
1. Generation of relevant data, Stakeholders, and Timeliness 2.1. Include both qualitative and quantitative measures of capacity level within targeted institutions 2.2. Number (men and women and other vulnerable groups) 3.1. Use scale from 1 to 5: 5: Fully aware 4: Mostly aware 3: Partially aware 2: Partially not aware 1: Aware of neither predicted adverse impacts of climate change nor of appropriate responses 3.2. Use scale from 1 to 5: 5: All 4: Almost all 3: Half 2: Some 1: None 4.1. Summarize in an overall scale (1-5): 5: Highly responsive (All defined elements ) 4: Mostly responsive (Most defined elements) 3: Moderately responsive (Some defined elements) 2: Partially responsive (Lacks most elements) 1: Non responsive (Lacks all elements ) 4.2. Summarize in an overall scale (1-5): 5: Fully improved 4: Mostly Improved 3: Moderately improved 2: Somewhat improved 1: Not improved 5. Depends on the targeted natural asset: Biological (species): measure through changes in population numbers (dynamics, structure, etc.) Land: measure changes in hectares. Baseline data will be necessary to estimate the change. Supporting indicators baseline and target (as well as contextual information) are needed such as the following: Farmers adopting recommended technologies, Ha. of land improved, Average deforestation rate Etc. Use scale from 1 to 5. 5: Very effective (All elements are present) 4: Effective (Most elements are present) 3: Moderately effective (Some elements are present) 2: Partially effective (Most elements are not present) 1: Ineffective (No elements are present) 6.1. Summarize in an overall scale (1-5): 5: Very high improvement 4: High improvement 3: Moderate improvement 2: Limited improvement 1: No improvement 6.2. Household income by source of livelihood in project area (USD) prior and post project intervention 7. Summarize in an overall scale (1-5). 5: All (Fully integrated) 4: Most 3: Some 2: Most not integrated 1: None
Fund Output Indicator Units
1.1. Number, sector(s) and level(s) of projects or interventions in separate fields of monitoring plan 1.2. Number 2.1.1. Number of staff (male/female) of targeted institutions: a. Obtain baseline information: total number of staff from targeted institutions b. Define target 2.1.2. Number of staff (male/female) of targeted institutions: a. Obtain baseline information: total number of staff from targeted institutions b. Define target: needs to be defined by project proponents 2.2.1. Quantitative: Percentage (includes women – and other vulnerable groups – and men). Qualitative: Adequacy: include direct analysis of major areas; adequacy/effectiveness of systems or analysis of perceptions of populations and institutions. 2.2.2. Number (broken down by gender and, if possible, by vulnerable groups defined in the area of intervention) of people 3.1. Number and type (in separate columns) at local level. 3.2. Number 4.1. Number and type 4. 2. Number and type (entered in separate columns) 5. Number of interventions by type of natural asset and intervention 6.1. Number and type (in separate columns of monitoring plan) 6.2. Income sources per household; description of income source and number of households. 7.1. Number/Sector 7.2. Number; Effectiveness (see previous indicator) through enforcement level.