## Overview
Project Performance Report (PPR)
| Period of Report (Dates) | 16 September 2015-31 July 2016
| Project Title: | Climate Change Adaptation Programme in the Coastal Zone of Mauritius
| Project Summary: | The objective of the project is “to increase climate resilience of communities and livelihoods in coastal areas of Mauritius”. The project comprises of five key outcomes as follows: 1. Increased adaptive capacity within relevant development and natural resources sectors. It comprises of the application of adaptation measures to protect currently vulnerable coastal ecosystem and community at three priority sites: Mon Choisy, Quatre Soeurs and Rivière des Galets. 2. Reduced exposure at national level to climate-related hazards and threats. This component will focus on development of an Early Warning System for incoming Storm Surge manned on 24/7 basis such that the coastal communities in the Republic of Mauritius are able to safely evacuate prior to future storm surge events. 3. Strengthened institutional capacity to reduce risks associated with climate-induced socio-economic losses. This component is targeted to build capacity for ongoing replication of effective coastal adaptive measures by both the Government and private sector. Capacity development will cover a range of Ministries, NGOs, the private sector and the community at large. Short courses on Coastal Engineering, Cost Benefit Analysis of Coastal Adaptation Measures will be developed and delivered. A Handbook on coastal adaptation for coastal communities will packaged as training modules for the coastal communities. 4. Improved Policies and Regulations that promote and enforce resilience measures A National Coastal Zone Adaptation Strategy that addresses all climate perceived risks in the Coastal Zone of Republic of Mauritius will be determined. 5. Effective capturing and dissemination of lessons from the applied activities in the programme. Public awareness campaigns on climate change in the coastal zone of Mauritius will be developed and broadcasted in the media. The project will also have a regional dimension whereby the lessons learned from this Adaptation Project will be disseminated to other countries in the Southern Indian Ocean.
|  |  | Countries | Project Type: |  | GEF Focal Area: | GEF 4 Focal Areas | GEF 2 / 3 Operational Programme: | Overall Rating of the project in the evaluation by the project evaluator: | GEF-4 Focal Area Strategic Program: | GEF-3 Focal Area Strategic Program:
| Database Number: |  | Afghanistan | FP | Yes | Biodiversity | 1 | 1 | U | BD-SP1-PA Financing | 1: Arid & semi-arid ecosystems
Implementing Entity (IE) [name]: |  | United Nations Development Programme (UNDP) | Albania | MSP | No | Climate Change Adaptation | 2 | 2 | S | BD-SP2-Marine PA | 2: Coastal, marine & freshwater ecosystems
| Type of IE: | Multilateral Implementing Entity | Algeria | EA |  | Climate Change Mitigation | 3 | 3 | MU | BD-SP3-PA Networks | 3: Forest ecosystems
| Country(ies): | Mauritius | Angola |  |  | International Waters | 5 | 5 | Good | BD-SP5-Markets | 13: Conservation and Sustainable Use of Biological Diversity Important to Agriculture
Relevant Geographic Points (i.e. cities, villages, bodies of water): |  | Port Louis | Argentina |  |  | Multiple Focal Area |  |  |  | BD-SP7-Invasive Alien Species(IAS) | 6: Promoting the adoption of renewable energy by removing barriers and reducing implementation costs
[8 empty] | CC-SP2- Industrial EE | 8: Waterbody based operational program
| Project Milestones | [6 empty] | CC-SP3-RE,CC-SP4-Biomass | 9: Integrated Land and Water multiple focal area
| Milestone |  | Bahamas | [6 empty] | CC-SP5-Transport | 10: Contaminants based operational program
AFB Approval Date: |  | 2011-09-15
IE-AFB Agreement Signature Date: |  | 2012-07-19 | [6 empty] | CC-SP6-LULUCF | 12: Integrated Ecosystem Management
Start of Project/Programme: |  | 2012-08-30 | [6 empty] | Cross cutting capacity building | 14: Persistent Organic Pollutants
Mid-term Review Date (if planned): |  | 2014-10-27
| Terminal Evaluation Date: | 2018-01-01
|  | List documents/ reports/ brochures / articles that have been prepared about the project. | Cyprus
|  | AF Project Reports: • Inception Workshop Report (04 October 2012) • Quarterly Reports submitted to the UNDP CO (Progress Reports/Financial Reports/Quarterly Work Plans) • Mid Term Evaluation Report • AF Project Audit Report for the period 01 January 2012 to 31 December 2014 • AF Project Audit Report for the period 01 January 2015 to 31 December 2015 • Project Performance Report (30 August 2012-30 August 2013) • Project Performance Report (30 August 2013-30 August 2014) • Project Performance Report (15 August 2014-15 September 2015) Reports by Project Outcomes Outcome 1 : Construction of Refuge Centre at Quatre Soeurs Reports • Expressions of Interest document for Consultancy Services for Design, Preparation of Bid Document and Supervision of Works for Construction of a Refuge Centre, Drainage System and Ancillary Works at Quatre Soeurs • Bid Evaluation Report for Expressions of Interest for Consultancy Services for Design, Preparation of Bid Document and Supervision of Works for the Construction of a Refuge Centre, Drainage System and Ancillary Works at Quatre Soeurs • Request for Proposal document for Consultancy Services for Design, Preparation of Bid Document and Supervision of Works for Construction of a Refuge Centre, Drainage System and Ancillary Works at Quatre Soeurs • Technical Bid Evaluation Report for the Request for Proposal for Consultancy Services for Design, Preparation of Bid Document and Supervision of Works for Construction of a Refuge Centre, Drainage System and Ancillary Works at Quatre Soeurs • Financial Bid Evaluation Report for the Request for Proposal for Consultancy Services for Design, Preparation of Bid Document and Supervision of Works for Construction of a Refuge Centre, Drainage System and Ancillary Works at Quatre Soeurs Consultancy Services for the Design, Preparation of Bid Document and Supervision of Works for the Construction of a Refuge Centre, Drainage System and Ancillary Works at Quatre Soeurs Reports/contracts signed • Signed Contract Agreement • Inception Workshop Report • Detailed Technical Assessment Reports (including survey reports, geotechnical investigation reports & climate change risk assessment) • Architectural design of Refuge Centre and detailed design reports including detailed cost estimates • Evacuation Plan for the vulnerable community exposed to coastal inundation at Quatre Soeurs • EIA Report • Bid Documents | Czech Republic
Consultancy Services for Coastal Adaptation works at Mon Choisy and Riviere des Galets Reports/contracts • Signed Contract Agreement • Inception Workshop Report • Detailed Technical Assessment Reports for Mon Choisy and Riviere des Galets • Report on Adapting to Sea Level Rise: A Baseline for Protection and Managed Retreat in Riviere des Galets • Adaptation Options Report for Mon Choisy and Riviere des Galets • National Validation Workshop Report • Report on An Economic Valuation and Cost Benefit Analysis of Adaptation and Enhanced Ecosystem Resilience for Mon Choisy Beach • Cost Benefit Analysis for adaptation to Sea Level Rise: Protection or Managed Retreat in Rivière des Galets • Feasibility Study Reports for Mon Choisy and Riviere des Galets • Design Report for Riviere des Galets • Design Report for Mon Choisy • Independent Technical Review Report for Coastal Adaptation Measures at Mon Choisy • Independent Technical Review Report for Coastal Adaptation Measures at Riviere des Galets Environment Impact Assessment (EIA) Reports • Signed Contract Agreement • Preliminary EIA Report-Coastal Adaptation Works Programme for Proposed Offshore Breakwater Structure and Beach Upgrading at Mon Choisy • Social Impact Assessment Report-Coastal Adaptation Works Programme for Proposed Offshore Breakwater Structure and Beach Upgrading at Mon Choisy • Final EIA Report-Coastal Adaptation Works Programme: Proposed Sea Defense Revetment Wall at Riviere des Galets • Design Review Report of Coastal Adaptation Measures at Riviere des Galets • Design Review Report of Coastal Adaptation Measures at Mon Choisy Outcome 2: Early Warning System for incoming Storm Surge in the Republic of Mauritius Reports/contracts Signed • Contract Agreement for Consultancy Services for implementation of an Early Warning System for incoming Storm Surge in the Republic of Mauritius • Inception Workshop Report • Detailed Technical Assessment Report for implementation of an Early Warning System for Storm Surge in the Republic of Mauritius • System Design Report for implementation of an Early Warning System for Storm Surge in the Republic of Mauritius • Project Completion Report Outcome 3-Training Training Manuals/Handbooks/Contracts signed • Request for Proposal document for consultancy services for the design and delivery of a CPD course on Disaster Risk Reduction in the Coastal Zone of Mauritius • Request for Proposal document for consultancy services for the design and delivery of a CPD course on Integrated Coastal Zone Management • Signed Contract Agreements • Training Manual on Coastal and Marine Environment for Engineers • Training Manual on Coastal Protection Works • Training Manual on Cost Benefit Analysis for Coastal Zone Management and Adaptation Options to Climate Change in Mauritius • Draft Handbook on Integrated Coastal Zone Management
Outcome 4-Policy Mainstreaming Reports • Expressions of Interest document for recruitment of a Consultant/expert for Policy Mainstreaming • Bid Evaluation Report for shortlisting of consultant/experts for Policy Mainstreaming (Expression of Interest stage) • Request for Proposal document for recruitment of a consultant/expert for Policy Mainstreaming (1st & 2nd round of procurement) • Revised Request for Proposal document for Consultancy Services for the preparation of National Coastal Zone Strategy for the Republic of Mauritius Press/media: Outcome 1 • https://undp.exposure.co/20000-mangroves-strong- access to storyline on mangroves plantation project at Grand Sable • CNN piece on coastal adaptation work at Quatre Soeurs/Grand Sable: http://edition.cnn.com/video/data/2.0/video/international/2014/06/16/spc-inside-africa-mauritius-a.cnn.html • http://www.lemauricien.com/article/face-aux-effets-nefastes-du-changement-climatique-les-villageois-grand-port-s-engagent-prote- Face aux effets néfastes du changement climatique: Les villageois de Grand-Port s’engagent à protéger leur region • http://glispa.org/images/glispa/events/12.4.2013-Solution-Search-Press-Release.pdf: GLISPA!Highlight-Mauritian!NGO!Wins!Island!Bright!Spot!Award Outcome 2 • CNN piece on upcoming Early Warning System- http://edition.cnn.com/video/data/2.0/video/international/2014/06/16/spc-inside-africa- mauritius-c.cnn.html • Signature of MoU with Mauritius Meteorological Services-http://www.gov.mu/English/News/Pages/default.aspx-access to events •Risques de raz-de-maree-L’Express dated 22 January 2015- http://www.lexpress.mu/article/257846/risques-raz-maree •Ce Systeme d’alerte sauvera des vies-Le Mauricien dated 14 March 2015- http://www.lemauricien.com/article/deepak-vatvani- Deepak Vatvani (Conseiller de la firme Deltares) •MoU with Mauritius, Deltares and UNESCO-IHE- https://www.deltares.nl/en/news/mou-with-mauritius-deltares-and-unesco-ihe •Early-Warning System for storm surge and tide in Mauritius- https://www.deltares.nl/en/projects/implementation-of-an-early-warning-system-for-storm-surge-and-tide-in-mauritius •Cyclone Storm Surge Forecasts for Mauritius- https://www.deltares.nl/en/news/cyclone-storm-surge-forecasts-for-mauritius Outcome 3: Website link: http://lcms.uom.ac.mu/lms/course/view.php?id=585 Website link: http://lcms.uom.ac.mu/lms/course/search.php?search=coastal+engineering Above link to access to course materials for courses completed under the AF Project in Mauritius & Rodrigues: a. Short Course on Coastal and Marine Environment for Engineers (Rodrigues & Mauritius) b. Short Course on Coastal Protection Works (Mauritius) c. Short Course on Decision analysis of coastal management and adaptation options to climate change (Mauritius) d. Short Course on Design of Coastal Structures (Soft Measures) (Mauritius) e. Short Course on Cost Benefit Analysis of Coastal Management and Adaptation Options to Climate Change in (Rodrigues) f. Short Course on Ocean Data Collection and Analysis (Mauritius) g. Short Course on Climate Change and Coastal Zone Management (Mauritius) h. Short course on Introduction to Open Source Geospatial Tools (Mauritius) i. Short course on Disaster Risk Reduction in the Coastal Zone of Mauritius j. Short course on Integrated Coastal Zone Management
Outcome 4 (Website links) • Expressions of interest for recruitment of a consultant/expert for Policy Mainstreaming- https://Jobs-admin.undp.org, http://ppo.govmu.org Outcome 5 Website links: mbc.intnet.mu to access Short video clips for: a. Launching ceremony for Marine Mobile Education Unit b. Educational tour at Ile D’Ambre c. Signature of MoU between Attitude Group and Ministry i.c.w. ‘Greening Mauritius’ campaign including plantation of mangroves Facebook.com: Reef Conservation a. Sensitisation Campaigns carried out by Bis Lamer under the Adaptation Fund Board. Other Website links • Activities under the AF Project in the presence of Honourable Minister and UNDP Resident Representative- http://environment.govmu.org/English/Pages/default.aspx Articles on the Adaptation Fund Project • Republic of Mauritius Portal (31 August 2012) • Commission de L’Ocean Indien (ACCLIMATE) 03 September 2012 • GLISPA Highlight: Mauritian NGO Wins Island Bright Spot Award- 4 December 2013 • ADD-GASAT International Conference (17-19 April 2014) • Quarterly Newspaper Vol 1 of the Ministry of Environment, Sustainable Development and Disaster and Beach Management: October to December 2015 • Le Matinal dated 23.01.15 • Le Mauricien dated 22.01.15 • L’Express dated 22.01.15 • Le Mauricien dated 14.03.15 Mangrove Plantation Project at Quatre Soeurs/Grand Sable • Le Mauricien dated 09 March 2013 • Le Mauricien dated 15 June 2013 • Le Mauricien dated 14 June 2014 • Le Matinal dated 17 June 2014 • Le Mauricien dated 26 July 2015 • Samedi Plus 02-08 April 2016 Riviere des Galets • Le Matinal dated 26 March 2013 • Le Defi Quotidien dated 16 June 2014 • L’Express dated 05 May 2016 Early Warning System • The Economist magazine dated 12 January 2013 • L’Express dated 16 January 2013 • Le Mauricien dated 14 March 2014 • Le Defi Quotidien dated 21 March 2014 • Week End dated 23 March 2014 • Early Warning System for storm surge set up before next cyclonic season (http://www.govmu.org/English/News/Pages/Early-Warning-System-for-storm-surge-set-up-before-next-cyclonic-season.aspx)-21 January 2015 • Early-Warning System for storm surge and tide in Mauritius (https://www.deltares.nl/en/projects/implementation-of-an-early-warning-system-for-storm-surge-and-tide-in-mauritius) • Cyclone Storm Surge Forecasts for Mauritius (https://www.deltares.nl/en/news/cyclone-storm-surge-forecasts-for-mauritius) • MoU with Mauritius, Deltares and UNESCO-IHE (https://www.deltares.nl/en/news/mou-with-mauritius-deltares-and-unesco-ihe) • Le Matinal dated 23 January 2015 • Le Mauricien dated 22 January 2015 • L'Express dated 22 January 2015 • Le Mauricien dated 14 March 2015 • Le Matinal dated 12 August 2015 • Le Mauricien dated 10 August 2015
Training and Capacity Building • Le Mauricien dated 10 February 2016 Partnerships: a. Memorandum of Agreement signed between Ministry of Environment, Sustainable Development, Disaster and Beach Management and Grand Sable Fishermen Association (NGOs) on 10 April 2013 b. Memorandum of Agreement signed between Ministry of Environment, Sustainable Development, Disaster and Beach Management and Grand Sable Women Planters Farmers Entrepreneur Association (NGOs) on 03 July 2013 c. Memorandum of Understanding signed between Ministry of Environment, Sustainable Development, Disaster and Beach Management and Mauritius Meteorological Services (13 March 2014) d. Memorandum of Understanding signed between Ministry of Environment, Sustainable Development, Disaster and Beach Management and University of Mauritius (22 May 2014) e. Memorandum of Understanding signed between Ministry of Environment, Sustainable Development, Disaster and Beach Management and Reef Conservation Mauritius (09 May 2014) f. Memorandum of Understanding signed between Ministry of Environment, Sustainable Development, Disaster and Beach Management and Rodrigues Regional Assembly (19 November 2015) g. Memorandum of Understanding signed between Ministry of Environment, Sustainable Development, and Disaster and Beach Management and the Attitude Foundation (01 December 2015) h. Memorandum of Understanding signed between Ministry of Environment, Sustainable Development, and Disaster and Beach Management and Stichting Deltares and UNESCO-IHE i. Memorandum of Understanding signed between Ministry of Environment, Sustainable Development, and Disaster and Beach Management and Rogers Foundation, Reef Conservation (30 March 2016) Banners produced under AF Project: • 1 Banner on Mangroves Plantation & Sensitisation Project in the region of Grand Sable/Quatre Soeurs • 1 Banner on Riviere des Galets Project Site (vulnerability to storm surges) • 2 Banners on Training and Capacity Building Programme • 1 Banner on Problem statement of Mon Choisy & Riviere des Galets Project site • 2 Banner on Coastal Adaptation Options for Mon Choisy & Riviere des Galets project site • 1 Banner on Sensitisation Campaigns conducted under AF Project • 1 Banner on Early Warning System for Storm Surge
Short Video Clips produced under AF Project: • 1 Short Video Clip on Mangroves plantation at Grand Sable on 09 September 2013 (by Mauritius Broadcasting Corporation) • 1 Short Video Clip on Mangroves sensitization programmes • 1 Short Video Clip on the occasion of Signature of MoU Ceremony with the Mauritius Meteorological Services held on 13 March 2014 • 1 Short TV Reportage on Riviere des Galets (23 June 2014) • 1 Short Video Clip on Educational Tour held at Ile D’Ambre on 09 September 2014 • Inception Workshop for Coastal Adaptation Measures at Mon Choisy & Riviere des Galets- 25 September 2014 • 1 Short Video Clip on National Validation Workshop on Implementation of an Early Warning System for Storm Surge on 22 January 2015 • 1 Short Video Clip on National Validation Workshop on Coastal Adaptation Measures at Mon Choisy and Riviere des Galets held on 09 April 2015 • 1 Short Video Clip on Symbolic Mangroves Plantation by the Honourable Minister of Environment, Sustainable Development, Disaster and Beach Management at Anse la Raie on 03 June 2015 • 1 Short Video Clip on Official Sensitisation and Awareness Raising Campaign with Marine Mobile Education Unit & Symbolic Mangroves Plantation by the Honourable Minister of Environment, Sustainable Development, Disaster and Beach Management at Poste de Flacq on 04 June 2015 • 1 Short Video Clip on exhibition organised under the AF Project in the context of World Environment Day 2015 held on 05 June 2015 • Laying of Foundation Ceremony for the construction of a Refuge Centre at Quatre Soeurs-15 August 2015 • National Workshop for implementation of an Early Warning System for incoming Storm Surge in the Republic of Mauritius-22 January 2015 • Press Conference on implementation of an Early Warning System for incoming Storm Surge in the Republic of Mauritius-07 August 2015 • Short Course on Coastal and Marine Environment for Engineers in Rodrigues-15 July 2015 • Short Course on Cost Benefit Analysis of Coastal Management and Adaptation Options to Climate Change in Rodrigues-25 May 2015 • Unveiling of Display Board to commemorate the successful implementation of mangroves project at Grand Sable-25 July 2015 • Short Video Clip on Adaptation Fund Project in the context of COP 21 • Press Conference on Signature of a Memorandum of Understanding between this Ministry, UNESCO IHE and Stichting Deltares • Press Conference on a Simulation Evacuation Exercise at Quatre Soeurs • Award of Certificate Ceremony for the Short course on Integrated Coastal Zone Management • Short Video Clip on the impacts of climate change in the coastal region of Mauritius List of Cabinet/Information Papers: • The Cabinet Office was informed on 13 November 2013 on forthcoming Coastal Adaptation Works at Riviere des Galets • The Cabinet Office was informed on 09 May 2014 on the participation of the Mangroves Project in the Global Island Partnership 2013 Solution Search Award. This project was recognised as a best practice partnership by the United Nations Commission on Sustainable Development and the GSWPFEA won the first prize, known as the Island Bright Spot Award 2013. • The Cabinet Office was informed on 13 June 2014 that the United Nations, through the UNDP, has showcased the mangroves project at the UN Headquarters in New York in the context of celebrations of the World Environment Day (International) on 5 June 2014. The storyline of the project was also posted on the UNDP website. • The Cabinet took note on 15 January 2016 that the Minister of Environment, Sustainable Development, Disaster and Beach Management would sign a Memorandum of Understanding with Stichting Deltares and UNESCO IHE Institute for Water Education, Netherlands for the development of an Early Warning System for Storm Surge Parliamentary Questions •PQ 692-To ask the Honourable Minister of Environment, Sustainable Development and Disaster and Beach Management – Whether, in regard to the inhabitants of the EDC at Rivière des Galets who are at risk during bad weather conditions, he will state if any decision has been taken in regard to the relocation thereof? (http://mauritiusassembly.govmu.org/English/questions/Documents/PQ2015/pq13october2015.pdf) • PQ 657-In regard to the inhabitants of Rivère des Galets, where matters stand as to the proposed relocation thereof-(http://mauritiusassembly.govmu.org/English/questions/Documents/PQ2016/pq28june2016.pdf)
List the Website address (URL) of project. |  |  | Democratic People's Republic of Korea
|  | www.adaptation-fund.org | Democratic Republic of the Congo
Denmark
| Project contacts: |  | Djibouti
National Project Manager/Coordinator |  |  | Dominica
| Name: | Mrs. D. Lan Ng | Dominican Republic
| Email: | dirdoe@govmu.org | Ecuador
| Date: | 2016-08-01 | Egypt
| Government DA |  | El Salvador
| Name: |  | Equatoral Guinea
| Email: |  | Eritrea
| Date: |  | Estonia
| Implementing Entity |  | Ethiopia
| Name: | United Nations Development Programme (UNDP) | Fiji
| Email: | simon.springett@undp.org | Finland
| Date: | 2016-08-01 | France
| Executing Agency |  | Gambia
| Name: | Ministry of Environment, Sustainable Development, and Disaster and Beach Management | Georgia
| Email: | ojadoo@govmu.org | Germany
| Date: | 2016-08-01 | Ghana
| Executing Agency |  | Greece
| Name: | Ministry of Environment, Sustainable Development, and Disaster and Beach Management (Project Manager) | Grenada
| Email: | mnkhedah@yahoo.com | Guatemala
| Date: | 2016-08-01 | Guinea
| Executing Agency |  | Guinea Bissau
| Name: |  | Guyana
| Email: |  | Haiti
| Date: |  | Honduras
Hungary
Iceland
India
Indonesia
Iran (Islamic Republic of)
Iraq
Ireland
Israel
Italy
Jamaica
Japan
Jordan
Kazakhstan
Kenya
Kiribati
Kuwait
Kyrgyzstan
Lao People’s Democratic Republic
Latvia
Lebanon
Lesotho
Liberia
Libyan Arab Jamahiriya
Liechtenstein
Lithuania
Luxembourg
Madagascar
Malawi
Malaysia
Maldives
Mali
Malta
Marshall Islands
Mauritania
Mauritius
Mexico
Micronesia, Federated States of
Monaco
Mongolia
Montenegro
Morocco
Mozambique
Myanmar
Namibia
Nauru
Nepal
Netherlands
New Zealand
Nicaragua
Niger
Nigeria
Norway
Oman
Pakistan
Palau
Panama
Papua New Guinea
Paraguay
Peru
Philippines
Poland
Portugal
Qatar
Republic of Korea
Republic of Moldova
Romania
Russian Federation
Rwanda
Saint Kitts and Nevis
Saint Lucia
Saint Vincent and the Grenadines
Samoa
San Marino
Sao Tome and Principe
Saudi Arabia
Senegal
Serbia
Seychelles
Sierra Leone
Singapore
Slovakia
Slovenia
Solomon Islands
Somalia
South Africa
Spain
Sri Lanka
Sudan
Suriname
Swaziland
Sweden
Switzerland
Syrian Arab Republic
Tajikistan
Thailand
The former Yugoslav Republic of Macedonia
Timor-Leste
Togo
Tonga
Trinidad and Tobago
Tunisia
Turkey
Turkmenistan
Tuvalu
Uganda
Ukraine
United Arab Emirates
United Kingdom of Great Britain and Northern Ireland
United Republic of Tanzania
United States of America
Uruguay
Uzbekistan
Vanuatu
Venezuela, Bolivarian Republic of
Viet Nam
Yemen
Zambia
Zimbabwe

## FinancialData
Financial information: cumulative from project start to 31 July 2016
DISBURSEMENT OF AF GRANT FUNDS
How much of the total AF grant as noted in Project Document plus any project preparation grant has been spent to date?
|  | Estimated cumulative total disbursement as of [31 July 2016] | 1516941
|  | Add any comments on AF Grant Funds. (word limit=200) | The disbursement up to the reporting period ending 31 July 2016 amounted to USD 1,516,941 (exclusive of management fee) which represent 18% of the total budget. The Project budget was revised and approved by the Adaptation Fund Board on 22 May 2014 (Board decision B.23-24/5) as follows; Outcome Prodoc Revised Budget (USD) (USD) 1 6,465,700 6,680,440 2 133,705 310,365 3 394,025 394,025 4 350,000 200,000 5 561,350 320,000 The Procurement of the following Consultancy Services & Works were completed during the reporting period; Consultancy Services (i) Consultancy Services for the preparation of Environment Impact Assessment Reports for Coastal Adaptation Works at Mon Choisy and Riviere des Galets awarded to Scene-Ries Consult Ltd for a contract amount of (MUR 1,069,500 & USD 13,800 inclusive of VAT). (ii) Consultancy Services for the Design and Delivery of a Short Course on Disaster Risk Reduction in the Coastal Zone of Mauritius awarded to TACSYM Ltd for a contract amount of MUR 419, 204 (iii) Consultancy Services for the Design and Delivery of a Short Course on Integrated Coastal Zone Management awarded to The University of Western Australia for a contract amount of AUD 65,460 Works (i) Contract for construction of a Refuge Centre, Drainage System and Ancillary Works at Quatre Soeurs awarded to Best Construct Co Ltd for a contract amount of MUR 43,563,951.62 inclusive of VAT Contracts Signed (i) Contract signed between Ministry of Environment, Sustainable Development, and Disaster and Beach Management and Scene-Ries Consult Ltd for Consultancy Services for the preparation of Environment Impact Assessment Reports for Coastal Adaptation Works at Mon Choisy and Riviere des Galets on 15 January 2016 (ii) Contract signed between Ministry of Environment, Sustainable Development, and Disaster and Beach Management and TACSYM Ltd for Consultancy Services for the design and delivery of a short course on Disaster Risk Reduction in the coastal zone of Mauritius on 12 January 2016 (iii) Contract signed between Ministry of Environment, Sustainable Development, and Disaster and Beach Management and The University of Western Australia for Consultancy Services for the Design and Delivery of a Short Course on Integrated Coastal Zone Management on 25 February 2016
|  | INVESTMENT INCOME | 0
Amount of annual investment income generated from the Adaptation Fund’s grant |  |  | Amount of annual investment income generated from the Adaptation Fund’s grant |  |  | Amount of annual investment income generated from the Adaptation Fund’s grant | Amount of annual investment income generated from the Adaptation Fund’s grant | Amount of annual investment income generated from the Adaptation Fund’s grant | Amount of annual investment income generated from the Adaptation Fund’s grant | Amount of annual investment income generated from the Adaptation Fund’s grant | Amount of annual investment income generated from the Adaptation Fund’s grant | Amount of annual investment income generated from the Adaptation Fund’s grant | Amount of annual investment income generated from the Adaptation Fund’s grant | Amount of annual investment income generated from the Adaptation Fund’s grant | Amount of annual investment income generated from the Adaptation Fund’s grant | Amount of annual investment income generated from the Adaptation Fund’s grant | Amount of annual investment income generated from the Adaptation Fund’s grant | Amount of annual investment income generated from the Adaptation Fund’s grant | Amount of annual investment income generated from the Adaptation Fund’s grant | Amount of annual investment income generated from the Adaptation Fund’s grant | Amount of annual investment income generated from the Adaptation Fund’s grant | Amount of annual investment income generated from the Adaptation Fund’s grant | Amount of annual investment income generated from the Adaptation Fund’s grant | Amount of annual investment income generated from the Adaptation Fund’s grant | Amount of annual investment income generated from the Adaptation Fund’s grant | Amount of annual investment income generated from the Adaptation Fund’s grant | Amount of annual investment income generated from the Adaptation Fund’s grant | Amount of annual investment income generated from the Adaptation Fund’s grant | Amount of annual investment income generated from the Adaptation Fund’s grant | Amount of annual investment income generated from the Adaptation Fund’s grant | Amount of annual investment income generated from the Adaptation Fund’s grant | Amount of annual investment income generated from the Adaptation Fund’s grant | Amount of annual investment income generated from the Adaptation Fund’s grant | Amount of annual investment income generated from the Adaptation Fund’s grant | Amount of annual investment income generated from the Adaptation Fund’s grant | Amount of annual investment income generated from the Adaptation Fund’s grant | Amount of annual investment income generated from the Adaptation Fund’s grant | Amount of annual investment income generated from the Adaptation Fund’s grant | Amount of annual investment income generated from the Adaptation Fund’s grant | Amount of annual investment income generated from the Adaptation Fund’s grant | Amount of annual investment income generated from the Adaptation Fund’s grant | Amount of annual investment income generated from the Adaptation Fund’s grant | Amount of annual investment income generated from the Adaptation Fund’s grant | Amount of annual investment income generated from the Adaptation Fund’s grant | Amount of annual investment income generated from the Adaptation Fund’s grant | Amount of annual investment income generated from the Adaptation Fund’s grant | Amount of annual investment income generated from the Adaptation Fund’s grant | Amount of annual investment income generated from the Adaptation Fund’s grant | Amount of annual investment income generated from the Adaptation Fund’s grant | Amount of annual investment income generated from the Adaptation Fund’s grant | Amount of annual investment income generated from the Adaptation Fund’s grant | Amount of annual investment income generated from the Adaptation Fund’s grant | Amount of annual investment income generated from the Adaptation Fund’s grant | Amount of annual investment income generated from the Adaptation Fund’s grant | Amount of annual investment income generated from the Adaptation Fund’s grant | Amount of annual investment income generated from the Adaptation Fund’s grant | Amount of annual investment income generated from the Adaptation Fund’s grant | Amount of annual investment income generated from the Adaptation Fund’s grant | Amount of annual investment income generated from the Adaptation Fund’s grant | Amount of annual investment income generated from the Adaptation Fund’s grant | Amount of annual investment income generated from the Adaptation Fund’s grant | Amount of annual investment income generated from the Adaptation Fund’s grant | Amount of annual investment income generated from the Adaptation Fund’s grant | Amount of annual investment income generated from the Adaptation Fund’s grant | Amount of annual investment income generated from the Adaptation Fund’s grant | Amount of annual investment income generated from the Adaptation Fund’s grant | Amount of annual investment income generated from the Adaptation Fund’s grant
Amount of annual investment income generated from the Adaptation Fund’s grant
EXPENDITURE DATA
|  | List ouput and corresponding amount spent for the current reporting period | ITEM / ACTIVITY / ACTION | AMOUNT
|  |  | Output 1.1, 1.2, 1.4, 1.5, 1.6 (Outputs merged under 1 Consultancy Services) | 112505.98
|  |  | Output 1.3 (Works) | 572.24
|  |  | Outcome 1 subtotal | 113078.22
|  |  | Output 2.1, 2.2 (Outputs merged under 1 Consultancy Services) | 151526.54
|  |  | Outcome 2 subtotal | 151526.54
Output 3.1
|  |  | Output 3.2 | 70304.03
|  |  | Output 3.3 | 7893.68
|  |  | Outcome 3 subtotal | 78197.71
Output 4.1
Output 4.2
Output 4.3
Output 4.4
Outcome 4 subtotal
|  |  | Output 5.1 | 13433.75
|  |  | Output 5.2 | 0
|  |  | Output 5.3 | 6017.42
|  |  | Output 5.4 | 483.95
|  |  | Output 5.5 | 0
|  |  | Outcome 5 subtotal | 19935.12
|  |  | Execution Costs | 109581.97
|  |  | TOTAL | 472319.56
|  | PLANNED EXPENDITURE SCHEDULE | ITEM / ACTIVITY / ACTION | Est. Completion Date | PROJECTED COST
|  | List outputs planned and corresponding projected cost for the upcoming reporting period | 1.1 Detailed technical assessment of each site, with chronology of previous flood and erosion events and collection of nearshore oceanographic data, during “quiet” periods and “active” periods (one month each) to inform the design of the technical interventions at each of the three sites. | Expected Completion date for Design of Coastal Adaptation Measures for Mon Choisy (October 2016) Completion date for Design of Coastal Adaptation Measures for Riviere des Galets (August 2016) | 307680
1.2 Technical design of coastal protection measures at each of three sites, with detailed costing, carried out in a gender sensitive way.
|  |  | 1.3 Successful construction of physical interventions at each of the three sites. | (i) Construction of Refuge Centre at Q. Soeurs (USD 1,095,000) July 2017 (ii) Mon Choisy (USD 500,000) (December 2017) (iii) Riviere des Galets (USD 430,000) (September 2017) | 2025000
|  |  | 1.4 Analysis of data and development of recommendations on how the interventions can be adjusted for other vulnerable coastal locations in ROM. | To start after completion of 1.1, 1.2 and 1.3 | 0
|  |  | 1.5 Monitoring programme designed, to include scoping of suitable parameters, including beach width and slope; depth of adjacent lagoonal sediments; wave height, period, and run-up; direction of nearshore currents, etc. | To start after completion of 1.1, 1.2 and during implementation of 1.3 | 0
|  |  | 1.6 A targeted coastal process/weather event monitoring system in place | To start after completion of 1.1, 1.2 and during implementation of 1.3 | 0
|  |  | 2.1 Assessment of the current sea state monitoring systems (Mauritius Meteorological Services and Mauritius Oceanography Institute) and definition of required critical parameters and operational requirements for an . early warning system | Project Completed | 0
|  |  | 2.2 The early warning system installed and implemented (with links to early warning system for cyclones), with communication linkages established from level of National Coast Guard at Headquarters down to the level of coastal communities. |  | 0
|  |  | 3.1 “Handbook on Coastal Adaptation” packaged as training modules for coastal communities, relevant Government agencies, and private sector stakeholders (such as hotel operators); training sessions delivered on a regular basis over the course of the project (at least twice annually). | • 1 Handbook for Coastal Communities (January 2017) | 30000
|  |  | 3.2 Short course on Coastal Engineering designed and delivered (twice during programme period). | • Short Course on CBA applied to Climate Change Initiatives (12-16 September 2016) • Short Course on CBA (International) | 31000
3.3 Specialized course on Cost-Benefit Analysis of coastal adaptation measures designed and delivered (annually, over four years).
|  |  | 4.1 A National Coastal Zone Adaptation that addresses all perceived climate change risks in the coastal zone of ROM over at least the next 20 years, with recommendations for supporting policies and regulations. | • Launching of RFP on an Open International Bidding (Closing date: 26 Septenmber 2016) • Bid Evaluation • Notification to bidders • Award of Contract for Consultancy Services • Inception Report of the National Coastal Zone Adaptation Strategy for RoM • Final Report on Review of strategies, policies, laws, regulations & projects pertaining to coastal zone in RoM-January 2017 • Final Report on options for adaptation policies & measures & consultative workshop-March 2017 • Final Report on National Coastal Zone Adaptation Strategy for RoM-May 2017 • Final Report on required structure & process for 'clearing house'-June 2017 Expected Completion Date: September 2017 | 150000
4.2 A set of recommendations on best technical and institutional adaptation practices suitable for the coastal zone of ROM.
4.3 Definition of the required structure and processes for one “clearinghouse” for climate change oversight in the coastal zone of ROM (a unit or institution, or collection of individuals from various agencies, which is able to make final decisions on the climate appropriateness of future development projects; also having a follow-up enforcement capacity).
4.4 Recommendations for new economic instruments
5.1 Handbook, training modules, and website content capturing best coastal adaptation practices for the Mauritius context.
5.2 Dissemination of lessons learned from the programme with coastal stakeholders in other locations in the southern Indian Ocean.
|  |  | 5.3 Interpretive signs and small-scale models of coastal processes designed and installed at each site, explaining the science of climate change and coastal processes (in lay terms), so that the linkages between weather, stability of coastal features, and adaptation measures are clear. | • Climate Change Community Sensitisation Game (Snake and Ladders) • Electronic Quiz Game on impacts of Climate Change • Development of Do's and Don’t's sheet at sea sheet with the pouch for boat operators and fishermen as sensitisation material | 37000
|  |  | 5.4 Public awareness campaigns on climate change in the coastal zone designed and delivered, involving the Mauritian media (TV, radio, Internet). | Public awareness campaigns
5.5 Priority ranking of vulnerable coastal sites established, to guide the order of future investment by the Government of Mauritius and the private sector.
|  |  | Execution Costs | Project Manager/Project Assistant/Project Technical Assistant | 118000
TOTAL
|  |  | TOTAL |  | 2698680
ACTUAL CO-FINANCING (If the MTR or TE have not been undertaken this reporting period, DO NOT report on actual co-financing.)
|  | How much of the total co-financing as committed in the Project Document has actually been realized? | No co-financing committed in the Project Document
|  | Estimated cumulative actual co-financing as verified during Mid-term Review (MTR) or Terminal Evaluation (TE). | 320645
|  | Add any comments on actual co-financing in particular any issues related to the realization of in-kind, grant, credits, loans, equity, non-grant instruments and other types of co-financing. (word limit=200) | 320,645 USD as Government of Mauritius in-kind contribution for purchase of land of an extent of 12,850 m2 at Quatre Soeurs for construction of the Refuge Centre.

## Risk Assesment
RISK ASSESMENT
IDENTIFIED RISKS
List all Risks identified in project preparation phase and what steps are being taken to mitigate them
Identified Risk | Current Status | Steps Taken to Mitigate Risk
High level endorsement of proposed policy and regulatory changes to support coastal adaptation may be lacking (enabling legislation may be delayed); there may also be concerns about creating a new climate change oversight function within the Ministry of Environment, Sustainable Development, Disaster and Beach Management (MESDDBM) (degree: moderate) | Coastal adaptation projects and initiatives are fully supported by the Ministry (degree: low) | • The various programme activities and progress are discussed at the Project Steering Committee held once every 3 Months • All Technical issues are discussed at the Technical Committee level
Government of Mauritius commitment to climate change management could wane as development priorities become more prominent and compete, especially in the run-up to elections. (degree: moderate) | Mauritius has witnessed in the recent past some of the impacts of climate change including flash floods, variability in rainfall distribution amongst others. The Government is thus well aware of climate change impacts and it is one of the national priority to build climate resilience. Up to now the change in Government has not affected the climate change management in Mauritius (degree: low) | • Constant reiteration of the risks of climate change and the positive net benefits of adaptation investments are being disseminated.
Delays in fund transfers and procurement of technical services and equipment. (degree: moderate) | The procurement process in line with the current Public Procurement Act is lengthy. The procurement of highly technical expertise required the project to undertake international bidding Delay in fund transfer from the donor to the UNDP CO resulted in the Ministry to negotiate with the Ministry of Finance and Economic Developement to meet the project expenditure from the Government funds in the meantime (degree: low) | • Programme activities were initially designed and paced to ensure completion over five years. Following the first round of procurement and lessons learnt, a budget reallocation (USD 391,400) from the Component ‘Policy Mainstreaming’ and ‘Knowledge Dissemination’ to Coastal Adaptation Works at Mon Choisy & Riviere des Galets and Early Warning System was effected in consultation with the UNDP CO. • The Revised Budget allocation was endorsed by the Financial Secretary, the Designated National Authority and subsequently approved by the Adaptation Fund Board (AFB) in March 2014. • The Request for a 1 Year Project Extension was exceptionally approved by the Adaptation Fund Board. The new completion date for the project will be around August 2018. • The Programme Board will also provide required oversight for management of programme inputs.
MESDBM may have limited management capacity for programme activities, and for the eventual assumption of climate change management oversight and enforcement; conflicts between the CC Cell and the ICZM Division may arise. (degree: moderate) | A new climate change bill at the level of the Ministry has been prepared which clearly defines the roles of each division. (degree: low) | • UNDP will maintain a strong link with the programme, and the various programme activities that address institutional aspects will be guided by consultants, who will bring international expertise and experience from other countries, which should inform the situation in the Republic of Mauritius.
Climate variability accelerates and coastal degradation occurs at a faster pace than anticipated. (degree: moderate) | Modelling of different scenarios of the climate change variability and impacts thereof has been included in the scope of the services of the international consultants. The design has taken into consideration the above risk factor where required (degree: low) | The climate change modelling, as part of the deliverables under the component 1 has addressed this potential risk to the satisfaction of the Technical Committee and Project Steering Committee
There may be a misunderstanding about the jurisdictional area of an agency that has climate change management oversight and right of enforcement. (degree: moderate) | The component on Policy Mainstreaming has been drafted to clearly define the responsibilities of each Ministry as a specific deliverable. (degree: low) | It is precisely the analysis of overlapping jurisdictions and conflicting regulations that will sort out respective roles and improve the situation for all Ministries/agencies, so that coastal adaptation can proceed accordingly. The consultant for Policy Maintreaming will come up with a National Coastal Zone Adaptation Strategy for the Republic of Mauritius
Districts (local government) may perceive themselves in a peripheral role, with their development put aside for the sake of climate change adaptation. (degree: moderate) | • The officials of all Local authorities in RoM have been trained in the field of coastal engineering/climate change adaptation/CBA as part of the capacity building programme under the project. • The delivery of the Short Courses started since September 2013. To date 12 Short Courses in the field of Coastal Engineering, Coastal and Marine Environment for Engineers, Cost and Benefit Analysis, amongst others have been delivered under the Project in Mauritius and Rodrigues. (degree: low) | The District Councils are represented in the Programme Board and in programme activities. The positive results of the coastal protection measures are disseminated and well understood by the District Councils.
Varying, possibly conflicting, perceptions of the climate change risks and coastal adaptation approaches may become apparent, based on previous experiences and technical expertise. (degree: moderate) | • The most feasible option for the climate change adaptation is being looked at based on its own merits to achieve a sustainable solution. For example, at one of the project coastal site, Riviere des Galets, the option of relocation of the vulnerable communities exposed to storm surge had also been explored in consultation with the local community. • Regular stakeholders meetings and sensitisation are held under the project to reduce conflicting issues amongst the local community/fishers/NGO's/Government/Private sector and the local authorities (degree: low) | • Frequent dialogue with programme partners on reinforcement of principles of climate change management and appropriate adaptation measures has been taken. • Regular stakeholders meetings and sensitisation are held under the project to reduce conflicting issues amongst the local community/fishers/NGO's/Government/Private sector and the local authorities • To date, sensitisation campaigns have been conducted using a mobile education unit and some 15000 people have been sensitised.
Critical Risks Affecting Progress (Not identified at project design)
Identify Risks with a 50% or > likelihood of affecting progress of project
Identified Risk | Current Status | Steps Taken to Mitigate Risk
The bid prices substantially higher than the amounts earmarked in the budget in the Project Document, for component 1 and component 2. (degree: high) | • The financial offer for Component 1 (Consultancy Services for Mon Choisy & Riviere des Galets) was 275% higher • The financial offer forComponent 2 (Consultancy Services for Early Warning System) was higher than 400% than the budgeted amount in the AF Project document. (degree: moderate) | • Following the 1st round of procurement, the scope of the works had to be reviewed to focus on the key deliverables and implementation within the project budget. A budget revision and extension of time was approved by the Adaptation Fund Board
The process of land availability and acquisition for the construction of the Refuge Centre at Quatre Soeurs under the Component 1 was an issue. (degree: high) | • A Site located on higher grounds, of an extent of 3A04P owned by the private sector was identified for the construction of Refuge Centre at Quatre Soeurs. • The land acquisition procedures was completed by the Ministry of Housing and Lands in June 2015 and land vested to the MESDDBM. (degree: low) | • The land acquisition process was successfully completed in June 2015 by the Mnistry of Housing and Lands. • The project targets as set in the project document will be met under component 1. The scope of works for the respective sites are hereunder listed: Mon Choisy- Wave dissipating structures, beach nourishment, ecosystem based adaptation including seagrass regeneration, plantation of coastal vegetation for dune stabilisation Riviere des Galets - construction of rock revetment, implementation of wave overtopping wall. Quatre Soeurs-The original project scope has been upscaled to provide a newly designed Refuge Centre, which will be a first in its kind in the RoM and in the Indian Ocean to be used as a dedicated Refuge Centre The original scope to retrofit an existing building (approximately 1000 sq ft) has been reviewed to construct a full fledge Refuge centre (10000 sq ft) at more appropriate site acquired by the government of Mauritius and located at 25m above mean sea level as a sustainable solution against storm surge. The original site was not appropriate to house a Refuge Centre against storm surges. Accordingly, the Government of Mauritius was approached and an appropriate site was identified by the Technical Committee based on an agreed site selection matrix and which represented a co-contribution from the Government of Mauritius The output targets have not been affected following the budget reallocation under Component 1. Instead, the targets are being enhanced to achieve a long term and sustainable adaptation measures Mangroves Plantation Project Under component 1, the mangroves plantation project was succesfully completed. Some 20,000 mangroves had been planted along the coastline of Q. Soeurs & region compared with 10,000 as prescribed in the project document. The project has also been replicated to other coastal sites in the Republic of Mauritius with the collaboration of the private sector/NGO's/fishermen & women associations
Proposed relocation option at Riviere des Galets, even though more sustainable, may be costly and not feasible, as foreseen in the project document. (degree: moderate) | • Frequent dialogue with the community is being sustained for a voluntary resettlement. Additional studies has been conducted under the Consultancy Services for Riviere des Galets to assess the best adaptation options. • Following completion of studies under the AF Project, the relocation project being a long term sustainable solution for Riviere des Galets will be implemented by the Government of Mauritius. • The land acquisition process for the proposed relocation of the inhabitants has started at the level of Ministry of Housing and lands (degree: low) | • Government and private sector co-financing will be envisaged for implementation of the resettlement option by the MESDDBM in the longer term.
Risk Measures: Were there any risk mitigation measures employed during the current reporting period? If so, were risks reduced? If not, why were these risks not reduced?
Add any comments relevant to risk mitigation (word limit = 500)
UNDP CO procured the consultancy services for Mon Choisy & Riviere des Galets upon request of the Ministry and approval of NDA . The AFB facilitated faster procurement and therefore reduced the risks of delays in delivery. The Mon Choisy Project had to undergo two independent design reviews (1 under the EIA and 1 by the UNDP) to minimise the risks of outcry from the relevant stakeholders (fisher/beach users/hotels operators etc.)

## Rating
RATING ON IMPLEMENTATION PROGRESS
For rating definitions please see bottom of page.
| Progress on Key Milestones |  | Expected Progress |  | Progress to Date | Rating
Project Manager/ Coordinator: | Detailed technical assessment of each site |  | Procurement of consultancy services for the preparation of feasibility studies, Environmental Impact Assessment Reports, Design, Preparation of Bid Documents and Supervision of Works for the implementation of coastal adaptation measures at Mon Choisy and Rivière des Galets, Mauritius completed. Land acquisition procedures for Quatre Soeurs completed. Procurement for consultancy services for the design, preparation of tender documents and supervision of works for the construction of Refuge Centre, drainage system and Ancillary works at Quatre Soeurs. Completed Invitation to Bid for the construction of Refuge Centre, drainage system and Ancillary works at Quatre Soeurs. Completed Bid Evaluation for works for the construction of Refuge Centre, drainage system and Ancillary works at Quatre Soeurs. Completed Mangroves Plantation Project completed. |  | COMPONENT 1 Mon Choisy & Riviere des Galets - The Contract for Consultancy Services for Coastal Adaptation Measures at Mon Choisy and Riviere des Galets was awarded to Indufor Oy in consortium with eCoast and C.L.A.M.S ltd for a contract amount of USD 817,850 excluding VAT. - To date the following stages have been completed by the consultants (i) inception workshop (ii) detailed technical assessment phase (iii) Options for Coastal Adaptation Measures including Cost Benefit Analysis (iv) Feasibility Studies (V) A baseline report for a managed retreat project at Riviere des Galets (vi) Preliminary design report for both sites have been submitted. - Several discussions and design review activities to decide final final design have been conducted. - The consultants will submit the bid documents and revised design reports by 19 August 2016. Environmental Impact Assessment (EIA) Consultancy Services - The contract for Consultancy Services for Preparation of EIA Reports for Coastal Adaptation Works at Mon Choisy and Riviere des Galets was awarded to Scene-Ries Consult Ltd in association with Dr V. Ing Sundar, Department of Ocean Engineering, India Institute of Technology, Madras, Chennai- India. - An Inception meeting was held on 15 January 2016 at the MESDDBM in the presence of the Acting Senior Chief Executive and representatives of this Ministry and EIA Consultant, Scene-Ries Consult ltd. - A monitoring committee was constituted under the chair of the project Team to follow up on the EIA studies and sort out any bottlenecks upfront. Several site visits and monitoring meetings were held during the EIA process. - The EIA consultant was associated with Dr Ing. V. Sundar from IIT Madras, India to undertake design reviews of the proposed adaptation works for Mon Choisy and Riviere des Galets. Dr Ing. V. Sundar conducted a mission visit from 7 to 8 February 2016 at Mon Choisy and Riviere des Galets. - The pre final design review report for Mon Choisy was submitted on 15 March and for Riviere des Galets on 17 March 2016. Environment Impact Assessment (EIA) for Mon Choisy - The pre-final version of the EIA and SIA Report for the proposed coastal adaptation measures at Mon Choisy was received on 28 April 2016. A meeting was held on 19 May 2016 with the EIA Consultant, Scene-Ries Consult Ltd to discuss on the way forward to amend the EIA Report for Mon Choisy so as to reflect more comprehensively the recommendations of the design review. - The committee approved the payment to the EIA Consultant for submission of the pre-final EIA Report for Mon Choisy including a retention fee of 10%. - Following the Independent design review conducted by the UNDP, the revised design report for Mon Choisy will be submitted by Indufor Oy and the EIA & SIA Report amended accordingly by the EIA Consultant. This will constitute a variation to the existing contract with the Ministry. Environment Impact Assessment (EIA) Riviere des Galets - In view of the EIA, several consultations were held with all stakeholders. This included consultations with inhabitants of Riviere des Galets, Chemin Grenier Village Councillors, representative of the District Council of Savanne. They were held on the 28th January, 5th February, and from the 2nd to 12th February for informal group discussions. - The draft EIA for Riviere des Galets was submitted on 22nd February 2016. It was subject to discussion at the Technical Committee and the comments were transmitted to the consultants and the final EIA report was delivered. - The Final EIA Report incorporating the views and comments of the Technical Committee was submitted on 31 March 2016 to the EIA Division of the Ministry in 20 copies in compliance with EPA 2002. Notice for Public Inspection of EIA Report - A notice for Public Inspection of the EIA Report for the undertaking ‘Sea Defense Wall at Riviere des Galets’ was published in the local press on 20 April 2016. The closing date for submission of public comments was 06 May 2016. Site Visit by EIA Committee at Riviere des Galets - A Site Visit was conducted at Riviere des Galets on 28 April 2016 by representatives of the EIA Committee which comprised of the EIA Division of the Ministry, Ministry of Tourism and External Communications, Forestry Services, Ministry of Health and Quality of Life, Wastewater Management Authority, Ministry of Ocean Economy, Marine Resources, Fisheries, Shipping and Outer Island, Road Development Authority, and in the presence AF Project team and Scene-Ries Consult Ltd. - A request for additional information was officially submitted by EIA Committee to the EIA Consultant. Technical Committee and decisions Mon Choisy - The Technical Committee at its 24th meeting held on 22 April 2016 approved the design of 4 out of 5 adaptation measures proposed for Mon Choisy; (i) Beach Re-profiling and dune planting (ii) Installation of 20 Fixed Mooring Buoys (iii) Seagrass Restoration Programme (iv) Establishment of a Voluntary Marine Conservation Areas. As regards to the proposed offshore structures, the Technical Committee approved the alternative to the proposed rock mound structure (200m x 35 m), as recommended in the Design Review Report submitted by the EIA Consultant, i.e use of geo-synthetics (including arrays of geo-bags to form the submerged breakwater) and also requested Indufor Oy to re-evaluate the technical and financial viability of reef balls and WAD construction, particularly in regards to the sole-source contracting difficulties for implementation in Mauritius. - The consultants Indufor Oy were informed on the decision of the Technical Committee on 27 April 2016 and the main concerns raised for Mon Choisy, more specifically: (i) the design calculation of the submerged rock structure to justify the sizing (200*35m) (ii) the impact of the proposed structure on the overall equilibrium of the beach and sediment transport (iii) mitigating measures through modelling scenarios (iv) the recommendation of the EIA Consultant to remove approx. 100 no. of trees along the Mon Choisy foreshore, as opposed to the 400 no. proposed in the preliminary design report submitted by Indufor Oy. Riviere des Galets -The consultants Indufor Oy were informed on the decision of the Technical Committee on 25 April 2016 and the amendments proposed in light to the design review: (i) the crown parapet to be of concave design in lieu of the modified circular recurve and extended over the entire length of the rock revetment (ii) Item B of the Bill of Quantities ‘Relocation of the Squatters’, which is subject to strict UNDP Environmental and Social Safeguards, be deleted. - The consultants Indufor Oy were also informed that the Technical Committee approved ‘in principle’ the design report for Riviere de Galets and were requested to submit the bid document for the construction of the coastal adaptation works by 25 May 2016. Design Review by UNDP - Dr. Peter Wulf (Independent Technical Reviewer) was asked to review all the documents and provide commentary on the technical quality of the work undertaken and the coastal protection proposed. -Dr. Peter Wulf undertook mission from 20-24 June 2016. Site vist to River des Galets and Mon Choisy were undertaken to identify matters. - A teleconference was held on 23 June 2016 in the morning with UNDP RTA, UNDP CO, Indufor, Project team and Director and Senior Chief Executive of the Ministry to discuss Coastal Adaptation measures for Mon Choisy and Riviere des Galets after the technical assessments by Dr.Peter Wulf , expected ministry will able to take discussion after going through commentary. - Steering Committe was held on 23 June 2016 afternoon. After the Mr.Peter Wulf presentation, Steering Committe was able to agree on the way forward. - Independent technical Review Report was submitted on 7 and 14 July 2016. Subsequent that presentation, the Steering Committee voted that the Project Management Unit asked Indufor to undertake the following: Mon Choisy (a) prepare new and/or modify the current design and other relevant reports with respect to the wave dissipation structure with the new preferred structure to be pre-cast reef units in a range of sizes and placed from a depth of 50cm to 2 metres in the area to the south and north of the natural reef with approximately two thirds being placed to the south of the existing reef; (b) the groyne to the south of Mon Choisy be removed; and (c) that between 150 and 200 Casuarinas be replaced commencing at the southern end of Mon Choisy as the first phase of tree replaced and the beach re-profiled in this area. Additional trees would likely be replaced in the future based on the outcomes of the initial replacement. Endemic species such as WHAT will be planted to provide beach protection along with shade in the future. Riviere des Galets (a) design the rock wall in proximity to the two larger house where it was not possible to construct a parapet wall and increase the height of the rock wall in this location to approximately four (4) metres and changing the batter of the rock wall to 1:1.5 for the first two vertical metres and then 1:2 for the remainder of the rock wall to allow access by fishing vessels; and (b) design a parapet wall to be constructed on top of the existing rock wall at the two properties at the eastern end of the project area (nearest the cemetery) to a height of approximately 600mm. After the submission of report, official request was send from Ministry to consultancy to submit the bid documents and revised design reports by 19 August 2016. Quatre Soeurs - The procedures for acquisition of land of an extent of 3A04P for construction of Refuge Centre at Quatre Soeurs were completed by the Ministry of Housing and Lands in June 2015 and land vested to the MESDDBM. Procurement - The Request for Proposal for Consultancy Services for Design, Preparation of Tender Document and Supervision of Works for Construction of the Refuge Centre, Drainage System and Ancillary Works at Quatre Soeurs was launched on 16 February 2015. - The opening of bids was on 25 March 2015 and a Prebid Conference was held on 10 March 2015 at the seat of the MESDDBM . - A Bid Evaluation Committee was constituted by the Departmental Bid Committee of this Ministry for bid evaluation of Consultancy Services for Design, Preparation of Tender Document and Supervision of Works for Construction of the Refuge Centre, Drainage System and Ancillary Works at Quatre Soeurs. The contract for consultancy services was awarded on 06 July 2015 to the Consortium: Mega Design Ltd, SEE Engineering Consultants, Steget, Chuttur & Partners Ltd for the price of USD 137,258 (incl. of VAT) . Reports submitted -To date the following deliverables have been completed by the consultants; (i) Inception Workshop report (ii) Detailed Technical Assessment including survey report, geotechnical investigation report and climate change risk assessment reports (iii) The architectural design of Refuge Centre and detailed design reports for works including detailed cost estimates , (iv) Final EIA report (v) Final Bid documents (vi) Building maintenance and evacuation plan. Procurement of contractor for Works Prebid Conference and Site Visit A Prebid Conference was held on 13 April 2016 at the seat of the MESDDBM. A site visit was conducted following the Prebid Conference at the Quatre Sœurs project site on 15 April 2016 in the presence of representatives from the UNDP, AF Project team and the bidders. The potential bidders took cognizance of the site. Deadline for Submission of bids The deadline for submission of bids for the Construction of the Refuge Centre, Drainage System and Ancillary Works at Quatre Soeurs was on 4 May 2016. 5 bids were received at the opening of bids on 4 May 2016 and a Bid Evaluation Committee constituted by the Departmental Bid Committee of this Ministry to conduct the bid evaluation Award of Contract for works - The bid evaluation was completed and the contract for works for the Construction of the Refuge Centre, Drainage System and Ancillary Works at Quatre Soeurs was awarded on 24 June 2016 to the best evaluated bidder - Best Construct Co. ltd for a price of MUR 43,563,951.62 . -Signature of the contract for construction of works was signed on 22 July 2016. Mangroves plantation project (Ecosystem based adaptation) - The mangroves project was completed. Some 20,000 mangroves seedlings were planted in the lagoonal areas of Grand Sable, Petit Sable and Quatre Soeurs by the Grand Sable Fishermen Association (GSFA). 5 tranches of USD 7,000 were already disbursed to GSFA (in line with the Memorandum of Agreement signed). - Following success, the mangroves project was replicated in other areas in the Republic of Mauritius in partnership with the private sector and the local community. Replication of Mangrove plantation at Baie du Cap - A symbolic plantation of 400 mangrove seedlings and unveiling of Display Board Ceremony to commemorate the successful implementation of coastal adaptation projects was carried out in Baie du Cap on 16 October 2015. A Memorandum of understanding (MoU) signed with the private sector - A MoU was signed between Attitude Foundation ( private sector ) and this Ministry to promote cooperation in the following (i) Plantation of mangroves (ii) Promotion of alternative livelihood for women in the coastal zone (iii) Organization of sensitization campaigns (iv) production of video clips on the 1st December 2015 . - 4,000 mangroves propagules were grown in a nursery and planted in the region of Anse la Raie, Grand Sable, Petit Sable and Pointe aux Piments on 6th November 2015 and 2nd December 2015 | MS
Technical design of coastal protection measures at each of three sites
Successful construction of physical interventions at each of the three sites
Analysis of data and development of recommendations on how the interventions can be adjusted for other vulnerable coastal locations in ROM
Monitoring programme designed, to include scoping of suitable parameters, including beach width and slope; depth of adjacent lagoonal sediments; wave height, period, and run-up; direction of nearshore current
A targeted coastal process/weather event monitoring system in place
| Assessment of the current sea state monitoring systems (Mauritius Meteorological Services and Mauritius Oceanography Institute) and definition of required critical parameters and operational requirements for an early warning system. |  | Procurement of consultancy Services for the implementation of an Early Warning System for incoming storm surge in the Republic of Mauritius to be completed The Early Warning System for incoming Storm Surge for the Republic of Mauritius installed at the Mauritius Meteorological Services and fully operational |  | Component 2: Early Warning System for Storm Surge for the Republic of Mauritius Memorandum of Understanding A Memorandum of Understanding (MoU) was signed between the MESDDBM and Mauritius Meteorological Services (MMS) for joint implementation of the project component on 13 March 2014. Consultancy Services awarded to Stichting Deltares The consultancy services for implementation of the Early Warning System for incoming Storm Surge in the Republic of Mauritius was awarded to Stitching Deltares, a leading independent research and internationally operating specialist consultancy institute. The consultants effected several field missions in Mauritius since 2014 until 2015. In July 2015, hands-on training on Delft-FEWS components and Mauritius EWS was delivered to officials from the MMS, Mauritius Oceanography Institute, NDRRMC. The main goal of the training sessions was to make the participants more comfortable dealing with the Delft-FEWS Early Warning System. In addition, the sessions provided the opportunity to explore the initial version of the EWS. The Consultants effected a last mission from 03 to 07 August 2015 in Mauritius. The EWS was implemented and operational at the Mauritius Meteorological Services (MMS). Some 20 participants from the MMS, Mauritius Oceanography Institute, National Disaster Risk Reduction Management Centre, Ministry of Housing and Lands (Hydrographic unit) and the project team received training on the operation of the EWS and Delft FEWS and Delft 3D models. Overseas Training in The Netherlands 3 officials (1 from the National Disaster Risk Reduction Management Centre, 1 from the AF Project team and 1 from MMS received 2 weeks training course in The Netherlands from 24 August to 05 September 2015. Mauritius is the first SIDS country to have implemented its own storm surge Early Warning System. Mission visit of International Consultant from Deltares Mr D. Vatvani, Project Coordinator of Deltares was on a 1 week mission visit to participate in a working session at the Ministry and to conduct further training organized by the World Meterological Organisation on storm surge, swells and modeling. The working session was held in the presence of the UN Resident Coordinator and UNDP Resident Representative, Offiials of this Ministry in order to finalize the way forward for the AF Project. Signature of Memorandum of Understanding (MoU) with Stitchting Deltares and UNESCO -IHE With a view to ensuring the sustainability of the project in relation to capacity building, technical support and technology transfer for a more effective use of the numerical model of the EWS, an MoU between this Ministry through the Adaptation Fund, Stichting Deltares and UNESCO- IHE was signed on 20 January 2016 in the Kingdom of Netherlands in the presence of the Hon Minister R. Dayal and the Project Manager. Purpose To secure technical assistance in terms of research and capacity building for coastal zone adaptation and operation of the Early Warning System for Storm and Tidal Surge. The Government of Mauritius (Cabinet office) approved of the Memorandum of Understanding (MoU) signed between this Ministry, Stichting Deltares and UNESCO IHE. The main areas of cooperation under the MoU are listed below: • Facilitate scientific and research exchange of scientists, research scholars and specialists, etc. for the purpose of research, training, consultation and exchange of expertise • Ensure Continuous Professional Development for staff of the Mauritius Meteorological Services • Training and capacity building in the field of disaster risk reduction management, coastal engineering and adaptation to climate change • Exchange of scientific and technical information and documentation • Organization of bilateral scientific and technical seminars/ workshops/ conferences and training courses on problems of interest to both countries. • Other forms of scientific and technological cooperation as may be mutually agreed upon by the parties within the scope of this MoU Steering Committee The setting up of a steering committee at the level of the Ministry of Environment was also agreed to monitor the implementation of the MoU A Project Steering Committee was set up under the Chair of the Ag. Senior Chief Executive. A first meeting was held on the 19 April 2016 followed by a skype meeting on the 4th July 2016 under the chair of the Ag Senior Chief Executive. Proposals from Stichting Deltares for trainings is currently being considered with respect to the theoretical classes and exercises for learning on generic Integrated Coastal Zone Management principles and to be scheduled in the August 2016. | S
The early warning system installed and implemented
| Handbook on Coastal Adaptation” packaged as training modules for coastal communities, relevant Government agencies, and private sector stakeholders |  | Courses developed and implemented |  | Component 3 : Training 4 Handbooks produced under the Adaptation Fund Project • 1 Handbook entitled ‘Training Manual for Coastal Protection Works’ • 1 Handbook entitled ‘Training Manual on Coastal and Marine Environment for Engineers’ • 1 Handbook on 'Cost Benefit Analysis for Coastal Management and Adaptation Options to Climate Change' • 1 Handbook on Integrated Coastal Zone Management under process 12 Short Courses designed and delivered in Mauritius and Rodrigues as follows: Coastal Engineering/Coastal and Marine Environment/ICZM/Disaster Risk Reduction/Open Geospatial tools • Short Course on Coastal and Marine Environment for Engineers (CMEE) in Mauritius • Short Course on Coastal and Marine Environment for Engineers (CMEE) in Rodrigues • Short Course on Coastal Engineering (Specialisation 1) Mauritius • Short Course on Coastal Engineering (Specialisation 2) Design of Coastal Adaptation/ Protection Structures including a case study for Mon Choisy (Mauritius) • Short Course on Ocean Data Collection and Analysis (Mauritius) • Short Course on Climate Change and Coastal Zone Management (Mauritius) • Short Course on Open Geospatial tools • Short Course on Disaster Risk Reduction • Short Course on ICZM Short Course on Cost Benefit Analysis for Coastal Adaptation Measures •Short Course on Cost and Benefit Analysis of Coastal Adaptation Measures •Short Course on Cost Benefit Analysis/Climate Change Economics •Short Course on Cost and Benefit Analysis of Coastal Management and Adaptation Options to Climate Change (Rodrigues) 469 Engineers and technical staff (both from public and private sector) have been trained under the Adaptation Fund Project Activities during September 2015-July 2016 - Short course on Introduction to Open Source Geospatial Tools A short course on Introduction to Open Source Geospatial Tools was delivered at the University of Mauritius from 21 to 25 September 2015 by Mrs M. Cawley, Founder of Boomerang Geospatial who provide training and consulting on GIS (Geographic Information System). 25 Participants from the technical cadre attended the short course. - Short Course on Disaster Risk Reduction in the Coastal Zone of Mauritius The course was held on the 13th, 14th, 15th, 18th January 2016 at the seat of the University of Mauritius (UoM) and an evacuation drill carried out on 16th January 2016 at Quatre Soeurs. - Evacuation Drill Day An evacuation drill was devised by the course participants to test an evacuation plan for the region of Quatre Soeurs. This enabled the inhabitants at Quatre Soeurs to seek refuge in the Refuge Centre which will be constructed under the Adaptation Fund. This exercise was done in collaboration with the National Disaster Risk Reduction Management Centre and other stakeholders including the coastal communities. The evacuation drill required the planning of various meetings with the relevant stakeholder, site visits in the local region of Quatre Soeurs and the production of materials. This included the design and printing of a Banner, Road Signs (Assembly points, direction for emergency evacuation route) and purchase of reflective jackets for participants amongst others. - Short Course on Integrated Coastal Zone Management. The ICZM course was carried out from the 29th January 2016, 2nd February to the 5th February 2016 at The Core Building, Ebene. The course included a field visit at the Adaptation Fund Project Site, Mon Choisy conducted on the 3rd of February. The course was delivered by the resource persons from the University of Western Australia Mr A. Pomeroy and Mr R. Lowe. 35 participants attended the course. Award of Certificate Ceremony for the Short course on Integrated Coastal Zone Management A half day workshop and an award of Certificate ceremony which consisted of a handing over of certificates for the ICZM course, was scheduled on the 5th of February 2016 in the Presence of the Hon. Minister of Environment, the Assistant Secretary of the Africa Branch, Mr Matthew Neuhaus from the Australian Department of Foreign Affairs and Trade, the Australian Commissioner, Her Excellency Ms Susan Coles and amongst some other 40 invitees. | HS
Short course on Coastal Engineering designed and delivered
Specialized course on Cost-Benefit Analysis of coastal adaptation measures designed and delivered
| A National Coastal Zone Adaptation that addresses all perceived climate change risks in the coastal zone of ROM over at least the next 20 years, with recommendations for supporting policies and regulations |  | Procurement Procedures for Consultancy Services completed |  | Policy Mainstreaming • Expression of Interest completed • 6 international consultants shortlisted • TOR finalized • List of acts for Republic of Mauritius compiled • Gap analysis undertaken by Technical Committee • List of reports and documents w.r.t. Policy in coastal zone of Mauritius compiled Launching of Expressions of Interests for Policy Mainstreaming In line with the deliverables under the Adaptation Fund Project, it is intended to recruit a high profile consultant/expert for Policy Mainstreaming. The main objective is to determine a National Coastal Zone Adaptation Strategy that will address all climate perceived risks in the coastal zone of Republic of Mauritius over the next 20 years and actively supporting adaptation to them, as well as, recommendations for economic instruments to scale up adaptation in the coastal zone. Request for Proposal (RFP) document for Consultancy Services (First Round of Procurement) The RFP document for above consultancy Services was launched on 18 December 2015 to the shortlisted firms approved by the Project Steering Committee. At the closing date on 10 February 2016. However, no bids were received. RFP document for Consultancy Services (Second Round of Procurement) The bids for the above consultancy services have been relaunched following a restricted bidding mode of procurement at National Level on the 29th February and the closing date for submission of bids was 31 March 2016. No bids were received. Request for Proposal (RFP) document for above consultancy Services (Third Round of Procurement) The ToR has been reviewed by the Project team in collaboration with the UNDP. The third round of procurement will be launched in August 2016 for the above consultancy services. | MS
A set of recommendations on best technical and institutional adaptation practices suitable for the coastal zone of ROM.
Definition of the required structure and processes for one “clearinghouse” or climate change oversight in the coastal zone of ROM
| Handbook, training modules, and website content capturing best coastal adaptation practices for the Mauritius context |  | This component shall be implemented upon completion of the works and monitoring of the effectiveness of the adaptation measures through lessons learned. |  | Component 5: knowledge Dissemination A Handbook on coastal Adaptation for the coastal Communities A handbook targeted to coastal communities, NGOs and private sector stakeholders is currently being developed since March 2016. It has as main objective to explain the effects of climate change in the coastal zone of Mauritius and capture the coastal adaptation practices for the Mauritius. It will be issued in English, French and Mauritian Creole. The First Chapter of the Handbook was submitted in June 2016 and is currently under review at the Level of this Ministry. A Technical working group chaired under the Deputy Director, of the Ministry has been constituted. Monthly meetings are held since June 2016 to monitor the progress of development of handbook. Interpretive signs and smallscale models Signature of Memorandum of Understanding A first MoU was signed between Reef Conservation and the MESDDBM to kick start the joint implementation of the project on sensitization of the Coastal Communities using a Marine Mobile Unit, development of sensitization materials and 3D Small Scale Models on mangroves ecosystem, coastal zones, coastal adaptation works, as well as, educational tours on mangroves ecosystem, coastal zones and coastal adaptation works. Memorandum of Understanding with Reef Conservation (NGO) and Rogers Foundation ltd (Private Sector) A MoU was signed on 30 March 2016 between Reef Conservation (NGO) , Rogers Foundation Ltd (Private Sector) and this Ministry for the joint undertaking of the activities listed under Component 3: Training and Component 5: Knowledge Dissemination, for a period of 1 year. This initiative provides a platform for public and private partnership to endeavour to adapt in the coastal zone of Mauritius. The areas of cooperation were; • Sensitisation among the Coastal Communities taking into consideration gender and outreach campaigns using the Marine Mobile Educational Unit, also known as ‘Bis Lamer’. • Development of learning/sensitization materials. This will include: 1. A Handbook on coastal Adaptation for the coastal Communities 2. An electronic quiz game 3. 3D small scale Bis Lamer with protective carry case 4. A Do’s and Don’ts sheet at sea with the pouch for boat operators and fishermen. 5. The development of Climate Change community sensitisation game (snakes and Ladder) Current Status • 5 Small Scale Models developed • 2 Display Boards Installed • 3D Small Scale Bis Lamer Model completed • 3D Small Scale Model for South East Marine Protected Area, Marine Park Completed • 3D Climate Change Globe Model • Electronic Quizz Game Electronic Game Application The development of a concept for a game application on climate change targeted for children aged 12 and above has been developed. The purpose is to create an innovative tool to raise awareness about impacts of climate change, targeted for the youth. Public awareness campaigns Development of 1 Marine Mobile Education Unit A Marine Mobile Unit was developed by the Rogers Group (private sector) in collaboration with Reef Conservation (NGO) and the Ministry. The Marine Mobile Education Unit was officially launched on 09 September 2014 at Rogers House, Port Louis. Current Status • 26 sensitization/public awareness campaigns conducted using the Marine Mobile Educational in schools, community centers, social welfare centers and shopping malls. • 2721 students (primary and secondary schools) and coastal communities sensitised as follows; a) Primary School Children of Standard IV, V and VI of St FranXavier RCA on 29 September 2015 b) Elderly Associations and local Communities at Pandit Dayanand Recreational Centre on 30-Sep-15 c) Coastal Communities of Blue Bay Public Beach on 23-Jan-16 d) General Population in the region of Trianon Shopping Mall on 16-Apr-16 e) Secondary School Students of Form 1 to 5 at SSS Swami Vivekananda on 19-Apr-16 f) Secondary School Students of Form 4 & 5 at SSS Rajcoomar Gujadhur on 5-May-16 g) Coastal communities of Bain Boeuf Public Beach on 21-May-16 h) Primary School Students at Quatre Cocos on 26 May 2016 i) Primary School Students at Bois des Amourettes GS 14 June 2016 j) Palmar Community Centre on 18 June 2016 k) Secondary School Students of Form 3 and 4 SSS Pailles on 28 June 2016 l) Secondary School Students of Form 3 and 4 SSS La Gaulette on 30 June 2016 Some 15,000 people have already been sensitized to date on Climate Change Adaptation using the Marine Mobile Educational Unit. Resource Centre in Rodrigues • A working session was held with the Office of the Chief Commissioner, Commissioner of Environment and Island Chief Executive of the Rodrigues Regional Assembly (RRA) on 17 and 18 November 2014. Representatives from the UNDP CO, UoM, and the Project Team attended the working session. The signature of a MoU with the RRA was agreed. The construction of a new resource centre within the South East Marine Protected Area (SEMPA) in Rodrigues was approved by the RRA. The progress of activities in Rodrigues were as follows; • A site visit was effected on 23 Dec 2014 by the Rodrigues Cadastral Office, Public Infrastructure Division, Environment Unit and SEMPA team to discuss the project requirements. • A second site visit was effected on 27 Jan 2015 by the Commissioner of Environment, Departmental Head, Commission of Environment, Global Consultants and SEMPA team for finalization of overall project requirements. • An official request was sent by the Commission of Environment (Rodrigues) to the Commission of Public Infrastructure for drafting of Preliminary Design of the Resource Centre. • Vesting of land by the Cadastral Office (Rodrigues) to SEMPA completed • Consultancy Services for Design and Preparation of Tender Docs by Global Consultant (Procurement completed) • Construction and hosting of Resource Centre in 2017 by the Rodrigues Regional Assembly • Development and funding of educational materials under the AF Project, such as, 3D Model of the SEMPA, and other learning materials The construction work for the SEMPA Interpretation Centre started on 10 May 2016 and the completion date is January 2017. | S
Dissemination of lessons learned from the programme with coastal stakeholders in other locations in the southern Indian Ocean
Interpretive signs and smallscale models of coastal processes designed and installed at each site, explaining the science of climate change and coastal processes
Public awareness campaigns on climate change in the coastal zone designed and delivered
[5 empty] | Overall Rating | S
Please Provide the Name and Contact information of person(s) reponsible for completeling the Rating section
| Name: | Nuvin KHEDAH, project manager
| Email: | mnkhedah@yahoo.com
Please justify your rating. Outline the positive and negative progress made by the project since it started. Provide specific recommendations for next steps. . (word limit=500)
Despite two setbacks on important procurement processes (Outcome 1 and 2) the progress made during the reporting period is satisfactory. Thanks to budget revision and a good collaboration between the Ministry of Environment and SD and the other stakeholders, the project team was able to identify alternative procurement methods (through UNDP for Outcome 1 and with support from Meteorological Services through a MoU signed for Outcome 2) which allowed to successfully relaunch the RFPs. The consultant's (outcome 1) meagre performance has warranted a design review to ensure technical soundness of structural measures. The mangroves plantation project was successfully (refer to above for more details) The Early Warning System for Incoming Storm Surge in the RoM was implemented and operational at the Mauritius Meteorological Services (refer to above for more details) The procurement of the land for construction of the Refuge Center at Quatre Soeurs by the Government of Mauritius was completed (refer to above for more details) and contract for the construction works awarded. Thanks to a very robust partnership (MoU) signed with the University of Mauritius, in particular the newly created faculty of Ocean Studies, the delivery under Outcome 3 is more than satisfactory with an expected high level of durability. Progress under this training component allowed to create a momentum around the project and keep the stakeholders interested and involved during the procurement process which will benefit the whole project in the long term. Delivery of Outcome 3 also links to delivery of Outcome 5 (Knowledge Management and Dissemination) and all training materials/training manuals/ and lessons learned are compiled for future diffusion at national and international levels. Due to high level of priority of procurements for Outcome 1 and 2, and emphasis put on training and capacity building from the start of the project, implementation of the Policy Mainstreaming component (Outcome 4) had been postponed to the next reporting period, without comprimising the full delivery of this Outcome. The next phase of the project, following the procurement of consultancy services and completion of studies will be to embark on procurement of contractor for works at Mon Choisy and Riviere des Galets and start of constrution works. The construcion of the Refuge Centre is also expected to be completed by the end of the next reporting period. Training and KM activities will continue, building on an excellent dynamix and the component 4 on Policy Mainstreaming will also be launched and completed in the next reporting period.
| Progress on Key Milestones |  | Expected Progress |  | Progress to Date | Rating
Implementing Agency | Detailed technical assessment of each site |  | Consultancy services for the preparation of feasability studies, Environmental Impact Assessment reports, Design, preparation of bid documents and supervision of works for the implementation of coastal adaptation measures at Mon Choisy and Riviere de Galets. Consultancy services for design, preparation of tender document and supervision of works for the construction of Refuge Centre, Drainage System and Ancillary works at Quatre Soeurs. |  | Quatre Soeurs Technical assessment of the site, conceptual/architectural design, EIA, preparation of bid document, bid and bid evaluation are completed and contract works awarded and actual works will start in August 2016 . Mon Choisy and Riviere des Galets Technical assessment of the site, Feasibility study, Cost benefit analysis are completed. Consultations and discussions have conducted regarding to the final designs and will be updated. Once they will be finalized bid document will be prepared and bids for construction works will be launched. 22000 Mangroves planted and good performance in terms of gender balance. | MS
Technical design of coastal protection measures at each of three sites
| Successful construction of physical interventions at each of the three sites |  | Construction of Refuge Centre at Quatre Soeurs:
| Analysis of data and development of recommendations on how the interventions can be adjusted for other vulnerable coastal locations in ROM |  | Analysis of data and development of recommendations on how the interventions can be adjusted for other vulnerable coastal locations in ROM |  | The contract for consultancy services for Mon Choisy & Riviere des Galets included development of baseline for future work at the 2 sites. This is in line with plans to inform 21 more vulnerable sites with methodologies for analysis, modeling, and concrete recommendations for a coastal zone monitoring system. Government of Mauritius have discussed and agreed that the proposed constructions at the two sites are initial steps. The result of the adaptation works at those two sites will be monitored and the results used to implement solutions at other sites. | MS
| Monitoring programme designed, to include scoping of suitable parameters, including beach width and slope; depth of adjacent lagoonal sediments; wave height, period, and run-up; direction of nearshore current |  | Monitoring programme designed, to include scoping of suitable parameters, including beach width and slope; depth of adjacent lagoonal sediments; wave height, period, and run-up; direction of nearshore current
| A targeted coastal process/weather event monitoring system in place |  | A targeted coastal process/weather event monitoring system in place
| Assessment of the current sea state monitoring systems (Mauritius Meteorological Services and Mauritius Oceanography Institute) and definition of required critical parameters and operational requirements for an early warning system. |  | Assessment of the current sea state monitoring systems and an Early Warning system |  | The numerical model and the setting up of a fully automated Early Warning System for Storm and tidal Surge at the Mauritius Meteorological Services was completed and is operational as from September 2015. This project also warranted detail bathymetry data off the coast Mauritius, Rodrigues and Agalega to be retreived from Indian Authorities. | S
| The early warning system installed and implemented |  | The early warning system installed and implemented |  | A first version of the Early Warning System installed at the Mauritius Meteorological Services on the two high performance computers procured by the project. The hands on training was also delivered to officials from Mauritius Meteorological Services, Mauritius Oceanography Institute and NDRRMC. Memorandum of Understanding ( MoU ) with Stitchting Deltares and UNESCO -IHE was signed to ensuring the sustainability of the project in relation to capacity building, technical support and technology transfer for a more effective use of the numerical model of the Early Warning System. Ministry of Environment was also agreed to monitor the implementation of the MoU. | S
| Handbook on Coastal Adaptation” packaged as training modules for coastal communities, relevant Government agencies, and private sector stakeholders |  | Available |  | 3 Handbooks have already developed under the Adaptation Fund Project • 2 Handbooks entitled ‘Training Manual for Coastal Protection Works’ and ‘Training Manual on Coastal and Marine Environment for Engineers’ produced under the programme. • 1 Handbook on Cost Benefit Analysis for Coastal Management and Adaptation Options to Climate Change developed. • 1 Handbook on INTEGRATED COASTAL ZONE MANAGEMENT FOR SMALL ISLAND DEVELOPING STATES under production (expected completion in September 2016) | S
| Short course on Coastal Engineering designed and delivered |  | 9 Short Courses completed (in total) in collaboration with the University of Mauritius. 3 courses are delivered during this reporting period |  | Short Course on Open Geospatial tools delivered in September 2015 Short Course on Disaster Risk Reduction delivered in January 2016 Short Course on Integrated Coastal Zone Management delivered in January-February 2016
| Specialized course on Cost-Benefit Analysis of coastal adaptation measures designed and delivered |  | 3 Short Courses (CBA) have already delivered before this reporting period. Preparation for another CBA course completed. |  | 3 Short Courses (CBA) have already delivered before this reporting period. • Short Course on Cost and Benefit Analysis Applied to Climate Change Initiatives will be delivered in September 2016.
| A National Coastal Zone Adaptation that addresses all perceived climate change risks in the coastal zone of ROM over at least the next 20 years, with recommendations for supporting policies and regulations |  | Expected in 2016 /17 • Review of documents pertaining to coastal zone management • Final National Coastal Zone Adaptation Strategy • Creation of ‘clearing house’ for climate change • Recommendation for new economic instruments to fund climate change related projects |  | The request for proposal for this consultancy service was launched two times (Dec 2015 and Feb 2016), but no bids were received. The TOR was amended in consultation with UNDP and a new RFP is expected to be launched in August 2016. | MS
A set of recommendations on best technical and institutional adaptation practices suitable for the coastal zone of ROM.
Definition of the required structure and processes for one “clearinghouse” or climate change oversight in the coastal zone of ROM
Recommendations for new economic instruments
| Handbook, training modules, and website content capturing best coastal adaptation practices for the Mauritius context |  | Expected 2016/17 |  | Handbook on integrated Coastal Zone Management for the coastal zone Mauritius will be completed by January 2017. | S
| Dissemination of lessons learned from the programme with coastal stakeholders in other locations in the southern Indian Ocean |  | • Regional Seminar planned |  | The project team participated in two regional conferences in collaboration with the Indian Ocean Rim Association (IORA), Global Water Partnership (GWP), and University of Mauritius in October 2015 and June 2016 where 200 participants from the region (SADC countries) were present. The salient issues, lessons learned and best practices were showcased.
| Interpretive signs and smallscale models of coastal processes designed and installed at each site, explaining the science of climate change and coastal processes |  | Completed |  | 5 Small Scale Models developed & 2 Display Board Installed are already compleated before this reporting period. Following 2 small scale model developped during this reporting period. • 3D Small Scale Model for South East Marine Protected Area, Marine Park • 3D Climate Change Globe Model and Magnetic Game and Electronic Quizz Game will be expected in 2016/17.
| Public awareness campaigns on climate change in the coastal zone designed and delivered |  | 800 students (primary and secondary schools) and coastal communities sensitised |  | 1 Marine Mobile Education Unit developed jointly with private sector/NGO • 12 sensitization/public awareness campaigns conducted using the Marine Mobile Educational in schools, community centers, social welfare centers and shopping malls completed during the reporting period
| Priority ranking of vulnerable coastal sites established, to guide the order of future investment by the Government of Mauritius and the private sector |  | Expected in 2017 - 18 |  | Expected in 2017 - 18
[5 empty] | Overall Rating | MS
Please Provide the Name and Contact information of person(s) reponsible for completeling the Rating section
| Name: | T. Sawako, Environment Programme Officer
| Email: | sawako.tanaka@undp.org
| Progress on Key Milestones |  | Expected Progress |  | Progress to Date | Rating
Other
Overall Rating
Please Provide the Name and Contact information of person(s) reponsible for completeling the Rating section
Name:
Email:
Please justify your rating and address the following points: 1. Indicate trends, both positive and negative, in achievement of outcomes as per the project indicators. 2. Detail critical risks that have affected progress. 3. Outline response to MTR undertaken this reporting period. 4. Outline action plan to address projects with a rating of HU, U or MU. Please keep your input to 1200 words | The overall rating is moderate satisfactory because the project actions/activities planned for current reporting period are progressing, but main part has been delayed. There are several positive trend in achievement of outcomes as per the project indicators. Outcome 1 has been the main strategic focus during the reporting period. Indufor in a consortium with eCoast and CLAMS Ltd were engaged to undertake a number of studies in relation to works to be undertaken at Mon Choisy and Riviere des Galets. They conducted community survey at the site as well. The Project Management Unit within the Ministry of Environment, Sustainable Development, and Disaster and Beach Management (Ministry) expressed concerns regarding to the adaptation options and could not come to the conclusion of the Final Design for a couple of months. However, after the Design Review conducted by UNDP consultant, Steering Committe was able to agree on the way forward. Considering the proposed adaptation measures will have long term impacts and has the largest project investment (USD 6,680,440), it was deemed that it was important to take the necessary time to achieve the required designs. Key decisions have now been made and it is expected that the project will achieve a satisfactory rating in the next reporting period. Quite good progress has been achieved with regard to the Quatre Soeurs site. The process of land availability and acquisition for the construction of the Refuge Centre at Quatre Soeurs was one of the main risks at the beginning. However, the land acquisition process was successfully completed in June 2015 by the Ministry of Housing and Lands and the necessary procedures to be able to start the construction of the Refuge Centre, Drainage System and Ancillary Works at Quatre Soeurs were finished during this reporting period. The representatives from the community joined the day of the handing over the project site and have been keeping good communication. The construction works started in August 2016. The mangroves project completed successfully. It was an effective community-based adaptation strategy and the mangroves project was replicated in other areas in the Republic of Mauritius in partnership with the private sector and the local community. Outcome 2 has already completed and the EWS is operational at the Mauritius Meteorological Services since 2015. In addition, the Memorandum of Understanding (MoU) is made between Government of Mauritius and Stitchting Deltares and UNESCO -IHE. This will help in the implementation of the EWS and further regional cooperation. Data sharing has been key issue in Mauritius. As suggested by MTR, development of regional partnership agreement on data-sharing during next reporting period will help future effectiveness of this system. Component 3 is in good progress and expected targets are achieved. Capacity development training activities have been organized including site visits to the actual project implementing sites. Events are organized with involvement of the community that have direct impact from the project works and helped their capacity development. Appropriate impact assessment of the training activities will be needed in the next reporting period. Outcome 4 has been delayed since the RFP for Policy Mainstreaming did not receive any proposals. The present policy review and learning activities were conducted during the review of TOR. Then, the third round of invitations to bid launched in August 2016. As suggested by MTR, baseline studies as well as strong support and understanding from line ministries are needed in implementing stage. The implementation of components 5 is in good progress with no major bottlenecks. A memorandum of understanding has been signed with the University of Mauritius (UoM) has produced good results. Several training courses and sensitization activities on climate change and coastal adaptation have been strengthening of climate change adaptation capacity of the future generation.
2. Detail critical risks that have affected progress.
Rating Definitions
|  |  | Highly Satisfactory (HS) | Project actions/activities planned for current reporting period are progressing on track or exceeding expectations to acheive all major outcomes/outputs for given reporting period, without major shortcomings. The project can be presented as “good practice”.
|  |  | Satisfactory (S) | Project actions/activities planned for current reporting period are progressing on track to achieve most of its major outcomes/outputs with only minor shortcomings.
|  |  | Marginally Satisfactory (MS) | Project actions/activities planned for current reporting period are progressing on track to achieve most major relevant outcomes/outputs, but with either significant shortcomings or modest overall relevance.
|  |  | Marginally Unsatisfactory (MU) | Project actions/activities planned for current reporting period are not progressing on track to achieve major outcomes/outputs with major shortcomings or is expected to achieve only some of its major outcomes/outputs.
|  |  | Unsatisfactory (U) | Project actions/activities planned for current reporting period are not progressing on track to achieve most of its major outcomes/outputs.
|  |  | Highly Unsatisfactory (U) | Project actions/activities planned for current reporting period are not on track and shows that it is failing to achieve, and is not expected to achieve, any of its outcomes/outputs.

## Project Indicators
PROJECT Indicators
Please provide all indicators being tracked for the project as outlined in the project document
Type of Indicator (indicators towards Objectives, Outcomes, etc…)
Type of Indicator | Indicator | Baseline | Progress since inception | Target for Project End
Outcome 1 | Physical infrastructure improved to withstand climate change and variability-induced stress | The beach at Mon Choisy is eroding at a rate of about 2 metres/year; Riviere des Galets is exposed to storm surges, with a failing seawall, openings in the wave overtopping wall, and an inadequate drainage system in the village; buildings in Quatre Soeurs frequently flood during high tides | 0/3 Mangroves Project completed and replication to other coastal sites in RoM (see details at output level) Studies completed-(see details at output level) Bid document for Mon Choisy & Riviere des Galets expected on 19 August 2016 Contract for Construction works for Quatre Soeurs awarded and construction works started in August 2016 (see details at output level) | No further erosion at Mon Choisy (beach accretion of 2 metres over 3 years); no surge flooding and no further shore erosion at Riviere des Galets; and, no flooding of coastal public buildings at Quatre Soeurs. The target for numbers of beneficiaries (as per prodoc) are as follows: Mon Choisy: 1,500-2000 people; Riviere des Galets: 100-150 people; Quatre Soeurs: 1000 people.
Output 1 | Number of physical assets strengthened or constructed to withstand conditions resulting from climate variability and change (by asset types) | No physical asset in place at site 1 (Mon choisy ) to withstand conditions resulting from climate change | 0/1 1. Contract awarded to Indufor Oy in September 2014 for services in respect of Coastal Adaptation Measures at Mon Choisy & Riviere des Galets •Technical assessment of site: completed • Feasibility study : completed • Options for Coastal Adaptation including Cost/benefit analysis: completed • Design of adaptation measures: ongoing • EIA Study: ongoing • Independent Technical Review of Design for Mon Choisy completed | Physical works properly designed and constructed at Mon choisy 1.1 Clear chronology of coastal process “events” at each site over the last 25 years and oceanographic dataset (2 months of data) for each of the three sites. COMPLETED 1.2 Detailed technical specifications and costs for coastal protection measures at each of the three sites, carried out in a gender sensitive way. COMPLETED 1.3 Physical works properly designed and constructed at each of the three sites, including: detached offshore submerged wave attenuation structures (sloped rock mounds); planting of mangroves; and,planting of beach crest vegetation at Mon Choisy; detached offshore submerged wave attenuation structures (sloped rock mounds); planting of beach crest vegetation; and, development of a drainage scheme for the backshore at Riviere des Galets; planting of mangroves; UPCOMING-EXPECTED START DATE FOR WORKS: JAN 2017 1.4 Comprehensive data on the effectiveness of the structures at each of the three sites: UPCOMING 1.4 Recommendations for structural adjustments (location, design, materials, etc.) for interventions at other coastal sites in ROM: UPCOMING 1.5 Monitoring design report: UPCOMING 1.6 A functional monitoring system in place: UPCOMING
|  | No physical asset in place at site 2 (Quatre Soeurs) to withstand conditions resulting from climate change | 0/1 1. The Contract for Consultancy Services for Design, Preparation of bid document and Supervision of Works for the Construction of a Refuge Centre, Drainage System and Ancillary Works at Quatre Soeurs was awarded to the Consortium Mega Design in association with Design Forum, STEGET, SEE Engineering Consultants Co Ltd and Chuttur & Partners Ltd on 06 June 2015 2. Acquisition of freehold land on higher grounds of an extent of 3A04P (1ha2,850 m2) for construction of a Refuge Centre at Quatre Soeurs was completed on 08 June 2015 3. Mangrove plantation component (100% completion) with 20,000 mangroves planted and replication of the mangroves project at (6) other sites in the Republic of Mauritius | Physical works properly designed and constructed at Quatre Soeurs 1.1 Clear chronology of coastal process “events” at each site over the last 25 years and oceanographic dataset (2 months of data) for each of the three sites. NOT RELEVANT (Refuge Centre) 1.2 Detailed technical specifications and costs for coastal protection measures at each of the three sites, carried out in a gender sensitive way. COMPLETED 1.3 Physical works properly designed and constructed at each of the three sites, including: detached offshore submerged wave attenuation structures (sloped rock mounds); planting of mangroves; and,planting of beach crest vegetation at Mon Choisy; detached offshore submerged wave attenuation structures (sloped rock mounds); planting of beach crest vegetation; repair and re-sloping of the seawall; sealing the wave- overtopping wall; and, development of a drainage scheme for the backshore at Riviere des Galets; planting of mangroves; re-constructing public buildings at risk on stilts at Quatre Soeurs. WORKS STARTING AUGUST 2016 1.4 Comprehensive data on the effectiveness of the structures at each of the three sites. UPCOMING 1.4 Recommendations for structural adjustments (location, design, materials, etc.) for interventions at other coastal sites in ROM. UPCOMING 1.5 Monitoring design report: UPCOMING 1.6 A functional monitoring system in place. UPCOMING
|  | No physical asset in place at site 3 (Riviere des Galets) to withstand conditions resulting from climate change | 1. Contract awarded to Indufor Oy for services in respect of Coastal Adaptation Measures at Mon Choisy & Riviere des Galets •Technical assessment of site: completed • Feasibility study : completed • Options for Coastal Adaptation including Cost/benefit analysis: completed • Design of adaptation measures: ongoing • EIA Study: Completed • Independent Technical Review of Design for Riviere des Galets completed | Physical works properly designed and constructed at Riviere des Galets 1.1 Clear chronology of coastal process “events” at each site over the last 25 years and oceanographic dataset (2 months of data) for each of the three sites. COMPLETED 1.2 Detailed technical specifications and costs for coastal protection measures at each of the three sites, carried out in a gender sensitive way. COMPLETED 1.3 Physical works properly designed and constructed at each of the three sites, including: detached offshore submerged wave attenuation structures (sloped rock mounds); planting of mangroves; and,planting of beach crest vegetation at Mon Choisy; detached offshore submerged wave attenuation structures (sloped rock mounds); planting of beach crest vegetation; repair and re-sloping of the seawall; sealing the wave- overtopping wall; and, development of a drainage scheme for the backshore at Riviere des Galets; planting of mangroves; re-constructing public buildings at risk on stilts at Quatre Soeurs. UPCOMING-EXPECTED START DATE FOR CONSTRUCTION WORKS: QUATRE SOEURS -AUGUST 2016 , RIVIERE DES GALETS/MON CHOISY -JANUARY 2017 1.4 Comprehensive data on the effectiveness of the structures at each of the three sites. UPCOMING 1.4 Recommendations for structural adjustments (location, design, materials, etc.) for interventions at other coastal sites in ROM. UPCOMING 1.5 Monitoring design report: UPCOMING 1.6 A functional monitoring system in place. UPCOMING
Outcome 2 | Relevant threat and hazard information generated and disseminated to stakeholders on a timely basis | MMS provides warnings to shipping based on perceived wave climate, and cyclone warnings for the general populace, but this system does not anticipate rogue swell conditions. | Project Completed- see details at output level EWS installed at the MMS | By 2018, more than 3,400 people in current surge zones) are able to safely evacuate prior to future storm surge events (there are no people left in the surge zone when the surge hits).
Output 2 | Development of early warning systems | No existing EWS for storm surges | • Inception Workshop-COMPLETED • Assessment of existing system at the Mauritius Meteorological Services--COMPLETED • National Workshop (Client and End User’s feedbacks)-COMPLETED • Assessment Report-COMPLETED • Design of an optimal Early Warning System for incoming Storm Surge in the Republic of Mauritius-COMPLETED • Setting up of Storm Surge Model-COMPLETED • Design Report-COMPLETED • Initial set up of the Early Warning System at the Mauritius Meteorological Services-COMPLETED • Procurement of Computer Equipments-COMPLETED • Procurement of Hydrographic data from the Indian Hydrographic Office-COMPLETED • Calibration of the Early Warning System model-COMPLETED • Final System Implementation-COMPLETED • Training (Mauritius & Netherlands) & Evaluation-COMPLETED | 1 early warning system up and running and effective during future storm events, such that no people in vulnerable coastal areas are exposed to storm surges in the future. 2.1 Assessment of the usefulness and practicality of the satellite data and the MMS system: COMPLETED 2.1 Parameters and analytical procedures for the early waning system defined: COMPLETED 2.2 Early warning system up and running and effective during future storm events, such that no people in vulnerable coastal areas are exposed to storm surges in the future. PROJECT COMPLETED
Outcome 3 | Number and type of targeted institutions with the capacity to minimise exposure to CC. | Public agencies are unclear on their obligations regarding management of climate change effects in the coastal zone, and the private sector and general populace do not know what options there are for coastal adaptation, nor how to initiate such measures in the most practical, cost-effective manner. | Partnership with the University of Mauritius set up. Other Collaborations • CEEPA (Centre of Environmental Economics and Policy in Africa) • University of Western Australia • India Institute of Technology, Madras, Chennai Involvement of all relevant national institutions secured. 1. Ministry of Environment, Sustainable Development, and Disaster and Beach Management 2. UNDP 3. Mauritius Oceanography Institute 4. Commission for Environment (Rodrigues Regional Assembly) 5. District Council of Pamplemousses 6. District Council of Riviere du Rempart 7. District Council of Savanne 8. Beach Authority 9. Ministry of Tourism and External Communications 10. Mauritius Meteorological Services 11. Ministry of Ocean Economy, Marine Resources, Fisheries, Shipping and Outer Island (AFRC) 12. Ministry of Housing and Lands 13. Ministry of Local Government 14. Outer Islands Development Corporation 15. Municipality of Vacoas/Phoenix 16. Road Development Authority 17. Ministry of Public Infrastructure and Land Transport (Public Infrastructure Division) 18. District Council of Grand Port 19. District Council of Black River 20. Tourism Authority 21. National Development Unit 22. National Coast Guard 23. Prime Minister’s Office 24. National Disaster Risk Reduction and Management Centre 25. Ministry of Social Integration and Economic Empowerment 26. Scene Ries Consult Ltd 27. Vyyaass Consulting Engineer Ltd 28. Luxconsult (Mtius) Ltd 29. GIBB (Mauritius) Ltd 30. Servansingh Jadav and Partners 31. University of Mauritius 32. Universite des Mascareignes 33. MACOSS (Ngos) 458 Participants trained as at 30 June 2016 | By 2016, at least 300 people, at least half of them women, trained. 458 People (officials from Ministries/departments, local authorities and the private sector) were trained as at 30 June 2016 & awarded a certificate of attendance (at least half of them women) 1 Short Course on CBA Applied to Climate Change Initiatives has been planned in September 2016
Output 3 | No. of staff trained to respond to, and mitigate impacts of, climate-related events | No coastal engineering capacities available at national level | 0/40 Collaboration with the University of Mauritius secured. 12 Short Courses completed in collaboration with the University of Mauritius. 458 Participants trained as at 30 June 2016. 1. Short Course on Coastal and Marine Environment for Engineers delivered in September 2013- 56 Participants trained 2. Short Course on Coastal Engineering delivered in October 2013- 54 Participants trained in the field of Coastal Engineering 3. Short Course on Cost and Benefit Analysis of Coastal Adaptation Measures delivered in December 2013- 41 Participants trained 4. Short Course on Coastal and Marine Environment for Engineers replicated in Rodrigues Islands in July 2014- 28 participants trained in Rodrigues Islands 5. Short Course on Coastal Adaptation Structures (soft measures) including a case study of Mon Choisy delivered in August 2014- 41 Participants trained. 6. Short Course on Cost Benefit Analysis/Climate Change Economics delivered in September 2014- 38 Participants trained 7. Short Course on Ocean Data Collection and Analysis delivered in January 2015- 29 Participants trained 8. Short Course on Climate Change and Coastal Zone Management delivered in June 2015- 33 participants trained 9. Short Course on Cost and Benefit Analysis of Coastal Management and Adaptation Options to Climate Change delivered in Rodrigues Islands delivered in May 2015- 42 Participants trained in Rodrigues Island 10. Short Course on Open Geospatial tools delivered in September 2015- 25 Participants trained 11. Short Course on Disaster Risk Reduction delivered in January 2016- 36 Participants trained 12. Short Course on Integrated Coastal Zone Management delivered in January-February 2016- 35 Participants trained | Coastal engineering short course designed and delivered (2x); at least 40 trainees certified. COMPLETED 3.1 Handbook complete, fully relevant to Mauritius coastal context, and used for coastal stakeholder and practitioner training twice per year over three years (at least 300 people, at least half of them women, formally trained). 3 Handbooks & Trainings COMPLETED 3.2 Coastal engineering short course designed and delivered (2x); at least 40 trainees certified. 337 Engineers and technical staff (both from public and private sector) in Mauritius & Rodrigues trained 3.3 C-B Analysis course designed and delivered (4 x); at least 100 trainees certified.COMPLETED 121 Government officials (Mauritius & Rodrigues) trained. 1 CBA Handbook COMPLETED
Outcome 4 | Climate change priorities are integrated into national development strategy | Current policies and regulations are inconsistent with regard to management of climate change effects in the coastal zone (they do not envision the coastal zone in 2060), and do not provide clear guidance or incentives for practical implementation of adaptive measures. | Terms of Reference launched 6 Consultants shortlisted for RFP Stage Shortlist of Individuals not approved by the Project Steering Committee New Terms of Reference drafted in consultation with UNDP CO Expected launching: June 2016 | All relevant policies, strategies, plans, and regulations are consistent in a) having a clear vision statement for adaptation in the coastal zone; b) in recognizing climate change impacts in the coastal zone over the next 50 years; and c) in clear Government institutional responsibilities for adaptation in the coastal zone. UPCOMING
Output 4 | Number, type and sector of policies introduced or adjusted to address Climate Change Risks. | National ICZM strategy does not fully integrate climate change and is not properly enforced | 0/1 Terms of Reference launched 6 Consultants shortlisted for RFP Stage Shortlist of Individuals not approved by the Project Steering Committee New Terms of Reference drafted in consultation with UNDP CO Expected launching: June 2016 | National Coastal Zone Adaptation Strategy in place which addresses all perceived climate change risks in the coastal zone over the next 20 years, with clear recommendations for appropriate policies, regulations, and guidelines for adaptation. UPCOMING 4.1 National Coastal Zone Adaptation Strategy in place which addresses all perceived climate change risks in the coastal zone over the next 20 years, with clear recommendations for appropriate policies, regulations, and guidelines for adaptation. UPCOMING 4.1 District Outline Schemes (all 9) and the National Tourism Development Plan recognize spatial limitations and capacity limits related to climate change risks, and provide guidance on appropriate locations and designs for infrastructure. UPCOMING 4.2 A “toolbox” with the most appropriate technical, institutional regulatory, and economic instruments available for all coastal practitioners in ROM; recommendations feeding into the policy and regulatory review. UPCOMING 4.3 Clear recommendations on the structure and processes of an oversight and regulatory body that addresses all climate change issues in the coastal zone with jurisdictional clarity. UPCOMING 4.3 Eventual establishment of that body (whether through the ICZM Division in the Ministry or the Climate Change Division). UPCOMING 4.4 Clear analysis and recommendations for design and implementation of economic instruments that will facilitate public and private sector compliance with the best coastal adaptation practices. UPCOMING
Outcome 5 | Effective capturing and dissemination of lessons from the applied activities in the programme. | There is no consistent awareness nor understanding of the implications of climate change in the coastal zone; households, communities, and Government organizations do not factor into their plans and activities the possible climate change effects 50 years from now. | To be implemented based on completion of component 1 | By 2018, effective capturing and dissemination of lessons from the applied activities in the programme.
Output 5 | Dissemination of lessons learned from the programme with coastal stakeholders in other locations in the southern Indian Ocean. | Mauritian coastal practitioners able to disseminate lessons from the programme to other countries in the southern Indian Ocean and to examine the experiences in those countries | 0/3 To be implemented based on completion of component 1 | Handbook, training modules capturing best coastal adaptation practices in the mauritian context and dissemination of lessons learned in other locations of the Southern Indian Ocean 5.1. Handbook, training modules, and website content produced. COMPLETED 5.2 Mauritian coastal practitioners able to disseminate lessons from the programme to other countries in the southern Indian Ocean and to examine the experiences in those countries. UPCOMING- A Regional Conference planned in the next reporting period 5.3 Interpretive models and signs. These sites marketed and visitor attendance recorded. 7 Small Scale Models developed & 2 Display Board Installed 5.4 Relevant public awareness campaigns designed and delivered to all coastal villages in the 23% of beaches at risk in Island of Mauritius. 15000 People (coastal communities) sensitised 5.5 All vulnerable coastal sites in ROM mapped, scaled, and assessed for importance and degree of risk to climate change in the future. UPCOMING 5.5 Replication of coastal adaptation measures initiated, with Government of Mauritius and private sector funding (at least three sites initiated before the end of the project using other sources of funding). UPCOMING

## Lessons Learned
QUALITATIVE MEASURES and LESSONS LEARNED
Please complete the following section every reporting period
Implementation and Adaptive Management | Response
What implementation issues/lessons, either positive or negative, affected progress? | 1. The procurement of services and works have to follow lengthy procedures which impact in the project execution. 2. Most of the procurements had to undergo at least 2 rounds of procurement due to budget or scarcity areas & availability of international consultants 3. The land acquisition process for Quatre Soeurs by the Government was a lenghty process (1 yr) 4. The procurement of hydrographic data which was available at the Indian Hydrographic Unit was a lenghthy process (6 months). The Early Warning System for Storm Surge could not be finalised until availability of data. 5. The design for Mon Choisy & Riviere des Galets had to undergo 2 design reviews before finalisation of the most appropriate adaptation measures 6. The involvement and sensitisation of the community is an important factor for a successful implementation of adaptation project at the target site.
Were there any delays in implementation? If so, include any causes of delays. What measures have been taken to reduce delays? | 1. To reduce procurement timeframe for second round of procurement the Government sollicited the support of the UNDP. However, for procurements above USD 1,000,000 the UNDP procurement procedures are also lengthy, as necessary clearances from the Regional Bureau for Africa were required at various steps. Thanks to the close liaison between the Ministry and UNDP and between UNDP CO and UNDP RBA, the actual procurement was completed in 6 month's time. 2. The design for Mon Choisy & Riviere des Galets had to undergo 2 design reviews before finalisation of the most appropriate adaptation measures
Describe any changes undertaken to improve results on the ground or any changes made to project outputs (i.e. changes to project design) | 1. The site for Construction of a Refuge centre at Quatre Soeurs was reviewed at the Inception Phase to a more secured and accessible location to be resilient to storm surges and flooding. A suitable site of an extent of 12,850 M2 to the tune of USD 320,645 was identified at Quatre Soeurs and procured by the Government of Mauritius. This represent an in-kind contribution from the Government of Mauritius to the AF Project. 2. A budget reallocation between project components was warranted and approved by the AFB in May 2014
How have gender considerations been taken into consideration during the reporting period? What have been the lessons learned as a consequence of inclusion of such considerations on project performance or impacts? | 1. The compliance of the project with Equal Opportunity Act is mandatory as per Government legal framework. Focus on Gender has been fully integrated into project activities through involvement of women CSOs and NGOs in activities (Women's association have been actively involved in implementation of coastal adaptation projects, such as: mangrove plantation and sensitisation campaigns conducted by the women associations to coastal stakeholders on importance of mangroves on the coastal eco-system. The participation of women in all consultative meetings and coastal adaptation project was assessed positively at the Mid-Term Review. 2. Out of the 469 People trained under Outcome 3 (36% were Female & 64% Male) 3. Out of the 15000 People sensitised under Outcome 5 (45% were Female & 55% Male)
Please complete the following section at mid-term and project completion
Lessons for Adaptation | Response
Climate Resilience Measures
What have been the lessons learned, both positive and negative, in implementing climate adaptation measures that would be relevant to the design and implementation of future projects/programmes for enhanced resilience to climate change? | The budget allocation of the project at the project development phase for implementation of climate resilient measures need to allow for cost escallation to foresee the actual cost at the implementation phase as a buffer to allow the timelag between the project conception until the execution of the project. To ensure that the impacts of the climate change measures reach to the coastal communities, a community based approach was adopted for implementation of the mangroves project. This has involved the direct participation of the coastal communities and enhanced their livelihoods.
What is the potential for the climate resilience measures undertaken by the project/programme to be replicated and scaled up both within and outside the project area? | The Adaptation Fund Project has allowed appropriate and indepth studies at the AF Project sites to develop appropriate adaptation measures. Other sites in the Coastal Zone of Republic of Mauritius face the same challenges of beach erosion. The recommended adaptation measures have a great potential to be replicated/adapted to increase climate resilience. The ecosystem adaptation project on 'mangroves plantation' gained international recognition and has alerady been replicated at six other sites in the Republic of Mauritius
Concrete Adaptation Interventions
What have been the lessons learned, both positive and negative, in implementing concrete adaptation interventions that would be relevant to the design and implementation of future projects/programmes implementing concrete adaptation interventions? | This project has allowed the introduction of a CBA to enable the appropriate choice of adaptation measures based on lifetime costing. This is a new approach that was introduced to select the most appropriate option for climate resilience projects.
What is the potential for the concrete adaptation interventions undertaken by the project/programme to be replicated and scaled up both within and outside the project area? | The mangroves project has been replicated to other vulnerable coastal areas in the Republic of Mauritius. Short Training courses have been replicated to Rodrigues island The Training on the Early Warning System for Storm Surge for the Meteorological Services staff in Rodrigues island and replication of the EWS in Rodrigues is under way.
Community/National Impact
What would you consider to be the most successful aspects for the target communities? | Mangroves project The involvement of the community in project implementation through community based approach has enhanced a sense of project ownership Sensitisation Campaigns Sensitisation campaigns that have been carried out through innovative means of a mobile education unit has allowed a larger community outreach for the communities Early Warning System Implementation of EWS has allowed coastal communities to be informed on an enhanced forecasting system in the event of storm surges
What measures are/have been put in place to ensure sustainability of the project/program results? | A Memorandum of Understanding has been signed with the NGO's on community based projects to allow programmes to be continued in future based on the current lessons learnt.
What measures are being/could have been put in place to improve project/program results? | Project results on increasing resilience of the coastal communities at Quatre Soeurs increased through the land acquisition on higher grounds as opposed to the initial site which was on lower ground. On this particular output, besides the setting up of the Refuge Centre, alternative routes are also being identified and secured to allow mass evacuation in event of storm surge and calamities
Knowledge Management
How has existing information/data/knowledge been used to inform project development and implementation? What kinds of information/data/knowledge were used? | Project conceived based on assessment of all existing data available from previous works conducted which subsequently feeds in the design of the adaptation measures. In the context of implementation of Early Warning System the availability of bathymetry charts were critical for validation of the model. The data was not in possession at national level and had to be procured at international level. Intervention at highest level was also required to access data retained by the Indian Authorities following survey conducted by the indian navy in the region of Mauritius.
If learning objectives have been established, have they been met? Please describe. | 3 Training courses on CBA were delivered. The objective is to inculcate the option of having a CBA besides EIA which is a mandatory requirement. Mauritius has got no local expertise in coastal engineering and this project delivered Training on Coastal Engineering and this had been a unique opportunity to bring international expertise at local level. A MOU was signed with the University of Mauritius so that award courses on Coastal Engineering may be developed under the suppport of this project and build capacity at the University of Mauritius level for sustaining the training programme in the longer term. Two post graduate courses on (a) climate change adaptation and disaster risk management and (b) coastal engineering has been mounted with the support of this programme at the University of Mauritius to ensure sustainability of the training programme.
Describe any difficulties there have been in accessing or retrieving existing information (data or knowledge) that is relevant to the project. Please provide suggestions for improving access to the relevant data. | We need to have appropriate intervention at Government level to access data either through a Memorandum of Understanding. Data is also retained by various authorities (local) in their own format. It is suggested to harmonise all coastal data and data be readily available for future design of coastal adaptation measures.
Has the identification of learning objectives contributed to the outcomes of the project? In what ways have they contributed? | Climate change impacts thereof were not a common knowledge at the level of the coastal communities. The development of learning materials and tools including the mobile education unit was proven to disseminate the climate change issues and raise awareness among the community and therefore be better prepared to face and adapt at local level The training was extended to practically all institutions concerned with the coastal projects to achieve the objective under outcome 3, e.g. coastal planners from local authorities were involved which build capacity in delivery with a climate change induced risk perspective

## Results Tracker
Results Tracker for Adaptation Fund (AF) Projects
Goal: Assist developing-country Parties to the Kyoto Protocol that are particularly vulnerable to the adverse effects of climate change in meeting the costs of concrete adaptation projects and programmes in order to implement climate-resilient measures. Impact: Increased resiliency at the community, national, and regional levels to climate variability and change.
Important: Please read the following guidance document (also posted on the Adaptation Fund website) before entering your data
Link: http://www.adaptation-fund.org/sites/default/files/Results%20Framework%20and%20Baseline%20Guidance%20final.pdf
Adaptation Fund Strategic Results Framework
Project ID | 00062857
Implementing Entity | United Nations Development Programme (UNDP)
Type of implementing entity | MIE
Country | Mauritius
Region | Africa
Sector | Coastal management
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Impact: Increased resiliency at the community, national, and regional levels to climate variability and change | Core Indicator: No. of beneficiaries |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project
|  | Total | 6350 | 6350 |  | Total | 740000 | 75400 | 664000 | Total | 22985 | 5485 | 17500 | Total
|  | % of female beneficiaries |  | 30% |  | % of female beneficiaries | 30% | 30% | 30% | % of female beneficiaries | 30% | 30% | 30% | % of female beneficiaries
|  | % of Youth beneficiaries |  | 20% |  | % of Youth beneficiaries | 20% | 20% | 20% | % of Youth beneficiaries | 20% | 20% | 20% | % of Youth beneficiaries
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 1: Reduced exposure to climate-related hazards and threats | Indicator 1: Relevant threat and hazard information generated and disseminated to stakeholders on a timely basis | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness
|  | Total | 3400 | Storm surge | 2: Partially effective | Total | 54000 | Storm surge | 4: Effective | Total | 3400 | Storm surge | 3: Moderately effective | Total
|  | % of female targeted | 50% |  |  | % of female targeted | 50% |  |  | % of female targeted | 50% |  |  | % of female targeted
Output 1.1 Risk and vulnerability assessments conducted and updated | Indicator 1.1: No. of projects/programmes that conduct and update risk and vulnerability assessments | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | 2 | Coastal management | National | 2: Undertaking or updating of assessments in progress | 2 | Coastal management | National | 3: Risk and vulnterability assessments completed or updated | 2 | Coastal management | National | 2: Undertaking or updating of assessments in progress
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
Output 1.2 Targeted population groups covered by adequate risk reduction systems | Core Indicator 1.2: No. of Early Warning Systems | No. of adopted Early Warning Systems | Category targeted | Hazard | Storm surge | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  | 1 | 2: Monitoring and warning service | Geographical coverage | National | 3 | 2: Monitoring and warning service | Geographical coverage | National | 1 | 2: Monitoring and warning service | Geographical coverage | National |  |  | Geographical coverage
|  |  |  | Number of municipalities | 7 |  |  | Number of municipalities | 7 |  |  | Number of municipalities | 2 |  |  | Number of municipalities
|  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 2: Strengthened institutional capacity to reduce risks associated with climate-induced socioeconomic and environmental losses | Indicator 2: Capacity of staff to respond to, and mitigate impacts of, climate-related events from targeted institutions increased | Number of staff targeted |  | Sector | Capacity level | Number of staff targeted |  | Sector | Capacity level | Number of staff targeted |  | Sector | Capacity level | Number of staff targeted |  | Sector | Capacity level
|  | Total | 300 | Coastal management | 2: Low capacity | Total | 485 | Coastal management | 4: High capacity | Total | 258 | Coastal management | 3: Medium capacity | Total
|  | % of female targeted | 50% |  |  | % of female targeted | 50% |  |  | % of female targeted | 50% |  |  | % of female targeted
Output 2.1 Strengthened capacity of national and sub-national centres and networks to respond rapidly to extreme weather events | Indicator 2.1.1: No. of staff trained to respond to, and mitigate impacts of, climate-related events | Total staff trained | % of female staff trained | Type |  | Total staff trained | % of female staff trained | Type |  | Total staff trained | % of female staff trained | Type |  | Total staff trained | % of female staff trained | Type
|  | 300 | 50% | Public |  | 485 | 50% | Public |  | 258 | 50% | Public
| Indicator 2.1.2: No. of targeted institutions with increased capacity to minimize exposure to climate variability risks | Type | Scale | Sector | Capacity level | Type | Scale | Sector | Capacity level | Type | Scale | Sector | Capacity level | Type | Scale | Sector | Capacity level
|  | Public | National | Coastal management | 2: Low capacity | Public | National | Coastal management | 4: High capacity | Public | National | Coastal management | 3: Medium capacity
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 3: Strengthened awareness and ownership of adaptation and climate risk reduction processes | Indicator 3.1: Increase in application of appropriate adaptation responses | Percentage of targeted population applying adaptation measures |  | Sector |  | Percentage of targeted population applying adaptation measures |  | Sector |  | Percentage of targeted population applying adaptation measures |  | Sector |  | Percentage of targeted population applying adaptation measures |  | Sector
|  | 20% |  | Coastal management |  | 30% |  | Coastal management |  | 15 |  | Coastal management
Output 3: Targeted population groups participating in adaptation and risk reduction awareness activities | Indicator 3.1.1: Percentage of targeted population awareness of predicted adverse impacts of climate change, and of appropriate responses | No. of targeted beneficiaries | % of female participants targeted | Level of awareness |  | No. of targeted beneficiaries | % of female participants targeted | Level of awareness |  | No. of targeted beneficiaries | % of female participants targeted | Level of awareness |  | No. of targeted beneficiaries | % of female participants targeted | Level of awareness
|  | 5000 | 50% | 3: Partially aware |  | 50000 | 50% | 4: Mostly aware |  | 4000 | 60% | 4: Mostly aware
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Target performance at completion
Outcome 4: Increased adaptive capacity within relevant development sector services and infrastructure assets | Indicator 4.1: Increased responsiveness of development sector services to evolving needs from changing and variable climate | Project/programme sector | Geographical scale | Response level |  | Project/programme sector | Geographical scale | Response level |  | Project/programme sector | Geographical scale | Response level |  | Project/programme sector | Geographical scale | Response level
|  | Coastal management | National | 3: Moderately responsive (Some defined elements) |  | Coastal management | National | 4: Mostly responsive (Most defined elements) |  | Coastal management | National | 3: Moderately responsive (Some defined elements)
| Core Indicator 4.2: Assets produced, developed, improved or strengthened | Sector | Targeted asset | Changes in asset (quantitative or qualitative) |  | Sector | Targeted asset | Changes in asset (quantitative or qualitative) |  | Sector | Targeted asset | Changes in asset (quantitative or qualitative) |  | Sector | Targeted asset | Changes in asset (quantitative or qualitative)
|  | Coastal management | 2: Physical asset (produced/improved/strenghtened) | 3: Moderately improved |  | Coastal management | 2: Physical asset (produced/improved/strenghtened) | 5: Fully improved |  | Coastal management | 2: Physical asset (produced/improved/strenghtened) | 3: Moderately improved
|  | Disaster risk reduction | 2: Physical asset (produced/improved/strenghtened) | 3: Moderately improved |  | Disaster risk reduction | 2: Physical asset (produced/improved/strenghtened) | 5: Fully improved |  | Disaster risk reduction | 2: Physical asset (produced/improved/strenghtened) | 3: Moderately improved
Output 4: Vulnerable development sector services and infrastructure assets strengthened in response to climate change impacts, including variability | Indicator 4.1.1: No. and type of development sector services to respond to new conditions resulting from climate variability and change | Number of services | Type |  | Sector | Number of services | Type |  | Sector | Number of services | Type |  | Sector | Number of services | Type |  | Sector
|  | 2 | Coastal protection measures |  | Coastal management | 3 | coastal protection measures |  | Coastal management | 1 | coastal protection measures |  | Coastal management
|  | 1 | Construction of refuge centre for communities at risk |  | Disaster risk reduction | 1 | Construction of refuge centre for communities at risk |  | Disaster risk reduction | 1 | Construction of refuge centre for communities at risk |  | Disaster risk reduction
|  | Baseline information |  |  |  | Baseline information |  |  |  | Performance at mid-term |  |  |  | Target performance at completion
Outcome 5: Increased ecosystem resilience in response to climate change and variability-induced stress | Indicator 5: Ecosystem services and natural resource assets maintained or improved under climate change and variability-induced stress | Natural resource improvement level |  | Sector | Type | Natural resource improvement level |  | Sector | Type | Natural resource improvement level |  | Sector | Type | Natural resource improvement level |  | Sector | Type
|  | 1: Ineffective |  | Coastal management | biological assets | 4: Effective |  | Coastal management | biological assets
Output 5: Vulnerable ecosystem services and natural resource assets strengthned in response to climate change impacts, including variability | Core Indicator 5.1: Natural Assets protected or rehabilitated | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/ rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Mangroves | 1 | ha protected | 2: Partially effective | Mangroves | 2 | ha protected | 4: Effective | Mangroves | 1 | ha protected | 4: Effective
|  | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Coasts | 2 | km protected | 3: Moderately effective | Coasts | 2 | km protected | 4: Effective
|  | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Baseline information |  |  |  | Targeted performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 6: Diversified and strengthened livelihoods and sources of income for vulnerable people in targeted areas | Indicator 6.1: Increase in households and communities having more secure access to livelihood assets | No. of targeted households | % of female headed households | Improvement level |  | No. of targeted households | % of female headed households | Improvement level |  | No. of targeted households | % of female headed households | Improvement level |  | No. of targeted households | % of female headed households | Improvement level
|  | 60 | 50% | 2: Limited improvement |  | 115 | 50% | 4: High improvement
| Indicator 6.2: Increase in targeted population's sustained climate-resilient alternative livelihoods | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
|  | 60 | 1000% | From 5% to 10% | Agricultural-related | 60 | 10% | From 5% to 10% | Fishing
|  | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
[6 empty] | 55 | 100% | From 30% to 40% | Agribusiness
|  | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
|  | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
Output 6 Targeted individual and community livelihood strategies strengthened in relation to climate change impacts, including variability | Indicator 6.1.1: No. and type of adaptation assets created or strengthened in support of individual or community livelihood strategies | Number of Assets | Type of Assets | Sector | Adaptation strategy | Number of Assets | Type of Assets | Sector | Adaptation strategy | Number of Assets | Type of Assets | Sector | Adaptation strategy | Number of Assets | Type of Assets | Sector | Adaptation strategy
|  | 1 | Natural capital | Coastal management | Community-based adaptation | 3 | Natural capital | Coastal management | Community-based adaptation | 55 | Human capital | Coastal management | Mangrove reforestation
| Core Indicator 6.1.2: Increased income, or avoided decrease in income | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | 60 | Fishing |  | 200 | 60 | Fishing |  | 200 | 55 | Handicrafts |  | 100
|  | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
[6 empty] | 55 | Agribusiness |  | 300
|  | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 7: Improved policies and regulations that promote and enforce resilience measures | Indicator 7: Climate change priorities are integrated into national development strategy | Integration level |  |  |  | Integration level |  |  |  | Integration level |  |  |  | Integration level
|  | 3: Some |  |  |  | 4: Most |  |  |  | 3: Some
Output 7:Improved integration of climate-resilience strategies into country development plans | Indicator 7.1: No. of policies introduced or adjusted to address climate change risks | No. of Policies introduced or adjusted | Sector | Scale | Type | No. of Policies introduced or adjusted | Sector | Scale | Type | No. of Policies introduced or adjusted | Sector | Scale | Type | No. of Policies introduced or adjusted | Sector | Scale | Type
|  | 2 | Coastal management | National | Environmental policy | 2 | Coastal management | National | Environmental policy |  | Coastal management | National | Environmental policy
| Indicator 7.2: No. of targeted development strategies with incorporated climate change priorities enforced | No. of Development strategies | Regulation |  | Effectiveness | No. of Development strategies | Regulation |  | Effectiveness | No. of Development strategies | Regulation |  | Effectiveness | No. of Development strategies | Regulation |  | Effectiveness
|  | 3 | 1: Not enforced (No elements implemented) |  | 2: Partially effective | 3 | 1: Not enforced (No elements implemented) |  | 2: Partially effective |  | 3: Partially enforced (Some elements implemented) |  | 3: Moderately effective
Glacier lake outburst flood
|  | Inland flooding | fr | biological assets |  | Company policy | 5: Fully enforced (All elements implemented)
|  | Salinization | Decrease | land |  | Communication & Information policy | 4: Enforced (Most elements implemented)
|  | Drought | Same | water areas |  | Defense policy | 3: Partially enforced (Some elements implemented)
|  | Wind |  | subsoil assets | increased adpative capacity | Domestic policy | 2: Partially not enforced (Most elements not implemented) |  | Agribusiness
|  | Coastal flooding |  | air | achieved | Economic policy | 1: Not enforced (No elements implemented) |  | Agricultural-related | Financial capital
|  | Storm surge | Please choose |  | enhanced level of protection | Education policy |  |  | Agriculture | Human capital
|  | Hurricane | Selected | [5 empty] | Aquaculture | Physical capital
|  |  | Not relevant |  |  | 5: All (Fully integrated) |  |  | Construction/repairing business | Social capital
[6 empty] | 4: Most |  |  | Cultivation | Natural capital
[6 empty] | 3: Some |  |  | Fishing | Personal capital
Select | 5: All | Select |  |  | Community | 2: Most not integrated |  | Other | Forestry | Adaptation strategies
1 | 4: Almost all | Private | Type | Yes | Multi-community | 1: None |  | Agriculture | Handicrafts
2 | 3: Half | Public | Scale | No | Departmental |  |  | Coastal management | Livestock production
3 | 2: Some | NGO | Sector |  | National |  |  | Disaster risk reduction | Manufacturing
4 | 1: None |  |  |  |  | 5: Very high improvement | Established | Food security | other
|  | National |  |  |  | 4: High improvement | Maintained | Health | Services
|  | Regional |  |  |  | 3: Moderate improvement | Improved | Urban development | Tourism-related
|  | Local |  |  |  | 2: Limited improvement |  | Water management | Trading
[6 empty] | 1: No improvement |  | Multi-sector
|  | 1 -generated information is irrelevant, and neither the stakeholders reached nor the timeframe managed were achieved | 1: No info transferred on time | 4: High capacity | 5: Fully aware | 5: Highly responsive (All defined elements ) | 5: Fully improved | Roads | 5: Very effective
Asia-Pacific | NIE | 2 -the existence of some challenge in any of the three aspects of the indicator (generation of dissemination, stakeholders reached or timeframe managed) | 2: Somewhat info transferred | 3: Medium capacity | 4: Mostly aware | 4: Mostly responsive (Most defined elements) | 4: Mostly Improved | Gov Buildings | 4: Effective
Latin America and Caribbean | RIE | 3 -relevant information is generated and disseminated to all identified stakeholders on timely basis | 3: Info transferred on time | 2: Low capacity | 3: Partially aware | 3: Moderately responsive (Some defined elements) | 3: Moderately improved | Causeways | 3: Moderately effective
Africa | MIE |  |  | 1: No capacity | 2: Partially not aware | 2: Partially responsive (Lacks most elements) | 2: Somewhat improved | Airports | 2: Partially effective
Eastern Europe |  |  |  |  | 1: Aware of neither | 1: Non responsive (Lacks all elements ) | 1: Not improved | Schools | 1: Ineffective
| ha protected | [6 empty] | Training Centres
| ha rehabilitated | [5 empty] | Monitoring/Forecasting capacity | Hospitals
Afghanistan, Islamic Rep. of | km protected | [5 empty] | Policy/regulatory reform | Drinking water systems
Angola | km rehabilitated | 1: Risk knowledge | 1: No plans conducted or updated |  |  |  | Capacity development | Other
Albania |  | 2: Monitoring and warning service | 2: Undertaking or updating of assessments in progress |  |  | Communication & Information policy | Sustainable forest management
Argentina |  | 3: Dissemination and communication | 3: Risk and vulnterability assessments completed or updated |  |  | Domestic policy | Strengthening infrastructure | 1: Health and Social Infrastructure (developed/improved)
Armenia | Forests | 4: Response capability |  |  |  | Economic policy | Supporting livelihoods | 2: Physical asset (produced/improved/strenghtened)
Antigua and Barbuda | Mangroves |  |  |  |  | Education policy | Mangrove reforestation
Azerbaijan | Coasts |  | From 0 to 0.5% |  |  | Energy policy | Coastal drainage and infrastructure
Burundi | Rangelands |  | From 0.5 to 1% |  |  | Environmental policy | Irrigation system
Benin | Cultivated land/Agricultural land |  | From 1% to 5% |  |  | Foreign policy | Community-based adaptation
Burkina Faso | Catchment area/Watershed/Aquifer |  | From 5% to 10% |  |  | Health policy | Erosion control
Bangladesh | Protected areas/National parks |  | From 10% to 20% |  |  | Housing policy | Soil water conservation
Bulgaria | Other |  | From 20% to 30% |  |  | Human resource policies | Microfinance
Bahrain |  |  | From 30% to 40% |  |  | Information policy | Special Program for women
Bahamas, The |  |  | From 40% to 50% |  |  | Macroeconomic policy | Livelihoods
Bosnia and Herzegovina |  |  | Above 50% |  |  | Monetary policy | Water storage
Belarus | [5 empty] | Population policy | ICT and information dissemination
Belize | [5 empty] | Private policy
Bolivia | [5 empty] | Public policy
Brazil | [5 empty] | Science policy
Barbados | [5 empty] | Social policy
Bhutan |  | 3- relevant information is generated and disseminated to all identified stakeholders on timely basis |  |  |  | Transportation policy
Botswana |  | describe |  |  |  | Urban policy
Central African Republic |  | 2- the existence of some challenge in any of the three aspects of the indicator |  |  |  | Water policy
Chile |  | describe |  |  |  | Other policy
China, People's Republic of |  | 1- generated information is irrelevant and neither the stakeholders reached nor the timeframe managed were achieved
Cote d'Ivoire |  | describe
Cameroon
Congo, Dem. Rep. of
Congo, Republic of
Cook Islands
Colombia
Comoros
Cape Verde
Costa Rica
Cuba
Czech Republic
Djibouti
Dominica
Dominican Republic
Algeria
Ecuador
Egypt
Eritrea
Estonia
Ethiopia
Fiji
Micronesia, Fed. States of
Gabon
Georgia
Ghana
Guinea
Gambia, The
Guinea-Bissau
Equatorial Guinea
Grenada
Guatemala
Guyana
Honduras
Croatia
Haiti
Hungary
Indonesia
India
Iran, Islamic Republic of
Jamaica
Jordan
Kazakhstan
Kenya
Kyrgyz Republic
Cambodia
Kiribati
Saint Kitts and Nevis
Korea, Republic of
Lao People's Democratic Republic
Lebanon
Liberia
Libya
Saint Lucia
Sri Lanka
Lesotho
Lithuania
Latvia
Morocco
Moldova
Madagascar
Maldives
Mexico
Marshall Islands
Macedonia, former Yugoslav Republic of
Mali
Malta
Myanmar
Montenegro
Mongolia
Mozambique
Mauritania
Mauritius
Malawi
Malaysia
Namibia
Niger
Nigeria
Nicaragua
Niue
Nepal
Nauru
Oman
Pakistan
Panama
Peru
Philippines
Palau
Papua New Guinea
Poland
Korea, Dem. People's Rep. of
Paraguay
Romania
Russian Federation
Rwanda
Saudi Arabia
Sudan
Senegal
Solomon Islands
Sierra Leone
El Salvador
San Marino
Serbia
Sao Tome and Principe
Suriname
Slovak Republic
Slovenia
Swaziland
Seychelles
Syrian Arab Republic
Chad
Togo
Thailand
Tajikistan
Turkmenistan
Tonga
Trinidad and Tobago
Tunisia
Turkey
Tuvalu
Tanzania
Uganda
Ukraine
Uruguay
Uzbekistan
Saint Vincent and the Grenadines
Venezuela
Vietnam
Vanuatu
Samoa
Yemen, Republic of
South Africa
Zambia
Zimbabwe
Timor-Leste

## Units for Indicators
Fund Outcome Indicator Units
1. Generation of relevant data, Stakeholders, and Timeliness 2.1. Include both qualitative and quantitative measures of capacity level within targeted institutions 2.2. Number (men and women and other vulnerable groups) 3.1. Use scale from 1 to 5: 5: Fully aware 4: Mostly aware 3: Partially aware 2: Partially not aware 1: Aware of neither predicted adverse impacts of climate change nor of appropriate responses 3.2. Use scale from 1 to 5: 5: All 4: Almost all 3: Half 2: Some 1: None 4.1. Summarize in an overall scale (1-5): 5: Highly responsive (All defined elements ) 4: Mostly responsive (Most defined elements) 3: Moderately responsive (Some defined elements) 2: Partially responsive (Lacks most elements) 1: Non responsive (Lacks all elements ) 4.2. Summarize in an overall scale (1-5): 5: Fully improved 4: Mostly Improved 3: Moderately improved 2: Somewhat improved 1: Not improved 5. Depends on the targeted natural asset: Biological (species): measure through changes in population numbers (dynamics, structure, etc.) Land: measure changes in hectares. Baseline data will be necessary to estimate the change. Supporting indicators baseline and target (as well as contextual information) are needed such as the following: Farmers adopting recommended technologies, Ha. of land improved, Average deforestation rate Etc. Use scale from 1 to 5. 5: Very effective (All elements are present) 4: Effective (Most elements are present) 3: Moderately effective (Some elements are present) 2: Partially effective (Most elements are not present) 1: Ineffective (No elements are present) 6.1. Summarize in an overall scale (1-5): 5: Very high improvement 4: High improvement 3: Moderate improvement 2: Limited improvement 1: No improvement 6.2. Household income by source of livelihood in project area (USD) prior and post project intervention 7. Summarize in an overall scale (1-5). 5: All (Fully integrated) 4: Most 3: Some 2: Most not integrated 1: None
Fund Output Indicator Units
1.1. Number, sector(s) and level(s) of projects or interventions in separate fields of monitoring plan 1.2. Number 2.1.1. Number of staff (male/female) of targeted institutions: a. Obtain baseline information: total number of staff from targeted institutions b. Define target 2.1.2. Number of staff (male/female) of targeted institutions: a. Obtain baseline information: total number of staff from targeted institutions b. Define target: needs to be defined by project proponents 2.2.1. Quantitative: Percentage (includes women – and other vulnerable groups – and men). Qualitative: Adequacy: include direct analysis of major areas; adequacy/effectiveness of systems or analysis of perceptions of populations and institutions. 2.2.2. Number (broken down by gender and, if possible, by vulnerable groups defined in the area of intervention) of people 3.1. Number and type (in separate columns) at local level. 3.2. Number 4.1. Number and type 4. 2. Number and type (entered in separate columns) 5. Number of interventions by type of natural asset and intervention 6.1. Number and type (in separate columns of monitoring plan) 6.2. Income sources per household; description of income source and number of households. 7.1. Number/Sector 7.2. Number; Effectiveness (see previous indicator) through enforcement level.