## Overview
Project Performance Report (PPR)
| Period of Report (Dates) | October 2015-October 2016
| Project Title: | Promoting climate resilience in the rice sector through pilot investments in Alaotra Mangoro Region
| Project Summary: | In the framework of the implementation of its NAPA, the Government of the Republic of Madagascar has recieved support from the Adaptation Fund for the implementation of the project " PROMOTING CLIMATE RESILIENCE IN THE RICE SECTOR THROUGH PILOT INVESTMENTS IN ALAOTRA-MANGORO REGION ", which seeks to transform the rice sub-sector towards building resilience to impacts of climate change. The project is comprised of three components 1) strengthening of technical and scientific capacities, 2) implementation of a rice production cycle that is resilient and adapted and 3)leveraging policy change in the rice sector. The project is implemented in the Alaotra-Mangoro region, the primary rice production area in Madagascar, in three pilot districts. The project is implemented through the Ministry of Environment and Forests and works at the local level with producers and local partners, along with decentralised ministries and regional technical partners.
|  |  | Countries | Project Type: |  | GEF Focal Area: | GEF 4 Focal Areas | GEF 2 / 3 Operational Programme: | Overall Rating of the project in the evaluation by the project evaluator: | GEF-4 Focal Area Strategic Program: | GEF-3 Focal Area Strategic Program:
| Database Number: | AFB-5060-1111-2G49 | Afghanistan | FP | Yes | Biodiversity | 1 | 1 | U | BD-SP1-PA Financing | 1: Arid & semi-arid ecosystems
Implementing Entity (IE) [name]: |  | UNEP | Albania | MSP | No | Climate Change Adaptation | 2 | 2 | S | BD-SP2-Marine PA | 2: Coastal, marine & freshwater ecosystems
| Type of IE: | MIE | Algeria | EA |  | Climate Change Mitigation | 3 | 3 | MU | BD-SP3-PA Networks | 3: Forest ecosystems
| Country(ies): | MADAGASCAR | Angola |  |  | International Waters | 5 | 5 | Good | BD-SP5-Markets | 13: Conservation and Sustainable Use of Biological Diversity Important to Agriculture
Relevant Geographic Points (i.e. cities, villages, bodies of water): |  | The Alaotra Mangoro region is located in the center-East of Madagascar. The region covers 33 054 Km². and is comprised of (05) Districts themselves sub-divided into 79 communes. The regional capital is Ambatondrazaka, approximately 250 Km from Antananarivo. The project is working in the three districts of Andilamena (8 communes), Amparafaravola (20 communes), and Ambatondrazaka (20 communes). The Alaotra Mangoro contains many bodies of water and rivers, Lake Alaotra being the most important lake in the region, with an area of 20 000 ha. | Argentina |  |  | Multiple Focal Area |  |  |  | BD-SP7-Invasive Alien Species(IAS) | 6: Promoting the adoption of renewable energy by removing barriers and reducing implementation costs
[8 empty] | CC-SP2- Industrial EE | 8: Waterbody based operational program
| Project Milestones | [6 empty] | CC-SP3-RE,CC-SP4-Biomass | 9: Integrated Land and Water multiple focal area
| Milestone |  | Bahamas | [6 empty] | CC-SP5-Transport | 10: Contaminants based operational program
AFB Approval Date: |  | 2011-12-14
IE-AFB Agreement Signature Date: |  | 2012-03-01 | [6 empty] | CC-SP6-LULUCF | 12: Integrated Ecosystem Management
Start of Project/Programme: |  | 2012-10-01 | [6 empty] | Cross cutting capacity building | 14: Persistent Organic Pollutants
Mid-term Review Date (if planned): |  | December 2015 - March 2016 (completed)
| Terminal Evaluation Date: | October-December 2017 (expected)
|  | List documents/ reports/ brochures / articles that have been prepared about the project. | Cyprus
|  | Radio Broadcast (AMOMIX and RDB) and TV Broadcast (TVM Alaotra Mangoro) ; 1 documentary film on crop rotation Rice and vegetable with CALA experts ; 1 documentary film on sensitizing farmers during the training on compost production by the STOI-MIN expert ; Broadcasting programs on local TV and radio (AMOMIX, RDB) in Ambatondrazaka every Sunday (10mn) ; Posters, flyers, Pamphlets, word of mouth, awareness raising; panels and displays showing general objectives, specific objectives and method of work of the AF RICE PROJECT; Website creation and Forum ; Mailing ; ; Awareness-raising on MIRR practice (AMOMIX, RDB and TVM Alaotra Mangoro) ; Project indication panel ; Animation on the ground ; Debate workshop for farmers ; Suggestion box. | Czech Republic
List the Website address (URL) of project. |  |  | Democratic People's Republic of Korea
|  | www.mef.gov.mg | Democratic Republic of the Congo
Denmark
| Project contacts: |  | Djibouti
National Project Manager/Coordinator |  |  | Dominica
| Name: | RAZANAMIHARISOA Jane Alice | Dominican Republic
| Email: | jrazanamiharisoa@ymail.com | Ecuador
| Date: | 2013-12-10 | Egypt
| Government DA |  | El Salvador
| Name: | Nivoary RAMAROSON | Equatoral Guinea
| Email: | nivoohary@yahoo.fr | Eritrea
| Date: | 2016-07-15 | Estonia
| Implementing Entity |  | Ethiopia
| Name: | Lars Christiansen, UNEP Task Manager | Fiji
| Email: | lachr@dtu.dk | Finland
| Date: | 2013-12-16 | France
| Executing Agency |  | Gambia
| Name: |  | Georgia
| Email: |  | Germany
| Date: |  | Ghana
| Executing Agency |  | Greece
| Name: |  | Grenada
| Email: |  | Guatemala
| Date: |  | Guinea
| Executing Agency |  | Guinea Bissau
| Name: |  | Guyana
| Email: |  | Haiti
| Date: |  | Honduras
Hungary
Iceland
India
Indonesia
Iran (Islamic Republic of)
Iraq
Ireland
Israel
Italy
Jamaica
Japan
Jordan
Kazakhstan
Kenya
Kiribati
Kuwait
Kyrgyzstan
Lao People’s Democratic Republic
Latvia
Lebanon
Lesotho
Liberia
Libyan Arab Jamahiriya
Liechtenstein
Lithuania
Luxembourg
Madagascar
Malawi
Malaysia
Maldives
Mali
Malta
Marshall Islands
Mauritania
Mauritius
Mexico
Micronesia, Federated States of
Monaco
Mongolia
Montenegro
Morocco
Mozambique
Myanmar
Namibia
Nauru
Nepal
Netherlands
New Zealand
Nicaragua
Niger
Nigeria
Norway
Oman
Pakistan
Palau
Panama
Papua New Guinea
Paraguay
Peru
Philippines
Poland
Portugal
Qatar
Republic of Korea
Republic of Moldova
Romania
Russian Federation
Rwanda
Saint Kitts and Nevis
Saint Lucia
Saint Vincent and the Grenadines
Samoa
San Marino
Sao Tome and Principe
Saudi Arabia
Senegal
Serbia
Seychelles
Sierra Leone
Singapore
Slovakia
Slovenia
Solomon Islands
Somalia
South Africa
Spain
Sri Lanka
Sudan
Suriname
Swaziland
Sweden
Switzerland
Syrian Arab Republic
Tajikistan
Thailand
The former Yugoslav Republic of Macedonia
Timor-Leste
Togo
Tonga
Trinidad and Tobago
Tunisia
Turkey
Turkmenistan
Tuvalu
Uganda
Ukraine
United Arab Emirates
United Kingdom of Great Britain and Northern Ireland
United Republic of Tanzania
United States of America
Uruguay
Uzbekistan
Vanuatu
Venezuela, Bolivarian Republic of
Viet Nam
Yemen
Zambia
Zimbabwe

## FinancialData
Financial information: cumulative from project start to OCTOBER 2015-OCT 2016
DISBURSEMENT OF AF GRANT FUNDS
How much of the total AF grant as noted in Project Document plus any project preparation grant has been spent to date?
Estimated cumulative total disbursement as of 30 Septembre 2016 |  | 1951627
Add any comments on AF Grant Funds. (word limit=200)
EXPENDITURE DATA
List ouput and corresponding amount spent for the current reporting period (Oct 2015 - 30 sept 2016) |  | Output | AMOUNT
Output 1.1.1 Best Available Technologies and Integrated Resilient Rice Model (Modèle Intégré de Riziculture Résiliente - MIRR) selected and publicized
|  | 1.2.1 Crop models are available for rice vulnerability mapping | 2380
|  | 1.2.2 Updated, dynamic agricultural calendars and climate early warnings taking into account current and projected variability disseminated to local population | 9985
|  | 1.2.3 Agricultural extension staff trained on climate risk management in an agro-ecosystem context | 65400
|  | 2.1.1 climate resilient rice varieties selected through participatory field testing | 48538
2.1.2 An operational multiplication and dissemination scheme for adapted seed varieties
|  | 2.1.3 Updated fertilisation guidelines according to best available standards and taking climate conditions into consideration | 341840
|  | 2.1.4 Integrated pest management is implemented | -
|  | 2.1.5 Water efficiency, management and conservation technologies and infrastructures are implemented | 6800
|  | 2.2.1 Best available land preparation, production and harvesting techniques disseminated to reduce deforestation, maintain soil fertility and integrity, and to provide adequate growing conditions | 41000
|  | 2.2.2 Watershed rehabilitation in productive landscapes introduced, including through reforestation and adaptation of agroforestry practices | 44053
|  | 2.2.3 Soil conservation and livestock management techniques adapted to topography and landscape in light of future climate conditions | 20000
|  | 2.2.4 Revitalization of producer’s cooperatives and water user associations for collaborative natural resources allocations (e.g. land and water) and management | 12000
2.2.5 Water quality assessments
|  | 2.3.1 Increased utilization of rice by-product especially rice straw | 16000
|  | 2.3.2 Post-harvest storage facilities with phytosanitary control, serving as trading points and markets | 49880
|  | 3.1.1 gaps and possible maladaptations in the current rice policy are identifed and recommendations on upscaling project outcomes towards rice policy reform are made | -
|  | 3.2.1 a report on best practices and lessons learned for rice adaptation in madagascar | -
|  | 3.2.2 A strategy for communicating information on adaptation techniques to farmers is implemented | 16180
|  | Cross-cutting costs Component 1 | 6300
|  | Cross-cutting costs Component 2 | 62226
|  | Cross-cutting costs Component 3 | 3600
|  | Project operations/Execution costs | 103209
|  | TOTAL | 849391
PLANNED EXPENDITURE SCHEDULE
List outputs planned and corresponding projected cost for the upcoming reporting period | Output | ITEM | PROJECTED COST | Est. Completion Date
1.1.1 Best Available Technologies and Integrated Resilient Rice Model (Modèle Intégré de Riziculture Résiliente - MIRR) selected and publicized
|  | Publication services | 15000 | Q1 2017
1.2.1 Crop models are available for rice vulnerability mapping
|  | NC for data acquisition to perform rice modelling | 1000 | Q1 2017
|  | National agriculture modelling expert | 1000 | Q1 2017
|  | NC expert SIG | 4500 | Q1 2017
1.2.2 Updated, dynamic agricultural calendars and climate early warnings taking into account current and projected variability disseminated to local population
|  | National agriculture modelling expert | 30000 | Q2 2017
|  | National Consultant meteorologist | 24500 | Q2 2017
|  | sub-contract with National Radio | 18000 | Q3 2017
|  | National CRM Expert | 5800 | Q1 2017
| Cross-cutting component costs | Project Coordinator | 3927 | Q4 2017
1.2.3 Agricultural extension staff trained on climate risk management in an agro-ecosystem context
|  | National agroforestery expert | 22800 | Q1 2017
|  | Climate Risk Management workshop | 20000 | Q3 2017
2.1.1 climate resilient rice varieties selected through participatory field testing
|  | agricultural inputs (seeds, fertilizers, land and tools) | 148737 | Q4 2017
2.1.2 An operational multiplication and dissemination scheme for adapted seed varieties
|  | Agriculture imput | 15000 | Q3 2017
|  | sub-contract with CALA (pre-base seeds) | 81000 | Q3 2017
2.1.3 Updated fertilisation guidelines according to best available standards and taking climate conditions into consideration
|  | Sub-contract with STOI Madagascar | 6987 | Q3 2017
|  | Sub-contract with CALA for soil quality analysis | 16000 | Q3 2017
|  | National Soil quality Expert | 4500 | Q3 2017
2.1.4 Integrated pest management is implemented
|  | IPM training workshop | 30000 | Q3 2017
|  | Aquisition of IPM and phytosanitary equipment | 18000 | Q3 2017
|  | IPM Expert | 35000 | Q3 2017
| Cross-cutting component costs | Project Coordinator | 4000 | Q4 2017
2.1.5 Water efficiency, management and conservation technologies and infrastructures are implemented
| 21. Rehabilitation of damaged gravitational irrigation infrastructure and canals | sub-contract with water engineering firm | 845000 | Q3 2017
|  | water management and infrastructure specialist | 61200 | Q3 2017
| 24. Implementation of irrigation and water conservation (including water harvesting) practices adapted to new climate trends and conditions with related training of water users | water management training workshops | 45000 | Q3 2017
2.2.1 Best available land preparation, production and harvesting techniques disseminated to reduce deforestation, maintain soil fertility and integrity, and to provide adequate growing conditions
| 25. Implement and disseminate Integrated Resilient Rice Model (MIRR) for production through training and extension | Local MIRR training | 36000 | Q2 2017
|  | national riziculture experts | 48800 | Q3 2017
|  | training workshops for local leaders | 18000 | Q2 2017
|  | National agroforestery expert | 60000 | Q3 2017
|  | sub-contract Min Agri vulgarisation agricole | 21000 | Q3 2017
| Cross-cutting component costs | Project Coordinator | 4000 | Q4 2017
2.2.2 Watershed rehabilitation in productive landscapes introduced, including through reforestation and adaptation of agroforestry practices
|  | sub-contract Ministry of forests (SNGF) | 76847 | Q3 2017
|  | Sub-contract with the three commune of the site project | 78000 | Q3 2017
|  | NC-resilient species study | 6000 | Q1 2017
|  | SLM Community training | 35000 | Q2 2017
2.2.3 Soil conservation and livestock management techniques adapted to topography and landscape in light of future climate conditions
| 30. Adaptation and reintroduction of soil conservation methods for erosion control (tillage, sediment barriers, mulching) in upland and lowland uses | sub-contract Ministry of Agriculture | 125000 | Q3 2017
| 32. Assessment of resilience in livestock management within rice cultivation systems and adaptation of practices for resilience, erosion control, and increased productivity | Livestock expert | 15000 | Q1 2017
| Cross-cutting component costs | Project Coordinator | 4000 | Q4 2017
2.2.4 Revitalization of producer’s cooperatives and water user associations for collaborative natural resources allocations (e.g. land and water) and management
|  | Water user Association training workshop | 40000 | Q2 2017
|  | Community Based Natural Resources management expert | 29000 | Q3 2017
|  | equipment and office supplies for WUG | 15000 | Q3 2017
2.2.5 Water quality assessments
|  | national water quality expert | 12000 | Q2 2017
2.3.1 Increased utilization of rice by-product especially rice straw
| 35. Introduction of techniques and technologies for the utilization of rice straws in animal feed and for energy production (training and extension) | national rice straw expert | 6000 | Q1 2017
|  | socio-economist | 6000 | Q1 2017
|  | Workshops on rice by-products | 45000 | Q3 2017
2.3.2 Post-harvest storage facilities with phytosanitary control, serving as trading points and markets
|  | Civil Engineer | 18499 | Q3 2017
|  | Sub-contract private sector firm | 100120 | Q2 2017
|  | training on community-managed reserves | 10000 | Q2 2017
|  | National Consultant - Community managed storage | 20000 | Q2 2017
| Cross-cutting component costs | Chief Technical Advisor (CTA) | 19000 | Q4 2017
|  | CTA travel | 15595 | Q4 2017
|  | Local Technicians (3) | 13200 | Q3 2017
|  | Office supplies for Local Technicians (3) | 8033 | Q3 2017
|  | Travel costs for regional directorates | 12000 | Q3 2017
|  | Operating costs for regional directorates (fuel and expendables) | 7500 | Q3 2017
|  | Materials and supplies for Local Technicians | 6000 | Q3 2017
|  | Driver | 4125 | Q4 2017
|  | Vehicles (incl. 3 motorcycles) and maintenance | 6572 | Q4 2017
3.1.1 gaps and possible maladaptations in the current rice policy are identifed and recommendations on upscaling project outcomes towards rice policy reform are made
|  | national agriculture task force consultant | 28000 | Q3 2017
|  | National development planing policy consultant | 30000 | Q3 2017
|  | National rice policy consultant | 32000 | Q3 2017
|  | Meeting and workshop of upscaling MIRR | 30000 | Q3 2017
|  | national market analysis consultant | 45000 | Q2 2017
3.2.1 a report on best practices and lessons learned for rice adaptation in madagascar
|  | National agriculture policy consultant | 5000 | Q2 2017
| 3.2.2 A strategy for communicating information on adaptation techniques to farmers is implemented | National Rural communication specialist | 30080 | Q3 2017
|  | awareness raising Meetings and workshops | 23920 | Q4 2017
4. Project/Programme Execution cost
|  | Project Coordinator | 22500 | Q4 2017
|  | National financial manager | 18750 | Q4 2017
|  | Administrative support | 12495 | Q4 2017
|  | Travel for PM | 12720 | Q4 2017
|  | Office equipment and expendables (PCU) | 5000 | Q4 2017
|  | Communication, translation and printing costs | 11458 | Q4 2017
Baseline study
|  | Mid and Final evaluation | 35000 | Q4 2017
|  | M§E Officer | 10829 | Q4 2017
|  | audit | 6000 | Q4 2017
|  | inception and steering meetings | 16379 | Q4 2017
|  | TOTAL | 2753373
ACTUAL CO-FINANCING (If the MTR or TE have not been undertaken this reporting period, DO NOT report on actual co-financing.)
How much of the total co-financing as committed in the Project Document has actually been realized?
Estimated cumulative actual co-financing as verified during Mid-term Review (MTR) or Terminal Evaluation (TE).
Add any comments on actual co-financing in particular any issues related to the realization of in-kind, grant, credits, loans, equity, non-grant instruments and other types of co-financing. (word limit=200)

## Procurement (hidden)
PROCUREMENT DATA |  |  | 01 nov 2015 à 30 sept 2016
Please provide information for all contracts over $2,500 USD
Please provide the number of contracts under $2,500, signed during this reporting period: |  |  | 1
LIST OF CONTRACTS
List all contracts related to the project/program with signature dates
Contract Type | Agency / Contracted party | Contract Value/Amount (USD) | Signature Date | Contract Number | budget code | Payment to Date | Remaining Balance
Long-term Contract | Mme Jane Razanamiharisoa | 91500 | 2012-sep-08 | 01/12 | 1101 | 54000 | 37500
Long-term Contract | Mr. Tahiry Herilalaina | 76250 | 2012-sep-08 | 02/12 | 1102 | 45000 | 31250
Long-term Contract | Mr. Marcellin Lalason | 50813 | 2012-sep-08 | 03/12 | 1301 | 39996 | 10817
Individual Consultancy contract | Mme JOANA Talafré | 120000 | 2013-02-20 | 04/13 | 1212 | 60496 | 59504
Consultancy contract | Gaétan QUESNE and Henri Rakotobe | 35792 | 2013-02-27 | 05/13 | 5501 | 35792 | 0
Consultancy Contract | Madame RAKOTOARISOA Jacqueline and Monsieur Rabeson Raymond | 60000 | 2013-06-26 | 06/13 | 1201 | 60000 | 0
Contract amendment with additional costs | Madame RAKOTOARISOA Jacqueline and Monsieur Rabeson Raymond | 25350 | 2014-09-05 | 06/13 amendment | 1201 | 25350 | 0
Individual Consultancy contract | Madame RASOAFALIMANANA Mbolarinosy | 50000 | 2013-06-26 | 07/13 | 1207 | 50000 | 0
Individual Consultancy contract | Monsieur Rabeson Raymond | 6000 | 2013-09-12 | 07bis/13 | 1201 | 6000 | 0
Individual Consultancy contract | Mr. Ratsimbazafy Tiana | 15000 | 2014-07-23 | 08/14 | 1230 | 15000 | 0
Individual Consultancy contract | Monsieur Andrianirina Michelliarson | 15000 | 2014-07-23 | 09/14 | 1215 | 6000 | 9000
Individual Consultancy contract | Monsieur Rakotoarison Levy | 60000 | 20 aout 14 | 10/13 | 1209 | 60000 | 0
Individual Consultancy contract | Mr. Ratsimbazafy Jean-Pierre | 5000 | 2014-03-17 | 12 bis/14 | 1201 | 1620 | 3380
Individual Consultancy contract | Razafindrakoto Helison Romuald | 25000 | 2013-03-07 | 12/14 | 1204 | 25000 | 0
Individual Consultancy contract | Andriamalantomanga Tsiory Dimbimalala | 52600 | 2014-03-07 | 13/14 | 1225 | 14420 | 38180
Individual Consultancy contract | Rabemanantsoa Heritiana Adrianala | 14000 | 2014-03-17 | 14/14 | 1219 | 14000 | 0
Individual Consultancy contract | Ranaivojaona Harinomejanahary Voahanginirina | 9000 | 2014-03-28 | 15/14 | 1227 | 3600 | 5400
Individual Consultancy contract | Rasamison Jules | 9000 | 2014-03-28 | 16/14 | 1227 | 3600 | 5400
Individual Consultancy contract | Randriafiraisampiremena Jules | 9000 | 2014-03-28 | 17/14 | 1227 | 3600 | 5400
MOU | Silo Nationale des Graines Forestieres (SNGF) | 201500 | 2014-04-25 | MOU-1 | 2102 | 80600 | 120900
Long-term Contract | RAMAROSOA Erick Lauret | 11550 | 2014-07-25 | 20/14 | 1228 | 3575 | 7975
MOU | CALA | 180000 | 2014-09-08 | MOU-2 | 2309 | 108000 | 72000
MOU | STOI AGRI (Société Trading de l'Ocean Indien) | 258050 | 2014-11-28 | MOU | 2302 | 77013 | 181037
MOU | International Rice Research Institute | 35000 | 2014-09-22 | MOU-3 | 2204 | 35000 | 0
Individual Consultancy contract | JOELIBARISON | 50000 | 2015-05-18 | 022/15 | 1206 | 35000 | 15000
Individual Consultancy contract | RAZAFINDRAKOTO CHARLOTTE | 74000 | 2015-05-18 | 029/15 | 1213 | 22200 | 51800
Individual Consultancy contract | RAKITRINIAINA Mandarimiorandraibe | 30000 | 2015-05-18 | 024/15 | 1214 | 21000 | 9000
Individual Consultancy contract | RAFALIMANANTSOA JULE | 20000 | 2015-05-18 | 026/15 | 1216 | 14000 | 6000
Individual Consultancy contract | RAKOTOARISOA NY HERY MIANDRAZO | 20000 | 2015-05-18 | 028/15 | 1217 | 14000 | 6000
Individual Consultancy contract | SYLVAIN RODOLPHE Ralaiarimalala | 50000 | 2015-05-20 | 027/15 | 1218 | 35000 | 15000
Individual Consultancy contract | RANAIVOARISOA JOPELANA Toavina | 76000 | 2015-05-18 | 025/15 | 1223 | 53200 | 22800
Individual Consultancy contract | RANDRIANORO DESIRE | 35000 | 2015-05-20 | 023/15 | 1229 | 24500 | 10500
Individual Consultancy contract | RANDRIAMANANAZY GILLES | 68000 | 20-Aout-15 | 030/15 | 1226 | 6800 | 61200
Individual Consultancy contract | ANDRIANAHARINOSY Mireille Natacha | 14500 | 2015-11-23 | 031/15 | 1205 | 14500 | 8700
BIDS
List all bids for each contact signed with date of open call and winning bid
CONTRACT & Procurement Method | Submitted Bids | Bid Amount (USD) | Winning Bid Amount (USD) | Selection Justification for the Winner
01/12. Personnel Recruitment - competitive | Mme Jane Razanamiharisoa | 100000 | 90000 | Selection was based on technical merits, experience and expertise. A recruitment panel was launched within the Ministry of Environment for the selection of suitable candidates. No financial offers were required as the salaries were fixed.
| RAMAROVELO Jean Marc | 150000
| HERINIRINA Harisoa Rondro | 120000
02/12 Personnel Recruitment- competitive | Mr. Tahiry Herilalaina | 100000 | 75000 | Selection was based on technical merits, experience and expertise. A recruitment panel was launched within the Ministry of Environment for the selection of suitable candidates. No financial offers were required as the salaries were fixed.
| RASOLOMANDIMBY Tahina Fenosoa | 120000
| RAVOAVY Augustin Bertrand | 145000
03/12 Personnel Recruitment - competitive | Mr. Marcellin Lalason | 50000 | 50000 | Selection was based on technical merits, experience and expertise. A recruitment panel was launched within the Ministry of Environment for the selection of suitable candidates. No financial offers were required as the salaries were fixed.
| RANDRIAMPIERENANA Prisca | 100000
| RAKOTOMAMPIANINA Jean | 80000
04/13. Call for Proposals - international competitive' | Joana Talafré | 150000 | 120000 | Financial bids were requested only for those candidates who fulfilled technical requirements. Contract attributed to highest ranking candidate for both technical and financial proposals. Contract amount revised from 150K to 120K following budet revision and number of days reduced.
| Alexandre Borde | 165000
Shalaby Hani
Olivier Beucher
05/13. Call for Proposals - international competitive | Gaetan Quesne | 35000 | 35000 | Financial bids were requested only for candidates deemed technically qualified to perform the baseline study. A review panel was put together to analyse proposed methodologies and candidates, and a proposal was made to support consortia of international and national consultants. UNEP participated in the recruitment panel. Contract amount was adjusted to account for real hours worked between national and international consultant (a combination of two proposals).
| Henri Rakotobe | 20000
Raparany Serge
Mike Jennings
Narayan Dhital
Kasibothia Sridhar
Corradi Chiara Assunta Riccarda
Barova Harimanga
06/13 (call for proposals) - competitive | Ramangarivelo Lidya Nirina | 45000 |  | After discussion and exchanges and for greater efficiency and complementarity, the Evaluation Committee decided to retain the nominations of Mr. Rabeson and Mrs. Jacqueline Rakotoarisoa consortium. It was deemed that Mr Rabeson by his experiences both in agriculture research and adaptation to climate change, could the lead study in terms of analysis and methodology while Mrs. Rakotoarisoa with her experiences and excellent knowledge of the context and local cultures, could arrange collection and verification of local data. The consultants were encouraged to join forces and present a joint bid. In later months, the contract was expanded to adjust for significantly increased scope of work.
| Rabeson Raymond | 80000 | 60000
| Rakotoarisoa Jacqueline | 85000
07/13- Call for Proposals -competitive | RASOAFALIMANANA Mbolarinosy | 70000 | 50000 | Financial bids required only for those candidates who fulfilled technical requirements. Contract attributed to highest rating candidates for both technical and financial. After discussion and exchanges and for efficiency, the evaluation committee decided to accept the nomination of Ms. Mbolaharinosy Rasoafalimanana based on her experience and excellent knowledge of the local context and culture and her ability to lead the entire study proposals. The contract was negotiated on the basis of the amount available for the work (50K) with a consortium of consultants, based on number of days worked.
| Barova harimanga | 72000
| Rabeson Raymond | 65000
| Ratsimbazafy Jean-Pierre | 75000
| Randrianoro Desire | 80000
| Randriambolamanana Hoby Nantenaina | 90000
07bis/13 - single source | Rabeson Raymond | 6000 | 6000 | Only one candidate was sought out as it was known that he had previously obtained training in DSSAT and ORYZA and was qualified to deliver the required training.
08/13 - competitive | RATSIMBAZAFY Tiana Andrianiaina ( selected canditate) | 37500 | 15000 | After discussion and exchanges and for greater efficiency and complementarity, the evaluation committee decided to accept applications from Mr. Ratsimbafazy Tiana Andrianiaina, through his experiences in agriculture and especially in the use of fertilizer. He also has experiences in collaborations with other agriculture engineers, and NGOs conducting technical tests with farmer. Mr. Tiana has put together a team to address his TORs.
| Randrianasolo Fihevitsoa Rabarijaona | 40000
| Levy Rakotoarison | 50000
| Razafindrabe Manantsoavina Warren | 52000
09/14 - competitive | RAKOTOBE RAHELIARISOA Holinantenaina | 20000 |  | After discussion and exchanges, the evaluation committee decided to accept applications from M. Andrianirina Michelliarson, due to his experiences from the Environment National Reaserch Center (CNRE) and excellent credentials in comparative methodological analysis of water quality and climate change adaptation. He has led the group for the first and second national communications. His team includes an agricultural national expert, who also worked on the development of the national communication.
| Andrianirina Michelliarson (selected candidate) | 17000 | 15000
Ratsimbazafy Jean Pierre.
| Rejo robert Andriamananjara | 30000
10/13 - competitive | Levy Rakotoarisoa | 56000 | 60000 | After discussion and exchanges and for greater efficiency, the evaluation committee decided to accept applications from Mr Levy Rakotoarison due to his experience in agriculture research and Climate change Adaptation. He will direct the whole survey in terms of analysis and methodology by his experience and excellent knowledge of the context and the local cultures, will be in charge of the collections and verification of the local data. Contract amount is slightly higher than proposal as consultant missed a few activities of the TOR in his proposal.
Marthe Rafarasoa
| Raminoson Rina | 65000
12 bis/14 - competitive | Mr. Ratsimbazafy Jean-Pierre | 5000 | 5000 | The evaluation committee decided to accept applications from Mr Ratsimbazafy Jean Pierre due to his experiences in agriculture research and Climate change Adaptation
| Mme Olitina Ratovo | 7500
| Mr RAFALIMANANTSOA Jules | 9000
12/14 - competitive | Rija Fidèle | 30000 |  | The evaluation committee decided to accept applications from Mr Razafindrakoto Helison due to his experiences in agriculture research and climate change adaptation, and knowledge of watershed modeling and experience in software and application of hydrological modeling
| Helison Razafindrakoto ROMUALD | 26000 | 25000
13/14 - competitive | Miharimanana Marie | 20000 |  | After discussion and exchanges and for greater efficiency, the evaluation committee decided to accept applications from Mr Andriamalantomanga Tsiory Dimbimalala through his experiences with farmer communication and climate change impact on agriculture. Contract amount is slightly higher than proposal as consultant missed a few activities of the TOR in his proposal.
| Andriamalantomanga Tsiory Dimbimalala | 17500 | $19,000
| Manampisoa Tanjona | 24000
14/14 - competitive | Heritiana Andrianala Rabemanantsoa | 15000 | 14000 | After discussion and exchanges and for greater efficiency, the evaluation committee decided to accept applications from Mr Rabemanantsoa Heritiana Andrianala through his experiences in agriculture research and Climate change Adaptation as well as experience on the economy and socially.
| Razanakolona Tahina | 165000
| Rakotobe Henri | 18000
15/14 - competitive | RANAIVOJAONA Harinomenjanahary Voahanginirina |  | 9000 | Over 35 candidates were presented for this post of local technician. The top candidates indicated here represent the shortlist, from which the leading candidate was selected. No financial offers were required as the salaries were fixed by the project.
Rabemanda Jean Gabriel
Razafinandrianina Justine
16/14 - competitive | Rasamison Jules |  | 9000
Andry nirina Rakotoarivelo
17/14 - competitive | Randriafiraisampirenena Jules |  | 9000
Razakalanitra Malala Navalona Mariah
022/15 competitive | Joelibarison | 65400 | 50000 | Upon discussion the candidate with the highest number if points (78) was selected
| Ravololomahefa Haritiana | 36700
029/15 competitive LB 1213 | RAZAFINDRAKOTO CHARLOTTE | 134445 | 74000 | the dynamic candidate was selected due to her expertise and experience in the agricultural sectors and AFRICA RICE, which is the only technique known in the Mangoro Alaotra region
| Joelibarison | 16071
024/15 competitive | Andriamihaingo Narivelo | 32143
| Rabemanantsoa Njaratiana | 18705
| Rakitriniaina Mandariniorandraibe | 35850 | 30000 | the candidate was selected due to experience and knowledge in revitalizing association and federations. He has a sound knowledge of the socio-organizational culture of the regions.
| ANDIANIRINA Michelliarson | 25000
026/15 competitive | Rampanjato Andrianantenaina | 16071
| Rakotoarivelo Manitra | 26073
| Ravololomahefa Haritiana | 10583
| Rafalimanantsoa Jules | 22465 | 20000 | The candidate selected had the highest rating (68) and was deemed by the evaluators as having the most merit as per his credentials.
028/15 competitive | Andriamihaingo Narivelo
Rabemanantsoa Andrianala Heritiana
| Rakotoarisoa Ny Hery Miandrazo |  | 20000 | the candidate was selected due to his knowledge and application in the area of macro and micro economics. He has already participated in several projects and is well-experienced in the area of rural economics.
027/15 competitive | Randriamiharisoa Andriamalala Luc | 10740
Rabenarivahiny René
| Sylvain Rodolphe RALAIARIMALALA | 46607 | 50000 | The selected candidate had the highest score and had more experience on issues related to livestock than most candidates.
025/15 competitive | Randriamanantsoa Eric
| Ranaivoarisoa J.Toavina | 79400 | 76000 | The selected candidate has high competence in forestry-related communications and has a forestry engineering background. He has also participated in several agro-forestry projects
Manitrera Safidy
023/15 competitive LB 1229 | Randrianoro Désiré | 36720 | 35000 | This is the only meteorologist that applied for this post; he also has the technical credentials.
| Ratsimbazafy Jean Pierre | 45230 | n
030/15 Competitive LB 1226 | RANDRIAMANANAZY GILLES | 68000 | 68000 | This candidate had the highest score and has the experience in hydraulic infrastructure. He is aware of different systemes such as the (NYCHRI) even if those are not used in Madagascar, and is also knowledgeable on intregated management of water resources used in Madagascar.
| RAKOTOARINARIVO Solonirina | 72000 | 68000
031/15 Competitive LB 1205 | ANDRIANAHARINOSY Mireille Natacha | 14500 | 50000 | This candidate had the highest score and has experience in the management of climate risks. She has field experience in the management of climate data and their use in development planning, in the establishment of risk maps, and in developing early warning systems to climate hazards
| Ratsimbazafy Jean Pierre | 15000
Rakotomalala Naritiana
20/14 - Competitive (driver) | RAMAROSOA Erick Lauret | 12000 | 11550 | The candidate has been selected especially due to his experiences found at the Department of Climate Change: Project driver on the Third of National Communication under the UNFCCC.
| RANDRIANANTOANINA Harinala | 13500
| RANAIVOSON Jean Eric Radonirina | 14800
MOU-1 - Single source | SNGF (Silo National de Grainer et Foresterie) |  | 201500 | The SNGF is a national organization specialized in the research and production of forest seeds. The MOU was negotiated on a non-competitive basis.
MOU-2 - Single source | CALA |  | 180000 | The CALA - Agricultural Center on the Alaotra Lake, is the representative of the FOFIFA on regionally level wich is an institution working in the rice sector, including research on varieties adapted on climate change. MOU was negotiated on a non-competitive basis.
| STOI AGRI (Société Trading de l'Ocean Indien) |  | 258050 | Compost production Company, The MOU was negotiated on a non-competitive basis.
MOU-2 - Single source | IRRI |  | 35000 | IRRI is an internationally recognized rice research center. The MOU was negotiated on a non-competitive basis.

## Risk Assesment
RISK ASSESSMENT
IDENTIFIED RISKS
List all Risks identified in project preparation phase and what steps are being taken to mitigate them
Identified Risk | Current Status | Steps Taken to Mitigate Risk
Slow administration functionning due to lack of human and financial ressources | M | This risk has been reduced following the MTR. The roles of each team member has been clarified and better distributed. Training was provided to Chantal RAZANAMARIA, hired in February 2016 to undertake the M&E of the project activities on MS project. However, her contract stopped in October 2016 after her resignation. A new M&E expert will be hired in November 2016. His/her training needs will be assessed. The roles of each team members will be redefined accordingly.
Frequent political change. This creates a degree of uncertainty | L | Political changes during the third trimester of 2016 have resulted in some delays in the project implementation. However, this risk is now low because the next elections (presidential elections) are planned from 2018.
Accesibility of sites during cyclonic/rainy/ flooding period (december-april) could affect inter regional transport and cause delays in performing required field visits and inputs delivery from other regions or from capital | L | Local Technical Staff (LTS) – as local project representatives – are on site and follow the activities. The LTS are very active and competent, and provide progress reports to the PCU on a monthly basis. Therefore, despite inaccessibility of sites around december, the PCU is abreast of the progress and delays in information transmission is minimized.
Lack of population buy-in on project activities | M | The PCU organises focus groups during the field missions undertaken approximately every 6 weeks. During these focus groups, the team investigates the satisfaction of the beneficiairies and grievance of local communities if any. Additionally, following the MTR recommendations, focus groups have been used to raise awareness of project beneficiaries on the need for them to take full autonomy to enable them to benefit from the project interventions beyond the project. Improvement in communities' understanding of the necessity to become independant of the project has been observed. However, the risk remain rated as Medium because local communities still regularly raise the continuation of the project as one of their needs. Furthermore, gaining their autonomy on each aspect of the project is still going to require a lot of efforts until the end of the project.
There is a risk that the upscaling and replication strategy developed for this project might be insufficient in ensuring uptake of the approach to the rest of the country. Political instability in the country may delay or prevent the adoption of policy recommendations adopted by the project. | M | Since the implementation of the demonstration plots during the first rice cultivation season in 2014-2015, the number of people asking for training on MIRR practices as constantly increased (i.e. approximately 20 times more farmers adopting the MIRR practices in all three sites between season 1 and season 2). Furthermore, other communes are asking for support on these techniques in their own capacity and some other project have asked CALA for information on this techniques. The upscaling potential is therefore very strong. In addition, upscaling of the project interventions will be facilitated by the strengthening of the rice platform planned for the first trimester of 2017. However, the project will end in 2017 and the time left to advertise the successes of the practice and transfer knowledge on how to implement it in other areas is limited. This is the reason why this risk is still considered as Medium. No political instability is foreseen until the end of the project.
Critical Risks Affecting Progress (Not identified at project design)
Identify Risks with a 50% or > likelihood of affecting progress of project
Identified Risk | Current Status | Steps Taken to Mitigate Risk
There could be project delays due to delays in processing cash advance requests with UNEP, as well as due to change in financial procedures in UNEP or in GoM | Low | A financial report on the remaining budget available on the bank account of the project and expected disbursements within the following three months will be submitted monthly to UNEP TM from January 2017.
Procurement delays | Low | MOUs with other government sectors (Agriculture, Water and Forest) have been developed at the national and the regional level. Additionally, the large majority of the contracts with the required experts have been created and signed. The remaining experts will be appointed early on to ensure that no delay is caused by the procurement process during the last year of the project. | n
The reforestation target of the project might not be met | High | The government partner in charge of the restoration interventions performed very poorly during the first and second planting seasons. There is one planting season remaining and the target of 1000 ha per site will likely not be reached. However, the number of hectares restored successfully in 2016-2017 will be maximised through the collaboration of several experienced NGOs to undertake this work under the close supervision of the project team and DREEF. A detailed call for tender will be published in January 2017.
Lack of financial bids and lack of clarity regarding procurement | Medium | A more thorough documentation of bids and offers received has been instated within the project management team and close monitoring by UNEP was undertaken. Procurement rules have been further clarified with the PCU including the new staff members. UNEP and the Chief Technical Advisor will participate to the analysis and selection of the candidates to bids from November 2016.
Risk Measures: Were there any risk mitigation measures employed during the current reporting period? If so, were risks reduced? If not, why were these risks not reduced?
Add any comments relevant to risk mitigation (word limit = 500)
The improved communication system between the CTA and the PCU has been maintained during the last reporting period with regular skype calls for problem solving, technical support, financial reporting, and addressing issues related to the day-to-day management of the project. Following the recommendations of the MTR, the roles and responsibilities among the PCU members have also been further clarified during the combined mission of UNEP and the CTA in December 2015. A Monitoring and Evaluation expert pointed was created to: i) monitor consultants delivery of expected outputs; ii) ensure quality control and timeliness of delivery; and iii) data collection and analysis on the project results. These tasks will be amended in December 2016 if required based on the changes within the team members. The MTR was completed and the results were shared with AF Secretariat for information. Formal management response and implementation plan for MTR recommendations were developed in December 2015 by the PCU, the CTA and the UNEP TM. These responses and plan were presented to the Project Steering Committee and project's consultants in January 2016. The majority of the recommendations were implemented in 2016. The outstanding ones (e.g. monthly reporting on finances) will be implemented from January 2017. MoUs with the project partners where developed to clarify the responsibility of project partners in the project implementation. As result, sources of delay including procurement difficulties and capacity shortages will be avoided, and the progress rate of the project is expected to be raised.
e
Note on C29: Lucille Palazy: Je ne suis pas sure à quoi l'écriture en rouge fait référence?

## Rating
RATING ON IMPLEMENTATION PROGRESS
For rating definitions please see bottom of page.
| Progress on Key Milestones | Expected Progress | Progress to Date | Rating
Project Manager/Coordinator: | Outcome 1.1 Knowledge base on best practices for climate resilience in rice, based on existing local knowledge and international research | This outcome should be completed by the end of 2016. | The comparative study of rice production techniques was completed in collaboration with IRRI. A MIRR seminar was organized in september 2014 with IRRI support, which allowed for the consultation of stakeholders from the region (producers, water user associations, ministries, NGOs, organizations and private sector) and the subsequent approval of MIRR guidelines. A report of the workshop and the draft MIRR guidelines were produced. After the MIRR seminar , demonstration plots have been set up according to the situation of the land: good water control, poor water control.These results made it possible to identify the appropriate seeds and nutrient inputs for each soil type that have been contributed by the composts. Now we are in the phase of large-scale application.Now 7 seed farmer groups (GPS) have obtained certificates by ANCOS, an authority that gives seed certification taking into account the necessary standards on climate change. The publication of the guidelines is still pending, as some new data has emerged from local testing that need to be integrated in the final guidelines. The publication of the guidelines will take place in the first quarter of 2017 | S
| Outcome 1.2 Malagasy government, research institutions and local communities have the tools and methods to assess, monitor, and understand climate change impacts on rice. | This outcome should be underway in 2015, with the development of technical capacity for stakeholders at all levels. Estimated completion Q4 2016. | The project made it possible to acquire materials and equipment for the different activities of the project, such as computers and rice modeling software, training on DSSAT and ORYZA. collection. Up-to-date agricultural calendars and training were completed. Training on agroforestry practices will continue until 2017 and training for the climate risk management (CRM) has already been completed. A hydrological model for 2050 has been completed and the agricultural calendar model for 2050 will be completed in the first half of 2017. | MU
| Outcome 2.1. Sustainable increase in rice yields (using MIRR) | This outcome should be halfway completed in 2015 and completed by the end of the project. | The pre-selection of rice and non-rice varieties was completed in 2014-2015, followed by some local testing to determine feasibility and adaptability. CALA is currently working on the production of basic seed for the 2016-2017 season (large-scale application). Soil and water analyzes were completed and will continue until the end of the project. The updating of the fertilization guidelines was also completed and the project successfully tested a local compost production program. The training of the peasants on practice has made it possible to disseminate the production of composts. Composting associations have been formed and farmers already have the capacity to produce composts. The rehabilitation of the water infrastructure will begin in the first quarter of 2017 and the results of the fertilization guidelines will be disseminated with the MIRR guidelines in the first quarter of 2017 | MS
| Outcome 2.2. Ecosystem services maintained | Reforestation targets were designed to be 70% achieved by 2015 (approximately 6000 ha). Other activities under the outcome were intended to begin in 2015 and to continue until the end of the project | The results of the first reforestation campaign (2014-2015) are not satisfactory (20% success rate). The second season (2015-2016) is less satisfactory (45% success rate) Established by the PCU. The revitalization activities of Water Users' Associations (WUAs) and the training of members and cooperatives have been completed. These have led to the resolution of various disputes and led to the formation of new associations and members. These new members formulated Requests for training from the PCU consultant responsible. Activities such as the dissemination of technological packages, the rehabilitation of lavakas and the various training courses on erosion control, among others, will be carried out during the first quarter of 2017 | MU
| Outcome 2.3. Post Harvest losses reduced | The outcome was designed to have been completed in 2015 | Work with socio-economic analysis of post-harvest losses and rehabilitation options for storage has been completed.The construction of three storage rooms has begun in September 2016, along with training of communities on the management of storage facilities. Activities on the use of rice by products such as straws have also been carried out with the support of livestock experts. | MU
| Outcome 3.1 Technical norms and standards in rice cultivation reviewed and where necessary modified to take climate change into account | This outcome was designed to be initiated towards the end of the project, once sufficient lessons have been achieved from local activities. It was designed to be finalized in 2017. | This result is already ready to be published. After the study on the comparative analysis of rice production techniques and technologies at Alaotra Mangoro and other rice granaries and taking into account the recommendations of the Integrated Model Resilient Rice Harvest (Seminar MIRR), demonstration plots have been set up according to the situation of the land: good water control, poor water control. These results made it possible to identify the appropriate seeds and nutrient inputs for each soil type that have been contributed by the composts. Now we are in the phase of large-scale application. Now 7 seed farmer groups (GPS) have obtained certificates by ANCOS, an authority that gives seed certification taking into account the necessary standards on climate change. | MS
|  |  | Overall rating | MS
Please Provide the Name and Contact information of person(s) reponsible for completeling the Rating section
| Name: | Jane Razanamiharisoa
| Email: | jrazanamiharisoa@ymail.com
Please justify your rating. Outline the positive and negative progress made by the project since it started. Provide specific recommendations for next steps. . (word limit=500)
The project has encountered delays. However the MTR, which was finalized in March 2016, has helped identify problems and means of improvements. Plans to address these recommendations have been developed by the PCU, UNEP Task manager and CTA. Improvement in management practices and tools were implemented and continue to be rolled-out, including TOR for PCU team members, planning of activities using project monitoring tools, more active monitoring of activities and delivery of outputs and collaboration with other teams working on rice production.
| Progress on Key Milestones | Expected Progress | Progress to Date | Rating
Implementing Agency | Outcome 1.1 Knowledge base on best practices for climate resilience in rice, based on existing local knowledge and international research | This outcome should be completed by the end of 2015. | See above and below from national coordinator and CTA for progress description. Based on a recent field mission (December 2016), UNEP agrees that the MIRR activities after a slow start is making good progress and seems on track to achieve its targets. Sustainability is a concern, however, as mentioned elsewhere, and this will remain a focus during 2017. | S
| Outcome 1.2 Malagasy government, research institutions and local communities have the tools and methods to assess, monitor, and understand climate change impacts on rice. | This outcome should be underway in 2015, with the development of technical capacity for stakeholders at all levels. Estimated completion Q4 2016. | See above and below from national coordinator and CTA for progress description. Some training activities are remaining, but seems to be on good track. | MS
| Outcome 2.1. Sustainable increase in rice yields (using MIRR) | This outcome should be halfway completed in 2015 and completed by the end of the project. | See above and below from national coordinator and CTA for progress description. UNEP agrees that the MIRR activities after a slow start is making good progress and seems on track to achieve its targets. Sustainability is a concern, however, as mentioned elsewhere, and this will remain a focus during 2017 | S
| Outcome 2.2. Ecosystem services maintained | Reforestation targets were designed to be 70% achieved by 2015 (approximately 6000 ha). Other activities udner the outcome were intended to begin in 2015 and to continue until the end of the project | See above and below from national coordinator and CTA for progress description. As noted below, reforestation activities have been severely underperforming so far. In consultation with UNEP, the contract with the government collaborator (SNGF) have now been terminated. Alternative delivery methods will be sought for the last planting season to catch up on some of the deficits in terms target and to demonstrate at least one successful planting season before the project closes. | U
| Outcome 2.3. Post Harvest losses reduced | The outcome was designed to have been completed in 2015 | See above and below from national coordinator and CTA for progress description. As noted below, the storage facilities which had started construction during the fall of 2016, have not met the agreed technical specifications of the contract. The half finished buildings will have to be demolished and rebuilt with a new contractor. Legal action is being taken against the contractor to cost-recover funds already paid on contracts to the extent possible. While this will lead to a delay, there should be no problem delivering the structures before project end. Other activities are progressing ok. | MU
| Outcome 3.1 Technical norms and standards in rice cultivation reviewed and where necessary modified to take climate change into account | This outcome was designe to be initiated towards the end of the project, once sufficient lessons have been achieved from local activities. It was designed to be finalized in 2017. | See above and below from national coordinator and CTA for progress description. As noted below, there has been some delays and problems on some activities related to this outcome. This will be a high focus outcome for the last year approaching project closure, as part of overall sustainability efforts. | MU
MS
Please Provide the Name and Contact information of person(s) reponsible for completeling the Rating section
| Name: | Lars Christiansen
| Email: | lachr@dtu.dk
| Progress on Key Milestones | Expected Progress | Progress to Date | Rating
Chief Technical Advisor | Outcome 1.1 Knowledge base on best practices for climate resilience in rice, based on existing local knowledge and international research | This outcome should be completed by the end of 2015. | The comparative study of rice production techniques was completed in collaboration with IRRI. A MIRR seminar was organized in september 2014 with IRRI support, which allowed for the consultation of stakeholders from the region (producers, water user associations, ministries, NGOs, organizations and private sector) and the subsequent approval of MIRR guidelines. The MIRR guidelines were produced and are being distributed in Malagasy locally. A french version will be made available soon to relevant government institutions at the central level. | S
| Outcome 1.2 Malagasy government, research institutions and local communities have the tools and methods to assess, monitor, and understand climate change impacts on rice. | This outcome should be underway in 2015, with the development of technical capacity for stakeholders at all levels. Estimated completion Q4 2016. | The project acquired materials and equipment for the different project activities, such as computers and rice modelling software, training on DSSAT and ORYZA was completed. The compilation of the data required for running the models has recently been finalised. The models are currently being processed by bachelor students under the supervision of the expert. The agricultural calendars for the coming planting season will then be produced based on the results of these models. A hydrological model for 2050 has been completed. Training on CRM was also provided to 20 government representatives. Further training will be provided to agricultural extension staff in 2017. | MS
| Outcome 2.1. Sustainable increase in rice yields (using MIRR) | This outcome should be halfway completed in 2015 and completed by the end of the project. | The pre-selection of rice and non-rice varieties was completed in 2014-2015, followed by local testing to determine adaptability. The CALA provided farmers with base seeds for the season 2014-2015 and 2015-2016. They will also provide base seeds for the season 2016-2017 to complete the local production by certified farmers. The soil and water analyses have been completed and will be ongoing through the end of the project. The update of fertilization guidelines was also completed and the project successfully tested a local compost productions scheme. The rehabilitation of water infrastructure is planned to start in March 2017. The training activities on integrated pest management will also be provided in 2017. The progress has not been as fast as expected because of the few farmers willing to adopt the MIRR practices at the beginning of the project. This number is only getting bigger now, while this is the last year of the project. The results on average yield can therefore not be seen yet. | MS
| Outcome 2.2. Ecosystem services maintained | Reforestation targets were designed to be 70% achieved by 2015 (approximately 6000 ha). Other activities udner the outcome were intended to begin in 2015 and to continue until the end of the project | Although reforestation work has begun, the project has not been able to achieve with a satisfactory level the reforestation targets, owing to the bad performance of the contracted party (SNGF). Approximately 10% of expected target was achieved so far. Additionally, these 350 hectares have a high mortality rate (<50%). The target of 3900 hectares has defined at MTR will likely not be met by the end of the project. Other activities have been achieved including for example the revitalization of WUAs and training on crop rotation. Other trainings have not yet started and are foreseen for 2017 including sustainable land management to control erosion control and large-scale dissemination of the MIRR package. | U
| Outcome 2.3. Post Harvest losses reduced | The outcome was designed to have been completed in 2015 | Work has begun with the socio-economic analysis of post harvest losses and rehabilitation options for storage. The sites have been identified and procurement for construction was initiated in July 2016. However, the construction to date is unsatisfactory as it does not follow the technicalities of the call for tender. The construction has to be redone. After the construction is finalised, training for community-management of storage facilities and conservation of the products will be provided to local communities. Activities on the use of rice by products such as straws, have also been provided with the support of livestock experts. However, no concrete results of this training have been monitored to date. | MU
| Outcome 3.1 Technical norms and standards in rice cultivation reviewed and where necessary modified to take climate change into account | This outcome was designe to be initiated towards the end of the project, once sufficient lessons have been achieved from local activities. It was designed to be finalized in 2017. | The project developed a rural communication strategy which implementation was initiated and stopped shortly after. A new expert will be hired early 2017. New activities have been added, including on the analysis of economic perpsectives and market analysis for the regional rice production. These activities will be undertaken in 2017. The activities regarding the revision of technical guidelines and national strategies have not been initiated yet. | MU
|  |  | TOTAL RATING | MS
Please Provide the Name and Contact information of person(s) reponsible for completeling the Rating section
| Name: | Lucille Palazy
| Email: | lucille.palazy@gmail.com
| Please justify your rating and address the following points: 1. Indicate trends, both positive and negative, in achievement of outcomes as per the project indicators. 2. Detail critical risks that have affected progress. 3. Outline response to MTR undertaken this reporting period. 4. Outline action plan to address projects with a rating of HU, U or MU. Please keep your input to 1200 words | The project has been delayed and it has not been possible to make up for lost time to this day. Delivery is slow, with changes in senior staff implying the renegotiation of previous agreements and MOUs. Procurement is also slow, and there is often a lack of suitable candidates for consultancies. The quality of some outputs provided by consultants has sometimes left to be desired, creating longer delays for revision of documents and reports. Monitoring of consultant's outputs has been ad hoc, with no clear system in place to follow the project indicators. Recommendations provided by the draft Midterm Review (MTR) have been reviewed by the project team and strategies have been developed to enhance output delivery. For example, an M&E expert has now been appointed to monitor consultants and deliverables more closely, and collect data on the indicators. Roles and responsibilities between members of the project team have been clarified, with lead responsibilities remaining in the hands of the project manager. Last, the involvement of the CTA in the project will be strengthened during the last of the project through an increased number of field mission to support the team in meeting the project targets before the end of the project.
Highly Satisfactory (HS)
Satisfactory (S)
|  | Marginally Satisfactory (MS) | The results obtained to date (in the fourth year of the project implementation phase) remain far from the expected results based on the initial plans. However, visible efforts have been made by the project coordination team and the progress rate was significantly increased following the MTR.
Marginally Unsatisfactory (MU)
Unsatisfactory (U)
Highly Unsatisfactory (U)

## Project Indicators
PROJECT Indicators (*as revised following baseline study)
Please provide all indicators being tracked for the project as outlined in the project document
Type of Indicator (indicators towards Objectives, Outcomes, etc…)
Type of Indicator | Indicator | Baseline | Progress since inception | Target for Project End
Outcome 1.1 Knowledge base on best practices for climate resilience in rice, based on existing local knowledge and international research | Percentage of farmers with access to selected and publicized MIRR | There is currently no MIRR available although various ameliorated techniques have been developed in recent decades | Documentary analytical work has been completed and guidelines on the application of the MIRR are being finalized. A workshop was held with all stakeholders to discuss and validate technical findings. MIRR has been tested locally for two seasons (2014-2015 and 2015-2016) and will be scaled up during the next season (2016-2017). (90% completed) To date, 1 417 farmers (258 in Manakambahiny, 754 in Ambohijanahary and 405 in Bemaitso) out of a targeted population of 2 100 farmers (corresponding to 68%) have been trained to use the MIRR practices. Importantly, the number of targeted farmed was not defined at the inception stage. The most logical way of defining it based on the MTR recommendation is to estimate the number rice cultivation farmers in the targeted sites. The resulting total is 398 in Manakambahiny, 1 034 in Ambohijanahary and 545 in Bemaitso. Based on the project budget, a target of 90% of the targeted farmers adopting the MIRR practices is unrealistic. The proposed new target is 80%. However, regarding the upscaling potential, the initial target could potentially be met in the near future. | Based on existing ameliorated techniques such as SCV, SRI & SRA, and based on new research, 1 Resilient Rice Model is selected and published. At least 90% of farmers targeted by the project has received technical support and has been trained to implement the technique according to technical guidelines.
Output 1.1.1 Best Available Technologies and Integrated Resilient Rice Model (Modèle Intégré de Riziculture Résiliente - MIRR) selected and publicized | # and type of technical guidelines for MIRR developed and publicized based on best available technologies and technique | A series of guidelines for rice cultivation techniques, technical guidelines for direct seeding and system of rice intensification, are available from regional directorate of rural development but not yet widely disseminated | Guidelines in Malagasy have been produced by the corresponding consultant. They will soon be issued in french. Three types of guidelines have been developped: i) for rice cultivation under bad water management conditions: ii) rice cultivation under good water management conditions; and iii) rain-fed rice-cultivation on hill sides. Each of these guidelines include the following key techniques: seeding, field preparation, fertilisation, weeding, phytosanitary maintenance and harvest. The final draft of these guidelines will be published after the last cultivation campaign, early 2017. (90% completed) | 1 Recommended Integrated Resilient Rice Model developed and published, including a series of at least 1 technical guidelines with the following key stages/techniques:  Seeding  Planting  Harvest  Post-harvest  Fertilization  Integrated pest management  Water management
Outcome 1.2 Malagasy government, research institutions and local communities have the tools and methods to assess, monitor, and understand climate change impacts on rice. | Level of use of the tools and methods made available to Malagasy government, research institutions and local communities to assess, monitor and understand climate change impacts on rice production | Current tools to address, monitor, and understand climate change impacts on rice are hampered by a lack of data and weak potential to convey information to farmers. Data on observed climate patterns is not being systematically collected at an appropriately local level making it difficult to create models and planting calendars. Dissemination of what information exists is also weak given the limited number of extension staff. While these staff appear to already be trained in climate issues, the information is not being disseminated to farmers. | Work has been initiated in almost all planned activities, however there have been significant delays. The theoretical part of the outcome (research, analysis and studies) have been completed, however the local implementation is yet to be completed. See below for detail (50% complete) The MoU with DGM and the contract with local radios to undertake the diffusion of 3 to 4 days climate forecast and seasonal forecasts is under the process of being signed by DGM. - Training on climate change trends and impacts was provided as part of the MIRR training workshop to 200 government staff. - Awareness-raising on climate change trends and impacts was provided to the public through the development of communication tools such as pamphlets (distribution started but will be done further by next communication consultant), radio talks on local radio by MIRR and compost expert. - Training on the MIRR was provided during several events at the national (Sept 2014), regional (August 2015) and local levels (2014-2015). However, technical guidelines have not yet been finalised. - Vulnerability maps will be produced by Foibe Taosaritanin'i Madagaikara (FTM) ou Institut Geographique et Hyydrographique de Madagascar in collaboration with the national consultant responsible for the development of the alternative models DSSAT et Oryza and the national consultants in charge of creating the agricultural calendars and in charge of providing training on CRM. | All regional extension services, research institutions including CALA, and at least 90% of targeted farmers are aware of climate change trends and impacts through awareness raising and information sessions, have access to regular climate forecasts through local communication channels (radio, newspapers), and have been trained and implement MIRR and its technical guidelines, including vulnerability maps.
Output 1.2.1 Malagasy government, research institutions and local communities have the tools and methods to assess, monitor, and understand climate change impacts on rice. | Number of rice cropping system models based on expected climate change scenarios, including vulnerability maps of future rice production, and hydrological models developed | Currently, there is no rice cropping system model that includes vulnerability maps of future rice production under potential climate change impacts and hydrological models developed. | A climate based hydrological model was developed in 2014. The national consultant appointed to build this model first compiled detailed downscaled data on: water availability under the climate change scenario, climate risks including those impacting rice cultivation, and pest risk induced by climate change. Gaps filled in: Meteorological and cultural data acquisition to perform rice modeling using Oryza and DSSAT; Development of a vulnerability map (Overlay current climate and climate change maps on maps delineating crops, forests and grazing areas. Work on the migration of land use in time according to the new climate that will take place in the area. Make maps of isohyets, evapotranspiration, simple hydrographic networks and existing water points, boundaries of the region and watersheds). Corresponding info disseminated: The dissemination of complilated data to the corresponding stakeholders at regional and local levels is necessary in order to provide real climate change situation within its agricultural impacts. It will be done by providing to the stakeholders a booklet containing data including its interpretation and vulnerability map (print version) in big format and advertised in public areas. Training was provided on Oryza and DSSAT models to 15 people (six national and regional staff of MEEMF, two staff from MADR, two from FOFIFA, two from the National Institute of Geography and Hydrography, and three from National Institute of Statistics). A consultant was appointed to collect the required data to build the models. Two bachelor students will be responsible for buidling the Oryza and DSSAT models based on this data and to update the agricultural calendars accordingly under the supervision of the consultant. The ToRs for the SIG consultant for the development of the vulnerability maps will be published in December 2016. | Detailed available downscaled data on expected climate change risks and impacts on rice sector at the local level compiled; identified gaps on available data are filled in; and all data are disseminated to relevant stakeholders at the regional and local levels. 4 rice cropping system models with vulnerability maps developed according to 4 different expected climate change scenarios (driest, low dry, low humid, and most humid scenarios) and 1 hydrological model developed based on available downscaled data on expected climate change risks and impacts.
Output 1.2.2 Updated, dynamic agricultural calendars and climate early warnings taking into account current and projected variability disseminated to local population | Frequency of dissemination of updated dynamic agricultural calendars and climate information, including flood early warnings in the three projected sites | Agricultural calendars under current climate conditions are well defined for all seed varieties developed, yet farmers do not necessarily apply them. The challenge resides in distributing and encouraging the application of established calendars amongst farmers through training and diffusion. Furthermore, new agricultural calendars will need to be developed on the basis of projected future climate trends. With respect to the diffusion of climate information, networks for analyzing and disseminating climate data are also insufficient:  Manakambahiny – In Ambalavato, farmers have access to daily meteorological forecasts in the newspaper and on the Radio Nationale Malgache. In Ambaibo, farmers also have access to daily forecasts. This information, however, is not very useful as it cannot provide longer forecasts that would aid in, for instance, determining seedling date or predicting potential floods.  Bemaintso and Ambohijanahary – Farmers have access to daily forecasts, but the forecasts do not help them adapt their growing calendar with enough forewarning or to choose which seed variety to use. | The MoU with local radio to disseminate the climate forecast over 3/4 days, early warnings for floods and seasonal forecast information was developped. The selected local radio is Radio Amomix. It is the main radio in Alaotra Mangoro region. Agricultural calendars have been updated and training on their use was provided in December 2015 to 305 farmers and extension staff. The specific calendars for 2017-2018 will be developed based on the results of DSSAT and Oryza models. (50% complete) | Climate information and 3- 4 day forecasts, including flood early warnings, made available to farmers through local communication systems. Dynamic agricultural calendars updated and disseminated to at least 80% of targeted farmers.
Output 1.2.3 Agricultural extension staff trained on climate risk management in an agro-ecosystem context | Number of agricultural extension staff in the three districts trained on climate risk management in agro– ecosystem context (gender and district disaggregated) | Extension workers were trained in climate change issues through the BV Lac project, and they do not necessarily lack training. The challenge is disseminating information from extension workers to farmers given how little contact they have with farmers. The presence of extension workers in the project sites is the following:  Manakambahiny – The municipality contains the city Ambatondrazaka, which is the capital of the Alaotra-Mangoro Region. There are 15 to 20 agriculture staff, of which 9 to 11 extension workers cover the 5 districts of the region. Their presence in the field is weak.  Bemaintso – The municipality is part of the Andilamena district where 2 extension workers for rural engineering are located. They use radio to broadcast information to farmers.  Ambohijanahary – The municipality is part of the Amparafaravola district, for which there are 4 extension workers (2 for agriculture and 2 for engineering). | A first training sessions was organised in April 2016 for 20 people including staff of extension services and local authority representatives. A second training session will be organised in 2017 to extend the number of people trained to the totality of agriculture extension staff. | 100 % of staff trained on climate change aspects and how to disseminate new knowledge to farmers, including women.
Outcome 2.1. Sustainable increase in rice yields (using MIRR) | Percentage of change in rice yields in all three project sites | Rice yields in 2012-2013 for irrigated rice in the project areas were:  Manakambahiny – 3.41 tons/ha average (roughly 3 tons/ha for Mk34 and 3.5 tons/ha for Dista and Tsemaka)  Bemaintso – 0.7 tons/ha for MK34 and 1.5 tons/ha for Dista (the low yields observed in Bemaintso are due to floods – care should therefore be taken while analyzing these data)  Ambohijanahary – 2 tons/ha for MK34 and 3 tons for Tsemaka  Tsemaka – Farmers use the variety to increase yields under challenging water conditions; however, farmers report that it does not sell as well at market as MK34.  MKx – Variety developed and distributed by CALA.  Dista – Farmers use the variety in cases where the planting rains start late.  SEBOTA – The variety was developed for the BV Lac project in partnership with CALA and with help from CIRAD. It is designed to tolerate poor water management conditions, but the seed has not been distributed to many farmers due to limited reproduction of the seed and to patent issues.  FOFIFA – This is a group of early maturing varieties that can be produced in the rainy and dry seasons. They are developed by CALA. The last variety developed under this group is FOFIFA 174. | The average rice production among the targeted farmers was 2.15 T/ha in season 2013-2014. It increased to 4.75 T/ha in season 2014-2015 and 6.25 T/ha in season 2015-2016 thanks to the adoption of the MIRR practices by trained farmers. The number of people adopting the MIRR practices has significantly increased from one cultivation season to the other. However, it takes a long time and several demonstration seasons for the majority of the farmers to be willing to change their practices. During the last year of the project, the larger water rehabilitation works will be completed, which is expected to increase yield signficantly as it is a major constraint to rice production in the areas of the project. | Individual rice yields for targeted producers increase by 25% in relation to current averages in each project area.
Output 2.1.1 Climate resilient rice varieties selected through participatory field testing | Number and types of climate resilient rice varieties tested and selected within the three project sites (Municipalities of Manakambahiny, Ambohijanahary and Bemaintso) | Current rice farming is dominated by the seed variety MK34, though it is not necessarily resilient. The next most prominent varieties are Dista and Tsemaka. | The climate-resilient rice varieties created and tested by CALA in the laboratory were presented to the farmers during a workshop in September 2014. Among the varieties presented, the farmers selected three varieties. These varieties were thereafter tested in the field. These varieties are SEBOTA 231, X265 and Madikatra. Based on consultation of CALA, no activities to strengthen their facilities and capacities were deemed necessary. CALA facilities and capacities is sufficient to develop the required varieties. | CALA facilities and capacities are strengthened to develop at least 5 varieties that are tested and proven resilient in both laboratory and field settings in the three project sites.
Output 2.1.2 An operational multiplication and dissemination scheme for adapted seed varieties | Annual quantity and quality of adapted certified seeds produced and distributed in each of the project sites | Seed multiplication appears to be dominated by four main facilities. Challenges include production capacity for CALA and the publication and dissemination of seed-specific planting guidelines. | To date, 0.439 tons of seeds were distributed for the season 2014-2015 for the tree sites (Manakambahiny, Ambohijanahary and Bemaitso), 5.650 tons for the season 2015-2016 for the tree sites (Manakambahiny, Ambohijanahary and Bemaitso) and 4.848 tons for the season 2016-2017 for the two sites (Ambohijanahary and Bemaitso). In case of the season 2016-2017 for the Manakambahiny site, the seeds are not distributed yet but it will be done before the end of this year no later than the beginning of the campaign. Production of adapted seeds is being conducted. During the first years of the project, it has been difficult to identify farmers willing to specificialise in the production of MIRR seeds. Production was therefore done by the CALA. However, local producers in Manakambahiny and Bemaitso have recently received the certification from the National Agency for the Official Control of Seeds and Plants (ANCOS) for the production of rice seeds for the new varieties. As a result, a significant part of the seeds used for the season 2016-2017 is produced by local farmers. The farmers is Ambohijanahary did not receive the certification because they did not meet all the criteria. However, they will be further supported by the project to obtain the certification in 2017. | At least 5 tons total of seeds for all 5 varieties that were tested and proven resilient are produced annually and distributed in the 3 project sites.
Output 2.1.3 Updated fertilisation guidelines according to best available standards and taking climate conditions into consideration | Number of farmers who apply updated fertilisation guidelines in all three project sites (Municipalities of Manakambahiny, Ambohijanahary and Bemaintso) | Farmers do not appear to follow any specific guidelines for fertilizer application. Farmers vary on how and when they use compost, manure, urea, NPK, and/or DAP. Many farmers do not use any chemical fertilizer practices.fertilisers are not commonly used | To date, a total of 2 212 farmers (504 in Manakambahiny, 897 in Ambohijanahary, 811 in Bemaitso) have received theoretical and practical training on the production and use of organic compost. This figure corresponds to the number of the target people of the project as well as some from the surrounding communities interested in the training. Training has not been limited to the target population. Among the farmers who received training, 87% are applying the fertilisation guidelines provided. The contract with STOI was extended to enable new farmers adopting the MIRR practices during the season 2016-2017 to receive training. The farmers who adopted the MIRR practices in the previous year, now produce their compost independantly from the project. The last year of the project will focus on ensuring that the autonomous production system is functional. | 90% of targeted farmers have been trained and/or received technical support and apply fertilisation guidelines updated as part of the development of the MIRR.
Output 2.1.4 Integrated pest management is implemented | Number of farmers trained in integrated pest management in all three project sites (gender and age disaggregated) | In general, farmers had no information or training about the appropriate protocols for using pesticide in pest control. While some used commercial pesticides, they applied them with little knowledge of best practices. | A national IPM expert has been appointed to provide training on pest management and the activities are expected to be completed by the end of Q2 2017. | 400 farmers trained in integrated pest management, gender and age disaggregated (and among them 50% women and young)
Output 2.1.5a Water efficiency, management and conservation technologies and infrastructures are implemented | Number of Km of rehabilitated irrigation canals and number of reservoirs dredged in all three project sites | Infrastructure in the 3 municipalities was in a state of significant disrepair with damaging siltation and reduced irrigation capacities throughout. There is a large need for rehabilitating canals and dam infrastructure. | A civil engineer was appointed by the project to undertake the feasibility study for the rehabilitation of water management infrastructure. He is currently the prioritising the needs identified with local communities to develop the call for tender. Based on the reports and consultations to date, the priority interventions to be implemented in the project sites will include the construction of water intakes, sand catchment systems, water points, livestock passages, bridges, strengthening of the irrigation and drainage canals, strengthening of river banks in Manakambahiny, strengthening of dikes, rehabilitation of diversion dams, and canal dredging. The prioritisation process will be finalised early 2017. The scale of the interventions remain unchanged but the targets will likely need to be amended. Any changes will be sent to the AF for approval. Considering water needs during the rice cultivation season (January to May), it is not possible to initiate the rehabilitation interventions during this period. Call for tender willtherefore be published after the end of the rice cultivation season in March 2017. The construction will then start in May 2017. | The following targets will require costly investments for which the current available budget (US$575,000) may not be sufficient. Some fund reallocations between outputs may be possible (see recommendation 8) to increase the available budget envelop and achieve the following targets. If budget reallocations are not possible, the following targets would therefore need to be decreased. Manakambahiny: 35 km of primary canals cured, dredged, and maintained with norms that take expected climate change impacts into account (future precipitation regimes, drainage and run-off); 4 water intake points along the Ilakana River rehabilitated, strengthened and made more resilient to expected climate change impacts. Bemaintso: The dam is drained and dredged; 14 km of primary canals and 21 km of secondary canals are cured, dredged, and maintained all with norms that take expected climate change impacts into account. Ambohijanahary: The dam at Anony is rehabilitated, primary water control valves are repaired; 13 km of primary canal are drained, dredged, and repaired; and primary canal is extended to irrigate 600 ha of additional rice fields all with norms that take expected climate change impacts into account.
Output 2.1.5b Water efficiency, management and conservation technologies and infrastructures are implemented | Percentage of change in water availability and in water use efficiency in all seasons to water users associations in all three project sites | There is a decrease in water availability during the dry season in all 3 Districts, and water losses reach up to 50 %. | The water infrastructure will be finalised by August 2017. Decrease in water loss and increase water availability are expected as soon as the new infrastructure is functional. (20% complete) | 35 % increase in water availability in all seasons in all 3 districts. Water loss estimation decrease from 50% to 25%.
Outcome 2.2. Ecosystem services maintained | Percentage change in land covered by biomass and in overall productivity (rice, vegetables and livestock) in project sites | There is no evidence of activities to increase land covered by biomass such as agro forestry practices, reforestation, or vegetable crop rotations. No farmers use soil quality or water quality improvement techniques. | There have been significant delays in achieving this outcome, mostly owing to the difficulties encountered by the main service provider, the SNGF. A plan to catch up on the delays was developed (including the creation of a specific bank account for the project funds to facilitate project-related disbursement) was signed by SNGF. However, the second planting season was not successful either. 68 hectares out of 900 have been reforested during the first season. 278 out of 1200 were reforested during the second planting season.A high mortality rate (>50%) was recorded among these 346 hectares. As a result, the contract will be cancelled in December 2016. At least one NGO per site will be appointed during the last planting season to maximise the number of hectares successfully reforested by the end of the project. Regarding the communal restoration, the contract have been signed and the bank account for the project is open in each site. The communes have selected the restoration sites and the sites for installation of the nurseries. The resforestation activities for 100 hectares in each commune will start in January 2017. The consultant has done research on how to value the rice straw and has trained the farmers on its application. Without a follow-up study to be done later by the consultant, we do not currently have any information on the results. Vegetable production has increased from 0.15 tons in 2013 to 2 tons in 2016 following the training provided on off season cultivation since 2014. | Change in overall land area covered by forests (i.e. net reforestation) of at least 50km2 across the combined 3 municipalities. Data on vegetables and livestock productivity/yields collected by extension services, and increase in overall productivity of rice, vegetables and livestock of 5 % throughout the life of the project and across the project sites.
Output 2.2.1 Best available land preparation, production and harvesting techniques disseminated to reduce deforestation, maintain soil fertility and integrity, and to provide adequate growing conditions | Percentage application of resilient rice model, including rice–vegetables rotation systems, in all three project sites (gender disaggregated) | Rice/vegetable crop rotations are used on only very small pieces of rice fields. Guidelines for rice/vegetable rotation practices were developed under the BV Lac project, but their dissemination was somewhat limited. | CALA provided training on rice-vegetable crop rotation in 2015 and 2016. In 2015, 65 farmers have cultivated non-rice crops (i.e. carots, onions, beans, potatoes, cabage, tomatoes) on an average of 0.06 hectare each. In 2016, 903 farmers have cultivated non-rice crops (i.e. cabage, courgettes, cucumber, beet, coliflower, pepper, Petsaï, vetch, carots, onions, beans, potatoes, tomatoes) on an average of 0.17 hectare each. Approximately 80% of this production was for commercial purposes. | At least 75% of targeted farmers practice rice/vegetable crop rotation on an area larger than 0.1 ha and for commercial purposes (and among them at least 50%of women and young).
Output 2.2.2 Watershed rehabilitation in productive landscapes introduced, including through reforestation and adaptation of agro forestry practices | # of ha reforested; # of farmers and land/forest users trained on sustainable agro-forestry and land management in all three project sites (gender and age disaggregated) | some reforestation underway in the broader basin but not in project sites; currently there are no people trained on SLM and agroforestry in the project sites | There have been significant delays in achieving this outcome, mostly owing to the difficulties encountered by the main service provider, the SNGF. A plan to catch up on the delays was developed (including the creation of a specific bank account for the project funds to facilitate project-related disbursement) was signed by SNGF. However, the second planting season was not successful either. 68 hectares out of 900 have been reforested during the first season. 278 out of 1200 were reforested during the second planting season.A high mortality rate (>50%) was recorded among these 346 hectares (20% complete). As a result, the contrat will be cancelled in December 2016. At least one NGO per site will be appointed during the last planting season to maximise the number of hectares successfully reforested by the end of the project. Regarding the communal restoration, the contract have been signed and the bank account for the project is open in each site. The communes have selected the restoration sites and the sites for installation of the nurseries. The resforestation activities for 100 hectares in each commune will start in January 2017. To date 257 farmers and extension workers have been trained on agroforestry in the project sites. This includes the production of 20 posters, 50 pamphlets and 28 training sessions. The contract of the national consultant was amended because of additional requests for training from local communities. ToRs for a consultant or organisation to provide training on land management for upland and lowland communities will be published in January 2017. | In total, at least 50km2 of area distributed in the 3 districts are reforested (5,000 ha). At least 400 farmers trained in sustainable agro forestry and land management (and among them 50% of women and young).
Output 2.2.3 Soil conservation and livestock management techniques adapted to topography and landscape in light of future climate conditions | % change in erosion rate | The project PRODAIRE has been training workers for the DREF in monitoring erosion rates. The DREF has therefore the in-house capacities to monitor erosion rates in the project sites. Average erosion rate in the region is 12 mm.yr.1, according to Cox, R. et.al, 2009 “ Erosion Rates and Sediment Contributions in Madagascar Inferred from 10 Analysis of Lavaka, Slope, and River Sediment” | A contract is under development with DREEF to undertake this measurement of erosion rate. However, considering the limited progress of the reforestation activities to date, this measurement will be done after the next planting season. This rate will then be compared with the erosion rate at baseline. | 50 % reduction in erosion rates.
Output 2.2.4 Revitalization of producer’s cooperatives and water user associations for collaborative natural resources allocations (e.g. land and water) and management | Number of members of farmer’s cooperatives and water user associations trained on water management and administrative management within the three project sites | Water user cooperatives exist in the three project areas; however, in all areas members expressed a need for training in administrative management as well as training in water management. | An analysis of the situation regarding Water user associations has been conducted and recommendations were made on means to strengthen the WUAs. Thereafter, training was provided to 84 WUA members on water management. Furthermore, training for WUAs is planned in 2017 on administrative and financial management. Last, additional training will be provided on water management following the request of several other WUAs. | 75 % of the members of water user cooperatives in the project area have been trained on water management and administrative management.
Output 2.2.5 Water quality assessments | Percentage change in water quality (e.g. reduction in turbidity, pollutant content, microbial content, sediment content) in all three project sites | There is currently no water quality analysis conducted in any of the three municipalities | Measure will be done because construction of infrastructure and after. The methodology was developed in 2014. Training will be provided to Regional Water Direction on sampling. They will send samples to CRDE for analysis by the selected consultant. | Water quality assessment is conducted in all 3 project sites by the DIREAU with technical support provided by the project if needed. Water quality increase by 10% from the date of the first analysis
Outcome 2.3. Post Harvest losses reduced | Percentage change in post harvest losses | Post–harvest losses are estimated to be between 5 and 10% of total harvest. | The construction of three climate-resilient storage facilities was initiated in July 2016. However, the construction to date has not followed the technicalities of the call for tender. The construction has therefore been suspended. The contract will be ceased and another company will be appointed in January 2016. As soon as the construction will be achieved, training on the management of the storage facility and on the conservation of the products will be provided. | Post-harvest losses are reduced to less than 4%.
Output 2.3.1 Increased utilization of rice by–product especially rice straw | Percentage change in use of rice straws in animal feeding and for briquetting | There are regional variations in the degree to which farmers exploit rice stalks for other uses. In some municipalities, residues are simply burned in the field. | The use of rice straw in the project sites was analysed through the survey of 40 families. Thereafter, 350 farmers were trained on the use and commercialisation of rice straw as a source of energy and other uses. The effects of this training on the use and commercialisation of rice straws as a results of the training will be measured in 2017. | 75% of farmers use or commercialize rice straws.
Output 2.3.2 Post–harvest storage facilities with phytosanitary control, serving as trading points and markets | Number of renovated storage facilities in all three project sites | Storage facilities in the project sites exist, but they are not in adequate condition | A comprehensive feasibility study has been completed and recommendations were made on the rehabilitation and construction of upgraded resilient storage facilities. Based on the consultations with the mayor of each targeted commune, the land ownership for the existing infrastructure referred to in the baseline is unclear. As a result, there was a risk that community management systems could not be implemented. It was therefore decided to build new infrastructure on public land. The sites selected in a participatory manner with local communities are also close to main hall for security purposes. The construction of three climate-resilient storage facilities was initiated in July 2016. However, the construction to date has not followed the technicalities of the call for tender. The construction has therefore been suspended. The contract will be ceased and another company will be appointed in January 2016. As soon as the construction will be achieved, training on the management of the storage facility and on the conservation of the products will be provided. | 75% of existing facilities have been renovated.
Outcome 3.1 Technical norms and standards in rice cultivation reviewed and where necessary modified to take climate change into account | Number and types of technical norms and standards in rice cultivation reviewed and modified at the national level to take climate change into account | No recommendation or revision has currently been made to technical norms and standards in rice cultivation. | This outcome is designed to be initiated towards the end of the project, once sufficient lessons have been achieved from local activities. It is intended to be finalized in 2017. The validation workshop of the National Rice Strategy on Rice Cultivation developed by the Ministry of Agriculture is planned for 19 December 2016. The MIRR expert of the project will participate to the workshop for the intergration of the MIRR practices into this strategy. Specific technical guidelines for MIRR practices have been developped. A workshop will be organised in December 2016 to discuss the revision of national technical guidelines on rice cultivation based on the MIRR results. The ToRs will then be developed and the relevant partner will be appointed to develop the proposed revisions. | At least one national strategy on rice cultivation and at least one technical guideline for the following rice cultivation stages/techniques are revised and updated at the national level: • Seeding • Planting • Harvest • Post–harvest • Fertilization • Integrated pest management • Water management
Output 3 .1.1a Gaps and possible maladaptations in the current rice policy are identified and recommendations on rice policy reform are made | Number and types of activities identified and implemented for up scaling and replication from MIRR application in broader Alaotra basin and in other regions | While there is an Agricultural Development Strategy at the national level, it does not have a true application at the regional level due to financing. There is no specific policy for growing rice. | A workshop between the Ministry of Agriculture, FOFIFA, CALA and other relevant partners will be organised at the beginning of 2017 to discuss the results of the MIRR, and the developement of a replication and upscaling strategy. The ToRs will then be developed and the relevant partner will be appointed to develop the strategy and its action plan. | 1 replication strategy and action plan developed, including at least 5 to 10 operational activities for up scaling and replication of MIRR practices in the broader Alaotra basin and beyond.
Output 3.1.1b Gaps and possible maladaptations in the current rice policy are identified and recommendations on rice policy reform are made | Number and types of recommendations on rice policy reforms made | The National Strategy on Rural Development (SNDR) was completed; however, this strategy has not been published or disseminated. | A workshop between the Ministry of Agriculture, FOFIFA, CALA and other relevant partners will be organised in December 2016 to discuss the revision of the SNDR, together with the discussion on the revision of the national technical guidelines on rice cultivation (please see Indicator 3.1). The ToRs will then be developed and the relevant partner will be appointed to develop the proposed revisions. | The SNDR is revised with measures to increase climate change resilience of rice production, and then the strategy is published and disseminated.
Outcome indicator 3.2 Conditions in place for a full adaptation of the rice sub–sector | Number and type of stakeholders to which the report on best practices and lessons learned is distributed | Lessons learned and best practices will be identified and collected during project implementation | A meeting will be organised with the consultants who worked on the project during the second trimester of 2017 to gather the lessons learned and best practices. After the workshop, the selected consultants will be appointed to produce the report in collaboration with the PCU. | 1 report at end of project.
Output indicator 3.2.1 A report on best practices and lessons learned for rice adaptation in Madagascar | Number and type of stakeholders to which the report on best practices and lessons learned is distributed | See above | See above | See above
Output indicator 3.2.2 A strategy for communicating information on adaptation techniques to farmers is implemented | TBC | TBC | Activities have begun since 2014 and are designed to last until project completion. A rural communication strategy was developed. During the first stage of its implementation, radio talks on MIRR practices have been broadcasted locally and pamphlets have been developed and distributed. However, because of insufficient performance, the contract with the communication expert was ceased. The ToRs will be published in January 2017 to hire a new expert. | At least one documentary on MIRR practices developped and broadcasted on national TV and radio talks broadcasted on local and national radios. Field visits and training for 2 or 3 representatives of farmers association throughout Alaotra-Mangoro to the project sites. Field visits and training for Regional Agriculture Delegation and other relevant groups (e.g. Associations Paysannes Régionales, Vulgarisateurs Agricoles, Fédération des AUEs...) of other selected regions.

## Lessons Learned
QUALITATIVE MEASURES and LESSONS LEARNED
Please complete the following section every reporting period
Implementation and Adaptive Management | Response
What implementation issues/lessons, either positive or negative, affected progress? | The project has encountered significant difficulties with some service providers who did not have the required capacity to deliver results. This is the case of the SNGF as well as some consultants. A more thorough capacity assessment for service providers should be conducted before signing agreements, particularly those that are signed on a non-competitive basis. The project has also encountered significant difficulties in terms of management processes, procurement, etc. In future, comprehensive training and harmonization of procedures should be conducted early on. Based on the experience gained during the project implementation phase to date, contracting government institutions for the implementation of project activities should preferably be avoided in the future. Indeed, if the government institutions hired as a service provider does not perform, it is challenging to oblige these institutions to apply corrective actions or to break their contracts because it is necessary for government institutions such as the Implementing Agency to maintain good relationships with other government institutions. A further lesson, based on the poor performance of selected service providers for building of the storage facilities, is that due diligence for the contract awarding needs to much more thorough, and once awarded, close and frequent monitoring of works and adherence to agreed technical specifications needs to be done by the project coordination team and/or hired technical experts. UNEP has now provided additional guidance in this regard.
Were there any delays in implementation? If so, include any causes of delays. What measures have been taken to reduce delays? | Yes. Delays were caused by a variety of reasons: changes in procedures at UNEP and within MEF, changes in personnel in MEF and other key ministries, lack of capacity of service providers and low quality of outputs, difficulties in procurement of required expertise and resources. These have all been addressed individually and are being monitored by the CTA and TM.(see risk section for additional mitigation detail)
Describe any changes undertaken to improve results on the ground or any changes made to project outputs (i.e. changes to project design) | Changes to delivery strategies and mechanisms occur on an ongoing basis, to deal with shortcomings, challenges, or delays. In addition, activities were added to promote the sustainability of the project such as the communication strategy and the certification of seed producers. Further changes are expected in 2017 to increase the capacity of farmers to maintain the use of the whole MIRR practices' package beyond the project. For example, training for the production of non-rice seeds will be integrated. Last, awareness raising on bushfires will be provided to increase the sustainability of the reforestation interventions.
How have gender considerations been taken into consideration during the reporting period? What have been the lessons learned as a consequence of inclusion of such considerations on project performance or impacts? | Service providers do not yet monitor women participation systematically. It is necessary to doublecheck with every consultants and institutions that women participation and women benefits from the project needs to be measured separately. The same problem was met with the measurement of youth participation in the project.
Please complete the following section at mid-term and project completion
Lessons for Adaptation | Response
Climate Resilience Measures
What have been the lessons learned, both positive and negative, in implementing climate adaptation measures that would be relevant to the design and implementation of future projects/programmes for enhanced resilience to climate change? | The high turnover in government staff in Madagascar requires very regular meetings by the PCU with government representatives to make sure that representatives in the key institutions are aware of and fully support the project.
What is the potential for the climate resilience measures undertaken by the project/programme to be replicated and scaled up both within and outside the project area? | The involvement of the Ministry of Agriculture should have been stronger from the beginning of the project. Additionally, the turnover within all institutions resulted in limited awareness of the Ministry of Agriculture on the project whose MIRR component falls directly under their mandate. Their involvement will be significantly increased during the last year of the project. For future projects, the key government institutions should be involved in every step of the project design and implementation.
Concrete Adaptation Interventions
What have been the lessons learned, both positive and negative, in implementing concrete adaptation interventions that would be relevant to the design and implementation of future projects/programmes implementing concrete adaptation interventions? | All partners have the tendancy to implement their interventions without taking climate change into account despite the emphasise on climate change in the ToRs. Most of the time only past trends and current conditions are considered. A close control of the consideration of future climate conditions by the experts appointed by the project is therefore required for every project activities.
What is the potential for the concrete adaptation interventions undertaken by the project/programme to be replicated and scaled up both within and outside the project area? | A replication and upscaling strategy will be developed in 2017 together with an action plan containing concrete on-the-ground interventions. Additionally, field visit to the intervention sites and training will be organised for representatives from other farmers' organisations in the region, as well as selected stakeholders and agriculture extension staff from other selected regions during the last year of the project. Finally, farmers not benefitting from the project have adopted some of the MIRR practices because they learned from the demonstration sites implemented. The project intervention are therefore already being upscaled locally. There is still significant work to be achieve in 2017 to promote maintenance of the interventions but the potential for replication and upscaling is considered as good.
Community/National Impact
What would you consider to be the most successful aspects for the target communities? | To date, the most successful interventions for local communities is the introduction of the following practices: production and use of organic compost, use of climate-resilient species, cultivation of counter-season rice and production of non-rice crops. These practices have led to a significant increase in rice and crop yields.
What measures are/have been put in place to ensure sustainability of the project/program results? | One of the recommendations of the MTR was to increase awareness of the beneficiaries on the fact that the funds would stop soon and it was the farmers responsibility to ensure that they would have all the tools and knowledge necessary before the end of the project to be able to continue benefitting from the project outputs beyond its end. As a result, since the beginning of 2016, the sustainability of the interventions were discussed with local communities on a more regular basis. Regarding the MIRR, some aspects still need to be sustained (e.g. rice seed production in Ambohijanahary, non-rice seed production in all sites) but the project beneficiaires can now implement most of the MIRR elements without the project support. For the restoration interventions, long-term management agreements will be developped and awareness-raising campaigns against bushfires will be implemented. These measures will promote the maintenance of the project outputs in the long term.
What measures are being/could have been put in place to improve project/program results? | The development of a communication strategy was added to the project activities to support the upscaling and replication of the interventions. In addition, two new activities will be implemented in 2017 to sustain the project interventions: training on the production of non-rice seeds and awareness-raising against bushfires.
Knowledge Management
How has existing information/data/knowledge been used to inform project development and implementation? What kinds of information/data/knowledge were used? | Following the bad results obtained by SNGF during two planting seasons, the PCU is currently identifying potential plant species to be used in the reforestation interventions. To do so, relevant government institutions and NGOs are being consulted to benefit from their experience, and litterature research is underway.
If learning objectives have been established, have they been met? Please describe. | N/A
Describe any difficulties there have been in accessing or retrieving existing information (data or knowledge) that is relevant to the project. Please provide suggestions for improving access to the relevant data. | No particular difficulties have been encountered regarding access to existing information relevant to the project.
Has the identification of learning objectives contributed to the outcomes of the project? In what ways have they contributed? | N/A

## New Results Tracker
Results Tracker for Adaptation Fund (AF) Projects
Goal: Assist developing-country Parties to the Kyoto Protocol that are particularly vulnerable to the adverse effects of climate change in meeting the costs of concrete adaptation projects and programmes in order to implement climate-resilient measures. Impact: Increased resiliency at the community, national, and regional levels to climate variability and change.
Important: Please read the following guidance document (also posted on the Adaptation Fund website) before entering your data
Link: http://www.adaptation-fund.org/sites/default/files/Results%20Framework%20and%20Baseline%20Guidance%20final.pdf
Adaptation Fund Strategic Results Framework
Project ID | AFB-5060-1111-2G49
Implementing Entity | UNEP
Type of implementing entity | MIE
Country | Madagascar
Region | Africa
Sector | Agriculture
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Impact: Increased resiliency at the community, national, and regional levels to climate variability and change | Core Indicator: No. of beneficiaries |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project
|  | Total | 0 | 0 | 0 | Total | 26.264 | 4.538 | 21.726 | Total | 1200 | 200 | 1000 | Total
|  | % of female beneficiaries | 0% | 0% | 0% | % of female beneficiaries | 33% | 19% | 40% | % of female beneficiaries |  |  |  | % of female beneficiaries
|  | % of Youth beneficiaries | 0% | 0% | 0% | % of Youth beneficiaries | 43% | 15% | 50% | % of Youth beneficiaries |  |  |  | % of Youth beneficiaries
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 1: Reduced exposure to climate-related hazards and threats | Indicator 1: Relevant threat and hazard information generated and disseminated to stakeholders on a timely basis | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness
|  | Total |  |  |  | Total |  |  |  | Total |  |  |  | Total
|  | % of female targeted |  |  |  | % of female targeted |  |  |  | % of female targeted |  |  |  | % of female targeted
Output 1.1 Risk and vulnerability assessments conducted and updated | Indicator 1.1: No. of projects/programmes that conduct and update risk and vulnerability assessments | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
Output 1.2 Targeted population groups covered by adequate risk reduction systems | Core Indicator 1.2: No. of Early Warning Systems | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 2: Strengthened institutional capacity to reduce risks associated with climate-induced socioeconomic and environmental losses | Indicator 2: Capacity of staff to respond to, and mitigate impacts of, climate-related events from targeted institutions increased | Number of staff targeted |  | Sector | Capacity level | Number of staff targeted |  | Sector | Capacity level | Number of staff targeted |  | Sector | Capacity level | Number of staff targeted |  | Sector | Capacity level
|  | Total |  |  |  | Total |  |  |  | Total |  |  |  | Total
|  | % of female targeted |  |  |  | % of female targeted |  |  |  | % of female targeted |  |  |  | % of female targeted
Output 2.1 Strengthened capacity of national and sub-national centres and networks to respond rapidly to extreme weather events | Indicator 2.1.1: No. of staff trained to respond to, and mitigate impacts of, climate-related events | Total staff trained | % of female staff trained | Type |  | Total staff trained | % of female staff trained | Type |  | Total staff trained | % of female staff trained | Type |  | Total staff trained | % of female staff trained | Type
| Indicator 2.1.2: No. of targeted institutions with increased capacity to minimize exposure to climate variability risks | Type | Scale | Sector | Capacity level | Type | Scale | Sector | Capacity level | Type | Scale | Sector | Capacity level | Type | Scale | Sector | Capacity level
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 3: Strengthened awareness and owernship of adaptation and climate risk reduction processes | Indicator 3.1: Increase in application of appropriate adaptation responses | Percentage of targeted population applying adaptation measures |  | Sector |  | Percentage of targeted population applying adaptation measures |  | Sector |  | Percentage of targeted population applying adaptation measures |  | Sector |  | Percentage of targeted population applying adaptation measures |  | Sector
|  | 10% |  | Agriculture |  | 75 |  | Agriculture |  | 25% |  | Agriculture
Output 3: Targeted population groups participating in adaptation and risk reduction awareness activities | Indicator 3.1.1: Percentage of targeted population awareness of predicted adverse impacts of climate change, and of appropriate responses | No. of targeted beneficiaries | % of female participants targeted | Level of awareness |  | No. of targeted beneficiaries | % of female participants targeted | Level of awareness |  | No. of targeted beneficiaries | % of female participants targeted | Level of awareness |  | No. of targeted beneficiaries | % of female participants targeted | Level of awareness
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Target performance at completion
Outcome 4: Increased adaptive capacity within relevant development sector services and infrastructure assets | Indicator 4.1: Increased responsiveness of development sector services to evolving needs from changing and variable climate | Project/programme sector | Geographical scale | Response level |  | Project/programme sector | Geographical scale | Response level |  | Project/programme sector | Geographical scale | Response level |  | Project/programme sector | Geographical scale | Response level
| Core Indicator 4.2: Assets produced, developed, improved or strengthened | Sector | Targeted asset | Changes in asset (quantitative or qualitative) |  | Sector | Targeted asset | Changes in asset (quantitative or qualitative) |  | Sector | Targeted asset | Changes in asset (quantitative or qualitative) |  | Sector | Targeted asset | Changes in asset (quantitative or qualitative)
|  | Agriculture | 2: Physical asset (produced/improved/strenghtened) | 1: Not improved |  | Agriculture | 2: Physical asset (produced/improved/strenghtened) | 4: Mostly Improved |  | Agriculture | 2: Physical asset (produced/improved/strenghtened) | 2: Somewhat improved
|  | Water management | 2: Physical asset (produced/improved/strenghtened) | 1: Not improved |  | Water management | 2: Physical asset (produced/improved/strenghtened) | 4: Mostly Improved |  | Water management | 2: Physical asset (produced/improved/strenghtened) | 1: Not improved
Output 4: Vulnerable development sector services and infrastructure assets strengthened in response to climate change impacts, including variability | Indicator 4.1.1: No. and type of development sector services to respond to new conditions resulting from climate variability and change | Number of services | Type |  | Sector | Number of services | Type |  | Sector | Number of services | Type |  | Sector | Number of services | Type |  | Sector
|  | Baseline information |  |  |  | Baseline information |  |  |  | Performance at mid-term |  |  |  | Target performance at completion
Outcome 5: Increased ecosystem resilience in response to climate change and variability-induced stress | Indicator 5: Ecosystem services and natural resource assets maintained or improved under climate change and variability-induced stress | Natural resource improvement level |  | Sector | Type | Natural resource improvement level |  | Sector | Type | Natural resource improvement level |  | Sector | Type | Natural resource improvement level |  | Sector | Type
Output 5: Vulnerable ecosystem services and natural resource assets strengthned in response to climate change impacts, including variability | Core Indicator 5.1: Natural Assets protected or rehabilitated | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Cultivated land/Agricultural land | 0 | ha rehabilitated | 1: Ineffective | Cultivated land/Agricultural land | 500 | ha rehabilitated | 4: Effective | Cultivated land/Agricultural land | 10 | ha rehabilitated | 2: Partially effective
|  | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Catchment area/Watershed/Aquifer | 0 | ha rehabilitated | 1: Ineffective | Catchment area/Watershed/Aquifer | 4000 | ha rehabilitated | 4: Effective | Forests | 4000 | ha rehabilitated | 1: Ineffective
|  | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Baseline information |  |  |  | Targeted performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 6: Diversified and strengthened livelihoods and sources of income for vulnerable people in targeted areas | Indicator 6.1: Increase in households and communities having more secure access to livelihood assets | No. of targeted households | % of female headed households | Improvement level |  | No. of targeted households | % of female headed households | Improvement level |  | No. of targeted households | % of female headed households | Improvement level |  | No. of targeted households | % of female headed households | Improvement level
| Indicator 6.2: Increase in targeted population's sustained climate-resilient alternative livelihoods | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
|  | 0 | N/A | N/A | N/A | 1000 | 35% | From 10% to 20% | Agriculture | 200 | 25% | From 1% to 5% | Agriculture
|  | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
|  | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
|  | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
Output 6 Targeted individual and community livelihood strategies strengthened in relation to climate change impacts, including variability | Indicator 6.1.1: No. and type of adaptation assets created or strengthened in support of individual or community livelihood strategies | Number of Assets | Type of Assets | Sector | Adaptation strategy | Number of Assets | Type of Assets | Sector | Adaptation strategy | Number of Assets | Type of Assets | Sector | Adaptation strategy | Number of Assets | Type of Assets | Sector | Adaptation strategy
| Core Indicator 6.1.2: Increased income, or avoided decrease in income | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 7: Improved policies and regulations that promote and enforce resilience measures | Indicator 7: Climate change priorities are integrated into national development strategy | Integration level |  |  |  | Integration level |  |  |  | Integration level |  |  |  | Integration level
Output 7:Improved integration of climate-resilience strategies into country development plans | Indicator 7.1: No. of policies introduced or adjusted to address climate change risks | No. of Policies introduced or adjusted | Sector | Scale | Type | No. of Policies introduced or adjusted | Sector | Scale | Type | No. of Policies introduced or adjusted | Sector | Scale | Type | No. of Policies introduced or adjusted | Sector | Scale | Type
| Indicator 7.2: No. of targeted development strategies with incorporated climate change priorities enforced | No. of Development strategies | Regulation |  | Effectiveness | No. of Development strategies | Regulation |  | Effectiveness | No. of Development strategies | Regulation |  | Effectiveness | No. of Development strategies | Regulation |  | Effectiveness

## Old Results Tracker
Results Tracker for Adaptation Fund (AF) Projects
Goal: Assist developing-country Parties to the Kyoto Protocol that are particularly vulnerable to the adverse effects of climate change in meeting the costs of concrete adaptation projects and programmes in order to implement climate-resilient measures. Impact: Increased resiliency at the community, national, and regional levels to climate variability and change.
Important: Please read the following Results Framework and Baseline Guidance (also posted on the Adaptation Fund website) before entering your data
Link: http://www.adaptation-fund.org/sites/default/files/Results%20Framework%20and%20Baseline%20Guidance%20final.pdf
Please select the relevant Fund level Outcome and Output indicators that allign with the project objectives and outcomes
OBJECTIVE 1
Fund Outcome | Please select from dropdown menu below | Fund Outcome Indicator | Please select from dropdown menu below | Target at CEO Endorsement (see Units in next sheet) | Baseline (see Units in next sheet) | Mid-term Results | Terminal Results
Outcome 1: Reduced exposure at national level to climate-related hazards and threats Outcome 2: Strengthened institutional capacity to reduce risks associated with climate-induced socioeconomic and environmental losses Outcome 3: Strengthened awareness and ownership of adaptation and climate risk reduction processes at local level Outcome 4: Increased adaptive capacity within relevant development and natural resource sectors Outcome 5: Increased ecosystem resilience in response to climate change and variability-induced stress Outcome 6: Diversified and strengthened livelihoods and sources of income for vulnerable people in targeted areas Outcome 7: Improved policies and regulations that promote and enforce resilience measures | 4 | 1. Relevant threat and hazard information generated and disseminated to stakeholders on a timely basis 2.1. No. and type of targeted institutions with increased capacity to minimize exposure to climate variability risks 2.2. Number of people with reduced risk to extreme weather events 3.1. Percentage of targeted population aware of predicted adverse impacts of climate change, and of appropriate responses 3.2. Modification in behavior of targeted population 4.1. Development sectors' services responsive to evolving needs from changing and variable climate 4.2. Physical infrastructure improved to withstand climate change and variability-induced stress 5. Ecosystem services and natural assets maintained or improved under climate change and variability-induced stress 6.1. Percentage of households and communities having more secure (increased) access to livelihood assets 6.2. Percentage of targeted population with sustained climate-resilient livelihoods 7. Climate change priorities are integrated into national development strategy | 4.2 | 4 | 2 | TBC
Fund Output | Please select from dropdown menu below | Fund Output Indicator | Please select from dropdown menu below | Target at CEO Endorsement (see Units in next sheet) | Baseline (see Units in next sheet) | Mid-term Results | Terminal Results
Output 1: Risk and vulnerability assessments conducted and updated at a national level Output 2.1: Strengthened capacity of national and regional centres and networks to respond rapidly to extreme weather events Output 2.2: Targeted population groups covered by adequate risk reduction systems Output 3: Targeted population groups participating in adaptation and risk reduction awareness activities Output 4: Vulnerable physical, natural, and social assets strengthened in response to climate change impacts, including variability Output 5: Vulnerable physical, natural, and social assets strengthened in response to climate change impacts, including variability Output 6: Targeted individual and community livelihood strategies strengthened in relation to climate change impacts, including variability Output 7: Improved integration of climate-resilience strategies into country development plans | 4 | 1.1. No. and type of projects that conduct and update risk and vulnerability assessments 1.2. Development of early warning systems 2.1.1. No. of staff trained to respond to, and mitigate impacts of, climate-related events 2.1.2. Capacity of staff to respond to, and mitigate impacts of, climate-related events from targeted institutions increased 2.2.1. Percentage of population covered by adequate risk-reduction systems 2.2.2. No. of people affected by climate variability 3.1 No. and type of risk reduction actions or strategies introduced at local level 3.2 No. of news outlets in the local press and media that have covered the topic 4.1. No. and type of health or social infrastructure developed or modified to respond to new conditions resulting from climate variability and change (by type) 4. 2. No. of physical assets strengthened or constructed to withstand conditions resulting from climate variability and change (by asset types) 5. No. and type of natural resource assets created, maintained or improved to withstand conditions resulting from climate variability and change (by type of assets) 6.1. No. and type of adaptation assets (physical as well as knowledge) created in support of individualor community-livelihood strategies 6.2. Type of income sources for households generated under climate change scenario 7.1. No., type, and sector of policies introduced or adjusted to address climate change risks 7.2. No. or targeted development strategies with incorporated climate change priorities enforced | 4.2 | Irrigation and drainage infrastructure is improved in 3 sites as follows: Manakambahiny: 35 km of primary canals cured, dredged, and maintained,; Bemaintso: The dam is drained and dredged; 14 km of primary canals and 21 km of secondary canals are cured, dredged, and maintained; Ambohijanahary: The dam at Anony is rehabilitated, primary water control valves are repaired; 13 km of primary canal are drained, dredged, and repaired; and primary canal is extended to irrigate 600 ha of additional rice fields. | 0 physical assets are made resilient to impacts of climate change | TBC
OBJECTIVE 2
Fund Outcome | Please select from dropdown menu below | Fund Outcome Indicator | Please select from dropdown menu below | Target at CEO Endorsement | Baseline | Mid-term Results | Terminal Results
Outcome 1: Reduced exposure at national level to climate-related hazards and threats Outcome 2: Strengthened institutional capacity to reduce risks associated with climate-induced socioeconomic and environmental losses Outcome 3: Strengthened awareness and ownership of adaptation and climate risk reduction processes at local level Outcome 4: Increased adaptive capacity within relevant development and natural resource sectors Outcome 5: Increased ecosystem resilience in response to climate change and variability-induced stress Outcome 6: Diversified and strengthened livelihoods and sources of income for vulnerable people in targeted areas Outcome 7: Improved policies and regulations that promote and enforce resilience measures | 5 | 1. Relevant threat and hazard information generated and disseminated to stakeholders on a timely basis 2.1. No. and type of targeted institutions with increased capacity to minimize exposure to climate variability risks 2.2. Number of people with reduced risk to extreme weather events 3.1. Percentage of targeted population aware of predicted adverse impacts of climate change, and of appropriate responses 3.2. Modification in behavior of targeted population 4.1. Development sectors' services responsive to evolving needs from changing and variable climate 4.2. Physical infrastructure improved to withstand climate change and variability-induced stress 5. Ecosystem services and natural assets maintained or improved under climate change and variability-induced stress 6.1. Percentage of households and communities having more secure (increased) access to livelihood assets 6.2. Percentage of targeted population with sustained climate-resilient livelihoods 7. Climate change priorities are integrated into national development strategy | 5 | 4 - Mostly Effective. Change in overall land area covered by forests (i.e. net reforestation) of at least 50km2 across the combined 3 municipalities. | 2 | TBC
Fund Output | Please select from dropdown menu below | Fund Output Indicator | Please select from dropdown menu below | Target at CEO Endorsement | Baseline | Mid-term Results | Terminal Results
Output 1: Risk and vulnerability assessments conducted and updated at a national level Output 2.1: Strengthened capacity of national and regional centres and networks to respond rapidly to extreme weather events Output 2.2: Targeted population groups covered by adequate risk reduction systems Output 3: Targeted population groups participating in adaptation and risk reduction awareness activities Output 4: Vulnerable physical, natural, and social assets strengthened in response to climate change impacts, including variability Output 5: Vulnerable physical, natural, and social assets strengthened in response to climate change impacts, including variability Output 6: Targeted individual and community livelihood strategies strengthened in relation to climate change impacts, including variability Output 7: Improved integration of climate-resilience strategies into country development plans | 5 | 1. Relevant threat and hazard information generated and disseminated to stakeholders on a timely basis 2.1. No. and type of targeted institutions with increased capacity to minimize exposure to climate variability risks 2.2. Number of people with reduced risk to extreme weather events 3.1. Percentage of targeted population aware of predicted adverse impacts of climate change, and of appropriate responses 3.2. Modification in behavior of targeted population 4.1. Development sectors' services responsive to evolving needs from changing and variable climate 4.2. Physical infrastructure improved to withstand climate change and variability-induced stress 5. Ecosystem services and natural assets maintained or improved under climate change and variability-induced stress 6.1. Percentage of households and communities having more secure (increased) access to livelihood assets 6.2. Percentage of targeted population with sustained climate-resilient livelihoods 7. Climate change priorities are integrated into national development strategy | 5 | At least 5000 ha reforested across 3 districts | Limited or no reforestation activities in target areas | TBC
OBJECTIVE 3
Fund Outcome | Please select from dropdown menu below | Fund Outcome Indicator | Please select from dropdown menu below | Target at CEO Endorsement | Baseline | Mid-term Results | Terminal Results
Outcome 1: Reduced exposure at national level to climate-related hazards and threats Outcome 2: Strengthened institutional capacity to reduce risks associated with climate-induced socioeconomic and environmental losses Outcome 3: Strengthened awareness and ownership of adaptation and climate risk reduction processes at local level Outcome 4: Increased adaptive capacity within relevant development and natural resource sectors Outcome 5: Increased ecosystem resilience in response to climate change and variability-induced stress Outcome 6: Diversified and strengthened livelihoods and sources of income for vulnerable people in targeted areas Outcome 7: Improved policies and regulations that promote and enforce resilience measures |  | 1. Relevant threat and hazard information generated and disseminated to stakeholders on a timely basis 2.1. No. and type of targeted institutions with increased capacity to minimize exposure to climate variability risks 2.2. Number of people with reduced risk to extreme weather events 3.1. Percentage of targeted population aware of predicted adverse impacts of climate change, and of appropriate responses 3.2. Modification in behavior of targeted population 4.1. Development sectors' services responsive to evolving needs from changing and variable climate 4.2. Physical infrastructure improved to withstand climate change and variability-induced stress 5. Ecosystem services and natural assets maintained or improved under climate change and variability-induced stress 6.1. Percentage of households and communities having more secure (increased) access to livelihood assets 6.2. Percentage of targeted population with sustained climate-resilient livelihoods 7. Climate change priorities are integrated into national development strategy
Fund Output | Please select from dropdown menu below | Fund Output Indicator | Please select from dropdown menu below | Target at CEO Endorsement | Baseline | Mid-term Results | Terminal Results
Output 1: Risk and vulnerability assessments conducted and updated at a national level Output 2.1: Strengthened capacity of national and regional centres and networks to respond rapidly to extreme weather events Output 2.2: Targeted population groups covered by adequate risk reduction systems Output 3: Targeted population groups participating in adaptation and risk reduction awareness activities Output 4: Vulnerable physical, natural, and social assets strengthened in response to climate change impacts, including variability Output 5: Vulnerable physical, natural, and social assets strengthened in response to climate change impacts, including variability Output 6: Targeted individual and community livelihood strategies strengthened in relation to climate change impacts, including variability Output 7: Improved integration of climate-resilience strategies into country development plans |  | 1.1. No. and type of projects that conduct and update risk and vulnerability assessments 1.2. Development of early warning systems 2.1.1. No. of staff trained to respond to, and mitigate impacts of, climate-related events 2.1.2. Capacity of staff to respond to, and mitigate impacts of, climate-related events from targeted institutions increased 2.2.1. Percentage of population covered by adequate risk-reduction systems 2.2.2. No. of people affected by climate variability 3.1 No. and type of risk reduction actions or strategies introduced at local level 3.2 No. of news outlets in the local press and media that have covered the topic 4.1. No. and type of health or social infrastructure developed or modified to respond to new conditions resulting from climate variability and change (by type) 4. 2. No. of physical assets strengthened or constructed to withstand conditions resulting from climate variability and change (by asset types) 5. No. and type of natural resource assets created, maintained or improved to withstand conditions resulting from climate variability and change (by type of assets) 6.1. No. and type of adaptation assets (physical as well as knowledge) created in support of individualor community-livelihood strategies 6.2. Type of income sources for households generated under climate change scenario 7.1. No., type, and sector of policies introduced or adjusted to address climate change risks 7.2. No. or targeted development strategies with incorporated climate change priorities enforced
OBJECTIVE 4
Fund Outcome | Please select from dropdown menu below | Fund Outcome Indicator | Please select from dropdown menu below | Target at CEO Endorsement | Baseline | Mid-term Results | Terminal Results
Outcome 1: Reduced exposure at national level to climate-related hazards and threats Outcome 2: Strengthened institutional capacity to reduce risks associated with climate-induced socioeconomic and environmental losses Outcome 3: Strengthened awareness and ownership of adaptation and climate risk reduction processes at local level Outcome 4: Increased adaptive capacity within relevant development and natural resource sectors Outcome 5: Increased ecosystem resilience in response to climate change and variability-induced stress Outcome 6: Diversified and strengthened livelihoods and sources of income for vulnerable people in targeted areas Outcome 7: Improved policies and regulations that promote and enforce resilience measures |  | 1. Relevant threat and hazard information generated and disseminated to stakeholders on a timely basis 2.1. No. and type of targeted institutions with increased capacity to minimize exposure to climate variability risks 2.2. Number of people with reduced risk to extreme weather events 3.1. Percentage of targeted population aware of predicted adverse impacts of climate change, and of appropriate responses 3.2. Modification in behavior of targeted population 4.1. Development sectors' services responsive to evolving needs from changing and variable climate 4.2. Physical infrastructure improved to withstand climate change and variability-induced stress 5. Ecosystem services and natural assets maintained or improved under climate change and variability-induced stress 6.1. Percentage of households and communities having more secure (increased) access to livelihood assets 6.2. Percentage of targeted population with sustained climate-resilient livelihoods 7. Climate change priorities are integrated into national development strategy
Fund Output | Please select from dropdown menu below | Fund Output Indicator | Please select from dropdown menu below | Target at CEO Endorsement | Baseline | Mid-term Results | Terminal Results
Output 1: Risk and vulnerability assessments conducted and updated at a national level Output 2.1: Strengthened capacity of national and regional centres and networks to respond rapidly to extreme weather events Output 2.2: Targeted population groups covered by adequate risk reduction systems Output 3: Targeted population groups participating in adaptation and risk reduction awareness activities Output 4: Vulnerable physical, natural, and social assets strengthened in response to climate change impacts, including variability Output 5: Vulnerable physical, natural, and social assets strengthened in response to climate change impacts, including variability Output 6: Targeted individual and community livelihood strategies strengthened in relation to climate change impacts, including variability Output 7: Improved integration of climate-resilience strategies into country development plans |  | 1.1. No. and type of projects that conduct and update risk and vulnerability assessments 1.2. Development of early warning systems 2.1.1. No. of staff trained to respond to, and mitigate impacts of, climate-related events 2.1.2. Capacity of staff to respond to, and mitigate impacts of, climate-related events from targeted institutions increased 2.2.1. Percentage of population covered by adequate risk-reduction systems 2.2.2. No. of people affected by climate variability 3.1 No. and type of risk reduction actions or strategies introduced at local level 3.2 No. of news outlets in the local press and media that have covered the topic 4.1. No. and type of health or social infrastructure developed or modified to respond to new conditions resulting from climate variability and change (by type) 4. 2. No. of physical assets strengthened or constructed to withstand conditions resulting from climate variability and change (by asset types) 5. No. and type of natural resource assets created, maintained or improved to withstand conditions resulting from climate variability and change (by type of assets) 6.1. No. and type of adaptation assets (physical as well as knowledge) created in support of individualor community-livelihood strategies 6.2. Type of income sources for households generated under climate change scenario 7.1. No., type, and sector of policies introduced or adjusted to address climate change risks 7.2. No. or targeted development strategies with incorporated climate change priorities enforced

## Old Units for Indicators
Fund Outcome Indicator Units
1. Generation of relevant data, Stakeholders, and Timeliness 2.1. Include both qualitative and quantitative measures of capacity level within targeted institutions 2.2. Number (men and women and other vulnerable groups) 3.1. Use scale from 1 to 5: 5: Fully aware 4: Mostly aware 3: Partially aware 2: Partially not aware 1: Aware of neither predicted adverse impacts of climate change nor of appropriate responses 3.2. Use scale from 1 to 5: 5: All 4: Almost all 3: Half 2: Some 1: None 4.1. Summarize in an overall scale (1-5): 5: Highly responsive (All defined elements ) 4: Mostly responsive (Most defined elements) 3: Moderately responsive (Some defined elements) 2: Partially responsive (Lacks most elements) 1: Non responsive (Lacks all elements ) 4.2. Summarize in an overall scale (1-5): 5: Fully improved 4: Mostly Improved 3: Moderately improved 2: Somewhat improved 1: Not improved 5. Depends on the targeted natural asset: Biological (species): measure through changes in population numbers (dynamics, structure, etc.) Land: measure changes in hectares. Baseline data will be necessary to estimate the change. Supporting indicators baseline and target (as well as contextual information) are needed such as the following: Farmers adopting recommended technologies, Ha. of land improved, Average deforestation rate Etc. Use scale from 1 to 5. 5: Very effective (All elements are present) 4: Effective (Most elements are present) 3: Moderately effective (Some elements are present) 2: Partially effective (Most elements are not present) 1: Ineffective (No elements are present) 6.1. Summarize in an overall scale (1-5): 5: Very high improvement 4: High improvement 3: Moderate improvement 2: Limited improvement 1: No improvement 6.2. Household income by source of livelihood in project area (USD) prior and post project intervention 7. Summarize in an overall scale (1-5). 5: All (Fully integrated) 4: Most 3: Some 2: Most not integrated 1: None
Fund Output Indicator Units
1.1. Number, sector(s) and level(s) of projects or interventions in separate fields of monitoring plan 1.2. Number 2.1.1. Number of staff (male/female) of targeted institutions: a. Obtain baseline information: total number of staff from targeted institutions b. Define target 2.1.2. Number of staff (male/female) of targeted institutions: a. Obtain baseline information: total number of staff from targeted institutions b. Define target: needs to be defined by project proponents 2.2.1. Quantitative: Percentage (includes women – and other vulnerable groups – and men). Qualitative: Adequacy: include direct analysis of major areas; adequacy/effectiveness of systems or analysis of perceptions of populations and institutions. 2.2.2. Number (broken down by gender and, if possible, by vulnerable groups defined in the area of intervention) of people 3.1. Number and type (in separate columns) at local level. 3.2. Number 4.1. Number and type 4. 2. Number and type (entered in separate columns) 5. Number of interventions by type of natural asset and intervention 6.1. Number and type (in separate columns of monitoring plan) 6.2. Income sources per household; description of income source and number of households. 7.1. Number/Sector 7.2. Number; Effectiveness (see previous indicator) through enforcement level.