## Overview
Project Performance Report (PPR)
| Period of Report (Dates) | October 2013 - October 2014
| Project Title: | Promoting climate resilience in the rice sector through pilot investments in Alaotra Mangoro Region
| Project Summary: | In the framework of the implementation of its NAPA, the Government of the Republic of Madagascar has recieved support from the Adaptation Fund for the implementation of the project « PROMOTING CLIMATE RESILIENCE IN THE RICE SECTOR THROUGH PILOT INVESTMENTS IN ALAOTRA-MANGORO REGION », which seeks to transform the rice sub-sector towards resilience to the impacts of climate change. The project is comprised of three components 1) strengthening of technical and scientific capacities, 2) implementation of a rice production cycle that is resilient and adapted and 3)leveraging policy change in the rice sector. The project is implemented in the Alaotra-Mangoro region, the primary rice production area in Madagascar, in three pilot districts. The project is implemented through the Ministry of Environment and Forests and works at the local level with producers and local partners, along with decentralised ministries and regional technical partners.
|  |  | Countries | Project Type: |  | GEF Focal Area: | GEF 4 Focal Areas | GEF 2 / 3 Operational Programme: | Overall Rating of the project in the evaluation by the project evaluator: | GEF-4 Focal Area Strategic Program: | GEF-3 Focal Area Strategic Program:
| Database Number: | AFB-5060-1111-2G49 | Afghanistan | FP | Yes | Biodiversity | 1 | 1 | U | BD-SP1-PA Financing | 1: Arid & semi-arid ecosystems
Implementing Entity (IE) [name]: |  | UNEP | Albania | MSP | No | Climate Change Adaptation | 2 | 2 | S | BD-SP2-Marine PA | 2: Coastal, marine & freshwater ecosystems
| Type of IE: | MIE | Algeria | EA |  | Climate Change Mitigation | 3 | 3 | MU | BD-SP3-PA Networks | 3: Forest ecosystems
| Country(ies): | MADAGASCAR | Angola |  |  | International Waters | 5 | 5 | Good | BD-SP5-Markets | 13: Conservation and Sustainable Use of Biological Diversity Important to Agriculture
Relevant Geographic Points (i.e. cities, villages, bodies of water): |  | The Alaotra Mangoro region is located in the center-East of Madagascar. The region covers 33 054 Km². and is comprised of (05) Districts themselves sub-divided into79 communes. The regional capital is t Ambatondrazaka, approximately 250 Km from Antananarivo. The project is working in the three districts of Andilamena (8 communes), Amparafaravola (20 communes), and Ambatondrazaka (20 communes). The Alaotra Mangoro contains many bodies of water and rivers, Lake Alaotra being the most important lake in the region, with an area of 20 000 ha. | Argentina |  |  | Multiple Focal Area |  |  |  | BD-SP7-Invasive Alien Species(IAS) | 6: Promoting the adoption of renewable energy by removing barriers and reducing implementation costs
[8 empty] | CC-SP2- Industrial EE | 8: Waterbody based operational program
| Project Milestones | [6 empty] | CC-SP3-RE,CC-SP4-Biomass | 9: Integrated Land and Water multiple focal area
| Milestone |  | Bahamas | [6 empty] | CC-SP5-Transport | 10: Contaminants based operational program
AFB Approval Date: |  | 2011-12-14
IE-AFB Agreement Signature Date: | [8 empty] | CC-SP6-LULUCF | 12: Integrated Ecosystem Management
Start of Project/Programme: |  | 2012-10-01 | [6 empty] | Cross cutting capacity building | 14: Persistent Organic Pollutants
Mid-term Review Date (if planned): |  | 2015-07-01
| Terminal Evaluation Date: | April-May 2017
|  | List documents/ reports/ brochures / articles that have been prepared about the project. | Cyprus
|  | Interim report on the comparative analysis of rice cultivation techniques; interim report on technical guidelines for MIRR; final report on Rice Resilient Model on Climate Change (IRRI); report on training sessions on Oryza 2000 and DSSAT; interim report on the pre-selection of adapted varities; final report on update fertilisation formulas, guidelines and packets; interim report on locally available fertilizer resources; final report on local level water quality; final report on rehabilitation of storage facilities; Communication strategy; interim report on hydrological model, flyers on project information and on MIRR. | Czech Republic
List the Website address (URL) of project. |  |  | Democratic People's Republic of Korea
|  | www.mef.gov.mg | Democratic Republic of the Congo
Denmark
| Project contacts: |  | Djibouti
National Project Manager/Coordinator |  |  | Dominica
| Name: | RAZANAMIHARISOA Jane Alice | Dominican Republic
| Email: | jrazanamiharisoa@ymail.com | Ecuador
| Date: | 2013-12-10 | Egypt
| Government DA |  | El Salvador
| Name: | Germain RANDRIASANDRATANA, Ministry of Environment and Forests - Directorate of Climate Change | Equatoral Guinea
| Email: | randriasandratana@yahoo.fr | Eritrea
| Date: | 2013-12-10 | Estonia
| Implementing Entity |  | Ethiopia
| Name: | Lars Christiansen, UNEP Task Manager | Fiji
| Email: | lachr@dtu.dk | Finland
| Date: | 2013-12-16 | France
| Executing Agency |  | Gambia
| Name: |  | Georgia
| Email: |  | Germany
| Date: |  | Ghana
| Executing Agency |  | Greece
| Name: |  | Grenada
| Email: |  | Guatemala
| Date: |  | Guinea
| Executing Agency |  | Guinea Bissau
| Name: |  | Guyana
| Email: |  | Haiti
| Date: |  | Honduras
Hungary
Iceland
India
Indonesia
Iran (Islamic Republic of)
Iraq
Ireland
Israel
Italy
Jamaica
Japan
Jordan
Kazakhstan
Kenya
Kiribati
Kuwait
Kyrgyzstan
Lao People’s Democratic Republic
Latvia
Lebanon
Lesotho
Liberia
Libyan Arab Jamahiriya
Liechtenstein
Lithuania
Luxembourg
Madagascar
Malawi
Malaysia
Maldives
Mali
Malta
Marshall Islands
Mauritania
Mauritius
Mexico
Micronesia, Federated States of
Monaco
Mongolia
Montenegro
Morocco
Mozambique
Myanmar
Namibia
Nauru
Nepal
Netherlands
New Zealand
Nicaragua
Niger
Nigeria
Norway
Oman
Pakistan
Palau
Panama
Papua New Guinea
Paraguay
Peru
Philippines
Poland
Portugal
Qatar
Republic of Korea
Republic of Moldova
Romania
Russian Federation
Rwanda
Saint Kitts and Nevis
Saint Lucia
Saint Vincent and the Grenadines
Samoa
San Marino
Sao Tome and Principe
Saudi Arabia
Senegal
Serbia
Seychelles
Sierra Leone
Singapore
Slovakia
Slovenia
Solomon Islands
Somalia
South Africa
Spain
Sri Lanka
Sudan
Suriname
Swaziland
Sweden
Switzerland
Syrian Arab Republic
Tajikistan
Thailand
The former Yugoslav Republic of Macedonia
Timor-Leste
Togo
Tonga
Trinidad and Tobago
Tunisia
Turkey
Turkmenistan
Tuvalu
Uganda
Ukraine
United Arab Emirates
United Kingdom of Great Britain and Northern Ireland
United Republic of Tanzania
United States of America
Uruguay
Uzbekistan
Vanuatu
Venezuela, Bolivarian Republic of
Viet Nam
Yemen
Zambia
Zimbabwe

## FinancialData
Financial information: cumulative from project start to September 30 2014
DISBURSEMENT OF AF GRANT FUNDS
How much of the total AF grant as noted in Project Document plus any project preparation grant has been spent to date?
Estimated cumulative total disbursement as of 30 September 2014 |  | 455217
Add any comments on AF Grant Funds. (word limit=200)
EXPENDITURE DATA
List ouput and corresponding amount spent for the current reporting period (Oct 1 2013 - 30 sept 2014) |  | Output | AMOUNT
|  | Output 1.1.1 Best Available Technologies and Integrated Resilient Rice Model (Modèle Intégré de Riziculture Résiliente - MIRR) selected and publicized | 78656
|  | 1.2.1 Crop models are available for rice vulnerability mapping | 20153
|  | 1.2.2 Updated, dynamic agricultural calendars and climate early warnings taking into account current and projected variability disseminated to local population | 4532
|  | 1.2.3 Agricultural extension staff trained on climate risk management in an agro-ecosystem context | 0
|  | 2.1.1 climate resilient rice varieties selected through participatory field testing | 15000
2.1.2 An operational multiplication and dissemination scheme for adapted seed varieties
|  | 2.1.3 Updated fertilisation guidelines according to best available standards and taking climate conditions into consideration | 52500
|  | 2.1.4 Integrated pest management is implemented | 0
|  | 2.1.5 Water efficiency, management and conservation technologies and infrastructures are implemented | 0
|  | 2.2.1 Best available land preparation, production and harvesting techniques disseminated to reduce deforestation, maintain soil fertility and integrity, and to provide adequate growing conditions | 0
|  | 2.2.2 Watershed rehabilitation in productive landscapes introduced, including through reforestation and adaptation of agroforestry practices | 80600
2.2.3 Soil conservation and livestock management techniques adapted to topography and landscape in light of future climate conditions
|  | 2.2.4 Revitalization of producer’s cooperatives and water user associations for collaborative natural resources allocations (e.g. land and water) and management | 249
|  | 2.2.5 Water quality assessments | 6000
|  | 2.3.1 Increased utilization of rice by-product especially rice straw | 0
|  | 2.3.2 Post-harvest storage facilities with phytosanitary control, serving as trading points and markets | 9800
|  | 3.1.1 gaps and possible maladaptations in the current rice policy are identifed and recommendations on upscaling project outcomes towards rice policy reform are made | 0
|  | 3.2.1 a report on best practices and lessons learned for rice adaptation in madagascar | 0
|  | 3.2.2 A strategy for communicating information on adaptation techniques to farmers is implemented | 2800
Cross-cutting costs Component 1
|  | Cross-cutting costs Component 2 | 85500
|  | Cross-cutting costs Component 3 | 840
|  | Project operations/Execution costs | 98587
|  | TOTAL | 455217
PLANNED EXPENDITURE SCHEDULE
List outputs planned and corresponding projected cost for the upcoming reporting period | Output | ITEM | PROJECTED COST | Est. Completion Date
| 1.1.1 Best Available Technologies and Integrated Resilient Rice Model (Modèle Intégré de Riziculture Résiliente - MIRR) selected and publicized | Publication services | 10000 | Q4 2015
| 1.2.1 Crop models are available for rice vulnerability mapping | Data acquisition costs | 1000 | Q3 2015
|  | national agriculture and rice experts | 12000 | Q3 2015
|  | Sub-contract mapping services | 10000 | Q3 2016
| 1.2.2 Updated, dynamic agricultural calendars and climate early warnings taking into account current and projected variability disseminated to local population | National agriculture and rice experts | 16000 | Q1 2015
|  | group training (updated calendars and rice models) | 20000 | Q3 2015
|  | international crm expert | 25000 | Q4 2015
|  | National Consultant meteorologist | 24000 | Q4 2017
|  | sub-contract with National Radio | 15000 | Q4 2017
| 1.2.3 Agricultural extension staff trained on climate risk management in an agro-ecosystem context | international crm expert | 30000 | Q4 2015
|  | national extension specialists | 40000 | Q4 2015
|  | Climate Risk Management workshop | 20000 | Q4 2015
|  | national agro-forestry experts | 30000 | Q4 2015
| Cross-cutting Component costs | Project Coordinator | 3600 | Q4 2017
| 2.1.1 climate resilient rice varieties selected through participatory field testing | agricultural inputs (seeds, fertilizers, land and tools) | 96504 | Q3 2015
|  | sub-contract with FOFIFA | 60000 | Q3 2015
|  | national agriculture researchers | 15000 | Q3 2015
| 2.1.2 An operational multiplication and dissemination scheme for adapted seed varieties | agricultural inputs | 20000 | Q2 2016
|  | sub-contract with CALA (pre-base seeds) | 138000 | Q2 2016
| 2.1.3 Updated fertilisation guidelines according to best available standards and taking climate conditions into consideration | national agriculture/fertilisation experts | 18000 | Q3 2014
|  | National soil science experts | 6000 | Q3 2015
|  | Sub-contract with CALA for soil quality analysis | 20000 | Q3 2015
|  | sub-contract with BIOTECH Madagascar (for Taroka) | 35400 | Q2 2016
|  | sub-contract with GUANOMAD (for Guano) | 5000 | Q2 2016
| 2.1.4 Integrated pest management is implemented | N_A
| 2.1.5 Water efficiency, management and conservation technologies and infrastructures are implemented | sub-contract with water engineering firm | 150000 | Q2 2016
|  | water management and infrastructure specialist | 4000 | Q2 2016
|  | sub-contract with civil engineering firm | 125000 | Q4 2016
|  | water management and infrastructure specialist | 6000 | Q4 2016
|  | water management and infrastructure specialist | 5000 | Q4 2016
| 2.2.1 Best available land preparation, production and harvesting techniques disseminated to reduce deforestation, maintain soil fertility and integrity, and to provide adequate growing conditions | Local MIRR training | 18000 | Q1 2016
|  | national riziculture experts | 6000 | Q2 2016
|  | national riziculture experts | 10000 | Q3 2016
|  | national agro-forestry expert | 5000 | Q1 2017
|  | sub-contract for extension services | 3000 | Q1 2017
| 2.2.2 Watershed rehabilitation in productive landscapes introduced, including through reforestation and adaptation of agroforestry practices | sub-contract Ministry of forests (SNGF) | 52893.75 | Q4 2016
|  | Sub-contract with Commune Manakambahiny | 15000 | Q4 2016
|  | Sub-contract commune bemaintso | 15000 | Q4 2016
|  | Sub-contract commune Ambohijanahary | 15000 | Q4 2016
|  | Sub-contract for SLM Community Training | 35000 | Q4 2016
| 2.2.3 Soil conservation and livestock management techniques adapted to topography and landscape in light of future climate conditions | Livestock expert | 23000 | Q4 2015
| 2.2.4 Revitalization of producer’s cooperatives and water user associations for collaborative natural resources allocations (e.g. land and water) and management | Water user Association training workshop | 10000 | Q1 2016
|  | Community Based Natural Resources management expert | 16000 | Q2 2017
|  | equipment and office supplies for WUG | 2000 | Q2 2017
| 2.2.5 Water quality assessments | Sub-contract Ministry of water | 15000 | Q4 2017
| 2.3.1 Increased utilization of rice by-product especially rice straw | N-A
| 2.3.2 Post-harvest storage facilities with phytosanitary control, serving as trading points and markets | economist | 4200 | Q4 2014
|  | sub-contract private sector firm | 121411 | Q4 2015
|  | training on community-managed reserves | 10000 | Q3 2015
|  | National Consultant - Community managed storage | 12000 | Q3 2015
|  | International consulatant - Phytosanitary standards and climate change | 30000 | Q3 2015
| Cross-cutting component costs | Chief Technical Advisor (CTA) | 28000 | Q4 2017
|  | CTA travel | 6000 | Q4 2017
|  | Local Technicians (3) | 7200 | Q4 2017
|  | Office supplies for Local Technicians (3) | 525 | Q4 2017
|  | Travel costs for regional directorates | 3750 | Q4 2017
|  | Operating costs for regional directorates (fuel and expendables) | 3469 | Q4 2017
|  | Driver | 3300 | Q4 2017
|  | Project Coordinator | 3600 | Q4 2017
|  | Vehicles (incl. 3 motorcycles) and maintenance | 2417 | Q4 2017
| 3.1.1 gaps and possible maladaptations in the current rice policy are identifed and recommendations on upscaling project outcomes towards rice policy reform are made | N-A
| 3.2.1 a report on best practices and lessons learned for rice adaptation in madagascar | N-A
| 3.2.2 A strategy for communicating information on adaptation techniques to farmers is implemented | National Rural communication specialist | 7320 | Q4 2017
|  | awareness raising Meetings and workshops | 16000 | Q4 2017
| Cross-cutting component costs | Project Coordinator | 3600 | Q4 2017
| 4. Project/Programme Execution cost | project coordinator | 7200 | Q4 2017
|  | national financial manager | 15000 | Q4 2017
|  | administrative support | 9996 | Q4 2017
|  | Travel for PM | 7194 | Q4 2017
|  | Office equipment and expendables (PCU) | 3000 | Q4 2017
|  | Communication, translation and printing costs | 3000 | Q4 2017
|  | mid-term evaluation | 35000 | Q4 2015
|  | inception and steering meetings | 2000 | Q4 2017
|  | TOTAL | 1546579.75
ACTUAL CO-FINANCING (If the MTR or TE have not been undertaken this reporting period, DO NOT report on actual co-financing.)
How much of the total co-financing as committed in the Project Document has actually been realized?
Estimated cumulative actual co-financing as verified during Mid-term Review (MTR) or Terminal Evaluation (TE).
Add any comments on actual co-financing in particular any issues related to the realization of in-kind, grant, credits, loans, equity, non-grant instruments and other types of co-financing. (word limit=200)

## Procurement (hidden)
PROCUREMENT DATA
Please provide information for all contracts over $2,500 USD
Please provide the number of contracts under $2,500, signed during this reporting period: |  |  | 1
LIST OF CONTRACTS
List all contracts related to the project/program with signature dates
Contract Type | Agency / Contracted party | Contract Value/Amount (USD) | Signature Date | Contract Number | budget code | Payment to Date | Remaining Balance
Long-term Contract | Mme Jane Razanamiharisoa | 90000 | 2012-sep-08 | 01/12 | 1101 | 36000 | 54000
Long-term Contract | Mr. Tahiry Herilalaina | 75000 | 2012-sep-08 | 02/12 | 1102 | 30000 | 45000
Long-term Contract | Mr. Marcellin Lalason | 50000 | 2012-sep-08 | 03/12 | 1301 | 30000 | 20000
Individual Consultancy contract | Mme JOANA Talafré | 120000 | 2013-02-20 | 04/13 | 1212 | 33496 | 86504
Consultancy contract | Gaétan QUESNE and Henri Rakotobe | 35792 | 2013-02-27 | 05/13 | 5501 | 35792 | 0
Consultancy Contract | Madame RAKOTOARISOA Jacqueline and Monsieur Rabeson Raymond | 60000 | 2013-06-26 | 06/13 | 1201 | 42000 | 18000
Contract amendment with additional costs | Madame RAKOTOARISOA Jacqueline and Monsieur Rabeson Raymond | 25350 | 2014-09-05 | 06/13 amendment | 1201 | 12675 | 12675
Individual Consultancy contract | Madame RASOAFALIMANANA Mbolarinosy | 50000 | 2013-06-26 | 07/13 | 1207 | 35000 | 15000
Individual Consultancy contract | Monsieur Rabeson Raymond | 6000 | 2013-09-12 | 07bis/13 | 1201 | 3000 | 3000
Individual Consultancy contract | Mr. Ratsimbazafy Tiana | 15000 | 2014-07-23 | 08/14 | 1230 | 10500 | 4500
Individual Consultancy contract | Monsieur Andrianirina Michelliarson | 15000 | 2014-07-23 | 09/14 | 1215 | 6000 | 9000
Individual Consultancy contract | Monsieur Rakotoarison Levy | 60000 | 20 aout 14 | 10/13 | 1209 | 42000 | 18000
Individual Consultancy contract | Mr. Randrianoro Désiré | 1000 | 2014-02-04 | 11/14 | 5401 | 0 | 1000
Individual Consultancy contract | Mr. Ratsimbazafy Jean-Pierre | 5000 | 2014-03-17 | 12 bis/14 | 1201 | 1620 | 3380
Individual Consultancy contract | Razafindrakoto Helison Romuald | 25000 | 2013-03-07 | 12/14 | 1204 | 7500 | 17500
Individual Consultancy contract | Andriamalantomanga Tsiory Dimbimalala | 19000 | 2014-03-07 | 13/14 | 1225 | 2800 | 16200
Individual Consultancy contract | Rabemanantsoa Heritiana Adrianala | 14000 | 2014-03-17 | 14/14 | 1219 | 9800 | 4200
Individual Consultancy contract | Ranaivojaona Harinomejanahary Voahanginirina | 9000 | 2014-03-28 | 15/14 | 1227 | 1200 | 7800
Individual Consultancy contract | Rasamison Jules | 9000 | 2014-03-28 | 16/14 | 1227 | 1200 | 7800
Individual Consultancy contract | Randriafiraisampiremena Jules | 9000 | 2014-03-28 | 17/14 | 1227 | 1200 | 7800
MOU | Silo Nationale des Graines Forestieres (SNGF) | 201500 | 2014-04-25 | MOU-1 | 2102 | 80600 | 120900
LOng-term Contract | RAMAROSOA Erick Lauret | 11550 | 2014-07-25 | 20/14 | 1228 | 275 | 11275
MOU | CALA | 180000 | 2014-09-08 | MOU-2 | 2309 |  | 180000
MOU | International Rice Research Institute | 35000 | 2014-09-22 | MOU-3 | 2204 | 26000 | 9000
BIDS
List all bids for each contact signed with date of open call and winning bid
CONTRACT & Procurement Method | Submitted Bids | Bid Amount (USD) | Winning Bid Amount (USD) | Selection Justification for the Winner
01/12. Personnel Recruitment - competitive | Mme Jane Razanamiharisoa | 100000 | 90000 | Selection was based on technical merits, experience and expertise. A recruitment panel was launched within the Ministry of Environment for the selection of suitable candidates. No financial offers were required as the salaries were fixed.
| RAMAROVELO Jean Marc | 150000
| HERINIRINA Harisoa Rondro | 120000
02/12 Personnel Recruitment- competitive | Mr. Tahiry Herilalaina | 100000 | 75000 | Selection was based on technical merits, experience and expertise. A recruitment panel was launched within the Ministry of Environment for the selection of suitable candidates. No financial offers were required as the salaries were fixed.
| RASOLOMANDIMBY Tahina Fenosoa | 120000
| RAVOAVY Augustin Bertrand | 145000
03/12 Personnel Recruitment - competitive | Mr. Marcellin Lalason | 50000 | 50000 | Selection was based on technical merits, experience and expertise. A recruitment panel was launched within the Ministry of Environment for the selection of suitable candidates. No financial offers were required as the salaries were fixed.
| RANDRIAMPIERENANA Prisca | 100000
| RAKOTOMAMPIANINA Jean | 80000
04/13. Call for Proposals - international competitive' | Joana Talafré | 150000 | 120000 | Finanical bids were requested only for those candidates who fulfilled technical requirements. Contract attributed to highest ranking candidate for both technical and financial proposals. Contract amount revised from 150K to 120K following budet revision and number of days reduced.
| Alexandre Borde | 165000
Shalaby Hani
Olivier Beucher
05/13. Call for Proposals - international competitive | Gaetan Quesne | 35000 | 35000 | Financial bids were request only for candidates deemed technically qualified to perform the baseline study. A review panel was put together to analyse proposed methodologies and candidates, and a proposal was made to support consortia of international and national consultants. UNEP participated in the recruitment panel. Contract amount was adjusted to account for real hours worked between national and international consultant (a combination of two proposals).
| Henri Rakotobe | 20000
Raparany Serge
Mike Jennings
Narayan Dhital
Kasibothia Sridhar
Corradi Chiara Assunta Riccarda
Barova Harimanga
06/13 (call for proposals) - competitive | Ramangarivelo Lidya Nirina | 45000 |  | After discussion and exchanges and for greater efficiency and complementarity, the Evaluation Committee decided to retain the nominations of Mr and Mrs Jacqueline Rabeson consortium. Indeed, Mr Rabeson by his experiences both agriculture research and adaptation to climate change, could lead all of the study in terms of analysis and methodology while Mrs. Rakotoarisoa with her experiences and excellent knowledge of the context and local cultures, could arrange collection and verification of local data. The consultants were encouraged to join forces and present a joint bid. In later months, the contract was expanded to adjust for significantly increased scope of work.
| Rabeson Raymond | 80000 | 60000
| Rakotoarisoa Jacqueline | 85000
07/13- Call for Proposals -competitive | RASOAFALIMANANA Mbolarinosy | 70000 | 50000 | Financial bids required only for those candidates who fulfilled technical requirements. Contract attributed to highest rating candidates for both technical and financial.After discussion and exchanges and for efficiency, the evaluation committee decided to accept the nomination of Ms. Mbolaharinosy RASOAFALIMANANA based on her experience and excellent knowledge of the local context and culture and her ability to lead the entire study proposals. Negotiated contract was on the Basis of the Amount available for the work (50K) with a consortium of consultants, based on number of days Worked.
| Barova harimanga | 72000
| Rabeson Raymond | 65000
| Ratsimbazafy Jean-Pierre | 75000
| Randrianoro Desire | 80000
| Randriambolamanana Hoby Nantenaina | 90000
07bis/13 - single source | Rabeson Raymond | 6000 | 6000 | Only one candidate was sought out as it was known that he had previously obtained training in DSSAT and ORYZA and was qualified to deliver the required training.
08/13 - competitive | RATSIMBAZAFY Tiana Andrianiaina ( selected canditate) | 37500 | 15000 | After discussion and exchanges and for greater efficiency and complementarity, the evaluation committee decided to accept applications from M. RATSIMBAZAFY Tiana Andrianiaina, through his experiences in agriculture and especially in the use of fertilizer. He work also with an other agriculture engineer who was worked with ONG in technical test with farmer. Mr. Tiana has put together a team to address his TORs.
| Randrianasolo Fihevitsoa Rabarijaona | 40000
| Levy Rakotoarison | 50000
| Razafindrabe Manantsoavina Warren | 52000
09/14 - competitive | RAKOTOBE RAHELIARISOA Holinantenaina | 20000 |  | After discussion and exchanges, the evaluation committee decided to accept applications from M. ANDRIANIRINA Michelliarson, through his experiences at a time at Environment National Reaserch Center (CNRE) and his excellent experience in comparative methodological analysis of water quality and Climate change Adaptation where he conduct adaptation group for the first and second national communication. Among his team, there is an agricultural national expert, who also worked on the development of the national communication.
| Andrianirina Michelliarson (selected candidate) | 17000 | 15000
Ratsimbazafy Jean Pierre.
| Rejo robert Andriamananjara | 30000
10/13 - competitive | Levy Rakotoarisoa | 56000 | 60000 | After discussion and exchanges and for greater efficiency, the evaluation committee decided to accept applications from Mr Levy RAKOTOARISON due to his experience in agriculture research and Climate change Adaptation. He will direct the whole survey in terms of analysis and methodology by his experience and excellent knowledge of the context and the local cultures, will be in charge of the collections and verification of the local data. Contract amount is slightly higher than proposal as consultant missed a few activities of the TOR in his proposal.
Marthe Rafarasoa
| Raminoson Rina | 65000
11/14 - single source | Mr. Randrianoro Désiré |  | 1000 | Due to the low amount, a single candidate, known to be qualified, was sought out.
12 bis/14 - competitive | Mr. Ratsimbazafy Jean-Pierre | 5000 | 5000 | The evaluation committee decided to accept applications from Mr Ratsimbazafy Jean Pierre due to his experiences in agriculture research and Climate change Adaptation
| Mme Olitina Ratovo | 7500
| Mr RAFALIMANANTSOA Jules | 9000
12/14 - competitive | Rija Fidèle | 30000 |  | The evaluation committee decided to accept applications from Mr Razafindrakoto Helison due to his experiences in agriculture research and Climate change Adaptation, and jurisdiction over the watershed modeling and experience in software and application of hydrological modeling
| Helison Razafindrakoto ROMUALD | 26000 | 25000
13/14 - competitive | Miharimanana Marie | 20000 |  | After discussion and exchanges and for greater efficiency, the evaluation committee decided to accept applications from Mr Andriamalantomanga Tsiory Dimbimalala through his experiences at a the farmer communication and Climate change impact in agriculture. Contract amount is slightly higher than proposal as consultant missed a few activities of the TOR in his proposal.
| Andriamalantomanga Tsiory Dimbimalala | 17500 | $19,000
| Manampisoa Tanjona | 24000
14/14 - competitive | Heritiana Andrianala Rabemanantsoa | 15000 | 14000 | After discussion and exchanges and for greater efficiency, the evaluation committee decided to accept applications from Mr Rabemanantsoa Heritiana Andrianala through his experiences in agriculture research and Climate change Adaptation as well as experience on the economy and socially.
| Razanakolona Tahina | 165000
| Rakotobe Henri | 18000
15/14 - competitive | RANAIVOJAONA Harinomenjanahary Voahanginirina |  | 9000 | Over 35 candidates were presented for this post of local technician. The top candidates indicated here represent the shortlist, from which the leading candidate was selected. No financial offers were required as the salaries were fixed by the project.
Rabemanda Jean Gabriel
Razafinandrianina Justine
16/14 - competitive | Rasamison Jules |  | 9000
Andry nirina Rakotoarivelo
17/14 - competitive | Randriafiraisampirenena Jules |  | 9000
Razakalanitra Malala Navalona Mariah
20/14 - Competitive (driver) | RAMAROSOA Erick Lauret | 12000 | 11550 | The candidate has been selected especially due to his experiences found at the Department of Climate Change: Project driver on the Third of National Communication under the UNFCCC.
| RANDRIANANTOANINA Harinala | 13500
| RANAIVOSON Jean Eric Radonirina | 14800
MOU-1 - Single source | SNGF (Silo National de Grainer et Foresterie) |  | 201500 | The SNGF is a national organization specialized in the research and production of forest seeds. The MOU was negotiated on a non-competitive basis.
MOU-2 - Single source | CALA |  | 180000 | The CALA - Agricultural Center on the Alaotra Lake, is the representative of the FOFIFA on regionally level wich is an institution working in the rice sector, including research on varieties adapted on climate change. MOU was negotiated on a non-competitive basis.
MOU-2 - Single source | IRRI |  | 35000 | IRRI is an internationally recognized rice research center. The MOU was negotiated on a non-competitive basis.

## Risk Assesment
RISK ASSESMENT
IDENTIFIED RISKS
List all Risks identified in project preparation phase and what steps are being taken to mitigate them
Identified Risk | Current Status | Steps Taken to Mitigate Risk
Slow administration functionning due to lack of human and financial ressources | Low | All staff is currently in place, including local technicians in charge of coordinating local actions. New senior level staff from regional and national ministries are being briefed as they make their arrival into the project, which has taken some time.
Frequent political change, with elections now foreseen to be completed in December 2013. This creates a degree of uncertainty | Low | There have been some changes among senior-level staff in various ministries which have created some delays as people were being briefed. The project team is briefing senior management on an ongoing basis
Accesibility of sites during cyclonic/rainy/ flooding period (december-april) could affect inter regional transport and cause delays in performing required field visits and inputs delivery from other regions or from capital | Medium | In-field activities have been made difficult by epidemics and climate impacts. The presence of local technicians is somewhat mitigating this risk, since communication can now occur without travelling to the sites. However, activities may continue to be hampered during severe weather events, delaying activities by consultants and project partners.
Lack of population buy-in on project activities | Low | A communication strategy has been developed to ensure contact is made and maintained with local populations, and a strategy for developing buy-in is in place, through the activities of the rural communications specialist
there is a risk that the upscaling and replication strategy developed for this project might be insufficient in ensuring uptake of the approach to the rest of the country. Political instability in the country may delay or prevent the adoption of policy recommendations adopted by the project. | Low | It is too early to say whether this risk will materialize. However, the project is gaining in visibility as activities on the ground are becoming more visible.
Critical Risks Affecting Progress (Not identified at project design)
Identify Risks with a 50% or > likelihood of affecting progress of project
Identified Risk | Current Status | Steps Taken to Mitigate Risk
There could be project delays due to delays in processing cash advance requests with UNEP, as well as due to change in financial procedures in UNEP or in GoM | High | Changes in UNEP procedures in 2013 resulted in delays in processing cash advances, leading to an interruption in availability of funds for the project. From 2014, cash advance requests are being prepared in advance for accelerated transfer. Furthermore,budget simplifications have also been instated in order to facilitate procurement by the Ministry and its partner organizations. There have been delays due to lenghty discussions on budget, leading to a further interruption in fund availbility, while cash advances were being processed in 2014. These delays are being absorbed, and enhanced procedures put in place to avoid similar situations in the future.The PCU will make a big effort to respect the deadline and improve work methods.
Procurement delays | High | There have been some delays in procurement owing to the delegation of purchasing authorities from the project to various partners, who have sometimes refused or been unable to discharge their responsibilities in adequate time. Negotiations with other ministries and institutional partners have been lenghty, and there is a lack of clarity on the procurement responsibilities between various project partners. There have been delays in signing MOUs and inter-institutional agreements (namely with min Water, Min Agri, and DRDA) following changes in senior personnel. Furthermore, the intent and function of such agreements (MOUs) was not clear; it was therefore decided to raise the issue during the PSC, and to explain the purpose of agreements. Follow-up on MOUs is now being made at the PSC level. The project also encountered delays in launching the calls for proposals for various consultancies because of an error in procedure, which led to the calls having to be relaunched. In addition, a few calls for proposals have remained unanswered. It was decided that if international expertise could not be identified, the project would transfer the calls for proposals to national or regional expertise. Additional efforts at publicising project offers will be made by the CTA and UNEP. Finally the project encountered delays owing to the illness of the national project director.
Lack of financial bidds | Medium | All application documents relating to internationally call tenders are grouped at the NPD. The Coordinator and the administrative does not have those applications document. In the future, these document will be available at the Administrative Manager.Some bidders for national consultants have not proposed financial bids.These bidders are requested directly to them during the interview.
Risk Measures: Were there any risk mitigation measures employed during the current reporting period? If so, were risks reduced? If not, why were these risks not reduced?
Add any comments relevant to risk mitigation (word limit = 500)
Despite attempts at accelerating budgeting and procurement processes, the measures set in place in late 2013 were insufficient to avoid a further interruption in fund availbility. The process has now been streamlined, and procedures clarified. A schedule of tasks was developed whereby the team would start financial reports and cash advance requests on specific dates throughout the year, with clear timelines for comments and revisions by UNEP and the CTA. Similar process was followed to develop a detailed procurement plan, with specific dates noted for the initiation of procurement processes, along with roles and responsibilities of each team member in its delivery. An online collaboration platform (Smartsheet) was established for the team to share documentation, monitor progress on various tasks, and ensure appropriate time management. Regarding procurement, efforts are underway to clarify responsibilities and duties among the various ministerial partners, and to facilitate the procurement of goods through other ministries. This includes working in advance with ministries to develop precise lists of goods, cahiers de charge, and other specifications. However, there remains some reluctance on the part of some partners to deliver their procurement responsibilities as part of the MOUs agreed with the project. Senior management intervention often proves necessary.

## Rating
RATING ON IMPLEMENTATION PROGRESS
For rating definitions please see bottom of page.
| Progress on Key Milestones |  | Expected Progress |  | Progress to Date | Rating
Project Manager/Coordinator: | Stakeholder Consultation at all levels |  | Confirmation of activities and of the project objectives, and development of project oversight and management structures as per project document |  | Consultations are proceeding in a satisfactory way, albeit with some delays. | satisfactory
| Development of project management tools |  | Elaboration of annual work plans, terms of reference, procurement plan, budget revisions and establishment of project management structures at central and decentralized level |  | Some issues have been seen in adherence to workplans, timelines and budget planning. A new online project management tool has been proposed and implemented by the CTA. Hopefully this will help the national team better plan, coordinate and execute project management activities | moderately unsatisfactory
| Baseline Study |  | Revision of project indicators and provision of baseline data |  | Completed as planned and management response prepared and approved by PSC | satisfactory
| Component 1 Milestones | Development of the MIRR Development of rice guidelines, technologies, models and knowledge products | Development of the MIRR expected by end 2013. Guidelines and other MIRR-related products expected early 2014, trainings delivered in early 2014 |  | The MIRR workshop was held in September 2014, with the assstance of the IRRI international Center. Guidelines are now being produced for dissemination to local populations and extension services. The activity has been delayed, but is being delivered in line with quality requirements | moderately unsatisfactory
| Component 2 Milestones | Rice varieties selected and produced Water technologies deployed Ecosystems rehabilitated and productive Post harvest losses reduced | Expected delivery for 2015 and 2016 |  | A number of preparatory studies are in the making and MoU and other preparations for execution of activities are also underway. It is expected that a large number of activities and expenditures will be achieved in 2015. | moderately unsatisfactory
| Component 3 Milestones | Norms, standards and policies revised | Expected delivery for 2016 and 2017 |  | This is still in early stages and planned for second half of project. | moderately unsatisfactory
[5 empty] | Overall rating | Satisfactory
Please Provide the Name and Contact information of person(s) reponsible for completeling the Rating section
| Name: | RAZANAMIHARISOA Jane Alice Laurette
| Email: | jrazanamiharisoa@ymail.com
Please justify your rating. Outline the positive and negative progress made by the project since it started. Provide specific recommendations for next steps. . (word limit=500)
Early in the project, there was a delay in the implementation of activities since the establishment of the institutional structure took much longer than expected. This is the case also for the event calls for national consultants should revive calls for some cases because there is not enough applicants. The delay is also due to the organization of responsibilities between the project team and CTA (who does what, how). The development of the MOUs also is not easy given the specificities of institutions on their responsibilities (central level) and changes in both central and regional staffs thus requiring more sensitization and playdoyers. Despite this delay the project is in its second year of implementation and advance step by step. We solved the problem of lack of advertisement of positions by increasing the number of newspapers and places for display as well as improving the organization of responsibilities for the coming of the CTA and the use of the tool "smart sheet" to view activities and their interactions and enable planning of respective roles following the plan procurement.
| Progress on Key Milestones |  | Expected Progress |  | Progress to Date | Rating
Implementing Agency | Stakeholder Consultation at all levels |  | Confirmation of activities and of the project objectives, and development of project oversight and management structures as per project document |  | Consultations are proceeding in a satisfactory way, albeit with some delays. | MS
| Development of project management tools |  | Elaboration of annual work plans, terms of reference, procurement plan, budget revisions and establishment of project management structures at central and decentralized level |  | Some issues have been seen in adherence to workplans, timelines and budget planning. A new online project management tool has been proposed and implemented by the CTA. Hopefully this will help the national team better plan, coordinate and execute project management activities | MS
| Baseline Study |  | Revision of project indicators and provision of baseline data |  | Completed as planned and management response prepared and approved by PSC | S
| Component 1 Milestones | Development of the MIRR Development of rice guidelines, technologies, models and knowledge products | Development of the MIRR expected by end 2013. Guidelines and other MIRR-related products expected early 2014, trainings delivered in early 2014 |  | After some delays the MIRR workshop has now been implemented and a MIRR selected for implementation. This has been a bottleneck for implementation of component 2, so it is expected that this achievement will open up for greater progress in 2015. | MS
| Component 2 Milestones | Rice varieties selected and produced Water technologies deployed Ecosystems rehabilitated and productive Post harvest losses reduced | Expected delivery for 2015 and 2016 |  | A number of preparatory studies are in the making and MoU and other preparations for execution of activities are also underway. It is expected that a large number of activities and expenditures will be achieved in 2015. | N/A
| Component 3 Milestones | Norms, standards and policies revised | Expected delivery for 2016 and 2017 |  | This is still in early stages and planned for second half of project. | N/A
[5 empty] | Overall rating | Moderately satisfactory
Please Provide the Name and Contact information of person(s) reponsible for completeling the Rating section
| Name: | Lars Christiansen
| Email: | lachr@dtu.dk
| Progress on Key Milestones |  | Expected Progress |  | Progress to Date | Rating
Chief Technical Advisor | Stakeholder Consultation at all levels |  | Confirmation of activities and of the project objectives, and development of project oversight and management structures as per project document |  | This activity is underway and has been strengthened by the development of a rural communication strategy. The process for identifying project beneficiaries, associations and groups, is also underway, although with some delay. | MS
| Development of project management tools |  | Elaboration of annual work plans, terms of reference, procurement plan, budget revisions and establishment of project management structures at central and decentralized level |  | This is underway. The project team is continuously working on improving its management tools. The team experienced delays in delivery of project activities and budget planning, as well as procurement delays. | MS
| Baseline Study |  | Revision of project indicators and provision of baseline data |  | Completed | S
| Component 1 Milestones | Development of the MIRR Development of rice guidelines, technologies, models and knowledge products | Development of the MIRR expected by end 2013. Guidelines and other MIRR-related products expected early 2014, trainings delivered in early 2014 |  | The MIRR workshop was held in September 2014, with the assstance of the IRRI international Center. Guidelines are now being produced for dissemination to local populations and extension services. The activity has been delayed, but is being delivered in line with quality requirements | MS
| Component 2 Milestones | Rice varieties selected and produced Water technologies deployed Ecosystems rehabilitated and productive Post harvest losses reduced | Expected delivery for 2015 and 2016 |  | Many activities have begun. The pre-selection of rice varieties is completed based on documentary evidence, and contracts are being negotiated for the production of pre-base seeds and seed multiplication. Water quality monitoring systems are being put in place, and reforestation efforts ahve been initiated through the communes and the national government. Procurement is being initiated for the rehabilitation of post-harvest infrastructures. The activities have been delayed. | S
| Component 3 Milestones | Norms, standards and policies revised | Expected delivery for 2016 and 2017 |  | N-A | N-A
[5 empty] | Overall Rating | Moderaly Satisfactory
Please Provide the Name and Contact information of person(s) reponsible for completeling the Rating section
| Name: | Joana Talafre, Chief Technical Advisor
| Email: | joana.talafre@okapiconsulting.ca
| Please justify your rating and address the following points: 1. Indicate trends, both positive and negative, in achievement of outcomes as per the project indicators. 2. Detail critical risks that have affected progress. 3. Outline response to MTR undertaken this reporting period. 4. Outline action plan to address projects with a rating of HU, U or MU. Please keep your input to 1200 words |  | The project has been delayed and it has not been possible to make up for lost time to this day. Delivery is slow, with changes in senior staff implying the renegotiation of previous agreements and MOUs. Procurement is also slow, and there is often a lack of suitable candidates for consultancies. Procurement of goods and materials is also slow, and at this time there is no no clear identified mechanism for accelerating procedures. There continue to be administrative bottlenecks within the MEF for approvals of various project actions (signature of agreements, contracts, procurement and payments). The quality of some outputs provided by consultants has sometimes left to be desired, creating longer delays for revision of documents and reports. Clearer TORs, with added deliverables allowing for progressive quality assessment, are being pursued when feasible, to allow for review of outputs produced by consultants. Roles and responsibilities between members of the project team are continuously being clarified, with lead responsibilities clearly remaining in the hands of the project manager. Over the course of the next period, response delays for review of technical outputs produced by Consultants will be shortened to allow for more revisions.
Rating Definitions
|  |  | Highly Satisfactory (HS) | Project actions/activities planned for current reporting period are progressing on track or exceeding expectations to acheive all major outcomes/outputs for given reporting period, without major shortcomings. The project can be presented as “good practice”.
|  |  | Satisfactory (S) | Project actions/activities planned for current reporting period are progressing on track to achieve most of its major outcomes/outputs with only minor shortcomings.
|  |  | Marginally Satisfactory (MS) | Project actions/activities planned for current reporting period are progressing on track to achieve most major relevant outcomes/outputs, but with either significant shortcomings or modest overall relevance.
|  |  | Marginally Unsatisfactory (MU) | Project actions/activities planned for current reporting period are not progressing on track to achieve major outcomes/outputs with major shortcomings or is expected to achieve only some of its major outcomes/outputs.
|  |  | Unsatisfactory (U) | Project actions/activities planned for current reporting period are not progressing on track to achieve most of its major outcomes/outputs.
|  |  | Highly Unsatisfactory (U) | Project actions/activities planned for current reporting period are not on track and shows that it is failing to achieve, and is not expected to achieve, any of its outcomes/outputs.

## Project Indicators
PROJECT Indicators (*as revised following baseline study)
Please provide all indicators being tracked for the project as outlined in the project document
Type of Indicator (indicators towards Objectives, Outcomes, etc…)
Type of Indicator | Indicator | Baseline | Progress since inception | Target for Project End
Outcome 1.1 Knowledge base on best practices for climate resilience in rice, based on existing local knowledge and international research | Percentage of farmers with access to selected and publicized MIRR | There is currently no MIRR available although various ameliorated techniques have been developed in recent decades | Documentary analytical work has been completed and guidelines on the application of the MIRR are being finalized. A workshop was held with all stakeholders to discuss and validate technical findings. A MIRR is therefore now available for testing locally. (90% completed) | Based on ameliorated techniques and new research, 1 MIRR is selected
Output 1.1.1 Best Available Technologies and Integrated Resilient Rice Model (Modèle Intégré de Riziculture Résiliente - MIRR) selected and publicized | # and type of technical guidelines for MIRR developed and publicized based on best available technologies and technique | A series of guidelines for rice cultivation techniques, technical guidelines for direct seeding and system of rice intensification, are available from regional directorate of rural development but not yet widely disseminated | Work is being completed on the overall MIRR guidelines, with an interim draft submitted and a final draft under preparation. Technical guidelines on the individual MIRR elements (fertilizer, Integrated Pest Management etc.) are under development (50% completed) | 1 recommended Integrated Resilient Rice Model developed and published including at least1 technical guidelines on seeding, planting, harvest, post-harvest, fertilization, IPM, water management
Outcome 1.2 Malagasy government, research institutions and local communities have the tools and methods to assess, monitor, and understand climate change impacts on rice. | Level of use of the tools and methods made available to Malagasy government, research institutions and local communities to assess, monitor and understand climate change impacts on rice production | Current tools to address, monitor, and understand climate change impacts on rice are hampered by a lack of data and weak potential to convey information to farmers. Data on observed climate patterns is not being systematically collected at an appropriately local level making it difficult to create models and planting calendars. Dissemination of what information exists is also weak given the limited number of extension staff. While these staff appear to already be trained in climate issues, the information is not being disseminated to farmers. | Consultants have been recruited and work is under way to develop alternate crop models using up to date climate and crop data. Work is also underway to develop alternate calendars. Expected completion december 2014. (40% completed) | All regional extension services, research institutions including CALA, and at least 90% of targeted farmers are aware of climate change trends and impacts through awareness raising and information sessions, have access to regular climate forecasts through local communication channels (radio, newspapers), and have been trained and implement MIRR and its technical guidelines, including vulnerability maps.
Output 1.2.1 Malagasy government, research institutions and local communities have the tools and methods to assess, monitor, and understand climate change impacts on rice. | Number of rice cropping system models based on expected climate change scenarios, including vulnerability maps of future rice production, and hydrological models developed | Currently, there is no rice cropping system model that includes vulnerability maps of future rice production under potential climate change impacts and hydrological models developed. | Work is underway to gather data and to run crop models based on training provided using ORYZA and DSSAT. Consultants have being recruited for the development of a hydrological model and work is in progress for the updating of agricultural calendars. (50% complete) | Detailed available downscaled data on expected climate change risks and impacts on rice sector at the local level compiled; identified gaps on available data are filled in; and all data are disseminated to relevant stakeholders at the regional and local levels. 4 rice cropping system models with vulnerability maps developed according to 4 different expected climate change scenarios (driest, low dry, low humid, and most humid scenarios) and 1 hydrological model developed based on available downscaled data on expected climate change risks and impacts.
Output 1.2.2 Updated, dynamic agricultural calendars and climate early warnings taking into account current and projected variability disseminated to local population | Frequency of dissemination of updated dynamic agricultural calendars and climate information, including flood early warnings in the three projected sites | Agricultural calendars under current climate conditions are well defined for all seed varieties developed, yet farmers do not necessarily apply them. The challenge resides in distributing and encouraging the application of established calendars amongst farmers through training and diffusion. Furthermore, new agricultural calendars will need to be developed on the basis of projected future climate trends. With respect to the diffusion of climate information, networks for analyzing and disseminating climate data are also insufficient:  Manakambahiny – In Ambalavato, farmers have access to daily meteorological forecasts in the newspaper and on the Radio Nationale Malgache. In Ambaibo, farmers also have access to daily forecasts. This information, however, is not very useful as it cannot provide longer forecasts that would aid in, for instance, determining seedling date or predicting potential floods.  Bemaintso and Ambohijanahary – Farmers have access to daily forecasts, but the forecasts do not help them adapt their growing calendar with enough forewarning or to choose which seed variety to use. | Consultants have been recruited and are working towards the adaptatio of agricultural calendars. A rural communications specialist has provided advice on radio programming in support of producers. An MOU is being prepared for signature with radio operators to facilitate transmission of climate and agricultural information loally. Weather stations have been purchased and will be installed in Q4 of 2014. (50% complete) | Climate information and 3- 4 day forecasts, including flood early warnings, made available to farmers through local communication systems. Dynamic agricultural calendars updated and disseminated to at least 80% of targeted farmers.
Output 1.2.3 Agricultural extension staff trained on climate risk management in an agro– ecosystem context | Number of agricultural extension staff in the three districts trained on climate risk management in agro– ecosystem context (gender and district disaggregated) | Extension workers were trained in climate change issues through the BV Lac project, and they do not necessarily lack training. The challenge is disseminating information from extension workers to farmers given how little contact they have with farmers. The presence of extension workers in the project sites is the following:  Manakambahiny – The municipality contains the city Ambatondrazaka, which is the capital of the Alaotra-Mangoro Region. There are 15 to 20 agriculture staff, of which 9 to 11 extension workers cover the 5 districts of the region. Their presence in the field is weak.  Bemaintso – The municipality is part of the Andilamena district where 2 extension workers for rural engineering are located. They use radio to broadcast information to farmers.  Ambohijanahary – The municipality is part of the Amparafaravola district, for which there are 4 extension workers (2 for agriculture and 2 for engineering). | The activity has been postponed to 2015. Recruitment for a consultant to deliver traiing on risk management is underway (0% complete) | 100 % of staff trained on climate change aspects and how to disseminate new knowledge to farmers, including women.
Outcome 2.1. Sustainable increase in rice yields (using MIRR) | Percentage of change in rice yields in all three project sites | Rice yields in 2012-2013 for irrigated rice in the project areas were:  Manakambahiny – 3.41 tons/ha average (roughly 3 tons/ha for Mk34 and 3.5 tons/ha for Dista and Tsemaka)  Bemaintso – 0.7 tons/ha for MK34 and 1.5 tons/ha for Dista (the low yields observed in Bemaintso are due to floods – care should therefore be taken while analyzing these data)  Ambohijanahary – 2 tons/ha for MK34 and 3 tons for Tsemaka  Tsemaka – Farmers use the variety to increase yields under challenging water conditions; however, farmers report that it does not sell as well at market as MK34.  MKx – Variety developed and distributed by CALA.  Dista – Farmers use the variety in cases where the planting rains start late.  SEBOTA – The variety was developed for the BV Lac project in partnership with CALA and with help from CIRAD. It is designed to tolerate poor water management conditions, but the seed has not been distributed to many farmers due to limited reproduction of the seed and to patent issues.  FOFIFA – This is a group of early maturing varieties that can be produced in the rainy and dry seasons. They are developed by CALA. The last variety developed under this group is FOFIFA 174. | Activities foreseen in 2015 | Individual rice yields for targeted producers increase by 25% in relation to current averages in each project area.
Output 2.1.1 Climate resilient rice varieties selected through participatory field testing | Number and types of climate resilient rice varieties tested and selected within the three project sites (Municipalities of Manakambahiny, Ambohijanahary and Bemaintso) | Current rice farming is dominated by the seed variety MK34, though it is not necessarily resilient. The next most prominent varieties are Dista and Tsemaka. | Rice varieties have been selected and final reports submitted. The findings of the selection work were presented to the MIRR workshop in September 2014, and validated by stakeholders. MOUS are being signed with local research institutions for the testing of variety selection at local level (30% complete) | CALA facilities and capacities are strengthened to develop at least 5 varieties that are tested and proven resilient in both laboratory and field settings in the three
Output 2.1.2 An operational multiplication and dissemination scheme for adapted seed varieties | Annual quantity and quality of adapted certified seeds produced and distributed in each of the project sites | Seed multiplication appears to be dominated by four main facilities. Challenges include production capacity for CALA and the publication and dissemination of seed-specific planting guidelines. | Work is underway and MOUS are being negotiated with local organizations to support the production of pre-base seeds and the multiplication of seeds. (10% complete) | At least 5 tons total of seeds for all 5 varieties that were tested and proven resilient are produced annually and distributed in the 3 project sites.
Output 2.1.3 Updated fertilisation guidelines according to best available standards and taking climate conditions into consideration | Number of farmers who apply updated fertilisation guidelines in all three project sites (Municipalities of Manakambahiny, Ambohijanahary and Bemaintso) | Farmers do not appear to follow any specific guidelines for fertilizer application. Farmers vary on how and when they use compost, manure, urea, NPK, and/or DAP. Many farmers do not use any chemical fertilizer practices.fertilisers are not commonly used | Fertilisation guidelines have been reviewed, revised and updated. Findings of research on fertilisation guidelines was presented at the MIRR workshop and validated by stakeholdesr in September 2014. Work continues on an ongoing basis to support the use of locally available fertilization. (50% complete) | 90% of targeted farmers have been trained and/or received technical support and apply fertilisation guidelines updated as part of the development of the MIRR.
Output 2.1.4 Integrated pest management is implemented | Number of farmers trained in integrated pest management in all three project sites (gender and age disaggregated) | In general, farmers had no information or training about the appropriate protocols for using pesticide in pest control. While some used commercial pesticides, they applied them with little knowledge of best practices. | Activities foreseen for 2015 | 400 farmers trained in integrated pest management, gender and age disaggregated (and among them 50% women and young)
Output￼ 2.1.5a Water efficiency, management and conservation technologies and infrastructures are implemented | Number of Km of rehabilitated irrigation canals and number of reservoirs dredged in all three project sites | Infrastructure in the 3 municipalities was in a state of significant disrepair with damaging siltation and reduced irrigation capacities throughout. There is a large need for rehabilitating canals and dam infrastructure. | Activities foreseen for 2015 | Manakambahiny: 35 km of primary canals cured, dredged, and maintained with norms that take expected climate change impacts into account (future precipitation regimes, drainage and run-off); 4 water intake points along the Ilakana River rehabilitated, strengthened and made more resilient to expected climate change impacts. Bemaintso: The dam is drained and dredged; 14 km of primary canals and 21 km of secondary canals are cured, dredged, and maintained all with norms that take expected climate change impacts into account. Ambohijanahary: The dam at Anony is rehabilitated, primary water control valves are repaired; 13 km of primary canal are drained, dredged, and repaired; and primary canal is extended to irrigate 600 ha of additional rice fields all with norms that take expected climate change impacts into account.
Output￼ 2.1.5b Water efficiency, management and conservation technologies and infrastructures are implemented | Percentage of change in water availability and in water use efficiency in all seasons to water users associations in all three project sites | There is a decrease in water availability during the dry season in all 3 Districts, and water losses reach up to 50 %. | Activities foreseen for 2015 | 35 % increase in water availability in all seasons in all 3 districts. Water loss estimation decrease from 50% to 25%.
Outcome 2.2. Ecosystem services maintained | Percentage change in land covered by biomass and in overall productivity (rice, vegetables and livestock) in project sites | There is no evidence of activities to increase land covered by biomass such as agro forestry practices, reforestation, or vegetable crop rotations. No farmers use soil quality or water quality improvement techniques. | Revegetation of degraded slopes and forests is underway with signing of MOU between SNGF and Project (start in April 2014). Sub contract with three communes(Bemaitso, Manakambahiny, Ambohijanahary) are also elaborated for signature.These subcontracts are about revegetation of degraded slopes and forests for completing the activities developped by SNGF .The activity to perform local level water quality monitoring is developed . Others activities foreseen for 2015. | Change in overall land area covered by forests (i.e. net reforestation) of at least 50km2 across the combined 3 municipalities.Data on vegetables and livestock productivity/yields collected by extension services, and increase in overall productivity of rice, vegetables and livestock of 5 % throughout the life of the project and across the project sites.
Output 2.2.1 Best available land preparation, production and harvesting techniques disseminated to reduce deforestation, maintain soil fertility and integrity, and to provide adequate growing conditions | Percentage application of resilient rice model, including rice–vegetables rotation systems, in all three project sites (gender disaggregated) | Rice/vegetable crop rotations are used on only very small pieces of rice fields. Guidelines for rice/vegetable rotation practices were developed under the BV Lac project, but their dissemination was somewhat limited. | Activities foreseen for 2015 | At least 75% of targeted farmers practice rice/vegetable crop rotation on an area larger than 0.1 ha and for commercial purposes (and among them at least 50%of women and young).
Output 2.2.2 Watershed rehabilitation in productive landscapes introduced, including through reforestation and adaptation of agro forestry practices | # of ha reforested; # of farmers and land/forest users trained on sustainable agro-forestry and land management in all three project sites (gender and age disaggregated) | some reforestation underway in the broader basin but not in project sites; currently there are no people trained on SLM and agroforestry in the project sites | Work has begun with the negotiation and signature of MOUS with the National Grain Silo for the production of seedlings and the three pilot communes for community-based reforestation. Materials will be purchased and reforestation works will begin in 2015 season (10% complete) | 8500 ha reforested around project sites; 300 farmers and land/forest users trained (50% women)
Output Indicator 2.2.2.a | Number of ha reforested in all three project sites | Rice/vegetable crop rotations are used on only very small pieces of rice fields. Data on vegetables and livestock productivity/yields are currently not collected by extension services. | Work has begun with the negotiation and signature of MOUS with the National Grain Silo for the production of seedlings and the three pilot communes for community-based reforestation. Materials will be purchased and reforestation works will begin in 2015 season (10% complete) | Data on vegetables and livestock productivity/yields collected by extension services, and increase in overall productivity of rice, vegetables and livestock of 5 % throughout the life of the project and across the project sites.
Output Indicator 2.2.2.b | Number of farmers and land/forest users trained on sustainable agro forestry and land management in all three project sites (gender and age disaggregated) | Farmers have currently not been trained in sustainable agro forestry and land management practices. | Activities foreseen for 2015
Output 2.2.3 Soil conservation and livestock management techniques adapted to topography and landscape in light of future climate conditions | % change in erosion rate | The project PRODAIRE has been training workers for the DREF in monitoring erosion rates. The DREF has therefore the in-house capacities to monitor erosion rates in the project sites. Average erosion rate in the region is 12 mm.yr.1, according to Cox, R. et.al, 2009 “ Erosion Rates and Sediment Contributions in Madagascar Inferred from 10 Analysis of Lavaka, Slope, and River Sediment” | Activities foreseen for 2015. Negotiations are underway with the Ministry of Agriculture | 50 % reduction in erosion rates.
Output 2.2.4 Revitalization of producer’s cooperatives and water user associations for collaborative natural resources allocations (e.g. land and water) and management | Number of members of farmer’s cooperatives and water user associations trained on water management and administrative management within the three project sites | Water user cooperatives exist in the three project areas; however, in all areas members expressed a need for training in administrative management as well as training in water management. | Activities to begin in 2015. Recruitment of consultants is underway. | 75 % of the members of water user cooperatives in the project area have been trained on water management and administrative management.
Output 2.2.5 Water quality assessments | Percentage change in water quality (e.g. reduction in turbidity, pollutant content, microbial content, sediment content) in all three project sites | There is currently no water quality analysis conducted in any of the three municipalities | Consultants were recruited and developed a methodological framework for water quality testing in project sites. A contract is being signed with a laboratory to support water quality analyses on an annual basis. A first set of water samples will be taken at the end of December 2014 (15% complete) | 15% increase in water quality by end of project
Outcome 2.3. Post Harvest losses reduced | Percentage change in post harvest losses | Post–harvest losses are estimated to be between 5 and 10% of total harvest. | Activities have begun with the recruitment of consultants for pre-feasibility studies | Post-harvest losses are reduced to less than 4%.
Output 2.3.1 Increased utilization of rice by–product especially rice straw | Percentage change in use of rice straws in animal feeding and for briquetting | There are regional variations in the degree to which farmers exploit rice stalks for other uses. In some municipalities, residues are simply burned in the field. | Consultats are being recruited to support this work in 2015. | 75% of farmers use or commercialize rice straws.
Output 2.3.2 Post–harvest storage facilities with phytosanitary control, serving as trading points and markets | Number of renovated storage facilities in all three project sites | Storage facilities in the project sites exist, but they are not in adequate condition | Consultants were recruited and produced a study on existing means of phytosanitary control, post-harvest infrastructure, and the cost and benefits of their rehabilitation. Procurement will be initiated for the rehabilitation of recommended infrastructures and according to recommended standards | 75% of existing facilities have been renovated.
Outcome 3.1 Technical norms and standards in rice cultivation reviewed and where necessary modified to take climate change into account | Number and types of technical norms and standards in rice cultivation reviewed and modified at the national level to take climate change into account | No recommendation or revision has currently been made to technical norms and standards in rice cultivation. | Activities to begin in 2015 | At least one national strategy on rice cultivation and at least one technical guideline for the following rice cultivation stages/techniques are revised and updated at the national level: • Seeding • Planting • Harvest • Post–harvest • Fertilization • Integrated pest management • Water management
Output 3 .1.1a Gaps and possible maladaptations in the current rice policy are identified and recommendations on rice policy reform are made | Number and types of activities identified and implemented for up scaling and replication from MIRR application in broader Alaotra basin and in other regions | While there is an Agricultural Development Strategy at the national level, it does not have a true application at the regional level due to financing. There is no specific policy for growing rice. | Activities to begin in 2015 | 1 replication strategy and action plan developed, including at least 5 to 10 operational activities for up scaling and replication of MIRR practices in the broader Alaotra basin and beyond.
Output 3.1.1b Gaps and possible maladaptations in the current rice policy are identified and recommendations on rice policy reform are made | Number and types of recommendations on rice policy reforms made | The National Strategy on Rural Development (SNDR) was completed; however, this strategy has not been published or disseminated. | Activities foreseen for 2017 | The SNDR is revised with measures to increase climate change resilience of rice production, and then the strategy is published and disseminated.
Outcome indicator 3.2 Conditions in place for a full adaptation of the rice sub–sector | Number and type of stakeholders to which the report on best practices and lessons learned is distributed | Lessons learned and best practices will be identified and collected during project implementation | Activities foreseen for 2017 | 1 report at end of project.

## Lessons Learned
QUALITATIVE MEASURES and LESSONS LEARNED
Please complete the following section every reporting period
Implementation and Adaptive Management | Response
What implementation issues/lessons, either positive or negative, affected progress? | Adequate delegation of authority to the project manager should be ensured at the start of the project, to avoide excessive reliance on the National Project Director for approvals, which can create delays. Furthermore, clarification of roles and responsibilities for procurement among project partners has been long in establishing, and negotiations are sometimes lengthy with certain partners, which leads to delays in procurement. MOUs should specify responsibilities and timelines for procurement and roles and responsibilities between the different ministries participating in the project should be clarified at the start of the project.
Were there any delays in implementation? If so, include any causes of delays. What measures have been taken to reduce delays? | The project is delayed by about one year. A process has been created whereby procurement of goods and services is anticipated, and individual workplans for team members have been produced to ensure each action is delivered on time. A Time-management tool has been setup (Smartsheet), enabling for real-time follow-up and online collaboration. More intense negotiations with partner ministries and organizations will be pursued in order to finalize agreements and procurements on time.
Describe any changes undertaken to improve results on the ground or any changes made to project outputs (i.e. changes to project design) | no changes to project outputs have been made. The activities are being monitored for rate of implementation and quality of output.
How have gender considerations been taken into consideration during the reporting period? What have been the lessons learned as a consequence of inclusion of such considerations on project performance or impacts? | Gender considerations have been integrated in all aspects of the work, particularly in all the studies that form part of the MIRR discussions and recommendations. Women and Womens' groups are being consulted as part of the rural communication strategy.
Please complete the following section at mid-term and project completion
Lessons for Adaptation | Response
Climate Resilience Measures
What have been the lessons learned, both positive and negative, in implementing climate adaptation measures that would be relevant to the design and implementation of future projects/programmes for enhanced resilience to climate change?
What is the potential for the climate resilience measures undertaken by the project/programme to be replicated and scaled up both within and outside the project area?
Concrete Adaptation Interventions
What have been the lessons learned, both positive and negative, in implementing concrete adaptation interventions that would be relevant to the design and implementation of future projects/programmes implementing concrete adaptation interventions?
What is the potential for the concrete adaptation interventions undertaken by the project/programme to be replicated and scaled up both within and outside the project area?
Community/National Impact
What would you consider to be the most successful aspects for the target communities?
What measures are/have been put in place to ensure sustainability of the project/program results?
What measures are being/could have been put in place to improve project/program results?
Knowledge Management
How has existing information/data/knowledge been used to inform project development and implementation? What kinds of information/data/knowledge were used?
If learning objectives have been established, have they been met? Please describe.
Describe any difficulties there have been in accessing or retrieving existing information (data or knowledge) that is relevant to the project. Please provide suggestions for improving access to the relevant data.
Has the identification of learning objectives contributed to the outcomes of the project? In what ways have they contributed?

## Results Tracker
Results Tracker for Adaptation Fund (AF) Projects
Goal: Assist developing-country Parties to the Kyoto Protocol that are particularly vulnerable to the adverse effects of climate change in meeting the costs of concrete adaptation projects and programmes in order to implement climate-resilient measures. Impact: Increased resiliency at the community, national, and regional levels to climate variability and change.
Important: Please read the following Results Framework and Baseline Guidance (also posted on the Adaptation Fund website) before entering your data
Link: http://www.adaptation-fund.org/sites/default/files/Results%20Framework%20and%20Baseline%20Guidance%20final.pdf
Please select the relevant Fund level Outcome and Output indicators that allign with the project objectives and outcomes
OBJECTIVE 1
Fund Outcome | Please select from dropdown menu below | Fund Outcome Indicator | Please select from dropdown menu below | Target at CEO Endorsement (see Units in next sheet) | Baseline (see Units in next sheet) | Mid-term Results | Terminal Results
Outcome 1: Reduced exposure at national level to climate-related hazards and threats Outcome 2: Strengthened institutional capacity to reduce risks associated with climate-induced socioeconomic and environmental losses Outcome 3: Strengthened awareness and ownership of adaptation and climate risk reduction processes at local level Outcome 4: Increased adaptive capacity within relevant development and natural resource sectors Outcome 5: Increased ecosystem resilience in response to climate change and variability-induced stress Outcome 6: Diversified and strengthened livelihoods and sources of income for vulnerable people in targeted areas Outcome 7: Improved policies and regulations that promote and enforce resilience measures | 4 | 1. Relevant threat and hazard information generated and disseminated to stakeholders on a timely basis 2.1. No. and type of targeted institutions with increased capacity to minimize exposure to climate variability risks 2.2. Number of people with reduced risk to extreme weather events 3.1. Percentage of targeted population aware of predicted adverse impacts of climate change, and of appropriate responses 3.2. Modification in behavior of targeted population 4.1. Development sectors' services responsive to evolving needs from changing and variable climate 4.2. Physical infrastructure improved to withstand climate change and variability-induced stress 5. Ecosystem services and natural assets maintained or improved under climate change and variability-induced stress 6.1. Percentage of households and communities having more secure (increased) access to livelihood assets 6.2. Percentage of targeted population with sustained climate-resilient livelihoods 7. Climate change priorities are integrated into national development strategy | 4.2 | 4 | 2
Fund Output | Please select from dropdown menu below | Fund Output Indicator | Please select from dropdown menu below | Target at CEO Endorsement (see Units in next sheet) | Baseline (see Units in next sheet) | Mid-term Results | Terminal Results
Output 1: Risk and vulnerability assessments conducted and updated at a national level Output 2.1: Strengthened capacity of national and regional centres and networks to respond rapidly to extreme weather events Output 2.2: Targeted population groups covered by adequate risk reduction systems Output 3: Targeted population groups participating in adaptation and risk reduction awareness activities Output 4: Vulnerable physical, natural, and social assets strengthened in response to climate change impacts, including variability Output 5: Vulnerable physical, natural, and social assets strengthened in response to climate change impacts, including variability Output 6: Targeted individual and community livelihood strategies strengthened in relation to climate change impacts, including variability Output 7: Improved integration of climate-resilience strategies into country development plans | 4 | 1.1. No. and type of projects that conduct and update risk and vulnerability assessments 1.2. Development of early warning systems 2.1.1. No. of staff trained to respond to, and mitigate impacts of, climate-related events 2.1.2. Capacity of staff to respond to, and mitigate impacts of, climate-related events from targeted institutions increased 2.2.1. Percentage of population covered by adequate risk-reduction systems 2.2.2. No. of people affected by climate variability 3.1 No. and type of risk reduction actions or strategies introduced at local level 3.2 No. of news outlets in the local press and media that have covered the topic 4.1. No. and type of health or social infrastructure developed or modified to respond to new conditions resulting from climate variability and change (by type) 4. 2. No. of physical assets strengthened or constructed to withstand conditions resulting from climate variability and change (by asset types) 5. No. and type of natural resource assets created, maintained or improved to withstand conditions resulting from climate variability and change (by type of assets) 6.1. No. and type of adaptation assets (physical as well as knowledge) created in support of individualor community-livelihood strategies 6.2. Type of income sources for households generated under climate change scenario 7.1. No., type, and sector of policies introduced or adjusted to address climate change risks 7.2. No. or targeted development strategies with incorporated climate change priorities enforced | 4.2 | Irrigation and drainage infrastructure is improved in 3 sites as follows: Manakambahiny: 35 km of primary canals cured, dredged, and maintained,; Bemaintso: The dam is drained and dredged; 14 km of primary canals and 21 km of secondary canals are cured, dredged, and maintained; Ambohijanahary: The dam at Anony is rehabilitated, primary water control valves are repaired; 13 km of primary canal are drained, dredged, and repaired; and primary canal is extended to irrigate 600 ha of additional rice fields. | 0 physical assets are made resilient to impacts of climate change
OBJECTIVE 2
Fund Outcome | Please select from dropdown menu below | Fund Outcome Indicator | Please select from dropdown menu below | Target at CEO Endorsement | Baseline | Mid-term Results | Terminal Results
Outcome 1: Reduced exposure at national level to climate-related hazards and threats Outcome 2: Strengthened institutional capacity to reduce risks associated with climate-induced socioeconomic and environmental losses Outcome 3: Strengthened awareness and ownership of adaptation and climate risk reduction processes at local level Outcome 4: Increased adaptive capacity within relevant development and natural resource sectors Outcome 5: Increased ecosystem resilience in response to climate change and variability-induced stress Outcome 6: Diversified and strengthened livelihoods and sources of income for vulnerable people in targeted areas Outcome 7: Improved policies and regulations that promote and enforce resilience measures | 5 | 1. Relevant threat and hazard information generated and disseminated to stakeholders on a timely basis 2.1. No. and type of targeted institutions with increased capacity to minimize exposure to climate variability risks 2.2. Number of people with reduced risk to extreme weather events 3.1. Percentage of targeted population aware of predicted adverse impacts of climate change, and of appropriate responses 3.2. Modification in behavior of targeted population 4.1. Development sectors' services responsive to evolving needs from changing and variable climate 4.2. Physical infrastructure improved to withstand climate change and variability-induced stress 5. Ecosystem services and natural assets maintained or improved under climate change and variability-induced stress 6.1. Percentage of households and communities having more secure (increased) access to livelihood assets 6.2. Percentage of targeted population with sustained climate-resilient livelihoods 7. Climate change priorities are integrated into national development strategy | 5 | 4 - Mostly Effective. Change in overall land area covered by forests (i.e. net reforestation) of at least 50km2 across the combined 3 municipalities. | 2
Fund Output | Please select from dropdown menu below | Fund Output Indicator | Please select from dropdown menu below | Target at CEO Endorsement | Baseline | Mid-term Results | Terminal Results
Output 1: Risk and vulnerability assessments conducted and updated at a national level Output 2.1: Strengthened capacity of national and regional centres and networks to respond rapidly to extreme weather events Output 2.2: Targeted population groups covered by adequate risk reduction systems Output 3: Targeted population groups participating in adaptation and risk reduction awareness activities Output 4: Vulnerable physical, natural, and social assets strengthened in response to climate change impacts, including variability Output 5: Vulnerable physical, natural, and social assets strengthened in response to climate change impacts, including variability Output 6: Targeted individual and community livelihood strategies strengthened in relation to climate change impacts, including variability Output 7: Improved integration of climate-resilience strategies into country development plans | 5 | 1. Relevant threat and hazard information generated and disseminated to stakeholders on a timely basis 2.1. No. and type of targeted institutions with increased capacity to minimize exposure to climate variability risks 2.2. Number of people with reduced risk to extreme weather events 3.1. Percentage of targeted population aware of predicted adverse impacts of climate change, and of appropriate responses 3.2. Modification in behavior of targeted population 4.1. Development sectors' services responsive to evolving needs from changing and variable climate 4.2. Physical infrastructure improved to withstand climate change and variability-induced stress 5. Ecosystem services and natural assets maintained or improved under climate change and variability-induced stress 6.1. Percentage of households and communities having more secure (increased) access to livelihood assets 6.2. Percentage of targeted population with sustained climate-resilient livelihoods 7. Climate change priorities are integrated into national development strategy | 5 | At least 5000 ha reforested across 3 districts | Limited or no reforestation activities in target areas
OBJECTIVE 3
Fund Outcome | Please select from dropdown menu below | Fund Outcome Indicator | Please select from dropdown menu below | Target at CEO Endorsement | Baseline | Mid-term Results | Terminal Results
Outcome 1: Reduced exposure at national level to climate-related hazards and threats Outcome 2: Strengthened institutional capacity to reduce risks associated with climate-induced socioeconomic and environmental losses Outcome 3: Strengthened awareness and ownership of adaptation and climate risk reduction processes at local level Outcome 4: Increased adaptive capacity within relevant development and natural resource sectors Outcome 5: Increased ecosystem resilience in response to climate change and variability-induced stress Outcome 6: Diversified and strengthened livelihoods and sources of income for vulnerable people in targeted areas Outcome 7: Improved policies and regulations that promote and enforce resilience measures |  | 1. Relevant threat and hazard information generated and disseminated to stakeholders on a timely basis 2.1. No. and type of targeted institutions with increased capacity to minimize exposure to climate variability risks 2.2. Number of people with reduced risk to extreme weather events 3.1. Percentage of targeted population aware of predicted adverse impacts of climate change, and of appropriate responses 3.2. Modification in behavior of targeted population 4.1. Development sectors' services responsive to evolving needs from changing and variable climate 4.2. Physical infrastructure improved to withstand climate change and variability-induced stress 5. Ecosystem services and natural assets maintained or improved under climate change and variability-induced stress 6.1. Percentage of households and communities having more secure (increased) access to livelihood assets 6.2. Percentage of targeted population with sustained climate-resilient livelihoods 7. Climate change priorities are integrated into national development strategy
Fund Output | Please select from dropdown menu below | Fund Output Indicator | Please select from dropdown menu below | Target at CEO Endorsement | Baseline | Mid-term Results | Terminal Results
Output 1: Risk and vulnerability assessments conducted and updated at a national level Output 2.1: Strengthened capacity of national and regional centres and networks to respond rapidly to extreme weather events Output 2.2: Targeted population groups covered by adequate risk reduction systems Output 3: Targeted population groups participating in adaptation and risk reduction awareness activities Output 4: Vulnerable physical, natural, and social assets strengthened in response to climate change impacts, including variability Output 5: Vulnerable physical, natural, and social assets strengthened in response to climate change impacts, including variability Output 6: Targeted individual and community livelihood strategies strengthened in relation to climate change impacts, including variability Output 7: Improved integration of climate-resilience strategies into country development plans |  | 1.1. No. and type of projects that conduct and update risk and vulnerability assessments 1.2. Development of early warning systems 2.1.1. No. of staff trained to respond to, and mitigate impacts of, climate-related events 2.1.2. Capacity of staff to respond to, and mitigate impacts of, climate-related events from targeted institutions increased 2.2.1. Percentage of population covered by adequate risk-reduction systems 2.2.2. No. of people affected by climate variability 3.1 No. and type of risk reduction actions or strategies introduced at local level 3.2 No. of news outlets in the local press and media that have covered the topic 4.1. No. and type of health or social infrastructure developed or modified to respond to new conditions resulting from climate variability and change (by type) 4. 2. No. of physical assets strengthened or constructed to withstand conditions resulting from climate variability and change (by asset types) 5. No. and type of natural resource assets created, maintained or improved to withstand conditions resulting from climate variability and change (by type of assets) 6.1. No. and type of adaptation assets (physical as well as knowledge) created in support of individualor community-livelihood strategies 6.2. Type of income sources for households generated under climate change scenario 7.1. No., type, and sector of policies introduced or adjusted to address climate change risks 7.2. No. or targeted development strategies with incorporated climate change priorities enforced
OBJECTIVE 4
Fund Outcome | Please select from dropdown menu below | Fund Outcome Indicator | Please select from dropdown menu below | Target at CEO Endorsement | Baseline | Mid-term Results | Terminal Results
Outcome 1: Reduced exposure at national level to climate-related hazards and threats Outcome 2: Strengthened institutional capacity to reduce risks associated with climate-induced socioeconomic and environmental losses Outcome 3: Strengthened awareness and ownership of adaptation and climate risk reduction processes at local level Outcome 4: Increased adaptive capacity within relevant development and natural resource sectors Outcome 5: Increased ecosystem resilience in response to climate change and variability-induced stress Outcome 6: Diversified and strengthened livelihoods and sources of income for vulnerable people in targeted areas Outcome 7: Improved policies and regulations that promote and enforce resilience measures |  | 1. Relevant threat and hazard information generated and disseminated to stakeholders on a timely basis 2.1. No. and type of targeted institutions with increased capacity to minimize exposure to climate variability risks 2.2. Number of people with reduced risk to extreme weather events 3.1. Percentage of targeted population aware of predicted adverse impacts of climate change, and of appropriate responses 3.2. Modification in behavior of targeted population 4.1. Development sectors' services responsive to evolving needs from changing and variable climate 4.2. Physical infrastructure improved to withstand climate change and variability-induced stress 5. Ecosystem services and natural assets maintained or improved under climate change and variability-induced stress 6.1. Percentage of households and communities having more secure (increased) access to livelihood assets 6.2. Percentage of targeted population with sustained climate-resilient livelihoods 7. Climate change priorities are integrated into national development strategy
Fund Output | Please select from dropdown menu below | Fund Output Indicator | Please select from dropdown menu below | Target at CEO Endorsement | Baseline | Mid-term Results | Terminal Results
Output 1: Risk and vulnerability assessments conducted and updated at a national level Output 2.1: Strengthened capacity of national and regional centres and networks to respond rapidly to extreme weather events Output 2.2: Targeted population groups covered by adequate risk reduction systems Output 3: Targeted population groups participating in adaptation and risk reduction awareness activities Output 4: Vulnerable physical, natural, and social assets strengthened in response to climate change impacts, including variability Output 5: Vulnerable physical, natural, and social assets strengthened in response to climate change impacts, including variability Output 6: Targeted individual and community livelihood strategies strengthened in relation to climate change impacts, including variability Output 7: Improved integration of climate-resilience strategies into country development plans |  | 1.1. No. and type of projects that conduct and update risk and vulnerability assessments 1.2. Development of early warning systems 2.1.1. No. of staff trained to respond to, and mitigate impacts of, climate-related events 2.1.2. Capacity of staff to respond to, and mitigate impacts of, climate-related events from targeted institutions increased 2.2.1. Percentage of population covered by adequate risk-reduction systems 2.2.2. No. of people affected by climate variability 3.1 No. and type of risk reduction actions or strategies introduced at local level 3.2 No. of news outlets in the local press and media that have covered the topic 4.1. No. and type of health or social infrastructure developed or modified to respond to new conditions resulting from climate variability and change (by type) 4. 2. No. of physical assets strengthened or constructed to withstand conditions resulting from climate variability and change (by asset types) 5. No. and type of natural resource assets created, maintained or improved to withstand conditions resulting from climate variability and change (by type of assets) 6.1. No. and type of adaptation assets (physical as well as knowledge) created in support of individualor community-livelihood strategies 6.2. Type of income sources for households generated under climate change scenario 7.1. No., type, and sector of policies introduced or adjusted to address climate change risks 7.2. No. or targeted development strategies with incorporated climate change priorities enforced

## Units for Indicators
Fund Outcome Indicator Units
1. Generation of relevant data, Stakeholders, and Timeliness 2.1. Include both qualitative and quantitative measures of capacity level within targeted institutions 2.2. Number (men and women and other vulnerable groups) 3.1. Use scale from 1 to 5: 5: Fully aware 4: Mostly aware 3: Partially aware 2: Partially not aware 1: Aware of neither predicted adverse impacts of climate change nor of appropriate responses 3.2. Use scale from 1 to 5: 5: All 4: Almost all 3: Half 2: Some 1: None 4.1. Summarize in an overall scale (1-5): 5: Highly responsive (All defined elements ) 4: Mostly responsive (Most defined elements) 3: Moderately responsive (Some defined elements) 2: Partially responsive (Lacks most elements) 1: Non responsive (Lacks all elements ) 4.2. Summarize in an overall scale (1-5): 5: Fully improved 4: Mostly Improved 3: Moderately improved 2: Somewhat improved 1: Not improved 5. Depends on the targeted natural asset: Biological (species): measure through changes in population numbers (dynamics, structure, etc.) Land: measure changes in hectares. Baseline data will be necessary to estimate the change. Supporting indicators baseline and target (as well as contextual information) are needed such as the following: Farmers adopting recommended technologies, Ha. of land improved, Average deforestation rate Etc. Use scale from 1 to 5. 5: Very effective (All elements are present) 4: Effective (Most elements are present) 3: Moderately effective (Some elements are present) 2: Partially effective (Most elements are not present) 1: Ineffective (No elements are present) 6.1. Summarize in an overall scale (1-5): 5: Very high improvement 4: High improvement 3: Moderate improvement 2: Limited improvement 1: No improvement 6.2. Household income by source of livelihood in project area (USD) prior and post project intervention 7. Summarize in an overall scale (1-5). 5: All (Fully integrated) 4: Most 3: Some 2: Most not integrated 1: None
Fund Output Indicator Units
1.1. Number, sector(s) and level(s) of projects or interventions in separate fields of monitoring plan 1.2. Number 2.1.1. Number of staff (male/female) of targeted institutions: a. Obtain baseline information: total number of staff from targeted institutions b. Define target 2.1.2. Number of staff (male/female) of targeted institutions: a. Obtain baseline information: total number of staff from targeted institutions b. Define target: needs to be defined by project proponents 2.2.1. Quantitative: Percentage (includes women – and other vulnerable groups – and men). Qualitative: Adequacy: include direct analysis of major areas; adequacy/effectiveness of systems or analysis of perceptions of populations and institutions. 2.2.2. Number (broken down by gender and, if possible, by vulnerable groups defined in the area of intervention) of people 3.1. Number and type (in separate columns) at local level. 3.2. Number 4.1. Number and type 4. 2. Number and type (entered in separate columns) 5. Number of interventions by type of natural asset and intervention 6.1. Number and type (in separate columns of monitoring plan) 6.2. Income sources per household; description of income source and number of households. 7.1. Number/Sector 7.2. Number; Effectiveness (see previous indicator) through enforcement level.