## Overview
Project Performance Report (PPR)
| Period of Report (Dates) | 01 November 2012 to 31 October 2013
| Project Title: | Implementation of Concrete Adaptation Measures to Reduce Vulnerability of Livelihoods and Economy of Coastal Communities of Tanzania
| Project Summary: | Tanzania is impacted by climate change mainly through its effects on rainfall patterns, temperature extremes and sea level rise. The direct impacts of these changes are likely to result in more frequent and intense droughts, the destruction of infrastructures in the coast and inland through flooding, inundation, erosion and storms; if no action is taken, the socio-economic impacts will include agricultural yield decreases, decreased water availability and quality, and losses of lives and livelihoods, as well as the accelerated degradation of ecosystems that form the basis of the Tanzanian economy. To respond to this, the government developed a project proposal to adapt to the climate change in the coast of Dar es salaam. In December the Adaptation Fund Board considered the proposal and approved a five years project with a total of USD 5,008,564. Implementation of the project started in November 2012. The project consists of the following outcomes, supported by on the ground activities implemented primarily in the vicinity of Dar Es Salaam: 1. Adverse impacts of SLR and floods on coastal infrastructures and settlements are reduced. 2. Coastal ecosystems are rehabilitated and Integrated Coastal Area Management is implemented. 3. Knowledge of climate impacts and adaptation is increased. The project is being implemented by the United Nations Environment Programme (UNEP) and executed by the Vice Presidents Office (Division of Environment) in close cooperation with sectoral ministries as well as Dar es Salaam City Council.
|  |  | Countries | Project Type: |  | GEF Focal Area: | GEF 4 Focal Areas | GEF 2 / 3 Operational Programme: | Overall Rating of the project in the evaluation by the project evaluator: | GEF-4 Focal Area Strategic Program: | GEF-3 Focal Area Strategic Program:
| Database Number: | AFB-5060-1111-2G48 | Afghanistan | FP | Yes | Biodiversity | 1 | 1 | U | BD-SP1-PA Financing | 1: Arid & semi-arid ecosystems
Implementing Entity (IE) [name]: |  | UNEP | Albania | MSP | No | Climate Change Adaptation | 2 | 2 | S | BD-SP2-Marine PA | 2: Coastal, marine & freshwater ecosystems
| Type of IE: | MIE | Algeria | EA |  | Climate Change Mitigation | 3 | 3 | MU | BD-SP3-PA Networks | 3: Forest ecosystems
| Country(ies): | United Republic of Tanzania | Angola |  |  | International Waters | 5 | 5 | Good | BD-SP5-Markets | 13: Conservation and Sustainable Use of Biological Diversity Important to Agriculture
Relevant Geographic Points (i.e. cities, villages, bodies of water): |  | Dar es Salaam City (city centre, Ocean Road and Kigamboni-Mwalimu Nyerere Memorial Institute) | Argentina |  |  | Multiple Focal Area |  |  |  | BD-SP7-Invasive Alien Species(IAS) | 6: Promoting the adoption of renewable energy by removing barriers and reducing implementation costs
[8 empty] | CC-SP2- Industrial EE | 8: Waterbody based operational program
| Project Milestones | [6 empty] | CC-SP3-RE,CC-SP4-Biomass | 9: Integrated Land and Water multiple focal area
| Milestone |  | Bahamas | [6 empty] | CC-SP5-Transport | 10: Contaminants based operational program
AFB Approval Date: |  | 2011-12-14
IE-AFB Agreement Signature Date: |  | 2012-02-29 | [6 empty] | CC-SP6-LULUCF | 12: Integrated Ecosystem Management
Start of Project/Programme: | [8 empty] | Cross cutting capacity building | 14: Persistent Organic Pollutants
Mid-term Review Date (if planned): |  | May 1, 2015 (MTR), November 1, 2017 (Terminal)
Terminal Evaluation Date:
|  | List documents/ reports/ brochures / articles that have been prepared about the project. | Cyprus
|  | Inception Workshop Report, 2012; Quarterly Expenditure Reports (Q4, 2012, Q1,Q2,Q3&Q4, 2013); Project brief report to the Planning Commission of the United Republic of Tanzania for the Government year 2012/2013; TORs of: Project Steering Committee; National Project Coordinator; Senior Technical Adviser; Finance and Administrative Assistant; Feasibility Study and EIA for the proposed Construction and Rehabilitation of Seawall at Ocean Road and Kigamboni (Mwalimu Nyerere Memorial Institute) and Rehabilitation of Drainage Systems; Baseline Survey and Development of Indicators and Targets; Climate Change Knowledge Management Specialist; Coastal Zone Management Specialist; Sub-Contract Coastal Engineering Firm for Seawall Rehabilitation and Construction; and Sub Contract: Civil Engineering Firm for Drainage Rehabilitation; Tender Evaluation Report for Supply of the Project Vehicle 4WD Double Cabin (Tender No. ME 02/2013-2014/DE/G/01),2013; Evaluation Report of Expression of Interest Tender No. ME 002/2012 -13/DE/C/07 for a position of a senior technical adviser and Tender No. ME 002/2012-13/DE/C/07 for Consultancy services for Development of a baseline survey and development of indicators and targets | Czech Republic
List the Website address (URL) of project. |  |  | Democratic People's Republic of Korea
|  | http://www.unep.org/climatechange/adaptation/AccessToAdaptationFinance/AdaptationFundProjects/Tanzania | Democratic Republic of the Congo
Denmark
| Project contacts: |  | Djibouti
National Project Manager/Coordinator |  |  | Dominica
| Name: | Eng. Ladislaus Kyaruzi | Dominican Republic
| Email: | leoky2009@gmail.com | Ecuador
| Date: | 2013-10-31 | Egypt
| Government DA |  | El Salvador
| Name: | Eng. Ngosi C.X. Mwihava | Equatoral Guinea
| Email: | nmwihava@gmail.com | Eritrea
| Date: | 2013-10-31 | Estonia
| Implementing Entity |  | Ethiopia
| Name: | Lars Christiansen, UNEP task manager | Fiji
| Email: | lachr@dtu.dk | Finland
| Date: | 2013-10-31 | France
| Executing Agency |  | Gambia
| Name: | Vice President's Office | Georgia
| Email: | ps@vpo.go.tz | Germany
| Date: | 2013-10-31 | Ghana
| Executing Agency |  | Greece
| Name: |  | Grenada
| Email: |  | Guatemala
| Date: |  | Guinea
| Executing Agency |  | Guinea Bissau
| Name: |  | Guyana
| Email: |  | Haiti
| Date: |  | Honduras
Hungary
Iceland
India
Indonesia
Iran (Islamic Republic of)
Iraq
Ireland
Israel
Italy
Jamaica
Japan
Jordan
Kazakhstan
Kenya
Kiribati
Kuwait
Kyrgyzstan
Lao People’s Democratic Republic
Latvia
Lebanon
Lesotho
Liberia
Libyan Arab Jamahiriya
Liechtenstein
Lithuania
Luxembourg
Madagascar
Malawi
Malaysia
Maldives
Mali
Malta
Marshall Islands
Mauritania
Mauritius
Mexico
Micronesia, Federated States of
Monaco
Mongolia
Montenegro
Morocco
Mozambique
Myanmar
Namibia
Nauru
Nepal
Netherlands
New Zealand
Nicaragua
Niger
Nigeria
Norway
Oman
Pakistan
Palau
Panama
Papua New Guinea
Paraguay
Peru
Philippines
Poland
Portugal
Qatar
Republic of Korea
Republic of Moldova
Romania
Russian Federation
Rwanda
Saint Kitts and Nevis
Saint Lucia
Saint Vincent and the Grenadines
Samoa
San Marino
Sao Tome and Principe
Saudi Arabia
Senegal
Serbia
Seychelles
Sierra Leone
Singapore
Slovakia
Slovenia
Solomon Islands
Somalia
South Africa
Spain
Sri Lanka
Sudan
Suriname
Swaziland
Sweden
Switzerland
Syrian Arab Republic
Tajikistan
Thailand
The former Yugoslav Republic of Macedonia
Timor-Leste
Togo
Tonga
Trinidad and Tobago
Tunisia
Turkey
Turkmenistan
Tuvalu
Uganda
Ukraine
United Arab Emirates
United Kingdom of Great Britain and Northern Ireland
United Republic of Tanzania
United States of America
Uruguay
Uzbekistan
Vanuatu
Venezuela, Bolivarian Republic of
Viet Nam
Yemen
Zambia
Zimbabwe

## FinancialData
Financial information: cumulative from project start to 30 October 2013
DISBURSEMENT OF AF GRANT FUNDS
How much of the total AF grant as noted in Project Document plus any project preparation grant has been spent to date?
Estimated cumulative total disbursement as of 31 October 2013(USD)* | 60919
Add any comments on AF Grant Funds. (word limit=200)
EXPENDITURE DATA
List ouput and corresponding amount spent for the current reporting period | ITEM / ACTIVITY / ACTION | AMOUNT
| Output 1.1: Sea wall raised or rehabilitated in areas showing particular damage | 0
| Output 1.2: Effective storm and flood drainage systems in urban areas and near coastal communities | 0
| Output 2.1: Appropriate alternative energy (efficient cookstoves, small solar) technology transferred | 0
| Output 2.2: Mangrove rehabilitation through planting of resilient seedlings, dredging and the creation of no-take buffer zones;degraded coral reefs rehabilitated and protected | 0
| Output 2.3: Shoreline rehabilitated and stabilized using trees and grasses | 0
| Output 3.1: Performance of a baseline study | 0
| Output 3.2: A climate change coastal observatory for Tanzania for ongoing monitoring of CZM and Coastal environmental status and scientific research | 0
| Output 3.3: Lessons learned from the project outputs documented | 9662
| Output 3.4: District level administration have the capacity to adequately manage rehabilitated infrastructure | 0
| Output 3.5: One EBICAM plan for the coastal region approved | 0
| Project Execution | 51257.42
| GRAND TOTAL* | 60919.42
* Project expenditure reporting is done on quarterly basis. Expenditures reported in this PPR are therefore for the period project start - September 30, 2013. Expenditures for October 2013 will be included in the next PPR.
PLANNED EXPENDITURE SCHEDULE
List outputs planned and corresponding projected cost for the upcoming reporting period | ITEM / ACTIVITY / ACTION | PROJECTED COST | Est. Completion Date
| Output 1.1: Sea wall raised or rehabilitated in areas showing particular damage | 388000 | 2014-10-31
| Output 1.2: Effective storm and flood drainage systems in urban areas and near coastal communities | 103000 | 2014-10-31
| Output 2.1: Appropriate alternative energy (efficient cookstoves, small solar) technology transferred | 52500 | 2014-10-31
| Output 2.2: Mangrove rehabilitation through planting of resilient seedlings, dredging and the creation of no-take buffer zones;degraded coral reefs rehabilitated and protected | 27600 | 2014-10-31
| Output 2.3: Shoreline rehabilitated and stabilized using trees and grasses | 0
| Output 3.1: Performance of a baseline study | 20000 | 2014-04-30
| Output 3.2: A climate change coastal observatory for Tanzania for ongoing monitoring of CZM and Coastal environmental status and scientific research | 8000 | 2014-10-31
| Output 3.3: Lessons learned from the project outputs documented | 14919 | 2014-10-31
| Output 3.4: District level administration have the capacity to adequately manage rehabilitated infrastructure | 15000 | 2014-10-31
| Output 3.5: One EBICAM plan for the coastal region approved | 25000 | 2014-10-31
| Project Execution | 136449.74 | 2014-10-31
| GRAND TOTAL | 790468.74
ACTUAL CO-FINANCING (If the MTR or TE have not been undertaken this reporting period, DO NOT report on actual co-financing.)
How much of the total co-financing as committed in the Project Document has actually been realized? | Co-financing is non applicable to the project
Estimated cumulative actual co-financing as verified during Mid-term Review (MTR) or Terminal Evaluation (TE).
Add any comments on actual co-financing in particular any issues related to the realization of in-kind, grant, credits, loans, equity, non-grant instruments and other types of co-financing. (word limit=200)

## Risk Assesment
RISK ASSESMENT
IDENTIFIED RISKS
List all Risks identified in project preparation phase and what steps are being taken to mitigate them
Identified Risk | Current Status | Steps Taken to Mitigate Risk
Operational: The multiple ongoing initiatives on climate adaptation in Tanzania could cause operational delays for this project | Low | The inception workshop was held from 29-30 October 2012 that brought about 45 participants from different key ministries, institutions and organizations to agreeing on key roles of various stakeholders during the implementation of the project and identify activities that can complement the project activities. Additionally, the government has appointed the National Project Coordinator, Senior Technical Adviser and assistant administrative and financial manager as a dedicated team for project coordination to ensure that the project maintains its objectives.
Political: District-level stakeholders and administrations show low engagement for adaptation measures | Low | The Project Steering Committee been established among others, to provide overall guidance with regard to implementation of the project activities. Its members are: Permanent Secretary– Vice President’s Office (Chair); Director of Environment-Vice President’s Office; Director of Environment- First Vice President’s Office –Zanzibar; Director- Dar es Salaam City Council; District Executive Director – Pangani District Council; District Executive Director – Bagamoyo District Council; District Executive Director – Rufiji District Council; Municipal Executive Director – Temeke Municipal Council; Municipal Executive Director – Ilala Municipal Council; Director of Forest – Ministry of Natural Resources and Tourism; Director of Water Resources – Ministry of Water; Director- Ministry of Works;; UNEP Task Manager of the Project; and Assistant Director of Environmental Assessment- Vice President’s Office (Secretary). Also, Dar es Salaam City Council has appointed a focal person for this project.
Political: the project could experience difficulties in coordination and oversight for activities delivered at various sectors, levels of governments or by multiple partners | Low | The dedicated personnel for project management that has been established through the Vice President‘s Office will coordinate and monitor the project outputs and activities. Close collaboration among various ministries and stakeholders will be provided through among others the project steering committee.
Environmental: Extreme weather events such as tropical storms, floods or droughts could hinder progress in ecosystem rehabilitation and infrastructure activities | Medium | Protective infrastructure rehabilitation will be designed according to the best available technical standards and using the best available technology. The baseline study and feasibility study being undertaken will provide appropriate data and information to be used.
Financial: market and price fluctuations could cause price variations and variations in costs of certain project activities, leading to budgetary constraints. | Low | The feasibility study and Environmental Impact Assessment (EIA) will develop a financial risk strategy and contingency plans.
Critical Risks Affecting Progress (Not identified at project design)
Identify Risks with a 50% or > likelihood of affecting progress of project
Identified Risk | Current Status | Steps Taken to Mitigate Risk
Vice President's Office "the executing entity" low executions rate due to internal procurement procedures. | High | During the first year of project implementation the project has experienced severe delays due to slow procurement procedures within VPO. This was the result of a number of factors, including: 1. Inability to include project procurement in VPOs annual procurement plan from inception until mid 2013 (VPO regular planning years run from July-June), 2. Intricate procurement rules of the Tanzania national procurement act, which are being followed consistent with the national execution modalities of the project, 3. Lack of formal partnership with the VPO procurement unit to create streamlined and dedicated processes for the project (e.g. on-demand meetings of the procurement board). These factors in turn delayed execution of key contracts such as hiring of the Chief technical advisor (not hired until October 2013) and baseline study (expected contract signature in January 2014). The following measures are being taken to assure these issues will not affect implementation going forward: 1. For 2013/2014 project activities have been included in the annual work plan of the Office. 2: Consultations are ongoing with procurement unit counterparts to agree on fast-track procedures for project procurement and to set up a formal partnership (including a small budget allocation) to assure timely and dedicated procurement support. With these measures, it is expected that procurement of minor contracts (below $100,000) will be completed in around 1 month going forward.
Risk Measures: Were there any risk mitigation measures employed during the current reporting period? If so, were risks reduced? If not, why were these risks not reduced?
Add any comments relevant to risk mitigation (word limit = 500)

## Rating
RATING ON IMPLEMENTATION PROGRESS
For rating definitions please see bottom of page.
| Progress on Key Milestones |  | Expected Progress |  | Progress to Date | Rating
Project Manager/Coordinator: | Component 1 - Addressing climate change impacts on key infrastructure and settlements
| Rehabilitate, construct and upgrade coastal protection facilities to protect settlements economic and cultural infrastructure |  | Undertake EIA and feasibility study. Contract an engineering firm. Rehabilitate, construct and upgrade 1335 linear meters of seawall along the Ocean Road (Kivukoni-Upanga East) and Kigamboni (Mwalimu Nyerere Memorial Academy-staff quarters) |  | TORs of the engineering firm to rehabilitate, upgrade and construct developed. TORs of EIA and feasibility study developed. Procurement of a firm to undertake EIA and feasibility study in progress. | MS
| Cleaning up of the drainage channels, rehabilitation of storm drains |  | Develop TORs of the engineering firm Undertake EIA and feasibility study Contract an engineering firm Cleaning and maintenance of the drainage channels in Dar es salaam city centre Rehabilitate the storm drains in Dar es salaam city centre |  | TORs of the engineering firm to clean the drainage channels and rehabilitate strom drains developed. TORs of EIA and feasibility study developed. Procurement of a firm to undertake EIA and feasibility study in progress. | MS
Component 2 – Ecosystem-based Integrated Coastal Area Management
| Mangrove rehabilitation |  | Planting of resilient seedlings Dredging and clean-up operations Provision of small solar equipment Distribute fuel efficient cookstoves to 1,500 households Training members of households and small enterprises on fuel efficient technologies |  | TORs of coastal zone management specialist developed. | MU
| Coral reef rehabilitation and protection |  | Coral reefs rehabilitation Training fisheries and local government officers on coral reef conservation |  | TORs of coastal zone management specialist developed. | MU
| Shoreline stabilization through reforestation |  | Re-planting of native and resilient trees |  | TORs of coastal zone management specialist developed. | MU
Component 3 – Knowledge, coastal monitoring and policy linkages
| Stocktaking |  | Undertake baseline survey and development of indicators and targets. Undertake EIA and feasibility study. Develop a database of information relevant to adaptation in Tanzania |  | TORs of the consultancy to undertake baseline study develooped. TORs of EIA and feasibility study developed. Procurement of the firm or individual to undertake baseline study is in progress after re-advertizement. Procurement of a firm to undertake EIA and feasibility study in progress. | MS
| Coastal monitoring and assessment |  | Technical assessment of the vibility and resilience of proposed actions. Monitoring the key determinants of vulnerability i.e. SLR, water availability and precipitation patterns. Create Climate Change Observatory for Tanzania (CCOT) |  |  | MU
| Policy linkages |  | Document lessons learned from project outputs. Review infrastructure maintenance programs of Dar es Salaam City, Temeke, Kinondoni and Ilala Municalities. Develop an Ecosystem-Based Integrated Coastal Area Management Action Plan (EBICAM). |  | TORs of climate change knowledge management specialist developed. | MU
Project operation and management
| Procurement |  | Prepare procurement plans Procure consultancies Procure firms for goods and works services |  | Procurement Plan for 2013 prepared. Office supplies, computers and assoceries procured. Project car is being procured. Procurement Plan for 2014 being developed. | MU
| Establish project management team |  | Establish the National project management team. Identify the Senior Technical Adviser (STA) of the project. Establish Project Steering Committee |  | The National Project Coordinator has been identified. The project finance and administration assistant has been identified. The International Senior Technical Adviser has been appointed. The project steering committee formed. | S
[5 empty] | Overall Rating | MS
Please Provide the Name and Contact information of person(s) reponsible for completeling the Rating section
| Name: | Eng. Ladislaus Kyaruzi
| Email: | leoky2009@gmail.com
Please justify your rating. Outline the positive and negative progress made by the project since it started. Provide specific recommendations for next steps. . (word limit=500)
During 1st year of implementation, the Vice President's Office focused on raising awareness on the project activities with key stakeholders to be involved in project implementation. Procrement of key personnel was a key focus where formalising the arrangements took time and is the reason for the delay in project delivery relative to what was outlined when the project document was submitted for Board approval in Dec 2011. The arrangements that have been put in place include the following: 1- The National Project Coordinator will be responsible for the overall day to day management of the project; Finance and administration assistant will provide finance and adminsitration support; Senior Trechnical Adviser will provide overall technical guidance and support; and Focal person at Dar es salaam City Council will support overall implementation of the project activities in his areas. 2-Project Steering Committee has members from Vice President's Office, Dar es Salaam City and its three municipalities, Ministry of Works, ministry of Natural Resources and Tourism. In addition, project implementation from November 2012 to October 2013 has been relatively low because the of the largest bid processes of the particular hard works are scheduled for the second year. - The baseline study consultancy procuring has been extended sice the short listed firms did not submit the technical and financial proposal. Consequesntly the bid was re-advertized. To date, the evaluation of the applications for the baseline consultancy is in process.
| Progress on Key Milestones |  | Expected Progress |  | Progress to Date | Rating
Implementing Agency | Component 1 - Addressing climate change impacts on key infrastructure and settlements
| Rehabilitate, construct and upgrade coastal protection facilities to protect settlements economic and cultural infrastructure |  | Undertake EIA and feasibility study. Contract an engineering firm. Rehabilitate, construct and upgrade 1335 linear meters of seawall along the Ocean Road (Kivukoni-Upanga East) and Kigamboni (Mwalimu Nyerere Memorial Academy-staff quarters) |  | TORs of the engineering firm to rehabilitate, upgrade and construct developed. TORs of EIA and feasibility study developed. Procurement of a firm to undertake EIA and feasibility study in progress. | MU
| Cleaning up of the drainage channels, rehabilitation of storm drains |  | Develop TORs of the engineering firm Undertake EIA and feasibility study Contract an engineering firm Cleaning and maintenance of the drainage channels in Dar es salaam city centre Rehabilitate the storm drains in Dar es salaam city centre |  | TORs of the engineering firm to clean the drainage channels and rehabilitate strom drains developed. TORs of EIA and feasibility study developed. Procurement of a firm to undertake EIA and feasibility study in progress. | MU
Component 2 – Ecosystem-based Integrated Coastal Area Management
| Mangrove rehabilitation |  | Planting of resilient seedlings Dredging and clean-up operations Provision of small solar equipment Distribute fuel efficient cookstoves to 1,500 households Training members of households and small enterprises on fuel efficient technologies |  | TORs of coastal zone management specialist developed. | MU
| Coral reef rehabilitation and protection |  | Coral reefs rehabilitation Training fisheries and local government officers on coral reef conservation |  | TORs of coastal zone management specialist developed. | MU
| Shoreline stabilization through reforestation |  | Re-planting of native and resilient trees |  | TORs of coastal zone management specialist developed. | MU
Component 3 – Knowledge, coastal monitoring and policy linkages
| Stocktaking |  | Undertake baseline survey and development of indicators and targets. Undertake EIA and feasibility study. Develop a database of information relevant to adaptation in Tanzania |  | TORs of the consultancy to undertake baseline study develooped. TORs of EIA and feasibility study developed. Procurement of the firm or individual to undertake baseline study is in progress after re-advertizement. Procurement of a firm to undertake EIA and feasibility study in progress. | U
| Coastal monitoring and assessment |  | Technical assessment of the vibility and resilience of proposed actions. Monitoring the key determinants of vulnerability i.e. SLR, water availability and precipitation patterns. Create Climate Change Observatory for Tanzania (CCOT) |  |  | MU
| Policy linkages |  | Document lessons learned from project outputs. Review infrastructure maintenance programs of Dar es Salaam City, Temeke, Kinondoni and Ilala Municalities. Develop an Ecosystem-Based Integrated Coastal Area Management Action Plan (EBICAM). |  | TORs of climate change knowledge management specialist developed. | MU
Project operation and management
| Procurement |  | Prepare procurement plans Procure consultancies Procure firms for goods and works services |  | Procurement Plan for 2013 prepared. Office supplies, computers and assoceries procured. Project car is being procured. Procurement Plan for 2014 being developed. | U
| Establish project management team |  | Establish the National project management team. Identify the Senior Technical Adviser (STA) of the project. Establish Project Steering Committee |  | The National Project Coordinator has been identified. The project finance and administration assistant has been identified. The International Senior Technical Adviser has been appointed. The project steering committee formed. | MS
[5 empty] | Overall Rating | MU
Please Provide the Name and Contact information of person(s) reponsible for completeling the Rating section
| Name: | Lars Christiansen, UNEP TM
| Email: | lachr@dtu.dk
| Progress on Key Milestones |  | Expected Progress |  | Progress to Date | Rating
Other
Overall Rating
Please Provide the Name and Contact information of person(s) reponsible for completeling the Rating section
Name:
Email:
Please justify your rating and address the following points: 1. Indicate trends, both positive and negative, in achievement of outcomes as per the project indicators. 2. Detail critical risks that have affected progress. 3. Outline response to MTR undertaken this reporting period. 4. Outline action plan to address projects with a rating of HU, U or MU. Please keep your input to 1200 words
Rating Definitions
|  |  | Highly Satisfactory (HS) | Project actions/activities planned for current reporting period are progressing on track or exceeding expectations to acheive all major outcomes/outputs for given reporting period, without major shortcomings. The project can be presented as “good practice”.
|  |  | Satisfactory (S) | Project actions/activities planned for current reporting period are progressing on track to achieve most of its major outcomes/outputs with only minor shortcomings.
|  |  | Marginally Satisfactory (MS) | Project actions/activities planned for current reporting period are progressing on track to achieve most major relevant outcomes/outputs, but with either significant shortcomings or modest overall relevance.
|  |  | Marginally Unsatisfactory (MU) | Project actions/activities planned for current reporting period are not progressing on track to achieve major outcomes/outputs with major shortcomings or is expected to achieve only some of its major outcomes/outputs.
|  |  | Unsatisfactory (U) | Project actions/activities planned for current reporting period are not progressing on track to achieve most of its major outcomes/outputs.
|  |  | Highly Unsatisfactory (U) | Project actions/activities planned for current reporting period are not on track and shows that it is failing to achieve, and is not expected to achieve, any of its outcomes/outputs.

## Project Indicators
PROJECT Indicators
Please provide all indicators being tracked for the project as outlined in the project document
Type of Indicator (indicators towards Objectives, Outcomes, etc…)
Type of Indicator | Indicator | Baseline | Progress since inception | Target for Project End
Component 1 - Addressing climate change impacts on key infrastructure and settlements
| Length of sea walls raised and rehabilitated (m) | Dar es salaam seawall (2.6km) showing signs of severe degradation at Ocean Road and Kingomboni | TORs of the engineering firm to rehabilitate, upgrade and construct developed. TORs of EIA and feasibility study developed. Procurement of a firm to undertake EIA and feasibility study in progress. | 1335 linear meters of seawall rehabilitated along Ocean Road and Kingamboni
| Change in number of urban flooding events related to storm and severe rainfall | Average of 5 flooding events in Dar es Salaam city center during rainy seasons over the past 5 years | TORs of the engineering firm to clean the drainage channels and rehabilitate strom drains developed. TORs of EIA and feasibility study developed. Procurement of a firm to undertake EIA and feasibility study in progress. | a 50% reduction in the number of flooding events during rainy season.
Component 2 - Ecosystem-Based Integrated Coastal Area Management (EBICAM)
| % change in fuelwood use; Number of people with access to alternative or efficient energy sources (disagregated ed by gender) | Average wood fuel consumption per capita in Tanzania is 1 to 1.3m3; fuelwood efficiency is estimated at less than 10% on average in all sites; estimated mangrove deforestation rate is 2% per year | Scheduled for the second year. | at least 30% decrease in use of fuelwood; 1500 households have access to alternative and or efficient energy sources
| area of mangroves under rehabilitation | there are approximately 2,000 ha of mangroves in Dar es Salaam surroundings | TORs of coastal zone management specialist developed. | 40 hectares of mangroves under rehabilitation in severely degraded strands in Dar es Salaam area
| area of reef rehabilitated | No recent local data available. Latest data sets show low biocover in existing reefs | TORs of coastal zone management specialist developed. | 2000 m2 in front of Dar es Salaam, with an increase of 75% annually
| Km of shoreline stabilized using vegetation | rate of coastal erosion estimated between 3 and 8m per year according to recent site specific surveys | TORs of coastal zone management specialist developed. | 30,000m2 in Dar broader area
Component 3 - Knowledge, coastal monitoring and policy linkages
| availability of a comprehensive baseline study for coastal vulnerability; available knowledge gathered | no such study; there is no recent comprehensive desk review of available knowledge | The process to procure a firm to undertake baseline survey and development of indicators and targets in progress. | 1 baseline study in year 1
| Effective implementation of clearing house function | There is no climate change clearing house mechanism | Planned by mid-term of the project. | clearing house function is operational by mid-term
| Cost-effective measures are identified for upscaling and policy uptake | ad hoc assessments available but none specific to this project |  | measures are identified for upscaling and policy uptake on an ongoing basis
| number of policy briefs provided to key sectors and regulators; number of workshops | While there is a good degree of information on climate change, there is no systematic effort to inform policy makers based on project utcomes | Inception workshop held. | 3 briefing notes per year; 2 workshops during the project
| Amount dedicated to infrastructure maintenance from district budgets | infrastructure budgets within district administrations are low |  | Dar es Salaam Municipal councils earmarks appropriate annual allocations for infrastructure maintenance.
| Number of plans approved | no plans yet available but ICZM capacity exists |  | 1 plan

## Lessons Learned
QUALITATIVE MEASURES and LESSONS LEARNED
Please complete the following section every reporting period
Implementation and Adaptive Management | Response
What implementation issues/lessons, either positive or negative, affected progress? | Establishment of a project technical committee with delegates from Dar City Council, University of Dar es Salaam, Mwalimu Nyerere Memorial Acadamy (site of Kagamboni sea wall) as well as LDCF project stakeholders has strenghtened sustainability, created ownership and helped the team to identify and overcome project challenges. This is expected to be a strong supplement to the more politically focused project steering committee. A further lesson is that the project development and early implementation preparation should have been more aware of procurement risks and have acted earlier to setup systems to handle these in advance. The pros and cons of working within national procurement systems (as opposed e.g. to UN systems) should be carefully considered. Another lesson related to procurement is that it could be useful to pro-actively create a pool of approved experts from which national procurement can be facilitated.
Were there any delays in implementation? If so, include any causes of delays. What measures have been taken to reduce delays? | As mentioned in the risk assessment section, procurement have been the primary cause of delays evident in this project. Getting the Chief Technical Advisor (CTA) on board to assist the project team in validating the implementation strategy, budget and key TOR (not least those related to the sea wall and drainage construction work) has been a high priority for all parties. Delays in hiring of the CTA (and partly the consultant to conduct the baseline study, which is also crucial to moving forward) has thus blocked further progress on other activities. With the CTA on board from November 2013 (first in-county mission early December) and baseline study planned for completion Q1 2014 - this important barrier will be removed allowing progress on other activities. Please refer to risk assessment section for measures implemented to increase effectiveness of procurement going forward.
Describe any changes undertaken to improve results on the ground or any changes made to project outputs (i.e. changes to project design) | No changes undertaken to date.
How have gender considerations been taken into consideration during the reporting period? What have been the lessons learned as a consequence of inclusion of such considerations on project performance or impacts? | Within the national team, a finance and administration assistant is a woman which is equal to 50%. In the national inception workshop, approximately 32% of the participants were women.
Lessons and measures related to coordination with the LDCF project 'Developing core capacity to address adaptation to climate change in Tanzania in productive coastal zones' | The LDCF and AF projects are very closely coordinated, and in practice implemented almost as one. A joint project coordination team has been established at VPO, with one project coordinator handling the AF project and one handling the LDCF project. The two are reporting to, and coordinated through, the assistant director of environment mr Richard Muyungi. In practice the three are working very closely on a daily basis – i.e. sitting in the same office, having joint meetings etc. Additional examples of the close coordination and collaboration taking place between the two projects include: Joint project steering committee with joint meetings, joint technical committee, joint baseline study (to be conducted in Q2 2014), a shared Chief Technical advisor etc. All of this reduces costs, and assures that relevant lessons, outputs and expertise are consistently shared between the two projects. All joint activities and financial contributions are proportionately shared and kept completely separate to avoid co-mingling.
Please complete the following section at mid-term and project completion
Lessons for Adaptation | Response
Climate Resilience Measures
What have been the lessons learned, both positive and negative, in implementing climate adaptation measures that would be relevant to the design and implementation of future projects/programmes for enhanced resilience to climate change?
What is the potential for the climate resilience measures undertaken by the project/programme to be replicated and scaled up both within and outside the project area?
Concrete Adaptation Interventions
What have been the lessons learned, both positive and negative, in implementing concrete adaptation interventions that would be relevant to the design and implementation of future projects/programmes implementing concrete adaptation interventions?
What is the potential for the concrete adaptation interventions undertaken by the project/programme to be replicated and scaled up both within and outside the project area?
Community/National Impact
What would you consider to be the most successful aspects for the target communities?
What measures are/have been put in place to ensure sustainability of the project/program results?
What measures are being/could have been put in place to improve project/program results?
Knowledge Management
How has existing information/data/knowledge been used to inform project development and implementation? What kinds of information/data/knowledge were used?
If learning objectives have been established, have they been met? Please describe.
Describe any difficulties there have been in accessing or retrieving existing information (data or knowledge) that is relevant to the project. Please provide suggestions for improving access to the relevant data.
Has the identification of learning objectives contributed to the outcomes of the project? In what ways have they contributed?

## Results Tracker
Results Tracker for Adaptation Fund (AF) Projects
Goal: Assist developing-country Parties to the Kyoto Protocol that are particularly vulnerable to the adverse effects of climate change in meeting the costs of concrete adaptation projects and programmes in order to implement climate-resilient measures. Impact: Increased resiliency at the community, national, and regional levels to climate variability and change.
Important: Please read the following Results Framework and Baseline Guidance (also posted on the Adaptation Fund website) before entering your data
Link: http://www.adaptation-fund.org/sites/default/files/Results%20Framework%20and%20Baseline%20Guidance%20final.pdf
Please select the relevant Fund level Outcome and Output indicators that allign with the project objectives and outcomes
OBJECTIVE 1
Fund Outcome | Please select from dropdown menu below | Fund Outcome Indicator | Please select from dropdown menu below | Target at CEO Endorsement (see Units in next sheet) | Baseline (see Units in next sheet) | Mid-term Results | Terminal Results
Outcome 1: Reduced exposure at national level to climate-related hazards and threats Outcome 2: Strengthened institutional capacity to reduce risks associated with climate-induced socioeconomic and environmental losses Outcome 3: Strengthened awareness and ownership of adaptation and climate risk reduction processes at local level Outcome 4: Increased adaptive capacity within relevant development and natural resource sectors Outcome 5: Increased ecosystem resilience in response to climate change and variability-induced stress Outcome 6: Diversified and strengthened livelihoods and sources of income for vulnerable people in targeted areas Outcome 7: Improved policies and regulations that promote and enforce resilience measures | 4 | 1. Relevant threat and hazard information generated and disseminated to stakeholders on a timely basis 2.1. No. and type of targeted institutions with increased capacity to minimize exposure to climate variability risks 2.2. Number of people with reduced risk to extreme weather events 3.1. Percentage of targeted population aware of predicted adverse impacts of climate change, and of appropriate responses 3.2. Modification in behavior of targeted population 4.1. Development sectors' services responsive to evolving needs from changing and variable climate 4.2. Physical infrastructure improved to withstand climate change and variability-induced stress 5. Ecosystem services and natural assets maintained or improved under climate change and variability-induced stress 6.1. Percentage of households and communities having more secure (increased) access to livelihood assets 6.2. Percentage of targeted population with sustained climate-resilient livelihoods 7. Climate change priorities are integrated into national development strategy | 4.2 | 5 | 2
Fund Output | Please select from dropdown menu below | Fund Output Indicator | Please select from dropdown menu below | Target at CEO Endorsement (see Units in next sheet) | Baseline (see Units in next sheet) | Mid-term Results | Terminal Results
Output 1: Risk and vulnerability assessments conducted and updated at a national level Output 2.1: Strengthened capacity of national and regional centres and networks to respond rapidly to extreme weather events Output 2.2: Targeted population groups covered by adequate risk reduction systems Output 3: Targeted population groups participating in adaptation and risk reduction awareness activities Output 4: Vulnerable physical, natural, and social assets strengthened in response to climate change impacts, including variability Output 5: Vulnerable physical, natural, and social assets strengthened in response to climate change impacts, including variability Output 6: Targeted individual and community livelihood strategies strengthened in relation to climate change impacts, including variability Output 7: Improved integration of climate-resilience strategies into country development plans | 4 | 1.1. No. and type of projects that conduct and update risk and vulnerability assessments 1.2. Development of early warning systems 2.1.1. No. of staff trained to respond to, and mitigate impacts of, climate-related events 2.1.2. Capacity of staff to respond to, and mitigate impacts of, climate-related events from targeted institutions increased 2.2.1. Percentage of population covered by adequate risk-reduction systems 2.2.2. No. of people affected by climate variability 3.1 No. and type of risk reduction actions or strategies introduced at local level 3.2 No. of news outlets in the local press and media that have covered the topic 4.1. No. and type of health or social infrastructure developed or modified to respond to new conditions resulting from climate variability and change (by type) 4. 2. No. of physical assets strengthened or constructed to withstand conditions resulting from climate variability and change (by asset types) 5. No. and type of natural resource assets created, maintained or improved to withstand conditions resulting from climate variability and change (by type of assets) 6.1. No. and type of adaptation assets (physical as well as knowledge) created in support of individualor community-livelihood strategies 6.2. Type of income sources for households generated under climate change scenario 7.1. No., type, and sector of policies introduced or adjusted to address climate change risks 7.2. No. or targeted development strategies with incorporated climate change priorities enforced | 4.2 | 2 | 0
OBJECTIVE 2
Fund Outcome | Please select from dropdown menu below | Fund Outcome Indicator | Please select from dropdown menu below | Target at CEO Endorsement | Baseline | Mid-term Results | Terminal Results
Outcome 1: Reduced exposure at national level to climate-related hazards and threats Outcome 2: Strengthened institutional capacity to reduce risks associated with climate-induced socioeconomic and environmental losses Outcome 3: Strengthened awareness and ownership of adaptation and climate risk reduction processes at local level Outcome 4: Increased adaptive capacity within relevant development and natural resource sectors Outcome 5: Increased ecosystem resilience in response to climate change and variability-induced stress Outcome 6: Diversified and strengthened livelihoods and sources of income for vulnerable people in targeted areas Outcome 7: Improved policies and regulations that promote and enforce resilience measures | 5 | 1. Relevant threat and hazard information generated and disseminated to stakeholders on a timely basis 2.1. No. and type of targeted institutions with increased capacity to minimize exposure to climate variability risks 2.2. Number of people with reduced risk to extreme weather events 3.1. Percentage of targeted population aware of predicted adverse impacts of climate change, and of appropriate responses 3.2. Modification in behavior of targeted population 4.1. Development sectors' services responsive to evolving needs from changing and variable climate 4.2. Physical infrastructure improved to withstand climate change and variability-induced stress 5. Ecosystem services and natural assets maintained or improved under climate change and variability-induced stress 6.1. Percentage of households and communities having more secure (increased) access to livelihood assets 6.2. Percentage of targeted population with sustained climate-resilient livelihoods 7. Climate change priorities are integrated into national development strategy | 5 | 40 ha mangrove planted, 2000m2 coral reef rehabilitated | 0
Fund Output | Please select from dropdown menu below | Fund Output Indicator | Please select from dropdown menu below | Target at CEO Endorsement | Baseline | Mid-term Results | Terminal Results
Output 1: Risk and vulnerability assessments conducted and updated at a national level Output 2.1: Strengthened capacity of national and regional centres and networks to respond rapidly to extreme weather events Output 2.2: Targeted population groups covered by adequate risk reduction systems Output 3: Targeted population groups participating in adaptation and risk reduction awareness activities Output 4: Vulnerable physical, natural, and social assets strengthened in response to climate change impacts, including variability Output 5: Vulnerable physical, natural, and social assets strengthened in response to climate change impacts, including variability Output 6: Targeted individual and community livelihood strategies strengthened in relation to climate change impacts, including variability Output 7: Improved integration of climate-resilience strategies into country development plans | 5 | 1.1. No. and type of projects that conduct and update risk and vulnerability assessments 1.2. Development of early warning systems 2.1.1. No. of staff trained to respond to, and mitigate impacts of, climate-related events 2.1.2. Capacity of staff to respond to, and mitigate impacts of, climate-related events from targeted institutions increased 2.2.1. Percentage of population covered by adequate risk-reduction systems 2.2.2. No. of people affected by climate variability 3.1 No. and type of risk reduction actions or strategies introduced at local level 3.2 No. of news outlets in the local press and media that have covered the topic 4.1. No. and type of health or social infrastructure developed or modified to respond to new conditions resulting from climate variability and change (by type) 4. 2. No. of physical assets strengthened or constructed to withstand conditions resulting from climate variability and change (by asset types) 5. No. and type of natural resource assets created, maintained or improved to withstand conditions resulting from climate variability and change (by type of assets) 6.1. No. and type of adaptation assets (physical as well as knowledge) created in support of individualor community-livelihood strategies 6.2. Type of income sources for households generated under climate change scenario 7.1. No., type, and sector of policies introduced or adjusted to address climate change risks 7.2. No. or targeted development strategies with incorporated climate change priorities enforced | 5 | 40 ha mangrove planted, 2000m2 coral reef rehabilitated. | 0
OBJECTIVE 3
Fund Outcome | Please select from dropdown menu below | Fund Outcome Indicator | Please select from dropdown menu below | Target at CEO Endorsement | Baseline | Mid-term Results | Terminal Results
Outcome 1: Reduced exposure at national level to climate-related hazards and threats Outcome 2: Strengthened institutional capacity to reduce risks associated with climate-induced socioeconomic and environmental losses Outcome 3: Strengthened awareness and ownership of adaptation and climate risk reduction processes at local level Outcome 4: Increased adaptive capacity within relevant development and natural resource sectors Outcome 5: Increased ecosystem resilience in response to climate change and variability-induced stress Outcome 6: Diversified and strengthened livelihoods and sources of income for vulnerable people in targeted areas Outcome 7: Improved policies and regulations that promote and enforce resilience measures |  | 1. Relevant threat and hazard information generated and disseminated to stakeholders on a timely basis 2.1. No. and type of targeted institutions with increased capacity to minimize exposure to climate variability risks 2.2. Number of people with reduced risk to extreme weather events 3.1. Percentage of targeted population aware of predicted adverse impacts of climate change, and of appropriate responses 3.2. Modification in behavior of targeted population 4.1. Development sectors' services responsive to evolving needs from changing and variable climate 4.2. Physical infrastructure improved to withstand climate change and variability-induced stress 5. Ecosystem services and natural assets maintained or improved under climate change and variability-induced stress 6.1. Percentage of households and communities having more secure (increased) access to livelihood assets 6.2. Percentage of targeted population with sustained climate-resilient livelihoods 7. Climate change priorities are integrated into national development strategy | 7 | One (1) Ecosystem Based Integrated Coastal Area Management Plan (EBICAM) with CC adaptation action plan for the coastal region is approved - 5 fully integrated | 1 (none)
Fund Output | Please select from dropdown menu below | Fund Output Indicator | Please select from dropdown menu below | Target at CEO Endorsement | Baseline | Mid-term Results | Terminal Results
Output 1: Risk and vulnerability assessments conducted and updated at a national level Output 2.1: Strengthened capacity of national and regional centres and networks to respond rapidly to extreme weather events Output 2.2: Targeted population groups covered by adequate risk reduction systems Output 3: Targeted population groups participating in adaptation and risk reduction awareness activities Output 4: Vulnerable physical, natural, and social assets strengthened in response to climate change impacts, including variability Output 5: Vulnerable physical, natural, and social assets strengthened in response to climate change impacts, including variability Output 6: Targeted individual and community livelihood strategies strengthened in relation to climate change impacts, including variability Output 7: Improved integration of climate-resilience strategies into country development plans |  | 1.1. No. and type of projects that conduct and update risk and vulnerability assessments 1.2. Development of early warning systems 2.1.1. No. of staff trained to respond to, and mitigate impacts of, climate-related events 2.1.2. Capacity of staff to respond to, and mitigate impacts of, climate-related events from targeted institutions increased 2.2.1. Percentage of population covered by adequate risk-reduction systems 2.2.2. No. of people affected by climate variability 3.1 No. and type of risk reduction actions or strategies introduced at local level 3.2 No. of news outlets in the local press and media that have covered the topic 4.1. No. and type of health or social infrastructure developed or modified to respond to new conditions resulting from climate variability and change (by type) 4. 2. No. of physical assets strengthened or constructed to withstand conditions resulting from climate variability and change (by asset types) 5. No. and type of natural resource assets created, maintained or improved to withstand conditions resulting from climate variability and change (by type of assets) 6.1. No. and type of adaptation assets (physical as well as knowledge) created in support of individualor community-livelihood strategies 6.2. Type of income sources for households generated under climate change scenario 7.1. No., type, and sector of policies introduced or adjusted to address climate change risks 7.2. No. or targeted development strategies with incorporated climate change priorities enforced | 7.2 | One (1) Ecosystem Based Integrated Coastal Area Management Plan (EBICAM) with CC adaptation action plan for the coastal region is approved | 0 - no
OBJECTIVE 4
Fund Outcome | Please select from dropdown menu below | Fund Outcome Indicator | Please select from dropdown menu below | Target at CEO Endorsement | Baseline | Mid-term Results | Terminal Results
Outcome 1: Reduced exposure at national level to climate-related hazards and threats Outcome 2: Strengthened institutional capacity to reduce risks associated with climate-induced socioeconomic and environmental losses Outcome 3: Strengthened awareness and ownership of adaptation and climate risk reduction processes at local level Outcome 4: Increased adaptive capacity within relevant development and natural resource sectors Outcome 5: Increased ecosystem resilience in response to climate change and variability-induced stress Outcome 6: Diversified and strengthened livelihoods and sources of income for vulnerable people in targeted areas Outcome 7: Improved policies and regulations that promote and enforce resilience measures |  | 1. Relevant threat and hazard information generated and disseminated to stakeholders on a timely basis 2.1. No. and type of targeted institutions with increased capacity to minimize exposure to climate variability risks 2.2. Number of people with reduced risk to extreme weather events 3.1. Percentage of targeted population aware of predicted adverse impacts of climate change, and of appropriate responses 3.2. Modification in behavior of targeted population 4.1. Development sectors' services responsive to evolving needs from changing and variable climate 4.2. Physical infrastructure improved to withstand climate change and variability-induced stress 5. Ecosystem services and natural assets maintained or improved under climate change and variability-induced stress 6.1. Percentage of households and communities having more secure (increased) access to livelihood assets 6.2. Percentage of targeted population with sustained climate-resilient livelihoods 7. Climate change priorities are integrated into national development strategy
Fund Output | Please select from dropdown menu below | Fund Output Indicator | Please select from dropdown menu below | Target at CEO Endorsement | Baseline | Mid-term Results | Terminal Results
Output 1: Risk and vulnerability assessments conducted and updated at a national level Output 2.1: Strengthened capacity of national and regional centres and networks to respond rapidly to extreme weather events Output 2.2: Targeted population groups covered by adequate risk reduction systems Output 3: Targeted population groups participating in adaptation and risk reduction awareness activities Output 4: Vulnerable physical, natural, and social assets strengthened in response to climate change impacts, including variability Output 5: Vulnerable physical, natural, and social assets strengthened in response to climate change impacts, including variability Output 6: Targeted individual and community livelihood strategies strengthened in relation to climate change impacts, including variability Output 7: Improved integration of climate-resilience strategies into country development plans |  | 1.1. No. and type of projects that conduct and update risk and vulnerability assessments 1.2. Development of early warning systems 2.1.1. No. of staff trained to respond to, and mitigate impacts of, climate-related events 2.1.2. Capacity of staff to respond to, and mitigate impacts of, climate-related events from targeted institutions increased 2.2.1. Percentage of population covered by adequate risk-reduction systems 2.2.2. No. of people affected by climate variability 3.1 No. and type of risk reduction actions or strategies introduced at local level 3.2 No. of news outlets in the local press and media that have covered the topic 4.1. No. and type of health or social infrastructure developed or modified to respond to new conditions resulting from climate variability and change (by type) 4. 2. No. of physical assets strengthened or constructed to withstand conditions resulting from climate variability and change (by asset types) 5. No. and type of natural resource assets created, maintained or improved to withstand conditions resulting from climate variability and change (by type of assets) 6.1. No. and type of adaptation assets (physical as well as knowledge) created in support of individualor community-livelihood strategies 6.2. Type of income sources for households generated under climate change scenario 7.1. No., type, and sector of policies introduced or adjusted to address climate change risks 7.2. No. or targeted development strategies with incorporated climate change priorities enforced

## Units for Indicators
Fund Outcome Indicator Units
1. Generation of relevant data, Stakeholders, and Timeliness 2.1. Include both qualitative and quantitative measures of capacity level within targeted institutions 2.2. Number (men and women and other vulnerable groups) 3.1. Use scale from 1 to 5: 5: Fully aware 4: Mostly aware 3: Partially aware 2: Partially not aware 1: Aware of neither predicted adverse impacts of climate change nor of appropriate responses 3.2. Use scale from 1 to 5: 5: All 4: Almost all 3: Half 2: Some 1: None 4.1. Summarize in an overall scale (1-5): 5: Highly responsive (All defined elements ) 4: Mostly responsive (Most defined elements) 3: Moderately responsive (Some defined elements) 2: Partially responsive (Lacks most elements) 1: Non responsive (Lacks all elements ) 4.2. Summarize in an overall scale (1-5): 5: Fully improved 4: Mostly Improved 3: Moderately improved 2: Somewhat improved 1: Not improved 5. Depends on the targeted natural asset: Biological (species): measure through changes in population numbers (dynamics, structure, etc.) Land: measure changes in hectares. Baseline data will be necessary to estimate the change. Supporting indicators baseline and target (as well as contextual information) are needed such as the following: Farmers adopting recommended technologies, Ha. of land improved, Average deforestation rate Etc. Use scale from 1 to 5. 5: Very effective (All elements are present) 4: Effective (Most elements are present) 3: Moderately effective (Some elements are present) 2: Partially effective (Most elements are not present) 1: Ineffective (No elements are present) 6.1. Summarize in an overall scale (1-5): 5: Very high improvement 4: High improvement 3: Moderate improvement 2: Limited improvement 1: No improvement 6.2. Household income by source of livelihood in project area (USD) prior and post project intervention 7. Summarize in an overall scale (1-5). 5: All (Fully integrated) 4: Most 3: Some 2: Most not integrated 1: None
Fund Output Indicator Units
1.1. Number, sector(s) and level(s) of projects or interventions in separate fields of monitoring plan 1.2. Number 2.1.1. Number of staff (male/female) of targeted institutions: a. Obtain baseline information: total number of staff from targeted institutions b. Define target 2.1.2. Number of staff (male/female) of targeted institutions: a. Obtain baseline information: total number of staff from targeted institutions b. Define target: needs to be defined by project proponents 2.2.1. Quantitative: Percentage (includes women – and other vulnerable groups – and men). Qualitative: Adequacy: include direct analysis of major areas; adequacy/effectiveness of systems or analysis of perceptions of populations and institutions. 2.2.2. Number (broken down by gender and, if possible, by vulnerable groups defined in the area of intervention) of people 3.1. Number and type (in separate columns) at local level. 3.2. Number 4.1. Number and type 4. 2. Number and type (entered in separate columns) 5. Number of interventions by type of natural asset and intervention 6.1. Number and type (in separate columns of monitoring plan) 6.2. Income sources per household; description of income source and number of households. 7.1. Number/Sector 7.2. Number; Effectiveness (see previous indicator) through enforcement level.