## Overview
Project Performance Report (PPR)
| Period of Report (Dates) | 01 November 2017 to 31 October 2018
| Project Title: | Implementation of Concrete Adaptation Measures to Reduce Vulnerability of Livelihoods and Economy of Coastal Communities of Tanzania
| Project Summary: | Tanzania is impacted by climate change mainly through its effects on rainfall patterns, temperature extremes and sea level rise. The direct impacts of these changes are likely to result in more frequent and intense droughts, the destruction of infrastructures in the coast and inland through flooding, inundation, erosion and storms; if no action is taken, the socio-economic impacts will include agricultural yield decreases, decreased water availability and quality, and losses of lives and livelihoods, as well as the accelerated degradation of ecosystems that form the basis of the Tanzanian economy. To respond to this, the government developed a project proposal to adapt to the climate change in the coast of Dar es salaam. In December 2011 the Adaptation Fund Board considered the proposal and approved a five years project with a total of USD 5,008,564. Implementation of the project started in 1 November 2012. The project consists of the following outcomes, supported by on the ground activities implemented primarily in the vicinity of Dar Es Salaam: 1. Adverse impacts of SLR and floods on coastal infrastructures and settlements are reduced. 2. Coastal ecosystems are rehabilitated and Integrated Coastal Area Management is implemented. 3. Knowledge of climate impacts and adaptation is increased. The project is being implemented by the United Nations Environment Programme (UNEP) and executed by the Vice Presidents Office (Division of Environment) in close cooperation with sectoral ministries as well as Dar es Salaam City Council and Municipalities of Ilala, Temeke and Kinondoni.
|  |  | Countries | Project Type: |  | GEF Focal Area: | GEF 4 Focal Areas | GEF 2 / 3 Operational Programme: | Overall Rating of the project in the evaluation by the project evaluator: | GEF-4 Focal Area Strategic Program: | GEF-3 Focal Area Strategic Program:
| Database Number: | AFB-5060-1111-2G48 | Afghanistan | FP | Yes | Biodiversity | 1 | 1 | U | BD-SP1-PA Financing | 1: Arid & semi-arid ecosystems
Implementing Entity (IE) [name]: |  | UNEP | Albania | MSP | No | Climate Change Adaptation | 2 | 2 | S | BD-SP2-Marine PA | 2: Coastal, marine & freshwater ecosystems
| Type of IE: | MIE | Algeria | EA |  | Climate Change Mitigation | 3 | 3 | MU | BD-SP3-PA Networks | 3: Forest ecosystems
| Country(ies): | United Republic of Tanzania | Angola |  |  | International Waters | 5 | 5 | Good | BD-SP5-Markets | 13: Conservation and Sustainable Use of Biological Diversity Important to Agriculture
Relevant Geographic Points (i.e. cities, villages, bodies of water): |  | Dar es Salaam City (Ocean Road; Kigamboni-Mwalimu Nyerere Memorial Institute; Kinondoni Municipality: Tandale street in Tandale ward and Kawe street in Kawe ward; Ilala Municipality: Bungoni street in Buguruni ward; Temeke Municipality: Miburani-Mtoni Bustani streets in Mtoni ward and Butiama street (Butiama drainage) in Kijichi ward;Sarender Bridge, Kunduchi, Ununio and Mbweni; Kigamboni Municipality: Pembamnazi and Tundwi, Songani. | Argentina |  |  | Multiple Focal Area |  |  |  | BD-SP7-Invasive Alien Species(IAS) | 6: Promoting the adoption of renewable energy by removing barriers and reducing implementation costs
[8 empty] | CC-SP2- Industrial EE | 8: Waterbody based operational program
| Project Milestones | [6 empty] | CC-SP3-RE,CC-SP4-Biomass | 9: Integrated Land and Water multiple focal area
| Milestone |  | Bahamas | [6 empty] | CC-SP5-Transport | 10: Contaminants based operational program
AFB Approval Date: |  | 2011-12-14
IE-AFB Agreement Signature Date: |  | 2012-03-01 | [6 empty] | CC-SP6-LULUCF | 12: Integrated Ecosystem Management
Start of Project/Programme: |  | 2012-11-01 | [6 empty] | Cross cutting capacity building | 14: Persistent Organic Pollutants
Mid-term Review Date (if planned):
| Terminal Evaluation Date: | November 2015 - January 2016 (MTR - Done), December 2018 - April 2019 (Terminal - planned)
|  | List documents/ reports/ brochures / articles that have been prepared about the project. | Cyprus
|  | Inception Workshop Report 2012; Quarterly Expenditure Reports (Q4,2012, Q1, Q2, Q3&Q4, 2013; Q1,Q2,Q3,Q4, 2014, Q1, Q2&Q3, 2015); Project brief report to the Planning Commission of the United Republic of Tanzania for the Government; TORs of: Joint Project Steering Committee; National Project Coordinator; Senior Technical Adviser; Finance and Administrative Assistant; Tender Evaluation Repors for supply of the project vehicle; evaluation report for expression of interest for a position of senior technical adviser; evaluation report for a position of consultancy services for development of a baseline survey and development of indicators and various consultancies. Finalized TORs of: (Feasibility Study, EIA study for the proposed Construction and Rehabilitation of Seawall at Ocean Road and Kigamboni (Mwalimu Nyerere Memorial Institute) and Rehabilitation of Drainage Systems; Climate Change Knowledge Management Specialist; Coastal Zone Management Specialist; Memorandum of Understanding with UNOPS for construction and rehabilitation of seawall of Kigamboni and Ocean Road and drainage systems; Reef specialist, Rural energy consultant, mangrove specialist, Coastal Rehabilitation specialist, Mangrove specialist, sub-contract env. engineering firm for mangrove rehabilitation, Climate Change Observatory for Tanzania, Task Force to develop EBICAM Action Plan and sub-contract NGO reef rehabilitation ); Evaluation Report of Expression of Interest Tender No. ME 002/2012-13/DE/C/07 for Re-advertised Consultancy services for Development of a baseline survey and development of indicators and targets, Procurement plan 2014, Revised Project Budget, Revised Work Plan, Variance of the revised project budget, Report of the development of the Terms of Reference of various consultancies. Baseline study report,2014. PPR (November 2012-October 2013, November 2013 to October 2014). PPR B (1 November 2013 to 30 April 2014, 1 November 2014 to 30 April 2015), Audit reports 2013 and 2014, Final Draft Ecosystem Based Integrated Coastal Area Management (EBICAM) Action Plan for Dar es Salaam region. Brief report of UNEP task manager and senior technical adviser mission, 2013, Annual physical and financial performance for year 2013 and 2014, draft training materials on on appropriate energy technologies, Criteria of efficient cookstoves, Evaluation and negotiation reports of various consultancies, Bids amount of the consultancies, Procurement Plan 2015, Procurement management reporting, Inception reports of: Reef specialist, Climate change knowledge management specialist, Coastal zone management specialist, Rural energy consultant, Coastal rehabilitation specialist, Mangrove specialist, NGO for reef rehabilitation, NGO for mangrove rehabilitation, 3rd Revised budget, Revised Work Plan, Agreement between VPO and UNOPS, Management response to baseline study, Revised Results Framework, Action Plan for years 2012,2013,2014,2015,2016&2017, Steering Committee minutes (1st,2nd and 3rd meetings), Training report, Workshop reports, Contracts of consultancies. Second contract of STA, Senior technical Adviser (STA) Work Plans, STA Mission Reports (1-4); STA Quarterly Reports (2013-2014-2015-2016); EIA study Report, Feasibility study and Mid term review reports. Revised budget. Assessment report of the viability and resilience of proposed actions under the project. Training Material On Promotion of Solar Cookers for Inclusive Growth and Environmental Conservation; Training Material On Potential of Urban Forestry in Dar Es Salaam City for Inclusive Growth and Environmental Conservation ; Training Material to Producers and Users of Biomass Stoves; Establishment of Climate Change Observatory for Tanzania (CCOT); Mangrove Training Report, 2017; Final Consultant reports on: Climate Change Knowledge Management, Coastal Zone Management, Coastal rehabilitation and reef rehabilitation; Final consulatnts reports on Reef restoration, Mangrove Training Report, 2017; Final Consultant reports on: Climate Change Knowledge Management, Coastal Zone Management, Coastal rehabilitation and reef rehabilitation; Final consultants reports on Reef restoration, training manual on sustainable use of mangrove ecosystems, sustainable fishing on coral reefs, progress on Mangroves Planting Activities in Dar es Salaam Project Sites, progress report for the “coastal rehabilitation specialist, final report on coastal rehabilitation , final technical assessment of the viability and resilience of proposed actions under the project, approaches for monitoring of key determinants of vulnerability in the project area, review of district infrastructure maintenance programmes of Ilala, Kinondoni, Temeke municipalities and Dar es salaam city council in the context of project outputs, technical advice on the shoreline rehabilitation and stabilization using trees and grasses, assessment report of the economic viability and practical feasibility of adaptation measures to identify successful adaptation measures for replication or up - scaling , final consultancy report on climate change knowledge management, indicators of climate change vulnerability and their means of verification along the coast of Tanzania, final report on construction of seawalls, UNOPS take report, policy briefs on climate change vulnerability and adaptation along the coast of Tanzania: main issues for decision makers, integrated coastal zone management in Tanzania in the context of climate change adaptation: main issues for decision makers, Sustainable fishing on coral reefs, Coral reef education and awareness, Restoration of Tanzanian Coral Reefs to aid their Recovery, Sustainable Fishing on Coral Reefs. | Czech Republic
List the Website address (URL) of project. |  |  | Democratic People's Republic of Korea
|  | http://addis.unep.org/projectdatabases/01274/project_general_info | Democratic Republic of the Congo
Denmark
| Project contacts: |  | Djibouti
National Project Manager/Coordinator |  |  | Dominica
| Name: | Dr. Kanizio Fredrick Manyika | Dominican Republic
| Email: | kanzio.manyika@vpo.go.tz, Freddy_Manyika@hotmail.com | Ecuador
| Date: | 2018-10-31 | Egypt
| Government DA |  | El Salvador
| Name: | Amb. Joseph Sokoine | Equatoral Guinea
| Email: | joseph.sokoine@vpo.go.tz | Eritrea
| Date: | 2018-10-31 | Estonia
| Implementing Entity |  | Ethiopia
| Name: | Mara Baviera, UNEP Task Manager | Fiji
| Email: | mara.baviera@un.org | Finland
| Date: | 2018-10-31 | France
| Executing Agency |  | Gambia
| Name: | Vice President's Office | Georgia
| Email: | ps@vpo.go.tz | Germany
| Date: | 2018-10-31 | Ghana
| Executing Agency |  | Greece
| Name: |  | Grenada
| Email: |  | Guatemala
| Date: |  | Guinea
| Executing Agency |  | Guinea Bissau
| Name: |  | Guyana
| Email: |  | Haiti
| Date: |  | Honduras
Hungary
Iceland
India
Indonesia
Iran (Islamic Republic of)
Iraq
Ireland
Israel
Italy
Jamaica
Japan
Jordan
Kazakhstan
Kenya
Kiribati
Kuwait
Kyrgyzstan
Lao People’s Democratic Republic
Latvia
Lebanon
Lesotho
Liberia
Libyan Arab Jamahiriya
Liechtenstein
Lithuania
Luxembourg
Madagascar
Malawi
Malaysia
Maldives
Mali
Malta
Marshall Islands
Mauritania
Mauritius
Mexico
Micronesia, Federated States of
Monaco
Mongolia
Montenegro
Morocco
Mozambique
Myanmar
Namibia
Nauru
Nepal
Netherlands
New Zealand
Nicaragua
Niger
Nigeria
Norway
Oman
Pakistan
Palau
Panama
Papua New Guinea
Paraguay
Peru
Philippines
Poland
Portugal
Qatar
Republic of Korea
Republic of Moldova
Romania
Russian Federation
Rwanda
Saint Kitts and Nevis
Saint Lucia
Saint Vincent and the Grenadines
Samoa
San Marino
Sao Tome and Principe
Saudi Arabia
Senegal
Serbia
Seychelles
Sierra Leone
Singapore
Slovakia
Slovenia
Solomon Islands
Somalia
South Africa
Spain
Sri Lanka
Sudan
Suriname
Swaziland
Sweden
Switzerland
Syrian Arab Republic
Tajikistan
Thailand
The former Yugoslav Republic of Macedonia
Timor-Leste
Togo
Tonga
Trinidad and Tobago
Tunisia
Turkey
Turkmenistan
Tuvalu
Uganda
Ukraine
United Arab Emirates
United Kingdom of Great Britain and Northern Ireland
United Republic of Tanzania
United States of America
Uruguay
Uzbekistan
Vanuatu
Venezuela, Bolivarian Republic of
Viet Nam
Yemen
Zambia
Zimbabwe
Note on D33: Mara Baviera: Previous URL was not working

## FinancialData
Financial information: Cumulative from project start to 31 October 2018
DISBURSEMENT OF AF GRANT FUNDS
How much of the total AF grant as noted in Project Document plus any project preparation grant has been spent to date?
Estimated cumulative total disbursement as of 31st October 2018(USD)* | 4441629
Add any comments on AF Grant Funds. (word limit=200) | The figure is the total funds disbursed by the Executing Agency as reflected in quarterly expense reports submitted to UNEP covering up to September 30, 2018.
INVESTMENT INCOME | NA
Amount of annual investment income generated from the Adaptation Fund’s grant
EXPENDITURE DATA
List ouput and corresponding amount spent for the current reporting period | ITEM / ACTIVITY / ACTION | AMOUNT
| Output 1.1: Sea wall raised, rehabilitated and constructed in areas showing particular damage | 0
| Output 1.2: Effective storm and flood drainage systems in urban areas and near coastal communities cleaned, rehabilitated | 0
| Output 1.3: EIA and feasibility study undertaken | 977
| Output 2.1: Mangrove rehabilitated through planting of resilient seedlings, dredging and the creation of no-take buffer zones | 0
| Output 2.2: Appropriate alternative energy (efficient cook stoves, small solar) technology transferred for avoided deforestation including through training | 0
| Output 2.3: Coral reef rehabilitated and protected in coastal sites | 0
| Output 2.4: Shoreline rehabilitated and stabilized using indigeneous resilient trees and grasses | 0
| Output 3.1: Performance of a baseline study based on coastal vulnerability | 0
| Output 3.2: Climate change observatory for Tanzania for ongoing monitoring of CZM and coastal environmental status and scientific research created and operational | 9736.17
| Output 3.3: Assessment of the economic viability and practical feasibility of adaptation measures (i.e. through undertaking cost-benefit analyses) | 0
| Output 3.4:District level administration have the capacity to adequately manage rehabilitated infrastructure | 9920
| Output 3.5: One EBICAM action plan for the coastal region approved | 32595.76
| Monitoring and Evaluation | 8407.83
| Project Execution | 30981.19
| TOTAL | 92617.95
PLANNED EXPENDITURE SCHEDULE
List outputs planned and corresponding projected cost for the upcoming reporting period | ITEM / ACTIVITY / ACTION | PROJECTED COST | Est. Completion Date
| Output 1.1: Sea wall raised, rehabilitated and constructed in areas showing particular damage | 0 | 2018-06-05
| Output 1.2: Effective storm and flood drainage systems in urban areas and near coastal communities cleaned, rehabilitated | 0 | 2018-10-30
| Output 1.3: EIA and feasibility study undertaken | 0 | 2016-09-01
| Output 2.1: Mangrove rehabilitated through planting of resilient seedlings, dredging and the creation of no-take buffer zones | 14219 | 2019-03-30
| Output 2.2: Appropriate alternative energy (efficient cook stoves, small solar) technology transferred for avoided deforestation including through training | 257.07 | 2019-03-30
| Output 2.3: Coral reef rehabilitated and protected in coastal sites | 23300 | 2019-03-31
| Output 2.4: Shoreline rehabilitated and stabilized using indigeneous resilient trees and grasses | 33000 | 2019-03-30
| Output 3.1: Performance of a baseline study based on coastal vulnerability | 0 | 2014-09-30
| Output 3.2: Climate change observatory for Tanzania for ongoing monitoring of CZM and coastal environmental status and scientific research created and operational | 27100 | 2018-04-30
| Output 3.3: Assessment of the economic viability and practical feasibility of adaptation measures (i.e. through undertaking cost-benefit analyses) | 10544.62 | 2018-12-30
| Output 3.4:District level administration have the capacity to adequately manage rehabilitated infrastructure | 23333.86 | 2019-03-30
| Output 3.5: One EBICAM action plan for the coastal region approved | 0 | 2019-03-30
| Monitoring and Evaluation | 25884.52 | 2019-03-30
| Project Execution | 17032.57 | 2019-03-30
| TOTAL | 174671.64
ACTUAL CO-FINANCING (If the MTR or TE have not been undertaken this reporting period, DO NOT report on actual co-financing.)
How much of the total co-financing as committed in the Project Document has actually been realized? | Co-financing is not applicable to the project.
Estimated cumulative actual co-financing as verified during Mid-term Review (MTR) or Terminal Evaluation (TE). | Co-financing is not applicable to the project.
Add any comments on actual co-financing in particular any issues related to the realization of in-kind, grant, credits, loans, equity, non-grant instruments and other types of co-financing. (word limit=200)

## Risk Assesment
RISK ASSESSMENT
IDENTIFIED RISKS
List all Risks identified in project preparation phase and what steps are being taken to mitigate them
Identified Risk | Current Status | Steps Taken to Mitigate Risk
Operational: The multiple ongoing initiatives on climate adaptation in Tanzania could cause operational delays for this project | Low | The appointed National Project Coordinator, Senior Technical Adviser and Assistant Administrative and Financial Manager as a dedicated team for project. VPO signed a memorandum of understanding with Ilala municipal council on grass and tree planting as part of shoreline stabilization for coordination and to ensure the project maintains its objectives. In addition, the Project Steering Committee (PSC) has helped to resolve pending issues allowing a smooth progress of the planned activities. The Chairperson of the PSC who is the Permanent Secretary of the Vice President's Office ensures that there are no unnecessary delays of this project. PSC has been able to meet in 3rd March 2014, 22nd July 2014; 16 February 2015, 11 March 2016 and 19 June 2017. Appointed Focal points have remained the same people in Temeke and Kinondoni Municipalities and new Focal points for Ubungo and Kigamboni were appointed following split of Kinondoni and Temeke. However, focal points for Ilala and Dar es Salaam city council were replaced immediately following relocation of the former focal points to other government offices. The team is continuing to monitor this risk, but no further mitigation action has been found necessary in the reporting period
Political: District-level stakeholders and administrations show low engagement for adaptation measures | Low | The Project Steering Committee continues to provide overall guidance with regard to implementation of the project activities. Latest Steering Committee meeting was held on 19 June 2017. Another Project Steering Committee is planned towards end of November, 2018. Handover of the Seawall was done by the highest level during the Commemoration of Environmental Day on 5 June 2018. Regular site visits by local communities and district leaders to the project sites enhanced their engagement for adaptation measures on the coastal and marine environment. Political leaders have been fully engaged in the project monitoring.
Political: the project could experience difficulties in coordination and oversight for activities delivered at various sectors, levels of governments or by multiple partners | Low | The dedicated personnel for project management established through the Vice President‘s Office coordinates and monitors the project outputs and activities. Close collaboration among various ministries and stakeholders is provided through among others the Project Steering Committee. With the realisation of the first, second and third (and subsequent) Project Steering Committee meetings and appointement of the Focal Points from the project areas, greater cross-intitunional coordination has been achieved.
Environmental: Extreme weather events such as tropical storms, floods or droughts could hinder progress in ecosystem rehabilitation and infrastructure activities | Medium | The designs of the protective infrastructure rehabilitation are according to the best available technical standards and best available technology. Rehabilitation and construction of seawalls and drainage infrastructures were completed. The drainage at Mtoni Municipality collapsed due to exceptionally heavy rains in April 2018. Tanzania Meteorolgical Agency (TMA) recorded 250 mm as mean rainfall for April 2018, whereas the actual rainfall was 417.8mm, which is 166% of the mean. However, the collapsed drainage was quickly reconstructed up to higher design standards by using contractors own insurance bond. The team is continuing to monitor this risk, but no further mitigation action has been found necessary in the reporting period.
Financial: market and price fluctuations could cause price variations and variations in costs of certain project activities, leading to budgetary constraints. | Low | There have been no changes in costs for all consultancies for main project activities such seawall and drainage work; mangrove and coral reef rehabilitation since signing of the project agreement. Project activities are in good progress as per agreed revised work plan and budgets. In this regards, price variation and cost variation posed minimal budgetary constraints to the project activities since these were taken into account in the contracts. Despite of delayed final payments to some of the project consultancies, there is no incremental costs that have been associated with such delayed payments.
Critical Risks Affecting Progress (Not identified at project design)
Identify Risks with a 50% or > likelihood of affecting progress of project
Identified Risk | Current Status | Steps Taken to Mitigate Risk
Vice President's Office (VPO) "the executing entity" low executions rate due to internal procurement procedures. | Medium | A formal partnership of the project team with the VPO procurement unit continued to create streamlined and dedicated processes for the project. Furthermore, 2013, 2014, 2015, 2016, 2017 and 2018 project activities were included in the annual work plans of the VPO. This arrangement continued to help improved procurement process. To date, all 16 consultancies have been procured since the commenced of the project in 2012. Procurement of the labour costs for shoreline stabilization were finalized following completion of seawall. However, one activity, planting of grasses and trees has not commenced due to the fact that procurement took a longer time than expected. After two rounds of call for proposals, there were no interested service providers that submitted bids. Hence, the activity was delayed and thus VPO subsequently engaged Ilala Municipality to undertake the activity. To carry out the activity, VPO has signed an memorandum of understanding with Ilala Municipal council with respect to grass and tree planting as part of shoreline stabilization. The activity will be implemented as per revised workplan. In general, risks are covered by contactors. All financial matters are approved by the Permanent Secretary who is the Accounting Officer. The team is continuing to monitor this risk, but no further mitigation action has been found necessary in the reporting period.
Cash flow of the contractor: The main firm for construction works can face internal cash flow difficulties or bankruptcy causing delays for major construction works such as sea walls and drainage leading delay of completion of works | Low | Payments to the contractor have been based on deliverables/outputs and where necessary direct payments to the other sub-constructors was used to minimize the risks.
Land ownership disputes in proposed mangrove planting sites. | Medium | Although mangove sites are protected areas, there have been some incidences of illegal occupation and conversion into other land uses leading to land disputes. In view of this, the project identified alternative sitesin Kigamboni and Temeke that are on public land that could be planted with mangroves. These were validated by the Tanzania Forest Service and were approved by the steering committee.
Risk Measures: Were there any risk mitigation measures employed during the current reporting period? If so, were risks reduced? If not, why were these risks not reduced?
Add any comments relevant to risk mitigation (word limit = 500)
Most of the procured consultancies are progressing well with close monitoring of the Project Steering Committee, project management team, focal points and other stakeholders at both local and national level. Monitoring continued during the reporting period. Extreme weather was forseen to be medium risk and had actual impacts that required reconstruction of the Mtoni drainage channel. While this has resulted in some delays, the reconstruction was at no additional cost to the project. A risk mitigation measure built in place was to have the contractors insurance cover such events. In addition, due to lack of interested bidders in the planting of grasses and trees along Barak Obama road, VPO has signed an MOU with Ilala Municipal Council. as a mitigation measure. Increased costs and delivery failures associated with these risks were reduced, but delays have occurred.

## Rating
RATING ON IMPLEMENTATION PROGRESS
For rating definitions please see bottom of page.
| Progress on Key Milestones |  | Expected Progress |  | Progress to Date | Rating
Project Manager/Coordinator: | Component 1 - Addressing climate change impacts on key infrastructure and settlements
| Rehabilitate, construct and upgrade coastal protection facilities to protect settlements economic and cultural infrastructure |  | Contract an engineering firm to rehabilitate and construct seawalls. Rehabilitate, construct and upgrade 1,400 linear meters of seawall along the Ocean Road and Kigamboni (Mwalimu Nyerere Memorial Academy-staff quarters). Documentation of seawall rehabilitation and construction. |  | Dezo Civil Contractors Company Limited completed construction of 1,400 linear meters of seawalls at Ocean/Obama road and Kigamboni (Mwalimu Nyerere Memorial Academy. At Barack Obama road 950m out of 950m of walkway and IBD drain done, 950m out of 950m of guardrail posts done, A total of 3 beach access staircases and 22 sitting benches constructed and completed. Seven (7) Solar powered street lights were erected, one public toilet was constructed. At Kigamboni/Mwalimu Nyerere Memorial Academy site, sea wall length of 500m was constructed, 500m of walkway was done 500m of IBD drain done, beach access staircase were done, while18 benches have been constructed and completed. One public toilet was constructed and four security lights were erected at Kigamboni. All construction works were completed. Hand over of newly constructed seawalls was done on 5 June 2018. | S
| Cleaning up of the drainage channels, rehabilitation of storm drains |  | Contract an engineering firm for Rehabilitate/Cleaning and maintenance of five storm drains in Ilala, Temeke and Kinondoni Municipalities. Rehabilitate/Cleaning and maintenance of five storm drains in Ilala, Temeke and Kinondoni Municipalities. Documentation of drainage systems activities. Undertake trainings on ecosystem based coastal adaptation, |  | Dezo Civil Contractors Company Limited which were contracted by UNOPS to rehabilitate, upgrade and construct two sites of Bungoni and Mtoni drainages continued with the assignment and construction was completed as follows: At Ilala Bungoni Drainage Site:-  475m of base construction done.  475m of side slab construction done.  800m of landscape backfill was done.  One security light was erected.  Grasses were planted to prevent soil erosion.  Two pedestrian bridges were constructed.  The overall completion is 100%. At At Miburini-Mtoni Bustani Drainage:  A total length of 575 m of the drainage was completed.  Five foot bridges were constructed.  Collapsed drainage was reconstructed and design upgraded.  Progress of work on site is at 98% overall completion | S
| EIA and feasibility study |  | Undertake EIA and feasibility study in areas of seawalls and drainage systems. Establish procurement partnership. |  | EIA study and EIA Report were undertaken since 2016 approved on 13th September 2016 to allow construction works to commence. Environment and Social management Plan identified in the ESIA continues to be monitored .Feasibility study was undertaken by ARU Company. Final feasibility study Report is available. No more risks were anticipated during the report period. | S
Component 2 – Ecosystem-based Integrated Coastal Area Management
| Mangrove rehabilitation |  | Procure seedlings, saplings and materials for mangrove rehabilitation. Undertake trainings to promote conservation of rehabilitated areas within mangroves. Planting of resilient seedlings. |  | The new project sites that were identified in Kigamboni (Tungi Songani and Pembamnazi). Planting has been completed whereby 40ha have been planted with mangroves. The survival rates is estimated at 80%. This is high compared to the 65% estimate at the project design stage. Nevertheless, causes of the die back could be attributed to incerase of salinity where there is insuffient mix of fresh and seawater, effluents with toxic chemicals and interference with human activities. The mangrove specialist who was procured in August 2015 continued to provide advices to CODECO. Suitable mangrove species for Kigamboni for planting (area of 40ha) were planted based on recommendations from mangrove specialist. Monitoring of the survival rates will continued until March 2019 so as to allow gap filling during rainy season in March. | MS
| Appropriate alternative energy |  | Distribute fuel efficient cookstoves to 1,500 households. Procure rural energy consultant to prepare to prepare training materials on appropriate alternative energy technologies (efficient cookstoves, small solar). Train district officers and community representatives on fuel efficient technologies |  | Monitoring of 3,000 efficient cookstoves that were purchased and distributed to 3,000 households in Ilala, Kinondoni, and Temeke Municipalities, continued. Monitoring of cook stoves beneficiaries continued. | S
| Coral reef rehabilitation and protection |  | Restore live coverage, using in situ techniques for coral breeding and transplantation. Undertake awareness raising to fisheries and local government officers in order to further reduce unsustainable fishing methods and reef uses. Analyse lab-agri research. |  | Reef specialist consultant was who was procured in January 2015 and NGO for Reef rehabilitation (SUNARE) continued to monitor coral reefs at Sinda and Mwakatumbe islands marine reserves where restoration was done. The total restored area is 3000sqm which exceeds the 2000sqm that was proposed in the project design. Training manuals and materials on conservation of coral reefs as well as sustainable fishing methods prepared and training was undertaken. Final consultant report was prepared and submitted to VPO. | S
| Shoreline stabilization through reforestation |  | Replant native and resilient trees including bushes and grasses in sufficient density, along the shore with a particular focus on the rehabilitated infrastructures Procure coastal climate adaptation consultant. Shoreline stabilization labour cost. |  | VPO has signed MOU with Ilala Municipal Council to undertake planting of trees and grasses along Obama road seawall as part of shoreline stabilization. Indigenous species have been identified through enganegement of experts and Mui at and planting will start after of funds to Ilala Municipal Council. A total of 56,430 trees are expecetd to be planted. | MS
Component 3 – Knowledge, coastal monitoring and policy linkages
| Stocktaking |  | Undertake baseline survey and development of indicators and targets. Develop a database of information relevant to adaptation in Tanzania |  | Baseline study was completed in September 2014. The findings from the baseline report were used to revise the log-frame. The Results Framework and management response were endorsed by the Project Steering Committee on 16th February 2015 and shared with the AF Sec. Development of the database of relevant information of the project is being undertaken by through various consultancies and the project team. A Climate Change adaptation specialist was commissioned in July 2018 2018 to undertake vulnerability studies in the Municipal council in Dar es Salaam. | S
| Coastal monitoring and assessment |  | Technical assessment of the viability and resilience of proposed actions. Monitoring the key determinants of vulnerability i.e. SLR, water availability and precipitation patterns. Create Climate Change Observatory for Tanzania (CCOT). Organize meetings of CCOT. |  | The second meeting of CCOT was held in April 2018, Dar es Salaam to Dodoma. Therefore, the Second CCOT workshop was in April 2018 to validate the progress of the project. Field visits to all project sites were undertaken. The meeting and field visit of the CCOT members served as platform for sharing expereiences on coastal zone adaptation and management, hence promotion of sustainability. During the meeting, it was emphasized that integration of coastal adpatation issues in district and municipal plans and plans is needed. | S
| Policy linkages |  | Document lessons learned from project outputs. Review infrastructure maintenance programs of Dar es Salaam City, Temeke, Kinondoni and Ilala Municipalities. Develop an Ecosystem-Based Integrated Coastal Area Management Action Plan (EBICAM). Organise an inception workshop. Organize policy briefing workshops. Train district administration on budgetary allocations for rehabilitated infrastructures. |  | A Second policy brief workshop was held in April 2018 in Dar es Salaam. The workshop focused on production of policy briefs with respect to lesson learned from implementation of the project activities, in particular, coral reef restoration, sustainable fishing on coral reefs, mangrove planting, Integrated Coastal Zone Management and coral reef education and awareness. The other outputs (namely inception workshops, development of EBICAM and training of district administration on budgetary allocation for rehabilitated infrastructures) have been undertaken and reported in previous reporting periods and reflected in the relevant PPRs. | S
Project operation and management
| Procurement |  | Prepare procurement plans Procure consultancies Procure firms for goods and works services Procure a project vehicle and ensure its maintenance. Purchase computers and accessories. |  | Procurement Plan for 2018 prepared. Procurement of the Coastal climate adaptation consultant was done. However, procurement of the labour costs for shoreline stabilization was advertised two times. Since no firm submitted any proposal, VPO decided to sub contract the shoreline stabilization assignment to Ilala Municipal Council following completion of the seawall. Tree and grass planting will be done once funds from UNEP are availed to VPO and subsequently disbursed to Ilala Municipal Council. | S
| Monitoring and evaluation |  | Facilitate auditing. Perform mid-term evaluation and cost-effectiveness assessment. Travel to sites. Undertake steering committee and technical committee meetings. Bank transfer and statements. Perform final evaluation. |  | Audit report for 2016 started and is being finalized by Control and Audit General. The Fifth meeting of the Project Steering Committee (PSC) was held on 19 June 2017 and 6th Joint Steering committee is proposed November 2018 to mark completion of project activities | S
| Establish project management team |  | Establish the National project management team. Procure the Senior Technical Advisor. |  | The National Project Coordinator (NPC) remained the same. In addition, Financial and Administrative Manager was appointed in April 2017 following changes of Financial Managers who were promoted to new roles/assignment within the government of Tanzania remained the same until September 2018 when he was also given new assignment in a different institution. | S
[5 empty] | Overall Rating | S
Please Provide the Name and Contact information of person(s) reponsible for completing the Rating section
| Name: | Kanizio Fredrick Manyika
| Email: | Freddy_Manyika@hotmail.com
Please justify your rating. Outline the positive and negative progress made by the project since it started. Provide specific recommendations for next steps. (word limit=500)
Most project activities were completed in 2018. Construction of seawall at Ocean road and Kigamboni was slowed down by unprecedented long and heavy rains in March to June 2017 and 2018 during the same months. This led to reduced pace of construction works. However, most project activities have been completed as planned. Most of the activities are expected to be completed as planned in March 2019.
| Progress on Key Milestones |  | Expected Progress |  | Progress to Date | Rating
Implementing Agency | Component 1 - Addressing climate change impacts on key infrastructure and settlements
| Rehabilitate, construct and upgrade coastal protection facilities to protect settlements economic and cultural infrastructure |  | See above. |  | See above. | S
| Cleaning up of the drainage channels, rehabilitation of storm drains |  | See above. |  | See above. | S
| EIA and feasibility study |  | See above. |  | See above. | S
Component 2 – Ecosystem-based Integrated Coastal Area Management
| Mangrove rehabilitation |  | See above. |  | See above. | MS
| Appropriate alternative energy |  | See above. |  | See above. | S
| Coral reef rehabilitation and protection |  | See above. |  | See above. | MS
| Shoreline stabilization through reforestation |  | See above. |  | See above. | MS
Component 3 – Knowledge, coastal monitoring and policy linkages
| Stocktaking |  | See above. |  | See above. | S
| Coastal monitoring and assessment |  | See above. |  | See above. | MS
| Policy linkages |  | See above. |  | See above. | S
Project operation and management
| Procurement |  | See above. |  | See above. | MS
| Monitoring and evaluation |  | See above. |  | See above. | S
| Establish project management team |  | See above. |  | See above. | S
| Overall Rating |  |  |  |  | S
Please Provide the Name and Contact information of person(s) reponsible for completeling the Rating section
| Name: | Mara Baviera, UNEP Task Manager
| Email: | mara.baviera@un.org
| Progress on Key Milestones |  | Expected Progress |  | Progress to Date | Rating
Other
Overall Rating
Please Provide the Name and Contact information of person(s) reponsible for completeling the Rating section
Name:
Email:
| Please justify your rating and address the following points: 1. Indicate trends, both positive and negative, in achievement of outcomes as per the project indicators. 2. Detail critical risks that have affected progress. 3. Outline response to MTR undertaken this reporting period. 4. Outline action plan to address projects with a rating of HU, U or MU. Please keep your input to 1200 words |  | UNEP TM: The project has been delayed due to various issues relating to procurement, alternative siting, unexpected weather, and other issues discussed in other sections of this report. Despite these challenges, many risks have been mitigated and managed. The project is reaching the expected outcomes and has put a focus on sustaining outcomes by engaging local institutions and actors. In some cases, project target outputs were exceeded (e.g. doubling of beneficiaries for efficient cookstoves, high mangrove survival rates in some sites, exceeding of seawall construction by 50m) all or almost all are on track to be met.
Rating Definitions
|  |  | Highly Satisfactory (HS) | Project actions/activities planned for current reporting period are progressing on track or exceeding expectations to acheive all major outcomes/outputs for given reporting period, without major shortcomings. The project can be presented as “good practice”.
|  |  | Satisfactory (S) | Project actions/activities planned for current reporting period are progressing on track to achieve most of its major outcomes/outputs with only minor shortcomings.
|  |  | Marginally Satisfactory (MS) | Project actions/activities planned for current reporting period are progressing on track to achieve most major relevant outcomes/outputs, but with either significant shortcomings or modest overall relevance.
|  |  | Marginally Unsatisfactory (MU) | Project actions/activities planned for current reporting period are not progressing on track to achieve major outcomes/outputs with major shortcomings or is expected to achieve only some of its major outcomes/outputs.
|  |  | Unsatisfactory (U) | Project actions/activities planned for current reporting period are not progressing on track to achieve most of its major outcomes/outputs.
|  |  | Highly Unsatisfactory (U) | Project actions/activities planned for current reporting period are not on track and shows that it is failing to achieve, and is not expected to achieve, any of its outcomes/outputs.

## Project Indicators
PROJECT Indicators
Please provide all indicators being tracked for the project as outlined in the project document
Type of Indicator (indicators towards Objectives, Outcomes, etc…)
Type of Indicator | Indicator | Baseline | Progress since inception | Target for Project End
Component 1 - Addressing climate change impacts on key infrastructure and settlements
Quantitative | Length of sea walls raised and rehabilitated (m) | Dar es salaam seawall (2.6km) showing signs of severe degradation at Ocean Road and Kingamboni | At Obama/Ocean road 950m of seawall has been completed. 4 920m of walkway and IBD drain done, 950m of guardrail posts done,f 3 beach access staircases constructed and 22 sitting benches constrcuted and completed. One public toilet constrcuted. Seven (7) Solar power street lights erected. Progress of work on site is 100% completion. At Kigamboni/Mwalimu Nyerere Memorial Academy site, sea wall length of 500m was constructed, 250m out of 300m of walkway and 300m out of 500m of IBD drain done, beach access staircase is done while 18 benches have been completed. Progress of work on site is at 100% completed. Total length for the seawall constructed is 950(Obama road) + 500m (Kigamboni) = 1450m. | 1400 linear meters of seawall rehabilitated along Ocean Road and Kingamboni
Quantitative | Length of drainage channels contructed, rehabilitated and upgraded (m) | A total length of 6650m showing severe degradation. This is a total length of four sites of Butiama: 1650m, Kawe: 2650m, Bungoni: 1050m and Mtoni: 1300m. | Dezo Civil Contractors Company Limited which were contracted by UNOPS to rehabilitate, upgrade and construct two sites of Bungoni and Mtoni drainages. 1. At Ilala Bungoni, Ilala Bungoni Drainage Site i. 475m of base construction done. ii. 450m of side slab construction done. iii. 800m of landscape backfill done. iv. Progress of work on site is at 100 completion. v. One solar powered security light have been erected vi. Two pedestrian bridges have been constructed. 2. At Miburini-Mtoni Bustani Drainage : The following has been done: i. 550 of drainage was completed but collapsed following heavy rains in April 2018. Meanwhile all 550m have been reconstructed using new design ii. 5 pedestrian bridges have been constructed. iii. 550 of base construction done. iv. Progress of work on site is at 98% overall completion In this context drainage total length cleaned is 1025m (Ilala) + 1250m (Mtoni, Temeke) = 2275m: Total Length constructed is 475m (Ilala) + 550m(Mtoni, Temeke) =1125m. | By project end-point, at least 2300m of drainage channels cleaned and rehabilitetd
Component 2 - Ecosystem-Based Integrated Coastal Area Management (EBICAM)
Quantitative | Number of households receiving: i) efficient cookstoves; and ii) training on optimal use and maintenance of these stoves (disaggregated by age and gender). | Average wood fuel consumption per capita in Tanzania is 1 to 1.3m3; fuelwood efficiency is estimated at less than 10% on average in all sites; estimated mangrove deforestation rate is 2% per year | 3,000 efficient cook stoves were purchased and distributed to 2999 households. 2999 households were provided with cooking stoves in Ilala, Temeke, Kigamboni, Ubungo and Kigamboni. Monitoring of the beneficiaries continued. The target was doubled with the same budget as the unit prices were lower than indicated in the planned budget. | By project end-point, at least 1,500 households from Ilala, Kinondoni and Temeke Municipal Councils
Quantitative | Area of mangroves under rehabilitation | there are approximately 2,000 ha of mangroves in Dar es Salaam surroundings | Community Distinguished and Environmental Conservation (CODECO) which was recruited in September 2015 to rehabilitate mangroves.This continued with community sensitization and planting of mangroves in the new sites in Tungi Songani and Pembamnazi in Temeke Municipality. At Tundwi Songani, a total of 30,000 propagules of mangroves (equivalent to 12 ha) were planted in March to April 2018. The Survival rate is 85% of the planted mangroves, compared with the target 65%. At Pembanmnazi area 55,000 mangrove propagules (equivalent to total of 22ha was planted in the new sites. Training of local community was conducted in December 2017 and of mangroves was done during rainy season in March to June 2018. A total of 40ha was planted in at Mbweni, Tundwi - Songani and Pembamnazi. gap filling will be done in the next rainy season as a strategy to increase survival rates in all sites (Mbweni, Pembamnazi and Tundwi Songani). The mangrove specialist who was procured in August 2015 renewed his contracted and continued to provide technical advice. Planting started in April 2017 but only one site was planted (i.e. Mbweni), which was planted with 3,200 seedlings. Survival rate is estimated to be 50% from 80% in the previous season due to human activities, in particular, cattle encroachment and effluents from household and uplands, causing accumulation of heavy metals. Other planned sites namely: Salender Bridge, Ununio, Kunduchi were not planted following a land ownership disputes with claimants arising and technical challenges that arose when planting commenced. Steering Committee approved changes to the sites to Kigamboni and Temeke, following assessments from the Tanzanian Forest Service. Total of 40 hectares planted so far at surival rate of between 50-85%. | 40 ha of mangrove rehabilitated in one or more of the following areas: Salender Bridge, Kunduchi, Mbweni and Ununio. 65% survivorship of mangrove species was confirmed as a target.
Quantitative | Area of reef rehabilitated | No recent local data available. Latest data sets show low biocover in existing reefs | SUNARE and Reef restoration specialist continued to monitor development of 3,000m2 area of restored coral at Sinda and Mwakatumbe islands marine reserve. Reef specialist reviewed the report of the coral reef planting and recommended for replanting of some areas where survival rate was below 50%. The consultant submitted final reports on coral reef restoration. | 2000 m2 under rehabilitation. 1300m2 (65%) survivorship of coral reefs was confirmed as a target.
Quantitative | Km of shoreline stabilized using vegetation | rate of coastal erosion estimated between 3 and 8m per year according to recent site specific surveys | Planting of identified species awaited completion of the seawall to avoid disturbance to the planted vegetation. However, planting of native and resilient trees including bushes and grasses along the shore with a particular focus on the rehabilitated infrastructures were delayed. This was due to 2 rounds of procurements without bidders. In the end, a contract for planting of tree and grass as part of seawall stabilization has been signed between VPO and Ilala Municipal Council. After these delays some cash flow issues were encountered and the planting is awaiting cash dsibursement from UNEP targeted for early December 2018. | At least 56,430 m2 of coastal vegetation rehabilitated using three or more fast-growing plant species. 65% survivorship of shoreline vegetation species was confirmed as a target.
Component 3 - Knowledge, coastal monitoring and policy linkages
Quantitative | Availability of a comprehensive baseline study for coastal vulnerability; available knowledge gathered | No baseline data | One (1) baseline study was completed in September 2014. Six reports from Reef specialist, Climate change knowledge management specialist, Coastal zone management specialist, Rural energy consultant, Coastal rehabilitation specialist, Mangrove specialist, NGO for reef rehabilitation, NGO for mangrove rehabilitation and four policies briefs (see section) were produced by consultants. | 1 baseline study in year 1
Qualitative | Effective implementation of clearing house function | No baseline data | The second meeting of members of CCOT was undertaken in April, 2018. Final validation workshop was used as an information sharing platform CCOT members and various project partners in the coastal areas to share experience and lesson learned.CCOT operates through sharing and exchange of information from various network of stakeholders. VPO facilitates such exchange by bringing together various stakeholders. Members of CCOT from higher learning institutions, through their research programmes continued share research findings and information exchange at local, national and international levels | clearing house function is operational by mid-term
Qualitative | Cost-effective measures are identified for upscaling and policy uptake | No baseline data | Five reports were prepared as shown below: 1. Climate change vulnerability and adaptation along the coast of Tanzania: main issues for decision makers, 2. Integrated coastal zone management in Tanzania in the context of climate change adaptation: main issues for decision makers, 3. Sustainable fishing on coral reefs, 4. Coral reef education and awareness, and 5. Restoration of Tanzanian Coral Reefs to aid their Recovery and Sustainable Fishing on Coral Reefs. | At least 1 report.
Quantitative | number of policy briefs provided to key sectors and regulators; number of workshops | No baseline data 0 workshops | Policy workshop on EBICAM Action Plan was undertakein in June 2018. Five 'policy briefs' on seawall and drainage and mangrove planting ; climate change vulnerability and adaptation along the coast of Tanzania: main issues for decision makers, integrated coastal zone management in Tanzania in the context of climate change adaptation: main issues for decision makers, Sustainable fishing on coral reefs, Coral reef education and awareness, Restoration of Tanzanian Coral Reefs to aid their Recovery and Sustainable Fishing on Coral Reefs were finalised and presented at the stakeholders meetings. | Annually, 2 policy briefs (1 on measures to adapt to climate change, 1 on general lessons learned).2 workshops (1 on cost-effective measures to adapt to climate change, 1 on general lessons learned).
Quantitative | Number of reports developed through the AF project on required district budget allocations to maintain infrastructure for adaptation to climate change. | 0 | 1 final report on district level infrastructure maintenance programme available. The report recommends that apart from awareness programme local districts authorities need to integrate infrastructures maintenance in their planning and sustain outreach initiatives. This will ensure that both local district authorities and local communities fully take control and ownership of the constructed infrastructures. | 1 report.
Quantitative | Number of plans approved | no plans yet available but ICZM capacity exists | The EBICAM Action Plan of coastal regions of Tanzania (Dar es Salaam, Lindi, Mtwara, Tanga and Coast) and Zanzibar are integrated into regional and district action plans. Second consultative stakeholders workshop to validate the draft EBICAM Action Plan was held in April 2018 in Dar es Salaam to Dodoma. | One EBICAM Action plan of Region approved by end of project.

## Lessons Learned
QUALITATIVE MEASURES and LESSONS LEARNED
Please complete the following section every reporting period
Implementation and Adaptive Management | Response
What implementation issues/lessons, either positive or negative, affected progress? | Baseline information on land ownership and governance is prudent in the design of project implementation. Following arising of land tenure issues at Kinondoni, it was necessary to move to new site (Kigamboni Municipal Council), this subsequently resulted in to delayed implementation of the project activities. In addition, it is important to explore how non-project related matters such as land tenure and weather can impact the project and manage for risks accordingly. These issues need to be taken into account in the project design and resources to enable timely completion of the project. This can help to avert unforeseen delays in the procurement process and execution of the project activities. Having sufficient and robust baseline data is important for the optimal project design. It is better to concentrate efforts in a small number of project activities and sites in order to bring more impact of the project. There is need for involvement of multi-stakeholders (including spacial planning) and weather specialists in project design and implementation so as to be able to take on board future plans on the project sites. It is critical that the project design recognizes the importance of closely involving local stakeholders and weather specialists in the design and implementation of the project. Procurement delays was one of the constraints in the project implementation. However, procurement partnership and subcontracting some of the procurement activities (assigning UNOPS for infrastructure, early planning/start of procurement and partnerships internally in VPO) helped to address the challenge. In addition, the experiences of this project have clearly shown how land tenure is a critical factor to consider in the planning of mangrove activities. Even though selection of the project sites were done in the consultative manners, some stakeholders in particularly, those individuals who claim ownership in the mangrove protected area did not participate in the consultation since they do not have legal ownership. This resulted into potential conflict during implementation. However, having flexibility to change plans and scope as alternative sites can help to alleviate emerging challenges on land conflicts. However, the changes in project sites, despite of causing delays for project completion, did not affect the project indicators since the target to plant 40ha remained unchanged. Moreover, sustainability issues regarding maintenance of infrastructure investments (in kind or through budget) need engagement of local communities and district level so as to provider ownership of the infrastructure. Some Municipalities such as Temeke has already put in place plans and leveraged resources from other sources to upgrade and reconstruct all drainages in their jurisdiction taking into account noticeable adverse impacts of climate change. Project entry and exit strategy should be built and banked on the engagement of political leaders at all levels so as to ensure sustainability of the infrastructure. This is most evident for the drainage, where some signs of encroachment and trash arising from petty business garage activities in the vicinity are seen. Awareness creation and capacity building as precursor of sustainability need to be mainstreamed holistically across the entire ecosystem and should involve communities and leaders from both upper and lower stream. This can reduce or alleviate the problem of encroachment and waste/trash dumping across entire drainage. Clarity of the plot boundaries in the project areas are of essence for both.
Were there any delays in implementation? If so, include any causes of delays. What measures have been taken to reduce delays? | Delay of the baseline study that was expected to be completed in the first year of the project has caused delays in the implementation of the project. The baseline study was completed in September 2014. EIA and feasibility studies could not be undertaken in 2014. As a measure, the firm to undertake EIA study has been contracted and UNOPS contracted to work on seawall and drainage rehabilitation and construction and feasibility study. Delays in procurement of consultancies delayed the implementation of the project. As a measure all necessary consultancies were launched at the same time where currently about 88% of all required consultants have signed contracts. Change of paying system of UNEP to Umoja system caused a bit delay of activities for the period of July-December 2015 since the project lacked funds within this period. The lesson is that it might be of help to request enough funds throughout the year based on the annual work plan. Disbursement of funds was no longer a challenge after Umoja system was sorted out. However, planting of mangroves has delayed awaiting for the rainy season in March 2017. In addition, new councilors following General election in 2015 delayed processing of building permits by the Dar es salaam City Council for Ocean Road and Kigamboni Sea Wall Sites and by Ilala Municipal Council for Bungoni Drainage Site. Presence of focal points in the municipalities helped clarify the matter and buiding permits were issued. A further delaying factor has been related to cash flow issues of the contractor building the sea walls and drainage. Measures taken to improve this situation includes: making sure payments are tied to deliverables and, where possible, direct payments to the other sub-constructors (materials etc.). Other delaying factors include procurement and land tenure issues as outlined above.
Describe any changes undertaken to improve results on the ground or any changes made to project outputs (i.e. changes to project design) | At Obama/Ocean road 100meters without seawall was added as new construction (as opposed to the planned rehabilitation) to make the total length 920. At Kigamboni/Mwalimu Nyerere Memorial Academy site, an extra 120 of sea wall length has been constructed following savings from the budget. This additional length will protect Uhuru builing which was als in danger of being swept by sea waves. . This was also possible beacause of the saving from the budget for this component. The target for shoreline rehabilitation was increased to 56,430 m2 as a result of detailed assessments made in the baseline study, this length is expecetd to be planted with some grasess and trees. The Reef specialist monitored the site and recommended replanting in areas where survivorship of species was found to be below 65%.
How have gender considerations been taken into consideration during the reporting period? What have been the lessons learned as a consequence of inclusion of such considerations on project performance or impacts? | Within the national team, a Finance and Administration Assistant is a woman. The project design considered gender and most of the ward environmental committee members (8 out 12 members of the committee in Kindononi and Ilala) were women. In Kinondoni Municipality, planting of mangroves at Mbweni and Kunduchi were done by women. Project activities such as training and workshops took into account the issue of gender. Some project activities such as provision of efficient cook stoves which were provided to 1000 households in each district of Ilala, Kinondoni and Temeke municipalities are likely to benefit more women of each beneficiary household. The project focal point at Kigamboni was a woman who helped to advocate the project among women at Mwalimu Nyerere Academy, Kigamboni. Even though selection of project focal points in each of the municipalities was not based on gender balance as it was predetermined by the existence of the environmental focal points who automatically assumed the role of project focal pints, it was worth to learn that this did not affect the focus of the project ensure that more women and disadvantaged groups were the most beneficiaries of the project especially in the distribution of cookstoves and training of community groups . In addition, both the contractor and supervisor had two women in their teams that generated interests to other women to visit the project.
Lessons and measures related to coordination with the LDCF project 'Developing core capacity to address adaptation to climate change in Tanzania in productive coastal zones' | Mangrove planting requires a lot of stakeholders’ engagement, including individuals, local communities, scientists, fishermen, political leaders. The interplay between local communities and planners/government is fundamental in launching successful mangrove planting, seedling collection and monitoring. Although approaches used in mangrove planting were similar in both AF and LDCF projects, local context of each of the project sites determined the speed and extent at which the project activities were implemented. Progress of the project activities were slow in areas where there were some potential conflict such Kinondoni and Rufiji for both AF and LDCF projects. In both projects, it was evident that planning for mangrove planting need to extend for more than one season in order to enable continued monitoring and gap filling in case there is high mortality.
Please complete the following section at mid-term and project completion
Lessons for Adaptation | Response
Climate Resilience Measures
What have been the lessons learned, both positive and negative, in implementing climate adaptation measures that would be relevant to the design and implementation of future projects/programmes for enhanced resilience to climate change? | Sufficient and robust baseline data is important for the design and scope of the project and assesment of cost-benefits of the project. Such information is crucial for potential replicability of the project activities. It is critical that project design recognizes the importance of closely involving local stakeholders during design and implementation of the project. Understanding of climatic variations, land goverance and are important factors in implementing some project activities that are geared to enhance resilience to climate change.
What is the potential for the climate resilience measures undertaken by the project/programme to be replicated and scaled up both within and outside the project area? | Complimentarity of construction of seawalls and drainage systems is expected to increase resilience of seawalls against floods. The government has taken initiatives to ensure that more drainages channels are constructed. This is being done through a project known as Tanzania Urban Resilience Project funded by DFID through WB. Given this complimentarity, it was possible to address some challenges at Mtoni . At this site, part of length of the drainage that was planned to be built at the upper of Kilwa road was switched to lower part of across the road so as to allow future plans through Temeke Municipality to take into account expansion of the road and construction of new drainages.
Concrete Adaptation Interventions
What have been the lessons learned, both positive and negative, in implementing concrete adaptation interventions that would be relevant to the design and implementation of future projects/programmes implementing concrete adaptation interventions? | In order to multiply co-benefits and reduce collateral costs, the dynamics and nature of priority sites have to be studied when designing the specific actions that will be conducted in them. Project developers have to understand what people do around the sites, and how the interventions will modify the dynamics around them. The demographic, economic, social and pollution trends of a country and its regions have to be analyzed together with the climate trends when prioritizing components, activities and sites at project design. Ignoring demographic, economic and social trends can lead to mal-adaptation, in the worst-case scenario, and to missing the opportunity of making strategic investments, in the best-case scenario.
What is the potential for the concrete adaptation interventions undertaken by the project/programme to be replicated and scaled up both within and outside the project area? | The proper design of the project interventions arising from the training of communities on sustainable fishing and coral restoration, energy efficient cooking stoves, mangrove planting and climate change impacts that were conducted prior to project implementation and actual activities really reduce vulnerability people to climate change in the respective areas. In addition, training and awareness creation can leverage more community and political support. This attributable to the real reduced impacts those local communities are able to see and witness on the ground. This can result into multiplier effect and induce direct adaptation benefits and ensure the provision of significant environmental, social and economic co-benefits. There is increased awareness beyond the target stakeholders and some stakeholders who are beyond the project boundaries. Through EBICAM and CCOT platforms, sharing of information and experience enhanced knowledge management.
Community/National Impact
What would you consider to be the most successful aspects for the target communities? | Seawall construction despite being expensive and a relatively new adaptation measure in the country has raised awareness on climate change and the extent of both community and government engagement in addressing climate change. This is due to the fact that the constructed seawall is likely to trigger other benefits such as ecotourism and serve as one of the city parks and economic activity that will arise from petty traders flocking the area. In addition, rehabilitation and construction of drainage channels resulted into immediate benefits in reducing impacts of floods in the project sites, and this can be easily noticed by local communities where such infrastructures were constructed. Furthermore, involvement of the community has been significant through training, decision-making and implementing activities in the field including community members and groups, government stakeholders and other local stakeholder groups (non-government). Adoption of passive designs that incorporates simple technology, easy to maintain and climate change resilient.
What measures are/have been put in place to ensure sustainability of the project/program results? | All hard infrastructures, i.e. seawalls and drainage channels have been handed over to the respective municipal councils and institutions for their management. Experts at municipal council and the local communities have been involved in design, implementation and monitoring of the project activities. With respect to mangrove planting, engagement of Tanzania Forest Services (TFS) which is the sole custodian of mangrove protection in the country as well as involvement of local communities in the planting and monitoring of the project activities have enhanced sustainability of the project activities. Public awareness campaigns through the use of social media at national and local level, and use of PSC and the Technical Committees which will continue to exist beyond the project life. The issue of solid waste management will be taken into plans and budgets of the respective municipalities. Training and monitoring on piloting on use of efficient cookstoves was likely to enhance sustainability of the project results.
What measures are being/could have been put in place to improve project/program results? | The project did not have enough resources for printing of the project documents which are essential for information dissemination. The printing of policy briefs will improve dissemination of projects results beyond the project boundaries. However, printing is likely to be done using resources that will be saved from other activities.
Knowledge Management
How has existing information/data/knowledge been used to inform project development and implementation? What kinds of information/data/knowledge were used? | Baseline socio-economic, information and meteorological data helped to design the project and design of both infrastructures. Reports/studies that were used included Vulnerability Assessment of Coastal Areas to the Impacts of Climate Change that was conducted in 2009. However, in the realm of climate change continuous monitoring of meteorological data should determine the final design of the designs so as to enhance durability and sustainability of new adaptation strategies/structures.
If learning objectives have been established, have they been met? Please describe. | Learning objectives were met.
Describe any difficulties there have been in accessing or retrieving existing information (data or knowledge) that is relevant to the project. Please provide suggestions for improving access to the relevant data. | Lack of involvement of local government staff (municipal council) in the project was a challenge in the beginning. Signing an MOU with local goverenment and engagement of local communities increased access to data and information and boosts cooperation among actors.
Has the identification of learning objectives contributed to the outcomes of the project? In what ways have they contributed? | Yes, knowledge management, training workshop on energy efficiency, district financing, sustaiable fishing and coral reef rehabilitation and budgeting as well as ecosystem management supported the beneficiaries' knowledge. Skills obtained from those training are being used in planting of mangroves, seed and site selections for mangrove restoration, shoreline stabilization, planning and designing for other similar projects, and identification of beneficiaries for the efficient cook stoves, monitoring of construction works ensures quality of works.

## Results Tracker
Results Tracker for Adaptation Fund (AF) Projects
Goal: Assist developing-country Parties to the Kyoto Protocol that are particularly vulnerable to the adverse effects of climate change in meeting the costs of concrete adaptation projects and programmes in order to implement climate-resilient measures. Impact: Increased resiliency at the community, national, and regional levels to climate variability and change.
Important: Please read the following guidance document (also posted on the Adaptation Fund website) before entering your data
Link: http://www.adaptation-fund.org/sites/default/files/Results%20Framework%20and%20Baseline%20Guidance%20final.pdf
Adaptation Fund Strategic Results Framework
Project ID | AFB-5060-1111-2G48
Implementing Entity | UNEP
Type of implementing entity | MIE
Country | Tanzania
Region | Africa
Sector | Coastal management
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Impact: Increased resiliency at the community, national, and regional levels to climate variability and change | Core Indicator: No. of beneficiaries |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project | Limited impact | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project | Limited impacts | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project
|  | Total | 0 | 0 | 0 | Total | 1484942 | 182155 | 1302787 | Total | 3000 | 2999 | 0 | Total
|  | % of female beneficiaries | 0% | 0% | 0% | % of female beneficiaries | 60.67% | 58.2% | 61.01% | % of female beneficiaries | 90% | 90% | 0% | % of female beneficiaries
|  | % of Youth beneficiaries | 0% | 0% | 0% | % of Youth beneficiaries | 0% | 0% | 0% | % of Youth beneficiaries | 0% | 0% | 0% | % of Youth beneficiaries
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 1: Reduced exposure to climate-related hazards and threats | Indicator 1: Relevant threat and hazard information generated and disseminated to stakeholders on a timely basis | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness
|  | Total | 0 |  |  | Total | 0 |  |  | Total |  |  |  | Total
|  | % of female targeted |  |  |  | % of female targeted |  |  |  | % of female targeted |  |  |  | % of female targeted
Output 1.1 Risk and vulnerability assessments conducted and updated | Indicator 1.1: No. of projects/programmes that conduct and update risk and vulnerability assessments | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | 5 | Multi-sector | National | 3: Risk and vulnterability assessments completed or updated |  | Coastal management | National | 3: Risk and vulnterability assessments completed or updated | 5 | Multi-sector | National | 3: Risk and vulnterability assessments completed or updated
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
Output 1.2 Targeted population groups covered by adequate risk reduction systems | Core Indicator 1.2: No. of Early Warning Systems | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  | 0 |  | Geographical coverage |  | 0 |  | Geographical coverage |  | 0 |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 2: Strengthened institutional capacity to reduce risks associated with climate-induced socioeconomic and environmental losses | Indicator 2: Capacity of staff to respond to, and mitigate impacts of, climate-related events from targeted institutions increased | Number of staff targeted |  | Sector | Capacity level | Number of staff targeted |  | Sector | Capacity level | Number of staff targeted |  | Sector | Capacity level | Number of staff targeted |  | Sector | Capacity level
|  | Total | 0 | Coastal management | 2: Low capacity | Total | 60 | Coastal management | 4: High capacity | Total | 57 | Coastal management | 3: Medium capacity | Total
|  | % of female targeted | 0% |  |  | % of female targeted | 50% |  |  | % of female targeted | 37% |  |  | % of female targeted
Output 2.1 Strengthened capacity of national and sub-national centres and networks to respond rapidly to extreme weather events | Indicator 2.1.1: No. of staff trained to respond to, and mitigate impacts of, climate-related events | Total staff trained | % of female staff trained | Type |  | Total staff trained | % of female staff trained | Type |  | Total staff trained | % of female staff trained | Type |  | Total staff trained | % of female staff trained | Type
|  | 0 | 0% | Public |  | 60 | 50% | Public |  | 57 | 37% | Public
| Indicator 2.1.2: No. of targeted institutions with increased capacity to minimize exposure to climate variability risks | Type | Scale | Sector | Capacity level | Type | Scale | Sector | Capacity level | Type | Scale | Sector | Capacity level | Type | Scale | Sector | Capacity level
|  | Public | Local | Coastal management | 2: Low capacity | Public | Local | Coastal management | 4: High capacity | Public | Local | Coastal management | 3: Medium capacity
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 3: Strengthened awareness and owernship of adaptation and climate risk reduction processes | Indicator 3.1: Increase in application of appropriate adaptation responses | Percentage of targeted population applying adaptation measures |  | Sector |  | Percentage of targeted population applying adaptation measures |  | Sector |  | Percentage of targeted population applying adaptation measures |  | Sector |  | Percentage of targeted population applying adaptation measures |  | Sector
Output 3: Targeted population groups participating in adaptation and risk reduction awareness activities | Indicator 3.1.1: Percentage in targeted population awareness of predicted adverse impacts of climate change, and of appropriate responses | No. of targeted beneficiaries | % of female participants targeted | Level of awareness |  | No. of targeted beneficiaries | % of female participants targeted | Level of awareness |  | No. of targeted beneficiaries | % of female participants targeted | Level of awareness |  | No. of targeted beneficiaries | % of female participants targeted | Level of awareness
|  | 0 |  |  |  | 0
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Target performance at completion
Outcome 4: Increased adaptive capacity within relevant development sector services and infrastructure assets | Indicator 4.1: Increased responsiveness of development sector services to evolving needs from changing and variable climate | Project/programme sector | Geographical scale | Response level |  | Project/programme sector | Geographical scale | Response level |  | Project/programme sector | Geographical scale | Response level |  | Project/programme sector | Geographical scale | Response level
|  | Coastal management | Local | 2: Partially responsive (Lacks most elements) |  | Coastal management | Local | 4: Mostly responsive (Most defined elements) |  | Coastal management | Local | 3: Moderately responsive (Some defined elements)
| Core Indicator 4.2: Assets produced, developed, improved or strengthened | Sector | Targeted asset | Changes in asset (quantitative or qualitative) |  | Sector | Targeted asset | Changes in asset (quantitative or qualitative) |  | Sector | Targeted asset | Changes in asset (quantitative or qualitative) |  | Sector | Targeted asset | Changes in asset (quantitative or qualitative)
|  | Coastal management | 2: Physical asset (produced/improved/strenghtened) | 1: Not improved |  | Coastal management | 2: Physical asset (produced/improved/strenghtened) | 4: Mostly Improved |  | Coastal management | 2: Physical asset (produced/improved/strenghtened) | 1: Not improved
|  | Urban development | 2: Physical asset (produced/improved/strenghtened) | 1: Not improved |  | Urban development | 2: Physical asset (produced/improved/strenghtened) | 4: Mostly Improved |  | Urban development | 2: Physical asset (produced/improved/strenghtened) | 1: Not improved
Output 4: Vulnerable development sector services and infrastructure assets strengthened in response to climate change impacts, including variability | Indicator 4.1.1: No. and type of development sector services to respond to new conditions resulting from climate variability and change | Number of services | Type |  | Sector | Number of services | Type |  | Sector | Number of services | Type |  | Sector | Number of services | Type |  | Sector
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 5: Increased ecosystem resilience in response to climate change and variability-induced stress | Indicator 5: Ecosystem services and natural resource assets maintained or improved under climate change and variability-induced stress | Natural resource improvement level |  | Sector | Type | Natural resource improvement level |  | Sector | Type | Natural resource improvement level |  | Sector | Type | Natural resource improvement level |  | Sector | Type
|  | 3: Moderately effective |  | Coastal management | biological assets
Output 5: Vulnerable ecosystem services and natural resource assets strengthned in response to climate change impacts, including variability | Core Indicator 5.1: Natural Assets protected or rehabilitated | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Mangroves | 4 | ha rehabilitated | 2: Partially effective | Mangroves | 40 | ha rehabilitated | 4: Effective | Mangroves | 1 | ha rehabilitated | 2: Partially effective
|  | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Other | 1 | ha rehabilitated | 2: Partially effective | Other | 1 | ha rehabilitated | 4: Effective
|  | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Coasts | 1 | km rehabilitated | 2: Partially effective | Coasts |  |  | 4: Effective | Coasts | 1 |  | 2: Partially effective
|  | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Baseline information |  |  |  | Targeted performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 6: Diversified and strengthened livelihoods and sources of income for vulnerable people in targeted areas | Indicator 6.1: Increase in households and communities having more secure access to livelihood assets | No. of targeted households | % of female headed households | Improvement level |  | No. of targeted households | % of female headed households | Improvement level |  | No. of targeted households | % of female headed households | Improvement level |  | No. of targeted households | % of female headed households | Improvement level
| Indicator 6.2: Increase in targeted population's sustained climate-resilient alternative livelihoods | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
|  | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
|  | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
|  | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
Output 6 Targeted individual and community livelihood strategies strengthened in relation to climate change impacts, including variability | Indicator 6.1.1: No. and type of adaptation assets created or strengthened in support of individual or community livelihood strategies | Number of Assets | Type of Assets | Sector | Adaptation strategy | Number of Assets | Type of Assets | Sector | Adaptation strategy | Number of Assets | Type of Assets | Sector | Adaptation strategy | Number of Assets | Type of Assets | Sector | Adaptation strategy
| Core Indicator 6.1.2: Increased income, or avoided decrease in income | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | 0 |  |  |  | 0 |  |  |  | 0
|  | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 7: Improved policies and regulations that promote and enforce resilience measures | Indicator 7: Climate change priorities are integrated into national development strategy | Integration level |  |  |  | Integration level |  |  |  | Integration level |  |  |  | Integration level
Output 7:Improved integration of climate-resilience strategies into country development plans | Indicator 7.1: No. of policies introduced or adjusted to address climate change risks | No. of Policies introduced or adjusted | Sector | Scale | Type | No. of Policies introduced or adjusted | Sector | Scale | Type | No. of Policies introduced or adjusted | Sector | Scale | Type | No. of Policies introduced or adjusted | Sector | Scale | Type
|  | 0 | Coastal management | National | Environmental policy | 1 | Coastal management | National | Environmental policy/coastal zone | 0 | Coastal management | National | Environmental policy/coastal zone
| Indicator 7.2: No. of targeted development strategies with incorporated climate change priorities enforced | No. of Development strategies | Regulation |  | Effectiveness | No. of Development strategies | Regulation |  | Effectiveness | No. of Development strategies | Regulation |  | Effectiveness | No. of Development strategies | Regulation |  | Effectiveness
|  | 0 | 3: Partially enforced (Some elements implemented) |  | 3: Moderately effective | 1 | 4: Enforced (Most elements implemented) |  | 4: Effective | 1 | 3: Partially enforced (Some elements implemented) |  | 3: Moderately effective
Glacier lake outburst flood
|  | Inland flooding | fr | biological assets |  | Company policy | 5: Fully enforced (All elements implemented)
|  | Salinization | Decrease | land |  | Communication & Information policy | 4: Enforced (Most elements implemented)
|  | Drought | Same | water areas |  | Defense policy | 3: Partially enforced (Some elements implemented)
|  | Wind |  | subsoil assets | increased adpative capacity | Domestic policy | 2: Partially not enforced (Most elements not implemented) |  | Agribusiness
|  | Coastal flooding |  | air | achieved | Economic policy | 1: Not enforced (No elements implemented) |  | Agricultural-related | Financial capital
|  | Storm surge | Please choose |  | enhanced level of protection | Education policy |  |  | Agriculture | Human capital
|  | Hurricane | Selected | [5 empty] | Aquaculture | Physical capital
|  |  | Not relevant |  |  | 5: All (Fully integrated) |  |  | Construction/repairing business | Social capital
[6 empty] | 4: Most |  |  | Cultivation | Natural capital
[6 empty] | 3: Some |  |  | Fishing | Personal capital
Select | 5: All | Select |  |  | Community | 2: Most not integrated |  | Other | Forestry | Adaptation strategies
1 | 4: Almost all | Private | Type | Yes | Multi-community | 1: None |  | Agriculture | Handicrafts
2 | 3: Half | Public | Scale | No | Departmental |  |  | Coastal management | Livestock production
3 | 2: Some | NGO | Sector |  | National |  |  | Disaster risk reduction | Manufacturing
4 | 1: None |  |  |  |  | 5: Very high improvement | Established | Food security | other
|  | National |  |  |  | 4: High improvement | Maintained | Health | Services
|  | Regional |  |  |  | 3: Moderate improvement | Improved | Urban development | Tourism-related
|  | Local |  |  |  | 2: Limited improvement |  | Water management | Trading
[6 empty] | 1: No improvement |  | Multi-sector
|  | 1 -generated information is irrelevant, and neither the stakeholders reached nor the timeframe managed were achieved | 1: No info transferred on time | 4: High capacity | 5: Fully aware | 5: Highly responsive (All defined elements ) | 5: Fully improved | Roads | 5: Very effective
Asia-Pacific | NIE | 2 -the existence of some challenge in any of the three aspects of the indicator (generation of dissemination, stakeholders reached or timeframe managed) | 2: Somewhat info transferred | 3: Medium capacity | 4: Mostly aware | 4: Mostly responsive (Most defined elements) | 4: Mostly Improved | Gov Buildings | 4: Effective
Latin America and Caribbean | RIE | 3 -relevant information is generated and disseminated to all identified stakeholders on timely basis | 3: Info transferred on time | 2: Low capacity | 3: Partially aware | 3: Moderately responsive (Some defined elements) | 3: Moderately improved | Causeways | 3: Moderately effective
Africa | MIE |  |  | 1: No capacity | 2: Partially not aware | 2: Partially responsive (Lacks most elements) | 2: Somewhat improved | Airports | 2: Partially effective
Eastern Europe |  |  |  |  | 1: Aware of neither | 1: Non responsive (Lacks all elements ) | 1: Not improved | Schools | 1: Ineffective
| ha protected | [6 empty] | Training Centres
| ha rehabilitated | [5 empty] | Monitoring/Forecasting capacity | Hospitals
Afghanistan, Islamic Rep. of | km protected | [5 empty] | Policy/regulatory reform | Drinking water systems
Angola | km rehabilitated | 1: Risk knowledge | 1: No plans conducted or updated |  |  |  | Capacity development | Other
Albania |  | 2: Monitoring and warning service | 2: Undertaking or updating of assessments in progress |  |  | Communication & Information policy | Sustainable forest management
Argentina |  | 3: Dissemination and communication | 3: Risk and vulnterability assessments completed or updated |  |  | Domestic policy | Strengthening infrastructure | 1: Health and Social Infrastructure (developed/improved)
Armenia | Forests | 4: Response capability |  |  |  | Economic policy | Supporting livelihoods | 2: Physical asset (produced/improved/strenghtened)
Antigua and Barbuda | Mangroves |  |  |  |  | Education policy | Mangrove reforestation
Azerbaijan | Coasts |  | From 0 to 0.5% |  |  | Energy policy | Coastal drainage and infrastructure
Burundi | Rangelands |  | From 0.5 to 1% |  |  | Environmental policy | Irrigation system
Benin | Cultivated land/Agricultural land |  | From 1% to 5% |  |  | Foreign policy | Community-based adaptation
Burkina Faso | Catchment area/Watershed/Aquifer |  | From 5% to 10% |  |  | Health policy | Erosion control
Bangladesh | Protected areas/National parks |  | From 10% to 20% |  |  | Housing policy | Soil water conservation
Bulgaria | Other |  | From 20% to 30% |  |  | Human resource policies | Microfinance
Bahrain |  |  | From 30% to 40% |  |  | Information policy | Special Program for women
Bahamas, The |  |  | From 40% to 50% |  |  | Macroeconomic policy | Livelihoods
Bosnia and Herzegovina |  |  | Above 50% |  |  | Monetary policy | Water storage
Belarus | [5 empty] | Population policy | ICT and information dissemination
Belize | [5 empty] | Private policy
Bolivia | [5 empty] | Public policy
Brazil | [5 empty] | Science policy
Barbados | [5 empty] | Social policy
Bhutan |  | 3- relevant information is generated and disseminated to all identified stakeholders on timely basis |  |  |  | Transportation policy
Botswana |  | describe |  |  |  | Urban policy
Central African Republic |  | 2- the existence of some challenge in any of the three aspects of the indicator |  |  |  | Water policy
Chile |  | describe |  |  |  | Other policy
China, People's Republic of |  | 1- generated information is irrelevant and neither the stakeholders reached nor the timeframe managed were achieved
Cote d'Ivoire |  | describe
Cameroon
Congo, Dem. Rep. of
Congo, Republic of
Cook Islands
Colombia
Comoros
Cape Verde
Costa Rica
Cuba
Czech Republic
Djibouti
Dominica
Dominican Republic
Algeria
Ecuador
Egypt
Eritrea
Estonia
Ethiopia
Fiji
Micronesia, Fed. States of
Gabon
Georgia
Ghana
Guinea
Gambia, The
Guinea-Bissau
Equatorial Guinea
Grenada
Guatemala
Guyana
Honduras
Croatia
Haiti
Hungary
Indonesia
India
Iran, Islamic Republic of
Jamaica
Jordan
Kazakhstan
Kenya
Kyrgyz Republic
Cambodia
Kiribati
Saint Kitts and Nevis
Korea, Republic of
Lao People's Democratic Republic
Lebanon
Liberia
Libya
Saint Lucia
Sri Lanka
Lesotho
Lithuania
Latvia
Morocco
Moldova
Madagascar
Maldives
Mexico
Marshall Islands
Macedonia, former Yugoslav Republic of
Mali
Malta
Myanmar
Montenegro
Mongolia
Mozambique
Mauritania
Mauritius
Malawi
Malaysia
Namibia
Niger
Nigeria
Nicaragua
Niue
Nepal
Nauru
Oman
Pakistan
Panama
Peru
Philippines
Palau
Papua New Guinea
Poland
Korea, Dem. People's Rep. of
Paraguay
Romania
Russian Federation
Rwanda
Saudi Arabia
Sudan
Senegal
Solomon Islands
Sierra Leone
El Salvador
San Marino
Serbia
Sao Tome and Principe
Suriname
Slovak Republic
Slovenia
Swaziland
Seychelles
Syrian Arab Republic
Chad
Togo
Thailand
Tajikistan
Turkmenistan
Tonga
Trinidad and Tobago
Tunisia
Turkey
Tuvalu
Tanzania
Uganda
Ukraine
Uruguay
Uzbekistan
Saint Vincent and the Grenadines
Venezuela
Vietnam
Vanuatu
Samoa
Yemen, Republic of
South Africa
Zambia
Zimbabwe
Timor-Leste
Note on D21: Lars Christiansen: Note: these have been revised based on more detailed inventories conducted during 2016 by local authorities. They are still approximations however and thus represents a best guess based on current information. Information on youth was not possible to obtain at this point. The definition of direct beneficiaries applied is: people directly impacted by project interventions (e.g. protecting their personal property from impacts of coastal erosion or flooding, recepients of cookstoves, people participating in reforestation or coral activities and/or receiving training). The definition of indirect beneficiaries is: broader population living in neighborhoods targeted by interventions (i.e. Ocean/Obama road, Kigamboni, Ilala, Temeke and Kinandoni). Data is from local authorities and as such subject to some uncertainty and could be further revised in the final assessment by project closure. We are happy to share the raw data if this is of interest to AF. A wider definition of indirect beneficiaries could also include a general population of Dar es Salaam (e.g. including daily users of the very busy Ocean/Obama road), but we feel the above interpretation is more objective. We are happy to revise based on advise and further definition of terms from AFsec.
Note on M21: Lars Christiansen: This represents heads of households recepients of cookstoves distributed so far (we do not have information on size of households, so direct impact is significantly higher). As infrastructure work had only just started at time of reporting, neither direct or indirect impact can be claimed here (by far the largest target group of quoted targets)
Note on N21: Lars Christiansen: This represents heads of households recepients of cookstoves distributed so far (we do not have information on size of households, so direct impact is significantly higher). As infrastructure work had only just started at time of reporting, neither direct or indirect impact can be claimed here (by far the largest target group of quoted targets)
Note on E89: Lars Christiansen: why can't we provide zero as the baseline here??
Note on M89: Mara Baviera: performance at mid-term is 0
Note on D92: Lars Christiansen: Corals are not an option so have left out
Note on E95: Lars Christiansen: see above why can't this be 0?
Note on I95: Lars Christiansen: Cannot provide 1.5, which is the accurate target for shoreline rehabilitation. Very hard to use this template with so many restrictions on format!
Note on M95: Mara Baviera: Performance at mid-term is 0.

## Units for Indicators
Fund Outcome Indicator Units
1. Generation of relevant data, Stakeholders, and Timeliness 2.1. Include both qualitative and quantitative measures of capacity level within targeted institutions 2.2. Number (men and women and other vulnerable groups) 3.1. Use scale from 1 to 5: 5: Fully aware 4: Mostly aware 3: Partially aware 2: Partially not aware 1: Aware of neither predicted adverse impacts of climate change nor of appropriate responses 3.2. Use scale from 1 to 5: 5: All 4: Almost all 3: Half 2: Some 1: None 4.1. Summarize in an overall scale (1-5): 5: Highly responsive (All defined elements ) 4: Mostly responsive (Most defined elements) 3: Moderately responsive (Some defined elements) 2: Partially responsive (Lacks most elements) 1: Non responsive (Lacks all elements ) 4.2. Summarize in an overall scale (1-5): 5: Fully improved 4: Mostly Improved 3: Moderately improved 2: Somewhat improved 1: Not improved 5. Depends on the targeted natural asset: Biological (species): measure through changes in population numbers (dynamics, structure, etc.) Land: measure changes in hectares. Baseline data will be necessary to estimate the change. Supporting indicators baseline and target (as well as contextual information) are needed such as the following: Farmers adopting recommended technologies, Ha. of land improved, Average deforestation rate Etc. Use scale from 1 to 5. 5: Very effective (All elements are present) 4: Effective (Most elements are present) 3: Moderately effective (Some elements are present) 2: Partially effective (Most elements are not present) 1: Ineffective (No elements are present) 6.1. Summarize in an overall scale (1-5): 5: Very high improvement 4: High improvement 3: Moderate improvement 2: Limited improvement 1: No improvement 6.2. Household income by source of livelihood in project area (USD) prior and post project intervention 7. Summarize in an overall scale (1-5). 5: All (Fully integrated) 4: Most 3: Some 2: Most not integrated 1: None
Fund Output Indicator Units
1.1. Number, sector(s) and level(s) of projects or interventions in separate fields of monitoring plan 1.2. Number 2.1.1. Number of staff (male/female) of targeted institutions: a. Obtain baseline information: total number of staff from targeted institutions b. Define target 2.1.2. Number of staff (male/female) of targeted institutions: a. Obtain baseline information: total number of staff from targeted institutions b. Define target: needs to be defined by project proponents 2.2.1. Quantitative: Percentage (includes women – and other vulnerable groups – and men). Qualitative: Adequacy: include direct analysis of major areas; adequacy/effectiveness of systems or analysis of perceptions of populations and institutions. 2.2.2. Number (broken down by gender and, if possible, by vulnerable groups defined in the area of intervention) of people 3.1. Number and type (in separate columns) at local level. 3.2. Number 4.1. Number and type 4. 2. Number and type (entered in separate columns) 5. Number of interventions by type of natural asset and intervention 6.1. Number and type (in separate columns of monitoring plan) 6.2. Income sources per household; description of income source and number of households. 7.1. Number/Sector 7.2. Number; Effectiveness (see previous indicator) through enforcement level.