## Overview
Project Performance Report (PPR)
| Period of Report (Dates) | 1 February 2014 - 31 Januray 2015
| Project Title: | Enhancing Resilience of Coastal Communities to Climate Change in Samoa
| Project Summary: | This programme is designed to complete a holistic and country-wide approach to climate change adaptation in the coastal zones in Samoa. It will provide the vehicle to revise and implement the approved Coastal Infrastructure Management (CIM) Plans on the ground as a practical community based response to adaptation. The program will result in a “whole of country” adaptation response for coastal management at the nationwide scale. The implementation of appropriate responses will be supported by the programme through site specific design of adaptation interventions and active community engagement in the process. The programme will serve to implement the CIM Strategy, which was originally prepared in 2000 and revised in 2006 to include specific reference to CC related issues. In particular the predicted hazard zones were reviewed against the NAPA data (2005) and inter-alia the Climate Risk Profiles (2007) and reference was made to expected land use impacts from more frequent and intense cyclone events. There is an opportunity under this programme to consider the more detailed and updated climate change projections now available for Samoa. The Strategy which has as its central focus a theme of “resilience”, directs coastal adaptation to focus upon activities which will have a positive effect upon community resilience. It sets out a range of adaptation actions with a strong preference for “soft” actions such as managed retreat over “hard” engineered solutions such as seawalls. The CIM Strategy has been endorsed by Cabinet as official Government policy with respect to coastal management.
|  |  | Countries | Project Type: |  | GEF Focal Area: | GEF 4 Focal Areas | GEF 2 / 3 Operational Programme: | Overall Rating of the project in the evaluation by the project evaluator: | GEF-4 Focal Area Strategic Program: | GEF-3 Focal Area Strategic Program:
| Database Number: | PIMS No. 4667 | Afghanistan | FP | Yes | Biodiversity | 1 | 1 | U | BD-SP1-PA Financing | 1: Arid & semi-arid ecosystems
Implementing Entity (IE) [name]: |  | UNDP | Albania | MSP | No | Climate Change Adaptation | 2 | 2 | S | BD-SP2-Marine PA | 2: Coastal, marine & freshwater ecosystems
| Type of IE: | MIE | Algeria | EA |  | Climate Change Mitigation | 3 | 3 | MU | BD-SP3-PA Networks | 3: Forest ecosystems
| Country(ies): | Samoa | Angola |  |  | International Waters | 5 | 5 | Good | BD-SP5-Markets | 13: Conservation and Sustainable Use of Biological Diversity Important to Agriculture
Relevant Geographic Points (i.e. cities, villages, bodies of water): |  |  | Argentina |  |  | Multiple Focal Area |  |  |  | BD-SP7-Invasive Alien Species(IAS) | 6: Promoting the adoption of renewable energy by removing barriers and reducing implementation costs
[8 empty] | CC-SP2- Industrial EE | 8: Waterbody based operational program
| Project Milestones | [6 empty] | CC-SP3-RE,CC-SP4-Biomass | 9: Integrated Land and Water multiple focal area
| Milestone |  | Bahamas | [6 empty] | CC-SP5-Transport | 10: Contaminants based operational program
AFB Approval Date: |  | 2012-02-01
IE-AFB Agreement Signature Date: |  | 2012-04-01 | [6 empty] | CC-SP6-LULUCF | 12: Integrated Ecosystem Management
Start of Project/Programme: |  | 2013-01-28 | [6 empty] | Cross cutting capacity building | 14: Persistent Organic Pollutants
Mid-term Review Date (if planned):
Terminal Evaluation Date:
|  | List documents/ reports/ brochures / articles that have been prepared about the project. | Cyprus
|  | Programme Reports: Inception Workshop Report, Quarterly Progress Reports, AF/PPCR Joint Programme Steering Committee meeting (3 March 2014) minutes TORs for Programme Institutional Arrangement (AF/PPCR) - Technical Advisory Group, National Steering Committee, Joint Programme Management Unit (Programme Manager, Financial Management Specialist, Procurement Specialist, Environmental and Social Safeguards Specialist, Monitoring and Evaluation Specialist), Technical Advisor, Project Assistant (AF Specific), Technical Support Team (Community Liaison Officer, GIS Specialist, Coastal Morphology Specialist, Civil Engineer, Technical Planner) Technical Reports/Documents - Methodological Report on the review and Implementation of the Coastal Infrastructure Management (CIM) Plans, Preliminary Review of Coastal Protection Measures, Matrix of preliminary costing and prioritization of CIM Plan actions. Light Detection and Ranging (LiDAR) Software Training - PACCSAP | Czech Republic
List the Website address (URL) of project. |  |  | Democratic People's Republic of Korea
|  | www.undp-alm.org/projects/af-samoa | Democratic Republic of the Congo
Denmark
| Project contacts: |  | Djibouti
National Project Manager/Coordinator |  |  | Dominica
| Name: | MNRE (PUMA) - Kirisimasi Seumanutafa | Dominican Republic
| Email: | kirisimasi.seumanutafa@mnre.gov.ws | Ecuador
| Date: | 2015-03-30 | Egypt
| Government DA |  | El Salvador
| Name: | Mr. Aiono Mose Pouvi, Chief Executive Officer, Ministry of Foreign Affairs and Trade | Equatoral Guinea
| Email: |  | Eritrea
| Date: | 2015-03-30 | Estonia
| Implementing Entity |  | Ethiopia
| Name: | UNDP, Reis Lopez Rello | Fiji
| Email: | reis.lopez.rello@undp.org | Finland
| Date: | 2015-03-30 | France
| Executing Agency |  | Gambia
| Name: | Pou Onesemo, Assistant Chief Executive Officer, Planning and Urban Management Agency. | Georgia
| Email: | pou.onesemo@mnre.gov.ws | Germany
| Date: | 2015-03-30 | Ghana
| Executing Agency |  | Greece
| Name: | Suluimalo Amataga Penaia, Chief Executive Officer, Ministry of Natural Resources & Environment | Grenada
| Email: | amataga.penaia@mnre.gov.ws | Guatemala
| Date: | 2015-03-23 | Guinea
| Executing Agency |  | Guinea Bissau
| Name: |  | Guyana
| Email: |  | Haiti
| Date: |  | Honduras
Hungary
Iceland
India
Indonesia
Iran (Islamic Republic of)
Iraq
Ireland
Israel
Italy
Jamaica
Japan
Jordan
Kazakhstan
Kenya
Kiribati
Kuwait
Kyrgyzstan
Lao People’s Democratic Republic
Latvia
Lebanon
Lesotho
Liberia
Libyan Arab Jamahiriya
Liechtenstein
Lithuania
Luxembourg
Madagascar
Malawi
Malaysia
Maldives
Mali
Malta
Marshall Islands
Mauritania
Mauritius
Mexico
Micronesia, Federated States of
Monaco
Mongolia
Montenegro
Morocco
Mozambique
Myanmar
Namibia
Nauru
Nepal
Netherlands
New Zealand
Nicaragua
Niger
Nigeria
Norway
Oman
Pakistan
Palau
Panama
Papua New Guinea
Paraguay
Peru
Philippines
Poland
Portugal
Qatar
Republic of Korea
Republic of Moldova
Romania
Russian Federation
Rwanda
Saint Kitts and Nevis
Saint Lucia
Saint Vincent and the Grenadines
Samoa
San Marino
Sao Tome and Principe
Saudi Arabia
Senegal
Serbia
Seychelles
Sierra Leone
Singapore
Slovakia
Slovenia
Solomon Islands
Somalia
South Africa
Spain
Sri Lanka
Sudan
Suriname
Swaziland
Sweden
Switzerland
Syrian Arab Republic
Tajikistan
Thailand
The former Yugoslav Republic of Macedonia
Timor-Leste
Togo
Tonga
Trinidad and Tobago
Tunisia
Turkey
Turkmenistan
Tuvalu
Uganda
Ukraine
United Arab Emirates
United Kingdom of Great Britain and Northern Ireland
United Republic of Tanzania
United States of America
Uruguay
Uzbekistan
Vanuatu
Venezuela, Bolivarian Republic of
Viet Nam
Yemen
Zambia
Zimbabwe

## FinancialData
Financial information: cumulative from project start to 31 January 2015
DISBURSEMENT OF AF GRANT FUNDS
How much of the total AF grant as noted in Project Document plus any project preparation grant has been spent to date?
Estimated cumulative total disbursement as of 31 January 2015 | 358966 |  |  | 4.4602
Add any comments on AF Grant Funds. (word limit=200) | The expenditure for the second year of the project has increased somewhat compared to first project year,due to site-specific activities based on recent information available. A comprehensive review of CIM Plans and the LiDAR survey are expected to take place in the current, 3rd project year. Key studies and information gathering (i.e) LiDAR Survey and Technical Assistance has been done to facilitate project activity execution. In addition, close collaboration with the World Bank Pilot Program fror Climate Resilience (PPCR) has been underway during 2014 to develop coordinated management arrangement for the two programs and to formulate a methodology to review CIM Plans. Some institutional challenges and delays relate in particular to the procurement of the LiDAR services and personnel for the PMU. |  |  | 8048250
EXPENDITURE DATA
List ouput and corresponding amount spent for the current reporting period | ITEM / ACTIVITY / ACTION | AMOUNT (USD)
| Outcome 1 - Community Engagement in coastal vulnerability assessment, adaptation planning and awareness | 79697.53
| Output 1.1. CIM Plans reviewed in 25 districts with climate induced disaster risk management fully integrated, adopting a Watershed and Ridge to Reef Management approach | 14450.95
Output 1.2.Village hazard zone relocation plans formulated in at least 15 villages in selected districts
| Output 1.3. Training delivered to 300 village leaders in 139 villages on review of CIM Plans and relocation planning process integrating climate risks. | 65246.58
| Outcome 2 - Integrated Community-Based Coastal Adaptation and Disaster Risk Management measures | 113636.31
| Output 2.1 Climate proofing measures implemented on coastal roads and related infrastructure in at least 10 districts and 40 villages | 678.35
| Output 2.2. Shoreline protection measures implemented in at least 10 districts and 40 villages. | 2010.62
| Output 2.3. Water supply enhanced to withstand climate change risks in least 5 districts and 15 villages. | 824.14
| Output 2.4. Flood protection measures are implemented in at least 5 districts and 15 villages. | 110123.2
| Outcome 3 - Institutional strengthening to support climate resilient coastal management policy frameworks | 31050.32
| Output 3.1 Revised national organisation and institutional structures for CIM Plans implementation. | 30239.27
| Output 3.2 Village hazard zone relocation handbook prepared to guide further relocation planning activities. | 811.05
Output 3.3 Regulatory procedures for physical works implementation revised with climate change risks integrated.
Output 3.4 Policymakers and technical officers in the relevant Ministries and Authorities are trained on climate risk assessment and planning processes for coastal adaptation.
Output 3.5 Adaptation lessons learned and best practices generated through the adaptation implementation and related policy processes are captured and disseminated nationally and globally
| Project Management | 68010.36
| Procurement of Project vehicle (new) | 42794.96
| Stationery and Other Office Supplies | 1321.49
| Office Furniture | 2159.15
| Procurement of IT Equipment | 6540.65
| Contractual Services - Individual | 15194.11
| Unrealized Gain/Loss | 2626.57
| TOTAL | 295021.09
PLANNED EXPENDITURE SCHEDULE
List outputs planned and corresponding projected cost for the upcoming reporting period | ITEM / ACTIVITY / ACTION | PROJECTED COST (USD) | Est. Completion Date
Outcome 1 - Strengthened awareness and ownership of coastal adaptation and climate risk reduction processes at community and national levels in 25 Districts and 139 villages
| Output 1.1. No. of Districts covered by reviewed and updated CIM Plans with climate change risks fully integrated | 236956.52 | 2016-01-28
| Output 1.2. No. of Districts with village hazard zone relocation plans completed | 17391.3 | 2016-01-28
| Output 1.3. No. of community representatives trained on coastal risk assessment and adaptation and numbers of individuals engaged in those sessions | 26086.96 | 2016-01-28
Outcome 2 - Integrated Community-Based Coastal Adaptation and Disaster Risk Management measures
| Output 2.1 Climate proofing measures implemented on coastal roads and related infrastructure in at least 10 districts and 40 villages | 1078260.87 | 2016-01-28
| Output 2.2. Shoreline protection measures implemented in at least 10 districts and 40 villages. | 1378260.87 | 2016-01-28
| Output 2.3. Water supply enhanced to withstand climate change risks in least 5 districts and 15 villages. | 284782.61 | 2016-01-28
| Output 2.4. Flood protection measures are implemented in at least 5 districts and 15 villages. | 664720 | 2016-01-28
Outcome 3 - Institutional strengthening to support climate resilient coastal management policy frameworks
| Output 3.1 Revised national organisation and institutional structures for CIM Plans implementation. | 34782.61 | 2016-01-28
| Output 3.2 Village hazard zone relocation handbook prepared to guide further relocation planning activities. | 17391.3 | 2016-01-28
Output 3.3 Regulatory procedures for physical works implementation revised with climate change risks integrated.
| Output 3.4 Policymakers and technical officers in the relevant Ministries and Authorities are trained on climate risk assessment and planning processes for coastal adaptation. | 2173.91
Output 3.5 Adaptation lessons learned and best practices generated through the adaptation implementation and related policy processes are captured and disseminated nationally and globally
Project Management
| Information and Database Management Officer | 10434.78 | 2016-01-28
| Community Liaison and Cultural Officer | 10434.78 | 2016-01-28
| Promotion and Awareness Officer | 13913.04 | 2016-01-28
| Administrative Assistant | 15217.39 | 2016-01-28
| Stationery Material | 2173.91
| Asset Branding | 2173.91
| Office Furniture/Equipments | 2173.91
| UNDP support services (for procurement, payments etc) | 2173.91
| Mid-term evaluation | 26956.52
| TOTAL | 3826459.1
ACTUAL CO-FINANCING (If the MTR or TE have not been undertaken this reporting period, DO NOT report on actual co-financing.)
How much of the total co-financing as committed in the Project Document has actually been realized?
Estimated cumulative actual co-financing as verified during Mid-term Review (MTR) or Terminal Evaluation (TE).
Add any comments on actual co-financing in particular any issues related to the realization of in-kind, grant, credits, loans, equity, non-grant instruments and other types of co-financing. (word limit=200)

## Risk Assesment
RISK ASSESMENT
IDENTIFIED RISKS
List all Risks identified in project preparation phase and what steps are being taken to mitigate them
Identified Risk | Current Status | Steps Taken to Mitigate Risk
As this programme is designed to be complementary to the PPCR programme, any delay in that would impact on achieving desired “whole of country” joint project outputs and outcomes and reduce scope to deliver programme as outlined in proposal | Medium | Status moved from high to medium during the reporting period. Actions taken: Despite continual delay in the recruitment of the joint Programme Management Unit, concensus to progress with key program activities warrants sound progress. The request for Expressions of Interest to carry out the CIM Plan Review for 41 Districts was issued on the 21st November 2014 with submissions due on the 10th December 2014. A total of 16 submissions were received and a shortlist of 10 firms. The ToR and the corressponding Request for Proposal is being finalized. As agreed, due to funding requirements, interested firms will submit seperate financial proposal for the 16 districts under PPCR and the 25 districts under AF. The Technical Advisory Group (TAG) which provides the vehicle for selected Government and NGOs to coordinate project progress met 5 times during this reporting period. The Senior technical Advisor procured under AF is providing management and technical support to the PPCR and the AF, while awaiting the finalization of the PMU contract which is now intended to be in place by February 2015.
Extreme climatic events and geophysical hazards damage or eradicate programme results, or cause major disturbances resulting in delays due to needed emergency and recovery processes | High | Status is high as we are still in the Tropical Cyclone season ending April 2015. Actions taken: Disaster Management Office is one of the stakeholders of the Technical Advisory Group given their national mandate on disaster management which is an important component of the project.
Poor collaboration between project partners | Medium | Status decreased to medium as greater understanding and coordination within the TAG is being realised. Actions taken: Joint activities with govenrment agencies that are within the scope of the project and identified in the agency annual workplan. For instances the Independent water scheme for Lona and Masina jointly coordinated by the project and the Ministry of Women; the 1.4 km Fusi Saoluafata access road betwen the project and the land Transport Authority; The Manase beach replenishment project between the Samoa Tourisms Authority as examples. Within the MNRE where the Project unit is being hosted, the project has met and discuss potential areas of collaboration with other projects.
Weak cooperation by villages in proposed districts. | Low | The inception meeting that invited village majors, women and yout rep for all 41 districts in Savaii and Upolu generated a lot of interest. A wider consultation program geared to gain committment and ownership of the program by communities will be developed as part of the CIM plan Review program.
Land disputes amongst village members adversely affecting village relocation land use planning. | Medium | Consultation with communities for the development of the Relocation Handbook to capture the necessary processes and procedures, ensure village ownership and minimize disputes
Limited human resources in Government ministries and agencies to contribute to the activities. | Medium | A TOR for the Technical Advisory Group has been developed and approved by all members identified for their involvement in the project. Advertisements for 3 Additional technical staff to support their functions in programme implementation has gone out. Additonal positions are for a GIS /Database specilist, Community Liaison Officer, Media and Awreness Officer. The consultant expert team will have tasks to strengthen also existing gov. Through joint projects with line ministries, they are engaged to provide the technical arm for the project ensuring required standards are met.
A series of unusually adverse climatic conditions damage adaptation measures being implemented, or weaken the interest of key stakeholders to addressing adaptation issues. | Low | Disaster Management Office has been drawn in as one of the key stakeholders of the project. They are a member of the Technical Advisory Group and have offered Disaster Risk Reduction options for the project activities and CIM Plan actions identified. The impacts of Cyclone Evan actually reinforced the interest of stakeholders in the project.
The techniques and technologies developed are not gender sensitive – i.e. they increase inequity between men and women or change the social roles of men and women in a way that reduces self reliance. | Low | The approach taken on board by the project team with engaging communities and stakeholders is to ensure the involvement of all men, women and youth especially in the community level. Initial workshops have identified a member of each of these groups to participate. Gender is also at the core of the Economy-wide Adaptation project proposal being finalized through extensive consultations (LDCF 13M), also supported by UNDP and highly relevant to the AF programme.
Stakeholders are not able to perceive reductions in vulnerability over the time-scale determined by programme duration; | Low | Too early to report anything conclusive on this point as activities that would reduce vulnerability to communities have not yet been fully implemented.
Stakeholders are not able to distinguish vulnerability to climate change from baseline weaknesses in land, coastal, and water resources management | Low | Too early to report anything conclusive on this point as activities that would reduce vulnerability to communities have not yet been fully implemented.
Critical Risks Affecting Progress (Not identified at project design)
Identify Risks with a 50% or > likelihood of affecting progress of project
Identified Risk | Current Status | Steps Taken to Mitigate Risk
Extreme climatic events and geophysical hazards damage or eradicate programme results, or cause major disturbances resulting in delays due to needed emergency and recovery processes | Medium | It is difficult for the project to mitigate this risk. Even with comprehensive disaster risk management strategies in place in Samoa, the consequences of a cylcone, which is an annual risk in Samoa, cannot be fully controlled or mitigated.
Risk Measures: Were there any risk mitigation measures employed during the current reporting period? If so, were risks reduced? If not, why were these risks not reduced?
Add any comments relevant to risk mitigation (word limit = 500)
The following measures were undertaken to reduce risk in the project implementation delay; 1) the recruitment of the Senior Technical Adviser has supported implementation of the AF project in absence of a PMU. He has supported the procurement of the LiDAR through the refinement of the specifications and the TOR. He has supported the TORs preparation for the Vaiala and Saleia works, the CIM Review Team, the CIM Inventory TA. 2) the existing project team coordinated with the Water Resources Divsion, the Land Transport Authority and the Independent Water Scheme Association to carry out some of the priority activities of the CIM Plans and the Vaisigano Flood Study as well as support the recruitment of the PMU. 3. An LOA was signed between UNDP and MNRE so that UNDP could support the project in the absence of a PMU with procurement.

## Rating
RATING ON IMPLEMENTATION PROGRESS
For rating definitions please see bottom of page.
| Progress on Key Milestones |  | Expected Progress |  | Progress to Date | Rating
Project Manager/Coordinator: | Outcome 1: Strengthened awareness and ownership of coastal adaptation and climate risk reduction processes at community and national levels in 25 Districts and 139 villages through gender-sensitive processes
| 1.1. CIM Plans reviewed in 25 districts with climate induced disaster risk management fully integrated, adopting a Watershed and Ridge to Reef Management approach |  | 1. Development of revised CIM Plan template 2. Review of flood protection requirements 3. Preparation of revised IAMP 1 districts CIM Plans |  | It has been agreed that the PPCR will support the review and implementation of the identified actions for 16 Districts while AF will provide for the remaining 25. Furthermore, a single firm will be procured with possibility to have two teams on the ground to run the review for PPCR and AF districts simultaneously. An Expressions of Interest was issued on the 21st November 2014 with submissions due on the 10th December 2014. A total of 16 submissions were received and a shortlist of 10 firms was made after the evaluation of submissions by a select panel of evaluators. Contract was signed in March 2015. In order to fast-track the CIM Plan review excercise, two consultants have been recruited for an initial update/inventory excercise that will result in an updated CIM Plan database on the status of measures carried out so far. | Marginally satisfactory
| 1.2. Village hazard zone relocation plans formulated at least 15 villages in selected districts |  | 1. Development of selection criteria 2. Village consultations 3. Preparation of Village Hazard Zone Relocation Plans – Group 1 – 5 villages |  | The recruitment of a resettlement specialist is underway, contract is likely to be signed in March2015. | Marginally satisfactory
| 1.3. Training delivered to 300 village leaders in 139 villages on review of CIM Plans and relocation planning process integrating climate risks. |  | 1. Preliminary Sui o le Nuu briefing – Year 1 |  | 2 Initial Workshops held in Upolu and Savaii in February and March 2014 involved approx. 250 village leaders from 25 districts - Sui o Nuu (village major), Sui Tamaitai o Nuu (Women Group Rep). Further training and awareness activities will be programmed to alligned with the CIM Plan Review. Opportunities to collaborate with other ongoing efforts on climate adaptation and disaster risk reduction is promoted. | Satisfactory
Outcome 2: Increased adaptive capacity of coastal communities to adapt to coastal hazards and risks induced by climate change in 25 Districts and 139 villages
| 2.1. Climate proofing measures implemented on coastal roads and related infrastructure in at least 10 districts and 40 villages |  | 1. Review of CIM Plans Project database to specify roading projects. 2. Procurement of design consultant. 3. Preparation of site-specific designs and cost estimates for selected projects. 4. Implementation Year 1 projects - 10 villages. |  | The CIM Plan Database will be updated upon completion of the CIM Plan Review. However, other works were progressed given priority in current CIM Plan and other related plans. For instance; 1.4km of access road for Fusi Saoluafata is schedule to start late April and to complete by June 2015. Field visit is scheduled for two other recipients i.e 1 for Savaii and 1 for Upolu; The implementation of works for the identified zones in the drainage program has commenced with the contract signing complete to provide for key vulnerable areas i.e Zone 5 (Matautu to Afiamalu) of 11.552 km at a contract price of ST 160,918.70 and zone 6 (Moataa to Laulii) of 16.784 km at a contract price of SAT 221,332.45. These interventions have been derived from the CIM Plan prioritization matrix, Post-disaster Risk Assessment that was done by LTA on national roads after the Cyclone in 2012 and on the Recovery Plan developed by the agency and the respective District/Village CIM Plan. It was agreed that future projects for districts will be based on the outcome of the CIM Plan Review | Marginally Satisfactorily
| 2.2. Shoreline protection measures implemented in at least 10 districts and 40 villages. |  | 1. Review of CIM Plans Project database to specify shoreline protection measures projects. 2. Procurement of design consultant. 3. Preparation of site-specific designs and cost estimates for selected projects. 4. Implementation Year 1 projects - 10 villages. |  | The Design phase of the Vaiala Seawall (370m) and Saleia Rock Wall (765m) has commenced, contract awarded to Tinai Gordon and Associates (TGA) for a total Contract Price of SAT$186,000.00. The contract includes a feasibility study to inform the design and to include the supervision of works for the duration of the construction period. It is anticipated that constructions commence by mid April 2015AF in collaboration with LDCF-Tourism project is resourcing a feasibility study and the implementation of reccomended solutions for the Manase, an important torusims site that has been subject to beach erosion at an alarming rate. The toal length on area affected is 170m. Tonkin and Taylor Firm, NZ, was contracted and has put forth various replenishment options. They are now engaged to provide a detail design in approaching beach replenishment and AF has identified a contribution of ST 400,000.00 towards implementation of agreed options. The Manase model will be revisited for other beach replenishment sites i.e Siumu and Tafatafa as identified in the CIM Plans. | Marginally Satisfactorily
| 2.3 Water supply enhanced in least 5 districts and 15 villages. |  | 1. Review of CIM Plans Project database to specify Water supply enhancement projects. 2. Procurement of design consultant. 3. Preparation of site-specific and cost estimates for selected projects. 4. Implementation Year 1 projects – 3villages. |  | The implementation of community water supply enhancement projects has commenced with the contract signing on the 26th November 2014 with the successful bidder, for the rehabilitation and upgrade of Independent Water Scheme in Ma’asina , Lona and Lele’a (LOT 1). Bluebird Construction Limited has been awarded the contract for a total Contract Price of SAT$833,023.82, inclusive of taxation. The construction works are expected to commence on the 15th February and is anticipated to be completed by the 23rd June 2015. Total Population that will benefit is 544 (based on 2011 Population). | Marginally Satisfactorily
| 2.4 Flood protection measures are implemented in at least 5 districts and 15 villages |  | 1. Review of CIM Plans Project database to identify candidate flood protection measures projects. 2. Procurement of design consultant. 3. Preparation of preliminary designs and cost estimates for selected projects. 4. Implementation Year 1 projects –3 villages. |  | A flood study for the Vaisigano Catchment was conducted in collaboration with the Water Resources Division of the Ministry and resourced under AF. The contract was awarded to Water Technology from Melbourne Australia at the contract price of ST 120,000.00. The contract was completed on the 7th of June 2015 with the submission of their Final Report. Findings will inform design of drainage and required culverts along the main roads and other vulnerable area that got flooded from the vaisigano river. | Marginally Satisfactorily
Outcome 3: Strengthened institutional capacity of government sectors to integrate climate and disaster risk and resilience into coastal management-related policy frameworks, processes and responses.
| 3.1. Revised national organization and institutional structures for CIM Plans implementation. |  | 1. Review current organizations and structures. 2. Develop revised arrangements and suggested method of implementation. 3. Prepare MOU’s for agreement between key partners. |  | Has been initiated through internal discussions and the Technical Advisory Group, analyzing existing planning frameworks. There is currently an institutional review of MNRE, in which PUMA is one of the divisions. The development and implementation of CIM Plans will be a critical activity in the process. | Marginally Unsatisfactory
| 3.2 Village relocation handbook prepared to guide further relocation planning activities. |  | 1. Preparation of draft Village Relocation Handbook. 2. Consultation with key stakeholders and Sui o le Nuu briefings. 3. Finalized Village Hazard Zone Relocation Handbook |  | Recruitment of a resettlement specialist is currently ongoing, contract expected to be awared in March 2015. | Marginally Satisfactorily
| 3.3 Regulatory procedures for physical works implementation revised with climate change risks integrated. |  | 1. Review of contracts and procurement procedures. 2. Preparation of revised procurement manual and design guidelines for adaptation works incorporating CCA and DRM components. |  | No progress in this period. | Unsatisfactory.
| 3.4 Policymakers and technical officers in the relevant Ministries and Authorities are trained on climate risk assessment and planning processes for coastal adaptation. |  | 1. Conduct introductory workshop and training needs analysis. 2. Develop training plan and materials. 3. Training Workshops – Year 1. |  | No progress in this period. | Unsatisfactory
| 3.5 Adaptation lessons learned and best practices generated through the adaptation implementation and related policy processes are captured and disseminated nationally and globally through appropriate mechanisms |  | 1. Develop programme communications strategy and plan. 2. Prepare and operationalize web site material. 3. Prepare and publish programme communications. 4. Prepare material for Environment Week – Year 1. |  | Website has been prepared through UNDP assistance, project information has been disseminated at Environment week | Marginally satisfactory
[5 empty] | Overall Rating | Marginally Satisfactory
Please Provide the Name and Contact information of person(s) responsible for completing the Rating section
| Name: | Su'a Pou Onesemo, ACEO PUMA (MNRE) - Assistant Project Director
| Email: | pou.onesemo@mnre.gov.ws
Please justify your rating. Outline the positive and negative progress made by the project since it started. Provide specific recommendations for next steps. . (word limit=500)
The project has been delayed significantly and this supports the marginal satisfactory rating it has been given. However, efforts to allign key common activities of PPCR and AF, shall outweigh any disadvantage, as greater organization and coordination has emerged promising greater benefits that is sustainable to all stakeholders. In expenditure terms, this is not realized but we feel this shall not at all be the measure of progress as targets are intended towards thend of the program and that real success are realized well after the life of the project. As discussed in the progress to date, we envisage a enhanced consolidated implementation and delivery in the next reporting period.
| Progress on Key Milestones |  | Expected Progress |  | Progress to Date | Rating
Implementing Agency | Outcome 1: Strengthened awareness and ownership of coastal adaptation and climate risk reduction processes at community and national levels in 25 Districts and 139 villages through gender-sensitive processes
| 1.1. CIM Plans reviewed in 25 districts with climate induced disaster risk management fully integrated, adopting a Watershed and Ridge to Reef Management approach |  | 1. Development of revised CIM Plan template 2. Review of flood protection requirements 3. Preparation of revised IAMP 1 districts CIM Plans |  | The work relating to the CIM plans has been delayed and not really starting until 2015. Flood protection studies have been done for the Vaisigano river, and these studies have already benefitted another project in Samoa, however other flood studies are delayed. | Marginally Unsatisfactory
| 1.2. Village hazard zone relocation plans formulated at least 15 villages in selected districts |  | 1. Development of selection criteria 2. Village consultations 3. Preparation of Village Hazard Zone Relocation Plans – Group 1 – 5 villages |  | This work has been delayed and will start in 2015. | Unsatisfactory
| 1.3. Training delivered to 300 village leaders in 139 villages on review of CIM Plans and relocation planning process integrating climate risks. |  | 1. Preliminary Sui o le Nuu briefing – Year 1 |  | Two workshops held at the beginning of 2014. The work should be accelerated in 2015. | Marginally satisfactory
Outcome 2: Increased adaptive capacity of coastal communities to adapt to coastal hazards and risks induced by climate change in 25 Districts and 139 villages
| 2.1. Climate proofing measures implemented on coastal roads and related infrastructure in at least 10 districts and 40 villages |  | 1. Review of CIM Plans Project database to specify roading projects. 2. Procurement of design consultant. 3. Preparation of site-specific designs and cost estimates for selected projects. 4. Implementation Year 1 projects - 10 villages. |  | The CIM Plan Database will be updated upon completion of the CIM Plan Review that will start in 2015. The Design phase of the Vaiala Seawall (370m) and Saleia Rock Wall (765m) has commenced. | Marginally satisfactory
| 2.2. Shoreline protection measures implemented in at least 10 districts and 40 villages. |  | 1. Review of CIM Plans Project database to specify shoreline protection measures projects. 2. Procurement of design consultant. 3. Preparation of site-specific designs and cost estimates for selected projects. 4. Implementation Year 1 projects - 10 villages. |  | As stated several places above, the CIM plan review is delayed. However, some site work has begun, such as the collaboration with the GFE LDCF Climate resilient tourism project, where initial studies have recommended adaptation solutions for the tourism site Manase in Savai (recommendations include beach replenishment). | Marginally unsatisfactory
| 2.3 Water supply enhanced in least 5 districts and 15 villages. |  | 1. Review of CIM Plans Project database to specify Water supply enhancement projects. 2. Procurement of design consultant. 3. Preparation of site-specific and cost estimates for selected projects. 4. Implementation Year 1 projects – 3villages. |  | Contract for rehabilitation and upgrade of Independent Water Scheme in Ma’asina , Lona and Lele’a was signed in end 2014. Expected completion June 2015. | Marginally satisfactory
| 2.4 Flood protection measures are implemented in at least 5 districts and 15 villages |  | 1. Review of CIM Plans Project database to identify candidate flood protection measures projects. 2. Procurement of design consultant. 3. Preparation of preliminary designs and cost estimates for selected projects. 4. Implementation Year 1 projects –3 villages. |  | Flood studies for the central river in the capital Apia has been undertaken. | Marginally satisfactory
Outcome 3: Strengthened institutional capacity of government sectors to integrate climate and disaster risk and resilience into coastal management-related policy frameworks, processes and responses.
| 3.1. Revised national organization and institutional structures for CIM Plans implementation. |  | 1. Review current organizations and structures. 2. Develop revised arrangements and suggested method of implementation. 3. Prepare MOU’s for agreement between key partners. |  | No progress | Unsatisfactory
| 3.2 Village relocation handbook prepared to guide further relocation planning activities. |  | 1. Preparation of draft Village Relocation Handbook. 2. Consultation with key stakeholders and Sui o le Nuu briefings. 3. Finalized Village Hazard Zone Relocation Handbook |  | No progress | Unsatisfactory
| 3.3 Regulatory procedures for physical works implementation revised with climate change risks integrated. |  | 1. Review of contracts and procurement procedures. 2. Preparation of revised procurement manual and design guidelines for adaptation works incorporating CCA and DRM components. |  | No progress | Unsatisfactory
| 3.4 Policymakers and technical officers in the relevant Ministries and Authorities are trained on climate risk assessment and planning processes for coastal adaptation. |  | 1. Conduct introductory workshop and training needs analysis. 2. Develop training plan and materials. 3. Training Workshops – Year 1. |  | No progress | Unsatisfactory
| 3.5 Adaptation lessons learned and best practices generated through the adaptation implementation and related policy processes are captured and disseminated nationally and globally through appropriate mechanisms |  | 1. Develop programme communications strategy and plan. 2. Prepare and operationalize web site material. 3. Prepare and publish programme communications. 4. Prepare material for Environment Week – Year 1. |  | Website has been prepared through UNDP assistance, project information has been disseminated at Environment week, and at village leader's workshops. | Unsatisfactory
Unsatisfactory
Please Provide the Name and Contact information of person(s) responsible for completing the Rating section
| Name: | Mina Weydahl, Reis Lopez Rello
| Email: | mina.weydahl@undp.org; reis.lopez.rello@undp.org gabor.vereczi@undp.org
| Progress on Key Milestones |  | Expected Progress |  | Progress to Date | Rating
Other
Overall Rating
Please Provide the Name and Contact information of person(s) responsible for completing the Rating section
| Name: | Mina Weydahl
| Email: | mina.weydahl@undp.org
| Please justify your rating and address the following points: 1. Indicate trends, both positive and negative, in achievement of outcomes as per the project indicators. 2. Detail critical risks that have affected progress. 3. Outline response to MTR undertaken this reporting period. 4. Outline action plan to address projects with a rating of HU, U or MU. Please keep your input to 1200 words |  | The project has struggled since the inception, largely due to the challenges relating to joint project management with the World Bank PPCR project, and other delays in recruitment. Progress in 2014 has not been satisfactory until the end of the year, when several tenders and works as per project document was finally put out for bidding. It is the recommendation of UNDP that the project should urgently hire its own project manager, as one project unit for the two large projects (PPCR and AF) is not sufficient. The implementing partner (Ministry of Natural Resources and Environment) alo struggles a lot with very long processes for procurement and recruitment, which is known to UNDP through many other projects we implement. A Letter of Agreeent was signed with UNDP at the end of 2014, allowing UNDP to procure and hire directly where processes are very delayed with IP. This has resulted in the recruitement of 2 consultants that will undertake the CIM plan review (start mid March 2015) and the recruitment of a relocation specialist.
Rating Definitions
|  |  | Highly Satisfactory (HS) | Project actions/activities planned for current reporting period are progressing on track or exceeding expectations to achieve all major outcomes/outputs for given reporting period, without major shortcomings. The project can be presented as “good practice”.
|  |  | Satisfactory (S) | Project actions/activities planned for current reporting period are progressing on track to achieve most of its major outcomes/outputs with only minor shortcomings.
|  |  | Marginally Satisfactory (MS) | Project actions/activities planned for current reporting period are progressing on track to achieve most major relevant outcomes/outputs, but with either significant shortcomings or modest overall relevance.
|  |  | Marginally Unsatisfactory (MU) | Project actions/activities planned for current reporting period are not progressing on track to achieve major outcomes/outputs with major shortcomings or is expected to achieve only some of its major outcomes/outputs.
|  |  | Unsatisfactory (U) | Project actions/activities planned for current reporting period are not progressing on track to achieve most of its major outcomes/outputs.
|  |  | Highly Unsatisfactory (U) | Project actions/activities planned for current reporting period are not on track and shows that it is failing to achieve, and is not expected to achieve, any of its outcomes/outputs.

## Project Indicators
PROJECT Indicators
Please provide all indicators being tracked for the project as outlined in the project document
Type of Indicator (indicators towards Objectives, Outcomes, etc…)
Type of Indicator | Indicator | Baseline | Progress since inception | Target for Project End
Objective: Strengthened ability of coastal communities to make informed decisions about climate-change induced hazards and undertake concrete adaptation actions | Number of risk-exposed coastal communities protected through coastal adaptation measures based on climate-sensitive Coastal Infrastructure Management Plans (CIMP) | In the lack of systematic implementation of CIM Plans, the target villages and districts are highly exposed to climate-induced hazards | Leaders from all target villages and districts were involved in initial workshops held in Upolu and Savaii in February and March 2014. Three villages are engaged in a set of initial site-specific interventions initiated under Outcome 2. | By the end of the programme 139 villages in 25 districts are protected from climate-induced risks as a result of coastal adaptation measures implemented guided by revised CIM Plans
Outcome 1: Strengthened awareness and ownership of coastal adaptation and climate risk reduction processes at community and national levels in 25 Districts and 139 villages through gender-sensitive processes | No. of Districts covered by reviewed and updated CIM Plans with climate change risks fully integrated | The 6 CIM Plans prepared under IAMP1 have no DRM component. The 19 CIM Plans prepared under SIAM2 require review. | 0 districts completed so far. A set of initial site-specific interventions has been defined based on CIM Plan info and more recent assessments and consultations, covering a total of four districts. | By the end of year one at least 8, year two 18 and by the completion of the programme at least 25 districts will have their CIM Plans reviewed and updated with climate change risks fully integrated, through balanced involvement of man, women and youth population
| No. of Districts with village hazard zone relocation plans completed | There are currently no village relocation plans available to guide relocation activities for households to move out from coastal hazard zones. | No relocation planshave been prepared yet. | By the end of year one 5, year two 10 and by the completion of the programme at least 15 districts will have at least one village hazard zone relocation plan completed through balanced involvement of man, women and youth population. Trainees to disperse this knowledge to wider community for greater awareness
| No. of community representatives trained on coastal risk assessment and adaptation and numbers of individuals engaged in those sessions | Currently there has been no training for village leaders in coastal adaptation and climate risk reduction processes including village relocation planning. | 2 Initial Workshops held in Upolu and Savaii in February and March 2014 involved approx. 250 village leaders from 25 districts - Sui o Nuu (village major), Sui Tamaitai o Nuu (Women Group Rep). Three communities/villages have been involved in consultations for set of initial site-specific interventions initiated under Outcome 2. | By the end of the project at least 300 village representatives (including matais, women and youth groups) trained (year 1- 50, year 2- 100, year 3-200), involving traditional leaders, women and youth group representatives
Outcome 2: Increased adaptive capacity of coastal communities to adapt to coastal hazards and risks induced by climate change in 25 Districts and 139 villages | Km of coastal roads and related infrastructure improved to withstand climate change and variability-induced stress | There has been road reconstructions and upgrading undertaken in response to past hazards, such as the 2009 tsunami, but without integrating systematically climate change related risks in the process | No road reconstrucions or upgradings have taken place to date. | By the end of the programme at least 80km of coastal roads and related infrastructure is improved to withstand climate change and variability-induced stress
| Km of coastline with climate resilient shoreline and flood protection measures introduced, including vegetation planting along the coast and riparian streams and beach replenishment | There are only a few villages, where shoreline adaptation measures have been introduced through the PACC and CBDAMPIC projects, but only in a pilot fashion | Contracting for detail design of beach replenishment the Manaese area in Savaii is underway. | By the completion of the programme climate resilient shoreline and flood protection measures are introduced in at least 140km coastline and riparian streams, including vegetation planting in at least 60 km coast and 50 km of riparian streams, and beach replenishment techniques applied in at least 2 sites and 10 Km coastline
| N. of population and communities accessing improved water sector services and infrastructure to manage impacts on water supply induced by climate change and variability | The target villages lack robust water supply system to withstand climate-induced impacts in water supply | No villages have yet benefitted from improved water supply, however contract was signed on the 26th November 2014 for the rehabilitation and upgrade of Independent Water Scheme in Ma’asina , Lona and Lele’a (LOT 1). Bluebird Construction Limited has been awarded the contract for a total Contract Price of SAT$833,023.82, inclusive of taxation. The construction works is anticipated to be completed by the 23rd June 2015. | By the end of the programme at least 9,000 inhabitants in 15 villages have their water supply and associated infrastructure improved (in compliance with the Ministry of Health standards) to manage climate-induced impacts on water supply
| Perception of coastal communities on changes in climate-induced risks as a result of interventions | Baseline to be set at the beginning of the project | No progress | By the end of the project at least 80% of the coastal communities involved perceive risk reduction to climate-induced hazards
| Number of watersheds with integrated flood risk management measures implemented | Improved drainage and reduced flooding by the end of programme. | A flood study for the Vaisigano Catchment in Apia has been conducted. | Integrated flood-risk management plans/measures implemented in at least 10 watersheds/ 80 Km of waterways, involving at least 15 of villages.
Outcome 3: Strengthened institutional capacity of government sectors to integrate climate and disaster risk and resilience into coastal management-related policy frameworks, processes and responses | Revised national organization and institutional structures to implement CIM Plans | There is currently no organization specifically identified to co-ordinate the implementation of CIM Plan recommended works at the village and district level. | No instiutional structure in place to date. | A revised CIM Plan management institutional structure is set up by end of year one of the project
| A blueprint established and tested for Village relocation processes | There are currently no guidelines or procedures in place as to how to undertake village relocations in Samoa. | There are currenlty no guidelines developed. | A completed and operationally tested village relocation handbook is developed by the end of the project to guide future relocation planning exercises
| Improved regulatory procedures for physical works implementation with climate change and disaster risk considerations incorporated. | Current regulatory procedures for physical works are incomplete and do not have consistent references to either climate change or disaster risk considerations. | Revision of regulatory procedures not yet started. | Revised regulatory procedures for CIM Plan works is prepared by the end of year 3 of the programme
| Number of policy makers and technical officers trained on climate risk assessment and planning processes for coastal adaptation. | Policymakers and technical officers have low to moderate levels of understanding of climate risk assessment and planning processes for coastal adaptation. | No training for policy makers have yet taken place. | By the end of the programme at least 100 policymakers and technical officers exhibit improved levels of understanding of climate risk assessment and planning processes for coastal adaptation.
| Number of knowledge management products and South-South exchange events carried out | Absence of a communication strategy and lack of information management system to support adaptation of coastal villages and districts to climate change risks. | Website established. Project information has been disseminated at Environment week, and at village leader's workshops. | By the end of the programme a communication strategy is developed and information and lessons learnt are compiled and disseminated to local, regional and international stakeholders through at least 4 different mediums By the end of Year 1 the project web site is operational and not fewer than 5 project communications have been published. By the end of Year 2 not fewer than 10 further project communications have been published

## Lessons Learned
QUALITATIVE MEASURES and LESSONS LEARNED
Please complete the following section every reporting period
Implementation and Adaptive Management | Response
What implementation issues/lessons, either positive or negative, affected progress? | The main issue has been the coordination and alignment with the WB-funded PPCR process and activities. Being reminded of the importance of ensuring a standard approach to the review of the CIM Plan, 16 districts for PPCR and 25 under AF, was considered critical to minimize confusion when dealt with communities and villages. The PMU, to jointly manage the two projects, has taken more time than anticipated to be recruited. For the PPCR, much of the support for climate adaptation and disaster risk reduction activities, awaits the outcome of the CIM Plan Review. AF on the other hand, has progressed to implement some solutions identified through other national plans. However, the Government still feels the proposed CIM Plan Review will provide the latest information on prioritized adaptation and risk reduction options. This is a way forward and the timeframe of AF might have to change to align with PPCR.
Were there any delays in implementation? If so, include any causes of delays. What measures have been taken to reduce delays? | The project has experienced significant delays in implementation mainly due to challenges in aligning with the WB-funded PPCR project, in order to ensure a whole of a country integrated process, due to the following reasons: a) Setting up of joint project implementation structure and arrangements. This is the first time for the Government to create a single PMU for both projects and to also utilize the same steering committee. PPCR is executed by the Ministry of Finance (MoF) and the AF programme by Ministry of Natural Resources and Environment (MNRE) and its Planning and Urban Management Authority (PUMA). b) The departure of the PUMA ACEO caused a gap of leadership in the division that also stalled the project. With a new MNRE CEO and PUMA ACEO appointed in March 2014, leadership of the organization has been restored with renewed commitment on programme implementation. The project management unit is optimistic with regards to accelerated delivery in 2015, based on the following developments: a) A natinal senior technical advisor has been appointed for the project, with experience on climate change adaptation and CIM plan development. c) A new MNRE CEO and ACEO for PUMA was appointed in 2014 d) The Joint AF/PPCR Programme Steering Committee meeting met for the first time on 3 March 2014. The Technical Advisory Group (TAG) has met 5 times in 2014 facilitating the implementation of related project activities with respective agencies; DMO, WRD, PUMA, LTA, MWCSD, MWTI, CSSP. e) The government has signed an MoU with UNDP to progress procurement which considered slow. To date, UNDP has been asked to recruit the TA to undertake the CIM Plan Implementation Inventory. The project has also considered the possibility of using UNDP to recruit the Resettlement Specialist to prepare the relocation kandbook and pilot relocation plans. The ministry will monitor the viability of this MoU with UNDP.
Describe any changes undertaken to improve results on the ground or any changes made to project outputs (i.e. changes to project design) | The reallignment of the two projects is critical in achieving results that is nation-wide beneficial i.e benefit all 41 districts of the country by having an up to date CIM Plan. For AF, the schedule will be revised accordingly awaiting the CIM Plan Review program that will be agreed on with the winning contractor. Furthermore, as raised with UNDP, the targets for components 2 needs to be revised to reflect the budget allocated. PPCR has engaged a consultant to develop the Community Enagagement Plan that will guide community involvement in the project i.e 16 district under PPCR and 25 Districts under AF. The final Plan and the tool Kit shall be finalized mid February 2015.
How have gender considerations been taken into consideration during the reporting period? What have been the lessons learned as a consequence of inclusion of such considerations on project performance or impacts? | The envisaged Community Engagement Plan promotes greater recognition of gender and youths. In engaging the communities for project consultations, the typical avenue is through the village mayors and 'Sui tamaitai o Nuu' or female representatives of women's groups. There is also a recent addition to this group and that is the inclusion of a youth representative in all meetings pertaining to developments and other matters in the communities. The involvement of all the said representatives ensures that there is a contribution and representation of all these groups in all matters concerning their community. Consultation with communities is an important process for the CIM Plan Review and we forsee this in 2015, 2016, 2017.
Please complete the following section at mid-term and project completion
Lessons for Adaptation | Response
Climate Resilience Measures
What have been the lessons learned, both positive and negative, in implementing climate adaptation measures that would be relevant to the design and implementation of future projects/programmes for enhanced resilience to climate change?
What is the potential for the climate resilience measures undertaken by the project/programme to be replicated and scaled up both within and outside the project area?
Concrete Adaptation Interventions
What have been the lessons learned, both positive and negative, in implementing concrete adaptation interventions that would be relevant to the design and implementation of future projects/programmes implementing concrete adaptation interventions?
What is the potential for the concrete adaptation interventions undertaken by the project/programme to be replicated and scaled up both within and outside the project area?
Community/National Impact
What would you consider to be the most successful aspects for the target communities?
What measures are/have been put in place to ensure sustainability of the project/program results?
What measures are being/could have been put in place to improve project/program results?
Knowledge Management
How has existing information/data/knowledge been used to inform project development and implementation? What kinds of information/data/knowledge were used?
If learning objectives have been established, have they been met? Please describe.
Describe any difficulties there have been in accessing or retrieving existing information (data or knowledge) that is relevant to the project. Please provide suggestions for improving access to the relevant data.
Has the identification of learning objectives contributed to the outcomes of the project? In what ways have they contributed?

## Results Tracker
Results Tracker for Adaptation Fund (AF) Projects
Goal: Assist developing-country Parties to the Kyoto Protocol that are particularly vulnerable to the adverse effects of climate change in meeting the costs of concrete adaptation projects and programmes in order to implement climate-resilient measures. Impact: Increased resiliency at the community, national, and regional levels to climate variability and change.
Important: Please read the following Results Framework and Baseline Guidance (also posted on the Adaptation Fund website) before entering your data
Link: http://www.adaptation-fund.org/sites/default/files/Results%20Framework%20and%20Baseline%20Guidance%20final.pdf
Please select the relevant Fund level Outcome and Output indicators that allign with the project objectives and outcomes
OBJECTIVE 1
Fund Outcome | Please select from dropdown menu below | Fund Outcome Indicator | Please select from dropdown menu below | Target at CEO Endorsement (see Units in next sheet) | Baseline (see Units in next sheet) | Mid-term Results | Terminal Results
Outcome 1: Reduced exposure at national level to climate-related hazards and threats Outcome 2: Strengthened institutional capacity to reduce risks associated with climate-induced socioeconomic and environmental losses Outcome 3: Strengthened awareness and ownership of adaptation and climate risk reduction processes at local level Outcome 4: Increased adaptive capacity within relevant development and natural resource sectors Outcome 5: Increased ecosystem resilience in response to climate change and variability-induced stress Outcome 6: Diversified and strengthened livelihoods and sources of income for vulnerable people in targeted areas Outcome 7: Improved policies and regulations that promote and enforce resilience measures |  | 1. Relevant threat and hazard information generated and disseminated to stakeholders on a timely basis 2.1. No. and type of targeted institutions with increased capacity to minimize exposure to climate variability risks 2.2. Number of people with reduced risk to extreme weather events 3.1. Percentage of targeted population aware of predicted adverse impacts of climate change, and of appropriate responses 3.2. Modification in behavior of targeted population 4.1. Development sectors' services responsive to evolving needs from changing and variable climate 4.2. Physical infrastructure improved to withstand climate change and variability-induced stress 5. Ecosystem services and natural assets maintained or improved under climate change and variability-induced stress 6.1. Percentage of households and communities having more secure (increased) access to livelihood assets 6.2. Percentage of targeted population with sustained climate-resilient livelihoods 7. Climate change priorities are integrated into national development strategy |  | By the end of the programme 139 villages in 25 districts are protected from climate-induced risks as a result of coastal adaptation measures implemented guided by revised CIM Plans | In the lack of systematic implementation of CIM Plans, the target villages and districts are highly exposed to climate-induced hazards
Fund Output | Please select from dropdown menu below | Fund Output Indicator | Please select from dropdown menu below | Target at CEO Endorsement (see Units in next sheet) | Baseline (see Units in next sheet) | Mid-term Results | Terminal Results
Output 1: Risk and vulnerability assessments conducted and updated at a national level Output 2.1: Strengthened capacity of national and regional centres and networks to respond rapidly to extreme weather events Output 2.2: Targeted population groups covered by adequate risk reduction systems Output 3: Targeted population groups participating in adaptation and risk reduction awareness activities Output 4: Vulnerable physical, natural, and social assets strengthened in response to climate change impacts, including variability Output 5: Vulnerable physical, natural, and social assets strengthened in response to climate change impacts, including variability Output 6: Targeted individual and community livelihood strategies strengthened in relation to climate change impacts, including variability Output 7: Improved integration of climate-resilience strategies into country development plans |  | 1.1. No. and type of projects that conduct and update risk and vulnerability assessments 1.2. Development of early warning systems 2.1.1. No. of staff trained to respond to, and mitigate impacts of, climate-related events 2.1.2. Capacity of staff to respond to, and mitigate impacts of, climate-related events from targeted institutions increased 2.2.1. Percentage of population covered by adequate risk-reduction systems 2.2.2. No. of people affected by climate variability 3.1 No. and type of risk reduction actions or strategies introduced at local level 3.2 No. of news outlets in the local press and media that have covered the topic 4.1. No. and type of health or social infrastructure developed or modified to respond to new conditions resulting from climate variability and change (by type) 4. 2. No. of physical assets strengthened or constructed to withstand conditions resulting from climate variability and change (by asset types) 5. No. and type of natural resource assets created, maintained or improved to withstand conditions resulting from climate variability and change (by type of assets) 6.1. No. and type of adaptation assets (physical as well as knowledge) created in support of individualor community-livelihood strategies 6.2. Type of income sources for households generated under climate change scenario 7.1. No., type, and sector of policies introduced or adjusted to address climate change risks 7.2. No. or targeted development strategies with incorporated climate change priorities enforced | 3.1 | By the end of the programme at least 25 districts will have their CIM Plans reviewed and updated with climate change risks fully integrated, through balanced involvement of man, women and youth population | The 6 CIM Plans prepared under IAMP1 have no DRM component. The 19 CIM Plans prepared under SIAM2 require review.
OBJECTIVE 2
Fund Outcome | Please select from dropdown menu below | Fund Outcome Indicator |  | Target at CEO Endorsement | Baseline | Mid-term Results | Terminal Results
Outcome 1: Reduced exposure at national level to climate-related hazards and threats Outcome 2: Strengthened institutional capacity to reduce risks associated with climate-induced socioeconomic and environmental losses Outcome 3: Strengthened awareness and ownership of adaptation and climate risk reduction processes at local level Outcome 4: Increased adaptive capacity within relevant development and natural resource sectors Outcome 5: Increased ecosystem resilience in response to climate change and variability-induced stress Outcome 6: Diversified and strengthened livelihoods and sources of income for vulnerable people in targeted areas Outcome 7: Improved policies and regulations that promote and enforce resilience measures |  | 1. Relevant threat and hazard information generated and disseminated to stakeholders on a timely basis 2.1. No. and type of targeted institutions with increased capacity to minimize exposure to climate variability risks 2.2. Number of people with reduced risk to extreme weather events 3.1. Percentage of targeted population aware of predicted adverse impacts of climate change, and of appropriate responses 3.2. Modification in behavior of targeted population 4.1. Development sectors' services responsive to evolving needs from changing and variable climate 4.2. Physical infrastructure improved to withstand climate change and variability-induced stress 5. Ecosystem services and natural assets maintained or improved under climate change and variability-induced stress 6.1. Percentage of households and communities having more secure (increased) access to livelihood assets 6.2. Percentage of targeted population with sustained climate-resilient livelihoods 7. Climate change priorities are integrated into national development strategy | 3.1 | By the end of the project at least 300 village representatives (including matais, women and youth groups) trained (year 1- 50, year 2- 100, year 3-200), involving traditional leaders, women and youth group representatives | Currently there has been no training for village leaders in coastal adaptation and climate risk reduction processes including village relocation planning.
Fund Output | Please select from dropdown menu below | Fund Output Indicator | Please select from dropdown menu below | Target at CEO Endorsement | Baseline | Mid-term Results | Terminal Results
Output 1: Risk and vulnerability assessments conducted and updated at a national level Output 2.1: Strengthened capacity of national and regional centres and networks to respond rapidly to extreme weather events Output 2.2: Targeted population groups covered by adequate risk reduction systems Output 3: Targeted population groups participating in adaptation and risk reduction awareness activities Output 4: Vulnerable physical, natural, and social assets strengthened in response to climate change impacts, including variability Output 5: Vulnerable physical, natural, and social assets strengthened in response to climate change impacts, including variability Output 6: Targeted individual and community livelihood strategies strengthened in relation to climate change impacts, including variability Output 7: Improved integration of climate-resilience strategies into country development plans |  | 1.1. No. and type of projects that conduct and update risk and vulnerability assessments 1.2. Development of early warning systems 2.1.1. No. of staff trained to respond to, and mitigate impacts of, climate-related events 2.1.2. Capacity of staff to respond to, and mitigate impacts of, climate-related events from targeted institutions increased 2.2.1. Percentage of population covered by adequate risk-reduction systems 2.2.2. No. of people affected by climate variability 3.1 No. and type of risk reduction actions or strategies introduced at local level 3.2 No. of news outlets in the local press and media that have covered the topic 4.1. No. and type of health or social infrastructure developed or modified to respond to new conditions resulting from climate variability and change (by type) 4. 2. No. of physical assets strengthened or constructed to withstand conditions resulting from climate variability and change (by asset types) 5. No. and type of natural resource assets created, maintained or improved to withstand conditions resulting from climate variability and change (by type of assets) 6.1. No. and type of adaptation assets (physical as well as knowledge) created in support of individualor community-livelihood strategies 6.2. Type of income sources for households generated under climate change scenario 7.1. No., type, and sector of policies introduced or adjusted to address climate change risks 7.2. No. or targeted development strategies with incorporated climate change priorities enforced | 3.1 | By the end of the programme at least 25 districts will have their CIM Plans reviewed and updated with climate change risks fully integrated, through balanced involvement of man, women and youth population | The 6 CIM Plans prepared under IAMP1 have no DRM component. The 19 CIM Plans prepared under SIAM2 require review.
OBJECTIVE 3
Fund Outcome | Please select from dropdown menu below | Fund Outcome Indicator | Please select from dropdown menu below | Target at CEO Endorsement | Baseline | Mid-term Results | Terminal Results
Outcome 1: Reduced exposure at national level to climate-related hazards and threats Outcome 2: Strengthened institutional capacity to reduce risks associated with climate-induced socioeconomic and environmental losses Outcome 3: Strengthened awareness and ownership of adaptation and climate risk reduction processes at local level Outcome 4: Increased adaptive capacity within relevant development and natural resource sectors Outcome 5: Increased ecosystem resilience in response to climate change and variability-induced stress Outcome 6: Diversified and strengthened livelihoods and sources of income for vulnerable people in targeted areas Outcome 7: Improved policies and regulations that promote and enforce resilience measures |  | 1. Relevant threat and hazard information generated and disseminated to stakeholders on a timely basis 2.1. No. and type of targeted institutions with increased capacity to minimize exposure to climate variability risks 2.2. Number of people with reduced risk to extreme weather events 3.1. Percentage of targeted population aware of predicted adverse impacts of climate change, and of appropriate responses 3.2. Modification in behavior of targeted population 4.1. Development sectors' services responsive to evolving needs from changing and variable climate 4.2. Physical infrastructure improved to withstand climate change and variability-induced stress 5. Ecosystem services and natural assets maintained or improved under climate change and variability-induced stress 6.1. Percentage of households and communities having more secure (increased) access to livelihood assets 6.2. Percentage of targeted population with sustained climate-resilient livelihoods 7. Climate change priorities are integrated into national development strategy | 7 | Revised regulatory procedures for CIM Plan works is prepared by the end of year 3 of the programme | Current regulatory procedures for physical works are incomplete and do not have consistent references to either climate change or disaster risk considerations.
Fund Output | Please select from dropdown menu below | Fund Output Indicator | Please select from dropdown menu below | Target at CEO Endorsement | Baseline | Mid-term Results | Terminal Results
Output 1: Risk and vulnerability assessments conducted and updated at a national level Output 2.1: Strengthened capacity of national and regional centres and networks to respond rapidly to extreme weather events Output 2.2: Targeted population groups covered by adequate risk reduction systems Output 3: Targeted population groups participating in adaptation and risk reduction awareness activities Output 4: Vulnerable physical, natural, and social assets strengthened in response to climate change impacts, including variability Output 5: Vulnerable physical, natural, and social assets strengthened in response to climate change impacts, including variability Output 6: Targeted individual and community livelihood strategies strengthened in relation to climate change impacts, including variability Output 7: Improved integration of climate-resilience strategies into country development plans |  | 1.1. No. and type of projects that conduct and update risk and vulnerability assessments 1.2. Development of early warning systems 2.1.1. No. of staff trained to respond to, and mitigate impacts of, climate-related events 2.1.2. Capacity of staff to respond to, and mitigate impacts of, climate-related events from targeted institutions increased 2.2.1. Percentage of population covered by adequate risk-reduction systems 2.2.2. No. of people affected by climate variability 3.1 No. and type of risk reduction actions or strategies introduced at local level 3.2 No. of news outlets in the local press and media that have covered the topic 4.1. No. and type of health or social infrastructure developed or modified to respond to new conditions resulting from climate variability and change (by type) 4. 2. No. of physical assets strengthened or constructed to withstand conditions resulting from climate variability and change (by asset types) 5. No. and type of natural resource assets created, maintained or improved to withstand conditions resulting from climate variability and change (by type of assets) 6.1. No. and type of adaptation assets (physical as well as knowledge) created in support of individualor community-livelihood strategies 6.2. Type of income sources for households generated under climate change scenario 7.1. No., type, and sector of policies introduced or adjusted to address climate change risks 7.2. No. or targeted development strategies with incorporated climate change priorities enforced | 7.1 | A revised CIM Plan management institutional structure is set up by end of the project A completed and operationally tested village relocation handbook is developed by the end of the project to guide future relocation planning exercises | There is currently no organization specifically identified to co-ordinate the implementation of CIM Plan recommended works at the village and district level. There are currently no guidelines or procedures in place as to how to undertake village relocations in Samoa.
OBJECTIVE 4
Fund Outcome | Please select from dropdown menu below | Fund Outcome Indicator | Please select from dropdown menu below | Target at CEO Endorsement | Baseline | Mid-term Results | Terminal Results
Outcome 1: Reduced exposure at national level to climate-related hazards and threats Outcome 2: Strengthened institutional capacity to reduce risks associated with climate-induced socioeconomic and environmental losses Outcome 3: Strengthened awareness and ownership of adaptation and climate risk reduction processes at local level Outcome 4: Increased adaptive capacity within relevant development and natural resource sectors Outcome 5: Increased ecosystem resilience in response to climate change and variability-induced stress Outcome 6: Diversified and strengthened livelihoods and sources of income for vulnerable people in targeted areas Outcome 7: Improved policies and regulations that promote and enforce resilience measures |  | 1. Relevant threat and hazard information generated and disseminated to stakeholders on a timely basis 2.1. No. and type of targeted institutions with increased capacity to minimize exposure to climate variability risks 2.2. Number of people with reduced risk to extreme weather events 3.1. Percentage of targeted population aware of predicted adverse impacts of climate change, and of appropriate responses 3.2. Modification in behavior of targeted population 4.1. Development sectors' services responsive to evolving needs from changing and variable climate 4.2. Physical infrastructure improved to withstand climate change and variability-induced stress 5. Ecosystem services and natural assets maintained or improved under climate change and variability-induced stress 6.1. Percentage of households and communities having more secure (increased) access to livelihood assets 6.2. Percentage of targeted population with sustained climate-resilient livelihoods 7. Climate change priorities are integrated into national development strategy | 2.2 | By the end of the programme 139 villages in 25 districts are protected from climate-induced risks as a result of coastal adaptation measures implemented guided by revised CIM Plans | In the lack of systematic implementation of CIM Plans, the target villages and districts are highly exposed to climate-induced hazards
Fund Output | Please select from dropdown menu below | Fund Output Indicator | Please select from dropdown menu below | Target at CEO Endorsement | Baseline | Mid-term Results | Terminal Results
Output 1: Risk and vulnerability assessments conducted and updated at a national level Output 2.1: Strengthened capacity of national and regional centres and networks to respond rapidly to extreme weather events Output 2.2: Targeted population groups covered by adequate risk reduction systems Output 3: Targeted population groups participating in adaptation and risk reduction awareness activities Output 4: Vulnerable physical, natural, and social assets strengthened in response to climate change impacts, including variability Output 5: Vulnerable physical, natural, and social assets strengthened in response to climate change impacts, including variability Output 6: Targeted individual and community livelihood strategies strengthened in relation to climate change impacts, including variability Output 7: Improved integration of climate-resilience strategies into country development plans |  | 1.1. No. and type of projects that conduct and update risk and vulnerability assessments 1.2. Development of early warning systems 2.1.1. No. of staff trained to respond to, and mitigate impacts of, climate-related events 2.1.2. Capacity of staff to respond to, and mitigate impacts of, climate-related events from targeted institutions increased 2.2.1. Percentage of population covered by adequate risk-reduction systems 2.2.2. No. of people affected by climate variability 3.1 No. and type of risk reduction actions or strategies introduced at local level 3.2 No. of news outlets in the local press and media that have covered the topic 4.1. No. and type of health or social infrastructure developed or modified to respond to new conditions resulting from climate variability and change (by type) 4. 4.2. No. of physical assets strengthened or constructed to withstand conditions resulting from climate variability and change (by asset types) 5. No. and type of natural resource assets created, maintained or improved to withstand conditions resulting from climate variability and change (by type of assets) 6.1. No. and type of adaptation assets (physical as well as knowledge) created in support of individualor community-livelihood strategies 6.2. Type of income sources for households generated under climate change scenario 7.1. No., type, and sector of policies introduced or adjusted to address climate change risks 7.2. No. or targeted development strategies with incorporated climate change priorities enforced | 4.2 | By the end of the programme at least 80km of coastal roads and related infrastructure is improved to withstand climate change and variability-induced stress | There has been road reconstructions and upgrading undertaken in response to past hazards, such as the 2009 tsunami, but without integrating systematically climate change related risks in the process

## Units for Indicators
Fund Outcome Indicator Units
1. Generation of relevant data, Stakeholders, and Timeliness 2.1. Include both qualitative and quantitative measures of capacity level within targeted institutions 2.2. Number (men and women and other vulnerable groups) 3.1. Use scale from 1 to 5: 5: Fully aware 4: Mostly aware 3: Partially aware 2: Partially not aware 1: Aware of neither predicted adverse impacts of climate change nor of appropriate responses 3.2. Use scale from 1 to 5: 5: All 4: Almost all 3: Half 2: Some 1: None 4.1. Summarize in an overall scale (1-5): 5: Highly responsive (All defined elements ) 4: Mostly responsive (Most defined elements) 3: Moderately responsive (Some defined elements) 2: Partially responsive (Lacks most elements) 1: Non responsive (Lacks all elements ) 4.2. Summarize in an overall scale (1-5): 5: Fully improved 4: Mostly Improved 3: Moderately improved 2: Somewhat improved 1: Not improved 5. Depends on the targeted natural asset: Biological (species): measure through changes in population numbers (dynamics, structure, etc.) Land: measure changes in hectares. Baseline data will be necessary to estimate the change. Supporting indicators baseline and target (as well as contextual information) are needed such as the following: Farmers adopting recommended technologies, Ha. of land improved, Average deforestation rate Etc. Use scale from 1 to 5. 5: Very effective (All elements are present) 4: Effective (Most elements are present) 3: Moderately effective (Some elements are present) 2: Partially effective (Most elements are not present) 1: Ineffective (No elements are present) 6.1. Summarize in an overall scale (1-5): 5: Very high improvement 4: High improvement 3: Moderate improvement 2: Limited improvement 1: No improvement 6.2. Household income by source of livelihood in project area (USD) prior and post project intervention 7. Summarize in an overall scale (1-5). 5: All (Fully integrated) 4: Most 3: Some 2: Most not integrated 1: None
Fund Output Indicator Units
1.1. Number, sector(s) and level(s) of projects or interventions in separate fields of monitoring plan 1.2. Number 2.1.1. Number of staff (male/female) of targeted institutions: a. Obtain baseline information: total number of staff from targeted institutions b. Define target 2.1.2. Number of staff (male/female) of targeted institutions: a. Obtain baseline information: total number of staff from targeted institutions b. Define target: needs to be defined by project proponents 2.2.1. Quantitative: Percentage (includes women – and other vulnerable groups – and men). Qualitative: Adequacy: include direct analysis of major areas; adequacy/effectiveness of systems or analysis of perceptions of populations and institutions. 2.2.2. Number (broken down by gender and, if possible, by vulnerable groups defined in the area of intervention) of people 3.1. Number and type (in separate columns) at local level. 3.2. Number 4.1. Number and type 4. 2. Number and type (entered in separate columns) 5. Number of interventions by type of natural asset and intervention 6.1. Number and type (in separate columns of monitoring plan) 6.2. Income sources per household; description of income source and number of households. 7.1. Number/Sector 7.2. Number; Effectiveness (see previous indicator) through enforcement level.