## Overview
Project Performance Report (PPR)
| Project Title: | Project: "Building resilience to climate change and variability in vulnerable smallholders" (Project "GFCC")
| Project Summary: | The Project's overall objective is to contribute to building national capacity to adapt to climate change (CC) and variability by focusing on critical sectors of the country's economy. The specific objectives of this Project aim to: (i) reduce vulnerability and build resilience to climate change and variability for smallholders in the livestock sector located in the Landscape Units of the Basaltic Cuesta and East Hills eco-regions; (ii) strengthen local institutional networks in the selected Landscape Units and enhance the capacity of organizations to manage climate risks locally; (iii) manage the knowledge generated by developing mechanisms to better understand and monitor the impacts and variability of climate change, anticipate and assess negative events, take advantage of lessons learned, and identify and validate best practices and toolkits to adapt to climate change and variability.
|  |  | Countries | Project Type: |  | GEF Focal Area: | GEF 4 Focal Areas | GEF 2 / 3 Operational Programme: | Overall Rating of the project in the evaluation by the project evaluator: | GEF-4 Focal Area Strategic Program: | GEF-3 Focal Area Strategic Program:
| Database Number: | PROJECT AFB/NIE/Agri/2011/1 | Afghanistan | FP | Yes | Biodiversity | 1 | 1 | U | BD-SP1-PA Financing | 1: Arid & semi-arid ecosystems
| Implementing Entity (name): | Agencia Nacional de Investigación e Innovación (ANII) | Albania | MSP | No | Climate Change Adaptation | 2 | 2 | S | BD-SP2-Marine PA | 2: Coastal, marine & freshwater ecosystems
| Type of IE: | NIE | Algeria | EA |  | Climate Change Mitigation | 3 | 3 | MU | BD-SP3-PA Networks | 3: Forest ecosystems
| Country(ies): | Uruguay | Angola |  |  | International Waters | 5 | 5 | Good | BD-SP5-Markets | 13: Conservation and Sustainable Use of Biological Diversity Important to Agriculture
Relevant Geographic Points (i.e. cities, villages, bodies of water): |  | Basaltic Cuesta (Artigas, Salto, Tacuarembó and Rivera) and East Hills (Maldonado, Rocha and Lavalleja) | Argentina |  |  | Multiple Focal Area |  |  |  | BD-SP7-Invasive Alien Species(IAS) | 6: Promoting the adoption of renewable energy by removing barriers and reducing implementation costs
[8 empty] | CC-SP2- Industrial EE | 8: Waterbody based operational program
| Project Milestones | [6 empty] | CC-SP3-RE,CC-SP4-Biomass | 9: Integrated Land and Water multiple focal area
| Milestone |  | Bahamas | [6 empty] | CC-SP5-Transport | 10: Contaminants based operational program
| AFB Approval Date: | 2011-12-27 | [6 empty] | CC-SP6-LULUCF | 12: Integrated Ecosystem Management
| Start of Project/Programme: | 2012-10-22 | [6 empty] | Cross cutting capacity building | 14: Persistent Organic Pollutants
| Mid-term Review (if planned): | November 30, 2014 (to be rescheduled)
| Terminal Evaluation: | September 30, 2017
|  | List documents/ reports/ brochures / articles that have been prepared for the project. | Cyprus
|  | For the first call, the Project Operations Manual and the Field Manual were drafted, notwithstanding the terms of the open call for proposals to family farms engaged in livestock production and the dissemination material that was prepared. Regarding the 2nd Component, the Participative Diagnostics Document was developed. Additionally, the document related to the Initial Workshop was also developed. Agreement document with IPA for consultancy services. | Czech Republic
| List the Website address (URL) of the project. |  | Democratic People's Republic of Korea
Democratic Republic of the Congo
Denmark
| Project contacts: |  | Djibouti
| National Project Manager/Coordinator |  | Dominica
| Name: | Miguel Helou | Dominican Republic
| Email: | mhelou@anii.org.uy | Ecuador
| Date: | 2012-10-22 | Egypt
| Government DA |  | El Salvador
| Name: |  | Equatoral Guinea
| Email: |  | Eritrea
| Date: |  | Estonia
| Executing Agency |  | Ethiopia
| Name: | Dr. Alberto Castelar | Fiji
| Email: | acastelar@mgap.gub.uy | Finland
| Date: | 2012-10-22 | France
| Executing Agency |  | Gambia
| Name: | Ing Agr. Eduardo Maldini | Georgia
| Email: | emaldini@mgap.gub.uy | Germany
| Date: | 2012-10-22 | Ghana
| Executing Agency |  | Greece
| Name: |  | Grenada
| Email: |  | Guatemala
| Date: |  | Guinea
| Executing Agency |  | Guinea Bissau
| Name: |  | Guyana
| Email: |  | Haiti
| Date: |  | Honduras
Hungary
Iceland
India
Indonesia
Iran (Islamic Republic of)
Iraq
Ireland
Israel
Italy
Jamaica
Japan
Jordan
Kazakhstan
Kenya
Kiribati
Kuwait
Kyrgyzstan
Lao People’s Democratic Republic
Latvia
Lebanon
Lesotho
Liberia
Libyan Arab Jamahiriya
Liechtenstein
Lithuania
Luxembourg
Madagascar
Malawi
Malaysia
Maldives
Mali
Malta
Marshall Islands
Mauritania
Mauritius
Mexico
Micronesia, Federated States of
Monaco
Mongolia
Montenegro
Morocco
Mozambique
Myanmar
Namibia
Nauru
Nepal
Netherlands
New Zealand
Nicaragua
Niger
Nigeria
Norway
Oman
Pakistan
Palau
Panama
Papua New Guinea
Paraguay
Peru
Philippines
Poland
Portugal
Qatar
Republic of Korea
Republic of Moldova
Romania
Russian Federation
Rwanda
Saint Kitts and Nevis
Saint Lucia
Saint Vincent and the Grenadines
Samoa
San Marino
Sao Tome and Principe
Saudi Arabia
Senegal
Serbia
Seychelles
Sierra Leone
Singapore
Slovakia
Slovenia
Solomon Islands
Somalia
South Africa
Spain
Sri Lanka
Sudan
Suriname
Swaziland
Sweden
Switzerland
Syrian Arab Republic
Tajikistan
Thailand
The former Yugoslav Republic of Macedonia
Timor-Leste
Togo
Tonga
Trinidad and Tobago
Tunisia
Turkey
Turkmenistan
Tuvalu
Uganda
Ukraine
United Arab Emirates
United Kingdom of Great Britain and Northern Ireland
United Republic of Tanzania
United States of America
Uruguay
Uzbekistan
Vanuatu
Venezuela, Bolivarian Republic of
Viet Nam
Yemen
Zambia
Zimbabwe

## FinancialData
Financial information: cumulative from project start to [insert date]
DISBURSEMENT OF AF GRANT FUNDS
How much of the total AF grant (as noted in Project Document plus any project preparation grant) has been spent to date?
Estimated cumulative total disbursement as of October 2013 | 107233
Add any comments on AF Grant Funds (word limit=200). | Despite it was projected an execution of USD 2.197.431 for the calendar year 2013, 92% of the scheduled disbursements were planned to be disbursed on november and december. |  |  | 2021636.52
EXPENDITURE DATA
List item / activity / action and corresponding amount spent for the current reporting period | ITEM / ACTIVITY / ACTION | AMOUNT
| Component 1 | 141.34
| Component 2 | 40618.3542
| Component 3 | 14816.6423
| Component 4 | 21657.1914
| PFG Project Formulation Grant | 30000
PLANNED DISBURSEMENT SCHEDULE
List item / activity / action planned and corresponding projected cost for the upcoming reporting period | ITEM / ACTIVITY / ACTION | PROJECTED COST | Est. Completion Date
| Component 1 | 1876800 | 2014-10-01
| Component 2 | 194021.0141 | 2014-10-01
| Component 3 | 258029.1928 | 2014-10-01
| Component 4 | 73566.8398 | 2014-10-01
ACTUAL CO-FINANCING
How much of the total co-financing as committed in the Project Document has actually been realized? | 1.076%
If the MTR or TE have not been undertaken this reporting period, DO NOT report on actual co-financing.
Estimated cumulative actual co-financing as verified during Mid-term Review (MTR) or Terminal Evaluation (TE).
Add any comments on actual co-financing, in particular any issues related to the realization of in-kind, grant, credits, loans, equity, non-grant instruments and other types of co-financing (word limit=200).

## Risk Assessment
RISK ASSESSMENT
IDENTIFIED RISKS
List all Risks identified in project preparation phase and what steps are being taken to alleviate them (word limit = 200)
Identified Risk | Current Status | Steps Taken to Alleviate Risk
No demand for investments in adaptation. | Low | Dissemination activities were carried out in the area and there was good response to the first call for proposals.
Agricultural organizations are not interested in participating in local networks. | Low | Awareness initiatives were carried out in the area with farmers' organizations and the existing local network.
Project focus changes from adaptation to climate change and variability to production and productivity | Low | No increased risk was detected at the project design level. MGAP (Ministry of Livestock, Agriculture and Fisheries) policy reinforces the intention to keep the focus on adaptation and climate change, which is reflected in evaluation guidelines for the projects evaluated.
The smallholders targeted are unable to compete or sustain their livelihoods. | Low | Socio-economic reality keeps the identified risk LOW.
Delays in funds disbursement discourage farmers from participating in the project. | Low | The call for proposals is still in the evaluation stage, which is why no disbursements that could modify the established level of risk have been made yet.
Lack of transparency or political interference in allocation of resources. | Low | Execution is carried out through public calls, which ensures transparency. No institutional changes have been made since the Project was designed.
Lack of coordination between the various components. | Low | The work team is in the consolidation stage, building pertinent connections.
Critical Risks Affecting Progress (Not identified at project design)
Identify Risks with a 50% or < likelihood of affecting progress of project
Identified Risk | Current Status | Steps Taken to Alleviate Risk
Risk Measures: Were there any risk mitigation measures employed during the current reporting period? If so, were risks reduced? If not, why were these risks not reduced?
Add any comments relevant to risk elevation (word limit = 500)

## Rating
RATING ON IMPLEMENTATION PROGRESS
For rating definitions, please see bottom of page.
| Progress on Key Milestones | Expected Progress |  | Progress to Date | Rating
Project Manager/Coordinator:
Overall Rating
Please justify your rating. Outline the positive and negative progress made by the project since it started. Provide specific recommendations for next steps. (word limit=500)
| Progress on Key Milestones | Expected Progress |  | Progress to Date | Rating
Implementing Agency | Component 1 | According to operative plan at the end of 2013 up to 400 projects must be identified to receive financial support, in order to develop mitigation initiatives |  | 233 project proposals were received. The proposals are being validated and evaluated according to the protocol established in the Field Manual | Satisfactory
| Component 2 | Develompent of the participative diagnostic, kick of for strategic planning and development of several communication activities |  | Most o f the planned activities were executed or are under execution | Satisfactory
| Component 3 | Monitoring vulnerability and resilience to CC, systematization of information related to CC, systematization of research projects related to CC and development of research projects |  | Due to the public hiring procedures, there has been a delay in the hiring technical personnel. However, most of the planned activities were started | Marginally Satisfactory
| Component 4 | Execution of general administration, financial management and procurement, and overall reporting of the project |  | Most o f the planned activities were executed or are under execution | Satisfactory
|  |  |  | Overall Rating | Satisfactory
| Please justify your rating and address the following points: 1. Indicate trends, both positive and negative, in achievement of outcomes as per the project indicators. 2. Detail critical risks that have affected progress. 3. Outline response to MTR undertaken this reporting period. 4. Outline action plan to address projects with a rating of HU, U or MU. Please keep your input to 1200 words | After some initial delays in recruitment of human and technical resources and through the agreement with the IPLA, hopefully can accelerate project implementation. As mentioned, the main obstacle to the execution time of the project was the need to comply with state procurement procedures, which involve significant delays. From the agreement with the IPLA believe that the implementation speed can be improved significantly.
Rating Definitions
|  |  | Highly Satisfactory (HS) | Project actions/activities planned for current reporting period are progressing as planned or exceeding expectations to achieve all major objectives/outcomes for given reporting period, without major shortcomings. The project can be presented as “good practice”.
|  |  | Satisfactory (S) | Project actions/activities planned for current reporting period are progressing as planned to achieve most of its major objectives/outcomes with only minor shortcomings.
|  |  | Marginally Satisfactory (MS) | Project actions/activities planned for current reporting period are progressing as planned to achieve most major relevant objectives/outcomes, but with either significant shortcomings or modest overall relevance.
|  |  | Marginally Unsatisfactory (MU) | Project actions/activities planned for current reporting period are not progressing as planned to achieve major objectives/outcomes with major shortcomings or is expected to achieve only some of its major objectives/outcomes.
|  |  | Unsatisfactory (U) | Project actions/activities planned for current reporting period are not progressing as planned to achieve most of its major objectives/outcomes.
|  |  | Highly Unsatisfactory (U) | Project actions/activities planned for current reporting period are not on track and show that the project is failing to achieve, and is not expected to achieve, any of the objectives/outcomes.

## Project Indicators
PROJECT Indicators
Please provide all indicators being tracked for the project as outlined in the project document
Type of Indicator (indicators of Objectives, Outcomes, etc…)
Type of Indicator | Indicator | Baseline | Progress to date | Target | Progress to date | Target
| Farm plans implemented per Landscape Unit (LU). | 0 |  |  | 220 projects submitted, 0 projects approved. | 700 in Basaltic Cuesta, 640 in East Hills.
| Investments implemented per LU, per type. | 0 |  |  | 220 projects submitted, 0 projects approved. | 700 in Basaltic Cuesta, 640 in East Hills no distinction. US$7.260.000
| Source and availability of water for animal consumption. | Production systems with water shortage. |  |  | 0 | Not listed. Estimated: 60% of investment amount.
| Source and availability of forage in farms. | Degraded native grasslands, overgrazing, in many situations. Few forage banks. |  |  | 0 | Not listed. At least 80% of the projects propose actions aimed at increasing forage availability. 40 forage and grain banks.
| Green Index (NPP). | 3,300 kg DM/ha/yr in Basaltic Cuesta, 3,050 kg DM/ha/yr in East Hills. |  |  | 0 | Project will help improve NPP in farm holdings, measured in a sample of holdings.
| Stocking rate. | No data for Landscape Units. Estimated: 0.9 to 1 LU/ha. |  |  | 0 | Not listed. A decrease to 0.75-0.8 LU/ha is estimated in farm holdings participating in the project.
| Fertility rate per year. | Calving rate was 66%, according to DIEA [Department of Agricultural Statistics]. |  |  | 0 | Not listed. Estimated: 70% in farm holdings participating in the project.
| Estimated weight gain of animals per year, per category. | No data. Estimated at 90 kg. |  |  | 0 | No data. Estimated: 110 Kg in farm holdings participating in the project.
Annual statement on stock composition submitted to DICOSE [Directorate for Livestock Control].
| Networks have regular meetings as subgroups or independent MDRs [Rural Development Boards]. | 28 organizations and 7 MDR linked to the LU, without reference to climate change. |  |  | In the 7 MDRs and 10 organizations, monthly activities connected to the project are carried out. | It does not exist. 50% of organizations and 100% of MDRs discussed actions related to adaptation and climate change.
| Networks implement communications about CC, variability and adaptation. | 0 |  |  | Information related to calls for submission of projects is channeled through the MDRs and organizations. | It does not exist. The 7 MDRs participate in an adaptation to CC and variability information network.
| Networks submit proposals to the sponsoring MDRs, MGAP and SNE [National Emergency System]. | 0 |  |  | LU organizations are participating in the MDRs but have not submitted any proposals connected to CC. | The 7 MDRs receive and discuss proposals coming from the network linked to CC and variability.
| Networks seek and obtain funds from other programs to implement their development and CC agenda. | 0 |  |  | LU organizations lack funds for the implementation of development programs or adaptation to CC programs. | Networks submit proposals linked to development and adaptation to CC and variability to funding institutions.
| Young members and youth organizations participate in the network. | 0 |  |  | No youth organizations are participating in the MDR. | 15% of participants in MDR that are included in the networks are young members.
| Implementation of proposals and initiatives submitted by young members/youth organizations. | 0 |  |  | No proposals submitted by young members/youth organizations have been approved to date. | Young members submit at least 14 initiatives related to adaptation to CC and variability.
| Studies, regular reports on climate data and early warnings on adverse events are available at the LU level through the website. | Information available from INIA GRAS and Dirección Nacional de Meteorología [National Directorate of Meteorology]. |  |  | Active participation from UACC in building SNIA for generating agroclimatic information at the LU level. | UACC generates information about adaptation to CC and variability, available through the SNIA: agro-climatic monitoring with better spatial resolution and early warnings.
| Participation of key institutions and achievement of recognition thanks to national seminars as milestones for CC and variability, through participants’ evaluations. | 0 |  |  | No progress. Implementation starts in 2014. | 4 national seminars on topics related to adaptation to CC and variability.
| Published catalogue of best practices and toolkits for diagnostics, training, etc. | 0 |  |  | No progress. Implementation starts in 2014. | 1 catalogue of best practices for adaptation to CC and variability in the livestock sector.
| Positive peer and stakeholder reviews of funded studies and research projects. | 0 |  |  | No progress. Implementation starts in 2015. | Research projects, case studies and assessment studies funded by the project received positive reviews from peers.
| Increased awareness among the rural population about CC and variability, according to specific surveys. | 0 |  |  | Conducted awareness activities about the CC and variability problem. | Study on the level of awareness of CC and variability at the Landscape Unit level.

## AF Tracking Tool
Tracking Tool for Adaptation Fund (AF) Projects
Goal: Assist developing-country Parties to the Kyoto Protocol that are particularly vulnerable to the adverse effects of climate change in meeting the costs of concrete adaptation projects and programmes in order to implement climate-resilient measures. Impact: Increased resiliency at the community, national, and regional levels to climate variability and change.
Important: Please read the following Results Framework and Baseline Guidance (also posted on the Adaptation Fund website) before entering your data
Link: http://www.adaptation-fund.org/sites/default/files/Results%20Framework%20and%20Baseline%20Guidance%20final.pdf
Please select the relevant Fund level Outcome and Output indicators that align with the project objectives and outcomes
OBJECTIVE 1
Fund Outcome | Please select from dropdown menu below | Fund Outcome Indicator | Please select from dropdown menu below | Target at CEO Endorsement (see Units in next sheet) | Baseline (see Units in next sheet) | Mid-term Results | Terminal Results
1. Increased resilience of vulnerable smallholders through implementation of investments in adaptation. |  | Farm plans implemented per Landscape Unit (LU). | 3.1 |  | 1 |  | 5
|  | Investments implemented per LU, per type. | 3.1 |  | 1 |  | 5
|  | Source and availability of water for animal consumption. | 3.1 |  | 3 |  | 5
| 3 | Source and availability of forage in farms. | 3.1 |  | 2 |  | 5
|  | Green index. | 3.1 |  | 2 |  | 4
|  | Stocking rate. | 3.1 |  | 2 |  | 3
|  | Fertility rate per year. | 3.1 |  | 2 |  | 3
|  | Estimated weight gain of animals per year, per category. | 3.1 |  | 2 |  | 3
|  | Annual statement on stock composition submitted to DICOSE. | 3.1
Fund Output | Please select from dropdown menu below | Fund Output Indicator | Please select from dropdown menu below | Target at CEO Endorsement (see Units in next sheet) | Baseline (see Units in next sheet) | Mid-term Results | Terminal Results
Output 1: Risk and vulnerability assessments conducted and updated at a national level Output 2.1: Strengthened capacity of national and regional centres and networks to respond rapidly to extreme weather events Output 2.2: Targeted population groups covered by adequate risk reduction systems Output 3: Targeted population groups participating in adaptation and risk reduction awareness activities Output 4: Vulnerable physical, natural, and social assets strengthened in response to climate change impacts, including variability Output 5: Vulnerable physical, natural, and social assets strengthened in response to climate change impacts, including variability Output 6: Targeted individual and community livelihood strategies strengthened in relation to climate change impacts, including variability Output 7: Improved integration of climate-resilience strategies into country development plans |  | 1.1. No. and type of projects that conduct and update risk and vulnerability assessments 1.2. Development of early warning systems 2.1.1. No. of staff trained to respond to, and mitigate impacts of, climate-related events 2.1.2. Capacity of staff to respond to, and mitigate impacts of, climate-related events from targeted institutions increased 2.2.1. Percentage of population covered by adequate risk-reduction systems 2.2.2. No. of people affected by climate variability 3.1 No. and type of risk reduction actions or strategies introduced at local level 3.2 No. of news outlets in the local press and media that have covered the topic 4.1. No. and type of health or social infrastructure developed or modified to respond to new conditions resulting from climate variability and change (by type) 4. 2. No. of physical assets strengthened or constructed to withstand conditions resulting from climate variability and change (by asset types) 5. No. and type of natural resource assets created, maintained or improved to withstand conditions resulting from climate variability and change (by type of assets) 6.1. No. and type of adaptation assets (physical as well as knowledge) created in support of individualor community-livelihood strategies 6.2. Type of income sources for households generated under climate change scenario 7.1. No., type, and sector of policies introduced or adjusted to address climate change risks 7.2. No. or targeted development strategies with incorporated climate change priorities enforced
OBJECTIVE 2
Fund Outcome | Please select from dropdown menu below | Fund Outcome Indicator | Please select from dropdown menu below | Target at CEO Endorsement | Baseline | Mid-term Results | Terminal Results
There is a local institutional network that handles climatic risk at the LU level. It involves young members and also manages operational toolkits to respond to emergency situations, in close cooperation with MDRs (Rural Development Boards) and the SNE (National Emergency System). | 2 | Networks have regular meetings as subgroups or independent MDRs. | 2.1 |  | 28 Organizaciones y 7 MDR vinculadas a las UP, sin referencia al CC |  | El 50% de las Organizaciones y MDR de las UP participan y proponen acciones vinculadas a la Adaptación y CC
|  | Networks implement communications about CC, variability and adaptation. | 2.1 |  | Las Organizaciones y MDR de las UP no implementan comunicación sobre CC. |  | El 50% de las Organizaciones y 80% de las MDR de las UP viabilizan la comunicación sobre CC.
|  | Networks submit proposals to the sponsoring MDRs, MGAP and SNE. | 2.1 |  | Las Organizaciones existentes no presentan propuestas a las MDR, vinculadas al CC |  | La Red vinculada al Cambio Climático presenta propuestas ante las MDR, MGAP y SNE.
|  | Networks seek and obtain funds from other programs to implement their development and CC agenda. | 2.1 |  | Las Organizaciones y MDR no procuran financiamiento para temas vincualdos al CC |  | Las Organizaciones y las MDR procuran financiamiento para sus planes de adaptacicón y desarrollo.
|  | Young members and youth organizations participate in the network. | 2.2 |  | s/d |  | No existe. Estimamos que el 15% de los participantes son jóvenes.
|  | Implementation of proposals and initiatives submitted by young members/youth organizations. | 2.2 |  | 0 |  | 14
Fund Output | Please select from dropdown menu below | Fund Output Indicator | Please select from dropdown menu below | Target at CEO Endorsement | Baseline | Mid-term Results | Terminal Results
Output 1: Risk and vulnerability assessments conducted and updated at a national level Output 2.1: Strengthened capacity of national and regional centres and networks to respond rapidly to extreme weather events Output 2.2: Targeted population groups covered by adequate risk reduction systems Output 3: Targeted population groups participating in adaptation and risk reduction awareness activities Output 4: Vulnerable physical, natural, and social assets strengthened in response to climate change impacts, including variability Output 5: Vulnerable physical, natural, and social assets strengthened in response to climate change impacts, including variability Output 6: Targeted individual and community livelihood strategies strengthened in relation to climate change impacts, including variability Output 7: Improved integration of climate-resilience strategies into country development plans |  | 1.1. No. and type of projects that conduct and update risk and vulnerability assessments 1.2. Development of early warning systems 2.1.1. No. of staff trained to respond to, and mitigate impacts of, climate-related events 2.1.2. Capacity of staff to respond to, and mitigate impacts of, climate-related events from targeted institutions increased 2.2.1. Percentage of population covered by adequate risk-reduction systems 2.2.2. No. of people affected by climate variability 3.1 No. and type of risk reduction actions or strategies introduced at local level 3.2 No. of news outlets in the local press and media that have covered the topic 4.1. No. and type of health or social infrastructure developed or modified to respond to new conditions resulting from climate variability and change (by type) 4. 2. No. of physical assets strengthened or constructed to withstand conditions resulting from climate variability and change (by asset types) 5. No. and type of natural resource assets created, maintained or improved to withstand conditions resulting from climate variability and change (by type of assets) 6.1. No. and type of adaptation assets (physical as well as knowledge) created in support of individualor community-livelihood strategies 6.2. Type of income sources for households generated under climate change scenario 7.1. No., type, and sector of policies introduced or adjusted to address climate change risks 7.2. No. or targeted development strategies with incorporated climate change priorities enforced
OBJECTIVE 3
Fund Outcome | Please select from dropdown menu below | Fund Outcome Indicator | Please select from dropdown menu below | Target at CEO Endorsement | Baseline | Mid-term Results | Terminal Results
There is systematic control of CC and its impact on agriculture, as well as a catalogue of best practices, innovative toolkits and lessons learned from experiences carried out and supported by all stakeholders regarding adaptation to CC, with special emphasis on drought and hydric stress. | 7 | Studies, regular reports on climate data and early warnings on adverse events are available at the LU level through the website. | 7 |  | 2 |  | 4
|  | Participation of key institutions and achievement of recognition thanks to national seminars as milestones for CC and variability, through participants’ evaluations. | 7 |  | 2 |  | 4
|  | Published catalogue of best practices and toolkits for diagnostics, training, etc. | 7 |  | 2 |  | 4
|  | Positive peer and stakeholder reviews of funded studies and research projects. | 7 |  | 1 |  | 4
|  | Increased awareness among the rural population about CC and variability, according to specific surveys. | 7 |  | 2 |  | 3
Fund Output | Please select from dropdown menu below | Fund Output Indicator | Please select from dropdown menu below | Target at CEO Endorsement | Baseline | Mid-term Results | Terminal Results
Output 1: Risk and vulnerability assessments conducted and updated at a national level Output 2.1: Strengthened capacity of national and regional centres and networks to respond rapidly to extreme weather events Output 2.2: Targeted population groups covered by adequate risk reduction systems Output 3: Targeted population groups participating in adaptation and risk reduction awareness activities Output 4: Vulnerable physical, natural, and social assets strengthened in response to climate change impacts, including variability Output 5: Vulnerable physical, natural, and social assets strengthened in response to climate change impacts, including variability Output 6: Targeted individual and community livelihood strategies strengthened in relation to climate change impacts, including variability Output 7: Improved integration of climate-resilience strategies into country development plans |  | 1.1. No. and type of projects that conduct and update risk and vulnerability assessments 1.2. Development of early warning systems 2.1.1. No. of staff trained to respond to, and mitigate impacts of, climate-related events 2.1.2. Capacity of staff to respond to, and mitigate impacts of, climate-related events from targeted institutions increased 2.2.1. Percentage of population covered by adequate risk-reduction systems 2.2.2. No. of people affected by climate variability 3.1 No. and type of risk reduction actions or strategies introduced at local level 3.2 No. of news outlets in the local press and media that have covered the topic 4.1. No. and type of health or social infrastructure developed or modified to respond to new conditions resulting from climate variability and change (by type) 4. 2. No. of physical assets strengthened or constructed to withstand conditions resulting from climate variability and change (by asset types) 5. No. and type of natural resource assets created, maintained or improved to withstand conditions resulting from climate variability and change (by type of assets) 6.1. No. and type of adaptation assets (physical as well as knowledge) created in support of individualor community-livelihood strategies 6.2. Type of income sources for households generated under climate change scenario 7.1. No., type, and sector of policies introduced or adjusted to address climate change risks 7.2. No. or targeted development strategies with incorporated climate change priorities enforced
OBJECTIVE 4
Fund Outcome | Please select from dropdown menu below | Fund Outcome Indicator | Please select from dropdown menu below | Target at CEO Endorsement | Baseline | Mid-term Results | Terminal Results
Outcome 1: Reduced exposure at national level to climate-related hazards and threats Outcome 2: Strengthened institutional capacity to reduce risks associated with climate-induced socioeconomic and environmental losses Outcome 3: Strengthened awareness and ownership of adaptation and climate risk reduction processes at local level Outcome 4: Increased adaptive capacity within relevant development and natural resource sectors Outcome 5: Increased ecosystem resilience in response to climate change and variability-induced stress Outcome 6: Diversified and strengthened livelihoods and sources of income for vulnerable people in targeted areas Outcome 7: Improved policies and regulations that promote and enforce resilience measures |  | 1. Relevant threat and hazard information generated and disseminated to stakeholders on a timely basis 2.1. No. and type of targeted institutions with increased capacity to minimize exposure to climate variability risks 2.2. Number of people with reduced risk to extreme weather events 3.1. Percentage of targeted population aware of predicted adverse impacts of climate change, and of appropriate responses 3.2. Modification in behavior of targeted population 4.1. Development sectors' services responsive to evolving needs from changing and variable climate 4.2. Physical infrastructure improved to withstand climate change and variability-induced stress 5. Ecosystem services and natural assets maintained or improved under climate change and variability-induced stress 6.1. Percentage of households and communities having more secure (increased) access to livelihood assets 6.2. Percentage of targeted population with sustained climate-resilient livelihoods 7. Climate change priorities are integrated into national development strategy
Fund Output | Please select from dropdown menu below | Fund Output Indicator | Please select from dropdown menu below | Target at CEO Endorsement | Baseline | Mid-term Results | Terminal Results
Output 1: Risk and vulnerability assessments conducted and updated at a national level Output 2.1: Strengthened capacity of national and regional centres and networks to respond rapidly to extreme weather events Output 2.2: Targeted population groups covered by adequate risk reduction systems Output 3: Targeted population groups participating in adaptation and risk reduction awareness activities Output 4: Vulnerable physical, natural, and social assets strengthened in response to climate change impacts, including variability Output 5: Vulnerable physical, natural, and social assets strengthened in response to climate change impacts, including variability Output 6: Targeted individual and community livelihood strategies strengthened in relation to climate change impacts, including variability Output 7: Improved integration of climate-resilience strategies into country development plans |  | 1.1. No. and type of projects that conduct and update risk and vulnerability assessments 1.2. Development of early warning systems 2.1.1. No. of staff trained to respond to, and mitigate impacts of, climate-related events 2.1.2. Capacity of staff to respond to, and mitigate impacts of, climate-related events from targeted institutions increased 2.2.1. Percentage of population covered by adequate risk-reduction systems 2.2.2. No. of people affected by climate variability 3.1 No. and type of risk reduction actions or strategies introduced at local level 3.2 No. of news outlets in the local press and media that have covered the topic 4.1. No. and type of health or social infrastructure developed or modified to respond to new conditions resulting from climate variability and change (by type) 4. 2. No. of physical assets strengthened or constructed to withstand conditions resulting from climate variability and change (by asset types) 5. No. and type of natural resource assets created, maintained or improved to withstand conditions resulting from climate variability and change (by type of assets) 6.1. No. and type of adaptation assets (physical as well as knowledge) created in support of individualor community-livelihood strategies 6.2. Type of income sources for households generated under climate change scenario 7.1. No., type, and sector of policies introduced or adjusted to address climate change risks 7.2. No. or targeted development strategies with incorporated climate change priorities enforced

## Units for Indicators
Fund Outcome Indicator Units
1. Generation of relevant data, Stakeholders, and Timeliness 2.1. Include both qualitative and quantitative measures of capacity level within targeted institutions 2.2. Number (men and women and other vulnerable groups) 3.1. Use scale from 1 to 5: 5: Fully aware 4: Mostly aware 3: Partially aware 2: Partially not aware 1: Aware of neither predicted adverse impacts of climate change nor of appropriate responses 3.2. Use scale from 1 to 5: 5: All 4: Almost all 3: Half 2: Some 1: None 4.1. Summarize in an overall scale (1-5): 5: Highly responsive (All defined elements ) 4: Mostly responsive (Most defined elements) 3: Moderately responsive (Some defined elements) 2: Partially responsive (Lacks most elements) 1: Non responsive (Lacks all elements ) 4.2. Summarize in an overall scale (1-5): 5: Fully improved 4: Mostly Improved 3: Moderately improved 2: Somewhat improved 1: Not improved 5. Depends on the targeted natural asset: Biological (species): measure through changes in population numbers (dynamics, structure, etc.) Land: measure changes in hectares. Baseline data will be necessary to estimate the change. Supporting indicators baseline and target (as well as contextual information) are needed such as the following: Farmers adopting recommended technologies, Ha. of land improved, Average deforestation rate Etc. Use scale from 1 to 5. 5: Very effective (All elements are present) 4: Effective (Most elements are present) 3: Moderately effective (Some elements are present) 2: Partially effective (Most elements are not present) 1: Ineffective (No elements are present) 6.1. Summarize in an overall scale (1-5): 5: Very high improvement 4: High improvement 3: Moderate improvement 2: Limited improvement 1: No improvement 6.2. Household income by source of livelihood in project area (USD) prior and post project intervention 7. Summarize in an overall scale (1-5). 5: All (Fully integrated) 4: Most 3: Some 2: Most not integrated 1: None
Fund Output Indicator Units
1.1. Number, sector(s) and level(s) of projects or interventions in separate fields of monitoring plan 1.2. Number 2.1.1. Number of staff (male/female) of targeted institutions: a. Obtain baseline information: total number of staff from targeted institutions b. Define target 2.1.2. Number of staff (male/female) of targeted institutions: a. Obtain baseline information: total number of staff from targeted institutions b. Define target: needs to be defined by project proponents 2.2.1. Quantitative: Percentage (includes women – and other vulnerable groups – and men). Qualitative: Adequacy: include direct analysis of major areas; adequacy/effectiveness of systems or analysis of perceptions of populations and institutions. 2.2.2. Number (broken down by gender and, if possible, by vulnerable groups defined in the area of intervention) of people 3.1. Number and type (in separate columns) at local level. 3.2. Number 4.1. Number and type 4. 2. Number and type (entered in separate columns) 5. Number of interventions by type of natural asset and intervention 6.1. Number and type (in separate columns of monitoring plan) 6.2. Income sources per household; description of income source and number of households. 7.1. Number/Sector 7.2. Number; Effectiveness (see previous indicator) through enforcement level.

## Lessons Learned
QUALITATIVE MEASURES and LESSONS LEARNED
Please Complete the following section every reporting period
Implementation and Adaptive Management | Response
Describe any implementation issues/lessons affecting progress (positive and negative) | The process of hiring consultants took more time than planned, which delayed the execution of activities established in the Annual Plan of Operations for this year.
Were there any delays in implementation? If so, what are the measures taken to reduce delays? | An agreement was developed with the Instituto Plan Agropecuario in order to mitigate delays that followed the hiring of consultants; said agreement included several consultancies.
Describe any changes undertaken to improve results on the ground or any changes made to project outputs (i.e. changes to project design) | There were no changes to the Project’s design.
How have gender considerations been taken into consideration during the reporting period? | When designing the open call that was launched in July 2013, the plan included giving preferential consideration to projects submitted by women and young members.
Please Complete the following section at mid-term and project completion
Lessons for Adaptation | Response
Climate Resilient Measures
Please sescribe the Climate Resilient measures being undertaken by the project/programme.
Which of these masures has been most effective and why?
Which have been least effective and why?
Concrete Adaptation Interventions
Please desribe the concrete adaptation measures being undertaken by the project/programme
What are/were the most difficult aspects of implementing such measures?
What are/were the most successful aspects of the implementation of the interventions?
Community/National Impact
What would you consider to be the most successful aspects for the target communities?
What measures are/have been put in place to ensure sustainability of the project/programme results?
What measures are being/could have been put in place to improve project/programme results?
Knowledge Management
Describe what kind and how existing information/data/knowledge has been used to inform the development and the implementation of the project.
Describe any difficulties there have been in accessing or retrieving existing information (data or knowledge) that is relevant to the project. Please provide suggestions for improving access to the relevant data.
Have the Project Learning Objectives been met? Please describe.
Has the identification of learning objectives contributed to the outcomes of the project? In what/why have they contributed?

## AF Tracking Tool (2)
Tracking Tool for Adaptation Fund (AF) Projects
Goal: Assist developing-country Parties to the Kyoto Protocol that are particularly vulnerable to the adverse effects of climate change in meeting the costs of concrete adaptation projects and programmes in order to implement climate-resilient measures. Impact: Increased resiliency at the community, national, and regional levels to climate variability and change.
Important: Please read the following Results Framework and Baseline Guidance (also posted on the Adaptation Fund website) before entering your data
Link: http://www.adaptation-fund.org/sites/default/files/Results%20Framework%20and%20Baseline%20Guidance%20final.pdf
Please select the relevant Fund level Outcome and Output indicators that allign with the project objectives and outcomes
OBJECTIVE 1
Fund Outcome | Please select from dropdown menu below | Fund Outcome Indicator | Please select from dropdown menu below | Target at CEO Endorsement (see Units in next sheet) | Baseline (see Units in next sheet) | Mid-term Results | Terminal Results
Outcome 1: Reduced exposure at national level to climate-related hazards and threats Outcome 2: Strengthened institutional capacity to reduce risks associated with climate-induced socioeconomic and environmental losses Outcome 3: Strengthened awareness and ownership of adaptation and climate risk reduction processes at local level Outcome 4: Increased adaptive capacity within relevant development and natural resource sectors Outcome 5: Increased ecosystem resilience in response to climate change and variability-induced stress Outcome 6: Diversified and strengthened livelihoods and sources of income for vulnerable people in targeted areas Outcome 7: Improved policies and regulations that promote and enforce resilience measures | 1 | 1. Relevant threat and hazard information generated and disseminated to stakeholders on a timely basis 2.1. No. and type of targeted institutions with increased capacity to minimize exposure to climate variability risks 2.2. Number of people with reduced risk to extreme weather events 3.1. Percentage of targeted population aware of predicted adverse impacts of climate change, and of appropriate responses 3.2. Modification in behavior of targeted population 4.1. Development sectors' services responsive to evolving needs from changing and variable climate 4.2. Physical infrastructure improved to withstand climate change and variability-induced stress 5. Ecosystem services and natural assets maintained or improved under climate change and variability-induced stress 6.1. Percentage of households and communities having more secure (increased) access to livelihood assets 6.2. Percentage of targeted population with sustained climate-resilient livelihoods 7. Climate change priorities are integrated into national development strategy
Fund Output | Please select from dropdown menu below | Fund Output Indicator | Please select from dropdown menu below | Target at CEO Endorsement (see Units in next sheet) | Baseline (see Units in next sheet) | Mid-term Results | Terminal Results
Output 1: Risk and vulnerability assessments conducted and updated at a national level Output 2.1: Strengthened capacity of national and regional centres and networks to respond rapidly to extreme weather events Output 2.2: Targeted population groups covered by adequate risk reduction systems Output 3: Targeted population groups participating in adaptation and risk reduction awareness activities Output 4: Vulnerable physical, natural, and social assets strengthened in response to climate change impacts, including variability Output 5: Vulnerable physical, natural, and social assets strengthened in response to climate change impacts, including variability Output 6: Targeted individual and community livelihood strategies strengthened in relation to climate change impacts, including variability Output 7: Improved integration of climate-resilience strategies into country development plans |  | 1.1. No. and type of projects that conduct and update risk and vulnerability assessments 1.2. Development of early warning systems 2.1.1. No. of staff trained to respond to, and mitigate impacts of, climate-related events 2.1.2. Capacity of staff to respond to, and mitigate impacts of, climate-related events from targeted institutions increased 2.2.1. Percentage of population covered by adequate risk-reduction systems 2.2.2. No. of people affected by climate variability 3.1 No. and type of risk reduction actions or strategies introduced at local level 3.2 No. of news outlets in the local press and media that have covered the topic 4.1. No. and type of health or social infrastructure developed or modified to respond to new conditions resulting from climate variability and change (by type) 4. 2. No. of physical assets strengthened or constructed to withstand conditions resulting from climate variability and change (by asset types) 5. No. and type of natural resource assets created, maintained or improved to withstand conditions resulting from climate variability and change (by type of assets) 6.1. No. and type of adaptation assets (physical as well as knowledge) created in support of individualor community-livelihood strategies 6.2. Type of income sources for households generated under climate change scenario 7.1. No., type, and sector of policies introduced or adjusted to address climate change risks 7.2. No. or targeted development strategies with incorporated climate change priorities enforced
OBJECTIVE 2
Fund Outcome | Please select from dropdown menu below | Fund Outcome Indicator | Please select from dropdown menu below | Target at CEO Endorsement | Baseline | Mid-term Results | Terminal Results
Outcome 1: Reduced exposure at national level to climate-related hazards and threats Outcome 2: Strengthened institutional capacity to reduce risks associated with climate-induced socioeconomic and environmental losses Outcome 3: Strengthened awareness and ownership of adaptation and climate risk reduction processes at local level Outcome 4: Increased adaptive capacity within relevant development and natural resource sectors Outcome 5: Increased ecosystem resilience in response to climate change and variability-induced stress Outcome 6: Diversified and strengthened livelihoods and sources of income for vulnerable people in targeted areas Outcome 7: Improved policies and regulations that promote and enforce resilience measures |  | 1. Relevant threat and hazard information generated and disseminated to stakeholders on a timely basis 2.1. No. and type of targeted institutions with increased capacity to minimize exposure to climate variability risks 2.2. Number of people with reduced risk to extreme weather events 3.1. Percentage of targeted population aware of predicted adverse impacts of climate change, and of appropriate responses 3.2. Modification in behavior of targeted population 4.1. Development sectors' services responsive to evolving needs from changing and variable climate 4.2. Physical infrastructure improved to withstand climate change and variability-induced stress 5. Ecosystem services and natural assets maintained or improved under climate change and variability-induced stress 6.1. Percentage of households and communities having more secure (increased) access to livelihood assets 6.2. Percentage of targeted population with sustained climate-resilient livelihoods 7. Climate change priorities are integrated into national development strategy
Fund Output | Please select from dropdown menu below | Fund Output Indicator | Please select from dropdown menu below | Target at CEO Endorsement | Baseline | Mid-term Results | Terminal Results
Output 1: Risk and vulnerability assessments conducted and updated at a national level Output 2.1: Strengthened capacity of national and regional centres and networks to respond rapidly to extreme weather events Output 2.2: Targeted population groups covered by adequate risk reduction systems Output 3: Targeted population groups participating in adaptation and risk reduction awareness activities Output 4: Vulnerable physical, natural, and social assets strengthened in response to climate change impacts, including variability Output 5: Vulnerable physical, natural, and social assets strengthened in response to climate change impacts, including variability Output 6: Targeted individual and community livelihood strategies strengthened in relation to climate change impacts, including variability Output 7: Improved integration of climate-resilience strategies into country development plans |  | 1.1. No. and type of projects that conduct and update risk and vulnerability assessments 1.2. Development of early warning systems 2.1.1. No. of staff trained to respond to, and mitigate impacts of, climate-related events 2.1.2. Capacity of staff to respond to, and mitigate impacts of, climate-related events from targeted institutions increased 2.2.1. Percentage of population covered by adequate risk-reduction systems 2.2.2. No. of people affected by climate variability 3.1 No. and type of risk reduction actions or strategies introduced at local level 3.2 No. of news outlets in the local press and media that have covered the topic 4.1. No. and type of health or social infrastructure developed or modified to respond to new conditions resulting from climate variability and change (by type) 4. 2. No. of physical assets strengthened or constructed to withstand conditions resulting from climate variability and change (by asset types) 5. No. and type of natural resource assets created, maintained or improved to withstand conditions resulting from climate variability and change (by type of assets) 6.1. No. and type of adaptation assets (physical as well as knowledge) created in support of individualor community-livelihood strategies 6.2. Type of income sources for households generated under climate change scenario 7.1. No., type, and sector of policies introduced or adjusted to address climate change risks 7.2. No. or targeted development strategies with incorporated climate change priorities enforced
OBJECTIVE 3
Fund Outcome | Please select from dropdown menu below | Fund Outcome Indicator | Please select from dropdown menu below | Target at CEO Endorsement | Baseline | Mid-term Results | Terminal Results
Outcome 1: Reduced exposure at national level to climate-related hazards and threats Outcome 2: Strengthened institutional capacity to reduce risks associated with climate-induced socioeconomic and environmental losses Outcome 3: Strengthened awareness and ownership of adaptation and climate risk reduction processes at local level Outcome 4: Increased adaptive capacity within relevant development and natural resource sectors Outcome 5: Increased ecosystem resilience in response to climate change and variability-induced stress Outcome 6: Diversified and strengthened livelihoods and sources of income for vulnerable people in targeted areas Outcome 7: Improved policies and regulations that promote and enforce resilience measures |  | 1. Relevant threat and hazard information generated and disseminated to stakeholders on a timely basis 2.1. No. and type of targeted institutions with increased capacity to minimize exposure to climate variability risks 2.2. Number of people with reduced risk to extreme weather events 3.1. Percentage of targeted population aware of predicted adverse impacts of climate change, and of appropriate responses 3.2. Modification in behavior of targeted population 4.1. Development sectors' services responsive to evolving needs from changing and variable climate 4.2. Physical infrastructure improved to withstand climate change and variability-induced stress 5. Ecosystem services and natural assets maintained or improved under climate change and variability-induced stress 6.1. Percentage of households and communities having more secure (increased) access to livelihood assets 6.2. Percentage of targeted population with sustained climate-resilient livelihoods 7. Climate change priorities are integrated into national development strategy
Fund Output | Please select from dropdown menu below | Fund Output Indicator | Please select from dropdown menu below | Target at CEO Endorsement | Baseline | Mid-term Results | Terminal Results
Output 1: Risk and vulnerability assessments conducted and updated at a national level Output 2.1: Strengthened capacity of national and regional centres and networks to respond rapidly to extreme weather events Output 2.2: Targeted population groups covered by adequate risk reduction systems Output 3: Targeted population groups participating in adaptation and risk reduction awareness activities Output 4: Vulnerable physical, natural, and social assets strengthened in response to climate change impacts, including variability Output 5: Vulnerable physical, natural, and social assets strengthened in response to climate change impacts, including variability Output 6: Targeted individual and community livelihood strategies strengthened in relation to climate change impacts, including variability Output 7: Improved integration of climate-resilience strategies into country development plans |  | 1.1. No. and type of projects that conduct and update risk and vulnerability assessments 1.2. Development of early warning systems 2.1.1. No. of staff trained to respond to, and mitigate impacts of, climate-related events 2.1.2. Capacity of staff to respond to, and mitigate impacts of, climate-related events from targeted institutions increased 2.2.1. Percentage of population covered by adequate risk-reduction systems 2.2.2. No. of people affected by climate variability 3.1 No. and type of risk reduction actions or strategies introduced at local level 3.2 No. of news outlets in the local press and media that have covered the topic 4.1. No. and type of health or social infrastructure developed or modified to respond to new conditions resulting from climate variability and change (by type) 4. 2. No. of physical assets strengthened or constructed to withstand conditions resulting from climate variability and change (by asset types) 5. No. and type of natural resource assets created, maintained or improved to withstand conditions resulting from climate variability and change (by type of assets) 6.1. No. and type of adaptation assets (physical as well as knowledge) created in support of individualor community-livelihood strategies 6.2. Type of income sources for households generated under climate change scenario 7.1. No., type, and sector of policies introduced or adjusted to address climate change risks 7.2. No. or targeted development strategies with incorporated climate change priorities enforced
OBJECTIVE 4
Fund Outcome | Please select from dropdown menu below | Fund Outcome Indicator | Please select from dropdown menu below | Target at CEO Endorsement | Baseline | Mid-term Results | Terminal Results
Outcome 1: Reduced exposure at national level to climate-related hazards and threats Outcome 2: Strengthened institutional capacity to reduce risks associated with climate-induced socioeconomic and environmental losses Outcome 3: Strengthened awareness and ownership of adaptation and climate risk reduction processes at local level Outcome 4: Increased adaptive capacity within relevant development and natural resource sectors Outcome 5: Increased ecosystem resilience in response to climate change and variability-induced stress Outcome 6: Diversified and strengthened livelihoods and sources of income for vulnerable people in targeted areas Outcome 7: Improved policies and regulations that promote and enforce resilience measures |  | 1. Relevant threat and hazard information generated and disseminated to stakeholders on a timely basis 2.1. No. and type of targeted institutions with increased capacity to minimize exposure to climate variability risks 2.2. Number of people with reduced risk to extreme weather events 3.1. Percentage of targeted population aware of predicted adverse impacts of climate change, and of appropriate responses 3.2. Modification in behavior of targeted population 4.1. Development sectors' services responsive to evolving needs from changing and variable climate 4.2. Physical infrastructure improved to withstand climate change and variability-induced stress 5. Ecosystem services and natural assets maintained or improved under climate change and variability-induced stress 6.1. Percentage of households and communities having more secure (increased) access to livelihood assets 6.2. Percentage of targeted population with sustained climate-resilient livelihoods 7. Climate change priorities are integrated into national development strategy
Fund Output | Please select from dropdown menu below | Fund Output Indicator | Please select from dropdown menu below | Target at CEO Endorsement | Baseline | Mid-term Results | Terminal Results
Output 1: Risk and vulnerability assessments conducted and updated at a national level Output 2.1: Strengthened capacity of national and regional centres and networks to respond rapidly to extreme weather events Output 2.2: Targeted population groups covered by adequate risk reduction systems Output 3: Targeted population groups participating in adaptation and risk reduction awareness activities Output 4: Vulnerable physical, natural, and social assets strengthened in response to climate change impacts, including variability Output 5: Vulnerable physical, natural, and social assets strengthened in response to climate change impacts, including variability Output 6: Targeted individual and community livelihood strategies strengthened in relation to climate change impacts, including variability Output 7: Improved integration of climate-resilience strategies into country development plans | 1 | 1.1. No. and type of projects that conduct and update risk and vulnerability assessments 1.2. Development of early warning systems 2.1.1. No. of staff trained to respond to, and mitigate impacts of, climate-related events 2.1.2. Capacity of staff to respond to, and mitigate impacts of, climate-related events from targeted institutions increased 2.2.1. Percentage of population covered by adequate risk-reduction systems 2.2.2. No. of people affected by climate variability 3.1 No. and type of risk reduction actions or strategies introduced at local level 3.2 No. of news outlets in the local press and media that have covered the topic 4.1. No. and type of health or social infrastructure developed or modified to respond to new conditions resulting from climate variability and change (by type) 4. 2. No. of physical assets strengthened or constructed to withstand conditions resulting from climate variability and change (by asset types) 5. No. and type of natural resource assets created, maintained or improved to withstand conditions resulting from climate variability and change (by type of assets) 6.1. No. and type of adaptation assets (physical as well as knowledge) created in support of individualor community-livelihood strategies 6.2. Type of income sources for households generated under climate change scenario 7.1. No., type, and sector of policies introduced or adjusted to address climate change risks 7.2. No. or targeted development strategies with incorporated climate change priorities enforced