## Overview
Project Performance Report (PPR)
| Period of Report (Dates) | 1st January 2016 - 31 December 2016
| Project Title: | Enhancing Resilience of Samoa’s Coastal Communities to Climate Change
| Project Summary: | This programme is designed to complete a holistic and country-wide approach to climate change adaptation in the coastal zones in Samoa. It will provide the vehicle to revise and implement the approved Coastal Infrastructure Management (CIM) Plans on the ground as a practical community based response to adaptation. The program will result in a “whole of country” adaptation response for coastal management at the nationwide scale. The implementation of appropriate responses will be supported by the programme through site specific design of adaptation interventions and active community engagement in the process. The programme will serve to implement the CIM Strategy, which was originally prepared in 2000 and revised in 2006 to include specific reference to CC related issues. In particular the predicted hazard zones were reviewed against the NAPA data (2005) and inter-alia the Climate Risk Profiles (2007) and reference was made to expected land use impacts from more frequent and intense cyclone events. There is an opportunity under this programme to consider the more detailed and updated climate change projections now available for Samoa. The Strategy which has as its central focus a theme of “resilience”, directs coastal adaptation to focus upon activities which will have a positive effect upon community resilience. It sets out a range of adaptation actions that include both "soft” actions such as managed retreat and “hard” engineered solutions such as seawalls. The CIM Strategy has been endorsed by Cabinet as official Government policy with respect to coastal management.
|  |  | Countries | Project Type: |  | GEF Focal Area: | GEF 4 Focal Areas | GEF 2 / 3 Operational Programme: | Overall Rating of the project in the evaluation by the project evaluator: | GEF-4 Focal Area Strategic Program: | GEF-3 Focal Area Strategic Program:
| Database Number: | PIMS No. 4667 | Afghanistan | FP | Yes | Biodiversity | 1 | 1 | U | BD-SP1-PA Financing | 1: Arid & semi-arid ecosystems
Implementing Entity (IE) [name]: |  | UNDP | Albania | MSP | No | Climate Change Adaptation | 2 | 2 | S | BD-SP2-Marine PA | 2: Coastal, marine & freshwater ecosystems
| Type of IE: | MIE | Algeria | EA |  | Climate Change Mitigation | 3 | 3 | MU | BD-SP3-PA Networks | 3: Forest ecosystems
| Country(ies): | Samoa | Angola |  |  | International Waters | 5 | 5 | Good | BD-SP5-Markets | 13: Conservation and Sustainable Use of Biological Diversity Important to Agriculture
Relevant Geographic Points (i.e. cities, villages, bodies of water): |  | 25 Districts of Samoa | Argentina |  |  | Multiple Focal Area |  |  |  | BD-SP7-Invasive Alien Species(IAS) | 6: Promoting the adoption of renewable energy by removing barriers and reducing implementation costs
[8 empty] | CC-SP2- Industrial EE | 8: Waterbody based operational program
| Project Milestones | [6 empty] | CC-SP3-RE,CC-SP4-Biomass | 9: Integrated Land and Water multiple focal area
| Milestone |  | Bahamas | [6 empty] | CC-SP5-Transport | 10: Contaminants based operational program
AFB Approval Date: |  | 2012-01-02
IE-AFB Agreement Signature Date: |  | 2012-04-01 | [6 empty] | CC-SP6-LULUCF | 12: Integrated Ecosystem Management
Start of Project/Programme: |  | 2013-01-28 | [6 empty] | Cross cutting capacity building | 14: Persistent Organic Pollutants
Mid-term Review Date (if planned): |  | 2015-09-11
| Terminal Evaluation Date: | 30/06/2017
|  | List documents/ reports/ brochures / articles that have been prepared about the project. | Cyprus
|  | Programme Reports: Inception Workshop Report, Quarterly Progress Reports, AF/PPCR Joint Programme Steering Committee meeting (3 March 2014) minutes TORs for Programme Institutional Arrangement (AF/PPCR) - Technical Advisory Group, National Steering Committee, Joint Programme Management Unit (Programme Manager, Financial Management Specialist, Procurement Specialist, Environmental and Social Safeguards Specialist, Monitoring and Evaluation Specialist), Technical Advisor, Project Assistant (AF Specific), Technical Support Team (Community Liaison Officer, GIS Specialist, Coastal Morphology Specialist) Technical Reports/Documents - Methodological Report on the review and Implementation of the Coastal Infrastructure Management (CIM) Plans, Preliminary Review of Coastal Protection Measures, Matrix of preliminary costing and prioritization of CIM Plan actions. Light Detection and Ranging (LiDAR) Software Training - PACCSAP Press Release on CIMP Review Consultations Samoa Survey Report on LiDAR Acquisition (FUGRO LAD) LiDAR Quality Assurance Report (CRCSI) TORs for CIMP Review Team (Team Leader, Ecosystem Specialist, Livelihood Specialist, Civil Engineer, Geomorphologist, Spatial Risk and Disaster Risk Management Specialist, CIM Plans Translator Draft Revised CIM Plan Review Handbook 2016 Draft Relocation Strategy and Handbook 2016 Institutional Strengthening Review Report, MNRE Situational Analysis (Functional Review) Inception Reports of the Team Leader, Ecosystem Specialists, Livelihood Specialist, Civil Engineer, SRPDRM, Geomorphology specialist Status Report on Ecosystems for 15 Districts- Satupaitea, Gagaemauga 2, Gagaemauga 3, Gagaifomauga 1, Gagaifomauga 2, Vaisigano 1, Vaisigano 2, Alataua West, Itumalo Salega, Palauli le Falefa, Faasaleleaga 1, Faasaleleaga 2, Faasaleleaga 3, Faasalelaga 4, Aiga i le Tai Status Report on Civil Engineering Solutions for 15 Districts- Satupaitea, Gagaemauga 2, Gagaemauga 3, Gagaifomauga 1, Gagaifomauga 2, Vaisigano 1, Vaisigano 2, Alataua West, Itumalo Salega, Palauli le Falefa, Faasaleleaga 1, Faasaleleaga 2, Faasaleleaga 3, Faasalelaga 4, Aiga i le Tai Status Report on Livelihood for 15 Districts- Satupaitea, Gagaemauga 2, Gagaemauga 3, Gagaifomauga 1, Gagaifomauga 2, Vaisigano 1, Vaisigano 2, Alataua West, Itumalo Salega, Palauli le Falefa, Faasaleleaga 1, Faasaleleaga 2, Faasaleleaga 3, Faasalelaga 4, Aiga i le Tai | Czech Republic
List the Website address (URL) of project. |  |  | Democratic People's Republic of Korea
|  | www.undp-alm.org/projects/af-samoa | Democratic Republic of the Congo
Denmark
| Project contacts: |  | Djibouti
National Project Manager/Coordinator |  |  | Dominica
| Name: | Fetoloai Alama-Yandall, ACEO, Planning and Urban Management Agency | Dominican Republic
| Email: | fetoloai.alama@mnre.gov.ws | Ecuador
| Date: | 2017-01-19 | Egypt
| Government DA |  | El Salvador
| Name: | Ms. Peseta Noumea Simi, Chief Executive Officer, Ministry of Foreign Affairs and Trade | Equatoral Guinea
| Email: | noumea@mfat.gov.ws | Eritrea
| Date: | 2017-01-19 | Estonia
| Implementing Entity |  | Ethiopia
| Name: | Noto Negoro, Reis Lopez Rello, UNDP | Fiji
| Email: | notonegoro@undp.org; reis.lopez.rello@undp.org | Finland
| Date: | 2017-01-19 | France
| Executing Agency |  | Gambia
| Name: | Mr. Suluimalo Amataga Penaia, Chief Executive Officer, Ministry of Natural Resources and Environment | Georgia
| Email: | amataga.penaia@mnre.gov.ws | Germany
| Date: | 2017-01-19 | Ghana
| Executing Agency |  | Greece
| Name: | MNRE (PUMA) - Kirisimasi Seumanutafa | Grenada
| Email: | kirisimasi.seumanutafa@mnre.gov.ws | Guatemala
| Date: | 2017-01-19 | Guinea
| Executing Agency |  | Guinea Bissau
| Name: |  | Guyana
| Email: |  | Haiti
| Date: |  | Honduras
Hungary
Iceland
India
Indonesia
Iran (Islamic Republic of)
Iraq
Ireland
Israel
Italy
Jamaica
Japan
Jordan
Kazakhstan
Kenya
Kiribati
Kuwait
Kyrgyzstan
Lao People’s Democratic Republic
Latvia
Lebanon
Lesotho
Liberia
Libyan Arab Jamahiriya
Liechtenstein
Lithuania
Luxembourg
Madagascar
Malawi
Malaysia
Maldives
Mali
Malta
Marshall Islands
Mauritania
Mauritius
Mexico
Micronesia, Federated States of
Monaco
Mongolia
Montenegro
Morocco
Mozambique
Myanmar
Namibia
Nauru
Nepal
Netherlands
New Zealand
Nicaragua
Niger
Nigeria
Norway
Oman
Pakistan
Palau
Panama
Papua New Guinea
Paraguay
Peru
Philippines
Poland
Portugal
Qatar
Republic of Korea
Republic of Moldova
Romania
Russian Federation
Rwanda
Saint Kitts and Nevis
Saint Lucia
Saint Vincent and the Grenadines
Samoa
San Marino
Sao Tome and Principe
Saudi Arabia
Senegal
Serbia
Seychelles
Sierra Leone
Singapore
Slovakia
Slovenia
Solomon Islands
Somalia
South Africa
Spain
Sri Lanka
Sudan
Suriname
Swaziland
Sweden
Switzerland
Syrian Arab Republic
Tajikistan
Thailand
The former Yugoslav Republic of Macedonia
Timor-Leste
Togo
Tonga
Trinidad and Tobago
Tunisia
Turkey
Turkmenistan
Tuvalu
Uganda
Ukraine
United Arab Emirates
United Kingdom of Great Britain and Northern Ireland
United Republic of Tanzania
United States of America
Uruguay
Uzbekistan
Vanuatu
Venezuela, Bolivarian Republic of
Viet Nam
Yemen
Zambia
Zimbabwe

## FinancialData
Financial information: cumulative from project start to [insert date]
DISBURSEMENT OF AF GRANT FUNDS
Cumulative Total Disbursements from AF to end December 2016 (USD$) | 6696856
How much of the total AF grant as noted in Project Document plus any project preparation grant has been spent to date?
Estimated cumulative total disbursement as of 31 December 2016 | 5360176
Add any comments on AF Grant Funds. (word limit=200) | The cumulative total disbursement from AF to the end December 2016 is USD 6,696,856 with an actual cumulative expenditure as of 31 December 2016 being USD 5,360,176 The expenditure for the current year (2016) of the project has increased compared to the first three years of the project. This is expected seeing how the CIMP Review began in Q3 2016 with the consultants being recruited and the consultations of the CIMP’s. In addition, the Small Grants MoU was signed with the first tranche released to CSSP (50% of total grant) for the operational arrangement in CSSP as well as the first call for proposals, the small grants officer based at CSSP was also recruited. The development and preparation of the Relocation Strategy and Village Hazard Zones also began in parallel to the CIMPs. The delivery is seen to be biggest in Outcome 2, which is expected, as this is mostly infrastructure work for climate proofing coastal roads, shoreline protection, enhancing water supply and flood protection measures. The activities were launched and completed in this reporting period. This is also the component the small grant is under. The project looks to continue improving its delivery rate in the final year of the project 2017.
INVESTMENT INCOME
Amount of annual investment income generated from the Adaptation Fund’s grant
EXPENDITURE DATA
List outputs and corresponding amount spent for the current reporting period | ITEM / ACTIVITY / ACTION | AMOUNT
| Outcome 1: Strengthened awareness and ownership of coastal adaptation and climate risk reduction processes at community and national levels in 25 Districts and 139 villages through gender-sensitive processes | 175439
| Output 1.1. CIM Plans reviewed in 25 districts with climate induced disaster risk management fully integrated, adopting a Watershed and Ridge to Reef Management approach | 127569
| Output 1.2.Village hazard zone relocation plans formulated in at least 15 villages in selected districts | 33620
| Output 1.3. Training delivered to 300 village leaders in 139 villages on review of CIM Plans and relocation planning process integrating climate risks. | 14251
| Outcome 2 - Integrated Community-Based Coastal Adaptation and Disaster Risk Management measures | 2028686
| Output 2.1 Climate proofing measures implemented on coastal roads and related infrastructure in at least 10 districts and 40 villages | 844211
| Output 2.2. Shoreline protection measures implemented in at least 10 districts and 40 villages. | 835161
| Output 2.3. Water supply enhanced to withstand climate change risks in least 5 districts and 15 villages. | 153119
| Output 2.4. Flood protection measures are implemented in at least 5 districts and 15 villages. | 196195
| Outcome 3 - Institutional strengthening to support climate resilient coastal management policy frameworks | 137405
| Output 3.1 Revised national organization and institutional structures for CIM Plans implementation. | 30175
| Output 3.2 Village hazard zone relocation handbook prepared to guide further relocation planning activities. | 26346
| Output 3.3 Regulatory procedures for physical works implementation revised with climate change risks integrated. | 48938
| Output 3.4 Policymakers and technical officers in the relevant Ministries and Authorities are trained on climate risk assessment and planning processes for coastal adaptation. | 27558
| Output 3.5 Adaptation lessons learned and best practices generated through the adaptation implementation and related policy processes are captured and disseminated nationally and globally | 4388
| Project Management | 376203
| Unrealized Gain/Loss | -8842.89
| TOTAL | 2708890.11
PLANNED EXPENDITURE SCHEDULE
List outputs planned and corresponding projected cost for the upcoming reporting period | ITEM / ACTIVITY / ACTION | PROJECTED COST | Est. Completion Date
| Outcome 1 - Strengthened awareness and ownership of coastal adaptation and climate risk reduction processes at community and national levels in 25 Districts and 139 villages | 524861
| Output 1.1. No. of Districts covered by reviewed and updated CIM Plans with climate change risks fully integrated | 405845 | 2017-12-31
| Output 1.2. No. of Districts with village hazard zone relocation plans completed | 100000 | 2017-12-31
| Output 1.3. No. of community representatives trained on coastal risk assessment and adaptation and numbers of individuals engaged in those sessions | 19016 | 2017-12-31
| Outcome 2 - Integrated Community-Based Coastal Adaptation and Disaster Risk Management measures | 1709595
| Output 2.1 Climate proofing measures implemented on coastal roads and related infrastructure in at least 10 districts and 40 villages | 1093873 | 2017-12-31
| Output 2.2. Shoreline protection measures implemented in at least 10 districts and 40 villages. | 522518 | 2017-12-31
| Output 2.3. Water supply enhanced to withstand climate change risks in least 5 districts and 15 villages. | 31938 | 2017-12-31
| Output 2.4. Flood protection measures are implemented in at least 5 districts and 15 villages. | 61266 | 2017-12-31
| Outcome 3 - Institutional strengthening to support climate resilient coastal management policy frameworks | 301382
| Output 3.1 Revised national organization and institutional structures for CIM Plans implementation. | 35000 | 2017-12-31
| Output 3.2 Village hazard zone relocation handbook prepared to guide further relocation planning activities. | 120500 | 2017-12-31
| Output 3.3 Regulatory procedures for physical works implementation revised with climate change risks integrated. | 7332 | 2017-12-31
| Output 3.4 Policymakers and technical officers in the relevant Ministries and Authorities are trained on climate risk assessment and planning processes for coastal adaptation. | 33550 | 2017-12-31
| Output 3.5 Adaptation lessons learned and best practices generated through the adaptation implementation and related policy processes are captured and disseminated nationally and globally | 105000 | 2017-12-31
| Project Management | 152236
| Travel | 20000 | 2017-12-31
| Communications Specialist | 40000 | 2017-12-31
| Promotion and Awareness Officer | 20000 | 2017-12-31
| Administrative Assistant | 20000 | 2017-12-31
| Stationery Material | 5000 | 2017-12-31
| Asset Branding | 5000 | 2017-12-31
| Audit | 8500 | 2017-12-31
| Office Furniture/Equipment | 6000 | 2017-12-31
| TAG Meetings | 2736 | 2017-12-31
| UNDP support services (for procurement, payments etc.) | 5000 | 2017-12-31
| Terminal Evaluation | 20000 | 2017-12-31
| TOTAL | 2688074
ACTUAL CO-FINANCING (If the MTR or TE have not been undertaken this reporting period, DO NOT report on actual co-financing.)
How much of the total co-financing as committed in the Project Document has actually been realized?
Estimated cumulative actual co-financing as verified during Mid-term Review (MTR) or Terminal Evaluation (TE).
Add any comments on actual co-financing in particular any issues related to the realization of in-kind, grant, credits, loans, equity, non-grant instruments and other types of co-financing. (word limit=200)

## Procurement (hidden)
PROCUREMENT DATA
Please provide information for all contracts over $2,500 USD
Please provide the number of contracts under $2,500, signed during this reporting period: |  |  |  | 11 |  | Exchange rate: 2.5
LIST OF CONTRACTS
List all contracts related to the project/program with signature dates
Contract Type | Agency / Contracted party | Contract Value/Amount (USD) | Signature Date | Payment to Date | Remaining Balance
(Works Contract) Measure and Value | zone 6 Drainage Routine Maintenance between LTA and KLSS Lawnmowing & Drainage Services | 67859.7522 | 2015-11-01 | 67859.7522 | 0
(Works Contract) Measure and Value | Zone 7 Drainage Routine Maintenance between LTA and A&J Lawnmowing & Drainage Services | 67309.8 | 2015-11-01 | 67309.8 | 0
(Works Contract) Measure and Value | Construction of Vaiala Seawall contract between MNRE-PUMA and Silva Transport Ltd | 821749.2913 | 2015-06-16 | 821749.2913 | 0
(Works Contract) Measure and Value | Construction of Salei'a Rockwall contract between MNRE-PUMA and Apia Lua | 1015158.913 | 2015-07-29 | 922550.21 | 92608.703
(Services Contract) Time Based | Design &Supervision Services contract between MNRE-PUMA and TGA Ltd | 120334.7826 | 2015-01-26 | 120334.7826 | 0
(Works Contract) Measure and Value | Rehabilitation and Upgrade of Independent Water Scheme for Sili Village- MWCSD / IWSA/Kings Construction | 405000.5 | 2014-11-26 | 405000.5 | 0
(Works Contract) Measure and Value | Reconstruction of Mulifanua Access Road contract between LTA and Lee Transport Co. Ltd | 251180.68 | 2015-10-13 | 238621.65 | 12559.03
(Works Contract) Measure and Value | Construction of Pata, Falelatai Access Road contract between LTA and T&N Toleafoa Ltd | 239098.7522 | 2015-10-13 | 227143.81 | 11954.9422
(Works Contract) Measure and Value | Construction of Tufutafoe Link Road contract between LTA and FICO Construction Ltd | 331760 | 2015-11-01 | 315186.25 | 16573.75
(Works Contract) Measure and Value | Construction of Manase Beach Replenishment project. Contract STA and Apia Lua Ltd | 444967.56 | 2016-05-13 | 379750.17 | 65217.39
(Works Contract) Measure and Value | Construction of Mulinuuu Access Road contract between MNRE-PUMA and Lucky Construction | 136401 | 2015-12-03 | 88200 | 48201
(Services Contract) Time Based | Inventory on the Status of Implementation of the CIM Plans Interventions for the 41 Districts of Samoa contract between UNDP and Isikuki Punivalu & Associates (Ofeira Faasau) | 14090.23 | 2015-05-13 | 14090 | 0.23
(Services Contract) Time Based | Technical Advisory contract between MNRE-PUMA and Ulu Bismark Crawley | 263000.3565 | 2014-02-17 | 263000.3565 | 0
(Services Contract) Time Based | Public Education and Awareness Officer MNRE-PUMA and Leiloa Asaasa | 76482.8 | 2015-04-27 | 65152.1 | 11330.7
(Services Contract) Time Based | Programe Assistant Officer MNRE-PUMA and Tepora Ulisese | 85271.4 | 2014-01-27 | 72638.6 | 12632.8
(Service contract) deliverables and time based | Team Leader for the CIMP Review-Ms Satui Bentin | 125400 | 2016-08-01 | 25080 | 100320
(Service contract) deliverables and time based | Ecosystem Specialist for CIMP Review- Mr Tusani Reti | 42665 | 2016-09-12 | 17492.65 | 25172.35
(Service contract) deliverables and time based | Livelihood Specialist for CIMP Review- Mr. Geoffrey Dews | 55000 | 2016-10-17 | 5500 | 49500
(Service contract) deliverables and time based | Resettlement Specialist- Mr. Toeolesulusulu Cedric Schuster | 65000 | 2016-08-01 | 35750 | 29250
(Service contract) deliverables and time based | Institutional Strengthening Specialist- Faamausili Dr Matagialofi | 39600 | 2016-09-12 | 19272 | 20328
(Service contract) deliverables and time based | Civil Engineer for CIMP Review - Mr. John Townsend | 59290 | 2016-11-10 | 5950 | 53340
(LTA contract) based on number of pages translated | CIMP Review Translator- Mrs. Ainslie So'o | 60000 | 2016-12-13 | 0 | 60000
(RLA contract) deliverables and time based | Geomorphologist for the CIMP Review - GWP Consultants | 68831 | 2016-11-21 | 0 | 68831
(Service contract) deliverables and time based | Review of the National Road Standards- MWTI & Isikuki Punivalu and Associates with JMConsult | 42320 | 2016-08-29 | 42320 | 0
Audit Office-Samoa | Project Audit-Ah Chong Public Accounts | 5980 | 2016-01-01 | 5980 | 0
|  |  | TOTAL | 4225931.9226 | 677819.8952
BIDS
List all bids for each contact signed with date of open call and winning bid
CONTRACT & Procurement Method | Submitted Bids | Bid Amount (USD) | Winning Bid Amount (USD) | Selection Justification for the Winner
Construction of Access Road at Fusi, Saoluafata awarded to Lee Transport on the 9 April 2015, Tender Process. | Lee Transport | 274994.5 | Lee Transport (USD$274,994.50) | Lee Transport was ranked 1st as the substantial responsive and least cost bid therefore was awarded the contract.
| Lucky Construction | 354145
| silva | 430925
| Ah Liki Construction | 444491.8261
Routine Maintenance of open and close drainages from Malifa to Toomatagi and Malifa to Afiamalu (zone 6) awarded to KLSS Landscaping Services & Civil Works on the 1 November 2015. Tender Process. | Captain Mark | 65542.5 | KLSS Landscaping & Civil Services (USD$67,859.75) | KLSS is the Most Responsive bid
| KLSS | 67859.7522
| Samoa Markers | 71974.5783
| Civil Care | 75753.7522
| R&R | 78675.5
| Lee | 86587.7522
| Simalua Apisaloma | 88435.5
| 3T's | 95640.5
| Silva | 119874.0522
| Zero Mgmt | 123667.4957
Routine Maintenance of open and close drainages from Vaivase to Laulii (zone 7) awarded to A&J Lawnmawing & Drainage Services on the 1 November 2015. Tender Process. | A&J | 67309.8 | A&J Lawnmowing & Drainage Services (USD$67,309.80) | A&J Lawnmowing & Drainage Services was ranked 1st as the substantial responsive and least cost bid, therefore was awarded the contract.
| Civil Care | 74695.6261
| VIP | 77500
| Samoa Markers | 79188.4348
| KLSS | 80388.2522
| Lee | 85154
| East Coast | 86725.5
Construction of Vaiala seawall, awarded to Silva Transport on 16 June 2015. Tender Process | Transworks Ltd | 818436.4 | Silver Transport (USD$821,749.29) | Silva Transport is the most responsive bid with realistic bid price
| Ulia Construction | 802871.3
| Silva Transport Ltd | 821749.29
| Lucky Construction | 892930.7
| Lee Transport Ltd | 625636
Construction of Salei'a Rockwall awarded to Apia Lua on 29 July 2015. Tender Process. | Apia Lua Ltd | 1015158.91 | Apia Lua (USD$1,015,158.91) | Apia Lua is the most responsive bid
| Sakalafai Ltd | 2270591.3
| O. N Sons Ltd | 1139654.78
| Ah Liki Construction Ltd | 495502.078
| Transworks Ltd | 1842666.52
Design and Supervision Services awarded to TGA Ltd on the 29 January 2015. Tender Process | Isikuki Punivalu & Associates | 153445 | TGA Ltd (USD$120,334.78) | TGA was ranked #1 for its responsiveness and competitive bid price
| Tinai Gordon & Associates | 120334.78
| KEW Consult | 129934.87
Rehabilitation and Upgrade of Independent Water Scheme for Sili village under MWCSD / IWSA. Awarded to Kigs Construction on 25 January 2016. Tender Process. | PPG Engineering & Construction Ltd | 221510.85 | Kings Construction (USD$405,000.5) | Kings Construction Ltd is the most responsive bidder
| Blue Bird Construction Ltd | 362184.27
| Kings Construction Ltd | 405000.5
| Apia Lua Ltd/Transworks (Joint Venture) | 379103.37
Construction of Mulifanua Access Road awarded to Lee Transport on 13 October 2015. Tender Process. | Lee Transport | 241951.5261 | Lee Transport (USD$241,951.53) | Lee Transport was ranked 1st as the substantial responsive and least cost bid therefore was awarded the contract. Although SWEL, Lucky, T&N Toleafoa, Webster bid prices were lower than Lee, Lee's bid was more substantially responsive.
| Ah Liki Construction | 279906
| Lucky Construction | 193533.9261
| SWEL | 217657.7478
| T&N Toleafoa | 223286.2522
| Ulia Construction | 277970
| Webster Works & Infrastructure | 186257.5
Construction of Pata, Falelatai Access Road awarded to T&N Toleafoa Ltd on 26 October 2015 | T&N Toleafoa | 239098.7522 | T&N Toleafoa (USD 239,098.75) | T&N Toleafoa was ranked 1st as the substantial responsive and least cost bid therefore was awarded the contract
| Webster Works & Infrastructure | 282576.8
| SWEL | 227484.0696
CIM Strategy Review consultancy awarded to Tusani Reti on 29 June 2015 through UNDP. | Tusani Iosefatu Reti | 10000 | Tusani Iosefatu Reti (USD 10,000.00) | Lowest price amongst technically responsive proposal
| Shaun Williams | 23250
| Sam Sesega | 15200
Construction of Tufutafoe Link Road awarded to FICO Construction Ltd 1 November 2015. tender Process. | FICO | 331760 | FICO Construction (USD$331,760.00) | FICO was ranked 1st as the substantial responsive and least cost bid therefore was awarded the contract
| Webster Works & Infrastructure | 343695
| SWEL | 346874
Construction of Mulinuu Access Road awarded to Lucky Construction on 3 December 2015. Tender Process. | Lucky Construction | 153891.1 | Lucky Construction (USD$153,891.10) | Lucky was the only responsive bid with the reasonable cost bid
| Silva Transport Ltd | 148694.26
| Ulia Construction | 149036.25
| Lee Transport | 138950.9
CIMP Team Leader, Competitive Process-Advertisement, 24 June 2016 | Satui Bentin | 125400 | Satui Bentin (USD 125,400.00) | Satui was the most technically responsive and lowest financial and was within the allocated budget.
| Toeolesulusulu Cedric Schuster | 138877.12
| Sapa Saifaleupolu | 105700
| Geoff Dews | 148120
CIMP Ecosystem Specialist, Competitive Process: Advertisement, 15 July 2016 | Peter Smith | 95000 | Tusani Iosefatu Reti (USD 42,665.00) | Tusani was technically responsive and with the lowest financial proposal therefore was awarded this consultancy
| Tusani Iosefatu Reti | 42665
| Cenon Padolina | 74000
| Mark Fenn | 90800
CIMP Resettlement Specialist, competitive process-advertisement, 24 June 2016 | Toeolesulusulu Cedric Schuster | 65000 | Toeolesulusulu Cedric Schuster (USD 65,000) | The selected proposal was the highest technically responsive one and had the lowest financial proposal of USD86,382.90.
| Samuelu Simi Sesega | 119885.75
| Rosemary Faletoese | 94200
MNRE Institutional Review Specilaist, Competitive process- advertisement, 21 July 2016 | Bureieta Leauga | 65000 | Matagialofi Luaiufi (USD 39,600) | The selected bid was the most technically and financially responsive bid
| Sanjay Ektate | 77000
| Matagialofi Luaiufi | 39600
CIMP Civil Engineer, Advertisement, 3rd August 2016 | James Moeono |  | John Townsend (USD 59,290.00) | John was the most responsive bid, both technically and financially.
| John Townsend | 59290
| Thomas Tinai | 150000
| Ian Rowbottom | 117000
CIMP Geomorphologist, Advertisement, 3rd August 2016 | Jonathan McCue | 118000 | GWP Company (USD 68,831.00) | GWP was the most responsive and their bid was within the allocated budget. They bring onboard a team of expertise as well.
| Misko Ivezich | 105600
| Ben Pearson | 132000
| GWP Company | 68831
CIMP Livelihood Specialist, Competitive process-advertisement, | Geoff Dews | 55000 | Geoffrey Dews (USD 55,000.00) | Geoff was the most technically responsive specialist and bid was within the allocated budget.
| Sapa Saifaleupolu | 50000
| Siamomua Malama | 51600
| Frank Fong | 60000
| Atkinson Garth | 65000
CIMP Spatial and DRM Specialist, 14 November 2016 | Vilisi Tokalauvere | 35580 | Vilisi Tokalauvere (USD 35,580.00) | Vilisis bid was financially and technically responsive to the consultancy advertised therefore was awarded this contract.
| Christine Chan | 66000
Peter Gunson
| Valentine Thurairajah | 65900

## Risk Assesment
RISK ASSESMENT
IDENTIFIED RISKS
List all Risks identified in project preparation phase and what steps are being taken to mitigate them
Identified Risk | Current Status | Steps Taken to Mitigate Risk
As this programme is designed to be complementary to the PPCR programme, any delay in that would impact on achieving desired “whole of country” joint project outputs and outcomes and reduce scope to deliver programme as outlined in proposal. | Low | Status considered Low in 2016. Actions taken: As planned, a single firm with two teams were to run the review for PPCR and AF districts simultaneously. The approach was revisited during the world bank mission in November 2015 and therefore agreed to refine the methodology whereby a Team Leader will be recruited instead to manage the work plan of the consultation of all villages, liaise closely with relevant line agencies in identification and evaluation of village level sub-projects, develop a proposal and the required terms of reference for updating the CIM Plans for the respective districts; 16 for PPCR and 25 for AF. The AF CIMP Review Team Leader was successfully recruited in September 2016 followed by the team of Specialist including the Ecosystem Specialist, Livelihood Specialist, Civil Engineer , Spatial and DRM and Geomorphologists. The CIMP review exercise commenced in September with community consultations and ground truthing works and at the end of 2016, 15 districts out of 25 were completed. The remaining 10 districts is envisage to complete by first Quarter 2017. Revised CIM Plans drafts is plan to be available in March 2017
Extreme climatic events and geophysical hazards damage or eradicate programme results, or cause major disturbances resulting in delays due to needed emergency and recovery processes. | Medium | This risk level remains unchanged, as Samoas vulnerability to extreme climatic events has not changed. The Rainfall season or better known as the TC period that we are currently in from the months of October - April. is in line with the defects liability period for some infrastructural interventions of the project including access roads for Mulifanua, Pata and Tufutafoe in Savaii. This has allowed the project to test the capability of the structures to withstand heavy rain and flooding. 15 districts CIMP review have completed within the reporting period with new interventions being identified to improve resilience, any tropical cyclone occurrence will compromise the outcome of CIMP review assessment in the villages/districts. Which may lead to the restart of the process Actions: Disaster Management Office and Meteorology division are the key stakeholders of the Technical Advisory Group given their national mandate on disaster management and weather forecast to regularly provide advice/information. So far this has not been the case and the consultations is already in the last few phases for district consultations.
Poor collaboration between project partners. | Low | Status decreased to Low as greater understanding and coordination within the TAG is being realized. Actions taken: Joint activities with government agencies that are within the scope of the project are enhanced and identified in the agency annual workplan. For instances the review of CIMPs through consultations at the community/district level show active participation/support of project partners (ministries service providers) Independent water scheme for Sili village in Savaii jointly coordinated by the project and the Ministry of Women; Mulifanua, Pata Falelatai and Tufutafoe access roads etc. between the project and the Land Transport Authority; The Manase beach replenishment project between the Samoa Tourisms Authority as examples. Within MNRE, the Project unit is working with GIS/technical services for GIS support work; the Forestry/Environment Division for riparian replanting and coastal replanting etc.
Weak cooperation by villages in proposed districts. | Low | There is a very strong support realized during the CIM Plan review consultations completed for the first 15 districts. This cooperation will be further enhanced through the final CIM Plan sign off by Government and Representatives of the respective villages/districts.
Land disputes amongst village members adversely affecting village relocation land use planning. | Medium | Consultation with communities for the development of the Relocation Strategy and Handbook to capture the necessary processes and procedures, ensure village ownership and minimize disputes. Relocation Strategy and Handbook draft is available and is planned to officially launch by in April 2017.
Limited human resources in Government ministries and agencies to contribute to the activities. | Medium | Involvement of all key government ministries and agencies will be coordinated through the Technical Advisory Group. Two project support staff were recruited in 2014 to assist with project implementation with contracts ending early 2017. These staff contracts will be extended till the life of the project to further assist with implementation. CIMP review TAs have been recruited to deliver the CIMP review with other unavailable expertise in-house be procure through the project .
A series of unusually adverse climatic conditions damage adaptation measures being implemented, or weaken the interest of key stakeholders to addressing adaptation issues. | Low | Continuous monitoring of all adaptation measures will be undertaken to gauge newly implemented infrastructure capability. In addition the Disaster Management Office is working closely with the project team to provide advice on Disaster Risk Reduction options for project activities and CIMP actions identified. This risk has decreased to very low in the MTE report, as programme has taken the proper precaution to implement activities during the no-cyclonic season.
The techniques and technologies developed are not gender sensitive – i.e. they increase inequity between men and women or change the social roles of men and women in a way that reduces self reliance. | Low | The approach taken on board by the project team with engaging communities and stakeholders is to ensure the involvement of all levels of the community including men, women and youth. The climate resilience measures (i.e.) access roads, seawall, upgrade water reticulation systems currently being constructed in the selected villages benefits all level of the community. Specifically on CIMP review the ministry is working closely with the Ministry of Women and Social Development to ensure the active participation of women and youth joining the chiefs in all community consultations and this was evident in consultations
Stakeholders are not able to perceive reductions in vulnerability over the time-scale determined by programme duration; | Medium | A monitoring and evaluation survey at project sites (i.e.) Saleia Revetment wall, Vaiala Seawall & Lona & Maasina water reticulated systems to be conducted in quarter 2, 2017 to facilitate a conclusive rating.
Stakeholders are not able to distinguish vulnerability to climate change from baseline weaknesses in land, coastal, and water resources management. | Low | A monitoring and evaluation survey to be conducted in quarter 2, 2017 to facilitate a conclusive rating.
Critical Risks Affecting Progress (Not identified at project design)
Identify Risks with a 50% or > likelihood of affecting progress of project
Identified Risk | Current Status | Steps Taken to Mitigate Risk
Operational-Delayed Procurement as a result of multiple factors (i.e.) limited or no interest bidder/ Unsuccessful Negotiations/ | low | Procurement of Technical Specialists for the project significantly impacting on the delivery of Outcome 1 of the project (i.e.) recruiting of a CIMP review team. While the recruitment process commences early 2015, the new approach to recruit only the Team Leader was considered in late November 2015 after the negotiation with the only qualified firm failed . The delayed have been picked up in Quarter 4 of 2016 with Team Leader, Ecosystems Specialist, Civil Engineer , Translator, Resettlement/Relocation Specialist and the Livelihood came on board to progress the long delayed CIMP Review activity and Relocation/Resettlement activity.
Risk Measures: Were there any risk mitigation measures employed during the current reporting period? If so, were risks reduced? If not, why were these risks not reduced?
Add any comments relevant to risk mitigation (word limit = 500)
The National Election occurred on March 4 2016. The AWP and 1QWP were designed with due consideration of the care taker period while awaiting the new government formulation. Activities around this period was mainly focus review and monitoring and TA recruitment.

## Rating
RATING ON IMPLEMENTATION PROGRESS
For rating definitions please see bottom of page.
| Progress on Key Milestones |  | Expected Progress |  | Progress to Date | Rating
Project Manager/Coordinator: | Outcome 1: Strengthened awareness and ownership of coastal adaptation and climate risk reduction processes at community and national levels in 25 Districts and 139 villages through gender-sensitive processes
| 1.1. CIM Plans reviewed in 25 districts with climate induced disaster risk management fully integrated, adopting a Watershed and Ridge to Reef Management approach |  | 1. Development of revised CIM Plan template 2. Completed the Review of the CIM Plan Handbook (Nov 2016) 3. Completed 15 Districts/villages CIMP Review workshops. |  | As planned, a single firm with two teams were to run the review for PPCR and AF districts simultaneously. The approach was revisited during the World Bank mission in November 2015 and therefore agreed to refine the methodology whereby a Team Leader and the team of specialists comprised of Ecosystem Specialist, Livelihood Specialist, Civil Engineer, Spatial Risk and Disaster Risk Management Specialist will be recruited instead to manage the work plan of the consultation of all villages, liaise closely with relevant line agencies in identification and evaluation of village level sub-projects, develop a proposal and the required terms of reference for updating the CIM Plans for the respective districts; 16 for PPCR and 25 for AF. Five(5) of the six(6) key Technical Specialists to progress the review of CIMPs have signed contracts through the LOA with UNDP and have undertaken the CIMP review exercise in the last two quarters of 2016. The Spatial Risk and Disaster Risk Management Specialist position is undergoing recruitment process aiming to officially start in the first quarter of 2017. At the end of the reporting period, 16 districts have completed their CIMP review with the draft CIMPs scheduled to be ready in March 2017. Districts covered in CIMP Review in 2016 include: Satupaitea, Gagaemauga 2,Gagaemauga 3,Gagaifomauga 1,Gagaifomauga 2,Vaisigano 1,Vaisigano 2,Alataua West,Itumalo Salega,Palauli le Falefa Faasaleleaga 1,Faasaleleaga 2,Faasaleleaga 3,Faasalelaga 4,Aiga i le Tai Consultation Participants breakdown of roughly 60% men (including the youth) & 40% women The CIMP Review exercise is guided by Revised CIM Plan Handbook. Community/consultations programs comprised of presentation on Program Background covering the CC & DRM and CIMP review process followed by groups discussions and presentations. After each consultations a site visit is conducted into each village to verify issues discussed in working groups. | Satisfactory
| 1.2. Village hazard zone relocation plans formulated at least 15 villages in selected districts |  | 1. Development of selection criteria for villages to be relocated completed 2. Completed the National Relocation Strategy and Relocation Handbook. Draft available 3. Consultations with selected villages completed (Group 1- 5) |  | The Resettlement Specialist commenced work on the 1st August 2016. Selection criteria have been developed to guide the selection of the most vulnerable villages qualify for relocation planning. The draft Relocation Strategy and Handbook is available with Village Hazard Relocation (VHZR) Plans aiming to start for 15 villages in the first quarter of 2017. It is envisage that the VHZR Plans for the 15 villages will be in place by June 2017. | Satisfactory
| 1.3. Training delivered to 300 village leaders in 139 villages on review of CIM Plans and relocation planning process integrating climate risks. |  | 1. Preliminary Sui o le Nuu briefing – Year 1 2. Village consultation workshop on CIMP Review and Relocation Plans Development |  | 2 Initial Workshops held in Upolu and Savaii in February and March 2014 involved approx. 250 village leaders from 25 districts - Sui o Nuu (village major), Sui Tamaitai o Nuu (Women Group Rep). With the commencement of CIM Plan Review program in third quarter of 2016 for AF districts, we envisage continual involvement of communities as the review moves from districts to district till July 2017. In addition further direct trainings will be conducted through the roll out in 2017 to conducted by Technical Specialists on specific fields targeting groups (i.e.) farmers association on Climate Change Community based adaptation in Agriculture Sector, April 2017 , 2) Government Staff and local Engineers on potential topic Basic Principles of Cost Benefit Analysis, March 2017etc. Forestry Division of MNRE will also carry out trainings on Riparian planting through the 2 million tree campaign resourced by the AF project | Marginally Satisfactory
Outcome 2: Increased adaptive capacity of coastal communities to adapt to coastal hazards and risks induced by climate change in 25 Districts and 139 villages
| 2.1. Climate proofing measures implemented on coastal roads and related infrastructure in at least 10 districts and 40 villages |  | 1. Review of CIM Plans Project database to specify roading projects. 2. Procurement of design consultant. 3. Preparation of site-specific designs and cost estimates for selected projects. 4. Implementation Year 1 projects - 10 villages. |  | The CIM Plan Database has been updated upon completion of the CIM Plan Implementation status. Other intervention works were progressed given priority in current CIM Plan and other related plans. For instance; 1.4km of access road for Fusi Saoluafata has completed. The implementation of works for the identified zones in the drainage program for key vulnerable areas i.e. Zone 5 (Matautu to Afiamalu - 10 villages ) of 11.552 km at a contract price of ST 160,918.70 and zone 6 (Moataa to Laulii - 5 villages) of 16.784 km at a contract price of SAT 221,332.45 was completed in October 2015. The work was retendered for another 12 months and contracts were completed in October 2016. | Satisfactory
| 2.2. Shoreline protection measures implemented in at least 10 districts and 40 villages. |  | 1. Review of CIM Plans Project database to specify shoreline protection measures projects. 2. Procurement of design consultant. 3. Preparation of site-specific designs and cost estimates for selected projects. 4. Implementation Year 1 projects - 10 villages. 5. Tree planting at Water Catchment Areas and forestry through MNRE Forestry Division and the Water Resources Division completed for 3 areas (2 Upolu and 1 in Savaii) |  | The CIM Plan Database was updated upon completion of the CIM Plan Implementation status. The Vaiala Seawall (520m) was completed and launch in December 2015. The Saleia Rock Wall (765m) was completed in May 2016. The design and supervision services for the 2 sites was contracted to Tinai Gordon and Associates at a Contract Price of SAT$186,000.00. The implementation of access roads through the Lands Transport Authority for the Fusi access road has completed with three others (Pata, Mulifanua and Tufutafoe) completed during the first quarter of 2016. The Beach replenishment project services at Manase was successfully completed and launched 13 December 2016. 3 Catchment areas have been replanted through MNRE Forestry Division and Water Resource Division as part of the 2 million tree campaign to protect our water resources and infrastructure. | Satisfactory
| 2.3 Water supply enhanced in least 5 districts and 15 villages. |  | 1. Review of CIM Plans Project database to specify Water supply enhancement projects. 2. Procurement of design consultant. 3. Preparation of site-specific and cost estimates for selected projects. 4. Implementation Year 1 projects – 3villages. |  | The community water supply enhancement projects in Ma’asina , Lona and Lele’a has completed in August 2015. Bluebird Construction Limited has been awarded the contract for a total Contract Price of SAT$833,023.82, inclusive of taxation. All 3 villages or 544 people (based on 2011 Population Census) will have access to the water project. One project has been approved for Sili, on the island of Savaii, for 2016. | Satisfactory
| 2.4 Flood protection measures are implemented in at least 5 districts and 15 villages |  | 1. Review of CIM Plans Project database to identify candidate flood protection measures projects. 2. Procurement of design consultant. 3. Preparation of preliminary designs and cost estimates for selected projects. 4. Implementation Year 1 projects –3 villages. |  | A flood study for the Vaisigano Catchment that was conducted under the project will inform required intervention during the CIM Plan Review. Under EWACC (Economy Wide Approach Climate Change financed by the LDCF) is resourcing similar studies in other watershed areas within AF districts. Note efforts under 2.1 where drainages are being cleared to avoid flooding. | Marginally Satisfactorily
Outcome 3: Strengthened institutional capacity of government sectors to integrate climate and disaster risk and resilience into coastal management-related policy frameworks, processes and responses.
| 3.1. Revised national organization and institutional structures for CIM Plans implementation. |  | 1. Review current organizations and structures. 2. Develop revised arrangements and suggested method of implementation. 3. Prepare MOU’s for agreement between key partners. |  | MNRE PUMA has completed its institutional review which informs CIMP implementation structure and also the ministry operational matters. A TA was hired to look into restructuring and institutionalizing of the CIM Plans at all levels including division, ministry and sector level. Institutional Review Report now available | Satisfactory
| 3.2 Village relocation handbook prepared to guide further relocation planning activities. |  | 1. Preparation of draft Village Relocation Strategy and Handbook. 2. Consultation with key stakeholders and Sui o le Nuu briefings. 3. Finalized Village Hazard Zone Relocation Handbook and Plans |  | TA was successfully recruited in August to prepare the VRH and draft is now available and is undergoing consolidation | Satisfactory
| 3.3 Regulatory procedures for physical works implementation revised with climate change risks integrated. |  | 1. Review of contracts and procurement procedures. 2. Preparation of revised procurement manual and design guidelines for adaptation works incorporating CCA and DRM components. |  | The review of road standards with climate change risks integrated successfully completed by Isikuki Punivalu and Associates through Ministry of Works Transport and Infrastructure in the last quarter of 2016. | Marginally Satisfactory
| 3.4 Policymakers and technical officers in the relevant Ministries and Authorities are trained on climate risk assessment and planning processes for coastal adaptation. |  | 1. Conduct introductory workshop and training needs analysis. 2. Develop training plan and materials. 3. Training Workshops – Year 1. |  | With the CIM Plan Review now cleared for implementation, supporting workshops for policy makers and technical officers from other ministries who will be involved through the TAG on climate risk assessment and planning processes for coastal adaptation will be organized and conducted. | Marginally Satisfactory
| 3.5 Adaptation lessons learned and best practices generated through the adaptation implementation and related policy processes are captured and disseminated nationally and globally through appropriate mechanisms |  | 1. Develop programme communications strategy and plan. 2. Prepare and operationalize web site material. 3. Prepare and publish programme communications. 4. Prepare material for Environment Week – Year 1. |  | Website has been prepared through UNDP assistance as agreed due to capacity constraints in MNRE IT division, project information has been disseminated at Environment week, Information boards have also been produced for all project sites and project information disseminated during project launch | Marginally satisfactory
[5 empty] | Overall Rating | Satisfactory
Please Provide the Name and Contact information of person(s) responsible for completing the Rating section
| Name: | Fetoloai Y Alama (ACEO PUMA/Project Assistant Director)
| Email: | fetoloai.alama@mnre.gov.ws
Please justify your rating. Outline the positive and negative progress made by the project since it started. Provide specific recommendations for next steps. . (word limit=500)
The overall rating is Satisfactory for the 2016 considering the amount of activities conducted and picked up as per the 2016 MTE rating. This is particularly Outcome 1 and 3 where critical activities CIMP Review Specialist Recruitment, CIMP Review with 15 districts (80 villages) completed, Available Institutional Review report and Draft Relocation Strategy & Handbook, Small Grants MOU signed and funds transferred. Such progress is also reflected in the expenditure delivery to date. It is envisage that by the end of 2017, all the ongoing activities will be completed and wrapped up.
| Progress on Key Milestones |  | Expected Progress |  | Progress to Date | Rating
Implementing Agency | Outcome 1: Strengthened awareness and ownership of coastal adaptation and climate risk reduction processes at community and national levels in 25 Districts and 139 villages through gender-sensitive processes
| 1.1. CIM Plans reviewed in 25 districts with climate induced disaster risk management fully integrated, adopting a Watershed and Ridge to Reef Management approach |  | 1. Development of revised CIM Plan template 2. Review of flood protection requirements 3. Preparation of revised IAMP 1 districts CIM Plans 4. Preparation of revised IAMP 1 districts CIM Plans 5. Coastal Infrastructure Management Strategy 2006 reviewed and updated |  | In 2015, the inventory of the status of CIM Plans implementation to date has been completed and as well as the review of the CIM Plan Strategy. With regards to the CIMP Plan review, AF project have completed the recruitment of the consultants and they consist of a Team Leader, Ecosystem Specialist, Civil Engineer, Livelihood Specialist, Geomorphologist and Spatial and DRM Specialist. To date, they have completed CIMP consultations in 22 districts out of a total of 25 districts, the remaining will be completed at the beginning of April 2017. The team leader of AF CIMPs and PPCR CIMPs have met and have agreed on a similar template to make sure the CIMPs will have a similar layout. The template is now finalized and the team leader is working to insert all technical inputs into the final CIMPs before taking them back to the districts for signatures and launching, this will be completed in 2017. The TL for the CIMP during this period had a brief training with a UNDP Gender Specialist on how to report Gender involvement and inclusion in the CIMP review process. | Satisfactory
| 1.2. Village hazard zone relocation plans formulated at least 15 villages in selected districts |  | 1. Development of selection criteria 2. Village consultations 3. Preparation of Village Hazard Zone Relocation Plans – Group 1 – 5 villages 4. Preparation of Village Hazard Zone Relocation Plans – Group 2 – 5 villages |  | The Resettlement Specialist was recruited in August to develop the village hazard zone relocation plans for 15 villages as well as the village relocation handbook. The villages selected includes Falealupo, Neiafu, Sataua, Vaisala, Lefagaoalii, Lani Fagamalo, Satupaitea, Satuimalufilufi, Sauano/Saletele, Faleapuna, Vaiala, Salua, Apolima-Uta and Matautu (Vaisigano). He has completed village consultations in Saleia/Vaipouli, Lefagaoalii, Vaisala, Neiafu, Falealupo as well as representatives from the government, civil society and private sector. The VHZR Plans have been drafted after village consultations in December. The resettlement specialist have already completed a draft relocation strategy as well as the handbook. The 15 village plans will be completed and launched in 2017. | Marginally Satisfactory
| 1.3. Training delivered to 300 village leaders in 139 villages on review of CIM Plans and relocation planning process integrating climate risks. |  | 1. Preliminary Sui o le Nuu briefing – Year 1 2. Preliminary Sui o le Nuu briefing – Year 2 3. Preliminary Sui o le Nuu briefing - Year 3 & 4 4. Develop training materials and translate |  | The CIMP Review to date has completed consultations with 22 districts where the CIMP team and relevant lead agencies had the opportunity to exchange and discuss Climate Change issues and possible interventions. CIMP team has delivered training to 426 village leaders (40% (307) women and 60% (524) men) from 146 villages during the CIMP consultations. All the consultation materials was developed and translated to Samoan by the CIMP Team Leader. The relocation specialist has also completed consultation in 5 villages in Savaii (Neiafu, Falealupo, Vaisala, Lefagaoalii and Saleia). AF uses the Community Engagement Plan (CEP) prepared under PPR. The CEP considers these trainings done during CIMP consultations as part of the review. | Highly Satisfactory
Outcome 2: Increased adaptive capacity of coastal communities to adapt to coastal hazards and risks induced by climate change in 25 Districts and 139 villages
| 2.1. Climate proofing measures implemented on coastal roads and related infrastructure in at least 10 districts and 40 villages |  | 1. Review of CIM Plans Project database to specify roading projects. 2. Procurement of design consultant. 3. Preparation of site-specific designs and cost estimates for selected projects. 4. Implementation Year 1 projects - 10 villages. |  | This project target of 80km access road was reduced by 40% at the MTE stage. At this point in the project, they have completed climate proofing a total of 12.735km of coastal road and infrastructure. • Vaiala Seawall – 520m • Saleia Rockwall – 765m • Mulinuu heritage road – 420m • Pata Falelatai – 2.2km • Mulifanua – 1.55km • Tufutafoe- 5.88km As for the drainage programme, this is divided into two zones. • Zone 5 (Matautu-Afiamalu, 10villages) – 11.522km • Zone 5(Moata’a-Laulii, 5 villages) – 16.784km Thus, making the total coverage so far to 41.041km. LTA have proposed the completion of the Fusi Road (1.4km) that was damaged during Cyclone Evan and the TAG have approved this for 2017. The TAG have approved roads to be carried out in 2017 and the CIMP TL through the CIMP Prioritization list recommended one, which is Neiafu Road in Savaii unfortunately due to the limited funds available under this output. They have agreed to complete the following in 2017: 1. Safata (Sauniatu, Manunu , Solaua)- 4km 2. Salelologa Township (Maota and Foua Road) 3. Fusi Road – 1.4km A TA recruited to review road design and construction standards for climate resilience and disaster risk management under Ministry of Works Transport and Infrastructure was also completed in this PPR period. | Satisfactory
| 2.2. Shoreline protection measures implemented in at least 10 districts and 40 villages. |  | 1. Review of CIM Plans Project database to specify shoreline protection measures projects. 2. Procurement of design consultant. 3. Preparation of site-specific designs and cost estimates for selected projects. 4. Implementation Year 1 projects - 10 villages. 5. Tree planting at Water Catchment Areas and forestry through MNRE Forestry Division and the Water Resources Division completed for 3 areas (2 Upolu and 1 in Savaii) |  | In the MTE report, this target was considered ambitious and recommended to be in line with the activities of the line ministries or be reduced by 30%. The CIMP Consultation is ongoing at the moment. The TA recruited for the CIMP to provide the technical advice on relevant shoreline protection measures have produced a matrix for the TL to incorporate in the revised CIMPs. This will also feed into the CIMP database. The Project launched the completion of the Saleia River Embankment wall (765m) and bridge in July 2016. The Beach replenishment and breakwater along 170m of eastern Manase Beach (Savaii) project in Manase was completed and launched in December 2016 as well. This is a project that was co-financed with LDCF-ICCRITS project. These two is an additional shoreline protection to the already completed Vaiala Seawall (520m). The project supports the one million-tree campaign via the Forestry Division that looks at the rehabilitation of riparian areas and will cover 209 villages (Upolu) and 105 villages (Savaii). | Marginally Satisfactory
| 2.3 Water supply enhanced in least 5 districts and 15 villages. |  | 1. Review of CIM Plans Project database to specify Water supply enhancement projects. 2. Procurement of design consultant. 3. Preparation of site-specific and cost estimates for selected projects. 4. Implementation Year 1 projects – 3villages. 5. Implementation Year 2 projects – 3villages |  | The rehabilitation and upgrade of Independent Water Scheme in Ma’asina , Lona and Lele’a were completed in 2015 (544 inhabitants). The implementation of the water supply enhancement project for Sili (500 inhabitants)was completed in 2016 and is planned to be launched in 2017. The project target was to improve water supply for 9,000 inhabitants in 15 villages and so far only 4 villages with a population of close to 1000 is supported. This target can be improved via small grants projects. | Marginally Satisfactory
| 2.4 Flood protection measures are implemented in at least 5 districts and 15 villages |  | 1. Review of CIM Plans Project database to identify candidate flood protection measures projects. 2. Procurement of design consultant. 3. Preparation of preliminary designs and cost estimates for selected projects. 4. Implementation Year 1 projects –3 villages. 5. Implementation Year 2 projects – 3 villages |  | The flood study for the Vaisigano Catchment was completed under the EWACC project. The Saleia Embankment wall that was also launched under 2.2 will protect the village from river flooding the village but will divert it instead towards the sea. In addition, under 2.1 is the drainage programme that clears the drains. The CIMP team have onboard a company that specializes in geomorphology and hydrology work. They will be producing flood studies in the 25 districts of AF. They will put together a matrix indicating areas prone to flooding and what measures to put in place. A prioritization list from the TL as a result of the CIMPs Review will feed into the review of Small Grants proposals. | Marginally Satisfactory
Outcome 3: Strengthened institutional capacity of government sectors to integrate climate and disaster risk and resilience into coastal management-related policy frameworks, processes and responses.
| 3.1. Revised national organization and institutional structures for CIM Plans implementation. |  | 1. Review current organizations and structures. 2. Develop revised arrangements and suggested method of implementation. 3. Prepare MOU’s for agreement between key partners. |  | An Institutional Strengthening Specialist was hired in 2016 to conduct the institutional review for MNRE and identify how the CIMPs will be integrated across the government sectors. The specialist have produced the MNRE Functional Review Report noting inter alia institutional capacity constraints, including the SWOT outcome and Matrix Laws/Regulations/Conventions and Policies, A proposed Model for restructure identifying institutional development options, Restructure Implementation Plan including resource requirements assessed ( Infrastructure, funding, staffing) and clear recommendations for roles and responsibilities of the appropriate institution and line ministries in charge of CIM Plans implementation and suggested timeline for implementation. To work will be fully realized and completed in Q1 2017. | Highly Satisfactory
| 3.2 Village relocation handbook prepared to guide further relocation planning activities. |  | 1. Preparation of draft Village Relocation Handbook. 2. Consultation with key stakeholders and Sui o le Nuu briefings. 3. Finalized Village Hazard Zone Relocation Handbook |  | A TA was recruited in 2016 to produce the village relocation handbook. A draft relocation handbook is now available and is planned to be finalized in Q2 2017. Consultations for the handbook took place in December and the 5 villages the selected by the Ministry to pilot this in is Falealupo, Neiafu, Lefagaoalii, Saleia and Vaisala. | Marginally Satisfactory
| 3.3 Regulatory procedures for physical works implementation revised with climate change risks integrated. |  | 1. Review of contracts and procurement procedures. 2. Preparation of revised procurement manual and design guidelines for adaptation works incorporating CCA and DRM components. |  | This activity is coordinated with MWTI to conduct the review of road standards for resilience from climate change and natural disaster. The PPCR is developing a strategy to look at Road Network Vulnerability from Climate Change and the review of the road standards is a critical element of this strategy. The outcome of the revised and developed standards will allow MWTI through an asset management and quality assurance system to monitor the technical delivery and cost effectiveness of national service provider delivery of road infrastructural works. The current CIMP Review also looks to incorporate and mainstream CC and DRM across the government sectors. | Marginally Satisfactory
| 3.4 Policymakers and technical officers in the relevant Ministries and Authorities are trained on climate risk assessment and planning processes for coastal adaptation. |  | 1. Conduct introductory workshop and training needs analysis. 2. Develop training plan and materials. 3. Training Workshops – Year 1. 4. Training Workshops - Year 2 5. Training Workshops - Year 3&4 |  | The activity ties with the institutional review, as it will broaden the knowledge of policy makers and technical officers on the CIM Plans, the risk assessment and planning processes that it is promoting. In addition, The CIMP Review specialists provides training on site (for the geomorphologist) and off-site for the technical officers from the different sectors of government involved in the review. The project target is to train at least 100 policymakers by projects end and with the institutional workshop completed with more that 100 staff consulted about the CIMPs it has exceeded this target especially with the CIMP specialists also giving training. | Satisfactory
| 3.5 Adaptation lessons learned and best practices generated through the adaptation implementation and related policy processes are captured and disseminated nationally and globally through appropriate mechanisms |  | 1. Develop programme communications strategy and plan. 2. Prepare and operationalize web site material. 3. Prepare and publish programme communications. 4. Prepare material for Environment Week – Year 1. 5. Prepare materials for Environment Week - Year 2 |  | The project have not yet developed a communication strategy, this is still pending. The Project has a Facebook Page a twitter account to disseminate its project stories. Some interventions have been showcased in newspapers as well as in the MNRE newly launched website and In 2016 the project posted stories on the 1st CIMP Consultation, Saleia embankment and bridge opening as well as the Manase Beach Replenishment, the one million tree campaign. The project plans to develop an information booklet on the new species the Ecosystem Specialist discovered during the site visits for the CIMP consultations. | Marginally Satisfactory
[5 empty] | Overall Rating | Satisfactory
Please Provide the Name and Contact information of person(s) responsible for completing the Rating section
| Name: | Tessa Tafua / Reis Lopez Rello
| Email: | tessa.tafua@undp org / reis.lopez.rello@undp.org
| Please justify your rating and address the following points: 1. Indicate trends, both positive and negative, in achievement of outcomes as per the project indicators. 2. Detail critical risks that have affected progress. 3. Outline response to MTR undertaken this reporting period. 4. Outline action plan to address projects with a rating of HU, U or MU. Please keep your input to 1200 words |  | During the reporting period the project has focused on finalizing the CIM Plan review for the 25 target districts, the rest (16 districts) are being reviewed by the WB PPCR project, although both team leaders are coordinating efforts to have same templates that would allow information to be aggregated and analyzed at a national level when finalized. To date, 22 districts have reviewed its CIM Plans with AF resources through consultations and workshops with village leaders, women and youth and their feedback has been included to reflect a set of initial site-specific interventions under each CIMPs. To pave the way for CIM Plans implementation, the project’s staff has started to revise arrangements and suggested methods of implementation based on the current legal framework (laws, regulations, conventions and policies relevant to the CIMs) In addition, the project has completed climate proofing a total of 12.735km of coastal road and infrastructure and 28 km of drainage have been made functional again, overall vital interventions for economic and shelter purposes in a country that is heavily affected by cyclones heavy rains and floods. Some shortcomings are related to the water supply enhancement interventions as the project target was to improve water supply for 9,000 inhabitants in 15 villages and so far only 4 villages with a population of close to 1000 is supported. PMU and Steering committee are trying to use the Small Grants projects under this project through the Civil Society Support Programme (CSSP) to increase the water-related support to target villages. The next and last reporting period, project has a great challenge ahead to finalize all ongoing activities, to cover as much as possible all targets agreed during MTR, to synthesize results based on the terminal evaluation and to showcase these results and best practices at national and international fora through diverse media channels and knowledge products.
Rating Definitions
|  |  | Highly Satisfactory (HS) | Project actions/activities planned for current reporting period are progressing on track or exceeding expectations to achieve all major outcomes/outputs for given reporting period, without major shortcomings. The project can be presented as “good practice”.
|  |  | Satisfactory (S) | Project actions/activities planned for current reporting period are progressing on track to achieve most of its major outcomes/outputs with only minor shortcomings.
|  |  | Marginally Satisfactory (MS) | Project actions/activities planned for current reporting period are progressing on track to achieve most major relevant outcomes/outputs, but with either significant shortcomings or modest overall relevance.
|  |  | Marginally Unsatisfactory (MU) | Project actions/activities planned for current reporting period are not progressing on track to achieve major outcomes/outputs with major shortcomings or is expected to achieve only some of its major outcomes/outputs.
|  |  | Unsatisfactory (U) | Project actions/activities planned for current reporting period are not progressing on track to achieve most of its major outcomes/outputs.
|  |  | Highly Unsatisfactory (U) | Project actions/activities planned for current reporting period are not on track and shows that it is failing to achieve, and is not expected to achieve, any of its outcomes/outputs.

## Project Indicators
PROJECT Indicators
Please provide all indicators being tracked for the project as outlined in the project document
Type of Indicator (indicators towards Objectives, Outcomes, etc.…)
Type of Indicator | Indicator | Baseline | Progress since inception | Target for Project End
Objective: Strengthened ability of coastal communities to make informed decisions about climate-change induced hazards and undertake concrete adaptation actions | Number of risk-exposed coastal communities protected through coastal adaptation measures based on climate-sensitive Community integrated management Plans (CIMP) | In the lack of systematic implementation of CIM Plans, the target villages and districts are highly exposed to climate-induced hazards | At the end of the reporting period, 22 districts (out of 25) have completed their CIMP review with the draft CIMPs scheduled to be ready in March 2017. In each CIMPs review, relevant stakeholders like leaders from target villages, women and youth have been involved in workshops and their feedback has been included to reflect a set of initial site-specific interventions under each CIMPs. | By the end of the programme 139 villages in 25 districts are protected from climate-induced risks as a result of coastal adaptation measures implemented guided by revised CIM Plans.
Outcome 1: Strengthen awareness and ownership of coastal adaptation and climate risk reduction processes at community and national levels in 25 districts and 139 villages through Gender-sensitive processes | Number of districts covered by review and updated CIM Plans with climate change risks fully integrated | The 6 CIM Plans prepared under IAMP 1 have no DRM component. The 19 CIM Plans prepared under SIAM 2 require review | Completed 15 districts CIMP Review workshops/Consultations/Ground Truthing with communities in the reporting period. The CIM Plan Review commenced in September 2016 with the DRM component now included. CIMP Review workshops with target districts are expected to complete in April 2017. | By the end of year one at least 8, year two 18 and by the completion of the programme at least 25 districts will have their CIM Plans reviewed and updated with climate change risks fully integrated through balanced involvement of man, women, and youth population.
| Number of districts with village hazards zone relocation plans completed. | There are currently no village relocation plans available to guide relocation activities for households to move out rom coastal hazard zones. | The National Relocation Strategy and Handbook have been developed to facilitate relocation of the identified vulnerable communities. A selection criteria has been developed to guide relocation planning for 15 vulnerable villages. | By the end of year one 5, year two 10 and by the completion of the programme at least 15 districts will have at least one village hazard zone relocation plan completed through balanced involvement of man, women and youth population.
| Number of community representatives trained on coastal risk assessment and adaptation and numbers of individuals engaged in those sessions. | Currently, there has been no training for village leaders in coastal adaptation and climate reduction processes including village relocation planning. | Over 16 districts (70 villages, 164 participants) have completed their CIMP review through consultations and workshops have been enlightened of Climate Change, Risks and prompt of appropriate adaptation measures to aid understanding on CIMP review exercise | By the end of the project at least 300 village representatives (including matais, women and youth groups) trained (year 1-50, year 2-100, year 3-200) involving traditional leaders, women and youth representatives.
Outcome 2: Increased adaptive capacity of coastal communities to adapt to coastal hazards and risks induces by climate in 25 Districts and 139 villages. | Km of coastal roads and related infrastructure improved to withstand climate change and variability-induced stress | There has been road reconstructions and upgrading undertaken in response to past hazards, such as the 2009 tsunami but without integrating systematically climate change related risks in the process. | Four (4) access roads at a total length of 7.35km will all be completed by Quarter 1 of 2016. Additional access roads have been earmark in the 2017 AWP (approx. 6kms in total) to aid achieving 40km target (target has been reduced down to 40km). With the reduction to the target by 50%, the allocated budget for this activity is still insufficient in meeting the 40km target. | By the end of the programme at least 80km of coastal roads and related infrastructure is improved to withstand climate change and variability-induced stress.
| Km of coastline with climate resilient shoreline and flood protection measures introduced, including vegetation planting along the coast and riparian streams and beach replenishment. | There are only a few villages where shoreline adaptation measures have been introduced through the PACC and CBDAMPIC projects, but only in a pilot fashion. | The Vaiala Seawall (520m) was completed and launch in December 2015. The Saleia Rock Wall (1km) completed in June 2016. 3 Catchment areas have been replanted through MNRE Forestry Division and Water Resource Division as part of the 2 million tree campaign to protect our water resources and infrastructure. Replanting coverage equivalent to 3 hectares. | By the completion of the programme climate resilient shoreline and flood protection measures are introduced in at least 140km coastline and riparian streams, including vegetation planting in at least 60km coast and 50km of riparian streams, and beach replenishment techniques applied in at least 2 sites and 10 km coastline.
| Number of population and communities accessing improved water sector services and infrastructure to manage impacts on water supply induced by climate change and variability. | The target villages lack robust water supply system to withstand climate-induced impacts in water supply. | Population of 544 people from the 3 villages, Ma'asina, Lona and Lele'a is benefitting from the water enhancement projects. The Sili water enhancement project was completed in August 2016 for Sili village in the island of Savaii. Total number of beneficiaries (500 as per Census) | By the end of the programmes at least 9,000 inhabitants in 15 villages have their water supply and associated infrastructure improved to manage climate-induced impacts of water supply.
| Perception of coastal communities on changes in climate-induced risks as a result of interventions. | Low perception of communities relative to climate induced risks | Expecting high community involvement during the CIM Plan Review to start in 2016. | By the end of the project at least 80% of the coastal communities involved perceive risk reduction to climate-induced hazards.
| Number of watersheds with integrated flood risk management measures implemented | Improved drainage and reduced flooding by the end of programme. | A flood study for the Vaisigano Catchment in Apia has been conducted. Other catchment areas are being looked at under other projects i.e. LDCF and EWACC | Integrated flood-risk management plans/measures implemented in at least 10 watersheds/ 80 Km of waterways, involving at least 15 of villages.
Outcome 3: Strengthened institutional capacity of government sectors to integrate climate and disaster risk and resilient into coastal management related policy frameworks, processes and responses. | Revised national organization and institutional structures to implement CIM Plans. | There is currently no organization specifically identified to coordinate the implementation of CIM Plan recommended works at the village and district level. | Institutional review by government is ongoing. The project is intended to implement findings i.e. Streamlining CIM Plans in the proposed structure around the 2nd quarter 2016 | A revised CIM Plan management institutional structure is set up by the end of year one of the project.
| A blueprint established and tested for village relocation processes. | There are currently no guidelines or procedures in place as to how to undertake village relocations in Samoa. | A TA has been recruited to develop the relocation handbook. Handbook now available and is schedule to be tested in one of the selected villages | A complete and operationally tested village relocation handbook is developed by the end of the project to guide future relocation planning exercises.
| Improved regulatory procedures for physical works implementation with climate change and disaster risk considerations incorporated. | Current regulatory procedures for physical works are incomplete and do not have consistent references to either climate change or disaster risk considerations incorporated. | Related activities are the (1) Review of the PUMA Act; (2) Development of road standard integrating climate change risk | Revised regulatory procedures for CIM Plan works is prepared by the end of the year 3 of the programme.
| Number of policymakers and technical officers trained on climate risk assessment and planning processes for coastal adaptation. | Policymakers and technical officers have low to moderate levels of understanding of climate risk assessment and planning processes fir coastal adaptation. | Training is schedule to be part of the CIM Plan review process now schedule for second quarter 2017. | By the end of the Programme at least 100 policymakers and technical officers exhibit improved levels of understanding of climate risk assessment and planning processes for coastal adaptation.
| Number of knowledge management product and South-South exchange events carried out. | Absence of a communication strategy and lack of information management system to support adaptation of coastal villages and districts to climate change risks. | MNRE has established a Data and Knowledge Base Management Facility and the project will utilize it to exchange project products and experience. AF Project Facebook page is regularly maintained | By the end of the programme a communication strategy is developed and information and lessons learnt are compiled and disseminated to local, regional and international stakeholders through at least 4 different mediums. By the end of Year 1 the project web site is operational and not fewer than 5 project communications have been published. By the end of Year 2 not fewer than 10 further project communications have been published.

## Lessons Learned
QUALITATIVE MEASURES and LESSONS LEARNED
Please complete the following section every reporting period
Implementation and Adaptive Management | Response
What implementation issues/lessons, either positive or negative, affected progress? | The CIMP Review Methodology and TA recruitment coordination Finalizing a standard CIMP Review approach together with the coordination of TAs was one of the critical issues faced. MNRE intends to coordinate and align as much as possible the AF to PPCR WB to alleviate inconsistencies not only with the review methodology and also the timely availability of TAs required. The PMU that manages the two projects, has taken more time than anticipated to finalize approach to facilitate implementation of component one of the project. One of the issues that delayed the implementation of the CIMPs in Outcome 1 was due to the delay in the recruitment process for the CIMPs consultants that came onboard in Q3 and 4 this reporting period. The Project requested UNDP to assist the project through the LoA to recruit the consultants for the CIMPs. Six of the consultants were all recruited in 2016 with one remaining to be complete evaluation in Q1 2017. One of the issues encountered by the consultants is accessing the relevant data required for the work such as LiDAR data; this resulted in the delay of the Geomorphologist work. This was resolved by agreeing to bring the consultants in country to work and access the data directly. Project Management Services The Project Management Services (KVA Consult) funded by World Bank through the Ministry of Finance, primarily to provide the management support for both the AF and PPCR project has been suspended for the AF project in the early quarter 3 of 2016, Particularly on the key services of financial management and administrative support. These support services were very critical then for AF project considering the available capacity of AF support staff. The World Bank was concerned with the unbalance time input of the KVA on the two projects in that AF utilizes the majority of the contractual financial share which may compromise the quality of PPCR expected results. MNRE resolved by engaging the Principal Strategic Planning Officer and the AF Education and Awareness Officer to carry out the abolished roles as expected of the PMU. This transition took place directly in early 3rd quarter of 2016. Another issue encountered during this period is the lack of human resources under the project to provide necessary support to the consultants recruited for the CIMPs and the Relocation and resettlement consultancy. The issue is having the time to respond and review the reports provided by the consultants and coordinating the teams to accompany the consultants in the field. The Team Leader for the CIMPs took the lead in the coordination for the CIMPs and the PMU assigned staff from PUMA-MNRE to assist the work of the CIMPs and Relocation strategy overall. Lesson learnt from this is to ensure the project recruits a Project Manager and relevant project staff for future projects to ensure the project activities flows and the permanent staff under PUMA-MNRE time is not exhausted by the project especially if they have to oversee both Adaptation Fund Project as well as the WB-Funded PPCR project.
Were there any delays in implementation? If so, include any causes of delays. What measures have been taken to reduce delays? | With a steady improvement in delivery witnessed in 2016, Government is comfortable that this progress will continue in 2017, especially for the CIM Plan Review, Relocation Plan Development for 15 villages, Institutional review and the implementation of the Small Grant Scheme at village level. Other includes; A) The Technical Advisory Group (TAG) has met 4 times in 2016 facilitating the implementation of related project activities with respective agencies; DMO, WRD, PUMA, LTA, MWCSD, MWTI, CSSP. B) Access to LiDAR Data was a challenge at the start for the CIMP consultants and discussion and directive from the CEO MNRE allowed the release of the data for the CIMP Activities. C) To facilitate progress, key procurements will continue to be handled through UNDP as per the LoA. A communications Specialist will need to be recruited in 2017 to assist with the Communications Strategy. Small Project Implementation. The small project implementation faced significant delays for various reasons including delay in the finalization of the draft MOU between the key parties (MOF, MNRE & CSSP) to expedite the roll out of the Small Projects program for 25 AF district(139 villages). The key decision making staff of the ministries involved were tie up in other commitment but were managed to finalize the draft MOU and was signed in November 28th 2016 with the AF project support officer at CSSP office being recruited in January 2017. The inception workshop and the call for proposal for Savaii island will take place in April 2017.
Describe any changes undertaken to improve results on the ground or any changes made to project outputs (i.e. changes to project design) | The Adaptation Fund Board has considered and has decided to approve the extension of the programme completion date from 1 May 2016 to 1 November 2017.
How have gender considerations been taken into consideration during the reporting period? What have been the lessons learned as a consequence of inclusion of such considerations on project performance or impacts? | The inclusion of all levels of the community in consultations such as the CIMP review have been very successful particularly for the women's group, This is believed to be the result of both the government initiatives through the Ministry of Women, Community and Social Development and Civil Society organizations in promoting the invaluable role of women in communities. The involvement of women in meetings in all outcomes of the project provides education to women and also improves their status and recognition in villages through their development initiatives (i.e.) handicrafts, vegetable gardens and at the same time encourages their participation in village affairs. This is encouraging for the project as both gender are able to engage & freely express themselves in village development discussions The interventions of the project completed to date also addresses gender dimensions (i.e.) access roads supports both gender access to food source (plantations) and improves food production. Improved water reticulation systems through the Water enhancement projects serviced all level of community and reduce hardship domestically, for instance women no longer fetch water from streams for home use nor do laundry washing in rivers
Please complete the following section at mid-term and project completion
Lessons for Adaptation | Response
Climate Resilience Measures
What have been the lessons learned, both positive and negative, in implementing climate adaptation measures that would be relevant to the design and implementation of future projects/programmes for enhanced resilience to climate change? | It is very critical that communities at all levels are educated of Climate Change science basics, mitigation and adaptation measures. Understanding such fundamentals of climate change together with appreciation of available resources at the national level strengthens partnership and contributes to smooth implementation of climate change adaptation measures at the community level. In addition, the project supports the ministry 'National Environment Week' annually to educate communities targeting all levels (e.g. school children, CSOs, villages, youth group, women's, chiefs) to gain understanding of topics ranging from Integrated water management, Climate Change, Sustainable Developments practices, Policies & Legislations etc.
What is the potential for the climate resilience measures undertaken by the project/programme to be replicated and scaled up both within and outside the project area? | The climate resilient measures implemented by the project were primarily informed by feasibility assessments and studies conducted by Technical specialists engaged by the ministry. The development of the Relocation Strategy and Handbook to provide a framework for community relocation plans will benefit other communities on lessons learnt and also process to follow.
Concrete Adaptation Interventions
What have been the lessons learned, both positive and negative, in implementing concrete adaptation interventions that would be relevant to the design and implementation of future projects/programmes implementing concrete adaptation interventions? | Similarly to Climate Resilience Measure above.
What is the potential for the concrete adaptation interventions undertaken by the project/programme to be replicated and scaled up both within and outside the project area? | The concrete adaptation measures implemented by the project in the reporting period include seawall, revetment walls, water enhancement projects and access roads construction. All interventions were primarily informed by feasibility assessments and studies conducted by technical specialists engaged by the ministry. Such studies inform structural intervention designs and incorporates gender dimensions in it. The Manase Beach Replenishment project in the island of Savaii is one project to be replicated considering it is the first of its kind in Samoa that successfully restore sand loss in the area through erosion as a result of wave actions. The engineering intervention evidently provides protection for community assets
Community/National Impact
What would you consider to be the most successful aspects for the target communities? | The support of target communities to the projects should be acknowledged considering the in-kind contribution to access their resources (i.e.) lands for boulders & sand for construction of protection walls and access roads.
What measures are/have been put in place to ensure sustainability of the project/program results? | Through the review of CIM Plans, 5 thematic areas have been include to cover ridge to reef approach of the review. (Infrastructure, Livelihood, Environment, Governance). The governance component in which villages will be encouraged to develop and register by laws through the support of the Ministry of Women and Social Development will cater for sustainability aspect of the project but at the same time ensure ownership In addition Institutional Review of the Ministry and CIM Planning implementation is envisage will ensure CIM Planning and Implementation occurs at the Sectoral level within the government
What measures are being/could have been put in place to improve project/program results? | Through Technical Advisory Group coordinates all implementing partners of the project to ensure smooth implementation of project interventions. The TAG meets every quarter and when needed on urgent matters requiring resolution Furthermore the ministry engaged all relevant ministries/authorities in all community consultations of CIMP to responds to issues pertaining to village development in respect to their services provided to facilitate community understanding and appreciation of interventions.
Knowledge Management
How has existing information/data/knowledge been used to inform project development and implementation? What kinds of information/data/knowledge were used? | The database of CIMP actions created by the Ministry has been the source of information for community projects proposal to funding agents and provides the government with guidance on the requirements at the local level in relation to financial resources to improve resilience to climate change.
If learning objectives have been established, have they been met? Please describe. | Learning objectives is anticipated to be consolidated in 2017 subsequent to the completion of M&E surveys on interventions and institutional arrangements to properly document all lessons learnt in the course of the project.
Describe any difficulties there have been in accessing or retrieving existing information (data or knowledge) that is relevant to the project. Please provide suggestions for improving access to the relevant data. | There is a need for a centralized database on all GIS layers produced by government authorities and ministries in respect to their development works. The Technical Division of the Ministry of Natural Resources and Environment role as custodian of geographical information must be strengthened to ensure GIS information is well achieve and properly coordinated. It is envisage that through this project, information relative to CIMP interventions, implementation status etc. will be made available to aid the government realize improvements at the national and local level to date
Has the identification of learning objectives contributed to the outcomes of the project? In what ways have they contributed? | information on learning objectives will be provided latter in 2017 after proper monitoring and evaluations completed in quarter 2 & 3 on all outcomes of the project

## Results Tracker
Results Tracker for Adaptation Fund (AF) Projects
Goal: Assist developing-country Parties to the Kyoto Protocol that are particularly vulnerable to the adverse effects of climate change in meeting the costs of concrete adaptation projects and programmes in order to implement climate-resilient measures. Impact: Increased resiliency at the community, national, and regional levels to climate variability and change.
Important: Please read the following guidance document (also posted on the Adaptation Fund website) before entering your data
Link: http://www.adaptation-fund.org/sites/default/files/Results%20Framework%20and%20Baseline%20Guidance%20final.pdf
Adaptation Fund Strategic Results Framework
Project ID | 79825
Implementing Entity | UNDP
Type of implementing entity | MIE
Country | Samoa
Region | Pacific
Sector | Multi-sector
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Impact: Increased resiliency at the community, national, and regional levels to climate variability and change | Core Indicator: No. of beneficiaries |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project
|  | Total |  |  |  | Total |  |  |  | Total |  |  |  | Total
|  | % of female beneficiaries |  |  |  | % of female beneficiaries |  |  |  | % of female beneficiaries |  |  |  | % of female beneficiaries
|  | % of Youth beneficiaries |  |  |  | % of Youth beneficiaries |  |  |  | % of Youth beneficiaries |  |  |  | % of Youth beneficiaries
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 1: Reduced exposure to climate-related hazards and threats | Indicator 1: Relevant threat and hazard information generated and disseminated to stakeholders on a timely basis | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness
|  | Total |  |  |  | Total |  |  |  | Total |  |  |  | Total
|  | % of female targeted |  |  |  | % of female targeted |  |  |  | % of female targeted |  |  |  | % of female targeted
Output 1.1 Risk and vulnerability assessments conducted and updated | Indicator 1.1: No. of projects/programmes that conduct and update risk and vulnerability assessments | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
Output 1.2 Targeted population groups covered by adequate risk reduction systems | Core Indicator 1.2: No. of Early Warning Systems | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 2: Strengthened institutional capacity to reduce risks associated with climate-induced socioeconomic and environmental losses | Indicator 2: Capacity of staff to respond to, and mitigate impacts of, climate-related events from targeted institutions increased | Number of staff targeted |  | Sector | Capacity level | Number of staff targeted |  | Sector | Capacity level | Number of staff targeted |  | Sector | Capacity level | Number of staff targeted |  | Sector | Capacity level
|  | Total |  |  |  | Total |  |  |  | Total |  |  |  | Total
|  | % of female targeted |  |  |  | % of female targeted |  |  |  | % of female targeted |  |  |  | % of female targeted
Output 2.1 Strengthened capacity of national and sub-national centres and networks to respond rapidly to extreme weather events | Indicator 2.1.1: No. of staff trained to respond to, and mitigate impacts of, climate-related events | Total staff trained | % of female staff trained | Type |  | Total staff trained | % of female staff trained | Type |  | Total staff trained | % of female staff trained | Type |  | Total staff trained | % of female staff trained | Type
| Indicator 2.1.2: No. of targeted institutions with increased capacity to minimize exposure to climate variability risks | Type | Scale | Sector | Capacity level | Type | Scale | Sector | Capacity level | Type | Scale | Sector | Capacity level | Type | Scale | Sector | Capacity level
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 3: Strengthened awareness and owernship of adaptation and climate risk reduction processes | Indicator 3.1: Increase in application of appropriate adaptation responses | Percentage of targeted population applying adaptation measures |  | Sector |  | Percentage of targeted population applying adaptation measures |  | Sector |  | Percentage of targeted population applying adaptation measures |  | Sector |  | Percentage of targeted population applying adaptation measures |  | Sector
Output 3: Targeted population groups participating in adaptation and risk reduction awareness activities | Indicator 3.1.1: Percentage of targeted population awareness of predicted adverse impacts of climate change, and of appropriate responses | No. of targeted beneficiaries | % of female participants targeted | Level of awareness |  | No. of targeted beneficiaries | % of female participants targeted | Level of awareness |  | No. of targeted beneficiaries | % of female participants targeted | Level of awareness |  | No. of targeted beneficiaries | % of female participants targeted | Level of awareness
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Target performance at completion
Outcome 4: Increased adaptive capacity within relevant development sector services and infrastructure assets | Indicator 4.1: Increased responsiveness of development sector services to evolving needs from changing and variable climate | Project/programme sector | Geographical scale | Response level |  | Project/programme sector | Geographical scale | Response level |  | Project/programme sector | Geographical scale | Response level |  | Project/programme sector | Geographical scale | Response level
| Core Indicator 4.2: Assets produced, developed, improved or strengthened | Sector | Targeted asset | Changes in asset (quantitative or qualitative) |  | Sector | Targeted asset | Changes in asset (quantitative or qualitative) |  | Sector | Targeted asset | Changes in asset (quantitative or qualitative) |  | Sector | Targeted asset | Changes in asset (quantitative or qualitative)
Output 4: Vulnerable development sector services and infrastructure assets strengthened in response to climate change impacts, including variability | Indicator 4.1.1: No. and type of development sector services to respond to new conditions resulting from climate variability and change | Number of services | Type |  | Sector | Number of services | Type |  | Sector | Number of services | Type |  | Sector | Number of services | Type |  | Sector
|  | Baseline information |  |  |  | Baseline information |  |  |  | Performance at mid-term |  |  |  | Target performance at completion
Outcome 5: Increased ecosystem resilience in response to climate change and variability-induced stress | Indicator 5: Ecosystem services and natural resource assets maintained or improved under climate change and variability-induced stress | Natural resource improvement level |  | Sector | Type | Natural resource improvement level |  | Sector | Type | Natural resource improvement level |  | Sector | Type | Natural resource improvement level |  | Sector | Type
Output 5: Vulnerable ecosystem services and natural resource assets strengthned in response to climate change impacts, including variability | Core Indicator 5.1: Natural Assets protected or rehabilitated | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Baseline information |  |  |  | Targeted performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 6: Diversified and strengthened livelihoods and sources of income for vulnerable people in targeted areas | Indicator 6.1: Increase in households and communities having more secure access to livelihood assets | No. of targeted households | % of female headed households | Improvement level |  | No. of targeted households | % of female headed households | Improvement level |  | No. of targeted households | % of female headed households | Improvement level |  | No. of targeted households | % of female headed households | Improvement level
| Indicator 6.2: Increase in targeted population's sustained climate-resilient alternative livelihoods | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
|  | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
|  | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
|  | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
Output 6 Targeted individual and community livelihood strategies strengthened in relation to climate change impacts, including variability | Indicator 6.1.1: No. and type of adaptation assets created or strengthened in support of individual or community livelihood strategies | Number of Assets | Type of Assets | Sector | Adaptation strategy | Number of Assets | Type of Assets | Sector | Adaptation strategy | Number of Assets | Type of Assets | Sector | Adaptation strategy | Number of Assets | Type of Assets | Sector | Adaptation strategy
| Core Indicator 6.1.2: Increased income, or avoided decrease in income | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 7: Improved policies and regulations that promote and enforce resilience measures | Indicator 7: Climate change priorities are integrated into national development strategy | Integration level |  |  |  | Integration level |  |  |  | Integration level |  |  |  | Integration level
Output 7:Improved integration of climate-resilience strategies into country development plans | Indicator 7.1: No. of policies introduced or adjusted to address climate change risks | No. of Policies introduced or adjusted | Sector | Scale | Type | No. of Policies introduced or adjusted | Sector | Scale | Type | No. of Policies introduced or adjusted | Sector | Scale | Type | No. of Policies introduced or adjusted | Sector | Scale | Type
| Indicator 7.2: No. of targeted development strategies with incorporated climate change priorities enforced | No. of Development strategies | Regulation |  | Effectiveness | No. of Development strategies | Regulation |  | Effectiveness | No. of Development strategies | Regulation |  | Effectiveness | No. of Development strategies | Regulation |  | Effectiveness
Glacier lake outburst flood
|  | Inland flooding | fr | biological assets |  | Company policy | 5: Fully enforced (All elements implemented)
|  | Salinization | Decrease | land |  | Communication & Information policy | 4: Enforced (Most elements implemented)
|  | Drought | Same | water areas |  | Defense policy | 3: Partially enforced (Some elements implemented)
|  | Wind |  | subsoil assets | increased adpative capacity | Domestic policy | 2: Partially not enforced (Most elements not implemented) |  | Agribusiness
|  | Coastal flooding |  | air | achieved | Economic policy | 1: Not enforced (No elements implemented) |  | Agricultural-related | Financial capital
|  | Storm surge | Please choose |  | enhanced level of protection | Education policy |  |  | Agriculture | Human capital
|  | Hurricane | Selected | [5 empty] | Aquaculture | Physical capital
|  |  | Not relevant |  |  | 5: All (Fully integrated) |  |  | Construction/repairing business | Social capital
[6 empty] | 4: Most |  |  | Cultivation | Natural capital
[6 empty] | 3: Some |  |  | Fishing | Personal capital
Select | 5: All | Select |  |  | Community | 2: Most not integrated |  | Other | Forestry | Adaptation strategies
1 | 4: Almost all | Private | Type | Yes | Multi-community | 1: None |  | Agriculture | Handicrafts
2 | 3: Half | Public | Scale | No | Departmental |  |  | Coastal management | Livestock production
3 | 2: Some | NGO | Sector |  | National |  |  | Disaster risk reduction | Manufacturing
4 | 1: None |  |  |  |  | 5: Very high improvement | Established | Food security | other
|  | National |  |  |  | 4: High improvement | Maintained | Health | Services
|  | Regional |  |  |  | 3: Moderate improvement | Improved | Urban development | Tourism-related
|  | Local |  |  |  | 2: Limited improvement |  | Water management | Trading
[6 empty] | 1: No improvement |  | Multi-sector
|  | 1 -generated information is irrelevant, and neither the stakeholders reached nor the timeframe managed were achieved | 1: No info transferred on time | 4: High capacity | 5: Fully aware | 5: Highly responsive (All defined elements ) | 5: Fully improved | Roads | 5: Very effective
Asia-Pacific | NIE | 2 -the existence of some challenge in any of the three aspects of the indicator (generation of dissemination, stakeholders reached or timeframe managed) | 2: Somewhat info transferred | 3: Medium capacity | 4: Mostly aware | 4: Mostly responsive (Most defined elements) | 4: Mostly Improved | Gov Buildings | 4: Effective
Latin America and Caribbean | RIE | 3 -relevant information is generated and disseminated to all identified stakeholders on timely basis | 3: Info transferred on time | 2: Low capacity | 3: Partially aware | 3: Moderately responsive (Some defined elements) | 3: Moderately improved | Causeways | 3: Moderately effective
Africa | MIE |  |  | 1: No capacity | 2: Partially not aware | 2: Partially responsive (Lacks most elements) | 2: Somewhat improved | Airports | 2: Partially effective
Eastern Europe |  |  |  |  | 1: Aware of neither | 1: Non responsive (Lacks all elements ) | 1: Not improved | Schools | 1: Ineffective
| ha protected | [6 empty] | Training Centres
| ha rehabilitated | [5 empty] | Monitoring/Forecasting capacity | Hospitals
Afghanistan, Islamic Rep. of | km protected | [5 empty] | Policy/regulatory reform | Drinking water systems
Angola | km rehabilitated | 1: Risk knowledge | 1: No plans conducted or updated |  |  |  | Capacity development | Other
Albania |  | 2: Monitoring and warning service | 2: Undertaking or updating of assessments in progress |  |  | Communication & Information policy | Sustainable forest management
Argentina |  | 3: Dissemination and communication | 3: Risk and vulnterability assessments completed or updated |  |  | Domestic policy | Strengthening infrastructure | 1: Health and Social Infrastructure (developed/improved)
Armenia | Forests | 4: Response capability |  |  |  | Economic policy | Supporting livelihoods | 2: Physical asset (produced/improved/strenghtened)
Antigua and Barbuda | Mangroves |  |  |  |  | Education policy | Mangrove reforestation
Azerbaijan | Coasts |  | From 0 to 0.5% |  |  | Energy policy | Coastal drainage and infrastructure
Burundi | Rangelands |  | From 0.5 to 1% |  |  | Environmental policy | Irrigation system
Benin | Cultivated land/Agricultural land |  | From 1% to 5% |  |  | Foreign policy | Community-based adaptation
Burkina Faso | Catchment area/Watershed/Aquifer |  | From 5% to 10% |  |  | Health policy | Erosion control
Bangladesh | Protected areas/National parks |  | From 10% to 20% |  |  | Housing policy | Soil water conservation
Bulgaria | Other |  | From 20% to 30% |  |  | Human resource policies | Microfinance
Bahrain |  |  | From 30% to 40% |  |  | Information policy | Special Program for women
Bahamas, The |  |  | From 40% to 50% |  |  | Macroeconomic policy | Livelihoods
Bosnia and Herzegovina |  |  | Above 50% |  |  | Monetary policy | Water storage
Belarus | [5 empty] | Population policy | ICT and information dissemination
Belize | [5 empty] | Private policy
Bolivia | [5 empty] | Public policy
Brazil | [5 empty] | Science policy
Barbados | [5 empty] | Social policy
Bhutan |  | 3- relevant information is generated and disseminated to all identified stakeholders on timely basis |  |  |  | Transportation policy
Botswana |  | describe |  |  |  | Urban policy
Central African Republic |  | 2- the existence of some challenge in any of the three aspects of the indicator |  |  |  | Water policy
Chile |  | describe |  |  |  | Other policy
China, People's Republic of |  | 1- generated information is irrelevant and neither the stakeholders reached nor the timeframe managed were achieved
Cote d'Ivoire |  | describe
Cameroon
Congo, Dem. Rep. of
Congo, Republic of
Cook Islands
Colombia
Comoros
Cape Verde
Costa Rica
Cuba
Czech Republic
Djibouti
Dominica
Dominican Republic
Algeria
Ecuador
Egypt
Eritrea
Estonia
Ethiopia
Fiji
Micronesia, Fed. States of
Gabon
Georgia
Ghana
Guinea
Gambia, The
Guinea-Bissau
Equatorial Guinea
Grenada
Guatemala
Guyana
Honduras
Croatia
Haiti
Hungary
Indonesia
India
Iran, Islamic Republic of
Jamaica
Jordan
Kazakhstan
Kenya
Kyrgyz Republic
Cambodia
Kiribati
Saint Kitts and Nevis
Korea, Republic of
Lao People's Democratic Republic
Lebanon
Liberia
Libya
Saint Lucia
Sri Lanka
Lesotho
Lithuania
Latvia
Morocco
Moldova
Madagascar
Maldives
Mexico
Marshall Islands
Macedonia, former Yugoslav Republic of
Mali
Malta
Myanmar
Montenegro
Mongolia
Mozambique
Mauritania
Mauritius
Malawi
Malaysia
Namibia
Niger
Nigeria
Nicaragua
Niue
Nepal
Nauru
Oman
Pakistan
Panama
Peru
Philippines
Palau
Papua New Guinea
Poland
Korea, Dem. People's Rep. of
Paraguay
Romania
Russian Federation
Rwanda
Saudi Arabia
Sudan
Senegal
Solomon Islands
Sierra Leone
El Salvador
San Marino
Serbia
Sao Tome and Principe
Suriname
Slovak Republic
Slovenia
Swaziland
Seychelles
Syrian Arab Republic
Chad
Togo
Thailand
Tajikistan
Turkmenistan
Tonga
Trinidad and Tobago
Tunisia
Turkey
Tuvalu
Tanzania
Uganda
Ukraine
Uruguay
Uzbekistan
Saint Vincent and the Grenadines
Venezuela
Vietnam
Vanuatu
Samoa
Yemen, Republic of
South Africa
Zambia
Zimbabwe
Timor-Leste

## Units for Indicators
Fund Outcome Indicator Units
1. Generation of relevant data, Stakeholders, and Timeliness 2.1. Include both qualitative and quantitative measures of capacity level within targeted institutions 2.2. Number (men and women and other vulnerable groups) 3.1. Use scale from 1 to 5: 5: Fully aware 4: Mostly aware 3: Partially aware 2: Partially not aware 1: Aware of neither predicted adverse impacts of climate change nor of appropriate responses 3.2. Use scale from 1 to 5: 5: All 4: Almost all 3: Half 2: Some 1: None 4.1. Summarize in an overall scale (1-5): 5: Highly responsive (All defined elements ) 4: Mostly responsive (Most defined elements) 3: Moderately responsive (Some defined elements) 2: Partially responsive (Lacks most elements) 1: Non responsive (Lacks all elements ) 4.2. Summarize in an overall scale (1-5): 5: Fully improved 4: Mostly Improved 3: Moderately improved 2: Somewhat improved 1: Not improved 5. Depends on the targeted natural asset: Biological (species): measure through changes in population numbers (dynamics, structure, etc.) Land: measure changes in hectares. Baseline data will be necessary to estimate the change. Supporting indicators baseline and target (as well as contextual information) are needed such as the following: Farmers adopting recommended technologies, Ha. of land improved, Average deforestation rate Etc. Use scale from 1 to 5. 5: Very effective (All elements are present) 4: Effective (Most elements are present) 3: Moderately effective (Some elements are present) 2: Partially effective (Most elements are not present) 1: Ineffective (No elements are present) 6.1. Summarize in an overall scale (1-5): 5: Very high improvement 4: High improvement 3: Moderate improvement 2: Limited improvement 1: No improvement 6.2. Household income by source of livelihood in project area (USD) prior and post project intervention 7. Summarize in an overall scale (1-5). 5: All (Fully integrated) 4: Most 3: Some 2: Most not integrated 1: None
Fund Output Indicator Units
1.1. Number, sector(s) and level(s) of projects or interventions in separate fields of monitoring plan 1.2. Number 2.1.1. Number of staff (male/female) of targeted institutions: a. Obtain baseline information: total number of staff from targeted institutions b. Define target 2.1.2. Number of staff (male/female) of targeted institutions: a. Obtain baseline information: total number of staff from targeted institutions b. Define target: needs to be defined by project proponents 2.2.1. Quantitative: Percentage (includes women – and other vulnerable groups – and men). Qualitative: Adequacy: include direct analysis of major areas; adequacy/effectiveness of systems or analysis of perceptions of populations and institutions. 2.2.2. Number (broken down by gender and, if possible, by vulnerable groups defined in the area of intervention) of people 3.1. Number and type (in separate columns) at local level. 3.2. Number 4.1. Number and type 4. 2. Number and type (entered in separate columns) 5. Number of interventions by type of natural asset and intervention 6.1. Number and type (in separate columns of monitoring plan) 6.2. Income sources per household; description of income source and number of households. 7.1. Number/Sector 7.2. Number; Effectiveness (see previous indicator) through enforcement level.