## Overview
Project Performance Report (PPR)
| Period of Report (Dates) | October 2015
| Project Title: | Project: "Building resilience to climate change and variability in vulnerable smallholders" (Project "GFCC")
| Project Summary: | The Project's overall objective is to contribute to building national capacity to adapt to climate change (CC) and variability by focusing on critical sectors of the country's economy. The specific objectives of this Project aim to: (i) reduce vulnerability and build resilience to climate change and variability for smallholders in the livestock sector located in the Landscape Units of the Basaltic Cuesta and East Hills eco-regions; (ii) strengthen local institutional networks in the selected Landscape Units and enhance the capacity of organizations to manage climate risks locally; (iii) manage the knowledge generated by developing mechanisms to better understand and monitor the impacts and variability of climate change, anticipate and assess negative events, take advantage of lessons learned, and identify and validate best practices and toolkits to adapt to climate change and variability.
|  |  | Countries | Project Type: |  | GEF Focal Area: | GEF 4 Focal Areas | GEF 2 / 3 Operational Programme: | Overall Rating of the project in the evaluation by the project evaluator: | GEF-4 Focal Area Strategic Program: | GEF-3 Focal Area Strategic Program:
| Database Number: | PROJECT AFB/NIE/Agri/2011/1 | Afghanistan | FP | Yes | Biodiversity | 1 | 1 | U | BD-SP1-PA Financing | 1: Arid & semi-arid ecosystems
Implementing Entity (IE) [name]: |  | Agencia Nacional de Investigación e Innovación (ANII) | Albania | MSP | No | Climate Change Adaptation | 2 | 2 | S | BD-SP2-Marine PA | 2: Coastal, marine & freshwater ecosystems
| Type of IE: | NIE | Algeria | EA |  | Climate Change Mitigation | 3 | 3 | MU | BD-SP3-PA Networks | 3: Forest ecosystems
| Country(ies): | Uruguay | Angola |  |  | International Waters | 5 | 5 | Good | BD-SP5-Markets | 13: Conservation and Sustainable Use of Biological Diversity Important to Agriculture
Relevant Geographic Points (i.e. cities, villages, bodies of water): |  | Basaltic Cuesta (Artigas, Salto, Tacuarembó and Rivera) and East Hills (Maldonado, Rocha, Lavalleja and Treinta y Tres) | Argentina |  |  | Multiple Focal Area |  |  |  | BD-SP7-Invasive Alien Species(IAS) | 6: Promoting the adoption of renewable energy by removing barriers and reducing implementation costs
[8 empty] | CC-SP2- Industrial EE | 8: Waterbody based operational program
| Project Milestones | [6 empty] | CC-SP3-RE,CC-SP4-Biomass | 9: Integrated Land and Water multiple focal area
| Milestone |  | Bahamas | [6 empty] | CC-SP5-Transport | 10: Contaminants based operational program
AFB Approval Date: |  | 13-14/12/2011
IE-AFB Agreement Signature Date: |  | 2011-12-27 | [6 empty] | CC-SP6-LULUCF | 12: Integrated Ecosystem Management
Start of Project/Programme: |  | 2012-10-22 | [6 empty] | Cross cutting capacity building | 14: Persistent Organic Pollutants
Mid-term Review Date (if planned): |  | April 2016
| Terminal Evaluation Date: | September, 2017
|  | List documents/ reports/ brochures / articles that have been prepared about the project. | Cyprus
|  | Currently we have: Operating Manual, field manual, grid proposal evaluation, operating regulations for disbursement for payment of proposals and technical assistance, technical and operational regulations of the revolving fund, reports consulting baseline, field notebook and protocol use, MEGANE program and its implementation methodology to estimate amount of pasture, communicational posters. | Czech Republic
List the Website address (URL) of project. |  |  | Democratic People's Republic of Korea
|  | http://www.mgap.gub.uy/portal/page.aspx?2,MGAP,MGAPAmpliacion,O,es,0,PAG;CONC;599;3;D;proyecto-ganaderos-familiares-y-cambio-climatico-gfcc--donacion-fondo-de-adaptacion-del-protocolo-de-kyoto;1;PAG; | Democratic Republic of the Congo
Denmark
| Project contacts: |  | Djibouti
National Project Manager/Coordinator |  |  | Dominica
| Name: | Ing. Agr. Marcos Martínez | Dominican Republic
| Email: | marcosmartinez@mgap.gub.uy | Ecuador
| Date: | 2015-10-22 | Egypt
| Government DA |  | El Salvador
| Name: |  | Equatoral Guinea
| Email: |  | Eritrea
| Date: |  | Estonia
| Implementing Entity |  | Ethiopia
| Name: | Ing. Agr. Marcelo Batto | Fiji
| Email: | mbatto@anii.org.uy | Finland
| Date: | 2015-10-22 | France
| Executing Agency |  | Gambia
| Name: | Dr. Alberto Castelar | Georgia
| Email: | acastelar@mgap.gub.uy | Germany
| Date: | 2015-10-22 | Ghana
| Executing Agency |  | Greece
| Name: | Ing Agr. Jorge Marzaroli | Grenada
| Email: | jmarzaroli@mgap.gub.uy | Guatemala
| Date: | 2015-10-22 | Guinea
| Executing Agency |  | Guinea Bissau
| Name: |  | Guyana
| Email: |  | Haiti
| Date: |  | Honduras
Hungary
Iceland
India
Indonesia
Iran (Islamic Republic of)
Iraq
Ireland
Israel
Italy
Jamaica
Japan
Jordan
Kazakhstan
Kenya
Kiribati
Kuwait
Kyrgyzstan
Lao People’s Democratic Republic
Latvia
Lebanon
Lesotho
Liberia
Libyan Arab Jamahiriya
Liechtenstein
Lithuania
Luxembourg
Madagascar
Malawi
Malaysia
Maldives
Mali
Malta
Marshall Islands
Mauritania
Mauritius
Mexico
Micronesia, Federated States of
Monaco
Mongolia
Montenegro
Morocco
Mozambique
Myanmar
Namibia
Nauru
Nepal
Netherlands
New Zealand
Nicaragua
Niger
Nigeria
Norway
Oman
Pakistan
Palau
Panama
Papua New Guinea
Paraguay
Peru
Philippines
Poland
Portugal
Qatar
Republic of Korea
Republic of Moldova
Romania
Russian Federation
Rwanda
Saint Kitts and Nevis
Saint Lucia
Saint Vincent and the Grenadines
Samoa
San Marino
Sao Tome and Principe
Saudi Arabia
Senegal
Serbia
Seychelles
Sierra Leone
Singapore
Slovakia
Slovenia
Solomon Islands
Somalia
South Africa
Spain
Sri Lanka
Sudan
Suriname
Swaziland
Sweden
Switzerland
Syrian Arab Republic
Tajikistan
Thailand
The former Yugoslav Republic of Macedonia
Timor-Leste
Togo
Tonga
Trinidad and Tobago
Tunisia
Turkey
Turkmenistan
Tuvalu
Uganda
Ukraine
United Arab Emirates
United Kingdom of Great Britain and Northern Ireland
United Republic of Tanzania
United States of America
Uruguay
Uzbekistan
Vanuatu
Venezuela, Bolivarian Republic of
Viet Nam
Yemen
Zambia
Zimbabwe

## FinancialData
Financial information: cumulative from project start to [insert date]
DISBURSEMENT OF AF GRANT FUNDS
How much of the total AF grant as noted in Project Document plus any project preparation grant has been spent to date?
Estimated cumulative total disbursement as of October 2015 | 2873667
Add any comments on AF Grant Funds. (word limit=200)
INVESTMENT INCOME
Amount of annual investment income generated from the Adaptation Fund’s grant
EXPENDITURE DATA
List ouput and corresponding amount spent for the current reporting period | ITEM / ACTIVITY / ACTION | AMOUNT
| Comprehensive investments in water supply, best practices for native grasslands management shadow trees and animal management improvements benefitting approximately 700 farmers in the LU of the Basaltic Cuesta, 25% women household heads | 733665.915
| Comprehensive investments in water supply, best practices for native grasslands management, shadow trees and animal management improvements and agro-forestry schemes benefitting approximately 640 farmers in the LU of the East Hills Region, 25% women household heads | 1459956.415
| In depth diagnosis of the landscape units and development of a local network of grass-root organizations and public institutions that conducts a participatory assessment of local capacities and prepares and implements a strategic plan to address CC and variability | 171210.3575
| A training plan is formulated and implemented at local level responding to the weaknesses identified and focusing on CC and variability issues | 117200.2375
| Demonstration plots in schools and organizations on adaptation measures and youth communication projects are implemented making use of the CEIBAL Plan internet platform to the extent possible, to involve children and youth | 8228.4575
| Actions Plans identified in the Strategic Plan are developed and implemented at the LU level with technical support and coordinated with the training programme | 88400.5775
| The UACC of the MGAP is strengthened to monitor and evaluate CC with reference to the agricultural sector | 42381.1375
| Indicators and methodologies to monitor and evaluate CC and variability are identified and applied | 84207.8975
| Research projects provide a better understanding and/or technical recommendations to face climate variability with particular reference to droughts (water supply, fencing, shadows trees, stocking rate) | 84207.8975
| Systematic review and exchange of experiences regarding CC adaptation involving research and extension institutions and participatory systematization of project experience to elicit lessons learned for future projects and for the region | 84207.8975
| TOTAL | 2873666.79
PLANNED EXPENDITURE SCHEDULE
List outputs planned and corresponding projected cost for the upcoming reporting period | ITEM / ACTIVITY / ACTION | PROJECTED COST | Est. Completion Date
| Component 1 | 1876800 | 2015-10-01
| Component 2 | 281843.6525 | 2015-10-01
| Component 3 | 197039.8438 | 2015-10-01
| Component 4 | 70482.89 | 2015-10-01
| TOTAL | 2426166.3862
ACTUAL CO-FINANCING (If the MTR or TE have not been undertaken this reporting period, DO NOT report on actual co-financing.)
How much of the total co-financing as committed in the Project Document has actually been realized?
Estimated cumulative actual co-financing as verified during Mid-term Review (MTR) or Terminal Evaluation (TE).
Add any comments on actual co-financing in particular any issues related to the realization of in-kind, grant, credits, loans, equity, non-grant instruments and other types of co-financing. (word limit=200)

## Risk Assesment
RISK ASSESMENT
IDENTIFIED RISKS
List all Risks identified in project preparation phase and what steps are being taken to mitigate them
Identified Risk | Current Status | Steps Taken to Mitigate Risk
No demand for investments in adaptation. | Medium | The amount of technician private and technician of public institution this topdressing for making new proposal
Agricultural organizations are not interested in participating in local networks. | Low | The agricultural organizations are working actively: conducting seminars, adhering new farmers and senziting people about climatic change
Project focus changes from adaptation to climate change and variability to production and productivity | Low | The strategic line of MGAP adaptation to climate change is maintained, that line is reinforced at the level of central government. New research in agriculture reinforces the concept of a better use of natural field, incrmenta productivity, the systems are more resilient and improve biodiversity
The smallholders targeted are unable to compete or sustain their livelihoods. | Low | Only 3% of the smallholders renounced their proposal
Delays in funds disbursement discourage farmers from participating in the project. | Medium | A level MGAP has generated a protocol evaluation, approval and disbursement of the proposals, this has allowed shorten the internal times, but still large external transparency court proceedings. This has resulted in some closures occur some discomfort at producer level
Lack of transparency or political interference in allocation of resources. | Low | Execution is carried out through public calls, which ensures transparency. Projects are assessed using a grid of criteria, MDR al local level provide social control, and there are contracts between farmers and MGAP, and public records of all actions and decisions.
Lack of coordination between the various components. | Low | The creation of the Coordination Committee markedly improved coordination between components. In addition to conducting this meeting in UP, called ateneos, incrmento knowledge of the problematic and zonal solutions and exchange between both UP.
Critical Risks Affecting Progress (Not identified at project design)
Identify Risks with a 50% or > likelihood of affecting progress of project
Identified Risk | Current Status | Steps Taken to Mitigate Risk
The project is so efficient in the use of human resources, which leads to that for reasons beyond the same, the absence of a human resource development project affects | Medium | A protocol that in the absence of each resource person or persons who would assume the roles were available
Mainstreaming project in different MGAP units, leads to delays in project implementation | Medium | They were generated resolves committees where actions and responsibilities
Reaching the total number of beneficiaries and that investments in farms allow changes in productivity and this is sustainable and increases resilience | Medium | So far have not generated actions in this regard, it is studying a possible modification to the strategy
Risk Measures: Were there any risk mitigation measures employed during the current reporting period? If so, were risks reduced? If not, why were these risks not reduced?
Add any comments relevant to risk mitigation (word limit = 500)
In this period they were strengthened and generated action protocols in cases of execution risks mentioned above. The Committee focused more on finding action to improve the functioning of the execution, which in scheduling activities and raise awareness.

## Rating
RATING ON IMPLEMENTATION PROGRESS
For rating definitions please see bottom of page.
| Progress on Key Milestones |  | Expected Progress |  | Progress to Date | Rating
Project Manager/Coordinator: | Component1 |  | To have 400 projects approved in 2015. |  | 704 projects approved. | HS
| Component 2 |  | Develompent of the participative diagnostic, kick of for strategic planning and development of several communication activities |  | A Call to young members project related with CC and adaptability B MDR working in planification in actions to sensibility comunity in CC and adpatability C Beginning of 2016 defined participatory diagnosis and definitions of specific action | S
| Component 3 |  | Reference farms elected and monitoring process on the ground. |  | A- MEGANE: generating tool, which is available in http://megane.planagropecuario.org.uy/ was completed. B- Baseline: field survey was completed and the final data is processing. C- MGAP and BSE launched a pilot insurance for farmers family on the basis of a modern climatic index of drought. http://www.mgap.gub.uy/portal/afiledownload.aspx?2,1,12,O,S,0,13653%3BS%3B1%3B16 | MS
[5 empty] | Overall Rating | S
Please Provide the Name and Contact information of person(s) reponsible for completeling the Rating section
| Name: | Marcos Javier Martínez Techera
| Email: | marcosmartinez@mgap.gub.uy
Please justify your rating. Outline the positive and negative progress made by the project since it started. Provide specific recommendations for next steps. . (word limit=500)
Component 1: Despite the initial delay in the start of the project, it was a big boost in the second year at the level of the UP, which allowed the presentation of a importanto number of proposals, which managed to reach the total number of beneficiaries . Component 2: Farmers' organizations at the beginning of the program were not people working without clear objectives, with little training in issues relating to climate change and its consequences, and technicians had little training on issues of strategic planning, which leads to Levelling more time on these issues. This component also articulate strongly with other public institutions that have undergone changes in its direction, which delayed the start of execution. Component 3: This component was initially proposed work jointly with the rangeland field board, in terms of methodology and technological proposals applicable to farms, institutions that comprise only the University and the IPA, submitted proposals to it. Once agreed the signing of the work was delayed.
| Progress on Key Milestones |  | Expected Progress |  | Progress to Date | Rating
Implementing Agency | Component1 |  | To have 400 projects approved in 2015. |  | 704 projects approved. | HS
| Component 2 |  | Develompent of the participative diagnostic, kick of for strategic planning and development of several communication activities |  | A) Was made the call "Somos de Acá GFCC" for young members to submit projects with community actions related to climate change and adaptability B) The MDR will continue to be strengthened and are working on action planning community sensitization on climate change and adaptability C) The diagnosis was concluded and at the beginning of 2016 will be defined the participatory specific actions. | S
| Component 3 |  | Reference farms elected and monitoring process on the ground. |  | A) Was generated and is available the model of a Extensive Livestock Farm " MEGANE A" which measures the co - evolution of a natural pasture field and a herd of cattle that is grazing on it. B) Baseline: the field study was completed and is being processed the final data C) Was selected a group of producers to launch the insurance pilot for family farmers on the basis of a modern climatic index of drought , generated by MGAP and BSE. | MS
| Component 4 |  | Execution of general administration, financial management and procurement, and overall reporting of the project |  | Most of the planned activities were executed or are under execution | S
[5 empty] | Overall Rating | S
Please Provide the Name and Contact information of person(s) reponsible for completeling the Rating section
| Name: | Ing. Agr. Marcelo Batto
| Email: | mbatto@anii.org.uy
| Progress on Key Milestones |  | Expected Progress |  | Progress to Date | Rating
Other
Overall Rating
Please Provide the Name and Contact information of person(s) reponsible for completeling the Rating section
Name:
Email:
| Please justify your rating and address the following points: 1. Indicate trends, both positive and negative, in achievement of outcomes as per the project indicators. 2. Detail critical risks that have affected progress. 3. Outline response to MTR undertaken this reporting period. 4. Outline action plan to address projects with a rating of HU, U or MU. Please keep your input to 1200 words |  | Component 1: In the second year of the implementation, the UP improved the communication channels achieving a high number of proposal presentation, with a high percentage of approval. In this way it reached the total number of projected beneficiaries to the present date. Component 2: More time was needed for leveling the knowledge in both producer organizations and technicians, due to the lack of clear objectives and little training on issues related to climate change and its consequences. In the case of the technicians they had little training on strategic planning. This component is also strongly articulated with other public institutions that have undergone changes in its direction. Component 3: This component was initially proposed to work jointly with the rangeland field board, in terms of methodology and technological proposals applicable to farms, the institutions that comprise the University and the IPA, submitted proposals to it. Once agreed the signing of the work was delayed.
Rating Definitions
|  |  | Highly Satisfactory (HS) | Project actions/activities planned for current reporting period are progressing on track or exceeding expectations to acheive all major outcomes/outputs for given reporting period, without major shortcomings. The project can be presented as “good practice”.
|  |  | Satisfactory (S) | Project actions/activities planned for current reporting period are progressing on track to achieve most of its major outcomes/outputs with only minor shortcomings.
|  |  | Marginally Satisfactory (MS) | Project actions/activities planned for current reporting period are progressing on track to achieve most major relevant outcomes/outputs, but with either significant shortcomings or modest overall relevance.
|  |  | Marginally Unsatisfactory (MU) | Project actions/activities planned for current reporting period are not progressing on track to achieve major outcomes/outputs with major shortcomings or is expected to achieve only some of its major outcomes/outputs.
|  |  | Unsatisfactory (U) | Project actions/activities planned for current reporting period are not progressing on track to achieve most of its major outcomes/outputs.
|  |  | Highly Unsatisfactory (U) | Project actions/activities planned for current reporting period are not on track and shows that it is failing to achieve, and is not expected to achieve, any of its outcomes/outputs.

## Project Indicators
PROJECT Indicators
Please provide all indicators being tracked for the project as outlined in the project document
Type of Indicator (indicators towards Objectives, Outcomes, etc…)
Type of Indicator | Indicator | Baseline | Progress since inception | Target for Project End
| Farm plans implemented per Landscape Unit (LU). | 0 | Basalto: 187 projects submitted, and 133 projects approved Sierra del Este: 168 projects submitted. 299 projects approved. Total 355 submitted, 432 projects approved | In 2015 400 projects approved
| Investments implemented per LU, per type. | 0 | Basalto: 272 projects approved. Sierra del Este: 626 projects approved. Total: 898 projects approved | 700 in Basaltic Cuesta, 640 in East Hills no distinction. US$7.260.000
| Women beneficiaries | 0 | Of the 898 projects approved in this period, 17% are women | 25 % of the beneficiaries are women
| Source and availability of water for animal consumption. | Production systems with water shortage. | 84% of investment amount dedicated to water solution (596 approved proposal) | Not listed. Estimated: 60% of investment amount.
| Source and availability of forage in farms. | Degraded native grasslands, overgrazing, in many situations. Few forage banks. | 92 % of investment amount dedicated to increase forage availability ( 651 approved proposal) | Not listed. At least 80% of the projects propose actions aimed at increasing forage availability. 40 forage and grain banks.
| Net primary productivity (NPP) | 3,300 kg DM/ha/yr in Basaltic Cuesta, 3,050 kg DM/ha/yr in East Hills. | Not date avalaible until now. Monitoring at farms level | Project will help improve NPP in farm holdings, measured in a sample of holdings.
| Stocking rate. | From the baseline survey, stocking rates per hectare is 0,96 UG | Not date avalaible until now. Monitoring at farms level | Not listed. A decrease to 0.75-0.8 LU/ha is estimated in farm holdings participating in the project.
| Fertility rate per year. | Calving rate from the baseline survey, the average is 61,93 | Not date avalaible until now. Monitoring at farms level | Not listed. Estimated: 70% in farm holdings participating in the project.
| Estimated weight gain of animals per year, per category. | From the baseline survey, the average production of meat per hectare is 74,4 kg | Not date avalaible until now. Monitoring at farms level | No data. Estimated: 110 Kg in farm holdings participating in the project.
| Networks have regular meetings as subgroups or independent MDRs [Rural Development Boards]. | 28 organizations and 9 MDR linked to the LU, without reference to climate change. | Basalto: In the 4 MDRs and 8 organizations, carry out activities connected to the project. Sierra del Este: In the 5 MDRs and 14 organizations, carry out activities connected to the project. | * 50% of organizations and 100% of MDRs discussed actions related to adaptation and climate change.
| Networks implement communications about CC, variability and adaptation. | 0 | 9 MDR develop local projects to strengthen local networks. | * The 9 MDRs participate in an adaptation to CC and variability information network.
| Networks submit proposals to the sponsoring MDRs, MGAP and SNE [National Emergency System]. | 0 | 5 MDR local projects designed to strengthen networks for adaptation to climate change | The 9 MDRs receive and discuss proposals coming from the network linked to CC and variability.
| Networks seek and obtain funds from other programs to implement their development and CC agenda. | 0 | Organizations have found support at the individual level but not at the network level | Networks submit proposals linked to development and adaptation to CC and variability to funding institutions.
| Young members and youth organizations participate in the network. | 0 | young people who have 18 initiatives involving the MDR | 15% of participants in MDR that are included in the networks are young members.
| Implementation of proposals and initiatives submitted by young members/youth organizations. | 0 | 110 young people have submitted 18 initiatives aimed at adapting to climate change and variability | Young members submit at least 14 initiatives related to adaptation to CC and variability.
| Studies, regular reports on climate data and early warnings on adverse events are available at the LU level through the website. | Information available from INIA GRAS and Dirección Nacional de Meteorología [National Directorate of Meteorology]. | Participation in building SNIA for generating agroclimatic information at the LU level. | UACC generates information about adaptation to CC and variability, available through the SNIA: agro-climatic monitoring with better spatial resolution and early warnings.
| Participation of key institutions and achievement of recognition thanks to national seminars as milestones for CC and variability, through participants’ evaluations. | 0 | 4 seminars were held in summer - autumn 2016. Theme "Technical change and livestock adapatación to CC" | 4 national seminars on topics related to adaptation to CC and variability.
| Published catalogue of best practices and toolkits for diagnostics, training, etc. | 0 | After the experience of the farms reference the lessons learned in the process will be compiled in one catalog | 1 catalogue of best practices for adaptation to CC and variability in the livestock sector.
| Positive peer and stakeholder reviews of funded studies and research projects. | 0 | Studies and projects identified: resilience indicators (SARAS), resilient intensification in livestock sector (FAGRO, IPA), coinnovation methodology on farm (FAGRO-INIA), impact of extension methodology on decisión making for risk managment (UFFIP), MEGANE: simulation tools for decisión support on farm level (IPA), grassland and mapping states (FCIEN) | Research projects, case studies and assessment studies funded by the project received positive reviews from peers.
| Increased awareness among the rural population about CC and variability, according to specific surveys. | 0 | Conducted awareness activities about the CC and variability problem. At the End of the project specific surveys will be implemented to measure the impact on awareness. | Study on the level of awareness of CC and variability at the Landscape Unit level.

## Lessons Learned
QUALITATIVE MEASURES and LESSONS LEARNED
Please complete the following section every reporting period
Implementation and Adaptive Management | Response
What implementation issues/lessons, either positive or negative, affected progress? | Implementing agencies have an important role to play to streamline procedures and enforcement actions paper. Execution based on agreements with public institutes of private law expedites procedures
Were there any delays in implementation? If so, include any causes of delays. What measures have been taken to reduce delays? | Yes, there were delays in bureaucratic delays cuasa the effects of having agreements with partner institutions operating procedures. forms of cooperation with partners that made feasible the implementation of activities before the arrival of the funds were sought
Describe any changes undertaken to improve results on the ground or any changes made to project outputs (i.e. changes to project design) | Tools support for technical assistance (field notebook and field notebook) and adjustments in the submission form farm projects that pointed in the direction of giving more relavancia aspects of livestock management and natural field were developed. These elements are considered key to strengthening resliliencia of family farming systems.
How have gender considerations been taken into consideration during the reporting period? What have been the lessons learned as a consequence of inclusion of such considerations on project performance or impacts? | The proposals where the recipient was a woman counted in the evaluation grid with a higher percentage than if it was male. Anyway it was that this was not enough, so you think make a call specific to women
Please complete the following section at mid-term and project completion
Lessons for Adaptation | Response
Climate Resilience Measures
What have been the lessons learned, both positive and negative, in implementing climate adaptation measures that would be relevant to the design and implementation of future projects/programmes for enhanced resilience to climate change? | Actions concerning property taxes improve infrastructure are necessary but not sufficient for the purposes of improving the resilience of systems. It is necessary to strengthen public outreach strategies with a long-term vision
What is the potential for the climate resilience measures undertaken by the project/programme to be replicated and scaled up both within and outside the project area? | The potential of the measures is good, especially when it comes to measures of water and shade / shelter for livestock. It should think of strategies escalation of technical assistance in livestock management measures and grassland
Concrete Adaptation Interventions
What have been the lessons learned, both positive and negative, in implementing concrete adaptation interventions that would be relevant to the design and implementation of future projects/programmes implementing concrete adaptation interventions? | Greater emphasis is needed on management measures rodeo and grazing. It is necessary to continue to improve the mechanisms of reporting and verification (MRV). The field notebook eleborado during the project as an input for technicians is a preliminary step in this direction
What is the potential for the concrete adaptation interventions undertaken by the project/programme to be replicated and scaled up both within and outside the project area? | The potential impact of the measures in handling is very high. This demonstrated by other interventions that low-cost measures can have high productive impact on the livestock breeding sector.
Community/National Impact
What would you consider to be the most successful aspects for the target communities? | Improved building infrastructure, which reduces the negative impact of future droughts
What measures are/have been put in place to ensure sustainability of the project/program results? | Working with tables development seeking to continue the process of territorial development. On the other hand the gestation of new projects that will continue the intervention in the future.
What measures are being/could have been put in place to improve project/program results? | The baseline research and implementation of the network of reference farms.
Knowledge Management
How has existing information/data/knowledge been used to inform project development and implementation? What kinds of information/data/knowledge were used? | MGAP secondary information: Census 2000 and 2011 surveys. Information generated from the baseline survey assessment team generated with MGAP policy and Faculty of Agronomy. Project tracking information (UGP). The information used and relieved refers to characteristics of production systems when it comes to resources (land, labor, improvements), pracices management, use of information and links to networks of different types.
If learning objectives have been established, have they been met? Please describe. | Yes, it has succeeded in internalizing the MGAP the need to create a learning environment based on research-participation processes. They have generated agreements with partner institutions in order to install the network of reference farms
Describe any difficulties there have been in accessing or retrieving existing information (data or knowledge) that is relevant to the project. Please provide suggestions for improving access to the relevant data. | Difficulties intraministerial access to information by the absence of automatic mechanisms for obtaining it had to. These restrictions have been partially lifted creating new mechanisms between offices, which have viablizado obtaining essential information.
Has the identification of learning objectives contributed to the outcomes of the project? In what ways have they contributed? | Slowly changes are displayed in the perception of the producers on the farm problem. Specifically they begin to see that the property tax improved infrastructure is not the main constraint to improving production indicators, income and resilience, but must undertake changes in the management system. Punctually in handling rodeo (entore dates, revisación bull, analysis of gestation) in the nutritional management (supplementation recría) and cargo handling in time and space. In some producer groups begin to observe these changes on the perception of the need for technical advice in this regard. These groups will be the main partners to promote the network of reference farms

## Results Tracker
Results Tracker for Adaptation Fund (AF) Projects
Goal: Assist developing-country Parties to the Kyoto Protocol that are particularly vulnerable to the adverse effects of climate change in meeting the costs of concrete adaptation projects and programmes in order to implement climate-resilient measures. Impact: Increased resiliency at the community, national, and regional levels to climate variability and change.
Important: Please read the following guidance document (also posted on the Adaptation Fund website) before entering your data
Link: http://www.adaptation-fund.org/sites/default/files/Results%20Framework%20and%20Baseline%20Guidance%20final.pdf
Adaptation Fund Strategic Results Framework
Project ID | URY/NIE/Agri/2011/1
Implementing Entity | ANII
Type of implementing entity
Country | Uruguay
Region | Latin America and Caribbean
Sector | Agriculture
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Impact: Increased resiliency at the community, national, and regional levels to climate variability and change | Core Indicator: No. of beneficiaries |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project
|  | Total | 2100 | 1400 | 700 | Total | 2100 | 1400 | 700 | Total | 1284 | 856 | 428 | Total
|  | % of female beneficiaries | 21% | 25% | 15% | % of female beneficiaries | 21% | 25% | 15% | % of female beneficiaries | 21% | 25% | 15% | % of female beneficiaries
|  | % of Youth beneficiaries | 10% | 10% | 10% | % of Youth beneficiaries | 10% | 10% | 10% | % of Youth beneficiaries | 10% | 10% | 10% | % of Youth beneficiaries
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 1: Reduced exposure to climate-related hazards and threats | Indicator 1: Relevant threat and hazard information generated and disseminated to stakeholders on a timely basis | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness
|  | Total | 4500 | Drought | 2: Partially effective | Total | 4500 | Drought | 4: Effective | Total | 856 | Drought | 3: Moderately effective | Total
|  | % of female targeted | 25% |  |  | % of female targeted | 25% |  |  | % of female targeted | 25% |  |  | % of female targeted
Output 1.1 Risk and vulnerability assessments conducted and updated | Indicator 1.1: No. of projects/programmes that conduct and update risk and vulnerability assessments | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | , | Scale | Status
|  | 1 | Agriculture | Regional | 2: Undertaking or updating of assessments in progress | 2 | Agriculture | Regional | 3: Risk and vulnterability assessments completed or updated | 2 | Agriculture | Regional | 2: Undertaking or updating of assessments in progress
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
Output 1.2 Targeted population groups covered by adequate risk reduction systems | Core Indicator 1.2: No. of Early Warning Systems | No. of adopted Early Warning Systems | Category targeted | Hazard | Wind | No. of adopted Early Warning Systems | Category targeted | Hazard | Wind | No. of adopted Early Warning Systems | Category targeted | Hazard | Wind | No. of adopted Early Warning Systems | Category targeted | Hazard
|  | 1 | 2: Monitoring and warning service | Geographical coverage | National | 1 | 2: Monitoring and warning service | Geographical coverage | National | 1 | 2: Monitoring and warning service | Geographical coverage | National |  |  | Geographical coverage
|  |  |  | Number of municipalities | 19 |  |  | Number of municipalities | 19 |  |  | Number of municipalities | 19 |  |  | Number of municipalities
|  | No. of adopted Early Warning Systems | Category targeted | Hazard | Drought | No. of adopted Early Warning Systems | Category targeted | Hazard | Drought | No. of adopted Early Warning Systems | Category targeted | Hazard | Drought | No. of adopted Early Warning Systems | Category targeted | Hazard
|  | 1 | 3: Dissemination and communication | Geographical coverage | National | 1 | 4: Response capability | Geographical coverage | Regional | 1 | 3: Dissemination and communication | Geographical coverage | Regional |  |  | Geographical coverage
|  |  |  | Number of municipalities | 19 |  |  | Number of municipalities | 8 |  |  | Number of municipalities | 8 |  |  | Number of municipalities
|  | No. of adopted Early Warning Systems | Category targeted | Hazard | Inland flooding | No. of adopted Early Warning Systems | Category targeted | Hazard | Inland flooding | No. of adopted Early Warning Systems | Category targeted | Hazard | Inland flooding | No. of adopted Early Warning Systems | Category targeted | Hazard
|  | 1 | 3: Dissemination and communication | Geographical coverage | National | 1 | 3: Dissemination and communication | Geographical coverage | Regional | 1 | 3: Dissemination and communication | Geographical coverage | Regional |  |  | Geographical coverage
|  |  |  | Number of municipalities | 19 |  |  | Number of municipalities | 8 |  |  | Number of municipalities | 8 |  |  | Number of municipalities
|  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 2: Strengthened institutional capacity to reduce risks associated with climate-induced socioeconomic and environmental losses | Indicator 2: Capacity of staff to respond to, and mitigate impacts of, climate-related events from targeted institutions increased | Number of staff targeted |  | Sector | Capacity level | Number of staff targeted |  | Sector | Capacity level | Number of staff targeted |  | Sector | Capacity level | Number of staff targeted |  | Sector | Capacity level
|  | Total | 150 | Agriculture | 3: Medium capacity | Total | 200 | Agriculture | 4: High capacity | Total | 175 | Agriculture | 3: Medium capacity | Total
|  | % of female targeted | 10% |  |  | % of female targeted | 25% |  |  | % of female targeted | 20% |  |  | % of female targeted
Output 2.1 Strengthened capacity of national and sub-national centres and networks to respond rapidly to extreme weather events | Indicator 2.1.1: No. of staff trained to respond to, and mitigate impacts of, climate-related events | Total staff trained | % of female staff trained | Type |  | Total staff trained | % of female staff trained | Type |  | Total staff trained | % of female staff trained | Type |  | Total staff trained | % of female staff trained | Type
|  | 50 | 10% | Public |  | 100 | 25% | Public |  | 75 | 20% | Public
| Indicator 2.1.2: No. of targeted institutions with increased capacity to minimize exposure to climate variability risks | Type | Scale | Sector | Capacity level | Type | Scale | Sector | Capacity level | Type | Scale | Sector | Capacity level | Type | Scale | Sector | Capacity level
|  | Private | Regional | Agriculture | 2: Low capacity | Private | Regional | Agriculture | 4: High capacity | Private | Regional | Agriculture | 3: Medium capacity
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 3: Strengthened awareness and owernship of adaptation and climate risk reduction processes | Indicator 3.1: Increase in application of appropriate adaptation responses | Percentage of targeted population applying adaptation measures |  | Sector |  | Percentage of targeted population applying adaptation measures |  | Sector |  | Percentage of targeted population applying adaptation measures |  | Sector |  | Percentage of targeted population applying adaptation measures |  | Sector
|  | 24% |  | Agriculture |  | 70% |  | Agriculture |  |  |  | Agriculture
Output 3: Targeted population groups participating in adaptation and risk reduction awareness activities | Indicator 3.1.1: Percentage of targeted population awareness of predicted adverse impacts of climate change, and of appropriate responses | No. of targeted beneficiaries | % of female participants targeted | Level of awareness |  | No. of targeted beneficiaries | % of female participants targeted | Level of awareness |  | No. of targeted beneficiaries | % of female participants targeted | Level of awareness |  | No. of targeted beneficiaries | % of female participants targeted | Level of awareness
|  | 42% | 25% | 2: Partially not aware |  |  | 25% | 4: Mostly aware
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Target performance at completion
Outcome 4: Increased adaptive capacity within relevant development sector services and infrastructure assets | Indicator 4.1: Increased responsiveness of development sector services to evolving needs from changing and variable climate | Project/programme sector | Geographical scale | Response level |  | Project/programme sector | Geographical scale | Response level |  | Project/programme sector | Geographical scale | Response level |  | Project/programme sector | Geographical scale | Response level
|  | Agriculture | National | 2: Partially responsive (Lacks most elements) |  | Agriculture | Regional | 4: Mostly responsive (Most defined elements) |  | Agriculture | Regional | 3: Moderately responsive (Some defined elements)
| Core Indicator 4.2: Assets produced, developed, improved or strengthened | Sector | Targeted asset | Changes in asset (quantitative or qualitative) |  | Sector | Targeted asset | Changes in asset (quantitative or qualitative) |  | Sector | Targeted asset | Changes in asset (quantitative or qualitative) |  | Sector | Targeted asset | Changes in asset (quantitative or qualitative)
|  | Agriculture | 2: Physical asset (produced/improved/strenghtened) | 2: Somewhat improved |  | Agriculture | 2: Physical asset (produced/improved/strenghtened) | 4: Mostly Improved |  | Agriculture | 2: Physical asset (produced/improved/strenghtened) | 3: Moderately improved
Output 4: Vulnerable development sector services and infrastructure assets strengthened in response to climate change impacts, including variability | Indicator 4.1.1: No. and type of development sector services to respond to new conditions resulting from climate variability and change | Number of services | Type |  | Sector | Number of services | Type |  | Sector | Number of services | Type |  | Sector | Number of services | Type |  | Sector
|  | 1 | Departmental |  | Agriculture | 1 | Departmental |  | Agriculture | 1 | Departmental |  | Agriculture
|  | Baseline information |  |  |  | Baseline information |  |  |  | Performance at mid-term |  |  |  | Target performance at completion
Outcome 5: Increased ecosystem resilience in response to climate change and variability-induced stress | Indicator 5: Ecosystem services and natural resource assets maintained or improved under climate change and variability-induced stress | Natural resource improvement level |  | Sector | Type | Natural resource improvement level |  | Sector | Type | Natural resource improvement level |  | Sector | Type | Natural resource improvement level |  | Sector | Type
|  | 1: Ineffective |  | Agriculture | biological assets | 3: Moderately effective | 3 | Agriculture | biological assets | 2: Partially effective | 2 | Agriculture | biological assets
Output 5: Vulnerable ecosystem services and natural resource assets strengthned in response to climate change impacts, including variability | Core Indicator 5.1: Natural Assets protected or rehabilitated | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Rangelands | 300000 | ha rehabilitated | 1: Ineffective | Rangelands | 300000 | ha rehabilitated | 3: Moderately effective | Rangelands | 300000 | ha protected | 2: Partially effective
|  | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Baseline information |  |  |  | Targeted performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 6: Diversified and strengthened livelihoods and sources of income for vulnerable people in targeted areas | Indicator 6.1: Increase in households and communities having more secure access to livelihood assets | No. of targeted households | % of female headed households | Improvement level |  | No. of targeted households | % of female headed households | Improvement level |  | No. of targeted households | % of female headed households | Improvement level |  | No. of targeted households | % of female headed households | Improvement level
|  | 1400 | 10% | 2: Limited improvement |  | 1400 | 25% | 4: High improvement |  | 1400 | 17% | 3: Moderate improvement
| Indicator 6.2: Increase in targeted population's sustained climate-resilient alternative livelihoods | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
|  | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
|  | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
|  | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
Output 6 Targeted individual and community livelihood strategies strengthened in relation to climate change impacts, including variability | Indicator 6.1.1: No. and type of adaptation assets created or strengthened in support of individual or community livelihood strategies | Number of Assets | Type of Assets | Sector | Adaptation strategy | Number of Assets | Type of Assets | Sector | Adaptation strategy | Number of Assets | Type of Assets | Sector | Adaptation strategy | Number of Assets | Type of Assets | Sector | Adaptation strategy
|  | 1400 | Adaptation strategies | Agriculture | Water storage | 1400 | Adaptation strategies | Agriculture | Water storage |  | Adaptation strategies | Agriculture | Water storage
| Core Indicator 6.1.2: Increased income, or avoided decrease in income | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | 1400 | Agriculture |  | 9000 | 1400 | Agriculture |  | 11000 | [8 empty] | There is not data in impact on net income so far. Data will be available after the second survey at the end of the project
|  | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 7: Improved policies and regulations that promote and enforce resilience measures | Indicator 7: Climate change priorities are integrated into national development strategy | Integration level |  |  |  | Integration level |  |  |  | Integration level |  |  |  | Integration level
4: Most
Output 7:Improved integration of climate-resilience strategies into country development plans | Indicator 7.1: No. of policies introduced or adjusted to address climate change risks | No. of Policies introduced or adjusted | Sector | Scale | Type | No. of Policies introduced or adjusted | Sector | Scale | Type | No. of Policies introduced or adjusted | Sector | Scale | Type | No. of Policies introduced or adjusted | Sector | Scale | Type
|  | 1 | Agriculture | National | Public policy | 1 | Agriculture | Regional | public | 1 | Agriculture | Regional | public
|  | 1 | Agriculture | National | Water policy | 1 | Agriculture | Regional | water | 1 | Agriculture | Regional | water
| Indicator 7.2: No. of targeted development strategies with incorporated climate change priorities enforced | No. of Development strategies | Regulation |  | Effectiveness | No. of Development strategies | Regulation |  | Effectiveness | No. of Development strategies | Regulation |  | Effectiveness | No. of Development strategies | Regulation |  | Effectiveness
|  | 1 | 3: Partially enforced (Some elements implemented) |  | 3: Moderately effective | 1 | 4: Enforced (Most elements implemented) |  | 4: Effective | 1 | 3: Partially enforced (Some elements implemented) |  | 3: Moderately effective
Glacier lake outburst flood
|  | Inland flooding | fr | biological assets |  | Company policy | 5: Fully enforced (All elements implemented)
|  | Salinization | Decrease | land |  | Communication & Information policy | 4: Enforced (Most elements implemented)
|  | Drought | Same | water areas |  | Defense policy | 3: Partially enforced (Some elements implemented)
|  | Wind |  | subsoil assets | increased adpative capacity | Domestic policy | 2: Partially not enforced (Most elements not implemented) |  | Agribusiness
|  | Coastal flooding |  | air | achieved | Economic policy | 1: Not enforced (No elements implemented) |  | Agricultural-related | Financial capital
|  | Storm surge | Please choose |  | enhanced level of protection | Education policy |  |  | Agriculture | Human capital
|  | Hurricane | Selected | [5 empty] | Aquaculture | Physical capital
|  |  | Not relevant |  |  | 5: All (Fully integrated) |  |  | Construction/repairing business | Social capital
[6 empty] | 4: Most |  |  | Cultivation | Natural capital
[6 empty] | 3: Some |  |  | Fishing | Personal capital
Select | 5: All | Select |  |  | Community | 2: Most not integrated |  | Other | Forestry | Adaptation strategies
1 | 4: Almost all | Private | Type | Yes | Multi-community | 1: None |  | Agriculture | Handicrafts
2 | 3: Half | Public | Scale | No | Departmental |  |  | Coastal management | Livestock production
3 | 2: Some | NGO | Sector |  | National |  |  | Disaster risk reduction | Manufacturing
4 | 1: None |  |  |  |  | 5: Very high improvement | Established | Food security | other
|  | National |  |  |  | 4: High improvement | Maintained | Health | Services
|  | Regional |  |  |  | 3: Moderate improvement | Improved | Urban development | Tourism-related
|  | Local |  |  |  | 2: Limited improvement |  | Water management | Trading
[6 empty] | 1: No improvement |  | Multi-sector
|  | 1 -generated information is irrelevant, and neither the stakeholders reached nor the timeframe managed were achieved | 1: No info transferred on time | 4: High capacity | 5: Fully aware | 5: Highly responsive (All defined elements ) | 5: Fully improved | Roads | 5: Very effective
Asia-Pacific | NIE | 2 -the existence of some challenge in any of the three aspects of the indicator (generation of dissemination, stakeholders reached or timeframe managed) | 2: Somewhat info transferred | 3: Medium capacity | 4: Mostly aware | 4: Mostly responsive (Most defined elements) | 4: Mostly Improved | Gov Buildings | 4: Effective
Latin America and Caribbean | RIE | 3 -relevant information is generated and disseminated to all identified stakeholders on timely basis | 3: Info transferred on time | 2: Low capacity | 3: Partially aware | 3: Moderately responsive (Some defined elements) | 3: Moderately improved | Causeways | 3: Moderately effective
Africa | MIE |  |  | 1: No capacity | 2: Partially not aware | 2: Partially responsive (Lacks most elements) | 2: Somewhat improved | Airports | 2: Partially effective
Eastern Europe |  |  |  |  | 1: Aware of neither | 1: Non responsive (Lacks all elements ) | 1: Not improved | Schools | 1: Ineffective
| ha protected | [6 empty] | Training Centres
| ha rehabilitated | [5 empty] | Monitoring/Forecasting capacity | Hospitals
Afghanistan, Islamic Rep. of | km protected | [5 empty] | Policy/regulatory reform | Drinking water systems
Angola | km rehabilitated | 1: Risk knowledge | 1: No plans conducted or updated |  |  |  | Capacity development | Other
Albania |  | 2: Monitoring and warning service | 2: Undertaking or updating of assessments in progress |  |  | Communication & Information policy | Sustainable forest management
Argentina |  | 3: Dissemination and communication | 3: Risk and vulnterability assessments completed or updated |  |  | Domestic policy | Strengthening infrastructure | 1: Health and Social Infrastructure (developed/improved)
Armenia | Forests | 4: Response capability |  |  |  | Economic policy | Supporting livelihoods | 2: Physical asset (produced/improved/strenghtened)
Antigua and Barbuda | Mangroves |  |  |  |  | Education policy | Mangrove reforestation
Azerbaijan | Coasts |  | From 0 to 0.5% |  |  | Energy policy | Coastal drainage and infrastructure
Burundi | Rangelands |  | From 0.5 to 1% |  |  | Environmental policy | Irrigation system
Benin | Cultivated land/Agricultural land |  | From 1% to 5% |  |  | Foreign policy | Community-based adaptation
Burkina Faso | Catchment area/Watershed/Aquifer |  | From 5% to 10% |  |  | Health policy | Erosion control
Bangladesh | Protected areas/National parks |  | From 10% to 20% |  |  | Housing policy | Soil water conservation
Bulgaria | Other |  | From 20% to 30% |  |  | Human resource policies | Microfinance
Bahrain |  |  | From 30% to 40% |  |  | Information policy | Special Program for women
Bahamas, The |  |  | From 40% to 50% |  |  | Macroeconomic policy | Livelihoods
Bosnia and Herzegovina |  |  | Above 50% |  |  | Monetary policy | Water storage
Belarus | [5 empty] | Population policy | ICT and information dissemination
Belize | [5 empty] | Private policy
Bolivia | [5 empty] | Public policy
Brazil | [5 empty] | Science policy
Barbados | [5 empty] | Social policy
Bhutan |  | 3- relevant information is generated and disseminated to all identified stakeholders on timely basis |  |  |  | Transportation policy
Botswana |  | describe |  |  |  | Urban policy
Central African Republic |  | 2- the existence of some challenge in any of the three aspects of the indicator |  |  |  | Water policy
Chile |  | describe |  |  |  | Other policy
China, People's Republic of |  | 1- generated information is irrelevant and neither the stakeholders reached nor the timeframe managed were achieved
Cote d'Ivoire |  | describe
Cameroon
Congo, Dem. Rep. of
Congo, Republic of
Cook Islands
Colombia
Comoros
Cape Verde
Costa Rica
Cuba
Czech Republic
Djibouti
Dominica
Dominican Republic
Algeria
Ecuador
Egypt
Eritrea
Estonia
Ethiopia
Fiji
Micronesia, Fed. States of
Gabon
Georgia
Ghana
Guinea
Gambia, The
Guinea-Bissau
Equatorial Guinea
Grenada
Guatemala
Guyana
Honduras
Croatia
Haiti
Hungary
Indonesia
India
Iran, Islamic Republic of
Jamaica
Jordan
Kazakhstan
Kenya
Kyrgyz Republic
Cambodia
Kiribati
Saint Kitts and Nevis
Korea, Republic of
Lao People's Democratic Republic
Lebanon
Liberia
Libya
Saint Lucia
Sri Lanka
Lesotho
Lithuania
Latvia
Morocco
Moldova
Madagascar
Maldives
Mexico
Marshall Islands
Macedonia, former Yugoslav Republic of
Mali
Malta
Myanmar
Montenegro
Mongolia
Mozambique
Mauritania
Mauritius
Malawi
Malaysia
Namibia
Niger
Nigeria
Nicaragua
Niue
Nepal
Nauru
Oman
Pakistan
Panama
Peru
Philippines
Palau
Papua New Guinea
Poland
Korea, Dem. People's Rep. of
Paraguay
Romania
Russian Federation
Rwanda
Saudi Arabia
Sudan
Senegal
Solomon Islands
Sierra Leone
El Salvador
San Marino
Serbia
Sao Tome and Principe
Suriname
Slovak Republic
Slovenia
Swaziland
Seychelles
Syrian Arab Republic
Chad
Togo
Thailand
Tajikistan
Turkmenistan
Tonga
Trinidad and Tobago
Tunisia
Turkey
Tuvalu
Tanzania
Uganda
Ukraine
Uruguay
Uzbekistan
Saint Vincent and the Grenadines
Venezuela
Vietnam
Vanuatu
Samoa
Yemen, Republic of
South Africa
Zambia
Zimbabwe
Timor-Leste
Note on B8: opypa: ingresamos pero da error 404
Note on F21: opypa: revisar el total de benefi no serian 1400?
Note on G21: opypa: relacion 1:1?
Note on N21: opypa: BARALDO PASA EL Nº ACTUAL DE BENEF
Note on K27: opypa: lo subimos a efectivo
Note on M27: opypa: VERIFICAR BARALDO
Note on E28: opypa: en cuanto a la proporcion de mujeres nos queda la duda si en este caso no es l 100
Note on E40: opypa: son las de inumet que ya existian, pero son para eventos de temporal u olas de calor, no para squias
Note on K42: opypa:
Note on E43: opypa: pronosticos estacionales enso de gras e inumet
Note on E54: opypa: revisar con los numeros de tecnicos de dgdr mas opypa 3 mas ipa 20. seran 150
Note on D63: UACC: de la encuesta sale que este 24% es el que tiene un indice de practicas de adaptación "bueno"
Note on D65: uacc DE LA ENCUESTA SALE QUE EL 42% SE SIENTE PREPARADO PARA AFRONTAR SEQUIA HAY QUE HACER EL Nº
Note on H65: UACC_ A COMPLETAR CON BARALDO
Note on E89: opypa: BARALDO NOS PASE EL DATO DE HA CUBIERTAS CON BENEFICIARIOS
Note on D103: opypa: poner la cantidad total de prod fam de las dos up
Note on C104: opypa: NO APLICA A ESTE PROYECTO NO H AY DIVERSIFICACION DE ESTRATEGIAS
Note on C112: opypa: a responder con anii, no cuadraria en este proyecto
Note on L113: opypa: BARALDO PASA Nº DE SOLUCIONES DE AGUA
Note on G115: opypa: al año producto de ingreso neto de 30 por ha por año
Note on E128: opypa: los ppr anteriores tajamares etc

## Units for Indicators
Fund Outcome Indicator Units
1. Generation of relevant data, Stakeholders, and Timeliness 2.1. Include both qualitative and quantitative measures of capacity level within targeted institutions 2.2. Number (men and women and other vulnerable groups) 3.1. Use scale from 1 to 5: 5: Fully aware 4: Mostly aware 3: Partially aware 2: Partially not aware 1: Aware of neither predicted adverse impacts of climate change nor of appropriate responses 3.2. Use scale from 1 to 5: 5: All 4: Almost all 3: Half 2: Some 1: None 4.1. Summarize in an overall scale (1-5): 5: Highly responsive (All defined elements ) 4: Mostly responsive (Most defined elements) 3: Moderately responsive (Some defined elements) 2: Partially responsive (Lacks most elements) 1: Non responsive (Lacks all elements ) 4.2. Summarize in an overall scale (1-5): 5: Fully improved 4: Mostly Improved 3: Moderately improved 2: Somewhat improved 1: Not improved 5. Depends on the targeted natural asset: Biological (species): measure through changes in population numbers (dynamics, structure, etc.) Land: measure changes in hectares. Baseline data will be necessary to estimate the change. Supporting indicators baseline and target (as well as contextual information) are needed such as the following: Farmers adopting recommended technologies, Ha. of land improved, Average deforestation rate Etc. Use scale from 1 to 5. 5: Very effective (All elements are present) 4: Effective (Most elements are present) 3: Moderately effective (Some elements are present) 2: Partially effective (Most elements are not present) 1: Ineffective (No elements are present) 6.1. Summarize in an overall scale (1-5): 5: Very high improvement 4: High improvement 3: Moderate improvement 2: Limited improvement 1: No improvement 6.2. Household income by source of livelihood in project area (USD) prior and post project intervention 7. Summarize in an overall scale (1-5). 5: All (Fully integrated) 4: Most 3: Some 2: Most not integrated 1: None
Fund Output Indicator Units
1.1. Number, sector(s) and level(s) of projects or interventions in separate fields of monitoring plan 1.2. Number 2.1.1. Number of staff (male/female) of targeted institutions: a. Obtain baseline information: total number of staff from targeted institutions b. Define target 2.1.2. Number of staff (male/female) of targeted institutions: a. Obtain baseline information: total number of staff from targeted institutions b. Define target: needs to be defined by project proponents 2.2.1. Quantitative: Percentage (includes women – and other vulnerable groups – and men). Qualitative: Adequacy: include direct analysis of major areas; adequacy/effectiveness of systems or analysis of perceptions of populations and institutions. 2.2.2. Number (broken down by gender and, if possible, by vulnerable groups defined in the area of intervention) of people 3.1. Number and type (in separate columns) at local level. 3.2. Number 4.1. Number and type 4. 2. Number and type (entered in separate columns) 5. Number of interventions by type of natural asset and intervention 6.1. Number and type (in separate columns of monitoring plan) 6.2. Income sources per household; description of income source and number of households. 7.1. Number/Sector 7.2. Number; Effectiveness (see previous indicator) through enforcement level.