## Overview
Project Performance Report (PPR)
| Period of Report (Dates) | January-September 2016
| Project Title: | Developing agro-pastoral shade gardens as an adaptation strategy for poor rural communities
| Project Summary: | The project aims to help the rural pastoral communities of Djibouti to adapt to climate change by the development of climate resilient shade gardens. The overall objective of the project is to diversify and promote climate resilient agro-pastoral practices in rural Djibouti. The project aims to achieve this objective trough three outcomes: (1) Capacities to mobilize and secure sustainable water resources to agro-pastoral communities developed in the face of climate change; (2) Sustainable agro-pastoral systems developed, providing greater forage production capacities, diversifying agricultural productions and creating capacities for replication; (3) Microfinance products developed to facilitate and promote diversified and climate resilient agro-pastoral production systems.
|  |  | Countries | Project Type: |  | GEF Focal Area: | GEF 4 Focal Areas | GEF 2 / 3 Operational Programme: | Overall Rating of the project in the evaluation by the project evaluator: | GEF-4 Focal Area Strategic Program: | GEF-3 Focal Area Strategic Program:
| Database Number: | 4683 | Afghanistan | FP | Yes | Biodiversity | 1 | 1 | U | BD-SP1-PA Financing | 1: Arid & semi-arid ecosystems
Implementing Entity (IE) [name]: |  | United Nations Development Program | Albania | MSP | No | Climate Change Adaptation | 2 | 2 | S | BD-SP2-Marine PA | 2: Coastal, marine & freshwater ecosystems
| Type of IE: | MIE | Algeria | EA |  | Climate Change Mitigation | 3 | 3 | MU | BD-SP3-PA Networks | 3: Forest ecosystems
| Country(ies): | Djibouti | Angola |  |  | International Waters | 5 | 5 | Good | BD-SP5-Markets | 13: Conservation and Sustainable Use of Biological Diversity Important to Agriculture
Relevant Geographic Points (i.e. cities, villages, bodies of water): |  | Grand Bara and Petit Bara (Kourtimalei) | Argentina |  |  | Multiple Focal Area |  |  |  | BD-SP7-Invasive Alien Species(IAS) | 6: Promoting the adoption of renewable energy by removing barriers and reducing implementation costs
[8 empty] | CC-SP2- Industrial EE | 8: Waterbody based operational program
| Project Milestones | [6 empty] | CC-SP3-RE,CC-SP4-Biomass | 9: Integrated Land and Water multiple focal area
| Milestone |  | Bahamas | [6 empty] | CC-SP5-Transport | 10: Contaminants based operational program
AFB Approval Date: |  | 11 July 2012
IE-AFB Agreement Signature Date: |  | 2012-08-13 | [6 empty] | CC-SP6-LULUCF | 12: Integrated Ecosystem Management
Start of Project/Programme: |  | September 2012 | [6 empty] | Cross cutting capacity building | 14: Persistent Organic Pollutants
Mid-term Review Date (if planned): |  | 2014-09-30
| Terminal Evaluation Date: | 2017-08-31
|  | List documents/ reports/ brochures / articles that have been prepared about the project. | Cyprus
|  | www.projetbara.com. Brochures. Poster. Article in newspaper and TV journal (http://www.djibnet.com/news/rtd/) | Czech Republic
List the Website address (URL) of project. |  |  | Democratic People's Republic of Korea
|  | www.projectbara.com | Democratic Republic of the Congo
Denmark
| Project contacts: |  | Djibouti
National Project Manager/Coordinator |  |  | Dominica
| Name: | Houssein Rirache Robleh | Dominican Republic
| Email: | housseinrirach@yahoo.fr | Ecuador
| Date: | 2016-08-20 | Egypt
| Government DA |  | El Salvador
| Name: | Dini Abdallah Omar | Equatoral Guinea
| Email: | dini_omar@yahoo.fr | Eritrea
| Date: | 2016-09-25 | Estonia
| Implementing Entity |  | Ethiopia
| Name: | Idriss Ahmed Hared | Fiji
| Email: | idriss.hared@undp.org | Finland
| Date: | 2015-08-30 | France
| Executing Agency |  | Gambia
| Name: | Ministry of Habitat, Urbanism and Environment | Georgia
| Email: | housseinrirach@yahoo.fr | Germany
| Date: |  | Ghana
| Executing Agency |  | Greece
| Name: |  | Grenada
| Email: |  | Guatemala
| Date: |  | Guinea
| Executing Agency |  | Guinea Bissau
| Name: |  | Guyana
| Email: |  | Haiti
| Date: |  | Honduras
Hungary
Iceland
India
Indonesia
Iran (Islamic Republic of)
Iraq
Ireland
Israel
Italy
Jamaica
Japan
Jordan
Kazakhstan
Kenya
Kiribati
Kuwait
Kyrgyzstan
Lao People’s Democratic Republic
Latvia
Lebanon
Lesotho
Liberia
Libyan Arab Jamahiriya
Liechtenstein
Lithuania
Luxembourg
Madagascar
Malawi
Malaysia
Maldives
Mali
Malta
Marshall Islands
Mauritania
Mauritius
Mexico
Micronesia, Federated States of
Monaco
Mongolia
Montenegro
Morocco
Mozambique
Myanmar
Namibia
Nauru
Nepal
Netherlands
New Zealand
Nicaragua
Niger
Nigeria
Norway
Oman
Pakistan
Palau
Panama
Papua New Guinea
Paraguay
Peru
Philippines
Poland
Portugal
Qatar
Republic of Korea
Republic of Moldova
Romania
Russian Federation
Rwanda
Saint Kitts and Nevis
Saint Lucia
Saint Vincent and the Grenadines
Samoa
San Marino
Sao Tome and Principe
Saudi Arabia
Senegal
Serbia
Seychelles
Sierra Leone
Singapore
Slovakia
Slovenia
Solomon Islands
Somalia
South Africa
Spain
Sri Lanka
Sudan
Suriname
Swaziland
Sweden
Switzerland
Syrian Arab Republic
Tajikistan
Thailand
The former Yugoslav Republic of Macedonia
Timor-Leste
Togo
Tonga
Trinidad and Tobago
Tunisia
Turkey
Turkmenistan
Tuvalu
Uganda
Ukraine
United Arab Emirates
United Kingdom of Great Britain and Northern Ireland
United Republic of Tanzania
United States of America
Uruguay
Uzbekistan
Vanuatu
Venezuela, Bolivarian Republic of
Viet Nam
Yemen
Zambia
Zimbabwe

## FinancialData
Financial information: cumulative from project start to [30/09/2016]
DISBURSEMENT OF AF GRANT FUNDS
How much of the total AF grant as noted in Project Document plus any project preparation grant has been spent to date?
Estimated cumulative total disbursement as of 30/09/2016 | 2531645
Add any comments on AF Grant Funds. (word limit=200) | The overall delivery of the project is 58% compared to total project budget. Regarding the actual reporting period, the expenses are 64% of the money released. The remaining amount of money is entirely committed and already being subject of procurement. It is expected that the work will be completed over the next 3 months.
INVESTMENT INCOME
Amount of annual investment income generated from the Adaptation Fund’s grant
EXPENDITURE DATA
List ouput and corresponding amount spent for the current reporting period | ITEM / ACTIVITY / ACTION | AMOUNT
| Output 1.1. Rainfall-runoff and groundwater models developed and institutionalized within the Study and Research Center of Djibouti (Centre d’Etudes et de la Recherche de Djibouti, CERD ) and the Water Department of the Ministry of Agriculture to project likely climate change impacts on the water availability in the areas of Petit Bara and Grand Bara | 0
| Output 1.2: Based on model outputs, controlled groundwater extraction, artificial recharge and climate “smart” management plans that take into account seasonal changes in precipitation as well as long term mean amounts, projections, developed, and benefiting 30,000 people | 197105
| Output 1.3: Community-based surface water harvesting infrastructures, such as earth dams, percolation basins and subsurface dams which increase surface supply and groundwater tables in support of shade-garden pilot schemes (see 2.1) introduced and related local management rules and structures established | 102130
| Output 1.4: Good practice guidelines based on knowledge sharing for integrated groundwater and surface water maintenance and use developed through stakeholder-led and participatory processes including community water management teams, government water regulators, Ministry’s technical staff, and agriculture extension services | 7104
| Output 2.1: Six sets of 38 pilot community-managed agro-pastoral shade garden plots (1 ha per family) established that includes date palms, multi-purpose fence trees, local and regional varieties of climate resilient forage, vegetables and fruits (henna, dates, jujube, and mango, etc) benefiting 228 agro-pastoral families - approximately 2,800 people | 190170
| Output 2.2: Improved extension service for shade gardening benefiting 228 agro-pastoral families - approximately 2,800 people (targeted training for extension service personnel and agro-pastoralists designed and delivered on the issues grazing, forage management, cultivation techniques, crop protection, water efficiency, composting methods, etc, in the context of increasing climate change pressures) | 47465
| Output 2.3. Well-sized feed/forage stocking facilities created in both project locations to allow better management of forage availability over repeated drought periods | 46000
| Output 3.1: A three-tiered adaptation-oriented micro-finance scheme that supports climate-resilient shade gardening practices in the Grand and Petit Bara plains developed through partnership with the Djiboutian Agency for Social Development (Agence Djiboutienne de Developpement Sociale, ADDS ) which generates a total value of US$ 300,000 throughout the project | 10250
| Output 3.2: At least 300 agro-pastoralists have been organised to form agro-pastoral cooperatives (including women cooperatives) to facilitate training on climate-resilient agro-pastoral practices and to support the development of financial literacy and the diversification of agricultural activities | 22549
| Output 3.3: At least 4 established agro-pastoral cooperatives develop comprehensive climate adaptation plans incorporating lessons learned on best practices for shade gardens to be integrated into the National Programme for Food Security and the National Microfinance Policy in order to facilitate the replication of shade-garden-based adaptation solutions | 7878
| Project Execution cost | 25206
| TOTAL | 655857
PLANNED EXPENDITURE SCHEDULE
List outputs planned and corresponding projected cost for the upcoming reporting period | ITEM / ACTIVITY / ACTION | PROJECTED COST | Est. Completion Date
| Output 1.1. Rainfall-runoff and groundwater models developed and institutionalized within the Study and Research Center of Djibouti (Centre d’Etudes et de la Recherche de Djibouti, CERD ) and the Water Department of the Ministry of Agriculture to project likely climate change impacts on the water availability in the areas of Petit Bara and Grand Bara | 0
| Output 1.2: Based on model outputs, controlled groundwater extraction, artificial recharge and climate “smart” management plans that take into account seasonal changes in precipitation as well as long term mean amounts, projections, developed, and benefiting 30,000 people | 0
| Output 1.3: Community-based surface water harvesting infrastructures, such as earth dams, percolation basins and subsurface dams which increase surface supply and groundwater tables in support of shade-garden pilot schemes (see 2.1) introduced and related local management rules and structures established | 165000
| Output 1.4: Good practice guidelines based on knowledge sharing for integrated groundwater and surface water maintenance and use developed through stakeholder-led and participatory processes including community water management teams, government water regulators, Ministry’s technical staff, and agriculture extension services | 15000
| Output 2.1: Six sets of 38 pilot community-managed agro-pastoral shade garden plots (1 ha per family) established that includes date palms, multi-purpose fence trees, local and regional varieties of climate resilient forage, vegetables and fruits (henna, dates, jujube, and mango, etc) benefiting 228 agro-pastoral families - approximately 2,800 people | 300000
| Output 2.2: Improved extension service for shade gardening benefiting 228 agro-pastoral families - approximately 2,800 people (targeted training for extension service personnel and agro-pastoralists designed and delivered on the issues grazing, forage management, cultivation techniques, crop protection, water efficiency, composting methods, etc, in the context of increasing climate change pressures) | 82960
| Output 2.3. Well-sized feed/forage stocking facilities created in both project locations to allow better management of forage availability over repeated drought periods | 30000
| Output 3.1: A three-tiered adaptation-oriented micro-finance scheme that supports climate-resilient shade gardening practices in the Grand and Petit Bara plains developed through partnership with the Djiboutian Agency for Social Development (Agence Djiboutienne de Developpement Sociale, ADDS ) which generates a total value of US$ 300,000 throughout the project | 15000
| Output 3.2: At least 300 agro-pastoralists have been organised to form agro-pastoral cooperatives (including women cooperatives) to facilitate training on climate-resilient agro-pastoral practices and to support the development of financial literacy and the diversification of agricultural activities | 75000
| Output 3.3: At least 4 established agro-pastoral cooperatives develop comprehensive climate adaptation plans incorporating lessons learned on best practices for shade gardens to be integrated into the National Programme for Food Security and the National Microfinance Policy in order to facilitate the replication of shade-garden-based adaptation solutions | 15000
| Output :Project Execution cost | 36000
| TOTAL | 733960
ACTUAL CO-FINANCING (If the MTR or TE have not been undertaken this reporting period, DO NOT report on actual co-financing.)
How much of the total co-financing as committed in the Project Document has actually been realized?
Estimated cumulative actual co-financing as verified during Mid-term Review (MTR) or Terminal Evaluation (TE).
Add any comments on actual co-financing in particular any issues related to the realization of in-kind, grant, credits, loans, equity, non-grant instruments and other types of co-financing. (word limit=200)

## Risk Assesment
RISK ASSESMENT
IDENTIFIED RISKS
List all Risks identified in project preparation phase and what steps are being taken to mitigate them
Identified Risk | Current Status | Steps Taken to Mitigate Risk
Reluctance of farmers or pastoralists to engage in agro-pastoralist practices of shade gardens | Low/Decreasing | After several years of implementation, the project is no longer experiencing any reluctance of pastoralists to engage in agro-pastoral activities. The agro-pastoralism is seen by the communities as a viable means of livelihoods.
Repeated drought | Low/Decreasing | After the protracted drought period (2007-2011), the rain situation is better in the country. To better manage the available quantity of water even in the event of repeated droughts, the project management unit has undertaken a work on collecting the best practices in irrigation in Djibouti. The use of PVC pipes in place of traditional open air concrete channels was decided in order to eliminate the loss by evapo-transpiration of the water in the channels. The promotion of drip irrigation whenever it is cost effective has also been decided by the PMU. As in 2016, the rainfall situation is good this year and the rainfall in Petit Bara and Grand Bara has reached 100 mm. The water pond constructed by the project and small dams have collected more than 600 thousand cubic meter of water and has allowed to practice agriculture in a countinuous way since July 2015.
Initial studies reveal insufficient water availability and quality | Medium/Increasing | Comprehensive and detailed scientific exploration combining hydrogeology, hydrology, geology, and geophysics techniques was undertaken for the sitting of the wells. Chemistry of the existing water sources of the Grand Bara and Petit Bara (either surface or groundwater) has been studied. Areas that may reveal salinity of the underground water have been eliminated already from the drilling program. Areas with high probability of tapping water resources were selected and included in the drilling program as priority areas in 2014. Hydrology studies revealed that more than two millions cubic meter of water can be harvesed in the rainy season. Earth dams to collect this high volume of water will be constructed and decrease furthermore this identified risk. In 2015, results of the drilling of the boreholes have shown that the quantity of water in the boreholes is lesser than the planned quantity. The project is seeking and started to adop new stategies in order to decrease this risk to an acceptable level. This include the drilling of shallow wells in wadis in Grand and Petit Bara. This strategy is applied now to Hamboucto area near in Grand Bara and is successfull. Some new hydrogeological studies may be needed. In 2016, the project has also committed studies to assess possible locations for new wells. Based on these studies and previous studies, the project has undertaken the development of fur new boreholes.
Low level of cooperation between executing institutions | Low/Decreasing | A technical committee was established as a discussion platform among the involved institutions, The committee meets once every month to discuss issues that may delay the implementation of the project. This risk is not anymore important in the project, The tehcnical committee has solved the problem of cooperation between the government agencies.
Delays in project implementation due to simultaneous construction works for complementary projects | Medium/Increasing | After a decrease in the occurrence probability of this risk in 2015, this risk has increased in 2016. In particular, the project has experienced a long delay of the execution of the deep boreholes because of the technical non availibility of the drilling machines of the Ministry of Agriculture and the difficulty to find private companies in the local market as there are only few private companies with already heavy work loads. The project has contracted a company who started the work with a serious delay of several months and that has impacted the project implementation, This issue was solved with the intervention of the highest management of the Execution partner.
Insufficient interest and social cohesiveness amongst sedentary pastoral communities to adhere to the alternative production models proposed by the project | Low/Decreasing | The project management unit has met several times the communities and presented the objectives of the project for a sensitization purpose. The communities have expressed their interest in the shade gardening.
Theft of solar panels, pump parts or fencing materials in any of the shade garden zones | No change. Reporting against this risk will be done once the panels will installed after the drilling of the boreholes. In 2015 no change for this risk which not materialized. The project is currently under the process of procuring the solar panels.
Critical Risks Affecting Progress (Not identified at project design)
Identify Risks with a 50% or > likelihood of affecting progress of project
Identified Risk | Current Status | Steps Taken to Mitigate Risk
Unwelcome livestock (livestock from surrounding pastoralists) invading the agro-pastoral plots which can provoke disputes between the farmers and pastoralists | low | Secure metal and stone fencing will be constructed around each agro-pastoral site to deter all unwelcome animals. This will prevent the risk of invading livestock and potential disputes between the pastoralists and agro pastoralists.
Pollution from petrol spills when trucks overturn on highways | low | This will be prevented by placing the pilot sites at least 100 meters from the roadside or the required distance identified by the Environmental Impact Assessment
Risk of people becoming dependent on food aid in the beginning years of the project before fruit and vegetables can be cultivated | medium | Early contact has been initiated with the local office of World Food Program to see the possibility of WFP providing food aid in the starting years of the project. The discussions did not materialized in concrete solutions. The project has supported the communties in the starting-up phase. After a period of 4 months, a quarter of hectare is enough to provide fruit and vegetables as well as excess production to be sold on the market. The project stops its complementary supports after 4 months.
Limited capacity of local populations to perform maintenance on boreholes and solar-powered well pumps | medium | Water management groups already exist in surrounding regions. It is typical practice in the hierarchy of the village to assign roles, such as to maintain the wells. The project include activities to form and train the water management groups so that this group can process to regular maintenance of equipment and pipes. Actually these groups were formed and trained in two of the project sites.
Risk Measures: Were there any risk mitigation measures employed during the current reporting period? If so, were risks reduced? If not, why were these risks not reduced?
Add any comments relevant to risk mitigation (word limit = 500)

## Rating
RATING ON IMPLEMENTATION PROGRESS
For rating definitions please see bottom of page.
| Progress on Key Milestones |  | Expected Progress |  | Progress to Date | Rating
Project Manager/Coordinator: | construction of water infrastructures for the harvest of underground water or surface water |  | The project is progressing well. We have faced some issues with the quantity of water mobilized by the deep boreholes. In order to achieve the results, the government has decided to incude in the infrastructures to be developped the option of shallow wells that could be find in some wadis of the Grand and Petit Bara. This will be complemented by surface check dams in the wadis to increase the amount of infiltated water. This will allow us to target the same number of beneficiaries. Since the last report, 11 shallow wells have been supported for rehabilitation and used actually for agropastoral activities. |  | good progress | MS
| Development of the climate resilient shade gardens |  | The project is developping progressively the agropastoral shade gardens. The project has several years of experience from its inception. |  | good progress | S
| Rural beneficiaries are organized into agricultural anf financial cooperatives, have access to microfinance and develop climta resilient agro-pastoral enterprises |  | Initial studies have been completed but the organisation of the communities has slowy started. The microfinance aspects of the project did not progressed well. |  | very low progress | U
[5 empty] | Overall Rating | MS
Please Provide the Name and Contact information of person(s) reponsible for completeling the Rating section
| Name: | Mahamoud Houssein
| Email: | mahamoud.houssein@live.fr
Please justify your rating. Outline the positive and negative progress made by the project since it started. Provide specific recommendations for next steps. . (word limit=500)
Overall, the project is progressing well towards the achievement of its outcomes. Water insfrastructures have been developped and important of water is mobilized now for the agropastoral shade gardening. One major risk that has affected the project is an environmental risk. Indeed because of the aridity of the climate and hydrogeological conditions in the Grand an Petit Bara, the project is not able to mobilize the planned quantity of water. This is affecting the number of beneficiaries that is less than the plan at this stage of the project. At this stage of project implementation, 60 beneficiaries families have been targeted until now and are pursuing their learning in agriculture.
| Progress on Key Milestones |  | Expected Progress |  | Progress to Date | Rating
Implementing Agency | construction of water infrastructures for the harvest of underground water or surface water |  | the quantity of water mobilized by the project is less than what was planned in the project document due to geological natural conditions. However the work against this key milestone is progressing well and several water infrastructures have been developped by the project. |  | some progress and good trends | MS
| Development of the shade gardens |  | 35 hectares developped. |  | good progress | S
| Rural beneficiaries are organized into agricultural anf financial cooperatives, have access to microfinance and develop climta resilient agro-pastoral enterprises |  | Organization of the beneficiaries and microfinance aspects is progressing slowly. Need to accelerate more. |  | slow progress | MS
[5 empty] | Overall Rating | MS
Please Provide the Name and Contact information of person(s) reponsible for completeling the Rating section
| Name: | Houssein Rirache Robleh
| Email: | housseinrirach@yahoo.fr
| Progress on Key Milestones |  | Expected Progress |  | Progress to Date | Rating
Other | construction of water infrastructures for the harvest of underground water or surface water |  | Serious efforts deployed for the development of both underground and surface water but results are still not enough to reach the maximum number of people. Indeed the productivity (flowrates) of wells were not as much as expected in the project document and design, |  | medium progress | MS
| Development of the shade gardens |  | Agro-pastoral farms developped for 35 hectares but the project target is still far. Need to accelerate the project implementation. |  | medium progress | MS
| Rural beneficiaries are organized into agricultural anf financial cooperatives, have access to microfinance and develop climta resilient agro-pastoral enterprises |  | Cooperatives not established well or not functional in a proper manner yet. Communities not trained yet in microfinance. There is a need |  | low progress | U
[5 empty] | Overall Rating | MS
Please Provide the Name and Contact information of person(s) reponsible for completeling the Rating section
| Name: | Idriss Ahmed Hared, climate change policy specialist
| Email: | idriss.hared@undp.org
| Please justify your rating and address the following points: 1. Indicate trends, both positive and negative, in achievement of outcomes as per the project indicators. 2. Detail critical risks that have affected progress. 3. Outline response to MTR undertaken this reporting period. 4. Outline action plan to address projects with a rating of HU, U or MU. Please keep your input to 1200 words |  | After a good progress in 2014 and 2015, the project had implementation issues and those have slowed the project progress. These issues were a slow execution of contracts specially in the component 1 for the drilling of boreholes. The component 3 has also experienced some delays due to MOU non finalized between the involoved institutions on time. These issues were solved now and the project is again on a good trend now. The executing partner need to accelerate the project implementation and closely monitor the implementation risks.
Rating Definitions
|  |  | Highly Satisfactory (HS) | Project actions/activities planned for current reporting period are progressing on track or exceeding expectations to acheive all major outcomes/outputs for given reporting period, without major shortcomings. The project can be presented as “good practice”.
|  |  | Satisfactory (S) | Project actions/activities planned for current reporting period are progressing on track to achieve most of its major outcomes/outputs with only minor shortcomings.
|  |  | Marginally Satisfactory (MS) | Project actions/activities planned for current reporting period are progressing on track to achieve most major relevant outcomes/outputs, but with either significant shortcomings or modest overall relevance.
|  |  | Marginally Unsatisfactory (MU) | Project actions/activities planned for current reporting period are not progressing on track to achieve major outcomes/outputs with major shortcomings or is expected to achieve only some of its major outcomes/outputs.
|  |  | Unsatisfactory (U) | Project actions/activities planned for current reporting period are not progressing on track to achieve most of its major outcomes/outputs.
|  |  | Highly Unsatisfactory (U) | Project actions/activities planned for current reporting period are not on track and shows that it is failing to achieve, and is not expected to achieve, any of its outcomes/outputs.

## Project Indicators
PROJECT Indicators
Please provide all indicators being tracked for the project as outlined in the project document
Type of Indicator (indicators towards Objectives, Outcomes, etc…)
Type of Indicator | Indicator | Baseline | Progress since inception | Target for Project End
outcome 1 | indicator 1,1, Number of planned boreholes, dams and water storage basins with associated solar pumping equipment in place and operational | Existing water infrastrucres in the project areas: 2 borehole, 1 earth dam with a capacity of 500,000 cubic meter. Weak capacity of installed solar pumping systems. | Exploration of undergroung water finalized. Additional geophysics studies were undertaken in 2016 in order to identify new potential sites for water exploration. Location and design of surface water harvesting infrastructures finalized. | 6 boreholes, 6 earth dams, 8 subsurface dams, 6 reservoirs, 6 solar pumping equipment
| indicator 1,2, Water resource secured for shade garden irrigation to cover 228 ha and serve 30 000 people | In the project zones, only 10 hectares are cultivated with the existing water infrastructures | In terms of underground water resources, 2 boreholes were drilled, four boreholes under drilling program and 11 shallow wells rehabilitated. In terms of surface run-off harvesting, 1 water pond of 500 thousand cubic meter constructed as well as a check dam with a capacity of 100 thousand cubic meter. | 228 ha and at least 30,000 people are served with secure water infrastructure
output 1.1 | indicator 1.1.1: approved detailed EIA and submission | The Grand Bara and Petit Bara regions (project sites) are experiencing important land degradation. But there are not existing detailed studies describing the land degradation, biodiversity in the areas | EIE completed and finalized. There is not any displacement of population according to the EIE. All agropastoral shaded gardens are located within a distance of less than 3 km from the house of the communities. EIE validated and accepted by the Direction of Environment | Completion of EIA and pedological, hydrological, and hydro-geological
Output 1.2
| indicator 1.2.1: percentage of total hectares of agro-pastoralists land which is irrigated by boreholes | 31 hectares are irrigated by the boreholes at this time | Since its inception, the project has developped 12 ha in Rakoubiyeel and 5 ha in Kourtimalei. Additional 12 hectares were developed in Hamboucto supported by 11 shallow wells and surface check dam.It was decided to not develop a new agropastoral farm in Yabeh and to use the water of Yabeh well to secure and sustain the agro-pastoral farm of Kourtimalei which is actually irrigated by water pond water. The project has re-developped the borehole of Omar Jagac by proceeding to a new airlift and the discharge of the well was increased to 5 cubic meter per hour. The project is planning a 5 hectare, drip irrigated agro-pastoral farm in this area. Studies are actually committed to design the drip irrigation hydraulic system of Omar Jagac. It is expected to set-up the Omar Jagac drip irrigated agro-pastoral farm by november 2016. Around 20 families will be beneficiaries of this drip irrigated plot and selection of beneficiaries is ongoing. On the site training will be provided for the beneficiaries of this drip irrigated farm. | 228 ha
| indicator 1.2.2 Amount of time spent in search of water from boreholes | according to the WFP annual food security assessment report 2013, the time spent in search of water is 30 minutes for Arta and Ali Sabieh populations | 2 Boreholes completed, 4 under construction, 1 water pond and 1 check dam that are able to provide. Socio-economic studies to be committed in order to analyse the time spent for water fetch. | less than 30 minutes
Output 1,3, | indicator:1.3.1.Percentage of total hectares of agropastoralists land which is irrigated by surface water sources | Only 7 hectares are irrigated by the surface water at this time | development of 7 ha in Kourtimalei fully functionnal irrigated by an earth dam of 500,000 cubic meter rehabilated and upgraded by the project | 228 ha
| indicator:1.3.2.amount of time in search of water from surface water sources | according to the WFP annual food security assessment report 2013, the time spent in search of water is 30 minutes for Arta and Ali Sabieh populations | The project has increased the amount of water available for communities and thus reducing the time to search water, | less than 30 minutes
output 1.4 | indicator: 1.4.1:Number of maintenance efforts on water systems and percentage of successful local maintance efforts | none | not yet | 10 maintenances
| indicator: 1.4.2: management plans and good practice guidelines emphasized and enforced by the water infrastructure management committee | zero | 8 plots in Hamboucto, 12 in Rakoubyeel, 15 in Kourtimalei, 4 in Omar Jagac. In total the project has constructed 39 plots for a total of 60 families. | six sets of 38 pilot
outcome 2 | indicator 2.1: Number of shade gardens developed including irrigation reservoirs, distribution networks, and fencing | zero | 8 plots in Hamboucto, 12 in Rakoubyeel, 15 in Kourtimalei, 4 in Omar Jagac. In total the project has constructed 39 plots for a total of 60 families. | six sets of 38 pilot
| indicator:2.2: % of population who has developed shade gardens resilient to climate change | zero | Around 60 families engaged in agropastoral shade gardening at this stage of the project. It is expected to increase this number by 20 families by the end of november 2016. Depending on the discharge of the four deep wells that are under construction, this number can be increased by three times by the mid-2017. | 2800 people
output 2.2 | indicator 2.2.1: number of project beneficiaries disaggregated according to gender who that have been trained on cultivation techniques, crop rotation, livestock hygiene etc by specialists | zero | All of the 60 families were trained in cultivation, irrigation and composting techniques. A total of 20 women are currently trained for pastoral milk processing. The project is indeed supporting the development of the pastoral milk sector and one milk processing and selling point is under construction in the Kourtimalei area. | 228 families
| indicator 2.2.2: percentage change in beneficiaries capacities to cultivate their own land and raise livestock autonomously | zero | The agro-pastoral activities are seen as very positive and most of the beneficiaries have changed their behaviour. The project has provided on the site training to the beneficiairies and most of them are able now to cultivare their land by themselves. The availibity of seeds in the local market is one the challenge facing the communities. The project is working on the autonomisation of the communities in practicing the agro-pastoral activities. | 100%
output 2.3 | indicator 2.3.1: number of constructed storage facilities per agropastoral zone | zero | Three storages construction completed: Kourtimalei,Rakoubyeel and Hamboucto. In addition one processing and selling milk center is under construction in Kourtimalei area. The center will serve more than 100 families who sell goat and camel milk usually on the road. The center will provide clean tanks for the collection of milk, pasteurization unit, clean bottles and solar fridge. Milk will be collected from around 10 km around the milk center. | 6 constructed storages
| indicator 2.3.2: percentage of beneficiaries that utilize storage facilities | zero | The existing storage facilities are utilized by the 60 families who are the actual beneficiaries. They use the storage facilities to store the agricultural inputs and also their production. | 100%
outcome 3 | indicator 3.1: Number of MF products deployed to agro-pastoralists which provide loans ear-marked for adaptation to climate-change | zero | Progress in advocating for the provision of a government micro-credit line earmarked for adaptation activities. The project is experiencing delays in the development of MF products due to delays in the implementation of this component and change in political landscape of microfinance. The microfinance sector in Djibouti has experienced some difficulties the last two years and a reform of the sector is expected. The strong leadership of ADDS and CPEC that were identified in the project design did not yet materialized into concrete steps for the AF project. Meanwhile steps were taken in order to avoid any further delays in this component and technical meeting was organized between ADDS and the project management unit. A MOU was also prepared between the project and the State Secretariat for Solidarity for the implementation of this component on the ground. It is expected that the remaining project time will be enough to implement this component. | 7 different types of products to be deployed by the end of the projects: 1) water equipment and resource (drip irrigation, pumping equipment, water harvesting), 2) livestock product;3)agricultural inputs (4) loans for creating small climate change agro-pastoral enterprises
| indicator:3.2: % of total population using microcredit products | zero | not yet, project experiencing delays in the implementation of this component. | 100%
| indicator :3.3: community- driven adaptation plans are integrated into National Programme for Food Security and the National MF policy | zero | not yet, project experiencing delays in the implementation of this component. | 4 adaptation plans
output 3.1. | indicator:3.1.1: percentage of beneficiaries trained in microcredit principles | zero | not yet, project experiencing delays in the implementation of this component. | 100%
| indicator:3.1.2: number of technical guides prepared detailing how MF can be used for adaptation oriented activities | zero | technical guides not yet prepared but steps have been taken: study on adaptation oriented agropastoral product has been delivered, technical guides will be available in 2014 | 1 comprehensive technical guide
ouput 3.2 | indicator 3.2.1: number of loans and percentage of payback on loans | zero | not yet, project experiencing delays in the implementation of this component. | 228 loans at least and expected 100% paybacks
| indicator 3.2.2: percentage of population in each tier of 3-tiered microfinance programme (safety net, nao, and microfinance) | zero | not yet, project experiencing delays in the implementation of this component. | to be determined
output 3.3 | indicator: 3.3.1: percentage of population which has been organized into adaptation plan cooperatives | zero | not yet, project experiencing delays in the implementation of this component. | 100%
| indicator : 3.2.2: Attendance and participation at bi-annual workshops used to document community recommended measures to improve the adaptation oriented microfinance products | zero | not yet, project experiencing delays in the implementation of this component. | 6 bi-annual workshop expected to be conducted with the attendance and participation of approximately 300 persons

## Lessons Learned
QUALITATIVE MEASURES and LESSONS LEARNED
Please complete the following section every reporting period
Implementation and Adaptive Management | Response
What implementation issues/lessons, either positive or negative, affected progress? | Coordination among involved institutions was difficult to operate at the starting of the project and is still a challenge for the project. However the coordination has improved very well as the project is progressing in the implementation.
Were there any delays in implementation? If so, include any causes of delays. What measures have been taken to reduce delays? | Yes there were delays in the implementation of the project, in particular the development of the drilling of the boreholes and construction of rainwater harvesting infrastructures. The reason is that the engagement of the involved technical institutions and the delivery of the outcomes of the scientific studies undertaken by these institutions were been delayed. As such we are experiencing currently several months of delay. To reduce the delays, the project management unit has discussed with the technical committee of the project and the steering committee of the project to find solutions. Three measures have been proposed by these committees in order to reduce the delays: (i) call for the acceleration of the scientific studies to the national institutions (ii) strategic decision to anticipate the construction of the agricultural infrastructures for 12 hectares and strenghtening of existing 6 hectares in the project zones(iii) the contractual companies were convened and ordered to speed up the construction of infrastructures, Measures taken has improved the execution of the project and 2 boreholes were developped, However 4 boreholes are still remaining to be developped. The project has contracted a company for the drilling of remaining 4 boreholes but the drilling work started with 5 months of delays. The highest management of the executing partner was requested for intervention.
Describe any changes undertaken to improve results on the ground or any changes made to project outputs (i.e. changes to project design) | In the project document it was expected to issue 1 hectare per family, According to thoses involved projects in the zone, it is expected to start with 0,5 hectares per family. The project has decided further to give 0,25 hectares per family in order to benefit to a maximum of persons.
How have gender considerations been taken into consideration during the reporting period? What have been the lessons learned as a consequence of inclusion of such considerations on project performance or impacts? | It is planned in the project to construct several plant nurseries managed by women. The project management unit has identified already the group of women as well as the villages in which the nurseries will be sitted. The Omar Jagac and Rakoubyeel villages have been identified to host the nurseries because of the already existing water wells and because these sites are close to already identified agro-pastoral areas.
Please complete the following section at mid-term and project completion
Lessons for Adaptation | Response
Climate Resilience Measures
What have been the lessons learned, both positive and negative, in implementing climate adaptation measures that would be relevant to the design and implementation of future projects/programmes for enhanced resilience to climate change? | According that producers are at the beginning, the physical strength is a limiting factor as result implemented in the project zone by other partner, So 1 hectare for each family will be cut down to 0,5 hectare per family. The figure of 0,5 hectare could be donwsized to 0,25 hectares as the quantity of water mobilized is less than what the project was expecting. The transformation of pure pastoralists to agropastoralists is something which needs enough time. Specially in the context of arid climate which needs undeground water resources. Therefore the project duration should be more than 5 years.
What is the potential for the climate resilience measures undertaken by the project/programme to be replicated and scaled up both within and outside the project area? | The development of agropastoralism is a viable adaptation strategy. There is a high replication and upscaling potential for this type of adaptation option.This adaptation strategy has also potential benefits to increase the food security of the country as this is an option which target the most food insecure people. Meanwhile it is an option which needs time and important investment.
Concrete Adaptation Interventions
What have been the lessons learned, both positive and negative, in implementing concrete adaptation interventions that would be relevant to the design and implementation of future projects/programmes implementing concrete adaptation interventions? | Including the development of underground resources as an option to secure access to water for agriculture is a risk because the final discharge of the wells are not sure whatever being the geoscientific studies developped upfront which can only minimize the risk of failure. This is a lesson learned from the project. In place of using deep underground resources, future project should focus more on the combination shallow wells and surface water infrastructures (ponds or dam).
What is the potential for the concrete adaptation interventions undertaken by the project/programme to be replicated and scaled up both within and outside the project area? | Concrete adaptation interventions developped include the harvesting of surface runoff combined with underground water resources to secure water for communities and the development of agricultural plots for communities. Geoscientific studies were used as needed. Within the Grand and Petit Bara, these concrete adaptation interventions can be replicated and even outside the project area in the entire country.
Community/National Impact
What would you consider to be the most successful aspects for the target communities? | The most successful aspects for the target communities is the upgrading of their food security because they are producing themselves their vegetable (tomatoes, onions, okra) and fruit needs (melon, water melon). They also produce fodder for their animals.
What measures are/have been put in place to ensure sustainability of the project/program results? | The project has identified key problems that could threat the sustuanibility of the project results including : the non availaibility of seeds in the local market, the maintenance issues in the transport and irrigation network of the water, plants disease and also transport of excess vegetables and fruits to the market. The project is currently conducting reflections to find solutions for these identified threats to the sustainability.
What measures are being/could have been put in place to improve project/program results?
Knowledge Management
How has existing information/data/knowledge been used to inform project development and implementation? What kinds of information/data/knowledge were used? | Use of existing knowledge during the project development phase was very important. All relevant data and information with regards to drought impacts, food security, agropastoralism, disaster risk management, microfinance were collected during the project preparation.
If learning objectives have been established, have they been met? Please describe. | Learning was identified in the project document as much important as the construction of infrastructures. The key learning methods identified were on site trainings for communities, support to the exxtension services and relevant ministerial departments. Within component 1, the main identified knowledge value to be captured and disseminated was the design, applicability and effectiveness of water-related adaptation and resilience building solutions, climate smart water harvesting infrastructures and technologies as well as robust community management models. With regard to this, the project has supported the Center of Studies and Research of Djibouti in the production of hydrological modelling of the Petit Bara aquifers using the information and date generated during the development of the boreholes funded by the project. A scientific publication was submitted by CERD researchers to international journal. The knowldege generated will help in the sitting and design of new boreholes. Learning of agricultural technics by training of communities was identified as key element of the success of the project. Increasing the water modelling capabilities of the water department of the ministry of agriculture was also one of the leanring objective of the project. This has not yet been achieved but it is in the plan.Within component 2, the project has put emphasis on the training of communities on cultivation, composting, harvesting and commercialisation. The project has used both the technical capacities available at the ministry of agriculture level and external expertise when needed. Specific training curriculum was developped and can be used for other sites or future projects. Within the component 3, the project learning objectives (although not formulated as such) were the training of communities on microfinance and management of micro-enterprises, the development of technical guides for learning of climate adapted microfinance products. These learning objectives are in the process of achievement.
Describe any difficulties there have been in accessing or retrieving existing information (data or knowledge) that is relevant to the project. Please provide suggestions for improving access to the relevant data. | There were not significant difficulties in retrieving exising information in developping the project or implementing it.
Has the identification of learning objectives contributed to the outcomes of the project? In what ways have they contributed? | Yes, learning objectives and project outcomes have strong linkages in this project. This linkage is obvious with regard to learning of agricultural and water management technics by communities which have further helped them work on the given land, produce fruit and vegetables, thus becoming more food secure and more resilient to climate. These communities were pure pastoralists and had virtually zero knowledge on agricultural tehcnics.

## Results Tracker
Results Tracker for Adaptation Fund (AF) Projects
Goal: Assist developing-country Parties to the Kyoto Protocol that are particularly vulnerable to the adverse effects of climate change in meeting the costs of concrete adaptation projects and programmes in order to implement climate-resilient measures. Impact: Increased resiliency at the community, national, and regional levels to climate variability and change.
Important: Please read the following guidance document (also posted on the Adaptation Fund website) before entering your data
Link: http://www.adaptation-fund.org/sites/default/files/Results%20Framework%20and%20Baseline%20Guidance%20final.pdf
Adaptation Fund Strategic Results Framework
Project ID | 4683
Implementing Entity | United Nations Development Program
Type of implementing entity | MIE
Country | DJIBOUTI
Region | Africa
Sector | Food security
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Impact: Increased resiliency at the community, national, and regional levels to climate variability and change | Core Indicator: No. of beneficiaries |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project
|  | Total | 0 | 0 | 0 | Total | 30000 | 2800 | 27200 | Total | 10600 | 600 | 10000 | Total
|  | % of female beneficiaries |  |  |  | % of female beneficiaries |  |  |  | % of female beneficiaries | 40% | 40% | 40% | % of female beneficiaries
|  | % of Youth beneficiaries |  |  |  | % of Youth beneficiaries |  |  |  | % of Youth beneficiaries | 20% | 20% | 20% | % of Youth beneficiaries
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 1: Reduced exposure to climate-related hazards and threats | Indicator 1: Relevant threat and hazard information generated and disseminated to stakeholders on a timely basis | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness
|  | Total |  |  |  | Total |  |  |  | Total |  |  |  | Total
|  | % of female targeted |  |  |  | % of female targeted |  |  |  | % of female targeted |  |  |  | % of female targeted
Output 1.1 Risk and vulnerability assessments conducted and updated | Indicator 1.1: No. of projects/programmes that conduct and update risk and vulnerability assessments | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
Output 1.2 Targeted population groups covered by adequate risk reduction systems | Core Indicator 1.2: No. of Early Warning Systems | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 2: Strengthened institutional capacity to reduce risks associated with climate-induced socioeconomic and environmental losses | Indicator 2: Capacity of staff to respond to, and mitigate impacts of, climate-related events from targeted institutions increased | Number of staff targeted |  | Sector | Capacity level | Number of staff targeted |  | Sector | Capacity level | Number of staff targeted |  | Sector | Capacity level | Number of staff targeted |  | Sector | Capacity level
|  | Total |  |  |  | Total |  |  |  | Total |  |  |  | Total
|  | % of female targeted |  |  |  | % of female targeted |  |  |  | % of female targeted |  |  |  | % of female targeted
Output 2.1 Strengthened capacity of national and sub-national centres and networks to respond rapidly to extreme weather events | Indicator 2.1.1: No. of staff trained to respond to, and mitigate impacts of, climate-related events | Total staff trained | % of female staff trained | Type |  | Total staff trained | % of female staff trained | Type |  | Total staff trained | % of female staff trained | Type |  | Total staff trained | % of female staff trained | Type
| Indicator 2.1.2: No. of targeted institutions with increased capacity to minimize exposure to climate variability risks | Type | Scale | Sector | Capacity level | Type | Scale | Sector | Capacity level | Type | Scale | Sector | Capacity level | Type | Scale | Sector | Capacity level
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 3: Strengthened awareness and owernship of adaptation and climate risk reduction processes | Indicator 3.1: Increase in application of appropriate adaptation responses | Percentage of targeted population applying adaptation measures |  | Sector |  | Percentage of targeted population applying adaptation measures |  | Sector |  | Percentage of targeted population applying adaptation measures |  | Sector |  | Percentage of targeted population applying adaptation measures |  | Sector
Output 3: Targeted population groups participating in adaptation and risk reduction awareness activities | Indicator 3.1.1: Percentage of targeted population awareness of predicted adverse impacts of climate change, and of appropriate responses | No. of targeted beneficiaries | % of female participants targeted | Level of awareness |  | No. of targeted beneficiaries | % of female participants targeted | Level of awareness |  | No. of targeted beneficiaries | % of female participants targeted | Level of awareness |  | No. of targeted beneficiaries | % of female participants targeted | Level of awareness
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Target performance at completion
Outcome 4: Increased adaptive capacity within relevant development sector services and infrastructure assets | Indicator 4.1: Increased responsiveness of development sector services to evolving needs from changing and variable climate | Project/programme sector | Geographical scale | Response level |  | Project/programme sector | Geographical scale | Response level |  | Project/programme sector | Geographical scale | Response level |  | Project/programme sector | Geographical scale | Response level
| Core Indicator 4.2: Assets produced, developed, improved or strengthened | Sector | Targeted asset | Changes in asset (quantitative or qualitative) |  | Sector | Targeted asset | Changes in asset (quantitative or qualitative) |  | Sector | Targeted asset | Changes in asset (quantitative or qualitative) |  | Sector | Targeted asset | Changes in asset (quantitative or qualitative)
Output 4: Vulnerable development sector services and infrastructure assets strengthened in response to climate change impacts, including variability | Indicator 4.1.1: No. and type of development sector services to respond to new conditions resulting from climate variability and change | Number of services | Type |  | Sector | Number of services | Type |  | Sector | Number of services | Type |  | Sector | Number of services | Type |  | Sector
|  | Baseline information |  |  |  | Baseline information |  |  |  | Performance at mid-term |  |  |  | Target performance at completion
Outcome 5: Increased ecosystem resilience in response to climate change and variability-induced stress | Indicator 5: Ecosystem services and natural resource assets maintained or improved under climate change and variability-induced stress | Natural resource improvement level |  | Sector | Type | Natural resource improvement level |  | Sector | Type | Natural resource improvement level |  | Sector | Type | Natural resource improvement level |  | Sector | Type
Output 5: Vulnerable ecosystem services and natural resource assets strengthned in response to climate change impacts, including variability | Core Indicator 5.1: Natural Assets protected or rehabilitated | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Baseline information |  |  |  | Targeted performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 6: Diversified and strengthened livelihoods and sources of income for vulnerable people in targeted areas | Indicator 6.1: Increase in households and communities having more secure access to livelihood assets | No. of targeted households | % of female headed households | Improvement level |  | No. of targeted households | % of female headed households | Improvement level |  | No. of targeted households | % of female headed households | Improvement level |  | No. of targeted households | % of female headed households | Improvement level
|  | 228 | 10% | 1: No improvement |  | 228 | 10% | 5: Very high improvement |  | 60 | 5% | 4: High improvement
| Indicator 6.2: Increase in targeted population's sustained climate-resilient alternative livelihoods | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
|  | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
|  | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
|  | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
Output 6 Targeted individual and community livelihood strategies strengthened in relation to climate change impacts, including variability | Indicator 6.1.1: No. and type of adaptation assets created or strengthened in support of individual or community livelihood strategies | Number of Assets | Type of Assets | Sector | Adaptation strategy | Number of Assets | Type of Assets | Sector | Adaptation strategy | Number of Assets | Type of Assets | Sector | Adaptation strategy | Number of Assets | Type of Assets | Sector | Adaptation strategy
|  | 1 | Physical capital | Water management | Supporting livelihoods | 228 | Physical capital | Agriculture | Supporting livelihoods | 60 | Physical capital | Agriculture | Supporting livelihoods
| Core Indicator 6.1.2: Increased income, or avoided decrease in income | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | 6000 | Livestock production |  | 0.75 | 228 | Agriculture |  | 4 | 60 | Agriculture |  | 4
|  | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 7: Improved policies and regulations that promote and enforce resilience measures | Indicator 7: Climate change priorities are integrated into national development strategy | Integration level |  |  |  | Integration level |  |  |  | Integration level |  |  |  | Integration level
Output 7:Improved integration of climate-resilience strategies into country development plans | Indicator 7.1: No. of policies introduced or adjusted to address climate change risks | No. of Policies introduced or adjusted | Sector | Scale | Type | No. of Policies introduced or adjusted | Sector | Scale | Type | No. of Policies introduced or adjusted | Sector | Scale | Type | No. of Policies introduced or adjusted | Sector | Scale | Type
| Indicator 7.2: No. of targeted development strategies with incorporated climate change priorities enforced | No. of Development strategies | Regulation |  | Effectiveness | No. of Development strategies | Regulation |  | Effectiveness | No. of Development strategies | Regulation |  | Effectiveness | No. of Development strategies | Regulation |  | Effectiveness
Glacier lake outburst flood
|  | Inland flooding | fr | biological assets |  | Company policy | 5: Fully enforced (All elements implemented)
|  | Salinization | Decrease | land |  | Communication & Information policy | 4: Enforced (Most elements implemented)
|  | Drought | Same | water areas |  | Defense policy | 3: Partially enforced (Some elements implemented)
|  | Wind |  | subsoil assets | increased adpative capacity | Domestic policy | 2: Partially not enforced (Most elements not implemented) |  | Agribusiness
|  | Coastal flooding |  | air | achieved | Economic policy | 1: Not enforced (No elements implemented) |  | Agricultural-related | Financial capital
|  | Storm surge | Please choose |  | enhanced level of protection | Education policy |  |  | Agriculture | Human capital
|  | Hurricane | Selected | [5 empty] | Aquaculture | Physical capital
|  |  | Not relevant |  |  | 5: All (Fully integrated) |  |  | Construction/repairing business | Social capital
[6 empty] | 4: Most |  |  | Cultivation | Natural capital
[6 empty] | 3: Some |  |  | Fishing | Personal capital
Select | 5: All | Select |  |  | Community | 2: Most not integrated |  | Other | Forestry | Adaptation strategies
1 | 4: Almost all | Private | Type | Yes | Multi-community | 1: None |  | Agriculture | Handicrafts
2 | 3: Half | Public | Scale | No | Departmental |  |  | Coastal management | Livestock production
3 | 2: Some | NGO | Sector |  | National |  |  | Disaster risk reduction | Manufacturing
4 | 1: None |  |  |  |  | 5: Very high improvement | Established | Food security | other
|  | National |  |  |  | 4: High improvement | Maintained | Health | Services
|  | Regional |  |  |  | 3: Moderate improvement | Improved | Urban development | Tourism-related
|  | Local |  |  |  | 2: Limited improvement |  | Water management | Trading
[6 empty] | 1: No improvement |  | Multi-sector
|  | 1 -generated information is irrelevant, and neither the stakeholders reached nor the timeframe managed were achieved | 1: No info transferred on time | 4: High capacity | 5: Fully aware | 5: Highly responsive (All defined elements ) | 5: Fully improved | Roads | 5: Very effective
Asia-Pacific | NIE | 2 -the existence of some challenge in any of the three aspects of the indicator (generation of dissemination, stakeholders reached or timeframe managed) | 2: Somewhat info transferred | 3: Medium capacity | 4: Mostly aware | 4: Mostly responsive (Most defined elements) | 4: Mostly Improved | Gov Buildings | 4: Effective
Latin America and Caribbean | RIE | 3 -relevant information is generated and disseminated to all identified stakeholders on timely basis | 3: Info transferred on time | 2: Low capacity | 3: Partially aware | 3: Moderately responsive (Some defined elements) | 3: Moderately improved | Causeways | 3: Moderately effective
Africa | MIE |  |  | 1: No capacity | 2: Partially not aware | 2: Partially responsive (Lacks most elements) | 2: Somewhat improved | Airports | 2: Partially effective
Eastern Europe |  |  |  |  | 1: Aware of neither | 1: Non responsive (Lacks all elements ) | 1: Not improved | Schools | 1: Ineffective
| ha protected | [6 empty] | Training Centres
| ha rehabilitated | [5 empty] | Monitoring/Forecasting capacity | Hospitals
Afghanistan, Islamic Rep. of | km protected | [5 empty] | Policy/regulatory reform | Drinking water systems
Angola | km rehabilitated | 1: Risk knowledge | 1: No plans conducted or updated |  |  |  | Capacity development | Other
Albania |  | 2: Monitoring and warning service | 2: Undertaking or updating of assessments in progress |  |  | Communication & Information policy | Sustainable forest management
Argentina |  | 3: Dissemination and communication | 3: Risk and vulnterability assessments completed or updated |  |  | Domestic policy | Strengthening infrastructure | 1: Health and Social Infrastructure (developed/improved)
Armenia | Forests | 4: Response capability |  |  |  | Economic policy | Supporting livelihoods | 2: Physical asset (produced/improved/strenghtened)
Antigua and Barbuda | Mangroves |  |  |  |  | Education policy | Mangrove reforestation
Azerbaijan | Coasts |  | From 0 to 0.5% |  |  | Energy policy | Coastal drainage and infrastructure
Burundi | Rangelands |  | From 0.5 to 1% |  |  | Environmental policy | Irrigation system
Benin | Cultivated land/Agricultural land |  | From 1% to 5% |  |  | Foreign policy | Community-based adaptation
Burkina Faso | Catchment area/Watershed/Aquifer |  | From 5% to 10% |  |  | Health policy | Erosion control
Bangladesh | Protected areas/National parks |  | From 10% to 20% |  |  | Housing policy | Soil water conservation
Bulgaria | Other |  | From 20% to 30% |  |  | Human resource policies | Microfinance
Bahrain |  |  | From 30% to 40% |  |  | Information policy | Special Program for women
Bahamas, The |  |  | From 40% to 50% |  |  | Macroeconomic policy | Livelihoods
Bosnia and Herzegovina |  |  | Above 50% |  |  | Monetary policy | Water storage
Belarus | [5 empty] | Population policy | ICT and information dissemination
Belize | [5 empty] | Private policy
Bolivia | [5 empty] | Public policy
Brazil | [5 empty] | Science policy
Barbados | [5 empty] | Social policy
Bhutan |  | 3- relevant information is generated and disseminated to all identified stakeholders on timely basis |  |  |  | Transportation policy
Botswana |  | describe |  |  |  | Urban policy
Central African Republic |  | 2- the existence of some challenge in any of the three aspects of the indicator |  |  |  | Water policy
Chile |  | describe |  |  |  | Other policy
China, People's Republic of |  | 1- generated information is irrelevant and neither the stakeholders reached nor the timeframe managed were achieved
Cote d'Ivoire |  | describe
Cameroon
Congo, Dem. Rep. of
Congo, Republic of
Cook Islands
Colombia
Comoros
Cape Verde
Costa Rica
Cuba
Czech Republic
Djibouti
Dominica
Dominican Republic
Algeria
Ecuador
Egypt
Eritrea
Estonia
Ethiopia
Fiji
Micronesia, Fed. States of
Gabon
Georgia
Ghana
Guinea
Gambia, The
Guinea-Bissau
Equatorial Guinea
Grenada
Guatemala
Guyana
Honduras
Croatia
Haiti
Hungary
Indonesia
India
Iran, Islamic Republic of
Jamaica
Jordan
Kazakhstan
Kenya
Kyrgyz Republic
Cambodia
Kiribati
Saint Kitts and Nevis
Korea, Republic of
Lao People's Democratic Republic
Lebanon
Liberia
Libya
Saint Lucia
Sri Lanka
Lesotho
Lithuania
Latvia
Morocco
Moldova
Madagascar
Maldives
Mexico
Marshall Islands
Macedonia, former Yugoslav Republic of
Mali
Malta
Myanmar
Montenegro
Mongolia
Mozambique
Mauritania
Mauritius
Malawi
Malaysia
Namibia
Niger
Nigeria
Nicaragua
Niue
Nepal
Nauru
Oman
Pakistan
Panama
Peru
Philippines
Palau
Papua New Guinea
Poland
Korea, Dem. People's Rep. of
Paraguay
Romania
Russian Federation
Rwanda
Saudi Arabia
Sudan
Senegal
Solomon Islands
Sierra Leone
El Salvador
San Marino
Serbia
Sao Tome and Principe
Suriname
Slovak Republic
Slovenia
Swaziland
Seychelles
Syrian Arab Republic
Chad
Togo
Thailand
Tajikistan
Turkmenistan
Tonga
Trinidad and Tobago
Tunisia
Turkey
Tuvalu
Tanzania
Uganda
Ukraine
Uruguay
Uzbekistan
Saint Vincent and the Grenadines
Venezuela
Vietnam
Vanuatu
Samoa
Yemen, Republic of
South Africa
Zambia
Zimbabwe
Timor-Leste

## Units for Indicators
Fund Outcome Indicator Units
1. Generation of relevant data, Stakeholders, and Timeliness 2.1. Include both qualitative and quantitative measures of capacity level within targeted institutions 2.2. Number (men and women and other vulnerable groups) 3.1. Use scale from 1 to 5: 5: Fully aware 4: Mostly aware 3: Partially aware 2: Partially not aware 1: Aware of neither predicted adverse impacts of climate change nor of appropriate responses 3.2. Use scale from 1 to 5: 5: All 4: Almost all 3: Half 2: Some 1: None 4.1. Summarize in an overall scale (1-5): 5: Highly responsive (All defined elements ) 4: Mostly responsive (Most defined elements) 3: Moderately responsive (Some defined elements) 2: Partially responsive (Lacks most elements) 1: Non responsive (Lacks all elements ) 4.2. Summarize in an overall scale (1-5): 5: Fully improved 4: Mostly Improved 3: Moderately improved 2: Somewhat improved 1: Not improved 5. Depends on the targeted natural asset: Biological (species): measure through changes in population numbers (dynamics, structure, etc.) Land: measure changes in hectares. Baseline data will be necessary to estimate the change. Supporting indicators baseline and target (as well as contextual information) are needed such as the following: Farmers adopting recommended technologies, Ha. of land improved, Average deforestation rate Etc. Use scale from 1 to 5. 5: Very effective (All elements are present) 4: Effective (Most elements are present) 3: Moderately effective (Some elements are present) 2: Partially effective (Most elements are not present) 1: Ineffective (No elements are present) 6.1. Summarize in an overall scale (1-5): 5: Very high improvement 4: High improvement 3: Moderate improvement 2: Limited improvement 1: No improvement 6.2. Household income by source of livelihood in project area (USD) prior and post project intervention 7. Summarize in an overall scale (1-5). 5: All (Fully integrated) 4: Most 3: Some 2: Most not integrated 1: None
Fund Output Indicator Units
1.1. Number, sector(s) and level(s) of projects or interventions in separate fields of monitoring plan 1.2. Number 2.1.1. Number of staff (male/female) of targeted institutions: a. Obtain baseline information: total number of staff from targeted institutions b. Define target 2.1.2. Number of staff (male/female) of targeted institutions: a. Obtain baseline information: total number of staff from targeted institutions b. Define target: needs to be defined by project proponents 2.2.1. Quantitative: Percentage (includes women – and other vulnerable groups – and men). Qualitative: Adequacy: include direct analysis of major areas; adequacy/effectiveness of systems or analysis of perceptions of populations and institutions. 2.2.2. Number (broken down by gender and, if possible, by vulnerable groups defined in the area of intervention) of people 3.1. Number and type (in separate columns) at local level. 3.2. Number 4.1. Number and type 4. 2. Number and type (entered in separate columns) 5. Number of interventions by type of natural asset and intervention 6.1. Number and type (in separate columns of monitoring plan) 6.2. Income sources per household; description of income source and number of households. 7.1. Number/Sector 7.2. Number; Effectiveness (see previous indicator) through enforcement level.