## Overview
Project Performance Report (PPR)
| Period of Report (Dates) | Septembre 2012-January 2014
| Project Title: | Developing agro-pastoral shade gardens as an adaptation strategy for poor rural communities
| Project Summary: | The project aims to help the rural pastoral communities of Djibouti to adapt to climate change by the development of climate resilient shade gardens. The overall objective of the project is to diversify and promote climate resilient agro-pastoral practices in rural Djibouti. The project aims to achieve this objective trough three outcomes: (1) Capacities to mobilize and secure sustainable water resources to agro-pastoral communities developed in the face of climate change; (2) Sustainable agro-pastoral systems developed, providing greater forage production capacities, diversifying agricultural productions and creating capacities for replication; (3) Microfinance products developed to facilitate and promote diversified and climate resilient agro-pastoral production systems.
|  |  | Countries | Project Type: |  | GEF Focal Area: | GEF 4 Focal Areas | GEF 2 / 3 Operational Programme: | Overall Rating of the project in the evaluation by the project evaluator: | GEF-4 Focal Area Strategic Program: | GEF-3 Focal Area Strategic Program:
| Database Number: | 4683 | Afghanistan | FP | Yes | Biodiversity | 1 | 1 | U | BD-SP1-PA Financing | 1: Arid & semi-arid ecosystems
Implementing Entity (IE) [name]: |  | United Nations Development Program (UNDP) | Albania | MSP | No | Climate Change Adaptation | 2 | 2 | S | BD-SP2-Marine PA | 2: Coastal, marine & freshwater ecosystems
| Type of IE: | MIE | Algeria | EA |  | Climate Change Mitigation | 3 | 3 | MU | BD-SP3-PA Networks | 3: Forest ecosystems
| Country(ies): | Djibouti | Angola |  |  | International Waters | 5 | 5 | Good | BD-SP5-Markets | 13: Conservation and Sustainable Use of Biological Diversity Important to Agriculture
Relevant Geographic Points (i.e. cities, villages, bodies of water): |  | Villages | Argentina |  |  | Multiple Focal Area |  |  |  | BD-SP7-Invasive Alien Species(IAS) | 6: Promoting the adoption of renewable energy by removing barriers and reducing implementation costs
[8 empty] | CC-SP2- Industrial EE | 8: Waterbody based operational program
| Project Milestones | [6 empty] | CC-SP3-RE,CC-SP4-Biomass | 9: Integrated Land and Water multiple focal area
| Milestone |  | Bahamas | [6 empty] | CC-SP5-Transport | 10: Contaminants based operational program
AFB Approval Date: |  | 11 July 2012
IE-AFB Agreement Signature Date: |  | 23 July 2012 | [6 empty] | CC-SP6-LULUCF | 12: Integrated Ecosystem Management
Start of Project/Programme: |  | September 2012 | [6 empty] | Cross cutting capacity building | 14: Persistent Organic Pollutants
Mid-term Review Date (if planned): |  | 2014-09-30
| Terminal Evaluation Date: | 2017-08-31
|  | List documents/ reports/ brochures / articles that have been prepared about the project. | Cyprus
|  | The project has established an ambitious knowledge management strategy and action plan to be deployed from 2014. | Czech Republic
List the Website address (URL) of project. |  |  | Democratic People's Republic of Korea
|  | Website of the project will be developed in 2014 | Democratic Republic of the Congo
Denmark
| Project contacts: |  | Djibouti
National Project Manager/Coordinator |  |  | Dominica
| Name: | Houssein Rirache Robleh | Dominican Republic
| Email: | housseinrirach@yahoo.fr | Ecuador
| Date: | 2014-01-23 | Egypt
| Government DA |  | El Salvador
| Name: | Dini Abdallah Omar | Equatoral Guinea
| Email: | dini_omar@yahoo,fr | Eritrea
| Date: | 2014-01-23 | Estonia
| Implementing Entity |  | Ethiopia
| Name: | Idriss Ahmed Hared | Fiji
| Email: | idriss.hared@undp.org | Finland
| Date: | 2014-04-08 | France
| Executing Agency |  | Gambia
| Name: | Ministry of Habitat, Urbanism and Environment | Georgia
| Email: | dini_omar@yahoo.fr | Germany
| Date: |  | Ghana
| Executing Agency |  | Greece
| Name: |  | Grenada
| Email: |  | Guatemala
| Date: |  | Guinea
| Executing Agency |  | Guinea Bissau
| Name: |  | Guyana
| Email: |  | Haiti
| Date: |  | Honduras
Hungary
Iceland
India
Indonesia
Iran (Islamic Republic of)
Iraq
Ireland
Israel
Italy
Jamaica
Japan
Jordan
Kazakhstan
Kenya
Kiribati
Kuwait
Kyrgyzstan
Lao People’s Democratic Republic
Latvia
Lebanon
Lesotho
Liberia
Libyan Arab Jamahiriya
Liechtenstein
Lithuania
Luxembourg
Madagascar
Malawi
Malaysia
Maldives
Mali
Malta
Marshall Islands
Mauritania
Mauritius
Mexico
Micronesia, Federated States of
Monaco
Mongolia
Montenegro
Morocco
Mozambique
Myanmar
Namibia
Nauru
Nepal
Netherlands
New Zealand
Nicaragua
Niger
Nigeria
Norway
Oman
Pakistan
Palau
Panama
Papua New Guinea
Paraguay
Peru
Philippines
Poland
Portugal
Qatar
Republic of Korea
Republic of Moldova
Romania
Russian Federation
Rwanda
Saint Kitts and Nevis
Saint Lucia
Saint Vincent and the Grenadines
Samoa
San Marino
Sao Tome and Principe
Saudi Arabia
Senegal
Serbia
Seychelles
Sierra Leone
Singapore
Slovakia
Slovenia
Solomon Islands
Somalia
South Africa
Spain
Sri Lanka
Sudan
Suriname
Swaziland
Sweden
Switzerland
Syrian Arab Republic
Tajikistan
Thailand
The former Yugoslav Republic of Macedonia
Timor-Leste
Togo
Tonga
Trinidad and Tobago
Tunisia
Turkey
Turkmenistan
Tuvalu
Uganda
Ukraine
United Arab Emirates
United Kingdom of Great Britain and Northern Ireland
United Republic of Tanzania
United States of America
Uruguay
Uzbekistan
Vanuatu
Venezuela, Bolivarian Republic of
Viet Nam
Yemen
Zambia
Zimbabwe

## FinancialData
Financial information: cumulative from project start to [insert date]
DISBURSEMENT OF AF GRANT FUNDS
How much of the total AF grant as noted in Project Document plus any project preparation grant has been spent to date?
Estimated cumulative total disbursement as of 22/01/2014 | 856000
Add any comments on AF Grant Funds. (word limit=200)
EXPENDITURE DATA
List ouput and corresponding amount spent for the current reporting period | ITEM / ACTIVITY / ACTION | AMOUNT
| Output 1.1. Rainfall-runoff and groundwater models developed and institutionalized within the Study and Research Center of Djibouti (Centre d’Etudes et de la Recherche de Djibouti, CERD ) and the Water Department of the Ministry of Agriculture to project likely climate change impacts on the water availability in the areas of Petit Bara and Grand Bara. | 291512.55
| Output 1.2: Based on model outputs, controlled groundwater extraction, artificial recharge and climate “smart” management plans that take into account seasonal changes in precipitation as well as long term mean amounts, projections, developed, and benefiting 30,000 people. | 0
| Output 1.3: Community-based surface water harvesting infrastructures, such as earth dams, percolation basins and subsurface dams which increase surface supply and groundwater tables in support of shade-garden pilot schemes (see 2.1) introduced and related local management rules and structures established. | 22288.14
| Output 1.4: Good practice guidelines based on knowledge sharing for integrated groundwater and surface water maintenance and use developed through stakeholder-led and participatory processes; including community water management teams, government water regulators, Ministry’s technical staff, and agriculture extension services. | 0
| Output 2.1: Six sets of 38 pilot community-managed agro-pastoral shade garden plots (1 ha per family) established that includes date palms, multi-purpose fence trees, local and regional varieties of climate resilient forage, vegetables and fruits (henna, dates, jujube, and mango, etc) benefiting 228 agro-pastoral families - approximately 2,800 people. | 197817.93
| Output 2.2: Improved extension service for shade gardening benefiting 228 agro-pastoral families - approximately 2,800 people (targeted training for extension service personnel and agro-pastoralists designed and delivered on the issues grazing, forage management, cultivation techniques, crop protection, water efficiency, composting methods, etc, in the context of increasing climate change pressures). | 0
| Output 2.3. Well-sized feed/forage stocking facilities created in both project locations to allow better management of forage availability over repeated drought periods. | 55892.65
| Output 3.1: A three-tiered adaptation-oriented micro-finance scheme that supports climate-resilient shade gardening practices in the Grand and Petit Bara plains developed through partnership with the Djiboutian Agency for Social Development (Agence Djiboutienne de Developpement Sociale, ADDS ) which generates a total value of US$ 300,000 throughout the project. | 39057.71
| Output 3.2: At least 300 agro-pastoralists have been organised to form agro-pastoral cooperatives (including women cooperatives) to facilitate training on climate-resilient agro-pastoral practices and to support the development of financial literacy and the diversification of agricultural activities. | 25000
| Output 3.3: At least four established agro-pastoral cooperatives develop comprehensive climate adaptation plans, incorporating lessons learned on best practices for shade gardens to be integrated into the National Programme for Food Security and the National Microfinance Policy, in order to facilitate the replication of shade-garden-based adaptation solutions | 0
| Project Execution cost | 224358.43
| TOTAL | 855927.41
PLANNED EXPENDITURE SCHEDULE
List outputs planned and corresponding projected cost for the upcoming reporting period | ITEM / ACTIVITY / ACTION | PROJECTED COST | Est. Completion Date
| Output 1.1. Rainfall-runoff and groundwater models developed and institutionalized within the Study and Research Center of Djibouti (Centre d’Etudes et de la Recherche de Djibouti, CERD ) and the Water Department of the Ministry of Agriculture to project likely climate change impacts on the water availability in the areas of Petit Bara and Grand Bara. | 0 | 311/12/2014
| Output 1.2: Based on model outputs, controlled groundwater extraction, artificial recharge and climate “smart” management plans that take into account seasonal changes in precipitation as well as long term mean amounts, projections, developed, and benefiting 30,000 people | 404168 | 2014-08-31
| Output 1.3: Community-based surface water harvesting infrastructures, such as earth dams, percolation basins and subsurface dams which increase surface supply and groundwater tables in support of shade-garden pilot schemes (see 2.1) introduced and related local management rules and structures established. | 472168 | 2014-08-31
| Output 1.4: Good practice guidelines based on knowledge sharing for integrated groundwater and surface water maintenance and use developed through stakeholder-led and participatory processes including community water management teams, government water regulators, Ministry’s technical staff, and agriculture extension services. | 10000 | 2014-12-31
| Output 2.1: Six sets of 38 pilot community-managed agro-pastoral shade garden plots (1 ha per family) established that includes date palms, multi-purpose fence trees, local and regional varieties of climate resilient forage, vegetables and fruits (henna, dates, jujube, and mango, etc) benefiting 228 agro-pastoral families - approximately 2,800 people. | 306164 | 2014-12-31
| Output 2.2: Improved extension service for shade gardening benefiting 228 agro-pastoral families - approximately 2,800 people (targeted training for extension service personnel and agro-pastoralists designed and delivered on the issues grazing, forage management, cultivation techniques, crop protection, water efficiency, composting methods, etc, in the context of increasing climate change pressures) | 30000 | 2014-12-31
| Output 2.3. Well-sized feed/forage stocking facilities created in both project locations to allow better management of forage availability over repeated drought periods | 0 | 2014-12-31
| Output 3.1: A three-tiered adaptation-oriented micro-finance scheme that supports climate-resilient shade gardening practices in the Grand and Petit Bara plains developed through partnership with the Djiboutian Agency for Social Development (Agence Djiboutienne de Developpement Sociale, ADDS ) which generates a total value of US$ 300,000 throughout the project. | 0 | 2014-12-31
| Output 3.2: At least 300 agro-pastoralists have been organised to form agro-pastoral cooperatives (including women cooperatives) to facilitate training on climate-resilient agro-pastoral practices and to support the development of financial literacy and the diversification of agricultural activities. | 30000 | 2014-12-31
| Output 3.3: At least four established agro-pastoral cooperatives develop comprehensive climate adaptation plans incorporating lessons learned on best practices for shade gardens to be integrated into the National Programme for Food Security and the National Microfinance Policy in order to facilitate the replication of shade-garden-based adaptation solutions. | 0 | 2014-12-31
| Output :Project Execution cost | 57460 | 2014-12-31
| Total | 1309960
ACTUAL CO-FINANCING (If the MTR or TE have not been undertaken this reporting period, DO NOT report on actual co-financing.)
How much of the total co-financing as committed in the Project Document has actually been realized?
Estimated cumulative actual co-financing as verified during Mid-term Review (MTR) or Terminal Evaluation (TE).
Add any comments on actual co-financing in particular any issues related to the realization of in-kind, grant, credits, loans, equity, non-grant instruments and other types of co-financing. (word limit=200)

## Procurement (hidden)
PROCUREMENT DATA
Please provide information for all contracts over $2,500 USD
Please provide the number of contracts under $2,500, signed during this reporting period: |  |  |  | 5
LIST OF CONTRACTS
List all contracts related to the project/program with signature dates
Contract Type | Agency / Contracted party | Contract Value/Amount (USD) | Signiture Date | Payment to Date | Remaining Balance
contractual service | Saida Ali Mahamadé | 12000 | 2012-10-01 | 12000 | 0
Contractual service | Ali Adou Ahmed | 5423 | 2012-12-01 | 5423 | 0
Contractual service | Ali Adou Ahmed | 5423 | 2013-12-01 | 451 | 4972
repairing building | Buildex | 3367 | 2013-02-24 | 3367 | 0
Contractual service | Cara Tobin | 14486 | 2013-03-16 | 14486 | 0
Contractual service | Mohamed Omar Ibrahim | 9600 | 2013-06-13 | 6720 | 2880
Contractual service | AUBRY Alessandro | 24081 | 2013-10-20 | 5548 | 18533
Contractual service | Abdoulfatah Abdourahman Arab | 3800 | 2013-10-07 | 1900 | 1900
Contractual service | Ali OMAR CHIRWA | 2000 | 2013-11-01 | 1000 | 1000
Contractual service | Youssouf HASSAN CHEICK MOUSSA | 6000 | 2013-10-04 | 4000 | 2000
Contractual service | BUILDEX ALUMINIUM | 2500 | 2013-10-05 | 2500 | 0
Contractual service | Aden ATTEYEH | 830 | 2013-09-08 | 830 | 0
Contractual service | OKAMBAWA Codjo Irénée | 28120 | 2013-06-19 | 19684 | 8436
Contractual service | Agora Consulting | 22000 | 2013-07-08 | 6600 | 15400
Contractual service | CERD | 151791 | 2013-07-28 | 60716 | 91075
Contractual service | ARAG | 25000 | 2013-08-19 | 7500 | 17500
Contractual service | Société Africaine d'Ingénierie International (SAFI) | 87420 | 2013-06-22 | 26226 | 61194
Contractual service | Ali Adou Ahmed | 2130 | 2013-12-01 | 0 | 2130
Contractual service | Saida Ali Mahamadé | 3000 | 2013-10-01 | 2000 | 1000
Contractual service | Youssouf HASSAN CHEICK MOUSSA | 830 | 2013-09-07 | 830 | 0
works contract | Direction des Grands Travaux | 33180 | 2013-10-26 | 22288 | 10892
works contract | LUNE (lot N°5) | 27262.14 | 2013-12-21 | 5534.46 | 21727.68
works contract | LUNE (lot N°6) | 23050.85 | 2013-12-21 | 4610.17 | 18440.12
works contract | ATTEYEH (lot N°4) | 27505 | 2013-12-21 |  | 27505
works contract | ATTEYEH (lot N°2) | 25485 | 2013-12-21 |  | 25485
works contract | YABEH | 55892 | 2013-11-05 | 33479 | 22413
works contract | SAID WAIS (lot N°6) | 27344 | 2013-12-21 | 0 | 27344
works contract | SAID WAIS (lot N°7) | 28005 | 2013-12-21 | 0 | 28005
works contract | SAID WAIS (lot N°3) | 25706.22 | 2013-12-21 | 5141.24 | 20564.98
works contract | WABERI (lot N°1) | 27067 | 2013-12-21 | 0 | 27067
works contract | WABERI (lot N°3) | 22677 | 2013-12-21 | 0 | 22677
works contract | PROGRES (lot N°7) | 18559 | 0 | 0 | 18559
works contract | PROGRES (lot N°8) | 20135 | 2013-12-21 | 0 | 20135
works contract | ISMAEL DARAR (lot N°1) | 27720.35 | 2013-12-21 | 5544.07 | 22176.28
works contract | LUNE | 12661 | 2013-11-14 | 0 | 12661
works contract | ABDILLAHI GUEDI (lot N°2) | 27593.22 | 2013-12-21 | 5534.46 | 22058.76
Contractual service | ADEN ATTEYEH | 2000 | 2013-10-07 | 2000 | 0
|  | 841643.78 |  | 265912.4 | 575730.82
BIDS
List all bids for each contact signed with date of open call and winning bid
CONTRACT & Procurement Method | Submitted Bids | Bid Amount (USD) | Winning Bid Amount (USD) | Selection Justification for the Winner
Name of Contract , Procruement Method, Date of Call | Buildex Alluminium | 3367 | 3367 | Lowest financial offer
| Entreprise Mohamed ABDO MOHAMED | 3971
| Entreprise YACIN ATTEYEH SOUGAL | 3728
Restrictive list
2013-02-13
Name of Contract , Procruement Method, Date of Call | SAIDA ALI MAHAMADE | 120000 |  | Based on the roster list of Ministry Of Environment
2012-10-01
Name of Contract , Procruement Method, Date of Call | ALI ADOU AHMED | 5423 |  | Based on the roster list of the ministry of environment
2012-10-01
Name of Contract , Procruement Method, Date of Call | Cara Tobin | 14486 | 14486 | Selection was based on UNDP Roster
Name of Contract , Procruement Method, if appicable Date of Call | Mohamed Omar Ibrahim | 9600 | 9600 | Best Technical and financial offer
TACCO Conuslting
Habon Youssef Houssein
Open BID
2013-05-06
Name of Contract , Procruement Method, if appicable Date of Call | AUBRY ALESSANDRO | 24081 | 24081 | Selection was based on the ministry of environment Roster list
DEL GIUDICE CLAUDIO
GUGLIELMO BRACCESI
Restrictive list
2013-10-10
Name of Contract , Procruement Method, if appicable Date of Call | AbdoulFatah Abdourahman Arab | 3800 | 3800 | Selection was based on ministry of environment Roster list
Nourridine Elmi Robleh
Ahmed I brahim ILTIRI
Restrictive list
2013-09-30
Name of Contract , Procruement Method, if appicable Date of Call | Youssouf Hassan Cheick Moussa | 6000 | 6000 | Selection was based on ministry of environment Roster list
Liban Omar Hassan
Ibrahim Hassan
Restrictive list
2013-09-26
Name of Contract , Procruement Method, if appicable Date of Call | Buildex Alluminium | 2500 | 2500 | Lowest financial offer
| Entreprise Mohamed ABDO MOHAMED | 3250
| Entreprise Yacin ETTEYEH SOUGAL | 2700
Restrictive list
2013-09-29
Name of Contract , Procruement Method, if appicable Date of Call | OKAMBAWA Iénée Codjo | 28750 | 28120 | Best technical and financial offer
Abdallah Hamadou Mohamed
Malick Mohamed Garad
Open BID
2013-05-06
Name of Contract , Procruement Method, if appicable Date of Call | Agora Consulting | 22000 | 22000 | Direct agreement and decision made by the ministry of environment
Direct agreement
2013-07-08
Name of Contract , Procruement Method, if appicable Date of Call | Centre d'Etudes et de Recherche de Djibouti | 151791 | 151791 | Direct agreement based on MOU between CERD and MHUE based on the project document
Direct agreement
2013-07-28
Name of Contract , Procruement Method, if appicable Date of Call | ARAG | 25000 | 25000 | Best technical and financial offer
Cabinet d'expertise agricole
Free Intelligent
Restrictive list
2013-07-31
Name of Contract , Procruement Method, if appicable Date of Call | Société Africaine d'Ingénierie (SAFI) | 93000 | 87420 | Best Technical and financial offer and based on the recommendation of the ministry of environment
| SCET TUNISIE | 108094
| PROGEST | 0
Open BID
2013-05-06
Name of Contract , Procruement Method, if appicable Date of Call | ALI ADOU AHMED | 5423 | 5423 | Extension of contract
extension of contract
2013-12-01
Name of Contract , Procruement Method, if appicable Date of Call | SAIDA ALI MAHAMADE | 3000 | 3000 | Extension of contract
extension of contract
2013-10-01
Name of Contract , Procruement Method, if appicable Date of Call | Direction des Grands Travaux (DGT) | 33180 | 33180 | Involved as part of project implementation based on the project document
Direct agreement
2013-10-26
Name of Contract , Procruement Method, if appicable Date of Call | LUNE | 27262 | 27262 | Financial lowest offer
| WABERI | 30848
| ATTEYEH | 30494
| BARWAQO | 39590
Restrictive list
2013-11-27
Name of Contract , Procruement Method, if appicable Date of Call | WABERI | 25994 | 23050 | Financial lowest offer
| LUNE | 23050
| ATTEYEH | 26785
| BARWAQO | 34638
Restrictive list
2013-11-27
Name of Contract , Procruement Method, if appicable Date of Call | WABERI | 42180 | 27505 | Financial lowest offer
| ATTEYEH | 27505
| BOULALEH | 35248
| MMB | 35636
Restrictive list
2013-11-27
Name of Contract , Procruement Method, if appicable Date of Call | WABERI | 34053 | 25485 | Financial lowest offer
| ATTEYEH | 25485
| BOULALEH | 30116
| MMB | 35636
Restrictive list
2013-11-27
Name of Contract , Procruement Method, if appicable Date of Call | YABEH | 55892 | 55892 | Financial lowest offer
| Le PROGRES | 69423
| DJIBRIL | 61258
Restrictive list
2013-10-17
Name of Contract , Procruement Method, if appicable Date of Call | ECG SAID WAIS | 27344 | 27344 | Financial lowest offer
| ARREY | 32994
| HOUSSEIN ASSOWEH | 30424
| ARREY | 28944
Restrictive list
2013-11-27
Name of Contract , Procruement Method, if appicable Date of Call | ECG SAID WAIS | 28006 | 28005 | Financial lowest bid
| YOUSSOUF HARED ASSOWEH | 33263
| HOUSSEIN ASSOWEH | 31489
| ARREY | 37181
Restrictive list
2013-11-27
Name of Contract , Procruement Method, if appicable Date of Call | ECG SAID WAIS | 25706 | 25706 | Financial lowest offer
| MOUSSA RAYALEH ASSOWEH | 30169
| ARREY | 35367
| HOUSSEIN ASSOWEH | 30198
Restrictive list
2013-11-27
Name of Contract , Procruement Method, if appicable Date of Call | WABERI | 27067 | 27067 | Financial lowest offer
| DAHER IGUEH FARAH | 45570
| LUNE | 30799
| ATTEYEH | 30039
Restrictive list
2013-11-27
Name of Contract , Procruement Method, if appicable Date of Call | WABERI | 22677 | 22677 | Financial lowest offer
| LUNE | 24017
| ATTEYEH | 25418
| MACHAALLAH | 30147
Restrictive list
2013-11-27
Name of Contract , Procrurement Method, if appicable Date of Call | ATTEYEH | 22051 | 18559 | Financial lowest offer
| HORSED | 20480
| YABEH | 20407
| PROGRES | 18559
Restrictive list
2013-11-27
Name of Contract , Procruement Method, if appicable Date of Call | ATTEYEH | 24170 | 20136 | Financial lowest offer
| YABEH | 22271
| HORSED | 23023
| PROGRES | 20136
Restrictive list
2013-11-27
Name of Contract , Procruement Method, if appicable Date of Call | ISMAEL DARAR FARAH | 27720 | 27720 | Financial lowest offer
| HASSAN YOUSSOUF GUEDI | 34116
| ALLA-AMINE | 45571
| DAHER IGUEH FARAH | 45571
Restrictive list
2013-11-27
Name of Contract , Procruement Method, if appicable Date of Call | LUNE | 12661 | 12661 | Financial lowest offer
| HOUSSEIN HASSAN MOUSSE | 16050
| Entreprise WABERI | 13559
Restrictive list
2013-11-07
Name of Contract , Procruement Method, if appicable Date of Call | ABDILLAHI GUEDI DIRANEH | 27672 | 27672 | Financial lowest offer
| OMAR ALI ADJAB | 32489
| OSMAN DARAR | 34294
| HASSAN YOUSSOUF GUEDI | 30121
Restrictive list
2013-11-27

## Risk Assesment
RISK ASSESMENT
IDENTIFIED RISKS
List all Risks identified in project preparation phase and what steps are being taken to mitigate them
Identified Risk | Current Status | Steps Taken to Mitigate Risk
Reluctance of farmers or pastoralists to engage in agro-pastoralist practices of shade gardens | Decreasing | The project management unit has met several times with the communities and presented the objectives of the project for a sensitization purpose. The communities have expressed support and their interest in the shade gardening.
Repeated drought | Decreasing | After the protracted drought period (2007-2011), the rain situation is now improving in the country. To better manage the available quantity of water even in the event of repeated droughts, the project management unit has undertaken work on collecting the best irrigationpractices in Djibouti. The use of PVC pipes in place of traditional open air concrete channels was decided in order to eliminate the loss by evapo-transpiration of water in the channels. The promotion of drip irrigation, whenever it is cost effective, has also been decided by the PMU.
Initial studies reveal insufficient water availability and quality | Decreasing | Comprehensive and detailed scientific exploration combining hydrogeology, hydrology, geology, and geophysics techniques was undertaken for the sitting of the wells. Chemistry of the existing water sources of the Grand Bara and Petit Bara (either surface or groundwater) has been studied. Areas that may reveal salinity of the underground water have been eliminated already from the drilling program. Areas with high probability of tapping water resources were selected and included in the drilling program as priority areas in 2014. Hydrology studies revealed that more than two millions cubic meter of water can be harvesed in the rainy season. Earth dams to collect this high volume of water will be constructed and decrease furthermore this identified risk.
Low level of cooperation between executing institutions | Increasing | A technical committee was established as a discussion platform among the involved institutions. The committee meets once every month to discuss issues that may delay the implementation of the project.
Delays in project implementation due to simultaneous construction works for complementary projects | Decreasing | The PMU is maintaining regular contact with the tehcnical departments of the Ministry of Agriculture that will be involved in the construction of the water infrastructures. The planning of contruction of water infrastructures (boreholes, dams) is already determined with these line departments. Construction will be done in 2014.
Insufficient interest and social cohesiveness amongst sedentary pastoral communities to adhere to the alternative production models proposed by the project | Decreasing | The project management unit has met several times with the communities and presented the objectives of the project for a sensitization purpose. The communities have expressed support and their interest in the shade gardening.
Theft of solar panels, pump parts or fencing materials in any of the shade garden zones | No change. Reporting against this risk will be done once the panels will installed after the drilling of the boreholes.
Critical Risks Affecting Progress (Not identified at project design)
Identify Risks with a 50% or > likelihood of affecting progress of project
Identified Risk | Current Status | Steps Taken to Mitigate Risk
Unwelcome livestock (livestock from surrounding pastoralists) invading the agro-pastoral plots which can provoke disputes between the farmers and pastoralists | low | Secure metal and stone fencing will be constructed around each agro-pastoral site to deter all unwelcome animals. This will prevent the risk of invading livestock and potential disputes between the pastoralists and agro pastoralists.
Pollution from petrol spills when trucks overturn on highways | low | This will be prevented by placing the pilot sites at least 100 meters from the roadside or the required distance identified by the Environmental Impact Assessment
Risk of people becoming dependent on food aid in the beginning years of the project before fruit and vegetables can be cultivated | medium | Early contact have been initiated with the local office of the World Food Program to see the possibility if WFP providing food aid in the beginning years of the project. Discussions are ongoing. It is well established that a productive 1 hectare or even q
Limited capacity of local populations to perform maintenance on boreholes and solar-powered well pumps | medium | Water management groups already exist in surrounding regions. It is typical practice in the hierarchy of the village to assign roles, such as to maintain the wells. This project includes activities to form and train the water management groups so that the
Risk Measures: Were there any risk mitigation measures employed during the current reporting period? If so, were risks reduced? If not, why were these risks not reduced?
Add any comments relevant to risk mitigation (word limit = 500)
In its first review of the PPR, the AF Secretariat pointed out also that it was reported in the inception report, under the section ESSP of the inception report, that there may be some “voluntary resettlement”. It is indeed the case, and voluntary resettlement will happen for a small number of families, who will be asked to resettle closer to agro-pastoral farms. Indeed the location of agro-pastoral farms will depend on the sitting of boreholes and surface water infrastructures. Therefore it may be as far as several kilometers from where families are located now. However, it is important to note that these communities are nomads and the issue of movemnet is not problematic for them. Their type of houses are also made of wood, and is tailored for easy displacement because of their initial nomadic way of life. Consultations are ongoing and results will be communicated to the AF Secretariat once these consultations are finalized. AF Secretariat should note that these consultations will be finalized once the establishment of the water infrastructures is completed.

## Rating
RATING ON IMPLEMENTATION PROGRESS
For rating definitions please see bottom of page.
| Progress on Key Milestones |  | Expected Progress |  | Progress to Date | Rating
Project Manager/Coordinator: | Construction of water infrastructures for the harvest of underground water or surface water |  | to be completed mainly by the end of year 2 of implementation |  | good progress | S
| Development of the clmate resilient shade gardens |  | construction to start by the middle of year 2 of implementation |  | very good progress | HS
| Rural beneficiaries are organized into agricultural anf financial cooperatives, have access to microfinance and develop climta resilient agro-pastoral enterprises |  | preparatory process to start in the year 1 of implementation, enterprises to be developped in the year 3 of project implementation |  | good progress | S
[5 empty] | Overall Rating | S
Please Provide the Name and Contact information of person(s) reponsible for completeling the Rating section
| Name: | Houssein Rirache Robleh
| Email: | housseinrirach@yahoo.fr
Please justify your rating. Outline the positive and negative progress made by the project since it started. Provide specific recommendations for next steps. . (word limit=500)
The implementation of the project is progressing as planned in the project document. The geoscientific (hydrology, hydrogeology, geology and geotechnical, geophysics) studies which are the necessary requirements before undertaking the drilling program and the construction of the surface water infrastructures have been finalized, or are in the finalization stage. For the development of the climate shade gardens, the project has already started the construction of 13 hectares for 27 beneficiaries ahead of the planned time in the project document. Preparatory studies for the development of climate resilient enterprises is also on good track as two studies were already delivered : (1) a study on the fiscal framework for the micro-finance and (2) identification of potential climate resilient agro-pastoral products that could be funded by micro-finance,
| Progress on Key Milestones |  | Expected Progress |  | Progress to Date | Rating
Implementing Agency | Construction of water infrastructures for the harvest of underground water or surface water |  | To be completed mainly by the end of year 2 of implementation |  | Some progress and good trends | MS
| Development of the shade gardens |  | Construction to start by the middle of year 2 of implementation |  | Good progress | S
| Rural beneficiaries are organized into agricultural anf financial cooperatives, have access to microfinance and develop climta resilient agro-pastoral enterprises |  | Preparatory process to start in the year 1 of implementation, enterprises to be developped in the year 3 of project implementation |  | Good progress | S
[5 empty] | Overall Rating | S
Please Provide the Name and Contact information of person(s) reponsible for completeling the Rating section
| Name: | Idriss Ahmed Hared, Climate Change Policy Specialist
| Email: | idriss.hared@undp.org
| Progress on Key Milestones |  | Expected Progress |  | Progress to Date | Rating
Other
Overall Rating
Please Provide the Name and Contact information of person(s) reponsible for completeling the Rating section
| Name: | Idriss Ahmed Hared, Climate Change Policy Specialist
| Email: | idriss.hared@undp.org
| Please justify your rating and address the following points: 1. Indicate trends, both positive and negative, in achievement of outcomes as per the project indicators. 2. Detail critical risks that have affected progress. 3. Outline response to MTR undertaken this reporting period. 4. Outline action plan to address projects with a rating of HU, U or MU. Please keep your input to 1200 words |  | Overall, the project is progressing well towards the achievement of its outcomes. After the inception phase, the project has now moved into full implementation and is delivering on time and on scope. Mobilizing both underground and surface water under the outcome one is critical for this project. Outcome 2 cannot be achieved without securing the access to good quantity and quality water. And outcome three cannot be achieved unless outcome 2 is achieved, Some delays in the engagement of the national scientific institutions have slowe down the project, and results of the scientifc assessment were delivered several months late in 2013. The most critical risk that affected the project was coordination among the involved institutions. A technical committee, which is a discussion platform among the involved institutions was established in order to avoid any further delay in the project.
Rating Definitions
|  |  | Highly Satisfactory (HS) | Project actions/activities planned for current reporting period are progressing on track or exceeding expectations to acheive all major outcomes/outputs for given reporting period, without major shortcomings. The project can be presented as “good practice”.
|  |  | Satisfactory (S) | Project actions/activities planned for current reporting period are progressing on track to achieve most of its major outcomes/outputs with only minor shortcomings.
|  |  | Marginally Satisfactory (MS) | Project actions/activities planned for current reporting period are progressing on track to achieve most major relevant outcomes/outputs, but with either significant shortcomings or modest overall relevance.
|  |  | Marginally Unsatisfactory (MU) | Project actions/activities planned for current reporting period are not progressing on track to achieve major outcomes/outputs with major shortcomings or is expected to achieve only some of its major outcomes/outputs.
|  |  | Unsatisfactory (U) | Project actions/activities planned for current reporting period are not progressing on track to achieve most of its major outcomes/outputs.
|  |  | Highly Unsatisfactory (U) | Project actions/activities planned for current reporting period are not on track and shows that it is failing to achieve, and is not expected to achieve, any of its outcomes/outputs.

## Project Indicators
PROJECT Indicators
Please provide all indicators being tracked for the project as outlined in the project document
Type of Indicator (indicators towards Objectives, Outcomes, etc…)
Type of Indicator | Indicator | Baseline | Progress since inception | Target for Project End
Outcome 1 | Indicator 1.1: number of planned boreholes, dams and water storage basins with associated solar pumping equipment in place and operational. | Existing water infrastrucres in the project areas: 2 borehole, 1 earth dam with a capacity of 500,000 cubic meter. Weak liability of installed solar pumping systems. | Exploration of undergroung water finalized, drilling program ready. surface water harvesting program on the final design stage. | 6 boreholes, 6 earth dams, 8 subsurface dams, 6 reservoirs, 6 solar pumping equipment.
| Indicator 1.2: water resource secured for shade garden irrigation to cover 228 ha and serve 30 000 people. | In the project zones, only 10 hectares are cultivated with the existing water infrastructures. | Exploration of undergroung water finalized, drilling program ready. surface water harvesting program on the final design stage. | 228 ha and at least 30,000 people are served with secure water infrastructure.
Output 1.1 | Indicator 1.1.1: approved detailed EIA and submission. | The Grand Bara and Petit Bara regions (project sites) are experiencing important land degradation. But there are no existing detailed studies describing land degradation and biodiversity loss in the areas. | EIE ongoing, to be finalized once the wells, dams and shade gardens locations are established | Completion of EIA and pedological, hydrological, and hydro-geological studies.
Output 1.2 | Indicator 1.2.1: percentage of total hectares of agro-pastoralists land which is irrigated by boreholes. | Only 6 hectares are irrigated by the boreholes at this time. | Development of 6 ha in Rakoubiyeel and 1 ha in Omar Djagac representing 3% of the total target | 228 ha.
| Indicator 1.2.2: amount of time spent in search of water from boreholes. | According to the WFP annual food security assessment report 2013, the time spent in search of water is 30 minutes for Arta and Ali Sabieh populations. | Boreholes of the project not yet in place. | Less than 30 minutes.
Output 1.3 | Indicator 1.3.1: percentage of total hectares of agropastoralists land, which is irrigated by surface water sources. | Only 7 hectares are irrigated by the surface water at this time. | Development of 5 ha in Kourtimalei representing 2% of the total target. | 228 ha.
| Indicator 1.3.2: amount of time in search of water from surface water sources. | According to the WFP annual food security assessment report 2013, the time spent in search of water is 30 minutes for Arta and Ali Sabieh populations. | Construction of earth dams not yet completed, therefore we can not report on this indicator yest. | Less than 30 minutes.
Output 1.4 | Indicator 1.4.1: number of maintenance efforts on water systems and percentage of successful local maintance efforts. | None. | Not yet. | 10 maintenances.
| Indicator 1.4.2: management plans and good practice guidelines emphasized and enforced by the water infrastructure management committee. | None. | Not yet. | One climate smart management plan for surface water and onr climate smart management plan for groundwater resources.
Outcome 2 | Indicator 2.1: Number of shade gardens developed including irrigation reservoirs, distribution networks, and fencing. | Zero. | 3 shade gardens are under construction/ implementation, totaling 13 ha, including 3 irrigation reservoirs totaling 600 cubic meters, 4400 linear meter of robust fencing, distribution network totaling 1600 linear meter of length. | Six sets of 38 pilots.
| Indicator 2.2: % of population who has developed shade gardens resilient to climate change. | Zero. | In progress, selection process ongoing. | 2800 people.
Output 2.2 | Indicator 2.2.1: number of project beneficiaries disaggregated according to gender who that have been trained on cultivation techniques, crop rotation, livestock hygiene etc by specialists | Zero. | Beneficiaries not targeted yet. | 228 families.
| Indicator 2.2.2: percentage change in beneficiaries capacities to cultivate their own land and raise livestock autonomouly | Zero. | Beneficiaries not targeted yet. | 100%.
Output 2.3 | Indicator 2.3.1: number of constructed storage facilities per agropastoral zone. | Zero. | Two storages under construction in Kourtimalei and Rakoubyeel. | 6 constructed storages.
| Indicator 2.3.2: percentage of beneficiaries that utilize storage facilities. | Zero. | 27 agropastoral families of existing shade gardens using new storage facilities representing 12% of total targeted families. | 100%.
Outcome 3 | Indicator 3.1: Number of MF products deployed to agro-pastoralists which provide loans ear-marked for adaptation to climate-change | Zero. | Progress in advocating for the provision of a government micro-credit line earmarked for adaptation activities. | 7 different types of products to be deployed by the end of the projects: 1) water equipment and resource (drip irrigation, pumping equipment, water harvesting); 2) livestock product; 3) agricultural inputs; 4) loans for creating small climate change agro-pastoral enterprises.
| Indicator 3.2: % of total population using microcredit products. | Zero. | Not yet. | 100%.
| Indicator 3.3: community- driven adaptation plans are integrated into National Programme for Food Security and the National MF policy. | Zero. | Not yet. | 4 adaptation plans.
Output 3.1 | Indicator 3.1.1: percentage of beneficiaries trained in microcredit principles. | Zero. | Not yet. | 100%.
| Indicator 3.1.2: number of technical guides prepared detailing how MF can be used for adaptation oriented activities. | Zero. | Technical guides not yet prepared, but steps have been taken: study on adaptation oriented agropastoral product has been delivered, technical guides will be available in 2014. | 1 comprehensive technical guide.
Ouput 3.2 | Indicator 3.2.1: number of loans and percentage of payback on loans. | Zero. | Not yet. | 228 loans at least and expected 100% paybacks.
| Indicator 3.2.2: percentage of population in each tier of 3-tiered microfinance programme (safety net, nao, and microfinance) | Zero. | Not yet. | To be determined.
Output 3.3 | Indicator 3.3.1: percentage of population, which has been organized into adaptation plan cooperatives. | Zero. | Not yet. | 100%.
| Indicator : 3.2.2: Attendance and participation at bi-annual workshops used to document community recommended measures to improve the adaptation oriented microfinance products. | Zero. | Not yet. | 6 bi-annual workshop expected to be conducted with the attendance and participation of approximately 300 persons.

## Lessons Learned
QUALITATIVE MEASURES and LESSONS LEARNED
Please complete the following section every reporting period
Implementation and Adaptive Management | Response
What implementation issues/lessons, either positive or negative, affected progress? | Coordination among involved institutions was somehow difficult at the start of project implementation, and is still a challenge for the project.
Were there any delays in implementation? If so, include any causes of delays. What measures have been taken to reduce delays? | Yes there were delays in the implementation of the project, in particular the drilling of the boreholes and construction of rainwater harvesting infrastructures. The reason is that the engagement of the involved technical institutions and the delivery of the outcomes of the scientific studies undertaken by these institutions were delayed. As such we are currently experiencing a delay of several months. To reduce the delays, the project management unit has discussed with the technical committee of the project and the steering committee of the project to find solutions. Two measures have been proposed by these committees in order to reduce the delays: (i) call for the acceleration of the scientific studies to the national institutions; (ii) strategic decision to anticipate the construction of the agricultural infrastructures for 11 hectares and strenghtening of existing 6 hectares in the project zones.
Describe any changes undertaken to improve results on the ground or any changes made to project outputs (i.e. changes to project design) | N/A.
How have gender considerations been taken into consideration during the reporting period? What have been the lessons learned as a consequence of inclusion of such considerations on project performance or impacts? | It is planned in the project to construct several plant nurseries managed by women. The project management unit has identified already the group of women, as well as the villages in which the nurseries will be sitted. The Omar Jagac and Rakoubyeel villages have been identified to host the nurseries because of the already existing water wells and because these sites are close to already identified agro-pastoral areas.
Please complete the following section at mid-term and project completion
Lessons for Adaptation | Response
Climate Resilience Measures
What have been the lessons learned, both positive and negative, in implementing climate adaptation measures that would be relevant to the design and implementation of future projects/programmes for enhanced resilience to climate change?
What is the potential for the climate resilience measures undertaken by the project/programme to be replicated and scaled up both within and outside the project area?
Concrete Adaptation Interventions
What have been the lessons learned, both positive and negative, in implementing concrete adaptation interventions that would be relevant to the design and implementation of future projects/programmes implementing concrete adaptation interventions?
What is the potential for the concrete adaptation interventions undertaken by the project/programme to be replicated and scaled up both within and outside the project area?
Community/National Impact
What would you consider to be the most successful aspects for the target communities?
What measures are/have been put in place to ensure sustainability of the project/program results?
What measures are being/could have been put in place to improve project/program results?
Knowledge Management
How has existing information/data/knowledge been used to inform project development and implementation? What kinds of information/data/knowledge were used?
If learning objectives have been established, have they been met? Please describe.
Describe any difficulties there have been in accessing or retrieving existing information (data or knowledge) that is relevant to the project. Please provide suggestions for improving access to the relevant data.
Has the identification of learning objectives contributed to the outcomes of the project? In what ways have they contributed?

## Results Tracker
Results Tracker for Adaptation Fund (AF) Projects
Goal: Assist developing-country Parties to the Kyoto Protocol that are particularly vulnerable to the adverse effects of climate change in meeting the costs of concrete adaptation projects and programmes in order to implement climate-resilient measures. Impact: Increased resiliency at the community, national, and regional levels to climate variability and change.
Important: Please read the following Results Framework and Baseline Guidance (also posted on the Adaptation Fund website) before entering your data
Link: http://www.adaptation-fund.org/sites/default/files/Results%20Framework%20and%20Baseline%20Guidance%20final.pdf
Please select the relevant Fund level Outcome and Output indicators that allign with the project objectives and outcomes
OBJECTIVE 1
Fund Outcome | Please select from dropdown menu below | Fund Outcome Indicator | Please select from dropdown menu below | Target at project/programme approval (see Units in next sheet) | Baseline (see Units in next sheet) | Mid-term Results | Terminal Results
Outcome 1: Reduced exposure at national level to climate-related hazards and threats Outcome 2: Strengthened institutional capacity to reduce risks associated with climate-induced socioeconomic and environmental losses Outcome 3: Strengthened awareness and ownership of adaptation and climate risk reduction processes at local level Outcome 4: Increased adaptive capacity within relevant development and natural resource sectors Outcome 5: Increased ecosystem resilience in response to climate change and variability-induced stress Outcome 6: Diversified and strengthened livelihoods and sources of income for vulnerable people in targeted areas Outcome 7: Improved policies and regulations that promote and enforce resilience measures | 4 | 1. Relevant threat and hazard information generated and disseminated to stakeholders on a timely basis 2.1. No. and type of targeted institutions with increased capacity to minimize exposure to climate variability risks 2.2. Number of people with reduced risk to extreme weather events 3.1. Percentage of targeted population aware of predicted adverse impacts of climate change, and of appropriate responses 3.2. Modification in behavior of targeted population 4.1. Development sectors' services responsive to evolving needs from changing and variable climate 4.2. Physical infrastructure improved to withstand climate change and variability-induced stress 5. Ecosystem services and natural assets maintained or improved under climate change and variability-induced stress 6.1. Percentage of households and communities having more secure (increased) access to livelihood assets 6.2. Percentage of targeted population with sustained climate-resilient livelihoods 7. Climate change priorities are integrated into national development strategy | 4.2 | 4.2 Fully improved By project completion, targeted rural communities of Grand Bara and Petit Bara will have secured and sustainable quantities of water for both agricultural, pastoral and drinking purposes and cost recovery mechanisms will be put in place as well as capacity of the ministry of water reinforced | Currently, water availaibility even for drinking purposes is not secured in Grand Bara and Petit Bara. For the existing water points, there is not water use permit in place.
Fund Output | Please select from dropdown menu below | Fund Output Indicator | Please select from dropdown menu below | Target at project/programme approval | Baseline | Mid-term Results | Terminal Results
Output 1: Risk and vulnerability assessments conducted and updated at a national level Output 2.1: Strengthened capacity of national and regional centres and networks to respond rapidly to extreme weather events Output 2.2: Targeted population groups covered by adequate risk reduction systems Output 3: Targeted population groups participating in adaptation and risk reduction awareness activities Output 4: Vulnerable physical, natural, and social assets strengthened in response to climate change impacts, including variability Output 5: Vulnerable physical, natural, and social assets strengthened in response to climate change impacts, including variability Output 6: Targeted individual and community livelihood strategies strengthened in relation to climate change impacts, including variability Output 7: Improved integration of climate-resilience strategies into country development plans |  | 1.1. No. and type of projects that conduct and update risk and vulnerability assessments 1.2. Development of early warning systems 2.1.1. No. of staff trained to respond to, and mitigate impacts of, climate-related events 2.1.2. Capacity of staff to respond to, and mitigate impacts of, climate-related events from targeted institutions increased 2.2.1. Percentage of population covered by adequate risk-reduction systems 2.2.2. No. of people affected by climate variability 3.1 No. and type of risk reduction actions or strategies introduced at local level 3.2 No. of news outlets in the local press and media that have covered the topic 4.1. No. and type of health or social infrastructure developed or modified to respond to new conditions resulting from climate variability and change (by type) 4. 2. No. of physical assets strengthened or constructed to withstand conditions resulting from climate variability and change (by asset types) 5. No. and type of natural resource assets created, maintained or improved to withstand conditions resulting from climate variability and change (by type of assets) 6.1. No. and type of adaptation assets (physical as well as knowledge) created in support of individualor community-livelihood strategies 6.2. Type of income sources for households generated under climate change scenario 7.1. No., type, and sector of policies introduced or adjusted to address climate change risks 7.2. No. or targeted development strategies with incorporated climate change priorities enforced | 4.2 | By project completion, six water extraction boreholes, one injection well for artifical recharge, six earth dams with a minimal volumetric capacity of 300,000 cubic meter, eight subsurface dam will be constructed. Water tariff permit will be established. At least 10 staff of the department of water will be trained on surface water harvesting, artificial recharge and sustainable water resources management. | Altough the Grand Bara and Petit Bara host thousand of rural communities, the quantity of water availaible for agricultural purposes is small, There are only three boreholes and 4 earth dams mainly used for drinking water. Except one earth dam, all the three others have only small volumetric capacitites (twenty thousand cubic meter). There is not especific cost recovery for the access to this water currently.
OBJECTIVE 2
Fund Outcome | Please select from dropdown menu below | Fund Outcome Indicator | Please select from dropdown menu below | Target at project/programme approval (see Units in next sheet) | Baseline | Mid-term Results | Terminal Results
Outcome 1: Reduced exposure at national level to climate-related hazards and threats Outcome 2: Strengthened institutional capacity to reduce risks associated with climate-induced socioeconomic and environmental losses Outcome 3: Strengthened awareness and ownership of adaptation and climate risk reduction processes at local level Outcome 4: Increased adaptive capacity within relevant development and natural resource sectors Outcome 5: Increased ecosystem resilience in response to climate change and variability-induced stress Outcome 6: Diversified and strengthened livelihoods and sources of income for vulnerable people in targeted areas Outcome 7: Improved policies and regulations that promote and enforce resilience measures |  | 1. Relevant threat and hazard information generated and disseminated to stakeholders on a timely basis 2.1. No. and type of targeted institutions with increased capacity to minimize exposure to climate variability risks 2.2. Number of people with reduced risk to extreme weather events 3.1. Percentage of targeted population aware of predicted adverse impacts of climate change, and of appropriate responses 3.2. Modification in behavior of targeted population 4.1. Development sectors' services responsive to evolving needs from changing and variable climate 4.2. Physical infrastructure improved to withstand climate change and variability-induced stress 5. Ecosystem services and natural assets maintained or improved under climate change and variability-induced stress 6.1. Percentage of households and communities having more secure (increased) access to livelihood assets 6.2. Percentage of targeted population with sustained climate-resilient livelihoods 7. Climate change priorities are integrated into national development strategy | 6.1 | 6.1 High improvement 228 rural households are engaged in shade gardening activities and have more secured livelihoods | 35,000 people leaving in rural areas of Ali-Sabieh and Arta regions in which are located Grand and Petit Bara. Around 20,000 people are classified as food insecure people; average livestock asset is 10 goats per family; average daily income per person estimated 0,75 US dollar; There are only few families practigin agriculture in the targeted regions because of the water scarcity.
Fund Output | Please select from dropdown menu below | Fund Output Indicator | Please select from dropdown menu below | Target at project/programme approval | Baseline | Mid-term Results | Terminal Results
Output 1: Risk and vulnerability assessments conducted and updated at a national level Output 2.1: Strengthened capacity of national and regional centres and networks to respond rapidly to extreme weather events Output 2.2: Targeted population groups covered by adequate risk reduction systems Output 3: Targeted population groups participating in adaptation and risk reduction awareness activities Output 4: Vulnerable physical, natural, and social assets strengthened in response to climate change impacts, including variability Output 5: Vulnerable physical, natural, and social assets strengthened in response to climate change impacts, including variability Output 6: Targeted individual and community livelihood strategies strengthened in relation to climate change impacts, including variability Output 7: Improved integration of climate-resilience strategies into country development plans |  | 1.1. No. and type of projects that conduct and update risk and vulnerability assessments 1.2. Development of early warning systems 2.1.1. No. of staff trained to respond to, and mitigate impacts of, climate-related events 2.1.2. Capacity of staff to respond to, and mitigate impacts of, climate-related events from targeted institutions increased 2.2.1. Percentage of population covered by adequate risk-reduction systems 2.2.2. No. of people affected by climate variability 3.1 No. and type of risk reduction actions or strategies introduced at local level 3.2 No. of news outlets in the local press and media that have covered the topic 4.1. No. and type of health or social infrastructure developed or modified to respond to new conditions resulting from climate variability and change (by type) 4. 2. No. of physical assets strengthened or constructed to withstand conditions resulting from climate variability and change (by asset types) 5. No. and type of natural resource assets created, maintained or improved to withstand conditions resulting from climate variability and change (by type of assets) 6.1. No. and type of adaptation assets (physical as well as knowledge) created in support of individualor community-livelihood strategies 6.2. Type of income sources for households generated under climate change scenario 7.1. No., type, and sector of policies introduced or adjusted to address climate change risks 7.2. No. or targeted development strategies with incorporated climate change priorities enforced | 6.1 | 228 hectares of agricultural plots with robust enclosure and irrigationn network developped/ At least 6 tree nurseries managed by women created/ t Training on agricultural techniques provided to 228 new farmers | Only few families are practicing the agriculture in the Petit Bara and Grand Bara areas
OBJECTIVE 3
Fund Outcome | Please select from dropdown menu below | Fund Outcome Indicator | Please select from dropdown menu below | Target at project/programme approval | Baseline | Mid-term Results | Terminal Results
Outcome 1: Reduced exposure at national level to climate-related hazards and threats Outcome 2: Strengthened institutional capacity to reduce risks associated with climate-induced socioeconomic and environmental losses Outcome 3: Strengthened awareness and ownership of adaptation and climate risk reduction processes at local level Outcome 4: Increased adaptive capacity within relevant development and natural resource sectors Outcome 5: Increased ecosystem resilience in response to climate change and variability-induced stress Outcome 6: Diversified and strengthened livelihoods and sources of income for vulnerable people in targeted areas Outcome 7: Improved policies and regulations that promote and enforce resilience measures |  | 1. Relevant threat and hazard information generated and disseminated to stakeholders on a timely basis 2.1. No. and type of targeted institutions with increased capacity to minimize exposure to climate variability risks 2.2. Number of people with reduced risk to extreme weather events 3.1. Percentage of targeted population aware of predicted adverse impacts of climate change, and of appropriate responses 3.2. Modification in behavior of targeted population 4.1. Development sectors' services responsive to evolving needs from changing and variable climate 4.2. Physical infrastructure improved to withstand climate change and variability-induced stress 5. Ecosystem services and natural assets maintained or improved under climate change and variability-induced stress 6.1. Percentage of households and communities having more secure (increased) access to livelihood assets 6.2. Percentage of targeted population with sustained climate-resilient livelihoods 7. Climate change priorities are integrated into national development strategy | 6.2 | A three-tiered adaptation-oriented micro-finance scheme that supports climate-resilient shade gardening practices in the Grand and Petit Bara plains developed through partnership with ADDS which generates a total value of US$ 300,000 throughout the project for 228 families. Daily food consumption is not included in this income. | According to 2012 WFP assessment in rural areas, the daily income of these families is 0,75 $ US per person and they have to use this income for all their needs including the food (when the WFP food aid is not availaible).
Fund Output | Please select from dropdown menu below | Fund Output Indicator | Please select from dropdown menu below | Target at project/programme approval | Baseline | Mid-term Results | Terminal Results
Output 1: Risk and vulnerability assessments conducted and updated at a national level Output 2.1: Strengthened capacity of national and regional centres and networks to respond rapidly to extreme weather events Output 2.2: Targeted population groups covered by adequate risk reduction systems Output 3: Targeted population groups participating in adaptation and risk reduction awareness activities Output 4: Vulnerable physical, natural, and social assets strengthened in response to climate change impacts, including variability Output 5: Vulnerable physical, natural, and social assets strengthened in response to climate change impacts, including variability Output 6: Targeted individual and community livelihood strategies strengthened in relation to climate change impacts, including variability Output 7: Improved integration of climate-resilience strategies into country development plans |  | 1.1. No. and type of projects that conduct and update risk and vulnerability assessments 1.2. Development of early warning systems 2.1.1. No. of staff trained to respond to, and mitigate impacts of, climate-related events 2.1.2. Capacity of staff to respond to, and mitigate impacts of, climate-related events from targeted institutions increased 2.2.1. Percentage of population covered by adequate risk-reduction systems 2.2.2. No. of people affected by climate variability 3.1 No. and type of risk reduction actions or strategies introduced at local level 3.2 No. of news outlets in the local press and media that have covered the topic 4.1. No. and type of health or social infrastructure developed or modified to respond to new conditions resulting from climate variability and change (by type) 4. 2. No. of physical assets strengthened or constructed to withstand conditions resulting from climate variability and change (by asset types) 5. No. and type of natural resource assets created, maintained or improved to withstand conditions resulting from climate variability and change (by type of assets) 6.1. No. and type of adaptation assets (physical as well as knowledge) created in support of individualor community-livelihood strategies 6.2. Type of income sources for households generated under climate change scenario 7.1. No., type, and sector of policies introduced or adjusted to address climate change risks 7.2. No. or targeted development strategies with incorporated climate change priorities enforced | 6.2 | By the completion of the project, the 228 targted beneficiary families will have diversified income from the sell of agricultural products (vegetables, fruits, forage) and pastoral products (goats, goats and cows milk) | Currently the income of 228 targeted rural families is mainly based on the sell of animals (one to two animals per year generating a maximum of 100 USD), charcoal (increasing the depletion of scarce wood resources) and remittance from their families leaving in cities.
OBJECTIVE 4
Fund Outcome | Please select from dropdown menu below | Fund Outcome Indicator | Please select from dropdown menu below | Target at project/programme approval | Baseline | Mid-term Results | Terminal Results
Outcome 1: Reduced exposure at national level to climate-related hazards and threats Outcome 2: Strengthened institutional capacity to reduce risks associated with climate-induced socioeconomic and environmental losses Outcome 3: Strengthened awareness and ownership of adaptation and climate risk reduction processes at local level Outcome 4: Increased adaptive capacity within relevant development and natural resource sectors Outcome 5: Increased ecosystem resilience in response to climate change and variability-induced stress Outcome 6: Diversified and strengthened livelihoods and sources of income for vulnerable people in targeted areas Outcome 7: Improved policies and regulations that promote and enforce resilience measures |  | 1. Relevant threat and hazard information generated and disseminated to stakeholders on a timely basis 2.1. No. and type of targeted institutions with increased capacity to minimize exposure to climate variability risks 2.2. Number of people with reduced risk to extreme weather events 3.1. Percentage of targeted population aware of predicted adverse impacts of climate change, and of appropriate responses 3.2. Modification in behavior of targeted population 4.1. Development sectors' services responsive to evolving needs from changing and variable climate 4.2. Physical infrastructure improved to withstand climate change and variability-induced stress 5. Ecosystem services and natural assets maintained or improved under climate change and variability-induced stress 6.1. Percentage of households and communities having more secure (increased) access to livelihood assets 6.2. Percentage of targeted population with sustained climate-resilient livelihoods 7. Climate change priorities are integrated into national development strategy
Fund Output | Please select from dropdown menu below | Fund Output Indicator | Please select from dropdown menu below | Target at project/programme approval | Baseline | Mid-term Results | Terminal Results
Output 1: Risk and vulnerability assessments conducted and updated at a national level Output 2.1: Strengthened capacity of national and regional centres and networks to respond rapidly to extreme weather events Output 2.2: Targeted population groups covered by adequate risk reduction systems Output 3: Targeted population groups participating in adaptation and risk reduction awareness activities Output 4: Vulnerable physical, natural, and social assets strengthened in response to climate change impacts, including variability Output 5: Vulnerable physical, natural, and social assets strengthened in response to climate change impacts, including variability Output 6: Targeted individual and community livelihood strategies strengthened in relation to climate change impacts, including variability Output 7: Improved integration of climate-resilience strategies into country development plans |  | 1.1. No. and type of projects that conduct and update risk and vulnerability assessments 1.2. Development of early warning systems 2.1.1. No. of staff trained to respond to, and mitigate impacts of, climate-related events 2.1.2. Capacity of staff to respond to, and mitigate impacts of, climate-related events from targeted institutions increased 2.2.1. Percentage of population covered by adequate risk-reduction systems 2.2.2. No. of people affected by climate variability 3.1 No. and type of risk reduction actions or strategies introduced at local level 3.2 No. of news outlets in the local press and media that have covered the topic 4.1. No. and type of health or social infrastructure developed or modified to respond to new conditions resulting from climate variability and change (by type) 4. 2. No. of physical assets strengthened or constructed to withstand conditions resulting from climate variability and change (by asset types) 5. No. and type of natural resource assets created, maintained or improved to withstand conditions resulting from climate variability and change (by type of assets) 6.1. No. and type of adaptation assets (physical as well as knowledge) created in support of individualor community-livelihood strategies 6.2. Type of income sources for households generated under climate change scenario 7.1. No., type, and sector of policies introduced or adjusted to address climate change risks 7.2. No. or targeted development strategies with incorporated climate change priorities enforced

## Units for Indicators
Fund Outcome Indicator Units
1. Generation of relevant data, Stakeholders, and Timeliness 2.1. Include both qualitative and quantitative measures of capacity level within targeted institutions 2.2. Number (men and women and other vulnerable groups) 3.1. Use scale from 1 to 5: 5: Fully aware 4: Mostly aware 3: Partially aware 2: Partially not aware 1: Aware of neither predicted adverse impacts of climate change nor of appropriate responses 3.2. Use scale from 1 to 5: 5: All 4: Almost all 3: Half 2: Some 1: None 4.1. Summarize in an overall scale (1-5): 5: Highly responsive (All defined elements ) 4: Mostly responsive (Most defined elements) 3: Moderately responsive (Some defined elements) 2: Partially responsive (Lacks most elements) 1: Non responsive (Lacks all elements ) 4.2. Summarize in an overall scale (1-5): 5: Fully improved 4: Mostly Improved 3: Moderately improved 2: Somewhat improved 1: Not improved 5. Depends on the targeted natural asset: Biological (species): measure through changes in population numbers (dynamics, structure, etc.) Land: measure changes in hectares. Baseline data will be necessary to estimate the change. Supporting indicators baseline and target (as well as contextual information) are needed such as the following: Farmers adopting recommended technologies, Ha. of land improved, Average deforestation rate Etc. Use scale from 1 to 5. 5: Very effective (All elements are present) 4: Effective (Most elements are present) 3: Moderately effective (Some elements are present) 2: Partially effective (Most elements are not present) 1: Ineffective (No elements are present) 6.1. Summarize in an overall scale (1-5): 5: Very high improvement 4: High improvement 3: Moderate improvement 2: Limited improvement 1: No improvement 6.2. Household income by source of livelihood in project area (USD) prior and post project intervention 7. Summarize in an overall scale (1-5). 5: All (Fully integrated) 4: Most 3: Some 2: Most not integrated 1: None
Fund Output Indicator Units
1.1. Number, sector(s) and level(s) of projects or interventions in separate fields of monitoring plan 1.2. Number 2.1.1. Number of staff (male/female) of targeted institutions: a. Obtain baseline information: total number of staff from targeted institutions b. Define target 2.1.2. Number of staff (male/female) of targeted institutions: a. Obtain baseline information: total number of staff from targeted institutions b. Define target: needs to be defined by project proponents 2.2.1. Quantitative: Percentage (includes women – and other vulnerable groups – and men). Qualitative: Adequacy: include direct analysis of major areas; adequacy/effectiveness of systems or analysis of perceptions of populations and institutions. 2.2.2. Number (broken down by gender and, if possible, by vulnerable groups defined in the area of intervention) of people 3.1. Number and type (in separate columns) at local level. 3.2. Number 4.1. Number and type 4. 2. Number and type (entered in separate columns) 5. Number of interventions by type of natural asset and intervention 6.1. Number and type (in separate columns of monitoring plan) 6.2. Income sources per household; description of income source and number of households. 7.1. Number/Sector 7.2. Number; Effectiveness (see previous indicator) through enforcement level.