## Overview
Project Performance Report (PPR)
| Period of Report (Dates) | 21 May 2016 to 31 May 2017
| Project Title: | Enhancing Climate Change Resilience of Rural Community Living in Protected Area in Cambodia
| Project Summary: | The climate change-induced hazard of erratic rainfall, which leads to droughts and floods, is decreasing agricultural productivity in Cambodia thereby constraining efforts to reduce poverty levels. These erratic rainfall events are predicted to increase under future climate change scenarios. Some of the most vulnerable groups in Cambodia are rural communities living in Protected Areas (PAs). This is because of the dependence of these communities on ecosystem services and a lack of alternative, climate-resilient livelihoods. As a result of erratic rainfall and consequent decreasing agricultural productivity, these communities are increasingly reliant on forest ecosystems to provide supplementary food sources and income from collecting and selling non-timber forest products (NTFPs) and fuelwood. Widespread degradation of forest ecosystems, however, is reducing the efficacy of this adaptation response. The consequences of the climate change-induced hazard of erratic rainfall include: i) increased erosion as a result of floods which damages crop production; ii) crop failure or reduction of yield as a result of drought; and iii) damaged infrastructure as a result of extreme rainfall events which limits access to urban markets. An Adaptation Fund (AF) project has been developed by UNEP and the Ministry of Environment (MoE) in Cambodia to address the vulnerability of rural communities to climate change using ecoagriculture. The project “Enhancing Climate Change Resilience of Rural Communities living in Protected Areas in Cambodia” aims to enhance the climate change resilience of communities living around five community protected area (CPA) intervention sites, as well as downstream communities, to the climate change-induced hazard of erratic rainfall. The project has three main components: 1. Protocols for ecoagriculture interventions Component 1 will use bio-physical, ecological and socio-economic research to develop restoration and conservation agriculture protocols to be implemented in Component 2. 2. Concrete ecoagriculture adaptation interventions Component 2 will ensure that the restored forests and productive agricultural areas are maintained and the benefits maximised. Alternative livelihoods established through the AF project will increase the resilience of local communities to the effects of climate change. 3. Institutional capacity, awareness raising and upscaling of ecoagriculture interventions Component 3 will create an enabling environment for the ecoagriculture concept to be implemented in other PAs in Cambodia, through awareness raised at a local and national level, and an upscaling strategy supported by policy revision where required. The AF project activities will be based on the best available knowledge, technology and proven approaches regarding restoring natural capital and intensifying agriculture in PAs. These activities, within five years, will enhance food supply and conserve topsoil at the CPA intervention sites. The AF project will also implement measures to build the capacity of local communities to restore and intensify agriculture. This improved capacity will increase the climate change resilience of local communities. It will also enable replication and upscaling of the AF project approach to other CPAs, thereby sustaining benefits beyond the lifetime of the AF project.
|  |  | Countries | Project Type: |  | GEF Focal Area: | GEF 4 Focal Areas | GEF 2 / 3 Operational Programme: | Overall Rating of the project in the evaluation by the project evaluator: | GEF-4 Focal Area Strategic Program: | GEF-3 Focal Area Strategic Program:
| Database Number: | AFB-5060-1111-2H81 | Afghanistan | FP | Yes | Biodiversity | 1 | 1 | U | BD-SP1-PA Financing | 1: Arid & semi-arid ecosystems
Implementing Entity (IE) [name]: |  | UNEP | Albania | MSP | No | Climate Change Adaptation | 2 | 2 | S | BD-SP2-Marine PA | 2: Coastal, marine & freshwater ecosystems
| Type of IE: | MIE | Algeria | EA |  | Climate Change Mitigation | 3 | 3 | MU | BD-SP3-PA Networks | 3: Forest ecosystems
| Country(ies): | Kingdom of Cambodia | Angola |  |  | International Waters | 5 | 5 | Good | BD-SP5-Markets | 13: Conservation and Sustainable Use of Biological Diversity Important to Agriculture
Relevant Geographic Points (i.e. cities, villages, bodies of water): |  | Project offices: #48 Preah Sihanouk Blvd., 2nd Floor, Phnom Penh, Cambodia Protected Areas: Boeungper Wildlife Sanctuary (Chiork Boeungprey Community Protected Area (CPA), Chorm Thlok CPA and Skor Krouch CPA), Phnom Kulen National Park (Chop Tasok CPA) and Phnom Prech Wildlife Sanctuary (Ronouk Khgneng). | Argentina |  |  | Multiple Focal Area |  |  |  | BD-SP7-Invasive Alien Species(IAS) | 6: Promoting the adoption of renewable energy by removing barriers and reducing implementation costs
[8 empty] | CC-SP2- Industrial EE | 8: Waterbody based operational program
| Project Milestones | [6 empty] | CC-SP3-RE,CC-SP4-Biomass | 9: Integrated Land and Water multiple focal area
| Milestone |  | Bahamas | [6 empty] | CC-SP5-Transport | 10: Contaminants based operational program
AFB Approval Date: |  | 2012-06-28
IE-AFB Agreement Signature Date: |  | 2013-03-08 | [6 empty] | CC-SP6-LULUCF | 12: Integrated Ecosystem Management
Start of Project/Programme: |  | 2013-05-21 | [6 empty] | Cross cutting capacity building | 14: Persistent Organic Pollutants
Mid-term Review Date (if planned): |  | 2016-12-01
| Terminal Evaluation Date: | 2018-05-01
|  | List documents/ reports/ brochures / articles that have been prepared about the project. | Cyprus
|  | Project reports: Inception Workshop Report 2013; Follow-up Inception Workshop Report 2013; Baseline Study; Project Progress at Mid-term summary (not the formal mid-term review). Technical reports: • gap analysis (including the results of an institutional mapping exercise); • multi-use plant species assessment (including identification of climate-resilient indigenous plant species), with results disaggregated by CPA; • crop variety assessment (including identification of climate-resilient crop varieties), with results disaggregated by CPA; • planting schedule (based on useful plant species assessment); • improved rice variety assessment report; • hydrological assessment report (including water challenges, potential water sources and proposed interventions), with results disaggregated by CPA; • economic assessment of interventions; • technical protocols for ecoagculture interventions; • REDD+ feasibility assessment; • 5 CPA management plans; • Training needs assessment; and • Livelihoods needs asssessment. Articles: http://www.unep.org/stories/story/rural-communities-cambodia-find-ways-overcome-impacts-climate-change | Czech Republic
List the Website address (URL) of project. |  |  | Democratic People's Republic of Korea
|  | http://afcambodia.org/ | Democratic Republic of the Congo
Denmark
| Project contacts: |  | Djibouti
National Project Manager/Coordinator |  |  | Dominica
| Name: | Mr. Ouk Navann | Dominican Republic
| Email: | AFCPA@online.com.kh | Ecuador
| Date: | 2017-05-31 | Egypt
| Government DA |  | El Salvador
| Name: | Dr. Tin Ponlok | Equatoral Guinea
| Email: | Etap@online.com.kh | Eritrea
| Date: | 2017-05-31 | Estonia
| Implementing Entity |  | Ethiopia
| Name: | Atifa Kassam | Fiji
| Email: | atifa.kassam@unep.org | Finland
| Date: | 2017-05-31 | France
| Executing Agency |  | Gambia
| Name: | Dr. Yin Kimsean | Georgia
| Email: | cceap@online.com.kh | Germany
| Date: | 2017-05-31 | Ghana
| Executing Agency |  | Greece
| Name: |  | Grenada
| Email: |  | Guatemala
| Date: |  | Guinea
| Executing Agency |  | Guinea Bissau
| Name: |  | Guyana
| Email: |  | Haiti
| Date: |  | Honduras
Hungary
Iceland
India
Indonesia
Iran (Islamic Republic of)
Iraq
Ireland
Israel
Italy
Jamaica
Japan
Jordan
Kazakhstan
Kenya
Kiribati
Kuwait
Kyrgyzstan
Lao People’s Democratic Republic
Latvia
Lebanon
Lesotho
Liberia
Libyan Arab Jamahiriya
Liechtenstein
Lithuania
Luxembourg
Madagascar
Malawi
Malaysia
Maldives
Mali
Malta
Marshall Islands
Mauritania
Mauritius
Mexico
Micronesia, Federated States of
Monaco
Mongolia
Montenegro
Morocco
Mozambique
Myanmar
Namibia
Nauru
Nepal
Netherlands
New Zealand
Nicaragua
Niger
Nigeria
Norway
Oman
Pakistan
Palau
Panama
Papua New Guinea
Paraguay
Peru
Philippines
Poland
Portugal
Qatar
Republic of Korea
Republic of Moldova
Romania
Russian Federation
Rwanda
Saint Kitts and Nevis
Saint Lucia
Saint Vincent and the Grenadines
Samoa
San Marino
Sao Tome and Principe
Saudi Arabia
Senegal
Serbia
Seychelles
Sierra Leone
Singapore
Slovakia
Slovenia
Solomon Islands
Somalia
South Africa
Spain
Sri Lanka
Sudan
Suriname
Swaziland
Sweden
Switzerland
Syrian Arab Republic
Tajikistan
Thailand
The former Yugoslav Republic of Macedonia
Timor-Leste
Togo
Tonga
Trinidad and Tobago
Tunisia
Turkey
Turkmenistan
Tuvalu
Uganda
Ukraine
United Arab Emirates
United Kingdom of Great Britain and Northern Ireland
United Republic of Tanzania
United States of America
Uruguay
Uzbekistan
Vanuatu
Venezuela, Bolivarian Republic of
Viet Nam
Yemen
Zambia
Zimbabwe

## Financial Data
Financial information: cumulative from project start to 31 May 2017
DISBURSEMENT OF AF GRANT FUNDS
How much of the total AF grant as noted in Project Document plus any project preparation grant has been spent to date?
Cumulative total disbursement as of 31 May 2017 | 2289106 |  |  | 2289106.43 | -0.43
Add any comments on AF Grant Funds. (word limit=200) | The amount reported above is the cumulative expenditure from 23 May 2013 up until 31 May 2017. The expenditure reported below is for the reporting period 01 June 2016 to 31 May 2017. While cummulative disbursements are low in comparison to what was expected at this point, the project has made significant savings during the implementation of the demonstration and planting activities under Component 2 and has managed to reach its targets with less budget than anticipated. A project extension was approved by the Project Board/ Project Steering Committee and is being requested in order to allow for more time for the additional funds to be spent.
EXPENDITURE DATA
List output and corresponding amount spent for the current reporting period | ITEM / ACTIVITY / ACTION | AMOUNT
| 1.1 Information generated on climate change impacts and preferred ecoagriculture interventions through a consultative and participatory approach | 42409
| 1.2 Economic assessments undertaken to identify most appropriate ecoagriculture interventions and associated micro-finance and insurance products | 800
| 1.3 Forest restoration and conservation agriculture protocols developed for CPA intervention sites based on results from Output 1.1 and 1.2 | 35997
| 2.1 Capacity of local community for building climate resilience increased, including capacity to plan, implement and maintain ecoagriculture interventions under Output 2.2 | 16870
| 2.2 Forest restoration and conservation agriculture protocols implemented to build climate resilience (developed in Component 1) in CPA intervention sites | 399767.15
| 2.3 Local communities’ livelihoods enhanced and diversified through sustainable development of NTFPs and the promotion of sustainable alternative livelihood strategies | 79327.45
| 2.4 Socio-economic and ecosystem monitoring of AF project impacts downstream of CPA intervention sites | 17854.06
| 3.1 Awareness increased at a local level of the importance of ecoagriculture for protecting and enhancing commercial and subsistence activities | 41398.25
| 3.2 Ecoagriculture activities promoted through institutional capacity building and proposed revisions to policies, strategies and legislation | 2400
| 3.3 National ecoagriculture upscaling strategy developed and institutionalised for CPAs in Cambodia | 0
| 4. Project/Programme Execution cost | 52525.93
Monitoring and Evaluation
| TOTAL | 689348.84
PLANNED EXPENDITURE SCHEDULE
List outputs planned and corresponding projected cost for the upcoming reporting period | ITEM / ACTIVITY / ACTION | PROJECTED COST | Est. Completion Date
| 1.1 Information generated on climate change impacts and preferred ecoagriculture interventions through a consultative and participatory approach | 29732 | 2018-05-16
| 1.2 Economic assessments undertaken to identify most appropriate ecoagriculture interventions and associated micro-finance and insurance products | - | 2018-05-16
| 1.3 Forest restoration and conservation agriculture protocols developed for CPA intervention sites based on results from Output 1.1 and 1.2 | 45288 | 2018-05-16
| 2.1 Capacity of local community for building climate resilience increased, including capacity to plan, implement and maintain ecoagriculture interventions under Output 2.2 | 36828 | 2018-05-16
| 2.2 Forest restoration and conservation agriculture protocols implemented to build climate resilience (developed in Component 1) in CPA intervention sites | 581503 | 2018-05-16
| 2.3 Local communities’ livelihoods enhanced and diversified through sustainable development of NTFPs and the promotion of sustainable alternative livelihood strategies | 38736 | 2018-05-16
| 2.4 Socio-economic and ecosystem monitoring of AF project impacts downstream of CPA intervention sites | 44972 | 2018-05-16
| 3.1 Awareness increased at a local level of the importance of ecoagriculture for protecting and enhancing commercial and subsistence activities | 36057 | 2018-05-16
| 3.2 Ecoagriculture activities promoted through institutional capacity building and proposed revisions to policies, strategies and legislation | 22400 | 2018-05-16
| 3.3 National ecoagriculture upscaling strategy developed and institutionalised for CPAs in Cambodia | 21000 | 2018-05-16
| 4. Project/Programme Execution cost | 49476 | 2018-05-16
| Monitoring and Evaluation | 37510 | 2018-05-16
| TOTAL | 943502
ACTUAL CO-FINANCING (If the MTR or TE have not been undertaken this reporting period, DO NOT report on actual co-financing.)
How much of the total co-financing as committed in the Project Document has actually been realized? | Co-financing is non applicable to the project
Estimated cumulative actual co-financing as verified during Mid-term Review (MTR) or Terminal Evaluation (TE).
Add any comments on actual co-financing in particular any issues related to the realization of in-kind, grant, credits, loans, equity, non-grant instruments and other types of co-financing. (word limit=200)

## Rating
RATING ON IMPLEMENTATION PROGRESS
For rating definitions please see bottom of page.
| Progress on Key Milestones |  | Expected Progress |  | Progress to Date | Rating
Project Manager/Coordinator: | Component 1: Protocols for ecoagriculture interventions.
| Information on preferred ecoagriculture interventions gathered through a particpatory approach. |  | Consulants gather information from participating communities. Reports on preferred ecoagriculture interventions. Establish MSc research in local institutions. |  | Consultants have visited project intervention sites and collected the relevant information. The five relevant reports (Insitutional gap analysis; botanical report; agriculture report, climate forecasting report; and hydrological report) have been submitted and finalised. 06 Msc students from Royal University of Agriculture and 5 Msc students from Royal University of Phnom Penh have received bursaries through the project and began their research dissertations since the beginning of 2015. These students have visited the project intervention sites under the supervision of the Research and Monitoring consultants and gathered the information required for their dissertations. An additional 04 Msc students have recieved bursaries for their academic year 2017-2018. | HS
| Economic assesments undertaken to identify appropriate ecoagriculture interventions |  | Consulants gather information from participating communities. Reports on economic assessments of preferred ecoagriculture interventions. |  | Consultants have visited project intervention sites and collected the relevant information. The three relevant reports (Microfinance/Insurance assessment; Market assessment; socio-economic assessment) have been submitted and finalised. Based on the findings of these assessments, training on family financial management has been undertaken. In addition, a Liveilhoods Expert Group has been hired to develop alternative livelihood strategies for local communities, including pig/chicken farming and beekeeping. | S
Component 2: Concrete ecoagriculture interventions.
| Training on ecoagriculture interventions has started. |  | Training material developed. Train CPA management committees and local community members on climate change and ecoagriculture interventions. |  | Training material has been developed by the National Training Expert and relevant consultants contracted to undertake specific training. 53 training events have been conducted. This includes: i) 1 training needs assessment; ii) 7 Training of Trainer events (involving CPA management commitees and local extension officers) on seven separate topics; ii) 45 (9 topics at each of the 5 CPAs) community training workshops. | HS
| Forest restoration and conservation agriculture protocols implemented |  | Nurseries established. Forest restoration has started. Homegardens established. Climate-resilient rice trials undertaken. |  | All three nurseries have been constructed, inaugurated and started its seedling germination processes. Forest restoration is being conducted at all five CPAs. 547,690 indigenous trees have been planted during these restoration efforts. In addition, 338,542 fruit trees have been planted around villages. 1193 homegardens have been established and supported for equippments and seedlings. 872 households in total have recieved and planted drought-resilient rice varieties. | HS
| Local communities' s livelihoods are enhanced. |  | A livelihood development plan for each CPA is developed. Additional livelihood activities are introduced to target communities. |  | A draft livelihood development plan for each CPA has been prepared. 155 CPA families have been provided chicken for raising and 60 families have provided cricket nesting for cricket raising. For Water supply, project teams have dug 3 ponds for Chiork Boeungprey nusery together with its automatic solar water pumping system and storage tankers. 150 open tube wells fitted with hand pumps, and 132 small pumping wells and 10 large pumping wells were provided to households in CPA project targeted sites and downstream project sites. In Ronouk Khgeng, 74 rain water harvesting storage tank have been distributed to all households. In Chop Tasok a complete water supply system, which links a natural spring to all households and the project nursery has been constructed including 7 storage tankers. In addition, 2 water storage tankers have been constracuted for Skor Krouch CPA. In addition, 2 spill dumps have been finally constructed by May 2016 at Chorm Thlork and Chup Tasok. | HS
| Socio-economic and ecosystem monitoring of project impacts. |  | A research and monitoring framework is developed. Monitoring tools are developed. Monitoring of project interventions is carried out. |  | A reasearch and monitoring framework as well as monitoring tools have been developed. The research and monitoring team visited the target CPAs. During this visit they collected data to assess progress against the projects results framework. In addition, data was collected to monitor the impact of the reforestation and homegardening interventions. A research and monitoring report has been submitted. Monitoring will continue throughout the lifespan of the project. | MS
Component 3: Institutional capacity, awareness and upscaling of ecoagriculture interventions.
| Awareness raising campaign is implemented.. |  | An awareness raising campaign is implemented The project web-site is designed and functioning. |  | The awareness raising campaign is being implemented. To date this has included trainings on climate change awareness, development of posters that have been disseminated to CPAs and preparation of brochures on nursery management. In addition, two 'roadside reststops' have been built by the project and branded with awareness-raising products. Futher more, two more road rest areas have started its constrcution and expected to finished by mid 2018. The project website is designed and functioning. Some forest planting events with T-shirts distibuting informing about project feasibility and activities. Tree camping events have been organised with participants from universit students, school children, Phnom Penh yourt club and women staff from Ministry of Enviroment. | HS
| CPA Management plans updated/developed. |  | Prepare CPA management plans. |  | CPA management plans have been developed and finalzed for 4 CPAs including Chiork Boeungprey, Chorm Thlork, Skor Krouch and Chup Tasok. On the other hand, Ronouk khgneng management plan has been revised and finalized. | S
Project operation and management
| Project management unit. |  | Manage project activities according to workplan. Recruit necessary consultants. Undertake annual audit. |  | Project activities have been well coordinated and are largely progressing according to the workplan prepared. The necessary recruitment processes have been followed to recruit consultants. The annual audit was undertaken. | S
| Procurement |  | Prepare procurement plan. Procure consultancies for fourth year. Procure goods and services for ecoagriculture interventions. |  | A procurement plan was prepared. The necessary recruitment processes have been followed to recruit consultants. The necessary procurement processes have been followed to procure goods (for example seedlings for reforestation) and services (for example water supply construction firms) necessary for the ecoagriculture interventions. | S
[5 empty] | Overall Rating | S
Please Provide the Name and Contact information of person(s) reponsible for completeling the Rating section
| Name: | Ouk Navann, National Project Coordinator
| Email: | navanouk@gmail.com
Please justify your rating. Outline the positive and negative progress made by the project since it started. Provide specific recommendations for next steps. . (word limit=500)
The project has made good progress during its implementing period of the 4 years. The project main activities on the ground focuses on the construction of water supply infrastructure, reforestation, homegarden establishment, distribution of climate-resilient rice seeds, promotion of chicken, pig and cricket farming, construction of eco-tourism facilities and construction of roadside rest areas. All project experts have complete their reports and produced the necessary outputs such as awareness raising, livelihood development plans, CPA management plans and reseach and monitoring reports. Msc students supported by project re working very well and the second round of scholarships provision are on track. In general, I am pleased to rate the project performance as Satisfactory.
| Progress on Key Milestones |  | Expected Progress |  | Progress to Date | Rating
Implementing Agency | Component 1: Protocols for ecoagriculture interventions.
| Information on preferred ecoagriculture interventions gathered through a particpatory approach. |  | Consulants gather information from participating communities. Reports on preferred ecoagriculture interventions. Establish MSc research in local institutions. |  | Consultants have visited project intervention sites and collected the relevant information. The five relevant reports (Insitutional gap analysis; botanical report; agriculture report, climate forecasting report; and hydrological report) have been submitted and finalised. 06 Msc students from Royal University of Agriculture and 5 Msc students from Royal University of Phnom Penh have received bursaries through the project and began their research dissertations since the beginning of 2015. These students have visited the project intervention sites under the supervision of the Research and Monitoring consultants and gathered the information required for their dissertations. An additional 04 Msc students have recieved bursaries for their academic year 2017-2018. | HS
| Economic assesments undertaken to identify appropriate ecoagriculture interventions |  | Consulants gather information from participating communities. Reports on economic assessments of preferred ecoagriculture interventions. |  | Consultants have visited project intervention sites and collected the relevant information. The three relevant reports (Microfinance/Insurance assessment; Market assessment; socio-economic assessment) have been submitted and finalised. Based on the findings of these assessments, training on family financial management has been undertaken. In addition, a Liveilhoods Expert Group has been hired to develop alternative livelihood strategies for local communities, including pig/chicken farming and beekeeping. | S
Component 2: Concrete ecoagriculture interventions.
| Training on ecoagriculture interventions has started. |  | Training material developed. Train CPA management committees and local community members on climate change and ecoagriculture interventions. |  | Training material has been developed by the National Training Expert and relevant consultants contracted to undertake specific training. 53 training events have been conducted. This includes: i) 1 training needs assessment; ii) 7 Training of Trainer events (involving CPA management commitees and local extension officers) on seven separate topics; ii) 45 (9 topics at each of the 5 CPAs) community training workshops. | HS
| Forest restoration and conservation agriculture protocols implemented |  | Nurseries established. Forest restoration has started. Homegardens established. Climate-resilient rice trials undertaken. |  | All three nurseries have been constructed, inaugurated and started its seedling germination processes. Forest restoration is being conducted at all five CPAs. 547,690 indigenous trees have been planted during these restoration efforts. In addition, 338,542 fruit trees have been planted around villages. 1193 homegardens have been established and supported for equippments and seedlings. 872 households in total have recieved and planted drought-resilient rice varieties. | S
| Local communities' s livelihoods are enhanced. |  | A livelihood development plan for each CPA is developed. Additional livelihood activities are introduced to target communities. |  | A draft livelihood development plan for each CPA has been prepared. 155 CPA families have been provided chicken for raising and 60 families have provided cricket nesting for cricket raising. For Water supply, project teams have dug 3 ponds for Chiork Boeungprey nusery together with its automatic solar water pumping system and storage tankers. 150 open tube wells fitted with hand pumps, and 132 small pumping wells and 10 large pumping wells were provided to households in CPA project targeted sites and downstream project sites. In Ronouk Khgeng, 74 rain water harvesting storage tank have been distributed to all households. In Chop Tasok a complete water supply system, which links a natural spring to all households and the project nursery has been constructed including 7 storage tankers. In addition, 2 water storage tankers have been constracuted for Skor Krouch CPA. In addition, 2 spill dumps have been finally constructed by May 2016 at Chorm Thlork and Chup Tasok. | S
| Socio-economic and ecosystem monitoring of project impacts. |  | A research and monitoring framework is developed. Monitoring tools are developed. Monitoring of project interventions is carried out. |  | A reasearch and monitoring framework as well as monitoring tools have been developed. The research and monitoring team visited the target CPAs. During this visit they collected data to assess progress against the projects results framework. In addition, data was collected to monitor the impact of the reforestation and homegardening interventions. A research and monitoring report has been submitted. Monitoring will continue throughout the lifespan of the project. | S
Component 3: Institutional capacity, awareness and upscaling of ecoagriculture interventions.
| Awareness raising campaign is implemented.. |  | An awareness raising campaign is implemented The project web-site is designed and functioning. |  | The awareness raising campaign is being implemented. To date this has included trainings on climate change awareness, development of posters that have been disseminated to CPAs and preparation of brochures on nursery management. In addition, two 'roadside reststops' have been built by the project and branded with awareness-raising products. Futher more, two more road rest areas have started its constrcution and expected to finished by mid 2018. The project website is designed and functioning. Some forest planting events with T-shirts distibuting informing about project feasibility and activities. Tree camping events have been organised with participants from universit students, school children, Phnom Penh yourt club and women staff from Ministry of Enviroment. | MS
| CPA Management plans updated/developed. |  | Prepare CPA management plans. |  | CPA management plans have been developed and finalzed for 4 CPAs including Chiork Boeungprey, Chorm Thlork, Skor Krouch and Chup Tasok. On the other hand, Ronouk khgneng management plan has been revised and finalized. | S
Project operation and management
| Project management unit. |  | Manage project activities according to workplan. Recruit necessary consultants. Undertake annual audit. |  | Project activities have been well coordinated and are largely progressing according to the workplan prepared. The necessary recruitment processes have been followed to recruit consultants. The annual audit was undertaken. | HS
| Procurement |  | Prepare procurement plan. Procure consultancies for fourth year. Procure goods and services for ecoagriculture interventions. |  | A procurement plan was prepared. The necessary recruitment processes have been followed to recruit consultants. The necessary procurement processes have been followed to procure goods (for example seedlings for reforestation) and services (for example water supply construction firms) necessary for the ecoagriculture interventions. | S
[5 empty] | Overall Rating | S
Please Provide the Name and Contact information of person(s) reponsible for completeling the Rating section
| Name: | Atifa Kassam
| Email: | atifa.kassam@unep.org
Please justify your rating. Outline the positive and negative progress made by the project since it started. Provide specific recommendations for next steps. . (word limit=500)
The project has been progressing very well. Planting and livelihood demonstration activities have gone very well due to the dedication from the project team in ensuring this is done through time spent with communities in the field. I have given the project an overall rating of Satisfactory to Highly Satisfactory. The project needs to concentrate efforts on compiling and documenting lessons learned in order to influence policy making processes. Lastly, the project team also need to work on a sustainability strategy for the project going forward.
| Progress on Key Milestones |  | Expected Progress |  | Progress to Date | Rating
Chief Technical Advisor | Component 1: Protocols for ecoagriculture interventions.
| 1.1 Information generated on climate change impacts and preferred ecoagriculture interventions through a consultative and participatory approach |  | Information collection and report generation complete. |  | Consultants have visited project intervention sites and collected the relevant information. The five relevant reports (Insitutional gap analysis; botanical report; agriculture report, climate forecasting report; and hydrological report) have been submitted and finalised. 06 Msc students from Royal University of Agriculture and 5 Msc students from Royal University of Phnom Penh have received bursaries through the project and began their research dissertations since the beginning of 2015. These students have visited the project intervention sites under the supervision of the Research and Monitoring consultants and gathered the information required for their dissertations. An additional 04 Msc students have recieved bursaries for their academic year 2017-2018. | HS
| 1.2 Economic assessments undertaken to identify most appropriate ecoagriculture interventions and associated micro-finance and insurance products |  | Economic assessments complete. |  | Consultants have visited project intervention sites and collected the relevant information. All five economic assessments have been submitted to the PMU and incorporated into restoration protocols. These reports include: • 1 x report identifying locally available weather index-based insurance and micro-finance products; • 1 x market assessment of micro-finance opportunities for farmers at CPA intervention sites (including potential business plans for such products); • 1 x local agricultural market assessment; • 1 x cost-benefit analysis of potential crop/tree species to be planted; and • 1 x socio-economic assessment of proposed ecoagriculture approaches. | HS
| 1.3 Forest restoration and conservation agriculture protocols developed for CPA intervention sites based on results from Output 1.1 and 1.2 |  | Forest restoration and conservation agriculture protocols developed. Continuing technical advice and guidance to complete forest restoration and ecoagriculture as per the technical protocols. |  | Draft forest restoration and conservation agriculture protocols have been developed. These reports still need to be finalised. There is ongoing technical suppot from the PMU, CTA, community liason planting officers (Government counterparts) and expert consultants guiding the implementation of project interventions. | MS
Component 2: Concrete ecoagriculture interventions.
| Training on ecoagriculture interventions has started. |  | Training material developed. Train CPA management committees and local community members on climate change and ecoagriculture interventions. |  | Training material has been developed by the National Training Expert and relevant consultants contracted to undertake specific training. 53 training events have been conducted. This includes: i) 1 training needs assessment; ii) 7 Training of Trainer events (involving CPA management commitees and local extension officers) on seven separate topics; ii) 45 (9 topics at each of the 5 CPAs) community training workshops. | S
| Forest restoration and conservation agriculture protocols implemented |  | Nurseries established. Forest restoration has started. Homegardens established. Climate-resilient rice trials undertaken. |  | All three nurseries have been constructed, inaugurated and started its seedling germination processes. Forest restoration is being conducted at all five CPAs. 547,690 indigenous trees have been planted during these restoration efforts. In addition, 338,542 fruit trees have been planted around villages and in chamkar. 1193 homegardens have been established and supported for equippments and seedlings. 872 households in total have recieved and planted drought-resilient rice varieties. | HS
| Local communities' s livelihoods are enhanced. |  | A livelihood development plan for each CPA is developed. Additional livelihood activities are introduced to target communities. Water supply infrastructure is built to provide drinking water and water for alternative livelihood activities. |  | Al ivelihood development plan for each CPA has been prepared. 155 CPA families have been provided with training and materials for chicken-raising and 60 families have provided with training and materials for cricket-raising. Community members have also recieved training on: i) ecotourism; ii) leaf-roof contruction; and iii) vegetable selling. For Water supply, project teams have dug 3 ponds for Chiork Boeungprey nusery together with its automatic solar water pumping system and storage tankers. 150 open tube wells fitted with hand pumps, and 132 small pumping wells and 10 large pumping wells were provided to households in CPA project targeted sites and downstream project sites. In Ronouk Khgeng, 74 rain water harvesting storage tank have been distributed to all households. In Chop Tasok a complete water supply system, which links a natural spring to all households and the project nursery has been constructed including 7 storage tankers. In addition, 2 water storage tankers have been constracuted for Skor Krouch CPA. In addition, 2 spill dumps have been finally constructed by May 2016 at Chorm Thlork and Chup Tasok. | S
| Socio-economic and ecosystem monitoring of project impacts. |  | A research and monitoring framework and monitoring tools are developed. Monitoring of project interventions is carried out. |  | A reasearch and monitoring framework as well as monitoring tools have been developed. The research and monitoring team have conducted monitoring at the target CPAs as well as neighbouring CPas. During these visits, they collected data to assess progress against the projects results framework. In addition, data was collected to monitor the impact of the reforestation and homegardening interventions. 3 research and monitoring report has been submitted. Monitoring will continue throughout the lifespan of the project. | HS
Component 3: Institutional capacity, awareness and upscaling of ecoagriculture interventions.
| Awareness raising campaign is implemented.. |  | An awareness raising campaign is implemented The project web-site is designed and functioning. Road rest areas (with awareness-raising materials) are constructed. |  | The awareness raising campaign is being implemented. To date this has included trainings on climate change awareness, development of posters that have been disseminated to CPAs and preparation of brochures on nursery management. In addition, two 'roadside reststops' have been built by the project and branded with awareness-raising products. Futher more, two more road rest areas have started its constrcution and expected to finished by mid 2018. The project website is designed and functioning. Some forest planting events with T-shirts distibuting informing about project feasibility and activities. These planting activities have involved thousands of community members, raising their awareness of forest conservation and climate change. Three camping events have been organised with participants from universit students, school children, Phnom Penh yourt club and women staff from Ministry of Enviroment. | HS
| CPA Management plans updated/developed. |  | Prepare CPA management plans. |  | CPA management plans have been developed and finalzed for 4 CPAs including Chiork Boeungprey, Chorm Thlork, Skor Krouch and Chup Tasok. On the other hand, Ronouk khgneng management plan has been revised and finalized. | S
| 3.3 National ecoagriculture upscaling strategy developed and institutionalised for CPAs in Cambodia |  | Consultant to develop upscaling strategy contracted. |  | During the 5th PSC meeting it was decided to develop a Project Idea Note for the upsclaing of project activites. ToRs for a consultant to develop a upsclaing strategy have been developed. | MS
Project operation and management
| Project management unit. |  | Manage project activities according to workplan. Recruit necessary consultants. Undertake annual audit. |  | Project activities have been well coordinated and are largely progressing according to the workplan prepared. The necessary recruitment processes have been followed to recruit consultants. The annual audit was undertaken. | S
| Procurement |  | Prepare procurement plan. Procure consultancies for fourth year. Procure goods and services for ecoagriculture interventions. |  | A procurement plan was prepared. The necessary recruitment processes have been followed to recruit consultants. The necessary procurement processes have been followed to procure goods (for example seedlings for reforestation) and services (for example water supply construction firms) necessary for the ecoagriculture interventions. | S
[5 empty] | Overall Rating | S
Please Provide the Name and Contact information of person(s) reponsible for completeling the Rating section
| Name: | C4 EcoSolutions
| Email: | nicholas.tye@c4es.co.za
| Please justify your rating and address the following points: 1. Indicate trends, both positive and negative, in achievement of outcomes as per the project indicators. 2. Detail critical risks that have affected progress. 3. Outline response to MTR undertaken this reporting period. 4. Outline action plan to address projects with a rating of HU, U or MU. Please keep your input to 1200 words |  | The project has continued to make good progress towards the achievement of expected outcomes during the fourth year of implementation. In particular, the project has made excellent good progress on on-the-ground activities, such as the construction of water supply infrastructure, reforestation, homegarden establishment, distribution of climate-resilient rice seeds, promotion of chicken and pig farming, construction of eco-tourism facilities and construction of roadside rest areas. The PMU have developed efficient structures for completing the necessary arrangements for implementation - having learned lessons during the first three years of implementation - and on the-ground implementation is proceeding well. The PMU and government counterparts have also managed to find cost-effective ways of implementing activities (including extensive involvement by the local communities), which means that the project is achieving its targets and outcomes within the allocated budgets. This has (and will continue to) allowed for the upscaling of project intervention to neighbouring CPAs. The involvement of different government sectors, NGOs, community leaders and thousands of community members in the reforestation and homdegardening activities of the project is a very noteworthy acheivement. Experts employed by the project have also produced the necessary outputs, including livelihood development plans, CPA management plans and reseach and monitoring reports. No critical risks affecting project progress have been identified. Overall, because of the project towards excellent on-the-ground interventions, I would rate the performance of the project as Satisfactory to Highly Satisfactory.
Rating Definitions
|  |  | Highly Satisfactory (HS) | Project actions/activities planned for current reporting period are progressing on track or exceeding expectations to acheive all major outcomes/outputs for given reporting period, without major shortcomings. The project can be presented as “good practice”.
|  |  | Satisfactory (S) | Project actions/activities planned for current reporting period are progressing on track to achieve most of its major outcomes/outputs with only minor shortcomings.
|  |  | Marginally Satisfactory (MS) | Project actions/activities planned for current reporting period are progressing on track to achieve most major relevant outcomes/outputs, but with either significant shortcomings or modest overall relevance.
|  |  | Marginally Unsatisfactory (MU) | Project actions/activities planned for current reporting period are not progressing on track to achieve major outcomes/outputs with major shortcomings or is expected to achieve only some of its major outcomes/outputs.
|  |  | Unsatisfactory (U) | Project actions/activities planned for current reporting period are not progressing on track to achieve most of its major outcomes/outputs.
|  |  | Highly Unsatisfactory (U) | Project actions/activities planned for current reporting period are not on track and shows that it is failing to achieve, and is not expected to achieve, any of its outcomes/outputs.

## Project Indicators
PROJECT Indicators
Please provide all indicators being tracked for the project as outlined in the project document
Type of Indicator (indicators towards Objectives, Outcomes, etc…)
Type of Indicator | Indicators | Baseline |  | Progress since inception | Target for project end
Objective: Enhance the climate change resilience of communities living around at least three CPA intervention sites, as well as downstream communities, to the climate change-induced hazard of erratic rainfall. | Obj 1 Percentage change in the climate change vulnerability index at each target CPA. | The following table shows the current climate change vulnerability index score at each CPA. The maximun vulnerability index score is 120, but normally ranges between 0 and 50. |  | The clmate change vulnerablity index for each target CPA was measured in mid-2016 (approximate mid-point of the project) by the Research and Monitoring consultants. Overall, the climate change vulnerability index has increased in each target community, contrary to the anticipated result (see Figure to the right). However, as noted by the consultants, the increase in vulnerability was driven by an increase in exposure risk, outside the control of the project. On the other hand, the adaptive capacity of communities - which the project could influene - has greatly increased (see Figure to the right). The consultants summarise: "The analysis showed that the vulnerability of the target respondents has increased compared to the baseline. As discussed earlier, the exposure of the community to climate change have significantly increased compared to the time when the baseline was conducted. Even if the adaptive capacity has improved, this is not enough to overcome the risk that the community experienced. The data would show that the extent by which the respondents are exposed to climate change (i.e. based on the scores they attribute to the indicators of exposure to climate change) is significantly high compared to the baseline. The overall score on CC exposure was not overturned even with the increase in Adaptive Capacity of the community members. It should be noted further that the average sensitivity index has also slightly increased which further aggravated the Vulnerability. But then, the scenario could have been worse without the project. The result highlights the importance of the project in mitigating the impact of climate change to the vulnerable communities." | A 20% decrease in the climate change vulnerability index at each target CPA by the end of the project.
Vulnerability index
|  | Chiork Boeungprey | 10.4
|  | Chorm Thlok | 15.2
|  | Skor Krouch | 25.8
|  | Chop Tasok | 12.1
|  | Ronouk Khgneng | 27.6
| Obj 2 Number of project beneficiaries, gender dissagragated, benfitting from the project's ecoagriculture interventions. | No beneficiaries before the start of the project |  | 3 nurseries have been constructed and community nursery management teams have been established. 126 community members (52 at Beung Per, 35 at Phnom Kulen and 39 at Phnom Prich) are actively involved in the community nursery management teams. 1891 households in total (~5 people per household) have recieved fruit trees for planting around their homestead (54 households in Chop Tasok, 57 in Ronouk Khgeng, 198 in Chiork Beungprey, in 600 Chom Thlork and in 982 Skor Krouch). 872 households (64 in 2014, 329 in 2015 and 479 in 2016) in total have recieved and planted drought-resilient rice varieties. (4 Chirok Beungprey, 507 Chom Thlork, 351 in Skor Krouch, and 10 in Chup Tasok). 1193 households (244 in 2014 and 279 in 2015 and 670 in 2016) in total are benefitting from homegarden activities. (43 households in Chop Tasok, 60 in Ronouk Khgeng, 100 in Chiork Beungprey, 573 in Chom Thlork and 417 in Skor Krouch). 155 households (10 in 2014, 140 in 2015) in total are benefitting from household chicken farming activities. (14 households in Chop Tasok, 25 in Ronouk Khgeng, 28 in Chiork Beungprey, in 54 Chom Thlork and in 34 Skor Krouch). 60 families in total have recieved cricket raising training skills with supply of cricket nestling. 48 training events and 2 exchange studies have taken place (with ~100 participants per event). For water supply infrastructure, project teams have dug 3 ponds for Chiork Boeungprey nusery together with its automatic solar water pumping system and storage tankers. 150 open ring wells, 132 small pumping wells and 10 large pumping wells have been supplied to most households in project target areas and somewhere downstream communities (Open ring well: 37 in Chiork Beungprey and 63 in Chorm Thlork and 47 in other CPAs; Small pumping well: 52 in Skor Krouch, 13 in Rounouk Khnheng and 67 in other CPAs; Larger pumping well: 10 in others CPAs). In Ronouk Khgeng, 74 rain harvesting and storage tankers have been distributed to 74 households. In Chop Tasok a complete water supply system, which links a natural spring to all households and the project nursery has been constructed together with its 7 storage tankers. Furthermore, two storage tankers have been built for Skor Krouch CPA. In addition, 2 spill dumps have been finally constructed by May 2016 at Chorm Thlork and Chup Tasok. Water supply infrastructure, reforestation activities and the strengthening of community management committees is benefitting all households within the five project intervention sites. | At least 1000 people, 50% of which are women, are benefitting from the project's interventions by the end of the project.
Outcome 1: Technical expertise and a local enabling framework for forest restoration and ecoagriculture interventions that build climate resilience developed at CPA intervention sites through a consultative and participatory process. | Outcome 1. Change in the capacity of national and local government officials to implement forest restoration and conservation agriculture interventions that build climate resilience. | National and local government officials have limited capacity to implement forest restoration and conservation agriculture interventions that build climate resilience. |  | The technical knowledge required to implement forest restoration and conservation agriculture interventions has been aquired through at least 11 technical assessments and reports. The technical knowledge developed through these assessments, including climate-resilient species selections, market assessments and hydrological studies, will build the capacity of the government to implement forest restoration and conservation agriculture interventions.These reports have been shared with government officials. Government officials involved with the implementation of the project (1 project manager, 3 department/general directors, 11 government counterparts, 10 additional support staff from the Local Community Livelihood Department, and 30-40 field rangers from the GDANCP (General Department of Administration for Nature Conservation and Protection - Protected Area Management). ~20 field rangers have attended training events on climate change, ecoagriculture, forest patrolling, nursery management ang land tenure rights. Furthermore, through their experience implemeting the project, these government staff continue to develop the capacity to implement forest restoration and conservation agriculture. | 15 national and local government officials in the Research and Community Protected Area Development Department have fully developed capacity to implement forest restoration and conservation agriculture interventions that build climate resilience.
Output 1.1: Information generated on climate change impacts and preferred ecoagriculture interventions through a consultative and participatory approach. | 1.1.1 Number and type of specialist reports developed for the project – through a participatory approach with local communities where relevant – in the first year. | No specialist reports on climate changes impacts and the preferred ecoagriculture interventions. |  | National consultants were recruited to undertake the necessary assessments. The 6 reports required have been submitted and cleared by the PMU and Chief Technical Advisor. | At least 6 specialist reports submitted to the PMU by the end of the first year of the project. These reports must include: • 1 x gap analysis (including the results of an institutional mapping exercise); • 1 x multi-use plant species assessment (including identification of climate-resilient indigenous plant species), with results disaggregated by CPA; • 1 x crop variety assessment (including identification of climate-resilient crop varieties), with results disaggregated by CPA; • 1 x planting schedule (based on useful plant species assessment); • 1 x improved rice variety assessment report; and • 1 x hydrological assessment report (including water challenges, potential water sources and proposed interventions), with results disaggregated by CPA.
| 1.1.2 Number of MSc research projects on ecoagriculture initiated at a local university. | No MSc research projects on ecoagriculture in Cambodia. |  | 11 MSc students have thus far been supported through the project - 6 from Royal University of Agriculture and 5 from the Royal University of Phnom Penh. 4 additional students will be supported starting in September 2017. | At least 5 MSc projects on ecoagriculture initiated at local universities over the duration of the AF project.
Output 1.2: Economic assessments undertaken to identify most appropriate ecoagriculture interventions and associated micro-finance and insurance products. | 1.2.1 Number and type of economic assessment reports developed for the project – through a participatory approach with local communities where relevant – in the first year. | No economic assessment reports on the preferred ecoagriculture interventions and associated micro-finance/insurance products. |  | Consultants have been recruited to undertake the necessary assesments. The five reports required have been developed, submitted and cleared by the PMU and Chief Technical Advisor. | At least 5 economic assessment reports submitted to the PMU by the end of the first year of the project. These reports must include: • 1 x report identifying locally available weather index-based insurance and micro-finance products; • 1 x market assessment of micro-finance opportunities for farmers at CPA intervention sites (including potential business plans for such products); • 1 x local agricultural market assessment; • 1 x cost-benefit analysis of potential crop/tree species to be planted; and • 1 x socio-economic assessment of proposed ecoagriculture approaches.
Output 1.3: Forest restoration and conservation agriculture protocols developed for CPA intervention sites based on results from Output 1.1 and 1.2. | 1.3.1 Number and type of technical protocols – informed by output 1.1 – for ecoagriculture interventions developed in the second year of project. | There are no formal, technical protocols specific to the ecoagriculture approaches and project sites proposed by the AF project. |  | 5 technical protocols have been completed and submitted to the PMU. | At least 5 technical protocols (1 per CPA) for the preferred ecoagriculture interventions submitted to the PMU in the second year of the project. These reports must include protocols for: • restoration; • chamkar-based agroforestry; • homegarden establishment; • planting useful species around chamkar; • growing climate-resilient rice; and • implementing additional activities.
Outcome 2: Multi-use forests established and maintained and agricultural practices diversified/intensified to supply a diverse range of food and stabilize topsoil, despite an increase in climate change-induced droughts and floods. | Outcome 2 Number of households that have benefited from chamkar-based agroforestry plots and intensified/diversified homegardens at the target CPAs. | No chamkar-based agroforestry plots have been established at the five target CPAs. |  | 1891 households in total (~5 people per household) have recieved fruit trees for planting around their homestead and in their chamkar (54 households in Chop Tasok, 57 in Ronouk Khgeng, 198 in Chiork Beungprey, in 600 Chom Thlork and in 982 Skor Krouch). By August 2017, there are 321,276 of indigenous trees have been planted in the 5 CPA project targeted sites and in other downstream communities forest areas. 1193 (244 in 2014 and 279 in 2015 ansd 670 in 2016) households in total are benefitting from homegarden activities. (43 households in Chop Tasok, 60 in Ronouk Khgeng, 100 in Chiork Beungprey, 573 in Chom Thlork and 417 in Skor Crouch). | 1000 households have benefited from chamkar-based agroforestry plots and 800 households have benefited from intensified/diversified homegardens at the target CPAs by the end of the project.
There is 1 intensified/diversified homegarden at Chop Tasok.
There are no intensified/diversified homegardens at the other four target CPAs. Therefore only 1 household has benefited an intensified/diversified homegarden.
Output 2.1: Capacity of local community for building climate resilience increased, including capacity to plan, implement and maintain ecoagriculture interventions under Output 2.2. | 2.1.1 Number of CPA Management Committees, local authority members and agricultural extensions officers located throughout Cambodia trained on climate change and ecoagriculture interventions. | There has been no formal training encompassing the full ecoagriculture approach preferred by the AF project. |  | The CPA management committes, local authorities and extension officers have taken part in 7 different training events. 70 CPA Management Committees have been trained. 30 local authority members have been trained. 20 agricultural extension workers have been trained. | Mid-term: At least 30 CPA Management Committees; 10 local authorities members; and 5 agricultural extension officers throughout Cambodia trained on climate change and ecoagriculture interventions over the duration of the AF project. End of project: At least 60 (i.e. 50%) CPA Management Committees; 20 local authority members; and 10 agricultural extension officers throughout Cambodia trained on climate change and ecoagriculture interventions over the duration of the AF project.
| 2.1.2 Number of CPA community members, gender disaggregated, at project intervention sites trained on climate change and ecoagriculture interventions. | There has been no formal training encompassing the full ecoagriculture approach preferred by the AF project. |  | 48 training events (9 topics in each of the 5 CPAs) have been undertaken on nursery management and seed propagation, climate change, ecoagriculture, sustainable liveilhoods, livestock farming, land tenure, financial management, our community our hope, patrolling strategy and leadership in providing ecotourist services as well as two exchange studies . On average, 100 people have been involved in each training event. Therefore, approximately 4800 CPA community members have been trained. | Mid-term: A total of at least 1250 CPA community members (30% of which should be women) trained on climate change and ecoagriculture interventions. End of project: A total of at least 2500 CPA community members (30% of which should be women) trained on climate change and ecoagriculture interventions.
| 2.1.3 Number of patrolling committees established/strengthened. | 1 formal patrolling committee at Ronouk Khgneng. |  | A patrolling committee has been established at all 5 CPAs. A reporting mechanism has been established and each team submits a monthly report to government counterparts. These patrrolling teams are supported with $150 per month for food and petrol costs. | 4 patrolling committees established (Chiork Boeungprey, Chorm Thlok, Skor Krouch and Chop Tasok) and 1 patrolling committee strengthened (Ronouk Khgneng).
| 2.1.4 Annual number of transgressions in each CPA between July 2014 and the end of the AF project. | 1 incident in 2012–2013 at Ronouk Khgneng. |  | Patrolling committees have begun to sumbit monthly patrolling reports. The decrease in the number of transgressions will be measured once baseline values are established through these reports. In Beung Per, at least 27.5 ha in Chorm thlok CPA and 3 ha in Chiok Boeungprey CPA of illegally cleared forest has been confiscated and reforested. | At least a 40% reduction in the annual number of transgressions in each CPA between July 2014 and the end of the AF project.
No reliable data on the current incidence of transgression was available for the remaining four CPAs. The baseline number of transgressions per year in each CPA will be measurable once patrolling committees have been established in each CPA.
Output 2.2: Forest restoration and ecoagriculture protocols implemented to build climate resilience (developed in Component 1) in CPA intervention sites. | 2.2.1 Number of community-managed nurseries established at project intervention sites. | No functioning nurseries at any of the five CPAs. |  | The first AF nursery has been established to service the three CPAs within Beungprey Wildlife Sanctuary. The nursery was officially inaugurated by the Minister of the Environment on July 14, 2014. The Second AF nursery in Chup Tasok CPA of Kulen National Park was inaugurated on 06 March 2015 and the third AF nursery in Rounouk Khgneng CPA of Phnom Prech Wildlife Sanctury was inaugurated on 18 May 2015. All three nurseries have their own nursery management teams who have been well trained on nursery management and seedling propagation. | At least 3 nurseries established during the first year of the AF project, including: • 1 in Boeungper, • 1 in Phnom Kulen; and • 1 in Phnom Prech.
| 2.2.2 Number of qualified community-liaison planting officers contracted to assist with implementation of project activities at intervention sites. | 0 community liaison planting officers have been contracted. |  | 10 Government counterparts (fulfilling the role of community liaison planting officers) have been contracted and continue to work for the project. | 10 community liaison planting officers contracted in the first year, including: • 4 in Boeungper, • 3 in Phnom Kulen; and • 3 in Phnom Prech.
| 2.2.3 Hectares of degraded forest within target CPAs restored. | No forest restoration has taken place at the five target CPAs. |  | IIn June 2015, 40,000 indigenous tress were used to restore 27.5ha area of reclaimed, degraded land within Chorm Thlork. In addition, in 2016, 15000 indigenous trees were planted on a confiscated cleared land of around 2.5 hectares in Chop Tasok CPA of Kulen National Park. By August 2017, there are 321,276 of indigenous trees have been planted in the 5 CPA project targeted sites and in other downstream communities forest areas. These indigenous trees have been used in the reforestation of degraded land, have been planted in chamkar, and have been used in enrichment planting in moderately degraded forest. | At least 30 ha of degraded forest restored in Chorm Thlok CPA before the end of the project.
| 2.2.4 Number of intensified/diversified homegardens established at the target CPAs. | There is 1 intensified/diversified homegarden at Chop Tasok. |  | 1193 (244 in 2014 and 279 in 2015 and 670 in 2016) households in total are benefitting from homegarden activities. (43 households in Chop Tasok, 60 in Ronouk Khgeng, 100 in Chiork Beungprey, 573 in Chom Thlork and 417 in Skor Crouch). A demonstration agroforestry plot has been established at Chom Thlork. Chamkar-based agroforestry plots have been piloted since August 2015. | Mid-term: 300 intensified/diversified homegardens established at the five target CPAs. A diversified/intensified homegarden should include at least 20 species, of which: i) at least 5 are indigenous fruit/soil-binding tree species; and ii) at least 8 are different vegetable species. Furthermore, the species planted within the homegarden should be representative of at least 4 different canopy layers (emergent, canopy, understory, shrub and herb). End of project: 800 intensified/diversified homegardens established at the five target CPAs. A diversified/intensified homegarden should include at least 20 species, of which: i) at least 5 are indigenous fruit/soil-binding tree species; and ii) at least 8 are different vegetable species. Furthermore, the species planted within the homegarden should be representative of at least 4 different canopy layers (emergent, canopy, understory, shrub and herb).
There are no intensified/diversified homegardens at the other four target CPAs.
| 2.2.5 Percentage of households at each CPA growing climate-resilient rice. | No households in any of the CPAs are growing climate-resilient rice varieties. |  | Consultants have been recruited to design the appropriate, scientific protocols for this intervention. In addition, project teams have distributed climate-resilient rice varieties for trialing for 64 households by August 2014 of which each family received 25kgs of rice resilience seeds species and 329 households by June 2015 of which each household received 20kgs of climate-resilient rice varieties. In early June 2016, 489 households received around 10 kgs of climate-resilient rice varieties. In total, there are 872 families have trialed climate rice resilience species. This represents ~45% if the ~1900 families living in the target CPAs. | Mid-term: 5% of households at each CPA growing climate-resilient rice varieties introduced by the AF project. End of project 15% of households at each CPA growing climate-resilient rice varieties introduced by the AF project.
| 2.2.6 Proportion of households in the five target CPAs that report an improvement in i) access to water; ii) access to new seed varieties; and iii) access to improved rice storage techniques, as a result of additional interventions. | The percentage of farmers who irrigate their crops is: 0% at Chiork Boeungprey; 12% at Chorm Thlok; 6% at Skor Krouch; 6% at Chop Tasok; and 19% at Ronouk Khgneng. No climate-resilient rice seeds have been introduced at the five target CPAs. No households at Chorm Thlok or Chop Tasok have access to improved rice storage techniques. |  | Project teams have dug 3 ponds for Chiork Boeungprey nusery together with its automatic solar water pumping system and storage tankers. 150 open tube wells fitted with hand pumps, 132 small pumping wells and 10 large pumping wells have been supplied to most households in CPA project targeted areas and some downstream communities (Open ring well: 37 in Chiork Beungprey and 63 in Chorm Thlork and 47 on other CPAs; Small pumping well: 52 in Skor Krouch, 13 in Ronouk khnheng and 67 in other CPAs; Large pumping wells: 10 in other CPAs). In Ronouk Khgeng, 74 rain harvesting tankers have been distributed to all 74 households. In Chop Tasok a complete water supply system, which links a natural spring to all households and the project nursery has been constructed together with its 7 water storage tankers. Further more, 2 water storage tankers were also constructed for Skor Krouch CPA. In addition, 2 spill dumps have been finally constructed by May 2016 at Chorm Thlork and Chup Tasok. With regard to access to new seed varieties - 1193 households received seed packs for home-gardens with some new seed varieties (about 63% of households). An average of 63% of households report improved access to water in Chiork Boeungprey, Skor Krouch and Chup Tasok. 15% of households in Chorm Thlork report improved access to water, while 100% of households in Ronouk Khnheng report improved access to water. | Mid-term: 50 % of households in the five target CPAs report an improvement in i) access to water; and ii) access to new seed varieties as a result of additional interventions. 50% of households in Chorm Thlok and Chop Tasok report an improvement in access to improved crop storage techniques as a result of additional interventions. End of project: 80% of households in the five target CPAs report an improvement in i) access to water; and ii) access to new seed varieties as a result of additional interventions. 80% of households in Chorm Thlok and Chop Tasok report an improvement in access to improved rice storage techniques as a result of additional interventions.
Output 2.3: Local communities’ livelihoods enhanced and diversified through sustainable development of NTFPs and the promotion of sustainable alternative livelihood strategies. | 2.3.1 Number of sustainable alternative livelihood strategies developed – through a participatory approach with local communities where relevant – through the project. | No sustainable alternative livelihood strategies have been developed by experts at any of the five target intervention sites. |  | Consultants have been recruited to identify appropriate alternative livelihood strategies. At least 3 alternative livelihood strategies have been identified in each site. These include chicken-raising, cricket-raising, ecotourism ventures, vegetable-selling, production and selling of roofing. | At least 3 alternative livelihood strategies developed per CPA by consultants contracted by the AF project. These will include: micro-finance insurance products and small-scale businesses for NTFPs identified in Component 1.
| 2.3.2 Percentage of target households adopting sustainable alternative livelihood strategies (dissagregated by gender). | 34% of household at Chorm Thlok and 45% of households at Skor Krouch derive income from labour. |  | The project team have distributed to 214 households (10 in 2014, 145 in 2015 and 59 in 2016) in total to start household chicken farming activities. (48 households in Chop Tasok while the additional 39 families in 2016 have both chicken and pigs (19 families are under project's alternative support mechnisms in exchange for return plots of land for reforestation activities), 50 in Ronouk Khgeng while the additional 20 families in 2016 have both chickens and pigs, 28 in Chiork Beungprey, 54 in Chom Thlork and 34 in Skor Krouch). In addition, there are 60 families from the 5 CPAs were trained on cricket raising skills and were equipped with cricket raising nestling. 15 families have been trained to make roofing using leaves from the forest. | 25% of households in the five target CPAs have adopted at least 1 sustainable alternative livelihood strategy or alternate source of income developed by the AF project. At least 30% of the beneficiaries of these alternative livelihood strategies should be women.
43% of households at Ronouk Khgneng derive income from livestock sales.
14% of household at Chorm Thlok, 12% of households at Chop Tasok and 31% at Ronouk Khgneng derive income from NTFP products.
< 10% of households at all CPAs derive income from any other sources.
Output 2.4: Socio-economic and ecosystem monitoring of AF project impacts downstream of CPA intervention sites | 2.4.1 Number of socio-economic and ecological monitoring reports and research protocols (for project duration and long-term) developed to measure impacts of the project: i) in the intervention sites; and ii) downstream of the intervention sites. | No formal specialist reports on socio-economic and ecological monitoring developed. |  | Both an International and a National Research and Monitoring Coordinator have been recruited to develop a research and monitoring plan and produce monitoring tools. Workplans and tools have been presented to the PMU. The coordinators are also guiding the MSc students regarding their research topics. The project team is also consistently collecting relevant monitoring data (for example information related to the climate-resilient rice trials) which willl be consolidated in the monitoring reports to be produced by the coordinators. Thus far 3 research and monitoring reports have been submitted and approved by the PMU. | Mid-term: • At least 1 research/monitoring tool developed and implemented to measure the impact of AF project interventions in downstream communities. • At least 5 ecological and socio-economic baseline monitoring reports (1 per CPA). End of project: • Research/monitoring tool to measure the impact of AF project interventions in downstream communities implemented at least 3 times. • At least 10 ecological and socio-economic monitoring reports (2 per CPA, 1 for baseline values and 1 for end of project).
Outcome 3: Integration of climate change risks and ecoagriculture into Cambodia’s adaptation framework and related sector policies. | Outcome 3: No., type, and sector of policy revisions to address climate change risks proposed . | No proposed revisions to integrate climate change and ecoagriculture into agricultural, forestry and development policies, strategies and plans. |  | An Institutional Expert has been recruited to undertake an institutional mapping exercise. A final report has been submitted. This consultant, together with the project team, has also updated/developed a CPA Management Plan for all five targeted communtiies. These management plans designate different usage zones within the CPAs, specify sustainable harvesting targets for NTFPs, and specificy climate change adaptation strategies for each of the target communties. A consultant will be hired during the final year of the project to proposed specific revisions to other deveopment policies and strategies building on lesssons learned through the project. | At least 3 revisions to incorporate climate change and ecoagriculture into relevant environmental, agricultural, forestry and/or development policies/plans proposed by the end of the AF project.
Output 3.1: Awareness increased at a local level of the importance of ecoagriculture for protecting and enhancing commercial and subsistence activities. | 3.1.1 Number of ‘events’ held and/or products developed to raise awareness on climate change and the benefits of adaptive agricultural techniques. | No previous ‘events’ to raise awareness, and no existing use of the ecoagriculture approach in Cambodia. |  | An Awareness Campaign Expert has been recruited to design an appropriate campaign. In addition, another consultant for training was also hired to design a relevant training course. As a result, 48 training events and 2 exchange studies have taken place with approximately 100 participants per event. Furthermore, a project web site has been developed and is awaiting official approval from the MoE. Posters demonstrating the concept of ecoagriculture have been distributed to the target CPAs. Brochures about nursery management have also been developed. Recently, two road rest areas have been constructed and equipped with awareness-rasing materials. An additional two road rest areas have started its construction and expected to finished by mid 2018. There are three camping events have been organized with participants from university students, school children, Phnom Penh yourth clup and women staff from the ministry of envisroment. there are also many forest planting evens organized with T-shirt informing about project feasibility and activities distributed to participants. These planting activities have involved thousands of community members, raising their awareness of forest conservation and climate change. | At least 28 ‘events’ held and/or prodcuts developed to raise awareness of climate change and ecoagriculture, including workshops, campaigns, education initiatives at schools/universities, a web-based data network portal and a documentary film.
| 3.1.2 Percentage change in the climate change awareness index and understanding of ecoagriculture in the target communities. | The following table shows the current values for the climate change awareness index at each CPA (based on the results of the household survey). The climate change awareness index can vary between 0 and 100%. |  | Climate change awareness was measured by the research and monitoring experts through household surveys. Climate change awareness has increased at project intervention sites. See table alongside. The average climate change awareness is 45.3%. | Mid-term: • Average awareness index score of 30% at the five target CPAs. • 30% of community members at the five target CPAs understand the concept of ecoagriculture. End of project: • Average awareness index score of 50% at the five target CPAs. • 50% of community members at the five target CPAs understand the concept of ecoagriculture.
|  | CPA | Climate change awareness index
|  | Chiork Boeungprey | 16%
|  | Chorm Thlok | 10%
|  | Skor Krouch | 30%
|  | Chop Tasok | 12%
|  | Ronouk Khgneng | 42%
The following table shows the percentage of households at each CPA that understand the concept of ecoagriculture.
Concept understood
|  | Chiork Boeungprey | 6%
|  | Chorm Thlok | 4%
|  | Skor Krouch | 6%
|  | Chop Tasok | 0%
|  | Ronouk Khgneng | 0%
| 3.1.3 Number and type of REDD+ feasibility studies and Project Idea Notes (if applicable). | No REDD+ feasibility study that investigating the potential to integrate/promote ecoagriculture or species from multi-use forests into REDD+ projects exists. |  | A consultant was recruited to undertke a REDD+ feasibility study. The final report has been submitted and approved. Based on the finding of this report, it was recommended that REDD+ is not a feasible option for this project, and therefore no Project Idea Note will be produced. | At least 1 REDD+ feasibility study and Project Idea Note (if applicable) investigating the potential to integrate/promote ecoagriculture or species from multi-use forests into REDD+ projects developed in the first year of the AF project.
Output 3.2: Ecoagriculture activities promoted through institutional capacity building and proposed revisions to policies, strategies and legislation. | 3.2.1 Number of CPA management plans developed/revised to incorporate the ecoagriculture approach. | Ronouk Khgneng and Chiork Boeungprey (due to be revised) have a CPA management plans, but they do not include strategies for the implementation or maintenance of ecoagriculture interventions. CPA management plans have yet to be developed for Chorm Thlok, Skor Krouch and Chop Tasok. |  | A land tenure specialist and insitutional expert have been recruited to contribute to the development of CPA management plans. Final reports from both of these consultants have been submitted. The institutional expert, together with the project team, has developed/updated CPA management plans for each of the target CPAs (updating the CPA management plan for Ronouk Khgeng and Chiork Beungprey and developing new plans for the other three CPAs). These four CPA Management Plans are completely finished. | At least 5 CPA management plans developed/revised to incorporate the ecoagriculture approach by the end of the AF project.
Output 3.3: National ecoagriculture upscaling strategy developed and institutionalised for CPAs in Cambodia. | 3.3.1 Number of national ecoagriculture upscaling strategies developed. | No national ecoagriculture upscaling strategy exists in Cambodia. |  | During the 5th PSC meeting it was decided to develop a Project Idea Note for upsclaing of the AF project. Will this will be done in late 2017/early 2018. In addition, a consultant will be hired to develop an upscaling strategy. | 1 national ecoagriculture upscaling strategy developed by the end of the AF project.

## Lessons Learned
QUALITATIVE MEASURES and LESSONS LEARNED
Please complete the following section every reporting period
Implementation and Adaptive Management | Response
What implementation issues/lessons, either positive or negative, affected progress? | It is time-consuming and complex to organise communities to plant large numbers of trees. Based on experience gained during the first few years of implementation, the PMU has realised that it it will be difficult to plant more than 500,000 trees per year with local communities. Workplans have been adjusted to meet this constraint. Planting more trees than this during the wet season will require the involvement of additional government departments. This will be considered during the next year of the project. Community members involved in the nursery management teams also have other work/household commitments, and therefore were not able to spend an adequate amount of time producing the high volume of trees required for planting in degraded forest and around households. To encourage their continued participation, the AF project began paying US$0.2 per seedling prodcued by the nursery, thereby compensating nursery teams membes for time taken away from other livelihood actvities. This has resulted in increased seedling production and improved project implementation. The cost per seedling remains <20% of the cost if that seedling were to be procured through a private company.
Were there any delays in implementation? If so, include any causes of delays. What measures have been taken to reduce delays? | No significant delays were experienced during this reporting period.
Describe any changes undertaken to improve results on the ground or any changes made to project outputs (i.e. changes to project design) | As described in the first PPR, 10 Government Counterparts (serving as the Community Liaison Planting officers identified in the Project Document) were recruited to improve communication with the target communities and increase their willingness to participate in project activities. Also as reported in the first PPR, based on the recommendations of the baseline study, and endorsed by the Project Steering Committee, the project restoration interventions (Output 2.2) have been adjusted to focus on agricultural land within CPAs in addition to the degraded forest areas which were initiatlly targeted by the project. No additional changes changes to project outputs have been made.
How have gender considerations been taken into consideration during the reporting period? What have been the lessons learned as a consequence of inclusion of such considerations on project performance or impacts? | Women attend workshops in the field more. Gender-sensitive workshops - women allowed to bring children to meetings. Gender considerations have been taken into account during the reporting period, particularly through: i) the inclusion of at least 50% female participants in training activities; and ii) strong participation of women in the tree-planting/reforestation actvities of the project. To achieve a strong female representation in training actvities, the project team has adapted training sessions in two main ways: - It has been observed that when training sessions are held in centralised locations (i.e. at training institutes within larger cities) it is mostly men that are selected by the community to attend. However, when the training sessions are conducted within the community, there are more women attending the training event than men. Therefore, the training has been planned to predominantly take place at the project sites. - Mothers with young children are encouraged to bring their children along to the training events. In this way the project does not exclude women who may not have been able to attend the training because they were taking care of their children. The tree-planting/reforestation activities are carried out by community members (rather than hiring in external workers). Women are encouraged to take part in these activities. As there are often more women than men in the community (as men are more likely to take on migrant labour), there are usually more women than men undertaking this actvity.
Please complete the following section at mid-term and project completion
Lessons for Adaptation | Response
Climate Resilience Measures
What have been the lessons learned, both positive and negative, in implementing climate adaptation measures that would be relevant to the design and implementation of future projects/programmes for enhanced resilience to climate change? | - It takes time at the beginning of the project to: i) develop the protocols and logistical systems to implement climate adaptation measures; and ii) build the trust of local communities. This should be incorporated into the design and plannng of project implementation. On-the-ground activities should be scheduled to begin in the second or third year of the project. - The involvement of experienced government staff aids the implementation of project activities. - A thorough Baseline Assessment lays the foundation for successful project monitoring and reporting
What is the potential for the climate resilience measures undertaken by the project/programme to be replicated and scaled up both within and outside the project area? | There is high potential for the climate resilience measures to be replicated and scaled up across Cambodia. The Minitry of Environment is investigating alternativ funding sources to replicate this project across all 120 CPAs in Cambodia.
Concrete Adaptation Interventions
What have been the lessons learned, both positive and negative, in implementing concrete adaptation interventions that would be relevant to the design and implementation of future projects/programmes implementing concrete adaptation interventions? | - Communities value water supply infrastructure. Constructing this early in the project lifespan helps to build community trust and lays the foundation for adaptation measures that require water. - Adaptation interventions had the best impact is where techniques introduced (regarding installation, planting maintenance etc) are easy to implement.
What is the potential for the concrete adaptation interventions undertaken by the project/programme to be replicated and scaled up both within and outside the project area? | There is high potential for the climate resilience measures to be replicated and scaled up across Cambodia. The Minitry of Environment is investigating alternativ funding sources to replicate this project across all 120 CPAs in Cambodia.
Community/National Impact
What would you consider to be the most successful aspects for the target communities? | The supply of water infrastruture has been very well received by target communities. In addition, the alternative livelihood options (homegardens, chicken-raising, cricket-raising, livestock-raising, etc) have been well received. Communities also have an increased appreciation for forest resources and have actively participated in reforestation activities.
What measures are/have been put in place to ensure sustainability of the project/program results? | The project activities have been mainstreamed into the work programme of the Ministry of Environment. Communities have received extensive training to allow them to continue the interventions once the project concludes. An upscaling strategy will be developed to replicate and sustain project interventions.
What measures are being/could have been put in place to improve project/program results? | The project would have benefitted from an improved coordination mechanism. Efforts are being made to share the succesful results of the prject outside of the Ministry of Environment with other government departments and project implementers.
Knowledge Management
How has existing information/data/knowledge been used to inform project development and implementation? What kinds of information/data/knowledge were used? | Lessons learned and best practices from other adaptation projects was used to inform the design of this project. In particular, these best practices informed the on-the-ground interventions.
If learning objectives have been established, have they been met? Please describe. | No specific learning objectives have been established.
Describe any difficulties there have been in accessing or retrieving existing information (data or knowledge) that is relevant to the project. Please provide suggestions for improving access to the relevant data. | There have been no specific difficulties in accessing information to inform the design of the project. Difficulties have been encountered when trying to continue coordination with other projects and both retrieve and share lessons learned during the project lifespan. The main difficulties associated with accessing community knowledge (and retrieving this existing information relates directly to the educational capacity of the local community, indigenous language conveyance challenges for the team and also the challenges (and costs associated with) physical accessing the sites especially during rainy seasons. It is suggested that national adaptation project coordination meetings should be convened by the Climate Change Department in Cambodia.
Has the identification of learning objectives contributed to the outcomes of the project? In what ways have they contributed? | No specific learning objectives have been established.

## Risk Assesment
RISK ASSESMENT
IDENTIFIED RISKS
List all Risks identified in project preparation phase and what steps are being taken to mitigate them
Identified Risk | Current Status | Steps Taken to Mitigate Risk
Current climate and seasonal variability and/or hazard events result in poor restoration results or agricultural yields. | Low | The Botanist, Agricultural Climate Forecasting Expert and Agricultural Adaptation Expert have identified appropriate flood- and drought-resistant species to utilise during restoration activities. Restoration actvities have been timed to coincide with the onset of the wet season. Restoration activities are rescheduled if flooding is experienced/predicted.
Intervention sites may be sold for Economic Land Concessions. | Low | The intervention sites are situated within CPAs, which by law cannot be sold as Economic Land Concessions. A Land Tenure Expert has undertaken a study to confirm the legal status of CPAs and educate local community members about their land tenure rights.
Disagreement amongst stakeholders with regards to demonstration site selection. | Low | The interventions sites were selected using an agreed upon list of criteria to ensure that the selection process was transparent and equitable. The selection process was conducted through a participatory approach, with multiple meetings/workshops with local communities. At each project site, the relevant CPA Community Management Committees have identified the specific sites for project activities. Additional CPAs that recieve support from the project are also selected through a transparent process. The Provincial Environmental Department sends a request for a specific CPA that it has identified as being in need of support. Members of the National Project Team then assess the request based on pre-determined criteria. These criteria for additional sites are: i) need for additional water supply infrastructure; and ii) need and capacity to undertake tree planting (in forest and home gardens). If the CPA meets these requirements then support in the form of water supply infrastructure and seedlings for reforestaton and home-gardenng are supplied.
Communities may not adopt activities during or after the AF project. | Low | Extensive community consultations have been held since the initiation of the project. These consultations have been conducted during the baseline study and as part of the duties of the 18 National experts. Therefore local knowledge is included in the design of project interventions and activities, reducing the risk that local communities may not adopt the project interventions. In addition to the work conducted by consultants to the project, the national government counterparts (team leaders, assistant team leaders and field leaders) visit each of the target communities regularly to inform community members of project activities and ensure their continued support. During one such visit, each household within all five CPA intervention sites was visited to assess their willingness to participate in the project activities and obtain a "family profile". Based on this information, 279 households were selected to participate in project activities during the second and third year. Because these households were selected based on their willingness and capacity to participate, the risk of them not adopting project activities is low. Additional households have since indicated their willingness to participate in the project because of the tangible benefits that they observed in other households. Therefore, through demonstration of interventions with willing households during the first few years of the project, the communities are willingly adopting the activities of the AF project and are considered likley to continue these activities once the project has ended. Water infrastructure, including ponds, dams, wells and distribution systems, have also been constructed at each of the project sites. This tangible benefit to local communities has generated additional support for the project. Finally, the project is, and will continue to, undertake training in local communities to promote ecoagriculture and highlight the benefits provided by the AF project interventions. To date, training has been provided on nursery management, seed propagation, climate change awareness, ecoagriculture, land tenure, family livestock farming and family financial management.
Loss of government support may result in lack of prioritisation of AF project activities. | Low | 10 government counterparts (team leaders, assistant team leaders and field leaders) have been hired by the project to facilitate the implementation of project activities. The government therefore has a vested interest to maintain its support of project activities. In addition, regular government stakeholder consultations have taken place to keep them informed of project progress and the benefits that the project offers to their ongoing agriculture and forestry programmes. Several high-level government officials, including the Minister of Environment, have also been involved in the inauguration of project intervention sites. The physical demonstration of project activities to government officials has ensured their continued support of the project.
Institutional capacities and relationships are not sufficient to provide effective solutions to climate problems that are complex and multi-sectoral. | Medium | Institutional capacity development is included in the design of the project. To date, an Institutional capacity expert has undertaken an institutional mapping exercise and gap analysis in relevant government departments and research institutions to determine potential shortfalls for the planning and implementation of ecoagriculture interventions in CPAs. The results of this assessment have been used to ensure that the necessary and appropriate government departments have been included in the implementation of project activities (e.g. staff from the Ministry of Agriculture have been involved in the training on ecoagriculture and the selection of drought-resilient rice varieties). In addition, national experts have been hired where appropriate to contribute specialised technical expertise. These experts have transferred knowledge and skills to government officials. High-level government officials, including the Minister of Environment, have also been involved in the inauguration of project intervention sites. This has ensured awareness of, and support for, the project across multiple government departments.
Capacity constraints of local institutions may limit the ability to undertake the research and interventions. | Medium | The Royal University of Phnom Penh and the Royal Agriculture University have been approached to contribute to the long-term research objectives of the project. These are the premier research institutions within Phnom Penh. Fifteen MSc students with appropriate supervisors have been supported to undertake research related to the AF project. Furthermore, an International Research and Monitoring Coordinator (in addition to a National Research and Monitoring Coordinator) has been recruited to guide the research and monitoring activities of the students, national experts and project monitoring team. Finally, the CTA for the project is actively engaged to provide technical advice on project interventions, monitoring and research.
Priority interventions implemented are not found to be cost-effective. | Low | Cost-effectiveness was an important consideration in the design of the project, and thus the risk that interventions are found not to be cost-effective is low. In addition, an Agricultural Market Assessment expert was hired with the specific objective to analyse the cost-benefit of selected interventions. The findings of this expert were used to guide further project interventions. Procurement procedures followed by the AF project ensure that cost-effective implementation arrangements are followed.
Lack of commitment/buy-in from local communities may result in failure of intervention sites. | Low | Please see the description of the steps taken to mitigate the "Communities may not adopt activities during or after the AF project" risk identified above. Overall, communities voluntarily participate in project interventions, and therefore buy-in is ensured. Furthermore, by providing tangible benefits to communities during the early stages of the project, the AF project has encouraged commitment of local communties to the activities of the project.
Critical Risks Affecting Progress (Not identified at project design)
Identify Risks with a 50% or > likelihood of affecting progress of project
Identified Risk | Current Status | Steps Taken to Mitigate Risk
The percieved threat of CPA land being sold as an Economic Land Concession has led to communities clearing land within the CPA for farming activities, which threatens the project's restoration objectivies. | Medium | Based on the recommendations of the baseline study, the project restoration interventions have been adjusted to focus on agricultural land within CPAs in addition to the degraded forest areas which were initiatlly targeted by the project. This is due to the recently identified increased risk of land clearance within CPA's following the Economic Land Concessions which has resulted in less communally owned areas of degraded forests available for restoration. An agroforestry approach will be adopted in the agricultural lands within CPAs which will increase the ecological diversity and functioning of these areas while maintaining the livelihoods of the local farmers. Because local communities continue to derive income and livelihoods from these lands, this will reduce the threat of land clearance once project activities have ended. In addition, local community members in the Chom Thlork CPA (where this risk is high) have signed contracts with the government pledging not to clear additional areas of forest within the CPA. Training on land tenure and community land tenure rights has also been provided to local communities. This training has emphasised the fact that CPA's cannot legally be sold as an Economic Land Concession, and therefore community members do not need to clear land in order to "claim" it. Since the start of the project, the Government of Cambodia has ceased granting Economic Land Concessions, and this has further reduced this risk.
Government counterparts, assigned to work part-time with the project do not have sufficient time to dedicate to the project, which negatively the implementation of project activities. | Low | Thorough workplans have been developed for the project to enable the government counterparts the opportunity to manage their time and set aside time to work on the project in advance. Through the involvement of high-level government officials in project activities, the project has garnered significant support within the MoE. Government staff are therefore encouraged to work on the project.
Risk Measures: Were there any risk mitigation measures employed during the current reporting period? If so, were risks reduced? If not, why were these risks not reduced?
Add any comments relevant to risk mitigation (word limit = 500)
No additional risks were identified during the current reporting period. Previous risk mitigation measures identified continued to be implemented (where applicable) and were effective in reducing risks.

## Results Tracker
Results Tracker for Adaptation Fund (AF) Projects
Goal: Assist developing-country Parties to the Kyoto Protocol that are particularly vulnerable to the adverse effects of climate change in meeting the costs of concrete adaptation projects and programmes in order to implement climate-resilient measures. Impact: Increased resiliency at the community, national, and regional levels to climate variability and change.
Important: Please read the following guidance document (also posted on the Adaptation Fund website) before entering your data
Link: http://www.adaptation-fund.org/sites/default/files/Results%20Framework%20and%20Baseline%20Guidance%20final.pdf
Adaptation Fund Strategic Results Framework
Project ID | AFB-5060-1111-2H81
Implementing Entity | UNEP
Type of implementing entity | MIE
Country | Cambodia
Region | Asia-Pacific
Sector | Multi-sector
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Impact: Increased resiliency at the community, national, and regional levels to climate variability and change | Core Indicator: No. of beneficiaries |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project
|  | Total | 0 | 0 | 0 | Total | 10000 | 1000 | 9000 | Total | 18455 | 9455 | 9000 | Total
|  | % of female beneficiaries | 0% | 0% | 0% | % of female beneficiaries | 50% | 50% | 50% | % of female beneficiaries | 50% | 50% | 50% | % of female beneficiaries
|  | % of Youth beneficiaries | 0% | 0% | 0% | % of Youth beneficiaries |  |  |  | % of Youth beneficiaries |  |  |  | % of Youth beneficiaries
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 1: Reduced exposure to climate-related hazards and threats | Indicator 1: Relevant threat and hazard information generated and disseminated to stakeholders on a timely basis | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness
|  | Total |  |  |  | Total |  |  |  | Total |  |  |  | Total
|  | % of female targeted |  |  |  | % of female targeted |  |  |  | % of female targeted |  |  |  | % of female targeted
Output 1.1 Risk and vulnerability assessments conducted and updated | Indicator 1.1: No. of projects/programmes that conduct and update risk and vulnerability assessments | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
Output 1.2 Targeted population groups covered by adequate risk reduction systems | Core Indicator 1.2: No. of Early Warning Systems | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 2: Strengthened institutional capacity to reduce risks associated with climate-induced socioeconomic and environmental losses | Indicator 2: Capacity of staff to respond to, and mitigate impacts of, climate-related events from targeted institutions increased | Number of staff targeted |  | Sector | Capacity level | Number of staff targeted |  | Sector | Capacity level | Number of staff targeted |  | Sector | Capacity level | Number of staff targeted |  | Sector | Capacity level
|  | Total |  |  |  | Total |  |  |  | Total |  |  |  | Total
|  | % of female targeted |  |  |  | % of female targeted |  |  |  | % of female targeted |  |  |  | % of female targeted
Output 2.1 Strengthened capacity of national and sub-national centres and networks to respond rapidly to extreme weather events | Indicator 2.1.1: No. of staff trained to respond to, and mitigate impacts of, climate-related events | Total staff trained | % of female staff trained | Type |  | Total staff trained | % of female staff trained | Type |  | Total staff trained | % of female staff trained | Type |  | Total staff trained | % of female staff trained | Type
| Indicator 2.1.2: No. of targeted institutions with increased capacity to minimize exposure to climate variability risks | Type | Scale | Sector | Capacity level | Type | Scale | Sector | Capacity level | Type | Scale | Sector | Capacity level | Type | Scale | Sector | Capacity level
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 3: Strengthened awareness and owernship of adaptation and climate risk reduction processes | Indicator 3.1: Increase in application of appropriate adaptation responses | Percentage of targeted population applying adaptation measures |  | Sector |  | Percentage of targeted population applying adaptation measures |  | Sector |  | Percentage of targeted population applying adaptation measures |  | Sector |  | Percentage of targeted population applying adaptation measures |  | Sector
Output 3: Targeted population groups participating in adaptation and risk reduction awareness activities | Indicator 3.1.1: Percentage of targeted population awareness of predicted adverse impacts of climate change, and of appropriate responses | No. of targeted beneficiaries | % of female participants targeted | Level of awareness |  | No. of targeted beneficiaries | % of female participants targeted | Level of awareness |  | No. of targeted beneficiaries | % of female participants targeted | Level of awareness |  | No. of targeted beneficiaries | % of female participants targeted | Level of awareness
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Target performance at completion
Outcome 4: Increased adaptive capacity within relevant development sector services and infrastructure assets | Indicator 4.1: Increased responsiveness of development sector services to evolving needs from changing and variable climate | Project/programme sector | Geographical scale | Response level |  | Project/programme sector | Geographical scale | Response level |  | Project/programme sector | Geographical scale | Response level |  | Project/programme sector | Geographical scale | Response level
| Core Indicator 4.2: Assets produced, developed, improved or strengthened | Sector | Targeted asset | Changes in asset (quantitative or qualitative) |  | Sector | Targeted asset | Changes in asset (quantitative or qualitative) |  | Sector | Targeted asset | Changes in asset (quantitative or qualitative) |  | Sector | Targeted asset | Changes in asset (quantitative or qualitative)
Output 4: Vulnerable development sector services and infrastructure assets strengthened in response to climate change impacts, including variability | Indicator 4.1.1: No. and type of development sector services to respond to new conditions resulting from climate variability and change | Number of services | Type |  | Sector | Number of services | Type |  | Sector | Number of services | Type |  | Sector | Number of services | Type |  | Sector
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Target performance at completion
Outcome 5: Increased ecosystem resilience in response to climate change and variability-induced stress | Indicator 5: Ecosystem services and natural resource assets maintained or improved under climate change and variability-induced stress | Natural resource improvement level |  | Sector | Type | Natural resource improvement level |  | Sector | Type | Natural resource improvement level |  | Sector | Type | Natural resource improvement level |  | Sector | Type
|  | 2: Partially effective |  | Multi-sector | biological assets | 5: Very effective |  | Multi-sector | biological assets | 5: Very effective |  | Multi-sector | biological assets
Output 5: Vulnerable ecosystem services and natural resource assets strengthned in response to climate change impacts, including variability | Core Indicator 5.1: Natural Assets protected or rehabilitated | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Forests | 1 | ha rehabilitated | 2: Partially effective | Forests | 30 | ha rehabilitated | 4: Effective | Forests | 672 | ha rehabilitated | 4: Effective
|  | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Baseline information |  |  |  | Targeted performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 6: Diversified and strengthened livelihoods and sources of income for vulnerable people in targeted areas | Indicator 6.1: Increase in households and communities having more secure access to livelihood assets | No. of targeted households | % of female headed households | Improvement level |  | No. of targeted households | % of female headed households | Improvement level |  | No. of targeted households | % of female headed households | Improvement level |  | No. of targeted households | % of female headed households | Improvement level
| Indicator 6.2: Increase in targeted population's sustained climate-resilient alternative livelihoods | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
|  | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
|  | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
|  | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
Output 6 Targeted individual and community livelihood strategies strengthened in relation to climate change impacts, including variability | Indicator 6.1.1: No. and type of adaptation assets created or strengthened in support of individual or community livelihood strategies | Number of Assets | Type of Assets | Sector | Adaptation strategy | Number of Assets | Type of Assets | Sector | Adaptation strategy | Number of Assets | Type of Assets | Sector | Adaptation strategy | Number of Assets | Type of Assets | Sector | Adaptation strategy
| Core Indicator 6.1.2: Increased income, or avoided decrease in income | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 7: Improved policies and regulations that promote and enforce resilience measures | Indicator 7: Climate change priorities are integrated into national development strategy | Integration level |  |  |  | Integration level |  |  |  | Integration level |  |  |  | Integration level
|  | 3: Some |  |  |  | 4: Most
Output 7:Improved integration of climate-resilience strategies into country development plans | Indicator 7.1: No. of policies introduced or adjusted to address climate change risks | No. of Policies introduced or adjusted | Sector | Scale | Type | No. of Policies introduced or adjusted | Sector | Scale | Type | No. of Policies introduced or adjusted | Sector | Scale | Type | No. of Policies introduced or adjusted | Sector | Scale | Type
|  | 1 | Multi-sector | National | Environmental policy | 1 | Multi-sector | National | Environmental policy | 0 | Multi-sector | National | Environmental policy
| Indicator 7.2: No. of targeted development strategies with incorporated climate change priorities enforced | No. of Development strategies | Regulation |  | Effectiveness | No. of Development strategies | Regulation |  | Effectiveness | No. of Development strategies | Regulation |  | Effectiveness | No. of Development strategies | Regulation |  | Effectiveness
Glacier lake outburst flood
|  | Inland flooding | fr | biological assets |  | Company policy | 5: Fully enforced (All elements implemented)
|  | Salinization | Decrease | land |  | Communication & Information policy | 4: Enforced (Most elements implemented)
|  | Drought | Same | water areas |  | Defense policy | 3: Partially enforced (Some elements implemented)
|  | Wind |  | subsoil assets | increased adpative capacity | Domestic policy | 2: Partially not enforced (Most elements not implemented) |  | Agribusiness
|  | Coastal flooding |  | air | achieved | Economic policy | 1: Not enforced (No elements implemented) |  | Agricultural-related | Financial capital
|  | Storm surge | Please choose |  | enhanced level of protection | Education policy |  |  | Agriculture | Human capital
|  | Hurricane | Selected | [5 empty] | Aquaculture | Physical capital
|  |  | Not relevant |  |  | 5: All (Fully integrated) |  |  | Construction/repairing business | Social capital
[6 empty] | 4: Most |  |  | Cultivation | Natural capital
[6 empty] | 3: Some |  |  | Fishing | Personal capital
Select | 5: All | Select |  |  | Community | 2: Most not integrated |  | Other | Forestry | Adaptation strategies
1 | 4: Almost all | Private | Type | Yes | Multi-community | 1: None |  | Agriculture | Handicrafts
2 | 3: Half | Public | Scale | No | Departmental |  |  | Coastal management | Livestock production
3 | 2: Some | NGO | Sector |  | National |  |  | Disaster risk reduction | Manufacturing
4 | 1: None |  |  |  |  | 5: Very high improvement | Established | Food security | other
|  | National |  |  |  | 4: High improvement | Maintained | Health | Services
|  | Regional |  |  |  | 3: Moderate improvement | Improved | Urban development | Tourism-related
|  | Local |  |  |  | 2: Limited improvement |  | Water management | Trading
[6 empty] | 1: No improvement |  | Multi-sector
|  | 1 -generated information is irrelevant, and neither the stakeholders reached nor the timeframe managed were achieved | 1: No info transferred on time | 4: High capacity | 5: Fully aware | 5: Highly responsive (All defined elements ) | 5: Fully improved | Roads | 5: Very effective
Asia-Pacific | NIE | 2 -the existence of some challenge in any of the three aspects of the indicator (generation of dissemination, stakeholders reached or timeframe managed) | 2: Somewhat info transferred | 3: Medium capacity | 4: Mostly aware | 4: Mostly responsive (Most defined elements) | 4: Mostly Improved | Gov Buildings | 4: Effective
Latin America and Caribbean | RIE | 3 -relevant information is generated and disseminated to all identified stakeholders on timely basis | 3: Info transferred on time | 2: Low capacity | 3: Partially aware | 3: Moderately responsive (Some defined elements) | 3: Moderately improved | Causeways | 3: Moderately effective
Africa | MIE |  |  | 1: No capacity | 2: Partially not aware | 2: Partially responsive (Lacks most elements) | 2: Somewhat improved | Airports | 2: Partially effective
Eastern Europe |  |  |  |  | 1: Aware of neither | 1: Non responsive (Lacks all elements ) | 1: Not improved | Schools | 1: Ineffective
| ha protected | [6 empty] | Training Centres
| ha rehabilitated | [5 empty] | Monitoring/Forecasting capacity | Hospitals
Afghanistan, Islamic Rep. of | km protected | [5 empty] | Policy/regulatory reform | Drinking water systems
Angola | km rehabilitated | 1: Risk knowledge | 1: No plans conducted or updated |  |  |  | Capacity development | Other
Albania |  | 2: Monitoring and warning service | 2: Undertaking or updating of assessments in progress |  |  | Communication & Information policy | Sustainable forest management
Argentina |  | 3: Dissemination and communication | 3: Risk and vulnterability assessments completed or updated |  |  | Domestic policy | Strengthening infrastructure | 1: Health and Social Infrastructure (developed/improved)
Armenia | Forests | 4: Response capability |  |  |  | Economic policy | Supporting livelihoods | 2: Physical asset (produced/improved/strenghtened)
Antigua and Barbuda | Mangroves |  |  |  |  | Education policy | Mangrove reforestation
Azerbaijan | Coasts |  | From 0 to 0.5% |  |  | Energy policy | Coastal drainage and infrastructure
Burundi | Rangelands |  | From 0.5 to 1% |  |  | Environmental policy | Irrigation system
Benin | Cultivated land/Agricultural land |  | From 1% to 5% |  |  | Foreign policy | Community-based adaptation
Burkina Faso | Catchment area/Watershed/Aquifer |  | From 5% to 10% |  |  | Health policy | Erosion control
Bangladesh | Protected areas/National parks |  | From 10% to 20% |  |  | Housing policy | Soil water conservation
Bulgaria | Other |  | From 20% to 30% |  |  | Human resource policies | Microfinance
Bahrain |  |  | From 30% to 40% |  |  | Information policy | Special Program for women
Bahamas, The |  |  | From 40% to 50% |  |  | Macroeconomic policy | Livelihoods
Bosnia and Herzegovina |  |  | Above 50% |  |  | Monetary policy | Water storage
Belarus | [5 empty] | Population policy | ICT and information dissemination
Belize | [5 empty] | Private policy
Bolivia | [5 empty] | Public policy
Brazil | [5 empty] | Science policy
Barbados | [5 empty] | Social policy
Bhutan |  | 3- relevant information is generated and disseminated to all identified stakeholders on timely basis |  |  |  | Transportation policy
Botswana |  | describe |  |  |  | Urban policy
Central African Republic |  | 2- the existence of some challenge in any of the three aspects of the indicator |  |  |  | Water policy
Chile |  | describe |  |  |  | Other policy
China, People's Republic of |  | 1- generated information is irrelevant and neither the stakeholders reached nor the timeframe managed were achieved
Cote d'Ivoire |  | describe
Cameroon
Congo, Dem. Rep. of
Congo, Republic of
Cook Islands
Colombia
Comoros
Cape Verde
Costa Rica
Cuba
Czech Republic
Djibouti
Dominica
Dominican Republic
Algeria
Ecuador
Egypt
Eritrea
Estonia
Ethiopia
Fiji
Micronesia, Fed. States of
Gabon
Georgia
Ghana
Guinea
Gambia, The
Guinea-Bissau
Equatorial Guinea
Grenada
Guatemala
Guyana
Honduras
Croatia
Haiti
Hungary
Indonesia
India
Iran, Islamic Republic of
Jamaica
Jordan
Kazakhstan
Kenya
Kyrgyz Republic
Cambodia
Kiribati
Saint Kitts and Nevis
Korea, Republic of
Lao People's Democratic Republic
Lebanon
Liberia
Libya
Saint Lucia
Sri Lanka
Lesotho
Lithuania
Latvia
Morocco
Moldova
Madagascar
Maldives
Mexico
Marshall Islands
Macedonia, former Yugoslav Republic of
Mali
Malta
Myanmar
Montenegro
Mongolia
Mozambique
Mauritania
Mauritius
Malawi
Malaysia
Namibia
Niger
Nigeria
Nicaragua
Niue
Nepal
Nauru
Oman
Pakistan
Panama
Peru
Philippines
Palau
Papua New Guinea
Poland
Korea, Dem. People's Rep. of
Paraguay
Romania
Russian Federation
Rwanda
Saudi Arabia
Sudan
Senegal
Solomon Islands
Sierra Leone
El Salvador
San Marino
Serbia
Sao Tome and Principe
Suriname
Slovak Republic
Slovenia
Swaziland
Seychelles
Syrian Arab Republic
Chad
Togo
Thailand
Tajikistan
Turkmenistan
Tonga
Trinidad and Tobago
Tunisia
Turkey
Tuvalu
Tanzania
Uganda
Ukraine
Uruguay
Uzbekistan
Saint Vincent and the Grenadines
Venezuela
Vietnam
Vanuatu
Samoa
Yemen, Republic of
South Africa
Zambia
Zimbabwe
Timor-Leste
Note on M89: 30 ha have been restored. Inaddition, 321,276 indigenous trees have been planted. Estmating 500 trees per hectare, an additional 642 ha have been restored.

## Results Tracker (old)
Results Tracker for Adaptation Fund (AF) Projects
Goal: Assist developing-country Parties to the Kyoto Protocol that are particularly vulnerable to the adverse effects of climate change in meeting the costs of concrete adaptation projects and programmes in order to implement climate-resilient measures. Impact: Increased resiliency at the community, national, and regional levels to climate variability and change.
Important: Please read the following Results Framework and Baseline Guidance (also posted on the Adaptation Fund website) before entering your data
Link: http://www.adaptation-fund.org/sites/default/files/Results%20Framework%20and%20Baseline%20Guidance%20final.pdf
Please select the relevant Fund level Outcome and Output indicators that allign with the project objectives and outcomes
OBJECTIVE 1
Fund Outcome | Please select from dropdown menu below | Fund Outcome Indicator | Please select from dropdown menu below | Target at CEO Endorsement (see Units in next sheet) | Baseline (see Units in next sheet) | Mid-term Results | Terminal Results
Outcome 1: Reduced exposure at national level to climate-related hazards and threats Outcome 2: Strengthened institutional capacity to reduce risks associated with climate-induced socioeconomic and environmental losses Outcome 3: Strengthened awareness and ownership of adaptation and climate risk reduction processes at local level Outcome 4: Increased adaptive capacity within relevant development and natural resource sectors Outcome 5: Increased ecosystem resilience in response to climate change and variability-induced stress Outcome 6: Diversified and strengthened livelihoods and sources of income for vulnerable people in targeted areas Outcome 7: Improved policies and regulations that promote and enforce resilience measures | 5 | 1. Relevant threat and hazard information generated and disseminated to stakeholders on a timely basis 2.1. No. and type of targeted institutions with increased capacity to minimize exposure to climate variability risks 2.2. Number of people with reduced risk to extreme weather events 3.1. Percentage of targeted population aware of predicted adverse impacts of climate change, and of appropriate responses 3.2. Modification in behavior of targeted population 4.1. Development sectors' services responsive to evolving needs from changing and variable climate 4.2. Physical infrastructure improved to withstand climate change and variability-induced stress 5. Ecosystem services and natural assets maintained or improved under climate change and variability-induced stress 6.1. Percentage of households and communities having more secure (increased) access to livelihood assets 6.2. Percentage of targeted population with sustained climate-resilient livelihoods 7. Climate change priorities are integrated into national development strategy | 5 | 5 | 2
Fund Output | Please select from dropdown menu below | Fund Output Indicator | Please select from dropdown menu below | Target at CEO Endorsement (see Units in next sheet) | Baseline (see Units in next sheet) | Mid-term Results | Terminal Results
Output 1: Risk and vulnerability assessments conducted and updated at a national level Output 2.1: Strengthened capacity of national and regional centres and networks to respond rapidly to extreme weather events Output 2.2: Targeted population groups covered by adequate risk reduction systems Output 3: Targeted population groups participating in adaptation and risk reduction awareness activities Output 4: Vulnerable physical, natural, and social assets strengthened in response to climate change impacts, including variability Output 5: Vulnerable physical, natural, and social assets strengthened in response to climate change impacts, including variability Output 6: Targeted individual and community livelihood strategies strengthened in relation to climate change impacts, including variability Output 7: Improved integration of climate-resilience strategies into country development plans | 5 | 1.1. No. and type of projects that conduct and update risk and vulnerability assessments 1.2. Development of early warning systems 2.1.1. No. of staff trained to respond to, and mitigate impacts of, climate-related events 2.1.2. Capacity of staff to respond to, and mitigate impacts of, climate-related events from targeted institutions increased 2.2.1. Percentage of population covered by adequate risk-reduction systems 2.2.2. No. of people affected by climate variability 3.1 No. and type of risk reduction actions or strategies introduced at local level 3.2 No. of news outlets in the local press and media that have covered the topic 4.1. No. and type of health or social infrastructure developed or modified to respond to new conditions resulting from climate variability and change (by type) 4. 2. No. of physical assets strengthened or constructed to withstand conditions resulting from climate variability and change (by asset types) 5. No. and type of natural resource assets created, maintained or improved to withstand conditions resulting from climate variability and change (by type of assets) 6.1. No. and type of adaptation assets (physical as well as knowledge) created in support of individualor community-livelihood strategies 6.2. Type of income sources for households generated under climate change scenario 7.1. No., type, and sector of policies introduced or adjusted to address climate change risks 7.2. No. or targeted development strategies with incorporated climate change priorities enforced | 5 | i) At least 30 ha of degraded forest restored in Chorm Thlok CPA before the end of the project, ii) 800 intensified/diversified homegardens established at the five target CPA | i) No forest restoration has taken place at the five target CPAs, ii) there is 1 intensified/diversified homegarden at Chop Tasok and none in the other four CPA's
OBJECTIVE 2
Fund Outcome | Please select from dropdown menu below | Fund Outcome Indicator | Please select from dropdown menu below | Target at CEO Endorsement | Baseline | Mid-term Results | Terminal Results
Outcome 1: Reduced exposure at national level to climate-related hazards and threats Outcome 2: Strengthened institutional capacity to reduce risks associated with climate-induced socioeconomic and environmental losses Outcome 3: Strengthened awareness and ownership of adaptation and climate risk reduction processes at local level Outcome 4: Increased adaptive capacity within relevant development and natural resource sectors Outcome 5: Increased ecosystem resilience in response to climate change and variability-induced stress Outcome 6: Diversified and strengthened livelihoods and sources of income for vulnerable people in targeted areas Outcome 7: Improved policies and regulations that promote and enforce resilience measures | 7 | 1. Relevant threat and hazard information generated and disseminated to stakeholders on a timely basis 2.1. No. and type of targeted institutions with increased capacity to minimize exposure to climate variability risks 2.2. Number of people with reduced risk to extreme weather events 3.1. Percentage of targeted population aware of predicted adverse impacts of climate change, and of appropriate responses 3.2. Modification in behavior of targeted population 4.1. Development sectors' services responsive to evolving needs from changing and variable climate 4.2. Physical infrastructure improved to withstand climate change and variability-induced stress 5. Ecosystem services and natural assets maintained or improved under climate change and variability-induced stress 6.1. Percentage of households and communities having more secure (increased) access to livelihood assets 6.2. Percentage of targeted population with sustained climate-resilient livelihoods 7. Climate change priorities are integrated into national development strategy | 7 | 4 | 1
Fund Output | Please select from dropdown menu below | Fund Output Indicator | Please select from dropdown menu below | Target at CEO Endorsement | Baseline | Mid-term Results | Terminal Results
Output 1: Risk and vulnerability assessments conducted and updated at a national level Output 2.1: Strengthened capacity of national and regional centres and networks to respond rapidly to extreme weather events Output 2.2: Targeted population groups covered by adequate risk reduction systems Output 3: Targeted population groups participating in adaptation and risk reduction awareness activities Output 4: Vulnerable physical, natural, and social assets strengthened in response to climate change impacts, including variability Output 5: Vulnerable physical, natural, and social assets strengthened in response to climate change impacts, including variability Output 6: Targeted individual and community livelihood strategies strengthened in relation to climate change impacts, including variability Output 7: Improved integration of climate-resilience strategies into country development plans | 7 | 1.1. No. and type of projects that conduct and update risk and vulnerability assessments 1.2. Development of early warning systems 2.1.1. No. of staff trained to respond to, and mitigate impacts of, climate-related events 2.1.2. Capacity of staff to respond to, and mitigate impacts of, climate-related events from targeted institutions increased 2.2.1. Percentage of population covered by adequate risk-reduction systems 2.2.2. No. of people affected by climate variability 3.1 No. and type of risk reduction actions or strategies introduced at local level 3.2 No. of news outlets in the local press and media that have covered the topic 4.1. No. and type of health or social infrastructure developed or modified to respond to new conditions resulting from climate variability and change (by type) 4. 2. No. of physical assets strengthened or constructed to withstand conditions resulting from climate variability and change (by asset types) 5. No. and type of natural resource assets created, maintained or improved to withstand conditions resulting from climate variability and change (by type of assets) 6.1. No. and type of adaptation assets (physical as well as knowledge) created in support of individualor community-livelihood strategies 6.2. Type of income sources for households generated under climate change scenario 7.1. No., type, and sector of policies introduced or adjusted to address climate change risks 7.2. No. or targeted development strategies with incorporated climate change priorities enforced | 7.1 | 1 national ecoagriculture upscaling strategy and at least 3 revisions to incorporate climate change and ecoagriculture into relevant environmental, agricultural, forestry and/or development policies/plans. | No upscaling strategy or revisions exist
OBJECTIVE 3
Fund Outcome | Please select from dropdown menu below | Fund Outcome Indicator | Please select from dropdown menu below | Target at CEO Endorsement | Baseline | Mid-term Results | Terminal Results
Outcome 1: Reduced exposure at national level to climate-related hazards and threats Outcome 2: Strengthened institutional capacity to reduce risks associated with climate-induced socioeconomic and environmental losses Outcome 3: Strengthened awareness and ownership of adaptation and climate risk reduction processes at local level Outcome 4: Increased adaptive capacity within relevant development and natural resource sectors Outcome 5: Increased ecosystem resilience in response to climate change and variability-induced stress Outcome 6: Diversified and strengthened livelihoods and sources of income for vulnerable people in targeted areas Outcome 7: Improved policies and regulations that promote and enforce resilience measures |  | 1. Relevant threat and hazard information generated and disseminated to stakeholders on a timely basis 2.1. No. and type of targeted institutions with increased capacity to minimize exposure to climate variability risks 2.2. Number of people with reduced risk to extreme weather events 3.1. Percentage of targeted population aware of predicted adverse impacts of climate change, and of appropriate responses 3.2. Modification in behavior of targeted population 4.1. Development sectors' services responsive to evolving needs from changing and variable climate 4.2. Physical infrastructure improved to withstand climate change and variability-induced stress 5. Ecosystem services and natural assets maintained or improved under climate change and variability-induced stress 6.1. Percentage of households and communities having more secure (increased) access to livelihood assets 6.2. Percentage of targeted population with sustained climate-resilient livelihoods 7. Climate change priorities are integrated into national development strategy
Fund Output | Please select from dropdown menu below | Fund Output Indicator | Please select from dropdown menu below | Target at CEO Endorsement | Baseline | Mid-term Results | Terminal Results
Output 1: Risk and vulnerability assessments conducted and updated at a national level Output 2.1: Strengthened capacity of national and regional centres and networks to respond rapidly to extreme weather events Output 2.2: Targeted population groups covered by adequate risk reduction systems Output 3: Targeted population groups participating in adaptation and risk reduction awareness activities Output 4: Vulnerable physical, natural, and social assets strengthened in response to climate change impacts, including variability Output 5: Vulnerable physical, natural, and social assets strengthened in response to climate change impacts, including variability Output 6: Targeted individual and community livelihood strategies strengthened in relation to climate change impacts, including variability Output 7: Improved integration of climate-resilience strategies into country development plans |  | 1.1. No. and type of projects that conduct and update risk and vulnerability assessments 1.2. Development of early warning systems 2.1.1. No. of staff trained to respond to, and mitigate impacts of, climate-related events 2.1.2. Capacity of staff to respond to, and mitigate impacts of, climate-related events from targeted institutions increased 2.2.1. Percentage of population covered by adequate risk-reduction systems 2.2.2. No. of people affected by climate variability 3.1 No. and type of risk reduction actions or strategies introduced at local level 3.2 No. of news outlets in the local press and media that have covered the topic 4.1. No. and type of health or social infrastructure developed or modified to respond to new conditions resulting from climate variability and change (by type) 4. 2. No. of physical assets strengthened or constructed to withstand conditions resulting from climate variability and change (by asset types) 5. No. and type of natural resource assets created, maintained or improved to withstand conditions resulting from climate variability and change (by type of assets) 6.1. No. and type of adaptation assets (physical as well as knowledge) created in support of individualor community-livelihood strategies 6.2. Type of income sources for households generated under climate change scenario 7.1. No., type, and sector of policies introduced or adjusted to address climate change risks 7.2. No. or targeted development strategies with incorporated climate change priorities enforced
OBJECTIVE 4
Fund Outcome | Please select from dropdown menu below | Fund Outcome Indicator | Please select from dropdown menu below | Target at CEO Endorsement | Baseline | Mid-term Results | Terminal Results
Outcome 1: Reduced exposure at national level to climate-related hazards and threats Outcome 2: Strengthened institutional capacity to reduce risks associated with climate-induced socioeconomic and environmental losses Outcome 3: Strengthened awareness and ownership of adaptation and climate risk reduction processes at local level Outcome 4: Increased adaptive capacity within relevant development and natural resource sectors Outcome 5: Increased ecosystem resilience in response to climate change and variability-induced stress Outcome 6: Diversified and strengthened livelihoods and sources of income for vulnerable people in targeted areas Outcome 7: Improved policies and regulations that promote and enforce resilience measures |  | 1. Relevant threat and hazard information generated and disseminated to stakeholders on a timely basis 2.1. No. and type of targeted institutions with increased capacity to minimize exposure to climate variability risks 2.2. Number of people with reduced risk to extreme weather events 3.1. Percentage of targeted population aware of predicted adverse impacts of climate change, and of appropriate responses 3.2. Modification in behavior of targeted population 4.1. Development sectors' services responsive to evolving needs from changing and variable climate 4.2. Physical infrastructure improved to withstand climate change and variability-induced stress 5. Ecosystem services and natural assets maintained or improved under climate change and variability-induced stress 6.1. Percentage of households and communities having more secure (increased) access to livelihood assets 6.2. Percentage of targeted population with sustained climate-resilient livelihoods 7. Climate change priorities are integrated into national development strategy
Fund Output | Please select from dropdown menu below | Fund Output Indicator | Please select from dropdown menu below | Target at CEO Endorsement | Baseline | Mid-term Results | Terminal Results
Output 1: Risk and vulnerability assessments conducted and updated at a national level Output 2.1: Strengthened capacity of national and regional centres and networks to respond rapidly to extreme weather events Output 2.2: Targeted population groups covered by adequate risk reduction systems Output 3: Targeted population groups participating in adaptation and risk reduction awareness activities Output 4: Vulnerable physical, natural, and social assets strengthened in response to climate change impacts, including variability Output 5: Vulnerable physical, natural, and social assets strengthened in response to climate change impacts, including variability Output 6: Targeted individual and community livelihood strategies strengthened in relation to climate change impacts, including variability Output 7: Improved integration of climate-resilience strategies into country development plans |  | 1.1. No. and type of projects that conduct and update risk and vulnerability assessments 1.2. Development of early warning systems 2.1.1. No. of staff trained to respond to, and mitigate impacts of, climate-related events 2.1.2. Capacity of staff to respond to, and mitigate impacts of, climate-related events from targeted institutions increased 2.2.1. Percentage of population covered by adequate risk-reduction systems 2.2.2. No. of people affected by climate variability 3.1 No. and type of risk reduction actions or strategies introduced at local level 3.2 No. of news outlets in the local press and media that have covered the topic 4.1. No. and type of health or social infrastructure developed or modified to respond to new conditions resulting from climate variability and change (by type) 4. 2. No. of physical assets strengthened or constructed to withstand conditions resulting from climate variability and change (by asset types) 5. No. and type of natural resource assets created, maintained or improved to withstand conditions resulting from climate variability and change (by type of assets) 6.1. No. and type of adaptation assets (physical as well as knowledge) created in support of individualor community-livelihood strategies 6.2. Type of income sources for households generated under climate change scenario 7.1. No., type, and sector of policies introduced or adjusted to address climate change risks 7.2. No. or targeted development strategies with incorporated climate change priorities enforced

## Units for Indicators
Fund Outcome Indicator Units
1. Generation of relevant data, Stakeholders, and Timeliness 2.1. Include both qualitative and quantitative measures of capacity level within targeted institutions 2.2. Number (men and women and other vulnerable groups) 3.1. Use scale from 1 to 5: 5: Fully aware 4: Mostly aware 3: Partially aware 2: Partially not aware 1: Aware of neither predicted adverse impacts of climate change nor of appropriate responses 3.2. Use scale from 1 to 5: 5: All 4: Almost all 3: Half 2: Some 1: None 4.1. Summarize in an overall scale (1-5): 5: Highly responsive (All defined elements ) 4: Mostly responsive (Most defined elements) 3: Moderately responsive (Some defined elements) 2: Partially responsive (Lacks most elements) 1: Non responsive (Lacks all elements ) 4.2. Summarize in an overall scale (1-5): 5: Fully improved 4: Mostly Improved 3: Moderately improved 2: Somewhat improved 1: Not improved 5. Depends on the targeted natural asset: Biological (species): measure through changes in population numbers (dynamics, structure, etc.) Land: measure changes in hectares. Baseline data will be necessary to estimate the change. Supporting indicators baseline and target (as well as contextual information) are needed such as the following: Farmers adopting recommended technologies, Ha. of land improved, Average deforestation rate Etc. Use scale from 1 to 5. 5: Very effective (All elements are present) 4: Effective (Most elements are present) 3: Moderately effective (Some elements are present) 2: Partially effective (Most elements are not present) 1: Ineffective (No elements are present) 6.1. Summarize in an overall scale (1-5): 5: Very high improvement 4: High improvement 3: Moderate improvement 2: Limited improvement 1: No improvement 6.2. Household income by source of livelihood in project area (USD) prior and post project intervention 7. Summarize in an overall scale (1-5). 5: All (Fully integrated) 4: Most 3: Some 2: Most not integrated 1: None
Fund Output Indicator Units
1.1. Number, sector(s) and level(s) of projects or interventions in separate fields of monitoring plan 1.2. Number 2.1.1. Number of staff (male/female) of targeted institutions: a. Obtain baseline information: total number of staff from targeted institutions b. Define target 2.1.2. Number of staff (male/female) of targeted institutions: a. Obtain baseline information: total number of staff from targeted institutions b. Define target: needs to be defined by project proponents 2.2.1. Quantitative: Percentage (includes women – and other vulnerable groups – and men). Qualitative: Adequacy: include direct analysis of major areas; adequacy/effectiveness of systems or analysis of perceptions of populations and institutions. 2.2.2. Number (broken down by gender and, if possible, by vulnerable groups defined in the area of intervention) of people 3.1. Number and type (in separate columns) at local level. 3.2. Number 4.1. Number and type 4. 2. Number and type (entered in separate columns) 5. Number of interventions by type of natural asset and intervention 6.1. Number and type (in separate columns of monitoring plan) 6.2. Income sources per household; description of income source and number of households. 7.1. Number/Sector 7.2. Number; Effectiveness (see previous indicator) through enforcement level.