## Overview
Project Performance Report (PPR)
| Period of Report (Dates) | July 2014 - September 2015
| Project Title: | Enhancing Adaptive Capacity of Communities to Climate Change-related Floods in the North Coast and Islands Region of PNG
| Project Summary: | The impact of climate change-related hazards in the Papua New Guinea (PNG) country has been increasing in intensity and frequency. Further impacts from climate change include the loss of food gardens due to extensive flooding (both in coastal and riverine areas) combined with extended periods of drought. The rising sea level is causing some of PNG’s islands to be gradually submerged. Salt water intrusion is affecting groundwater particularly in the islands and in coastal areas, threatening domestic water supplies and agriculture. With the onset and multitude of climate change impacts, the country’s economy, environment and people are becoming more vulnerable and are at risk of not meeting basic human development needs. Climate change puts at risk the achievement of the goals set out in PNG’s major development plans. Flooding in the coastal areas is one of the most important climate change related hazards in the North Coast and the Islands Region as settlements are usually located in the coasts, particularly the provincial capitals of East Sepik (Wewak), Madang (Madang), Morobe (Lae). Similarly, in the hinterland areas, climate change-related inland flooding is the most pressing hazard with the largest potential for wide-spread damage. The overall objective of this programme is to enhance the adaptive capacity of communities to make informed decisions about and adapt to climate change-driven hazards affecting both coastal and riverine communities in the North Coast and Islands Region of Papua New Guinea. In particular, the programme will focus on enhancing resilience towards occurrences of coastal and inland flooding events. The proposed programme will contribute to several outcomes and outputs listed within the Adaptation Fund Strategic Results Framework.
|  |  | Countries | Project Type: |  | GEF Focal Area: | GEF 4 Focal Areas | GEF 2 / 3 Operational Programme: | Overall Rating of the project in the evaluation by the project evaluator: | GEF-4 Focal Area Strategic Program: | GEF-3 Focal Area Strategic Program:
| Database Number: | PIMS 4452 | Afghanistan | FP | Yes | Biodiversity | 1 | 1 | U | BD-SP1-PA Financing | 1: Arid & semi-arid ecosystems
Implementing Entity (IE) [name]: |  | United Nations Development Programme | Albania | MSP | No | Climate Change Adaptation | 2 | 2 | S | BD-SP2-Marine PA | 2: Coastal, marine & freshwater ecosystems
| Type of IE: | Multilateral | Algeria | EA |  | Climate Change Mitigation | 3 | 3 | MU | BD-SP3-PA Networks | 3: Forest ecosystems
| Country(ies): | Papua New Guinea | Angola |  |  | International Waters | 5 | 5 | Good | BD-SP5-Markets | 13: Conservation and Sustainable Use of Biological Diversity Important to Agriculture
Relevant Geographic Points (i.e. cities, villages, bodies of water): |  | East Sepik, Madang, Morobe, New Ireland and Northern Provinces in Papua New Guinea | Argentina |  |  | Multiple Focal Area |  |  |  | BD-SP7-Invasive Alien Species(IAS) | 6: Promoting the adoption of renewable energy by removing barriers and reducing implementation costs
[8 empty] | CC-SP2- Industrial EE | 8: Waterbody based operational program
| Project Milestones | [6 empty] | CC-SP3-RE,CC-SP4-Biomass | 9: Integrated Land and Water multiple focal area
| Milestone |  | Bahamas | [6 empty] | CC-SP5-Transport | 10: Contaminants based operational program
AFB Approval Date: |  | 2012-03-23
IE-AFB Agreement Signature Date: |  | 2012-03-26 | [6 empty] | CC-SP6-LULUCF | 12: Integrated Ecosystem Management
Start of Project/Programme: |  | 2012-07-26 | [6 empty] | Cross cutting capacity building | 14: Persistent Organic Pollutants
Mid-term Review Date (if planned): |  | Mid-term evaluation is scheduled to be finalized in November 2015
| Terminal Evaluation Date: | Last quarter of 2017
|  | List documents/ reports/ brochures / articles that have been prepared about the project. | Cyprus
|  | National Inception Workshop Report, New Ireland Provincial Stakeholder Consultative Meeting, Community Based Mangrove Planting Handbook, Hazard Assessment report & maps for the 5 provinces, Provincial Inception Workshop reports (New Ireland, Northern, Madang, Morobe, East Sepik), Early warning systems field assessment reports, Communication Strategy, Climate Change Institutional and Capacity Assessment report, Early Warning Systems Inception report, Micro-Grant Agreements progressive reports (World Wide Fund for Nature, Foundation for People & Community Development, World Vision PNG and Adventist Development Relief Agency - PNG), Teaching Guide for Climate Change Adaptation for Lower Primary Schools in PNG, Press coverage - Inception Workshop on Flood Early Warning, Press coverage- Mangrove planting and conservation in East Sepik, Press Website Story on TV Infomercial - El Nino Preparedness (45 Second infomercial broadcasted on National TV for two months), Website story titled 'Local communities of Papua New Guinea are committed to fight climate change' Exposure Photo Story: Take Care of the Mangroves (https://undp-adaptation.exposure.co/take-care-of-the-mangroves). | Czech Republic
List the Website address (URL) of project. |  |  | Democratic People's Republic of Korea
|  | http://www.undp-alm.org/projects/af-papua-new-guinea https://www.facebook.com/www.occd.gov.pg | Democratic Republic of the Congo
Denmark
| Project contacts: |  | Djibouti
Interim Project Manager/Coordinator |  |  | Dominica
| Name: | Rabi Narayan Gaudo | Dominican Republic
| Email: | rabi.narayan.gaudo@undp.org | Ecuador
| Date: | 2015-10-15 | Egypt
| Government DA |  | El Salvador
| Name: | Jacob Ekinye | Equatorial Guinea
| Email: | jacobekinye@gmail.com | Eritrea
| Date: | 2015-10-15 | Estonia
| Implementing Entity |  | Ethiopia
| Name: | Roy Trivedy | Fiji
| Email: | roy.trivedy@one.un.org | Finland
| Date: | 2015-10-15 | France
| Executing Agency |  | Gambia
| Name: | Luanne Losi-Yawingu | Georgia
| Email: | lulan2431@gmail.com | Germany
| Date: | 2015-10-15 | Ghana
| Executing Agency |  | Greece
| Name: | Emmajil Ahai-Bogari | Grenada
| Email: | emmajil.rowanna@gmail.com | Guatemala
| Date: | 2015-10-15 | Guinea
| Executing Agency |  | Guinea Bissau
| Name: | Joycelyn Nagai Muriki | Guyana
| Email: | joycelyn.nagai-muriki@undp.org | Haiti
| Date: | 2015-10-15 | Honduras
Hungary
Iceland
India
Indonesia
Iran (Islamic Republic of)
Iraq
Ireland
Israel
Italy
Jamaica
Japan
Jordan
Kazakhstan
Kenya
Kiribati
Kuwait
Kyrgyzstan
Lao People’s Democratic Republic
Latvia
Lebanon
Lesotho
Liberia
Libyan Arab Jamahiriya
Liechtenstein
Lithuania
Luxembourg
Madagascar
Malawi
Malaysia
Maldives
Mali
Malta
Marshall Islands
Mauritania
Mauritius
Mexico
Micronesia, Federated States of
Monaco
Mongolia
Montenegro
Morocco
Mozambique
Myanmar
Namibia
Nauru
Nepal
Netherlands
New Zealand
Nicaragua
Niger
Nigeria
Norway
Oman
Pakistan
Palau
Panama
Papua New Guinea
Paraguay
Peru
Philippines
Poland
Portugal
Qatar
Republic of Korea
Republic of Moldova
Romania
Russian Federation
Rwanda
Saint Kitts and Nevis
Saint Lucia
Saint Vincent and the Grenadines
Samoa
San Marino
Sao Tome and Principe
Saudi Arabia
Senegal
Serbia
Seychelles
Sierra Leone
Singapore
Slovakia
Slovenia
Solomon Islands
Somalia
South Africa
Spain
Sri Lanka
Sudan
Suriname
Swaziland
Sweden
Switzerland
Syrian Arab Republic
Tajikistan
Thailand
The former Yugoslav Republic of Macedonia
Timor-Leste
Togo
Tonga
Trinidad and Tobago
Tunisia
Turkey
Turkmenistan
Tuvalu
Uganda
Ukraine
United Arab Emirates
United Kingdom of Great Britain and Northern Ireland
United Republic of Tanzania
United States of America
Uruguay
Uzbekistan
Vanuatu
Venezuela, Bolivarian Republic of
Viet Nam
Yemen
Zambia
Zimbabwe

## FinancialData
Financial information: Cumulative from project start to September30, 2015
DISBURSEMENT OF AF GRANT FUNDS
How much of the total AF grant as noted in Project Document plus any project preparation grant has been spent to date?
Estimated cumulative total disbursement as of [30 September 2015] | 3513204.03
Add any comments on AF Grant Funds. (word limit=200) | Significant progress was made in project implementation and disbursement since last PPR reporting period (30 June 2014). Cumulative expenditure (including commitments) accelerated from USD 583,755.02 in June 2014 to 3,513,204.03 in September 2015. The project delivered an additional USD 2,841,083.99 during this reporting period, exceeding the planned expenditure reported for this period in the previous PPR (USD 2,475,000). Accelerated delivery was made possible due to many factors including, but not limited to: appointment of focal person/team by the government to lead and coordinate project efforts with various national and local stakeholders; strategic partnerships with NGOs and CSOs to carry out community based adaptation planning and resilience-building measures; and based on request for support services by the government, UNDP providing procurement support for technical expertise required for the Early Warning System design and implementation. As a result, cumulative project delivery stands at USD 3,513,204.03 with a delivery rate of 58% of the total project budget (US$ 6,018,777). 3 out of 4 tranches have been released by the AF Board to the project so far, with a total of USD 5,074,307.00 already released by the AF Board for the project. The cumulative expenditure as of September 2015 constitutes around 70% of the released funds. It is expected that 85 to 90% of the released funds will be committed for disbursement by end of year 2015. Therefore, the fourth tranche amounting USD 944, 470.00 is requested to be disbursed in October 2015. Furthermore, based on the good practices in Climate Change Impact Assessment carried out by this project, OCCD in partnership with UNDP was able to catalyse co-financing from Australia to scale the methodology to there provinces in PNG.
INVESTMENT INCOME
Amount of annual investment income generated from the Adaptation Fund’s grant
EXPENDITURE DATA
List output and corresponding amount spent for the current reporting period | ITEM / ACTIVITY / ACTION | AMOUNT (USD)
| ACTIVITY 1: Adaptation to Coastal Flooding-related Risks and Hazards for North Coast and Islands Region Communities | 1058782.51
| 1.1 Coastal early warning systems established for observation, data collection and information management and dissemination in the North Coast and Islands Region | 210141.82
| 1.2 Coastal flood preparedness and response plan and systems established in the provinces of the North Coast and Island Region | 274997.7
| 1.3. Support system for community-led mangrove reforestation and conservation projects | 274113.49
| 1.4 Integrated coastal adaptation measures implemented to protect 8 communities in East Sepik Province, Oro Province and New Ireland Province. | 299529.5
| ACTIVITY 2: Adaptation to Inland Flooding-related Risks and Hazards for Riverine Communities in East Sepik, Northern, Madang and Morobe Provinces | 1268697.06
| 2.1 Inland flooding early warning systems established for observation, data collection and information management and dissemination in the provinces of the North Coast and Islands Region | 271248.38
| 2.2 Inland flood preparedness and response plan and systems established in the North Coast provinces | 311049.83
| 2.3 Integrated riverbank protection measures implemented to protect 8 communities in East Sepik Province, Oro Province and Morobe and Madang Provinces | 686398.85
| ACTIVITY 3: Institutional Strengthening to Support Climate and Disaster Resilient Policy Frameworks | 225047.99
| 3.1 Climate change-related risks and resilience from coastal and inland flooding integrated into coastal zone management related polices, legal and planning frameworks at the national and sub-national levels | 109733.31
| 3.2 Policy makers and planners at the national, provincial and district offices, institutions and extension services systemically trained to implement climate-sensitive policies and plans | 115314.68
| ACTIVITY 4: Awareness Raising and Knowledge Management | 71932.3
| 4.1 Lessons learned and best practices generated, captured and distributed to other communities, civil society, policy makers in government and globally through appropriate mechanisms | 25990.46
| 4.2 Climate change awareness and education programmes carried out to build next generations' resilience to climate change | 45941.84
| Activity 5: Project Management and Coordination | 216624.13
| TOTAL | 2841083.99
PLANNED EXPENDITURE SCHEDULE
List outputs planned and corresponding projected cost for the upcoming reporting period | ITEM / ACTIVITY / ACTION | PROJECTED COST | Est. Completion Date
| ACTIVITY 1: Adaptation to Coastal Flooding-related Risks and Hazards for North Coast and Islands Region Communities | 1144980.02 | 2016-09-01
| 1.1 Coastal early warning systems established for observation, data collection and information management and dissemination in the North Coast and Islands Region | 194626.7
| 1.2 Coastal early warning systems established for observation, data collection and information management and dissemination in the North Coast and Islands Region | 97248.3
| 1.3. Support system for community-led mangrove reforestation and conservation projects | 100052.51
| 1.4 Integrated coastal adaptation measures implemented to protect 8 communities in East Sepik Province, Oro Province and New Ireland Province. | 753052.51
| ACTIVITY 2: Adaptation to Inland Flooding-related Risks and Hazards for Riverine Communities in East Sepik, Northern, Madang and Morobe Provinces | 673880.02 | 2016-09-01
| 2.1 Inland flooding early warning systems established for observation, data collection and information management and dissemination in the provinces of the North Coast and Islands Region | 181893.53
| 2.2 Inland flood preparedness and response plan and systems established in the North Coast provinces | 1120.64
| 2.3 Integrated riverbank protection measures implemented to protect 8 communities in East Sepik Province, Oro Province and Morobe and Madang Provinces | 490865.85
| ACTIVITY 3: Institutional Strengthening to Support Climate and Disaster Resilient Policy Frameworks | 260914.92 | 2016-09-01
| 3.1 Climate change-related risks and resilience from coastal and inland flooding integrated into coastal zone management related polices, legal and planning frameworks at the national and sub-national levels | 206485.51
| 3.2 Policy makers and planners at the national, provincial and district offices, institutions and extension services systemically trained to implement climate-sensitive policies and plans | 54429.41
| ACTIVITY 4: Awareness Raising and Knowledge Management | 234800.09 | 2016-09-01
| 4.1 Lessons learned and best practices generated, captured and distributed to other communities, civil society, policy makers in government and globally through appropriate mechanisms | 132310.54
| 4.2 Climate change awareness and education programmes carried out to build next generations' resilience to climate change | 102489.55
| Activity 5: Project Management and Coordination | 190997.92 | 2016-09-01
| TOTAL | 2505572.97
ACTUAL CO-FINANCING (If the MTR or TE have not been undertaken this reporting period, DO NOT report on actual co-financing.)
How much of the total co-financing as committed in the Project Document has actually been realized? | 50000
Estimated cumulative actual co-financing as verified during Mid-term Review (MTR) or Terminal Evaluation (TE).
Add any comments on actual co-financing in particular any issues related to the realization of in-kind, grant, credits, loans, equity, non-grant instruments and other types of co-financing. (word limit=200) | Approximately 70% of the funds released by the AF board has already been committed. It is expected that 85 to 90% of the released funds will be committed by end of year 2015. The fourth tranche amounting USD 944, 470.00 is scheduled to be disbursed in October 2015.

## Procurement (hidden)
PROCUREMENT DATA
Please provide information for all contracts over $2,500 USD
Please provide the number of contracts under $2,500, signed during this reporting period: |  |  |  | 15
LIST OF CONTRACTS
List all contracts related to the project/program with signature dates
Contract Type | Agency / Contracted party | Contract Value/Amount (USD) | Signature Date | Payment to Date | Remaining Balance
Service Contract | Project Manager | 40000 | 2013-10-01 | 40000 | 0
Service Contract | Project Administrative and Financial Assistant | 12785.26 | September 2013 | 12785.26 | 0
Service Contract | Project Associate | 9600 | 2015-05-01 | 3600 | 6000
Individual Contractor | Communications Specialist | 4744.53 | July 2014 | 4744.53 | 0
Individual Contractor | Capacity Assessment Consultant - Institutional Specialist | 85100 | 2015-02-01 | 85100 | 0
Individual Contractor | Capacity Assessment Consultant - Technical Specialist | 79622 | 2015-02-01 | 79622 | 0
Micro-Capital Grant Agreement | World Wildlife Fund for Nature | 150000 | July 2014 | 45000 | 105000
Micro-Capital Grant Agreement | Foundation for People and Community Development | 75000 | July 2014 | 60000 | 15000
Micro-Capital Grant Agreement | World Vision - PNG | 150000 | 2015-05-01 | 45000 | 105000
Micro-Capital Grant Agreement | Adventist Development and Relief Agency -PNG | 300000 | 2015-04-01 | 90000 | 210000
Contractual Services-Companies | RMSI - Hazard Assessment | 136780 | 2014-02-01 | 136780 | 0
Contractual Services-Companies | Antea Belgium - Early Warning System | 417181 | 2015-03-01 | 83436.15 | 333744.85
Contractual Services-Companies | Antea Belgium - Vulnerability Needs Assessment | 980605 | 2015-04-01 | 196121 | 784484
BIDS
List all bids for each contact signed with date of open call and winning bid
CONTRACT & Procurement Method | Submitted Bids | Bid Amount (USD) | Winning Bid Amount (USD) | Selection Justification for the Winner
Hazard Assessment for target provinces of East Sepik, Madang, Morobe, Northern and New Ireland - International Contract (Institutional) | RMSI | 150000 | 136780 | Minimal financial proposal with qualification and experiences of the proponent. The country office bargained with the bid winner and reduced the bid amount to 136,780.00.
| Asian Institute of Technology, Thailand | 220050
| Sayers and Partners LLP, United Kingdom | No bid opening
| Regional Integrated Multi-hazard Early Warning System | 292770
Assessment of Early Warning Systems (EWS) for inland and coastal flooding- East Sepik, Madang, Morobe, Northern and New Ireland Provinces, Papua New Guinea International Contract (Institutional) September 2014 | Antea Belgium | 417181 | 417181 | Combined weighting of Technical (70%) and Financial (30%) proposals with minimum passing score of 70%
| Ambiental/UK | 337896
| RMSI/India | Proposal did not pass technical evaluation
| TARU/India | Proposal did not pass technical evaluation
| IMBROS/UK | Proposal did not pass technical evaluation
Climate Risk and Vulnerability Needs Assessment for Morobe, East Sepik, Madang, Northern and New Ireland Provinces of Papua New Guinea - International Contract (Institutional); September 14 | PT. Hatfield Indonesia | Proposal did not pass technical evaluation | 980605 | Combined weighting of Technical (70%) and Financial (30%) proposals with minimum passing score of 70%
| RMSI | Proposal did not pass technical evaluation
| GHD Pty Ltd | 1572096
| Finnish Overseas Consultant | Proposal did not pass technical evaluation
| Cardno (PNG) Ltd | Proposal did not pass technical evaluation
| Antea Belgium | 980605

## Risk Assesment
RISK ASSESMENT
IDENTIFIED RISKS
List all Risks identified in project preparation phase and what steps are being taken to mitigate them
Identified Risk | Current Status | Steps Taken to Mitigate Risk
Insufficient collaboration between project implementation partners and stakeholders | M | Regular contact is maintained with project partners and stakeholders. Terms of reference for various activities under the project are prepared in consolation with the project partners/stakeholders. Project partners and stakeholders are regularly updated on the progress under the project. The project Steering Committee comprising of all the relevant stakeholders including representatives from the five pilot provinces meets once in a year to review the project and guide effective implementation of project activities. OCCD, as the implementing partner, hosts regular meetings with the project management team and UNDP and other key stakeholders on a monthly basis. At the provincial level, the Provincial Climate Change Committee, headed by the provincial administrator and comprising of key provincial bodies is the key coordination mechanism for the project.
Weak cooperation by communities at proposed sites | M | Community level activities are being implemented by NGOs who already have a field presence in the targeted provinces. Awareness raising about climate change and its impacts is one of the major components of the community based approach which ensures better cooperation and engagement of the local communities in the implementation of the project. A climate adaptation education and awareness initiative is being prepared that will not only collate existing information and awareness materials on CCA but also design and produce new materials to fill in key information gaps. One of the other objective of the project is to capture and produce stories from site where CCA projects are currently being implemented.
Land use disputes within the communities affect implementation of project activities and plans | L | The project does not involve any activity that requires land acquisition. At this stage it is envisaged that flood gauges will be installed in some specific sites that requires community consultation to avoid vandalism of the equipment proposed to be installed. However, before the installation of equipment adequate awareness will be conducted to avoid disputes. The NGOs involved in community based climate adaptation projects have undertaken a series of awareness campaigns to sensitise the communities about the project goals and related activities to ensure that communities are well receptive of the project initiatives at that level. The mangrove sites are selected with due consultation with local communities and authorities to avoid disputes related to land ownership.
Limited human resources in PNG’s national and provincial agencies to adequately support to the activities and ensure the sustainability of the adaptation measures | M | A capacity assessment of key government agencies and institutions at the national and provincial level was conducted in the first quarter of 2015 to analyse their capacity development needs in relation to their CCA roles and responsibilities. The assessment report identifies capacity gaps at different levels and recommends capacity building actions/plans. A set of trainings are being planned in consolations with relevant stakeholders and partners in order to ensure that there is adequate capacity to sustain CCA initiatives at different levels. Competent technical experts and agencies are hired through global tender processes to provide high quality technical services to the project.
A series of unusually adverse climatic conditions impacts the adaptation measures being implemented, or weakens the interest of key stakeholders to address adaptation issues. | L | The adverse impact of climate related disasters has resulted in increased awareness and demand for disaster preparedness/CCA. . A severe dry spell induced by the strongest El Nino on record has impacted many provinces in PNG. This event has prompted the need for putting in place disaster preparedness and climate change adaptation measures at different levels. The project has actually enhanced the interest of key stakeholders in adaptation issues.
The best practices and adaptation measures adopted are not gender sensitive – i.e. they increase inequity between men and women or change the social roles of men and women in a way that reduces self reliance. | M | Community based disaster risk reduction and climate change adaptation projects are being implemented through NGOs that includes identification of hazards, vulnerabilities and risks and development and implementation of risk reduction/adaptation strategies in a participatory manner. The consultations at the community level involves both men and women and other vulnerable groups thus ensuring that the views of everyone is incorporated in the planning and decision making processes and the plans and strategies formulated under the project are gender sensitive. The Early Warning Assessment and Vulnerability Needs Assessment studies employ a gender-sensitive approach to understand issues affective women at different levels. The findings will inform designing of gender sensitive recommendations for improvement of early warning systems at different levels.
The selection of pilot sites does not follow the established criteria and is derailed due to political processes and influences. | L | This risk has been minimized as pilot sites were selected based on criteria established by the Project Document as well as through site visits, community consultations and feasibility studies. Site visits were made in order to verify the flood vulnerability of the pilot sites in order to establish project related to flood early warning and mangrove regeneration/conservation. Site visits also minimizes the risk of implementation of activities that are not feasible for a particular location. For example one of the proposed sites for mangrove conservation in East Sepik was omitted after a site visit that confirmed that the area is not suitable for mangrove planting. On the other hand site visits confirmed vulnerability of communities to flooding where community based climate adaptation projects are now being implemented.
The government is not supportive, politically and financially, to a cross-sectoral and integrated approach to the management of climate risks and opportunities. | L | The project is being implemented through Provincial Climate Change Committees established at the provincial level and Project Steering Committee established at the National level comprising of relevant govt departments and NGOs to ensure a systematic and all of the govt. approach to the issue of climate change. The project is led by OCCD as an institution rather than individuals within the institution. In 2015, despite to the change of the Director of Climate Change, due to the fact that OCCD as an institution and had appointed a team of focal points within their department for this project, the project experienced minimal delays in implementation The PMU established at the National level and Project assistants recruited at the provincial level provide all the necessary support for the of the project. Besides, the activities are funded through the project limiting risks of non-implementation due to lack of funding support from Government.
Critical Risks Affecting Progress (Not identified at project design)
Identify Risks with a 50% or > likelihood of affecting progress of project
Identified Risk | Current Status | Steps Taken to Mitigate Risk
The project is facing stiff competition from the flourishing resource extractive industry in attracting the best candidates for the full-time project positions (National Program Coordinator - NPC, Admin and Finance Specialist and Technical Specialist). Qualified professionals are in short supply relative to demand from all sectors. | M | Based on request for support expressed by the PNG Government / OCCD, UNDP appointed an interim project manager to oversee the project since the resignation of the project manager in October 2014. A full time project manager is currently being recruited. Project Administrative & Finance associate and driver/clerk were recruited recently to ensure timely and effective implementation of the project. a full time project associate has been working with project since beginning of 2015. Further staffing arrangements such as the appointment of project associate, will be explored in the next reporting period.
Budget cuts hindering OCCD's capacity to provide adequate support for the implementation of the project. | M | All levels of government within PNG including OCCD are currently experiencing severe budgetary constraints due to reduction in revenue caused by falling commodity prices. This has reduced the operation capacity of OCCD to deliver its projects and programs. The project is less likely to be affected by the budget cuts as the project activities are funded by the Adaptation Fund. In the next reporting period, it would be necessary for OCCD and key stakeholders to initiate discussions on sustainability in light of funding constraints faced throughout the government.
The recent policy and legislative changes may create ambiguity with regard to OCCD's broader roles and responsibilities in climate change thus affecting the project implementation. | M | A new Climate Change Act (July 2015) passed by PNG parliament paved the way to elevate the status of OCCD from an office t to an authority. While there are still lack of clarity with regard to how OCCD would take on its new mandate which requires major structural changes within the Office, the project is also less likely to be affected by the recent structural changes as the project is well defined and already into the third year of implementation.
Procurement policies/guidelines under UNDP National Implementation Modality (NIM) with country office support is likely to hinder implementation on the ground | M | A sizeable part of the project is being implemented through contracts with reputable contractors and consultants who were selected through global tendering processes led by UNDP based on request from the Government. Community based activities are implemented through reputable NGOs through Micro Grant Agreements that ensures speedy implementation of the project as the funds are managed by NGOs under their own implementation modalities. The grant agreements are reviewed and endorsed by the project steering committee and provides an oversight role to ensure effective implementation of the projects. In addition, as the AF Multilateral Implementing Entity, UNDP provides project oversights and quality assurance for the project implementation.
Risk Measures: Were there any risk mitigation measures employed during the current reporting period? If so, were risks reduced? If not, why were these risks not reduced?
Add any comments relevant to risk mitigation (word limit = 500)
All the above risk mitigation measures are in place to ensure that project risks are minimized.

## Rating
RATING ON IMPLEMENTATION PROGRESS
For rating definitions please see bottom of page.
| Progress on Key Milestones |  | Expected Progress |  | Progress to Date | Rating
Project Manager/Coordinator: | Designing of a end-to-end early warning system for coastal and inland flooding |  | Analysis of resource requirements, protocols for forecasting, monitoring and dissemination of warning and various options for effective dissemination of disaster warnings |  | One of the key components of the projects is to establish inland and coastal flood Early Warning Systems (EWS) in the selected provinces of North Coast and Island regions. In the above context, Antea Belgium, a reputed agency with relevant experiences was selected through a global tender to assess the EWS system. An inception workshop was conducted on 23rd of April 2015 to gather and analyse readily available data based on stakeholder interviews and relevant secondary sources to assess the current EWS situation in PNG and inform the implementation of the next phases (review of available information regarding coastal flood hazard, preliminary mapping of policies, regulations and institutions, and the existing systems at national and provincial levels).Antea Team has visited pilot provinces following the inception workshop and held consultation meetings with key stakeholders and conducted site visits. The report is expected to be completed in November 2015. The key deliverables of the project include, mapping of EWS agencies and departments for coastal and inland flooding. mapping of EWS projects/programs for coastal and inland flooding, analysis of existing protocols/mechanisms for monitoring, forecasting and dissemination of warning for inland and coastal flooding, analysis with clear identification of gaps, improvements and opportunities for enhancing EWS for inland and coastal flooding including the identification of regional and international information that can be effectively combined with local observation, analysis outlining the capacity and resource requirement (both hardware and software with detailed specifications) for relevant agencies and departments for enhancement of data observation, monitoring and forecasting and dissemination of warning for inland and coastal flooding hazards. This will include identification of equipment which can be rehabilitated, as well as cost effective analysis of investment in different levels of technological complexity, including the costs of operating and maintaining equipment, a detailed analysis of human resources capacity covering technical expertise, data and information processing and management, and the ability to interpret raw data and information to useable forms, analysis outlining various options for effective early warning dissemination to the last mile and recommendations outlining required improvements of EWS at the provincial and sub-provincial levels and a set of actions with indicators (milestones) and corresponding resources requirements that need to be undertaken to enhance EWS for inland and coastal flooding in PNG. | Satisfactory
| Integrated community based climate change adaptation/risk reduction measures implemented in project communities |  | Adaptation measures planned and implemented in selected vulnerable communities. |  | Community based disaster risk reduction (DRR) / climate change adaptation (CCA) activities have been initiated in 18 communities in three pilot provinces including Madang, Morobe and New Ireland. In Madang 2 DRR & CCA training courses were conducted for community members in 5 target communities involving approximately 900 participants half of which were women . 5 community based disaster risk reduction/climate change adaptions plans have been completed in consultation with relevant stakeholders. In Morobe and New Ireland Provinces start-up meetings were conducted in 8 target communities and relevant stakeholders including Lae district, Provincial Disaster & Emergency Services and the Office of Climate Change and Development. The logical frame work of the community based adaptation/risk reduction project was briefly shared with the respective communities highlighting how different stakeholders can contribute towards making communities more safer and resilient. The main activities highlighted during this meeting was on disaster and climate change adaptations, mitigation initiatives the hazards and risks assessments, linking indigenous early warning system and the baseline survey. | Marginally Satisfactory
| Vulnerable communities exposed to climate change awareness raising activities. |  | 75% of the population in pilot communities are exposed to awareness raising activities and materials. |  | 10 community CCA and DRR awareness have been conducted in 4 schools covered. A total, of 353 adults have actively participated in the awareness, with 202 males and 166 females. A total of 649 students have also, participated in DRR and CCA awareness activities in the 4 schools with 324 boys and 271 girls (under the age of 15). The 4 schools are WA put, Koroba and Dumpu Primary school in Using LLG and Karani Primary School in Bundi LLG. In Morobe and New Ireland Provinces awareness materials on various hazards are being developed in preparation for the disaster and climate change awareness training in target communities. Disaster risk management and climate-change terminologies are being translated to common language with pictorial illustrations for community to best understand and support the development of community disaster response and climate-change adaptation plan .
| Capacity development in climate change adaptation |  | Relevant stakeholders at different levels systematically training to implement climate-sensitive policies and plans |  | For the first time a capacity assessment has been completed for Climate change adaptation in PNG. Around 100 participants from national and sub-national level participated in the capacity assessment study. This report summarizes the key findings of the capacity gaps for climate change adaptation at the National and provincial level. The report presents desk review and scoping mission findings as well as a summary of the key findings from the self-assessment questionnaires, interviews and focus groups and a Capacity Development Action plan outlining specific a work plan of actions and actors to undertake the recommendations as well as indicative time line and budget. A capacity building plan is currently being prepared for stakeholders at different levels in line with the recommendations of the capacity assessment report. The assessment currently undertaken by Antea group also focuses on capacity gaps at different levels in relation to generation and dissemination of flood early warning. Some of the key trainings planned for next year includes a) climate change risks, climate trends, implications of seasonal variability, and medium and long term climate changes; b) climate change adaptation options in key areas (agriculture, infrastructure, health and sea level rise defence) c)Training on planning and budgeting for climate change adaptation at the provincial and district levels d) Climate change sensitive development plans at the provincial and district levels | Satisfactory
[5 empty] | Overall Rating | Satisfactory
Please Provide the Name and Contact information of person(s) responsible for completing the Rating section
| Name: | Rabi Narayan Gaudo
| Email: | rabi.narayan.gaudo@undp.org
Please justify your rating. Outline the positive and negative progress made by the project since it started. Provide specific recommendations for next steps. . (word limit=500)
Some of the key activities mentioned above have progressed well. Assessment of the flood and coastal early warning system which is progressing well will provide necessary recommendations for establishment of an effective EWS system. The EWS assessment will be conducted at different levels from National to community level to understand the analysis of resource requirements, protocols for forecasting, monitoring and dissemination of warning and various options for effective dissemination. The assessment will inform procurement of hardware and software for setting up an EWS system for inland and coastal flooding in PNG. Very good progress has been made in relation to implementation of community-led adaptation planning. The project is working in 18 communities in three provinces through various partners to enhance resilience of Local Level Government bodies and communities to climate induced inland and coastal flooding and other hazards through development of Community Disaster Response Plan and capacitated Community Disaster Management Committee and Task Forces. The community based projects also aim to strengthen the local/indigenous early warning systems for flooding. Raising awareness among vulnerable communities is a key component of the community interventions and approximately 5000 people have been reached so far through various awareness raising activities. A capacity assessment has been completed and based on the recommendations of the assessment a capacity development plan is being developed which will be implemented in the next phase of the project. The project activities were pushed back due to initial delays however, the project has made good progress in the year 2015. Some of the key challenges include finding local partners for implementation of community based activities, lack of data for various studies being conducted under the project, lack of buy-in from sub-national partners in relation to various assessments being conducted. The next phase of the program will focus on procurement of EWS equipment, implementation of the capacity building plan, flood preparedness planning at the provincial level, mangrove conservation /planting and climate adaptation education and awareness.
| Progress on Key Milestones |  | Expected Progress |  | Progress to Date | Rating
Implementing Agency | Establishment of a fully functional Project Management Unit |  | PMU established and fully and fully functional |  | The project supported the establishment of a project management unit within the Office of Climate Change and Development in May. The PMU provides all necessary support for the effective implementation of the project. Climate change offices and focal points for climate change in the five pilot provinces have been supported through the project and . Essential office equipment including laptop computers, stationery, internet dongles and prepaid credits were provided. 5 Project Assistants were required to support the implementation of the in the five pilot provinces. | Satisfactory
| Stakeholder engagement in key Activities |  | Relevant stakeholders are fully engaged in the implementation of the project |  | Key stakeholders participated in the relevant project activities. The project successfully involved National Weather Service, Conservation and Environmental Project Authority, National Disaster Centre, Department of National Planning , Department of Treasury and provincial authorities from five provinces through stakeholder consultations and project related workshops. Regular project updates were provided to Technical Working Group of Adaptation which comprises of government and non-government agencies working in the area of climate change. | Satisfactory
| Awareness raising program in schools and training institutions |  | School students in the target communities are exposed to CCA/DRR |  | 10awareness campaigns were conducted in 4 schools covered. A total of 649 students were exposed to DRR/CCA awareness activities that includes 324 boys and 271 girls. The 4 schools are Waput, Koroba and Dumpu Primary school in Usino LLG and Karani Primary School in Bundi LLG. Awareness on flooding, disaster preparedness and community based adaptation strategy was conducted in six schools along the tributaries of Ramu River in Madang district that covered approximately 500 students. A teachers guide on Climate Change Adaptation was developed for lower primary schools. | Satisfactory
[5 empty] | Overall Rating | Satisfactory
Please Provide the Name and Contact information of person(s) responsible for completing the Rating section
| Name: | Luanne Losi
| Email: | luanne.losi@occd.gov.pg
| Progress on Key Milestones |  | Expected Progress |  | Progress to Date | Rating
Other | Disaster Preparedness and response plans developed for three provinces |  | Disaster preparedness plans completed in three provinces |  | The hazard assessment for inland and coastal flooding has been completed. The report was finalized following a stakeholder validation workshop, which would inform flood preparedness and response plans in the pilot provinces. Two provinces (new Ireland Province and East Sepik) have been selected for the development of flood preparedness and response plans. A TOR was finalized to hire a international consultant to work with provincial counterparts in the development of the plan. The procurement for the consultant is currently underway. | Satisfactory
| Mangrove rehabilitation/conservation in vulnerable communities |  | Communities sensitize about the importance of mangrove conservation and mangrove nurseries established |  | Identification of potential nursery and suppliers for mangrove rehabilitation is being done in New Ireland Province. The target is to plant 8,000 seedlings across 35 hectares in New Ireland province. World Wide for Nature under the project titled “Raising Awareness and Enhancing Community Resilience to Climate Change and Impacts affecting Coastal and Riverine Communities in Madang Province "has initiated awareness raising and training on the importance of mangrove conservation. The awareness program reached 500 villagers. Trainings have also been conducted on best practices for mangrove and conservation as well as establishing mangrove nurseries. 6000 mangrove seedlings have been collected by WWF for planting. A grant agreement is negotiated with World Conservation Society to implement mangrove planting/conservation project in New Ireland province. The project will cover six communities and aims to plant/conserve mangrove in 30 hectares. | Satisfactory
| Capacity strengthened at different levels for climate risk sensitive planning |  | Climate vulnerability and risk data available to relevant stakeholders for planning purpose |  | Antea Belgium was contracted through global procurement to undertake the Climate Risk, Vulnerability and Need Assessment (VNA) in the five pilot provinces to understand the level of exposure to various climate risks. An inception workshop was conducted on 23rd of June to gather and analyse readily available data including initial screening of flood prone zones & key stakeholder groups as provided by the client and relevant secondary sources. The objective was to quickly take stock of the current situation regarding Climate Hazards in the five provinces and subsequently inform the implementation of the following phases. Following the workshop Antea experts have undertaken assessments in pilot provinces that involves extensive community based research . Once completed the report will guide the pilot provinces in climate risk sensitive planning as well as provide a realistic and scalable example of how VNA assessment may be conducted for the rest of PNG at the subnational level. The report is expected to be completed by first quarter of 2016. | Satisfactory
[5 empty] | Overall Rating | Satisfactory
Please Provide the Name and Contact information of person(s) responsible for completing the Rating section
| Name: | Gwen Maru; Shoko Takemoto
| Email: |  |  |  | gwen.maru@undp.org shoko.takemoto@undp.org
| Please justify your rating and address the following points: 1. Indicate trends, both positive and negative, in achievement of outcomes as per the project indicators. 2. Detail critical risks that have affected progress. 3. Outline response to MTR undertaken this reporting period. 4. Outline action plan to address projects with a rating of HU, U or MU. Please keep your input to 1200 words |  | The project has made significant project in this reporting period and therefore is rated “satisfactory.” Some key components of the project progressed well as described below. Flooding has been a recurrent disaster in Papua New Guinea however the understanding of the extent of the issue was lacking. The assessment of coastal and inland flooding risks has now provided the necessary inputs for the development of disaster preparedness response plans. An international consultant is being recruited to assist the provincial authorities to assist the provinces in the development of the plans. Community led mangrove conservation projects have progressed well with 10 communities in two provinces currently being targeted under the project. The number of credible partners at the provincial level to implement project activities is limited that has resulted in slow progress of the project. However, new partners have been identified and their proposals are currently being reviewed by PMU which will help expedite mangrove conservation/rehabilitation projects on ground. Integration of climate risk information into planning and budgeting is a vital component of the project. Once completed, the Climate Hazard, Vulnerability and Risk Assessment study will provide necessary information with regard to the projected climate risks on different time scales and recommendations to adapt to the projected climate changes. This will lead to climate sensitive policy and planning. 1. Trends As described above, key positive trend in this reporting period include the variety and number of partnership it established. The project was able to overcome implementation challenges and accelerate delivery in all components through building strategic partnerships. These included partnering with CSOs and NGOs to carry out community-based CCA and DRM planning and implementation of community-based adaptation measures; creating a multi-sectoral working group to design what a flood EWS for PNG that is scientifically rigorous while simultaneously practical and useful in flood-prone communities; scaling of VNA assessments to other provinces through co-financing agreements with other development partners; and strengthened partnership and network between the national CCA and DRM stakeholders with the provincial government through appointment of provincial project focal points in all pilot sites. 2. Risks Similar to other reporting year, and particular to the geopolitical context of PNG, negative trends and risks that the project faced included: frequent natural disasters such as drought, earthquakes and floods that influence work progress due to availability of national stakeholders as well as make field work difficult due to logistics and/or safety issues. In this reporting period, PNG faced severe drought and frost emergencies (from August 2015), earthquakes (magnitude 7.2 in May 2015) and flash flood incidences (February/ March 2015); change of government structure and focal points related to climate change, etc. The project responded to these risks through effective adaptive management to ensure that the CCA and DRM resilience-building objectives and initiatives meet both long-term capacity enhancements and investments as well as address urgent and immediate needs. Furthermore, the project ensured good working relationship with the government and other key stakeholders at various levels – including political, technical, and community levels. 3. Mid-Term Review The project MTR is delayed but ongoing and expected to be completed by end of November 2015. With more than 60% of project resources expensed and a number of key activities ongoing, the project expects to look to the MTR to identify ways in which project implementation can be enhanced and improved so that project can ensure to achieve maximum and sustainable impacts in the remaining months and years.
Rating Definitions
|  |  | Highly Satisfactory (HS) | Project actions/activities planned for current reporting period are progressing on track or exceeding expectations to achieve all major outcomes/outputs for given reporting period, without major shortcomings. The project can be presented as “good practice”.
|  |  | Satisfactory (S) | Project actions/activities planned for current reporting period are progressing on track to achieve most of its major outcomes/outputs with only minor shortcomings.
|  |  | Marginally Satisfactory (MS) | Project actions/activities planned for current reporting period are progressing on track to achieve most major relevant outcomes/outputs, but with either significant shortcomings or modest overall relevance.
|  |  | Marginally Unsatisfactory (MU) | Project actions/activities planned for current reporting period are not progressing on track to achieve major outcomes/outputs with major shortcomings or is expected to achieve only some of its major outcomes/outputs.
|  |  | Unsatisfactory (U) | Project actions/activities planned for current reporting period are not progressing on track to achieve most of its major outcomes/outputs.
|  |  | Highly Unsatisfactory (U) | Project actions/activities planned for current reporting period are not on track and shows that it is failing to achieve, and is not expected to achieve, any of its outcomes/outputs.
Koroba Assas—Community

## Project Indicators
PROJECT Indicators
Please provide all indicators being tracked for the project as outlined in the project document
Type of Indicator (indicators towards Objectives, Outcomes, etc.…)
Type of Indicator | Indicator | Baseline | Progress since inception | Target for Project End
Objective - Strengthened ability of coastal and riverine communities in Papua New Guinea to make informed decisions about and to undertake concrete actions to adapt to climate change-driven hazards affecting their specific locations | 1. Number of risk-exposed coastal communities protected through adaptation measures | In the current scenario, risk-exposed communities are to a large extent unable to adapt to climate change due to a lack of resources, capacity, knowledge and the necessary support through provincial and national institutions as well as policy frameworks. | 4 costal communities have been selected for the implementation of the coastal adaptation measures. Through a community based approach climate hazards, vulnerabilities and risks are being mapped in order to develop appropriate mitigation planning. The consultation process involves women and other vulnerable sections of the communities to ensure that their views are incorporated into the planning and decision making process. The PMU is working with World Vision International to identify and implement coastal risk reduction/adaptation measures in additional four communities . | By the end of the project at least 8 coastal communities are protected through adaptation measures against coastal flooding scenarios, with attention to the special concerns of women as participants and beneficiaries.
| 2. Number of risk-exposed riverine communities protected through adaptation measures |  | 14 riverine communities have been identified for the implementation of the river protection measures. Through a community based approach climate hazards, vulnerabilities and risks are being mapped in order to develop appropriate mitigation planning. The consultation process involves women and other vulnerable sections of the communities to ensure that their views are incorporated into the planning and decision making process. | Eight (8) riverine communities are protected through adaptation measures against inland flooding, with attention to the special concerns of women as participants and beneficiaries
| 3. Number of provinces with improved climate-related planning and policy frameworks to increase resilience |  | A detailed analysis of the climate hazards, vulnerabilities and risks is being undertaken for the five pilot provinces. The recommendations of the report will form an important component of all disaster risk management and climate change adaptation policies and plans (with budgets) in the Provinces. The assessment report will be available end of 2015. | At the end of the programme, adaptation to climate change is managed, monitored and planned at the provincial level in the targeted provinces and supported by a framework of policies and plans including disaster preparedness and response plans, coastal zone management plans.
Outcome 1 - Reduced exposure and increased adaptive capacity of coastal communities to flood-related risks and hazards in 8 communities and three cities of the 11 provinces of the North Coast and Islands Region. | 1. Number of communities benefitting from improved protection from coastal floods | The vast majority of communities exposed to coastal flooding is inadequately equipped with resources, capacity and support to adapt to the heightened risks from climate change The total number of inhabitants in the 8 target coastal communities that are vulnerable to coastal flooding is estimated at 16,000. An additional population of 120,000 in the cities of Lae, Wewak and Madang will benefit from the programme’s implementation | 10 coastal communities are benefitting from various community-based climate change adaptation interventions. While in 4 coastal villages community based risk assessments are being conducted to inform adaptation and preparedness planning 6 coastal communities are covered under the mangrove conservation projects. Awareness raising on CCA/DRR issues is a vital component of the community work that is being conducted under the project. | By the end of the project, 8 communities are protected from coastal flooding through adaptation measures that were put in place in a community-led way with the agreements/compacts agreed on by communities to preserve the mangrove forests
| 2. Number of EWS and voluntary weather stations in operation 3. Number of communities covered by the improved coastal warning system and weather information | There is lack of equipment and capacity of the PNGNWS, hence, the forecasting of disasters and extreme weather events is severely limited. | There exists substantial gaps in flood early warning. In this context a study has been conducted to inform the design of a functional EWS for PNG. Based on analysis of resource requirements, protocols for forecasting, monitoring and dissemination of warning and various options for effective dissemination of early warnings. The assessment will inform the comprehensive design of the EWS system, including the details of the procurement of the hardware and software to set up an EWS system for inland and coastal flooding in PNG including in the pilot communities. | At least 6 tidal gauges and at least 6 AWS and 10 voluntary weather stations established at strategic locations, meet WMO standards and contribute to the monitoring and early warning system. One AWS will have been installed in each target 8 communities.
| 4. Number of provinces with comprehensive disaster prepared ness and response plans for coastal flooding in place | The provincial and national-level disaster management frameworks are evidently inadequate to address the risks | Procurement of consultant for the development of disaster preparedness and response plans for coastal flooding has been completed. Consultations for the preparations of the disaster preparedness and response plan to commence in October 2015 for East Sepik and New Ireland Provinces in consultations with key stakeholders and respective provincial disaster office. Disaster preparedness and response plans for additional two provinces will be completed in 2016. | At least four provinces will have a comprehensive disaster preparedness and response plans for coastal flooding in place and will have conducted dry run tests.
| 5. Number of provincial capitals with assessed engineering measures for adaptation | No effort has been done on this aspect in the target provincial capitals. | This activity is yet to be implemented. Proposed next steps include: Consultation with provinces (esp works department and other industries) for the relevance of this study in Madang, Wewak and Lae and revise targets if necessary to 2 provinces (to be discussed at the Project Steering Committee Meeting). Review ToRs of similar studies in PNG (through ADB/World Bank) and develop a TOR to conduct the assessment. | For three provincial capitals of Lae, Madang and Wewak suitable coastal engineering measures for adaptation are identified and addressed through respective planning and funding.
| Number of community-led mangrove projects benefitting from support system for mangrove projects | Community-based mangrove projects are undertaken ad-hoc and largely without sufficient expertise and support | Training on rehabilitation/conservation of mangrove and development of nurseries has been initiated in Madang facilitated by WWF in 2014 that covers 6 communities. Mangrove programme in New Ireland (Djaul & New Handover) has recently imitated by ADRA in 4 communities that includes mangrove planting in 35 hectares. Proposals from NGOs are under consideration to scale of the activities in other places covering 6 additional communities. | 33 community-led mangrove conservation and/or reforestation projects, covering about 100 hectares are supported through the support network and nurseries
| Number of mangrove nurseries established and sustainably operating | None | A trainers guidebook on community based mangrove conservation and rehabilitation has been developed, printed and disseminated widely among relevant stakeholders including community members and relevant government departments . 6000 mangrove seedlings have been collected and three mangrove nurseries have been built to raise the seedlings. | Eight (8) regional nurseries operate sustainably supplying the requirements of the target sites and replication areas
| Resources allocated for continued operations of the nurseries |  | Two NGOs namely World Society and MICAD have submitted proposals for mangrove conservation work in New Ireland Province and East Sepik Provinces submitted proposals for review. | Before the end of the project, sufficient resources are allocated by government for the continued operations of the nurseries beyond the life of the project.
Outcome 2 - Reduced exposure and increased adaptive capacity of 8 riverine communities in 4 provinces | Number of communities benefitting from improved protection from inland flooding | The vast majority of communities exposed to inland flooding risk is inadequately equipped with resources, capacity and support to adapt to the changed scenario The total number of inhabitants in the 8 target riverine communities that are vulnerable to coastal flooding is estimated at a minimum 32000 people. | 14 costal communities have been selected for the implementation of the inland flooding adaptation measures. Through a community based approach climate hazards, vulnerabilities and risks are being mapped in order to develop appropriate mitigation planning. The consultation process involves women and other vulnerable sections of the communities to ensure that their views are incorporated into the planning and decision making process. | By the end of the project, eight communities are protected from inland flooding through adaptation measures that were put in place in a community-led way.
| Number of communities covered by the improved warning system and weather information Number of EWS and voluntary weather stations in operation | Disaster preparedness is limited by the lack of and state of facilities and plans There is lack of equipment and capacity of the PNGNWS is weak, hence the forecasting of disasters and weather patterns is limited. | An assessment of EWS systems at different level is currently underway. The assessment will provide specifications of EWS equipment to be procured and installed at different locations. The EWS assessment kicked off with an inception workshop in order to consult with key stakeholders. The report will be ready at the end of this year. | At least 6 AWS and at least 20 voluntary weather stations established at strategic locations, meet WMO standards and contribute to the monitoring and early warning system. One AWS will have been installed in each target 8 communities.
| Number of provinces with comprehensive disaster preparedness and response plan for inland flooding | The provincial and national-level disaster management frameworks are evidently inadequate | Procurement of consultant for the development of disaster preparedness and response plan and standard operating procedures has been initiated. The development of the plans will commence in October 2015 for East Sepik and New Ireland Provinces in consultation with key stakeholders and respective provincial disaster management offices. | At least four provinces will have a comprehensive disaster preparedness and response plan for inland flooding in place and will have conducted dry run tests.
Outcome 3 - Strengthened institutional capacity at national and sub-national levels to integrate climate change-related risks into sectoral policies and management practices | Number of national and provincial level policies, strategies, plans and coordinating mechanisms reviewed and incorporating resilience to climate change | Adaptation to the changed climate scenario of the present and future is inadequately considered in national and provincial level policies and planning frameworks | A detailed analysis of the climate hazards, vulnerabilities and risks is being undertaken for the five pilot provinces. The recommendations of the report will inform climate sensitive planning at provincial level and help develop appropriate strategies for climate change adaptation. | At the end of the project, all major development plans in the targeted provinces reflect climate change and adaptation considerations and coastal zone management policies are developed for the most populated areas (especially Wewak, Kavieng, Madang, Lae)
| Number of provincial and national-level officers trained in climate adaptation planning and implementation | At the provincial level the lack of resources, capacity and in some cases basic management mechanisms/plans is evident | A capacity building assessment has been completed to inform a capacity development plan through series of trainings at different levels. A training plan has been developed to train stakeholders at different levels in climate risk management, climate sensitive planning and budgeting. 2 DRR & CCA refresher’s training courses were conducted to members of WDMCs in 5 target communities in June & July 2015 covering 50 participants half of which were women. | At the provincial level, there is a strong link between all climate change officers/focal points and the communities in their respective provinces and the officers are equipped with the resources and capacity to identify and manage adaptation needs in the province
| Participation of women in project activities | Participation of women is very minimal | 35 women were trained in mangrove nursery and planting in 2015 through community based mangrove planting initiatives. Awareness programmes conducted in schools and communities so far covered a 202 males and 166 females . A total 324 boys and 271 girls were reached through awareness raising programmes. | Increased (at least 20%) number of women participating in capacity building activities at national and subnational level
Outcome 4 - Strengthened awareness and ownership of adaptation and climate change-related risk reduction processes at national and sub-national levels | % of the risk-affected population exposed to awareness raising activities and materials | Awareness raising efforts is ad-hoc, uncoordinated and often undertaken with insufficient technical basis | Under the mangrove conservation activities more than 2000 people were reached in 6 communities. Besides, approximately 5000 people in 20 communities in Morobe, New Ireland Province and Madang are reached through various awareness campaigns conducted by NGO partners. A 45 second El Nino preparedness TV infomercial was aired for two months that reached TV viewers through out the Papua New Guinea. | 75 % of the risk-affected population is exposed to awareness raising activities and materials.
| Integration of climate change into the national school curricula and university academic programmes | Only few schools cover climate change in their classes and activates; there is very limited guidance for teachers | Discussions are underway with the Department of Education and Institute of Public Administration to explore the possibilities of incorporating climate change adaptation and DRM into school curriculum and public service curriculum. FPCD developed a teaching guide on climate change adaptation for lower primary schools in PNG. A proposal from World Conservation Society for facilitating introduction of CCA into school curriculum in five provinces is currently being reviewed. | The topics of climate change and adaptation are introduced in PNG’s school curricula and university academic programmes and teachers are equipped with the required knowledge and material
| Amount of funding mobilized via CSR and sponsorship agreements | CSR funding sources is currently nil. | Department For Foreign Affairs and Trade, Australian Government has contributed 500,000 USD to the project which will support community level climate vulnerability and risk assessment. Further to this possibilities of mobilizing additional resources through CSR programmes is being explored. | By the end of the project agreements on continuation of awareness raising and adaptation activities (especially replication) through contributions from Corporate Social Responsibility programmes and private sector participation are reached (including projects under infrastructure tax credit schemes) and make resources available for the community-led adaption in at least 10 further communities (estimated 500,000 USD)

## Lessons Learned
QUALITATIVE MEASURES and LESSONS LEARNED
Please complete the following section every reporting period
Implementation and Adaptive Management | Response
What implementation issues/lessons, either positive or negative, affected progress? | Delay in procurement process of institutional and individual contracts to implement various project activities impeded the progress under the project
Were there any delays in implementation? If so, include any causes of delays. What measures have been taken to reduce delays? | The resignation of project manager in October 2014 hindered implementation of the project. Despite several efforts a project manager is yet to be recruited. However, with the appointment of project focal point within the OCCD as well as the recruitment of five provincial assistants placed in the provinces, the implementation of the project has picked up speed.
Describe any changes undertaken to improve results on the ground or any changes made to project outputs (i.e. changes to project design) | The project has garnered strategic partnership through grant agreement with NGO partners, in order to build on and scale ongoing work on the ground. This has enabled the acceleration of implementation of community level activities including community level risk assessment, adaptation planning and awareness raining. The NGOs are also leading implementation of mangrove conservation/planting work at the community level.
How have gender considerations been taken into consideration during the reporting period? What have been the lessons learned as a consequence of inclusion of such considerations on project performance or impacts? | The dimensions of gender and vulnerability are considered in all aspects of the project, including the planning and implementation of the project activities. The participation of women was indicated as a key consideration and priority in ToRs of experts and activities, such as the community based climate risk assessment and adaptation planning Similarly, the school children including girls were direct beneficiaries of awareness raising activities held in schools. Women at the community level will benefit from various trainings e.g., first aid training and will be included in the committees formed at the community level.
Please complete the following section at mid-term and project completion
Lessons for Adaptation | Response
Climate Resilience Measures
What have been the lessons learned, both positive and negative, in implementing climate adaptation measures that would be relevant to the design and implementation of future projects/programmes for enhanced resilience to climate change? | Climate Change Adaptation is relatively a new area of practice in Papua New Guinea, especially at the subnational levels. The institutional systems and structures for managing CCA at different levels is yet to develop fully and there is lack of understanding of CCA at different levels. Besides, the capacity of the agencies at different levels to engage with and utilize high level technical inputs is limited. Future projects need to take into account these facts listed above by ensuring that substantive investments will be made in terms of time and resources into a pedagogic approach, where stakeholders have ample tools and resources to enhance their skills and capacities for CCA. Capacity development, strengthening of CCA systems at different levels and community based CCA initiatives are strongly recommended for the future projects/programs.
What is the potential for the climate resilience measures undertaken by the project/programme to be replicated and scaled up both within and outside the project area? | The project has made the provincial authorities aware of approaching CCA issues in a structured way e.g., assessment of risks, establishing and strengthening systems for CCA, capacity development of relevant institutions and staff and implementation of tangible CCA measures at the community level. The project has also created an awareness and demand for enhanced CCA and DRR preparedness and response plans, and to approach them in an integrated manner. There is a good chance of the project activities to be replicated elsewhere.
Concrete Adaptation Interventions
What have been the lessons learned, both positive and negative, in implementing concrete adaptation interventions that would be relevant to the design and implementation of future projects/programmes implementing concrete adaptation interventions? | Community based activities including community led mangrove conservation, community risk reduction and adaptation planning initiatives are well received by communities and relevant provincial authorities although it was difficult to find credible organizations to partner with to implement activities at the community level. Strengthen of the provincial CCA structure that includes establishment of CCA committee, assessment of the capacity gaps at the provincial level to design capacity development plans are well received by the provincial government. Any future program should have the right mix of capacity building and tangible risk reduction initiatives. However, in the context of PNG it is challenging to implement community level activities due to higher operating cost, inaccessibility / remoteness of communities and because of high level of security risks due to land disputes and tribal conflicts.
What is the potential for the concrete adaptation interventions undertaken by the project/programme to be replicated and scaled up both within and outside the project area? | Community based risk reduction and mangrove conservation projects have a high chance of replicability as communities see tangible benefits out of such interventions.
Community/National Impact
What would you consider to be the most successful aspects for the target communities? | Awareness raising on CCA is one of key components of community based activities that helps communities understand the risks associated with climate change vis-a-vis the role of the communities in reducing the risks and adapting to the changing climate. Awareness raising has also helped communities to better engage in project activities.
What measures are/have been put in place to ensure sustainability of the project/program results? | While sustaining the project activities without AF support is considered beyond the capacity of many provinces due funding the provinces are capable of operationalizing the CCA/DRM Plans. Following the completion of the climate risk assessment in five provinces an advocacy initiative will be launched to include the recommendations of the assessment in the policies and planning and earmark regular budget for CCA which will ensure sustainability of the project results. The project has also established systems and structures at the sub-national level to address CC issues including establishment of Provincial Climate Change Committees. The provincial authorities have also earmarked funding for CCA in their annual budgets which is one of the biggest achievements of the project which will sustain CCA beyond the project period.
What measures are being/could have been put in place to improve project/program results? | Some of the measures that are put in place to improve the project results include regular engagement with relevant stakeholders to keep them abreast of project activities. The project is trying to implement activities through the newly established provincial climate change office to effectively engage them in the project implementation. Besides, the project has also engaged with NGO partners who have a presence at the provincial level to implement relevant project activities.
Knowledge Management
How has existing information/data/knowledge been used to inform project development and implementation? What kinds of information/data/knowledge were used? | The flood hazard and risk analysis in five pilot provinces have informed the disaster preparedness and response planning. Similarly assessment of capacity gaps has informed the project to establish a capacity development plan on CCA at different levels. The on going assessment will help design an effective flood early warning system and the climate vulnerability and risk assessment will inform policies and plans to be climate resilient. The knowledge products, documents and reports produced under the project include; National Inception Workshop Report, New Ireland Provincial Stakeholder Consultative Meeting, Community Based Mangrove Planting Handbook, Hazard Assessment report & maps for the 5 provinces, Provincial Inception Workshop reports (New Ireland, Northern, Madang, Morobe, East Sepik), Early warning systems field assessment reports, Communication Strategy, Climate Change Institutional and Capacity Assessment report, Early Warning Systems Inception report, Micro-Grant Agreements progressive reports (World Wide Fund for Nature, Foundation for People & Community Development, World Vision PNG and Adventist Development Relief Agency - PNG), Teaching Guide for Climate Change Adaptation for Lower Primary Schools in PNG, Press coverage - Inception Workshop on Flood Early Warning, Press coverage- Mangrove planting and conservation in East Sepik, Press Website Story on TV Infomercial - El Nino Preparedness (45 Second infomercial broadcasted on National TV for two months), Website story titled 'Local communities of Papua New Guinea are committed to fight climate change'.
If learning objectives have been established, have they been met? Please describe. | Learning objectives have been established . A capacity assessment report has been completed that includes analysis of prevailing climate change adaptation policies, structures and frameworks, and identifies the priority capacity development needs of Office of Climate Change and Development and other key government actors based on that a comprehensive capacity development programme for the entire country but specifying the 5 specific components has been designed.
Describe any difficulties there have been in accessing or retrieving existing information (data or knowledge) that is relevant to the project. Please provide suggestions for improving access to the relevant data. | Some of the assessments encountered difficulties in accessing information/data. For example EWS assessment had issues retrieving data with regard to past disasters from National Disaster Centre which is the focal point for Disaster Management in PNG. Similar data related to water level, rain fall etc. are not systematically kept by relevant departments/agencies hence was not accessible to the project. Basic GIS/spatial data is not available for undertaking climate risk assessment and the GIS/Spatial data is being developed. Signing MoU between agencies may resolve this issue and allow for the data and information to be shared (subject to its availability).
Has the identification of learning objectives contributed to the outcomes of the project? In what ways have they contributed? | Training and capacity building to enhance CCA capacities of national and local government staff is expected to contribute to the achievement of project outcomes. A range of trainings have been identified to be implemented in the next reporting period. So far trainings has been completed with regard to hazard assessment and development of GIS/spatial data base. Two workshops have been conducted on flood early warning and climate risk assessment/vulnerability assessment.

## Results Tracker
Results Tracker for Adaptation Fund (AF) Projects
Goal: Assist developing-country Parties to the Kyoto Protocol that are particularly vulnerable to the adverse effects of climate change in meeting the costs of concrete adaptation projects and programmes in order to implement climate-resilient measures. Impact: Increased resiliency at the community, national, and regional levels to climate variability and change.
Important: Please read the following guidance document (also posted on the Adaptation Fund website) before entering your data
Link: http://www.adaptation-fund.org/sites/default/files/Results%20Framework%20and%20Baseline%20Guidance%20final.pdf
Adaptation Fund Strategic Results Framework
Project ID | 00074956
Implementing Entity | 001429
Type of implementing entity | MIE
Country | Papua New Guinea
Region | Asia-Pacific
Sector | Multi-sector
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Impact: Increased resiliency at the community, national, and regional levels to climate variability and change | Core Indicator: No. of beneficiaries |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project
|  | Total | 0 | 0 | 0 |  | 136000 | 32000 | 104000 | Total | 50000 | 6000 | 45000 | Total
|  | % of female beneficiaries | 0% | 0% | 0% | % of female beneficiaries | 50% | 50% | 50% | % of female beneficiaries | 50% | 50% | 50% | % of female beneficiaries
|  | % of Youth beneficiaries | 0% | 0% | 0% | % of Youth beneficiaries | 30% | 30% | 30% | % of Youth beneficiaries | 30% | 30% | 30% | % of Youth beneficiaries
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 1: Reduced exposure to climate-related hazards and threats | Indicator 1: Relevant threat and hazard information generated and disseminated to stakeholders on a timely basis | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness
|  | Total | 0 | Inland flooding | 1: Ineffective | Total | 32000 | Inland flooding | 4: Effective | Total | 40 | Inland flooding | 1: Ineffective | Total
|  | % of female targeted | 0% |  |  | % of female targeted | 50% |  |  | % of female targeted | 20% |  |  | % of female targeted
Output 1.1 Risk and vulnerability assessments conducted and updated | Indicator 1.1: No. of projects/programmes that conduct and update risk and vulnerability assessments | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
Output 1.2 Targeted population groups covered by adequate risk reduction systems | Core Indicator 1.2: No. of Early Warning Systems | No. of adopted Early Warning Systems | Category targeted | Hazard | Inland flooding | No. of adopted Early Warning Systems | Category targeted | Hazard | Inland flooding | No. of adopted Early Warning Systems | Category targeted | Hazard | Inland flooding | No. of adopted Early Warning Systems | Category targeted | Hazard
|  | 0 | 1: Risk knowledge | Geographical coverage | Local | 1 | 1: Risk knowledge | Geographical coverage | Local | 0 | 1: Risk knowledge | Geographical coverage | Local |  |  | Geographical coverage
|  |  |  | Number of municipalities | 0 |  |  | Number of municipalities | 8 |  |  | Number of municipalities | 8 |  |  | Number of municipalities
|  | No. of adopted Early Warning Systems | Category targeted | Hazard | Coastal flooding | No. of adopted Early Warning Systems | Category targeted | Hazard | Coastal flooding | No. of adopted Early Warning Systems | Category targeted | Hazard | Coastal flooding | No. of adopted Early Warning Systems | Category targeted | Hazard
|  | 0 | 1: Risk knowledge | Geographical coverage | Local | 1 | 1: Risk knowledge | Geographical coverage | Local | 0 | 1: Risk knowledge | Geographical coverage | Local |  |  | Geographical coverage
|  |  |  | Number of municipalities | 0 |  |  | Number of municipalities | 8 |  |  | Number of municipalities | 8 |  |  | Number of municipalities
|  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 2: Strengthened institutional capacity to reduce risks associated with climate-induced socioeconomic and environmental losses | Indicator 2: Capacity of staff to respond to, and mitigate impacts of, climate-related events from targeted institutions increased | Number of staff targeted |  | Sector | Capacity level | Number of staff targeted |  | Sector | Capacity level | Number of staff targeted |  | Sector | Capacity level | Number of staff targeted |  | Sector | Capacity level
|  | Total |  |  |  | Total |  |  |  | Total |  |  |  | Total
|  | % of female targeted |  |  |  | % of female targeted |  |  |  | % of female targeted |  |  |  | % of female targeted
Output 2.1 Strengthened capacity of national and sub-national centres and networks to respond rapidly to extreme weather events | Indicator 2.1.1: No. of staff trained to respond to, and mitigate impacts of, climate-related events | Total staff trained | % of female staff trained | Type |  | Total staff trained | % of female staff trained | Type |  | Total staff trained | % of female staff trained | Type |  | Total staff trained | % of female staff trained | Type
|  | 0 | 0% | Public |  | 100 | 50% | Public |  | 40 | 20% | Public
| Indicator 2.1.2: No. of targeted institutions with increased capacity to minimize exposure to climate variability risks | Type | Scale | Sector | Capacity level | Type | Scale | Sector | Capacity level | Type | Scale | Sector | Capacity level | Type | Scale | Sector | Capacity level
|  | Public | Local | Multi-sector | 2: Low capacity | Public | Local | Multi-sector | 4: High capacity | Public | Local | Multi-sector | 3: Medium capacity
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 3: Strengthened awareness and owernship of adaptation and climate risk reduction processes | Indicator 3.1: Increase in application of appropriate adaptation responses | Percentage of targeted population applying adaptation measures |  | Sector |  | Percentage of targeted population applying adaptation measures |  | Sector |  | Percentage of targeted population applying adaptation measures |  | Sector |  | Percentage of targeted population applying adaptation measures |  | Sector
|  | 0% |  | Disaster risk reduction |  | 75% |  | Disaster risk reduction |  | 18% |  | Disaster risk reduction
Output 3: Targeted population groups participating in adaptation and risk reduction awareness activities | Indicator 3.1.1: Percentage in targeted population awareness of predicted adverse impacts of climate change, and of appropriate responses | No. of targeted beneficiaries | % of female participants targeted | Level of awareness |  | No. of targeted beneficiaries | % of female participants targeted | Level of awareness |  | No. of targeted beneficiaries | % of female participants targeted | Level of awareness |  | No. of targeted beneficiaries | % of female participants targeted | Level of awareness
|  | 0 | 0% | 1: Aware of neither |  | 32000 | 50% | 4: Mostly aware |  | 6000 | 50% | 3: Partially aware
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 4: Increased adaptive capacity within relevant development sector services and infrastructure assets | Indicator 4.1: Increased responsiveness of development sector services to evolving needs from changing and variable climate | Project/programme sector | Geographical scale | Response level |  | Project/programme sector | Geographical scale | Response level |  | Project/programme sector | Geographical scale | Response level |  | Project/programme sector | Geographical scale | Response level
| Core Indicator 4.2: Assets produced, developed, improved or strengthened | Sector | Targeted asset | Changes in asset (quantitative or qualitative) |  | Sector | Targeted asset | Changes in asset (quantitative or qualitative) |  | Sector | Targeted asset | Changes in asset (quantitative or qualitative) |  | Sector | Targeted asset | Changes in asset (quantitative or qualitative)
Output 4: Vulnerable development sector services and infrastructure assets strengthened in response to climate change impacts, including variability | Indicator 4.1.1: No. and type of development sector services to respond to new conditions resulting from climate variability and change | Number of services | Type |  | Sector | Number of services | Type |  | Sector | Number of services | Type |  | Sector | Number of services | Type |  | Sector
|  | Baseline information |  |  |  | Target perofrmance at completion |  |  |  | Performance at midterm |  |  |  | Performance at completion
Outcome 5: Increased ecosystem resilience in response to climate change and variability-induced stress | Indicator 5: Ecosystem services and natural resource assets maintained or improved under climate change and variability-induced stress | Natural resource improvement level |  | Sector | Type | Natural resource improvement level |  | Sector | Type | Natural resource improvement level |  | Sector | Type | Natural resource improvement level |  | Sector | Type
|  | 1: Ineffective |  | Disaster risk reduction | biological assets | 3: Moderately effective |  | Disaster risk reduction | biological assets | 2: Partially effective |  | Disaster risk reduction | biological assets
Output 5: Vulnerable ecosystem services and natural resource assets strengthned in response to climate change impacts, including variability | Core Indicator 5.1: Natural Assets protected or rehabilitated | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Baseline information |  |  |  | Targeted performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 6: Diversified and strengthened livelihoods and sources of income for vulnerable people in targeted areas | Indicator 6.1: Increase in households and communities having more secure access to livelihood assets | No. of targeted households | % of female headed households | Improvement level |  | No. of targeted households | % of female headed households | Improvement level |  | No. of targeted households | % of female headed households | Improvement level |  | No. of targeted households | % of female headed households | Improvement level
| Indicator 6.2: Increase in targeted population's sustained climate-resilient alternative livelihoods | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
|  | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
|  | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
|  | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
Output 6 Targeted individual and community livelihood strategies strengthened in relation to climate change impacts, including variability | Indicator 6.1.1: No. and type of adaptation assets created or strengthened in support of individual or community livelihood strategies | Number of Assets | Type of Assets | Sector | Adaptation strategy | Number of Assets | Type of Assets | Sector | Adaptation strategy | Number of Assets | Type of Assets | Sector | Adaptation strategy | Number of Assets | Type of Assets | Sector | Adaptation strategy
| Core Indicator 6.1.2: Increased income, or avoided decrease in income | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 7: Improved policies and regulations that promote and enforce resilience measures | Indicator 7: Climate change priorities are integrated into national development strategy | Integration level |  |  |  | Integration level |  |  |  | Integration level |  |  |  | Integration level
|  | 2: Most not integrated |  |  |  | 4: Most |  |  |  | 3: Some
Output 7:Improved integration of climate-resilience strategies into country development plans | Indicator 7.1: No. of policies introduced or adjusted to address climate change risks | No. of Policies introduced or adjusted | Sector | Scale | Type | No. of Policies introduced or adjusted | Sector | Scale | Type | No. of Policies introduced or adjusted | Sector | Scale | Type | No. of Policies introduced or adjusted | Sector | Scale | Type
|  | 0 | Multi-sector | National | Environmental policy | 1 | Multi-sector | National | Environmental policy | 1 | Multi-sector | National | Environmental policy
| Indicator 7.2: No. of targeted development strategies with incorporated climate change priorities enforced | No. of Development strategies | Regulation |  | Effectiveness | No. of Development strategies | Regulation |  | Effectiveness | No. of Development strategies | Regulation |  | Effectiveness | No. of Development strategies | Regulation |  | Effectiveness
Glacier lake outburst flood
|  | Inland flooding | fr | biological assets |  | Company policy | 5: Fully enforced (All elements implemented)
|  | Salinization | Decrease | land |  | Communication & Information policy | 4: Enforced (Most elements implemented)
|  | Drought | Same | water areas |  | Defense policy | 3: Partially enforced (Some elements implemented)
|  | Wind |  | subsoil assets | increased adpative capacity | Domestic policy | 2: Partially not enforced (Most elements not implemented) |  | Agribusiness
|  | Coastal flooding |  | air | achieved | Economic policy | 1: Not enforced (No elements implemented) |  | Agricultural-related | Financial capital
|  | Storm surge | Please choose |  | enhanced level of protection | Education policy |  |  | Agriculture | Human capital
|  | Hurricane | Selected | [5 empty] | Aquaculture | Physical capital
|  |  | Not relevant |  |  | 5: All (Fully integrated) |  |  | Construction/repairing business | Social capital
[6 empty] | 4: Most |  |  | Cultivation | Natural capital
[6 empty] | 3: Some |  |  | Fishing | Personal capital
Select | 5: All | Select |  |  | Community | 2: Most not integrated |  | Other | Forestry | Adaptation strategies
1 | 4: Almost all | Private | Type | Yes | Multi-community | 1: None |  | Agriculture | Handicrafts
2 | 3: Half | Public | Scale | No | Departmental |  |  | Coastal management | Livestock production
3 | 2: Some | NGO | Sector |  | National |  |  | Disaster risk reduction | Manufacturing
4 | 1: None |  |  |  |  | 5: Very high improvement | Established | Food security | other
|  | National |  |  |  | 4: High improvement | Maintained | Health | Services
|  | Regional |  |  |  | 3: Moderate improvement | Improved | Urban development | Tourism-related
|  | Local |  |  |  | 2: Limited improvement |  | Water management | Trading
[6 empty] | 1: No improvement |  | Multi-sector
|  | 1 -generated information is irrelevant, and neither the stakeholders reached nor the timeframe managed were achieved | 1: No info transferred on time | 4: High capacity | 5: Fully aware | 5: Highly responsive (All defined elements ) | 5: Fully improved | Roads | 5: Very effective
Asia-Pacific | NIE | 2 -the existence of some challenge in any of the three aspects of the indicator (generation of dissemination, stakeholders reached or timeframe managed) | 2: Somewhat info transferred | 3: Medium capacity | 4: Mostly aware | 4: Mostly responsive (Most defined elements) | 4: Mostly Improved | Gov Buildings | 4: Effective
Latin America and Caribbean | RIE | 3 -relevant information is generated and disseminated to all identified stakeholders on timely basis | 3: Info transferred on time | 2: Low capacity | 3: Partially aware | 3: Moderately responsive (Some defined elements) | 3: Moderately improved | Causeways | 3: Moderately effective
Africa | MIE |  |  | 1: No capacity | 2: Partially not aware | 2: Partially responsive (Lacks most elements) | 2: Somewhat improved | Airports | 2: Partially effective
Eastern Europe |  |  |  |  | 1: Aware of neither | 1: Non responsive (Lacks all elements ) | 1: Not improved | Schools | 1: Ineffective
| ha protected | [6 empty] | Training Centres
| ha rehabilitated | [5 empty] | Monitoring/Forecasting capacity | Hospitals
Afghanistan, Islamic Rep. of | km protected | [5 empty] | Policy/regulatory reform | Drinking water systems
Angola | km rehabilitated | 1: Risk knowledge | 1: No plans conducted or updated |  |  |  | Capacity development | Other
Albania |  | 2: Monitoring and warning service | 2: Undertaking or updating of assessments in progress |  |  | Communication & Information policy | Sustainable forest management
Argentina |  | 3: Dissemination and communication | 3: Risk and vulnterability assessments completed or updated |  |  | Domestic policy | Strengthening infrastructure | 1: Health and Social Infrastructure (developed/improved)
Armenia | Forests | 4: Response capability |  |  |  | Economic policy | Supporting livelihoods | 2: Physical asset (produced/improved/strenghtened)
Antigua and Barbuda | Mangroves |  |  |  |  | Education policy | Mangrove reforestation
Azerbaijan | Coasts |  | From 0 to 0.5% |  |  | Energy policy | Coastal drainage and infrastructure
Burundi | Rangelands |  | From 0.5 to 1% |  |  | Environmental policy | Irrigation system
Benin | Cultivated land/Agricultural land |  | From 1% to 5% |  |  | Foreign policy | Community-based adaptation
Burkina Faso | Catchment area/Watershed/Aquifer |  | From 5% to 10% |  |  | Health policy | Erosion control
Bangladesh | Protected areas/National parks |  | From 10% to 20% |  |  | Housing policy | Soil water conservation
Bulgaria | Other |  | From 20% to 30% |  |  | Human resource policies | Microfinance
Bahrain |  |  | From 30% to 40% |  |  | Information policy | Special Program for women
Bahamas, The |  |  | From 40% to 50% |  |  | Macroeconomic policy | Livelihoods
Bosnia and Herzegovina |  |  | Above 50% |  |  | Monetary policy | Water storage
Belarus | [5 empty] | Population policy | ICT and information dissemination
Belize | [5 empty] | Private policy
Bolivia | [5 empty] | Public policy
Brazil | [5 empty] | Science policy
Barbados | [5 empty] | Social policy
Bhutan |  | 3- relevant information is generated and disseminated to all identified stakeholders on timely basis |  |  |  | Transportation policy
Botswana |  | describe |  |  |  | Urban policy
Central African Republic |  | 2- the existence of some challenge in any of the three aspects of the indicator |  |  |  | Water policy
Chile |  | describe |  |  |  | Other policy
China, People's Republic of |  | 1- generated information is irrelevant and neither the stakeholders reached nor the timeframe managed were achieved
Cote d'Ivoire |  | describe
Cameroon
Congo, Dem. Rep. of
Congo, Republic of
Cook Islands
Colombia
Comoros
Cape Verde
Costa Rica
Cuba
Czech Republic
Djibouti
Dominica
Dominican Republic
Algeria
Ecuador
Egypt
Eritrea
Estonia
Ethiopia
Fiji
Micronesia, Fed. States of
Gabon
Georgia
Ghana
Guinea
Gambia, The
Guinea-Bissau
Equatorial Guinea
Grenada
Guatemala
Guyana
Honduras
Croatia
Haiti
Hungary
Indonesia
India
Iran, Islamic Republic of
Jamaica
Jordan
Kazakhstan
Kenya
Kyrgyz Republic
Cambodia
Kiribati
Saint Kitts and Nevis
Korea, Republic of
Lao People's Democratic Republic
Lebanon
Liberia
Libya
Saint Lucia
Sri Lanka
Lesotho
Lithuania
Latvia
Morocco
Moldova
Madagascar
Maldives
Mexico
Marshall Islands
Macedonia, former Yugoslav Republic of
Mali
Malta
Myanmar
Montenegro
Mongolia
Mozambique
Mauritania
Mauritius
Malawi
Malaysia
Namibia
Niger
Nigeria
Nicaragua
Niue
Nepal
Nauru
Oman
Pakistan
Panama
Peru
Philippines
Palau
Papua New Guinea
Poland
Korea, Dem. People's Rep. of
Paraguay
Romania
Russian Federation
Rwanda
Saudi Arabia
Sudan
Senegal
Solomon Islands
Sierra Leone
El Salvador
San Marino
Serbia
Sao Tome and Principe
Suriname
Slovak Republic
Slovenia
Swaziland
Seychelles
Syrian Arab Republic
Chad
Togo
Thailand
Tajikistan
Turkmenistan
Tonga
Trinidad and Tobago
Tunisia
Turkey
Tuvalu
Tanzania
Uganda
Ukraine
Uruguay
Uzbekistan
Saint Vincent and the Grenadines
Venezuela
Vietnam
Vanuatu
Samoa
Yemen, Republic of
South Africa
Zambia
Zimbabwe
Timor-Leste

## Units for Indicators
Fund Outcome Indicator Units
1. Generation of relevant data, Stakeholders, and Timeliness 2.1. Include both qualitative and quantitative measures of capacity level within targeted institutions 2.2. Number (men and women and other vulnerable groups) 3.1. Use scale from 1 to 5: 5: Fully aware 4: Mostly aware 3: Partially aware 2: Partially not aware 1: Aware of neither predicted adverse impacts of climate change nor of appropriate responses 3.2. Use scale from 1 to 5: 5: All 4: Almost all 3: Half 2: Some 1: None 4.1. Summarize in an overall scale (1-5): 5: Highly responsive (All defined elements ) 4: Mostly responsive (Most defined elements) 3: Moderately responsive (Some defined elements) 2: Partially responsive (Lacks most elements) 1: Non responsive (Lacks all elements ) 4.2. Summarize in an overall scale (1-5): 5: Fully improved 4: Mostly Improved 3: Moderately improved 2: Somewhat improved 1: Not improved 5. Depends on the targeted natural asset: Biological (species): measure through changes in population numbers (dynamics, structure, etc.) Land: measure changes in hectares. Baseline data will be necessary to estimate the change. Supporting indicators baseline and target (as well as contextual information) are needed such as the following: Farmers adopting recommended technologies, Ha. of land improved, Average deforestation rate Etc. Use scale from 1 to 5. 5: Very effective (All elements are present) 4: Effective (Most elements are present) 3: Moderately effective (Some elements are present) 2: Partially effective (Most elements are not present) 1: Ineffective (No elements are present) 6.1. Summarize in an overall scale (1-5): 5: Very high improvement 4: High improvement 3: Moderate improvement 2: Limited improvement 1: No improvement 6.2. Household income by source of livelihood in project area (USD) prior and post project intervention 7. Summarize in an overall scale (1-5). 5: All (Fully integrated) 4: Most 3: Some 2: Most not integrated 1: None
Fund Output Indicator Units
1.1. Number, sector(s) and level(s) of projects or interventions in separate fields of monitoring plan 1.2. Number 2.1.1. Number of staff (male/female) of targeted institutions: a. Obtain baseline information: total number of staff from targeted institutions b. Define target 2.1.2. Number of staff (male/female) of targeted institutions: a. Obtain baseline information: total number of staff from targeted institutions b. Define target: needs to be defined by project proponents 2.2.1. Quantitative: Percentage (includes women – and other vulnerable groups – and men). Qualitative: Adequacy: include direct analysis of major areas; adequacy/effectiveness of systems or analysis of perceptions of populations and institutions. 2.2.2. Number (broken down by gender and, if possible, by vulnerable groups defined in the area of intervention) of people 3.1. Number and type (in separate columns) at local level. 3.2. Number 4.1. Number and type 4. 2. Number and type (entered in separate columns) 5. Number of interventions by type of natural asset and intervention 6.1. Number and type (in separate columns of monitoring plan) 6.2. Income sources per household; description of income source and number of households. 7.1. Number/Sector 7.2. Number; Effectiveness (see previous indicator) through enforcement level.