## Overview
Project Performance Report (PPR)
| Period of Report (Dates) | 01/04/18 - 31/03/19
| Project Title: | Building Resilient Food Security Systems to Benefit the Southern Egypt Region .
Southern Egypt Region” Project in Egypt
| Project Summary: | The World Food Programme estimates that Southern Egypt, a region that is already economically stressed and whose food supplies are under constant threat of disruption, stands to lose a minimum of 30 percent of its food production by 2050 as a result of climate change impacts. These impacts include reduced crop and livestock productivity, increasing crop-water demand and reduced water use efficiency, and increases in pest and disease infestations. In response, the Government has proposed a project that aims to 1) improve the adaptive capacity of the Southern zone of Egypt in the face of anticipated climate-induced reduction in food production through the introduction and use of water saving irrigation and other adaptation techniques; the establishment of agro-forestry greenhouses and plots with sub-surface irrigation, including nurseries for growing trees and new varieties; and the development of livestock and poultry hubs for selection and breeding of new heat resistant varieties. 2) build institutional capacity at the national, regional, and local levels to enable sustainability and replication throughout the zone and the country to understand climate trends and impacts; replicate adaptation interventions through the training of government technical staff; document and share lessons learned and best practices; share project results; mainstream new approaches in local and regional planning; and target universities through including these lessons in the curriculum. The two objectives are cornerstones of Egypt's National Adaptation Strategy.
|  | ` | Countries | Project Type: |  | GEF Focal Area: | GEF 4 Focal Areas | GEF 2 / 3 Operational Programme: | Overall Rating of the project in the evaluation by the project evaluator: | GEF-4 Focal Area Strategic Program: | GEF-3 Focal Area Strategic Program:
| Database Number: |  | Afghanistan | FP | Yes | Biodiversity | 1 | 1 | U | BD-SP1-PA Financing | 1: Arid & semi-arid ecosystems
Implementing Entity (IE) [name]: |  | United Nations World Food Programme | Albania | MSP | No | Climate Change Adaptation | 2 | 2 | S | BD-SP2-Marine PA | 2: Coastal, marine & freshwater ecosystems
| Type of IE: | MULTILATERAL IMPLEMENTING ENTITY | Algeria | EA |  | Climate Change Mitigation | 3 | 3 | MU | BD-SP3-PA Networks | 3: Forest ecosystems
| Country(ies): | Egypt | Angola |  |  | International Waters | 5 | 5 | Good | BD-SP5-Markets | 13: Conservation and Sustainable Use of Biological Diversity Important to Agriculture
Relevant Geographic Points (i.e. cities, villages, bodies of water): |  | Assuit, Sohag , Qena, Luxor, Asswan | Argentina |  |  | Multiple Focal Area |  |  |  | BD-SP7-Invasive Alien Species(IAS) | 6: Promoting the adoption of renewable energy by removing barriers and reducing implementation costs
[8 empty] | CC-SP2- Industrial EE | 8: Water body based operational program
| Project Milestones | [6 empty] | CC-SP3-RE,CC-SP4-Biomass | 9: Integrated Land and Water multiple focal area
| Milestone |  | Bahamas | [6 empty] | CC-SP5-Transport | 10: Contaminants based operational program
AFB Approval Date: |  | 29 June, 2012.
IE-AFB Agreement Signature Date: |  | 23 July, 2012. | [6 empty] | CC-SP6-LULUCF | 12: Integrated Ecosystem Management
Start of Project/Programme: |  | March 31, 2013 | [6 empty] | Cross cutting capacity building | 14: Persistent Organic Pollutants
Mid-term Review Date (if planned): |  | September, 2015
| Terminal Evaluation Date: | June, 2018
|  | List documents/ reports/ brochures / articles that have been prepared about the project. | Cyprus
|  | Audio-visual material: - Aswan harvesting days broadcast on Tiba satellite TV channel - General Supervisor interview on Misr Elzeraea (Egyptian Agricultural Satellite) channel - project manager interview on Tiba satellite Channel - Minister of Agriculture during field trip in Sohag and visit to canals lined by the project - T.V. interview with the Minister of Agriculture during the inauguration of the project PMU - Programme on the training on sorghum production and project interventions-shown on Tiba channel - Project wheat production expert interview- Tiba channel -3 Interviews with the project manager on South Valley local radio channel -1 interview with the project manager on the General Program national radio channel - Project documentary (20 Minutes) On-line material: - Project website -Project YouTube channel (https://www.youtube.com/channel/UCSwyykkhNwFgvZTL0mCFP4Q) Facebook groups ( one for each governorate ) aimed to create a link between volunteers and project experts: Assuit group: https://www.facebook.com/groups/1391044347832895/ Souhag group: https://www.facebook.com/groups/1391044347832895/ Qena group: https://www.facebook.com/groups/1428651090707357/ Luxor group: https://www.facebook.com/groups/485776041523036/ Aswan group: https://www.facebook.com/groups/1403712143226253/ -'Tackling Climate Change in Upper Egypt' Story on project published on WFP Egypt Country page and WFP Arabic website -WFP MENA Tweeted about the story adding a link to the WFP Egypt Country page. Retweeted 53 times, received 29 favourites and 15,000 impressions. The story was discussed as a model for successful social media outreach during annual WFP regional communications workshop Printed material: • 2 flyers on interventions towards decreasing the negative effect of extreme weather events in newly reclaimed and old lands project youtube chanel : https://www.youtube.com/channel/UCSwyykkhNwFgvZTL0mCFP4Q - 2 brochures on climate adaptation in wheat production • Interview with Prof. Hani Elkateb (Scientific consultant of President Abdel Fattah El SiSi): Climate Change project is one of the most profitable projects in Upper Egypt (newspaper article in Ahram El Ektidadi newspaper) -148 articles in national governmental newspapers and magazines (Ahram, Akhbar, Gomhoreia, El Mesaa, Roz al Yousef, Ahram Weekly, and El Ahram El Mesaaei), independent newspapers (El Watan, Watani, El Youm El Sabee, Masr El Youm, and El Fagr) and local newspapers (Sout Luxor, Sout Sohag and Sout Aswan) | Czech Republic
List the Website address (URL) of project. |  |  | Democratic People's Republic of Korea
|  | http://climatechange-eg.org/ | Democratic Republic of the Congo
Denmark
| Project contacts: |  | Djibouti
National Project Manager/Coordinator |  |  | Dominica
| Name: | Eng. Othman El Shaikh | Dominican Republic
| Email: | othmanelshiakh@gmail.com | Ecuador
| Date: |  | Egypt
| Government DA |  | El Salvador
| Name: | Mr. Mohamed Salah El Saied, Chairman Egyptian Environmental Affairs Agency (EEAA) | Equatorial Guinea
| Email: | NA | Eritrea
| Date: |  | Estonia
| Implementing Entity |  | Ethiopia
| Name: | Dr. Ithar Khalil, WFP Egypt Country Office | Fiji
| Email: | ithar.khalil@wfp.org | Finland
| Date: |  | France
| Executing Agency |  | Gambia
| Name: | Dr. Ali Hozyen - Supervisor General - Executive Agency for Comprehensive Development Projects (EACDP)- Ministry of Agriculture | Georgia
| Email: | hozayen2004@hotmail.com | Germany
| Date: |  | Ghana
| Executing Agency |  | Greece
| Name: |  | Grenada
| Email: |  | Guatemala
| Date: |  | Guinea
| Executing Agency |  | Guinea Bissau
| Name: |  | Guyana
| Email: |  | Haiti
| Date: |  | Honduras
Hungary
Iceland
India
Indonesia
Iran (Islamic Republic of)
Iraq
Ireland
Israel
Italy
Jamaica
Japan
Jordan
Kazakhstan
Kenya
Kiribati
Kuwait
Kyrgyzstan
Lao People’s Democratic Republic
Latvia
Lebanon
Lesotho
Liberia
Libyan Arab Jamahiriya
Liechtenstein
Lithuania
Luxembourg
Madagascar
Malawi
Malaysia
Maldives
Mali
Malta
Marshall Islands
Mauritania
Mauritius
Mexico
Micronesia, Federated States of
Monaco
Mongolia
Montenegro
Morocco
Mozambique
Myanmar
Namibia
Nauru
Nepal
Netherlands
New Zealand
Nicaragua
Niger
Nigeria
Norway
Oman
Pakistan
Palau
Panama
Papua New Guinea
Paraguay
Peru
Philippines
Poland
Portugal
Qatar
Republic of Korea
Republic of Moldova
Romania
Russian Federation
Rwanda
Saint Kitts and Nevis
Saint Lucia
Saint Vincent and the Grenadines
Samoa
San Marino
Sao Tome and Principe
Saudi Arabia
Senegal
Serbia
Seychelles
Sierra Leone
Singapore
Slovakia
Slovenia
Solomon Islands
Somalia
South Africa
Spain
Sri Lanka
Sudan
Suriname
Swaziland
Sweden
Switzerland
Syrian Arab Republic
Tajikistan
Thailand
The former Yugoslav Republic of Macedonia
Timor-Leste
Togo
Tonga
Trinidad and Tobago
Tunisia
Turkey
Turkmenistan
Tuvalu
Uganda
Ukraine
United Arab Emirates
United Kingdom of Great Britain and Northern Ireland
United Republic of Tanzania
United States of America
Uruguay
Uzbekistan
Vanuatu
Venezuela, Bolivarian Republic of
Viet Nam
Yemen
Zambia
Zimbabwe

## Financial data
Financial information
DISBURSEMENT OF AF GRANT FUNDS
How much of the total AF grant as noted in Project Document plus any project preparation grant has been spent to date?
Estimated cumulative total disbursement as of [31/3/2019] | USD 5,163,505.90
Add any comments on AF Grant Funds. (word limit=200)
INVESTMENT INCOME | 2601
Amount of annual investment income generated from the Adaptation Fund’s grant
EXPENDITURE DATA
List ouput and corresponding amount spent for the current reporting period | ITEM / ACTIVITY / ACTION | AMOUNT
| 1.1 Community Mobilization | 26602.71
| 1.2 Monitoring System | 16867.21
| 1.3 Water Saving Techniques | 314767.44
| 1.4 Resilience in Agriculture Production | 190187.84
| 1.5 Resilience in Livestock Production | 46916.22
| 2.1 Training of Government Officials | 30783.45
| 2.2 Lessons Learned | 25195.66
| 2.3 Results Sharing | 23055.51
| 2.4Academic Integration | 33620.74
| Project Execution Costs | 93511.44
| TOTAL | 801508.22
PLANNED EXPENDITURE SCHEDULE
List outputs planned and corresponding projected cost for the upcoming reporting period | ITEM / ACTIVITY / ACTION | PROJECTED COST | Est. Completion Date
| Output 1.1 | 0 | 30.4.2020
| Output 1.2 | 0 | 30.4.2020
| Output 1.3 | 0 | 30.4.2020
| Output 1.4 | 444419 | 30.4.2020
| Output 1.5 | 63488 | 30.4.2020
| Output 2.1 | 75032 | 30.4.2020
| Output 2.2 | 6926 | 30.4.2020
| Output 2.3 | 80842 | 30.4.2020
| Output2.4 | 0 | 30.4.2020
| TOTAL | 670707 | 30.4.2020
| Project Execution Costs | 50651.55 | 30.4.2020
| Project Management Fee |  | 30.4.2020
| TOTAL | 721358.32
ACTUAL CO-FINANCING (If the MTR or TE have not been undertaken this reporting period, DO NOT report on actual co-financing.)
How much of the total co-financing as committed in the Project Document has actually been realized? | NA
Estimated cumulative actual co-financing as verified during Mid-term Review (MTR) or Terminal Evaluation (TE). | NA
Add any comments on actual co-financing in particular any issues related to the realization of in-kind, grant, credits, loans, equity, non-grant instruments and other types of co-financing. (word limit=200) | Government in-kind contributions were as follows: - Space was provided in the directorates of different governorates for project sub-offices and the PMU. - Government facilitated access to subsidized inputs - Use of media including radio and TV to cover achievements of project activities. - Important events related to the project were recorded by government provided cameraman as well as broadcast nationally. - Programmes demonstrating project activities were broadcast for farmers through the national tv channel on agriculture.

## Procurements (hidden)
PROCUREMENT DATA
Please provide information for all contracts over $2,500 USD
Please provide the number of contracts under $2,500, signed during this reporting period: |  |  |  | 521
LIST OF CONTRACTS
List all contracts related to the project/program with signature dates
Contract Type | Agency / Contracted party | Contract Value/Amount (USD) | Signature Date | Payment to Date(USD) | Remaining Balance
MOU | Directorate of Agriculture in Aswan | 81081.0811 | May2016 | 59459.4595 | 21621.6216
MOU | Animal Production Research Institute | 108108.1081 | May2016 | 62162.1622 | 45945.9459
MOU | AOI | 297297.2973 | 42583 | 121621.6216 | 175675.6757
BIDS
List all bids for each contact signed with date of open call and winning bid
BIDS
List all bids for each contact signed with date of open call and winning bid
CONTRACT & Procurement Method | Submitted Bids | Bid Amount (USD) | Winning Bid Amount (USD) | Selection Justification for the Winner
Veterinary equipment | El Fatmya for Trade | 49659.0909 | 49659.0909 | Scored the highest in technical & financial evaluations
Tony Medico
| Samrilio Co. | 56818.1818
| Ingaz Co. | 68181.8182
| Delta For Trade | 70454.5455
Bid for canal lining materials for Isna-Luxor Gov. | Arnot Co.for Construction | 34090.9091 |  | Scored the highest in technical & financial evaluations
| Samir for Construction | 25397.7273 | 25397.7273
| Sobhi for Construction | 39772.7273
Bid for canal lining materials for Banban-Aswan Gov. | Yosef for Construction | 8522.7273 |  | Scored the highest in technical & financial evaluations
| Samir for Construction | 9494.3182 | 8522.7273
| Fared for Construction | 10795.4545
Bid for canal lining materials for Banban-Aswan Gov. | Yosef for Construction | 15693.1818 |  | Scored the highest in technical & financial evaluations
| Samir for Construction | 17045.4545 | 15693.1818
| Fared for Construction | 15909.0909
Bid for canal lining materials for Isna-Luxor Gov. | Yosef for Construction | 17159.0909 |  | Scored the highest in technical & financial evaluations
| Almothda for Construction | 18409.0909 | 16022.7273
| Maka for Construction | 16022.7273
printed materiald | Shado Print | 2914.7727 | 2914.7727 | Scored the highest in technical & financial evaluations
| Beeatshro for printing | 3068.1818
| Next for Trade | 3011.3636
Elctronic Machines (50Computer&50Printers) | RTS Co. | 88950 | 81931.8182 | Scored the highest in technical & financial evaluations
| Alahly Co. | 81932
Elctronic Machines (5 Photocoper) | Nas Tecnolgy Co. | 19886.3636 | 19886.3636 | Scored the highest in technical & financial evaluations
| Toshiba Co. | 20454.5455
5 documentaries for Project | Z. Desin Co. | 28068.1818 | 28068.1818 | Scored the highest in technical & financial evaluations
| Seven ProdacionCo. | 28977.2727

## Risk Assesment
RISK ASSESMENT
IDENTIFIED RISKS
List all Risks identified in project preparation phase and what steps are being taken to mitigate them
Identified Risk | Current Status | Steps Taken to Mitigate Risk
Unforeseen changes in poverty, hunger, nutrition, and other socio-economic variables due to external factors such as Triple F crisis, pandemics, climate change. | Medium | Food prices have been closely monitored to identify significant changes in prices and inform activities accordingly. 10 new varieties of wheat, maize, sorghum and sugar cane and improved agricultural practices were introduced, contributing to the strengthening of community resilience to extreme weather events and increasing temperatures. The use of early warning system to relay information on upcoming extreme weather events to farmers continued, significanlty reducing losses in such events.
Potential conflict between farmers engaged in adaptation and applying new techniques and traditional farmers who are not. | Low | This risk has not materialized in the reporting period.
Lack of trust in the government honouring its commitments to offer the announced benefits to the beneficiaries. | low | As was the case in previous years, the project continued to build local trust and ownership through the involvement of communities in the identification of priorities, activity planning and implementation. Wide sharing of the Government's honouring of its commitments in the project implementation in festive harvest days that acknowledged the government's role and the resulting positive achievements also continued. The project continued to bring concerned government officials together with community members, media, and civil society, which continued to ffectively promoted the trust in the Government's active role in supporting the project and realising its announced objectives.
Non-sustainability of the project due to institutional or financial factors | low | The substantially positive results achieved continued to demonstrate the economic feasibility of the project interventions. As a result, the numbers of farmers replicating and up scaling in their lands, mostly at their own expenses continued to increase during this reporting period. The Ministry of Agriculture continued to adopt the wheat cultivation interventions in its programmes and during the reporting period. Further, project interventions were adopted in the Ministry's sugar cane and sorghum national campaings. As in previous years, the project prioritised building capacities of the new partner NGOs that joined the project during this reporting period to anchor the project at the local level. It also continued to oversee and support the NGOs with whom partnerships were established during the previous reporting period. Enhancing capacities of the new loans beneficiaries through specialized trainings to help them sustainably manage their projects continued. Engagement of extension officers in trainings and demonstration fields continued to be a priority.
Security risk: Egypt in general has witnessed an increase in crime compared to the past, which poses a risk to property | Low | No crimes of this nature have been recorded during the reporting period. As per normal practice, animal heads supplied during the reporting period for loans were insured.
Political Risk i.e. non-smooth transition from the interim to the elected Government, leading to changes which impact project implementation. - Finally, all political parties of all ideological backgrounds already indicated they would honour Egypt’s commitments towards international agreements, UNFCCC included | Low | This risk has not materialised in the reporting period.
Critical Risks Affecting Progress (Not identified at project design)
Identify Risks with a 50% or > likelihood of affecting progress of project
Identified Risk | Current Status | Steps Taken to Mitigate Risk
No critical risks with a 50% or more likelihood of affecting progress were identified and/or materialized druing the reporting period | N.A | N.A
Risk Measures: Were there any risk mitigation measures employed during the current reporting period? If so, were risks reduced? If not, why were these risks not reduced?
Add any comments relevant to risk mitigation (word limit = 500)
N.A.

## Rating
RATING ON IMPLEMENTATION PROGRESS
For rating definitions please see bottom of page.
| Progress on Key Milestones | Expected Progress18-19 | Progress to April 2019 | Rating
Project Manager/Coordinator: | 1.1. Community level mobilization and climate adaptation planning (including awareness) | Continue mobilization of volunteers for awareness raizing. Dissemination of project interventions through theater in the targeted villages and neighboring for 5000 beneficiaries | 855 volunteers were mobiliezed and trained in the 49 project villages to raise awareness about climate change, its impacts on agriculture, and education of communities on potential preparedness techniques in agriculture and livestock. 132 on- farm theater performances were made, disseminating information about the project interventions reaching 21605 beneficiaries | HS
| 1.2. Establishment of a climate change and food security monitoring system | Continued use of early warning system and disseminination of alerts through the climate information centers in the partner NGOs. spread early warning messages by localized short messages SMS to 5000 SMSs | * 95000 usages of the online early warning system were recorded and 10000 farmers got messages from the early warning system through the extension workers and local radio stations established by the project and hosted in the local NGOs. * Negotiations are under way with SMS providers to ensure that the early climate warning services continue to be scaled up after project funding ends, through financial allocations to CSR. This has taken longer than expected due to delays in issuance security clearnaces by the National Agency for Regulation of Telecommunications. | HS
| 1.3. Introduction and use of water saving irrigation and other adaptation techniques | 75 new Water User Associations to be established. Follow- up on water user associations and promoting adoption of water saving techniques for 5000 beneficiaries | canal lining in the period between irrigation intervals was completed in 1500 acres, with a total lenght of 23694 meters. The installation of six solar water irrigation pumps was completed and 696 farmers were trained on their management, operation and maintenance skills. soil laser leveling completed in 3363 acres, benefiting a total of 5939 beneficiary capacity of 49 local NGOs enhanced and 120 WUAs established, benefiting 5217 beneficiaries 1474 beneficiaries were trained on soft skills on water saving technologies. Training were done in collaboration with irrigation directorates. | HS
| 1.4. Building resilience in agricultural production | extension fields and on-farm training for introduction of heat tolerant varieties of common crops & dissemination of changing of sowing dates and intercropping practices to 3000 benefciaries extension fields for introduction improved agricultural techniques for cash crops cultivation to 100 benefiacaries . Enhancing the value of cash crops by introducting simple post-harvest equipment anf on- farm training to 5000 beneficiaries on-farm training to introduce heat tolerant varieties of common crops such as wheat, maize, sorghum and water-saving sugar cane varieties & dissemination of changing of sowing dates and intercropping practices in addition to the introduction of heat tolerant varieties and techniques of cash crops such as pomegranate green beans, banana, basilicum, and tomato for 2000 benefciaries Farm-to-farm visits for 100 beneficiaries | " extension fields implemented to upscale the intoduction of new varities of wheat, maize, sorghum and water-saving sugar cane varieties and disseminated changing of sowing dates and intercropping practices to 3650 acres. extension fields were implemented to introduce pomegranate, basilicum, and tomato cultivation techniques in of350 acres. Value of tomato and pomegranate enhanced through the establishment of 5 simple post-harvest units for tomato sundrying and and pomegranate deseeding, beefiting 2884 beneficiaries. 729 beneficiaries were engaged in 54 farm-to-farm visits to demonstration field is research stations of the Agriculture Research Center that exposed them to new intervensions 100 harvest days were undertaken to demonstrate the project interventions and its positive impacts. | HS
| 1.5. Building resilience through livestock and poultry production' | Train 9000 beneficiaries on specifics of animal raising/keeping introduce bees and ducks for in-kind loans in collaboration with partners NGOs to 3000 beneficiaries | 20357 were trained on specifics of raising/keeping of duck Equipment provided to Ten vet units that benefited 10652 benficairies during the reporting period Ducks and honey bees were introduced as inkind loans for 16731 beneficiaries. Goat loans were recycled to 1603 new beneficiaries. | HS
| 2.1. Training of government technical staff | Training the PMU staff on related technical topics 22 employees | *to improve the extension sector capacity to scale-up climate adaptation interventions,100 extension workers received 100 motorcycles from the project. training the 22 PMU staff on related topics including communication skills and project management 195 governmental focal points were trained on the utilization of the system developed under output 1.2 and the use of the andriod system to disseminate information among farmers. | HS
| Output 2.2 Documentation of lessons learned and best practice | produce 6 short animated documentaries, each focusing on one of the project interventions under component 1 | * 5 visibility materials (desk calendar and blocknote, desk organiser) were designed , printed and used for dissemination among partner agencies, and national local authorities, including local and national political representatives. * project website was kept updated * 5 Facebook groups were maintained with 7000 beneficiaries, the groups are successfully linking project experts, local youth and volunteers *7 documentaries were produced on the project interventions for climate-resilience. The CDs are disseminated to concerned stakeholders including the governorates, NGOs and the Ministry of Agriculture. | HS
| 2.3Sharing project results and lessons learned and mainstreaming new approaches in local and national planning | Annual workshops that join project actors from community, department, regional and national level to discuss opportunities and constraints, and share experience and learning for 80 participants Periocal meetings of local and project steering and technical committees held | *6 Presentations were made to the Minister of Agriculture and senior government officials *15 Site visits organized bringing 120 relevant officials to visit the project fields and see the achievements * A total of 32 meetings were convened for local steering, Project steering and technical committees * Annual workshops were organised, brining together 73 project actors from community, department, regional and national levels organized to discuss opportunities and constraints, and share experience and learning. | HS
| Output 2.4. Integration of climate adaptation solutions into University curriculum | Organization of student trainings and field visits for 50 students | *25 trainings organized-700 students from three universities participated in trainings and field visits to the project sites to get exposed to project interventions in climate adaptation . | HS
|  |  | Overall Rating | HS
Training of 200 governemental focal points on utilization of the system developed under output 1.2 and means of disseminating information
Please Provide the Name and Contact information of person(s) responsible for completing the Rating section
Name: | Eng. Othman El Shaikh, Project Manager
Email: | othmanelshaikh@gmail.com
Please justify your rating. Outline the positive and negative progress made by the project since it started. Provide specific recommendations for next steps. . (word limit=500) | The project proceeded to gain a good step towards reaching expected outcomes during this year of implementation. In particular, the project has made excellent progress in activities on the ground, such as water supply interventions, early warning solutions to extreme weather events, and in-kind micro-credit schemes. The PMU has developed powerful structures to complete the necessary arrangements for implementation - after learning the lessons during the first five years of implementation - and the implementation on the ground is going excellently. The PMU and government counterparts have also been able to find cost-effective ways of implementing activities (including extensive community engagement), which means that the project reaches its objectives and results within the allocated budgets. This has allowed (and will continue) to raise the level of project intervention to nearby villages. No significant risks affecting project progress are recognized. Overall, because of the project for excellent interventions on the ground, I will assess the project's performance as satisfactory to a high degree of Highly Satisfactory.
|  |  | Progress to Date | Rating
Progress on Key Milestones
Implementing Agency | 1.1. Community level mobilization and climate adaptation planning (including awareness) | Continue mobilization of volunteers for awareness raizing. Dissemination of project interventions through theater in the targeted villages and neighboring for 5000 beneficiaries | The project continued to engage more volunteers to efficiently and effectively raise awareness of climate change and how it can be adapted to. With a total number of 855 volunteers, the project was able to upscale its different intervensions in 49 villages. The use of attractive community mobilzation techniques, namely on-farm theater, continued where 132 performances were staged to date reaching some 21605 beneficiaries. | HS
| 1.2. Establishment of a climate change and food security monitoring system | Continued use of early warning system and disseminination of alerts through the climate information centers in the partner NGOs. spread early warning messages by localized short messages SMS to 5000 SMSs | Use of the early warning system continued successfully, were 95,000 usages of the on-line version were recorded. In addition, 10000 farmers got messages of the system through extension officers and local stations established in the climate information centers established by the project in the partner NGOs. A minimun of 210,000 farmers are estimated to have benefited indirectly through the verbal spreading of the warning alerts within the villages (word of mouth). The system supported farmers reduce their wheatand maize losses due to 2 heat waves to an average of 5%, compared to a 40% loss rate reported by other farmers. Dissemination of alert messages through SMS was delayed as dicsussions on sustainable mechanisms for funding of service after the project lifetime is taking longer than anticipated. | s
| 1.3. Introduction and use of water saving irrigation and other adaptation techniques | 75 new Water User Associations to be established. Follow- up on water user associations and promoting adoption of water saving techniques for 5000 beneficiaries | 75 New Water user associations were established under the project during the reporting period, bring the total associations established by the project to 120, all continued to operate effecitvely. Introduction of canal lining, soil laser leveling and other soft irrigation management techniques continued successfully and actvities were achieved as planned. The installation of solar panels was successfully completed during this reporting period. | HS
| 1.4. Building resilience in agricultural production | extension fields and on-farm training for introduction of heat tolerant varieties of common crops & dissemination of changing of sowing dates and intercropping practices to 3000 benefciaries extension fields for introduction improved agricultural techniques for cash crops cultivation to 100 benefiacaries . Enhancing the value of cash crops by introducting simple post-harvest equipment anf on- farm training to 5000 beneficiaries on-farm training to introduce heat tolerant varieties of common crops such as wheat, maize, sorghum and water-saving sugar cane varieties & dissemination of changing of sowing dates and intercropping practices in addition to the introduction of heat tolerant varieties and techniques of cash crops such as pomegranate green beans, banana, basilicum, and tomato for 2000 benefciaries Farm-to-farm visits for 100 beneficiaries | The dissemination of varieties with improved weather shock tolerance and reduced water consumption continued, reaching more beneficairies. Improved agricultural practices including raised bed cultivation, change of sowing dates and modified stem spacing also continued. The models for Intercropping of fava-beans with sugar cane and wheat with sugar cane were further dissimated. Very positive results were recorded- including 35% increases in productivity and 20-25% savings in water. These results were widely dissiminated through festive harvest days that were very effective in case-showing the achieved results for up scaling and replication throughout the villages. All planned targets under this output were successfully achieved. | HS
| 1.5. Building resilience through livestock and poultry production' | Train 9000 beneficiaries on specifics of animal raising/keeping introduce bees and ducks for in-kind loans in collaboration with partners NGOs to 3000 beneficiaries | Operationalization of the animal loans schemes continued successfully in the 5 governorates, recaching a total of 18334 since project start. The project- supported vet units are successfully serving some 10650 from the beneficiaries of the animal loans as well as other animal keepers from the project villgaes as well as neighbouring villages. Partner NGOs continue to successfully manage the loans and the on-farm breading programme for the goats under the revolving fund scheme. Duck loans contined, with a very high demand rate. | HS
| 2.1. Training of government technical staff | Training the PMU staff on related technical topics 22 employees | During the reporting period, 22 employess of the project PMU have been trained on several aspects including communication and strategic management. This brings the total of people benefiting fronm capacity building since the project start to 100 extension, 22 project staff and 195 governmental focal points. | HS
| Output 2.2 Documentation of lessons learned and best practice | produce 6 short animated documentaries, each focusing on one of the project interventions under component 1 | * 5 visibility materials (desk calendar and blocknote, desk organiser) were designed , printed and used for dissemination among partner agencies, and national local authorities, including local and national political representatives. * project website was kept updated * 5 Facebook groups were maintained with 7000 beneficiaries, the groups are successfully linking project experts, local youth and volunteers *7 documentaries were produced on the project interventions for climate-resilience. The CDs are disseminated to concerned stakeholders including the governorates, NGOs and the Ministry of Agriculture. | S
| Output 2.3 Sharing project results and lessons learned and mainstreaming new approaches in local and national planning | Annual workshops that join project actors from community, department, regional and national level to discuss opportunities and constraints, and share experience and learning for 80 participants Periocal meetings of local and project steering and technical committees held | The project has been made visible at several levels through presentations to the minister of Agriculture and other senior officials. Site visits have also been effectively undertaken. However, it was not possible to organise events for project beneficiaries to share their experineces with others due for upscaling due to shortage of time during this reporting period. The annual workshop of the project implemented, successfully bring the different stakeholders together for experience sharing and team building. | s
| Output 2.4. Integration of climate adaptation solutions into University curriculum | Organization of student trainings and field visits for 50 students | The project successfully engaged 516 students during the repoting period. The project continued to collaborate with 3 Universities and 5 secondary schools | HS
|  |  | Overall Rating | HS
Please justify your rating. Outline the positive and negative progress made by the project since it started. Provide specific recommendations for next steps. . (word limit=500) | The project continued its highly satisfactory performance during the reporting period. It continued to effectively gain villager's trust through mobilization and demostration of effecitve and substantial results . It also allowed it to expand to new neighbouring villages, where now the project supports 49 villages. The project also supported wheat and maize farmers to effectively face two extreme weather spells by effectively alerting farmers on upcoming extreme weather events and offer recommendations on how to reduce losses. New beneficiaries were exposed to physical and soft water savings technicques , effectively supporting them to realise 35% reductions in water consumption. Although, the work plan of the reporting period did not include installation new solar pumps, training of new farmers on its use and benefits continues. Comparison of actual verses planned progress of all the outputs, concludes that the project has progressed very well during this reporting period.
Please Provide the Name and Contact information of person(s) responsible for completing the Rating section
| Name: | Dr. Ithar Khalil, Head of Resilience Building Unit, WFP Egypt
| Email: | ithar.khalil@wfp.org
Please justify your rating and address the following points: 1. Indicate trends, both positive and negative, in achievement of outcomes as per the project indicators. 2. Detail critical risks that have affected progress. 3. Outline response to MTR undertaken this reporting period. 4. Outline action plan to address projects with a rating of HU, U or MU. Please keep your input to 1200 words

## Project Indicators
PROJECT Indicators
Please provide all indicators being tracked for the project as outlined in the project document
Type of Indicator (indicators towards Objectives, Outcomes, etc…)
Type of Indicator | Indicator | Baseline | Progress since inception2018 | Progress since inception to April 2019 | Target for Project End
Objective | Proportion of Southern Egypt farming communities that are more climate resilient through adoption of water efficient irrigation, risk reduction measures in agriculture and livestock, diversified income sources, and access to early warning systems and adaptation guidance | Over 90% of southern Egypt rural inhabitants are vulnerable to climate change and variability and demonstrate low level of knowledge of risk reduction measures | Although it is coming to our attention that increasing numbers of farmers from neighbouring villages and districts are interested in replicating project interventions, an in-depth assessment is needed to quantify the percentage of people replicating throughout the Southern zone. | Although it is coming to our attention that increasing numbers of farmers from neighbouring villages and districts are interested in replicating project interventions, an in-depth assessment is needed to quantify the percentage of people replicating throughout the Southern zone. | Over 50% of southern Egypt farming communities practice risk reduction measures
Outcome 1 | Percentage of target population in Southern Egypt demonstrating knowledge of climate change and variability and means to reduce risk to their livelihoods | 30% of sample interviewed as part of the baseline assessment knew about climate change with varied levels of understanding | An estimated 80% of target population understand climate change phenomenon, risks to livelihoods, and adaptation solutions | An estimated 87% of target population understand climate change phenomenon, risks to livelihoods, and adaptation solutions | Over 90% of target population understand climate change phenomenon, risks to livelihoods, and adaptation solutions
| Number of people adopting optimal efficiency in irrigation using low-cost technologies Such as; • Canal lining and other surface irrigation low-cost solutions • Water user associations established and active in effective management of water resources and waterways | More than 90% of people reported doing clearing of canals. Less than 1% reported adopting any other measures to conserve water. No water associations available | • 120 water user associations have been established. • 19000 direct beneficiaries started adopting improved efficiency in irrigation using low cost technologies where canal lining activities have been finished in14 in addition to 35 neighboring villages of the project villages. Canals to be lined were selected in partnership with local communities and the engineering designs and cost estimates have been prepared by local experts . | • 120 water user associations have been established. • 20336 direct beneficiaries started adopting improved efficiency in irrigation using low cost technologies where canal lining activities have been finished in14 in addition to 35 neighboring villages of the project villages. Canals to be lined were selected in partnership with local communities and the engineering designs and cost estimates have been prepared by local experts . | Over 20,000 direct and 28000 indirect people adopting optimal efficiency in irrigation using low-cost technologies A minimum of 12 water user associations established and actively operating
| Number of people adopting at least one climate risk reduction measure in agriculture and livestock | 1,800 people reported adopting at least one risk reduction measure in agriculture and livestock. | 35,000 direct farmers and extension workers are adopting some climate risk reduction measures in agriculture and livestock . In addition of 70,000 indirect beneficiaries. | 35,000 direct farmers and extension workers are adopting some climate risk reduction measures in agriculture and livestock . In addition of 70,000 indirect beneficiaries. | 38,000 direct and over 100,000 indirect people adopting at least one climate risk reduction measures in agriculture and livestock
output 1.1 | Number of people participating in awareness sessions and mobilized to participate in project activities | Baseline value are those people who participated in the baseline survey conducted as part of project preparation, which are over 1500 people | 119,500 people participated in awareness sessions and mobilized to participate in project activities | 120,901 people participated in awareness sessions and mobilized to participate in project activities | Over 130,000 people over the project life
output 1.2 | Number of people using the system | Zero, because no such system is in place at the moment | 74,000 have direct access to the software. It is estimated that 115,000 indirect beneficiaries are reached. In addition, the software now generates early warning messages for wheat maize sorghum and sugar cane . | 74,000 have direct access to the software. It is estimated that 115,000 indirect beneficiaries are reached. In addition, the software now generates early warning messages for wheat maize sorghum and sugar cane . | Over 100 direct participants in Cairo and participating governorates trained to use the system
| Number of people benefiting from the system with climate information, early warning and adaptation guidance | Zero, because no such system is in place at the moment |  |  | Over 130,000 direct beneficiaries from the system and over one million indirect beneficiaries from the potential scale-up of system use.
Output 1.3 | Number of acres benefiting from optimal irrigation efficiency using low-cost solutions. | Less than 1% at the baseline | 4,962 acres directly benefited from 60 water users associations established and water saving activates | 4,962 acres directly benefited from 60 water users associations established and water saving activates | Over 4000 acres directly benefiting
| Proportion of target communities benefiting from adequate services of water users associations. | Zero at the baseline because no water users associations were established in the target zone. | To date all canals undergoing efficiency improvement benefited from water users associations under the umbrella of local NGOs . | To date all canals undergoing efficiency improvement benefited from water users associations under the umbrella of local NGOs . | All canals undergoing improved irrigation efficiency will also benefit from water user associations established and strengthened under the project.
output 1.4 | Number of people from among the target population benefiting from demonstration farms, extension services, and farm-to-farm visits to enhance their resilience and reduce climate risks. | None of the population are currently benefiting from any interventions for this purpose. | To date, 35,598 people benefited directly from the project activities that provided access to heat resistant strategic plants (wheat and sorghum , sugar cane and maize), as well as how to change sowing dates, and other soft techniques to reduce climate risks. In addition, some 89,500 people benefited indirectly through seeing the achieved results and adopting the introduced practices in their own fields. | To date, 41,871 people benefited directly from the project activities that provided access to heat resistant strategic plants (wheat and sorghum , sugar cane and maize), as well as how to change sowing dates, and other soft techniques to reduce climate risks. In addition, some 95,816 people benefited indirectly through seeing the achieved results and adopting the introduced practices in their own fields. | Over 37,000 people benefit directly and over 100,000 indirectly benefiting from access to heat resistant strategic plants, as well as learn how to change sowing dates, and other soft techniques to reduce climate risks.
output 1.4 | Number of people engaged in income diversification strategies to reduce risks and vulnerability of food security to climate. | Less than 5% of people are engaged in income diversification strategies. | 7,000farmers were engaged in intercropping activities and high value crops | 7,000farmers were engaged in intercropping activities and high value crops | The above figure includes about 10,000 beneficiaries are engaged in income diversification schemes (intercropping, high value crops, and/or organic farming
Output 1.5 | No. of women trained on risk reduction in raising large ruminants, small ruminants and poultry; animal nutrition and alternative fodder. | Zero women trained on climate risk reduction to livestock | 25,500 beneficiaries from the training on reduction techniques of climate risk to livestock | 29,260 beneficiaries from the training on reduction techniques of climate risk to livestock | Over 36,000 women will be trained on reduction techniques of climate risk to livestock
Output 1.5 | Proportion of women accessing adequate vet services in their villages as it relates to climate related risks and diseases. | About 98% of respondents to the baseline survey indicated inadequacy of vet services in their villages. | 90 % borrowers engaged in raising livestock will have access to proper vet services equipped to reduce climate risk | 90 % borrowers engaged in raising livestock will have access to proper vet services equipped to reduce climate risk | Over 90% of women engaged in raising livestock will have access to proper vet services equipped to reduce climate risk
Output 1.5 | Number of women benefiting from small loans to acquire heat tolerant livestock varieties. | No access to specialized livestock financing schemes is currently available in target communities. | 17,500 women benefiting from small loans to acquire heat tolerant livestock varieties | 26,117 women benefiting from small loans to acquire heat tolerant livestock varieties | 18,200 women will have access to specialized livestock revolving schemes during project life.
Outcome 2 | % increase in budget allocated to adaptation in local, regional and national plans. | Zero | Senior governmental officials indicated that the interventions introduced by the project will be added to the National Campaign to increase the productivity of wheat as of next year. *requests from local authorities and MALR seniors to scale up the project interventions in different directs . * Most of the project interventions are included in the national climate adaptation plan. | Senior governmental officials indicated that the interventions introduced by the project will be added to the National Campaign to increase the productivity of wheat as of next year. *requests from local authorities and MALR seniors to scale up the project interventions in different directs . * Most of the project interventions are included in the national climate adaptation plan. | A positive trend sufficient to sustain and scale-up interventions of this project
Outcome 2 | Key institutions needed capacity development to deliver services for climate risk reduction in rural communities. | There are no programs or staff dedicated to adaptation services in key local governmental and non-governmental institutions. | 45 Climate information centres have been established in partner NGOs to deliver services for climate risk reduction. In addition 45 similar centres have been established in the disrict-level offices of the agricultural directorates of the 5 project governorates. The NGO centres have 300 dedicated volunteers while there are 2 staff members in each government center. In addition a MOU has been signed between BMU and extension sector in the ministry of agriculture aimed to host the early warning units in the MALR organogram . | 51 Climate information centres have been established in partner NGOs to deliver services for climate risk reduction. In addition 51 similar centres have been established in the disrict-level offices of the agricultural directorates of the 5 project governorates. The NGO centres have 340 dedicated volunteers while there are 2 staff members in each government center. In addition a MOU has been signed between BMU and extension sector in the ministry of agriculture aimed to host the early warning units in the MALR organogram . | Government programs developed to deliver: • Climate information hubs to scale up use of systems developed under output 1.2 • Adaptation knowledge and services embedded in government extension services • Revolving funds extending beyond the project areas to benefit other communities in Southern Egypt aiming to spread water conservation technologies and heat tolerant varieties in agriculture and livestock
Output 2.1 | Number of people trained; % of trainees that are able to properly retain message from training. | Training programmes for government on climate risk management to benefit rural communities will still be developed. Number of people trained is zero at the baseline. | *to improve the extension sector capacity to scale-up climate adaptation interventions,100 extension workers received 100 motorcycles from the project under MOU between the project and extension sector. * 250 governmental focal points have been trained on managment of agro- meteorological data, comunication skills, utilization of the system developed under output 1.2 and means of desemination information. 210 governmental focal points were trained on the utilization of the system developed under output 1.2 and the use of the andriod system to disseminate information among farmers. | *to improve the extension sector capacity to scale-up climate adaptation interventions,100 extension workers received 100 motorcycles from the project under MOU between the project and extension sector. * 250 governmental focal points have been trained on managment of agro- meteorological data, comunication skills, utilization of the system developed under output 1.2 and means of desemination information. 210 governmental focal points were trained on the utilization of the system developed under output 1.2 and the use of the andriod system to disseminate information among farmers. | Software developed and launched nationally to link climate stations belonging to different government agencies together, and developing adaptation guidance for each climate scenario for use by online users nationwide.
Output 2.1 | Number of advocacy meetings | Zero | * 300 officials at local and central government, as well as parliament, aware of climate proofing agriculture and water management. * The Egyptian Parliament stressed the importance of disseminating climate adaptation interventions and commended the project interventions. | * 300 officials at local and central government, as well as parliament, aware of climate proofing agriculture and water management. * The Egyptian Parliament stressed the importance of disseminating climate adaptation interventions and commended the project interventions. | 300 officials at local and central government, as well as parliament, aware of climate proofing agriculture and water management
Output 2.2 | Number of awareness materials printed | No materials are produced on climate risk reduction in agriculture | *seven brochures, 121press releases issued, 6 visibility materials (desk calendar and blocknote, desk organiser) were designed, printed and disseminated and more than (50) articles were written about the project. *7 documentary film produced on project interventions and disseminated to concerned stakeholders. | *seven brochures, 121press releases issued, 6 visibility materials (desk calendar and blocknote, desk organiser) were designed, printed and disseminated and more than (50) articles were written about the project. *7 documentary film produced on project interventions and disseminated to concerned stakeholders. | • At least five different printed products • At least 4 different press releases issued
output 2.2 | Number of online messages | Zero | 5 Facebook groups, one for each governorate, were maintained with an average number of 7000 participants in each. In addition, aYoutube channel with 1000 views is effectively used. As well as the project website was kept updated. * In addition to 35000 visits to the project website | 5 Facebook groups, one for each governorate, were maintained with an average number of 7000 participants in each. In addition, aYoutube channel with 1000 views is effectively used. As well as the project website was kept updated. * In addition to 35000 visits to the project website | At least 10
output 2.2 | Number of TV spots and programmes aired. | Zero | *35 Tv spots was produced and aired. * 25 radio interviews were conducted with project stakeholders about the different intervensions and success in their villages | *35 Tv spots was produced and aired. * 25 radio interviews were conducted with project stakeholders about the different intervensions and success in their villages | • At least 10 TV spots produced and aired • At least 10 radio spots produced and aired
output 2.3 | Number of awareness and advocacy events held for new parliamentarians and policy makers. | Zero | *80 advocacy events have been held for policy makers (presentations, site visits, events). * Annual workshop to discuss opportunities and constraints has been held for all active actors with the participation 70 participants. In addition, preparations to the annual workshop to be held in May. * Project mid-term evaluation was conducted in 2015. *10 Presentations were made to the Minister of Agriculture and senior government officials *60 Site visits organized bringing 301 relevant officials to visit the project fields and see the achievements *27 events were organized for beneficiaries to present their experiences to other potential beneficiaries, with 570 average number of beneficiaries in each * A total of 28 meetings were convened for local steering, Project steering and technical committees * Annual workshop was organised, brining together 70 project actors from community, department, regional and national levels organized to discuss opportunities and constraints, and share experience and learning. . | *80 advocacy events have been held for policy makers (presentations, site visits, events). * Annual workshop to discuss opportunities and constraints has been held for all active actors with the participation 70 participants. In addition, preparations to the annual workshop to be held in May. * Project mid-term evaluation was conducted in 2015. *10 Presentations were made to the Minister of Agriculture and senior government officials *60 Site visits organized bringing 301 relevant officials to visit the project fields and see the achievements *27 events were organized for beneficiaries to present their experiences to other potential beneficiaries, with 570 average number of beneficiaries in each * A total of 28 meetings were convened for local steering, Project steering and technical committees * Annual workshop was organised, brining together 70 project actors from community, department, regional and national levels organized to discuss opportunities and constraints, and share experience and learning. . | At least 10
Output 2.4 | Number of students benefiting from lessons learned from project interventions | Zero | *2145 university students from three universities participated in project interventions in climate adaptation and have been trained on compute skills. | *2195 university students from three universities participated in project interventions in climate adaptation and have been trained on compute skills. | 300 yearly from the 3 key universities in Southern Egypt

## Lessons Learned
`
QUALITATIVE MEASURES and LESSONS LEARNED
Please complete the following section every reporting period
| Implementation and Adaptive Management | Response
| What implementation issues/lessons, either positive or negative, affected progress? | * Mobility of extension workers was supported by motorcycles during the reporting period. This significanlty impacted their outreach and ability to disseminate good practices from the project to much wider circles of farmers beyond the project villages and throughout the different districts of the project governorates. *The deployment of volunteers to mobilize communities and raise awareness is very effective in the catalysing the spread to new neighbouring villages
| Were there any delays in implementation? If so, include any causes of delays. What measures have been taken to reduce delays? | Due to late project start-up, and although the current reporting period is referred to as YEAR 6, it technically and financially refers to the targets of YEAR5 in the project document. For synchronization, the annual work plan and forecast expenditures of the reporting year were developed in relation to the actual start date of the project.
| Describe any changes undertaken to improve results on the ground or any changes made to project outputs (i.e. changes to project design) | No material changes have been made to the project document since the start of implementation.
| How have gender considerations been taken into consideration during the reporting period? What have been the lessons learned as a consequence of inclusion of such considerations on project performance or impacts? | As is normally the practice for any WFP projects, gender equality is encouraged at all levels, such as membership of steering and project support commitees, project staff, loans beneficiaries and other activities. -The Agro-processing activities included the construction of two units for sub-bed drying of tomatoes and pomegranate peeling. Managed by the local NGOs, women were the primary target of the labor force of these units. Like the animal loans, these units introduced the concept of adding value to crops to significantly increase their selling price and have created a new livelihood for women in the villages. - The project also had positive effects on women empowerment that went beyond what was foresen in the project design. Whilst the loans scheme aimed to diversify income sources through animal keeping projects for women (taking into consideration the cultural norms), it was noted that the new income from these loans continued to allow the women to take up new occupations by setting up SMEs and trading clothes and handicrafts. This created a micro economy within the project areas that is run by women.
Please complete the following section at mid-term and project completion
| Lessons for Adaptation | Response
Climate Resilience Measures
| What have been the lessons learned, both positive and negative, in implementing climate adaptation measures that would be relevant to the design and implementation of future projects/programmes for enhanced resilience to climate change? | Building climate resilience is a multidimensional issue in which several stakeholders have different, yet complementary roles to play. To effectively achieve its objectives, such measures thus involve cooperation among numerous stakeholders, at the central, regional and local levels. Innately, each of these stakeholder groups had its own needs, priorities, governance and/or governing regulations as well as way of doing things. Thus measures and tools are needed to integrate inputs, create synergies and facilitate cooperation among these diversified players, towards the successful and sustained realization of the project objectives. Many lessons can be drawn from the consultative approach used by the project to enhance stakeholder engagement and building ownership and how this has affected efficiency, effectiveness and potentials for sustainability after its lifetime. In particular: *Intensive consultations with the different stakeholders at the early phases of the project cycle was a good means for their engagement. Likewise, their involvement in different committees had benefits on several fronts. Firstly, and as each stakeholder group provided input from its own perspective, these consultations provided a good platform for integrating and complementing these multi-dimensional inputs in a way that enriched the design. Secondly, it created a sense of involvement that gradually evolved into ownership of the different activities, and triggered their support in the different phases of the project. It has also initiated a team-spirit that smoothened effective collaboration towards one goal. *Deployment of local volunteers has been effective in many aspects. Being from the same villages, they substantially facilitated the project outreach and community mobilization activities. The deployment of female volunteers has been very effective as it supported activities that would have otherwise been difficult e.g. the household visits, and thereafter women’s participation in project activities. Entrusting volunteers with management of outputs such as the climate information centers after the project lifetime will also effectively enhance sustainability of such outputs. *The involvement of stakeholders at the different local, sub-national and national levels has supported the project in several ways. The support of the local committees enhanced the daily management of the activities. Higher-level committees, on the other hand, gave longer-term support and guidance. Engaging senior-level officials, they were effective tools in addressing major challenges faced by the project. They were also effective in the duplication and upscaling of project activities on a wider geographical coverage. *Brining representatives from all the project villages together with senior governmental officials as well the technical experts of the interventions they are implementing annually was very effective. It created a heterogeneous network of practitioners that shares experiences across the governorates, discusses challenges and highlights success stories, provides technical and managerial support as needed and shapes the project interventions in the upcoming year. Equally important, it creates sustainable working relationships that would help these key players maintain and even further develop the activities in the future.
| What is the potential for the climate resilience measures undertaken by the project/programme to be replicated and scaled up both within and outside the project area? | Replication and upscaling of many of the project interventions is already done by farmers in the project villages. Local units and NGOs from other villages have also approached the project to expand its activities to their villages. New interventions are adopted by different governmental authorities such as extension campaign for sorghum, wheat vegetables, and sugarcane.
Concrete Adaptation Interventions
| What have been the lessons learned, both positive and negative, in implementing concrete adaptation interventions that would be relevant to the design and implementation of future projects/programmes implementing concrete adaptation interventions? | * There are several ways to implement climate adaptation interventions. Generally, approaches that empower partners, engage stakeholders or seek more profound impact take longer to implement than others. However, on the longer term such activities are more sustainable and are more effective in implementation of concrete adaptation interventions. For example, building the capacity of local partners and then entrusting them with hosting and operating assets such as climate information centers is more sustainable than directly offering climate information to farmers through the project, as it would cease after its life time. *the use of domestic varieties, national experts and low-cost techniques is a good means for enhancing sustainability of adaptation interventions. It is supports upscaling and replication. *As climate impacts household’s livelihoods and food security in several ways, an integrated approach that deploys several interventions such as enhancing crop tolerance, increasing productivity, improving natural resources usage efficiency, diversification of income sources, etc is needed to effectively build resilience.
| What is the potential for the concrete adaptation interventions undertaken by the project/programme to be replicated and scaled up both within and outside the project area? | Many of the project intervensions are already being replicated both in the project villages as well as in new villages. The project intervensions in wheat have already been adopted by the National Wheat campaign for ntaional upscaling.
Community/National Impact
| What would you consider to be the most successful aspects for the target communities? | The project's positive results achieved in building the communities resilience to climate impacts on their food security and livelihoods. In particular, the project's ability to safeguard production against weather spells, enhance efficiency of natural resources usage and diversify incomes are among the most successful aspects that have profoundly impacted the project communities.
| What measures are/have been put in place to ensure sustainability of the project/program results? |  The Ministry is an essential partner in the project and a main beneficiary of its results. AS SUCH, AND WITNESSING THE POSITIVE RESULTS, IT WOULD BE IN ITS BEST INTEREST TO SUSTAIN THE ACTVITIES.  The project’s unprecedented reliance on the full participation of the target groups and their organizations at community level in all stages.  The project’s coordinating committees, from the central level to the grassroots level, includes representatives from many ministries and governmental authorities, and the project succeeded in creating strong linkages with these. The project’s alignment, not just with the national strategies and priorities, but also its alignment with and direct participation in the technical aspects of the Ministry of Agriculture’s action plans. This was represented in the project’s adoption of the varieties that the ministry targets spreading as part of its strategy. It was also seen in the adoption of raised bed farming, and the rehabilitation of Mesqas, both of which are part of the Ministry of Agriculture’s nationwide aims. Furthermore, the project makes a major contribution to the National Wheat Campaign through applying and spreading the general recommendations issued by the Crop Research Institute (affiliated to the Ministry of Agriculture), especially Upper Egypt. All these factors create a direct benefit for state organizations in supporting the project’s sustainability on an institutional level and merging its components within its structure.  The inclusion of the project’s offices, whether the headquarters or the governorate offices, inside governmental directorates, and through official decisions. Further, in order to protect the project’s headquarters in light of the repeated changes in leadership, the existence of an institutional governmental party that takes responsibility for, and participates or takes complete ownership of all the project’s activities  The project’s reliance in its technical aspects on permanent official research bodies, some of which are affiliated with regional universities, while other are affiliated to governmental research centers (most of them are affiliated with the agricultural research centers affiliated to the Ministry of Agriculture). Even the experts who cooperated with the project on an individual basis belong to the same authorities, which created organic ties and mutual concerns in the project with the related research institutes  The project’s reliance in its agricultural components on domestic varieties, which were recommended by Egyptian research institutes, rather than imported crops. This increases the chances of sustaining execution through the existing mechanisms, whereby it would have been much more complicated and difficult had the project relied on imported seeds, especially as the seeds used are breeding (fundamental) seeds, which means they can be used for replanting for 4-5 years  The existence of a simplified plan and explicit or implicit agreements for the handover after the completion of the project  The office space of the Headquarters is additionally secured through an open-ended legal lease contract, so long as the project continues the formalization of relations with the partner authorities, and documenting in different ways through cooperation agreements that define current and future responsibilities - The project capacity building of and reliance on local stakeholders, namely local NGOs for the management of the different activities/ outputs
| What measures are being/could have been put in place to improve project/program results? | Several measures have been adopted to improve results. Examples of this include use of innovative techniques such as theatre performances to mobilize the communities. Likewise, the use of live performances rather than recorded replays for stronger results is another example. The different activities undertaken to build the capacity of the partner NGOs for example to enhance their management and communication skills has improved their abilities to engage with community members and effectively manage the different activities. The capacity building of the WUAs has improved their abilities to undertake the different water management activities. The change of the goats’ supplier has also improved the types and physical conditions of the goats received. Likewise, the extension of the goats’ loan cycle to be 12 instead of 6 months is also to improve the results from this lending mechanism.
Knowledge Management
| How has existing information/data/knowledge been used to inform project development and implementation? What kinds of information/data/knowledge were used? | Several studies on climate effects on agriculture and associated economic impacts in Egypt have been consulted during the development of the project. Information and data from several studies, reports and publications on the socio-economic status of the Southern Egypt area has also been key in the design of the project. As mentioned in the project document, intensive consultations with the various stakeholders of the project has also generated a wealth of information that has effectively influenced the design of the different interventions and implementation mechanisms of the project. During implementation, the project generates reports that are shared with the different stakeholders for dissemination of information. The Steering Committee convenes regularly to review project technical reports. The project also produces several knowledge products such as flyers, brochures, visibility printed materials as well as on-line materials that the different project stakeholders and local governments have access to. In addition, the project stakeholders had the opportunity to visit project activities in the field and compare studies with local scenarios. Feedback received from the various stakeholders engaged in the different activities/ committees informs the implementation.
| If learning objectives have been established, have they been met? Please describe. | Yes, as indicated in the project annual reports issued so far, several governmental focal points and officials, volunteers, community members and farmers have been trained on several aspects such as communication skills, climate-smart agriculture, strategic planning, computer skills, and animal keeping among others. NGO members have been capacitated in the domains of financial and project management as well as loans management. Through its engagement with academia, the project has supported the learning of university and secondary agriculture of climate adaptation techniques in agriculture.
| Describe any difficulties there have been in accessing or retrieving existing information (data or knowledge) that is relevant to the project. Please provide suggestions for improving access to the relevant data. | NA
| Has the identification of learning objectives contributed to the outcomes of the project? In what ways have they contributed? | The project design and implementation has given ample learning opportunities, not only from the results, but also from the different processes. Its participatory approach engaged the different stakeholders in a way by which they learned about climate change, its impacts on agriculture, different adaptation techniques as well as how such techniques could be deployed to safeguard livelihoods against climate impacts. This on-the job training, along with the different course trainings, technical support, exchange visits, and other forms of learning has enabled the different stakeholder groups to realize how they can effectively contribute to building resilience and has substantially enhanced their capacities to actually assume responsibilities in this regards, contributing to the different project outcomes.

## Results Tracker
Results Tracker for Adaptation Fund (AF) Projects
Goal: Assist developing-country Parties to the Kyoto Protocol that are particularly vulnerable to the adverse effects of climate change in meeting the costs of concrete adaptation projects and programmes in order to implement climate-resilient measures. Impact: Increased resiliency at the community, national, and regional levels to climate variability and change.
Important: Please read the following guidance document (also posted on the Adaptation Fund website) before entering your data
Link: http://www.adaptation-fund.org/sites/default/files/Results%20Framework%20and%20Baseline%20Guidance%20final.pdf
Adaptation Fund Strategic Results Framework
Project ID | EGY/MIE/Food/2011/1
Implementing Entity | WFP
Type of implementing entity | MIE
Country | Egypt
Region | Africa
Sector | Agriculture
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Impact: Increased resiliency at the community, national, and regional levels to climate variability and change | Core Indicator: No. of beneficiaries |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project
|  | Total | 0 | 0 | 0 | Total | 48000 | 20000 | 28000 | Total | 26000 | 14000 | 12000 | Total
|  | % of female beneficiaries | 0% | 0% | 0% | % of female beneficiaries | 40% | 40% | 40% | % of female beneficiaries | 25% | 25% | 25% | % of female beneficiaries
|  | % of Youth beneficiaries | 0% | 0% | 0% | % of Youth beneficiaries | 20% | 20% | 20% | % of Youth beneficiaries | 11% | 11% | 11% | % of Youth beneficiaries
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 1: Reduced exposure to climate-related hazards and threats | Indicator 1: Relevant threat and hazard information generated and disseminated to stakeholders on a timely basis | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness
|  | Total | 0
Output 1.1 Risk and vulnerability assessments conducted and updated | Indicator 1.1: No. of projects/programmes that conduct and update risk and vulnerability assessments | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
Output 1.2 Targeted population groups covered by adequate risk reduction systems | Core Indicator 1.2: No. of Early Warning Systems | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
Geographical coverage
[5 empty] | 0 | [10 empty] | Number of municipalities
|  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 2: Strengthened institutional capacity to reduce risks associated with climate-induced socioeconomic and environmental losses | Indicator 2: Capacity of staff to respond to, and mitigate impacts of, climate-related events from targeted institutions increased | Number of staff targeted |  | Sector | Capacity level | Number of staff targeted |  | Sector | Capacity level | Number of staff targeted |  | Sector | Capacity level | Number of staff targeted |  | Sector | Capacity level
|  | Total | 0 | Multi-sector | 1: No capacity | Total | 300 | Agriculture | 4: High capacity | Total | 180 | Multi-sector | 4: High capacity | Total
|  | % of female targeted | 0% |  |  | % of female targeted | 40% |  |  | % of female targeted | 35% |  |  | % of female targeted
Output 2.1 Strengthened capacity of national and sub-national centres and networks to respond rapidly to extreme weather events | Indicator 2.1.1: No. of staff trained to respond to, and mitigate impacts of, climate-related events | Total staff trained | % of female staff trained | Type |  | Total staff trained | % of female staff trained | Type |  | Total staff trained | % of female staff trained | Type |  | Total staff trained | % of female staff trained | Type
|  | 0 | 0% | Public |  | 440 | 35% | Public |  | 440 | 30% | Public
| Indicator 2.1.2: No. of targeted institutions with increased capacity to minimize exposure to climate variability risks | Type | Scale | Sector | Capacity level | Type | Scale | Sector | Capacity level | Type | Scale | Sector | Capacity level | Type | Scale | Sector | Capacity level
|  | NGO | Local | Agriculture | 1: No capacity | NGO | Local | Food security | 3: Medium capacity | NGO | Local | Food security | 4: High capacity
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 3: Strengthened awareness and owernship of adaptation and climate risk reduction processes | Indicator 3.1: Increase in application of appropriate adaptation responses | Percentage of targeted population applying adaptation measures |  | Sector |  | Percentage of targeted population applying adaptation measures |  | Sector |  | Percentage of targeted population applying adaptation measures |  | Sector |  | Percentage of targeted population applying adaptation measures |  | Sector
Output 3: Targeted population groups participating in adaptation and risk reduction awareness activities | Indicator 3.1.1: Percentage in targeted population awareness of predicted adverse impacts of climate change, and of appropriate responses | No. of targeted beneficiaries | % of female participants targeted | Level of awareness |  | No. of targeted beneficiaries | % of female participants targeted | Level of awareness |  | No. of targeted beneficiaries | % of female participants targeted | Level of awareness |  | No. of targeted beneficiaries | % of female participants targeted | Level of awareness
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Target performance at completion |  |  |  | Target performance at completion
Outcome 4: Increased adaptive capacity within relevant development sector services and infrastructure assets | Indicator 4.1: Increased responsiveness of development sector services to evolving needs from changing and variable climate | Project/programme sector | Geographical scale | Response level |  | Project/programme sector | Geographical scale | Response level |  | Project/programme sector | Geographical scale | Response level |  | Project/programme sector | Geographical scale | Response level
| Core Indicator 4.2: Assets produced, developed, improved or strengthened | Sector | Targeted asset | Changes in asset (quantitative or qualitative) |  | Sector | Targeted asset | Changes in asset (quantitative or qualitative) |  | Sector | Targeted asset | Changes in asset (quantitative or qualitative) |  | Sector | Targeted asset | Changes in asset (quantitative or qualitative)
Output 4: Vulnerable development sector services and infrastructure assets strengthened in response to climate change impacts, including variability | Indicator 4.1.1: No. and type of development sector services to respond to new conditions resulting from climate variability and change | Number of services | Type |  | Sector | Number of services | Type |  | Sector | Number of services | Type |  | Sector | Number of services | Type |  | Sector
|  | Baseline information |  |  |  | Baseline information |  |  |  | Baseline information |  |  |  | Baseline information
Outcome 5: Increased ecosystem resilience in response to climate change and variability-induced stress | Indicator 5: Ecosystem services and natural resource assets maintained or improved under climate change and variability-induced stress | Natural resource improvement level |  | Sector | Type | Natural resource improvement level |  | Sector | Type | Natural resource improvement level |  | Sector | Type | Natural resource improvement level |  | Sector | Type
Output 5: Vulnerable ecosystem services and natural resource assets strengthned in response to climate change impacts, including variability | Core Indicator 5.1: Natural Assets protected or rehabilitated | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Baseline information |  |  |  | Targeted performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 6: Diversified and strengthened livelihoods and sources of income for vulnerable people in targeted areas | Indicator 6.1: Increase in households and communities having more secure access to livelihood assets | No. of targeted households | % of female headed households | Improvement level |  | No. of targeted households | % of female headed households | Improvement level |  | No. of targeted households | % of female headed households | Improvement level |  | No. of targeted households | % of female headed households | Improvement level
| Indicator 6.2: Increase in targeted population's sustained climate-resilient alternative livelihoods | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
|  | 136000 | 0% | From 0 to 0.5% | Agriculture | 102000 | 10% | From 20% to 30% | Agriculture | 102000 | 4% | From 20% to 30% | Agriculture
|  | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
|  | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
|  | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
Output 6 Targeted individual and community livelihood strategies strengthened in relation to climate change impacts, including variability | Indicator 6.1.1: No. and type of adaptation assets created or strengthened in support of individual or community livelihood strategies | Number of Assets | Type of Assets | Sector | Adaptation strategy | Number of Assets | Type of Assets | Sector | Adaptation strategy | Number of Assets | Type of Assets | Sector | Adaptation strategy | Number of Assets | Type of Assets | Sector | Adaptation strategy
|  | 0 | Financial capital | Food security | Supporting livelihoods | 18200 | Physical capital | Food security | Microfinance | 7500 | Physical capital | Food security | Microfinance
|  | 0 | Physical capital | Water management | Strengthening infrastructure | 4000 | Physical capital | Water management | Strengthening infrastructure | 3900 | Physical capital | Water management | Strengthening infrastructure
| Core Indicator 6.1.2: Increased income, or avoided decrease in income | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 7: Improved policies and regulations that promote and enforce resilience measures | Indicator 7: Climate change priorities are integrated into national development strategy | Integration level |  |  |  | Integration level |  |  |  | Integration level |  |  |  | Integration level
Output 7:Improved integration of climate-resilience strategies into country development plans | Indicator 7.1: No. of policies introduced or adjusted to address climate change risks | No. of Policies introduced or adjusted | Sector | Scale | Type | No. of Policies introduced or adjusted | Sector | Scale | Type | No. of Policies introduced or adjusted | Sector | Scale | Type | No. of Policies introduced or adjusted | Sector | Scale | Type
| Indicator 7.2: No. of targeted development strategies with incorporated climate change priorities enforced | No. of Development strategies | Regulation |  | Effectiveness | No. of Development strategies | Regulation |  | Effectiveness | No. of Development strategies | Regulation |  | Effectiveness | No. of Development strategies | Regulation |  | Effectiveness
Glacier lake outburst flood
|  | Inland flooding | fr | biological assets |  | Company policy | 5: Fully enforced (All elements implemented)
|  | Salinization | Decrease | land |  | Communication & Information policy | 4: Enforced (Most elements implemented)
|  | Drought | Same | water areas |  | Defense policy | 3: Partially enforced (Some elements implemented)
|  | Wind |  | subsoil assets | increased adpative capacity | Domestic policy | 2: Partially not enforced (Most elements not implemented) |  | Agribusiness
|  | Coastal flooding |  | air | achieved | Economic policy | 1: Not enforced (No elements implemented) |  | Agricultural-related | Financial capital
|  | Storm surge | Please choose |  | enhanced level of protection | Education policy |  |  | Agriculture | Human capital
|  | Hurricane | Selected | [5 empty] | Aquaculture | Physical capital
|  |  | Not relevant |  |  | 5: All (Fully integrated) |  |  | Construction/repairing business | Social capital
[6 empty] | 4: Most |  |  | Cultivation | Natural capital
[6 empty] | 3: Some |  |  | Fishing | Personal capital
Select | 5: All | Select |  |  | Community | 2: Most not integrated |  | Other | Forestry | Adaptation strategies
1 | 4: Almost all | Private | Type | Yes | Multi-community | 1: None |  | Agriculture | Handicrafts
2 | 3: Half | Public | Scale | No | Departmental |  |  | Coastal management | Livestock production
3 | 2: Some | NGO | Sector |  | National |  |  | Disaster risk reduction | Manufacturing
4 | 1: None |  |  |  |  | 5: Very high improvement | Established | Food security | other
|  | National |  |  |  | 4: High improvement | Maintained | Health | Services
|  | Regional |  |  |  | 3: Moderate improvement | Improved | Urban development | Tourism-related
|  | Local |  |  |  | 2: Limited improvement |  | Water management | Trading
[6 empty] | 1: No improvement |  | Multi-sector
|  | 1 -generated information is irrelevant, and neither the stakeholders reached nor the timeframe managed were achieved | 1: No info transferred on time | 4: High capacity | 5: Fully aware | 5: Highly responsive (All defined elements ) | 5: Fully improved | Roads | 5: Very effective
Asia-Pacific | NIE | 2 -the existence of some challenge in any of the three aspects of the indicator (generation of dissemination, stakeholders reached or timeframe managed) | 2: Somewhat info transferred | 3: Medium capacity | 4: Mostly aware | 4: Mostly responsive (Most defined elements) | 4: Mostly Improved | Gov Buildings | 4: Effective
Latin America and Caribbean | RIE | 3 -relevant information is generated and disseminated to all identified stakeholders on timely basis | 3: Info transferred on time | 2: Low capacity | 3: Partially aware | 3: Moderately responsive (Some defined elements) | 3: Moderately improved | Causeways | 3: Moderately effective
Africa | MIE |  |  | 1: No capacity | 2: Partially not aware | 2: Partially responsive (Lacks most elements) | 2: Somewhat improved | Airports | 2: Partially effective
Eastern Europe |  |  |  |  | 1: Aware of neither | 1: Non responsive (Lacks all elements ) | 1: Not improved | Schools | 1: Ineffective
| ha protected | [6 empty] | Training Centres
| ha rehabilitated | [5 empty] | Monitoring/Forecasting capacity | Hospitals
Afghanistan, Islamic Rep. of | km protected | [5 empty] | Policy/regulatory reform | Drinking water systems
Angola | km rehabilitated | 1: Risk knowledge | 1: No plans conducted or updated |  |  |  | Capacity development | Other
Albania |  | 2: Monitoring and warning service | 2: Undertaking or updating of assessments in progress |  |  | Communication & Information policy | Sustainable forest management
Argentina |  | 3: Dissemination and communication | 3: Risk and vulnterability assessments completed or updated |  |  | Domestic policy | Strengthening infrastructure | 1: Health and Social Infrastructure (developed/improved)
Armenia | Forests | 4: Response capability |  |  |  | Economic policy | Supporting livelihoods | 2: Physical asset (produced/improved/strenghtened)
Antigua and Barbuda | Mangroves |  |  |  |  | Education policy | Mangrove reforestation
Azerbaijan | Coasts |  | From 0 to 0.5% |  |  | Energy policy | Coastal drainage and infrastructure
Burundi | Rangelands |  | From 0.5 to 1% |  |  | Environmental policy | Irrigation system
Benin | Cultivated land/Agricultural land |  | From 1% to 5% |  |  | Foreign policy | Community-based adaptation
Burkina Faso | Catchment area/Watershed/Aquifer |  | From 5% to 10% |  |  | Health policy | Erosion control
Bangladesh | Protected areas/National parks |  | From 10% to 20% |  |  | Housing policy | Soil water conservation
Bulgaria | Other |  | From 20% to 30% |  |  | Human resource policies | Microfinance
Bahrain |  |  | From 30% to 40% |  |  | Information policy | Special Program for women
Bahamas, The |  |  | From 40% to 50% |  |  | Macroeconomic policy | Livelihoods
Bosnia and Herzegovina |  |  | Above 50% |  |  | Monetary policy | Water storage
Belarus | [5 empty] | Population policy | ICT and information dissemination
Belize | [5 empty] | Private policy
Bolivia | [5 empty] | Public policy
Brazil | [5 empty] | Science policy
Barbados | [5 empty] | Social policy
Bhutan |  | 3- relevant information is generated and disseminated to all identified stakeholders on timely basis |  |  |  | Transportation policy
Botswana |  | describe |  |  |  | Urban policy
Central African Republic |  | 2- the existence of some challenge in any of the three aspects of the indicator |  |  |  | Water policy
Chile |  | describe |  |  |  | Other policy
China, People's Republic of |  | 1- generated information is irrelevant and neither the stakeholders reached nor the timeframe managed were achieved
Cote d'Ivoire |  | describe
Cameroon
Congo, Dem. Rep. of
Congo, Republic of
Cook Islands
Colombia
Comoros
Cape Verde
Costa Rica
Cuba
Czech Republic
Djibouti
Dominica
Dominican Republic
Algeria
Ecuador
Egypt
Eritrea
Estonia
Ethiopia
Fiji
Micronesia, Fed. States of
Gabon
Georgia
Ghana
Guinea
Gambia, The
Guinea-Bissau
Equatorial Guinea
Grenada
Guatemala
Guyana
Honduras
Croatia
Haiti
Hungary
Indonesia
India
Iran, Islamic Republic of
Jamaica
Jordan
Kazakhstan
Kenya
Kyrgyz Republic
Cambodia
Kiribati
Saint Kitts and Nevis
Korea, Republic of
Lao People's Democratic Republic
Lebanon
Liberia
Libya
Saint Lucia
Sri Lanka
Lesotho
Lithuania
Latvia
Morocco
Moldova
Madagascar
Maldives
Mexico
Marshall Islands
Macedonia, former Yugoslav Republic of
Mali
Malta
Myanmar
Montenegro
Mongolia
Mozambique
Mauritania
Mauritius
Malawi
Malaysia
Namibia
Niger
Nigeria
Nicaragua
Niue
Nepal
Nauru
Oman
Pakistan
Panama
Peru
Philippines
Palau
Papua New Guinea
Poland
Korea, Dem. People's Rep. of
Paraguay
Romania
Russian Federation
Rwanda
Saudi Arabia
Sudan
Senegal
Solomon Islands
Sierra Leone
El Salvador
San Marino
Serbia
Sao Tome and Principe
Suriname
Slovak Republic
Slovenia
Swaziland
Seychelles
Syrian Arab Republic
Chad
Togo
Thailand
Tajikistan
Turkmenistan
Tonga
Trinidad and Tobago
Tunisia
Turkey
Tuvalu
Tanzania
Uganda
Ukraine
Uruguay
Uzbekistan
Saint Vincent and the Grenadines
Venezuela
Vietnam
Vanuatu
Samoa
Yemen, Republic of
South Africa
Zambia
Zimbabwe
Timor-Leste

## Units for Indicators
Fund Outcome Indicator Units
1. Generation of relevant data, Stakeholders, and Timeliness 2.1. Include both qualitative and quantitative measures of capacity level within targeted institutions 2.2. Number (men and women and other vulnerable groups) 3.1. Use scale from 1 to 5: 5: Fully aware 4: Mostly aware 3: Partially aware 2: Partially not aware 1: Aware of neither predicted adverse impacts of climate change nor of appropriate responses 3.2. Use scale from 1 to 5: 5: All 4: Almost all 3: Half 2: Some 1: None 4.1. Summarize in an overall scale (1-5): 5: Highly responsive (All defined elements ) 4: Mostly responsive (Most defined elements) 3: Moderately responsive (Some defined elements) 2: Partially responsive (Lacks most elements) 1: Non responsive (Lacks all elements ) 4.2. Summarize in an overall scale (1-5): 5: Fully improved 4: Mostly Improved 3: Moderately improved 2: Somewhat improved 1: Not improved 5. Depends on the targeted natural asset: Biological (species): measure through changes in population numbers (dynamics, structure, etc.) Land: measure changes in hectares. Baseline data will be necessary to estimate the change. Supporting indicators baseline and target (as well as contextual information) are needed such as the following: Farmers adopting recommended technologies, Ha. of land improved, Average deforestation rate Etc. Use scale from 1 to 5. 5: Very effective (All elements are present) 4: Effective (Most elements are present) 3: Moderately effective (Some elements are present) 2: Partially effective (Most elements are not present) 1: Ineffective (No elements are present) 6.1. Summarize in an overall scale (1-5): 5: Very high improvement 4: High improvement 3: Moderate improvement 2: Limited improvement 1: No improvement 6.2. Household income by source of livelihood in project area (USD) prior and post project intervention 7. Summarize in an overall scale (1-5). 5: All (Fully integrated) 4: Most 3: Some 2: Most not integrated 1: None
Fund Output Indicator Units
1.1. Number, sector(s) and level(s) of projects or interventions in separate fields of monitoring plan 1.2. Number 2.1.1. Number of staff (male/female) of targeted institutions: a. Obtain baseline information: total number of staff from targeted institutions b. Define target 2.1.2. Number of staff (male/female) of targeted institutions: a. Obtain baseline information: total number of staff from targeted institutions b. Define target: needs to be defined by project proponents 2.2.1. Quantitative: Percentage (includes women – and other vulnerable groups – and men). Qualitative: Adequacy: include direct analysis of major areas; adequacy/effectiveness of systems or analysis of perceptions of populations and institutions. 2.2.2. Number (broken down by gender and, if possible, by vulnerable groups defined in the area of intervention) of people 3.1. Number and type (in separate columns) at local level. 3.2. Number 4.1. Number and type 4. 2. Number and type (entered in separate columns) 5. Number of interventions by type of natural asset and intervention 6.1. Number and type (in separate columns of monitoring plan) 6.2. Income sources per household; description of income source and number of households. 7.1. Number/Sector 7.2. Number; Effectiveness (see previous indicator) through enforcement level.