## Overview
Project Performance Report (PPR)
| Period of Report (Dates) | 30 March 2017 to 30 March 2018
| Project Title: | Reducing risk and vulnerability to climate change in the region of La Depresión Momposina in Colombia
| Project Summary: | The project "Reducing climate change risk and vulnerability in the region of La Mojana, Colombia" aims to reduce the vulnerability of communities and increase the resilience of ecosystems in this region, which is facing flood and drought risks associated with change and climate variability. The project will mainly operate in the municipalities of Ayapel, San Marcos and San Benito Abad. This project comprises four components: the first seeks to consolidate an information system on the hydrological and climate patterns at a regional level. The national and local governments and regional institutions will receive detailed information about the climate scenarios and hydrological and climatic variability trends, so that they can take preventive measures that reduce vulnerability and risk generation. These measures will be reflected both in the planning instruments, and in the implementation of adaptation actions that the project will carry out in the region. The second component intends to improve the ecological and environmental conditions of the region. Wetland restoration actions will be implemented in order to contribute an improvement of the water dynamics as a measure of risk reduction and protection of population in the medium term. These actions will be coordinated with the third component, which objective is strengthening agro-ecological and adaptive measures that help to reduce the vulnerability of communities to climate change impacts. Finally, the fourth component aims to strengthen local capacities to face the challenges that climate change brings to local governments, civil society and producer organizations. So partnership mechanisms and training programs will be established, as well as reinforcement of territorial, environmental and sector planning instruments in the region.
|  |  | Countries | Project Type: |  | GEF Focal Area: | GEF 4 Focal Areas | GEF 2 / 3 Operational Programme: | Overall Rating of the project in the evaluation by the project evaluator: | GEF-4 Focal Area Strategic Program: | GEF-3 Focal Area Strategic Program:
| Database Number: | COL83662-68537 | Afghanistan | FP | Yes | Biodiversity | 1 | 1 | U | BD-SP1-PA Financing | 1: Arid & semi-arid ecosystems
Implementing Entity (IE) [name]: |  | Ministry of Environment and Sustainable Development (MADS) | Albania | MSP | No | Climate Change Adaptation | 2 | 2 | S | BD-SP2-Marine PA | 2: Coastal, marine & freshwater ecosystems
| Type of IE: | National Implementation | Algeria | EA |  | Climate Change Mitigation | 3 | 3 | MU | BD-SP3-PA Networks | 3: Forest ecosystems
| Country(ies): | Colombia | Angola |  |  | International Waters | 5 | 5 | Good | BD-SP5-Markets | 13: Conservation and Sustainable Use of Biological Diversity Important to Agriculture
Relevant Geographic Points (i.e. cities, villages, bodies of water): |  | Region of the Depresión Momposina in Colombia, municipalities of Ayapel in Córdoba and San Benito Abad and San Marcos Sucre; swamps of the Ayapel, San Marcos and San Benito. | Argentina |  |  | Multiple Focal Area |  |  |  | BD-SP7-Invasive Alien Species(IAS) | 6: Promoting the adoption of renewable energy by removing barriers and reducing implementation costs
[8 empty] | CC-SP2- Industrial EE | 8: Waterbody based operational program
| Project Milestones | [6 empty] | CC-SP3-RE,CC-SP4-Biomass | 9: Integrated Land and Water multiple focal area
| Milestone |  | Bahamas | [6 empty] | CC-SP5-Transport | 10: Contaminants based operational program
AFB Approval Date: |  | 2012-06-29
IE-AFB Agreement Signature Date: |  | 2012-10-12 | [6 empty] | CC-SP6-LULUCF | 12: Integrated Ecosystem Management
Start of Project/Programme: |  | 21 and 22 March 2013 | [6 empty] | Cross cutting capacity building | 14: Persistent Organic Pollutants
Mid-term Review Date (if planned): |  | 2016-06-01
| Terminal Evaluation Date: | 2019-06-30
|  | List documents/ reports/ brochures / articles that have been prepared about the project. | Cyprus
|  | Project implementation reports *Inception Workshop Report *Social and environmental safeguard document for the project *Progress Report on activities by APAPI (Producer Association) *Minutes of the municipal revision of the Territorial Planning Scheme (EOT) for San Benito Abad *Minutes of the Committee meetings. *Quarterly Progress Reports • Minutes of the Advisory Committee meetings • Minutes of meetings of the Technical Committee • Minutes of meetings of the Steering Committee • Quarterly reports • Bi-monthly reports to the territorial division • Annual report • Midterm Review Technical reports: * Agro-ecological practices resilient to the effects of climate change. Strengthening of pioneer experience already established, and design and implementation of 11 agro-ecological innovations. October 2013 - March 2014. * Agro-ecological practices resilient to the effects of climate change. Creation of field schools. October 2013 - March 2014. * Preliminary community plans for climate change adaptation of 11 participating communities for the project "Reducing climate change risk and vulnerability in the region of La Mojana, Colombia". October 2013 - March 2014. * Implementation of production practices adaptable to climate change: Agriculture climatically adapted to climate change. October 2013 - March 2014. * The journey taken in the implementation of production practices adapted to climate change. October 2013 - March 2014. * Sharing experiences of the restoration, propagation and conservation of native seeds in community seedbeds. June - September 2014. * Design and implementation of six community seedbeds for the restoration, propagation and conservation of native seeds. June -September 2014. * Local community meetings for doing an inventory of native seeds. June -September 2014. * Results of the follow-up on mercury tracking in the agro-ecological innovations implemented. June -September 2014. * Follow-up and monitoring of the intervention process for the innovations implemented: final narrative document. June -September 2014. * Local scenarios for climate change * Proposal on early warning system design and establishment of a forecast center * Design document for the first phase of the restoration of wetlands * Technical and financial documents for the agriculture production initiatives * Strategic plans of the associations * Regulations for the functions of rice mills * Good practice documents to mitigate mercury contamination * Report on rainwater collection systems *Proposal for training of “rural advocates on climate change” (“Promotores Rurales” - community coordinators)- Universidad de Córdoba *Plans for training, adaptation measures and organizational strengthening • IDEAM technical report: Geo-Referencing, ground level surveys, overflow levels, liquid gauges, cross sections, installation of stretches of viewpoints in UNDP stations in the region of La Mojana. • Report on preventive maintenance of hydrological stations for the Climate Change project COL83662. 2017 • Design of the strategy to implement a regional agro-meteorological forecasting center for the region of La Mojana with a community emphasis. August 2017 • Design and implementation of a strategy for carrying out hydraulic works (infrastructure development, dredging and uncovering of water courses) for flood control and hydrological management in the project's target area. May 2017 • Reports (3) containing bathymetry of the Mosquito, Pasifueres and San Matías pipes. November 2017 • Water quality report for the Mosquito, Pasifueres and San Matías pipes. February 28, 2018 • First progress report on the characterization of ecosystem services in three regions of La Mojana. 2017 • Ecological research of aquatic ecosystems: (Conceptual and methodological framework for the study of the ecology of aquatic habitats in the La Mojana region) 2017 • Methodological proposal on the restoration of aquatic habitats in three pilots: (Set of restoration strategies and the area to be covered in the three municipalities as a result of field visits, work with the community and meetings with experts. This includes various techniques, revegetation, among others). 2017 • Methodological proposal for the rehabilitation of amphibian lifestyles in ten families of project COL83662-68537. 2017 • Report of the co-creation workshop: activities and results of the co-creation workshop led by the Alexander von Humboldt biological resources research institute with the support of the University of Córdoba. May 2017 • Final Report on the Characterization of Ecosystem Services in three municipalities of La Mojana. December 2017 • First progress report on aquatic habitat restoration exercises in three pilots (Advances in the implementation of restoration activities). 2017 • First progress report on rehabilitation of amphibian lifestyles in ten families. 2017 • Document containing technical monitoring proposal for the rehabilitation of wetlands in the La Mojana region. 2017 • Document summarizing outreach and community ownership activities. 2017 • Work proposal for the Farmers’ Biodiversity Squares. August 2017 • Methodological proposal for workshop of Rural Promoters for adaptation. September 2017 • Document for the establishment and maintenance of agrosylvopastoral systems as a measure for adaptation to climate change and climate variability • Training plan for the implementation of agrosilvopastoral systems in the region of La Mojana. September 2017 • Technical report on the definition of agrosilvopastoral system models and their establishment as a measure for adaptation to climate change and climate variability. February 12, 2018 • Technical report on participatory property planning for the establishment of the agrosylvopastoral systems. September 2017 • Technical report on the definition of agrosilvopastoral system models, their establishment, management and technical monitoring as a measure of adaptation to climate variability and climate change. September 2017 • Technical report on soil analysis recommendations for agrosilvopastoral systems. February 2018 • Collective knowledge methodology for La Mojana. July 2016 • Report of architectural designs adapted to the climatic conditions of La Mojana • Design and socialization of architectural project. August 2016 • Work execution report of El Torno-La Mojana. September 2016 • Self-construction primer for housing adapted to the climatic conditions of La Mojana. February 2017 • Training module in adaptive architecture. February 2017 • Lessons learned and technical recommendations for applying the adaptive approach in La Mojana. February 2017 • Technical document on the implementation of community-based adaptation in the region of La Mojana. November 2017 • Proposal to exchange experiences for the communities of Ayapel, San Marcos and San Benito Abad- in the region of La Mojana. April 2017 • Training plan for the diploma in "actions of adaptation to climate change oriented to the productive component" by the University of Sucre. August 2017 • Training plan for rural promoters to adapt to climate change in the La Mojana Region - Colombia, carried out by the University of Sucre. January 2017 • Basic training plan on accounting and administrative issues for community associations in the framework of the project "Reducing risk and vulnerability to climate change in the region of the Momposina lowlands in Colombia". September 2017 Workshop reports: * Report on three workshops on adaptation to climate change carried out in La Mojana on November 25-27, 2013. * Monitoring of mercury concentration in the La Mojana region. * Report on expert workshop to know the current status of the presence of mercury in the La Mojana zone. • Training report for rural promoters in the planning and establishment of adapted family production systems • Report of a gastronomic encounter and tour on the agricultural biodiversity in the community of El Pital, with a chef from Bogotá and a representative of GHL with the aim of bringing the gastronomic and hotel sector closer to the producers and envision possible articulations as a marketing channel and the development of gastronomic innovations, as a sustainability strategy for the project of adaptation to climate change • Work reports for the Farmers’ Biodiversity Squares. • Reports of workshops on Early Warning Systems and creation of community committees. • Report of participatory land-use planning workshops in coordination with sustainable Colombian livestock project, with the support of MADS and MADR. • Report of a practical workshop on the management of substrates for greenhouses in the implementation of agrosilvopastoral systems. • Report of bird sighting activity "El Canto de la Mojana", as part of the celebration of World Wetlands Day in the community of Sincelejito. Communication materials: * Institutional video of the project transmitted on Señal Institucional on July 27, 2014. Journalist: Alejandro Gonzalez. * Publication of a news report done from a visit to communities of the project. August 28, 2014. Newspaper of national circulation 'El Espectador'. Journalist: Angelica Maria Cuevas. * Program on the environmental problem of the La Mojana region and measures implemented with the project. Transmitted for one week on the radio station Blu Radio; program 'Blu Verde'. Journalist: Maria Lourdes Zimmerman. * Publication of a news report done from a visit to communities benefiting from the project. Broadcast on Caracol television channel, September 6, 2014. Journalist: Mauricio "el Pato" Salcedo. * Video "Building Future in La Mojana", February 2015. Communications Office of the Ministry of Environment and Sustainable Development. * Brochure "Results of the Project up to December 31, 2014". * Bulletins on hydrometeorological alerts for the La Mojana region Calendario la Vida en un Territorio Anfibio https://twitter.com/infopresidencia/status/573988964912099328/photo/1 http://www.elmeridianodesucre.com.co/region/item/49777-buscan-comunidades-adaptables http://elmeridianodecordoba.com.co/region/municipios/item/72060-buscan-comunidades-adaptables https://www.youtube.com/watch?v=Lyg0eyok62M http://www.bluradio.com/72375/la-mojana-region-que-dia-dia-afronta-problematica-ambiental http://www.bluradio.com/72506/con-exito-avanza-el-proyecto-de-adaptacion-al-cambio-climatico-en-la-mojana https://twitter.com/uribegaviria/status/966784362565038081 22 de febrero 2018 https://twitter.com/PnudColombia/status/959177112635756544 01 de febrero 2018 https://twitter.com/uribegaviria/status/935130274752532486 27 de noviembre del 2017 https://twitter.com/ericortes/status/898268863950966785 17 de agosto del 2017 https://twitter.com/uribegaviria/status/892033880156491777 31 de julio del 2017 https://twitter.com/gpsxcmi/status/890702806000316422 27 de julio del 2017 https://twitter.com/RegionCaribeCO/status/874313725213278208 12 de junio 2017 https://twitter.com/RegionCaribeCO/status/874313725213278208 12 de junio del 2017 https://twitter.com/LaRazonCo/status/873892495771488256 11 de junio 2017 https://twitter.com/OFrancoTorres/status/873640160075841537 10 de junio 2017 https://twitter.com/uribegaviria/status/873594757712416768 10 de junio del 2017 https://www.laflecha.co/a-fondo/cronica-el-canto-de-los-humedales-de-la-mojana/ 02/02/2018 http://www.eluniversal.com.co/regional/cordoba-y-sucre-se-unen-para-preservacion-de-humedales-en-la-mojana-271508 13 de abril 2018 https://youtu.be/fZ4MmFEMQD0 03/08/2017 https://youtu.be/ykckBrgAVpA 01/08/2017 https://youtu.be/29hG5zsHrm8 16/06/2017 https://www.youtube.com/watch?v=CSfqH4qqPgw&feature=youtu.be 16/06/2017 http://larazon.co/2017/06/1-800-familias-de-la-mojana-en-cordoba-y-sucre-avanzan-en-adaptacion-al-cambio-climatico/ 01/06/2017 http://larazon.co/2017/06/humedales-en-la-region-de-la-mojana-son-focalizados-para-su-restauracion/ 01/06/2017 http://larazon.co/2018/02/avistamiento-de-aves-en-la-mojana-en-conmemoracion-al-dia-mundial-de-los-humedales/ 02/02/2018 https://www.efe.com/efe/america/sociedad/el-torno-un-pueblo-modelo-del-blindaje-contra-cambio-climatico-en-colombia/20000013-3245702 23/04/2017 https://pnudcolombia.exposure.co/el-regreso-de-los-humedales-perdidos-de-la-mojana 22/05/2017 https://medium.com/@ColombiaPNUD/huertas-familiares-contra-el-cambio-clim%C3%A1tico-34bb8a86388#.57ccg3sak 11/03/2017 https://pnudcolombia.exposure.co/el-canto-de-los-humedales-de-la-mojana?embed=true https://www.facebook.com/instituto.humboldt/posts/1680544698679746 05/02/2018 http://www.minambiente.gov.co/index.php/noticias-minambiente/3255-mas-de-400-000-personas-en-la-mojana-se-beneficiaran-con-us-38-millones-donados-por-el-fondo-verde-del-clima 03/10/2017 | Czech Republic
List the Website address (URL) of project. |  |  | Democratic People's Republic of Korea
Democratic Republic of the Congo
Denmark
| Project contacts: |  | Djibouti
National Project Manager/Coordinator |  |  | Dominica
| Name: | Diana Isabel Díaz Rodríguez | Dominican Republic
| Email: | diana.diaz@undp.org | Ecuador
| Date: | April 6, 2015 | Egypt
| Government DA |  | El Salvador
| Name: | Angélica María Mayolo Obregón | Equatorial Guinea
| Email: | amayolo@minambiente.gov.co | Eritrea
| Date: |  | Estonia
| Implementing Entity |  | Ethiopia
| Name: | Jimena Puyana | Fiji
| Email: | jimena.puyana@undp.org | Finland
| Date: |  | France
| Executing Agency |  | Gambia
| Name: | Mariana Rojas | Georgia
| Email: | marrojas@minambiente.gov.co | Germany
| Date: | January 2017 | Ghana
| Executing Agency |  | Greece
| Name: |  | Grenada
| Email: |  | Guatemala
| Date: |  | Guinea
| Executing Agency |  | Guinea Bissau
| Name: |  | Guyana
| Email: |  | Haiti
| Date: |  | Honduras
Hungary
Iceland
India
Indonesia
Iran (Islamic Republic of)
Iraq
Ireland
Israel
Italy
Jamaica
Japan
Jordan
Kazakhstan
Kenya
Kiribati
Kuwait
Kyrgyzstan
Lao People’s Democratic Republic
Latvia
Lebanon
Lesotho
Liberia
Libyan Arab Jamahiriya
Liechtenstein
Lithuania
Luxembourg
Madagascar
Malawi
Malaysia
Maldives
Mali
Malta
Marshall Islands
Mauritania
Mauritius
Mexico
Micronesia, Federated States of
Monaco
Mongolia
Montenegro
Morocco
Mozambique
Myanmar
Namibia
Nauru
Nepal
Netherlands
New Zealand
Nicaragua
Niger
Nigeria
Norway
Oman
Pakistan
Palau
Panama
Papua New Guinea
Paraguay
Peru
Philippines
Poland
Portugal
Qatar
Republic of Korea
Republic of Moldova
Romania
Russian Federation
Rwanda
Saint Kitts and Nevis
Saint Lucia
Saint Vincent and the Grenadines
Samoa
San Marino
Sao Tome and Principe
Saudi Arabia
Senegal
Serbia
Seychelles
Sierra Leone
Singapore
Slovakia
Slovenia
Solomon Islands
Somalia
South Africa
Spain
Sri Lanka
Sudan
Suriname
Swaziland
Sweden
Switzerland
Syrian Arab Republic
Tajikistan
Thailand
The former Yugoslav Republic of Macedonia
Timor-Leste
Togo
Tonga
Trinidad and Tobago
Tunisia
Turkey
Turkmenistan
Tuvalu
Uganda
Ukraine
United Arab Emirates
United Kingdom of Great Britain and Northern Ireland
United Republic of Tanzania
United States of America
Uruguay
Uzbekistan
Vanuatu
Venezuela, Bolivarian Republic of
Viet Nam
Yemen
Zambia
Zimbabwe

## FinancialData
Financial information: cumulative from project start to March 2018
DISBURSEMENT OF AF GRANT FUNDS
How much of the total AF grant as noted in Project Document plus any project preparation grant has been spent to date?
Estimated cumulative total disbursement as of [31/03/2018 | 4672980
Add any comments on AF Grant Funds. (word limit=200) | 61% execution rate as of march 2018
INVESTMENT INCOME | 17,074.71 (for year 2017)
Amount of annual investment income generated from the Adaptation Fund’s grant
EXPENDITURE DATA
List ouput and corresponding amount spent for the current reporting period | ITEM / ACTIVITY / ACTION | AMOUNT
| 1.1 - Hydrologic and hydraulic models for the Depresión Momposina region and the project’s target area include ecological variables and support medium- and long-term decision-making | - |  |  |  | -
| 1.2 - Climate scenarios, trends in climate variability, and vulnerability analysis for the target area supports decision-making for planning instruments and the implementation of adaptation measures | 105186.48
| 1.3 - Mechanisms for gathering, processing, and managing hydroclimatological information at the regional and local levels are strengthened and articulated with the national hydroclimatological network | 102891.46
| 1.4 - An early warning system developed at the local level prepares local communities to reduce their vulnerability to extreme weather events | 35782.9
| Total component 1 | 243860.84
| 2.1 Hydraulic works: infrastructure development, dredging and water flow clearing for flood prevention and hydrological management | 151284.51
| 2.2 Ecosystems associated to the hydrodynamics of the target area are rehabilitated; their capacity to mitigate effects of floods is improved | 334780.13
| Total component 2 | 486064.64
| 3.1 – Agricultural production practices resilient to climate change and directed towards women (vegetable gardens and organic crops on piles and native rice implemented in the target area). | 124678.54
| 3.2 – Structural measures for households and schools that respond to climate risks or threats designed and developed for the benefit of approximately 660 people. | 24912.09
| 3.3 There are at least 250 agro-silvopastoral measures resilient to climate which are established to help the small peasant to mitigate the effects of floods. | 336198.26
| Total component 3 | 485788.89
| 4.1 – Platforms for the association and strengthening of local communities have been established for their appropriation and to reproduce adaptation measures developed by the project. |  |  |  |  | -
| 4.2 – Communities and local authorities in target municipalities trained in climate change risks related to flood and adaptation measures that reduce vulnerability. | 7191
| 4.3 - Climate risk management issues which are integrated to regional and local instruments of territorial, environmental and sectoral planning are articulated to the national planning directives. | 75800.12
| 4.4 - Coordination among national, regional and local institutions guarantees sustainability of adaptation actions. | 67246.78
| Total component 4 | 240104.27
| 5.1 Monitoring and evaluation | 9684.08
| 5.2 Project Management | 80182.29
| Total component 5 | 89866.37
| TOTAL | 1455818.64
| Depreciation of assets | 26203.39
PLANNED EXPENDITURE SCHEDULE
List outputs planned and corresponding projected cost for the upcoming reporting period | ITEM / ACTIVITY / ACTION |  | PROJECTED COST | Est. Completion Date | Status
| Component 1. The existing HEIS is strengthened and used by local- and regional-level stakeholders, improving their resilience to the impacts of climate change. | 1.1 - Hydrologic and hydraulic models for the Depresión Momposina region and the project’s target area include ecological variables and support medium- and long-term decision-making | 0
|  | 1.2 - Climate scenarios, trends in climate variability, and vulnerability analysis for the target area supports decision-making for planning instruments and the implementation of adaptation measures | 141000 | 31/04/2017 | In procurement process
|  | 1.3 - Mechanisms for gathering, processing, and managing hydroclimatological information at the regional and local levels are strengthened and articulated with the national hydroclimatological network | 85500 | 2017-11-30 | In procurement process
|  | 1.4 - An early warning system developed at the local level prepares local communities to reduce their vulnerability to extreme weather events | 140000 | 2017-07-30 | In procurement process
|  |  | 366500 | 31/11/2017
| Component 2. Rehabilitation of wetlands and their hydrology in the target area as a means to reduce risk to flooding and drought associated with climate change and variability. | 2.1 - Hydraulic works for flood control and hydraulic management are in place | 334000 | 2017-07-31 | ToR to be defined
|  | 2.2 - Ecosystems associated with the hydrodynamics of the target area are restored | 336500 | 2017-02-28 | Hired
|  |  | 670500 | 2017-07-31
| Component 3. Introduction of climate change-resilient agroecological practices and building designs helps local communities to reduce their vulnerability to the impacts of climate change. | 3.1 - Climate change-resilient production practices adopted in the target area. | 190717 | 2017-06-30 | In procurement process
|  | 3.2 - An adaptive architecture programme (e.g., houses on stilts and/or floating housing) developed in flood-prone areas of the target area | 263537.28 | 2017-05-31 | In procurement process
|  | 3.3 - Agro-silvopastoral models incorporated into the multiple-use fluvial landscape contribute to the reduction of vulnerability of local farmers | 227500 | 2017-05-31 | In procurement process
|  |  | 681754.28 | 2017-05-31
| Component 4. Relevant institutional and social structures strengthened for mainstreaming climate risk management and adaptation measures into planning and decision-making processes. | 4.1 - Platforms for association and strengthening local communities are established for their appropriation and replication of the adaptation measures developed by the project | 8000 | 2017-06-30 | In procurement process
|  | 4.2 - Training programme for the local communities and civil authorities for the implementation and sustainability of the climate change adaptation measures of project components 1, 2, and 3 | 7000 | 2017-06-30 | In procurement process
|  | 4.3 - Climate risk management considerations built into regional and local territorial, environmental, and sectoral planning tools are articulated with national planning guidelines | 66000 | 2017-06-30 | In procurement process
|  | 4.4 - Coordination among national, regional and local institutions guarantees sustainability of adaptation measures. | 42000 | 2017-05-31 | In procurement process
|  |  | 123000 | 2017-06-30
| Component 5. Project Management | 5.1 - Monitoring and evaluation | 8000 | 2017-04-30
|  | 5.2 - Project Management | 93000 | 2017-12-15
|  |  | 101000 | 2017-12-15
1942754.28
ACTUAL CO-FINANCING (If the MTR or TE have not been undertaken this reporting period, DO NOT report on actual co-financing.)
How much of the total co-financing as committed in the Project Document has actually been realized?
Estimated cumulative actual co-financing as verified during Mid-term Review (MTR) or Terminal Evaluation (TE).
Add any comments on actual co-financing in particular any issues related to the realization of in-kind, grant, credits, loans, equity, non-grant instruments and other types of co-financing. (word limit=200)

## Risk Assesment
RISK ASSESMENT
IDENTIFIED RISKS
List all Risks identified in project preparation phase and what steps are being taken to mitigate them
Identified Risk | Current Status | Steps Taken to Mitigate Risk
Political: There is uncertainty about the local political will of mainstreaming adaptation measures into the planning instruments. | low | This risk goes from medium to low, due to the fact that in the current phase of the project, climate change considerations have been incorporated into the planning instruments. Likewise, through the Ministry of Environment and Sustainable Development, the National Government launched, in June 2017 the National Policy on Climate Change. This framework policy ensures that the issue of Climate Change is incorporated into local policies. In addition to this, the project continues to focus efforts on supporting the strengthening of the capacities of local authorities so that climate change issues are incorporated into administrative procedures. In this sense, the training courses and the delivery of technical information to local authorities are ongoing programs.
Environmental/political: The anthropogenic degradation continues in the region, as a result of deforestation and conventional cattle raising practices. | medium | This risk remains at medium level. The project continues with its training work for the protection and conservation of natural resources, and the actions of wetland recovery and establishment of agrosilvopastoral systems have been used to increase the level of commitment and awareness in relation to this issue. 108 letters of commitment have been signed with owners of the areas where the project promotes such actions, and 1,125 environmental and social safeguards have been signed, in which families commit to caring for the La Mojana ecosystem.
Institutional: Decision making processes are slow at the local and regional levels. | low | The direct communication and commitment with associated government agencies (National Adaptation Fund, National Planning Department (DNP), Regional Environment Corporation (CAR), Mayor's offices and Governor's offices) has been maintained. Continuity of the meetings with the project advisory, technical and management committees. The level of this risk has changed to low, since the project has strengthened the mechanisms for coordination with the different local entities. The advisory committee has strengthened the articulation of the institution, thus facilitating decision-making. Similarly, technical and directive committees are still being held. These are the main spaces to decision making mechanisms about the project. This risk remains low; the technical team of the project has transferred its base of operations to the municipality of San Marcos, and has a working space at the offices of the environmental authority, which seeks to ensure that the follow-up to the processes developed with this entity and local authorities is effective and facilitates the management of decisions in a timely manner.
Operational: There is resistance on the part of some actors to the adoption of proposed measures. | Low | This risk changes from medium to low since the project has been managed to improve the synergies with local entitities by means of coordination and interrelation actions. This risk remains low. In this period, the project has sought to socialize the different measures in order to ensure a full understanding thereof and their implementation by the different actors participating in the project.
Financial: Delays in executing funding at the regional level. | Low | Adjustments have been made in the planning and operation of the project to ensure it receives the necessary resources by the time they are required in order to avoid any delays.
Financial: The Government of Colombia is not able to leverage sufficient financial resources for the sustainability of project actions. | Low | During the last period, the project has made a great effort to involve different government institutions to the project actions so that they take ownership of the results and guarantee the project sustainability. The capacities of the following institutions have been strengthened and the sustainability of the actions are ensured as follows: • IDEAM: It has extended the meteorological and hydrological monitoring network by means of the installation and operation of automated hydrological stations and millimeter monitoring stations of creeks. The inclusion of these stations to the IDEAM network ensures the generation of information and maintenance of the stations. The Humboldt institute will strengthen its capacities and knowledge in the restoration and conservation of the swamp forest wetland. The scientific information generated from this activity will serve as a reference to intervene other ecosystems in the country with similar characteristics to La Mojana. • Local universities such as Cordoba, Sucre, Pontificia Bolivariana: Agreements have been signed through the Humboldt Institute to support wetland restoration and the transfer of methodologies and knowledge related to the restoration of the ecosystem at the amphibian level. By means of these actions, the universities themselves can continue to implement research and restoration actions in the region. • National Adaptation Fund (NAF): The project has provided support and technical assistance to the National Adaptation Fund; 1. Formulation of the Action Plan of La Mojana. NAF has taken advantage of the project experience to replicate some of the adaptation measures in the 11 municipalities of La Mojana. For example, the implementation of family vegetable gardens adapted to the climate conditions, wetland restoration (the Fund contributed with USD850 to increase project restoration actions, rainwater harvesting systems, amongst others. The government of Colombia, through the Colombian Adaptation Fund, the Ministry of Environment and Sustainable Development, the National Planning Department and other entities, has taken advantage of the impact of the project to scale up the adaptation measures promoted by the project, and has presented a project to the Green Climate Fund to support the 11 municipalities of the sub-region of La Mojana.
Critical Risks Affecting Progress (Not identified at project design)
Identify Risks with a 50% or > likelihood of affecting progress of project
Identified Risk | Current Status | Steps Taken to Mitigate Risk
Operational: Displacement of the communities to other zones. | High | During the reporting period, this risk has been elevated from low to high due to the presence of new armed groups in the project area that has increased the risk for displacement. The risk is thus associated with security conditions which have been present recently in the area, where threats have been issued and there has been an increased presence of armed actors, land dispossession, among others. To manage this issue, the project has strengthened its participation in the communities by recruiting more technical professionals who can provide a more regular and closer technical assistance to families in the adaptation of measures. These measures have been effective to maintain the motivation and promote the active participation of communities in the project actions. To ensure that the security conditions do not jeopardize the development of activities, the project is participating in the departmental guarantee roundtables, in which regional authorities participate and where periodical analysis of context and preventive measures that help protect communities are carried out. In addition to this, the project continues to maintain a permanent presence in the communities and provide technical assistance to families.
Political: There is weak governance and security in the region | High | This risk remains high despite the fact that the Peace agreement has been signed. The security in the area may be affected by the presence of dissident groups and criminal gangs that may come into conflict to dispute territorial control. To mitigate this risk, the project team has strengthened its knowledge on safety measures. Close communication with local communities and authorities is kept constant, so that any unsafe situation may be anticipated in advance. In two cases during this period of time, it was necessary to evacuate the personnel of the communities due to the presence of outlawed groups. This risk remains high, due to the fact that the security conditions in the area have deteriorated and there is an increase in crime. The project continues with the application of security protocols established by the UN office in Colombia and which follow UN security procedures based on national risk assessments, this includes the presence of a national security officer and training for UNDP and project staff. In addition, departmental tables of guarantees are organized, where there is a constant monitoring of the security situation in the area. This monitoring allows to have the necessary information to implement the security measures in case they are required.
Environmental: presence of mercury in the soil and water in the zone of influence, which could affect productive initiatives locally. | High | * A study was conducted to establish the traceability of mercury contamination. *Socialization of good practices is being carried out to mitigate pollution in soil, water and crops. *An inventory of rice species that are resilient to mercury contamination has been carried out. *An inventory of good practices to mitigate mercury poisoning through the consumption of fish Articulation has been sought with the Colombian Adaptation Fund, Corpomojana and the University of Cordoba, so that the results of the technical studies and the mitigation measures that are being generated on heavy metal contamination are socialized with the communities of La Mojana, and so that a campaign of good practices is implemented, so that communities can reduce the risk of contamination. For them, educational workshops have been held in the communities of influence of the project.
Environmental: Period of extreme drought, caused by the presence of El Niño - in addition climate vulnerability accentuated due to the transition from El Niño to La Niña | High | Rainwater collection systems were established both for households and communities to ensure water supply for the household. * Assistance has been provided to families regarding adaptation measures that benefit crops. For example, agro-forestry and mixed farming techniques, shade planting and drip irrigation. * A precipitation analysis is being carried out on the basis of the information provided by the Adaptation Fund in order to have information that allows us to give a precise guidance to communities on the measures that should be adopted. * Coordination with agro-climatic committees in Sucre and Córdoba for the dissemination of agro-climatic bulletins. * Work in cooperation with local authorities to take into account regional forecasts. In addition to the continuation of these measures, the project has concentrated its community work on farming techniques to help the recovery of degraded soils. Soil studies are being conducted to determine whether the soil requires any special treatment to avoid its degradation; and then promote the care and protection of water sources. This risk goes from medium to high, due to the fact that the activities that are being executed in the project require that the meteorological conditions be neutral in order to be able to advance. Progress has been made in the planning of activities to take advantage of the dry seasons that are necessary in hydraulic works, as well as for the construction of community centers. In like manner, planning measures have been implemented so that the restoration actions correspond to the rainy seasons. Monthly participation continues in the agro-climatic roundtables, with the purpose of monitoring the weather conditions in the region.
Risk Measures: Were there any risk mitigation measures employed during the current reporting period? If so, were risks reduced? If not, why were these risks not reduced?
Add any comments relevant to risk mitigation (word limit = 500)
During the period it was necessary to activate mitigation measures for risks related to safety issues and climatological phenomena. In terms of security, the presence of armed actors outside the law has increased in the region. In the municipality of San Benito, there is evidence of the presence of these actors, which have exacerbated conflicts over land tenure. The monitoring of security analysis and the protection measures of the technical team has been reinforced. As for climate variability, it was also necessary to activate the mitigation measures, since 2017 was an atypical year, as there was rainfall above the average of the historical series and the differences are accentuated towards the middle of the year, particularly in the months of May, June, July, August and September. In the last months of the year and the beginning of 2018, a period of reduced rainfall was registered, driving communities to implement the risk management measures to ensure that the productive systems were maintained both in winter and drought seasons.

## Rating
RATING ON IMPLEMENTATION PROGRESS
For rating definitions please see bottom of page.
| Progress on Key Milestones |  | Expected Progress |  | Progress to Date | Rating
Project Manager/Coordinator: | Output 1.1 - Hydrologic and hydraulic models for the Depresión Momposina region and the project’s target area support medium- and long-term decision-making. |  | Activity completed in the previous report |  | Completed Activity | Highly satisfactory
| Output 1.2 - Climate scenarios, trends in climate variability, and vulnerability analysis for the target area supports decision-making for planning instruments and the implementation of adaptation measures |  | 6 local authorities in the area of ​​influence of the project have access to technical information related to climate phenomena and allow them to make decisions |  | Technical consultancy has been provided to: the Governor's Office of Sucre, Corpomojana, the Corporation of the Valleys of the Sinú and San Jorge Rivers (CVS), Mayor’s offices of Ayapel and San Benito for the handling and interpretation of the information generated by the project, which is being used in the formulation of projects, as well as in their planning documents. Altogether 5 local authorities had access and direct technical consultancy in relation to the information that has been disseminated. Additionally, in association with the IDEAM, the forum “Socialization of the results of the Third National Communication on Climate Change” was carried out, with the participation of 11 local institutions, (27 people); from the following institutions: 7 mayor’s offices (Achí, Caimito, Majagual, La Unión, Ayapel, San Marcos and San Benito Abad), 2 corporations: CVS and Corpomojana, 2 governor’s offices, Cordoba and Sucre, and 2 NGOs: Paisajes Rurales and Asociación Agropecuaria. The socialization of the scenarios will allow the local authorities to know the climate trends for the region and to count on a useful tool at the time of planning actions related to productive activities that are resilient to the climatic conditions of the region. The IDEAM, Forum, had an interactive section in which the participants were able to learn, under a practical approach, how to gain access to the information within local settings. In like manner the vulnerability report was socialized, as well as the measures for adaptationthat must be promoted in the country. In agreement with the results of the Climate Change Scenarios, in Cordoba, “the Department may present temperatures of 2,2°C higher than current temperatures by the end of the century. The smaller temperature differences could be generated on the mountainous areas of Abibe, San Jerónimo and Ayapel”. “The main impacts may be generated on the biodiversity associated to the mountainous areas due to the gradual increases of temperature in the territory. The cattle farming sector may be affected given the issue of thermal stress, as well as the reduction in rainfall for the municipalities of the north. The ecosystem service of water provision could be affected for those populations that have been susceptible of droughts throughout the century due to the reduction in rainfall and strong increases in temperature”. As to the department of Sucre, by the end of the century the temperature “could be of 2.1°C in addition to the current temperature of reference. For the next 25 years the department of Sucre may see a rise in temperature of one degree, on average. In general, increases in precipitation rates in the department might not take places according to the modeled scenarios. In general, the Department may present reduced precipitations up to 16% less than the current reference value”. The main effects can be seen in the livestock and agricultural sector due to the accentuated temperature increases. The health sector could be affected due to the interaction with nutritional factors of those populations with food crops affected by the increase in temperature. In general, the water supply service can be affected, as well as the communities of species most susceptible to thermal stress. | Highly satisfactory
| Output 1.3 - Mechanisms for gathering, processing, and managing hydroclimatological information at the regional and local levels are strengthened and coordinated with the national hydroclimatological network.D37 |  | 28 communities in the area of ​​influence of the project have the tools to monitor bodies of water |  | The maintenance of the 9 automated stations located in the project area was carried out, in order to guarantee the transmission of the hydroclimatological data to the network of IDEAM stations. IDEAM enabled the project to directly access hydro-climatic information through the Hydras3 satellite data reception system, in order to monitor in real time the climatic events that occur above the historical averages, considering extreme drought or floods at river-basin level. This information has been socialized with the Three (3) Municipal Risk Management Councils and the two (2) Environmental Authorities of the region. An observer was hired to monitor the automated station located in Caño Barro, which is a tributary of the Ayapel marsh and affects the communities of the municipalities of San Marcos and Ayapel with overflows due to its geographic position. This monitoring will allow to notify the local risk management offices in case of a sudden increase in water levels and generate early warnings for decision making. Geo-referencing and ground level surveys, overflow levels, liquid gauges, cross-sectional surveys, and installation of sight sections in 11 stations of La Mojana were carried out, in order to establish the correspondence between the base reference levels and the establishment of the local early warnings system. Five limnimetric stations were installed in the communities of Las Delicias, Cuiva, La Plaza and Las Pozas, to complete a total of 18 limnimetric stations, which allows communities to survey the levels of bodies of water, obtaining daily information that feeds the community-based system of early warnings. This action allows communities, municipal mayor’s offices, environmental authorities, and other state entities to make decisions regarding the risk of floods and drought. During the rainy season registered in the second semester of 2017, with the information collected the communities of Ayapel and San Marcos, actions to prepare for the risk of flooding were coordinated in a timely manner with the municipal mayor’s offices; the communities of Seheve and the Torno, stated that it is the first time that they get early attention from local authorities. | Highly satisfactory
| Output 1.4 - An early warning system developed at the local level prepares local communities to reduce their vulnerability to extreme weather events. |  | 27 community committees of SATH were formed and 14 were strengthened |  | 27 Community-based Early Warning committees have been established and are operating with the monitoring of water bodies, 7 in the department of Córdoba, in the communities of Ayapel (Seheve, Cecilia, Sincelejito, Mata de Caña, Pañuelo, Alfonso Lopez, Rondón) and 20 in the department of Sucre, in San Marcos (Cuenca, Las Flores, El Torno, El Pital, La Mancha, Parcelas de Viloria, Parcelas de Gloria) and San Benito Abad, Las Delicias, Chinchorro, Parcelas de Santa fe, Caño Cayman, La Plaza, Cuiva, Las Posas, Urbano in San Benito Abad, Las Chispas, Tosnovan, Pasifueres, El Chupo, Venezuela, a total of 262 people make up the committees, of which 121 are men and 141 are women. The conformation and strengthening of these committees was achieved through training on basic concepts of the EWS, where the participants were explained what an Early Warning System is, what it is used for, how it works and how it is structured. In this sense, 4 subgroups were created and divided into the Water and Hygiene Team, communication and information of the EWS, housing and temporary shelters. Each of these sub-groups have specific functions, according to the topics in which they are trained. Coordination was made between the communities and local institutions, improving access to hydroclimatic information through the participation of the communities in 4 departmental agroclimatic tables. The participation of the communities not only facilitated access to climatological information, but also helped in conveying their recommendations for the establishment of their crops. In total, 20 communities have participated in the agroclimatic tables, for a total of 35 people, of which 19 are men and 16 are women. The Steering Committee of the project defined that, in order to guarantee the sustainability to the Early Warning System, a Climate Services Center will be established, which will be operating in the facilities of the Corpomojana Environmental Authority, for which the contracting process for adaptation of the facilities has started, in those places where the Climate Services Center will operate, as well as the hiring of personnel that will be operating the Center. | Highly satisfactory
| Output 2.1 - Hydraulic works for flood control and hydraulic management are in place. |  | Development of the strategy of hydrological recovery for flood control |  | Having prepared and socialized the proposal for recovery of the hydric dynamics that contributes to the control of floods, the strategy has been socialized with the environmental authorities and the communities, who validated the actions proposed by the project. Three GRANT's (subsidy agreements) were signed with the associations ASOAGRIPESCHIS, ASOMATIAS and ASOFASAN, which will carry out the actions defined for intervention in the Pasifueres (San Benito), San Matías (Ayapel) and Caño Mosquito (San Marcos) canals, respectively. The work with the base organizations guarantees the transfer of the methodology of this type of activities, and at the same time it guarantees the sustainability of the actions, since the communities will have the opportunity to identify in an experiential way, the benefits that the recovery of the water dynamics of the canals may bring. Baseline consolidation activities were developed to determine the specific actions in terms of sediment removal, plant material removal and establishment of riparian vegetation in the defined canals, which are described below: - (2) two overflights with Drones, with image processing to obtain ortomosaics and (2) bathymetry surveys of the San Matías canal in three defined control points and the respective analysis of the cross sections, which was financed by the environmental authority with jurisdiction in Ayapel, represented by the Autonomous Regional Corporation of the Valleys of Sinú and San Jorge - CVS, for a value of COP $36,000,000 (USD12,000) - Implementation of (2) overflights with Drones, survey and analysis of two (2) Bathymetry surveys in three control points in the Mosquito and Pasifueres canals located in the municipality of San Marcos and San Benito de Abad, respectively. - Sampling of physicochemical, bacteriological and hydrobiological parameters to establish the baseline water quality of the Pasifueres, Mosquito and San Matías canals. - Strengthening of capacities of the associations ASOAGRIPESCHIS, ASOMATIAS and ASOFASAN, through the exchange of experiences with the GIZ agency, within the framework of the EbA Program "Adaptation Strategies based on Ecosystems in Colombia and Ecuador", to learn about the work carried out by the ASPROCIG association in the removal of sediments and production of plant material in the Sicará pipe located in San Bernardo del Viento, in the Department of Cordoba. -Generation of orthomosaics from the overflight with a DRONE, whose attributes allow to estimate the shape of the riverbed, the vegetation cover and the geomorphology of the pipes for the design of hydric rehabilitation works. 4 workshops were held addressed to the communities of Las Chispas and Pasifueres (influence of Caño Pasifueres), Community of La Mancha and Campanito (influence of Caño Mosquito), and Sincelejito, Mata de Caña, Rondón and Corea (influence of Caño San Matías, with the participation of 174 people (60 Women and 114 men). Following a defined methodology, two additional canals were prioritized for intervention, corresponding to the Las Delicias canal, located in the Municipality of San Benito de Abad and the Seheve canal, located in Ayapel. The proposed actions were approved by the Project Management and Technical Committee and they are in the process of signing two (2) additional grants. A visit was made by the Environmental Authority to the prioritized canals, in order to inspect the proposed actions and grant their endorsement to the hydric recovery actions. | Satisfactory
| Output 2.2 - Ecosystems associated with the hydrodynamics of the target area are restored. |  | Follow up to the Letter of Agreement signed with the Alexandre Von Humboldt Institute, for the rehabilitation of 700 has of Ecosystems of Wetland areas in La Mojana. |  | Output 2.2 - Ecosystems associated with the hydrodynamics of the target area are restored. Within the framework of the letter of agreement with the Alexander Von Humboldt Institute, 5 meetings and 2 visits have been made in the areas under restoration, as well as 1 monitoring committee. These meetings have obtained the following results: Characterization of ecosystem services in three regions of La Mojana. This analysis was developed in partnership with the University of Córdoba, where the indicators for monitoring were defined, and it highlights the importance of the use of drawings as monitoring tools, since a large part of the community does not know how to write. Work was done on ensuring the understanding of the concepts of good living conditions, governance and resilience in accordance with the social and ecosystem dynamics of the wetlands. The qualitative approach analyzes were constructed using tools such as social cartography, seasonal calendars and ethnographic tours. Coverage map analyzes were carried out from the local perspective to identify macrohabitats, use of spaces and local practices. Maps were made from social cartography to identify threats, key species and macrohabitats. Having carried out the aquatic ecology research, in partnership with the University of Cordoba, there is a methodology for characterizing the temporal and spatial variation that includes the results of high water and rising water levels. For the ecological characterization, macro conserved and degraded habitats were taken as reference with the following configurations: zapal, zapal- ciénaga, rio- zapal, potrero- zapal, bufalera- zapal, arrozal- zapal. Reference values for conservation: Zapal isolated conservation, Zapal - rio El Torno, Zapal - canal in Las Flores, Zapal - Ciénaga in Las Flores. As results, analyses were obtained by macrohabitat of all the species. The objective of this characterization of species serves to make decisions on the restoration. The healthy ecosystem (ideal scenario) will be taken as reference towards where the degraded ecosystem is gradually to be taken. A very important achievement of this phase is the acquisition of the bioacoustics and phototrapping equipment, which have already been installed in the area, after the training of a team of several institutions at the University of Córdoba. Advances in the implementation of restoration activities. This activity is carried out in the field by the Rural Landscapes Corporation. The communities of Pasifueres, El Torno, Pital, Sincelejito-Seheve and Cuenca were prioritized. For each site, a land survey analysis was carried out in relation to flood gradients. An important advance was made of 800 records of useful plants for restoration of the different types of wetlands. For each selected plot of land, an assessment of the property will be carried out, as well as of the sources of plant material, and then a specific design of the restoration strategy will be made with the owner, in accordance with the characteristics of the macrohabitats of each plot of land. 76 Hectares of vegetation cover and approximately 5000 m2 in productive paddocks have been recovered directly. | Satisfactory
| Output 3.1 - Production practices resilient to climate change are adopted in the target area. |  | 100 families benefit from adapted, family-based productive systems 1,800 families receive training and technical assistance to ensure the sustainability of their family productive systems |  | 162 family gardens adapted to the conditions of flood and drought have been implemented; the orchards have a diversity of vegetables such as; sweet pepper, eggplant, white cucumber, squash, chives, long beans and tomatoes. Likewise species of food crops such as yucca, plantain, yams and beans have been incorporated. 162 tool kits were delivered, including wire mesh, barbed wire, staples, pallets, shower heads, machetes and files. Twenty-two reinforcement workshops were developed on the planning and establishment of gardens adapted to climate change and climate variability, in which 4,340 families participated (1996 women, 2344 men). The topics were aimed at improving production systems and solving phytosanitary problems (diseases, pests, nutritional deficiencies), with the preparation and application of biopreparations. As for planning, guidelines were given regarding the relocation of horticultural and medicinal species, according to the climatic conditions. The community-based productive initiative for fish farming in ponds was strengthened, which has been a very positive response from the fishing community of Cecilia against the drought that occurred in the first quarter of 2018 in the San Jorge River basin . This activity has been complemented with the establishment of crops of legumes and essential food crops such as sweet pepper, tomato, squash, green beans and eggplant. 20% of this production is being used by families for self-consumption and the remaining 80% is taken to market within the community, generating surpluses for an amount of COP $460,000 (USD 184). These actions are increasing the resilience capacity of families, since before the project, their only productive activity was fishing in the San Jorge River, which in times of drought is affected by low water levels, and families are left without sources of income . Preparation of a methodological proposal for the development of the craftsmanship program with natural fibers, with groups of women identified in the municipalities of San Marcos and San Benito Abad in the department of Sucre. This initiative is articulated with component 2, which will serve for macrophyte management in order to ensure that the water dynamics maintain their natural flow and that the flows of the recovered canals do not exceed their levels. It is expected that this activity will benefit at least 120 women from the communities of Cuenca and El Torno. | Highly satisfactory
| Output 3.2 - Adaptive architecture programmes developed in flood-prone areas of the target area. |  | 5 community centers are built |  | A technical analysis was carried out to define the communities where the 10 Adapted Community Centers will be built, for which a review of the flood threat scenarios generated by the Colombian Adaptation Fund was made, where the flood levels of each one of the communities were identified. This exercise was complemented with vulnerability assessments, where criteria were applied such as the percentage of the territory that is flooded, and time that the community takes to resettle to a safe place. These variables were evaluated with a matrix that showed some percentages that allowed to prioritize the communities where the constructions will be made. It was defined, based on this analysis, that the community centers will be built in those communities that do not exceed flood levels of 1.5 meters in height in a period of return of 100 years according to the risk scenarios of the Colombian Adaptation Fund. In the same way, the budgetary evaluation was carried out for the construction of the 10 community centers and the contracting of the audit seeking to guarantee that the community centers comply with all the norms required by the Colombian construction code and the designs that were previously agreed with the communities. The bidding process for contracting was made public, however, to this date it has not been possible to find a bidder. A meeting was held with the National Planning Department, where the housing designs and adapted community centers were socialized with the objective of scaling the designs of adaptive architecture and for these to be used as a prototype for housing and community centers for the areas of Colombia that have similar conditions as La Mojana and which, in turn, can be financed with Government Funds. The National Planning Department undertook to carry out an evaluation of this alternative and it is expected to be able to continue with the process throughout the year. | Highly satisfactory
| Output 3.3 - Agro-silvopastoral models incorporated into the multiple-use fluvial landscape contribute to the reduction of vulnerability of local farmers. |  | 100 hectares of Sylvopastorile and agroforestry systems are implemented |  | The implementation of agrosylvopastoral systems began, for which the primary information was collected, which allowed the identification of the most favorable areas and the elaboration of the designs for the establishment of agrosylvopastoral systems. The information was collected through secondary sources; the documents that were consulted in the definition of the models and the definition of the methodology are: Integral Climatic Vulnerability Assessment, Hydrodynamic Modeling of La Mojana, carried out by the Adaptation Fund, the Ecoregional Planning of La Mojana, carried out by the Alexander von Humboldt Institute and the Institutional Action Plan of Corpomojana 2016-2019. Similarly, information was collected with primary and secondary sources, which included technical advice from FEDEGAN, Corpoica, Universities of Córdoba and Sucre, the MADS and the participation of small farmers. Land use planning exercises were carried out, in which the following aspects were identified: 90% of producers manage continuous grazing systems, and only 10% have divisions of pastures and implement such divisions with large pastures that exceed 3 hectares. The management of pastures is done with natural grass, without any type of renewal or fertilization practices. The producers are fully aware of the forest species that adapt to the conditions of their land and are aware of the deficient arborization within their lands as a result of inadequate cultural practices, such as slash and burn for pasture planting and crops, excessive fumigation with agrochemicals and indiscriminate felling to obtain wood. The water sources for the different productive activities do not have protection to regulate the access of cattle and to avoid their contamination. The producers specify the cultivation areas and their rotations, as well as the areas dedicated to livestock and areas of wetlands or nearby shores. There are identified flood areas, areas susceptible to flooding, and areas with minimal risk of flooding. Through this process 4 agrosylvopastoral models were defined, which are described below: Division of paddocks for rotation and rational grazing. This model was defined with the objective of replacing extensive grazing with rotational grazing that can rapidly increase the productivity of the cattle farm, and at the same time to help improve the distribution of organic fertilization produced by animal manure and urine and prevent livestock activity from contaminating the canals and rivers. Trees scattered in paddocks; by natural regeneration or established at low densities. (30 - 40 trees per hectare); This agrosylvopastoril system seeks the selection and/or establishment of tree species and forest shrubs, fruit trees, herbaceous and woody herbage plants adapted to the climatic and environmental conditions of the area. These plant species provide shade to livestock, generating greater comfort during rumination and digestion. In addition, this type of models serve for other purposes such as housing construction, medicine, firewood, human and animal food, and they generate productive, environmental and climate benefits that contribute to carbon capture, oxygen production, nitrogen fixation, as well as serving as habitat for birds and insects, helping to maintain biodiversity. Live fences. (300 - 400 trees per km); trees and shrubs, fruit trees, herbaceous plants and woody plants are planted, which provide the following benefits, among others: food and shade for livestock, reduction of the negative impacts of winds on pastures and crops, protection of soils from flooding by reducing the effects of water runoff, and improvement of soil conditions by contributing organic matter and distributing moisture. Other benefits of this system are the conservation of the landscape and habitats for local species, production of firewood and timber, regulation of microclimates, among others. Mixed forage banks: these systems make an efficient use of the land, being commonly found in the farms of small dairy producers or dual purpose farms. The forage produced in a bank is cut, hauled and given to the animals throughout the year. With these 4 models of Systems it has been possible to benefit 93 livestock producers from 6 communities in the municipalities of Ayapel and San Marcos, and 160 hectares have been established and 209,000 seedlings of species such as totumo and guasimo have been planted, as well as 2,180 kg of grass seeds of the braquipará, angleton and climacuna species. The benefits of these systems are reflected in the increase of two liters of milk per cow per day, the milking cycle of a cow is 180 days, with which small farmers have an increase in their income of COP $288,000 (USD 112) for each head of livestock, for 6 months. Another benefit that farmers are receiving is the increase in the weight of livestock. During periods of drought without agorsylvopastoral systems, livestock on average lose 1 kilogram of weight per week, and in a period of drought such as those that are recorded in the area (16 weeks) each head of livestock can lose, on average, 16 kilograms of weight. The kilogram of meat in the area is sold at COP $5,500 (USD 2.2), that is, with agrosylvopastoral systems in a normal period of drought, a producer is earning COP $88,000 (USD 35.2) for each head of livestock. Another added value of agrosylvopastoral systems is that the practice of transhumance is avoided, which generally represents a cost of COP $10,000 (4 USD) on a monthly basis for each head of livestock, that is to say that during periods of drought USD 16 are being saved for each head of livestock. In addition to the economic benefits, the Agrosylvospastoral Systems offer socio-environmental benefits, such as: greater coverage of soils due to grass, forage hedges and the arboreal component that is sown. With the live fences an increase in the presence of birds is observed, and even birds have reappeared that had not been seen after the floods. The connectivity with areas of greater coverage of trees is improved. With the availability of feed for the livestock, and combined with the practice of storage of water that is incorporated by the producers, the pressure of livestock on areas within the wetlands is being reduced, contributing to the recovery thereof, as well as helping reactivate the biological processes as a consequence of having a greater richness of flora. To complete the 250 hectares of sylvopastoral properties, 47 cattle producers have been identified from the municipalities of Ayapel, San Marcos and San Benito Abad for the implementation of 90 hectares of agrosylvopastoral systems. Likewise the signing of a subsidy agreement with one of the associations for the implementation of these new hectares is being managed. | Highly satisfactory
| Output 4.1 - Platforms for association and strengthening of local communities are established for their appropriation and replication of the adaptation measures |  | 25 CBO’s are strengthened through the project and promote actions of adaptation to climate change. |  | 23 grassroots organizations have participated in processes to strengthen their capacities, of which 7 have received training from the National Learning Service (SENA) on basic accounting and administration issues, as well as technical training processes for the entrepreneurship of productive units with minor species. These trainings strengthen associations in the management of programs and projects that facilitate the continuity of processes of adaptation to climate change. 317 people have participated in these trainings, of which 207 are women and 110 are men. 5 grassroots organizations (Association of Farmers, Fishermen and Restorers of the Sincelejito Corregimiento, Ayapel - ECOSINCELEJITO, San Matías Association of Producers and Farmers - ASOMATIAS, Association of Farmers from Vereda El Chinchorro, Association of Farmers, Livestock Producers, Fish Farmers and Environmentalists of Pasifueres - ASPASFU, Association of Women of Cuiva) have received support in the implementation of community assemblies for the election of their boards of directors, consolidation of statutes, and presentation of their legal obligations to the Colombian State. As part of the strategy for sustainability of family production systems, the project, with the support of the National Learning Service (SENA), has been supporting, through producer associations, the commercialization of the surpluses through the farmer’s markets of biodiversity. This activity has supported 11 associations (Palo Alto, Cuiva, El Torno, La Mancha, Venecia, Chinchorro, Las Delicias, Tosnovan, El Pital, and Las Flores, who have marketed products such as sweet pepper, eggplant, long beans, plantain, apple trees and dry coconuts. This activity had the support of SENA and the mayor’s office of San Marco, as well as Social Assistance from the catholic church (Pastoral Social). Coordination was carried out, through the UNDP's products for peace program, with a well-known Colombian chef and an international Hotel Group, who are supporting small producers with the commercialization of their products, so that they can visit the productive initiatives of the families that are participating in the project and identify some agricultural products that could have an added value to complement their business offerings through these products. During the visit, a gastronomic laboratory was carried out in the community of Pital, in San Marcos, where it was identified that 2 products had the potential to be commercialized in this type of market: sweet chili and manually processed creole rice. Based on this experience, the project makes the decision to support the establishment of one hectare of sweet pepper in 2 communities in order to access the gastronomic and hotel market. The Diploma course in "Actions of adaptation to climate change oriented to the productive component" was carried out in partnership with the University of Sucre; 26 public officials (14 men and 12 women) from 7 mayor’s offices, two environmental authorities and 2 governor’s offices participated in this course, which hada a duration of 3 months. This course aimed to provide tools for officials to incorporate climate change issues in the formulation of productive projects. | Highly satisfactory
| Output 4.2 - Training programme for the local communities and civil authorities for the implementation and sustainability of the climate change adaptation measures of project components 1, 2, and 3. |  | Training given to 35 civil employees, 115 promoters and 18,000 families on issues related to climate change. |  | 1,892 people, 747 women and 1145 men have received training in different topics related to adaptation to climate change, as described below: To promote the appropriation and dissemination of adaptation measures, 12 educational murals have been painted in reference to the adaptation to climate change in the communities of Chinchorro, Pital, Venecia, La Mancha, El Torno, Parcelas de Viloria, Mata de Caña, Sincelejito, Cecilia, Las Flores, Parcelas de Santa Fe, La Plaza, Las Pozas and El Chupo, These activities were led by the rural promoters, who involved the youth and members of the community. In this activity 139 people participated, 67 of them were women and 72 were men. 6 workshops were held on basic concepts of adaptation to climate change, aimed at students of educational institutions. 105 students, among them 50 boys and 55 girls participated in this activity. Technical advice to adapted family product systems in 19 communities (532 people, 143 men and 389 women). On the occasion of the celebration of the international day of the wetlands, one (1) bird watching day activity was held in the community of Sincelejito-Ayapel, with the support of the Audubon Society, a non-profit organization for the conservation of nature, where 28 people from different communities of the region participated (12 women and 16 men). This activity made it possible to make visible the work that the communities have been developing in terms of ecological restoration of wetlands. For the strengthening of capacities, 24 workshops have been carried out, in which 1088 people have participated, of which 864 are men and 224 are women. | Highly satisfactory
| Output 4.3 - Climate risk management considerations built into regional, local and environmental planning tools are coordinated with national planning guidelines |  | 3 risk management plans, in the municipalities of Ayapel, San Marcos and San Benito, incorporate considerations on climate change |  | The revision of the Risk Management plan of the Municipality of San Marcos was supported, for which 2 work meetings were held during which the climatological information generated by the project was incorporated. To this end, the scenarios of climate change and the vulnerability analysis were taken into account. Based on this information, the climatic profile of the municipality was defined, which was prepared by the project and was reviewed by the technical team on Risk Management of the Directorate of Climate Change of the Ministry of Environment and Sustainable Development. Additionally, within the framework of component 1, for the installation of the linimetric stations, the project had the participation of a technician from the risk management offices of the municipalities of San Marcos and San Benito. | Satisfactory
| Output 4.4 - Coordination among national, regional and local institutions guarantees sustainability of adaptation actions. |  | Articulation with the different local, regional and national institutions |  | Interinstitutional coordination is continued at the local level. In this sense, joint actions have been carried out with local universities, governor’s offices, SENA, the Corporations, Corpoica and producers associations. These coordinations have served as technical support to the different activities of the project. | Highly satisfactory
| 5.1 Monitoring & Assessment |  | Preparation of POA, Procurement Plan, Review and budgetary adjustment |  | Three technical committees, three steering committees and two consultants were held, where the following topics were addressed: Project extension approval - Presentation of Adjustments in the goals approved by the Kyoto Protocol fund. Presentation of progress in the execution of the project Presentation and application for approval of the project POA for 2018 Grant approval request to complete canal rehabilitation actions Grant approval request to establish 90 ha of sylvopastoral systems Grant approval request to support Artisan Women (in the use of fibers) Presentation of progress of the restoration actions within the framework of the letter of agreement with the Humboldt Institute Presentation of the project to give sustainability to the SAT by Corpomojana Technical proposal for the rehabilitation of canals. Presentation of the progress in the construction of the "Project Sustainability Strategy". Presentation of adapted soil-based housing, articulation with the National Adaptation Fund. Three quarterly and one annual reports were made, reflecting the progress of the project. There were two Monitoring visits in the field by Project Managers, and one by UNDP management. In March, the Kyoto Protocol visit was held. | Satisfactory
| 5.2 Project Management |  | Preparation of TOR for acquisitions and GRANT. Performance of evaluations of technical staff and renewal of contracts. Management of hiring of new staff members. Preparation of reports |  | The delegation of components 2 and 3 by MADS to UNDP was managed. Budget revision and adjustment of the POA was made. Financial follow-up was carried out The extension of the execution of the project was managed Monthly monitoring of payroll contracts The installation of the digital tracking of the vehicle was managed Accountability actions were held in 2 communities on the contributions of the project An execution of 93% of the POA was achieved. | Satisfactory
[5 empty] | Overall Rating | Highly satisfactory
Overall Rating
Please Provide the Name and Contact information of person(s) responsible for completing the Rating section
| Name: | Diana Isabel Díaz
| Email: | diana.diaz@undp.org
Please justify your rating. Outline the positive and negative progress made by the project since it started. Provide specific recommendations for next steps. . (word limit=500)
The project has made significant progress during this period, and it has managed to have a positive impact both at the community and institutional levels in the region of La Mojana. The project has achieved high visibility and impact generated with adaptation measures. The project has driven a positive change in the lives of more than 19 thousand families. The rating of this period is highly satisfactory because of the achievements reached in the 4 project components. For component 1, 3 of the 4 products are already consolidated and defined. The project is now at the consolidation phase of the early warning system, through the climate services center that will be installed in Corpomojana, with which the sustainability of component 1 actions will be guaranteed in the medium term. Likewise, there are 27 community-based early warning committees, which are in charge of ensuring the continuity of the actions of the component. In respect of component 2, which was among the ones that was falling behind, during this period it was possible to advance considerably; there are technical and institutional arrangements that have facilitated the rolling out of activities for the rehabilitation of ecosystems. A great deal of involvement has been achieved both by the communities and by the environmental authorities, who are providing technical support for the recovery of both water dynamics and wetland ecosystems, both of which aim to mitigate the adverse effects on the environment of climate change, since water recovery will help control and regulate floods and the restoration of ecosystems will help improve water conditions in communities. Component 3, like Component 1, is in the consolidation phase of its products and outcomes; work is being carried out on the exit strategy for this component, for which alliances are being made with entities such as SENA and the mayor’s offices to support small producers in the marketing of surpluses, in such a way that allows them to contribute with long-term sustainability to their productive systems. Component 4 has managed to drive ownership and commitment on the part of communities, grassroots organizations, as well as from local and regional institutions. Through training and education, it has been possible to have a positive impact in terms of knowledge, attitudes and practices related to climate change that are significantly contributing to the adaptation of inhabitants to climate change.
| Progress on Key Milestones |  | Expected Progress |  | Progress to Date | Rating
Implementing Agency | Output 1.1 - Hydrologic and hydraulic models for the Depresión Momposina region and the project’s target area support medium- and long-term decision-making. |  | Activity completed in the previous report |  | Activity completed in the previous report | Highly satisfactory
| Output 1.2 - Climate scenarios, trends in climate variability, and vulnerability analysis for the target area support decision-making for planning instruments and the implementation of adaptation measures |  | 6 local authorities in the area of ​​influence of the project have access to technical information related to climate phenomena and allow them to make decisions |  | The climate change scenarios and vulnerability analysis were delivered to 7 local authorities. The project continues to provide technical support to local institutions for the inclusion of such information in decision making (eg: formulation of projects with climate change considerations reported in output 4). In addition, the capacities of officials from 11 local institutions (7 mayor’s offices, 2 regional environmental authorities, 2 governor’s offices and 2 NGOs) were strengthened. They now have access to information from the Third National Communication on Climate Change and have the capacity to interpret the information related to the regional climate change scenarios 2011-2100, the vulnerability and risk assessments at the municipal level, and some actions that can be implemented to reduce the vulnerability of the population. | Highly Satisfactory
| Output 1.3 - Mechanisms for gathering, processing, and managing hydroclimatological information at the regional and local levels are strengthened and coordinated with the national hydroclimatological network. |  | 28 communities in the area of ​​influence of the project have the tools to monitor bodies of water |  | The respective maintenance (ground level surveys, overflow level surveys, liquid gauges, cross sections) of the meteorological stations installed by the project was carried out (9), thus ensuring that the stations continue to transmit the information with accurate data to the national hydro-climatic monitoring systems of the IDEAM. The country uses Hydras 3 as satellite reception system of hydroclimatic data in real time, so that the precipitation, temperature and flow data can be registered. The project currently has access to this information, which is interpreted by project professionals to monitor the condition of the San Jorge River basin, and then it is delivered to the regional environmental authorities and territorial entities as technical support for decision making regarding the generation or not of early warnings according to the protocols developed by the National Risk Management Unit. At the local level, it is worth noting the installation of 4 new viewing points that complete a network of 17 easily interpretable limnimetric stations for the communities that allow them to make decisions about their livelihoods according to the behavior of the levels of the bodies of water around them, benefiting 28 communities. | Highly Satisfactory
| Output 1.4 - An early warning system developed at the local level prepares local communities to reduce their vulnerability to extreme weather events. |  | 27 SATH community committees were formed and 14 were strengthened |  | To achieve the consolidation of the SAT, in the reporting period, progress was made in 2 aspects: 1. Definition of technical and personnel requirements for the establishment of a Regional Climate Services Center that will allow for collecting, processing and transmitting hydro-climatic warnings and forecasts at a regional scale in a timely manner and considering local specificities, for which a strategic alliance was made with CORPOMOJANA (Regional Environmental Authority), which will host the Climate Service Center in its facilities and will be responsible for providing sustainability once the project is completed. For this, it will have the technical advice of the IDEAM and the University of Cordoba. 2. The establishment of 13 new community committees for early warnings was achieved and the strengthening of the 14 existing committees was continued (7 in the Department of Córdoba and 20 in the department of Sucre), which have the goal of disseminating the hydroclimatological information collected through the limnimetric stations and generated in the agroclimatic bulletins issued by the agroclimatic working tables in their respective communities. Subsequently, the community committees will receive the information directly from the climate services center that is in the process of consolidation. Additionally, the project continued to support the participation of the communities (35 participants for the reporting period) at the agroclimatic tables, allowing them to access information on climate phenomena and their potential impacts on crops. | Satisfactory
| Output 2.1 - Hydraulic works for flood control and hydraulic management are in place. |  | Development of the strategy of hydrological recovery for flood control |  | According to the hydrodynamic information, the climate change scenarios and the vulnerability of the communities, the recovery of the water dynamics of 5 canals was prioritized (1 San Marcos, 2 in San Benito Abad and 2 in Ayapel). A methodological proposal was prepared for the physical and biological intervention of the canals, where all the activities will be implemented together with the communities, thus ensuring that they remain with the installed capacities both to maintain the intervened zones and to manage new interventions in conjunction with the environmental authorities who validated the methodology and granted the necessary permits to carry out such interventions. To this end, micro-capital agreements have been signed with 3 associations in the area (Asoagripeschis, Asomatias and Asofasan) that have received technical assistance on matters of: baseline survey (bathymetry and orthophotomosaics), sediment removal and production of plant material. Four workshops were developed with the communities of the area of ​​influence of the canals that will be intervened, seeking to socialize the methods of intervention in the canals (including training on techniques for the manual removal of macrophytes that can be applied directly in other canals of the region), in which 174 people participated. | Satisfactory
| Output 2.2 - Ecosystems associated with the hydrodynamics of the target area are restored. |  | Follow up to the Letter of Agreement signed with the Alexandre Von Humboldt Institute, for the rehabilitation of 700 has of Ecosystems of Wetland areas in La Mojana. |  | The research proposed by the Humboldt Institute has been completed with the purpose of having basic information for intervention, through a process of social strengthening within the areas for the recovery of ecosystem services of the wetlands. These research includes: 1. Characterization of ecosystem services by collecting the perceptions of the communities in relation to the uses of the species of flora, fauna and their habitats. 2. Ecology of the aquatic ecosystems where the macrohabitats of interest were characterized (physics, chemistry, and biology), including temporal and spatial variation, thus allowing to define the composition, structure and function of healthy ecosystems (characteristics that must be recovered in the areas to be intervened). 3. Monitoring program for wetland restoration with the definition of ecological (physical and biological) and social indicators (governance, community and productivity). It also has the prioritization of communities and areas to intervene (Pasifures, El Torno, Pital, Sincelejito, Seheve and Cuenca), and a record of 800 useful species for restoration with which landscaping arrangements are made as agreed with the owners of the properties. 94 hectares of connecting forests have been rehabilitated in the reported period with the participation of 219 families. With these, 134 hectares have been reached in total. It is planned to reach the remaining 566 within the next period. | Marginally Satisfactory
| Output 3.1 - Production practices resilient to climate change are adopted in the target area. |  | 100 families benefit from adapted, family-based productive systems 18,000 families receive training and assistance to ensure the sustainability of their family productive systems |  | The project helped provide technical assistance to 4340 families (during the reporting period) in terms of planning, establishment and maintenance of family gardens that involve considerations of climate change and variability, also taking into account cultural considerations of plant species consumed by communities and promoting the rescue of native seeds. The project supported the establishment of 162 new adapted family gardens, providing families with tools for their construction, advising on the designs and providing technical assistance for the development of the crops. In addition, it continued to provide technical support to the pond fish farming initiative promoted by the project in 2015, which has been complemented with the establishment of essential food crops and has proved to be an effective adaptation measure, considering the fact that during the last drought period 48 families (240 people) had uninterrupted access to food and generated surplus production that they did not have in previous periods of drought. | Highly Satisfactory
| Output 3.2 - Adaptive architecture programmes developed in flood-prone areas of the target area. |  | 5 community centers are built |  | In the reported period, the sites for the construction of the 10 community centers were selected, taking into account the 100-year flood projections and social variables that ensure that these sites can serve as shelter in cases of extreme flooding. The management efforts were put forth for the donation of the properties (transfer of public deeds to community associations or construction permits in public properties of the city halls) and the bidding process was opened for the contracting of the construction company, where unfortunately no bidder complied with the bidding process and the conditions for awarding of the contract. It is highlighted that the community center built by the project has become a space that encourages dialogue and social cohesion, which benefits 150 families. It develops exchanges of knowledge and promotes the solution of community problems that contribute to reducing their vulnerability by consolidating more resilient communities. Having the architectural designs of housing and community center adapted to the climate has allowed the project to make them available to the National Planning Department to be considered as prototypes to replicate in other areas of Colombia with similar biophysical conditions. | Marginally Satisfactory
| Output 3.3 - Agro-silvopastoral models incorporated into the multiple-use fluvial landscape contribute to the reduced vulnerability of local farmers. |  | 100 hectares of Sylvopastorile and agroforestry systems are implemented |  | A strategy was designed for the implementation of agrosylvopastoral systems that has allowed the establishment of 160 hectares of land owned by 93 small cattle farmers in the municipalities of Ayapel and San Marcos, bringing benefits to their families (465 people) through the improvement of pastures for livestock, management of paddocks for rotation, sowing of forage hedges, live fences and scattered trees that contribute to improving livestock conditions, making their farms more productive and decreasing economic losses during times of drought and flooding. These systems have also brought benefits in the recovery of the hydric dynamics of the wetlands, since the pressure of livestock grazing within sherds and floodplains has been reduced, and it is expected that they contribute in the recovery of bird species offering them habitat or food (Biological monitoring is currently being carried out and the results will be presented in the next period). The benefits of these systems have been so important that several beneficiaries are transferring the acquired knowledge to their neighbors, contributing in the propagation of productive practices adapted to the climate. | Highly Satisfactory
| Output 4.1 - Platforms for association and strengthening local communities are established for their appropriation and replication of the adaptation measures developed by the project. |  | 25 CBO’s are strengthened through the project and promote actions of adaptation to climate change. |  | It is worth highlighting the platforms promoted by the project in partnership with the National Learning Service - SENA, referred to as Farmers’ Biodiversity Squares (Plazas Campesinas de la Biodiversidad) where 11 associations market the surplus production of the adapted productive systems established in their small plots, which contributes in giving sustainability to project interventions and generate income to nourish their diet with products that they do not produce locally. During the reporting period, 12 community organizations were strengthened through different topics that include: training in administrative tools for the management of basic finances, training on organizational and legal aspects of associations according to Colombian legislation, and training for productive entrepreneurship . The above, with the purpose of complementing training on climate change issues that strengthen the social and organizational fabric to face adverse events caused by climate (e.g.: formulate projects and manage resources). | Highly Satisfactory
| Output 4.2 - Training programme for the local communities and civil authorities for the implementation and sustainability of the climate change adaptation measures of project components 1, 2, and 3. |  | Training for 35 officials, 115 promoters and 1,800 families on climate change issues. |  | 1,892 people were trained on issues of adaptation to climate change. The topics addressed in the training were: operation and mechanism of a system of early warnings, water rehabilitation and ecosystem restoration and adapted production systems, among other topics. | Highly satisfactory
| Output 4.3 - Climate risk management considerations built into regional, local and environmental planning tools are coordinated with national planning guidelines |  | 3 risk management plans, in the municipalities of Ayapel, San Marcos and San Benito, incorporate climate change considerations |  | The project continuously supports regional and local institutions by providing information regarding climate change and its effects on the territory. Particularly, it contributed to the revision of the Risk Management Plan of the municipality of San Marcos, where climate change and variability considerations were incorporated. Additionally, the project supports the formulation of projects to the Government of Sucre, Corpomojana, and the Sinú and San Jorge Valleys, which involve the management of resources to implement adaptation measures to climate change, and the generation of early warnings and hydroclimatic forecasts for decision making at the local level. | Highly Satisfactory
| Output 4.4 - Coordination among national, regional and local institutions guarantees sustainability of adaptation actions. |  | Articulation with the different local, regional and national institutions |  | The project has spaces of continuous coordination with institutions of national, regional and local level in which decisions of technical and strategic orientation of the project are taken with the purpose of ensuring the sustainability of the actions implemented within the project. To date, the following sustainability strategies have been agreed: It has been managed with the CARs to give sustainability to the water rehabilitation actions and the recovered ecosystem areas. The Corporation of the Valleys of Sinú and San Jorge has committed to technical support and monitoring. Corpomojana, in turn, will host and ensure the sustainability of the forecast center. For this, it has already obtained resources from the national government for the financing of the technical equipment that will operate the Center. With the Green Climate Fund project, which was managed thanks to the positive impacts of the project, it will give continuity to the issues of early warnings, ecosystem restoration and community training on matters related to adaptation to climate change | Highly Satisfactory
| 5.1 - Monitoring and Assessment |  | Preparation of POA, Procurement Plan, Review and budgetary adjustment |  | The project has fulfilled the preparation of its planning instruments (annual operating plan, procurement plan and budget reviews) that have been reviewed and approved by the technical and management committee instances. The project has carried out three technical committees and three management committees in the reporting period, showing the progress in the implementation of the project and receiving feedback and strategy guidance from participating institutions. Based on the recommendations of the Mid Term Evaluation, the project managed the extension of the project before the Kyoto Protocol Adaptation Fund, after which the new end date is June 2019. Finally, a follow-up visit was carried out to the actions implemented with the communities, with the participation of the Kyoto Protocol Adaptation Fund, the Ministry of Environment and Sustainable Development and the UNDP. | Highly Satisfactory
| 5.2 - Project Management |  | Preparation of TOR for acquisitions and GRANT. Performance of evaluations of technical staff and renewal of contracts. Management of hiring of new staff members. Preparation of reports |  | All the processes of hiring personnel and acquisitions required by the project have been managed in a timely manner. It is worth noting the adaptive management applied by the coordination of the project, the institutional management at different levels fostered by the project and the level of relationship of the work team with the communities, which have bolstered the success of the adaptation measures promoted and the appropriation thereof by the communities. | Highly Satisfactory
Overall Rating
| Please justify your rating and address the following points: 1. Indicate trends, both positive and negative, in achievement of outcomes as per the project indicators. 2. Detail critical risks that have affected progress. 3. Outline response to MTR undertaken this reporting period. 4. Outline action plan to address projects with a rating of HU, U or MU. Please keep your input to 1200 words |  | During the reported period, the project has made significant progress towards meeting the established goals. It is worth highlighting the work done to consolidate the actions promoted and the search for their sustainability, through the strengthening of communities and their forms of organization, as well as the search for partnerships with local, regional and national governments that allow to continue and strengthen the achievements of the project in the future. it is also worth noting the commitment and work of the community-based committees of early warnings that constitute networks organized and coordinated with the local, regional and national institutions, to effectively respond to adverse hydroclimatological impacts, thus reducing the vulnerability of the rural families of La Mojana. This same social ownership is notorious in the adaptation measures fostered by the project, generating tangible impacts on the livelihoods of the families, represented in a richer diet and more stable income when faced with periods of flood or drought. The project has also shown to have good practices and lessons learned that are of interest for multiple actors, including government entities, agencies or NGOs implementing projects. The project will continue to systematize their experiences and develop a communication strategy to be able to get more stakeholders to use and replicate what they have learned within the framework of this project. There are still some delays in the execution, mainly related to the difficulty of finding companies or personnel that understand the local context and that can provide their professional services in La Mojana. The project continues to work to overcome these delays and complete the planned activities with the intention of generating the highest possible benefits for the communities. |  |  | Satisfactory (S)
Please Provide the Name and Contact information of person(s) responsible for completing the Rating section
| Name: | Jimena Puyana
| Email: | jimena.puyana@undp.org
| Progress on Key Milestones |  | Expected Progress |  | Progress to Date | Rating
Other | Output 1.1 - Hydrologic and hydraulic models for the Depresión Momposina region and the project’s target area support medium- and long-term decision-making.D9. |  | Activity completed in the previous report |  | This activity was completed as of March 2017 | Highly satisfactory
| Output 1.2 - Climate scenarios, trends in climate variability, and vulnerability analysis for the target area supports decision-making for planning instruments and the implementation of adaptation measures |  | 6 local authorities in the area of ​​influence of the project have access to technical information related to climate phenomena and allow them to make decisions |  | The project has worked on the socialization of the information of climatic scenarios and, in general, on all the strengthening that has been done to the environmental information system, which implies the acquisition and improvement of equipment and, following that, the generation, processing and socialization of information that may influence the decisions that may be affected by the hydrometerological and climatic conditions of the La Mojana region. Not only has it been responsible for generating spaces with local authorities; this information has also been decisive when making decisions on the project and for the implementation of the different measures of Adaptation to Climate Change. In this period 11 local institutions, (27 people); of the following institutions, 7 mayor’s offices (Achí, Caimito, Guaranda, Majagual, Ayapel, San Marcos and San Benito Abad), 2 corporations CVS and Corpomojana, 2 governor’s offices, Cordoba and Sucre, 2 NGOs, Paisajes Rurales and Asociación Agropecuaria, received the information of the scenarios of climate chantge prepared by the Third National Communication. These scenarios contain regional and municipal information that allows the authorities to make decisions for the planning of their municipalities. | Highly satisfactory
| Output 1.3 - Mechanisms for gathering, processing, and managing hydroclimatological information at the regional and local levels are strengthened and coordinated with the national hydroclimatological network. |  | 28 communities in the area of ​​influence of the project have the tools to monitor bodies of water |  | For the project, it has been a great challenge to involve the communities in the generation of information and, at the same time, to have them develop the capacity to process the information that is generated with the hydrometeorological equipment installed in the region. With the support of IDEAM, easy-to-read limnimetric stations have been installed by the communities, which has allowed them to become more familiar with the importance of dealing with these alerts, and to make decisions in order to reduce the possible impact caused by recurrent hydro-meteorological threats in the region. Likewise, it is worth highlighting the work done by the rice growers guilds in Córdoba and Sucre, who have mechanisms in place for monitoring and following up on the hydro-meteorological variables that can affect their production processes. Spaces are created for the exchange of information and the mechanisms to reduce vulnerability before the impacts are generated. In it, the local authorities and communities linked to the project participate actively. In these spaces, 20 communities represented by 35 people received the alert bulletins generated by the agroclimatic working tables of Cordoba and Sucre, with which the small producers could access reliable information that allows them to plan the establishment of their crops in accordance with the weather conditions of the region. | Highly satisfactory
| Output 1.4 - An early warning system developed at the local level prepares local communities to reduce their vulnerability to extreme weather events. |  | 27 SATH community committees were formed and 14 were strengthened |  | During the reporting period, work was done to strengthen the proposal for the definitive establishment of the Early Warnings System. This included work with the community committees, on their consolidation, on installing the necessary equipment for the measurement of the flows, on the integration of all this information, in permanent link with the risk management offices of the Municipalities and departments and in the definition of the local operator of the Early Warnings System in the Environmental Corporation of La Mojana, CORPOMOJANA. All this work was foreseen to allow the Early Warnings System to enter into operation, through a Climate Services Center installed and operating in CORPOMOJANA, a regional entity that has shown to have the will to make this happen, and is managing the sustainability of the Service Center, presenting a project to finance, with national public sources, the commissioning and operation once the project ends. | Highly satisfactory
| Output 2.1 - Hydraulic works for flood control and hydraulic management are in place. |  | Development of the strategy of hydrological recovery for flood control |  | During the last year it was possible to consolidate the intervention proposal for the rehabilitation of 5 canals, of which 3 have already begun rehabilitation activities. This proposal considered all the information of the hydrodynamic modeling and the analysis of climate change variability, allowing decisions to be made regarding the rehabilitation and intervention needs of the prioritized canals. Within this proposal, apart from defining the need to make a baseline and identify monitoring activities, the leadership of the communities in the rehabilitation activities was established within the intervention methodology. This was made possible through the signing of three GRANTS with farmers associations that are within the area of ​​intervention of the three prioritized canals, and which started activities in the reported period. In all this work the accompaniment of environmental corporations in the region has been essential: the CVS and CORPOMOJANA, entities that have participated in the collection of information for the design of interventions in the canals, and now in the execution, verifying and authorizing each one of the activities contemplated for the rehabilitation of the 3 canals and the 2 additional ones that will be worked on during the following period. | Satisfactory
| Output 2.2 - Ecosystems associated with the hydrodynamics of the target area are restored. |  | Follow up to the Letter of Agreement signed with the Alexandre Von Humboldt Institute, for the rehabilitation of 700 has of Ecosystems of Wetland areas in La Mojana. |  | Through the rehabilitation activities of wetland ecosystems executed through the Alexander von Humboldt Institute and with the support of regional partners such as the University of Córdoba and Corporación Paisajes Rurales, knowledge has been generated, until now non-existent in the country, in relation to the processes of rehabilitation of wetland ecosystems. In other words, within the framework of the activities carried out in this component, priority areas have been defined in the region of La Mojajana (11 municipalities) to carry out rehabilitation actions and the most appropriate measures have been defined to address the problem, including the generation of seedlings incident to this type of ecosystem. All this work will undoubtedly serve so that different environmental entities of the region, and local public entities, have the necessary information to formulate better public investment projects that address the problems of the region in the face of the degradation of this type of ecosystem. In support of the above, the following activities have been developed: Characterization of ecosystem services in the region Ecological research of aquatic ecosystems 3 pilots of aquatic habitat restoration exercises Implementation of amphibian lifestyles in 10 families Technical proposal for technical monitoring Strategy and activities for outreach and community ownership In the remainder of the project, all activities developed around this Output should be concentrated on the implementation of restored hectares to comply with the goals of the logical framework, which has been delayed as compared to what programmed, thus entailing a great challenge for the project and its implementation in the year that remains, also taking into account how difficult it can be to intervene a wetland ecosystem, given the changing climate conditions for the region and the characteristics of this type of ecosystems | Marginally Satisfactory (MS)
| Output 3.1 - Production practices resilient to climate change are adopted in the target area. |  | 100 families benefit from adapted, family-based productive systems 1,800 families receive training and techincal assistance to ensure the sustainability of their family productive systems |  | The activities to promote productive systems adapted to climate change have been developed since the beginning of the implementation of this project. Taking into account the installed capacity and progress achieved with families linked to the project through the establishment of 1,333 family gardens and 1,217 organic family crops, 729 hectares of native rice sown, 3 community rice mills with storehouse area and an established community fish pond, the project team has made progress during the last period in continuing to provide accompaniment to families that continue to develop this type of activities. Farmer’s markets have been promoted in the urban areas of the region, in which the communities bring the products grown in their family gardens to commercialize them. This has been a great initiative that begins to open local markets, thus decreasing the vulnerability of families, as not only is it contributing to food security problems, but it is also generating additional income. During the reporting period, progress was made in defining the strategy for the promotion of artisanal fibers with women from the region. It is expected that in the coming year these activities will be implemented. | Highly satisfactory
| Output 3.2 - Adaptive architecture programmes developed in flood-prone areas of the target area. |  | 5 community centers are built |  | During the reported period, the construction of the community centers has not been achieved; however, the entire pre-contractual stage has been completed. The areas in which the community centers would be carried out were also identified, having, as a technical support, the modeling information of the flood threat and the authorization of the municipal mayor’s offices to carry out the work. It is expected that in the coming period we will be able to contract the construction of the community centers, because of the 11 that are planned, we have built one as a pilot, which has allowed us to identify the costs of the remaining ones. However, it is a great achievement for the project to have the designs of this infrastructure because they respond to the needs of the communities and respond to the hydrometerological phenomena of the region. They can be replicated not only by the local public institutions, but also by the communities themselves, because they generated self-construction mechanisms that allow for these orientations. The community center already built in the community of El Torno (San Marcos - Sucre) has contributed to the empowerment of the community. The center is not only used as a temporary shelter in case of flood risk, but it has also strengthened the union and the association of the community around the need to implement measures to adapt to climate change. They are aware that the more united and strengthened they are as a community, it will be easier to face these challenges posed by climate change. This is how the community center has become a space for dialogue and coordination that has promoted ties around the social problems of the community. | Marginally Satisfactory (MS)
| Output 3.3 - Agro-silvopastoral models incorporated into the multiple-use fluvial landscape contribute to the reduced vulnerability of local farmers. |  | 100 hectares of Sylvopastorile and agroforestry systems are implemented |  | In this period, significant progress has been made in these activities. 160 hectares of Agrosylvopastoral Systems were implemented and the immediate implementation of 90 additional hectares is planned. This process has generated, in the participating families, the need to expand the activities developed and serve as an example to other members of the community to develop the project and the Agrosylvopastoral arrangements in their plots, since they have seen the results in the short time of implementation, thus raising important awareness for maintaining the activities that have been developed. The achievements and the empowerment of participant families that has been fostered has been possible thanks to the implementation mechanisms facilitated by the UNDP, such as the direct implementation through the technical team of the project and the GRANT implementation (Subsidy Agreements) with the farmers’ associations of each participant community. | Highly satisfactory
| Output 4.1 - Platforms for association and strengthening local communities are established for their appropriation and replication of the adaptation measures developed by the project |  | 25 CBO’s are strengthened through the project and promote actions of adaptation to climate change. |  | The strengthening of local capacities has been fundamental in the execution of each of the components of the project. This has been achieved through two mechanisms, the training of rural promoters who are also linked to each of the activities of adaptation to climate change that have been developed, and through the support to the formalization and strengthening of the Farmers Associations within the communities linked to the project. The support provided in this training process by the public Universities of the region has been fundamental, and thanks to this it has been possible for 23 organizations to be continuously involved in processes to strengthen their capacities, of which 7 have received training from the National Learning Service (SENA) in accounting and basic administration issues, in addition to technical training processes for the entrepreneurship of productive units with minor species. | Highly satisfactory
| Output 4.2 - Training programme for the local communities and civil authorities for the implementation and sustainability of the climate change adaptation measures of project components 1, 2, and 3. |  | Training given to 35 civil employees, 115 promoters and 18,000 families on issues related to climate change. |  | Just as farmer associations have been included in the process of strengthening their capacities, this work has also been carried out with the public officials of the region through the development of the diploma course in "Actions for adaptation to climate change oriented to the productive component"; 26 public officials from 7 mayor’s offices, two environmental authorities and 2 governor’s offices participated in this diploma course, which had a duration of 3 months. This diploma course allowed local actors to start participating in other instances of dialogue on issues of adaptation to climate change arising in the region, such as the agroclimatic working tables, convened by the productive associations of each department, in which, in addition to the participation of producers, municipalities and environmental corporations are also linked, since these entities also promote productive activities in the region. In addition to the training processes, the participation of local public authorities in each of the adaptation measures has been fundamental, since they are linked to each of the activities that are carried out by the different components of the project, such as the Early Warnings System, the construction of community centers, the rehabilitation of canals and the inclusion of climate change issues in development planning instruments. | Highly satisfactory
| Output 4.3 - Climate risk management considerations built into regional, local and environmental planning tools are coordinated with national planning guidelines |  | 3 risk management plans, in the municipalities of Ayapel, San Marcos and San Benito, incorporate considerations on climate change |  | The work with the institutional authorities has been permanent. The corporations and municipalities are participating in different instaces created in the region around the issues of adaptation to climate change, such as the departmental adaptation table of the Department of Córdoba, the agroclimatic tables of Córdoba and Sucre and the project's advisory committees, whose purpose is to identify common points around the activities promoted in the region. As a result of this participation, the formulation of public investment projects has been promoted, so that, with domestic sources, measures of adaptation to climate change will be implemented, previously identified and prioritized in the development planning instruments. In a previous period of execution of the project, the incorporation of climate change criteria was supported in the Development Plans. Now in the period that is being reported in this PPR the formulation of Risk Management Plans is being supported, which make use of the information that has been generated. | Highly satisfactory
| Output 4.4 - Coordination among national, regional and local institutions guarantees sustainability of adaptation actions. |  | Coordination with the different local, regional and national institutions |  | Through the different committees that the project has: Steering Committee, Technical Committee and Advisory Committee spaces have been generated for institutional articulation, which have enabled a continuous and active participation of each of the participating entities. The dynamics of implementation of the project during the last year have been significant, achieving the fulfillment of the established goals and at the same time giving rise to a reduction in the levels of vulnerability of the families and communities linked to the project. | Highly satisfactory
| 5.1Monitoring and Assessment |  | Preparation of POA, Procurement Plan, Review and budgetary adjustment |  | The project has been implemented under the UNDP procedures, developing all the monitoring, auditing and evaluation processes that have been defined. However, from the Project Directorate under the Ministry of Environment and Sustainable Development, a continuous and permanent follow-up has been carried out to the activities developed, supporting, at the same time, the technical decisions that are required for the implementation of the adaptation measures. | Highly satisfactory
| 5.2 Project Management |  | Preparation of TOR for acquisitions and GRANT. Performance of evaluations of technical staff and renewal of contracts. Management of hiring of new staff members. Preparation of reports |  | The Ministry of Environment and Sustainable Development has supported coordination in all activities related to the execution of the activities and all that this implies, such as the review of the TOR and participation in the selection processes that have been carried out. To facilitate execution, delegations of components 2 and 3 were requested to the UNDP, which means that the activities will be executed directly by UNDP, and direct technical support will be continued in each of the decisions taken in relation to these components. | Highly satisfactory
[5 empty] | Overall Rating | Satisfactory
Please Provide the Name and Contact information of person(s) responsible for completing the Rating section
| Name: | Mariana Rojas Laserna
| Email: | marrojas@minambiente.gov.co
| Please justify your rating and address the following points: 1. Indicate trends, both positive and negative, in achievement of outcomes as per the project indicators. 2. Detail critical risks that have affected progress. 3. Outline response to MTR undertaken this reporting period. 4. Outline action plan to address projects with a rating of HU, U or MU. Please keep your input to 1200 words "Por favor, justifique su calificación y tratar los siguientes puntos: |  | During the reported period, significant advances can be seen in relation to the execution of the project and raising awareness with stakeholder families, who show increasing ownership with respect to the developed measures. Emphasis in the construction of local and institutional capacities has been made in order to guarantee, to a great extent, the sustainability of the promoted activities; in turn, spaces with other local public organizations for the promotion of new projects have been generated, which replicate or give continuity to the measures for adaptation to climate change using, for this purpose, the information and knowledge generated by the project In the final phase that the project is undergoing, the achievements, difficulties and advances have been disseminated to other projects of similar characteristics, which are starting to be implemented throughout in the country, becoming a reference for each of the planning and implementation processes developed by them. In relation to the implementation during this last year, it is worth highlighting the progress made on activities of implementation of Agrosylvopastorile Systems, rehabilitation of the natural hydric dynamics of tributaries (3 prioritized tributaries), and establishment of the Early Warnings System. The success in its implementation has been the active participation of the environmental authorities, the municipal governments and mayor’s offices that by their own initiative have advanced actions to give continuity to the developed activities. This has also been possible through the different settings for interinstitutional dialogue in which the national government, through the project, has generated the capabilities and taken the information to the region, making it possible for them to gain access to different sources of funding. In the year that is left for implementation of the project, it is mainly expected to fulfill the activities of rehabilitation of wetland ecosystems, the two additional tributaries prioritized for rehabilitation, the definitive consolidation of the Center of Climate Services for the operation of the Early Warnings System and the construction of the community centers, because in this last case, the adverse conditions incident to the region have made it difficult to contract for this type of works with such specific designs and unprecedented in the region. Nevertheless, the possibilities that facilitate this process are already being assessed with the implementer (the UNDP).
[5 empty] | Overall Rating | Satisfactory
|  |  | Satisfactory (s) | Satisfactory
Rating Definitions
| Highly Satisfactory (HS) | Project actions/activities planned for current reporting period are progressing on track or exceeding expectations to acheive all major outcomes/outputs for given reporting period, without major shortcomings. The project can be presented as “good practice”.
| Satisfactory (S) | Project actions/activities planned for current reporting period are progressing on track to achieve most of its major outcomes/outputs with only minor shortcomings.
| Marginally Satisfactory (MS) | Project actions/activities planned for current reporting period are progressing on track to achieve most major relevant outcomes/outputs, but with either significant shortcomings or modest overall relevance.
| Marginally Unsatisfactory (MU) | Project actions/activities planned for current reporting period are not progressing on track to achieve major outcomes/outputs with major shortcomings or is expected to achieve only some of its major outcomes/outputs.
| (U) | Project actions/activities planned for current reporting period are not progressing on track to achieve most of its major outcomes/outputs.
| Highly Unsatisfactory (U) | Project actions/activities planned for current reporting period are not on track and shows that it is failing to achieve, and is not expected to achieve, any of its outcomes/outputs.

## Project Indicators
PROJECT Indicators
Please provide all indicators being tracked for the project as outlined in the project document
Type of Indicator (indicators towards Objectives, Outcomes, etc…)
Type of Indicator | Indicator | Baseline | Progress since inception | Target for Project End /
Objective | Number of poor households in three municipalities in the project area vulnerable to climate-related events (disaggregated by gender). | La Mojana was severely affected by the La Niña event of 2010-2011. Approximately 211,857 people (43.4% of the total population) were affected in 2010 by flooding in this area. The three target municipalities present an average NBI of 62.25% which is well above the national average of 27.27%, indicating high levels of poverty and low levels of access to education, housing, health, and basic sanitation and sewer services. | 33,084 people, 19,568 women and 13,516 men (6,616 families) vulnerable to the effects of climate change, of whom 58% are women (19,568), in 44 communities, benefit from project activities and develop capacities for adaptation. The components of the project have benefited the population of La Mojana as follows: Component 1: 19,085 people (9,564 women and 9,521 men) Component 2: 15,928 (7,947 women and 7,981 men) Component 3: 8. 312 people (3,901 women and 4,411 men) Component 4: 806 people (465 women and 341 men) and (26 public officials) Of the total beneficiaries, 5,847 benefit from several components. |  By the end of the project, at least 54,000 of the most vulnerable people (10,800 families) in the municipalities of Ayapel, San Marcos, and San Benito Abad of the Depresión Momposina region, covering an area of 406,054 ha, will benefit from the proposed direct solutions to problems caused by flooding.
Outcome 1: The existing hydroclimatological and ecological information system (HEIS) is strengthened and used by local- and regional-level stakeholders, improving their resilience to the impacts of climate change. | 1. Number of hydroclimatological stations in La Mojana reporting climate-related data as part of the national network. |  The project area has: a) two (2) automated flow stations linked to IDEAM’s alert system (in the Cauca River near the project area); b) five (5) precipitation-measuring stations; c) two (2) climatological stations; d) one (1) water level-measuring station in the San Marcos lagoon/wetlands complex; and e) one (1) water level-measuring station in the Ayapel lagoon/wetlands complex.  There are no local monitoring networks. | Indicator completed in the previous report. Eleven (11) automatic hydro climatological stations and an ADCP are creating information that helps the decision-making process related to the climate risks management. These stations are integrated in the IDEAM (Institute of Hydrology, Meteorology and Environmental Studies) monitoring network. With the installation of these stations, the San Jorge’s and Cauca’s rivers’ basins are being monitored; these rivers have influence in the Mojana region. The Mojana’s stations network is comprised of five (5) rain gauge stations, two (2) meteorological stations and four (4) hydrological stations. These stations are transmitting information via satellite to IDEAM’s (Institute of Hydrology, Meteorology and Environmental Studies) forecast room; this allows preparing forecasts and warning bulletins, which are submitted to local institutions. This information is included in the monthly bulletins prepared by Cordoba and Sucre`s agro climatic technical tables. Said bulletins are delivered to the producers of the region each month. The IDEAM (Institute of Hydrology, Meteorology and Environmental Studies) has provided Cordoba University with access to the climatological information platforms in order to strengthen research processes in th |  By the end of the project at least two (2) automated hydrological stations, two (2) automated climatological stations, and five (5) automated precipitation stations, some with satellite transmission operating.
| 2. Number of institutions and local- and regional-level stakeholders that have access to climate change-related information and integrate it into their work. |  There is only a national-level climate change effects scenario evaluation tool in use. | During this period 11 local institutions, (27 people); of the following institutions, 7 mayor’s offices (Achí, Caimito, Guaranda, Majagual, Ayapel, San Marcos and San Benito Abad), 2 corporations, CVS and Corpomojana, 2 governor’s offices, Cordoba and Sucre, 2 NGOs, Paisajes Rurales and Asociación Agropecuaria, received the information of the scenarios of climate change prepared by the Third National Communication. These scenarios contain regional and municipal information that allows the authorities to make decisions for the planning of their municipalities. In the same way, 20 communities, 35 people, among which 19 are men and 16 women, received the warning bulletins generated by the agroclimatic tables of Cordoba and Sucre, with which the small producers could access reliable information that allows them to plan the establishment of their crops according to the weather conditions of the region. 50 institutions and local stakeholders have access to information related to climate change that is generated by the project and can integrate it into their work. They are: 1) Planning office and risk management committee at the mayoral office in Ayapel 2) Planning office and risk management committee at the mayoral office in San Marcos 3) Planning office and risk management committee at the mayoral office in San Benito Abad 4) Municipal Council of Ayapel 5) Municipal Council of San Marcos 6) Municipal Council of San Benito Abad 7) CORPOMOJANA (CARs) 8) CVS - The Regional Autonomous Corporation for the Sinú and San Jorge Valleys 9) Universidad Pontificia Bolivariana (Montería campus) 10) Risk Council for the Department of Córdoba 11) Risk Council for the Department of Sucre 12) National Adaptation Fund 13) Alexander Von Humboldt Institute 14) Sucre regional government 15) National Planning Department 16) Seheve: Fishermen and Agricultural Producers Association ASOPESAGRO (Ayapel) 17) Cecilia:Fishing and Livestock Productive Association ASOPROPEGACE (Ayapel) 18) Sincelejito; Association of Farmers, Fishermen and Restorers ECOAYAPEL (Ayapel) 19) Rondón; Community Action Board of Rondón (Ayapel) 20) Los Negritos: Association of Men and Women Farmers (Ayapel) 21) Alfonso Lopez: Association of Producers for Development (Ayapel) 22) Alfonso Lopez: Community Action Council (Ayapel) 23) Pañuelo: Community Action Council (Ayapel) 24) Alemania: Community Action Council (Ayapel) 25) Guartinaja: Community Action Council (Ayapel) 26) El Cuchillo: Community Action Council (Ayapel) 27) Corea: Community Action Council (Ayapel) 28) Mata de Caña: Community Action Council (Ayapel) 29) 8Las Guaduas: Community Action Council (Ayapel) 30) Las Chispas: Association of Farmers and Fishermen ASOAGRIPESCHIS (San Benito Abad) 31) Chinchorro: Association of Farmers (San Benito Abad) 32) Pasifueres:Association of Farmers, Livestock Producers, Fish Farmers and Environmentalists ASPASFU (San Benito Abad) 33) Tosnovan: Agricultural Association of Indigenous Peoples, Afro-descendants, Farmers and Displaced Persons ASOAGROCAMTOS (San Benito Abad) 34) Cuiva: Association of Women (San Benito Abad) 35) La Plaza: Community Action Council (San Benito Abad) 36) Las Pozas: Community Action Council (San Benito Abad) 37) Parcelas de Santa Fe: Community Action Council (San Benito Abad) 38) Venezuela: Community Action Council Parcelas (San Benito Abad) 39) Las Delicias: Community Action Council (San Benito Abad) 40) Cauchal: Community Action Council (San Benito Abad) 41) Caño Caimán: Community Action Council (San Benito Abad) 42) La Costera: Community Action Council La Costera (San Marcos) 43) Cuenca: Community Action Council Cuenca (San Marcos) 44) La Costera: Association of Farmers and Fishermen of La Costera AGRIPEC (San Marcos) 45) El Pital: Association of Fishermen, Farmers and Protectors of Natural Resources APAPI (San Marcos) 46) Las Flores: Agricultural Association of Indigenous Peoples, Afro-descendants, Farmers and Displaced Persons of Las Flores, San Marcos, Sucre ASOAGROCAMLASFLORES. (San Marcos) 47) El Torno: Association of Women, Women Farmers and Fishermen - Farmers ASOCAMTOR (San Marcos) 48) Parcelas de Viloria:Association of Farmers of Viloria, La Mancha, Venecia Tres and Mancha Tres (San Marcos) 49) Palo Alto: Association of Agroecological Producers. 50) La Mancha: Association of Agricultural and Fish Farming Families of San Jorge (San Marcos) This information corresponds to: i) the results from the La Mojana hydrological and hydraulic modeling processes, performed by the National Adaptation Fund; ii) the results of the participatory rural appraisal about the vulnerability to climate change and climate variability, iii) eco-regional analysis for restoration, iv) methodology for the creation of development plans with the incorporation of Climate Change elements, data sheets about actions (gardens, silvopastoral systems, rainwater training, seed bank, rice mills), v) good practices calendar, vi) posters about good practices to mitigate mercury contamination in fish and rice seeding. | By the end of the project direct access at the local and regional levels to information related to climate change is increased in the three targeted municipalities as follow: a) three mayoral offices (Ayapel, San Marcos, and San Benito Abad); b) three CLOPADs; c) two CREPADs; d) two CARs (CVS and CORPOMOJANA); and e) eleven CBOs
| 3. Number of rural communities and local and regional institutions in the target area benefiting from an early warning system that reduces risks to extreme climate events. |  There is no early warning system in the project area; the only warnings provided are alerts regarding the Cauca River and rainfall that IDEAM issues through periodic bulletins.  Daily bulletins from CVS based on IDEAM’s reports. | 19,085 people (9,564 women and 9,521 men) are benefiting from the warnings system in 43 communities. The benefits to the inhabitants have been passed on through the creation of 27 Community Committees of Warning Systems, installation of limnimetric stations that monitor water bodies and climatological information that facilitates decision making. | 100% of rural communities (6,440 women and 6,860 men) and local and regional institutions in the project area benefit from an early warning system after 5 years.
Outcome 2: Rehabilitation of wetlands and their hydrology in a target area as a means to reduce risk to flooding and drought associated with climate change. | 1. Percentage of households in La Mojana that benefit from infrastructure to control flooding (disaggregated by gender). |  A provisional work in the Sejeve area to control flooding and 146 affected families in 2010 in the towns of Sincelejito, Cecilia, and Sejeve (Ayapel municipality).  Zero (0) infrastructure and 500 affected families in 2010 in the towns of El Pital, Cuenca y Las Flores (San Marcos municipality).  Zero (0) infrastructure and 138 affected families in 2010 in the towns of Las Chispas, Pasifiere, Tornobán, Chinchorro y El Torno (San Benito Abad municipality). Note: Baseline data does not change, however they have been updated for 2012. | Work has begun on water rehabilitation for the control of floods in 5 canals of importance in the area of ​​influence of the project, bringing benefits to 15,928 people. The activities that have been planned contribute to the recovery of the water dynamics of the following canals: Caño Mosquito, Caño San Matías, Caño Seheve, Caño las Delicias, and Caño San Matías, interventions that are bringing benefits to the following populations. • At least 50% of the families, 3,568 people (2,143 men and 1,425 women) in the localities of Sincelejito, Cecilia and Rondón, Corea, Mata de Caña, Los Negritos, Cuchillo, Alfonso López, Barcelona Caracolí, San Elena, Las Marias and Sejeve (Ayapel municipality). • At least 50% of the families 6,630 people (3,476 women and 2,884 men) in the townships of Las Delicias, Pasifueres, Venezuela, El Cauchal, Tosnovan and La Guaripa (Municipality of San Benito Abad). • At least 50% of families (3,323 women and 2,737 men) in the districts of El Torno, Campanito, Monosolo, Venice, La Mancha, Parcelas de la Gloria and Parcelas de Viloria (municipality of San Marcos) |  At the end of the project, at least 50% of families in the three selected municipalities benefit from the infrastructure to control floods, as follows: • At least 50% of the families (1,543 men and 1,127 women) in the towns of Sincelejito, Cecilia, and, Rondón, Corea, Mata de Caña, Los Negritos, Cuchillo, Alfonso Lopez, Barcelona Caracolí, San Elena, Las Marías (municipality of Ayapel). • At least 50% of families (3,323 women and 2,737 men) in the districts of El Torno, Campanito, Monosolo, Venice, La Mancha, Parcelas de la Gloria and Parcelas de Viloria (municipality of San Marcos). • At least 50% of families; 801 women and 709 men in the localities of Las Delicias, Pasifueres, Tosnovan and La Gauripa (municipality of San Benito Abad).
| 2. Area (ha) of rehabilitated wetlands that help to reduce vulnerability to climate change. |  250 hectares reforested with Acacia magnum in 2004 along the La Quebradona stream in the Ayapel lagoon/wetlands complex (Ayapel municipality).  120 hectares reforested in 2004 with oak trees along the Muñoz, San Mateo and Trejos streams (San Marcos municipality; most trees were lost in 2005 due to flooding).  Zero (0) ha rehabilitated in the San Benito Abad municipality. | 134 Hectares have been directly intervened in recovery of vegetation cover and approximately 5000 m2 in productive paddocks, as follows 10.97 hectares rehabilitated from the tributary system of the Ayapel Marsh / wetland complex. 58.02 rehabilitated from the tributary system of the San Jorge River along Santiago and the Canoas streams). The representative ecosystems of las Ciénagas, Cuenca or Costanera, Las Flores, Florida, small micro-basins such as the streams and creeks of La Hicotea, Los Emilianitos, Aguasclaras, Aguasprietas, Mabobo, La Pita. 47.01 hectares rehabilitated from the tributary system of the San Benito Abad wetlands. | At the end of the project, at least 700 hectares of the tributary system of the three main lagoons / wetland complex were rehabilitated as follows: 550 rehabilitated hectares of the Ayapel marsh affluent system / wetland complex. The ecosystems representative of this sector are the San Jorge rivers, which passes through the western side of the town of Sehéve and the Cauca river through the San Matias canyon next to Sincelejito, with a wide network of drainages. Other important aquatic ecosystems such as Caño Viejo and Ayapel marsh stand out . Potential ecosystems (affected) and selected for restoration include: Zapal Bajo del Latal, Zapal La Lucha, Caño San Matias, Zapal La Cienguita, Zapal Madre Vieja. • 75 hectares rehabilitated from the tributary system of the San Jorge River along Santiago and the Canoas streams). The representative ecosystems of this sector are the Cuenca or Costanera Marshes, Las Flores, Florida, although we also find small micro-basins such as streams and creeks like La Hicotea, Los Emilianitos, Aguasclaras, Aguasprietas, Mabobo, La Pita. 75 hectares rehabilitated from the tributary system of the San Benito Abad wetlands. Las Delicias and Pasifueres canals are identified as the main ecosystems and water regulators of the area. Potential (affected) sites selected for restoration include: Zapal Doña Polita, Caño Pasifueres, Zapal Los Beltrán, Zapal Boronbolo and Zapal Los Chavez.
Outcome 3: Introduction of climate change-resilient agroecological practices and building designs helps local communities to reduce their vulnerability to the impacts of climate change. | 1. Number of local agroecological initiatives that are resilient to climate change adopted by the communities (disaggregated by gender) in the target area of the project. |  In the Ayapel area the following is in progress: a) nine trials using gardens built on stilts (known locally as “trojas”) that cover 0.86 ha and benefit 178 families.  In the San Marcos and San Benito area, the following has been developed: a) productive farmyards with 12 CBOs; and b) 80 organic gardens on river flats, covering 20 ha. | 7 productive initiatives benefit: i) 23 adapted community gardens benefit 433 families. The community gardens are contributing to increase the resilience of families, ensuring family feeding and generating surpluses that allow them to sustain their crops. ii) 1,987 (3,901 women and 4,411 men) families have family gardens adapted to the conditions of drought and flood. The orchards have diversified products ensuring that families can access a healthy diet, improving the health and nutrition conditions in the families. The number of families benefited by municipality is as follows: Ayapel, 802 families, San Benito, 628 and San Marcos, 502. iii) 1,217 (included in the 1,987 of the gardens) families established organic crops with the following varieties: corn 2,214 ha, beans 295,2, ha, pigeonpea 20 ha, plantain, cassava 78,62. On average, each family cultivated 2 ha. 6,922 men and 3,165 women. iv) 2,761 hectares of native rice resistant to local climatic conditions and mercury pollution benefit 1,217 families (6,922 men and 3,165 women). v) Three rice mills for processing of the harvest. These infrastructures allow families to store rice for periods of extreme weather. This activity benefits 601 families and 3,005 people (1,382 women and 1,623 men). vi) A fish pond that benefits 48 families, (240 people, 110 women and 130 men) With this fish pond, fish production is guaranteed during periods of drought, and it helps mitigate pollution. vii) 120 women participate in the actions for the production of artisanal fibers. The production of handmade fibers is linked to the restoration of wetlands with native species that contribute to the stabilization of slopes. | At the end of the project, at least seven (7) local agroecological initiatives have been implemented in the target municipalities, as follows: • Twenty (20) orchards have been built on stilts for the cultivation of vegetables and tubers (for example, onions, lettuce, yams, squash and tomatoes), which cover two (2) hectares in the municipalities of the project and benefit 415 families (996 women and 1,079 men). • One thousand three hundred and thirty three (1,333) family gardens adapted to situations of drought and flood that benefit an equal number of families (3,370 are women and 3,295 are men). For the cultivation of eggplant, tomato, sweet pepper, kidney beans, squash, green onions, cucumber, coriander and medicinal plants. • 1,217 families establish organic crops with the following varieties: corn 1,007 ha, beans 108,8 ha, pigeonpea 20 ha, plantain 14,52 ha, cassava 20,17 ha. Benefiting 6,922 men and 3,165 women • 729.3 hectares of native rice resistant to local climatic conditions and mercury contamination benefit 1,217 families (6,922 men and 3,165 women). • Three rice mills for processing of the harvest, installed to store rice for periods of extreme weather. Benefiting 1423 families (3272 women and 3843 men). • A fish pond that benefits 48 families (110 women and 130 men) for the production of fish during periods of drought and mitigation of mercury contamination in fish. • A natural fiber-based handicraft production program that benefits 120 women of the three municipalities.
| 2. Number of adaptive structural architectural measures undertaken in the target area to reduce vulnerability to flooding. |  10 educational units built on stilts in the communities of Cecilia (3), El Totumo (4), El Cuchillo (1), and La Coquera (2) (Ayapel municipality) with the support of the Education Ministry.  Proposal to build 8 classrooms in the municipality of Ayapel.  There are no adaptive housing units in the municipalities of Ayapel, San Marcos, and San Benito Abad; however, some designs have been developed. | No changes are reported. 501 houses and 14 educational centers have been adapted with rainwater capure and storage facilities: 3 Childcare centers in the Torno community 3 Childcare centers in the basin-based community 3 Childcare centers in the Pital community 1 Childcare centers in the Flores community 1 School in the Tosnovan community 1 School in the Pasifueres community 1 School in the Pital community 1 School in the Chinchorro community The adjustments are aimed at providing families and children with water in times of drought. 209 (109 girls and 100 boys) 2,505 people benefit from the structural measures in their houses for the supply of drinking water in periods of drought (1,348 women and 1,157 men). Water storage structures have the appropriate risk management measures against flooding. These infrastructures are built above flooding levels. As a result of the community consultations about a house prototype that can be adapted to the climate conditions of the Mojana region, the project has presented a model of vernacular house adapted to climate conditions (temperature increase and flooding). The project will carry out dissemination and coordination work so that the house model may be undertaken by the national government and incorporated into the housing program of the government for population highly vulnerable to the climate conditions of the region. Additionally, a community center adapted to the climate conditions of the region was built, which benefits 150 families. | At the end of the project, structural measures have been implemented in at least seventy schools and homes, as follows: • Fourteen (14) educational centers have adapted structural measures. The adjustments are aimed at providing children with water in times of drought. Benefiting (109 girls and 100 boys) • Five hundred and one (501) homes have structural measures for adaptation (rainwater collection systems for drought seasons). Benefiting 1,348 women and 1,157 men. The structures for water storage have in place risk management measures against floods, and are built above flood levels. • Eleven (11) constructed communal buildings and four (4) models of vernacular housing adapted to cope with flood risks.
| 3.Number of Ha established with agro-silvopastoral systems in the target area of the project. |  50.7 ha established in agro-silvopastoral systems for three users in the rural area of the Ayapel municipality.  Zero (0) ha in the municipalities of San Marcos and San Benito Abad. | 162 ha of agrosylvopastoral systems have been established that benefit 93 small farmers. In Ayapel, 70 ha of 46 producers and in San Marcos 92 ha of 47 producers. For the next period, 47 livestock producers with an availability of 89 hectares have been identified. . | An additional 250 have been established in agro-sylvopastoral systems in the rural area of ​​the project's target area (100 ha in the municipality of Ayapel, 75 ha in the municipality of San Marcos, and 75 ha in the municipality of San Benito Abad).
Outcome 4: Relevant institutional and social structures strengthened for mainstreaming climate risk management and adaptation measures into planning and decision-making processes. | 1. Number of public agencies and CBOs that jointly participate in climate risk management and adaptation planning. |  There are 7 active civil organizations (AGROPISCA, ASOPECE, ASODEPACA, ASOPESIN, ASOAGROLLERAS, ASONEGRITOS, and ASOPESPAL) in the Ayapel municipality; however, they currently do not address the issue of adaptation to climate change.  There are 8 active civil organizations (FIDES, AGROMOJANA, COOAGRISANMARCOS, Comité de Mujeres, COPEVI, ACUASUCRE, Asociación de Pescadores, and SERVIPESCA) in the San Marcos municipality; however, they currently do not address the issue of adaptation to climate change.  There are 38 civil organizations in the San Benito Abad municipality; however, it is unknown how many are active.  There are 9 public agencies (MADS, IDEAM, CVS, CORPONOJANA, departmental governments of Córdoba and Sucre, and mayoral offices of Ayapel, San Marcos, and San Benito Abad) with knowledge about climate change issues in the target area, but that currently do not adequately articulate with the CBOs. | Indicator completed in the previous report. 42 communities of the three municipalities of San Marcos, San Benito Abad and Ayapel; 38 OBS, including three (3) women's organizations (Asociación de Cuiva, Asofasan and Asocantor) and community leaders (155 rural promoters for adaptation to climate change) and 21 institutions from the 3 municipalities, are strengthened in the implementation of adaptation and risk management in the face of the effects of climate change, on issues related to good agroecological practices, rescue of native seeds adapted to the Mojana region, ecological restoration of wetlands, early warning systems and adaptive infrastructure and good livestock practices. Community Action Board of the Seheve Community 2. Community Action Board of Rondón 3. Community Action Board of Alfonso Lopez 4. Community Action Board of Pañuelo 5. Community Action Board of Alemania 6. Community Action Board of Guartinaja 7. Community Action Board of El Cuchillo 8. Community Action Board of Guaduas Community Action Board of Corea Community Action Board of Barcelona Community Action Board of Mata de Caña 12. Community Action Board of Las Chispas 13. Community Action Board of La Plaza 14. Community Action Board of Las Pozas 15. Community Action Board of Parcelas de Santa Fe 16. Community Action Board of Parcelas de Venezuela Community Action Board of Parcelas de Las Delicias Community Action Board of El Cauchal Community Action Board of Caño Caimán Community Action Board of La Costera Community Action Board of Cuenca Community Action Board of El Torno Association of Fishermen and Agricultural Producers of Bocas de Seheve ASOPESAGRO Fishing and Livestock Productive Association of Cecilia ASOPROPEGACE Association of Farmers, Fishermen and Restorers of the Corregimiento de Sincelejito, Ayapel ECOSINCELEJITO 26. Association of Men and Women Farmers of Los Negritos 27. Association of Producers for the Development of Alfonso Lopez Association of women farmers and swine producers of the Cuchillo-Ayapel AMAPOC Association of producers and farmers of San Matías- ASOMATIAS- Association of Farmers and Fishermen of Las Chispas ASOAGRIPESCHIS Vereda El Chinchorro Farmers Association Association of Farmers, Livestock Producers, Fish Farmers and Environmentalists of Pasifueres ASPASFU Agricultural Association of Indigenous Peoples, Afro-descendants, Farmers and Displaced Persons of Tosnovan ASOAGROCAMTOS 34. Association of Women of Cuiva Association of Farmers and Fishermen of La Costera AGRIPEC. Association of Fishermen, Farmers and Protectors of Natural Resources of El Pital APAPI Agricultural Association of Indigenous Peoples, Afro-descendants, Farmers and Displaced Persons of las Flores, San Marcos, Sucre ASOAGROCAMLASFLORES 38. Association of Women, Women Farmers and Fishermen - Farmers of the El Torno District ASOCAMTOR 39. Association of Farmers of Viloria, La Mancha, Venecia Tres and Mancha Tres 40. Association of Agroecological Producers. Agrosolidaria 41. Association of Agricultural and Fish Farming Families of San Jorge 42. Association of Campanito 21 local and regional institutions strengthen their capacities for climate risk management and promote adaptation measures in the face of climate variability and climate change. This strengthening has been carried out through the completion of the diploma course "Tools for adaptation to climate change and risk management" carried out by the Pontificia Universidad Bolivariana in Monteria, and a diploma course in adaptation actions to climate change aimed at the productive component, offered by the University of Sucre in San Marcos. 6 mayor’s offices (San Marcos, San Benito Abad, Ayapel, Guaranda, Majagual and Caimito) 2 Governor’s offices (Cordoba and Sucre) 2 CARS, (Corpomojana and CVS) Water Plan of Córdoba, Social Pastoral University of Cordoba University of Sucre Government of Sucre Alexander Von Humboldt Institute Universidad Pontificia Bolivariana |  25 CBOs, including a women association of craft weavers, and community leaders of the 3 municipalities (10 in Ayapel, 12 in San Marcos, and 3 in San Benito Abad, of which at least 3 are women) are strengthened and promoting skills for adaptation in their communities and which are articulated with the local, regional, and national public agencies.
| 2. Number of local and regional plans that mainstream adaptation to climate change considerations. |  Regional Environmental Corporations – CARs (CVS and CORPOMOJANA) have Regional Environmental Management Plans (PGARs) and 4-Year Action Plans (PACs) that consider climate change issues but do not include strategies to reduce vulnerability or adaptation considerations.  The Departmental Development Plans (PDDs) for Córdoba and Sucre include strategic guidelines for risk management and disaster prevention, but do not make reference to climate change and adaptation.  The three municipalities have Land Zoning Plans (POTs) and Municipal Development Plans (PDMs) that include strategic guidelines for risk management and disaster prevention, but only include a general mention of climate change and its effects (floods, landslides, avalanches). | Climate change considerations have been incorporated into 11 plans: (3) Municipal development plans for Ayapel, San Marcos, and San Benito Abad. (3) Land use plans for Ayapel, San Marcos, and San Benito Abad. (1) Corpomojana action plan. (1) Departmental climate change plan for CVS. (2) Departmental development plans (1) Risk Management Plan, San Benito |  Twelve (12) plans that incorporate considerations for adaptation to climate change: a) two PGARs for the CARs; b) two PACs the CARs; c) two PDDs for departmental governments; d) three municipal POTs; and e) three municipal PDMs
| 3. Number of government staff (local, regional, and national) and community members who effectively apply new skills to climate change risk reduction (disaggregated by gender). |  Basic emergency management training for flood risks has been conducted for the communities of Cecilia, Sincelejito, and Sejeve (Ayapel municipality), Viloria (San Marcos municipality), and Las Chispas (San Benito Abad municipality) with support from CARITAS – Germany, the diocese of Sucre and Montelíbano (Sucre) and the National Secretariat of Pastoral Social.  The community has basic knowledge about ecological rehabilitation and houses or other constructions on stilts, but has not connected this with reduced climatic risk and adaptation.  The community has medium-level knowledge about traditional and alternative systems for agricultural production.  The CARs (CVS and CORPOMOJANA) have basic knowledge about climatic change and adaptation.  CARs have a high level of knowledge about: a) ecological rehabilitation and b) alternative and traditional agricultural systems. | 64% of the population of the 42 communities in the area of ​​influence of the project, 33,084 people of whom 59% are women, have improved their knowledge in adaptation to climate change and variability. 13 training and education programs have been developed to strengthen knowledge in the following topics: adapted agroecology, adapted self-construction, agrosylvopastoril systems, ecological restoration, water recovery, nursery, organization and social cohesion, fish farming, accounting and administration, management of warning systems, hydroclimatological monitoring, among others. To carry out this training, different techniques and tools have been used, such as workshops, meetings, method demonstration, field trips and leaflets, murals, film forums, diploma courses, among others. |  At least 50% of the population in 11 communities (including approximately 3,170 women) in the project area, the three mayoral offices, the CLOPADs, the two CARs, and the two CREPADs (Córdoba and Sucre) have adequate knowledge about measures of adaptation to climate change that are proposed by the project, including interpretation and use of hydroclimatological information, ecological rehabilitation and wetlands conservation, agroecological practices and adaptive architecture; and their roles in adapting to the impacts of climate change.
| 4. Lessons learned from pilot activities in La Mojana disseminated through the National Climate Change Portal (NCCP) and the Adaptation Learning Mechanism (ALM). |  Zero (0) | 6 lessons learned were socialized with officials from different projects of the Ministry of Environment and Sustainable Development, and 23 officials participated in this socialization. The socialized lessons learned were about: intervention strategy, early warning systems, rehabilitation of wetlands, adapted production systems, adaptive architecture and community and institutional strengthening. They were able to share their experiences and make recommendations for the new MADS projects. Participation in the forum "The National Environmental System and Disaster Risk Management in the Regions", organized by the Ministry of Environment and Sustainable Development and the National Disaster Risk Management Unit, wher the valuable project experience in Disaster Risk Management was shared with the audience from an environmental perspective, contributing to the construction of sustainable and resilient territories in the face of disaster risks. The experience of the project was shared, along with other initiatives carried out by the National Adaptation Fund. In that exchange, it was agreed to coordinate closely with The Nature Conservancy, who will be carrying out adaptation interventions based on ecosystems in the La Mojana region, and who will take advantage of the lessons learned from the project around this issue during their field work. Good practices and lessons learned have been captured in the following technical reports, documents, videos and articles: Agro-meteorological Brochures for the Mojana Region workshop reports on community risk mapping and early warning system Design document of the 1st phase of wetland restoration Good practices report on: water management and rice production practices for managing mercury contamination risk Strategic plan for the adaptive management of agriculture production activities Training plan and method for rural advocates (community contacts) Implementation report on adaptation measures: for food security (Pastoral Social Montelibano) and for water supply (Fundación SAHED) Guidelines for Departmental Zoning Plans Guide to incorporating climate change issues into Land Zoning Plans Methodological guidance notes for adaptation in: • Forest restoration • Agricultural productive activities • Home gardens • Seed banks • Agro-silvo-pastoral measures • water capture and storage. Handbook about the application of Land-use Plans Handbook /Manual on self-construction of adapted houses Handbook on the functioning of Rice mills Calendar of good practices for climate change adaptation Poster about good practices to mitigate mercury contamination Agenda including vulnerability analysis handed to local promoters and authorities Calendar ‘Life in an amphibian territory’ Methodology for the establishment of an early warning system Methodology for the recovery of water dynamics Videos and articles: https://www.youtube.com/watch?v=K4G-223BM9g&feature=youtu.be https://twitter.com/infopresidencia/status/573988964912099328/photo/1 http://www.elmeridianodesucre.com.co/region/item/49777-buscan-comunidades-adaptables http://elmeridianodecordoba.com.co/region/municipios/item/72060-buscan-comunidades-adaptables https://www.youtube.com/watch?v=Lyg0eyok62M http://www.bluradio.com/72375/la-mojana-region-que-dia-dia-afronta-problematica-ambiental http://www.bluradio.com/72506/con-exito-avanza-el-proyecto-de-adaptacion-al-cambio-climatico-en-la-mojana Currently these and other documentation is being organized and uploaded at the project page on the UNDP CC Adaptation portal: http://www.undp-alm.org/projects/af-colombia http://www.co.undp.org/content/colombia/es/home/ourwork/environmentandenergy/successstories/huertas-familiares-contra-el-cambio-climatico.html http://elmeridiano.co/restauran-30-hectareas-de-bosques/49703 https://youtu.be/K4G-223BM9g http://elmeridiano.co/restauran-30-hectareas-de-bosques/49703 La memoria ambiental de La Mojana http://elmeridiano.co/modelo/50955 http://www.co.undp.org/content/colombia/es/home/operations/projects/environment_and_energy/reduccion-del-riesgo-y-de-la-vulnerabilidad-frente-al-cambio-cli.html |  At least ten (10) lessons learned for each project component, including one gender-related lesson learned, are disseminated through the NCCP and the ALM.
Note on G20: Montse: Hay manera de contalbilizarlo cuantas lecciones van por componente? Por lo que veo esto ya esta por cumplirse

## Lessons Learned
QUALITATIVE MEASURES and LESSONS LEARNED
Please complete the following section every reporting period
Implementation and Adaptive Management | Response
What implementation issues/ lessons, positive or negative, affected the project progress? | As part of the learning process in the implementation of the project, it was decided to locate the project management in an operational office in the municipality of San Marcos in the facilities of Corpomojana to generate greater synergy and ownership of the results of the project. Through the training processes, the institutional approach, especially with the governor’s offices, has improved participation and the incorporation of climate change issues into the agendas of local governments. This has been evidenced through requests for support that local authorities, such as CVS and the Gobernment of Sucre have requested from the project, to support projects that incorporate elements of climate change. Although progress has been made in adapting to periods of drought, this continues to be a challenge for medium-scale production issues, given that communities give greater importance to flood conditions than drought conditions. For this, a wide dissemination scheme is being implemented for the appropriation of crop techniques for dry seasons.
Were there any delays in implementation? If so, include any causes of delays. What measures have been taken to reduce delays? | The delays in this period were presented in components 1, 2 and 3. In component one, due to the difficulty of recruiting specialized professionals to operate the forecast center with availability to move to the remote areas of the project. To remedy this delay, approaches are being implemented with universities and networks of local professionals, in order to be able to complete the group of professionals that will operate in the climatological services center. In component 2, the delays are due to the lack of background and technical studies that would allow the design of rehabilitation and restoration strategies. In component 3, in product 3.2, in the topic of adaptive architecture, due to the lack of bidders for the construction of adapted community centers. Alternatives to expedite contracting are being analyzed with the UNDP procurement center and project management.
Describe any changes undertaken to improve results on the ground or any changes made to project outputs (i.e. changes to project design) | In response to the recommendations of the midterm evaluation and in accordance with the current conditions of the territory, adjustments were made to the goals of component 3, product 3.1 and product 3.2. In component 2, goal adjustments were not made, but adjustments were made to the approach and intervention areas. These modifications were approved by the Kyoto Protocol Board in December 2017
How have gender considerations been taken into consideration during the reporting period? What have been the lessons learned as a consequence of inclusion of such considerations on project performance or impacts? | The project continues to strengthen the work with women. In this sense, they have promoted their leadership in marketing initiatives for surplus production systems, as well as their participation in the decision-making spaces of the communities. In the actions of ecological restoration, women are leading the processes of production of plant material in nurseries. Through these activities, women feel that they are being recognized in their communities as participants in their development.
Please complete the following section at mid-term and project completion
Lessons for Adaptation | Response
Climate Resilience Measures
What have been the lessons learned, both positive and negative, in implementing climate adaptation measures that would be relevant to the design and implementation of future projects/programmes for enhanced resilience to climate change? | The implementation of the participatory rural diagnosis and the vulnerability analysis allowed the project to be adjusted and to redefine some adaptation measures to respond to community needs in order to reduce the vulnerability to climate phenomena. Through these community consultations, it was possible to identify that the drought phenomenon affects access to water for human consumption, food production and livestock activities. That is why the project strengthened actions aimed at responding to these needs. It is important to consider post-harvest management (including budgets) in the implementation of adaptation measures associated with livelihoods, so that families can develop a culture of food storage for critical climate periods. Adaptation measures on ecosystem restoration should be designed to restore biodiversity and ecosystem services; it generates commitment on the part of communities to take care of said services. Similarly, actions to raise awareness of water sources should be carried out, especially in communities with high water deficiency rates during periods of drought in order to reduce climate vulnerabilities. It is necessary to consider the time and budget needed in order to design adaptation measures to respond to the conditions of the context. In the case of La Mojana, it is important to take into account in the project desing the difficult access to the community which is conditioned by weather seasons. The difficult access to the area increases the costs of implementation actions and requires time for community agreements. Integrating young people and children into the process of raising awareness and training on climate change adaptation enables the recovery of ancestral knowledge, generates intergenerational dialogues and promotes understanding of climate change problems in their territories.
What is the potential for the climate resilience measures undertaken by the project/programme to be replicated and scaled up both within and outside the project area? | Structural measures for rain water harvest are highly replicable since their construction is simple; costs are relatively low compared to the benefits, especially because they solve the problem of safe water supply. Community measures to monitor water levels in creeks are a highly replicable measure because communities can independently monitor possible floods or droughts. Operating rice mills and rice grain dryers guarantees managing the post- harvest and conserving the product. This measure ensures food safety to families during severe climate seasons. Training actions carried out in component 4: the good acceptance among local stakeholders allows defining the ongoing training strategy carried out in partnership with local universities. The training process addresses issues about the project and other issues of community interest to strengthen and facilitate the appropriation processes for the adaptation to climate change.
Concrete Adaptation Interventions
What have been the lessons learned, both positive and negative, in implementing concrete adaptation interventions that would be relevant to the design and implementation of future projects/programmes implementing concrete adaptation interventions? | The installation of limnimetric and automatic stations in the region has allowed the collection, processing and management of hydro climatological information at the regional and local levels. To March 2017, there have been activities carried out in order to articulate into the national hydro climatological network. Communities are collecting daily information at 13 points with the limnimetric stations and through the SAT committees. Organizational processes are key for the sustainability of actions and for the improvement of the impact on adaptation measures; however, some actions, such as the vegetable gardens, are more successful if implemented in a family frame, which is due to, in most cases, it is the women who are in charge of the maintenance and care of the vegetable gardens. Family vegetable gardens make it easier for women to include this activity as part of their household chores. Community-based vegetable gardens promote associativity and contribute to a better management of land use, but it requires women to move from their homes to the place where the vegetable gardens are located; this increases the time women spend on these activities, and thus their working hours. Adaptive architecture adaptation measures should consider all climatological aspects of the region. The project only considered aspects related to floods, and for the region of La Mojana it is important consider the high temperatures of the area, and the architecture program could provide a collective process in order to preserve biodiversity and to manage water resources. As families become aware that they can have their homes adapted to weather conditions and that they can build them with local materials, there can be a high degree of commitment to take care of forests and water sources.
What is the potential for the concrete adaptation interventions undertaken by the project/programme to be replicated and scaled up both within and outside the project area? | Family vegetable gardens are an effective adaptation measure against climatic variability and climate change which perfectly fits into the socio-economic conditions of La Mojana families. The project has promoted agrobiodiversity as a measure to meet the nutritional needs of the low-income population and of those who do not have access to large tracts of land to develop their crops. This measure provides short-term results and ownership from communities; thus, it is a strategy that guarantees livelihoods and increases the resilience of the populations exposed to climate risks. On the other hand, since women manage family vegetable gardens, it recognizes their contribution in the improvement of families’ livelihoods. The implementation of rainwater harvesting measures is an easy-to-install and easy-to-maintain action; the cost-benefit is efficient and guarantees the quality of water for human consumption. In addition to this, this adaptation measure contributes to decrease the pressure in the aquifers and promotes their preservation. At the same time, it generates awareness of the importance of taking care of water resources. Community nursery gardens for the production of plant material promote the recovery of native species at risk, contribute to the preservation of biodiversity, and encourage collective work and appropriation of the territory. The recovery of native seeds is a low-cost measure, promotes the recovery of ancestral knowledge, guarantees food security and food quality in the face of severe weather events.
Community/National Impact
What would you consider to be the most successful aspects for the target communities? | The project reoriented the activity to provide the community with mechanisms for water catchment and basic treatment, through tanks (capacity of 1000 liters), and activated carbon and sand filters. This measure, that undoubtedly affects the quality of life of the population, reduces vulnerability and generates ownership of the project from the community. It also has a positive impact on the living conditions of women and children, who according to the culture in La Mojana, are in charge of supplying water for the family. This measure is preventing women from having to travel various hours to load 20 liters of water per day. The project has developed activities to foster social and economic inclusion of the beneficiary population. This is demonstrated through activities in component 3, since they contribute to reduce vulnerability to Climate Change. Management and approach with the community and teaching the importance of restoring ecosystems. To this end, the technical team has delivered workshops, and has created community-managed plant banks, which will be essential for the wetland rehabilitation process.
What measures are/have been put in place to ensure sustainability of the project/program results? | The project has succeeded in including and articulating climate change issues within development plans at the regional, departmental and local levels, contributing to the strengthening of issue-related institutions and providing continuity to the activities towards the management of climate change. Currently in Córdoba, the CVS - Regional Environmental Entity (in its 2016-2019 plan, "Cordoba Hídrica y Biodiversa") has the program "Risk Management, Adaptation and Mitigation against Climate Change" in order to reduce the vulnerability of the territory. The program includes the project to start the implementation of the Departmental Plan for Adaptation to Climate Change. This action plan incorporates the State Inter-agency Panel on Climate Change (MICC). This group has been meeting periodically with a portfolio of projects aimed at complying with climate change measures. Corpomojana has been implementing initiatives in the municipalities under its influence in order to apply the policies for Adaptation to Climate Change, revising the Territorial Plans of Land Use in each municipality; it intends to verify the inclusion of the Adaptation to Climate Change policies in these planning instruments. At the community level, there has been specialized training on climate variability and change for 115 rural promoters to adapt to climate change. Then, they replicate their knowledge with families in their communities, thus ensuring the implementation of the adaptation measures. Strengthening base-line organizations and incorporating climate issues into their work agendas ensures that communities’ processes continue to implement adaptation measures, as these partnerships are strengthening their capacity in the management of economic resources to continue the implementation.
What measures are being/could have been put in place to improve project/program results? | Training for food processing, establishing food banks that can be preserved for times of both drought and flood. Water management for agricultural activities. This measure would contribute to reduce the impacts of drought on food production for self-consumption. Promotion of ecotourism as a measure that promotes the care of the environment and the conservation of biodiversity, through the exchange of local experiences and knowledge.
Knowledge Management
How has existing information/data/knowledge been used to inform project development and implementation? What kinds of information/data/knowledge were used? | The project has developed analyzes and studies that have helped to define and adjust the intervention strategy, these analyzes are a participatory rural diagnosis, which aided to improve the project baseline. This diagnosis confirmed that droughts are a phenomenon that has a high negative impact on the livelihoods in La Mojana. Vulnerability analysis. This analysis aided to determine the climatic phenomena that affected each community the most, and thus the appropriate adaptation measures to increase the resilience in each of the communities. The hydrodynamic modeling, provided by the National Adaptation Fund, has allowed the technical improvement of adaptation measures, for example, for adapted housing, the flood risk scenarios were used to determine the flood levels. Likewise, this study helped define and select, in a more precise way, the creeks in which the works for the control of floods must be done. The eco-regional analysis helped us determine the areas where the restoration actions will be carried out.
If learning objectives have been established, have they been met? Please describe. | The design of the technical data sheets for each of the adaptation measures has allowed structuring the methodologies for the implementation of each of the adaptation measures. These sheets also have information on the costs and profitability of each one of the measures. The climate variability analysis has provided a better knowledge on the behavior of the climate in the region. This information has been instrumental for the education of families on the actions that must develop in their communities to reduce vulnerability.
Describe any difficulties there have been in accessing or retrieving existing information (data or knowledge) that is relevant to the project. Please provide suggestions for improving access to the relevant data. | The greatest difficulty was to interpret the information generated by the hydrodynamic modeling, since the technical complexity of this tool requires experts with the necessary knowledge to apply the information in each of the measures. The project overcame this difficulty by hiring an expert advisor in hydronimetric modeling who performs the interpretation and analysis of this information to apply it in a practical way in each one of the measures. Another difficulty is the transfer of techno-scientific information to the inhabitants, due to their low level of education. Although communities have empirical knowledge and are able to recognize environmental cues from the impact of climate change on their day-to-day activities, the technicalities of the information sometimes limit their understanding, especially the information that can be applied to agricultural activities. Therefore, the project has been using teaching methodologies, theoretical-practical learnings and the exchange of experiences as a methodology for knowledge transfer.
Has the identification of learning objectives contributed to the outcomes of the project? In what ways have they contributed? | The technical and territory information generated by the project has contributed to the formulation of La Mojana action plan, which is led by the National Adaptation Fund. Similarly, the information and lessons learned from the project have served as the basis for the formulation of an adaptation project to be presented to the Green Climate Fund, which is intended to benefit the 11 municipalities of La Mojana.

## Units for Indicators
Fund Outcome Indicator Units
1. Generation of relevant data, Stakeholders, and Timeliness 2.1. Include both qualitative and quantitative measures of capacity level within targeted institutions 2.2. Number (men and women and other vulnerable groups) 3.1. Use scale from 1 to 5: 5: Fully aware 4: Mostly aware 3: Partially aware 2: Partially not aware 1: Aware of neither predicted adverse impacts of climate change nor of appropriate responses 3.2. Use scale from 1 to 5: 5: All 4: Almost all 3: Half 2: Some 1: None 4.1. Summarize in an overall scale (1-5): 5: Highly responsive (All defined elements ) 4: Mostly responsive (Most defined elements) 3: Moderately responsive (Some defined elements) 2: Partially responsive (Lacks most elements) 1: Non responsive (Lacks all elements ) 4.2. Summarize in an overall scale (1-5): 5: Fully improved 4: Mostly Improved 3: Moderately improved 2: Somewhat improved 1: Not improved 5. Depends on the targeted natural asset: Biological (species): measure through changes in population numbers (dynamics, structure, etc.) Land: measure changes in hectares. Baseline data will be necessary to estimate the change. Supporting indicators baseline and target (as well as contextual information) are needed such as the following: Farmers adopting recommended technologies, Ha. of land improved, Average deforestation rate Etc. Use scale from 1 to 5. 5: Very effective (All elements are present) 4: Effective (Most elements are present) 3: Moderately effective (Some elements are present) 2: Partially effective (Most elements are not present) 1: Ineffective (No elements are present) 6.1. Summarize in an overall scale (1-5): 5: Very high improvement 4: High improvement 3: Moderate improvement 2: Limited improvement 1: No improvement 6.2. Household income by source of livelihood in project area (USD) prior and post project intervention 7. Summarize in an overall scale (1-5). 5: All (Fully integrated) 4: Most 3: Some 2: Most not integrated 1: None
Fund Output Indicator Units
1.1. Number, sector(s) and level(s) of projects or interventions in separate fields of monitoring plan 1.2. Number 2.1.1. Number of staff (male/female) of targeted institutions: a. Obtain baseline information: total number of staff from targeted institutions b. Define target 2.1.2. Number of staff (male/female) of targeted institutions: a. Obtain baseline information: total number of staff from targeted institutions b. Define target: needs to be defined by project proponents 2.2.1. Quantitative: Percentage (includes women – and other vulnerable groups – and men). Qualitative: Adequacy: include direct analysis of major areas; adequacy/effectiveness of systems or analysis of perceptions of populations and institutions. 2.2.2. Number (broken down by gender and, if possible, by vulnerable groups defined in the area of intervention) of people 3.1. Number and type (in separate columns) at local level. 3.2. Number 4.1. Number and type 4. 2. Number and type (entered in separate columns) 5. Number of interventions by type of natural asset and intervention 6.1. Number and type (in separate columns of monitoring plan) 6.2. Income sources per household; description of income source and number of households. 7.1. Number/Sector 7.2. Number; Effectiveness (see previous indicator) through enforcement level.

## Results Tracker
Results Tracker for Adaptation Fund (AF) Projects
Goal: Assist developing-country Parties to the Kyoto Protocol that are particularly vulnerable to the adverse effects of climate change in meeting the costs of concrete adaptation projects and programmes in order to implement climate-resilient measures. Impact: Increased resiliency at the community, national, and regional levels to climate variability and change.
Important: Please read the following guidance document (also posted on the Adaptation Fund website) before entering your data
Link: http://www.adaptation-fund.org/sites/default/files/Results%20Framework%20and%20Baseline%20Guidance%20final.pdf
Adaptation Fund Strategic Results Framework
Project ID | 83662-68537
Implementing Entity | UNDP |  | Output 2.2: Targeted population groups covered by adequate risk reduction systems //Grupos de población destinatarios cubiertos por los sistemas de reducción de riesgos adecuadas
Type of implementing entity
Country | Colombia
Region | Latin America and Caribbean
Sector | Multi-sector
0
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Target performance at completion
Impact: Increased resiliency at the community, national, and regional levels to climate variability and change | Core Indicator: No. of beneficiaries |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project
|  | Total | 211857 | 54000 | 157857 | Total | 18297 | 7319 | 10978 | Total | 17111 | 15555 | 1556 | Total | 36393 | 33084 | 3309
|  | % of female beneficiaries | 55% | 55% | 55% | % of female beneficiaries | 62% | 62% | 62% | % of female beneficiaries | 50% | 50% | 50% | % of female beneficiaries | 58% | 58% | 16%
|  | % of Youth beneficiaries |  |  |  | % of Youth beneficiaries | 10% | 10% | 10% | % of Youth beneficiaries | 15% | 15% | 15% | % of Youth beneficiaries | 16% | 16%
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 1: Reduced exposure to climate-related hazards and threats | Indicator 1: Relevant threat and hazard information generated and disseminated to stakeholders on a timely basis | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness
|  | Total | 0 | Inland flooding | 1: Ineffective | Total | 7319 | Inland flooding | 3: Moderately effective | Total | 15555 | Inland flooding | 2: Partially effective | Total | 33084 | Drought | 4: Effective
|  | % of female targeted | 0% |  |  | % of female targeted | 62% |  |  | % of female targeted | 50% |  |  | % of female targeted | 58%
Output 1.1 Risk and vulnerability assessments conducted and updated | Indicator 1.1: No. of projects/programmes that conduct and update risk and vulnerability assessments | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
Output 1.2 Targeted population groups covered by adequate risk reduction systems | Core Indicator 1.2: No. of Early Warning Systems | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard | Inland flooding | No. of adopted Early Warning Systems | Category targeted | Hazard
|  | 0 | 3: Dissemination and communication | Geographical coverage | Local | 1 | 3: Dissemination and communication | Geographical coverage | Local | 1 | 3: Dissemination and communication | Geographical coverage | Local | 27 | 2: Monitoring and warning service | Geographical coverage | Local
|  |  |  | Number of municipalities | 3 |  |  | Number of municipalities | 3 |  |  | Number of municipalities | 3 |  |  | Number of municipalities | 3
|  | No. of adopted Early Warning Systems | Category targeted | Hazard | Inland flooding | No. of adopted Early Warning Systems | Category targeted | Hazard | Inland flooding | No. of adopted Early Warning Systems | Category targeted | Hazard | Inland flooding | No. of adopted Early Warning Systems | Category targeted | Hazard | Inland flooding
|  | 0 | 2: Monitoring and warning service | Geographical coverage | Local | 1 | 2: Monitoring and warning service | Geographical coverage | Local | 1 | 2: Monitoring and warning service | Geographical coverage | Local | 27 | 3: Dissemination and communication | Geographical coverage | Local
|  |  |  | Number of municipalities | 3 |  |  | Number of municipalities | 3 |  |  | Number of municipalities | 3 |  |  | Number of municipalities | 3
|  | No. of adopted Early Warning Systems | Category targeted | Hazard |  |  | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage |  | 27 | 1: Risk knowledge | Geographical coverage | Local
|  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities | 3
|  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage |  | 7 |  | Geographical coverage
|  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 2: Strengthened institutional capacity to reduce risks associated with climate-induced socioeconomic and environmental losses | Indicator 2: Capacity of staff to respond to, and mitigate impacts of, climate-related events from targeted institutions increased | Number of staff targeted |  | Sector | Capacity level | Number of staff targeted |  | Sector | Capacity level | Number of staff targeted |  | Sector | Capacity level | Number of staff targeted |  | Sector | Capacity level
|  | Total | 0 | Disaster risk reduction | 1: No capacity | Total | 33 | Multi-sector | 3: Medium capacity | Total | 33 | Multi-sector | 3: Medium capacity | Total | 57 | Disaster risk reduction | 3: Medium capacity
|  | % of female targeted | 0% |  |  | % of female targeted | 39% |  |  | % of female targeted | 39% |  |  | % of female targeted | 35%
Output 2.1 Strengthened capacity of national and sub-national centres and networks to respond rapidly to extreme weather events | Indicator 2.1.1: No. of staff trained to respond to, and mitigate impacts of, climate-related events | Total staff trained | % of female staff trained | Type |  | Total staff trained | % of female staff trained | Type |  | Total staff trained | % of female staff trained | Type |  | Total staff trained | % of female staff trained | Type
[14 empty] | 57 | 35% | Public
| Indicator 2.1.2: No. of targeted institutions with increased capacity to minimize exposure to climate variability risks | Type | Scale | Sector | Capacity level | Type | Scale | Sector | Capacity level | Type | Scale | Sector | Capacity level | Type | Scale | Sector | Capacity level
[14 empty] | Public | Regional | Disaster risk reduction | 3: Medium capacity
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 3: Strengthened awareness and owernship of adaptation and climate risk reduction processes | Indicator 3.1: Increase in application of appropriate adaptation responses | Percentage of targeted population applying adaptation measures |  | Sector |  | Percentage of targeted population applying adaptation measures |  | Sector |  | Percentage of targeted population applying adaptation measures |  | Sector |  | Percentage of targeted population applying adaptation measures |  | Sector
|  | 50% |  | Food security |  | 56% |  | Food security |  | 70% |  |  |  | 30 |  | Food security
Output 3: Targeted population groups participating in adaptation and risk reduction awareness activities | Indicator 3.1.1: Percentage in targeted population awareness of predicted adverse impacts of climate change, and of appropriate responses | No. of targeted beneficiaries | % of female participants targeted | Level of awareness |  | No. of targeted beneficiaries | % of female participants targeted | Level of awareness |  | No. of targeted beneficiaries | % of female participants targeted | Level of awareness |  | No. of targeted beneficiaries | % of female participants targeted | Level of awareness
|  | 0 | 0% | 3: Partially aware |  | 7319 | 6200% | 4: Mostly aware |  | 9125 | 50% | 4: Mostly aware |  | 13200 | 50% | 4: Mostly aware
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 4: Increased adaptive capacity within relevant development sector services and infrastructure assets | Indicator 4.1: Increased responsiveness of development sector services to evolving needs from changing and variable climate | Project/programme sector | Geographical scale | Response level |  | Project/programme sector | Geographical scale | Response level |  | Project/programme sector | Geographical scale | Response level |  | Project/programme sector | Geographical scale | Response level
|  | Disaster risk reduction | Local | 2: Partially responsive (Lacks most elements) |  | Disaster risk reduction | Local | 1: Non responsive (Lacks all elements ) |  | Disaster risk reduction | Regional |  |  | Disaster risk reduction | Regional | 3: Moderately responsive (Some defined elements)
| Core Indicator 4.2: Assets produced, developed, improved or strengthened | Sector | Targeted asset | Changes in asset (quantitative or qualitative) |  | Sector | Targeted asset | Changes in asset (quantitative or qualitative) |  | Sector | Targeted asset | Changes in asset (quantitative or qualitative) |  | Sector | Targeted asset | Changes in asset (quantitative or qualitative)
|  | Water management | 2: Physical asset (produced/improved/strengthened) | 2: Somewhat improved |  | Water management | 1: Health and Social Infrastructure (developed/improved) | 4: Mostly Improved |  | Water management | 1: Health and Social Infrastructure (developed/improved) | 4: Mostly Improved |  | Disaster risk reduction | 1: Health and Social Infrastructure (developed/improved) | 3: Moderately improved
|  | Food security | 2: Physical asset (produced/improved/strenghtened) | 2: Somewhat improved |  | Food security | 2: Physical asset (produced/improved/strenghtened) | 5: Fully improved |  | Food security | 1: Health and Social Infrastructure (developed/improved) | 4: Mostly Improved |  | Disaster risk reduction | 1: Health and Social Infrastructure (developed/improved) | 4: Mostly Improved
|  | Agriculture | 2: Physical asset (produced/improved/strengthened) | 1: Not improved |  | Agriculture | 2: Physical asset (produced/improved/strengthened) | 3: Moderately improved |  | Agriculture | 1: Health and Social Infrastructure (developed/improved) | 4: Mostly Improved |  | Disaster risk reduction | 1: Health and Social Infrastructure (developed/improved) | 4: Mostly Improved
|  | Multi-sector | 1: Health and Social Infrastructure (developed/improved) | 1: Not improved | [9 empty] | Disaster risk reduction | 1: Health and Social Infrastructure (developed/improved) | 3: Moderately improved
Output 4: Vulnerable development sector services and infrastructure assets strengthened in response to climate change impacts, including variability | Indicator 4.1.1: No. and type of development sector services to respond to new conditions resulting from climate variability and change | Number of services | Type |  | Sector | Number of services | Type |  | Sector | Number of services | Type |  | Sector | Number of services | Type |  | Sector
|  | 0 | Community |  | Water management | 515 | Community |  | Water management | 515 | Community |  | Water management
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 5: Increased ecosystem resilience in response to climate change and variability-induced stress | Indicator 5: Ecosystem services and natural resource assets maintained or improved under climate change and variability-induced stress | Natural resource improvement level |  | Sector | Type | Natural resource improvement level |  | Sector | Type | Natural resource improvement level |  | Sector | Type | Natural resource improvement level |  | Sector | Type
|  | 1: Ineffective |  | Multi-sector | water areas | 2: Partially effective |  | Multi-sector |  | 3: Moderately effective
Output 5: Vulnerable ecosystem services and natural resource assets strengthened in response to climate change impacts, including variability | Core Indicator 5.1: Natural Assets protected or rehabilitated | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Forests | 1 | ha rehabilitated | 1: Ineffective | Forests | 22 | ha rehabilitated | 3: Moderately effective | Forests | 40 | ha rehabilitated | 3: Moderately effective | Forests | 3 | 4: Effective
|  | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Mangroves |  | ha rehabilitated | 1: Ineffective | [8 empty] | Mangroves | 2 | 4: Effective
|  | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Cultivated land/Agricultural land |  | ha rehabilitated | 1: Ineffective | [8 empty] | Cultivated land/Agricultural land | 3 | 4: Effective
|  | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Other |  | ha rehabilitated | [9 empty] | Other | 2 | 4: Effective
|  | Baseline information |  |  |  | Targeted performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 6: Diversified and strengthened livelihoods and sources of income for vulnerable people in targeted areas | Indicator 6.1: Increase in households and communities having more secure access to livelihood assets | No. of targeted households | % of female headed households | Improvement level |  | No. of targeted households | % of female headed households | Improvement level |  | No. of targeted households | % of female headed households | Improvement level |  | No. of targeted households | % of female headed households | Improvement level
|  | 0 | 0% | 2: Limited improvement |  | 2365 | 63% | 4: High improvement |  | 311 | 50% | 4: High improvement |  | 1987 | 60% | 4: High improvement
| Indicator 6.2: Increase in targeted population's sustained climate-resilient alternative livelihoods | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
|  | 0 | 5% | From 0 to 0.5% | Agricultural-related | 2365 | 63% | From 5% to 10% | Agricultural-related | 3111 | 50% | From 20% to 30% | Agricultural-related | 1987 | 60% | From 20% to 30% | Agricultural-related
|  | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
|  | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
|  | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
Output 6 Targeted individual and community livelihood strategies strengthened in relation to climate change impacts, including variability | Indicator 6.1.1: No. and type of adaptation assets created or strengthened in support of individual or community livelihood strategies | Number of Assets | Type of Assets | Sector | Adaptation strategy | Number of Assets | Type of Assets | Sector | Adaptation strategy | Number of Assets | Type of Assets | Sector | Adaptation strategy | Number of Assets | Type of Assets | Sector | Adaptation strategy
|  | 0 | Adaptation strategies | Multi-sector | Livelihoods | 31 | Adaptation strategies | Multi-sector | Livelihoods | 35 | Adaptation strategies | Multi-sector | Supporting livelihoods
| Core Indicator 6.1.2: Increased income, or avoided decrease in income | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 7: Improved policies and regulations that promote and enforce resilience measures | Indicator 7: Climate change priorities are integrated into national development strategy | Integration level |  |  |  | Integration level |  |  |  | Integration level |  |  |  | Integration level
3: Some
Output 7:Improved integration of climate-resilience strategies into country development plans | Indicator 7.1: No. of policies introduced or adjusted to address climate change risks | No. of Policies introduced or adjusted | Sector | Scale | Type | No. of Policies introduced or adjusted | Sector | Scale | Type | No. of Policies introduced or adjusted | Sector | Scale | Type | No. of Policies introduced or adjusted | Sector | Scale | Type
|  | 0 | Multi-sector | Local | Other policy | 8 | Multi-sector | Local |  | 9 | Multi-sector | Local
| Indicator 7.2: No. of targeted development strategies with incorporated climate change priorities enforced | No. of Development strategies | Regulation |  | Effectiveness | No. of Development strategies | Regulation |  | Effectiveness | No. of Development strategies | Regulation |  | Effectiveness | No. of Development strategies | Regulation |  | Effectiveness
Glacier lake outburst flood
|  | Inland flooding | fr | biological assets |  | Company policy | 5: Fully enforced (All elements implemented)
|  | Salinization | Decrease | land |  | Communication & Information policy | 4: Enforced (Most elements implemented)
|  | Drought | Same | water areas |  | Defense policy | 3: Partially enforced (Some elements implemented)
|  | Wind |  | subsoil assets | increased adaptive capacity | Domestic policy | 2: Partially not enforced (Most elements not implemented) |  | Agribusiness
|  | Coastal flooding |  | air | achieved | Economic policy | 1: Not enforced (No elements implemented) |  | Agricultural-related | Financial capital
|  | Storm surge | Please choose |  | enhanced level of protection | Education policy |  |  | Agriculture | Human capital
|  | Hurricane | Selected | [5 empty] | Aquaculture | Physical capital
|  |  | Not relevant |  |  | 5: All (Fully integrated) |  |  | Construction/repairing business | Social capital
[6 empty] | 4: Most |  |  | Cultivation | Natural capital
[6 empty] | 3: Some |  |  | Fishing | Personal capital
Select | 5: All | Select |  |  | Community | 2: Most not integrated |  | Other | Forestry | Adaptation strategies
1 | 4: Almost all | Private | Type | Yes | Multi-community | 1: None |  | Agriculture | Handicrafts
2 | 3: Half | Public | Scale | No | Departmental |  |  | Coastal management | Livestock production
3 | 2: Some | NGO | Sector |  | National |  |  | Disaster risk reduction | Manufacturing
4 | 1: None |  |  |  |  | 5: Very high improvement | Established | Food security | other
|  | National |  |  |  | 4: High improvement | Maintained | Health | Services
|  | Regional |  |  |  | 3: Moderate improvement | Improved | Urban development | Tourism-related
|  | Local |  |  |  | 2: Limited improvement |  | Water management | Trading
[6 empty] | 1: No improvement |  | Multi-sector
|  | 1 -generated information is irrelevant, and neither the stakeholders reached nor the timeframe managed were achieved | 1: No info transferred on time | 4: High capacity | 5: Fully aware | 5: Highly responsive (All defined elements ) | 5: Fully improved | Roads | 5: Very effective
Asia-Pacific | NIE | 2 -the existence of some challenge in any of the three aspects of the indicator (generation of dissemination, stakeholders reached or timeframe managed) | 2: Somewhat info transferred | 3: Medium capacity | 4: Mostly aware | 4: Mostly responsive (Most defined elements) | 4: Mostly Improved | Gov Buildings | 4: Effective
Latin America and Caribbean | RIE | 3 -relevant information is generated and disseminated to all identified stakeholders on timely basis | 3: Info transferred on time | 2: Low capacity | 3: Partially aware | 3: Moderately responsive (Some defined elements) | 3: Moderately improved | Causeways | 3: Moderately effective
Africa | MIE |  |  | 1: No capacity | 2: Partially not aware | 2: Partially responsive (Lacks most elements) | 2: Somewhat improved | Airports | 2: Partially effective
Eastern Europe |  |  |  |  | 1: Aware of neither | 1: Non responsive (Lacks all elements ) | 1: Not improved | Schools | 1: Ineffective
| ha protected | [6 empty] | Training Centres
| ha rehabilitated | [5 empty] | Monitoring/Forecasting capacity | Hospitals
Afghanistan, Islamic Rep. of | km protected | [5 empty] | Policy/regulatory reform | Drinking water systems
Angola | km rehabilitated | 1: Risk knowledge | 1: No plans conducted or updated |  |  |  | Capacity development | Other
Albania |  | 2: Monitoring and warning service | 2: Undertaking or updating of assessments in progress |  |  | Communication & Information policy | Sustainable forest management
Argentina |  | 3: Dissemination and communication | 3: Risk and vulnerability assessments completed or updated |  |  | Domestic policy | Strengthening infrastructure | 1: Health and Social Infrastructure (developed/improved)
Armenia | Forests | 4: Response capability |  |  |  | Economic policy | Supporting livelihoods | 2: Physical asset (produced/improved/strengthened)
Antigua and Barbuda | Mangroves |  |  |  |  | Education policy | Mangrove reforestation
Azerbaijan | Coasts |  | From 0 to 0.5% |  |  | Energy policy | Coastal drainage and infrastructure
Burundi | Rangelands |  | From 0.5 to 1% |  |  | Environmental policy | Irrigation system
Benin | Cultivated land/Agricultural land |  | From 1% to 5% |  |  | Foreign policy | Community-based adaptation
Burkina Faso | Catchment area/Watershed/Aquifer |  | From 5% to 10% |  |  | Health policy | Erosion control
Bangladesh | Protected areas/National parks |  | From 10% to 20% |  |  | Housing policy | Soil water conservation
Bulgaria | Other |  | From 20% to 30% |  |  | Human resource policies | Microfinance
Bahrain |  |  | From 30% to 40% |  |  | Information policy | Special Program for women
Bahamas, The |  |  | From 40% to 50% |  |  | Macroeconomic policy | Livelihoods
Bosnia and Herzegovina |  |  | Above 50% |  |  | Monetary policy | Water storage
Belarus | [5 empty] | Population policy | ICT and information dissemination
Belize | [5 empty] | Private policy
Bolivia | [5 empty] | Public policy
Brazil | [5 empty] | Science policy
Barbados | [5 empty] | Social policy
Bhutan |  | 3- relevant information is generated and disseminated to all identified stakeholders on timely basis |  |  |  | Transportation policy
Botswana |  | describe |  |  |  | Urban policy
Central African Republic |  | 2- the existence of some challenge in any of the three aspects of the indicator |  |  |  | Water policy
Chile |  | describe |  |  |  | Other policy
China, People's Republic of |  | 1- generated information is irrelevant and neither the stakeholders reached nor the timeframe managed were achieved
Cote d'Ivoire |  | describe
Cameroon
Congo, Dem. Rep. of
Congo, Republic of
Cook Islands
Colombia
Comoros
Cape Verde
Costa Rica
Cuba
Czech Republic
Djibouti
Dominica
Dominican Republic
Algeria
Ecuador
Egypt
Eritrea
Estonia
Ethiopia
Fiji
Micronesia, Fed. States of
Gabon
Georgia
Ghana
Guinea
Gambia, The
Guinea-Bissau
Equatorial Guinea
Grenada
Guatemala
Guyana
Honduras
Croatia
Haiti
Hungary
Indonesia
India
Iran, Islamic Republic of
Jamaica
Jordan
Kazakhstan
Kenya
Kyrgyz Republic
Cambodia
Kiribati
Saint Kitts and Nevis
Korea, Republic of
Lao People's Democratic Republic
Lebanon
Liberia
Libya
Saint Lucia
Sri Lanka
Lesotho
Lithuania
Latvia
Morocco
Moldova
Madagascar
Maldives
Mexico
Marshall Islands
Macedonia, former Yugoslav Republic of
Mali
Malta
Myanmar
Montenegro
Mongolia
Mozambique
Mauritania
Mauritius
Malawi
Malaysia
Namibia
Niger
Nigeria
Nicaragua
Niue
Nepal
Nauru
Oman
Pakistan
Panama
Peru
Philippines
Palau
Papua New Guinea
Poland
Korea, Dem. People's Rep. of
Paraguay
Romania
Russian Federation
Rwanda
Saudi Arabia
Sudan
Senegal
Solomon Islands
Sierra Leone
El Salvador
San Marino
Serbia
Sao Tome and Principe
Suriname
Slovak Republic
Slovenia
Swaziland
Seychelles
Syrian Arab Republic
Chad
Togo
Thailand
Tajikistan
Turkmenistan
Tonga
Trinidad and Tobago
Tunisia
Turkey
Tuvalu
Tanzania
Uganda
Ukraine
Uruguay
Uzbekistan
Saint Vincent and the Grenadines
Venezuela
Vietnam
Vanuatu
Samoa
Yemen, Republic of
South Africa
Zambia
Zimbabwe
Timor-Leste

## Results tracker revised
Results Tracker for Adaptation Fund (AF) Projects
Goal: Assist developing-country Parties to the Kyoto Protocol that are particularly vulnerable to the adverse effects of climate change in meeting the costs of concrete adaptation projects and programmes in order to implement climate-resilient measures. Impact: Increased resiliency at the community, national, and regional levels to climate variability and change.
Important: Please read the following guidance document (also posted on the Adaptation Fund website) before entering your data
Link: http://www.adaptation-fund.org/sites/default/files/Results%20Framework%20and%20Baseline%20Guidance%20final.pdf
Adaptation Fund Strategic Results Framework
Project ID | 83662-68537
Implementing Entity | UNDP |  | Output 2.2: Targeted population groups covered by adequate risk reduction systems //Grupos de población destinatarios cubiertos por los sistemas de reducción de riesgos adecuadas
Type of implementing entity
Country | Colombia
Region | Latin America and Caribbean
Sector | Multi-sector
0
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Impact: Increased resiliency at the community, national, and regional levels to climate variability and change | Core Indicator: No. of beneficiaries |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project
|  | Total | 211857 | 54000 | 157857 | Total | 18297 | 7319 | 10978 | Total | 17111 | 15555 | 1556 | Total
|  | % of female beneficiaries | 0.55 | 0.55 | 0.55 | % of female beneficiaries | 0.62 | 0.62 | 0.62 | % of female beneficiaries | 0.5 | 0.5 | 0.5 | % of female beneficiaries
|  | % of Youth beneficiaries |  |  |  | % of Youth beneficiaries | 10% | 10% | 10% | % of Youth beneficiaries | 15% | 15% | 15% | % of Youth beneficiaries
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 1: Reduced exposure to climate-related hazards and threats | Indicator 1: Relevant threat and hazard information generated and disseminated to stakeholders on a timely basis | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness
|  | Total | 0 | Inland flooding | 1: Ineffective | Total | 7319 | Inland flooding | 3: Moderately effective | Total | 15555 | Inland flooding | 2: Partially effective | Total
|  | % of female targeted | 0 |  |  | % of female targeted | 62% |  |  | % of female targeted | 50% |  |  | % of female targeted
Output 1.1 Risk and vulnerability assessments conducted and updated | Indicator 1.1: No. of projects/programmes that conduct and update risk and vulnerability assessments | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
Output 1.2 Targeted population groups covered by adequate risk reduction systems | Core Indicator 1.2: No. of Early Warning Systems | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard | Inland flooding | No. of adopted Early Warning Systems | Category targeted | Hazard
|  | 0 | 3: Dissemination and communication | Geographical coverage | Local | 1 | 3: Dissemination and communication | Geographical coverage | Local | 1 | 3: Dissemination and communication | Geographical coverage | Local |  |  | Geographical coverage
|  |  |  | Number of municipalities | 3 |  |  | Number of municipalities | 3 |  |  | Number of municipalities | 3 |  |  | Number of municipalities
|  | No. of adopted Early Warning Systems | Category targeted | Hazard | Inland flooding | No. of adopted Early Warning Systems | Category targeted | Hazard | Inland flooding | No. of adopted Early Warning Systems | Category targeted | Hazard | Inland flooding | No. of adopted Early Warning Systems | Category targeted | Hazard
|  | 0 | 2: Monitoring and warning service | Geographical coverage | Local | 1 | 2: Monitoring and warning service | Geographical coverage | Local | 1 | 2: Monitoring and warning service | Geographical coverage | Local |  |  | Geographical coverage
|  |  |  | Number of municipalities | 3 |  |  | Number of municipalities | 3 |  |  | Number of municipalities | 3 |  |  | Number of municipalities
|  | No. of adopted Early Warning Systems | Category targeted | Hazard |  |  | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 2: Strengthened institutional capacity to reduce risks associated with climate-induced socioeconomic and environmental losses | Indicator 2: Capacity of staff to respond to, and mitigate impacts of, climate-related events from targeted institutions increased | Number of staff targeted |  | Sector | Capacity level | Number of staff targeted |  | Sector | Capacity level | Number of staff targeted |  | Sector | Capacity level | Number of staff targeted |  | Sector | Capacity level
|  | Total | 0 | Disaster risk reduction | 1: No capacity | Total | 33 | Multi-sector | 3: Medium capacity | Total | 33 | Multi-sector | 3: Medium capacity | Total
|  | % of female targeted | 0 |  |  | % of female targeted | 39% |  |  | % of female targeted | 39% |  |  | % of female targeted
Output 2.1 Strengthened capacity of national and sub-national centres and networks to respond rapidly to extreme weather events | Indicator 2.1.1: No. of staff trained to respond to, and mitigate impacts of, climate-related events | Total staff trained | % of female staff trained | Type |  | Total staff trained | % of female staff trained | Type |  | Total staff trained | % of female staff trained | Type |  | Total staff trained | % of female staff trained | Type
| Indicator 2.1.2: No. of targeted institutions with increased capacity to minimize exposure to climate variability risks | Type | Scale | Sector | Capacity level | Type | Scale | Sector | Capacity level | Type | Scale | Sector | Capacity level | Type | Scale | Sector | Capacity level
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 3: Strengthened awareness and owernship of adaptation and climate risk reduction processes | Indicator 3.1: Increase in application of appropriate adaptation responses | Percentage of targeted population applying adaptation measures |  | Sector |  | Percentage of targeted population applying adaptation measures |  | Sector |  | Percentage of targeted population applying adaptation measures |  | Sector |  | Percentage of targeted population applying adaptation measures |  | Sector
|  | 50% |  | Food security |  | 56% |  | Food security |  | 0.7
Output 3: Targeted population groups participating in adaptation and risk reduction awareness activities | Indicator 3.1.1: Percentage in targeted population awareness of predicted adverse impacts of climate change, and of appropriate responses | No. of targeted beneficiaries | % of female participants targeted | Level of awareness |  | No. of targeted beneficiaries | % of female participants targeted | Level of awareness |  | No. of targeted beneficiaries | % of female participants targeted | Level of awareness |  | No. of targeted beneficiaries | % of female participants targeted | Level of awareness
|  | 0 | 0% | 3: Partially aware |  | 7319 | 62% | 4: Mostly aware |  | 9125 | 50% | 4: Mostly aware
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 4: Increased adaptive capacity within relevant development sector services and infrastructure assets | Indicator 4.1: Increased responsiveness of development sector services to evolving needs from changing and variable climate | Project/programme sector | Geographical scale | Response level |  | Project/programme sector | Geographical scale | Response level |  | Project/programme sector | Geographical scale | Response level |  | Project/programme sector | Geographical scale | Response level
|  | Disaster risk reduction | Local | 2: Partially responsive (Lacks most elements) |  | Disaster risk reduction | Local | 1: Non responsive (Lacks all elements ) |  | Disaster risk reduction | Regional
| Core Indicator 4.2: Assets produced, developed, improved or strengthened | Sector | Targeted asset | Changes in asset (quantitative or qualitative) |  | Sector | Targeted asset | Changes in asset (quantitative or qualitative) |  | Sector | Targeted asset | Changes in asset (quantitative or qualitative) |  | Sector | Targeted asset | Changes in asset (quantitative or qualitative)
|  | Water management | 2: Physical asset (produced/improved/strengthened) | 2: Somewhat improved |  | Water management | 1: Health and Social Infrastructure (developed/improved) | 4: Mostly Improved |  | Water management | 1: Health and Social Infrastructure (developed/improved) | 4: Mostly Improved
|  | Food security | 2: Physical asset (produced/improved/strenghtened) | 2: Somewhat improved |  | Food security | 2: Physical asset (produced/improved/strenghtened) | 5: Fully improved |  | Food security | 1: Health and Social Infrastructure (developed/improved) | 4: Mostly Improved
|  | Agriculture | 2: Physical asset (produced/improved/strengthened) | 1: Not improved |  | Agriculture | 2: Physical asset (produced/improved/strengthened) | 3: Moderately improved |  | Agriculture | 1: Health and Social Infrastructure (developed/improved) | 4: Mostly Improved
Output 4: Vulnerable development sector services and infrastructure assets strengthened in response to climate change impacts, including variability | Indicator 4.1.1: No. and type of development sector services to respond to new conditions resulting from climate variability and change | Number of services | Type |  | Sector | Number of services | Type |  | Sector | Number of services | Type |  | Sector | Number of services | Type |  | Sector
|  | 0 | Community |  | Water management | 515 | Community |  | Water management | 515 | Community |  | Water management
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 5: Increased ecosystem resilience in response to climate change and variability-induced stress | Indicator 5: Ecosystem services and natural resource assets maintained or improved under climate change and variability-induced stress | Natural resource improvement level |  | Sector | Type | Natural resource improvement level |  | Sector | Type | Natural resource improvement level |  | Sector | Type | Natural resource improvement level |  | Sector | Type
|  | 1: Ineffective |  | Multi-sector | water areas | 2: Partially effective |  | Multi-sector |  | 3: Moderately effective
Output 5: Vulnerable ecosystem services and natural resource assets strengthened in response to climate change impacts, including variability | Core Indicator 5.1: Natural Assets protected or rehabilitated | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Forests |  | ha rehabilitated | 1: Ineffective | Forests | 22 | ha rehabilitated | 3: Moderately effective | Forests | 40 | ha rehabilitated | 3: Moderately effective
|  | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Baseline information |  |  |  | Targeted performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 6: Diversified and strengthened livelihoods and sources of income for vulnerable people in targeted areas | Indicator 6.1: Increase in households and communities having more secure access to livelihood assets | No. of targeted households | % of female headed households | Improvement level |  | No. of targeted households | % of female headed households | Improvement level |  | No. of targeted households | % of female headed households | Improvement level |  | No. of targeted households | % of female headed households | Improvement level
|  | 13200 | 0.48 | 2: Limited improvement |  | 2365 | 63% | 4: High improvement |  | 311 | 50% | 4: High improvement
| Indicator 6.2: Increase in targeted population's sustained climate-resilient alternative livelihoods | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
|  | 13200 | 0.48 | From 0 to 0.5% | Agricultural-related | 2365 | 63% | From 5% to 10% | Agricultural-related | 3111 | 50% | From 20% to 30% | Agricultural-related
|  | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
|  | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
|  | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
Output 6 Targeted individual and community livelihood strategies strengthened in relation to climate change impacts, including variability | Indicator 6.1.1: No. and type of adaptation assets created or strengthened in support of individual or community livelihood strategies | Number of Assets | Type of Assets | Sector | Adaptation strategy | Number of Assets | Type of Assets | Sector | Adaptation strategy | Number of Assets | Type of Assets | Sector | Adaptation strategy | Number of Assets | Type of Assets | Sector | Adaptation strategy
|  | 0 | Adaptation strategies | Multi-sector | Livelihoods | 31 | Adaptation strategies | Multi-sector | Livelihoods | 35 | Adaptation strategies | Multi-sector | Supporting livelihoods
| Core Indicator 6.1.2: Increased income, or avoided decrease in income | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 7: Improved policies and regulations that promote and enforce resilience measures | Indicator 7: Climate change priorities are integrated into national development strategy | Integration level |  |  |  | Integration level |  |  |  | Integration level |  |  |  | Integration level
3: Some
Output 7:Improved integration of climate-resilience strategies into country development plans | Indicator 7.1: No. of policies introduced or adjusted to address climate change risks | No. of Policies introduced or adjusted | Sector | Scale | Type | No. of Policies introduced or adjusted | Sector | Scale | Type | No. of Policies introduced or adjusted | Sector | Scale | Type | No. of Policies introduced or adjusted | Sector | Scale | Type
|  | 0 | Multi-sector | Local | Other policy | 8 | Multi-sector | Local |  | 9 | Multi-sector | Local
| Indicator 7.2: No. of targeted development strategies with incorporated climate change priorities enforced | No. of Development strategies | Regulation |  | Effectiveness | No. of Development strategies | Regulation |  | Effectiveness | No. of Development strategies | Regulation |  | Effectiveness | No. of Development strategies | Regulation |  | Effectiveness
Glacier lake outburst flood
|  | Inland flooding | fr | biological assets |  | Company policy | 5: Fully enforced (All elements implemented)
|  | Salinization | Decrease | land |  | Communication & Information policy | 4: Enforced (Most elements implemented)
|  | Drought | Same | water areas |  | Defense policy | 3: Partially enforced (Some elements implemented)
|  | Wind |  | subsoil assets | increased adaptive capacity | Domestic policy | 2: Partially not enforced (Most elements not implemented) |  | Agribusiness
|  | Coastal flooding |  | air | achieved | Economic policy | 1: Not enforced (No elements implemented) |  | Agricultural-related | Financial capital
|  | Storm surge | Please choose |  | enhanced level of protection | Education policy |  |  | Agriculture | Human capital
|  | Hurricane | Selected | [5 empty] | Aquaculture | Physical capital
|  |  | Not relevant |  |  | 5: All (Fully integrated) |  |  | Construction/repairing business | Social capital
[6 empty] | 4: Most |  |  | Cultivation | Natural capital
[6 empty] | 3: Some |  |  | Fishing | Personal capital
Select | 5: All | Select |  |  | Community | 2: Most not integrated |  | Other | Forestry | Adaptation strategies
1 | 4: Almost all | Private | Type | Yes | Multi-community | 1: None |  | Agriculture | Handicrafts
2 | 3: Half | Public | Scale | No | Departmental |  |  | Coastal management | Livestock production
3 | 2: Some | NGO | Sector |  | National |  |  | Disaster risk reduction | Manufacturing
4 | 1: None |  |  |  |  | 5: Very high improvement | Established | Food security | other
|  | National |  |  |  | 4: High improvement | Maintained | Health | Services
|  | Regional |  |  |  | 3: Moderate improvement | Improved | Urban development | Tourism-related
|  | Local |  |  |  | 2: Limited improvement |  | Water management | Trading
[6 empty] | 1: No improvement |  | Multi-sector
|  | 1 -generated information is irrelevant, and neither the stakeholders reached nor the timeframe managed were achieved | 1: No info transferred on time | 4: High capacity | 5: Fully aware | 5: Highly responsive (All defined elements ) | 5: Fully improved | Roads | 5: Very effective
Asia-Pacific | NIE | 2 -the existence of some challenge in any of the three aspects of the indicator (generation of dissemination, stakeholders reached or timeframe managed) | 2: Somewhat info transferred | 3: Medium capacity | 4: Mostly aware | 4: Mostly responsive (Most defined elements) | 4: Mostly Improved | Gov Buildings | 4: Effective
Latin America and Caribbean | RIE | 3 -relevant information is generated and disseminated to all identified stakeholders on timely basis | 3: Info transferred on time | 2: Low capacity | 3: Partially aware | 3: Moderately responsive (Some defined elements) | 3: Moderately improved | Causeways | 3: Moderately effective
Africa | MIE |  |  | 1: No capacity | 2: Partially not aware | 2: Partially responsive (Lacks most elements) | 2: Somewhat improved | Airports | 2: Partially effective
Eastern Europe |  |  |  |  | 1: Aware of neither | 1: Non responsive (Lacks all elements ) | 1: Not improved | Schools | 1: Ineffective
| ha protected | [6 empty] | Training Centres
| ha rehabilitated | [5 empty] | Monitoring/Forecasting capacity | Hospitals
Afghanistan, Islamic Rep. of | km protected | [5 empty] | Policy/regulatory reform | Drinking water systems
Angola | km rehabilitated | 1: Risk knowledge | 1: No plans conducted or updated |  |  |  | Capacity development | Other
Albania |  | 2: Monitoring and warning service | 2: Undertaking or updating of assessments in progress |  |  | Communication & Information policy | Sustainable forest management
Argentina |  | 3: Dissemination and communication | 3: Risk and vulnerability assessments completed or updated |  |  | Domestic policy | Strengthening infrastructure | 1: Health and Social Infrastructure (developed/improved)
Armenia | Forests | 4: Response capability |  |  |  | Economic policy | Supporting livelihoods | 2: Physical asset (produced/improved/strengthened)
Antigua and Barbuda | Mangroves |  |  |  |  | Education policy | Mangrove reforestation
Azerbaijan | Coasts |  | From 0 to 0.5% |  |  | Energy policy | Coastal drainage and infrastructure
Burundi | Rangelands |  | From 0.5 to 1% |  |  | Environmental policy | Irrigation system
Benin | Cultivated land/Agricultural land |  | From 1% to 5% |  |  | Foreign policy | Community-based adaptation
Burkina Faso | Catchment area/Watershed/Aquifer |  | From 5% to 10% |  |  | Health policy | Erosion control
Bangladesh | Protected areas/National parks |  | From 10% to 20% |  |  | Housing policy | Soil water conservation
Bulgaria | Other |  | From 20% to 30% |  |  | Human resource policies | Microfinance
Bahrain |  |  | From 30% to 40% |  |  | Information policy | Special Program for women
Bahamas, The |  |  | From 40% to 50% |  |  | Macroeconomic policy | Livelihoods
Bosnia and Herzegovina |  |  | Above 50% |  |  | Monetary policy | Water storage
Belarus | [5 empty] | Population policy | ICT and information dissemination
Belize | [5 empty] | Private policy
Bolivia | [5 empty] | Public policy
Brazil | [5 empty] | Science policy
Barbados | [5 empty] | Social policy
Bhutan |  | 3- relevant information is generated and disseminated to all identified stakeholders on timely basis |  |  |  | Transportation policy
Botswana |  | describe |  |  |  | Urban policy
Central African Republic |  | 2- the existence of some challenge in any of the three aspects of the indicator |  |  |  | Water policy
Chile |  | describe |  |  |  | Other policy
China, People's Republic of |  | 1- generated information is irrelevant and neither the stakeholders reached nor the timeframe managed were achieved
Cote d'Ivoire |  | describe
Cameroon
Congo, Dem. Rep. of
Congo, Republic of
Cook Islands
Colombia
Comoros
Cape Verde
Costa Rica
Cuba
Czech Republic
Djibouti
Dominica
Dominican Republic
Algeria
Ecuador
Egypt
Eritrea
Estonia
Ethiopia
Fiji
Micronesia, Fed. States of
Gabon
Georgia
Ghana
Guinea
Gambia, The
Guinea-Bissau
Equatorial Guinea
Grenada
Guatemala
Guyana
Honduras
Croatia
Haiti
Hungary
Indonesia
India
Iran, Islamic Republic of
Jamaica
Jordan
Kazakhstan
Kenya
Kyrgyz Republic
Cambodia
Kiribati
Saint Kitts and Nevis
Korea, Republic of
Lao People's Democratic Republic
Lebanon
Liberia
Libya
Saint Lucia
Sri Lanka
Lesotho
Lithuania
Latvia
Morocco
Moldova
Madagascar
Maldives
Mexico
Marshall Islands
Macedonia, former Yugoslav Republic of
Mali
Malta
Myanmar
Montenegro
Mongolia
Mozambique
Mauritania
Mauritius
Malawi
Malaysia
Namibia
Niger
Nigeria
Nicaragua
Niue
Nepal
Nauru
Oman
Pakistan
Panama
Peru
Philippines
Palau
Papua New Guinea
Poland
Korea, Dem. People's Rep. of
Paraguay
Romania
Russian Federation
Rwanda
Saudi Arabia
Sudan
Senegal
Solomon Islands
Sierra Leone
El Salvador
San Marino
Serbia
Sao Tome and Principe
Suriname
Slovak Republic
Slovenia
Swaziland
Seychelles
Syrian Arab Republic
Chad
Togo
Thailand
Tajikistan
Turkmenistan
Tonga
Trinidad and Tobago
Tunisia
Turkey
Tuvalu
Tanzania
Uganda
Ukraine
Uruguay
Uzbekistan
Saint Vincent and the Grenadines
Venezuela
Vietnam
Vanuatu
Samoa
Yemen, Republic of
South Africa
Zambia
Zimbabwe
Timor-Leste