## Overview
Project Performance Report (PPR)
| Period of Report (Dates) | November 1, 2013 - October 31, 2014
| Programme Title: | ENHANCING THE RESILIENCE OF THE AGRICULTURE SECTOR AND COASTAL AREAS TO PROTECT LIVELIHOODS AND IMPROVE FOOD SECURITY
| Programme Summary: | Jamaica is vulnerable to climate related hazards, in particular hurricanes, floods, storm surges and droughts, due largely to its geographical location and the exposure of social and economic assets in coastal areas. This situation is made worse by the country’s low adaptive capacity especially in the climate sensitive sectors of the economy. The agriculture sector and coastal resources are among those at greatest risk, given their significant contribution to the country’s GDP and to the labour force. These two sectors were also highlighted as among the five most vulnerable to climate change in assessments conducted for Jamaica’s Second National Communication (SNC) to the United Nations Framework Convention on Climate Change (UNFCCC). Additionally, Vision 2030 Jamaica – National Development Plan articulates climate change adaptation as a priority for not only a healthy, natural environment, but also for achieving developed country status by 2030. The activities identified in Government of Jamaica Adaptation Fund Programme (GOJ/AFP) are drawn from the adaptation priorities that were identified in the vulnerability and adaptation assessments for the agriculture and coastal resources sectors. The programme focuses on environmental and natural resource management activities; namely, coastal rehabilitation, inland flood and erosion control, and land and water management. The Overall Objective of the GOJ/AFP is to protect livelihoods and food security in vulnerable communities by: • improving land and water management for the agricultural sector • strengthening coastal protection; and • building institutional and local capacity for Climate Change Adaptation and Natural Resources Management
|  | Component 1 - Increasing the climate resilience of the Negril Coastline: Hard engineering structures (breakwaters) will be installed to control coastal erosion in the most vulnerable sections of the Negril coastline to protect the beaches from climate related hazards such as seal-level rise and intense storms. Location: Long Bay, Negril Component 2- Enhancing climate resilience of the agricultural sector by improving water and land management in select communities Location: Manchester, Trelawny, St. Mary, St. Ann, St. Catherine, St. Thomas and Clarendon Component 3 - Improving institutional and local level capacity for coastal and agricultural adaptation and awareness raising for behaviour modification | Countries | Project Type: |  | GEF Focal Area: | GEF 4 Focal Areas | GEF 2 / 3 Operational Programme: | Overall Rating of the project in the evaluation by the project evaluator: | GEF-4 Focal Area Strategic Program: | GEF-3 Focal Area Strategic Program:
| Database Number: | JAM/NIE/Multi/2011/1 | Afghanistan | FP | Yes | Biodiversity | 1 | 1 | U | BD-SP1-PA Financing | 1: Arid & semi-arid ecosystems
Implementing Entity (IE) [name]: |  | Planning Institute of Jamaica (PIOJ) | Albania | MSP | No | Climate Change Adaptation | 2 | 2 | S | BD-SP2-Marine PA | 2: Coastal, marine & freshwater ecosystems
| Type of IE: | National Implimenting Entity | Algeria | EA |  | Climate Change Mitigation | 3 | 3 | MU | BD-SP3-PA Networks | 3: Forest ecosystems
| Country(ies): | Jamaica | Angola |  |  | International Waters | 5 | 5 | Good | BD-SP5-Markets | 13: Conservation and Sustainable Use of Biological Diversity Important to Agriculture
Relevant Geographic Points (i.e. cities, villages, bodies of water): |  | Component 1 - Increasing climate resilience of the Negril coastline Location: Long Bay, Negril Component 2- Enhancing climate resilience of the agricultural sector by improving water and land management in select communities Location: Manchester, Trelawny, St. Mary, St. Ann, St. Catherine, St. Thomas and Clarendon Component 3 - Improving institutional and local level capacity for coastal and agricultural adaptation and awareness raising for behaviour modification Location: Westmoreland/Hanover; target communities in Component 2 | Argentina |  |  | Multiple Focal Area |  |  |  | BD-SP7-Invasive Alien Species(IAS) | 6: Promoting the adoption of renewable energy by removing barriers and reducing implementation costs
[8 empty] | CC-SP2- Industrial EE | 8: Waterbody based operational program
| Programme Milestones | [6 empty] | CC-SP3-RE,CC-SP4-Biomass | 9: Integrated Land and Water multiple focal area
| Milestone |  | Bahamas | [6 empty] | CC-SP5-Transport | 10: Contaminants based operational program
AFB Approval Date: |  | 2012-06-29
IE-AFB Agreement Signature Date: |  | 2012-07-23 | [6 empty] | CC-SP6-LULUCF | 12: Integrated Ecosystem Management
Start of Project/Programme: |  | 2012-11-02 | [6 empty] | Cross cutting capacity building | 14: Persistent Organic Pollutants
Mid-term Review Date (if planned): |  | 2015-04-30
| Terminal Evaluation Date: | 2016-03-01
|  | List documents/ reports/ brochures / articles that have been prepared about the project. | Cyprus
|  | Newspaper Article (Jamaica Observer - November 4, 2013) Report on sea-level rise and storm surge modelling; KAP survey Environmental Impact Assessment (EIA) Report; Natural Resources Valuation Report Signs erected in target communities to identify demonstration plots/ land husbandry activities Partnered with Ministry of Water, Land, Environment and Climate Change (MWLECC) in commemoration of World Water Day 2014 – placed advertisement in Gleaner supplement and flyers were handed out. - An interview expressing the NIEs concern in response to media campaign by a group of Negril stakeholders was published in the Daily Gleaner on May 14, 2014. Article published in Gleaner on May 29, 2014 indicating that NIE was seeking to make up lost implementation time. Advertorial placed in two leading national newspapers (July) to provide general information to the public on the GOJ/AFP FAQs, Fact Sheets and brochures prepared and disseminated to stakeholders | Czech Republic
List the Website address (URL) of project. |  |  | Democratic People's Republic of Korea
|  | http://dev.adaptja.pioj.gov.jm (under construction) | Democratic Republic of the Congo
Denmark
| Programme contacts: |  | Djibouti
National Project Manager/Coordinator |  |  | Dominica
| Name: |  | Dominican Republic
| Email: |  | Ecuador
| Date: |  | Egypt
Government DA
| Name: | Albert Daley, Climate Change Division, Ministry of Water, Land, Environment & Climate Change
| Email: | a.daley@mwlecc.gov.jm
| Date: | 2014-07-01
| Implementing Entity |  | El Salvador
| Name: | Shelia McDonald-Miller | Equatoral Guinea
| Email: | smmiller@pioj.gov.jm | Eritrea
| Date: | 2012-12-03 | Estonia
| Executing Agency |  | Ethiopia
| Name: | Ministry of Agriculture and Fisheries | Fiji
| Email: |  | Finland
| Date: |  | France
| Executing Agency |  | Gambia
| Name: | National Environment and Planning Agency | Georgia
| Email: |  | Germany
| Date: |  | Ghana
| Executing Agency |  | Greece
| Name: | National Works Agency | Grenada
| Email: |  | Guatemala
| Date: |  | Guinea
| Executing Agency |  | Guinea Bissau
| Name: | Ministry of Tourism & Entertinment | Guyana
| Email: |  | Haiti
| Date: |  | Honduras
Hungary
Iceland
India
Indonesia
Iran (Islamic Republic of)
Iraq
Ireland
Israel
Italy
Jamaica
Japan
Jordan
Kazakhstan
Kenya
Kiribati
Kuwait
Kyrgyzstan
Lao People’s Democratic Republic
Latvia
Lebanon
Lesotho
Liberia
Libyan Arab Jamahiriya
Liechtenstein
Lithuania
Luxembourg
Madagascar
Malawi
Malaysia
Maldives
Mali
Malta
Marshall Islands
Mauritania
Mauritius
Mexico
Micronesia, Federated States of
Monaco
Mongolia
Montenegro
Morocco
Mozambique
Myanmar
Namibia
Nauru
Nepal
Netherlands
New Zealand
Nicaragua
Niger
Nigeria
Norway
Oman
Pakistan
Palau
Panama
Papua New Guinea
Paraguay
Peru
Philippines
Poland
Portugal
Qatar
Republic of Korea
Republic of Moldova
Romania
Russian Federation
Rwanda
Saint Kitts and Nevis
Saint Lucia
Saint Vincent and the Grenadines
Samoa
San Marino
Sao Tome and Principe
Saudi Arabia
Senegal
Serbia
Seychelles
Sierra Leone
Singapore
Slovakia
Slovenia
Solomon Islands
Somalia
South Africa
Spain
Sri Lanka
Sudan
Suriname
Swaziland
Sweden
Switzerland
Syrian Arab Republic
Tajikistan
Thailand
The former Yugoslav Republic of Macedonia
Timor-Leste
Togo
Tonga
Trinidad and Tobago
Tunisia
Turkey
Turkmenistan
Tuvalu
Uganda
Ukraine
United Arab Emirates
United Kingdom of Great Britain and Northern Ireland
United Republic of Tanzania
United States of America
Uruguay
Uzbekistan
Vanuatu
Venezuela, Bolivarian Republic of
Viet Nam
Yemen
Zambia
Zimbabwe

## FinancialData
Financial information: cumulative from programme start to October 31, 2014
DISBURSEMENT OF AF GRANT FUNDS
How much of the total AF grant as noted in Project Document plus any project preparation grant has been spent to date?
Estimated cumulative total disbursement as of October 31, 2014 |  | 893016
Add any comments on AF Grant Funds. (word limit=200)
EXPENDITURE DATA
List ouput and corresponding amount spent for the current reporting period | Programme Component | ITEM / ACTIVITY / ACTION | AMOUNT
| Component 1: Increasing the climate resilience of the Negril coastline | Installation of breakwater structures (preparatory activities including design and modelling; EIA process) | 116106
|  | Project Execution | 52238
| Total Component 1 |  | 168344
| Component 2: Enhancing the climate resilience of the agricultural sector by improving water and land management in select communities | 2.1 Establishment of Micro-dam | 0
|  | 2.2 Establishment of small scale irrigation facilities | 70141
2.3 Implementation of rainwater harvesting and drip irrigation systems
|  | 2.4 Establishment and rehabilitation of soil conservation and land husbandry infrastructure | 10522
|  | 2.5 Establishment of Demonstration Plots | 34008
|  | Project Execution | 42905
| Total Component 2 |  | 157576
| Component 3: Improving institutional and local level capacity for sustainable management of natural resources and disaster risk reduction in the targeted vulnerable areas | Training of Local Communities in Disaster Risk Reduction and Natural Resources Management | 16206
|  | Development of Climate Risk Atlas | 56396
Development of Adaptation Plans for vulnerable areas along Negril coastline
|  | Establish farmer field schools to develop solutions and demonstrate good practices | 3273
|  | Conducting workshops and farmer training in climate smart agriculture | 9925
|  | Climate change awareness and education programmes developed and implemented in project communities | 1051
|  | Project Execution | 41
| Total Component 3 |  | 86892
| Programme Implementation (NIE) |  | 103336
|  | TOTAL | 516148
PLANNED EXPENDITURE SCHEDULE
List outputs planned and corresponding projected cost for the upcoming reporting period |  | ITEM / ACTIVITY / ACTION | PROJECTED COST | Est. Completion Date
Component 1
|  | EIA Public Meeting #2 - EIA Final Report | 3222.2727 | 2014-11-01
|  | Contract mobilization | 409090.9091 | 2015-05-01
|  | Environmental Enforcement Officers | 35870.9091 | 2015-10-01
|  | Contruction of breakwaters | 2727272.7273 | 2015-10-01
|  | Monitoring of coastal works | 50000 | 2015-10-01
|  | Project Execution | 158181.8182 | 2015-10-01
|  | Subtotal | 3383638.6364
Component 2
|  | Rain water harvesting systems | 190909.0909 | 2015-10-01
|  | Land Husbandry Grants Approved and implemented; gravity drip irrigation systems | 163636.3636 | 2015-10-01
|  | Production and productivity Grant | 518181.8182 | 2015-10-01
|  | Demonstration Plots and FFS training | 100000 | 2015-10-01
|  | Project Execution | 42905
|  | Subtotal | 972727.2727
Component 3
|  | Training of Communities in DRM | 64393.9397 | 2015-09-01
|  | Development of Guidelines for Beach Restoration | 54545.4545 | 2015-05-01
|  | Adaptation Plans | 38181.8182 | 2015-09-01
|  | Risk Atlas Development | 49378.788 | 2015-08-01
|  | Subtotal | 206500.0005 | 2015-10-01
|  | NIE Fee | 177272.7273 | 2015-10-01
|  | TOTAL | 4740138.6368
ACTUAL CO-FINANCING (If the MTR or TE have not been undertaken this reporting period, DO NOT report on actual co-financing.)
How much of the total co-financing as committed in the Project Document has actually been realized? |  | Co-financing is not applicable to this programme
Estimated cumulative actual co-financing as verified during Mid-term Review (MTR) or Terminal Evaluation (TE).
Add any comments on actual co-financing in particular any issues related to the realization of in-kind, grant, credits, loans, equity, non-grant instruments and other types of co-financing. (word limit=200)
Note on F9: Shelia Mcdonald-Miller: =869459 Implementation expenditure + 23557 PFG

## Risk Assesment
RISK ASSESMENT
IDENTIFIED RISKS
List all Risks identified in project preparation phase and what steps are being taken to mitigate them
Identified Risk | Current Status | Steps Taken to Mitigate Risk
Financial: budget over-runs/under-spend; mis-use of funds; inflation/ currency depreciation leading to increased costs for goods/services | Moderate | Budget planning workshops; Regular reviews Comprehensive Memoranda of Understanding (MOU) signed with Executing Entities to establish operational modalities; work plans/budgets must be approved by the Programme Steering Committee (PSC) prior to disbursement of funds; The NIE developed financial reporting templates/procedures and provided training to partners in use thereof; convened regular programme review meetings and undertook periodic monitoring visits to Executing Entities
Environmental: natural hazards (flood, drought, storms/hurricanes); pests and diseases. | High | Contingency planning; education programme and pest management Partners and communities are advised to design implementation plans and schedules to take account of the peak 'adverse climatic events' period; additionally there is information on how to respond in the event of such occurrences. Ongoing pest/disease control programmes are carried continously by the Ministry of Agriculture & Fisheries.
Stakeholder Buy-in | Moderate | Deepening of Stakeholder Engagement Participation of all major stakeholder groupings was secured during the programme development phase and continues to be a high priority during implementation. Additionally, there has been information, sensitization and mobilization sessions both with the programme team and among target communities since the launch of the programme. Special care is taken to involve local community groups and civil society organisations in programme activities. There is a high level of political buy-in with endorsement and support of the government and portfolio Ministry. Notwithstanding, unfolding events have signalled that Component 1 requires special attention and the NIE is committed to deepening stakeholder involvement in the target communities
Multiple Executing Entities | Moderate | There has been some degree of layering relating to the interface of different systems and procedures, as well as intra agency/ intra component kinks during implementation. To provide clarity, the NIE has signed a MOU with all Executing Entities which outlines the roles and responsibilities of the respective parties. clarification was provided during the kick-off workshop and focal points identified within each agency to facilitate a smoother implementation process. The establishment of the Programme Steering Committee (PSC) by the NIE ensures that a formal governance structure is fully operational to provide strategic oversight and coordination of interventions at the technical level. Generally, there is growing inter-agency co-operation among the Executing Entities with the co-opting of members from other agencies on several project committees to lend their expertise and support. Additionally, the PMU hosts regular team meetings with memberss of all EEs and other partner agencies involved in implementation of activities to provide a framework for collaboration and cross-fertilization of ideas among the main players. Agreements reached in meetings on programme implementation issues are documented and with emphasis on follow-up actions and timetable for completion. Generally, there is growing inter-agency co-operation among the Executing Entities with the co-opting of members from other agencies on several project committees to lend their expertise and support.
Procurement Delays | High | The PMU has supported all Executing Entities in the completion and approval of procurement plans. This enables the establishment of realistic lead times and proactive identification of special conditions such as required permits and seasonality of required materials/resources. Importantly, there has been training in the relevant (GOJ) procurement guidelines and procedures aimed at building capacity and avoiding breaches. Additional training is planned to further bolster the capacity of the programme team. The 'no-objection' process by the PMU provides guidance and oversight in ensuring that there is compliance with relevant procurement guidelines
Implementation/ Operational: Delays in project implementation schedule | Moderate to High | Collaborative approach to work planning and ongoing support provided by the Programme Management Unit. Regular technical meetings are convened among partners to coordinate activities. Several follow-up meetings and visits to Executing Entities to assist in identifying bottlenecks and resolving challenges. Inter- and intra-agency frameworks have been incorporated into the programme to reduce competition and avoid segmentation. Programme Steering Committee (PSC) reviews progress against work plans and implementation schedules. The NIE has also initiated round-table discussions with senior management of Executing Entities to solicit their support in improving the pace of implementation
Critical Risks Affecting Progress (Not identified at project design)
Identify Risks with a 50% or > likelihood of affecting progress of project
Identified Risk | Current Status | Steps Taken to Mitigate Risk
Risks associated with the complexity of maritime works (breakwater structures) | Moderate to High | Proper feasibility, scientific and environmental assessments undertaken, including Environental Impact Assessment, Natural Resources Valuation; international procurement conducted to garner the best available expertise. National (specialized) agencies to provide technical oversight and environmental monitoring; clear technical specifications to be included in tender documents; local monitoring committee to be formed to ensure compliance with environmental conditions and building standards
Low disaster risk perception of some target communities | Moderate | There has been low disaster risk perception in the targeted communities under component 3. This has affected the level of support and participation towards training sessions in Disaster Risk Reduction. ODPEM and MTE will continue to review the factors contributing to this. A mobilization plan has been devised and will be implemented in 2015. Comprehensive communication and awareness-raising activities to be undertaken in the coming months
Stakeholder resistance against Breakwater | High | Several consultations have been held throughout the target communities; in particular: JIS Think Tank session in November 2013 – online articles and electronic media reports provided information to the public - A communication strategy and action plan was developed collaboratively with programme partners to ensure continuous dissemination of information to all stakeholders As part of the EIA process, a survey of 355 stakeholders and 4 focal group meetings between January-March 2014 During 2014, letters were written by the NIE and dispatched to key stakeholders in the Negril community in order to provide clearer and better particulars of the programme. Intervention of the Minister of Tourism was solicited and a consultation held on July 3 with select Negril stakeholders; public presentation of EIA findings took place on July 29, 2014 and stakeholders were provided with additional time (30 days) in which to provide their input into the process. To mitigate the risk of incurring expenditure prematurely, the NIE placed a hold on the procurement of Engineer by NEPA to perform environmental monitoring, as the dissent was contributing to execution delays. A local monitoring committee is to be formed to assist in providing oversight during the construction phase. Sensitization activities and advocacy will continue in the affected communities and for the public in general.
Executing Entity's readiness to implement, including availability of human resources and capacity for financial management | Moderate | Following the official launch and inception report, there was significant lag time in actual start-up among the Executing Entities. The NIE has provided support to the Executing Entities to ensure the establishing of project bank accounts and improvements in implementation framework. Entities have now confirmed the availability of physical facilities and availability of adequate and/or dedicated staff. PMU established quantifiable and time bound targets for delivery of outputs by Executing Entities. Short-term technical support has been secured, where necessary, to alleviate the issue of limited human resources available to undertake project activities. Alternative operational arrangements to be instituted in at least one component, whereby direct payments will be made so as to minimize risk of delays to implementation due to length of chain, additional expenditure via interest charges and possibility of negative impacts on stakeholder relationships. The continued assessment of partner capacity by the PMU will ensure the ongoing development of capabilities.
Delay in settlement of claims by EE affecting stakeholder relations | Moderate | The PMU has convened meetings with the affected Execting Entities and provided assistance in reviewing and refining administrative processes to eliminate bottlenecks and improve payment processing timelines.
Risk Measures: Were there any risk mitigation measures employed during the current reporting period? If so, were risks reduced? If not, why were these risks not reduced?
Add any comments relevant to risk mitigation (word limit = 500)
Risk mitigation measures employed all contributed to reducing relevant risks. Meaures underaken included: Work plans/ budgets developed and approved prior to undertaking activities for respective components. Regular meetings and reporting systems instituted and feedback provided to facilitate improvements Continuing involvement of key local and national stakeholders to enhance transparency and secure buy-in Engagement of short-term support to reduce implementation delays and achieve planned outputs PMU convened meetings with senior management of Executing Entities to ensure high-level involvement in resolving implementation challenges Regarding the construction of the breakwater structures, a local monitoring committee is to be established so that the community will have direct input throughout the process. It should be noted that, notwithstanding all attempts at engagement, a group of stakeholders in component 1 continue to oppose the breakwaters whilst insisting on beach nourishment. It is widely accepted that Negril is an important contributor both to the tourism industry and the Jamaican economy as a whole. Therefore, there is an undertaking to continue to work with all the partners through ongoing consultations which are critical to the process of adaptive management and increased stakeholder ownership/buy-in. All future decisions, including contingency plans, are contingent on the decision and recommendations of the NRCA, the country’s national authority with responsibility for the effective management of the physical environment so as to ensure the conservation, protection and proper use of Jamaica’s natural resources. The PMU will continue to monitor existing risks, identify new ones and implement mitigating measures. Footnote: The NIE was informed in early December that the NRCA has approved the permits for the construction of the breakwaters. Stakeholders have been informed via letters as well as public notices disseminated via local media. The NIE has sinced convened meetings with the respective Executing Entities to devise a plan for effective multi-stakeholder (tourism and private sector, municipal, NGO, central government, public) engagement during this phase.

## Rating
RATING ON IMPLEMENTATION PROGRESS
For rating definitions please see bottom of page.
| Progress on Key Milestones |  | Expected Progress |  | Progress to Date | Rating
Project Manager/Coordinator: | Workshops/Capacity Building |  | Gender Workshop completed with input of all Executing Entities |  | Two (2) workshops aimed at mainstreaming gender into project implementation were organised by the PMU during the reporting period. The sessions were held in collaboration with the Institute of Gender and Development Studies, University of the West Indies, Mona and were attended by representatives of all Executing Entities and partner agencies. Based on feedback from participants, the workshops achieved the stated objectives of enhancing gender awareness and identifying practical ways to integrate gender considerations in climate change adaptation initiatives. | HS
| Stakeholders Consultation |  | National Stakeholders Consultation held |  | Due to schedule conflicts with other key activities of several executing partners, the National Stakeholders Consultation (NSC) had to be rescheduled to November 20, 2014. The event was staged in Mandeville, Manchester - one of the target parishes and saw the attendance/participation of more than 100 stakeholders from seven parishes. The NSC is part of the overall efforts of raising awareness of the importance of climate change adaptation and fostering a sense of ownership among beneficiaries. The Director General of the NIE, Programme Steering Committee members as well as the Custos Rotolorum of Manchester were among those in attendance. | HS
| Governance and Oversight guide Programme Implementation |  | Governance and Oversight Framework established and functioning effectively |  | The Programme Steering Committee (PSC)continued to serve as the main mechanism for the provision of technical advice and oversight during the period under review. The PSC is comprised of members from a cross-section of stakeholders with technical interest in and knowledge of natural hazards, risk and climate change issues, including community representatives, relevant government Ministries, Departments and Agencies, the Private Sector Organization of Jamaica, academia, and NGO partners. There were four (4) PSC meetings convened in 2014 -- three (3) regular and one (1) extra-ordinary. The PSC has effectively assisted with resolving strategic level issues and addressing risks that have the potential to adversely affect the implementation of the programme. Monitoring visits were made by the PMU to all Executing Entities to gain a better understanding of partners operating environment and verify reported expenditure. and confirm that work and results conform to requirements. Executing Entities reports were reviewed and feedback provided with recommendations for improvement, where necessary. Field visits were undertaken by the PMU to meet with existing/proposed beneficiaries in target communities (Manchester, Yallahs, Morant Bay, and Negril/ PGR). The PMU continued the series of regular team meetings (with 6 such meetings during the reporting period) with executing partners to support the implementation process. The meetings provided a platform for knowledge sharing while fostering inter and intra-agency collaboration and improving team building by highlighting how the different components interact with and support each other. This mechanism also serves as a framework for systematically identifying and helping to proactively resolve operational bottlenecks. | HS
| External Monitoring |  | Monitoring Missions Facilitated |  | In 2014 the PMU coordinated and facilitated two external monitoring visits: 1. Prof. Akihasa Mori - (February 24 -28, 2014) from Kyoto University who was conducting research on the effectiveness of the direct access modality and its effectiveness in enhancing local ownership. 2. Two representatives of the Adaptation Fund Secretariat (June/July 2014) who were conducting a portfolio monitoring visit to collect lessons learned from the direct access experience at different levels. In both cases meetings were held with beneficiaries /key stakeholders and field visits made to programme sites. | S
| Awareness Raising and Visibility |  | Engagement of Consultant and Implementation of Communication Plan |  | The GOJ/AFP partnered with the Inter- American Institute for Cooperation on Agriculture (IICA) in hosting a three day regional workshop “Mainstreaming Climate Change Adaption into Plans, Policies Programmes and Strategies held on April 7-9, 2014. The Programme Manager participated in Panos’ workshop and launch of regional climate change hub in Montego Bay (June). PM also attended meeting of select Negril stakeholders (hoteliers) convened by Panos and made presentation on overview of GOJ/AFP. The Programme was featured in the PIOJ’s internal publication Green Team Newsletter Volume 6 # 2- August 2014. The PM also participated in/supported NEPA’s display at Denbigh 2014 Agricultural Show. There were several postings on PIOJ Facebook page highlighting the programme. | MS
[5 empty] | Overall Rating | S
Please Provide the Name and Contact information of person(s) reponsible for completeling the Rating section
| Name: | Shelia McDonald-Miller
| Email: | smmiller@pioj.gov.jm
Please justify your rating. Outline the positive and negative progress made by the project since it started. Provide specific recommendations for next steps. . (word limit=500)
There were significant issues in collaboration between programme partners which have improved through the intervention of the NIE. Progress has been made with communities engaged in implementing activities that improve resilience. This has been a challenging year, with a number of issues to be tackled but looking at what has been done and the commitment of the partners on where the focus must be in year 3. There is need to rephase certain activities from year 2 to year 3 to reflect the continuing schedule lag
| Progress on Key Milestones |  | Expected Progress |  | Progress to Date | Rating
Implementing Entity | Component 1 Increased climate resilience of the Negril coastline |  | Completion of Environmental Impact Assessment. Procurement of consultants and contractor mobilization for construction of breakwaters; environmental monitoring of licenses and permits. |  | Modelling studies were done in December 2013 at the Centre of Applied Coastal Research Ocean Laboratory at the University of Delaware, USA. Based on performance and testing, the 2 proposed breakwaters have been designed to withstand event with 100-year return period The Environmental Impact Assessment (EIA) of the breakwater structures to be built in Negril was published and opened for comments by the public. It involved a survey of 355 stakeholders and 4 focal group meetings in Negril between January-March 2014. Public presentation was convened on July 29, 2014. Following this, the public had a period of 30 days within which to make additional submissions. Up to October 31, 2014 a decision on whether to grant the beach license to facilitate the construction of the breakwaters had not been issued; since May 2014 there has been considerable and sustained opposition to the proposed intervention by a group of hoteliers. Footnote: The NRCA has since approved the licences to allow for construction of the breakwaters | MS
| Component 2 Enhanced climate resilience of the agricultural sector through improved water and land management in select communities |  | Micro Dam established; land husbandry curriculum developed; demonstration plots established and farmers have access to increased irrigation water and producion schemes |  | Due to land tenure and geo-technical issues and following several attempts to identify potential alternative location sites, there has been a scope change in relation to the establishment of a micro-dam in N. Manchester. Alternatively, several water retention structures will be constructed/rehabilitated to serve the needs of the communities. A concrete tank with a capacity of 16000 gallons has been rehabilitated in Bushy Park, Manchester and supplies 10 to 15 drip irrigation systems via smaller water tanks. All five demonstration plots for land husbandry practices have been substantially established and farmers have started to be trained in diversion and hillside ditches techniques, continuous mounds, building of ballasted water ways and other soil conservation techniques. Approximately 380 farmers successfully completed training in skills, knowledge and techniques on sustainable land husbandry practices. The final draft of the curriculum has been produced by two officers of the RADA and should be finalized shortly. Eight (8) groups have been mobilized for establishment of WUGs towards sustainable management of water resources. | MS
| Component 3 Improved institutional and local capacity for sustainable management of natural resources and in disaster risk reduction in the targeted vulnerable areas. Raising awareness for behaviour modification |  | Engagement of Training Officer and Development of Training Plan; Increase in number of residents who accept that climate risks are relevant to their community. Procurement of Consultant for Storm Surge Modelling; completion of draft adaptation plans |  | The training officer has been engaged and training plan developed. Training activities have been beset by low community support and participation, as well as low disaster risk perception by residents. These challenges have necessitated the need for the development of a community mobilization and visibility plan (completed) to include the more direct engagement of community organizations and the full operationalization of the GOJ/AFP Communication Strategy and Action Plan in 2015. A consulting firm was engaged to develop storm surge modelling and sea level rise scenarios. Data collection via bathymetric and topographic (aerial) surveys was done and wave overtopping analysis conducted. The report was completed and the findings shared with Parish Disaster Committees and 2 Parish Councils (Westmoreland/Hanover). In relation to the risk atlas, asses mapping has been completed with ~4700 assets mapped using GPS; digitization of 5 community hazard maps has also been completed and the validation process is pending. There were some procurement delays in engaging the storm surge modelling consultant as well as delays in obtaining up-to-date imagery for Negril which impacted the completion of the vulnerability assessment and commencement of work on the adaptation plans. | MS
[5 empty] | Overall Rating | MS
Please Provide the Name and Contact information of person(s) reponsible for completeling the Rating section
| Name: | Shelia McDonald-Miller
| Email: | smmiller@pioj.gov.jm
| Progress on Key Milestones |  | Expected Progress |  | Progress to Date | Rating
Other
[5 empty] | Overall Rating | MS
Please Provide the Name and Contact information of person(s) reponsible for completeling the Rating section
Name:
Email:
| Please justify your rating and address the following points: 1. Indicate trends, both positive and negative, in achievement of outcomes as per the project indicators. 2. Detail critical risks that have affected progress. 3. Outline response to MTR undertaken this reporting period. 4. Outline action plan to address projects with a rating of HU, U or MU. Please keep your input to 1200 words |  | For the milestones, the rating of MS was given due to the slow pace of implementation over the last 2 years. This can be explained by factors such as changes in key management personnel in partner agencies since inception; inter-agency/intra component kinks; inadequate understanding of the project by some stakeholders and limited buy-in of stakeholders in a critical component. In some areas, procurement was stymied due to receipt of non-responsive bids which necessitated a re-tendering exercise and led to more schedule delays. In Component 1 there were significant delays as much care had to be taken in ensuring that: the EIA process was comprehensive; there was adherence to the relevant environmental guidelines, and stakeholders had every opportunity to voice their reservations or objections. With the NRCA approval now in place, the way is cleared for procurement of contractors to begin the construction process in 2015 The PIOJ continues to work with our partners to ensure that the overall direction of the programme remains in line with the agreed targets. Dialogue with the respective stakeholders to identify alternative solutions is a regular feature of our interaction; establishing synergistic relationships with other projects while leveraging existing resources has helped to improve the value-added. The governance structure remains strong and there is buy-in at the political level. Despite the overall rating of MS, the trend of progress certainly demonstrates improvement overtime. For example, cumulative disbursement as at October 31, 2014 is US$893,016. This means that the expenditure over the last 12 months, while relatively low, has improved by over 70% in the current reporting period when compared to the preceding year. It is very likely that the NIE will have to seek an extension of the project in order to achieve all intended outcomes and objectives; the exact duration will be determined in consultation with executing partners in the first quarter of 2015 and AF approval sought.
Rating Definitions
|  |  | Highly Satisfactory (HS) | Project actions/activities planned for current reporting period are progressing on track or exceeding expectations to acheive all major outcomes/outputs for given reporting period, without major shortcomings. The project can be presented as “good practice”.
|  |  | Satisfactory (S) | Project actions/activities planned for current reporting period are progressing on track to achieve most of its major outcomes/outputs with only minor shortcomings.
|  |  | Marginally Satisfactory (MS) | Project actions/activities planned for current reporting period are progressing on track to achieve most major relevant outcomes/outputs, but with either significant shortcomings or modest overall relevance.
|  |  | Marginally Unsatisfactory (MU) | Project actions/activities planned for current reporting period are not progressing on track to achieve major outcomes/outputs with major shortcomings or is expected to achieve only some of its major outcomes/outputs.
|  |  | Unsatisfactory (U) | Project actions/activities planned for current reporting period are not progressing on track to achieve most of its major outcomes/outputs.
|  |  | Highly Unsatisfactory (U) | Project actions/activities planned for current reporting period are not on track and shows that it is failing to achieve, and is not expected to achieve, any of its outcomes/outputs.

## Project Indicators
PROJECT INDICATORS
Please provide all indicators being tracked for the project as outlined in the project document
Type of Indicator (indicators towards Objectives, Outcomes, etc…)
Type of Indicator | Indicator | Baseline | Progress since inception | Target for Project End
| Length (m) of breakwater installed | No breakwater | Engage Pre-Contstruction Consultants - Drawings, design report and modelling studies completed - Verification and approval of source material and Material assessment report completed Environmental Impact Assessment completed Natural Resources Valuation completed Several community sensitization/ consultations held Procurement activities in progress for Enforcement Officers to carry out monitoring activities during the construction phase | 990m of breakwater installed
| Number of micro dams constructed in North Manchester | 0 water catchment facility in North Manchester | Several sites in North Manchester visited and evaluated. Land tenure and geo-technical issues have necessitated a review of the proposed output. Based on feasibility assessment, the decision has been taken to replace micro dam with alternative water retention structures and water harvesting systems | Scope change - several water harvesting systems and irrigation infrastructure implemented
| number of irrigation and production schemes established in: St Thomas, St Ann, Trelawny, St Catherine, Clarendon, Manchester, St Mary | 0 irrigation and production schemes in the 21 targeted communities in 6 project parishes | Nineteen (19) of the 24 P & P schemes for 2014 have been approved and disbursed. Forty-three (43) communities identified and shortlisted; 6 Farmers groups were mobilised for establishment of Irrigation and Production Schemes | 45 schemes installed and operational in 15 communities serving over 750 male and female farmers
| Number of rainwater harvesting and gravity drip irrigation systems installed in: St Thomas, St Ann, Trelawny, St Catherine, St Mary, Clarendon | Inadequate access to irrigation facilities in selected communities in 6 project parishes | Design of irrigation systems completed and necessary permits and/or waivers were secured. Safety gears and administrative equipment have been procured. 30 water storage tanks (1000 gallons) have been procured. Eight (8) systems using roof catchment and tanks were installed during the reporting period. Two (2) rain water harvesting systems using tanks and catchment were rehabilitated. Nineteen (19) ¼ acre gravity drip irrigation systems have been installed | 30 rainwater harvesting; 20 ponds and springs 60 gravity drip irrigation systems installed and operational and serving 40 male and 20 female farmers directly
| Soil conservation and land husbandry infrastructure in Upper Rio Minho Watershed | Extensive soil erosion due to hillside farming, removal of forest cover and poor farming practices | Five (5) extension areas selected and 5 community sensitization sessions held with stakeholders. The following results were achieved during the reporting period: Hillside Ditch (M) 5669 Individual Basin (#) 2002 Live Barrier (M) 860 Continuous Mound (M) 5413* Water ways (M) 110 Cover crop (H) 0.6 Fruit Forest (H) 0.9 Timber Forest (H) 0 Land Preparation (H) 2.94 Ginger planted (H) 2.52 Yam planted (H) 1.05 *includes both demo plots and grants sub-component | App 18000m diversion /hillside ditches, 24600 individual basins, 3000m of waterway, 1200m continuous mound , 705 check dam/drop structures installed, 18000 m pineapple (vegetable barrier) and 13ha fruit forest and 15ha timber planted impacting 5 Extension Areas
| Number of climate-smart farmer field schools established in select communities | No climate-smart field schools in select communities | Preliminary consultations held with land owners to validate participation with the project 4 farmers field schools have been mobilised for the commencement of training during the 2014 Fall onion season; Approximately 1000 (26% female/74% male) farmers have been trained in skills, knowledge and techniques for sustainable practices and land husbandry | Seven climate-smart farmer field schools established and 90% farmers (male/female) trained to adopt climate smart agriculture practices
| Number of demonstration plots established in the Upper Rio Minho Watershed | Targeted communities do not have demonstration plots in place | The target for 2014 to establish at least 3 demonstration plots has been exceeded as four (4) demonstration plots are 85-90% complete whilst the 5th plot is approximate 70 % complete. The communities are Crooked River, Thompson Town, James Hill and Kellits. Two (2) workshops were held in Thompson Town and Crooked River. A land husbandry specialist has been assigned to the project - procurement plan and technical specifications for demonstration plots have been reviewed and certified by the technical officers. | Five demonstration plots established imparting skills, knowledge and techniques to 1510 farmers (male, female) who are adopting sustainable practices
| Number of water user groups established | 0 WUG in targeted communities | Eight (8) groups have been mobilised for the establishment or rehabilitation of WUG | 15 WUGs established and operational towards sustainable management of water resource
| Number and volume of awareness raising materials (audio visual) targeted to specific age groups, occupation groups, sex and persons with disability | No area specific public education programme | Communication plan and strategy developed spearheaded by the PMU in collaboration with executing partners Advertorial placed in two major daily newspapers to provide general information on the programme; FAQs and brochure prepared and disseminated to raise awareness; Fact sheets on all 3 components developed and shared at stakeholder meetings | Full roll out of awareness building programme; 70% of residents sensitized.
| Evidence of documentation and dissemination of best practices | No evidence of documented best practices in project areas | Best practices implemented and documented (from prior initiatives) include the Agro Eco-system Analysis whereby farmers are trained to analyse their farms to determine action threshold before application of integrated pest management strategies. This information is currently disseminated through the RADA network and used by farmers within and outsideof the project areas. | Information made available through virtual networks, RADA, parish libraries, College of Agriculture Science and Education, Jamaica Agriculture Society, Fishermen’s Cooperative, 4H Clubs and schools
| Number of (targeted) training programmes for local entities in DRR, natural resource management | Limited training in DRR for local entities in DRR and natural resource management, except the few hotels that have green certifications. Limited exposure to training with specific focus on climate change | Training Officer employed and community mobilization plan developed KAP Survey completed Training Plan for DRR developed Six (6) sensitization/training sessions conducted in four target communities. Approximately 120 persons benefitting to date The community hazard mapping process is a critical output which will support training component of the project by providing information about the respective communities. Information about the particular communities may include areas likely to be affected by various hazards and location of vulnerable elements such as population, buildings, infrastructure, and livelihoods. Additionally these maps will help to minimize potential loss of physical assets, human resources, and environmental capital. | Training programmes targeted at fishers (mostly male), male and female youth , micro and small business owners and other groups completed
| Guidelines and standards for beach restoration, shoreline protection for Negril | No specific technical guidelines for Negril | 30% completed. Maps and other outputs recently completed by ODPEM will be used by NEPA for preparation of guidelines for beach restoration and shoreline protection. | One set of guidelines and standards finalized
| Number of climate risk atlas for storm surge, sea level rise (specific for Negril) | 0 risk atlas information for storm surge and sea-level rise for Negril | Digitization of 5 Hazard Maps completed. Data collection (topographic aerial survey) completed. Report completed on storm surge modelling and sea level rise - a crucial input to the development of the risk atlas and adaptation plans | Risk Atlas completed
| Number of adaptation plans for vulnerable sections of Negril | 0 Plan |  | One adaptation plan completed and in use

## Lessons Learned
QUALITATIVE MEASURES and LESSONS LEARNED
Please complete the following section every reporting period
Implementation and Adaptive Management | Response
What implementation issues/lessons, either positive or negative, affected progress? | Key lessons include: - Nature and complexity (environmental dynamics) requires a number of scientific studies to be done and this has implications for both cost and time. - The need to address perceived gaps in consultation process on an ongoing basis by strengthening the mechanisms for the engagement of all stakeholders; - The importance of understanding the dynamics of various groups of the community and their influences - The need for clear distillation of the effects of climate change on livelihoods/ businesses before implementation of planned activities can begin successfully. The programme approach is to build partnerships with key national institutions (both State and NGO) in order to facilitate progress towards delivery of outputs and shared objectives. Integration of the Programme Management Team across different agencies via regular team sessions has allowed for strengthening relationships among government institutions as well as providing a platform for coordinated implementation and capacity development. The effective functioning of the PSC allows for transparency and good governance of the implementation process. Adequacy of technical capacity, lack of dedicated resources and competing priorities within Executing Entities continued to stymie progress of implementation in year 2, although to a lesser extent than in the preceding year.
Were there any delays in implementation? If so, include any causes of delays. What measures have been taken to reduce delays? | Negative stakeholder perception of some partners and a conflation of wide range of prior community issues with the project manifested in stakeholder opposition re proposed intervention in Component 1. This slowed the rate of progress as significant time and effort had to be spent addressing the concerns and allaying the fears expressed by the stakeholders. Construction of the breakwaters did not begin as planned due to several factors, inclcuding: - Delay in procurement process of environmental monitoring engineer involving NCC - Delay in completing EIA process - Length of time by the NRCA to issue decision on permit to construct The comprehensive EIA process and public consultations have been completed. Once a favourable decision is issued by the NRCA, the next steps (construction phase) will begin with care being taken to ensure close collaboration of the community during and after construction. A monitoring partnership is also to be established through the formation of a Local Monitoring Committee that will include public and private sector interests. There were delays in establishing the micro dam due to the infeasibility of geo-physical / geo-technical characteristics of proposed site; there were also issues with land tenure. A scope change request was made by the respective Executing Entity to substitute other measures which would address the vulnerabilities identified in the programme design phase. The request was favourably considered by the NIE. There was low operative execution in relation to the production and productivity schemes as well as the land husbandry curriculum due to competing priorities and lack of dedicated human resources. Measures to address this included short term staff and reallocation of resources. The prolonged dry spell slowed the implementation of the agro-forestry component of the demonstration plots. Procurement delays were experienced in the design and installation of rainwater harvesting system using ponds/ tanks due to non-responsive bids; this necessitated a re-tendering exercise. Recommendations were made to secure the services of a Procurement Specialist on a short term basis to expedite the procurement activities. The training sub-component experienced delays due to procurement challenges and changes in key personnel; there was also slow uptake by the target communities due to low disaster risk perception. Measures taken include provision of direct procurement support by the PMU, and discussions among partner agencies with recommendations for more effective mobilization initiatives, including partnering with other agencies (eg. Red Cross) for better synergistic effect. Generally, there was more direct and deliberate interactions between senior management (eg. Permanent Secretaries, CEOs) of affected entities and the PMU. The pace of implementation has been showing slow but steady improvements. The PMU will continue to provide effective support and follow-up at different levels.
Describe any changes undertaken to improve results on the ground or any changes made to project outputs (i.e. changes to project design) | The PMU has entered into discussions with the Climate Change Ministry (MWLECC) and agreement has been reached to sign a MOU between the NIE and MWLECC to facilitate requirements relating to the FIDIC rule governing construction works and improve inter-agency coordination under component 1. Challenges regarding land tenure, access, geo-physical characteristcs and sufficiency of budgetary allocations have necessitated a change of scope in relation to the micro dam under component 2. A technical team of the Executing Entity (MOAF) met with NIE to discuss the scope change request and review alternative outputs to address the vulnerabilities faced by the affected communities. Due to delays in the procurement processes there were several iterations of target dates and sequencing of severable deliverables in the workplans of executing entities. In order to improve results on the ground the NIE (i) provided direct procurement suppport (review of ToRs, advertisement, shortlisting, etc.) to executing partners; (ii) made representation to obtain needed resources (imagery from Forestry Department) to facilitate completion of asset mapping exercise; and (iii) approved the engagement of short term technical assistance to supplement capacity of partners. Additionally, there were special staff assignments within agencies (MOAF/RADA) to improve the rate of progress of the land husbandry curriculum.
How have gender considerations been taken into consideration during the reporting period? What have been the lessons learned as a consequence of inclusion of such considerations on project performance or impacts? | The NIE hosted two workshops (March and May 2014) on mainstreaming gender into project implementation. The objective of the workshops was to assist participants to gain a better understanding of the importance of addressing gender issues that impact climate change adaptation. The sessions were held in collaboration with the Institute of Gender and Development Studies, University of the West Indies, Mona. The NIE also has gender committe/focal point. In terms of gender, the GOJ/AFP targets benefits for both men and women. Both will benefit from community interventions but because women bear a greater level of the burden associated with natural disasters, they are likely to be more positively impacted by the work being done with respect to soil and land husbandry which will contribute to improved resilience, especially in upland communities, and reduce downstream flooding. Similarly, women will be the primary and most direct beneficiaries of the water harvesting and storage interventions. In rural Jamaica, women and children have primary responsibility for fetching water both for domestic and farming purposes, thus increasing their exposure to unsafe water and associated health issues. Ongoing activities such as workshops, stakeholder sensitization sessions, development of the communications strategy etc. were planned and executed on select days and during hours which guarantee greater participation of both men and women from the target communities. As a result, both men and women have been actively involved in programme activities. The composition of the PSC is an excellent example of gender equality as both men and women occupy decision-making positions.
Please complete the following section at mid-term and project completion
Lessons for Adaptation | Response
Climate Resilience Measures
What have been the lessons learned, both positive and negative, in implementing climate adaptation measures that would be relevant to the design and implementation of future projects/programmes for enhanced resilience to climate change? | An important lesson is the need to broaden stakeholder involvement ( segmenting and differentiating groups and related messages) on a continuing basis to prevent misconceptions mushrooming into dissent. It is also critical to establish relationship with community influencers/ gatekeepers/ local champions to enhance local ownership
What is the potential for the climate resilience measures undertaken by the project/programme to be replicated and scaled up both within and outside the project area? | A water storage and drip irrigation system was established in Bushy Park, Manchester. The tank supplied several small reservoirs which were in turn connected to drip irrigation systems. This is a good example of partnership as the costs of the equipment were borne by the programme, however the beneficiaries were responsible for building the base of the tanks. The initiative has helped by extending water availability to the area and to this category of farmers selected from among the most vulnerable. It will also serve as demonstration which can be replicated by other farmers both within and outside the project area in order to improve productivity in drought-prone areas
Concrete Adaptation Interventions
What have been the lessons learned, both positive and negative, in implementing concrete adaptation interventions that would be relevant to the design and implementation of future projects/programmes implementing concrete adaptation interventions? | In the future, a Cost Benefit Analysis (CBA) and Natural Resources Valuation (NRV) could be used in the process of prioritising adaptation measures from a list of possible adaptation options to improve stakeholder confidence and buy-in
What is the potential for the concrete adaptation interventions undertaken by the project/programme to be replicated and scaled up both within and outside the project area? | Development of land husbandry curriculum will allow for replication outside of the programme target areas, as well as application of the farmer field school technology. When developed, the risk atlas, adaptation plans and guidelines can be used by other coastal communities.
Community/National Impact
What would you consider to be the most successful aspects for the target communities? | Component 2: involvement in import-substitution programme (onions and irish potato) which helps to save foreign exchange for the island as well as promote food security. Livelihoods have been positively impacted by, inter alia, the establishment of demonstration plots and training in land husbandry techniques. In Thompson Town, Clarendon, for example, twenty-five (25) farmers including several women who are heads of households have pooled their resources to effectively manage the community demonstration plot for skills-building and income generation.
What measures are/have been put in place to ensure sustainability of the project/program results? | WUGs for sustainable use of water resources; linkages/partnerships with NGOs and other community organisations for greater synergy; education and training to enhance personal understanding and responsibility; direct link with national priorities in Vision 2030
What measures are being/could have been put in place to improve project/program results? | Measures being put in place include changes to MOU between NEPA and the NIE; new MOUs will be entered into between (a) NWA and the MWLECC and (b) MWLECC and PIOJ to facilitate the engagement of a Contractor under FIDDIC rules and make a clear distinction between regulator and contractor. To improve programme results, meetings were convened by the PMU with heads/senior management personnel of the Executing Entities to make them aware of the continuing delays in execution and solicit their commitment to supporting the GOJ/AFP. There is room for improvement/continuity in visibility and communications for awareness building and to enhance stakeholder buy-in
Knowledge Management
How has existing information/data/knowledge been used to inform project development and implementation? What kinds of information/data/knowledge were used? | In the development of the GOJ/AFP the NIE utilized the specific experience of several partners such as the Negril Coral Reef Preservation Society, Panos Caribbean, The Hazard Risk Reduction and Climate Change Adaptation Thematic Working Group, hoteliers, academics and public sector agencies. During implementation, expertise in coastal simulations by the University of Delaware has been employed, and Environmental Impact Assessment study was commissioned and carried out. The EIA study and Natural Resource Valuation (NRV) were prepared by independent consultants and provided objective bases for assessing the proposed interventions agains other alternatives. Communities/groups under component 2 were initially identified by the RADA network of extension officers in accordance with the Ministry of Agriculture and Fisheries' (MOAF) plans for food security. During implementation MOAF has continued to utilize information on food security and priority crops to inform the nature and timing of interventions in the target communities. The FFS concept was chosen to provide crop training in a group based, practical setting using the demonstration plots and other fields to improve land and water management. This approach to training helps to maximise the limited resources and the ‘learning by doing’ approach enhances the knowledge transfer for sustainable agricultural practices. Similarly, WUGs bring communities/farmers together to better manage the use of an important, but often limited resource (water). The WUG approach helps to build social capital formation and promotes inclusiveness which facilitates sustainability.
If learning objectives have been established, have they been met? Please describe.
Describe any difficulties there have been in accessing or retrieving existing information (data or knowledge) that is relevant to the project. Please provide suggestions for improving access to the relevant data.
Has the identification of learning objectives contributed to the outcomes of the project? In what ways have they contributed?

## Results Tracker
Results Tracker for Adaptation Fund (AF) Projects
Goal: Assist developing-country Parties to the Kyoto Protocol that are particularly vulnerable to the adverse effects of climate change in meeting the costs of concrete adaptation projects and programmes in order to implement climate-resilient measures. Impact: Increased resiliency at the community, national, and regional levels to climate variability and change.
Important: Please read the following Results Framework and Baseline Guidance (also posted on the Adaptation Fund website) before entering your data
Link: http://www.adaptation-fund.org/sites/default/files/Results%20Framework%20and%20Baseline%20Guidance%20final.pdf
Please select the relevant Fund level Outcome and Output indicators that allign with the project objectives and outcomes
OBJECTIVE 1
Fund Outcome | Please select from dropdown menu below | Fund Outcome Indicator | Please select from dropdown menu below | Target at CEO Endorsement (see Units in next sheet) | Baseline (see Units in next sheet) | Mid-term Results | Terminal Results
Outcome 1: Reduced exposure at national level to climate-related hazards and threats Outcome 2: Strengthened institutional capacity to reduce risks associated with climate-induced socioeconomic and environmental losses Outcome 3: Strengthened awareness and ownership of adaptation and climate risk reduction processes at local level Outcome 4: Increased adaptive capacity within relevant development and natural resource sectors Outcome 5: Increased ecosystem resilience in response to climate change and variability-induced stress Outcome 6: Diversified and strengthened livelihoods and sources of income for vulnerable people in targeted areas Outcome 7: Improved policies and regulations that promote and enforce resilience measures |  | 1. Relevant threat and hazard information generated and disseminated to stakeholders on a timely basis 2.1. No. and type of targeted institutions with increased capacity to minimize exposure to climate variability risks 2.2. Number of people with reduced risk to extreme weather events 3.1. Percentage of targeted population aware of predicted adverse impacts of climate change, and of appropriate responses 3.2. Modification in behavior of targeted population 4.1. Development sectors' services responsive to evolving needs from changing and variable climate 4.2. Physical infrastructure improved to withstand climate change and variability-induced stress 5. Ecosystem services and natural assets maintained or improved under climate change and variability-induced stress 6.1. Percentage of households and communities having more secure (increased) access to livelihood assets 6.2. Percentage of targeted population with sustained climate-resilient livelihoods 7. Climate change priorities are integrated into national development strategy
Fund Output | Please select from dropdown menu below | Fund Output Indicator | Please select from dropdown menu below | Target at CEO Endorsement (see Units in next sheet) | Baseline (see Units in next sheet) | Mid-term Results | Terminal Results
Output 1: Risk and vulnerability assessments conducted and updated at a national level Output 2.1: Strengthened capacity of national and regional centres and networks to respond rapidly to extreme weather events Output 2.2: Targeted population groups covered by adequate risk reduction systems Output 3: Targeted population groups participating in adaptation and risk reduction awareness activities Output 4: Vulnerable physical, natural, and social assets strengthened in response to climate change impacts, including variability Output 5: Vulnerable physical, natural, and social assets strengthened in response to climate change impacts, including variability Output 6: Targeted individual and community livelihood strategies strengthened in relation to climate change impacts, including variability Output 7: Improved integration of climate-resilience strategies into country development plans |  | 1.1. No. and type of projects that conduct and update risk and vulnerability assessments 1.2. Development of early warning systems 2.1.1. No. of staff trained to respond to, and mitigate impacts of, climate-related events 2.1.2. Capacity of staff to respond to, and mitigate impacts of, climate-related events from targeted institutions increased 2.2.1. Percentage of population covered by adequate risk-reduction systems 2.2.2. No. of people affected by climate variability 3.1 No. and type of risk reduction actions or strategies introduced at local level 3.2 No. of news outlets in the local press and media that have covered the topic 4.1. No. and type of health or social infrastructure developed or modified to respond to new conditions resulting from climate variability and change (by type) 4. 2. No. of physical assets strengthened or constructed to withstand conditions resulting from climate variability and change (by asset types) 5. No. and type of natural resource assets created, maintained or improved to withstand conditions resulting from climate variability and change (by type of assets) 6.1. No. and type of adaptation assets (physical as well as knowledge) created in support of individualor community-livelihood strategies 6.2. Type of income sources for households generated under climate change scenario 7.1. No., type, and sector of policies introduced or adjusted to address climate change risks 7.2. No. or targeted development strategies with incorporated climate change priorities enforced
OBJECTIVE 2
Fund Outcome | Please select from dropdown menu below | Fund Outcome Indicator | Please select from dropdown menu below | Target at CEO Endorsement | Baseline | Mid-term Results | Terminal Results
Outcome 1: Reduced exposure at national level to climate-related hazards and threats Outcome 2: Strengthened institutional capacity to reduce risks associated with climate-induced socioeconomic and environmental losses Outcome 3: Strengthened awareness and ownership of adaptation and climate risk reduction processes at local level Outcome 4: Increased adaptive capacity within relevant development and natural resource sectors Outcome 5: Increased ecosystem resilience in response to climate change and variability-induced stress Outcome 6: Diversified and strengthened livelihoods and sources of income for vulnerable people in targeted areas Outcome 7: Improved policies and regulations that promote and enforce resilience measures |  | 1. Relevant threat and hazard information generated and disseminated to stakeholders on a timely basis 2.1. No. and type of targeted institutions with increased capacity to minimize exposure to climate variability risks 2.2. Number of people with reduced risk to extreme weather events 3.1. Percentage of targeted population aware of predicted adverse impacts of climate change, and of appropriate responses 3.2. Modification in behavior of targeted population 4.1. Development sectors' services responsive to evolving needs from changing and variable climate 4.2. Physical infrastructure improved to withstand climate change and variability-induced stress 5. Ecosystem services and natural assets maintained or improved under climate change and variability-induced stress 6.1. Percentage of households and communities having more secure (increased) access to livelihood assets 6.2. Percentage of targeted population with sustained climate-resilient livelihoods 7. Climate change priorities are integrated into national development strategy
Fund Output | Please select from dropdown menu below | Fund Output Indicator | Please select from dropdown menu below | Target at CEO Endorsement | Baseline | Mid-term Results | Terminal Results
Output 1: Risk and vulnerability assessments conducted and updated at a national level Output 2.1: Strengthened capacity of national and regional centres and networks to respond rapidly to extreme weather events Output 2.2: Targeted population groups covered by adequate risk reduction systems Output 3: Targeted population groups participating in adaptation and risk reduction awareness activities Output 4: Vulnerable physical, natural, and social assets strengthened in response to climate change impacts, including variability Output 5: Vulnerable physical, natural, and social assets strengthened in response to climate change impacts, including variability Output 6: Targeted individual and community livelihood strategies strengthened in relation to climate change impacts, including variability Output 7: Improved integration of climate-resilience strategies into country development plans |  | 1.1. No. and type of projects that conduct and update risk and vulnerability assessments 1.2. Development of early warning systems 2.1.1. No. of staff trained to respond to, and mitigate impacts of, climate-related events 2.1.2. Capacity of staff to respond to, and mitigate impacts of, climate-related events from targeted institutions increased 2.2.1. Percentage of population covered by adequate risk-reduction systems 2.2.2. No. of people affected by climate variability 3.1 No. and type of risk reduction actions or strategies introduced at local level 3.2 No. of news outlets in the local press and media that have covered the topic 4.1. No. and type of health or social infrastructure developed or modified to respond to new conditions resulting from climate variability and change (by type) 4. 2. No. of physical assets strengthened or constructed to withstand conditions resulting from climate variability and change (by asset types) 5. No. and type of natural resource assets created, maintained or improved to withstand conditions resulting from climate variability and change (by type of assets) 6.1. No. and type of adaptation assets (physical as well as knowledge) created in support of individualor community-livelihood strategies 6.2. Type of income sources for households generated under climate change scenario 7.1. No., type, and sector of policies introduced or adjusted to address climate change risks 7.2. No. or targeted development strategies with incorporated climate change priorities enforced
OBJECTIVE 3
Fund Outcome | Please select from dropdown menu below | Fund Outcome Indicator | Please select from dropdown menu below | Target at CEO Endorsement | Baseline | Mid-term Results | Terminal Results
Outcome 1: Reduced exposure at national level to climate-related hazards and threats Outcome 2: Strengthened institutional capacity to reduce risks associated with climate-induced socioeconomic and environmental losses Outcome 3: Strengthened awareness and ownership of adaptation and climate risk reduction processes at local level Outcome 4: Increased adaptive capacity within relevant development and natural resource sectors Outcome 5: Increased ecosystem resilience in response to climate change and variability-induced stress Outcome 6: Diversified and strengthened livelihoods and sources of income for vulnerable people in targeted areas Outcome 7: Improved policies and regulations that promote and enforce resilience measures |  | 1. Relevant threat and hazard information generated and disseminated to stakeholders on a timely basis 2.1. No. and type of targeted institutions with increased capacity to minimize exposure to climate variability risks 2.2. Number of people with reduced risk to extreme weather events 3.1. Percentage of targeted population aware of predicted adverse impacts of climate change, and of appropriate responses 3.2. Modification in behavior of targeted population 4.1. Development sectors' services responsive to evolving needs from changing and variable climate 4.2. Physical infrastructure improved to withstand climate change and variability-induced stress 5. Ecosystem services and natural assets maintained or improved under climate change and variability-induced stress 6.1. Percentage of households and communities having more secure (increased) access to livelihood assets 6.2. Percentage of targeted population with sustained climate-resilient livelihoods 7. Climate change priorities are integrated into national development strategy
Fund Output | Please select from dropdown menu below | Fund Output Indicator | Please select from dropdown menu below | Target at CEO Endorsement | Baseline | Mid-term Results | Terminal Results
Output 1: Risk and vulnerability assessments conducted and updated at a national level Output 2.1: Strengthened capacity of national and regional centres and networks to respond rapidly to extreme weather events Output 2.2: Targeted population groups covered by adequate risk reduction systems Output 3: Targeted population groups participating in adaptation and risk reduction awareness activities Output 4: Vulnerable physical, natural, and social assets strengthened in response to climate change impacts, including variability Output 5: Vulnerable physical, natural, and social assets strengthened in response to climate change impacts, including variability Output 6: Targeted individual and community livelihood strategies strengthened in relation to climate change impacts, including variability Output 7: Improved integration of climate-resilience strategies into country development plans |  | 1.1. No. and type of projects that conduct and update risk and vulnerability assessments 1.2. Development of early warning systems 2.1.1. No. of staff trained to respond to, and mitigate impacts of, climate-related events 2.1.2. Capacity of staff to respond to, and mitigate impacts of, climate-related events from targeted institutions increased 2.2.1. Percentage of population covered by adequate risk-reduction systems 2.2.2. No. of people affected by climate variability 3.1 No. and type of risk reduction actions or strategies introduced at local level 3.2 No. of news outlets in the local press and media that have covered the topic 4.1. No. and type of health or social infrastructure developed or modified to respond to new conditions resulting from climate variability and change (by type) 4. 2. No. of physical assets strengthened or constructed to withstand conditions resulting from climate variability and change (by asset types) 5. No. and type of natural resource assets created, maintained or improved to withstand conditions resulting from climate variability and change (by type of assets) 6.1. No. and type of adaptation assets (physical as well as knowledge) created in support of individualor community-livelihood strategies 6.2. Type of income sources for households generated under climate change scenario 7.1. No., type, and sector of policies introduced or adjusted to address climate change risks 7.2. No. or targeted development strategies with incorporated climate change priorities enforced
OBJECTIVE 4
Fund Outcome | Please select from dropdown menu below | Fund Outcome Indicator | Please select from dropdown menu below | Target at CEO Endorsement | Baseline | Mid-term Results | Terminal Results
Outcome 1: Reduced exposure at national level to climate-related hazards and threats Outcome 2: Strengthened institutional capacity to reduce risks associated with climate-induced socioeconomic and environmental losses Outcome 3: Strengthened awareness and ownership of adaptation and climate risk reduction processes at local level Outcome 4: Increased adaptive capacity within relevant development and natural resource sectors Outcome 5: Increased ecosystem resilience in response to climate change and variability-induced stress Outcome 6: Diversified and strengthened livelihoods and sources of income for vulnerable people in targeted areas Outcome 7: Improved policies and regulations that promote and enforce resilience measures |  | 1. Relevant threat and hazard information generated and disseminated to stakeholders on a timely basis 2.1. No. and type of targeted institutions with increased capacity to minimize exposure to climate variability risks 2.2. Number of people with reduced risk to extreme weather events 3.1. Percentage of targeted population aware of predicted adverse impacts of climate change, and of appropriate responses 3.2. Modification in behavior of targeted population 4.1. Development sectors' services responsive to evolving needs from changing and variable climate 4.2. Physical infrastructure improved to withstand climate change and variability-induced stress 5. Ecosystem services and natural assets maintained or improved under climate change and variability-induced stress 6.1. Percentage of households and communities having more secure (increased) access to livelihood assets 6.2. Percentage of targeted population with sustained climate-resilient livelihoods 7. Climate change priorities are integrated into national development strategy
Fund Output | Please select from dropdown menu below | Fund Output Indicator | Please select from dropdown menu below | Target at CEO Endorsement | Baseline | Mid-term Results | Terminal Results
Output 1: Risk and vulnerability assessments conducted and updated at a national level Output 2.1: Strengthened capacity of national and regional centres and networks to respond rapidly to extreme weather events Output 2.2: Targeted population groups covered by adequate risk reduction systems Output 3: Targeted population groups participating in adaptation and risk reduction awareness activities Output 4: Vulnerable physical, natural, and social assets strengthened in response to climate change impacts, including variability Output 5: Vulnerable physical, natural, and social assets strengthened in response to climate change impacts, including variability Output 6: Targeted individual and community livelihood strategies strengthened in relation to climate change impacts, including variability Output 7: Improved integration of climate-resilience strategies into country development plans |  | 1.1. No. and type of projects that conduct and update risk and vulnerability assessments 1.2. Development of early warning systems 2.1.1. No. of staff trained to respond to, and mitigate impacts of, climate-related events 2.1.2. Capacity of staff to respond to, and mitigate impacts of, climate-related events from targeted institutions increased 2.2.1. Percentage of population covered by adequate risk-reduction systems 2.2.2. No. of people affected by climate variability 3.1 No. and type of risk reduction actions or strategies introduced at local level 3.2 No. of news outlets in the local press and media that have covered the topic 4.1. No. and type of health or social infrastructure developed or modified to respond to new conditions resulting from climate variability and change (by type) 4. 2. No. of physical assets strengthened or constructed to withstand conditions resulting from climate variability and change (by asset types) 5. No. and type of natural resource assets created, maintained or improved to withstand conditions resulting from climate variability and change (by type of assets) 6.1. No. and type of adaptation assets (physical as well as knowledge) created in support of individualor community-livelihood strategies 6.2. Type of income sources for households generated under climate change scenario 7.1. No., type, and sector of policies introduced or adjusted to address climate change risks 7.2. No. or targeted development strategies with incorporated climate change priorities enforced

## Units for Indicators
Fund Outcome Indicator Units
1. Generation of relevant data, Stakeholders, and Timeliness 2.1. Include both qualitative and quantitative measures of capacity level within targeted institutions 2.2. Number (men and women and other vulnerable groups) 3.1. Use scale from 1 to 5: 5: Fully aware 4: Mostly aware 3: Partially aware 2: Partially not aware 1: Aware of neither predicted adverse impacts of climate change nor of appropriate responses 3.2. Use scale from 1 to 5: 5: All 4: Almost all 3: Half 2: Some 1: None 4.1. Summarize in an overall scale (1-5): 5: Highly responsive (All defined elements ) 4: Mostly responsive (Most defined elements) 3: Moderately responsive (Some defined elements) 2: Partially responsive (Lacks most elements) 1: Non responsive (Lacks all elements ) 4.2. Summarize in an overall scale (1-5): 5: Fully improved 4: Mostly Improved 3: Moderately improved 2: Somewhat improved 1: Not improved 5. Depends on the targeted natural asset: Biological (species): measure through changes in population numbers (dynamics, structure, etc.) Land: measure changes in hectares. Baseline data will be necessary to estimate the change. Supporting indicators baseline and target (as well as contextual information) are needed such as the following: Farmers adopting recommended technologies, Ha. of land improved, Average deforestation rate Etc. Use scale from 1 to 5. 5: Very effective (All elements are present) 4: Effective (Most elements are present) 3: Moderately effective (Some elements are present) 2: Partially effective (Most elements are not present) 1: Ineffective (No elements are present) 6.1. Summarize in an overall scale (1-5): 5: Very high improvement 4: High improvement 3: Moderate improvement 2: Limited improvement 1: No improvement 6.2. Household income by source of livelihood in project area (USD) prior and post project intervention 7. Summarize in an overall scale (1-5). 5: All (Fully integrated) 4: Most 3: Some 2: Most not integrated 1: None
Fund Output Indicator Units
1.1. Number, sector(s) and level(s) of projects or interventions in separate fields of monitoring plan 1.2. Number 2.1.1. Number of staff (male/female) of targeted institutions: a. Obtain baseline information: total number of staff from targeted institutions b. Define target 2.1.2. Number of staff (male/female) of targeted institutions: a. Obtain baseline information: total number of staff from targeted institutions b. Define target: needs to be defined by project proponents 2.2.1. Quantitative: Percentage (includes women – and other vulnerable groups – and men). Qualitative: Adequacy: include direct analysis of major areas; adequacy/effectiveness of systems or analysis of perceptions of populations and institutions. 2.2.2. Number (broken down by gender and, if possible, by vulnerable groups defined in the area of intervention) of people 3.1. Number and type (in separate columns) at local level. 3.2. Number 4.1. Number and type 4. 2. Number and type (entered in separate columns) 5. Number of interventions by type of natural asset and intervention 6.1. Number and type (in separate columns of monitoring plan) 6.2. Income sources per household; description of income source and number of households. 7.1. Number/Sector 7.2. Number; Effectiveness (see previous indicator) through enforcement level.