## Overview
Project Performance Report (PPR)
| Period of Report (Dates) | September 2016 - August 2017
| Project Title: | Enhancing Resilience of Communities to the Adverse effects of Climate Change on Food Security in Mauritania
Effects of Climate Change on Food Security in Mauritania
| Project Summary: | The Mauritania's Ministry of Environment and Sustainable Development and the United Nations World Food Programme initiated a four-year project to strengthen resilience and promote food security in 100 villages located in the Wilayas of Assaba, Brakna, Guidimakha, Gorgol, Hodh El Chergui, Hodh El Gharbi, Tagant and Trarza. The overall goal of the project aims to improve adaptation in the area of food security in Mauritania by assisting the government in improving technical services at the community level so that village residents, who will be most affected by climate change, can undertake their own analysis of climate change impacts and prepare detailed adaptation plans – including harmonized plans for livestock, land and water management and the overall use of natural resources. The project will also promote climate resilience by protecting threatened resources, such as dunes, community fuel wood forests, and water sources. Finally, villages will be encouraged to explore ways to diversify the sources of livelihood and receive training, coaching, and asset investments to do so. The project includes three components: Component 1: Support technical services and the communities they serve to better understand climate risks, their impacts on resources and food security; and facilitate decentralized and participatory adaptation planning. Component 2: Design and implement concrete adaptation measures identified through community adaptation planning that aim to combat desertification and land degradation. Component 3: Design and implement concrete adaptation measures identified through community adaptation planning that aim to diversify and strengthen the livelihoods of the most vulnerable population.
|  |  | Countries | Project Type: |  | GEF Focal Area: | GEF 4 Focal Areas | GEF 2 / 3 Operational Programme: | Overall Rating of the project in the evaluation by the project evaluator: | GEF-4 Focal Area Strategic Program: | GEF-3 Focal Area Strategic Program:
| Database Number: | MTN/MIE/Food/2011/1/PD | Afghanistan | FP | Yes | Biodiversity | 1 | 1 | U | BD-SP1-PA Financing | 1: Arid & semi-arid ecosystems
Implementing Entity (IE) [name]: |  | United Nations Word Food Programme (WFP) | Albania | MSP | No | Climate Change Adaptation | 2 | 2 | S | BD-SP2-Marine PA | 2: Coastal, marine & freshwater ecosystems
| Type of IE: | Multilateral | Algeria | EA |  | Climate Change Mitigation | 3 | 3 | MU | BD-SP3-PA Networks | 3: Forest ecosystems
| Country(ies): | Mauritania | Angola |  |  | International Waters | 5 | 5 | Good | BD-SP5-Markets | 13: Conservation and Sustainable Use of Biological Diversity Important to Agriculture
Relevant Geographic Points (i.e. cities, villages, bodies of water): |  | Wilaya of Assaba (12 villages); Wilaya of Brakna (12 villages); Wilaya of Gorgol (10 villages); Wilaya of Guidimakha (12 villages); Wilaya of Hodh El Chergui (15 villages); Wilaya of Hodh El Gharbi (14 villages); Wilaya of Tagant (9 villages); Wilaya of Trarza (16 villages) | Argentina |  |  | Multiple Focal Area |  |  |  | BD-SP7-Invasive Alien Species(IAS) | 6: Promoting the adoption of renewable energy by removing barriers and reducing implementation costs
[8 empty] | CC-SP2- Industrial EE | 8: Waterbody based operational program
| Project Milestones | [6 empty] | CC-SP3-RE,CC-SP4-Biomass | 9: Integrated Land and Water multiple focal area
| Milestone |  | Bahamas | [6 empty] | CC-SP5-Transport | 10: Contaminants based operational program
AFB Approval Date: |  | July 2012
IE-AFB Agreement Signature Date: |  | July 23 2012 | [6 empty] | CC-SP6-LULUCF | 12: Integrated Ecosystem Management
Start of Project/Programme: |  | August 14 2014 | [6 empty] | Cross cutting capacity building | 14: Persistent Organic Pollutants
Mid-term Review Date (if planned): |  | January 2017
| Terminal Evaluation Date: | May 2019
|  | List documents/ reports/ brochures / articles that have been prepared about the project. | Cyprus
|  | Brochure of the project Poster of the Project Guidance note for the prioritization of project areas Project inception report ACC training report for technical regional services - Kaédi 9-12 Mach 2015 ACC training report for technical regional services - Kiffa 6-9 April 2015 ACC training report for NGO, Kaédi et Kiffa 8-12 June 2015 ACC training report for government representatives at central level 7-9 July 2015 Monitoring Project Activities factsheets Project Progress Report 1st semester 2015 Assessment of nurseries' seedlings production 2015 Brochure - Climate Change Adaptation Planning Approach at Community Level Brochure -Review of the first year of project implementation Report of the assessment study on Soil and Water conservation Report of the assessment study of the promotion of poultry farming programme Report of the assessment study of the beekeeping promotion programme Report of the assessement study of the fruit trees promotion programme Report of the Veterinary Auxiliary Training Veterinary Auxiliaries training manuel Assessment of nurseries' seedlings production 2016 | Czech Republic
https://www.youtube.com/watch?v=TJXPh0mQb9c (Reportage sur les réalisation -2016)
https://www.youtube.com/watch?v=NvMot1jn9js&t=25s (Reportage sur les réalisations du projet - 2017)
https://www.wfp.org/stories/building-resilience-and-adaptive-capacity-communities-sahel
https://www.facebook.com/ParsaccMauritania
http://parsacc.yolasite.com/etudes-et-rapports.php
List the Website address (URL) of project. |  |  | Democratic People's Republic of Korea
|  | http://parsacc.yolasite.com | Democratic Republic of the Congo
Denmark
| Project contacts: |  | Djibouti
International Project Manager/Coordinator |  |  | Dominica
| Name: | Ghazi GADER, Project coordinator | Dominican Republic
| Email: | ghazi.gader@wfp.org | Ecuador
| Date: | 14-Agust-2014 | Egypt
| Government DA |  | El Salvador
| Name: | Sidi Mohamed El Wavi, National Project Director | Equatoral Guinea
| Email: | elwavi.sm@gmail.com | Eritrea
| Date: | 14-Agust-2014 | Estonia
| Implementing Entity |  | Ethiopia
| Name: | Yasuhiro TSUMURA, WFP Deputy Country Director | Fiji
| Email: | yasuhiro.tsumura@wfp.org | Finland
| Date: | Agust-2016 | France
| Executing Agency |  | Gambia
| Name: | Alioune FALL, Project coordinator Assistant | Georgia
| Email: | lunef@yahoo.com | Germany
| Date: | 14-August-2014 | Ghana
| Executing Agency |  | Greece
| Name: | Maouloud N'Diaye, M&E specialist | Grenada
| Email: | ndiaye.maouloud@gmail.com | Guatemala
| Date: | 2015-10-01 | Guinea
| Executing Agency |  | Guinea Bissau
| Name: | Amadou SY, Communication consultant | Guyana
| Email: | amd2sy@hotmail.com | Haiti
| Date: | 2017-08-15 | Honduras
Hungary
Iceland
India
Indonesia
Iran (Islamic Republic of)
Iraq
Ireland
Israel
Italy
Jamaica
Japan
Jordan
Kazakhstan
Kenya
Kiribati
Kuwait
Kyrgyzstan
Lao People’s Democratic Republic
Latvia
Lebanon
Lesotho
Liberia
Libyan Arab Jamahiriya
Liechtenstein
Lithuania
Luxembourg
Madagascar
Malawi
Malaysia
Maldives
Mali
Malta
Marshall Islands
Mauritania
Mauritius
Mexico
Micronesia, Federated States of
Monaco
Mongolia
Montenegro
Morocco
Mozambique
Myanmar
Namibia
Nauru
Nepal
Netherlands
New Zealand
Nicaragua
Niger
Nigeria
Norway
Oman
Pakistan
Palau
Panama
Papua New Guinea
Paraguay
Peru
Philippines
Poland
Portugal
Qatar
Republic of Korea
Republic of Moldova
Romania
Russian Federation
Rwanda
Saint Kitts and Nevis
Saint Lucia
Saint Vincent and the Grenadines
Samoa
San Marino
Sao Tome and Principe
Saudi Arabia
Senegal
Serbia
Seychelles
Sierra Leone
Singapore
Slovakia
Slovenia
Solomon Islands
Somalia
South Africa
Spain
Sri Lanka
Sudan
Suriname
Swaziland
Sweden
Switzerland
Syrian Arab Republic
Tajikistan
Thailand
The former Yugoslav Republic of Macedonia
Timor-Leste
Togo
Tonga
Trinidad and Tobago
Tunisia
Turkey
Turkmenistan
Tuvalu
Uganda
Ukraine
United Arab Emirates
United Kingdom of Great Britain and Northern Ireland
United Republic of Tanzania
United States of America
Uruguay
Uzbekistan
Vanuatu
Venezuela, Bolivarian Republic of
Viet Nam
Yemen
Zambia
Zimbabwe

## FinancialData
3930312
Financial information: cumulative from project start to August 2017
DISBURSEMENT OF AF GRANT FUNDS | 4145921
How much of the total AF grant as noted in Project Document plus any project preparation grant has been spent to date?
Estimated cumulative total disbursement as of August 2017 | 3272156.1235
Add any comments on AF Grant Funds. (word limit=200) | The amount of $ 3 272 156 includes all expenses and commitments made by: 1. WFP on behalf of MEDD - Executing Entity, 2. MEDD as executing Entity.
INVESTMENT INCOME
Amount of annual investment income generated from the Adaptation Fund’s grant
EXPENDITURE DATA
List output and corresponding amount spent for the current reporting period | ITEM / ACTIVITY / ACTION | AMOUNT
| Output 1.1 Eight DREDD (regional technical services of MEDD) strengthened to access and analyze climate change information, to monitor local development and to mobilize and support communities | 121633.2264
| Output 1.2 Strengthening of Government's threat, risk and vulnerability analysis | 31009.0094
| Output 1.3: 20 inter-village associations established and supported | 3344.442
| Output 1.4:Communities trained in climate change threats and adaptation measures which reduce vulnerability, in particular related to food insecurity | 2675.5536
| Output 1.5:100 villages, being clustered according to landscape, ecosystem and livelihoods, have prepared adaptation plans that are integrated into local development planning. | 4013.3304
| Output 1.6: Communities share success stories and lessons learned, including support of 8 community radios | 0
| Output 1.7: Monitoring system in place (establishment, training, production of data and reports) to track climate events and ecologic development in project intervention zones. | 29036.2762
| Output 2.1: 1500 - 2000 ha of sand dunes fixated | 152408.2328
| Output 2.2: 1000 - 1500 ha of vulnerable zones protected | 139774.9607
| Output 2.3 1,000-1,500 ha of community fuel wood forests planted. | 79454.2769
| 2.4 Water retention structures built covering approximately 500 ha | 123151.2757
| Output 3.1 300,000 trees for revenue generation and food planted in protected areas | 102852.8343
| Output 3.2 4,000 technical staff and community leaders trained in livestock management, agricultural techniques and water utilization | 59173.7071
| Output 3.3 5,000 technical staff and community leaders trained and equipped agro-pastoral IGA, including plant multiplication | 114783.6177
| Output 3.4 6,000 technical staff and community leaders trained and equipped for poultry development | 103229.9335
| Output 3.5 1,000 technical staff and community leaders trained and equipped for apiculture | 11449.9336
| Output 3.6 Approx. 20 community cereal banks established. | 0
| Output 3.7 30,000 fuel efficient stoves built | 0
| Output 3.8 2,000 community members (mainly youth) trained and equipped to build and maintain fuel efficient stoves | 0
| EE - Project Execution Costs | 141904.0475
| MIE - Project Management Fee | 31655.995
| TOTAL | 1251550.6528
PLANNED EXPENDITURE SCHEDULE
List outputs planned and corresponding projected cost for the upcoming reporting period | ITEM / ACTIVITY / ACTION | PROJECTED COST | Est. Completion Date
| Output 1.1 Eight DREDD (regional technical services of MEDD) strengthened to access and analyze climate change information, to monitor local development and to mobilize and support communities | 367160 | 2018-09-30
| Output 1.2 Strengthening of Government's threat, risk and vulnerability analysis | 36000 | 2018-09-30
| Output 1.3: 20 inter-village associations established and supported | 21162.2247 | 2018-09-30
| Output 1.4:Communities trained in climate change threats and adaptation measures which reduce vulnerability, in particular related to food insecurity | 19121.4959 | 2018-09-30
| Output 1.5:100 villages, being clustered according to landscape, ecosystem and livelihoods, have prepared adaptation plans that are integrated into local development planning. | 20556.4251 | 2018-09-30
| Output 1.6: Communities share success stories and lessons learned, including support of 8 community radios | 148000 | 2018-09-30
| Output 1.7: Monitoring system in place (establishment, training, production of data and reports) to track climate events and ecologic development in project intervention zones. | 40000 | 2018-09-30
| Output 2.1: 1500 - 2000 ha of sand dunes fixated | 316247.6068 | 2018-09-30
| Output 2.2: 1000 - 1500 ha of vulnerable zones protected | 45000 | 2018-09-30
| Output 2.3 1,000-1,500 ha of community fuel wood forests planted. | 144000 | 2018-09-30
| 2.4 Water retention structures built covering approximately 500 ha | 442000 | 2018-09-30
| Output 3.1 300,000 trees for revenue generation and food planted in protected areas | 160000 | 2018-09-30
| Output 3.2 4,000 technical staff and community leaders trained in livestock management, agricultural techniques and water utilization | 135000 | 2018-09-30
| Output 3.3 5,000 technical staff and community leaders trained and equipped agro-pastoral IGA, including plant multiplication | 100000 | 2018-09-30
| Output 3.4 6,000 technical staff and community leaders trained and equipped for poultry development | 39000 | 2018-09-30
| Output 3.5 1,000 technical staff and community leaders trained and equipped for apiculture | 74496.6573 | 2018-09-30
| Output 3.6 Approx. 20 community cereal banks established. | 100000 | 2018-09-30
| Output 3.7 30,000 fuel efficient stoves built | 84000 | 2018-09-30
| Output 3.8 2,000 community members (mainly youth) trained and equipped to build and maintain fuel efficient stoves | 40000 | 2018-09-30
| EE - Project Execution Costs | 135278 | 2018-09-30
| MIE | 9500 | 2018-09-30
| TOTAL | 2476522.4098
ACTUAL CO-FINANCING (If the MTR or TE have not been undertaken this reporting period, DO NOT report on actual co-financing.)
How much of the total co-financing as committed in the Project Document has actually been realized? | The MEDD spent about 173 000 USD in 2015 (51 993 186 MRO) as co-financing. This amount was used to pay for project support staff salaries, purchase office supplies, furniture and and computer equipment for DREDDs and inspections. It also contributed to the acquisition of horticultural equipment, fencing material and vegetable seeds.
Estimated cumulative actual co-financing as verified during Mid-term Review (MTR) or Terminal Evaluation (TE). | WFP CO contributed in 2016 by co-financing 6 months project support staff salaries totalling about 21 000 USD (6 812 198 MRO). The cumulative actual co-financing is 194 000 USD.
Add any comments on actual co-financing in particular any issues related to the realization of in-kind, grant, credits, loans, equity, non-grant instruments and other types of co-financing. (word limit=200) | Government in-kind contribution consists on a space provided in the MEDD HQ in Nouakchott, for the PMU.

## Procurement (hidden)
PROCUREMENT DATA
Please provide information for all contracts over $2,500 USD
Please provide the number of contracts under $2,500, signed during this reporting period: |  |  |  | 27
LIST OF CONTRACTS
List all contracts related to the project/program with signature dates
Contract Type | Agency / Contracted party | Contract Value/Amount (USD) | Signature Date | Payment to Date | Remaining Balance
Individual Contract (Consultancy) | CFPR-Boghé | 27184.0005 | 2016-10-02 | 25663.592 | 1520.4085
Individual Contract (Consultancy) | Société Apidesert | 16924.7694 | 2016-10-01 | 5641.5898 | 11283.1796
Individual Contract (Consultancy) | CFPR-Boghé | 32474.9683 | 2016-11-01 | 32390.4303 | 84.538
Individual Contract (Consultancy) | CNRADA | 24977.5104 | 2017-01-16 | 22644.2146 | 2333.2959
Individual Contract (Consultancy) | MULTIMEDIA MAURITANIE | 2895.5358 | 2017-03-05 | 2895.5358 | 0
Individual Contract (Consultancy) | MULTIMEDIA MAURITANIE | 3423.1264 | 2017-07-07 | 3423.1264 | 0
Individual Contract (Consultancy) | CFPR-Boghé | 24741.0849 | 2017-04-24 | 24741.0849 | 0
Individual Contract (Consultancy) | MCG | 65148.63 | 2017-04-08 | 43207.48 | 21941.15
BIDS
List all bids for each contact signed with date of open call and winning bid
CONTRACT & Procurement Method | Submitted Bids | Bid Amount (USD) | Winning Bid Amount (USD) | Selection Justification for the Winner
Acquisition of equipment for the construction of a semi-intensive poultry house and six traditional poultry houses and on-site delivery / Wilaya of Brakna, request for quotation, 20/09/2016 | Boutique Essaad Commerce Général | 11065.7917 | 11065.7917 | The lowest-priced offer among the technically compliant/responsive offers was awarded.
| Boutique EL BIR - Commerce Général | 11666.5724
| Boutique El Najah - Commerce Divers | 11934.1517
Acquisition of equipment for the construction of one semi-intensive poultry house and 04 traditional poultry houses and on-site delivery. Wilaya of Gorgol, request for quotation, 20/09/2016 | Boutique El Adhwa - Commerce Divers | 8929.1169 | 8929.1169 | The lowest-priced offer among the technically compliant/responsive offers was awarded.
| Ets Chourough - Commerce Général | 9672.4557
| Société Nejat, Fourniture - Equipement- Construction | 9811.6196
Acquisition of equipment for the construction of one semi-intensive poultry house and 04 traditional poultry houses and on-site delivery. Wilaya of Guidimakha, request for quotation, 20/09/2016 | Boutique Tandia Med Commerce Général | 9484.2168 | 9484.2168 | The lowest-priced offer among the technically compliant/responsive offers was awarded.
| Ets TAGHADOUM pour Travaux et Construction | 10315.6644
| Boutique Ehel Lekhal - Commerce Divers | 10134.6382
Transport of poultry equipment and material for 50 project sites, request for quotation, 20/09/2016 | Pharmacie ABK | 8570.4588 | 8570.4588 | The lowest-priced offer was awarded.
| El Vadhel Transport | 11766.7025
| RIM CAR Sarl | 10776.7155
Acquisition of seeds, fertilizers, pesticides and other materials for market gardening, request for quotation, 05/10/2016 | AGRI-CO | 11560.1817 | 11560.1817 | The complete lowest-priced offer was awarded.
| ETS LES JARDINS | 12798.5106
| ETS Mohamed Mahmoud | 0
Manufacture and fixing of 411 cement stake, request for quotation, 10/10/2016 | Ets Boidaly et fils | 7353.2481 | 7353.2481 | The complete lowest-priced offer was awarded.
| Ets Moulaye Abderrahman | 7643.5079
| Ets Nour | 7933.7677
Manufacture and fixing of 411 cement stake, request for quotation, 10/10/2016 | Ets Demba Kara pour le Commerce et l'Entreprenariat | 9696.7642 | 9696.7642 | The complete lowest-priced offer was awarded.
| Ets BAALU | 11282.0513
Manufacture and fixing of 240 cement stake, 1260 iron stake and 6220 ml of fences, request for quotation, 10/10/2016 | ETS Jibril Boubacar Pour Travaux Divers | 8799.7518 | 8799.7518 | The complete lowest-priced offer was awarded.
| Quincaillerie IN.CO.AS pour les Matériaux divers | 16623.7906
| ETS TAGHADOUM | 15439.3388
Transport of seeds, fertilizers, pesticides and other materials for market gardening from NKC to 8 DREDD, request for quotation, 17/10/2016 | AGRI-CO | 2961.8346 | 2961.8346 | The complete lowest-priced offer was awarded.
| LES JARSDINS | 4654.3116
| ETS TAYBA | 3949.1129
Purchase of fence material, request for quotation, 08/12/2016 | ME.POL PLUS | 17817.2288 | 17817.2288 | The lowest-priced offer among the technically compliant/responsive offers was awarded.
| RECOGEM | 20808.2396
| Agrion | 19183.0811
Acquisition of horticultural equipment and for soil and water conservation, request for quotation, 12/01/2017 | Ets DAR Service Général | 23299.7863 | 23299.7863 | The complete lowest-priced offer was awarded.
| Quincaillerie Solution | 24472.1972
| Agrion | 25143.0901
Acquisition and installation of solar equipment for the irrigation of vegetable gardens and construction of water storage basins, request for quotation, 12/01/2017 | ETS MAURI -SOLAR | 24997.1888 | 24997.1888 | The lowest-priced offer among the technically compliant/responsive offers was awarded.
| Ets Zoulal pour le forage des puits et des ravaux Publics | 29377.0381
| MEDIAK SARL | 35421.1177
Acquisition and installation of an irrigation network equipment and construction of water storage basins for the irrigation of vegetable gardens, request for quotation, 12/01/2017 | MAANOUH SARL | 15208.591 | 15208.591 | The lowest-priced offer among the technically compliant/responsive offers was awarded.
| Cheikh Mohamed /Mohamed Abd Rahman | 17485.6629
| Dar EL Miyah | 21927.3586
Acquisition and installation of thermal GMP and construction of water storage basins, request for quotation, 12/01/2017 | AGRI-CO | 17412.5717 | 17412.5717 | The lowest-priced offer among the technically compliant/responsive offers was awarded.
| LES JARDINS | 21337.0066
| ETS Karim | 20184.4147
Design and manufacture of Project sites description signs, request for quotation, 17/01/2017 | Publicis | 15425.0534 | 15425.0534 | The lowest-priced offer among the technically compliant/responsive offers was awarded.
| Butterfly | 18300.9108
| Publicom | 17778.0277
| Flashpub | 16993.7029
Acquisition and transport of roosters, request for quotation, 17/01/2017 | Clinique et pharmacie vétérinaire ABK | 3513.9998 | 3513.9998 | The complete lowest-priced offer was awarded.
| Pharmacie Tewekoul | 3921.6237
| Pharmacie El Beitar | 3900.5398
Acquisition of fruit trees, Framework convention, 24/01/2017 | CNRADA | 35120.3194 | 35120.3194 | Direct purchase from the national specialized center
Acquisition of Acacia senegal seeds, Direct purchase, 15/02/2017 | Tourad Mohamed Vall | 8433.5995 | 8433.5995
Acquisition Nursery bags, request for quotation, 01/03/2017 | GRSC Sarl | 21365.1186 | 21365.1186 | The lowest-priced offer among the technically compliant/responsive offers was awarded.
| Ets Med Lemine O. Vekalou Commerce et services | 23595.5056
| EHABF | 26966.2921
| Ahmed Djibril | 24157.3034
Transport of fruit trees from CNRADA to 19 project sites, request for quotation, 23/03/2017 | ETS El Khair pour le Commerce Général et prestation de tous les services commerciaux | 11170.6398 | 11170.6398 | The complete lowest-priced offer was awarded.
| Ets Badi O. Abdi | 12956.6232
| Ets Teissir pour le commerce général | 12761.2307
Acquisition, transport and installation of 4 motor pump units and construction of 3 basins 4 m3, request for quotation, 27/03/2017 | AGRI-CO | 9358.4842 | 9358.4842 | The lowest-priced offer among the technically compliant/responsive offers was awarded.
| MIPA | 12692.5672
| Chinguity Agricole | 13493.7591
Digging a 12 m deep well at Tektaka and Nieliba (Guidimakha), request for quotation, 27/03/2017 | MFM | 10120.3194 | 10120.3194 | The complete lowest-priced offer was awarded.
| Cheikh Med Abderrahman | 12805.0152
| Dar EL Miyah | 14055.9991
Irrigation network installation, request for quotation, 27/03/2017 | Ets Karim | 16164.399 | 16164.399 | The lowest-priced offer among the technically compliant/responsive offers was awarded.
| AGRI-SIM | 18835.0388
| Tayba | 22748.2289
Irrigation network installation, request for quotation, 27/03/2017 | Les Jardins | 17120.2069 | 17120.2069 | The lowest-priced offer among the technically compliant/responsive offers was awarded.
| GPS | 19116.1588
| ETS Fewse Semences | 22208.4786
Manufacturing cement stakes and setting up fence, request for quotation, 18/04/2017 | ESAD Travaux Sarl NKC | 6446.5655 | 6446.5655 | The complete lowest-priced offer was awarded.
| Didi Commerce General et Services | 7091.1941
| Ets Abdellahi O. Ethmane | 6959.6372
Manufacturing cement stakes and setting up fence in Assaba, request for quotation, 26/05/2017 | ETS Jibril Boubacar Pour Travaux Divers | 16233.5554 | 16233.5554 | The complete lowest-priced offer was awarded.
| Mohamed Haidoum | 18682.1922
| TEYSSIR pour le Commerce et la Construction | 19830.9355
Manufacturing cement stakes and setting up fence in Hodh El Gharbi, request for quotation, 26/05/2017 | TEYSSIR pour le Commerce et la Construction | 16654.5373 | 16654.5373 | The complete lowest-priced offer was awarded.
| ETS Jibril Boubacar Pour Travaux Divers | 16913.1725
| Mohamed Haidoum | 16787.7736
Manufacturing cement stakes and setting up fence in Hodh El Chergui request for quotation, 26/05/2017 | Mohamed Haidoum | 17712.0305 | 17712.0305 | The complete lowest-priced offer was awarded.
| Ets Jibril Boubacar pour construction et services divers | 19497.8447
| Teyssir pour le commerce et la construction | 18669.8763
Purchase of agricol equipments, request for quotation, 10/05/2017 | Ets BAH KHATTARI | 75801 | 444.31 | The lowest-priced item among the technically compliant/responsive articles was awarded.
| KARIMPEX AGRODIS s.a.r.l | 92631.9 | 230.68
| Ets N.C.S | 70592 | 2832.4
| Ets ESSAVA | 85052 | 78775
Manufacturing cement stakes and setting up fence in Brakna, request for quotation, 07/06/2017 | ETS DIDI Commerce Général | 14223.9982 | 14223.9982 | The complete lowest-priced offer was awarded.
| Groupement Commercial | 14379.9251
| Abdellahi Ould Mohamaden | 15350.1369
Manufacturing cement stakes and setting up fence in Tagant, request for quotation, 07/06/2017 | Esad - Travaux - Sarl - Nouakchott | 14364.6688 | 14364.6688 | The complete lowest-priced offer was awarded.
| ETS Abdellahi Ould Ethmane | 16304.959
| Ahmed ouldMohamed Commerce Général Prestation de service | 16696.278
Extension of basins capacity, request for quotation,29/06/2017 | AGRI-CO | 16738.524 | 16738.524 | The lowest-priced offer among the technically compliant/responsive offers was awarded.
Acquisition, transport and installation of solar pumps and construction of basins of 4 m3 capacity, request for quotation, 19/07/2017 | ETS MAURI -SOLAR | 24590.622 | 24590.622 | The lowest-priced offer among the technically compliant/responsive offers was awarded.
| Ets Zoulal pour le forage des puits et des travaux Publics | 28899.2353
| MEDIAK SARL | 34845.011

## Risk Assesment
RISK ASSESMENT
IDENTIFIED RISKS
List all Risks identified in project preparation phase and what steps are being taken to mitigate them
Identified Risk | Current Status | Steps Taken to Mitigate Risk
External factors may delay project implementation | Medium to High | Government elections during the initially planned implementation period led to a delay in starting the project activities. However, as soon as the new administration was in place, the project has been making swift progress, catching up some of the delay. The project is a high priority of the Government, and will receive support where difficulties are encountered. Priority will be given to villages which have completed first their adaptation plans to begin implementation. Depending on the progress made by various villages in adaptation plan elaboration and implementation, budgets may be redistributed towards the better performing sites (based on periodic reviews of progress).
Communities find it difficult to take up the skills, learning and social cohesion necessary to secure protected areas | Medium | Communities will carry out the adaptation actions that they themselves prioritize, and will invest their own resources in addition to those provided by the project. The high degree of participation and ownership promoted by the project, coupled with the provision of income to support what are now major livelihoods, will render the risk of communities not sustaining project results very low.
There is little local specialized management and technical capacity related to climate change, particularly in the entities that are responsible for the project. | From High to Medium | The strengthening of decentralized services is a strategic priority for the Government. And the project is committed to provide valuable support and continuous contribution to increase the Government’s technical capacity at these levels.
Lack of adequately qualified partners | Low | A number of qualified partners with a similar project philosophy as WFP are working on the ground, and WFP has good experience in working with them. WFP has a good working experience with some adequately qualified partners which the project may rely on to carry out its activities.
People purchase greater amounts of livestock (beyond carrying capacity) | Low | The project will promote increased community sensitization and raise knowledge and skills towards sustainable natural resources management. Communities will better understand the impact of livestock on their environment. Alternative sources of income will be promoted.
Outsiders bring in additional livestock | Low | Communities will better understand the impact of livestock on their environment and will attach a monetary value to the use of protected areas. They will protect better their natural resources and prevent outsiders from bringing in additional livestock.
People cut down planted trees for fuel wood (other than community forest) | Low | Promoting community land ownership and access to alternative sources of income will help in easing significantly that risk. In addition, Government' strategy of promoting natural gas use over fuel wood in urban centres, will significantly contribute in reducing fuel wood demand in rural areas.
Natural disasters, in particular drought | Medium | As a matter of routine, WFP prepares contingency plans in close collaboration with Government to detect and address risks early on.
Lack of complementary projects and inputs | Low | The project falls fully within Government strategies and related donor strategies. The project advisory group will involve all relevant partners and stakeholders. Already synergies have been developpend with GIZ ACCMR project and WFP PRRO.
Critical Risks Affecting Progress (Not identified at project design)
Identify Risks with a 50% or > likelihood of affecting progress of project
Identified Risk | Current Status | Steps Taken to Mitigate Risk
Changes in regional project focal points (DREDD) | Medium | Since inception, three changes have occurred in the DREDD assignment as project regional focal points. The first change occurred at the beginning of the project and has no impact on the progress of the project as only one region / Wilaya has been affected. The second change occurred in August 2015 with the reassignment of 6 out of 8 DREDDs. The last one took place in August 2017 where 4 changes were made with the reassignment of 3 new DREDDs that have never worked with the project. These changes have disrupted the normal progression of project implementation as new focal points (DREDDs) need to become familiar with the project approach and reach out to the affected communities.
Use of Food for work tool | Overcome | The tendering process for purchasing food took a long time to be finalized thus implying delays on food distribution and frustrating communities involved in the Food For Assets activities. WFP and The Ministry of Environment agreed to combine Food tool with cash transfer tool.
Mobilisation of national contribution for 2017 - 2018 | Overcome | MEDD did not mobilize the national contribution for 2016 and 2017 which contributes to the payment of project support staff salaries. In 2016, WFP CO mobilized half of the required budget from PRRO. The remaining budget (50%) was mobilized from AF project funds. For 2017, salaries of support staff will be covered by the budget of Component 1 (output 1.1), as this contributes to the capacity building and strengthening of DREDDs. This will not affect the deliverables and achievements of objectives under component 1, nor the budget allocated to output 1.1.
Lack of capacity in the DREDDs in terms of staffing and skills. | Medium | In 04 DREDDs out of 08, we noted a lack of capacity in terms of technical and management skills (poor quality of supervision, reporting and management) and also in terms of staffing. This affected the quality of work and the deadlines for implementing activities in the concerned regions. The hiring of NGOs as project partners will reduce the gap and improve the project execution.
During the rainy season (June-August), many project sites become inaccessible due to the impracticability of the terrain. This situation is very cumbersome and causes a slowdown in the execution of activities. | Low | Adapt planning schedule and carry out other capacity building activities at Nouakchott or Wilayas Headquarters during these times.
DREDD as Regional responsibles for the environmental sector are fully busy with the bushfire campaign that runs from September to December of each year. In this period there is a lack in supervising project activity execution. | Medium | The project try to rely on the NGO partners to follow-up and supervise the project activities progress.
Despite of the different capacity building and support provided to NGOS, the performance of some of them is below expected. | Medium | Some contracts with NGOs had to be terminated and additional responsilibities were given to other more active partner NGOs present in the same Wilaya. Capacity building of NGO partners is also reinforced.
Risk Measures: Were there any risk mitigation measures employed during the current reporting period? If so, were risks reduced? If not, why were these risks not reduced?
Add any comments relevant to risk mitigation (word limit = 500)

## Rating
RATING ON IMPLEMENTATION PROGRESS
For rating definitions please see bottom of page.
| Progress on Key Milestones |  | Expected Progress |  | Progress to Date | Rating
Project Manager/ Coordinator: | Hiring NGOs project partners to support DREDD in project implementation activities |  | Planning, supervision, implementation and monitoring of project activities are improved |  | The project hired on March 2017, sixteen (16) NGOs and Group of NGO. Given a clear mandate, they elaborated their work plan to support DREDDs in raising communities awareness and monitoring of project activities within seventy four (74) Communities of the 8 Wilayas in which the project intervenes. We noticed significant improvements since, in regards to communities awareness and their apprpriation of project activities | HS
| Strengthening of Government authorities and technical services on Climate Change threat, risk and vulnerability analysis |  | An Early Warning System (EWS) is set up at community level |  | During the reporting period we noted a delay in the activity of setting up a community early warning system approach. We had meetings with the main partners such as the national meteorological office and agro-meteorological services and agreed to prepare an action plan that will be implemented in partnership with the national radio during the next year. The goal is to provide communities with simple and appropriate informations for an early warning system to better manage their livelihoods. | MS
| Communities share success stories and lessons learned, including support of 8 community radios |  | Community radios are on air, involving communities in programming and feed-back |  | A framework agreement has been signed between the Project and the National Broadcasting Radio. The purpose of this agreement is to set up a global partnership framework between the project and the Radio in order to develop (with a view to operationalizing) concrete measures to raise awareness and share the information developped between the public authorities, the beneficiary communities and local authorities, through radio broadcasts. The following themes could be considered: 1. Vulnerability of communities to climate change 2. The management of climate change adaptation, 3. Food safety analyzes, 4. Weather and seasonal forecasts, 5. Early warning system and 6. Prevailing market prices for products of subsistance. The results of designing and perfecting such mentioned above themes will lead us to take the following actions: a. To develop the capacity building of journalists from Radio Mauritania, Rural Radio and local Radios involved in the implementation of the Framework Convention related to the concepts of climate change, its challenges and the adaptation measures chosen and to be implemented by the project, b. Acquisition of equipment for the regional/local radio stations, c. Design, recording and broadcasting of radio programs according to a program schedule agreed between the two parties, d. Archiving of radio programs. | MS
| Communities are trained and sensitized about the adverse effects of CC and its impacts on natural resources, livelihood and food security |  | Communities are aware about the adverse effects of CC and its impacts on natural resources, livelihood and food security |  | During the reporting period, with the support of NGOs, 17 820 people (13 320 women, and 4 500 men) were reached through awareness programs covering the following themes: - Objectives and approach of the project, - Climate change challenges on natural resources, livelihoods and food security - Ownership, management of achievements and sustainability of activities | HS
| Monitoring system in place (training, production of data and reports) to track climate events and ecologic development in project intervention zones. |  | Monitoring system in place and operational |  | Given the Monitoring-Evaluation Guide developped by the project, discussions were conducted with concerned technical offices of MEDD at central level and the DREDDs at regional level to set up an ecological monitoring mechanism. The project will hire a national consultant to supervise the elaboration of this ecological monitoring mechanism. The monitoring will concern particularly the sand dune fixation areas, wood-fuel plantation areas and the protected grazing areas. The objective is to report on the SEPANE/MEDD indicators covering these activities. It's also planned to train the 8 DREDD's staff on the use of the ecological monitoring system. | S
| Concrete adaptation measures identified through community-based adaptation planning to combat desertification and land degradation initiated in the project area |  | Adaptation measures implementation initiated in the project area to combat desertification and land degradation |  | Since 2015, 59 nurseries have been established in which 570 846 forest seedlings have been produced for sand dunes fixation, village afforestation / reforestation and pastoral improvement programs. Sand dune fixation 525 ha of dunes have been set in 32 project sites. The mechanical fixation, which is the first step in the process of stabilizing sand dunes, covered 340 km of weaving. The objective is to protect houses, hydraulic infrastructures and agricultural lands in the sites, threatened by sand encroachment. Village plantation for fuel wood - 237 ha of collective land ranging from 5 to 10 ha were planted in 27 villages for fuelwood production. The objective is to provide communities with a space where they can extract their firewood needs, thus preserving existing natural resources already weakened by over-exploitation and overgrazing. These spaces will be managed by operating regulations that meet certain rules ensuring their sustainable exploitation by the Village Management Committee. Vulnerable protected area 25 Protected community areas ranging from 25 to 50 ha each totaling 1000 ha have been estabished. These spaces have been protected by fences. They will play an important role for these communities, particularly in a drought year when pasture will not be sufficient to cover livestock needs throughout the year. In 2017, pastoral improvements were made by planting certain local species in order to replenish the vegetation and improve the forage balance of these reserves. Operating regulations are being prepared to enable the management committees of these areas to better manage, exploit and ensure their sustainability. Water retention structures implementation Restoration of degraded lands and water and soil conservation activities are among the most important activities supported by the project. So far 18 water retention structures were built in 6 villages in Guidimakha and 4 villages in Gorgol. The structures which are water retention digues and some up 350m long are totally build by local population without heavy machinery only with local tools and supervising technicians offered by the project. These strutures will restore and protect nearly 300 ha of land and expand cultivable lands. | HS
| Concrete adaptation measures identified through community-based adaptation planning to diversify and strengthen the livelihoods of vulnerable populations initiated in the project area |  | Adaptation measures implementation initiated in the project area to diversify and strengthen the livelihoods of vulnerable populations |  | Fruit tree plantation programme A total of 3,166 households benefited from the project's support of providing 10,000 fruit trees (Mango, Lemon, Mandarin, Grapefruit, Orange, Goyaviers, etc.) to be planted in each household. This program was implemented with the support of Centre for Agricultural Research and Agricultural Development (CNRADA) and targeted two types of farms: 1. Family farms where the project has distributed and helped plant fruit trees in each household at the rate of 3 to 5 trees per household. It is a type of farming with a very high probability of success as the trees are inside the courtyard and a daily attention could be provided in terms of watering and maintenance by the beneficiaries. 2. Collective farms, fenced aeras covering areas ranging from 1 to 2 ha. The project has equipped these areas with basins and drip irrigation systems to ensure a regular watering and water saving. The program will be completed in November 2017 and the project will continue regular monitoring to ensure the success and ownership of the prjects by the beneficiaries. • 19 project sites in the 8 regions • 10 300 fruit trees planted • 3 166 households concerned • 18 770 direct beneficiaries | HS
[5 empty] | High Value Crop production 37 women's cooperatives totaling 8 728 households received direct support from the project. First, trainings on gardening techniques and cooperative management were provided. The project then provided fence material, horticultural equipment, high quality seed and solved for a large part of the sites, the water-related problems by providing digging or deepening of wells and installing water pumping equipment mainly solar pumps or diesel motor pumps. On site technical support was also provided during the two campaigns 2016 and 2017 to transmit to these cooperatives the know-how of the activity and to prepare them to become autonomous in the management of their vegetable gardens without any external support in order to ensure the sustainability of the activity. During the 2016/2017 season, 52 ha were cultivated with a total production of 52 tonnes of vegetables with an average yield per hectare of approximately 994 kg. Each cooperative produced an average of 1400 kg, of which 350 kg were consumed locally or preserved and 1050 kg have been sold to generate additional income. Average revenue per cooperative was valued at MRO 305,000. | HS
Poultry production programme 10 semi-intensive poultry houses and 40 traditional poultry houses were set up at 50 project sites, benefiting 500 families belonging to women's cooperatives and aiming at diversifying their income, improving food security and nutritional quality in poor rural areas. The 10 women's cooperatives for semi-intensive poultry houses are completely autonomous. They all started producing on their own without the support of the project. One of the Trarza's cooperative even reinvested a portion of the profits to expand the poultry house and increase the production's capacity to supply more villages nearby. In figures, the net benefits for 10 women producing a band of 500 chickens is MRO 409,130. The income per band and per woman is about MRO 40,913 and the income per woman per day is MRO 1364. Beyond the provision of white meat to the community, which improves food safety and nutritional quality in general, this activity has allowed profits which could be reinvested in other IGAs to help families to be more resilient. Traditional poultry houses have been established in isolated areas. The production of eggs and meat will allow in the medium term to improve the nutritional quality for families and especially for children and have benefits that will help better withstand the most difficult periods of the year.. This Programme was completed in April 2017. The project shoud ensure a follow up of these activities in order to make sure that all theseactivities could continue in the future without any support from the project.
Apiculture Beekeeping is an innovative activity introduced by the project. Eight Sites were targeted in 05 Wilayas where all the ecological and social conditions are met to guarantee the success of this activity. 2 sites in Trarza (Oum El Koura and Nassra 2), 3 sites in Gorgol (Haddad, Dimechgha and Dar El Beidha), 1 site in Brakna (Dounguel Réo), 1 site in Guidimakha (Ndeo) and 1 site in Tagant (Legdeim ). In each site an apiary of 30 hives was set up benefiting 10 families. The project also provided all the equipment necessary for the practice of beekeeping (Combinations, smokers, honey extractors, etc.) and provided the necessary training and technical supervision to ensure the success of the program. This program is currently in the Production phase and is scheduled to be finalized in March 2018. This activity is on the one hand very profitable economically, but it is very fragile on the other hand. It's necessary to continue the support to cover several technical issues related to the management and the maintenance of the apiaries. The project will document all the stages of the establishment of an apiary to ensure dissemination and scaling-up with other projects.
Trainings for the communities The project trained/coached about 11 000 participants in different activity technics as detailed in the follwing table: Training topic Nber of participants Women Men Veterinary assistants 35 1 34 High value crop production 8 728 6 982 1746 vegetable conservation 89 84 5 Cooperative management 80 28 52 Apiculture 517 284 233 Poultry farming 500 400 100 Fruit farming 2147 Soil and Water conservation 1 084
[5 empty] | Overall Rating | S
Please Provide the Name and Contact information of person(s) responsible for completing the Rating section
| Name: | Ghazi GADER
| Email: | ghazi.gader@wfp.org
Please justify your rating. Outline the positive and negative progress made by the project since it started. Provide specific recommendations for next steps. . (word limit=500)
Most of the activities have been implemented according to the annual work plan. Since the recruitment of NGOs and their training on CC and the integration of Adaptation to climate change into local planning, the support to DREDD and underlining raising communities awareness and monitoring of project activities have much improved in project intervention areas. We also pointed out the improvement of the synergy between the PARSACC and WFP's PRRO which has been extended to the Wilaya of Guidimakha where joint and complementary interventions were carried out this year in some Project sites covering mainly water and soil conservation activities. The support provided by the project in terms of solving the water related problems (well digging, solar equipment, irrigation networks, storage tanks ...) can be considered one of the most important adaptation measures which have been put in place for the benefit of local communities. Water is a major issue in Maritania when talking about adaptation to climate change. The results of soil and water conservation activities are already perceptible. In three project sites of the Wilaya of Gorgol where earth dams have been built, farmers have cultivated crops on restored lands behind dams. This will contribute to the improvement of agricultural production in these sites where the rainfaull is always in deficit. We started to notice the project good effects following the implementation of certain income-generating activities. For example, in the semi-intensive poultry farming activity, we observed the construction of an extension of the poultry house by one cooperative itself from the profits generated by the activity. Similar observations were made in 9 high value crop production cooperatives which created and financed new IGAs like butcher shops, community shops and fish shops themselves from profits generated from their activties. We underlined as well that the 10 semi-intensive poultry cooperatives are totally autonomous and directly linked to the market for the acquisition of inputs (chicks, food, medicines, etc.) and the marketing of their products, which generate substancial profit margins improving beneficiaries income and village food security and nutrition quality. Despite this good progress, there has been underachievement in some activities planned for this reporting period: - The establishment of an early warning system at the community level is still on standby because there are several initiatives at national level involving different partners that are not yet clear. The project preferred to wait for the evolution of these initiatives before engaging in the implementation of the EWS. It was decided to retain a very simple mechanism adapted to the needs of the target communities that will be deployed in partnership with the Nationa Office of Meteorology, The Agro-Meteorological Services, the National Broadcasting Radio and the DREDDs. An action plan is being prepared between the concerned partners which will be implemented next year. - The delay in the implementation of the Radio Support Program for the sharing of good project practices has been deliberately shifted by the project to integrate the EWS as previously described. To note also that a framework agreement with the Radio has already been signed as is described in the sheet 'Project Indicators'. - Regarding Village cereal Banks, after evaluating previous interventions of various projects that supported this activty in Mauritania, it was found that this experience was a failure both nationally and in the subregion. The difficulty lies in the fact that these investments require a very long and cumbersome process of accompaniment and follow-ups with the VCB management committees. WFP CO is also not in favor of investing in BCVs that have low chances of success. The same observation was made by some governors of the project's intervention regions where the experience of VCB failed. The MEDD is rather favorable of reallocating the planned investments for this activity towards income-generating activities and solving water related problems which remains in many project intervention sites.The implementing entity will soon contact the AF Secretariat on this matter to seek advice in view of the preparation of the request to the AF Board, as required by the AF policies. - We noted as well a delay in launching the improved stove program due to the load plan and the reduced staff of PMU. The evaluation of the program has been launched with the support of a national consultant and that implementation will begin at the end of 2017. This year 2017, we noted a new movement between DREDDs with the appointment of 3 new focal points who have never worked with the project. This situation is of course penalizing the normal progress of planned activities. Also, the performance evaluation of the NGOs after 6 months trial of work showed the limits of three of them. The project has ended their contracts and a redeployment of NGOs was operated in the uncovered areas.
| Progress on Key Milestones |  | Expected Progress |  | Progress to Date | Rating
Executing Entity | Hiring NGOs project partners to support DREDD in project implementation activities |  | Planning, supervision, implementation and monitoring of project activities are improved |  | The project hired on March 2017, sixteen (16) NGOs and Group of NGO. Given a clear mandate, they elaborated their work plan to support DREDDs in raising communities awareness and monitoring of project activities within seventy four (74) Communities of the 8 Wilayas in which the project intervene. We noticed significant improvements since in collaborating communities awareness and their apprpriation of project activities | HS
| Strengthening of Government authorities and technical services on Climate Change threat, risk and vulnerability analysis |  | An Early Warning System (EWS) is set up at community level |  | During the reporting period we noted a delay in the activity of setting up a community early warning system approach. We had meetings with the main partners such as the national meteorological office and agro-meteorological services and agreed to prepare an action plan that will be implemented in partnership with the national radio during the next year. The goal is to provide communities with simple and appropriate informations for an early warning system to better manage their livelihoods. | MS
| Communities share success stories and lessons learned, including support of 8 community radios |  | Community radios are on air, involving communities in programming and feed-back |  | A framework agreement has been signed between the Project and the National Broadcasting Radio. The purpose of this agreement is to set up a global partnership framework between the project and the Radio in order to develop (with a view to operationalizing) concrete measures to raise awareness and share the information developped between the public authorities, the beneficiary communities and local authorities, through radio broadcasts. The following themes could be considered: 1. Vulnerability of communities to climate change 2. The management of climate change adaptation, 3. Food safety analyzes, 4. Weather and seasonal forecasts, 5. Early warning system and 6. Prevailing market prices for products of subsistance. The results of designing and perfecting such mentioned above themes will lead us to take the following actions: a. To develop the capacity building of journalists from Radio Mauritania, Rural Radio and local Radios involved in the implementation of the Framework Convention related to the concepts of climate change, its challenges and the adaptation measures chosen and to be implemented by the project, b. Acquisition of equipment for the regional/local radio stations, c. Design, recording and broadcasting of radio programs according to a program schedule agreed between the two parties, d. Archiving of radio programs. | MS
| Communities are trained and sensitized about the adverse effects of CC and its impacts on natural resources, livelihood and food security |  | Communities are aware about the adverse effects of CC and its impacts on natural resources, livelihood and food security |  | During the reporting period, with the support of NGOs, 17 820 people (13 320 women, and 4 500 men) were reached through awareness programs covering the following themes: - Objectives and approach of the project, - Climate change challenges on natural resources, livelihoods and food security - Ownership, management of achievements and sustainability of activities | HS
| Monitoring system in place (training, production of data and reports) to track climate events and ecologic development in project intervention zones. |  | Monitoring system in place and operational |  | Given the Monitoring-Evaluation Guide developped by the project, discussions were conducted with concerned technical offices of MEDD at central level and the DREDDs at regional level to set up an ecological monitoring mechanism. The project will hire a national consultant to supervise the elaboration of this ecological monitoring mechanism. The monitoring will concern particularly the sand dune fixation areas, wood-fuel plantation areas and the protected grazing areas. The objective is to report on the SEPANE/MEDD indicators covering these activities. It's also planned to train the 8 DREDD's staff on the use of the ecological monitoring system. | S
| Concrete adaptation measures identified through community-based adaptation planning to combat desertification and land degradation initiated in the project area |  | Adaptation measures implementation initiated in the project area to combat desertification and land degradation |  | Since 2015, 59 nurseries have been established in which 570 846 forest seedlings have been produced for sand dunes fixation, village afforestation / reforestation and pastoral improvement programs. Sand dune fixation 525 ha of dunes have been set in 32 project sites. The mechanical fixation, which is the first step in the process of stabilizing sand dunes, covered 340 km of weaving. The objective is to protect houses, hydraulic infrastructures and agricultural lands in the sites, threatened by sand encroachment. Village plantation for fuel wood - 237 ha of collective land ranging from 5 to 10 ha were planted in 27 villages for fuelwood production. The objective is to provide communities with a space where they can extract their firewood needs, thus preserving existing natural resources already weakened by over-exploitation and overgrazing. These spaces will be managed by operating regulations that meet certain rules ensuring their sustainable exploitation by the Village Management Committee. Vulnerable protected area 25 Protected community areas ranging from 25 to 50 ha each totaling 1000 ha have been estabished. These spaces have been protected by fences. They will play an important role for these communities, particularly in a drought year when pasture will not be sufficient to cover livestock needs throughout the year. In 2017, pastoral improvements were made by planting certain local species in order to replenish the vegetation and improve the forage balance of these reserves. Operating regulations are being prepared to enable the management committees of these areas to better manage, exploit and ensure their sustainability. Water retention structures implementation Restoration of degraded lands and water and soil conservation activities are among the most important activities supported by the project. So far 18 water retention structures were built in 6 villages in Guidimakha and 4 villages in Gorgol. The structures which are water retention digues and some up 350m long are totally build by local population without heavy machinery only with local tools and supervising technicians offered by the project. These strutures will restore and protect nearly 300 ha of land and expand cultivable lands. | HS
| Concrete adaptation measures identified through community-based adaptation planning to diversify and strengthen the livelihoods of vulnerable populations initiated in the project area |  | Adaptation measures implementation initiated in the project area to diversify and strengthen the livelihoods of vulnerable populations |  | Fruit tree plantation programme A total of 3,166 households benefited from the project's support of providing 10,000 fruit trees (Mango, Lemon, Mandarin, Grapefruit, Orange, Goyaviers, etc.) to be planted in each household. This program was implemented with the support of Centre for Agricultural Research and Agricultural Development (CNRADA) and targeted two types of farms: 1. Family farms where the project has distributed and helped plant fruit trees in each household at the rate of 3 to 5 trees per household. It is a type of farming with a very high probability of success as the trees are inside the courtyard and a daily attention could be provided in terms of watering and maintenance by the beneficiaries. 2. Collective farms, fenced aeras covering areas ranging from 1 to 2 ha. The project has equipped these areas with basins and drip irrigation systems to ensure a regular watering and water saving. The program will be completed in November 2017 and the project will continue regular monitoring to ensure the success and ownership of the prjects by the beneficiaries. • 19 project sites in the 8 regions • 10 300 fruit trees planted • 3 166 households concerned • 18 770 direct beneficiaries | HS
[5 empty] | High Value Crop production 37 women's cooperatives totaling 8 728 households received direct support from the project. First, trainings on gardening techniques and cooperative management were provided. The project then provided fence material, horticultural equipment, high quality seed and solved for a large part of the sites, the water-related problems by providing digging or deepening of wells and installing water pumping equipment mainly solar pumps or diesel motor pumps. On site technical support was also provided during the two campaigns 2016 and 2017 to transmit to these cooperatives the know-how of the activity and to prepare them to become autonomous in the management of their vegetable gardens without any external support in order to ensure the sustainability of the activity. During the 2016/2017 season, 52 ha were cultivated with a total production of 52 tonnes of vegetables with an average yield per hectare of approximately 994 kg. Each cooperative produced an average of 1400 kg, of which 350 kg were consumed locally or preserved and 1050 kg have been sold to generate additional income. Average revenue per cooperative was valued at MRO 305,000. | HS
Poultry production programme 10 semi-intensive poultry houses and 40 traditional poultry houses were set up at 50 project sites, benefiting 500 families belonging to women's cooperatives and aiming at diversifying their income, improving food security and nutritional quality in poor rural areas. The 10 women's cooperatives for semi-intensive poultry houses are completely autonomous. They all started producing on their own without the support of the project. One of the Trarza's cooperative even reinvested a portion of the profits to expand the poultry house and increase the production's capacity to supply more villages nearby. In figures, the net benefits for 10 women producing a band of 500 chickens is MRO 409,130. The income per band and per woman is about MRO 40,913 and the income per woman per day is MRO 1364. Beyond the provision of white meat to the community, which improves food safety and nutritional quality in general, this activity has allowed profits which could be reinvested in other IGAs to help families to be more resilient. Traditional poultry houses have been established in isolated areas. The production of eggs and meat will allow in the medium term to improve the nutritional quality for families and especially for children and have benefits that will help better withstand the most difficult periods of the year.. This Programme was completed in April 2017. The project shoud ensure a follow up of these activities in order to make sure that all theseactivities could continue in the future without any support from the project.
Apiculture Beekeeping is an innovative activity introduced by the project. Eight Sites were targeted in 05 Wilayas where all the ecological and social conditions are met to guarantee the success of this activity. 2 sites in Trarza (Oum El Koura and Nassra 2), 3 sites in Gorgol (Haddad, Dimechgha and Dar El Beidha), 1 site in Brakna (Dounguel Réo), 1 site in Guidimakha (Ndeo) and 1 site in Tagant (Legdeim ). In each site an apiary of 30 hives was set up benefiting 10 families. The project also provided all the equipment necessary for the practice of beekeeping (Combinations, smokers, honey extractors, etc.) and provided the necessary training and technical supervision to ensure the success of the program. This program is currently in the Production phase and is scheduled to be finalized in March 2018. This activity is on the one hand very profitable economically, but it is very fragile on the other hand. It's necessary to continue the support to cover several technical issues related to the management and the maintenance of the apiaries. The project will document all the stages of the establishment of an apiary to ensure dissemination and scaling-up with other projects.
Trainings for the communities The project trained/coached about 11 000 participants in different activity technics as detailed in the follwing table: Training topic Nber of participants Women Men Veterinary assistants 35 1 34 High value crop production 8 728 6 982 1746 vegetable conservation 89 84 5 Cooperative management 80 28 52 Apiculture 517 284 233 Poultry farming 500 400 100 Fruit farming 2147 Soil and Water conservation 1 084
[5 empty] | Overall Rating | S
Please Provide the Name and Contact information of person(s) responsible for completing the Rating section
| Name: | Alioune Fall, Project Coordinator Assistant; |  |  | Sidi Mohamed El Wavi, National Project Director
| Email: | lunef@yahoo.com |  |  | elwavi.sm@gmail.com
| Progress on Key Milestones |  | Expected Progress |  | Progress to Date | Rating
Other
Overall Rating
Please Provide the Name and Contact information of person(s) responsible for completing the Rating section
Name:
Email:
| Please justify your rating and address the following points: 1. Indicate trends, both positive and negative, in achievement of outcomes as per the project indicators. 2. Detail critical risks that have affected progress. 3. Outline response to MTR undertaken this reporting period. 4. Outline action plan to address projects with a rating of HU, U or MU. Please keep your input to 1200 words |  | Regarding the outcome objective: "enhancing the resilience of vulnerable communities to the effects of climate change on food security" the project succeeded in building the resilience to climate change for direct beneficiaries . This is clear in diversifying income generating activities and improvement of the use of natural resources. A great work has been made in raising awerness of beneficiairies to build ownership and sustainability of the implmented activities. This work will be ensured by the DREDDs and regionl technical services as well as NGOs involved in the project. The project is a leading one in the Department and specifically distinguished in applying a participatory bottom-up approach starting at the community level, to the central level. While most activities achieved more than the planned at 3 component level, the project Mid-term review underligned for the Component 2, after two years of implementation of the field activities and monitoring of the Project's achievements, on one hand, differences, sometimes very considerable, between the initial unit costs considered in the project document and the actual costs (sand dune fixation and vulnerable area protection). In the other hand, the difficulty of programming areas as initially planned, like in the case of fuel-wood village reforestation due to land ownership, regulatory and social constraints. The EE approves the Mid-Term review adjustments for the Budgets and targets proposed for the Outputs 2.1, 2.2 and 2.3. (c.f. MTR report) and requests the AF to acknowledge these adjustments. Village cereal Banks experience in Mauritania was not successful. The MEDD is also favorable of reallocating planned investments previewed for Village Cereal Banks towards income-generating and resolving water-related problems activities at the component 3 level. In this regard, the EE request the AFB approval to permit to the PMU planning these activities.
Rating Definitions
|  |  | Highly Satisfactory (HS) | Project actions/activities planned for current reporting period are progressing on track or exceeding expectations to achieve all major outcomes/outputs for given reporting period, without major shortcomings. The project can be presented as “good practice”.
|  |  | Satisfactory (S) | Project actions/activities planned for current reporting period are progressing on track to achieve most of its major outcomes/outputs with only minor shortcomings.
|  |  | Marginally Satisfactory (MS) | Project actions/activities planned for current reporting period are progressing on track to achieve most major relevant outcomes/outputs, but with either significant shortcomings or modest overall relevance.
|  |  | Marginally Unsatisfactory (MU) | Project actions/activities planned for current reporting period are not progressing on track to achieve major outcomes/outputs with major shortcomings or is expected to achieve only some of its major outcomes/outputs.
|  |  | Unsatisfactory (U) | Project actions/activities planned for current reporting period are not progressing on track to achieve most of its major outcomes/outputs.
|  |  | Highly Unsatisfactory (HU) | Project actions/activities planned for current reporting period are not on track and shows that it is failing to achieve, and is not expected to achieve, any of its outcomes/outputs.

## Project Indicators
PROJECT Indicators
Please provide all indicators being tracked for the project as outlined in the project document
Type of Indicator (indicators towards Objectives, Outcomes, etc…)
Type of Indicator | Indicator | Baseline | Progress since inception | Target for Project End
OBJECTIVE 1: Enhanced understanding, skills and means of decentralized government and communities for leading and facilitating participatory adaptation planning | Number of community adaptation plans prepared through participative local planning supported with information and facilitation by DREDD | No adaptation plans exist in intervention zones | 87 villages prepared their ACC action plan with the support of DREDD and Regional technical services including civil society. This work is a result of the improvement of DREDD and project partners' skills on Climate change issues and integrating ACC into local development approach. With the support of NGOs, the baseline reference was improved and More than 50 Action plans have been updated. | 20 clusters of villages have established adaption plans in a participatory manner
Outcome 1.1: Strengthened awareness, ownership and facilitation capacities of government services (DREDD) | DREDD have played an active and supportive role in the mobilization, organization and implementation of inter-village adaption planning processes | DREDD do not have capacity to provide any support to communities | DREDD led, participated and facilitated in the elaboration of ACC action plans in the project area. DREDD supervise in a regular bases with the support of NGO and others regional technical services, implementation of project activities giving advice and technical support for the communities. | DREDD have succeeded to provide information, guidance and facilitation support to 20 village clusters
Output 1.1: Technical services strengthened to access and analyze climate change information, food security, livelihoods and vulnerability information, and to monitor local development, and mobilize and support communities. | DREDD have been trained, have communicated with department and local level, have visited communities, have facilitated village cluster establishment and discussions | DREDD do not visit communities and do not provide information, support, guidance or facilitate processes | - 2 training sessions organized in collaboration with GIZ's ACCMR project, for DREDDs and Regional technical services on Climate Change basics and the approach of Integrating Adaptation to Climate Change into Development planning. (80 participants). This training was followed by a practical exercise in one selected project site to implement the methodology in a real case with the active participation of the communities. Knowledge acquired during these aforementioned capacity building sessions permitted DREDD with regular visits to raise awareness on climate change impacts on food security and to monitor and guide the project's interventions. DREDDs received an additionnal support by the contracted 16 NGOs which have been also trained on Climate change issues and integrating adaptation to climaite change into local planning. These NGO provided support also Community sensitization and mobilization, data collection and monitoring of climate change adaptation measures at local level. | DREDDs have regular contact and trustful relationship with village clusters and communities that value their support
Output 1.2: Strengthening of Government authorities and technical services on CC threat, risk and vulnerability analysis capabilities by expanding current Vulnerability and Analysis methodologies to overlay climate threats and monitoring changes in landscapes using GIS technologies. | Preparation and communication to regional level of up-to-date and reliable information and analysis of climate change information and of government priorities | DREDD hardly receive any guidance, information and analysis from central level | During the reporting period we noted a delay in the activity of setting up a community early warning system approach. We had meetings with the main partners such as the national meteorological office and agro-meteorological services and agreed to prepare an action plan that will be implemented in partnership with the national radio during the next year. The goal is to provide communities with simple and appropriate informations for an early warning system to better manage their livelihoods. | Regular communications between central level and DREDD provide up-to date information and guidance, adapted to the capacity at regional level
Outcome 1.2: Strengthened awareness, ownership, planning and management capacities at community level for local natural resource management and climate change adaptation | Communities and their relevant sub-groups (e.g. women, livelihood groups, etc.) have actively participated in the preparation of the inter-village adaptation plans prepared and see their interests adequately reflected. | There is only little joint discussion at community level, and not all groups are involved; no inter-village discussions take place | The sensitized communities about climate change impacts have played a great role and actively participated to all steps of the process of elaboration of adaptation to climate change action plans, till the identification and prioritization of adaptation options. | About 100 villages in 20 village clusters understand, own and manage their adaption plans and their natural resources
Output 1.3: 20 inter-village associations established and supported. | Inter-village associations exist and are active in on form or the other in each of 20 targeted clusters | In some clusters, some form of cooperation structure may exist, on which the project can build. | The Mid-Term review confirmed that the establishing of inter-village associations in the framework of the AF project is not feasable, particularly due to social, and land ownership issues and also distance between villages. This work requires a lot of time and resources in order to achieve it (i.e. ProGRN experience). Wherever inter-village association structures exist, like AGLC, the project will continue supporting them during the project implementation period as they will ensure the sustainability of project activities. However the project is now working with the village management committies which are created and activated in all project sites and one of the NGO tasks is to work on giving these committees a legal status. | 20 inter-village associations with a role in managing natural resources and adaptation plans recognized by population and DREDD
Output 1.4: Communities trained in climate change threats and adaptation measures which reduce vulnerability, in particular related to food insecurity. | Number of people (gender-disaggregated) and communities trained | Communities are aware of degrading natural resources, but rarely of context, causes and adaptation options | The regular visits organized by DREDD to supervise project activities constitute occasions to raise awarness about threats of adverse effects of CC on natural resources, livelihoods and food security. Parallelly to the ACC action plans implementation, many trainings have been organized for communities in different topics (High value crop production, agriculture, Poultry, Apiculture, sand dune fixation, aforestation, Soil and Water conservation, etc.) which adress also issues related to Climate change impacts on natural ressources, livelihood and food security. With the support of NGO, awareness raising and training sessions have been organised for the targeted communities. 17 820 people (13 320 wemen, and 4 500 men) were involved in an awareness program about the following topics: - Objectives and approach of the project, - Climate change challenges on natural resources, livelihoods and food security - Ownership, management of achievements and sustainability of activities | Communities have the capacity to analyze and understand their situation, and adaptation options
Output 1.5: 100 villages, being clustered according to landscape, ecosystem and livelihoods, have prepared adaptation plans that are integrated into local development planning. Identification of adaptation technology requirements such as integrated livestock water and cropping systems. | 20 village cluster adaptation plans developed in a participatory way and officially recognized by DREDD | Communities and village associations do not prepare comprehensive adaptation plans | 87 villages prepared their ACC action plan with the support of DREDD and Regional technical services including civil society. These ACC action plans have been reviwed during the period March to August 2017 with the support of NGO hired by the project in march 2017. This work is a result of the improvement of DREDD, NGO and project partners' skills on ACC planning participatory approach based on 8 steps : 1. Identification of exposer units 2. Analysis of current vulnerability 3. Analysis of projected vulnerabilty (according to climate scenarios) 4. Identification of adaptaion options 5. Choice of prioritization criteria 6. Prioritization of adaptation options 7. Declination of adaptation options into actions and activities 8. Development of ACC action Plan | Adaptation plans include analysis, discussion of options, decision on priorities and analysis of implications (costs, maintenance)
| Specific studies on adaptation technology requirements are available at the relevant levels | A number of ad hoc studies exist within several projects, but are not systematically made available | n/a | Studies on technology for 3-4 “standard” adaptation assets are available to all partners and stakeholders
Output 1.6: Communities share success stories and lessons learned, including support of community radios focused specifically on sharing information on early warning and adaptation management. | Community radios are on air, involving communities in programming and feed-back | Communities of 15 sites in the project area have already listen regularly to radio transmissions on a radius ranging from 6 to 70 km. | Community radios (Local Radio) were already established by the Government in all Wilayas including the 8 wilayas targeted by the project. They have been associated to all workshops and trainings organized in the regional level and they were sensitized to the project objectives. A framework agreement has been signed between the Project and the National Radio. The objective of this agreement is to set up the global partnership framework linking the project and the Radio with a view to operationalizing concrete measures to raise awareness and share the information developed between the public authorities, the beneficiary communities and local authorities, through radio broadcasts that particularly concern: 1. Vulnerability of communities to climate change 2. The management of climate change adaptation, 3. Food safety analyzes, 4. Weather and seasonal forecasts, 5. Early warning system and 6. Prevailing market prices for subsistence products. This will covers the following actions: a. The capacity building of journalists from Radio Mauritania, Rural Radio and local Radios involved in the implementation of the Framework Convention in various fields related to the concepts of climate change, its challenges and the adaptation measures taken implemented or planned by the project, b. Acquisition of equipment for the regional/local radio stations, c. Design, recording and broadcasting of radio programs according to a program schedule agreed between the two parties. d. Archiving of radio programs. | CR goes live are on air, have with strong volunteer involvement and a sustainability strategy
Outcome 1.3: National ecologic monitoring system strengthened and tested | Participating communities and government services have provided quality, timely and reliable ecologic monitoring reports aligned with the national monitoring system | The ecologic monitoring system is established as part of PANE II System and set online in February 2014. | The Monitoring System of the PANE is already set up since 2014 by the MEDD with the support of GIZ and is online (http://www.medd-sepane.mr/). On the bases of the Monitoring-Evaluation Guide developped by the project, discussions have been conducted with concerned technical Directions of MEDD at central level and the DREDDs at regional level to set up aan acological monitoring mechanism. The project will hire a national consultant to supervise the elaboration of this ecological monitoring mechanism. The monitoring will concern particularly the sand dune fixation areas, wood-fuel plantation areas and the protected grazing areas. The objective is to report on the SEPANE/MEDD indicators covering these activities. | The new national ecologic monitoring system is known, used and maintained by DREED and in project village clusters.
Output 1.7: Monitoring system in place (training, production of data and reports) to track climate events and ecologic development in project intervention zones. | Number of people trained at regional and village cluster level; amount and quality of data provided by village clusters / regional teams | There is no systematic collection, consolidation and analysis of data on nationally agreed-upon indicators. | Training on the use of the monitoring and evaluation guide has been organized for the benefit of the 8 DREDDs. Periodically the ecological monitoring is carried out (DREDD - PMU) in the project intervention sites compared to the baseline situation. The results will be integrated into the national ecological monitoring system. | Participating DREDD and village clusters provide data on agreed-upon indicators; and receive, understand and use reports.
OBJECTIVE 2: Design and implement concrete adaptation measures identified through community adaptation planning that aim to combat desertification, soil erosion and land degradation | Number of implemented community adaptation plan action aiming to combat desertification, soil erosion and land degradation | No comprehensive community (cluster) adaptation plans exist in the intervention zones to be selected. | All the adaptation plans drawn up by the targeted communities, with the support of DREDDs and revied by the NGOs, integrate measures linked to combat desertification, soil erosion and land degradation. It's planned to train the 8 DREDD's staff on the use of the ecological monitoring system which will be setup next year. | 20 comprehensive adaptation plans have been implemented with respect to combat desertification, soil erosion and land degradation.
Outcome 2.1: Advance of sand dunes slowed down, halted or reversed | Reduced, halted or reversed dune advance in participating communities | 749 ha of dunes fixed in the project intervention area | With the process of mechanical and biological fixation of the dunes already engaged covering an area of 525 ha, the advance of the dunes has been slowed down at the treated sites. | Significant deceleration – and ideally reversal – of dune advance
Output 2.1: 1,500-2,000 ha of dunes fixated. | Plants – and other measures – have stopped advance of dunes | Sand dune fixation does take place as part of several projects, but hardly in the zones to be selected. | 525 ha of dunes have been set in 32 project sites. The mechanical fixation, which is the first step in the process of fixing dunes, covered 340 km of weaving. Number of participants to implement the activity : 4 100 Number of beneficiaries : 24 600 | Communities have fixated dunes and have a clear plan for maintaining / reinforcing fixation
Outcome 2.2: Increased vegetation cover in intervention zones | Increased Vegetation Cover Index in participating communities | The average density of vegetation is 67 plants per hectare in the project sites | 25 protected areas have been established. 27 wood-fuel plantation areas have been established | Increase of the average density per hectare by at least 10% in the participating village clusters until the end of the project with clear prospect of further increases)
Output 2.2: 1,000-1,500 ha of vulnerable zones protected. | Area of land protected from against uncontrolled grazing and bush fires | There will only be sporadic protected areas in selected village clusters | 25 Protected community areas ranging from 25 to 50 ha totaling 1000 ha have been established. These spaces have been protected by fences. They will play an important role for these communities, particularly during drought years when pasture will not be sufficient to cover livestock needs throughout the year. In 2017, pastoral improvements were made by planting some local species in order to replenish the vegetation and improve the forage balance of these reserves. Operating regulations are being prepared to enable the management committees of these areas to better manage, exploit and ensure their sustainability. Number of participants to implement the activity : 720 Number of beneficiaries : 4 690 | 1,000 – 1,500 ha of land protected and encompassed by sustainable management plan
Output 2.3: 1,000-1,500 ha of community fuel wood forests planted. | Area of land planted and controlled for fuel wood production; volume of produced fuel wood | There is hardly any controlled fuel wood plantation in areas to be selected | 237 ha of collective land of 5 to 10 ha were planted by village reforestation in 27 villages for fuelwood production. The objective is to provide communities with a space where they can extract their firewood needs, thus preserving existing natural resources already weakened by over-exploitation and overgrazing. These spaces will be managed by operating regulations that meet certain rules ensuring their sustainable exploitation by the Village Management Committee. Number of participants to implement the activity : 979 Number of beneficiaries : 5 760 The exploitation of these areas will not be before 10 to 15 years. | Participating communities cover at least 50% of their fuel wood requirements from controlled wood production
Outcome 2.3: Decreased loss of water and soil through surface run-off | Increased surface and sub-soil water availability | There are only 13 sites with water retention structures functioning in areas to be selected | The evaluation will be conducted after the programme implementation | Area where days of water availability has increased with at least 20%
Output 2.4: Water retention structures built covering approx. 500 ha. | Number, kind, surface size and volume (where applicable) of water retention structures | 13 sites have dams, check dams, Soil and water conservation structures, Soil restoration structures | So far 18 Water retention structures were built in 6 villages in Guidimakha and 4 villages in Gorgol. They are particularly dams, filter dikes and stone bunds. This strutures will restore and protect about 300 ha of land and expand cultivable lands. Number of participants to implement the activity : 1 084 Number of beneficiaries : 6 494 | Communities construct and maintain retention assets according to plan
OBJECTIVE 3 Design and implement concrete adaptation measures identified through community adaptation planning that aim to diversify and strengthen the livelihoods of the most vulnerable population » | Number and type of implemented community adaptation plan action aiming to diversify and strengthen the livelihoods of the most vulnerable population | No adaptation plans are in place, livelihood bases are hardly diversified in areas to be selected | The adaptation action plans drawn up in the different project sites integrate diverse income-generating activities to diversify and strengthen livelihoods and food security of targeted communities. | Communities have implemented adaptation plan action and continue to gain sustainable income from new sources
Outcome 3.1: Increased number of sources of income for participating households | Number and type of sources of income for participating households before and after the project | Livelihood bases are hardly diversified in areas to be selected – specific baselines to be established as part of adaptation plan preparation (The communities practice seven (7) income generating activities including 04 based on the exploitation of natural resources (agriculture, livestock, fishing and fruit picking) | So far, some new income-generating activities have been introduced in many project sites : - High value crop production, in 52% of total project sites - Poultry, in 55% of total project sites - Beekeeping, in 9% of total project sites - Fruit farming, in 21% of total project sites | At least 25% of village cluster population have increased their livelihood bases with new sources of income
Outcome 3.2: Increased income for participating households | Level of income for participating households before and after the project | Participating households are among the poorest in the selected areas. | Evaluation to be carried out during the third and fourth year of implementation of the project. | Participating households have increased their revenues by at least 40%
Outcome 3.3: Increased availability of and access to food for participating communities | Food gap (number of weeks/months) for participating households before and after the project | Participating households have the greatest food gap in the selected areas. (The number of food deficit months range from 1 to 10) | Evaluation to be carried out during the third and fourth year of implementation of the project. | Participating households have decreased their food gap by at least 50%
Output 3.1: Approx. 300,000 trees for revenue generation and food planted in protected areas. | Number of trees planted and growing in protected areas; amount of food and revenue gained from these. | Baseline to be established as part of adaptation plan | A total of 3,166 households benefited from the project's support of providing 10,000 fruit trees (Mango, Lemon, Mandarin, Grapefruit, Orange, Goyaviers, etc.) to be planted in each household. This program was implemented with the support of Centre for Agricultural Research and Agricultural Development (CNRADA) and targeted two types of farms: 1. Family farms where the project has distributed and helped plant fruit trees in each household at the rate of 3 to 5 trees per household. It is a type of farming with a very high probability of success as the trees are inside the courtyard and a daily attention could be provided in terms of watering and maintenance by the beneficiaries. 2. Collective farms, fenced aeras covering areas ranging from 1 to 2 ha. The project has equipped these areas with basins and drip irrigation systems to ensure a regular watering and water saving. The program will be completed in November 2017 and the project will continue regular monitoring to ensure the success and ownership of the prjects by the beneficiaries. • 19 project sites in the 8 regions • 10 300 fruit trees planted • 3 166 households concerned • 18 770 direct beneficiaries Also, in the 25 protected areas, 89 000 local fruit trees (Acacia senegal and Ziziphus) were planted to provide in the midterm addiational income to the targeted communities. | Planted trees already are – or have at least a clear prospect of – providing substantial amounts of food and income
Output 3.2: 4,000 technical staff and community leaders trained in livestock management, agricultural techniques and water utilization. | Number of people (gender disaggregated) trained |  | The project trained/coached about 11 000 participants in different activity technics as detailed in the follwing table: Training topic Nber of participants Women Men Veterinary assistants 35 1 34 High value crop production 8 728 6 982 1746 vegetable conservation 89 84 5 Cooperative management 80 28 52 Apiculture 517 284 233 Poultry farming 500 400 100 Fruit farming 2147 Soil and Water conservation 1 084 | Extension staff and cluster population are aware of and apply appropriate techniques
Output 3.3: 5,000 technical staff and community leaders trained and equipped for plant/seed multiplication. | Number of people (gender disaggregated) trained | Hardly any training is available in areas to be selected; extension staff requires training, too | High Value Crop production 37 women's cooperatives totaling 8 728 households received direct support from the project. First, trainings on gardening techniques and cooperative management were provided. The project then provided fence material, horticultural equipment, high quality seed and solved for a large part of the sites, the water-related problems by providing digging or deepening of wells and installing water pumping equipment mainly solar pumps or diesel motor pumps. On site technical support was also provided during the two campaigns 2016 and 2017 to transmit to these cooperatives the know-how of the activity and to prepare them to become autonomous in the management of their vegetable gardens without any external support in order to ensure the sustainability of the activity. During the 2016/2017 season, 52 ha were cultivated with a total production of 52 tonnes of vegetables with an average yield per hectare of approximately 994 kg. Each cooperative produced an average of 1400 kg, of which 350 kg were consumed locally or preserved and 1050 kg have been sold to generate additional income. Average revenue per cooperative was valued at MRO 305,000. | Extension staff and cluster population are aware of and apply appropriate techniques
Output 3.4: 4,000 technical staff and community leaders trained and equipped for poultry development. | Number of people (gender disaggregated) trained | Hardly any training is available in areas to be selected; extension staff requires training, too | 10 semi-intensive poultry houses and 40 traditional poultry houses were set up at 50 project sites, benefiting 500 families belonging to women's cooperatives and aiming at diversifying their income, improving food security and nutritional quality in poor rural areas. The 10 women's cooperatives for semi-intensive poultry houses are completely autonomous. They all started producing on their own without the support of the project. One of the Trarza's cooperative even reinvested a portion of the profits to expand the poultry house and increase the production's capacity to supply more villages nearby. In figures, the net benefits for 10 women producing a band of 500 chickens is MRO 409,130. The income per band and per woman is about MRO 40,913 and the income per woman per day is MRO 1364. Beyond the provision of white meat to the community, which improves food safety and nutritional quality in general, this activity has allowed profits which could be reinvested in other IGAs to help families to be more resilient. Traditional poultry houses have been established in isolated areas. The production of eggs and meat will allow in the medium term to improve the nutritional quality for families and especially for children and have benefits that will help better withstand the most difficult periods of the year.. This Programme was completed in April 2017. The project shoud ensure a follow up of these activities in order to make sure that all theseactivities could continue in the future without any support from the project. | Extension staff and cluster population are aware of and apply appropriate techniques
Output 3.5: 1,600 technical staff and community leaders trained and equipped for apiculture. | Number of people (gender disaggregated) trained | Hardly any training is available in areas to be selected; extension staff requires training, too | Eight Sites were targeted in 05 Wilayas where all the ecological and social conditions are met to guarantee the success of this activity. 2 sites in Trarza (Oum El Koura and Nassra 2), 3 sites in Gorgol (Haddad, Dimechgha and Dar El Beidha), 1 site in Brakna (Dounguel Réo), 1 site in Guidimakha (Ndeo) and 1 site in Tagant (Legdeim ). WFP supervised the procurement of equipment needed for the Programme implementation. The project hired Apidesert, a local specialised compagny, to oversee the Programme implementation and beneficiaries’ trainings. In each site an apiary of 30 hives was set up benefiting 10 families (480 bénéficiaires). The project also provided all the equipment necessary for the practice of beekeeping (Combinations, smokers, honey extractors, etc.) and provided the necessary training and technical supervision to ensure the success of the program. This program is currently in the Production phase and is scheduled to be finalized in March 2018. This activity is on the one hand very profitable economically, but it is very fragile on the other hand. It's necessary to continue the support to cover several technical issues related to the management and the maintenance of the apiaries. The project will document all the stages of the establishment of an apiary to ensure dissemination and scaling-up with other projects. It's important to note that the Apiculture is an innovative activity which was unknown in Mauritania and the majority of our communities did not find much interest. It requires favorable ecological and social conditions to be implmented. Another problem that has slowed down the implementation of the program is the severe climatic conditions, particularly the periods of high heat which delayed the activity’s implementation. This make that we will not be able to consume the planned budget. The project will focus on the finalization of the identified programme in the sites and work on capacity building of beneficiaries and regional technical services to ensure a follow up. It will also focus on creating small young artisan’s enterprises which will be able to manufacture the various products needed for beekeeping activities (hives, wax, etc.). An amount of 65 416 USD will be saved which we propose to reallocate to Output 3.4 (poultry development.) where there is still a demand for support and training. | Extension staff and cluster population are aware of and apply appropriate techniques
Output 3.6: Approx. 20 community cereal banks established. | Number of functioning village cereal bank associations; volume of cereals and money in bank. | No village-owned cereal banks exist in areas to be selected | n/a | Participating communities own their VCB, membership, money and food held by associations is stable
Output 3.7: 30,000 fuel efficient stoves provided. | Number of fuel efficient stoves built by participating communities; share of reduced consumption of fuel wood | Fuel-efficient stoves are hardly know and available in areas to be selected – to be confirmed during adaptation planning (The communities of 10 villages already use improved stoves) | n/a | Communities know, understand and use fuel efficient stoves; fuel-wood consumption by participating households reduced by at least 40%
Output 3.8: 2,000 community members (mostly youth) trained to build and maintain fuel efficient stoves. | Number of people (gender-disaggregated) trained | No training is available in areas to be selected; extension staff requires training, too. 14 artisans are already trained to manufacture improved stoves) | n/a | In all participating communities a group of people regularly builds and repairs fuel-efficient stoves;

## Lessons Learned
QUALITATIVE MEASURES and LESSONS LEARNED
Please complete the following section every reporting period
Implementation and Adaptive Management | Response
What implementation issues/lessons, either positive or negative, affected progress? | The lesson learned that we can point out is the establishment of a framework agreement with the Center for Traning of Rural Producers (CFPR) of Boghé which is under the supervision of ENFVA (National School of Agricultural Extension and Training) of the Ministry of Agriculture. CFPR has the infrastructure, equipments, knowledge and manpower to carry out training activities for beneficiaries identified in the ACC action plans. This framework agreement benefit the project in many aspects such as precious time saved during tendering of procurement procedures. Contracts are signed on the basis of the execution of the training program and according to standards agreed in advance.
Were there any delays in implementation? If so, include any causes of delays. What measures have been taken to reduce delays? | During the rainy season (June-August), many project sites become inaccessible due to the impracticability of the terrain. This situation is very cumbersome and causes a slowdown in the execution of activities. Also, DREDD as Regional responsibles for the environmental sector are fully busy with the bushfire campaign that runs from September to December of each year. In this period there is a lack in supervising project activity execution. NGOs recruitment at the beginning of 2017, helped attenuate this problem and improved the supervision of the project activities. Procurement tender procedures contributed also in delaying implementation. Sometimes qualified or suitable candidates are not always available.
Describe any changes undertaken to improve results on the ground or any changes made to project outputs (i.e. changes to project design) | The project Mid-term review underligned for Component 2, after two years of implementation and monitoring of Project's achievements, on one hand, differences, sometimes very considerable, between the initial unit costs considered in the project document and the actual costs (sand dune fixation, fuel wood plantation and vulnerable area protection). In the other hand, there was some difficulties of programming areas as initially planned, like in the case of fuel-wood village reforestation due to land ownership, regulatory and social constraints. So adjustments for the budgets and targets were proposed by the MTR for the Outputs 2.1, 2.2 and 2.3. to be realistic (see MTR report and information letter to the AF Secretariat). Also, for Component 3, there is a requested to make changes in Output 3.6. The evaluation of village cereal banks activity in Mauritania, as indicated in the rating, was negative and the EE requests to reallocate the budget initially planned for this output to Output 3.2 and 3.3 in order to implement Income Gnerating Activities and resolve water related problems still existing in many project sites. A formal request for the AF Board will be prepared shortly. | ;
How have gender considerations been taken into consideration during the reporting period? What have been the lessons learned as a consequence of inclusion of such considerations on project performance or impacts? | Gender have been taken into consideration during the elaboration of participatory adaptation action planning. Indeed, special attention was given to the gender aspect in income generating activities such as poultry (ratio of 80% women and 20% men), Apiculture and high valued crop production (ratio of 50% women and 50% men)
Please complete the following section at mid-term and project completion
Lessons for Adaptation | Response
Climate Resilience Measures
What have been the lessons learned, both positive and negative, in implementing climate adaptation measures that would be relevant to the design and implementation of future projects/programmes for enhanced resilience to climate change? | The lesson learned that we can point out is the inter-sectoral participation in developing local adaptation to climate change action plans. Knowing that climate change is a transversal issue, the key success factors to elaborate and implement adaptation planning are tied to the close collaboration and participation of all sectoral institutions at the regional level, thus capacity building programme in integrating adaptation to climate change into local development planning has concerned not only DREDD, but also decentralized technical services and NGO at regional level. Also, the future projects/programmes should be designed in smaller areas looking for convergence and integration with others partners. Integrating many activities in a same village will build a real resilience to climate change. Future projects/programmes for enhenced resilience to climate change should run over more than 4 years to maximise efficiency.
What is the potential for the climate resilience measures undertaken by the project/programme to be replicated and scaled up both within and outside the project area? | Replication and upscaling of many of the project interventions is already done by beneficiairies in many project villages (traditional poultry farming, High crop production, Soil and water conservation building structures...). Mauritania AF project is now considered as the leading Climate Change project within MEDD and many other environmental projects are now seeking synergies to benefit from its experience.
Concrete Adaptation Interventions
What have been the lessons learned, both positive and negative, in implementing concrete adaptation interventions that would be relevant to the design and implementation of future projects/programmes implementing concrete adaptation interventions? | Activities should be implemented by the communities themselves. Communities often have the know-how to implement several activities that require just a simple development to give more efficiency. A short training on these techniques gives them the ability to do things better. Beneficiaries must also be taught to the concept of partnership in carrying out activities as well as ownership to feel they are owners of assets and thus maintain their sustainability. This ensures that assets created under the project can be maintained and extended even beyond the duration of the project. So we have to build on the technical capacity of communities that have been able for centuries to adapt to the various changes which have occurred.
What is the potential for the concrete adaptation interventions undertaken by the project/programme to be replicated and scaled up both within and outside the project area? | The potential is strong.
Community/National Impact
What would you consider to be the most successful aspects for the target communities? | The problem of access to water is a central issue for adaptation to climate change. By partially addressing these aspects, the project has substantially contributed to strengthening community resilience in various areas: agriculture, livestock, drinking water, and so on.
What measures are/have been put in place to ensure sustainability of the project/program results? | The project has a strategy to deal with the project activities sustainability. It is based on three axes: Axis 1: Strengthening the capacity of DREDDs and decentralized technical services: These structures will continue their support to the communities after the project closes and even to extend this support to other groups of villages and regions. Axis 2: Capacity-development of targeted communities, particularly in management and technical issues (management of cooperatives, cropping techniques, seed production techniques, planting techniques, dune fixation techniques, Soil and Water conservation techniques, etc.). These capacities can be replicated beyond the project itself, and in some sites the effects are already evident: Some of project communities are investing by their own to expand an activity (case of poultry farming) or rehabilitate / maintain some assets (rehabilitation of small dams). Axis 3: Sensitization of the beneficiaries for the appropriation of the activities implemented by demonstrating their impact on the improvement of their livelihoods and their standard of living as well as their contribution to the improvement of their food security. This role is assigned to NGOs hired by the project since March 2017 which provide a proximity accompaniment for beneficiaries to a better appropriation of the achievements of the project. The project is also working with the NGOs to formalize the Village Management Committees so that they will have status allowing them to apply for funding from the donors and consolidate the implemented activities.
What measures are being/could have been put in place to improve project/program results?
Knowledge Management
How has existing information/data/knowledge been used to inform project development and implementation? What kinds of information/data/knowledge were used? | The project used different existing data sources to conduct vulnerability analyzes; namely data from FSMS surveys of WFP/CSA, ONS demographic data, and village surveys carried out by the project. We also used the data of the different national communications of Mauritania and Monotoring System the the Environmental National Action Plan (SEPANE).
If learning objectives have been established, have they been met? Please describe. | Yes, as indicated in the project's annual reports, several government focal points and central and regional level as well as representatives of civil society have been trained on several aspects such as climate change issues, participatory adaptation planning at local level. Also, members of the target communities were trained on different topics (High value crop production technics, cooperative management, poultry farming techniques, beekeeping techniques, dune fixation techniques, water and soil conservation work, planting techniques, management of pastoral reserves ...)
Describe any difficulties there have been in accessing or retrieving existing information (data or knowledge) that is relevant to the project. Please provide suggestions for improving access to the relevant data. | N/A
Has the identification of learning objectives contributed to the outcomes of the project? In what ways have they contributed? | The project consultation process before the implementation has given specially learning opportunities for the regional technical services and local administrative authorities. Its participatory approach engaged the different stakeholders in a way by which they learned about climate change, its impacts on food security and the necessity to adapt to safeguard natural resources and livelihoods against climate impacts. During the project implementation, on-the job training, along with the different course trainings, technical support, and other forms of learning has enabled the different stakeholder groups to realize how they can effectively contribute to building resilience. All this has enhanced capacities of all stakholders to contributing to the different project outcomes.

## Results Tracker
Results Tracker for Adaptation Fund (AF) Projects
Goal: Assist developing-country Parties to the Kyoto Protocol that are particularly vulnerable to the adverse effects of climate change in meeting the costs of concrete adaptation projects and programmes in order to implement climate-resilient measures. Impact: Increased resiliency at the community, national, and regional levels to climate variability and change.
Important: Please read the following guidance document (also posted on the Adaptation Fund website) before entering your data
Link: http://www.adaptation-fund.org/sites/default/files/Results%20Framework%20and%20Baseline%20Guidance%20final.pdf
Adaptation Fund Strategic Results Framework
Project ID | MTN/MIE/Food/2011/1/PD
Implementing Entity | WFP, Mauritania
Type of implementing entity | MIE
Country | Mauritania
Region | Africa
Sector | Food security
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Impact: Increased resiliency at the community, national, and regional levels to climate variability and change | Core Indicator: No. of beneficiaries |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project
|  | Total | 186718 | 37368 | 149350 | Total | 160590 | 23670 | 136920 | Total | 144769 | 20848 | 123921 | Total
|  | % of female beneficiaries | 59.15% |  |  | % of female beneficiaries | 50% | 50% | 50% | % of female beneficiaries | 61% | 61% | 61% | % of female beneficiaries
|  | % of Youth beneficiaries | 43.6% |  |  | % of Youth beneficiaries | 8% | 8% | 8% | % of Youth beneficiaries |  |  |  | % of Youth beneficiaries
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 1: Reduced exposure to climate-related hazards and threats | Indicator 1: Relevant threat and hazard information generated and disseminated to stakeholders on a timely basis | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness
|  | Total |  |  |  | Total |  |  |  | Total |  |  |  | Total
|  | % of female targeted |  |  |  | % of female targeted |  |  |  | % of female targeted |  |  |  | % of female targeted
Output 1.1 Risk and vulnerability assessments conducted and updated | Indicator 1.1: No. of projects/programmes that conduct and update risk and vulnerability assessments | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
Output 1.2 Targeted population groups covered by adequate risk reduction systems | Core Indicator 1.2: No. of Early Warning Systems | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  | 0 | 3: Dissemination and communication | Geographical coverage | Regional | 1 | 3: Dissemination and communication | Geographical coverage | Regional | 0 | 3: Dissemination and communication | Geographical coverage | Regional |  |  | Geographical coverage
|  |  |  | Number of municipalities | 0 |  |  | Number of municipalities | 75 |  |  | Number of municipalities | 0 |  |  | Number of municipalities
|  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 2: Strengthened institutional capacity to reduce risks associated with climate-induced socioeconomic and environmental losses | Indicator 2: Capacity of staff to respond to, and mitigate impacts of, climate-related events from targeted institutions increased | Number of staff targeted |  | Sector | Capacity level | Number of staff targeted |  | Sector | Capacity level | Number of staff targeted |  | Sector | Capacity level | Number of staff targeted |  | Sector | Capacity level
|  | Total | 300 | Multi-sector | 1: No capacity | Total | 300 | Multi-sector | 3: Medium capacity | Total | 213 | Multi-sector | 3: Medium capacity | Total
|  | % of female targeted | 10% |  |  | % of female targeted | 10% |  |  | % of female targeted | 10.33% |  |  | % of female targeted
Output 2.1 Strengthened capacity of national and sub-national centres and networks to respond rapidly to extreme weather events | Indicator 2.1.1: No. of staff trained to respond to, and mitigate impacts of, climate-related events | Total staff trained | % of female staff trained | Type |  | Total staff trained | % of female staff trained | Type |  | Total staff trained | % of female staff trained | Type |  | Total staff trained | % of female staff trained | Type
|  | 180 | 10% | Public |  | 180 | 10% | Public |  | 118 | 6.78% | Public
|  | 120 | 10% | NGO |  | 120 | 10% | NGO |  | 95 | 14.74% | NGO
| Indicator 2.1.2: No. of targeted institutions with increased capacity to minimize exposure to climate variability risks | Type | Scale | Sector | Capacity level | Type | Scale | Sector | Capacity level | Type | Scale | Sector | Capacity level | Type | Scale | Sector | Capacity level
|  | Public | National | Multi-sector | 1: No capacity | Public | National | Multi-sector | 3: Medium capacity | Public | National | Multi-sector | 3: Medium capacity
|  | Public | Regional | Multi-sector | 1: No capacity | Public | Regional | Multi-sector | 3: Medium capacity | Public | Regional | Multi-sector | 3: Medium capacity
|  | NGO | Regional | Multi-sector | 1: No capacity | NGO | Regional | Multi-sector | 3: Medium capacity | NGO | Regional | Multi-sector | 2: Low capacity
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 3: Strengthened awareness and owernship of adaptation and climate risk reduction processes | Indicator 3.1: Increase in application of appropriate adaptation responses | Percentage of targeted population applying adaptation measures |  | Sector |  | Percentage of targeted population applying adaptation measures |  | Sector |  | Percentage of targeted population applying adaptation measures |  | Sector |  | Percentage of targeted population applying adaptation measures |  | Sector
Output 3: Targeted population groups participating in adaptation and risk reduction awareness activities | Indicator 3.1.1: Percentage in targeted population awareness of predicted adverse impacts of climate change, and of appropriate responses | No. of targeted beneficiaries | % of female participants targeted | Level of awareness |  | No. of targeted beneficiaries | % of female participants targeted | Level of awareness |  | No. of targeted beneficiaries | % of female participants targeted | Level of awareness |  | No. of targeted beneficiaries | % of female participants targeted | Level of awareness
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Target performance at completion
Outcome 4: Increased adaptive capacity within relevant development sector services and infrastructure assets | Indicator 4.1: Increased responsiveness of development sector services to evolving needs from changing and variable climate | Project/programme sector | Geographical scale | Response level |  | Project/programme sector | Geographical scale | Response level |  | Project/programme sector | Geographical scale | Response level |  | Project/programme sector | Geographical scale | Response level
| Core Indicator 4.2: Assets produced, developed, improved or strengthened | Sector | Targeted asset | Changes in asset (quantitative or qualitative) |  | Sector | Targeted asset | Changes in asset (quantitative or qualitative) |  | Sector | Targeted asset | Changes in asset (quantitative or qualitative) |  | Sector | Targeted asset | Changes in asset (quantitative or qualitative)
|  | Agriculture | 2: Physical asset (produced/improved/strenghtened) | 1: Not improved |  | Agriculture | 2: Physical asset (produced/improved/strenghtened) | 4: Mostly Improved |  | Agriculture | 2: Physical asset (produced/improved/strenghtened) | 3: Moderately improved
|  | Food security | 2: Physical asset (produced/improved/strenghtened) | 1: Not improved |  | Food security | 2: Physical asset (produced/improved/strenghtened) | 4: Mostly Improved |  | Food security | 2: Physical asset (produced/improved/strenghtened) | 4: Mostly Improved
|  | Water management | 2: Physical asset (produced/improved/strenghtened) | 1: Not improved |  | Water management | 2: Physical asset (produced/improved/strenghtened) | 4: Mostly Improved |  | Water management | 2: Physical asset (produced/improved/strenghtened) | 3: Moderately improved
|  | Other | 2: Physical asset (produced/improved/strenghtened) | 1: Not improved |  | Other | 2: Physical asset (produced/improved/strenghtened) | 4: Mostly Improved |  | Other
Output 4: Vulnerable development sector services and infrastructure assets strengthened in response to climate change impacts, including variability | Indicator 4.1.1: No. and type of development sector services to respond to new conditions resulting from climate variability and change | Number of services | Type |  | Sector | Number of services | Type |  | Sector | Number of services | Type |  | Sector | Number of services | Type |  | Sector
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Baseline information
Outcome 5: Increased ecosystem resilience in response to climate change and variability-induced stress | Indicator 5: Ecosystem services and natural resource assets maintained or improved under climate change and variability-induced stress | Natural resource improvement level |  | Sector | Type | Natural resource improvement level |  | Sector | Type | Natural resource improvement level |  | Sector | Type | Natural resource improvement level |  | Sector | Type
Output 5: Vulnerable ecosystem services and natural resource assets strengthned in response to climate change impacts, including variability | Core Indicator 5.1: Natural Assets protected or rehabilitated | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Rangelands | 1000 | ha protected | 1: Ineffective | Rangelands | 1000 | ha protected | 4: Effective | Rangelands | 1000 | ha protected | 4: Effective
|  | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Catchment area/Watershed/Aquifer | 500 | ha protected | 1: Ineffective | Catchment area/Watershed/Aquifer | 500 | ha protected | 4: Effective | Catchment area/Watershed/Aquifer | 300 | ha protected | 4: Effective
|  | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Forests | 1500 | ha protected | 1: Ineffective | Forests | 1500 | ha protected | 4: Effective | Forests | 273 | ha protected | 4: Effective
|  | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Cultivated land/Agricultural land | 1000 | ha rehabilitated | 1: Ineffective | Cultivated land/Agricultural land | 1000 | ha rehabilitated | 4: Effective
|  | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Other | 2000 | ha protected | 1: Ineffective | Other | 2000 | ha protected | 4: Effective | Other | 525 | ha protected | 4: Effective
|  | Baseline information |  |  |  | Targeted performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 6: Diversified and strengthened livelihoods and sources of income for vulnerable people in targeted areas | Indicator 6.1: Increase in households and communities having more secure access to livelihood assets | No. of targeted households | % of female headed households | Improvement level |  | No. of targeted households | % of female headed households | Improvement level |  | No. of targeted households | % of female headed households | Improvement level |  | No. of targeted households | % of female headed households | Improvement level
| Indicator 6.2: Increase in targeted population's sustained climate-resilient alternative livelihoods | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
|  | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
|  | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
|  | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
Output 6 Targeted individual and community livelihood strategies strengthened in relation to climate change impacts, including variability | Indicator 6.1.1: No. and type of adaptation assets created or strengthened in support of individual or community livelihood strategies | Number of Assets | Type of Assets | Sector | Adaptation strategy | Number of Assets | Type of Assets | Sector | Adaptation strategy | Number of Assets | Type of Assets | Sector | Adaptation strategy | Number of Assets | Type of Assets | Sector | Adaptation strategy
| Core Indicator 6.1.2: Increased income, or avoided decrease in income | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | 16983 | Agricultural-related |  | 356.2333 |  | Agricultural-related |  |  | 12911 | Agricultural-related
|  | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | 72 | Fishing |  | 775.7767 |  | Fishing |  |  |  | Fishing
|  | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | 688 | Forestry |  | 372.36 |  | Forestry |  |  | 979 | Forestry
|  | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | 15069 | Livestock production |  | 1115.2 |  | Livestock production |  |  | 720 | Livestock production
|  | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | 3090 | Services |  | 1563.3067 |  | Services |  |  | 35 | Services
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 7: Improved policies and regulations that promote and enforce resilience measures | Indicator 7: Climate change priorities are integrated into national development strategy | Integration level |  |  |  | Integration level |  |  |  | Integration level |  |  |  | Integration level
Output 7:Improved integration of climate-resilience strategies into country development plans | Indicator 7.1: No. of policies introduced or adjusted to address climate change risks | No. of Policies introduced or adjusted | Sector | Scale | Type | No. of Policies introduced or adjusted | Sector | Scale | Type | No. of Policies introduced or adjusted | Sector | Scale | Type | No. of Policies introduced or adjusted | Sector | Scale | Type
| Indicator 7.2: No. of targeted development strategies with incorporated climate change priorities enforced | No. of Development strategies | Regulation |  | Effectiveness | No. of Development strategies | Regulation |  | Effectiveness | No. of Development strategies | Regulation |  | Effectiveness | No. of Development strategies | Regulation |  | Effectiveness
Glacier lake outburst flood
|  | Inland flooding | fr | biological assets |  | Company policy | 5: Fully enforced (All elements implemented)
|  | Salinization | Decrease | land |  | Communication & Information policy | 4: Enforced (Most elements implemented)
|  | Drought | Same | water areas |  | Defense policy | 3: Partially enforced (Some elements implemented)
|  | Wind |  | subsoil assets | increased adpative capacity | Domestic policy | 2: Partially not enforced (Most elements not implemented) |  | Agribusiness
|  | Coastal flooding |  | air | achieved | Economic policy | 1: Not enforced (No elements implemented) |  | Agricultural-related | Financial capital
|  | Storm surge | Please choose |  | enhanced level of protection | Education policy |  |  | Agriculture | Human capital
|  | Hurricane | Selected | [5 empty] | Aquaculture | Physical capital
|  |  | Not relevant |  |  | 5: All (Fully integrated) |  |  | Construction/repairing business | Social capital
[6 empty] | 4: Most |  |  | Cultivation | Natural capital
[6 empty] | 3: Some |  |  | Fishing | Personal capital
Select | 5: All | Select |  |  | Community | 2: Most not integrated |  | Other | Forestry | Adaptation strategies
1 | 4: Almost all | Private | Type | Yes | Multi-community | 1: None |  | Agriculture | Handicrafts
2 | 3: Half | Public | Scale | No | Departmental |  |  | Coastal management | Livestock production
3 | 2: Some | NGO | Sector |  | National |  |  | Disaster risk reduction | Manufacturing
4 | 1: None |  |  |  |  | 5: Very high improvement | Established | Food security | other
|  | National |  |  |  | 4: High improvement | Maintained | Health | Services
|  | Regional |  |  |  | 3: Moderate improvement | Improved | Urban development | Tourism-related
|  | Local |  |  |  | 2: Limited improvement |  | Water management | Trading
[6 empty] | 1: No improvement |  | Multi-sector
|  | 1 -generated information is irrelevant, and neither the stakeholders reached nor the timeframe managed were achieved | 1: No info transferred on time | 4: High capacity | 5: Fully aware | 5: Highly responsive (All defined elements ) | 5: Fully improved | Roads | 5: Very effective
Asia-Pacific | NIE | 2 -the existence of some challenge in any of the three aspects of the indicator (generation of dissemination, stakeholders reached or timeframe managed) | 2: Somewhat info transferred | 3: Medium capacity | 4: Mostly aware | 4: Mostly responsive (Most defined elements) | 4: Mostly Improved | Gov Buildings | 4: Effective
Latin America and Caribbean | RIE | 3 -relevant information is generated and disseminated to all identified stakeholders on timely basis | 3: Info transferred on time | 2: Low capacity | 3: Partially aware | 3: Moderately responsive (Some defined elements) | 3: Moderately improved | Causeways | 3: Moderately effective
Africa | MIE |  |  | 1: No capacity | 2: Partially not aware | 2: Partially responsive (Lacks most elements) | 2: Somewhat improved | Airports | 2: Partially effective
Eastern Europe |  |  |  |  | 1: Aware of neither | 1: Non responsive (Lacks all elements ) | 1: Not improved | Schools | 1: Ineffective
| ha protected | [6 empty] | Training Centres
| ha rehabilitated | [5 empty] | Monitoring/Forecasting capacity | Hospitals
Afghanistan, Islamic Rep. of | km protected | [5 empty] | Policy/regulatory reform | Drinking water systems
Angola | km rehabilitated | 1: Risk knowledge | 1: No plans conducted or updated |  |  |  | Capacity development | Other
Albania |  | 2: Monitoring and warning service | 2: Undertaking or updating of assessments in progress |  |  | Communication & Information policy | Sustainable forest management
Argentina |  | 3: Dissemination and communication | 3: Risk and vulnterability assessments completed or updated |  |  | Domestic policy | Strengthening infrastructure | 1: Health and Social Infrastructure (developed/improved)
Armenia | Forests | 4: Response capability |  |  |  | Economic policy | Supporting livelihoods | 2: Physical asset (produced/improved/strenghtened)
Antigua and Barbuda | Mangroves |  |  |  |  | Education policy | Mangrove reforestation
Azerbaijan | Coasts |  | From 0 to 0.5% |  |  | Energy policy | Coastal drainage and infrastructure
Burundi | Rangelands |  | From 0.5 to 1% |  |  | Environmental policy | Irrigation system
Benin | Cultivated land/Agricultural land |  | From 1% to 5% |  |  | Foreign policy | Community-based adaptation
Burkina Faso | Catchment area/Watershed/Aquifer |  | From 5% to 10% |  |  | Health policy | Erosion control
Bangladesh | Protected areas/National parks |  | From 10% to 20% |  |  | Housing policy | Soil water conservation
Bulgaria | Other |  | From 20% to 30% |  |  | Human resource policies | Microfinance
Bahrain |  |  | From 30% to 40% |  |  | Information policy | Special Program for women
Bahamas, The |  |  | From 40% to 50% |  |  | Macroeconomic policy | Livelihoods
Bosnia and Herzegovina |  |  | Above 50% |  |  | Monetary policy | Water storage
Belarus | [5 empty] | Population policy | ICT and information dissemination
Belize | [5 empty] | Private policy
Bolivia | [5 empty] | Public policy
Brazil | [5 empty] | Science policy
Barbados | [5 empty] | Social policy
Bhutan |  | 3- relevant information is generated and disseminated to all identified stakeholders on timely basis |  |  |  | Transportation policy
Botswana |  | describe |  |  |  | Urban policy
Central African Republic |  | 2- the existence of some challenge in any of the three aspects of the indicator |  |  |  | Water policy
Chile |  | describe |  |  |  | Other policy
China, People's Republic of |  | 1- generated information is irrelevant and neither the stakeholders reached nor the timeframe managed were achieved
Cote d'Ivoire |  | describe
Cameroon
Congo, Dem. Rep. of
Congo, Republic of
Cook Islands
Colombia
Comoros
Cape Verde
Costa Rica
Cuba
Czech Republic
Djibouti
Dominica
Dominican Republic
Algeria
Ecuador
Egypt
Eritrea
Estonia
Ethiopia
Fiji
Micronesia, Fed. States of
Gabon
Georgia
Ghana
Guinea
Gambia, The
Guinea-Bissau
Equatorial Guinea
Grenada
Guatemala
Guyana
Honduras
Croatia
Haiti
Hungary
Indonesia
India
Iran, Islamic Republic of
Jamaica
Jordan
Kazakhstan
Kenya
Kyrgyz Republic
Cambodia
Kiribati
Saint Kitts and Nevis
Korea, Republic of
Lao People's Democratic Republic
Lebanon
Liberia
Libya
Saint Lucia
Sri Lanka
Lesotho
Lithuania
Latvia
Morocco
Moldova
Madagascar
Maldives
Mexico
Marshall Islands
Macedonia, former Yugoslav Republic of
Mali
Malta
Myanmar
Montenegro
Mongolia
Mozambique
Mauritania
Mauritius
Malawi
Malaysia
Namibia
Niger
Nigeria
Nicaragua
Niue
Nepal
Nauru
Oman
Pakistan
Panama
Peru
Philippines
Palau
Papua New Guinea
Poland
Korea, Dem. People's Rep. of
Paraguay
Romania
Russian Federation
Rwanda
Saudi Arabia
Sudan
Senegal
Solomon Islands
Sierra Leone
El Salvador
San Marino
Serbia
Sao Tome and Principe
Suriname
Slovak Republic
Slovenia
Swaziland
Seychelles
Syrian Arab Republic
Chad
Togo
Thailand
Tajikistan
Turkmenistan
Tonga
Trinidad and Tobago
Tunisia
Turkey
Tuvalu
Tanzania
Uganda
Ukraine
Uruguay
Uzbekistan
Saint Vincent and the Grenadines
Venezuela
Vietnam
Vanuatu
Samoa
Yemen, Republic of
South Africa
Zambia
Zimbabwe
Timor-Leste
Note on H102: GADER Ghazi: Sand dune fixation
Note on K119: GADER Ghazi: Income level will be evaluated after the project termination
Note on L119: GADER Ghazi: Ménages ayant bénéficiés des activités : Maraichage, Aviculture, Arboriculture, Apiculture
Note on L127: GADER Ghazi: Veterinary Assistnants

## Units for Indicators
Fund Outcome Indicator Units
1. Generation of relevant data, Stakeholders, and Timeliness 2.1. Include both qualitative and quantitative measures of capacity level within targeted institutions 2.2. Number (men and women and other vulnerable groups) 3.1. Use scale from 1 to 5: 5: Fully aware 4: Mostly aware 3: Partially aware 2: Partially not aware 1: Aware of neither predicted adverse impacts of climate change nor of appropriate responses 3.2. Use scale from 1 to 5: 5: All 4: Almost all 3: Half 2: Some 1: None 4.1. Summarize in an overall scale (1-5): 5: Highly responsive (All defined elements ) 4: Mostly responsive (Most defined elements) 3: Moderately responsive (Some defined elements) 2: Partially responsive (Lacks most elements) 1: Non responsive (Lacks all elements ) 4.2. Summarize in an overall scale (1-5): 5: Fully improved 4: Mostly Improved 3: Moderately improved 2: Somewhat improved 1: Not improved 5. Depends on the targeted natural asset: Biological (species): measure through changes in population numbers (dynamics, structure, etc.) Land: measure changes in hectares. Baseline data will be necessary to estimate the change. Supporting indicators baseline and target (as well as contextual information) are needed such as the following: Farmers adopting recommended technologies, Ha. of land improved, Average deforestation rate Etc. Use scale from 1 to 5. 5: Very effective (All elements are present) 4: Effective (Most elements are present) 3: Moderately effective (Some elements are present) 2: Partially effective (Most elements are not present) 1: Ineffective (No elements are present) 6.1. Summarize in an overall scale (1-5): 5: Very high improvement 4: High improvement 3: Moderate improvement 2: Limited improvement 1: No improvement 6.2. Household income by source of livelihood in project area (USD) prior and post project intervention 7. Summarize in an overall scale (1-5). 5: All (Fully integrated) 4: Most 3: Some 2: Most not integrated 1: None
Fund Output Indicator Units
1.1. Number, sector(s) and level(s) of projects or interventions in separate fields of monitoring plan 1.2. Number 2.1.1. Number of staff (male/female) of targeted institutions: a. Obtain baseline information: total number of staff from targeted institutions b. Define target 2.1.2. Number of staff (male/female) of targeted institutions: a. Obtain baseline information: total number of staff from targeted institutions b. Define target: needs to be defined by project proponents 2.2.1. Quantitative: Percentage (includes women – and other vulnerable groups – and men). Qualitative: Adequacy: include direct analysis of major areas; adequacy/effectiveness of systems or analysis of perceptions of populations and institutions. 2.2.2. Number (broken down by gender and, if possible, by vulnerable groups defined in the area of intervention) of people 3.1. Number and type (in separate columns) at local level. 3.2. Number 4.1. Number and type 4. 2. Number and type (entered in separate columns) 5. Number of interventions by type of natural asset and intervention 6.1. Number and type (in separate columns of monitoring plan) 6.2. Income sources per household; description of income source and number of households. 7.1. Number/Sector 7.2. Number; Effectiveness (see previous indicator) through enforcement level.

## Financial annex
Explanatory notes on variances between planned and actual expenditures of outputs during the reporting period
ITEM / ACTIVITY / ACTION | Year 3 Actual amount spent US$ | Projected in Prodoc (US$) | Difference (negative amount indicates amount overspent) | % | Reason for over or underspending
Output 1.1 Eight DREDD (regional technical services of MEDD) strengthened to access and analyze climate change information, to monitor local development and to mobilize and support communities | 121633.2264 | 262500 | 140866.7736 | 46.34% | The hiring process of NGOs registered a very important delay and we started effectively in March 2017. So paiments to NGO partners only covered 6 months during the reporting period
Output 1.2 Strengthening of Government's threat, risk and vulnerability analysis | 31009.0094 | 56673.4911 | 25664.4817 | 54.72% | The establishment of an early warning system at the community level is still on standby because there are several initiatives at national level involving different partners that are not yet clear. The project preferred to wait for the evolution of these initiatives before engaging in the implementation of the EWS. It was decided to retain a very simple mechanism adapted to the needs of the target communities that will be deployed in partnership with the National Office of Meteorology, The Agro-Meteorological Services, the Radio and the DREDDs. An action plan is being prepared between the involved partner which will be implemented during the next year.
Output 1.3: 20 inter-village associations established and supported | 3344.442 | 24506.6667 | 21162.2247 | 13.65% | This output was assigned to NGO partners. The weak disbursement is due to the same reasons as for Output 1.1
Output 1.4:Communities trained in climate change threats and adaptation measures which reduce vulnerability, in particular related to food insecurity | 2675.5536 | 21797.0495 | 19121.4959 | 12.27% | This output was assigned to NGO partners. The weak disbursement is due to the same reasons as for Output 1.1
Output 1.5:100 villages, being clustered according to landscape, ecosystem and livelihoods, have prepared adaptation plans that are integrated into local development planning. | 4013.3304 | 24569.7555 | 20556.4251 | 16.33% | This output was assigned to NGO partners. The weak disbursement is due to the same reasons as for Output 1.1
Output 1.6: Communities share success stories and lessons learned, including support of 8 community radios | 0 | 100000 | 100000 | 0% | The delay in the implementation of the Radio Support Program for the sharing of good project practices has been deliberately shifted by the project to integrate the EWS as described in the rating and Project indicator sections. To note also that a framework agreement with the Radio has already been signed and imlplementation will start in november-december 2017
Output 1.7: Monitoring system in place (establishment, training, production of data and reports) to track climate events and ecologic development in project intervention zones. | 29036.2762 | 45000 | 15963.7238 | 64.53% | A delay on hiring the national consultant to setup the training programme on ecological monitiring system.
Output 2.1: 1500 - 2000 ha of sand dunes fixated | 152408.2328 | 225000 | 72591.7672 | 67.74% | As the reporting period ends on August 31, 2017, part of the budget specifically covering the cash payments of participants will only be spent during the months of September to November. This explains the remaining balances recorded. The ojective of implementing 1500 to 2000 ha of land dune fixation was non realistic. According to the MTR the potential objective which could be implmented is about 900 ha. This will need a total budget of about 1 020 872 USD, while the initial budget was 469 200 USD.
Output 2.2: 1000 - 1500 ha of vulnerable zones protected | 139774.9607 | 52000 | -87774.9607 | 268.8% | The total initial budget for this product is 703 500 USD. So far, the goal is fully achieved by implementing 1000 ha of protected areas with only 410 415 USD. We have budgeted 45 000 USD for the 4th year to continue the program of pastoral improvement and the training of management committees on the operating rules of these protected areas. The saved budget is reallocated to the dune fixation output which was underestimated.
Output 2.3 1,000-1,500 ha of community fuel wood forests planted. | 79454.2769 | 262500 | 183045.7231 | 30.27% | Cash distribution is still to be done for this activity from september to november 2017. The total initial budget for this output is 674 700 USD to implement 1000 to 1500 ha of community fuel wood forest plantations. However, due to land ownership, regulatory and social constraints, the potential area which could be covered planted is 400 ha. The MTR proposed adjustments for the initial budget and target for this output which will save about 303 587 USD to reallocate to Output 2.1 (Sand dune fixation) which was underestimated.
2.4 Water retention structures built covering approximately 500 ha | 123151.2757 | 225000 | 101848.7243 | 54.73% | The implementation is ongoing and will be finished in December 2017
Output 3.1 300,000 trees for revenue generation and food planted in protected areas | 102852.8343 | 112500 | 9647.1657 | 91.42% | Good progress
Output 3.2 4,000 technical staff and community leaders trained in livestock management, agricultural techniques and water utilization | 59173.7071 | 97500 | 38326.2929 | 60.69% | Part of the output was planned to be implemented by NGOs which started working only in March 2017
Output 3.3 5,000 technical staff and community leaders trained and equipped agro-pastoral IGA, including plant multiplication | 114783.6177 | 112500 | -2283.6177 | 102% | Progress according plannig
Output 3.4 6,000 technical staff and community leaders trained and equipped for poultry development | 103229.9335 | 15000 | -88229.9335 | 688.2% | It was planned to cover the programme in 2 years, but the project succeed to fully complete it during the reporting period.,with a slight budget overrun of USD 26 416. The project budgeted additional USD 39,000 for year 4 of the project implementation to follow-up achievements and work on the appraisal and sustainability especially of traditional poultry farming where there are still improvements to do. This budget will be taken from output 3.5 (Apiculture) that will not be fully consumed by the end of the project.
Output 3.5 1,000 technical staff and community leaders trained and equipped for apiculture | 11449.9336 | 52500 | 41050.0664 | 21.81% | The implementation of the program is still ongoing. It was naturally delayed because of the weather conditions with a very hot season which did not allow the delivery of hives. The program will be resumed in November 2017 and will run until March 2018 to work in the best possible condition for its success.
Output 3.6 Approx. 20 community cereal banks established. | 0 | 150000 | 150000 | 0% | The evaluation of previous interventions of various projects that supported this activty in Mauritania, showed that this experience was a failure both nationally and in the subregion. The difficulty lies in the fact that these investments require a very long work of accompaniment and follow-up of the VCB management committees. WFP CO is also not in favor of investing in BCVs that have week chance of success. The same observation was made by some governors of the project's intervention regions where the experience of VCB failed. The MEDD is rather favorable of reallocating the planned investments for this activity towards income-generating activities and solving water related problems which remains in many project intervention sites as it was requested in the rating section.
Output 3.7 30,000 fuel efficient stoves built | 0 | 97000 | 97000 | 0% | We noted a delay in launching the improved stove program due to the load plan and the reduced staff of PMU. The evaluation of the program has been launched with the support of a national consultant and implementation will begin at the end of 2017.
Output 3.8 2,000 community members (mainly youth) trained and equipped to build and maintain fuel efficient stoves | 0 | 45000 | 45000 | 0% | Same as Output 3.7
TOTAL | 1077990.6104 | 1981546.9628 |  | 54.4%