## Overview
Project Performance Report (PPR)
| Period of Report (Dates) | September 2015 - August 2016
| Project Title: | Enhancing Resilience of Communities to the Adverse effects of Climate Change on Food Security in Mauritania
Effects of Climate Change on Food Security in Mauritania
| Project Summary: | The Mauritania's Ministry of Environment and Sustainable Development and the United Nations World Food Programme initiated a four-year project to strengthen resilience and promote food security in 100 villages located in the Wilayas of Assaba, Brakna, Guidimakha, Gorgol, Hodh El Chergui, Hodh El Gharbi, Tagant and Trarza. The overall goal of the project aims to improve adaptation in the area of food security in Mauritania by assisting the government in improving technical services at the community level so that village residents, who will be most affected by climate change, can undertake their own analysis of climate change impacts and prepare detailed adaptation plans – including harmonized plans for livestock, land and water management and the overall use of natural resources. The project will also promote climate resilience by protecting threatened resources, such as dunes, community fuel wood forests, and water sources. Finally, villages will be encouraged to explore ways to diversify the sources of livelihood and receive training, coaching, and asset investments to do so. The project includes three components: Component 1: Support technical services and the communities they serve to better understand climate risks, their impacts on resources and food security; and facilitate decentralized and participatory adaptation planning. Component 2: Design and implement concrete adaptation measures identified through community adaptation planning that aim to combat desertification and land degradation. Component 3: Design and implement concrete adaptation measures identified through community adaptation planning that aim to diversify and strengthen the livelihoods of the most vulnerable population.
|  |  | Countries | Project Type: |  | GEF Focal Area: | GEF 4 Focal Areas | GEF 2 / 3 Operational Programme: | Overall Rating of the project in the evaluation by the project evaluator: | GEF-4 Focal Area Strategic Program: | GEF-3 Focal Area Strategic Program:
| Database Number: | MTN/MIE/Food/2011/1/PD | Afghanistan | FP | Yes | Biodiversity | 1 | 1 | U | BD-SP1-PA Financing | 1: Arid & semi-arid ecosystems
Implementing Entity (IE) [name]: |  | United Nations Word Food Programme (WFP) | Albania | MSP | No | Climate Change Adaptation | 2 | 2 | S | BD-SP2-Marine PA | 2: Coastal, marine & freshwater ecosystems
| Type of IE: | Multilateral | Algeria | EA |  | Climate Change Mitigation | 3 | 3 | MU | BD-SP3-PA Networks | 3: Forest ecosystems
| Country(ies): | Mauritania | Angola |  |  | International Waters | 5 | 5 | Good | BD-SP5-Markets | 13: Conservation and Sustainable Use of Biological Diversity Important to Agriculture
Relevant Geographic Points (i.e. cities, villages, bodies of water): |  | Wilaya of Assaba (12 villages); Wilaya of Brakna (12 villages); Wilaya of Gorgol (10 villages); Wilaya of Guidimakha (12 villages); Wilaya of Hodh El Chergui (15 villages); Wilaya of Hodh El Gharbi (14 villages); Wilaya of Tagant (9 villages); Wilaya of Trarza (16 villages) | Argentina |  |  | Multiple Focal Area |  |  |  | BD-SP7-Invasive Alien Species(IAS) | 6: Promoting the adoption of renewable energy by removing barriers and reducing implementation costs
[8 empty] | CC-SP2- Industrial EE | 8: Waterbody based operational program
| Project Milestones | [6 empty] | CC-SP3-RE,CC-SP4-Biomass | 9: Integrated Land and Water multiple focal area
| Milestone |  | Bahamas | [6 empty] | CC-SP5-Transport | 10: Contaminants based operational program
AFB Approval Date: |  | July 2012
IE-AFB Agreement Signature Date: |  | July 23 2012 | [6 empty] | CC-SP6-LULUCF | 12: Integrated Ecosystem Management
Start of Project/Programme: |  | August 14 2014 | [6 empty] | Cross cutting capacity building | 14: Persistent Organic Pollutants
Mid-term Review Date (if planned): |  | January 2017
| Terminal Evaluation Date: | May 2019
|  | List documents/ reports/ brochures / articles that have been prepared about the project. | Cyprus
|  | Brochure of the project Poster of the Project Guidance note for the prioritization of project areas Project inception report ACC training report for technical regional services - Kaédi 9-12 Mach 2015 ACC training report for technical regional services - Kiffa 6-9 April 2015 ACC training report for NGO, Kaédi et Kiffa 8-12 June 2015 ACC training report for government representatives at central level 7-9 July 2015 Monitoring Project Activities factsheets Project Progress Report 1st semester 2015 Assessment of nurseries' seedlings production 2015 Brochure - Climate Change Adaptation Planning Approach at Community Level Brochure -Review of the first year of project implementation Report of the assessment study on Soil and Water conservation Report of the assessment study of the promotion of poultry farming programme Report of the assessment study of the beekeeping promotion programme Report of the assessement study of the fruit trees promotion programme Report of the Veterinary Auxiliary Training Veterinary Auxiliaries training manuel Assessment of nurseries' seedlings production 2016 | Czech Republic
https://www.youtube.com/watch?v=TJXPh0mQb9c
https://www.wfp.org/stories/building-resilience-and-adaptive-capacity-communities-sahel
http://parsacc.yolasite.com/etudes-et-rapports.php
List the Website address (URL) of project. |  |  | Democratic People's Republic of Korea
|  | http://parsacc.yolasite.com | Democratic Republic of the Congo
Denmark
| Project contacts: |  | Djibouti
International Project Manager/Coordinator |  |  | Dominica
| Name: | Ghazi GADER, Project coordinator | Dominican Republic
| Email: | ghazi.gader@wfp.org | Ecuador
| Date: | 14-Agust-2014 | Egypt
| Government DA |  | El Salvador
| Name: | Sidi Mohamed El Wavi, National Project Director | Equatoral Guinea
| Email: | elwavi.sm@gmail.com | Eritrea
| Date: | 14-Agust-2014 | Estonia
| Implementing Entity |  | Ethiopia
| Name: | Yasuhiro TSUMURA, WFP Deputy Country Director | Fiji
| Email: | yasuhiro.tsumura@wfp.org | Finland
| Date: | Agust-2016 | France
| Executing Agency |  | Gambia
| Name: | Alioune FALL, Project coordinator Assistant | Georgia
| Email: | lunef@yahoo.com | Germany
| Date: | 14-August-2014 | Ghana
| Executing Agency |  | Greece
| Name: | Maouloud N'Diaye, M&E specialist | Grenada
| Email: | ndiaye.maouloud@gmail.com | Guatemala
| Date: | October-2015 | Guinea
| Executing Agency |  | Guinea Bissau
| Name: |  | Guyana
| Email: |  | Haiti
| Date: |  | Honduras
Hungary
Iceland
India
Indonesia
Iran (Islamic Republic of)
Iraq
Ireland
Israel
Italy
Jamaica
Japan
Jordan
Kazakhstan
Kenya
Kiribati
Kuwait
Kyrgyzstan
Lao People’s Democratic Republic
Latvia
Lebanon
Lesotho
Liberia
Libyan Arab Jamahiriya
Liechtenstein
Lithuania
Luxembourg
Madagascar
Malawi
Malaysia
Maldives
Mali
Malta
Marshall Islands
Mauritania
Mauritius
Mexico
Micronesia, Federated States of
Monaco
Mongolia
Montenegro
Morocco
Mozambique
Myanmar
Namibia
Nauru
Nepal
Netherlands
New Zealand
Nicaragua
Niger
Nigeria
Norway
Oman
Pakistan
Palau
Panama
Papua New Guinea
Paraguay
Peru
Philippines
Poland
Portugal
Qatar
Republic of Korea
Republic of Moldova
Romania
Russian Federation
Rwanda
Saint Kitts and Nevis
Saint Lucia
Saint Vincent and the Grenadines
Samoa
San Marino
Sao Tome and Principe
Saudi Arabia
Senegal
Serbia
Seychelles
Sierra Leone
Singapore
Slovakia
Slovenia
Solomon Islands
Somalia
South Africa
Spain
Sri Lanka
Sudan
Suriname
Swaziland
Sweden
Switzerland
Syrian Arab Republic
Tajikistan
Thailand
The former Yugoslav Republic of Macedonia
Timor-Leste
Togo
Tonga
Trinidad and Tobago
Tunisia
Turkey
Turkmenistan
Tuvalu
Uganda
Ukraine
United Arab Emirates
United Kingdom of Great Britain and Northern Ireland
United Republic of Tanzania
United States of America
Uruguay
Uzbekistan
Vanuatu
Venezuela, Bolivarian Republic of
Viet Nam
Yemen
Zambia
Zimbabwe

## FinancialData
3930312
Financial information: cumulative from project start to December 2016
DISBURSEMENT OF AF GRANT FUNDS | 3930312
How much of the total AF grant as noted in Project Document plus any project preparation grant has been spent to date?
Estimated cumulative total disbursement as of August 2016 | 1999831 |  |  | 50.88%
Add any comments on AF Grant Funds. (word limit=200) | The amount of $ 1 999 831 includes all expenses and commitments made by: 1. WFP on behalf of MEDD - Executing Entity, 2. MEDD as executing Entity.
INVESTMENT INCOME
Amount of annual investment income generated from the Adaptation Fund’s grant
EXPENDITURE DATA
List output and corresponding amount spent for the current reporting period | ITEM / ACTIVITY / ACTION | AMOUNT
| Output 1.1 Eight DREDD (regional technical services of MEDD) strengthened to access and analyze climate change information, to monitor local development and to mobilize and support communities | 55557.9951
| Output 1.2 Strengthening of Government's threat, risk and vulnerability analysis | 12402.3347
Output 1.3: 20 inter-village associations established and supported
Output 1.4:Communities trained in climate change threats and adaptation measures which reduce vulnerability, in particular related to food insecurity
Output 1.5:100 villages, being clustered according to landscape, ecosystem and livelihoods, have prepared adaptation plans that are integrated into local development planning.
Output 1.6: Communities share success stories and lessons learned, including support of 8 community radios
| Output 1.7: Monitoring system in place (establishment, training, production of data and reports) to track climate events and ecologic development in project intervention zones. | 19838.4267
| Output 2.1: 1500 - 2000 ha of sand dunes fixated | 100466.9134
| Output 2.2: 1000 - 1500 ha of vulnerable zones protected | 136338.8771
| Output 2.3 1,000-1,500 ha of community fuel wood forests planted. | 59954.0475
| 2.4 Water retention structures built covering approximately 500 ha | 8686.5365
| Output 3.1 300,000 trees for revenue generation and food planted in protected areas | 28827.7833
| Output 3.2 4,000 technical staff and community leaders trained in livestock management, agricultural techniques and water utilization | 35165.605
| Output 3.3 5,000 technical staff and community leaders trained and equipped agro-pastoral IGA, including plant multiplication | 52401.6313
| Output 3.4 6,000 technical staff and community leaders trained and equipped for poultry development | 139047.881
| Output 3.5 1,000 technical staff and community leaders trained and equipped for apiculture | 76780.3038
Output 3.6 Approx. 20 community cereal banks established.
Output 3.7 30,000 fuel efficient stoves built
Output 3.8 2,000 community members (mainly youth) trained and equipped to build and maintain fuel efficient stoves
| EE - Project Execution Costs | 86050.0143
| MIE - Project Management Fee | 45388.47
| TOTAL | 856906.8196
PLANNED EXPENDITURE SCHEDULE
List outputs planned and corresponding projected cost for the upcoming reporting period | ITEM / ACTIVITY / ACTION | PROJECTED COST | Est. Completion Date
| Output 1.1 Eight DREDD (regional technical services of MEDD) strengthened to access and analyze climate change information, to monitor local development and to mobilize and support communities | 262500 | 2017-09-30
| Output 1.2 Strengthening of Government's threat, risk and vulnerability analysis | 56673.4911 | 2017-09-30
| Output 1.3: 20 inter-village associations established and supported | 24506.6667 | 2017-09-30
| Output 1.4:Communities trained in climate change threats and adaptation measures which reduce vulnerability, in particular related to food insecurity | 21797.0495 | 2017-09-30
| Output 1.5:100 villages, being clustered according to landscape, ecosystem and livelihoods, have prepared adaptation plans that are integrated into local development planning. | 24569.7555 | 2017-09-30
| Output 1.6: Communities share success stories and lessons learned, including support of 8 community radios | 100000 | 2017-09-30
| Output 1.7: Monitoring system in place (establishment, training, production of data and reports) to track climate events and ecologic development in project intervention zones. | 45000 | 2017-09-30
| Output 2.1: 1500 - 2000 ha of sand dunes fixated | 225000 | 2017-09-30
| Output 2.2: 1000 - 1500 ha of vulnerable zones protected | 52000 | 2017-09-30
| Output 2.3 1,000-1,500 ha of community fuel wood forests planted. | 262500 | 2017-09-30
| 2.4 Water retention structures built covering approximately 500 ha | 225000 | 2017-09-30
| Output 3.1 300,000 trees for revenue generation and food planted in protected areas | 112500 | 2017-09-30
| Output 3.2 4,000 technical staff and community leaders trained in livestock management, agricultural techniques and water utilization | 97500 | 2017-09-30
| Output 3.3 5,000 technical staff and community leaders trained and equipped agro-pastoral IGA, including plant multiplication | 112500 | 2017-09-30
| Output 3.4 6,000 technical staff and community leaders trained and equipped for poultry development | 15000 | 2017-09-30
| Output 3.5 1,000 technical staff and community leaders trained and equipped for apiculture | 52500 | 2017-09-30
| Output 3.6 Approx. 20 community cereal banks established. | 150000 | 2017-09-30
| Output 3.7 30,000 fuel efficient stoves built | 97000 | 2017-09-30
| Output 3.8 2,000 community members (mainly youth) trained and equipped to build and maintain fuel efficient stoves | 45000 | 2017-09-30
| EE - Project Execution Costs | 105000 | 2017-09-30
| MIE | 65250 | 2017-09-30
| TOTAL | 2151796.9628
ACTUAL CO-FINANCING (If the MTR or TE have not been undertaken this reporting period, DO NOT report on actual co-financing.)
How much of the total co-financing as committed in the Project Document has actually been realized? | n a
Estimated cumulative actual co-financing as verified during Mid-term Review (MTR) or Terminal Evaluation (TE). | n a
Add any comments on actual co-financing in particular any issues related to the realization of in-kind, grant, credits, loans, equity, non-grant instruments and other types of co-financing. (word limit=200) | n a

## Procurement
PROCUREMENT DATA
Please provide information for all contracts over $2,500 USD
Please provide the number of contracts under $2,500, signed during this reporting period: |  |  |  | 1
LIST OF CONTRACTS
List all contracts related to the project/program with signature dates
Contract Type | Agency / Contracted party | Contract Value/Amount (USD) | Signature Date | Payment to Date | Remaining Balance
Individual Contract (Consultancy) | Moustapha Ould Mohamed | 8921 | 2016-02-04 | 8921 | 0
Individual Contract (Consultancy) | Société Apidesert | 5134 | 2016-03-07 | 5134 | 0
Individual Contract (Consultancy) | Dr Ahmed Brahim Khlil | 7495 | 2016-03-15 | 7495 | 0
Individual Contract (Consultancy) | CFPR-Boghé | 28084 | 2016-04-01 | 26540 | 1544
Individual Contract (Consultancy) | CNRADA | 12365 | 2016-04-03 | 12365 | 0
Individual Contract (Consultancy) | MULTIMEDIA MAURITANIE | 7066 | 2016-04-25 | 7066 | 0
Individual Contract (Consultancy) | Dr Ahmed Brahim Khlil | 17065 | 2016-06-15 | 11377 | 5688
BIDS
List all bids for each contact signed with date of open call and winning bid
CONTRACT & Procurement Method | Submitted Bids | Bid Amount (USD) | Winning Bid Amount (USD) | Selection Justification for the Winner
Purchase of fencing equipments, request for quotation, 07/06/2016 | Quincaillerie Riviéra | 149462.138 | 82234.5454 | The lowest-priced offer among the technically compliant/responsive offers was awarded.
| Karimpex | 17880.3443
| ETS Bah Ould Khatary | 82234.5454
| Ets NCS | 90803.5269
| ETS Mohamed Hafed Ahmed Nouh | 80985.6178
| Agrico | 18865.8219
Purchase of apiculture equipments, request for quotation, 20/07/2016 | ETS AFIA | 97030.8123 | 72918.7675 | The lowest-priced offer among the technically compliant/responsive offers was awarded.
| ETS SCT | 72918.7675
| ETS GMEL | 98554.6218
Printing of project panels. Request for quotation - 15/09/2015 | AGCPB | 5346 | 5346 | The lowest-priced offer was awarded.
| Butterfly | 7524
| PUBLICIS | 7326
Fertilizers purchase, short list Request for quotation - 12/11/2015 | AGRI-CO | 5376 | 5376 | The lowest-priced offer among the technically compliant/responsive offers was awarded.
| EMEM Services | 6469
Horticultural equipment purchase, short list Request for quotation - 12/11/2015 | AGRI-CO | 16366 | 16366 | The lowest-priced offer among the technically compliant/responsive offers was awarded.
| NAVASEM | 23301
| EMEM Services | 18005
Vegetable crop seeds purchase, short list Request for quotation - 12/11/2015 | AGRI-CO | 3941 | 3941 | The lowest-priced offer among the technically compliant/responsive offers was awarded.
| NAVASEM | 6545
| EMEM Services | 6332
Manufacture and fixing of 136 cement stake, Glaguima - Assaba, Direct agreement - 18/11/2015 | Glaguima Village Management Committee | 2605 | 2605
Manufacture and fixing of 336 cement stake - Brakna sites, Direct agreement -10/11/2015 | Mauritanienne pour les travaux | 7906 | 7906
Manufacture and fixing of 704 cement stake - Gorgol sites, Direct agreement - 17/11/2015 | Deh Mohamed, Entrepreneur, Gorgol | 17581 | 17581
Manufacture and fixing of 412 cement stake - Guidimakha sites, Direct agreement - 10/11/2015 | Ets El Kheir, Guidimakha | 9535 | 9535
Manufacture and fixing of 252 cement stake - Hodh El Chergui sites, Direct agreement | Commerce Général pour Automobile et bâtiment | 6136 | 6136
Manufacture and fixing of 520 cement stake - Hodh El Gharbi sites, Direct agreement - 10/11/2015 | Mohamed Ahmed O. El Moujtaba | 12859 | 12859
Manufacture and fixing of 204 cement stake, Howeitat -Tagant, Direct agreement - 17/11/2015 | Howeitat Participatory Oasis Management Association | 3775 | 3775
Manufacture and fixing of 204 cement stake, Nimlane - Tagant, Direct agreement - 17/11/2015 | Nimlane Participatory Oasis Management Association | 4196 | 4196
Manufacture and fixing of 148 cement stake, Oum El Koura - Trarza, Direct agreement - 17/11/2015 | El Mouhguem Ewkar Cooperative | 3133 | 3133
Purchase of 40 tires for 8 regional project vehicles Toyota Hilux - 15/03/2016 | EMC | 6688 | 6688 | The lowest-priced offer was awarded.
| ETS KKAZ | 7275
| ETS Sidi Med O Abdelaziz | 7040
Purchase of plastic Bags for nurseries, short list Request for quotation - 23/02/2016 | GRCS SARL | 14028 | 14028 | The lowest-priced offer was awarded.
| ETS Mohamed Lemine Ould Vekalou Commerce et Services | 15505
| GNSTP | 18458
Purchase of basic medicines and veterinary equipment for trained auxiliary veterinaries, short list Request for quotation - 15/04/2016 | CPVR – Sarl | 5780 | 5780 | The lowest-priced offer was awarded.
| Société Chinguitty Vétérinaire | 608
| Pharma RIF | 5988
Manufacture and fixing of 226 cement stake, Request for quotation - 27/06/2016 | Mauritanienne pour les Travaux | 5142 | 5142 | The lowest-priced offer was awarded.
| ETS GCB, Commerce et Services | 6428
| Ets B.H. | 7714
Manufacture and fixing of 240 cement stake, Request for quotation - 27/06/2016 | Soudure du Taissir | 5188 | 5188 | The lowest-priced offer was awarded.
| Taysir Pour l'Entreprenariat, Construction et Soudure | 5597
| Ets Nour, Commerce Général | 6144
Manufacture and fixing of 352 cement stake, Request for quotation - 15/07/2016 | Med Ahmed O Moujtaba | 8568 | 8568 | The lowest-priced offer was awarded.
| Yeslem O Lelle | 9644
| Cheikh Sid'Ahmed O Sidi O Limam | 9644
Manufacture and fixing of 176 cement stake, Request for quotation - 30/08/2016 | ETS Jibril Boubacar Pour Travaux Divers | 5351 | 5351 | The lowest-priced offer was awarded.
| Sidi Mohamed Ould Ahmed | 6087
| ETS ENNASR | 7328
Forest seeds purchase, direct purchase - 07/05/2016 | Ets Ahmed Ould Beibou - Assaba | 2968 | 2968 | Not available in the market. Acquisition on order
Agriculture NFI purchase for Nbeiket Lahwech Site, request for quotation 15/04/2016 | SOMATEC Equipement et Fourniture | 4543 | 4543 | The lowest-priced offer was awarded.
| Ahmed O. Mohamed Commerce Général | 4897
| ETS Mohamed Mahmoud O M'HAMED | 5072
Purchase and on-site delivery of equipment for the construction of 03 semi-intensive poultry houses and 09 traditional poultry houses in the wilaya of Trarza. Request for quotation - 06/06/2016 | Ets TAWAKOUL - Commerce Général | 16975 | 16975 | The lowest-priced offer was awarded.
| Ets Rayane, Matériel & Matériaux de construction | 18187
| Raghani et frères, Services Généraux - fourniture et suivi des travaux | 18245
Purchase and on-site delivery of equipment for the construction of 01 semi-intensive poultry house and 06 traditional poultry houses in the Wilaya of Brakna. Request for quotation - 20/06/2016 | Boutique Essaad Commerce Général | 11066 | 11066 | The lowest-priced offer was awarded.
| Boutique EL BIR - Commerce Général | 11667
| Boutique El Najah - Commerce Divers | 11934
Purchase and on-site delivery of equipment for the construction of 01 semi-intensive poultry house and 04 traditional poultry houses in the Wilaya of Gorgol, Request for quotation - 20/06/2016 | Boutique El Adhwa - Commerce Divers | 8929 | 8929 | The lowest-priced offer was awarded.
| Ets Chourough - Commerce Général | 9672
| Société Nejat, Fourniture - Equipement- Construction | 9812
Purchase and on-site delivery of equipment for the construction of 01 semi-intensive poultry house and 04 traditional poultry houses in the Wilaya of Guidimakha, Request for quotation - 20/06/2016 | Boutique Tandia Med Commerce Général | 9484 | 9484 | The lowest-priced offer was awarded.
| Ets TAGHADOUM pour Travaux et Construction | 10316
| Boutique Ehel Lekhal - Commerce Divers | 10135
Purchase and on-site delivery of equipment for the construction of 01 semi-intensive poultry house and 01 traditional poultry house in the Wilaya of Assaba Request for quotations - 21/06/2016 | ETS NASSER, Commerce Général | 3665 | 3665 | The lowest-priced offer was awarded.
| Ets OUMCHGAG vente de matériaux de construction | 3823
| El Kheir bâtiments et travaux | 3905
Purchase and on-site delivery of equipment for the construction of 01 semi-intensive poultry house and 07 traditional poultry houses in the Wilaya of Hodh El Chegui Request for quotation - 21/06/2016 | Ets Ely Maouloud & Frères | 10596 | 10596 | The lowest-priced offer was awarded.
| AS-EDER pour le commerce | 11302
| Ets EL BOUROURE | 10914
Purchase and on-site delivery of equipment for the construction of 02 semi-intensive poultry houses and 05 traditional poultry houses in the Wilaya of Hodh El Gharbi Request for quotation - 21/06/2016 | Boutique Doumess | 10053 | 10053 | The lowest-priced offer was awarded.
| Ets Cheikh Tourad pour le commerce général | 11503
| Ets Lenwar commerce général | 10816
Purchase and on-site delivery of equipment for the construction 04 traditional poultry houses in the Wilaya of Tagant, Request for quotation - 21/06/2016 | Ets Khalifa et frères, commerce général | 4595 | 4595 | The lowest-priced offer was awarded.
| Boutique Samah, matériaux de construction | 5373
| Boutique EL HOUDA, Commerce Général | 4950
Purchase of feeders and drinkers for traditional and semi-intensive poultry houses, Request for quotation - 21/06/2016 | ts EMAN | 14455 | 14455 | The lowest-priced offer was awarded.
| Pharmacie Tewekoul | 20634
| Pharmacie El Jewde | 24730
Purchase of solar freezers for semi-intensive poultry houses, Request for quotation - 21/06/2016 | GLP SA | 24382 | 24382 | The lowest-priced offer was awarded.
| Boutique Chourouk Solaire | 26560
| Cds eau et energie | 33361
Purchase and on-site delevery and installation of equipment for solar lighting in 10 semi-intensive 10mx5m poultry houses, Request for quotation - 21/06/2016 | SOTREQ | 4813 | 4813 | The lowest-priced offer was awarded.
| El Baraka Solaire | 10890
| Ets Lumieres du nouvel centenaire | 13400
Purchase of semi-intensive poultry houses equipements, Request for quotation -21/06/2016 | Ets Kothar | 15486 | 15486 | The lowest-priced offer was awarded.
| Clinique et pharmacie veterinaire El Emel | 18103
Purchase of food, day-old chicks, vaccines and medicines supply for semi-intensive and traditional poultry houses, Request for quotation -21/06/2016 | Clinique et pharmacie vétérinaire ABK | 23081 | 23081 | The lowest-priced offer was awarded.
| Pharmacie El Beitar | 25044
Construction of poultry houses for the wilayas of Trarza, Brakna, Gorgol and Guidimaka, direct agreement - 21/06/2016 | Mohamed Ould Sidina | 3903 | 3903 | This type of construction requires a specialized workforce. This mason was chosen with reference to his experience in the ProlPRAF project in the region
Construction of semi-intensive poultry houses for the wilaya of Trarza direct agreement - 21/06/2016 | Souleymane Ould shagh | 6619 | 6619 | This type of construction requires a specialized workforce. This mason was chosen with reference to his experience in the ProlPRAF project in the region
Construction of traditional and semi-intensive poultry houses for the wilayas of Brakna, Gorgol and Guidimaka, direct agreement - 21/06/2016 | Mohamed Sidina Ould Hmednah Meilid | 10692 | 10692 | This type of construction requires a specialized workforce. This mason was chosen with reference to his experience in the ProlPRAF project in the region
Construction of traditional and semi-intensive poultry houses for the wilayas of H. Chergui, H Gharbi et Assaba, direct agreement - 21/06/2016 | Abderrahmane Ould Mohamed | 11682 | 11682 | This type of construction requires a specialized workforce. This mason was chosen with reference to his experience in the ProlPRAF project in the region
Transport of plant material for the mechanical dune fixation in Nbeiket Lahwech site, direct agreement - 24/06/2016 | Ethmane Cheikh O. Sid Emou | 7395 | 7395 | Negociation with the carrier. Difficult feild conditions

## Risk Assesment
RISK ASSESMENT
IDENTIFIED RISKS
List all Risks identified in project preparation phase and what steps are being taken to mitigate them
Identified Risk | Current Status | Steps Taken to Mitigate Risk
External factors may delay project implementation | Medium to High | Government elections during the initially planned implementation period led to a delay in starting the project activities. However, as soon as the new administration was in place, the project has been making swift progress and hopes to catch up with the planned schedule. The project is a high priority of the Government, and will receive support where difficulties are encountered. Priority will be given to villages which have completed first their adaptation plans to begin implementation. Depending on the progress made by various villages in adaptation plan elaboration and implementation, budgets may be redistributed towards the better performing sites (based on periodic reviews of progress).
Communities find it difficult to take up the skills, learning and social cohesion necessary to secure protected areas | Medium | Communities will carry out the adaptation actions that they themselves prioritize, and will invest their own resources in addition to those provided by the project. The high degree of participation and ownership promoted by the project, coupled with the provision of income to support what are now major livelihoods, will render the risk of communities not sustaining project results very low.
There is little local specialized management and technical capacity related to climate change, particularly in the entities that are responsible for the project. | From High to Medium | The strengthening of decentralized services is a strategic priority for the Government. And the project is committed to provide valuable support and continuous contribution to increase the Government’s technical capacity at these levels.
Lack of adequately qualified partners | Low | A number of qualified partners with a similar project philosophy as WFP are working on the ground, and WFP has good experience in working with them. WFP has a good working experience with some adequately qualified partners which the project may rely on to carry out its activities.
People purchase greater amounts of livestock (beyond carrying capacity) | Low | The project will promote increased community sensitization and raise knowledge and skills towards sustainable natural resources management. Communities will better understand the impact of livestock on their environment. Alternative sources of income will be promoted.
Outsiders bring in additional livestock | Low | Communities will better understand the impact of livestock on their environment and will attach a monetary value to the use of protected areas. They will protect better their natural resources and prevent outsiders from bringing in additional livestock.
People cut down planted trees for fuel wood (other than community forest) | Low | Promoting community land ownership and access to alternative sources of income will help in easing significantly that risk. In addition, Government' strategy of promoting natural gas use over fuel wood in urban centres, will significantly contribute in reducing fuel wood demand in rural areas.
Natural disasters, in particular drought | Medium | As a matter of routine, WFP prepares contingency plans in close collaboration with Government to detect and address risks early on.
Lack of complementary projects and inputs | Low | The project falls fully within Government strategies and related donor strategies. The project advisory group will involve all relevant partners and stakeholders. Already synergies have been developpend with GIZ ACCMR project and WFP PRRO.
Critical Risks Affecting Progress (Not identified at project design)
Identify Risks with a 50% or > likelihood of affecting progress of project
Identified Risk | Current Status | Steps Taken to Mitigate Risk
Changes in regional project focal points (DREDD) | Medium | Since the inception, 2 changes have occurred in the DREDD position as project focal points at the regional level. One in the beginning of The first change occurred at project start and has no impact on project progress because only one region / Wilaya was affected. The second change happened in August 2015 whereas 6 out of the 8 regions the project intervene were concerned. where the project works. This change has disturbed Consequently, the normal project implementation progress will be affected as the new focal points (DREDD) need to familiarize with the project sites and establish contacts with concerned communities. There was no disturbance such as shuffling of civil servants (DREDD) in the 2015 - 2016 campaign.
Use of Food for work tool | Overcome | The tendering process for purchasing food took a long time to be finalized thus implying delays on food distribution and frustrating communities involved in the Food For Assets activities. WFP and The Ministry of Environment agreed to combine Food tool with cash transfer tool.
Fund transfer from AF Bord | Medium | Despite the timely submission of the annual project performance report, the disbursement of the second tranche by the AF Secretariat took a long time to be transferred. The project account funds were very low at some stage was at a certain time almost empty,thus we were running high risk for and we risked not to honoring some of the commitments already engaged.
Mobilisation of national counterpart for 2017 - 2018 | High | MEDD did not mobilize the national counterpart for 2016 which contributes to the payment of project support staff salaries. To resolve the problem,WFP mobilized half of the required budget from PRRO. The remaining budget (50%) was mobilized from AF project funds. For 2017, MEDD has promised to discuss earlier with the Ministry of Economy and Finance to mobilize the national counterpart budget to cover salaries of the project's support staff. We still await for the decision.
Lack of capacity in the DREDDs in terms of staffing and skills. | Medium | In 04 DREDDs out of 08, we noted a lack of capacity in terms of technical and management skills (poor quality of supervision, reporting and management) and also in terms of staffing. This affected the quality of work and the deadlines for implementing activities in the concerned regions. The hiring of NGOs as project partners will reduce the gap and improve the project execution.
Risk Measures: Were there any risk mitigation measures employed during the current reporting period? If so, were risks reduced? If not, why were these risks not reduced?
Add any comments relevant to risk mitigation (word limit = 500)

## Rating
RATING ON IMPLEMENTATION PROGRESS
For rating definitions please see bottom of page.
| Progress on Key Milestones |  | Expected Progress |  | Progress to Date | Rating
Project Manager/Coordinator: | Hiring NGOs project partners to support DREDD in project implementation activities |  | Planning, supervision, implementation and monitoring of project activities are improved |  | 16 NGOs and Group of NGO were selected to support DREDDs in the 74 Communities in the 8 Wilayas. The hiring process of NGOs registered a very important delay because of the sensitivity of the issue. The MEDD had a very bad experience with NGOs in the implementation of a previous major project. So, precautions have been taken to ensure that the process is carried out in a transparent manner so as to select only well-performing NGOs. | MS
| Strengthening of Government authorities and technical services on Climate Change threat, risk and vulnerability analysis |  | An Early Warning System (EWS) is set up at community level |  | Discussions are ongoing with project partners (ONM, SAM, GIZ, OSA, OXFAM, Rural Radios …) on synergy to develop a framework on providing reliable climate information and the way to do that. | MS
| Communities share success stories and lessons learned, including support of 8 community radios |  | Community radios are on air, involving communities in programming and feed-back |  | 2 Meetings have been organized with representatives of National Radio, Rural Radio and Local Radio. Discussions focused on their capacity in terms of broadcasting in the project intervention areas and the needs in terms of capacity building and equipment. As there are still outstanding issues, it was agreed that we continue finalizing all aspects and strat implementation after the second year so we will be also gathering the success project stories which can be shared through the Community Radios. | MS
| Communities are trained and sensitized about the adverse effects of CC and its impacts on natural resources, livelihood and food security |  | Communities are aware about the adverse effects of CC and its impacts on natural resources, livelihood and food security |  | During the reporting period, regular visits organized by DREDD to supervise project activities constitute occasions to raise awareness about threats of adverse effects of CC on natural resources, livelihoods and food security. Parallelly to the ACC action plans implementation, many trainings have been organized for communities in different topics (High value crop production, agriculture, Poultry, Apiculture, dune fixation, plantation, etc.) which address also issues related to Climate change impacts on natural resources, livelihood and food security. | S
| Village cluster organizations established | Output 1.4:Communities trained in climate change threats and adaptation measures which reduce vulnerability, in particular related to food insecurity | Village cluster organizations established | Output 1.4:Communities trained in climate change threats and adaptation measures which reduce vulnerability, in particular related to food insecurity | The establishing of inter-village associations in the framework of the AF project is not feasible, particularly due to social, and land property issues and also distance between villages. This work requires a lot of time and resources in order to achieve it (i.e. ProGRN experience). The project has been working actively with the village management committees which are reactivated in all project sites and in case of inter-village association structures exist, like AGLC, the project will continue supporting them during the project implementation period as they will ensure the sustainability of project activities. | S
| Monitoring system in place (training, production of data and reports) to track climate events and ecologic development in project intervention zones. |  | Monitoring system in place and operational |  | A monitoring-evaluation guide has been elaborated for the monitoring of the project's performances. It takes into account all the relevant indicators of the National Environmental Action Plan that fall within the scope of the project intervention. Training on the use of the monitoring and evaluation guide has been organized for the benefit of the 8 DREDDs. Periodically the ecological monitoring is carried out (DREDD - PMU) in the project intervention sites compared to the baseline situation. The results will be integrated into the national ecological monitoring system. | S
| Concrete adaptation measures identified through community-based adaptation planning to combat desertification and land degradation initiated in the project area |  | Adaptation measures implementation initiated in the project area to combat desertification and land degradation |  | - 310 ha of sand dunes fixed - 177 ha of community fuel wood forests afforested - 950 ha of vulnerable zones protected - 280 ha of degraded lands will be implemented starting from January 2017. Preparations are ahead to begin implementation across 10 sites in two Wilayas (Guidimakha and Gorgol). | S
| Concrete adaptation measures identified through community-based adaptation planning to diversify and strengthen the livelihoods of vulnerable populations initiated in the project area |  | Adaptation measures implementation initiated in the project area to diversify and strengthen the livelihoods of vulnerable populations |  | Fruit tree plantation has been carried out in N'Beiket Lahwech in the Wilaya of Hodh Chergui in the beginning of May 2016, which was visited by the Mauritanian President. 500 trees were planted for the benefit of 150 households (3 trees for each family). Also some equipment were distributed to these families. The fruit trees plantation Programme implementation will start beginning 2017 with the collaboration of Centre for Agricultural Research and Agricultural Development (CNRADA) in the 8 Wilayas with the following Programme: • 19 project sites in the 8 regions • 10 300 fruit trees to be planted • 3 166 households concerned • 18 770 direct beneficiaries ------------------------------------------------- 50 (40 traditional and 10 semi-intensive) shelters for the development of poultry farming in rural areas were built and equipped for the benefit of 400 women and 100 young men of the project within the 8 Wilayas of intervention. The Programme will be totally acheived in Fabruary 2017. ------------------------------------------------- 8 project sites in 5 Wilayas (Trarza, Brakna, Gorgol, Guidimakha and Tagant.) were identified to develop beekeeping activities. 72 Beneficiaries (37 men and 35 women). The direct beneficiaries are 432 people at the rate of 6 persons per household. Equipment is purchased and programme supervision will start in October-November 2016. ------------------------------------------------- - 40 veterinary assistants have been trained during 15 days and equipped with basic veterinary medicines and started working in the field covering project intervention areas and surrounding. ------------------------------------------------- - 82 rural high value crops producers have be trained during 5 days in the field of Cooperative management and organization. Objective: prepare the disengagement of the project and ensuring sustainability of the activity. - 4582 community producers have beien coached in implementing and producing high value crops in 37 project sites. Number of beneficiaries : 27492 . | S
[5 empty] | Overall Rating | S
Please Provide the Name and Contact information of person(s) responsible for completing the Rating section
| Name: | Ghazi GADER, WFP Project Coordinator
| Email: | ghazi.gader@wfp.org
Please justify your rating. Outline the positive and negative progress made by the project since it started. Provide specific recommendations for next steps. . (word limit=500)
Despite the delay in project start, there is satisfaction with the results achieved so far. Overall, progress is on track to achieve most of the results since project inception. Positive progress since inception: . Capacity building Programme implemented for different project partners at central and regional levels, . Adaptation to climate change action plans developed in most project sites, . Concrete adaptation measures identified through community-based adaptation planning implemented to combat desertification and land degradation (sand dune fixation, fuel wood plantation, vulnerable zones protection, soil and water conservation) . Concrete adaptation measures identified through community-based adaptation planning implemented to diversify and strengthen the livelihoods of vulnerable populations (High value crops production, poultry farming, apiculture, Fruit tree production, veterinary assistants trained and equipped) There is a good cooperation between the MEDD (EE) and the WFP (MIE) which together provide all the necessary conditions for the success of the project. During this reporting period we underlined the synergy between AF project and WFP PRRO where joint interventions were carried out in the sites of the Wilaya of Gorgol. This synergy will be reinforced and extended to other more sites in order to achieve common expected outcomes. Negative progress since inception: A delay in hiring NGO as project implementation partners. A small delay was registered to start fruit trees plantation Programme, due to contract discussion with CNRADA which took more time than planned. Water and Soil conservation retention structures building activities were delayed because of early rainfall season in the Wilaya of Guidimakha. A new tendering process has been launched by WFP and the implementation is planned to begin early 2017. Progress on establishing inter-village associations was marginally satisfactory. Actually, it's not feasible in the framework of the AF project particularly due to land property issues and also distance between villages. This work requires a lot of time and resources in order to achieve it (i.e. ProGRN experience). Wherever inter-village association structures exist, like AGLC established by GIZ' ProGRN Programme, the AF project will continue supporting them during the project implementation period as they will ensure the sustainability of project activities. However the project is now working with the village management committees which were created and activated in all project sites. Lack of capacity in the DREDDs in terms of staffing and skills. Therefore the implementation strategy should be improved, relying more on other partners such as NGOs which will start supporting DREDD in January 2017. On the basis of expenditure occurred during the first two years of project implementation, we have realized that some outputs such as 2.1, 2.3, 3.1, 3.2, 3.3, 3.4 were largely overestimated. Thus, these outputs should be reviewed and the corresponding budget initially allocated adjusted as well during the MTR.
| Progress on Key Milestones |  | Expected Progress |  | Progress to Date | Rating
Executing Entity | Hiring NGOs project partners to support DREDD in project implementation activities |  | Planning, supervision, implementation and monitoring of project activities are improved |  | 16 NGOs and Group of NGO were selected to support DREDDs in the 74 Communities in the 8 Wilayas. The hiring process of NGOs registered a very important delay because of the sensitivity of the issue. The MEDD had a very bad experience with NGOs in the implementation of a previous major project. So, precautions have been taken to ensure that the process is carried out in a transparent manner so as to select only well-performing NGOs. | MS
| Strengthening of Government authorities and technical services on Climate Change threat, risk and vulnerability analysis |  | An Early Warning System (EWS) is set up at community level |  | Discussions are ongoing with project partners (ONM, SAM, GIZ, OSA, OXFAM, Rural Radios …) on synergy to develop a framework on providing reliable climate information and the way to do that. | MS
| Communities share success stories and lessons learned, including support of 8 community radios |  | Community radios are on air, involving communities in programming and feed-back |  | 2 Meetings have been organized with representatives of National Radio, Rural Radio and Local Radio. Agreeements on an action plan are scheduled to be finalized within calender year 2017. | MS
| Communities are trained and sensitized about the adverse effects of CC and its impacts on natural resources, livelihood and food security |  | Communities are aware about the adverse effects of CC and its impacts on natural resources, livelihood and food security |  | DREDDs trained on Climate Change issues played an important role in raising awareness to communities on threats of adverse effects of CC on natural resources, livelihoods and food security. In parallel to the ACC action plans implementation, many trainings have been organized for communities in different topics (High value crop production, agriculture, Poultry, Apiculture, dune fixation, plantation, etc.) which address also issues related to Climate change impacts on natural resources, livelihood and food security. | S
| Village cluster organizations established | Output 1.4:Communities trained in climate change threats and adaptation measures which reduce vulnerability, in particular related to food insecurity | Village cluster organizations established | Output 1.4:Communities trained in climate change threats and adaptation measures which reduce vulnerability, in particular related to food insecurity | It is very difficult to establish inter-village associations in the framework of the AF project, in particular due to social, land property issues and distance between villages. This is a highly sensitive issue and there are numerous examples which illustrate conflicts that led to serious problems between and/or within communities. In light of arguments mentioned above, the project decided to abondon the inter-village associations approach and instead focuses on single village association approach. Therefore, it is not relevent to evaluate this output. | N/A
| Monitoring system in place (training, production of data and reports) to track climate events and ecologic development in project intervention zones. |  | Monitoring system in place and operational |  | A monitoring-evaluation guide has been elaborated for the monitoring of the project's performances. It takes into account all the relevant indicators of the National Environmental Action Plan that fall within the scope of the project intervention. Training on the use of the monitoring and evaluation guide has been organized for the benefit of the 8 DREDDs. | S
| Concrete adaptation measures identified through community-based adaptation planning to combat desertification and land degradation initiated in the project area |  | Adaptation measures implementation initiated in the project area to combat desertification and land degradation |  | - 310 ha of sand dunes fixed - 177 ha of community fuel wood forests afforested - 950 ha of vulnerable zones protected - 280 ha of degraded lands will be implemented starting from January 2017. Preparations are ahead to begin implementation across 10 sites in two Wilayas (Guidimakha and Gorgol). | S
| Concrete adaptation measures identified through community-based adaptation planning to diversify and strengthen the livelihoods of vulnerable populations initiated in the project area |  | Adaptation measures implementation initiated in the project area to diversify and strengthen the livelihoods of vulnerable populations |  | Fruit tree plantation has been carried out in N'Beiket Lahwech in the Wilaya of Hodh Chergui in the beginning of May 2016, which was visited by the Mauritanian President. 500 trees were planted for the benefit of 150 households (3 trees for each family). Also some equipment were distributed to these families. The fruit trees plantation Programme implementation will start beginning 2017 with the collaboration of Centre for Agricultural Research and Agricultural Development (CNRADA) in the 8 Wilayas with the following Programme: • 19 project sites in the 8 regions • 10 300 fruit trees to be planted • 3 166 households concerned • 18 770 direct beneficiaries ------------------------------------------------- 50 (40 traditional and 10 semi-intensive) shelters for the development of poultry farming in rural areas were built and equipped for the benefit of 400 women and 100 young men of the project within the 8 Wilayas of intervention. The Programme will be totally acheived in Fabruary 2017. ------------------------------------------------- 8 project sites in 5 Wilayas (Trarza, Brakna, Gorgol, Guidimakha and Tagant.) were identified to develop beekeeping activities. 72 Beneficiaries (37 men and 35 women). The direct beneficiaries are 432 people at the rate of 6 persons per household. Equipment is purchased and programme supervision will start in October-November 2016. ------------------------------------------------- - 40 veterinary assistants have been trained during 15 days and equipped with basic veterinary medicines and started working in the field covering project intervention areas and surrounding. ------------------------------------------------- - 82 rural high value crops producers have be trained during 5 days in the field of Cooperative management and organization. Objective: prepare the disengagement of the project and ensuring sustainability of the activity. - 4582 community producers have beien coached in implementing and producing high value crops in 37 project sites. Number of beneficiaries : 27492 . | S
[5 empty] | Overall Rating | S
Please Provide the Name and Contact information of person(s) responsible for completing the Rating section
| Name: | Alioune Fall, Project Coordinator Assistant; | Sidi Mohamed El Wavi, National Project Director
| Email: | lunef@yahoo.com | elwavi.sm@gmail.com
| Progress on Key Milestones |  | Expected Progress |  | Progress to Date | Rating
Other
Overall Rating
Please Provide the Name and Contact information of person(s) responsible for completing the Rating section
Name:
Email:
| Please justify your rating and address the following points: 1. Indicate trends, both positive and negative, in achievement of outcomes as per the project indicators. 2. Detail critical risks that have affected progress. 3. Outline response to MTR undertaken this reporting period. 4. Outline action plan to address projects with a rating of HU, U or MU. Please keep your input to 1200 words |  | Since project inception, MEDD has noted an averall satisfactory progress. Concrete achievement and realizations such as sand dune fixation, plantations, High value crop production, poultry farming units are visible in targeted sites. We received very positive feedback from local communities about the impact of theses activities in their life. Mauritania AF project is now considered as the leading Climate Change project within MEDD and many other environmental projects are now seeking synergies to benefit from our experience. The Project has developped a capacity building programme that led to training of Government authorities in central and regional areas, technical services as well as civil society representatives to better understand Climate Change challenges and integrate adaptation into development planning. Adaptation to climate change action plans in most of our sites were jointly developed by technical services and communities through a participatory approach. Successful joint interventions, such as cash for assets (CFA) supported by wfp PRRO for AF project activities in 4 sites need to be reinforced and extended in order to achieve common expected outcomes. However the project did experience delays to hire NGOs because of precautionary measures taken by the MEDD to ensure transparency and avoid similar bad experiences to that effect. The fruit tree programme will be the biggest programme yet to be implemented in Mauritania. CNARADA the research center partner hired to implement the program needed extra time to grow plants to accommodate our demand.Other precautionary measures such as transport and skilled staff to carry out works played a role in delays to implement the programme. Water and Soil conservation retention structures building activities were planned but could not be executed because of early unforeseen weather activities (rainfall and inundation of sroad access) in the Wilaya of Guidimakha. Plans are being made to start the activities early in 2017. It is very difficult to establish inter-village associations in the framework of the AF project, in particular due to social, land property issues and distance between villages. This is a highly sensitive issue and there are numerous examples which illustrate conflicts that led to serious problems between and/or within communities. In light of arguments mentioned above, the project decided to abondon the inter-village associations approach and instead focuses on single village association approach. Lack of capacity in the DREDDs in terms of staffing and skills. Therefore the implementation strategy should be improved, relying more on other partners such as NGOs which will start supporting DREDD in January 2017. On the basis of expenditure occurred during the first two years of project implementation, we have realized that some outputs such as 2.1, 2.3, 3.1, 3.2, 3.3, 3.4 were largely overestimated. Thus, these outputs should be reviewed and the corresponding budget initially allocated adjusted as well during the MTR.
Rating Definitions
|  |  | Highly Satisfactory (HS) | Project actions/activities planned for current reporting period are progressing on track or exceeding expectations to achieve all major outcomes/outputs for given reporting period, without major shortcomings. The project can be presented as “good practice”.
|  |  | Satisfactory (S) | Project actions/activities planned for current reporting period are progressing on track to achieve most of its major outcomes/outputs with only minor shortcomings.
|  |  | Marginally Satisfactory (MS) | Project actions/activities planned for current reporting period are progressing on track to achieve most major relevant outcomes/outputs, but with either significant shortcomings or modest overall relevance.
|  |  | Marginally Unsatisfactory (MU) | Project actions/activities planned for current reporting period are not progressing on track to achieve major outcomes/outputs with major shortcomings or is expected to achieve only some of its major outcomes/outputs.
|  |  | Unsatisfactory (U) | Project actions/activities planned for current reporting period are not progressing on track to achieve most of its major outcomes/outputs.
|  |  | Highly Unsatisfactory (HU) | Project actions/activities planned for current reporting period are not on track and shows that it is failing to achieve, and is not expected to achieve, any of its outcomes/outputs.

## Project Indicators
PROJECT Indicators
Please provide all indicators being tracked for the project as outlined in the project document
Type of Indicator (indicators towards Objectives, Outcomes, etc…)
Type of Indicator | Indicator | Baseline | Progress since inception | Target for Project End
OBJECTIVE 1: Enhanced understanding, skills and means of decentralized government and communities for leading and facilitating participatory adaptation planning | Number of community adaptation plans prepared through participative local planning supported with information and facilitation by DREDD | No adaptation plans exist in intervention zones | 87 villages prepared their ACC action plan with the support of DREDD and Regional technical services including civil society. This work is a result of the improvement of DREDD and project partners' skills on Climate change issues and integrating ACC into local development approach. These ACC action plans will be reviwed starting from Junuary 2017 with the support of NGO engaged by the project in all intervention areas. | 20 clusters of villages have established adaption plans in a participatory manner
Outcome 1.1: Strengthened awareness, ownership and facilitation capacities of government services (DREDD) | DREDD have played an active and supportive role in the mobilization, organization and implementation of inter-village adaption planning processes | DREDD do not have capacity to provide any support to communities | DREDD led, participated and facilitated in the elaboration of ACC action plans in the project area. DREDD supervise implementation of project activities with advice and technical support for the communities. | DREDD have succeeded to provide information, guidance and facilitation support to 20 village clusters
Output 1.1: Technical services strengthened to access and analyze climate change information, food security, livelihoods and vulnerability information, and to monitor local development, and mobilize and support communities. | DREDD have been trained, have communicated with department and local level, have visited communities, have facilitated village cluster establishment and discussions | DREDD do not visit communities and do not provide information, support, guidance or facilitate processes | - 2 training sessions organized in collaboration with GIZ's ACCMR project, for DREDDs and Regional technical services on Climate Change basics and the approach of Integrating Adaptation to Climate Change into Development planning. (80 participants : 6 women and 74 men). This training was followed by a practical exercise in one selected project site to implement the methodology in a real case with the active participation of the communities. Knowledge acquired during these aforementioned capacity building sessions permitted DREDD with regular visits to raise awareness on climate change impacts on food security and to monitor and guide the project's interventions. The Project will be contracting NGOs which will provide support to DREDDs, Community sensitization and mobilization, data collection and monitoring of climate change adaptation measures at local level as well as improvement of ecological monitoring. | DREDDs have regular contact and trustful relationship with village clusters and communities that value their support
Output 1.2: Strengthening of Government authorities and technical services on CC threat, risk and vulnerability analysis capabilities by expanding current Vulnerability and Analysis methodologies to overlay climate threats and monitoring changes in landscapes using GIS technologies. | Preparation and communication to regional level of up-to-date and reliable information and analysis of climate change information and of government priorities | DREDD hardly receive any guidance, information and analysis from central level | Discussions are ongoing with project partners (ONM, SAM, GIZ, OSA, OXFAM, Rural Radios …) on synergy to develop a framework on providing reliable climate information and the way to do that. | Regular communications between central level and DREDD provide up-to date information and guidance, adapted to the capacity at regional level
Outcome 1.2: Strengthened awareness, ownership, planning and management capacities at community level for local natural resource management and climate change adaptation | Communities and their relevant sub-groups (e.g. women, livelihood groups, etc.) have actively participated in the preparation of the inter-village adaptation plans prepared and see their interests adequately reflected. | There is only little joint discussion at community level, and not all groups are involved; no inter-village discussions take place | In all sites where adaptation action plans have been elaborated, communities have played a great role and actively participated to all steps of the process till the identification and prioritization of adaptation options. | About 100 villages in 20 village clusters understand, own and manage their adaption plans and their natural resources
Output 1.3: 20 inter-village associations established and supported. | Inter-village associations exist and are active in on form or the other in each of 20 targeted clusters | In some clusters, some form of cooperation structure may exist, on which the project can build. | The establishing of inter-village associations in the framework of the AF project is not feasable, particularly due to social, and land property issues and also distance between villages. This work requires a lot of time and resources in order to achieve it (i.e. ProGRN experience). Wherever inter-village association structures exist, like AGLC, the project will continue supporting them during the project implementation period as they will ensure the sustainability of project activities. However the project is now working with the village management committies which are created and activated in all project sites. | 20 inter-village associations with a role in managing natural resources and adaptation plans recognized by population and DREDD
Output 1.4: Communities trained in climate change threats and adaptation measures which reduce vulnerability, in particular related to food insecurity. | Number of people (gender-disaggregated) and communities trained | Communities are aware of degrading natural resources, but rarely of context, causes and adaptation options | The regular visits organized by DREDD to supervise project activities constitute occasions to rase awarness about threats of adverse effects of CC on natural resources, livelihoods and food security. Parallelly to the ACC action plans implementation, many trainings have been organized for communities in different topics (High value crop production, agriculture, Poultry, Apiculture, sand dune fixation, aforestation, Soil and Water conservation, etc.) which adress also issues related to Climate change impacts on natural ressources, livelihood and food security. During the planned review of ACC action plans with the support of NGO, awareness raising and training sessions will be organised for the targeted communities about CC and food securitty issues. | Communities have the capacity to analyze and understand their situation, and adaptation options
Output 1.5: 100 villages, being clustered according to landscape, ecosystem and livelihoods, have prepared adaptation plans that are integrated into local development planning. Identification of adaptation technology requirements such as integrated livestock water and cropping systems. | 20 village cluster adaptation plans developed in a participatory way and officially recognized by DREDD | Communities and village associations do not prepare comprehensive adaptation plans | 87 villages prepared their ACC action plan with the support of DREDD and Regional technical services including civil society. This work is a result of the improvement of DREDD and project partners' skills on ACC planning participatory approach based on 8 steps : 1. Identification of exposer units 2. Analysis of current vulnerability 3. Analysis of projected vulnerabilty (according to climate scenarios) 4. Identification of adaptaion options 5. Choice of prioritization criteria 6. Prioritization of adaptation options 7. Declination of adaptation options into actions and activities 8. Development of ACC action Plan These ACC action plans will be reviwed starting from Junuary 2017 with the support of NGO contracted by the project in all intervention areas. | Adaptation plans include analysis, discussion of options, decision on priorities and analysis of implications (costs, maintenance)
| Specific studies on adaptation technology requirements are available at the relevant levels | A number of ad hoc studies exist within several projects, but are not systematically made available | n/a | Studies on technology for 3-4 “standard” adaptation assets are available to all partners and stakeholders
Output 1.6: Communities share success stories and lessons learned, including support of community radios focused specifically on sharing information on early warning and adaptation management. | Community radios are on air, involving communities in programming and feed-back | Communities of 15 sites in the project area have already listen regularly to radio transmissions on a radius ranging from 6 to 70 km. | Community radios (Local Radio) were already established by the Government in all Wilayas including the 8 wilayas targeted by the project. They have been associated to all workshops and trainings organized in the regional level and they were sensitized to the project objectives. Therefore, discussions are still underway with some partners for the best strategy to make these CR playing a real role in sharing information on EWS and successful adaptation stories. | CR goes live are on air, have with strong volunteer involvement and a sustainability strategy
Outcome 1.3: National ecologic monitoring system strengthened and tested | Participating communities and government services have provided quality, timely and reliable ecologic monitoring reports aligned with the national monitoring system | The ecologic monitoring system is established as part of PANE II System and set online in February 2014. | A monitoring-evaluation guide has been elaborated for the monitoring of the project's perfomances. It takes into account all the relevant indicators of the National Environmental Action Plan that fall within the scope of the project intervention. | The new national ecologic monitoring system is known, used and maintained by DREED and in project village clusters.
Output 1.7: Monitoring system in place (training, production of data and reports) to track climate events and ecologic development in project intervention zones. | Number of people trained at regional and village cluster level; amount and quality of data provided by village clusters / regional teams | There is no systematic collection, consolidation and analysis of data on nationally agreed-upon indicators. | Training on the use of the monitoring and evaluation guide has been organized for the benefit of the 8 DREDDs. Periodically the ecological monitoring is carried out (DREDD - PMU) in the project intervention sites compared to the baseline situation. The results will be integrated into the national ecological monitoring system. | Participating DREDD and village clusters provide data on agreed-upon indicators; and receive, understand and use reports.
OBJECTIVE 2: Design and implement concrete adaptation measures identified through community adaptation planning that aim to combat desertification, soil erosion and land degradation | Number of implemented community adaptation plan action aiming to combat desertification, soil erosion and land degradation | No comprehensive community (cluster) adaptation plans exist in the intervention zones to be selected. | All the adaptation plans drawn up by the targeted communities, with the support of DREDDs, integrate measures linked to combat desertification and degraded lands rehabilitation. | 20 comprehensive adaptation plans have been implemented with respect to combat desertification, soil erosion and land degradation.
Outcome 2.1: Advance of sand dunes slowed down, halted or reversed | Reduced, halted or reversed dune advance in participating communities | 749 ha of dunes fixed in the project intervention area | Trends being monitored. | Significant deceleration – and ideally reversal – of dune advance
Output 2.1: 1,500-2,000 ha of dunes fixated. | Plants – and other measures – have stopped advance of dunes | Sand dune fixation does take place as part of several projects, but hardly in the zones to be selected. | 310 ha of sand dunes fixed | Communities have fixated dunes and have a clear plan for maintaining / reinforcing fixation
Outcome 2.2: Increased vegetation cover in intervention zones | Increased Vegetation Cover Index in participating communities | The average density of vegetation is 67 plants per hectare in the project sites | Trends being monitored. | Increase of the average density per hectare by at least 10% in the participating village clusters until the end of the project with clear prospect of further increases)
Output 2.2: 1,000-1,500 ha of vulnerable zones protected. | Area of land protected from against uncontrolled grazing and bush fires | There will only be sporadic protected areas in selected village clusters | 600 ha were protected in 2016. Identification was done in collaboration with communities. Agreements between Communities, local Authorities and DREDD were concluded before the implementation. The total area protected sisce the project start covers 950 ha. Pastoral plantations have been made in the sites implemented in 2015 to improve grazing. Management plans will be established in order to sustain these protected areas. | 1,000 – 1,500 ha of land protected and encompassed by sustainable management plan
Output 2.3: 1,000-1,500 ha of community fuel wood forests planted. | Area of land planted and controlled for fuel wood production; volume of produced fuel wood | There is hardly any controlled fuel wood plantation in areas to be selected | - 177 ha of community fuel wood forests afforested | Participating communities cover at least 50% of their fuel wood requirements from controlled wood production
Outcome 2.3: Decreased loss of water and soil through surface run-off | Increased surface and sub-soil water availability | There are only 13 sites with water retention structures functioning in areas to be selected | The water retention structures evaluation study was finalized for the two Wilayas of the Gorgol and Guidimakha for 12 sites of the project. | Area where days of water availability has increased with at least 20%
Output 2.4: Water retention structures built covering approx. 500 ha. | Number, kind, surface size and volume (where applicable) of water retention structures | 13 sites have dams, check dams, Soil and water conservation structures, Soil restoration structures | An assessment study is completed. Preparations are ahead to begin implementation across 10 sites in two Wilayas (Guidimakha and Gorgol) to protect about 280 ha of degraded lands. This activity will be continued to other Wilayas and sites in forthcoming years. We decided to begin implementation after the rainy period, which start in June in the Wilaya of Guidimakha. tenders are launched to start implementation in January 17 | Communities construct and maintain retention assets according to plan
OBJECTIVE 3 Design and implement concrete adaptation measures identified through community adaptation planning that aim to diversify and strengthen the livelihoods of the most vulnerable population » | Number and type of implemented community adaptation plan action aiming to diversify and strengthen the livelihoods of the most vulnerable population | No adaptation plans are in place, livelihood bases are hardly diversified in areas to be selected | The adaptation action plans drawn up in the different project sites integrate diverse income-generating activities to diversify and strengthen livelihoods and food security of targeted communities. | Communities have implemented adaptation plan action and continue to gain sustainable income from new sources
Outcome 3.1: Increased number of sources of income for participating households | Number and type of sources of income for participating households before and after the project | Livelihood bases are hardly diversified in areas to be selected – specific baselines to be established as part of adaptation plan preparation (The communities practice seven (7) income generating activities including 04 based on the exploitation of natural resources (agriculture, livestock, fishing and fruit picking) | So far, some new income-generating activities have been introduced in many project sites : - High value crop production, in 52% of ttotal project sites - Poultry, in 55% of total project sites - Beekeeping, in 9% of total project sites - Fruit farming, in 21% of total project sites | At least 25% of village cluster population have increased their livelihood bases with new sources of income
Outcome 3.2: Increased income for participating households | Level of income for participating households before and after the project | Participating households are among the poorest in the selected areas. | Evaluation to be carried out during the third and fourth year of implementation of the project. | Participating households have increased their revenues by at least 40%
Outcome 3.3: Increased availability of and access to food for participating communities | Food gap (number of weeks/months) for participating households before and after the project | Participating households have the greatest food gap in the selected areas. (The number of food deficit months range from 1 to 10) | Evaluation to be carried out during the third and fourth year of implementation of the project. | Participating households have decreased their food gap by at least 50%
Output 3.1: Approx. 300,000 trees for revenue generation and food planted in protected areas. | Number of trees planted and growing in protected areas; amount of food and revenue gained from these. | Baseline to be established as part of adaptation plan | Fruit tree plantation has been carried out in N'Beiket Lahwech in the Wilaya of Hodh Chergui in the beginning of May 2016, which was visited by the Mauritanian President. 500 trees were planted for the benefit of 150 households (3 trees for each family). Also some equipment were distributed to these families. The fruit trees plantation Programme implementation will start beginning 2017 with the collaboration of Centre for Agricultural Research and Agricultural Development (CNRADA) in the 8 Wilayas with the following programme: • 19 project sites in the 8 regions • 10 300 fruit trees to be planted • 3 166 households concerned • 18 770 direct beneficiaries | Planted trees already are – or have at least a clear prospect of – providing substantial amounts of food and income
Output 3.2: 4,000 technical staff and community leaders trained in livestock management, agricultural techniques and water utilization. | Number of people (gender disaggregated) trained |  | A framework agreement was signed with Training Centre for Rural Producers of Boghé (CFPR). - 40 veterinary assistants (1 woman, and 39 men) have been trained and equipped with basic veterinary medicines to provide adequate services in their villages and neighboring with respect to climate-related risks and diseases. - 80 rural high value crops producers (28 women and 52 men) have be trained during 5 days in the field of Cooperative management and organization. Objective: prepare the disengagement of the project and ensuring sustainability of the activity. | Extension staff and cluster population are aware of and apply appropriate techniques
Output 3.3: 5,000 technical staff and community leaders trained and equipped for plant/seed multiplication. | Number of people (gender disaggregated) trained | Hardly any training is available in areas to be selected; extension staff requires training, too | Planting of high value crops started In November 2015 • 37 sites covering 67 ha • Necessary Material and seeds delivered for alla Village Management committies • Proramme oversee is ensured by Rigional Agriculture services to support the cooperatives during the different phases of the campaign. • 4582 community producers have been coached in implementing and producing high value crops in 37 project sites. • Number of beneficiaries : 27492. | Extension staff and cluster population are aware of and apply appropriate techniques
Output 3.4: 4,000 technical staff and community leaders trained and equipped for poultry development. | Number of people (gender disaggregated) trained | Hardly any training is available in areas to be selected; extension staff requires training, too | 50 (40 traditional and 10 semi-intensive) shelters for the development of poultry farming in rural areas were built and equipped for the benefit of 400 women and 100 young men of the project within the 8 wilayas of project intervention. On this basis and at the rate of 6 persons per household, the direct beneficiaries are evaluated at 3000 beneficiaries. The implementation is supported by a consulant hired by the project who's been working in a previous project (ProlPRAF) funded by the FIDA. It's a scaling up with some improvements of the ProlPRAF experience. Implementation is still ongoing. | Extension staff and cluster population are aware of and apply appropriate techniques
Output 3.5: 1,600 technical staff and community leaders trained and equipped for apiculture. | Number of people (gender disaggregated) trained | Hardly any training is available in areas to be selected; extension staff requires training, too | Technical study is completed. 8 project sites in 5 Wilayas (Trarza, Brakna, Gorgol, Guidimaka and Tagant.) were identified to develop beekeeping activities. 72 participants including 37 men and 35 women. The direct beneficiaries are 432 people at the rate of 6 persons per household. WFP supervised the procurement of equipment needed for the Programme implementation. The project hired Apidesert, a local specialised compagny, to oversee the Programme implementation and beneficiaries’ trainings. Starting date 1st October 2016. | Extension staff and cluster population are aware of and apply appropriate techniques
Output 3.6: Approx. 20 community cereal banks established. | Number of functioning village cereal bank associations; volume of cereals and money in bank. | No village-owned cereal banks exist in areas to be selected | n/a | Participating communities own their VCB, membership, money and food held by associations is stable
Output 3.7: 30,000 fuel efficient stoves provided. | Number of fuel efficient stoves built by participating communities; share of reduced consumption of fuel wood | Fuel-efficient stoves are hardly know and available in areas to be selected – to be confirmed during adaptation planning (The communities of 10 villages already use improved stoves) | n/a | Communities know, understand and use fuel efficient stoves; fuel-wood consumption by participating households reduced by at least 40%
Output 3.8: 2,000 community members (mostly youth) trained to build and maintain fuel efficient stoves. | Number of people (gender-disaggregated) trained | No training is available in areas to be selected; extension staff requires training, too. 14 artisans are already trained to manufacture improved stoves) | n/a | In all participating communities a group of people regularly builds and repairs fuel-efficient stoves;

## Lessons Learned
QUALITATIVE MEASURES and LESSONS LEARNED
Please complete the following section every reporting period
Implementation and Adaptive Management | Response
What implementation issues/lessons, either positive or negative, affected progress? | The lesson learned that we can point out during this reporting period is the establishment of a framework agreement with the Center for Traning of Rural Producers (CFPR) of Boghé which is under the supervision of ENFVA (National School of Agricultural Extension and Training) of the Ministry of Agriculture. CFPR has the infrastructure, equipments, knowledge and manpower to carry out training activities for beneficiaries identified in the ACC action plans. This framework agreement benefit the project in many aspects such as precious time saved during tendering of procurement procedures. Contracts are signed on the basis of the execution of the training program and according to standards agreed in advance.
Were there any delays in implementation? If so, include any causes of delays. What measures have been taken to reduce delays? | During the rainy season (June-August), many project sites become inaccessible due to the impracticability of the terrain. This situation is very cumbersome and causes a slowdown in the execution of activities. Also, DREDD as Regional responsibles for the environmental sector are fully busy with the bushfire campaign that runs from September to December of each year. In this period there is a lack in supervising project activity execution. NGOs recruitment at the beginning of 2017, will help attenuate this problem and improve supervision of the project activities. Procurement tender procedures contribute also in delaying implementation. Sometimes qualified or suitable candidates are not always available.
Describe any changes undertaken to improve results on the ground or any changes made to project outputs (i.e. changes to project design) | In the first PPR, we reported 400 ha of sand dunes fixation. But after final evaluation was undertaken we concluded that the 400 ha initially reported should have been split between sand dune fixation and community fuel wood forest plantation as follows: Output 2.1 : 305 ha of sand dune fixed Output 2.3 : 98 ha of community fuel wood forests afforested The analysis of the 2 year project implementation shows that outputs 2.1 and 2.3 were largely overestimated. Thus, we recommend that the aforementioned outputs to be reviewed and the corresponding initially allocated budget to be ajusted as well. This will be reflected in the budget for 2017. Furthermore, outputs 3.1, 3.2, 3.3, 3.4 shoud be also reviewed and adjusted during the MTR as they were also overestimated. | ;
How have gender considerations been taken into consideration during the reporting period? What have been the lessons learned as a consequence of inclusion of such considerations on project performance or impacts? | Gender have been taken into consideration during the elaboration of participatory adaptation action planning. Indeed, special attention was given to the gender aspect in income generating activities such as poultry (ratio of 80% women and 20% men), Apiculture and high valued crop production (ratio of 50% women and 50% men)
Please complete the following section at mid-term and project completion
Lessons for Adaptation | Response
Climate Resilience Measures
What have been the lessons learned, both positive and negative, in implementing climate adaptation measures that would be relevant to the design and implementation of future projects/programmes for enhanced resilience to climate change?
What is the potential for the climate resilience measures undertaken by the project/programme to be replicated and scaled up both within and outside the project area?
Concrete Adaptation Interventions
What have been the lessons learned, both positive and negative, in implementing concrete adaptation interventions that would be relevant to the design and implementation of future projects/programmes implementing concrete adaptation interventions?
What is the potential for the concrete adaptation interventions undertaken by the project/programme to be replicated and scaled up both within and outside the project area?
Community/National Impact
What would you consider to be the most successful aspects for the target communities?
What measures are/have been put in place to ensure sustainability of the project/program results?
What measures are being/could have been put in place to improve project/program results?
Knowledge Management
How has existing information/data/knowledge been used to inform project development and implementation? What kinds of information/data/knowledge were used?
If learning objectives have been established, have they been met? Please describe.
Describe any difficulties there have been in accessing or retrieving existing information (data or knowledge) that is relevant to the project. Please provide suggestions for improving access to the relevant data.
Has the identification of learning objectives contributed to the outcomes of the project? In what ways have they contributed?

## Results Tracker
Results Tracker for Adaptation Fund (AF) Projects
Goal: Assist developing-country Parties to the Kyoto Protocol that are particularly vulnerable to the adverse effects of climate change in meeting the costs of concrete adaptation projects and programmes in order to implement climate-resilient measures. Impact: Increased resiliency at the community, national, and regional levels to climate variability and change.
Important: Please read the following guidance document (also posted on the Adaptation Fund website) before entering your data
Link: http://www.adaptation-fund.org/sites/default/files/Results%20Framework%20and%20Baseline%20Guidance%20final.pdf
Adaptation Fund Strategic Results Framework
Project ID | MTN/MIE/Food/2011/1/PD
Implementing Entity | WFP, Mauritania
Type of implementing entity | MIE
Country | Mauritania
Region | Africa
Sector | Food security
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Impact: Increased resiliency at the community, national, and regional levels to climate variability and change | Core Indicator: No. of beneficiaries |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project
|  | Total | 186718 | 37368 | 149350 | Total | 160590 | 23670 | 136920 | Total |  |  |  | Total
|  | % of female beneficiaries | 59.15% |  |  | % of female beneficiaries | 50% | 50% | 50% | % of female beneficiaries |  |  |  | % of female beneficiaries
|  | % of Youth beneficiaries | 43.6% |  |  | % of Youth beneficiaries | 8% | 8% | 8% | % of Youth beneficiaries |  |  |  | % of Youth beneficiaries
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 1: Reduced exposure to climate-related hazards and threats | Indicator 1: Relevant threat and hazard information generated and disseminated to stakeholders on a timely basis | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness
|  | Total |  |  |  | Total |  |  |  | Total |  |  |  | Total
|  | % of female targeted |  |  |  | % of female targeted |  |  |  | % of female targeted |  |  |  | % of female targeted
Output 1.1 Risk and vulnerability assessments conducted and updated | Indicator 1.1: No. of projects/programmes that conduct and update risk and vulnerability assessments | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
Output 1.2 Targeted population groups covered by adequate risk reduction systems | Core Indicator 1.2: No. of Early Warning Systems | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  | 0 | 3: Dissemination and communication | Geographical coverage | Regional | 1 | 3: Dissemination and communication | Geographical coverage | Regional |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities | 0 |  |  | Number of municipalities | 75 |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 2: Strengthened institutional capacity to reduce risks associated with climate-induced socioeconomic and environmental losses | Indicator 2: Capacity of staff to respond to, and mitigate impacts of, climate-related events from targeted institutions increased | Number of staff targeted |  | Sector | Capacity level | Number of staff targeted |  | Sector | Capacity level | Number of staff targeted |  | Sector | Capacity level | Number of staff targeted |  | Sector | Capacity level
|  | Total | 300 | Multi-sector | 1: No capacity | Total | 300 | Multi-sector | 3: Medium capacity | Total |  |  |  | Total
|  | % of female targeted | 10% |  |  | % of female targeted | 10% |  |  | % of female targeted |  |  |  | % of female targeted
Output 2.1 Strengthened capacity of national and sub-national centres and networks to respond rapidly to extreme weather events | Indicator 2.1.1: No. of staff trained to respond to, and mitigate impacts of, climate-related events | Total staff trained | % of female staff trained | Type |  | Total staff trained | % of female staff trained | Type |  | Total staff trained | % of female staff trained | Type |  | Total staff trained | % of female staff trained | Type
|  | 180 | 10% | Public |  | 180 | 10% | Public
|  | 120 | 10% | NGO |  | 120 | 10% | NGO
| Indicator 2.1.2: No. of targeted institutions with increased capacity to minimize exposure to climate variability risks | Type | Scale | Sector | Capacity level | Type | Scale | Sector | Capacity level | Type | Scale | Sector | Capacity level | Type | Scale | Sector | Capacity level
|  | Public | National | Multi-sector | 1: No capacity | Public | National | Multi-sector | 3: Medium capacity
|  | Public | Regional | Multi-sector | 1: No capacity | Public | Regional | Multi-sector | 3: Medium capacity
|  | NGO | Regional | Multi-sector | 1: No capacity | NGO | Regional | Multi-sector | 3: Medium capacity
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 3: Strengthened awareness and owernship of adaptation and climate risk reduction processes | Indicator 3.1: Increase in application of appropriate adaptation responses | Percentage of targeted population applying adaptation measures |  | Sector |  | Percentage of targeted population applying adaptation measures |  | Sector |  | Percentage of targeted population applying adaptation measures |  | Sector |  | Percentage of targeted population applying adaptation measures |  | Sector
Output 3: Targeted population groups participating in adaptation and risk reduction awareness activities | Indicator 3.1.1: Percentage in targeted population awareness of predicted adverse impacts of climate change, and of appropriate responses | No. of targeted beneficiaries | % of female participants targeted | Level of awareness |  | No. of targeted beneficiaries | % of female participants targeted | Level of awareness |  | No. of targeted beneficiaries | % of female participants targeted | Level of awareness |  | No. of targeted beneficiaries | % of female participants targeted | Level of awareness
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Target performance at completion |  |  |  | Target performance at completion
Outcome 4: Increased adaptive capacity within relevant development sector services and infrastructure assets | Indicator 4.1: Increased responsiveness of development sector services to evolving needs from changing and variable climate | Project/programme sector | Geographical scale | Response level |  | Project/programme sector | Geographical scale | Response level |  | Project/programme sector | Geographical scale | Response level |  | Project/programme sector | Geographical scale | Response level
| Core Indicator 4.2: Assets produced, developed, improved or strengthened | Sector | Targeted asset | Changes in asset (quantitative or qualitative) |  | Sector | Targeted asset | Changes in asset (quantitative or qualitative) |  | Sector | Targeted asset | Changes in asset (quantitative or qualitative) |  | Sector | Targeted asset | Changes in asset (quantitative or qualitative)
|  | Agriculture | 2: Physical asset (produced/improved/strenghtened) | 1: Not improved |  | Agriculture | 2: Physical asset (produced/improved/strenghtened) | 4: Mostly Improved
|  | Food security | 2: Physical asset (produced/improved/strenghtened) | 1: Not improved |  | Food security | 2: Physical asset (produced/improved/strenghtened) | 4: Mostly Improved
|  | Water management | 2: Physical asset (produced/improved/strenghtened) | 1: Not improved |  | Water management | 2: Physical asset (produced/improved/strenghtened) | 4: Mostly Improved
|  | Other | 2: Physical asset (produced/improved/strenghtened) | 1: Not improved |  | Other | 2: Physical asset (produced/improved/strenghtened) | 4: Mostly Improved
Output 4: Vulnerable development sector services and infrastructure assets strengthened in response to climate change impacts, including variability | Indicator 4.1.1: No. and type of development sector services to respond to new conditions resulting from climate variability and change | Number of services | Type |  | Sector | Number of services | Type |  | Sector | Number of services | Type |  | Sector | Number of services | Type |  | Sector
|  | Baseline information |  |  |  | Baseline information |  |  |  | Baseline information |  |  |  | Baseline information
Outcome 5: Increased ecosystem resilience in response to climate change and variability-induced stress | Indicator 5: Ecosystem services and natural resource assets maintained or improved under climate change and variability-induced stress | Natural resource improvement level |  | Sector | Type | Natural resource improvement level |  | Sector | Type | Natural resource improvement level |  | Sector | Type | Natural resource improvement level |  | Sector | Type
Output 5: Vulnerable ecosystem services and natural resource assets strengthned in response to climate change impacts, including variability | Core Indicator 5.1: Natural Assets protected or rehabilitated | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Rangelands | 1500 | ha protected | 1: Ineffective | Rangelands | 1500 | ha protected | 4: Effective
|  | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Catchment area/Watershed/Aquifer | 500 | ha protected | 1: Ineffective | Catchment area/Watershed/Aquifer | 500 | ha protected | 4: Effective
|  | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Forests | 1500 | ha protected | 1: Ineffective | Forests | 1500 | ha protected | 4: Effective
|  | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Cultivated land/Agricultural land | 1000 | ha rehabilitated | 1: Ineffective | Cultivated land/Agricultural land | 1000 | ha rehabilitated | 4: Effective
|  | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Other | 2000 | ha protected | 1: Ineffective | Other | 2000 | ha protected | 4: Effective
|  | Baseline information |  |  |  | Targeted performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 6: Diversified and strengthened livelihoods and sources of income for vulnerable people in targeted areas | Indicator 6.1: Increase in households and communities having more secure access to livelihood assets | No. of targeted households | % of female headed households | Improvement level |  | No. of targeted households | % of female headed households | Improvement level |  | No. of targeted households | % of female headed households | Improvement level |  | No. of targeted households | % of female headed households | Improvement level
| Indicator 6.2: Increase in targeted population's sustained climate-resilient alternative livelihoods | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
|  | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
|  | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
|  | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
Output 6 Targeted individual and community livelihood strategies strengthened in relation to climate change impacts, including variability | Indicator 6.1.1: No. and type of adaptation assets created or strengthened in support of individual or community livelihood strategies | Number of Assets | Type of Assets | Sector | Adaptation strategy | Number of Assets | Type of Assets | Sector | Adaptation strategy | Number of Assets | Type of Assets | Sector | Adaptation strategy | Number of Assets | Type of Assets | Sector | Adaptation strategy
| Core Indicator 6.1.2: Increased income, or avoided decrease in income | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | 16983 | Agricultural-related |  | 356.2333 |  | Agricultural-related
|  | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | 72 | Fishing |  | 775.7767 |  | Fishing
|  | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | 688 | Forestry |  | 372.36 |  | Forestry
|  | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | 15069 | Livestock production |  | 1115.2 |  | Livestock production
|  | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | 3090 | Services |  | 1563.3067 |  | Services
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 7: Improved policies and regulations that promote and enforce resilience measures | Indicator 7: Climate change priorities are integrated into national development strategy | Integration level |  |  |  | Integration level |  |  |  | Integration level |  |  |  | Integration level
Output 7:Improved integration of climate-resilience strategies into country development plans | Indicator 7.1: No. of policies introduced or adjusted to address climate change risks | No. of Policies introduced or adjusted | Sector | Scale | Type | No. of Policies introduced or adjusted | Sector | Scale | Type | No. of Policies introduced or adjusted | Sector | Scale | Type | No. of Policies introduced or adjusted | Sector | Scale | Type
| Indicator 7.2: No. of targeted development strategies with incorporated climate change priorities enforced | No. of Development strategies | Regulation |  | Effectiveness | No. of Development strategies | Regulation |  | Effectiveness | No. of Development strategies | Regulation |  | Effectiveness | No. of Development strategies | Regulation |  | Effectiveness
Glacier lake outburst flood
|  | Inland flooding | fr | biological assets |  | Company policy | 5: Fully enforced (All elements implemented)
|  | Salinization | Decrease | land |  | Communication & Information policy | 4: Enforced (Most elements implemented)
|  | Drought | Same | water areas |  | Defense policy | 3: Partially enforced (Some elements implemented)
|  | Wind |  | subsoil assets | increased adpative capacity | Domestic policy | 2: Partially not enforced (Most elements not implemented) |  | Agribusiness
|  | Coastal flooding |  | air | achieved | Economic policy | 1: Not enforced (No elements implemented) |  | Agricultural-related | Financial capital
|  | Storm surge | Please choose |  | enhanced level of protection | Education policy |  |  | Agriculture | Human capital
|  | Hurricane | Selected | [5 empty] | Aquaculture | Physical capital
|  |  | Not relevant |  |  | 5: All (Fully integrated) |  |  | Construction/repairing business | Social capital
[6 empty] | 4: Most |  |  | Cultivation | Natural capital
[6 empty] | 3: Some |  |  | Fishing | Personal capital
Select | 5: All | Select |  |  | Community | 2: Most not integrated |  | Other | Forestry | Adaptation strategies
1 | 4: Almost all | Private | Type | Yes | Multi-community | 1: None |  | Agriculture | Handicrafts
2 | 3: Half | Public | Scale | No | Departmental |  |  | Coastal management | Livestock production
3 | 2: Some | NGO | Sector |  | National |  |  | Disaster risk reduction | Manufacturing
4 | 1: None |  |  |  |  | 5: Very high improvement | Established | Food security | other
|  | National |  |  |  | 4: High improvement | Maintained | Health | Services
|  | Regional |  |  |  | 3: Moderate improvement | Improved | Urban development | Tourism-related
|  | Local |  |  |  | 2: Limited improvement |  | Water management | Trading
[6 empty] | 1: No improvement |  | Multi-sector
|  | 1 -generated information is irrelevant, and neither the stakeholders reached nor the timeframe managed were achieved | 1: No info transferred on time | 4: High capacity | 5: Fully aware | 5: Highly responsive (All defined elements ) | 5: Fully improved | Roads | 5: Very effective
Asia-Pacific | NIE | 2 -the existence of some challenge in any of the three aspects of the indicator (generation of dissemination, stakeholders reached or timeframe managed) | 2: Somewhat info transferred | 3: Medium capacity | 4: Mostly aware | 4: Mostly responsive (Most defined elements) | 4: Mostly Improved | Gov Buildings | 4: Effective
Latin America and Caribbean | RIE | 3 -relevant information is generated and disseminated to all identified stakeholders on timely basis | 3: Info transferred on time | 2: Low capacity | 3: Partially aware | 3: Moderately responsive (Some defined elements) | 3: Moderately improved | Causeways | 3: Moderately effective
Africa | MIE |  |  | 1: No capacity | 2: Partially not aware | 2: Partially responsive (Lacks most elements) | 2: Somewhat improved | Airports | 2: Partially effective
Eastern Europe |  |  |  |  | 1: Aware of neither | 1: Non responsive (Lacks all elements ) | 1: Not improved | Schools | 1: Ineffective
| ha protected | [6 empty] | Training Centres
| ha rehabilitated | [5 empty] | Monitoring/Forecasting capacity | Hospitals
Afghanistan, Islamic Rep. of | km protected | [5 empty] | Policy/regulatory reform | Drinking water systems
Angola | km rehabilitated | 1: Risk knowledge | 1: No plans conducted or updated |  |  |  | Capacity development | Other
Albania |  | 2: Monitoring and warning service | 2: Undertaking or updating of assessments in progress |  |  | Communication & Information policy | Sustainable forest management
Argentina |  | 3: Dissemination and communication | 3: Risk and vulnterability assessments completed or updated |  |  | Domestic policy | Strengthening infrastructure | 1: Health and Social Infrastructure (developed/improved)
Armenia | Forests | 4: Response capability |  |  |  | Economic policy | Supporting livelihoods | 2: Physical asset (produced/improved/strenghtened)
Antigua and Barbuda | Mangroves |  |  |  |  | Education policy | Mangrove reforestation
Azerbaijan | Coasts |  | From 0 to 0.5% |  |  | Energy policy | Coastal drainage and infrastructure
Burundi | Rangelands |  | From 0.5 to 1% |  |  | Environmental policy | Irrigation system
Benin | Cultivated land/Agricultural land |  | From 1% to 5% |  |  | Foreign policy | Community-based adaptation
Burkina Faso | Catchment area/Watershed/Aquifer |  | From 5% to 10% |  |  | Health policy | Erosion control
Bangladesh | Protected areas/National parks |  | From 10% to 20% |  |  | Housing policy | Soil water conservation
Bulgaria | Other |  | From 20% to 30% |  |  | Human resource policies | Microfinance
Bahrain |  |  | From 30% to 40% |  |  | Information policy | Special Program for women
Bahamas, The |  |  | From 40% to 50% |  |  | Macroeconomic policy | Livelihoods
Bosnia and Herzegovina |  |  | Above 50% |  |  | Monetary policy | Water storage
Belarus | [5 empty] | Population policy | ICT and information dissemination
Belize | [5 empty] | Private policy
Bolivia | [5 empty] | Public policy
Brazil | [5 empty] | Science policy
Barbados | [5 empty] | Social policy
Bhutan |  | 3- relevant information is generated and disseminated to all identified stakeholders on timely basis |  |  |  | Transportation policy
Botswana |  | describe |  |  |  | Urban policy
Central African Republic |  | 2- the existence of some challenge in any of the three aspects of the indicator |  |  |  | Water policy
Chile |  | describe |  |  |  | Other policy
China, People's Republic of |  | 1- generated information is irrelevant and neither the stakeholders reached nor the timeframe managed were achieved
Cote d'Ivoire |  | describe
Cameroon
Congo, Dem. Rep. of
Congo, Republic of
Cook Islands
Colombia
Comoros
Cape Verde
Costa Rica
Cuba
Czech Republic
Djibouti
Dominica
Dominican Republic
Algeria
Ecuador
Egypt
Eritrea
Estonia
Ethiopia
Fiji
Micronesia, Fed. States of
Gabon
Georgia
Ghana
Guinea
Gambia, The
Guinea-Bissau
Equatorial Guinea
Grenada
Guatemala
Guyana
Honduras
Croatia
Haiti
Hungary
Indonesia
India
Iran, Islamic Republic of
Jamaica
Jordan
Kazakhstan
Kenya
Kyrgyz Republic
Cambodia
Kiribati
Saint Kitts and Nevis
Korea, Republic of
Lao People's Democratic Republic
Lebanon
Liberia
Libya
Saint Lucia
Sri Lanka
Lesotho
Lithuania
Latvia
Morocco
Moldova
Madagascar
Maldives
Mexico
Marshall Islands
Macedonia, former Yugoslav Republic of
Mali
Malta
Myanmar
Montenegro
Mongolia
Mozambique
Mauritania
Mauritius
Malawi
Malaysia
Namibia
Niger
Nigeria
Nicaragua
Niue
Nepal
Nauru
Oman
Pakistan
Panama
Peru
Philippines
Palau
Papua New Guinea
Poland
Korea, Dem. People's Rep. of
Paraguay
Romania
Russian Federation
Rwanda
Saudi Arabia
Sudan
Senegal
Solomon Islands
Sierra Leone
El Salvador
San Marino
Serbia
Sao Tome and Principe
Suriname
Slovak Republic
Slovenia
Swaziland
Seychelles
Syrian Arab Republic
Chad
Togo
Thailand
Tajikistan
Turkmenistan
Tonga
Trinidad and Tobago
Tunisia
Turkey
Tuvalu
Tanzania
Uganda
Ukraine
Uruguay
Uzbekistan
Saint Vincent and the Grenadines
Venezuela
Vietnam
Vanuatu
Samoa
Yemen, Republic of
South Africa
Zambia
Zimbabwe
Timor-Leste

## Units for Indicators
Fund Outcome Indicator Units
1. Generation of relevant data, Stakeholders, and Timeliness 2.1. Include both qualitative and quantitative measures of capacity level within targeted institutions 2.2. Number (men and women and other vulnerable groups) 3.1. Use scale from 1 to 5: 5: Fully aware 4: Mostly aware 3: Partially aware 2: Partially not aware 1: Aware of neither predicted adverse impacts of climate change nor of appropriate responses 3.2. Use scale from 1 to 5: 5: All 4: Almost all 3: Half 2: Some 1: None 4.1. Summarize in an overall scale (1-5): 5: Highly responsive (All defined elements ) 4: Mostly responsive (Most defined elements) 3: Moderately responsive (Some defined elements) 2: Partially responsive (Lacks most elements) 1: Non responsive (Lacks all elements ) 4.2. Summarize in an overall scale (1-5): 5: Fully improved 4: Mostly Improved 3: Moderately improved 2: Somewhat improved 1: Not improved 5. Depends on the targeted natural asset: Biological (species): measure through changes in population numbers (dynamics, structure, etc.) Land: measure changes in hectares. Baseline data will be necessary to estimate the change. Supporting indicators baseline and target (as well as contextual information) are needed such as the following: Farmers adopting recommended technologies, Ha. of land improved, Average deforestation rate Etc. Use scale from 1 to 5. 5: Very effective (All elements are present) 4: Effective (Most elements are present) 3: Moderately effective (Some elements are present) 2: Partially effective (Most elements are not present) 1: Ineffective (No elements are present) 6.1. Summarize in an overall scale (1-5): 5: Very high improvement 4: High improvement 3: Moderate improvement 2: Limited improvement 1: No improvement 6.2. Household income by source of livelihood in project area (USD) prior and post project intervention 7. Summarize in an overall scale (1-5). 5: All (Fully integrated) 4: Most 3: Some 2: Most not integrated 1: None
Fund Output Indicator Units
1.1. Number, sector(s) and level(s) of projects or interventions in separate fields of monitoring plan 1.2. Number 2.1.1. Number of staff (male/female) of targeted institutions: a. Obtain baseline information: total number of staff from targeted institutions b. Define target 2.1.2. Number of staff (male/female) of targeted institutions: a. Obtain baseline information: total number of staff from targeted institutions b. Define target: needs to be defined by project proponents 2.2.1. Quantitative: Percentage (includes women – and other vulnerable groups – and men). Qualitative: Adequacy: include direct analysis of major areas; adequacy/effectiveness of systems or analysis of perceptions of populations and institutions. 2.2.2. Number (broken down by gender and, if possible, by vulnerable groups defined in the area of intervention) of people 3.1. Number and type (in separate columns) at local level. 3.2. Number 4.1. Number and type 4. 2. Number and type (entered in separate columns) 5. Number of interventions by type of natural asset and intervention 6.1. Number and type (in separate columns of monitoring plan) 6.2. Income sources per household; description of income source and number of households. 7.1. Number/Sector 7.2. Number; Effectiveness (see previous indicator) through enforcement level.

## Financial annex
Explanatory notes on variances between planned and actual expenditures of outputs during the reporting period
ITEM / ACTIVITY / ACTION | Year 2 Actual amount spent US$ | Projected in Prodoc (US$) | Difference (negative amount indicates amount overspent) | Reason for over or underspending | % Planned budget spent
Output 1.1 Eight DREDD (regional technical services of MEDD) strengthened to access and analyze climate change information, to monitor local development and to mobilize and support communities | 55557.9951 | 328248.7426 | 272690.7475 | The hiring process of NGOs registered a very important delay because of the sensitivity of the issue. The MEDD had a very bad experience with NGOs in the implementation of a major project. So, precautions have been taken to ensure that the process is carried out in a transparent manner so as to select only well-performing NGOs. | 16.93%
Output 1.2 Strengthening of Government's threat, risk and vulnerability analysis | 12402.3347 | 77019.3896 | 64617.0549 | Discussions about the implementation of an Early Warning System (EWS) at community level are still ongoing with project partners (ONM, SAM, GIZ, OSA, OXFAM, Rural Radios …) on synergy to develop a framework on providing reliable climate information and the way to do that. | 16.1%
Output 1.3: 20 inter-village associations established and supported |  | 24506.6667 | 24506.6667 | Same reason as Output 1.1 | 0%
Output 1.4:Communities trained in climate change threats and adaptation measures which reduce vulnerability, in particular related to food insecurity |  | 21797.0495 | 21797.0495 | Same reason as Output 1.1 | 0%
Output 1.5:100 villages, being clustered according to landscape, ecosystem and livelihoods, have prepared adaptation plans that are integrated into local development planning. |  | 24569.7555 | 24569.7555 | Same reason as Output 1.1 | 0%
Output 1.6: Communities share success stories and lessons learned, including support of 8 community radios |  | 274750 | 274750 | As there are still outstanding issues concerning the partners involved to benefit from the support of the project (National Radio, Rural Radio and Local Radio), we have continued discussions to define the real needs and beneficiaries and agreed that implementation starts after the second year of project implementation. | 0%
Output 1.7: Monitoring system in place (establishment, training, production of data and reports) to track climate events and ecologic development in project intervention zones. | 19838.4267 | 96000 | 76161.5733 | Training in M&E for NGOs and communities did not take place during the reporting period. | 20.67%
Output 2.1: 1500 - 2000 ha of sand dunes fixated | 100466.9134 | 86400 | -14066.9134 | The analysis of the 2 year project implementation shows that output 2.1 is largely overestimated and incidentally the budget allocated underestimated. Thus, the output should be reviewed and the corresponding budget initially allocated adjusted as well. | 116.3%
Output 2.2: 1000 - 1500 ha of vulnerable zones protected | 136338.8771 | 434798.7148 | 298459.8377 | This output is almost fully achieved with the protection of 950 ha. This result is rather overestimated and we propose to reallocate the saved budget for the output 2.1 | 31.36%
Output 2.3 1,000-1,500 ha of community fuel wood forests planted. | 59954.0475 | 294150 | 234195.9525 | Afforestation was carried out, to consolidate sites planted in 2015 and start new sites. Cash distribution is still to be done for this activity | 20.38%
2.4 Water retention structures built covering approximately 500 ha | 8686.5365 | 294150 | 285463.4635 | The tendering process is taking more time than initially planned because received propositions were not appropriate. A new call for tender has been initiated. | 2.953%
Output 3.1 300,000 trees for revenue generation and food planted in protected areas | 28827.7833 | 275900 | 247072.2167 | The Programme implementation for 2016 will start in January 2017, after contract agreement has been reached with CNRADA. January is the best period in Mauritania to start plantation. | 10.45%
Output 3.2 4,000 technical staff and community leaders trained in livestock management, agricultural techniques and water utilization | 35165.605 | 202315.7895 | 167150.1845 | Part of the output was planned to be implemented by NGOs which are not yet in place so we were not able to consume the budget as initially planned | 17.38%
Output 3.3 5,000 technical staff and community leaders trained and equipped agro-pastoral IGA, including plant multiplication | 52401.6313 | 253894.7368 | 201493.1056 | The NGOs are not yet in place so we were not able to implement many community IGA activities. | 20.64%
Output 3.4 6,000 technical staff and community leaders trained and equipped for poultry development | 139047.881 | 215861.5789 | 76813.6979 | The program implementation is on track. It's to be finished in February 2017. | 64.42%
Output 3.5 1,000 technical staff and community leaders trained and equipped for apiculture | 76780.3038 | 125463.9474 | 48683.6436 | The Programme implementation for 2016 is still ongoing. Part of the planned budget will be executed in the next year. | 61.2%
Output 3.6 Approx. 20 community cereal banks established. |  | 0 | 0 | Planned for year 3 | 0%
Output 3.7 30,000 fuel efficient stoves built |  | 148220 | 148220 | Postponed to Year 3 | 0%
Output 3.8 2,000 community members (mainly youth) trained and equipped to build and maintain fuel efficient stoves |  | 92293.6842 | 92293.6842 | Postponed to Year 3 | 0%
TOTAL | 725468.3353 | 3270340.0555
We can note 4 general reasons for the low disbursement rate during the second year : 1. Many activities started in August after the rainy season (end of the reporting period) like plantation, water and soil conservation activities and Fruit tree plantations. 2. DREDDs, regional project coordinator, after the rainy season are fully involved in the annual bushfire programme monitoring for a period of 3 months with a low supervision of project activities. 3. We registered a delay in hiring NGO as project partners 4. The budget programmed for the second year was very ambitious with the objective to catch up on the delay recorded during the first year of the project implementation. This budget was over-estimated and we do not have the capacity to absorb it.