## Overview
Project Performance Report (PPR)
| Period of Report (Dates) | 25/03/2015 - 11/06/2016
| Project Title: | TF 015041 - INCREASING CLIMATE RESILIENCE AND ENHANCING SUSTAINABLE LAND MANAGEMENT IN THE SOUTHWEST OF THE BUENOS AIRES PROVINCE
| Project Summary: | The PDO is to contribute to reducing climate and man-made vulnerability of the agroecosystems in the Southwest of the Buenos Aires Province by increasing adaptive capacity of key local institutions and actors and piloting and disseminating climate resilient and sustainable land management practices. Participatory planning processes will be used to identify and pilot concrete adaptation measures focusing on water, crops and livestock management to promote climate resilience. The Project aims at benefitting farmers and farmer families engaged in small and medium-sized agricultural-cattle production on dry lands within the direct and indirect intervention zones; counties of Puán, Villarino and Patagones, and 9 further SWBA counties, respectively. Additionally, a wide range of actual and potential partner organizations working on related aspects within the area and up to national level will benefit from and contribute to a comprehensive set of capacity building and institutional strengthening measures. The continued, inter-sectoral and inter-institutional learning process in which the project is based, supported by cross-institutional work aimed at (1) creating an adequate political, social, and economic framework to ensure adoption, sustainability, continuity, and further development of the adaptation efforts; and (2) bolstering and fine-tuning adaptation measures identified and chosen through institutional and community-level capacity building.
|  |  | Countries | Project Type: |  | GEF Focal Area: | GEF 4 Focal Areas | GEF 2 / 3 Operational Programme: | Overall Rating of the project in the evaluation by the project evaluator: | GEF-4 Focal Area Strategic Program: | GEF-3 Focal Area Strategic Program:
| Database Number: | ARG/MIE/Rural/2011/1 | Afghanistan | FP | Yes | Biodiversity | 1 | 1 | U | BD-SP1-PA Financing | 1: Arid & semi-arid ecosystems
Implementing Entity (IE) [name]: |  | World Bank | Albania | MSP | No | Climate Change Adaptation | 2 | 2 | S | BD-SP2-Marine PA | 2: Coastal, marine & freshwater ecosystems
| Type of IE: | MIE | Algeria | EA |  | Climate Change Mitigation | 3 | 3 | MU | BD-SP3-PA Networks | 3: Forest ecosystems
| Country(ies): | Argentina | Angola |  |  | International Waters | 5 | 5 | Good | BD-SP5-Markets | 13: Conservation and Sustainable Use of Biological Diversity Important to Agriculture
Relevant Geographic Points (i.e. cities, villages, bodies of water): |  | Patagones, Villarino, Puan counties - Buenos Aires Province - Argentina | Argentina |  |  | Multiple Focal Area |  |  |  | BD-SP7-Invasive Alien Species(IAS) | 6: Promoting the adoption of renewable energy by removing barriers and reducing implementation costs
[8 empty] | CC-SP2- Industrial EE | 8: Waterbody based operational program
| Project Milestones | [6 empty] | CC-SP3-RE,CC-SP4-Biomass | 9: Integrated Land and Water multiple focal area
| Milestone |  | Bahamas | [6 empty] | CC-SP5-Transport | 10: Contaminants based operational program
AFB Approval Date: |  | December, 14th, 2012 (WB Approval Date: September 20th, 2013. GoA's grant agreement countersignature date March 18th, 2014)
IE-AFB Agreement Signature Date: |  | February 25th, 2013, GoA's grant agreement countersignature date March 18th, 2014 | [6 empty] | CC-SP6-LULUCF | 12: Integrated Ecosystem Management
Start of Project/Programme: |  | June -2015 (Inception Workshop) | [6 empty] | Cross cutting capacity building | 14: Persistent Organic Pollutants
Mid-term Review Date (if planned): |  | 30-September-2016
| Terminal Evaluation Date: | 30-December-2018
|  | List documents/ reports/ brochures / articles that have been prepared about the project. | Cyprus
|  | Project Description Brochure / Brochure on Resilience and Sustainable Land Management for the intervention area/ Multi-proposal poster for local schools and capacity building agents, opinion leaders and farmers / Chapter on "Economics of Land Degradation and Improvement – A Global Assessment for Sustainable Development", edited by the Economics of Land Degradation Initiative of the UNCCD (http://link.springer.com/book/10.1007/978-3-319-19168-3/ 61 media-articles) | Czech Republic
List the Website address (URL) of project. |  |  | Democratic People's Republic of Korea
Democratic Republic of the Congo
Denmark
| Project contacts: |  | Djibouti
National Project Manager/Coordinator |  |  | Dominica
| Name: | Octavio Perez Pardo | Dominican Republic
| Email: | oppardo@ambiente.gob.ar | Ecuador
| Date: |  | Egypt
| Government DA |  | El Salvador
| Name: | Dolores Duverges | Equatoral Guinea
| Email: | dduverges@ambiente.gob.ar | Eritrea
| Date: |  | Estonia
| Implementing Entity |  | Ethiopia
| Name: | Ruth Tiffer-Sotomayor | Fiji
| Email: | rtiffersotomayor@worldbank.org | Finland
| Date: | 2016-07-20 | France
| Executing Agency |  | Gambia
| Name: | Joaquin Etorena | Georgia
| Email: | jetorena@ambiente.gob.ar | Germany
| Date: |  | Ghana
| Executing Agency |  | Greece
| Name: |  | Grenada
| Email: |  | Guatemala
| Date: |  | Guinea
| Executing Agency |  | Guinea Bissau
| Name: |  | Guyana
| Email: |  | Haiti
| Date: |  | Honduras
Hungary
Iceland
India
Indonesia
Iran (Islamic Republic of)
Iraq
Ireland
Israel
Italy
Jamaica
Japan
Jordan
Kazakhstan
Kenya
Kiribati
Kuwait
Kyrgyzstan
Lao People’s Democratic Republic
Latvia
Lebanon
Lesotho
Liberia
Libyan Arab Jamahiriya
Liechtenstein
Lithuania
Luxembourg
Madagascar
Malawi
Malaysia
Maldives
Mali
Malta
Marshall Islands
Mauritania
Mauritius
Mexico
Micronesia, Federated States of
Monaco
Mongolia
Montenegro
Morocco
Mozambique
Myanmar
Namibia
Nauru
Nepal
Netherlands
New Zealand
Nicaragua
Niger
Nigeria
Norway
Oman
Pakistan
Palau
Panama
Papua New Guinea
Paraguay
Peru
Philippines
Poland
Portugal
Qatar
Republic of Korea
Republic of Moldova
Romania
Russian Federation
Rwanda
Saint Kitts and Nevis
Saint Lucia
Saint Vincent and the Grenadines
Samoa
San Marino
Sao Tome and Principe
Saudi Arabia
Senegal
Serbia
Seychelles
Sierra Leone
Singapore
Slovakia
Slovenia
Solomon Islands
Somalia
South Africa
Spain
Sri Lanka
Sudan
Suriname
Swaziland
Sweden
Switzerland
Syrian Arab Republic
Tajikistan
Thailand
The former Yugoslav Republic of Macedonia
Timor-Leste
Togo
Tonga
Trinidad and Tobago
Tunisia
Turkey
Turkmenistan
Tuvalu
Uganda
Ukraine
United Arab Emirates
United Kingdom of Great Britain and Northern Ireland
United Republic of Tanzania
United States of America
Uruguay
Uzbekistan
Vanuatu
Venezuela, Bolivarian Republic of
Viet Nam
Yemen
Zambia
Zimbabwe

## FinancialData
Financial information: cumulative from project start to 11 june 2016
DISBURSEMENT OF AF GRANT FUNDS
How much of the total AF grant as noted in Project Document plus any project preparation grant has been spent to date?
Estimated cumulative total disbursement as of June 2016 |  | 500000
Add any comments on AF Grant Funds. (word limit=200) |  | 376,654.48 USD were spent 296,496.18 USD were documented to WB
EXPENDITURE DATA
List ouput and corresponding amount spent for the current reporting period |  | ITEM / ACTIVITY / ACTION | AMOUNT
|  | COMPONENT 1.1 Outcome: Institutional and community level response and prevention capacities developed to reduce land degradation and desertification and local vulnerabilities of the agricultural sector to climate variability and change | 17174.06
Output 1.1.1: Institutional capacity building program directed at local public officers
|  | Training - "Sustainable and Resilient Municipalities" - Montevideo - AECID | 14057.06
Output 1.1.2: Information and Early-Warning System (IEWS) on Climate Change and Desertification developed and run through inter-institutional cooperation
|  | Training "Evapotranspiration Mapping for Water Security" NASA - WB | 3117
|  | COMPONENT 1.2 Promoting Climate-smart Socio-cultural Approaches to Land Management | 25379.83
Output 1.2.1: Training program for key local stakeholders, including specifically opinion leaders
|  | Meetings and training for farmers and stakeholders in Medanos 09/2015 | 25379.83
|  | COMPONENT 2 Concrete adaptation measures to improve climate resilience and sustainability of productive agroecosystems defined and selected based on participatory processes and piloted by local farmers in cooperation with partner organizations | 129461.41
Output 2.1: Program of interventions in Geographical Intervention Areas (GIAs), predefined on a participatory basis according to biophysical, economic and social criteria, offering a menu of options related to the management of water resources, crops, cattle and grazing lands
|  | Salaries and expenses for Local Consultant on Implementation Adaptation Practices in agroecosystems | 23126.73
|  | Salaries for consultant on Sistematization of Climate Change and Agroecosystems in Southwest BA | 11119.2
|  | Agroforestry Products for "Vivero Puan, Vivero Villarino, Plan Forrajero Patagones" sites | 58118.13
|  | Gardening Tools for "Vivero Puan , Vivero Villarino" sites | 13456.72
|  | Training for local producers | 20525.79
|  | Expenses | 3114.84
|  | COMPONENT 3 Enhanced local knowledge and capacity for adaptation and response, developed in a participatory manner | 25888.26
Output 3.1: Combined consultation, coordination, training, and knowledge sharing at the local level in the three counties of direct Project intervention to develop and validate intervention proposals and work plans
|  | Meetings in Patagones - Participative planning (06/2015) | 23535.58
Output 3.2: Capacity building for indicator development and measurement plans, systems of continuous improvement, training for local application groups, and mutual knowledge sharing in terms of the proposed activities between and beyond the counties
|  | Exchange of Experiencies with China (MOU China) - Monitoring practices to address Climate Change | 2352.68
|  | COMPONENT 4 Improved local, provincial and national level technical and institutional capacity to sustain, scale up and replicate the Project outcomes | 51267.59
Output 4.1.1: Creation of a policy framework taking into account regulatory requirements and resources needed to continue the Project’s main activities, and a commitment to disseminate the experiences and lessons learned
|  | Salaries for consultant on Capacity Building in Monitoring and Sustainability | 35533.92
|  | Salaries for consultant on Climate Change scenarios in the BA Province Southwest | 5128.08
|  | Salaries for consultant to Design Project Logo and Materials | 7929.06
|  | Expenses | 2676.53
|  | PROJECT IMPLEMENTATION UNIT | 127483.33
|  | PIU Office computers and furniture | 24304.73
|  | Prints - Communication material | 5472.2
|  | PIU members salaries and expenses | 84086.27
|  | Stationery Supplies | 4215.33
|  | Bank expenses | 2654.77
|  | General Expenses | 6750.03
|  | TOTAL | 376654.48
PLANNED EXPENDITURE SCHEDULE
List outputs planned and corresponding projected cost for the upcoming reporting period |  | ITEM / ACTIVITY / ACTION | PROJECTED COST | Est. Completion Date
|  | GOODS | 1088634.6667
| Component 1, Output 1.1.2 | Acquisition of Meteorological stations | 138000 | 2016-11-01
| Component 1, Output 1.1.2 | Acquisition of Particles collector | 16000 | 2016-11-01
| Component 1, Output 1.1.2 | Acquisition of Computer equipment | 32000 | 2016-10-01
| PIU | Acquisition of Mobile phones for PIU | 1050 | 2016-07-01
| Component 2, Output 2.1 | Acquisition of vehicles for field work | 90000 | 2016-09-01
| Component 2, Output 2.1 | Acquisition of agroforestry products for Implementation Sites | 95000 | 2016-09-01
| Component 2, Output 2.1 | Acquisition of minor tools for Implementation Sites | 10731.3333 | 2016-09-01
| Component 2, Output 2.1 | Acquisition of equipment for Implementation Sites | 93000 | 2016-09-01
| Component 2, Output 2.1 | Acquisition of laboratory supplies for Implementation Sites | 30000 | 2016-09-01
| Component 2, Output 2.1 | Acquisition of supplies for Implementation Sites | 1146.6667 | 2016-09-01
| Component 2, Output 2.1 | Acquisition of agroforestry products for Experiental Sites | 82333.3333 | 2016-10-01
| Component 2, Output 2.1 | Acquisition of minor tools for Experimental Sites | 55000 | 2016-09-01
| Component 2, Output 2.1 | Acquisition of equipment for Experimental Sites | 93000 | 2016-09-01
| Component 2, Output 2.1 | Acquisition of laboratory supplies for Experimental Sites | 1533.3333 | 2016-10-01
| Component 2, Output 2.1 | Acquisition of supplies for Experimental Sites | 50000 | 2016-10-01
| Component 2, Output 2.1 | Acquisition of equipment for local viveros | 56666.6667 | 2016-10-01
|  | NO CONSULTING SERVICES | 121586.6667
| Component 4, Output 4.1.1 | Provincial workshop on Climate Change and Resilience | 20000 | 2016-09-01
| Component 4, Output 4.1.1 | Publication of climate change adaptation measures for agroecosystems | 10000 | 2016-12-01
| Component 3, Output 3.2 | Presentation of the Project Monitoring Tools | 5000 | 2016-10-01
| PIU | Publication of calls for tenders and events | 23000 | 2016-12-01
| Component 4, Output 4.1.1 | Dissemination of the publication of climate change adaptation measures for agroecosystems | 10000 | 2016-12-01
| Component 2, Output 2.1 | Acquisition of services for Implementation Sites | 37933.3333 | 2016-09-01
| Component 2, Output 2.1 | Acquisition of services for Experimental Sites | 14453.3333 | 2016-10-01
| Component 2, Output 2.1 | Acquisition of services for local tree nurseries | 1200 | 2016-12-01
|  | CONSULTING SERVICES - FIRMS | 333000
| Component 4, Output 4.1.1 | Development of a Baseline for each Implementation Site | 92500 | 2016-12-01
| Component 1, Output 1.1.2 | Development of an Environmental Warning System Prototype | 80000 | 2017-03-01
| Component 3, Output 3.1 | Development of a Knowledge Management Strategy | 28000 | 2016-12-01
| Component 1, Output 1.1.3 | Training in LADA and WOCAT | 30000 | 2016-11-01
| Component 1, Output 1.1.3 | Specific studies for the Observatory on Land Degradation | 25000 | 2017-03-01
| Component 1, Output 1.2.2 | Developent of a platform for virtual training activities | 40000 | 2017-03-01
| Component 3, Output 3.1 | T raining of Farmers in Good Practices | 37500 | 2017-05-01
|  | CONSULTING SERVICES - INDIVIDUALS | 52000
| Component 2, Output 2.1 | Legal consultancy - Implementation Sites contracts | 7000 | 2016-10-01
| Component 4, Output 4.1.1 | Design of a Communication Strategy for the Project | 6000 | 2016-10-01
| Component1, Output 1.2.2 | Development of Contents for virtual training courses | 5000 | 2016-11-01
| Component 1, Output 1.1.2 | Develompent of rules for the operation of the EWS | 10000 | 2016-12-01
| Component 3, Output 3.1 | Good Practices Catalog | 6000 | 2016-11-01
| Component 1, Output | Public Budget specialist | 8000 | 2016-11-01
| Component 4, Output 4.1.1 | Development of articles on Climate Change and Resilience for local media | 10000 | 2016-12-01
|  | TOTAL | 1595221.3333
ACTUAL CO-FINANCING (If the MTR or TE have not been undertaken this reporting period, DO NOT report on actual co-financing.)
How much of the total co-financing as committed in the Project Document has actually been realized?
Estimated cumulative actual co-financing as verified during Mid-term Review (MTR) or Terminal Evaluation (TE).
Add any comments on actual co-financing in particular any issues related to the realization of in-kind, grant, credits, loans, equity, non-grant instruments and other types of co-financing. (word limit=200)

## Risk Assesment
RISK ASSESMENT
IDENTIFIED RISKS
List all Risks identified in project preparation phase and what steps are being taken to mitigate them
Identified Risk | Current Status | Steps Taken to Mitigate Risk
Stakeholder Risk: The number of involved stakeholders (national and provincial government agencies and municipal authorities, farmers and communities, scientific institutions, and NGOs) may difficult decision-making and slow down project implementation. Incentives/direct benefits at community level might prove insufficient to convince people to adopt behavioral changes and new ways of cooperation in order to achieve longer-term objectives especially outside the key intervention zones. | This Risk was rated High at the PPP and continues. | Indeed, the number of involved stakeholders, considering that this Project is fundamentally based on Participatory Planning Procedures in order to guarantee stakeholder ownership, poses a great challenge on timely execution. As the level of participation includes participatory management of activities, which is quite close to Community-Driven Development strategies, actions must be discussed, planned and carried out with stakeholders which are not usually trained with MIE - procedures, safeguards, legal procurement regulations, etc.; nor are they tipically framed for introducing environmental reasoning into productive matters. In order to cope with this challenges, the PIU implemented a system aimed at standardizing the planning procedures such as agreed Field-Site-Planning Forms including safeguards, indicators, planning schedules and procurement related information. Besides of facilitating the dialogue with the beneficiaries and local counterparts, this faciltated the analysis, exchange, correction and evaluation procedures of the PIU, the National Executing Agency and the MIE (World Bank). It is worth mentioning that this procedure also provided an important set of lessons learned that were systemized by the PIU and shared with the stakeholders through workshops on Project Planning, that contributes to local capacity development, which is expected to be a lasting result of the Project by itself (see Monitoring Arrangements of the Project Document).
Capacity: Financial Management and Procurement may prove challenging for the PIU and certain administrative processes may delay Project execution | This Risk was rated Low and proved to be Medium. | For the first months, the PIU managed to get support from areas of the Ministry of Agriculture which count on sound expertise with World-Bank procedures. Meanwhile, properly experienced financial management and procurement specialists were hired to strengthen the PIU.
Governance: Policy priorities across administrative levels (national, provincial, and municipal) could differ and/or change during Project implementation. Similarly, due to lack of synchronicity between political cycles and dynamics of ecosystem recovery, political counterparts may not prioritize Project-related cooperation. | This Risk was rated Moderate and may be revised into High in the future. | Humid conditions which have prevailed during the last three consecutive years, combined with a recent tax elimination on wheat production, negativelly affect political commitment to the overall long-term objective of the Project. Awareness-raising activities are currently being undertaken by the PIU jointly with local governments, in order to try to keep the momentum. Since the beggining of 2016, the PIU looked for a stronger articulation with the provincial and municipal institutions; particularly the Provincial Agency on Sustainable Development and the Agoindustry Ministry, to increase their involvement in the Project activities and their buy-in of its objectives.
Design: Changing climatic conditions could affect the success of particular adaptation measures to be piloted during Project implementation; climate change may take a different form than anticipated (more or less severe and different in specific aspects such as impact on rainfall totals, regularity, intensity, etc.) or occur more slowly than anticipated. The chosen adaptive practices may prove less effective than anticipated in reducing impacts of climate variability and change to farmers; farmers might not wish to adopt the chosen adaptive practices due to lack of inputs, financing, or TA. | This Risk was set Moderate and continues. This might be revised into High. | The El Niño Southern Oscillation is currently causing a humid cicle so the perception of risks and vulnerability that made key beneficiaries and stakeholder receptive to the Project Proposal is weakened. One strategy to overcome this situation was to support local public policies such as fodder production emergency plans, with the provision of subsidized seeds, in order to turn sustainable productive options more attractive to farmers. When designing Terms of Reference for studies to be undertaken on related issues, the PIU also emphazises on aspects of cost-benefit, as well as on the concept of opportunity-costs of inaction under the projected climate scenarios, which are both good ways to get across key messages to the farmers. In line with this, the PIU has agreed with the county governments (Municipalities) to have technical capacity building events at the mayor community fairs, so that awareness-raising is undertaken jointly. The focus on participory Project-Planning also proved to be an adecuate mean to mitigate this risk: stakeholders on the field make decisions and plan the Project activities jointly with the PIU, so the actions to be implemented are based on strong stakeholder-ownership. This approach, in turn, requires major investments in participatory planning, field visits and so forth, which may delay the implementation of field activities.
Social and Environmental: Moderate capacity for environmental and social management could negatively affect achievement of the PDO. The PIU has no previous experience on environmental and social management under the Bank safeguard policies. However, other divisions in the SAyDS have been implementing safeguard policies. | This Risk was set Low and continues. | A training for PIU staff was conducted by WB team on environmental and social management under the Bank safeguard policies. This led to the development of a checklist to be completed by the local partners and controlled by specialized staff of the PIU when consolidating Implementation Sites. Additionally, the PIU works together with World-Bank related Projects of the Ministry of Agriculture to prevent mistakesin this sense.
Delivery, Monitoring and Sustainability: In case the overall Project results would prove insufficient to create expected behavioral changes across different stakeholder groups, or the planned communication and dissemination efforts would not succeed, the Project may fail to promote expected replications and scale-up operations. | This Risk was set Medium and continues. | The very Project design establishes participatory planning processes which, although may delay effective project execution in the field at the beginning, tend to guarantee stakeholder commitment from the start. A monitoring process through indicators and local consulting workshops as well as local consultations are planned to monitor not only the impacts but also the processes. In this sense, risk is clearly mitigated. Nonetheless, initial assessments show that Intermediate Outcome Indicators might need to be re-formulated in order to monitor intermediate steps rather than milestones that can only be measured at project end, or which does not depend exclusively on project activities.
Staff turnover in the Project Implementing Unit. Local project counterparts could experience staff turnover that could delay project implementation. | This risk was not rated in WB - Document but can be now rated as High | This risk has effectively occured as PIU went through a restructuring of its authorities first (2014), then a period of general presidential elections (2015) and later, after the elections a restructuring from Secretariat to Ministry (2016). In the field, all authorities changed staff after the elections. The PIU managed, through sound field-work, institutional networking and timing of documents that did foster overall commitment (institutional cooperation agreements), to pas through this risks which can now be understood as left behind.
Lack of synchronicity between political and technical times. Due to the divergence between the political cycle and dynamics of ecosystem recovery, the political counterparts fail to prioritize cooperation in the project. | This risk was not rated in WB - Document but can be now rated as Medium. | Effectively, there were actions constrained by this risk: procurement processes are long and, although PIU made sound efforts in order to reduce excessive burocracy, some of the goods could be delivered when sewing- periods had past in 2016, due to the fact that these particular actions had to be re-agreed with the new authorities of the counties after elections. Having now incorporated proper two agricultural engineers to the PIU as institutional in-kind counterparts, these planning related risk could be reduced strongly.
Fluctuating exchange rate. Variations in the exchange rate could negatively impact project implementation in terms of interventions that require importing goods and services. | This risk was not rated in WB - Document but can be now rated as High. | In fact, this risk has a strong impact on procurement-processes that are the core of the projects execution: especially in the actual context, even prices of locally produced inputs (see mitigating measures in the Project Document) are oriented at a highly volatile exchange rate. In almost all bids, providers of agricultural goods fail to offer formally. Efforts to get valid offers are very demanding and in many cases imply extend processes. The PIU does solve this problem very well through inter- and intra-institutional networking, involving related procurement-departments of other Ministries and Programs, as well as the local stakeholders in order to amplify the map of possible providers.
Critical Risks Affecting Progress (Not identified at project design)
Identify Risks with a 50% or > likelihood of affecting progress of project
Identified Risk | Current Status | Steps Taken to Mitigate Risk
Policies - Changes in the National Government, at end of 2015, determined the elimination of formerly existing export taxes on wheat, making its production (one of the drivers of soil-erosion) more attractive for farmers than during the Project preparation phase, thus contributing to increased vulnerability in the face of climate variability. | 60% | The PIU is intending to articulate Project strategies with mayor county policies aimed at ecosystem recovery, such as the fodder production emergency plans and afforestation-plans which basically broaden the scale of land degradation reverting activities. First investents were made directly to foster the local fodder production emergency plans and to support the native trees production in local tree nurseries. The PIU also emphazises on aspects of cost-benefit, as well as on the concept of opportunity-costs of inaction under the projected climate scenarios, which are both good ways to get across key messages to the farmers. In line with this, the PIU has agreed with the county governments (Municipalities) to have technical capacity building events at the mayor community fairs, so that awareness-raising is undertaken jointly.
Recent cuts at the budgets of key local counterparts, such as the Universities and the National Institute for Agricultural Technology, are causing unexpected needs that affect the local counterpart's infrastructure (such as vehicles, fuel for machinery, salaries for technicians and others). That may weaken the local institutions as well as their possibilities to support activities already commited. | 70% | The PIU is undertaking efforts using it's strong potential for institutional networking in order to cope with these kind of challenges. For instance, it is currently promoting joint action with the Ministry of Agricultural Industry of the Buenos Aires Province so unexpected budget cuts can be compensated with allocation of resources from that side.
Risk Measures: Were there any risk mitigation measures employed during the current reporting period? If so, were risks reduced? If not, why were these risks not reduced?
Add any comments relevant to risk mitigation (word limit = 500)
Yes, there were, as mentioned in previous sections. For example, local authorities participated in a Trainning Programme in Montevideo, after which they were motivated and involved in Project Activities, and also were determined to participate in the joint signature of an Agreement for the creation of the Iberoamerican Sustainable Development and Resilient Local Governments Network. Actually, there were several working-meetings carried out with related national and Provincial Institutions were budget allocations for the next year were analyzed and Annual Operational Plans were exchanged and screened for possibilities of joint action. As a result the Provincial Environmental and Agricultural Institutions accepted the PIU's proposal to carry out a joint planninig workshop together with the heads of the involved counties which will be carried out 6 July 2016 and aims at building - up joint initiatives related to the Project.

## Rating
RATING ON IMPLEMENTATION PROGRESS
For rating definitions please see bottom of page.
| Progress on Key Milestones |  | Expected Progress |  | Progress to Date | Rating
Project Manager/Coordinator: | Project Inception Phase |  | Inception Workshop completed |  | Inmediately after the PIU was set up and operational (late March 2015), the Inception WS was conducted (in June and continued in August 2015) involving all local, provincial and national stakehoklders (approx. 150 participants). It included paralell sessions fore each project component, and workshops in order to come up with the first concrete results, recovering in that way some of the time lost during the first year after effectiveness: in the framework of the Inception Workshop, capacity development on Monitoring was conducted, as well as a field visit and consultative working meetings with key stakeholders. Media was strongly involved. The Inception Workshop was held in the intervention area, not at the capital city, so visibility in the field as well as engagement from potential beneficiaries could be fostered from the early stages. | HS
| Establishment of the PIU and Governance Structure |  | Governance Structure fully operational |  | Once the first disimbursement of grant proceeds was made, the PIU was established. From then on, it has been working at a satisfactory pace together with all expected key stakeholders and counterparts, and is also articulating to other related national and provincial institutions and their programs. Taking into account that the PIU became effective and operational in 2015, the pace of the execution is satisfactory, but considering the inicial delay in the setup of the operationality caused by the political context, we set this milestone as MS. | MS
| Execution of the Project activities according to the operational framework presented to the AF |  | Major indicators are progressing according to the operational framework |  | One year and two months after the effective accession from the PIU to the funds (late March, 2015), the participatory planning phase is being concluded involving all key stakeholders and counterparts: consultative processes and joint planning procedures are concluded or at an advanced progress level for all planned field sites. Actions in order to achieve ODPs are already beeing undertaken, such as agreements with other institutions, fostering of existing public policies aimed to guarantee the continuity beyond the expected project cycle, capacity development, dissemination and design of materials on basics of adaptation and lessons learned are being documented and shared and the field sites are being currently set up providing concrete instruments needed for the local activities that were agreed through a participatory process were beneficiaries were involved into managing proceedures. Arrangements in order to set up the Early Warning Systems are already in an advanced state. There is certain delay in the establishment of formal teacher courses due to the fact that complete change in Governemnet from National to local modified educational programs, but the PIU managed to design a proper teaching material which is currently being used in schools of the intervention area. Though actions on the field, such as massive seeding of gramines and trees or desalinization of irrigation systems are just at the beginning and are in some cases constrained by natural cycles, concrete activities are set in place after one year of effective execution. Key institutions participate actively in capacity building activities and the project visibility is strong due to the presence of the project in major county events and in the local media. | S
[5 empty] | Overall Rating | MS
Please Provide the Name and Contact information of person(s) reponsible for completeling the Rating section
| Name: | Joaquin Etorena
| Email: | jetorena@ambiente.gob.ar
Please justify your rating. Outline the positive and negative progress made by the project since it started. Provide specific recommendations for next steps. . (word limit=500)
The fact that the PIU is fully operative since one year and two month, and that the Project design is based on Participatory Planning in all fields with a multiciply of stakeholders, the pace of the advances must be qualified as satisfactory taking into account that all stakeholders could already be integrated in the Participatory Planning activities and many indicators already show advances that were expected for the second year of the Proyect cycle. Nonetheless, the inicial delay of the setup of the Governance of the Project affects the overall performance negatively when taking into account the formal date of the Project Effectiveness. As a consecuence, the PIU faces great challenges in keeping up with the expected results on a timely basis as some activities of the field sites are constrained by natural cycles. The PIU sees need for fostering the strategic aspects of the physical interventions as the provision of goods and services to farmers in the field must be more articulated to longer lasting institutional frameworks. There are efforts being undertaken in order to enhance the overall performance and field activities are currently being adjusted in cooperation with the projects beneficiaries. In parallel, special activities related to institutional networking are expected to boost overall performance: especially, the Project is articulating to public policies set in place by the county governments (local forrage banks and afforestation plans) as well as provincial key institutions (joint analysis of proper budget allocations, Annual Operational Plans), in order to activate positive synergies that will permit to enhance scale and scope of the current activities and support continuity beyond the project cycle.This vision is also shared by partner institutions that carry out an AF funded Project in Argentina (UCAR) and regulary share lessons learned with the PIU.
| Progress on Key Milestones |  | Expected Progress |  | Progress to Date | Rating
Implementing Agency | Progress towards achievement of Project Development Objective |  | The PDO is to reduce climate vulnerability of the agriculture sector in the Southwest of the Buenos Aires Province by increasing adaptive capacity of key local institutions and actors, and piloting climate resilient and sustainable land management measures. Specific outcome indicators and intermediate milestones have been set in Project's design, to measure progress towards achievement of PDO (please, see "Project Indicators" tab). |  | Participatory planning activities have been extensively conducted. However seldom concrete adaptation measures have been put in place in the field, so far. Out of the 4 targeted institutions that in FY16 were expected to reflect institution-specific adaptation needs in their budget allocations to increase their capacity to address climate-related challenges, between 1 and 3 have been reported to have achieved that objective (although no objective verification means have been provided). While the intermediate milestone for FY16 was an index value of 7 (in a 0-24 scale), no progress has been reported in terms or maintainance of improvement of conditions resulting from climate variability and change, on the productive agroecosystems located in the pilot sites (index value reported is the same as baseline). No progress has been reported in terms of generation and dissemination of relevant threat and hazard information to farmers and other stakeholders. | MU
| Disbursement |  | FY15-13%, FY16-51%, FY17-88%, FY18-100% |  | Project approval was more than two and half years ago and the cummulative disbursement of grant proceeds is 13%. Less than one third of resources projected to be disbursed during the first half of 2016 have been actually executed. | MU
| Overall Implementation Progress |  | As planned in approved Annual Operational Plans |  | The progress achieved in the implementation of the operational action plan proposed by the PIU for 2015 was limited. Out of the US$845,820 projected to be disbursed, according to such operational action plan, by December 2015 only US$158,114.72 (19%) had been executed and documented, most of which corresponds to the salaries of the PIU members, travels and meetings. At this moment current value of most of the results indicators is zero, or very close to the baseline. A number of workshops and meetings with local stakeholders, as well as workshops have been conducted in the Project area. Some of them are reflected in the results indicators matrix (mostly those related to communications and training), but most of them are only preparatory participatory activities for more substantive investments in the field, which are still rather delayed. | MU
[5 empty] | Overall Rating | MU
Please Provide the Name and Contact information of person(s) reponsible for completeling the Rating section
| Name: | Ruth Tiffer-Sotomayor (Senior Environmental Specialist, Task Team Leader)
| Email: | rtiffersotomayor@worldbank.org
| Progress on Key Milestones |  | Expected Progress |  | Progress to Date | Rating
Other
Overall Rating
Please Provide the Name and Contact information of person(s) reponsible for completeling the Rating section
Name:
Email:
| Please justify your rating and address the following points: 1. Indicate trends, both positive and negative, in achievement of outcomes as per the project indicators. 2. Detail critical risks that have affected progress. 3. Outline response to MTR undertaken this reporting period. 4. Outline action plan to address projects with a rating of HU, U or MU. Please keep your input to 1200 words |  | The trend of progress towards achievement of outcomes is modestly positive. Although some steps forward have made, the actual execution is very slow and, at its current rate, the risk of not achieving the expected results by the Project closing date is increasing. In addition to the risks assessed in the corresponding tab, it seems that in the case of this project, the political changes experienced by the Ministry of Environment and its project counterparts in the field have had a strong impact in project management, probably due to a combination of PIU's distraction from project implementation, coordination problems, and lack of close monitoring or proper strategic guidance from authorities. The arguably erratic "participatory planning" process led by the PIU, seems to have misled the project implementation towards a "christmas tree" like, rather oportunistic and disperse set of activities (mostly workshops and trainings), agreements and investments, which impacts and direct alignment with the Project objectives might be difficult to prove in the short term.The proposed action plan to re-enroute the Project towards its objectives involves a revision of its design during MTR (including the definition of the problems to be addressed by the Project, its theory of change, its intervention strategies, its planned activities and its progress and results indicators), eventually conducting a project restructuring to solve any identified issue, and the provision of support to the Ministry of Environment to set up a more systematic Project implementation monitoring mechanism.
Rating Definitions
|  |  | Highly Satisfactory (HS) | Project actions/activities planned for current reporting period are progressing on track or exceeding expectations to acheive all major outcomes/outputs for given reporting period, without major shortcomings. The project can be presented as “good practice”.
|  |  | Satisfactory (S) | Project actions/activities planned for current reporting period are progressing on track to achieve most of its major outcomes/outputs with only minor shortcomings.
|  |  | Marginally Satisfactory (MS) | Project actions/activities planned for current reporting period are progressing on track to achieve most major relevant outcomes/outputs, but with either significant shortcomings or modest overall relevance.
|  |  | Marginally Unsatisfactory (MU) | Project actions/activities planned for current reporting period are not progressing on track to achieve major outcomes/outputs with major shortcomings or is expected to achieve only some of its major outcomes/outputs.
|  |  | Unsatisfactory (U) | Project actions/activities planned for current reporting period are not progressing on track to achieve most of its major outcomes/outputs.
|  |  | Highly Unsatisfactory (U) | Project actions/activities planned for current reporting period are not on track and shows that it is failing to achieve, and is not expected to achieve, any of its outcomes/outputs.

## Project Indicators
PROJECT Indicators
Please provide all indicators being tracked for the project as outlined in the project document
Type of Indicator (indicators towards Objectives, Outcomes, etc…)
Type of Indicator | Indicator | Baseline | Progress since inception (11/06/2016) | Target for Project End (31/12/2018)
Outcome | Outcome 1 Targeted institutions that reflect institution-specific adaptation needs in their budget allocations to increase their capacity to address climate-related challenges (Number, Custom) | 0 | 3 | 10
Outcome | Outcome 2 Productive agroecosystems in the pilot sites maintained or improved to withstand conditions resulting from climate variability and change (Number, Custom) | 0 | 0 | 10
Outcome | Outcome 3 Relevant threat and hazard information generated and disseminated to farmers and other stakeholders on a timely basis (Yes/No, Custom) | NO | NO | YES
Output | Output 1: Targeted clients satisfied with agricultural services (percentage) (Percentage, Core) | 0% | 0% | 50%
| MALE (number) (Number, Core Supplement) | 0 | 0 | 176
| FEMALE (number) (Number, Core Supplement) | 0 | 0 | 44
Output | Output 2: Targeted clients- MALE (number) (Number, Core Supplement) | 0 | 0 | 352
| Targeted clients- FEMALE (number) (Number, Core Supplement) | 0 | 0 | 88
Output | Output 3: Targeted local public employees trained (Percentage, Custom) | 0% | 58.33% | 60%
| MALE (percentage of the total males+females) (Percentage, Custom Breakdown) | 0% | 50% | NS
| FEMALE (percentage of the total males+females) (Percentage, Custom Breakdown) | 0% | 8.33% | NS
Output | Output 4: IEWS developed/operational through inter-institutional cooperation (Yes/No, Custom) | N | N | Y
Output | Output 5: Active participation of at least the key institutions of the Observatory (Yes/No, Custom) | N | N | Y
Output | Output 6: Consulted people who report on modification(s) in their Project-related practices (Percentage, Custom) | 0% | 0% | 60%
| MALE (percentage of total: male+female) (Percentage, Custom Breakdown) | 0% | 0% | NS
| FEMALE (percentage of total: male+female) (Percentage, Custom Breakdown) | 0% | 0% | NS
Output | Output 7: Client days of training provided (number) (Number, Core) | 0 | 20 | 64
| FEMALE (number) (Number, Core Breakdown) | 0 | 19 | NS
Output | Output 8: Teacher training institutes within SWBA that cooperate with the Project and offer related training (Number, Custom) | 0 | 2 | 10
Output | Output 9: Cultural and socio-productive activities carried out in the Project zone jointly with the municipal governments (fairs, exhibitions, etc.) (Number, Custom) | 0 | 4 | 28
Output | Output 10: FEMALES participating in cultural and socio-productive activities carried out in the Project zone jointly with the municipal governments (fairs, exhibitions, etc.) (Number, Custom Breakdown) | 0 | 4 | NS
| MALES participating in cultural and socio-productive activities carried out in the Project zone jointly with the municipal governments (fairs, exhibitions, etc.) (Number, Custom Breakdown) | 0 | 4 | NS
Output | Output 11: Clients who have adopted an improved agr. technology promoted by the project (Number, Core) | 0 | 104 | 1400
| FEMALE (Number, Core Breakdown) | 0 | NS | 280
Output | Output 12: Adaptation/sustainable land management (SLM) technologies identified/verified through local participatory consultations under the Project framework that are demonstrated within the GIAs (Number, Custom) | 0 | 12 IDENTIFIED | 12
|  |  | 2 IMPLEMENTED | 9
Output | Output 13: Related articles/programs in the local media and political initiatives in the three municipal Councils of the directly targeted counties (Number, Custom) | 0 | 68 | 82
Output | Output 14: Related articles/programs in the local media in the three municipal Councils of the directly targeted counties (Number, Custom Breakdown) | 0 | 61 | 72
Output | Output 15: Related political initiatives in the three municipal Councils of the directly targeted counties (Number, Custom Breakdown) | 0 | 7 | 10
Output | Output 16: Workshops and other Knowledge Management events meet their targets in terms of participation of different stakeholder groups (Yes/No, Custom) | N | Y | Y
Output | Output 17: Targeted beneficiaries who have participated in related training and carry out their own means of M&E and continued improvement related to the measures they have adopted through participation in the P (Percentage, Custom) | 0% | 0% | 70%
| FEMALE (Percentage, Custom Breakdown) | 0% | 0% | 70%
Output | Output 18: Assumed institutional commitments for the continuity and sustainability of the Project results per sector and activity (Number, Custom) | 0 | 4 Local Governments | 1 per sector
Output | Output 19: Guidance material produced on critical pieces of policy framework, piloted adaptation practices, and potential sources of financing to support continued efforts to promote climate resiliency at differ (Yes/No, Custom) | N | Y | Y
NS = Not specified

## Lessons Learned
QUALITATIVE MEASURES and LESSONS LEARNED
Please complete the following section every reporting period
Implementation and Adaptive Management | Response
What implementation issues/lessons, either positive or negative, affected progress? | Having so many stakeholders made participatory Project-Planning a very long-lasting and complex process. This approach usually generates collateral benefits to the target groups, such as fostering organizational skills, etc. However, this important experience, may be invisible to project monitoring, or even be perceived as a delay in Project implementation, while it should be deemed an integral part of it. In line with this, it is considered that proper related Indicators should be designed to expose the progress in planification processes and the stakeholders buy-in. In line with this, the main lessons learned were that 1) to make participatory processes viable, and thus guarantee eligibility of the requested investments, it is useful to use standardarized pratices and documents, jointly designed with the stakeholders; and 2) the very participatory-planning should be conceptualized and sistematized as an integral process that is by itself an objective/indicator of the Project.
Were there any delays in implementation? If so, include any causes of delays. What measures have been taken to reduce delays? | EXTERNAL CAUSES: 1) Grant's proceeds first disimbursement was delayed due to changes in national authorities (under the same administration) which resulted in changes of internal procedures and designated representatives; as well as the originally designed PIU structure; 2) local and presidential election campaigns started in the intervention area and nationwide. This again was a strong constraint because political leadership and commitment to the Project had to be established (and re-established, after the elections led to a change in administration) in a context of severe uncertainty. INTERNAL CAUSES: 3) the skills and experience necessary to run an operation under World Bank policies had to be obtained by the PIU (the Soils Conservation Directorate, at the Ministry of Environment) through hiring external consultants, a lot of handholding from the World Bank, and a steep learning curve for the PIU, 4) the procurement processes suffered delays, until experienced staff was incorporated to the PIU.
Describe any changes undertaken to improve results on the ground or any changes made to project outputs (i.e. changes to project design) | No changes have been made to project design, although they will be probably addressed during MTR. The PIU is intending to reduce complexity and spread of Project investments by articulating them with mayor county-policies related to ecosystem-recovery, such as the fodder production and afforestation-plans; which seem to have the potential to broaden the scale and impact of the activities proposed by the Project, such as dunes fixation and wind-breaking through afforestation.
How have gender considerations been taken into consideration during the reporting period? What have been the lessons learned as a consequence of inclusion of such considerations on project performance or impacts? | Gender considerations cross-cut most Project activities. However, in the case of the farmers, it is clear that the Project deals mainly with elder male and often lone small scale producers, whose families live already in the villages nearby. For that reason the PIU has planned to foster family-related activities.
Please complete the following section at mid-term and project completion
Lessons for Adaptation | Response
Climate Resilience Measures
What have been the lessons learned, both positive and negative, in implementing climate adaptation measures that would be relevant to the design and implementation of future projects/programmes for enhanced resilience to climate change?
What is the potential for the climate resilience measures undertaken by the project/programme to be replicated and scaled up both within and outside the project area?
Concrete Adaptation Interventions
What have been the lessons learned, both positive and negative, in implementing concrete adaptation interventions that would be relevant to the design and implementation of future projects/programmes implementing concrete adaptation interventions?
What is the potential for the concrete adaptation interventions undertaken by the project/programme to be replicated and scaled up both within and outside the project area?
Community/National Impact
What would you consider to be the most successful aspects for the target communities?
What measures are/have been put in place to ensure sustainability of the project/program results?
What measures are being/could have been put in place to improve project/program results?
Knowledge Management
How has existing information/data/knowledge been used to inform project development and implementation? What kinds of information/data/knowledge were used?
If learning objectives have been established, have they been met? Please describe.
Describe any difficulties there have been in accessing or retrieving existing information (data or knowledge) that is relevant to the project. Please provide suggestions for improving access to the relevant data.
Has the identification of learning objectives contributed to the outcomes of the project? In what ways have they contributed?

## Results Tracker
Results Tracker for Adaptation Fund (AF) Projects
Goal: Assist developing-country Parties to the Kyoto Protocol that are particularly vulnerable to the adverse effects of climate change in meeting the costs of concrete adaptation projects and programmes in order to implement climate-resilient measures. Impact: Increased resiliency at the community, national, and regional levels to climate variability and change.
Important: Please read the following guidance document (also posted on the Adaptation Fund website) before entering your data
Link: http://www.adaptation-fund.org/sites/default/files/Results%20Framework%20and%20Baseline%20Guidance%20final.pdf
Adaptation Fund Strategic Results Framework
Project ID | ARG/MIE/Rural/2011/1
Implementing Entity | WORLD BANK
Type of implementing entity | MIE
Country | Argentina
Region | Latin America and Caribbean
Sector | Agriculture
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Impact: Increased resiliency at the community, national, and regional levels to climate variability and change | Core Indicator: No. of beneficiaries |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project
|  | Total |  |  |  | Total |  |  |  | Total |  |  |  | Total
|  | % of female beneficiaries |  |  |  | % of female beneficiaries |  |  |  | % of female beneficiaries |  |  |  | % of female beneficiaries
|  | % of Youth beneficiaries |  |  |  | % of Youth beneficiaries |  |  |  | % of Youth beneficiaries |  |  |  | % of Youth beneficiaries
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 1: Reduced exposure to climate-related hazards and threats | Indicator 1: Relevant threat and hazard information generated and disseminated to stakeholders on a timely basis | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness
|  | Total | 440 | Drought | 1: Ineffective | Total | 220 | Drought | 4: Effective | Total |  |  |  | Total
|  | % of female targeted | 20% |  |  | % of female targeted | 20% |  |  | % of female targeted |  |  |  | % of female targeted
Output 1.1 Risk and vulnerability assessments conducted and updated | Indicator 1.1: No. of projects/programmes that conduct and update risk and vulnerability assessments | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
Output 1.2 Targeted population groups covered by adequate risk reduction systems | Core Indicator 1.2: No. of Early Warning Systems | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard | Drought | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  | 0 |  | Geographical coverage |  | 1 | 2: Monitoring and warning service | Geographical coverage | Local |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities |  |  |  | Number of municipalities | 3 |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 2: Strengthened institutional capacity to reduce risks associated with climate-induced socioeconomic and environmental losses | Indicator 2: Capacity of staff to respond to, and mitigate impacts of, climate-related events from targeted institutions increased | Number of staff targeted |  | Sector | Capacity level | Number of staff targeted |  | Sector | Capacity level | Number of staff targeted |  | Sector | Capacity level | Number of staff targeted |  | Sector | Capacity level
|  | Total |  |  |  | Total |  |  |  | Total |  |  |  | Total
|  | % of female targeted |  |  |  | % of female targeted |  |  |  | % of female targeted |  |  |  | % of female targeted
Output 2.1 Strengthened capacity of national and sub-national centres and networks to respond rapidly to extreme weather events | Indicator 2.1.1: No. of staff trained to respond to, and mitigate impacts of, climate-related events | Total staff trained | % of female staff trained | Type |  | Total staff trained | % of female staff trained | Type |  | Total staff trained | % of female staff trained | Type |  | Total staff trained | % of female staff trained | Type
|  | 0 | 0% | Public |  | 7 | 8% | Public
| Indicator 2.1.2: No. of targeted institutions with increased capacity to minimize exposure to climate variability risks | Type | Scale | Sector | Capacity level | Type | Scale | Sector | Capacity level | Type | Scale | Sector | Capacity level | Type | Scale | Sector | Capacity level
|  | Public | Local | Agriculture | 2: Low capacity | Public | Local | Agriculture | 3: Medium capacity
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 3: Strengthened awareness and owernship of adaptation and climate risk reduction processes | Indicator 3.1: Increase in application of appropriate adaptation responses | Percentage of targeted population applying adaptation measures |  | Sector |  | Percentage of targeted population applying adaptation measures |  | Sector |  | Percentage of targeted population applying adaptation measures |  | Sector |  | Percentage of targeted population applying adaptation measures |  | Sector
Output 3: Targeted population groups participating in adaptation and risk reduction awareness activities | Indicator 3.1.1: Percentage of targeted population awareness of predicted adverse impacts of climate change, and of appropriate responses | No. of targeted beneficiaries | % of female participants targeted | Level of awareness |  | No. of targeted beneficiaries | % of female participants targeted | Level of awareness |  | No. of targeted beneficiaries | % of female participants targeted | Level of awareness |  | No. of targeted beneficiaries | % of female participants targeted | Level of awareness
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Target performance at completion
Outcome 4: Increased adaptive capacity within relevant development sector services and infrastructure assets | Indicator 4.1: Increased responsiveness of development sector services to evolving needs from changing and variable climate | Project/programme sector | Geographical scale | Response level |  | Project/programme sector | Geographical scale | Response level |  | Project/programme sector | Geographical scale | Response level |  | Project/programme sector | Geographical scale | Response level
| Core Indicator 4.2: Assets produced, developed, improved or strengthened | Sector | Targeted asset | Changes in asset (quantitative or qualitative) |  | Sector | Targeted asset | Changes in asset (quantitative or qualitative) |  | Sector | Targeted asset | Changes in asset (quantitative or qualitative) |  | Sector | Targeted asset | Changes in asset (quantitative or qualitative)
Output 4: Vulnerable development sector services and infrastructure assets strengthened in response to climate change impacts, including variability | Indicator 4.1.1: No. and type of development sector services to respond to new conditions resulting from climate variability and change | Number of services | Type |  | Sector | Number of services | Type |  | Sector | Number of services | Type |  | Sector | Number of services | Type |  | Sector
|  | Baseline information |  |  |  | Baseline information |  |  |  | Performance at mid-term |  |  |  | Target performance at completion
Outcome 5: Increased ecosystem resilience in response to climate change and variability-induced stress | Indicator 5: Ecosystem services and natural resource assets maintained or improved under climate change and variability-induced stress | Natural resource improvement level |  | Sector | Type | Natural resource improvement level |  | Sector | Type | Natural resource improvement level |  | Sector | Type | Natural resource improvement level |  | Sector | Type
|  | 1: Ineffective |  | Agriculture | land | 4: Effective |  | Agriculture | land
Output 5: Vulnerable ecosystem services and natural resource assets strengthned in response to climate change impacts, including variability | Core Indicator 5.1: Natural Assets protected or rehabilitated | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Baseline information |  |  |  | Targeted performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 6: Diversified and strengthened livelihoods and sources of income for vulnerable people in targeted areas | Indicator 6.1: Increase in households and communities having more secure access to livelihood assets | No. of targeted households | % of female headed households | Improvement level |  | No. of targeted households | % of female headed households | Improvement level |  | No. of targeted households | % of female headed households | Improvement level |  | No. of targeted households | % of female headed households | Improvement level
| Indicator 6.2: Increase in targeted population's sustained climate-resilient alternative livelihoods | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
|  | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
|  | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
|  | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
Output 6 Targeted individual and community livelihood strategies strengthened in relation to climate change impacts, including variability | Indicator 6.1.1: No. and type of adaptation assets created or strengthened in support of individual or community livelihood strategies | Number of Assets | Type of Assets | Sector | Adaptation strategy | Number of Assets | Type of Assets | Sector | Adaptation strategy | Number of Assets | Type of Assets | Sector | Adaptation strategy | Number of Assets | Type of Assets | Sector | Adaptation strategy
| Core Indicator 6.1.2: Increased income, or avoided decrease in income | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 7: Improved policies and regulations that promote and enforce resilience measures | Indicator 7: Climate change priorities are integrated into national development strategy | Integration level |  |  |  | Integration level |  |  |  | Integration level |  |  |  | Integration level
Output 7:Improved integration of climate-resilience strategies into country development plans | Indicator 7.1: No. of policies introduced or adjusted to address climate change risks | No. of Policies introduced or adjusted | Sector | Scale | Type | No. of Policies introduced or adjusted | Sector | Scale | Type | No. of Policies introduced or adjusted | Sector | Scale | Type | No. of Policies introduced or adjusted | Sector | Scale | Type
|  | 0 | Agriculture | Local | Public policy | 1 | Agriculture | Local | Public policy
| Indicator 7.2: No. of targeted development strategies with incorporated climate change priorities enforced | No. of Development strategies | Regulation |  | Effectiveness | No. of Development strategies | Regulation |  | Effectiveness | No. of Development strategies | Regulation |  | Effectiveness | No. of Development strategies | Regulation |  | Effectiveness
Glacier lake outburst flood
|  | Inland flooding | fr | biological assets |  | Company policy | 5: Fully enforced (All elements implemented)
|  | Salinization | Decrease | land |  | Communication & Information policy | 4: Enforced (Most elements implemented)
|  | Drought | Same | water areas |  | Defense policy | 3: Partially enforced (Some elements implemented)
|  | Wind |  | subsoil assets | increased adpative capacity | Domestic policy | 2: Partially not enforced (Most elements not implemented) |  | Agribusiness
|  | Coastal flooding |  | air | achieved | Economic policy | 1: Not enforced (No elements implemented) |  | Agricultural-related | Financial capital
|  | Storm surge | Please choose |  | enhanced level of protection | Education policy |  |  | Agriculture | Human capital
|  | Hurricane | Selected | [5 empty] | Aquaculture | Physical capital
|  |  | Not relevant |  |  | 5: All (Fully integrated) |  |  | Construction/repairing business | Social capital
[6 empty] | 4: Most |  |  | Cultivation | Natural capital
[6 empty] | 3: Some |  |  | Fishing | Personal capital
Select | 5: All | Select |  |  | Community | 2: Most not integrated |  | Other | Forestry | Adaptation strategies
1 | 4: Almost all | Private | Type | Yes | Multi-community | 1: None |  | Agriculture | Handicrafts
2 | 3: Half | Public | Scale | No | Departmental |  |  | Coastal management | Livestock production
3 | 2: Some | NGO | Sector |  | National |  |  | Disaster risk reduction | Manufacturing
4 | 1: None |  |  |  |  | 5: Very high improvement | Established | Food security | other
|  | National |  |  |  | 4: High improvement | Maintained | Health | Services
|  | Regional |  |  |  | 3: Moderate improvement | Improved | Urban development | Tourism-related
|  | Local |  |  |  | 2: Limited improvement |  | Water management | Trading
[6 empty] | 1: No improvement |  | Multi-sector
|  | 1 -generated information is irrelevant, and neither the stakeholders reached nor the timeframe managed were achieved | 1: No info transferred on time | 4: High capacity | 5: Fully aware | 5: Highly responsive (All defined elements ) | 5: Fully improved | Roads | 5: Very effective
Asia-Pacific | NIE | 2 -the existence of some challenge in any of the three aspects of the indicator (generation of dissemination, stakeholders reached or timeframe managed) | 2: Somewhat info transferred | 3: Medium capacity | 4: Mostly aware | 4: Mostly responsive (Most defined elements) | 4: Mostly Improved | Gov Buildings | 4: Effective
Latin America and Caribbean | RIE | 3 -relevant information is generated and disseminated to all identified stakeholders on timely basis | 3: Info transferred on time | 2: Low capacity | 3: Partially aware | 3: Moderately responsive (Some defined elements) | 3: Moderately improved | Causeways | 3: Moderately effective
Africa | MIE |  |  | 1: No capacity | 2: Partially not aware | 2: Partially responsive (Lacks most elements) | 2: Somewhat improved | Airports | 2: Partially effective
Eastern Europe |  |  |  |  | 1: Aware of neither | 1: Non responsive (Lacks all elements ) | 1: Not improved | Schools | 1: Ineffective
| ha protected | [6 empty] | Training Centres
| ha rehabilitated | [5 empty] | Monitoring/Forecasting capacity | Hospitals
Afghanistan, Islamic Rep. of | km protected | [5 empty] | Policy/regulatory reform | Drinking water systems
Angola | km rehabilitated | 1: Risk knowledge | 1: No plans conducted or updated |  |  |  | Capacity development | Other
Albania |  | 2: Monitoring and warning service | 2: Undertaking or updating of assessments in progress |  |  | Communication & Information policy | Sustainable forest management
Argentina |  | 3: Dissemination and communication | 3: Risk and vulnterability assessments completed or updated |  |  | Domestic policy | Strengthening infrastructure | 1: Health and Social Infrastructure (developed/improved)
Armenia | Forests | 4: Response capability |  |  |  | Economic policy | Supporting livelihoods | 2: Physical asset (produced/improved/strenghtened)
Antigua and Barbuda | Mangroves |  |  |  |  | Education policy | Mangrove reforestation
Azerbaijan | Coasts |  | From 0 to 0.5% |  |  | Energy policy | Coastal drainage and infrastructure
Burundi | Rangelands |  | From 0.5 to 1% |  |  | Environmental policy | Irrigation system
Benin | Cultivated land/Agricultural land |  | From 1% to 5% |  |  | Foreign policy | Community-based adaptation
Burkina Faso | Catchment area/Watershed/Aquifer |  | From 5% to 10% |  |  | Health policy | Erosion control
Bangladesh | Protected areas/National parks |  | From 10% to 20% |  |  | Housing policy | Soil water conservation
Bulgaria | Other |  | From 20% to 30% |  |  | Human resource policies | Microfinance
Bahrain |  |  | From 30% to 40% |  |  | Information policy | Special Program for women
Bahamas, The |  |  | From 40% to 50% |  |  | Macroeconomic policy | Livelihoods
Bosnia and Herzegovina |  |  | Above 50% |  |  | Monetary policy | Water storage
Belarus | [5 empty] | Population policy | ICT and information dissemination
Belize | [5 empty] | Private policy
Bolivia | [5 empty] | Public policy
Brazil | [5 empty] | Science policy
Barbados | [5 empty] | Social policy
Bhutan |  | 3- relevant information is generated and disseminated to all identified stakeholders on timely basis |  |  |  | Transportation policy
Botswana |  | describe |  |  |  | Urban policy
Central African Republic |  | 2- the existence of some challenge in any of the three aspects of the indicator |  |  |  | Water policy
Chile |  | describe |  |  |  | Other policy
China, People's Republic of |  | 1- generated information is irrelevant and neither the stakeholders reached nor the timeframe managed were achieved
Cote d'Ivoire |  | describe
Cameroon
Congo, Dem. Rep. of
Congo, Republic of
Cook Islands
Colombia
Comoros
Cape Verde
Costa Rica
Cuba
Czech Republic
Djibouti
Dominica
Dominican Republic
Algeria
Ecuador
Egypt
Eritrea
Estonia
Ethiopia
Fiji
Micronesia, Fed. States of
Gabon
Georgia
Ghana
Guinea
Gambia, The
Guinea-Bissau
Equatorial Guinea
Grenada
Guatemala
Guyana
Honduras
Croatia
Haiti
Hungary
Indonesia
India
Iran, Islamic Republic of
Jamaica
Jordan
Kazakhstan
Kenya
Kyrgyz Republic
Cambodia
Kiribati
Saint Kitts and Nevis
Korea, Republic of
Lao People's Democratic Republic
Lebanon
Liberia
Libya
Saint Lucia
Sri Lanka
Lesotho
Lithuania
Latvia
Morocco
Moldova
Madagascar
Maldives
Mexico
Marshall Islands
Macedonia, former Yugoslav Republic of
Mali
Malta
Myanmar
Montenegro
Mongolia
Mozambique
Mauritania
Mauritius
Malawi
Malaysia
Namibia
Niger
Nigeria
Nicaragua
Niue
Nepal
Nauru
Oman
Pakistan
Panama
Peru
Philippines
Palau
Papua New Guinea
Poland
Korea, Dem. People's Rep. of
Paraguay
Romania
Russian Federation
Rwanda
Saudi Arabia
Sudan
Senegal
Solomon Islands
Sierra Leone
El Salvador
San Marino
Serbia
Sao Tome and Principe
Suriname
Slovak Republic
Slovenia
Swaziland
Seychelles
Syrian Arab Republic
Chad
Togo
Thailand
Tajikistan
Turkmenistan
Tonga
Trinidad and Tobago
Tunisia
Turkey
Tuvalu
Tanzania
Uganda
Ukraine
Uruguay
Uzbekistan
Saint Vincent and the Grenadines
Venezuela
Vietnam
Vanuatu
Samoa
Yemen, Republic of
South Africa
Zambia
Zimbabwe
Timor-Leste

## Units for Indicators
Fund Outcome Indicator Units
1. Generation of relevant data, Stakeholders, and Timeliness 2.1. Include both qualitative and quantitative measures of capacity level within targeted institutions 2.2. Number (men and women and other vulnerable groups) 3.1. Use scale from 1 to 5: 5: Fully aware 4: Mostly aware 3: Partially aware 2: Partially not aware 1: Aware of neither predicted adverse impacts of climate change nor of appropriate responses 3.2. Use scale from 1 to 5: 5: All 4: Almost all 3: Half 2: Some 1: None 4.1. Summarize in an overall scale (1-5): 5: Highly responsive (All defined elements ) 4: Mostly responsive (Most defined elements) 3: Moderately responsive (Some defined elements) 2: Partially responsive (Lacks most elements) 1: Non responsive (Lacks all elements ) 4.2. Summarize in an overall scale (1-5): 5: Fully improved 4: Mostly Improved 3: Moderately improved 2: Somewhat improved 1: Not improved 5. Depends on the targeted natural asset: Biological (species): measure through changes in population numbers (dynamics, structure, etc.) Land: measure changes in hectares. Baseline data will be necessary to estimate the change. Supporting indicators baseline and target (as well as contextual information) are needed such as the following: Farmers adopting recommended technologies, Ha. of land improved, Average deforestation rate Etc. Use scale from 1 to 5. 5: Very effective (All elements are present) 4: Effective (Most elements are present) 3: Moderately effective (Some elements are present) 2: Partially effective (Most elements are not present) 1: Ineffective (No elements are present) 6.1. Summarize in an overall scale (1-5): 5: Very high improvement 4: High improvement 3: Moderate improvement 2: Limited improvement 1: No improvement 6.2. Household income by source of livelihood in project area (USD) prior and post project intervention 7. Summarize in an overall scale (1-5). 5: All (Fully integrated) 4: Most 3: Some 2: Most not integrated 1: None
Fund Output Indicator Units
1.1. Number, sector(s) and level(s) of projects or interventions in separate fields of monitoring plan 1.2. Number 2.1.1. Number of staff (male/female) of targeted institutions: a. Obtain baseline information: total number of staff from targeted institutions b. Define target 2.1.2. Number of staff (male/female) of targeted institutions: a. Obtain baseline information: total number of staff from targeted institutions b. Define target: needs to be defined by project proponents 2.2.1. Quantitative: Percentage (includes women – and other vulnerable groups – and men). Qualitative: Adequacy: include direct analysis of major areas; adequacy/effectiveness of systems or analysis of perceptions of populations and institutions. 2.2.2. Number (broken down by gender and, if possible, by vulnerable groups defined in the area of intervention) of people 3.1. Number and type (in separate columns) at local level. 3.2. Number 4.1. Number and type 4. 2. Number and type (entered in separate columns) 5. Number of interventions by type of natural asset and intervention 6.1. Number and type (in separate columns of monitoring plan) 6.2. Income sources per household; description of income source and number of households. 7.1. Number/Sector 7.2. Number; Effectiveness (see previous indicator) through enforcement level.