## Overview
Project Performance Report (PPR)
| Period of Report (Dates) | September 2016 to August 2017
| Project Title: | Addressing Climate Change Impacts on Marginalized Agricultural Communities Living in the Mahaweli River Basin of Sri Lanka
| Project Summary: | This is a project against natural hazards. Two marginalized communities in two hazardous prone areas were the targeted project areas. Main objective of this project is to secure community livelihoods and food security against climate change-induced rainfall variability leading to longer droughts and more intense rainfall. The project has two components i) "Develop household food security and build resilient livelihoods for rain-fed farming households" and ii) "Build institutional capacity in village, local, regional service delivery to reduce risks associated with climate-induced rainfall variability". Project start date was 11-Aug-2014 and date of completion will be 28-Feb-2019 after the extension of the project period.
|  |  | Countries | Project Type: |  | GEF Focal Area: | GEF 4 Focal Areas | GEF 2 / 3 Operational Programme: | Overall Rating of the project in the evaluation by the project evaluator: | GEF-4 Focal Area Strategic Program: | GEF-3 Focal Area Strategic Program:
| Database Number: |  | Afghanistan | FP | Yes | Biodiversity | 1 | 1 | U | BD-SP1-PA Financing | 1: Arid & semi-arid ecosystems
Implementing Entity (IE) [name]: |  | United Nations Word Food Programme (WFP) | Albania | MSP | No | Climate Change Adaptation | 2 | 2 | S | BD-SP2-Marine PA | 2: Coastal, marine & freshwater ecosystems
| Type of IE: | Multilateral | Algeria | EA |  | Climate Change Mitigation | 3 | 3 | MU | BD-SP3-PA Networks | 3: Forest ecosystems
| Country(ies): | Sri Lanka | Angola |  |  | International Waters | 5 | 5 | Good | BD-SP5-Markets | 13: Conservation and Sustainable Use of Biological Diversity Important to Agriculture
Relevant Geographic Points (i.e. cities, villages, bodies of water): |  | Nuwara Eliya and Polonnaruwa Districts (Walapane, Medirigiriya and Lankapura Divisions ) | Argentina |  |  | Multiple Focal Area |  |  |  | BD-SP7-Invasive Alien Species(IAS) | 6: Promoting the adoption of renewable energy by removing barriers and reducing implementation costs
[8 empty] | CC-SP2- Industrial EE | 8: Water body based operational program
| Project Milestones | [6 empty] | CC-SP3-RE,CC-SP4-Biomass | 9: Integrated Land and Water multiple focal area
| Milestone |  | Bahamas | [6 empty] | CC-SP5-Transport | 10: Contaminants based operational program
AFB Approval Date:
14 -Dec-2012
IE-AFB Agreement Signature Date: |  | 2012-12-21 | [6 empty] | CC-SP6-LULUCF | 12: Integrated Ecosystem Management
Start of Project/Programme: |  | 2014-08-11 | [6 empty] | Cross cutting capacity building | 14: Persistent Organic Pollutants
Mid-term Review Date (if planned): |  | Q2 2018
| Terminal Evaluation Date: | 28 Feb 2019
|  | List documents/ reports/ brochures / articles that have been prepared about the project. | Cyprus
|  | Agreement signed by World Food Programme (WFP) and Government of Sri Lanka. Addendum to Agreement signed by WFP and Government of Sri Lanka. Inception workshop report. Standard Operating Procedures of the project signed by WFP and Government of Sri Lanka. Baseline survey report, Annual rapid evaluation report Project Extension Letter, Sri Lanka Next Program Bulletin, Joint action plan prepared for UNDP and Ministry by Ministry of Environment and UNDP. | Czech Republic
List the Website address (URL) of project. |  |  | Democratic People's Republic of Korea
|  | www.ccap.lk | Democratic Republic of the Congo
Denmark
| Project contacts: |  | Djibouti
National Project Manager |  |  | Dominica
| Name: |  | Dominican Republic
| Email: |  | Ecuador
| Date: |  | Egypt
| Government DA |  | El Salvador
| Name: | Mr. Anura Disanayake | Equatorial Guinea
| Email: | secretary@environmentmin.gov.lk | Eritrea
| Date: | 2017-11-03 | Estonia
| Implementing Entity |  | Ethiopia
| Name: | Mr. Hoang | Fiji
| Email: | nguyenduc.hoang@wfp.org | Finland
| Date: | 2017-09-01 | France
| Executing Agency |  | Gambia
| Name: | Mr.W.T.H. Ruchira Withana | Georgia
| Email: | hruchirawithana@yahoo.com | Germany
| Date: | 2017-09-01 | Ghana
| Executing Agency |  | Greece
| Name: | Ms.Visaka Punyawana Hidellage | Grenada
| Email: | visaka.hidellage@undp.org | Guatemala
| Date: | 2017-11-03 | Guinea
| Executing Agency |  | Guinea Bissau
| Name: |  | Guyana
| Email: |  | Haiti
| Date: |  | Honduras
Hungary
Iceland
India
Indonesia
Iran (Islamic Republic of)
Iraq
Ireland
Israel
Italy
Jamaica
Japan
Jordan
Kazakhstan
Kenya
Kiribati
Kuwait
Kyrgyzstan
Lao People’s Democratic Republic
Latvia
Lebanon
Lesotho
Liberia
Libyan Arab Jamahiriya
Liechtenstein
Lithuania
Luxembourg
Madagascar
Malawi
Malaysia
Maldives
Mali
Malta
Marshall Islands
Mauritania
Mauritius
Mexico
Micronesia, Federated States of
Monaco
Mongolia
Montenegro
Morocco
Mozambique
Myanmar
Namibia
Nauru
Nepal
Netherlands
New Zealand
Nicaragua
Niger
Nigeria
Norway
Oman
Pakistan
Palau
Panama
Papua New Guinea
Paraguay
Peru
Philippines
Poland
Portugal
Qatar
Republic of Korea
Republic of Moldova
Romania
Russian Federation
Rwanda
Saint Kitts and Nevis
Saint Lucia
Saint Vincent and the Grenadines
Samoa
San Marino
Sao Tome and Principe
Saudi Arabia
Senegal
Serbia
Seychelles
Sierra Leone
Singapore
Slovakia
Slovenia
Solomon Islands
Somalia
South Africa
Spain
Sri Lanka
Sudan
Suriname
Swaziland
Sweden
Switzerland
Syrian Arab Republic
Tajikistan
Thailand
The former Yugoslav Republic of Macedonia
Timor-Leste
Togo
Tonga
Trinidad and Tobago
Tunisia
Turkey
Turkmenistan
Tuvalu
Uganda
Ukraine
United Arab Emirates
United Kingdom of Great Britain and Northern Ireland
United Republic of Tanzania
United States of America
Uruguay
Uzbekistan
Vanuatu
Venezuela, Bolivarian Republic of
Viet Nam
Yemen
Zambia
Zimbabwe

## FinancialData
Financial information: cumulative from 1st September 2016 to 31st August 2017
DISBURSEMENT OF AF GRANT FUNDS
How much of the total AF grant as noted in Project Document plus any project preparation grant has been spent to date?
Estimated cumulative total disbursement as of [11th Aug 2015] |  | 2161364.67
Add any comments on AF Grant Funds. (word limit=200) | The annual reporting period is from 1st September 2016 to 31st August 2017. In this period, the project showed significant progress as compared to the previous year. Project implementation peaked from October 2016 to December 2016, and showed further acceleration despite previously slow progress due to administrative changes. Ministry portfolios and the newly assigned officials became familiar with the project and its objectives. Delays in fund disbursement and new implementation arrangements affected progress. The total expenditure for this annual reporting period is 1,490,823.67 $
INVESTMENT INCOME | 0 |  | Note: Calculated based on Rs.152
Amount of annual investment income generated from the Adaptation Fund’s grant
EXPENDITURE DATA
List output and corresponding amount spent for the current reporting period | ITEM / ACTIVITY / ACTION | AMOUNT in US $ | Amount in LKR
| 1.1 Develop home garden-based agro forestry systems in target DSDs to diversify livelihoods and build adaptive capacity of households to climate change | 270625.84 | 41135127.68
| 1.2 Introduce and promote drought-tolerant crop varieties and agronomic practices to counter effects of rainfall variability | 32158.28 | 4888058.56
| 1.3 Identify and promote climate-resilient alternative income sources such as livestock, perennial cash crops and inland fisheries | 58863.75 | 8947290
| 1.4 Promote improved post-harvest technologies as viable climate-resilient livelihood sources for women farmers | 3579.58 | 544096.16
| 1.5 Build community assets and livelihood resources through cash-for-work to support climate risk reduction measures. | 376765.9 | 57268416.8
| 2.1 Train and mobilize officers at village, division and provincial level | 2394.69 | 363992.88
| 2.2 Strengthen Farmer Organizations with information, training and equipment to implement adaptation strategies | 94042.22 | 14294417.44
| 2.3 Pilot integrated watershed management models in micro watersheds to safeguard climate-sensitive livelihood assets such as land and water | 474185.93 | 72076261.36
| 2.4 Risk Assessment and Adaptation Planning conducted with target communities | - | -
| 2.5 Document and disseminate lessons of climate- resilient livelihood development and watershed management approaches and best practices | 11434.63 | 1738063.76
| 2.6 Design and implement early warning systems for climate-induced risks of landslides and drought in Mahaweli Basin | 93392.7 | 14195690.4
| 3.Project Execution Cost | 73380.15 | 11153782.8
| TOTAL | 1490823.67 | 226605197.84
PLANNED EXPENDITURE SCHEDULE
List outputs planned and corresponding projected cost for the upcoming reporting period | ITEM / ACTIVITY / ACTION | PROJECTED COST in US $ | Est. Completion Date
| 1.1 Develop diversified home garden based agro forestry in target DSDs to build household adaptive capacity to climate change | 335985.8531 | 31.08.2018
| 1.2 Introduce and promote drought-tolerant crop varieties and agronomic practices to counter effects of rainfall variability | 172501.2268 | 31.08.2018
| 1.3 Identify and promote climate-resilient alternative income sources among rural farm household dependent on rain fed agriculture | 539144.0516 | 31.08.2018
| 1.4 Promote improved post-harvest technologies as viable climate-resilient livelihood sources for women farmers | 241601.591 | 31.08.2018
| 1.5 Build community assets and livelihood resources through cash-for-work to support climate risk reduction measures | 196646.173 | 31.08.2018
| 2.1 Train and mobilize officers at village, division and provincial level to design, and monitor local adaptation strategies | 174390.4708 | 31.08.2018
| 2.2 Strengthen farmer organizations with information, training and equipment to implement adaptation strategies | 111933.2579 | 31.08.2018
| 2.3 Pilot integrated watershed management models in micro watersheds to safeguard climate-sensitive livelihood assets such as land and water | 199303.0915 | 31.08.2018
| 2.4 Risk Assessment and Adaptation planning conducted with target communities | 90920.5916 | 31.08.2018
| 2.5 Document and disseminate lessons of climate resilient livelihood development and watershed management approaches and best practices | 65493.68 | 31.08.2018
| 2.6 Design and implement early warning systems for climate-induced risks of landslides and drought in Mahaweli Basin | 57291.73 | 31.08.2018
| Total Activity Cost | 2185211.7173
| Execution Cost | 960409.97
| TOTAL | 3145621.6873
ACTUAL CO-FINANCING (If the MTR or TE have not been undertaken this reporting period, DO NOT report on actual co-financing.)
How much of the total co-financing as committed in the Project Document has actually been realized? | N/A
Estimated cumulative actual co-financing as verified during Mid-term Review (MTR) or Terminal Evaluation (TE).
Add any comments on actual co-financing in particular any issues related to the realization of in-kind, grant, credits, loans, equity, non-grant instruments and other types of co-financing. (word limit=200) | N/A

## Risk Assesment
RISK ASSESMENT
IDENTIFIED RISKS
List all Risks identified in project preparation phase and what steps are being taken to mitigate them
Identified Risk | Current Status | Steps Taken to Mitigate Risk
Scientific & technical information in relation to climate change & its effects on the Basin remain incomplete and uncertain | Low | In addition the Project is planning to work with the Department of Meteorology to obtain climate projections, which will be downscaled to the project areas to provide technical clarity to the district and divisional level stakeholders on the climate risks and associated impacts. Early warning systems are being installed. Hazard maps were prepared for both flood and landslide-prone areas and also, arrangements were made to conduct water and soil tests in the concern area, and the results will be disseminated to the concerned parties.
Lack of awareness among participating communities and local officials on climate change (CC) and potential impacts | Medium | Trainings on awareness creation were conducted in the area of climate change impact on agriculture, water resources and soil condition. Planning sessions were conducted with the relevant stakeholders including local communities and local officials, where their awareness was further built on climate change and potential impacts
Local government in project implementation areas fails to prioritize climate change policies in their strategies and plans | Medium | Through conducting field level discussions, regular field visits and meetings, there is an increased awareness of climate change policy among the field level officers.
Policy makers and politicians prioritize economic benefits over sustainable and resilient ecosystems | Low | Importance of prioritizing the long term, sustainable and resilient ecosystems over short-term economic benefits is being highlighted in National Steering Committees and National Level Inter-Ministerial planning sessions. The lessons captured in the project and especially project impacts will be used to establish this argument further.
Additional development support for alternative livelihoods and crops is unavailable in the target DSD at the required time | Low | The Project has ensured that the annual work plan of the Project is in line with the divisional level annual work programmes of the respective DS divisions. This has enabled the Project to mobilize additional funds from respective government agencies to replicate the activities identified under the project in the targeted areas. For example, the Provincial Agriculture Department has promoted home gardens, use of organic fertilizer etc. in the Project area using government funds.
Critical Risks Affecting Progress (Not identified at project design)
Identify Risks with a 50% or > likelihood of affecting progress of project
Identified Risk | Current Status | Steps Taken to Mitigate Risk
Protracted delays in project implementation are expected due to recurrent administration changes at the government and project implementation management, leading to great bottleneck towards the end of the project life, and a likelihood of delay in project completion. | Medium | A project extension was sought from the Adaptation Fund to complete the remaining activities as per the Project Document, which was received until Feb 2019. During a special National Steering Committee Meeting, it was decided to obtain the technical support of UNDP to implement the remaining activities of the Project. A joint action plan has already been prepared to ensure a coordinated effort is made over the next one and half years to deliver the Project.
Low implementation capacity of the EE at both central and local levels. | High | The EE has planned to take prompt action in getting technical and procurement-related support also by incorporating UNDP to accelerate the execution of the project activities. The MIE discussed with the EE and requested it to invest more in human resources for project management at the central level and technical project staff at the project site level. Government has assured MIE of taking prompt action in this direction while requesting for further technical support from MIE.
Internal mechanism between government ministries for project activity planning, technical review, approval and implementation, is not simple and identified as a risk to delay project implementation. | High | The required staff will be hired for the relevant vacant positions in the project for the rapid implementation of the project activities. The MIE discussed with the EE and agreed that both should have qualified technical staff for the project in order to work with other government technical institutions to resolve technical issues and get project activities approved quickly. The Government has agreed to take prompt action but at the same time requests for further technical support for the MIE.
Risk Measures: Were there any risk mitigation measures employed during the current reporting period? If so, were risks reduced? If not, why were these risks not reduced?
Add any comments relevant to risk mitigation (word limit = 500)
Project progress has reached a favorable condition compared to the early phase. However, overall project execution is still far from reaching the project targets. The low implementation capacity at both central and project-site levels as well as the complex cross-ministerial and cross-institution mechanism for project activity planning, cost estimates, approval and implementation is still a major bottleneck to be addressed in order to get activities implemented. An extension in time was requested and the extension has been received for one and a half years (till February 2019), along with the services of UNDP who is also involved in other climate change adaptation-related projects.

## Rating
#DIV/0!
RATING ON IMPLEMENTATION PROGRESS
For rating definitions please see bottom of page.
| Progress on Key Milestones |  | Expected Progress |  | Progress to Date | Rating
Project Manager/Coordinator: | 1.1 Develop home garden-based agro forestry systems in target DSDs to diversify livelihoods and build adaptive capacity of households to climate change |  | Conduct a survey to identify the current food consumption and nutrition practices among the households in the targeted areas. Assessing water availability and soil conditions to determine the best suited home garden species. Developing a food consumption index. Conduct training on home garden planning, organic agriculture inputs and production of budded plants for all FOs (189) and targeted families. Provide drought tolerant high yielding seeds suitable for the relevant Agro-ecological zones (e.g. seed paddy), planting materials and equipment and tools. Providing 130 rain water harvesting tanks. Monitoring home gardening activities through FOs and village level implementation committees quarterly and provide financial assistance to carry out monitoring activities. Introducing tree species needed for agro-forestry. Conduct animal husbandry training at Pulasthigama. |  | Baseline house hold survey including Food Consumption Score and House Hold Dietary Diversity Score were conducted and the final report was submitted by the Institute to the EE and to date the final payment was made to the relevant Institute. Home gardening in the project areas are being uplifted with appropriate trainings, workshops and by the distribution of the crops, fruit plants, drought tolerant high yielding seeds, pepper, ginger and plants to the targeted farmer communities and purchase of lemon, Hana plant for bio fencing . 800 Bee boxes were distributed. Construction of 20 agro wells in Polonnaruwa . 200 rainwater harvesting tanks and trees for agro forestry were also distributed. 1023 planting materials such as long knives, 7500 mamoties and 4039 flat iron rods were distributed to the farmers in both the DS areas of the project. Nursery training programs, poverty alleviation program, meetings with relevant organizations like wild life department, 15 farmers were trained, distributed with a cattle per head and the partial financial aid for the construction of cattle sheds were also provided for them. After their successful implementation, distribution of cattle to another fifty farmers being planned and which is on process to date. Milk and vegetable collection centre in Walapane DS is also in line and recommended by the Divisional Secretary of the Walapane DS. A landslide risk assessment certificate was also received from the National Building Research Organization (NBRO) for the successful implementation of the construction of the above mentioned collection centre. | HS
| 1.2 Introduce and promote drought tolerant crop varieties and agronomic practices to counter effects of rainfall variability |  | With the active participation of field extension officers, FO leaders and technical experts, develop a series of field training programs for drought tolerant agriculture. Conduct field trials with selected farmers on the use of the crop species, mixed and inter cropping which are most suitable for the area and the season. Study the soil salinity and soil acidity in target areas and proposed remedial measures for those problems. Introduce agronomic practices useful to tolerate flood and drought conditions. Introducing intersessional cultivation. Direct farmers to make agreements for forward contracts with relevant entities and mediate such activities. Awareness on soil conservation methods. Preparation of lands and introduce irrigation methods to low land paddy fields and uplands which have been abandoned due to landslides. Distribution of traditional local seeds to farmers through FOs in order to conserve and promote traditional verities. Identify and promote the traditional crop protection mechanisms those could bring resilience to climate change. Promoting reforestation in lands which are subjected to or vulnerable to landslides. Popularize drought tolerance crops. | 53.5121 | A request has been made to Natural Resources Management Centre (NRMC), Dept. of Agriculture to study the soil salinity and soil acidity in target areas. A work plan will be developed with NRMC as they have informed us to make arrangements to collect field soil and water samples and delivered to their Centre. Awareness program on Soil Erosion and Conservation Methods and Landslides and Disaster Management was done. Farmers and the representatives of the FOs ( 91 members) and Govt. Officers/ Field Officers were participated. The major participatory institutions were Divisional Secretariat( Walapane), Medirigiriya and Lankapura, Agrarian Development Dept., Agriculture Dept., Wild Life Dept., Forest Dept., Disaster Management Centre, National Building Resources Organization, National Water Supply and Drainage Board, Meteorological Dept. . It has been recorded that there are 194 beneficiary FOs in Walapane and 69 in Medirigiriya and Lankapura . . Possibilities of popularizing drought tolerant and high yielding paddy varieties were investigated. Obtain the assistance from LUPPD to prepare 24 land use plan maps to decide upon the suitability of patches of land for cultivations, conservations, adopt soil conservation measures. | S
| 1.3 Identify and promote climate-resilient alternate income sources such as livestock, perennial cash crops and inland fisheries |  | Technical assessment of suitability of alternative livelihood which were selected by relevant national agencies and their national agencies and their regional counterparts based on their suitability to climate change. Train selected FO members on small business management including alternative income sources. Provide agricultural equipment necessary for the implementation of the market oriented proposals on alternative income sources prepared by the selected members of the FOs and approved by the village level implementing and monitoring committees. Prepare a suitable market for products such as mushroom, pepper, dehydrated agro-products and those based on Kithul. Making linkages among already existing projects. Conduct a survey to identify alternative income generation ventures. Introduce agro-based industries and give directives. |  | Continuation of inland fishery development activities in selected tanks in Maderigiriya collaboration with NAQDA. Introducing fingerlings to supplement the protein needs of the surrounding communities . This would facilitate introducing drought tolerant and high yielding varieties in seasonal tanks too. Discussions were made to facilitate networking of self employee women groups( 100 Nos) in Walapane DS , especially who obtained traing and benefited by raw material packages( mushroom, kithul producers, bee keepers etc.) and so on to create sustainable production market as well as to upgrade their products as per the quality demands. Possibilities of establishing microfinancing opportunities and training FOs on accounting procedure to plan their carrier development activities. Export agriculture crops (i.e. Pepper) were introduced as intercrops in home gardens which is considered as a commercial crop were done collaboration with Export Agriculture Dept. and Inter Provincial Agriculture Dept. | MS
| 1.4 Promote improved post-harvest technologies as viable climate-resilient livelihood sources for farm women |  | Strengthen the existing women based Self-Help Groups (WSG) and /or establishing new groups in selected villages. Provide equipment and relevant training on post harvest technology for the established women based Self-Help Groups. Introduce a strategy for selling their products. Create market for the products developed. Set up a market for products prepared by using post harvest technologies. Introduce new products using post harvest technology where appropriate according to market demand. Create self-employment opportunities by producing confectionery using traditional food items. | 24.3106 | Discussions had been held with relevant agencies (Dept. of Agriculture, Mahaweli Authority of Sri Lanka, National Institute of Cooperative Development, Dept. of Cooperative Development and Institute of Post Harvest Technology) in this regard and the Institute of Post Harvest Technology (IPHT) has expressed their willingness to conduct 13 training programs ( 05 and 08 programs for Walapane and Medirigiriya respectively. IPHT has prepared a concept paper on this and they have submitted budgets for the training programs. Equipment distribution to support self employee livelihood promotion activities have been planned and development of conceptual proposal with sustainability assessment s to be obtained | MS
| 1.5 Build community incentives/ Payment for Ecosystem Services for natural resources management to implement climate risk reduction measures. |  | Provide tools and equipment which are used for agricultural purposes and plants used for stabilizing river bank for those households who are participating in the above programs. Provide financial support to construct agro wells. Plan to minimize the damages caused by floods and provide incentives for the labour contribution for structural interventions in reducing floods. Strengthen the FOs in order to enhance the welfare and livelihood of farmers. Safeguard ground water table by protecting small tanks and anicuts. Promote drinking water projects and prohibit all unauthorised pipelines those are used to obtain water. Provide the facilities needed for conserving streamlets. Provide shoes (boots) for farmers who are farming at night to protect from animals and snakes (Medirigiriya). | 27.6924 | 23 village irrigation systems were rehabilitated during the year (19 in Medirigiriya / Lankapura DS Divisions and 4 in Walapane DS). Cash for work approach (2 programmes) was used in rehabilitating tanks and tank bunds as a measure to inject additional cash to local economy and drought affected households. The village irrigation systems were rehabilitated considering both flood and drought risks, introducing climate adaptive strategies. These systems will serve as rainwater storages in rainy season and to be distributed in the dry season. Agro wells were completed in Madirigiriya / Lankapura DS. Implementing 3 drinking water projects in water scare areas were their prevalence via community maintenance mechanisms are to be formulated in Walapane DS. Agric equipment ( mamoties-7500, long knives- 1023, flat iron bars - 4039) were distributed among farmer community members) | MS
| 2.1 Train and mobilize officers at village, division and provincial level to design, and monitor local adaptation strategies |  | Developing a training module for climate change impacts on agriculture and natural resources and climate proofing on rural development with government and FO. Preparation of training modules in identification of risk of climate change on agriculture and natural resource management and mitigating those effects through traditional and appropriate new farming practices and conducting those trainings at village level. Trainings of officers at provincial, divisional and village level those who already engaged in rural development on climate proofing of rural development and natural resource management intervention. Provision of equipment and tools (GIS software, localized hazard maps, vulnerability assessment tools) for selected 08 Agrarian Service centres. Preparation of hazard zonation maps of each GN division and place them at appropriate places. Provision of suitable technical equipment or tools for rural disaster management committees. Training of relevant officers along with six members from each FO and paying incentives for them. | 49.6517 | Based on the maps prepared proposals were called . 14 awareness programs have been conducted for about 1,000 farmers. (In January 2016 - 02 Programs, in February 2016 - 02 Programs, in March 2016 - 04 programs, in June 2016 - 01 Program, in July 2016 - 05 programs). Disaster Management Centre/ Walapane and National Building Research Organization has engaged in installing early warning system in landslide prone areas in Walapane DS | MS
| 2.2 Strengthen Farmer Organizations (FO) with information, training and equipment to implement adaptation strategies |  | Carry out a survey of registered and unregistered FOs in the area. Preparation of technically sound management plan adopting a participatory approach and improve the performance of all minor irrigation schemes. Conduct workshops to improve awareness on appropriate water management strategies for the area. Preparing disaster mitigation and prevention assessment. Practical training for the members of FOs on financial reporting and accounting. Providing equipment for FO office premises and village level Agriculture Research and Production Assistants. Assisting to construct 25 agro-wells. Providing necessary electrical equipment for Agrarian Services Centres for project activities. |  | Renovation of existing irrigation projects. These are Ambiguity Maha Ela, Siyambalakumbura Ela, Attalakumbura Ela, Yombuwelthenna Ela, Maa Ussawa Ela and Meegollawa tank. Water shed Management- Subodhagama, Workshop on Accounts training program. | MS
| 2.3 Pilot integrated watershed management models in micro watersheds to safeguard climate sensitive livelihood assets such as land and water |  | Survey and mapping of micro watershed including on farmland use and land degradation. Planning and implementation of community based watershed conservation, interventions through appropriate agencies and experts by providing financial benefits to the community to appropriate their contribution. Renovation of agricultural roads in the area, desilting of tanks and provide funds for routine maintenance activities. Identification and mapping of catchment boundaries of streams, natural drains and springs and delineate them as reserves. Minor repairs and maintenance work on identified irrigation structures within the micro catchment to improve water yield and dry season storage. Protection of water sources and springs including which have not been already used or protected. Provide ownership of the farming lands to farmers and provision of compensation to the community for lands in acquiring reservations after surveying. | 34.4253 | Cash for work program, Renovation of agri roads , Rupaha Diwulapitiya, Rupaha Thibbatugoda, Hbbaragala upper road, Ulkatu Ela DS road, Oluwila Welyaya Road, Podimeenkadu, Divuladamanagoda, Palliyagodella, Palakkadu, Sinnakolaniya, Waulkele, Divulankadawala Mahasen Puranagama road, Gurugodella Erangama road, Divulankadawala LD old road, no.5 Mr.Kariyaperuma paddy field level agri road, Sanwardanayaya road, Dambagaswewa left bank road, Dambagaaswewa right bank road, Divulankadawala Mahasen puranagama aluth welyaya road, Kalingapura anicut road, Kalingapura Keth Ela, Kalinga Ela FC02, Sanwardanayaya road, Ukuthule Gama Meda road, Thunmansala Meegolla Agri road, ThunmansalaGama Meda Bolagandawela road, Welihida , Miriswatte road | S
| 2.4 Conduct periodic assessment of project results and lessons learnt at community, divisional and national levels |  | Training of FOs on conducting vulnerability risk assessment (VRA) among member households and conduct the awareness programs using the trained members. Conducting VRAs in every target FO with the involvement of one member from every target household. Evaluation of the results and prioritizing adaptive actions 3 years. Assist to execute a crop insurance mechanism for crop losses in the area. Provision of allocation for members to continue with introduced adaptation strategies that have been proven to be effective 3 years. Implementation of crop insurance scheme to compensate crop losses. | 19.2461 | During the reporting period, discussions were initiated to identify the process for VRA and consultations were done with relevant parties to identify indicators for vulnerability and risk assessment in the project targeted areas. The VRA will provide a sound base to promote crop insurance scheme based on the vulnerability and the risks to climate change. | MS
| 2.5 Document and disseminate lessons of climate resilient livelihood development and watershed management approaches and best practices |  | Conduct awareness workshops and seminars for policy development at provincial and national level. 25 exchange visits among project sites to promote replication and bring the adaptation focus into local planning processes, especially village development plans 3 years. A media campaign using both printed and electronic media, 30 media reports or program on project activities. | 22.4529 | Awareness program conducted by DMC, Nuwaraeliya, Web designing and creation of a web page, Exchange visit of farmers from Polonnaruwa to Walapane. Meetings conducted with the National Building Research Organization (NBRO). Organized a landslide Disaster Risk Reduction(DRR) program in Walapane in which installation of landslide early detection systems and 10 units of rain gauge systems were performed. | S
| 2.6 Design and implement early warning systems for climate induced risk of landslide and drought in Mahaweli Basin |  | Develop a flood early warning system and rain gauge network. 15 Sirens and telemeter raingauges to be established in Walapane DS. | 24.7664 | Procurement process for purchasing the necessary equipment (automated rain gauges, manual rain gauges, exhaustiveness, drones) of early warning system of floods and landslides in Walapane DS are in progress coupled with a centrally functioning software for the first time in Sri Lanka . 30 Nos of training drills collaboration with Grama Niladari , FOs have completed in Walapane DS. Location identification were done to establish relevant equipment with the local community parties and the Disaster management Centre and DS office Walapane | S
MS
Please Provide the Name and Contact information of person(s) responsible for completing the Rating section
| Name: | Mr.W.T.H. Ruchira Withana
| Email: | adaptationtionfundprojects@gmail.com
Please justify your rating. Outline the positive and negative progress made by the project since it started. Provide specific recommendations for next steps. . (word limit=500)
Hard components of the project activities have almost been successfully completed. There are still improvements with introducing and incorporating adaptive measures to be taken into consideration. Comprehensive training modules should be designed and conducted with emphasis on adaptive measures to address all the strata of the community. In order to share the experiences of the project activities, wider print media and other mass media collaboration have been planned. School children are considered as an important stakeholder in climate change adaptation work and project implementation, thus school children will be engaged in training programmes, awareness building programme, activity based learning activities in classrooms and school to build the awareness on climate change and climate change adaptation. It was noted that the project was almost on hold during 2015 due to the Presidential election that entailed changes in the Government, ministries and project management. The delay of the project implementation was compounded by the Parliamentary election in August 2015 that resulted in the new government gazette, and new Ministry portfolios were established. The project has come under the supervision of 3 Secretaries during this period . The current Secretary has come into power from 2017. The PMU staff changed drastically. At the same time, all the partner entities such as Ministry of Agriculture and Disaster Management also went through structural modifications and reforms. In fact, the EE had a fresh start of the project since February 2016. The Project Support Unit was reformed in March-April 2016 and new project staff came on board since then to embark on project implementation. Compared to the previous years, a marked achievement has been made between March 2016 and August 2016 and followed during this reporting period which shows a positive sign for the future achievements. However, it is well noted that in order to successfully complete the project and obtain the desired outputs within the targeted period of time, dedication of all parties with more concreate adaptation strategies should be adopted with relevant modifications.
| Progress on Key Milestones |  | Expected Progress |  | Progress to Date | Rating
Implementing Agency | 1.1 Develop home garden-based agro forestry systems in target DSDs to diversify livelihoods and build adaptive capacity of households to climate change |  | Conduct a survey to identify the current food consumption and nutrition practices among the households in the targeted areas. Assessing water availability and soil conditions to determine the best suited home garden species. Developing a food consumption index. Conduct training on home garden planning, organic agriculture inputs and production of budded plants for all FOs (189) and targeted families. Provide drought tolerant high yielding seeds suitable for the relevant Agro-ecological zones (e.g. seed paddy), planting materials and equipment and tools. Providing 130 rain water harvesting tanks. Monitoring home gardening activities through FOs and village level implementation committees quarterly and provide financial assistance to carry out monitoring activities. Introducing tree species needed for agro-forestry. Conduct animal husbandry training at Pulasthigama. |  | Final report was completed on identifying the current food consumption and nutrition practices among the households in the targeted areas in Walapane DS and Medirigiriya Lankapura DS. A survey was conducted to map suitable home gardens to be improved under the project, this includes assessing water availability and soil conditions to determine the crop varieties that can be promoted in the home gardens. A list of crop specifies identified for different project areas based on water availability, climate conditions and soil conditions were prepared. Training programmes (poly tunnel, mushroom production)were conducted in Walapane DS and agroforestry, other crops( peanut) programmes were in Medirigiriya and Lankapura DS divisions. 130 Nos of Rain water harvesting tanks were distributed among water stressed communities in Medirigiriya and Lankapura DS divisions (100 in Medirigiriya and 30 in Lankapura). Tree species such as Mango, Pomegranate, Oranges, Ambarella, Lime, Guava, and other perennial fruit plants were introduced as an additional income source and as a measure to enrich the catchment area. Trainings were conducted on cattle raring for the small holder farmers. | S
| 1.2 Introduce and promote drought tolerant crop varieties and agronomic practices to counter effects of rainfall variability |  | With the active participation of field extension officers, FO leaders and technical experts, develop a series of field training programs for drought tolerant agriculture. Conduct field trials with selected farmers on the use of the crop species, mixed and inter cropping which are most suitable for the area and the season. Study the soil salinity and soil acidity in target areas and proposed remedial measures for those problems. Introduce agronomic practices useful to tolerate flood and drought conditions. Introducing intersessional cultivation. Direct farmers to make agreements for forward contracts with relevant entities and mediate such activities. Awareness on soil conservation methods. Preparation of lands and introduce irrigation methods to low land paddy fields and uplands which have been abandoned due to landslides. Distribution of traditional local seeds to farmers through FOs in order to conserve and promote traditional varieties. Identify and promote the traditional crop protection mechanisms those could bring resilience to climate change. Promoting reforestation in lands which are subjected to or vulnerable to landslides. Popularize drought tolerance crops. | 53.5121 | Export agriculture crops (i.e. Pepper) were introduced as intercrops in home gardens. Pepper was also cultivated as a commercial crop with selected farmers. | S
| 1.3 Identify and promote climate-resilient alternate income sources such as livestock, perennial cash crops and inland fisheries |  | Technical assessment of suitability of alternative livelihood which were selected by relevant national agencies and their national agencies and their regional counterparts based on their suitability to climate change. Train selected FO members on small business management including alternative income sources. Provide agricultural equipment necessary for the implementation of the market oriented proposals on alternative income sources prepared by the selected members of the FOs and approved by the village level implementing and monitoring committees. Prepare a suitable market for products such as mushroom, pepper, dehydrated agro-products and those based on Kithul. Making linkages among already existing projects. Conduct a survey to identify alternative income generation ventures. Introduce agro-based industries and give directives. |  | Continuation of inland fishery development activities in selected tanks in Maderigiriya collaboration with NAQDA. Introducing fingerlings to supplement the protein needs of the surrounding communities . This would facilitate introducing drought tolerant and high yielding varieties in seasonal tanks too. Discussions were made to facilitate networking of self employee women groups( 100 Nos) in Walapane DS , especially who obtained traing and benefited by raw material packages( mushroom, kithul producers, bee keepers etc.) and so on to create sustainable production market as well as to upgrade their products as per the quality demands. Possibilities of establishing microfinancing opportunities and training FOs on accounting procedure to plan their carrier development activities. Export agriculture crops (i.e. Pepper) were introduced as intercrops in home gardens which is considered as a commercial crop were done collaboration with Export Agriculture Dept. and Inter Provincial Agriculture Dept. | MS
| 1.4 Promote improved post-harvest technologies as viable climate-resilient livelihood sources for farm women |  | Strengthen the existing women based Self-Help Groups (WSG) and /or establishing new groups in selected villages. Provide equipment and relevant training on post harvest technology for the established women based Self-Help Groups. Introduce a strategy for selling their products. Create market for the products developed. Set up a market for products prepared by using post harvest technologies. Introduce new products using post harvest technology where appropriate according to market demand. Create self-employment opportunities by producing confectionery using traditional food items. | 24.3106 | Women farmer group training on livlihood developemnt activites have been conducted. Establishing self employee women group network has been initiated ,Household cash management programmes have been designed. Alternativelivlihood opportunities ahve been expolyed with local women groups. post harvest technology developemnt for avrious localized products were done. The proposals incoloboration with Export Develeopnment Board have been received.Introducing Buy back systems and sustainability of the market needs to be assured for the income generation of their familites | MS
| 1.5 Build community incentives/ Payment for Ecosystem Services for natural resources management to implement climate risk reduction measures. |  | Provide tools and equipment which are used for agricultural purposes and plants used for stabilizing river bank for those households who are participating in the above programs. Provide financial support to construct agro wells. Plan to minimize the damages caused by floods and provide incentives for the labour contribution for structural interventions in reducing floods. Strengthen the FOs in order to enhance the welfare and livelihood of farmers. Safeguard ground water table by protecting small tanks and anicuts. Promote drinking water projects and prohibit all unauthorised pipelines those are used to obtain water. Provide the facilities needed for conserving streamlets. Provide shoes (boots) for farmers who are farming at night to protect from animals and snakes(Medirigiriya). | 27.6924 | Tree planting program. Partial Payments for Irrigation projects were done, they were Pathok wewa, Somaweera wewa, Kahambiliyawa Goda Idam Ela, Peter Wettu canal, Kiriwanamadhiththa, Welihinda wewa, Mada Ela, Mudunmale Ela, Lihiniyagala Ela , Goda mada Ela ,Morabedda Ela, Wewepihilla wewa, Kande Ela, Divulankadawala wewa, Elabatu wewa, Pulutuman wewa, Nelum wewa, Weheragala wewa, Ulkatu wewa, Sinnacolaniya canal , Hene wewa, Dambagahamada wewa, Daradaamuna Ela, Vadiga wewa, Thanthuneriya amuna. | MS
| 2.1 Train and mobilize officers at village, division and provincial level to design, and monitor local adaptation strategies |  | Developing a training module for climate change impacts on agriculture and natural resources and climate proofing on rural development with government and FO. Preparation of training modules in identification of risk of climate change on agriculture and natural resource management and mitigating those effects through traditional and appropriate new farming practices and conducting those trainings at village level. Trainings of officers at provincial, divisional and village level those who already engaged in rural development on climate proofing of rural development and natural resource management intervention. Provision of equipment and tools (GIS software, localized hazard maps, vulnerability assessment tools) for selected 08 Agrarian Service centres. Preparation of hazard zonation maps of each GN division and place them at appropriate places. Provision of suitable technical equipment or tools for rural disaster management committees. Training of relevant officers along with six members from each FO and paying incentives for them. | 49.6517 | Complement for women welfare society, Women training program, purchase of GPS for the projects area, village level hazard zonation mapping was done at Medirigiriya and NuwaraEliya by LUPPD.Prepared and printed 24 Nos of land use maps for Theripaha and Munwaththa in Walapane DS areas on soil conservation measures, development potentials and landslide details by LUPPD | MS
| 2.2 Strengthen Farmer Organizations with information, training and equipment to implement adaptation strategies |  | Carry out a survey of registered and unregistered FOs in the area. Preparation of technically sound management plan adopting a participatory approach and improve the performance of all minor irrigation schemes. Conduct workshops to improve awareness on appropriate water management strategies for the area. Preparing disaster mitigation and prevention assessment. Practical training for the members of FOs on financial reporting and accounting. Providing equipment for FO office premises and village level Agriculture Research and Production Assistants. Assisting to construct 25 agro-wells. Providing necessary electrical equipment for Agrarian Services Centres for project activities. |  | Farmers were encouraged to join in FOs and actively participate in community work related to climate adaptation activities. Training programmes to be conducted on improving water management capacities of small tanks for farmer organizations together with Department of Agrarian Development. A plan was devised to carry out the training programmes with the support of technical specialists to build the capacity of the farmer organizations on water management in the minor irrigation systems rehabilitated by the Project. All 25 agro-wells were constructed. Possibilities of construction of agro wells in Walapane is underway. | S
| 2.3 Pilot integrated watershed management models in micro watersheds to safeguard climate sensitive livelihood assets such as land and water |  | Survey and mapping of micro watershed including on farmland use and land degradation. Planning and implementation of community based watershed conservation, interventions through appropriate agencies and experts by providing financial benefits to the community to appropriate their contribution. Renovation of agricultural roads in the area, desilting of tanks and provide funds for routine maintenance activities. Identification and mapping of catchment boundaries of streams, natural drains and springs and delineate them as reserves. Minor repairs and maintenance work on identified irrigation structures within the micro catchment to improve water yield and dry season storage. Protection of water sources and springs including which have not been already used or protected. Provide ownership of the farming lands to farmers and provision of compensation to the community for lands in acquiring reservations after surveying. | 34.4253 | It is planned to implement integrated watershed management model and management plan in Walapane DS and Maderigiriya Lanakpura DS . In identified micro catchments/ reservations conservation measures have been identified, specified tree species( kumbuk, mee) to maximise the water retention capacities were planted. Rehabilitation of Cascade system development in Walapane DS ( construction work as well as the ecosystem based approach ) has been planned and the necessary approvals are to be finalized with BOQs and necessary approvals. 25 Nos of plant nurseries were established with local FO communities in the area and the plants from such nurseries were used in tree planting programmes of the area. Construction of agri roads( Walapane DS- , Pollonnaruwa DS) were done which would facilitate cultivation activities, marketing of livelihood promotion products. | S
| 2.4 Conduct periodic assessment of project results and lessons learnt at community, divisional and national levels |  | Training of FOs on conducting VRA among member households and conduct the awareness programs using the trained members. Conducting VRAs in every target FO with the involvement of one member from every target household. Evaluation of the results and prioritizing adaptive actions 3 years. Assist to execute a crop insurance mechanism for crop losses in the area. Provision of allocation for members to continue with introduced adaptation strategies that have been proven to be effective 3 years. Implementation of crop insurance scheme to compensate crop losses. | 19.2461 | Audit team and an independent review team has visited the peripheries and made their observations. Measures were taken to incorporate the rectifying measures and improve the quality of the implemented activities. UNDP has agreed to share their expertise in modifying the activities with more prominent adaptive measures. Possibilities of finding suitable crop insurance scheme are underway. 25 Nos of poly tunnels to cultivate selected crop species to combat harsh climatic conditions were constructed in Walapane DS | S
| 2.5 Document and disseminate lessons of climate resilient livelihood development and watershed management approaches and best practices |  | Conduct awareness workshops and seminars for policy development at provincial and national level. 25 exchange visits among project sites to promote replication and bring the adaptation focus into local planning processes, especially village development plans 3 years. A media campaign using both printed and electronic media, 30 media reports or program on project activities. | 22.4529 | Continuation of inland fishery development activities in selected tanks in Maderigiriya collaboration with NAQDA. Introducing fingerlings to supplement the protein needs of the surrounding communities . This would facilitatethe hiher income of the farmer groups via addtional income generation activities. Extension of poly tunnel programme on most economically viable crop species to be popularized. In site training for maintaing polytunnel crops were conducted in Agricultural Training Institute in Bindunuwewa. Project Web site was developed to share the lessons learnt and to exchange the technical aspects of climate adaptation strategies. Media and Print media publication plan(leaflets, broachure, video clips, documentory) are to be finalized and workout ASAP | S
| 2.6 Design and implement early warning systems for climate induced risk of landslide and drought in Mahaweli Basin |  | Develop a flood early warning system and rain gauge network. 15 Sirens and telemeter rain gauges to be established in Walapane DS. | 24.7664 | Procurement process for purchasing the necessary equipment( automated rain gauges, manual rain gauges, exhaustiveness, drones) of early warning system of floods and landslides in Walapane DS are in progress coupled with a centrally functioning software for the first time in Sri Lanka . 30 Nos of training drills collaboration with Grama Niladari , FOs have completed in Walapane DS. Location identification were done to establish relevant equipment with the local community parties and the Disaster management Centre and DS office Walapane | S
[5 empty] | Overall Rating | MS
Please Provide the Name and Contact information of person(s) responsible for completing the Rating section
| Name: | Mr. Nguyenduc HOANG
| Email: | nguyenduc.hoang@wfp.org
| Progress on Key Milestones |  | Expected Progress |  | Progress to Date | Rating
Other
Overall Rating
Please Provide the Name and Contact information of person(s) responsible for completing the Rating section
Name:
Email:
| Please justify your rating and address the following points: 1. Indicate trends, both positive and negative, in achievement of outcomes as per the project indicators. 2. Detail critical risks that have affected progress. 3. Outline response to MTR undertaken this reporting period. 4. Outline action plan to address projects with a rating of HU, U or MU. Please keep your input to 1200 words |  | The agreements and SOP created a common platform and it helped to ensure the AF guidelines are articulated. However in the operational aspect, as previously mentioned, multiple changes in government administration meant constant rotation of focal points. Familiarization of government officials with the project was time consuming and had temporarily paused project activities due to elections. With regards to project activities, as explained in the financial data tab, due to a constantly changing administration, all government recruitments (including project staff) were paused and only completed during 2016. In absence of project staff, procurements as well as implementation of planned activities was affected.
Rating Definitions
|  |  | Highly Satisfactory (HS) | Project actions/activities planned for current reporting period are progressing on track or exceeding expectations to achieve all major outcomes/outputs for given reporting period, without major shortcomings. The project can be presented as “good practice”.
|  |  | Satisfactory (S) | Project actions/activities planned for current reporting period are progressing on track to achieve most of its major outcomes/outputs with only minor shortcomings.
|  |  | Marginally Satisfactory (MS) | Project actions/activities planned for current reporting period are progressing on track to achieve most major relevant outcomes/outputs, but with either significant shortcomings or modest overall relevance.
|  |  | Marginally Unsatisfactory (MU) | Project actions/activities planned for current reporting period are not progressing on track to achieve major outcomes/outputs with major shortcomings or is expected to achieve only some of its major outcomes/outputs.
|  |  | Unsatisfactory (U) | Project actions/activities planned for current reporting period are not progressing on track to achieve most of its major outcomes/outputs.
|  |  | Highly Unsatisfactory (U) | Project actions/activities planned for current reporting period are not on track and shows that it is failing to achieve, and is not expected to achieve, any of its outcomes/outputs.

## Project Indicators
PROJECT Indicators
Please provide all indicators being tracked for the project as outlined in the project document
Type of Indicator (indicators towards Objectives, Outcomes, etc…)
Type of Indicator | Indicator | Baseline | Progress since inception | Target for Project End
Objective: To mitigate effects of climate change induced rainfall variability and its impacts on livelihood and food security in rainfed farming communities in three sub watersheds of the Mahaweli River Basin | Percentage of target population adopting risk reduction measures | Less than 10% of target population (14,039 households) practice climate risk reduction measures | The project has reached more than 10,000 household members in distributing agri-tools which can be used in home gardening. During this period number of training programs were conducted on home garden planning and organic agriculture inputs in Medirigiriya, Lankapura and in Walapane DS too. The commencement of rehabilitation work on 28 minor irrigation structures such as tanks and canals under the Project will ensure reaching the 75% of the targeted population out of 14,039 households practising improved water management once those minor irrigation schemes are completed. In addition establishment of more than 330 rain water harvesting tanks also directly help and also disseminate knowledge on improved water management. The Project has identified dairy and bee keeping as non-farm income sources and 15 families have been supported in dairy development and more than 200 bee boxes have been purchased to be distributed among entrepreneurial families.The second phase of teh Cattle farm project has been initiated. Baseline household survey including Food Consumption Score and House hold Dietary Diversity Score were conducted and the final report was submitted by the Institute to the EE and to date the final payment was made to the relevant Institute. Home gardening in the project areas are being uplifted with appropriate trainings, workshops and by the distribution of the crops, fruit plants, drought tolerant high yielding seeds, pepper, ginger and plants to the targeted farmer communities and purchase of lemon, Hana plant for bio fencing . Bee boxes were distributed. Construction of Agro wells in Polonnaruwa .Rainwater harvesting tanks and trees for agro forestry were also distributed. Planting materials such as knives, mamoties and steels were distributed to the farmers in both the DS areas of the project. Nursery training programs, poverty alleviation program, meetings with relevant organizations like wild life department, 15 farmers were trained, distributed with a cattle per head and the partial financial aid for the construction of cattle sheds were also provided for them. After their successful implementation, distribution of cattle to another fifty farmers being planned and which is on process to date. Milk and vegetable collection centre in Walapane DS is also in line and for which an estimate worth of Rs.1.99 MN was prepared and recommended by the Divisional Secretary of the Walapane DS. A landslide risk assessment certificate was also received from the National Building Research Organization(NBRO) for the successful implementation of the construction of the above mentioned collection centre. Current percentage achived for the indicator is 64% | 75% of target population (14,039 households) practice at least one climate risk reduction measure introduced through project interventions such as Responding to early warning and forecasting, Household level Non-farm income sources, Home garden food production, Improved water management, Post-harvest technologies, Resistant crop varieties, Knowledge of climate risks and adaptation strategies
| Household consumption score | Both DSDs indicate food insecurity in VAM (Vulnerability Analysis and Mapping Data) Walapane - Very High. Medirigiriya- Moderate. A more sensitive index similar to household consumption score will be developed through the project’s initial household consumption surveying. | Export agriculture crops as to introduce inter seasonal cultivations were distributed. Distribution of plants, green grams were done. Training on fishery. The training on home gardening, introduction of of non-farm activities to segments of targeted population, distribution of drought tolerant planting material, provision of agri-tools enabling long hours of working in the farmlands, rehabilitation of irrigation structures and makin improvements to agri roads enabling easy market access from farmlands will ensure improved food security directly and indirectly through farm-family income augmentation. Food consumption score is prepared. As per the Baseline survey conducted in year 2016 Food Consumption Score Pattern was measured by the Food Consumption Score. This value was 75.5 5 for Walapane DS and an average of 94.7% for Medirigiriya / Lankapura DS . A Household Diaetery Diversity Score of 71.85 was recorded for Walanane DS and 76.1% average for Medirigiriya / Lankapura DS | 14,039 farming households indicate improved levels of food security compared to the initial consumption survey
Outcome Diversified and strengthened livelihoods and sources of income for vulnerable farm families in minor irrigated and rain fed areas | Percentage of target households with sustained climate resilient livelihoods | Farm families under minor irrigation/rain fed conditions highly exposed to climate change related livelihood insecurity threat level : very high. [52% of the total HHs solely depend only on agriculture (crop production)]. | After their successful implementation, distribution of cattle to another fifty farmers being planned and which is on process to date. Milk and vegetable collection centre in Walapane DS is also in line and for which an estimate worth of Rs.1.99 Mn was prepared and recommended by the Divisional Secretary of the Walapane DS. A landslide risk assessment certificate was also received from the National Building Research Organization(NBRO) for the successful implementation of the construction of the above mentioned collection center.Planting materials, and seeds ,plants were distributed. 7300 families have been assisted in developing climate resilient livlihood opportunities so far | 14,039 target households have developed at least one climate resilient livelihood strategy of alternative source of income
| No. of women with new source of income | Women in target areas practice tradition rain fed farming. [Total employed women in labour force is 35.74% and 63% among them are involved in traditional rainfed farming]. | The Project has created direct new source of income through promoting dairy farming for 8 women. Some more women will be participating in the future activity. | Home gardens generate income in 50% of target population, women's contribution to household income increased by 50% in target households
Output 1.1 Develop home garden based agro forestry systems in target DSDs to diversify livelihoods and build adaptive capacity of households to climate change | No. of diversified home gardens created through project intervention Value of food and income generated through diversified home gardens | Home garden diversity low-medium Low->10 species of food and multi -purpose tree species,medium-10-25 High-<25 species. [Low Diversity HG - 83.1%, Medium Diversity HG - 16.9%, High Diversity HG - 0%] Annual income generated from Home garden No considerable income - 54.48%, <Rs.10000 - 10.66%, (Rs.10000-Rs.49000) - 19.45%, (Rs.50000-Rs.100000) - 8.21%, >Rs.100000 - 7.2% | The training on Home Gardening is being successfully conducted and perennial food crops (3 plants in 3 species) are distributed. So far more than 900 home garden trainings farmers of which more than 80% are women, have been trained. Actions are under way to develop 25 Model Home gardens in the DS Division. Project could not calculate this indicator as activities have yet to be implemented. | 14039 rain fed farming families benefit from home garden improvement- Diversity in home gardens improved - Household income from home gardens increased
Output 1.2 |  | Low awareness and adoption of drought tolerant agronomic practices [54.2%of households have adopted at least one drought mitigation agronomic practice. Such practices are listed in Table 3.2 below.] | Crop varieties such as green gram, peanut, lemon, Hana, ginger, pepper,Thibbatu, maize, bitter gourd, kurrakan have been introduced as suitable crops for the area to cultivate during drought season. 12 types( soil conservation measures, catchment conservation, introduce drought resistant plant varieties, live stock dvelopemnt activiites, livlihood develoepment activiites, climate resiliant home gardens, agro forestry systems, training and experiance sharing on climate resiliant effects on agriculture of drought mitigation practices have been impleemnted to mitigate climate impact resilent effects for beneficiaries so far
Introduce and promote drought tolerant crop varieties and agronomic practices to counter effects of rainfall variability | No. and type of drought mitigation practices introduced |  |  | All FO s trained to engage in drought tolerant agriculture, Farmer field trials conducted with national technical agencies for 500 farm families selected by FO s, Seed banks and seed distribution established in each ASC
Output 1.3 | No. and type of alternate livelihood assets created | Low level of access to non-farm livelihood assets including information Training/skills Market linkage Finance | Supporting 15 dairy farmers by providing cattle sheds and dairy cattle. There are 8 female farmers among them. More women participation in the future activity. Bee keeping , mushroom production., kithul production, poly tunnel cultivation , nursery establishment ect were some of teh livlihood activiites introduced maily for womenn groups | 6 technical assessments on livelihood assets created for climate resilience, and market chain analysis conducted
Identify and promote climate resilient alternate income sources such as livestock, perennial cash crops and inland fisheries | No of women participated in livelihood training |  | More than 10 women have been educated on dairy farming. More than 35 women have been trained on mushroom production. Around 2,152 women have been trained under all livelihood categories. | Trainings on dairy farming, mushroon cultivation, nursery management and bee keeping were provided to all FOs by specialized state agencies. Livelihood support equipment was provided to six viable livelihood proposals from every FO.
Output 1.4 |  | [Only 1.4% of HHs are engaged in postharvest activities] | Post harvest women trainings were conducted. Initial discussions with the Institute of Post Harvest Technology (IPHT) have been held to train entrepreneurial members in the target population to promote post-harvest technologies. 225 farm women have been involved in post harvest developemnt activities | Post harvest centres established in 8 ASCs in the 3 project DSDs, One post harvest village established in each ASC area 760 farm women in 08 villages linked with local livelihood incentive programs
Promote improved post harvest technologies as viable climate- resilient livelihood sources for farm women | No. of farm women engaged in project-introduced post harvest livelihoods
Output 1.5 | Percentage and level of community participation cash for work system | 0% participation in PES schemes in target area | Tree planting program. Partial Payments for Irrigation projects were done, they were Pathok wewa, Somaweera wewa, Kahambiliyawa Goda Idam Ela, Peter Wettu canal, Kiriwanamadhiththa, Welihinda wewa, Mada Ela, Mudunmale Ela, Lihiniyagala Ela , Goda mada Ela ,Morabedda Ela, Wewepihilla wewa, Kande Ela, Divulankadawala wewa, Elabatu wewa, Pulutuman wewa, Nelum wewa, Weheragala wewa, Ulkatu wewa, Sinnacolaniya canal , Hene wewa, Dambagahamada wewa, Daradaamuna Ela, Vadiga wewa, Thanthuneriya amuna. about 250 farmer organization memebers have been participated in Cash for For Programme | 1,500 households benefit from cash for work schemes in two micro catchments in target DSDs
Build community Assets and livelihood resources through cash for work to support climate risk reduction measures | Number of women participating in cash for work programme
Outcome 2 | Percentage of target population aware of predicted impacts of climate change and appropriate responsive adaptive actions to safeguard livelihood assets. | Lack of awareness of climate impacts and adaptive actions at household and community level, Extension officers and CBO officials have no training on climate proofing local community development. [Though at least one member of 79% of the HHs have heard about 'Climate Change Impacts' only 15% is clearly aware about it. 69% of the HHs do not take any adaptive actions to safeguard HH properties] | An additional 14.8% of HHs have been educated by the Project, on 'Climate Change Impacts and Adaptive Actions'. | All 14039 households participate in climate risk assessment in target area receive climate change awareness, At least 50% of community risk assessment meetings consist of women, All FO s in target area receive information and tools to develop local adaptive strategies to safeguard livelihood assets, All local and divisional-level officials engaged in agriculture, fisheries, forestry and disaster management receive at least one training on supporting adaptive strategies
Strengthened ownership of climate risk reduction processes and increased replication potential of adaptation strategies at local level and basin/sub national level
Output2.1 | No. of village, divisional and provincial officers trained to address climate risks | Training programmes on climate risk management are not available at regional and local level | Complement for women welfare society, Women training program, purchase of GPS for the projects area, village level hazard zonation mapping was done at Medirigiriya and NuwaraEliya by LUPPD. 2 TOT Programmes were conducted and about 175 Nos of Officers in Provincial and divisional leveles were trained | One training module developed, 6 TOTs developed and conducted, 250 officials trained at provincial, divisional, and village engaged in rural development, All Agrarian Service centres in project DSDs receive climate risk management tools
Train and mobilize officers at village, division and provincial level to design, and monitor local adaptation strategies
Output 2.2 | Capacity of FO s to respond to climate risk | FO s lack information on risks, and lack planning capacity t o address them, Some villages do not formalized FO s | Renovation of existing irrigation projects. These are Ambagaspitiya Maha Ela, Siyambalakumbura Ela, Attalakumbura Ela, Yombuwelthenna Ela, Maa Ussawa Ela and Meegollawa tank. Water shed Management- Subodhagama, Workshop on Accounts training program. | All FO s in target DSDs have developed management plans for local irrigation management and catchment conservation, Management plans are funded through community & government input, All FO s in the target divisions are registered with Agrarian Services and have elected representatives, At least 6 members each FO trained to conduct vulnerability reduction assessments as input 2.4
Strengthen FO s with information, training and equipment to implement adaptation strategies
Output 2.3 | Availability of watershed-level irrigation management plans. Increased extent cultivated under pilot minor irrigation scheme | No cluster/cascade level watershed management plans exist, CI in village tanks in lower catchment<90%, CI in anicut systems in middle catchment<70%. [The issue of non-availability of cluster/cascade level watershed irrigation management systems was highlighted and emphasized to have such system in the Baseline Survey Report as well. Not only irrigation water management but the necessity of proper management of drinking water was also recommended in the Baseline Report] | Cash for work program, Renovation of agri roads , Rupaha Diwulapitiya, Rupaha Thibbatugoda, Hbbaragala upper road, Ulkatu Ela DS road, Oluwila Welyaya Road, Podimeenkadu, Divuladamanagoda, Palliyagodella, Palakkadu, Sinnakolaniya, Waulkele, Divulankadawala Mahasen Puranagama road, Gurugodella Erangama road, Divulankadawala LD ol road, No;5 Mr.Kariyaperuma paddy field level agri road, Sanwardanayaya road, Dambagaswewa left bank road, Dambagaaswewa right bank road, Divulankadawala Mahasen puranagama aluth welyaya road, Kalingapura anicut road, Kalingapura Keth Ela, Kalinga Ela FC02, Sanwardanayaya road, Ukuthule Gama Meda road, Thunmansala Meegolla Agri road, ThunmansalaGama Meda Bolagandawela road, Welihida , Miriswatte road | Management plans for two micro watersheds developed and implemented FO s, Increase cropping intensity in both systems to over 100%
Pilot integrated watershed management plans to safeguard climate sensitive livelihood assets such as land and water
Output 2.4 | Level of awareness among awareness among target group of climate risk | Target population unaware of climate risks and adaptive measure | During this reporting period financially no work has been done but there are few discussions were made regarding vulnerability Risk Assessment (VRA) and crop insurance mechanism which were decided to give for the the relevant entity. | VRA s conducted in all FO s targeting 14,039 households at three month, 18 month and end of project, >45% female participation
Conduct Risk Assessment and Adaptation Planning with target communities
Output 2.5 Document and disseminate lessons of climate resilient livelihood development and watershed management approaches and best practices | No. of news outlets in the local press and media reported on project lessons, No. of new project proposals,/ new community based adaptation initiatives generated within and outside the DSDs | Reporting on climate adaptation in national media poor, No such project proposals exist | Awareness program conducted by DMC, Nuwaraeliya, Web designing and creation of a web page, Exchange visit of farmers from Polonnaruwa to Walapane. Meetings conducted with the National Building Research Organization (NBRO). Organized a landslide Disaster Risk Reduction(DRR) program in Walapane in which Installation of landslide early detection systems and 10 units of rain gauge systems were performed. So far only few news paper articles on the project activities have been published. Preparatory work has been done to produce broachres on selected project components and to produce comprehensive reports on the successful stories as well as to produce documentory. Case studies have been expolored on different aspects and some were elaborated as project proposals | 10 case studies generated, 5 policy briefs produced and shared with NPSC, 50 media reports on project outcomes, 2 provincial workshops to share project learning, 20 CBA proposals from other vulnerable communities generated through exchange visits
Output 2.6 | Development and functioning of early warning systems | No community based landslide warning in project DSDs, No drought/seasonal forecasting systems in place | Meeting was conducted with NBRO for this reporting period. Developing a community-based landslide warning system is being studied with the relevant organizations such as National Building Research Organization (NBRO) and Disaster Management Centre (DMC). Discussions has been initiated with the relevant parties such as NBRO and DMC for establishing drought/seasonal forecasting system. | Developed and implemented drought forecasting and timely dissemination model for Mahaweli basin, 15 community based landslide early warning systems with telemetric rain gauges are operationalized in Walapane DSD
Design and implement early warning systems for climate induced risk of landslide and drought in Mahaweli Basin

## Lessons Learned
QUALITATIVE MEASURES and LESSONS LEARNED
Please complete the following section every reporting period
Implementation and Adaptive Management | Response
What implementation issues/lessons, either positive or negative, affected progress? | Successful project activities already implemented at field level have contributed to uplift the living conditions of the farmer communities, introduce alternative livelihood activities, promote climate adaptive agricultural and irrigation practices as well. Wise and planned land use practices, soil conservation measures and conservation aspects have been emphasized and were coordinated with several responsible stakeholder organizations. However, limitations in fund disbursement during the project period due to the settlement of the new implementation arrangement with WFP and UNDP have caused the delay in the planned activities. Insufficiency of project staff in field set-up for executing the field work, inadequate number of staff in project support unit were some of the causes for not meeting the desired progress levels. Even though with limited number of PMU and divisional staff, the project was able to coordinate with a large number of stakeholder organizations and increase their awareness on the scope and mandate of the climate change adaptation activities.
Were there any delays in implementation? If so, include any causes of delays. What measures have been taken to reduce delays? | Lack of staff in the Project Support Unit, turnover of main staff in the project and change in the higher authorities of the Ministry led to the delay in the execution of major project activities. Change in the designated authorities in the hierarchy for getting the approval also delays the initiation of project activities. Staff recruitment is initiated through newspaper advertisements. It is being decided to get the technical and procurement related services from an organization and the process in progress.
Describe any changes undertaken to improve results on the ground or any changes made to project outputs (i.e. changes to project design) | There are no changes to project outputs or project design. However, due to the protracted delays in project implementation, a new implementation arrangement has been approved by the Adaptation Secretariat whereby UNDP joined the project as another excecuting entity. The Adaptation Secretariat has also granted an extension of the project end date for Februay 2019.
How have gender considerations been taken into consideration during the reporting period? What have been the lessons learned as a consequence of inclusion of such considerations on project performance or impacts? | When selecting beneficiaries, women: men ratio was considered. More than 50% women participation was entrusted whenever possible. Larger number of women and Farmer groups were involved in different project activities. In order to build the resilient livelihood activities, initiatives were taken to establish self employee network and to introduce micro financing systems. Cash to work programmes were organized with higher number of women participants representing a number of farmer organizations. Women farmer organization training and post harvest training for women were undertaken.
Please complete the following section at mid-term and project completion
Lessons for Adaptation | Response
Climate Resilience Measures
What have been the lessons learned, both positive and negative, in implementing climate adaptation measures that would be relevant to the design and implementation of future projects/programmes for enhanced resilience to climate change? | To date no mid-term evaluation has been conducted. A rapid review was done in May 2017 that led to the new implementation arrangement of the project where UNDP will be part. It would be good to conduct a mid-term evaluation for lessons learnt in order to effectively to achieve the result framework. The construction work at divisional secretariat level provides infrastructure facilities with adaptive measures, enabling the affected communities to withstand challenges by the climatic shocks in different ways and means. Different level training programmes were conducted with larger number of participants, addressing different climate adaptation components of the project. Knowledge sharing and capacity building were done for the targeted groups.
What is the potential for the climate resilience measures undertaken by the project/programme to be replicated and scaled up both within and outside the project area? | Government of Sri Lanka received funds from the Green Climate Fund to implement a seven year project in the Dry Zone of Sri Lanka on Climate Change Adaptation on water and agriculture as the main intervention area. The Ministry of Mahaweli Development and Environment is the implementing partner to UNDP to implement this project. The project has already approached the GCF project team in the Ministry to share the lessons leant from the AF Project. As the project will be implemented in the coming year with the support of UNDP, there are more opportunities to incorporate the lessons of this project in GCF funded Project.
Concrete Adaptation Interventions
What have been the lessons learned, both positive and negative, in implementing concrete adaptation interventions that would be relevant to the design and implementation of future projects/programmes implementing concrete adaptation interventions? | More technical considerations should be incorporated in implementing all project sub-activities to introduce more comprehensive adaptive measures.
What is the potential for the concrete adaptation interventions undertaken by the project/programme to be replicated and scaled up both within and outside the project area? | Successful cases can be replicated with wider community participation linking more NGOs, CBOs in an integrated approach in order to support marginalized communities in affected areas
What would you consider to be the most successful aspects for the target communities? | Through improved alternative livelihoods the poor and affected vulnerable groups will be able to uplift their living standards, and thus social welfare will be ensured
What measures are/have been put in place to ensure sustainability of the project/program results? | Strengthening FOs and women organizations and formation of community level monitoring mechanisms will ensure the sustainability of the project activities. As a result the field project authorities have been empowered for the relevant activities. They will be totally responsible for ensuring the substantiality of the project components
What measures are being/could have been put in place to improve project/program results? | Seek assistance and expertise from field level implementing organizations. Recruit consultant/experts to guide, advise on the technical matters, based on the TOR. Recruitment of sufficient PMU staff and divisional level staff.
Knowledge Management
How has existing information/data/knowledge been used to inform project development and implementation? What kinds of information/data/knowledge were used? | The field level information and data gathering organizations are to be included in decision making process, hence their knowledge and experiences could be channelled for implementing the project activities more appropriately. UNDP has collaborated as technical partners in implementing some of the training components and has advertised to find consultants to train and strengthen FOs to disseminate the knowledge and experience.
If learning objectives have been established, have they been met? Please describe. | Partially met and the planning work is in progress to design more comprehensive and integrated projects to address climatic resilience.
Describe any difficulties there have been in accessing or retrieving existing information (data or knowledge) that is relevant to the project. Please provide suggestions for improving access to the relevant data. | Limited resources and access to information and knowledge with specific climatic adaptive data/ information /databases in remote areas (drought tolerant seeds, crop varieties ). Specific data and collection is not adequate to plan and design comprehensive projects.
Has the identification of learning objectives contributed to the outcomes of the project? In what ways have they contributed? | Ensured food availability through diversified livelihoods and sources of income generation of the communities inhabiting in climatic vulnerable areas specially in climatic vulnerable seasons which would ultimately be contribute to upgrade economic sustainability and the social welfare of the marginalized communities

## Results Tracker
Results Tracker for Adaptation Fund (AF) Projects - Numbers will be available after baseline survey is completed
Goal: Assist developing-country Parties to the Kyoto Protocol that are particularly vulnerable to the adverse effects of climate change in meeting the costs of concrete adaptation projects and programmes in order to implement climate-resilient measures. Impact: Increased resiliency at the community, national, and regional levels to climate variability and change.
Important: Please read the following guidance document (also posted on the Adaptation Fund website) before entering your data
Link: http://www.adaptation-fund.org/sites/default/files/Results%20Framework%20and%20Baseline%20Guidance%20final.pdf
Adaptation Fund Strategic Results Framework
Project ID | LKA/MIE/Rural/2011/1
Implementing Entity | World Food Programme
Type of implementing entity | MIE
Country | SRI LANKA
Region | Asia-Pacific
Sector | Food security
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Impact: Increased resiliency at the community, national, and regional levels to climate variability and change | Core Indicator: No. of beneficiaries |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project
|  | Total | 17658 | 12393 | 5265 | Total | 14309 |  |  | Total |  |  |  | Total
|  | % of female beneficiaries | 41% | 33% | 25% | % of female beneficiaries |  |  |  | % of female beneficiaries |  |  |  | % of female beneficiaries
|  | % of Youth beneficiaries | 16% | 10% | 7% | % of Youth beneficiaries |  |  |  | % of Youth beneficiaries |  |  |  | % of Youth beneficiaries
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 1: Reduced exposure to climate-related hazards and threats | Indicator 1: Relevant threat and hazard information generated and disseminated to stakeholders on a timely basis | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness
|  | Total |  |  |  | Total |  |  |  | Total |  |  |  | Total
|  | % of female targeted |  |  |  | % of female targeted |  |  |  | % of female targeted |  |  |  | % of female targeted
Output 1.1 Risk and vulnerability assessments conducted and updated | Indicator 1.1: No. of projects/programmes that conduct and update risk and vulnerability assessments | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
Output 1.2 Targeted population groups covered by adequate risk reduction systems | Core Indicator 1.2: No. of Early Warning Systems | No. of adopted Early Warning Systems | Category targeted | Hazard | Drought | No. of adopted Early Warning Systems | Category targeted | Hazard | Drought | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  | 0 | 2: Monitoring and warning service | Geographical coverage | Regional | 15 | 2: Monitoring and warning service | Geographical coverage | Local |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities |  |  |  | Number of municipalities | 1 |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 2: Strengthened institutional capacity to reduce risks associated with climate-induced socioeconomic and environmental losses | Indicator 2: Capacity of staff to respond to, and mitigate impacts of, climate-related events from targeted institutions increased | Number of staff targeted |  | Sector | Capacity level | Number of staff targeted |  | Sector | Capacity level | Number of staff targeted |  | Sector | Capacity level | Number of staff targeted |  | Sector | Capacity level
|  | Total |  | Food security | 2: Low capacity | Total | 250 | Food security | 3: Medium capacity | Total |  |  |  | Total
|  | % of female targeted |  |  |  | % of female targeted |  |  |  | % of female targeted |  |  |  | % of female targeted
Output 2.1 Strengthened capacity of national and sub-national centres and networks to respond rapidly to extreme weather events | Indicator 2.1.1: No. of staff trained to respond to, and mitigate impacts of, climate-related events | Total staff trained | % of female staff trained | Type |  | Total staff trained | % of female staff trained | Type |  | Total staff trained | % of female staff trained | Type |  | Total staff trained | % of female staff trained | Type
| Indicator 2.1.2: No. of targeted institutions with increased capacity to minimize exposure to climate variability risks | Type | Scale | Sector | Capacity level | Type | Scale | Sector | Capacity level | Type | Scale | Sector | Capacity level | Type | Scale | Sector | Capacity level
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 3: Strengthened awareness and ownership of adaptation and climate risk reduction processes | Indicator 3.1: Increase in application of appropriate adaptation responses | Percentage of targeted population applying adaptation measures |  | Sector |  | Percentage of targeted population applying adaptation measures |  | Sector |  | Percentage of targeted population applying adaptation measures |  | Sector |  | Percentage of targeted population applying adaptation measures |  | Sector
Output 3: Targeted population groups participating in adaptation and risk reduction awareness activities | Indicator 3.1.1: Percentage in targeted population awareness of predicted adverse impacts of climate change, and of appropriate responses | No. of targeted beneficiaries | % of female participants targeted | Level of awareness |  | No. of targeted beneficiaries | % of female participants targeted | Level of awareness |  | No. of targeted beneficiaries | % of female participants targeted | Level of awareness |  | No. of targeted beneficiaries | % of female participants targeted | Level of awareness
[6 empty] | 14309 | 50%
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Target performance at completion |  |  |  | Target performance at completion
Outcome 4: Increased adaptive capacity within relevant development sector services and infrastructure assets | Indicator 4.1: Increased responsiveness of development sector services to evolving needs from changing and variable climate | Project/programme sector | Geographical scale | Response level |  | Project/programme sector | Geographical scale | Response level |  | Project/programme sector | Geographical scale | Response level |  | Project/programme sector | Geographical scale | Response level
| Core Indicator 4.2: Assets produced, developed, improved or strengthened | Sector | Targeted asset | Changes in asset (quantitative or qualitative) |  | Sector | Targeted asset | Changes in asset (quantitative or qualitative) |  | Sector | Targeted asset | Changes in asset (quantitative or qualitative) |  | Sector | Targeted asset | Changes in asset (quantitative or qualitative)
Output 4: Vulnerable development sector services and infrastructure assets strengthened in response to climate change impacts, including variability | Indicator 4.1.1: No. and type of development sector services to respond to new conditions resulting from climate variability and change | Number of services | Type |  | Sector | Number of services | Type |  | Sector | Number of services | Type |  | Sector | Number of services | Type |  | Sector
|  | Baseline information |  |  |  | Baseline information |  |  |  | Baseline information |  |  |  | Baseline information
Outcome 5: Increased ecosystem resilience in response to climate change and variability-induced stress | Indicator 5: Ecosystem services and natural resource assets maintained or improved under climate change and variability-induced stress | Natural resource improvement level |  | Sector | Type | Natural resource improvement level |  | Sector | Type | Natural resource improvement level |  | Sector | Type | Natural resource improvement level |  | Sector | Type
Output 5: Vulnerable ecosystem services and natural resource assets strengthened in response to climate change impacts, including variability | Core Indicator 5.1: Natural Assets protected or rehabilitated | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Baseline information |  |  |  | Targeted performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 6: Diversified and strengthened livelihoods and sources of income for vulnerable people in targeted areas | Indicator 6.1: Increase in households and communities having more secure access to livelihood assets | No. of targeted households | % of female headed households | Improvement level |  | No. of targeted households | % of female headed households | Improvement level |  | No. of targeted households | % of female headed households | Improvement level |  | No. of targeted households | % of female headed households | Improvement level
| Indicator 6.2: Increase in targeted population's sustained climate-resilient alternative livelihoods | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
|  | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
|  | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
|  | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
Output 6 Targeted individual and community livelihood strategies strengthened in relation to climate change impacts, including variability | Indicator 6.1.1: No. and type of adaptation assets created or strengthened in support of individual or community livelihood strategies | Number of Assets | Type of Assets | Sector | Adaptation strategy | Number of Assets | Type of Assets | Sector | Adaptation strategy | Number of Assets | Type of Assets | Sector | Adaptation strategy | Number of Assets | Type of Assets | Sector | Adaptation strategy
| Core Indicator 6.1.2: Increased income, or avoided decrease in income | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 7: Improved policies and regulations that promote and enforce resilience measures | Indicator 7: Climate change priorities are integrated into national development strategy | Integration level |  |  |  | Integration level |  |  |  | Integration level |  |  |  | Integration level
Output 7:Improved integration of climate-resilience strategies into country development plans | Indicator 7.1: No. of policies introduced or adjusted to address climate change risks | No. of Policies introduced or adjusted | Sector | Scale | Type | No. of Policies introduced or adjusted | Sector | Scale | Type | No. of Policies introduced or adjusted | Sector | Scale | Type | No. of Policies introduced or adjusted | Sector | Scale | Type
|  | 0 | Water management | Local | Water policy | 2 | Water management | Local | Water policy
| Indicator 7.2: No. of targeted development strategies with incorporated climate change priorities enforced | No. of Development strategies | Regulation |  | Effectiveness | No. of Development strategies | Regulation |  | Effectiveness | No. of Development strategies | Regulation |  | Effectiveness | No. of Development strategies | Regulation |  | Effectiveness
Glacier lake outburst flood
|  | Inland flooding | fr | biological assets |  | Company policy | 5: Fully enforced (All elements implemented)
|  | Salinization | Decrease | land |  | Communication & Information policy | 4: Enforced (Most elements implemented)
|  | Drought | Same | water areas |  | Defense policy | 3: Partially enforced (Some elements implemented)
|  | Wind |  | subsoil assets | increased adaptive capacity | Domestic policy | 2: Partially not enforced (Most elements not implemented) |  | Agribusiness
|  | Coastal flooding |  | air | achieved | Economic policy | 1: Not enforced (No elements implemented) |  | Agricultural-related | Financial capital
|  | Storm surge | Please choose |  | enhanced level of protection | Education policy |  |  | Agriculture | Human capital
|  | Hurricane | Selected | [5 empty] | Aquaculture | Physical capital
|  |  | Not relevant |  |  | 5: All (Fully integrated) |  |  | Construction/repairing business | Social capital
[6 empty] | 4: Most |  |  | Cultivation | Natural capital
[6 empty] | 3: Some |  |  | Fishing | Personal capital
Select | 5: All | Select |  |  | Community | 2: Most not integrated |  | Other | Forestry | Adaptation strategies
1 | 4: Almost all | Private | Type | Yes | Multi-community | 1: None |  | Agriculture | Handicrafts
2 | 3: Half | Public | Scale | No | Departmental |  |  | Coastal management | Livestock production
3 | 2: Some | NGO | Sector |  | National |  |  | Disaster risk reduction | Manufacturing
4 | 1: None |  |  |  |  | 5: Very high improvement | Established | Food security | other
|  | National |  |  |  | 4: High improvement | Maintained | Health | Services
|  | Regional |  |  |  | 3: Moderate improvement | Improved | Urban development | Tourism-related
|  | Local |  |  |  | 2: Limited improvement |  | Water management | Trading
[6 empty] | 1: No improvement |  | Multi-sector
|  | 1 -generated information is irrelevant, and neither the stakeholders reached nor the timeframe managed were achieved | 1: No info transferred on time | 4: High capacity | 5: Fully aware | 5: Highly responsive (All defined elements ) | 5: Fully improved | Roads | 5: Very effective
Asia-Pacific | NIE | 2 -the existence of some challenge in any of the three aspects of the indicator (generation of dissemination, stakeholders reached or timeframe managed) | 2: Somewhat info transferred | 3: Medium capacity | 4: Mostly aware | 4: Mostly responsive (Most defined elements) | 4: Mostly Improved | Gov Buildings | 4: Effective
Latin America and Caribbean | RIE | 3 -relevant information is generated and disseminated to all identified stakeholders on timely basis | 3: Info transferred on time | 2: Low capacity | 3: Partially aware | 3: Moderately responsive (Some defined elements) | 3: Moderately improved | Causeways | 3: Moderately effective
Africa | MIE |  |  | 1: No capacity | 2: Partially not aware | 2: Partially responsive (Lacks most elements) | 2: Somewhat improved | Airports | 2: Partially effective
Eastern Europe |  |  |  |  | 1: Aware of neither | 1: Non responsive (Lacks all elements ) | 1: Not improved | Schools | 1: Ineffective
| ha protected | [6 empty] | Training Centres
| ha rehabilitated | [5 empty] | Monitoring/Forecasting capacity | Hospitals
Afghanistan, Islamic Rep. of | km protected | [5 empty] | Policy/regulatory reform | Drinking water systems
Angola | km rehabilitated | 1: Risk knowledge | 1: No plans conducted or updated |  |  |  | Capacity development | Other
Albania |  | 2: Monitoring and warning service | 2: Undertaking or updating of assessments in progress |  |  | Communication & Information policy | Sustainable forest management
Argentina |  | 3: Dissemination and communication | 3: Risk and vulnerability assessments completed or updated |  |  | Domestic policy | Strengthening infrastructure | 1: Health and Social Infrastructure (developed/improved)
Armenia | Forests | 4: Response capability |  |  |  | Economic policy | Supporting livelihoods | 2: Physical asset (produced/improved/strengthened)
Antigua and Barbuda | Mangroves |  |  |  |  | Education policy | Mangrove reforestation
Azerbaijan | Coasts |  | From 0 to 0.5% |  |  | Energy policy | Coastal drainage and infrastructure
Burundi | Rangelands |  | From 0.5 to 1% |  |  | Environmental policy | Irrigation system
Benin | Cultivated land/Agricultural land |  | From 1% to 5% |  |  | Foreign policy | Community-based adaptation
Burkina Faso | Catchment area/Watershed/Aquifer |  | From 5% to 10% |  |  | Health policy | Erosion control
Bangladesh | Protected areas/National parks |  | From 10% to 20% |  |  | Housing policy | Soil water conservation
Bulgaria | Other |  | From 20% to 30% |  |  | Human resource policies | Microfinance
Bahrain |  |  | From 30% to 40% |  |  | Information policy | Special Program for women
Bahamas, The |  |  | From 40% to 50% |  |  | Macroeconomic policy | Livelihoods
Bosnia and Herzegovina |  |  | Above 50% |  |  | Monetary policy | Water storage
Belarus | [5 empty] | Population policy | ICT and information dissemination
Belize | [5 empty] | Private policy
Bolivia | [5 empty] | Public policy
Brazil | [5 empty] | Science policy
Barbados | [5 empty] | Social policy
Bhutan |  | 3- relevant information is generated and disseminated to all identified stakeholders on timely basis |  |  |  | Transportation policy
Botswana |  | describe |  |  |  | Urban policy
Central African Republic |  | 2- the existence of some challenge in any of the three aspects of the indicator |  |  |  | Water policy
Chile |  | describe |  |  |  | Other policy
China, People's Republic of |  | 1- generated information is irrelevant and neither the stakeholders reached nor the timeframe managed were achieved
Cote d'Ivoire |  | describe
Cameroon
Congo, Dem. Rep. of
Congo, Republic of
Cook Islands
Colombia
Comoros
Cape Verde
Costa Rica
Cuba
Czech Republic
Djibouti
Dominica
Dominican Republic
Algeria
Ecuador
Egypt
Eritrea
Estonia
Ethiopia
Fiji
Micronesia, Fed. States of
Gabon
Georgia
Ghana
Guinea
Gambia, The
Guinea-Bissau
Equatorial Guinea
Grenada
Guatemala
Guyana
Honduras
Croatia
Haiti
Hungary
Indonesia
India
Iran, Islamic Republic of
Jamaica
Jordan
Kazakhstan
Kenya
Kyrgyz Republic
Cambodia
Kiribati
Saint Kitts and Nevis
Korea, Republic of
Lao People's Democratic Republic
Lebanon
Liberia
Libya
Saint Lucia
Sri Lanka
Lesotho
Lithuania
Latvia
Morocco
Moldova
Madagascar
Maldives
Mexico
Marshall Islands
Macedonia, former Yugoslav Republic of
Mali
Malta
Myanmar
Montenegro
Mongolia
Mozambique
Mauritania
Mauritius
Malawi
Malaysia
Namibia
Niger
Nigeria
Nicaragua
Niue
Nepal
Nauru
Oman
Pakistan
Panama
Peru
Philippines
Palau
Papua New Guinea
Poland
Korea, Dem. People's Rep. of
Paraguay
Romania
Russian Federation
Rwanda
Saudi Arabia
Sudan
Senegal
Solomon Islands
Sierra Leone
El Salvador
San Marino
Serbia
Sao Tome and Principe
Suriname
Slovak Republic
Slovenia
Swaziland
Seychelles
Syrian Arab Republic
Chad
Togo
Thailand
Tajikistan
Turkmenistan
Tonga
Trinidad and Tobago
Tunisia
Turkey
Tuvalu
Tanzania
Uganda
Ukraine
Uruguay
Uzbekistan
Saint Vincent and the Grenadines
Venezuela
Vietnam
Vanuatu
Samoa
Yemen, Republic of
South Africa
Zambia
Zimbabwe
Timor-Leste

## Units for Indicators
Fund Outcome Indicator Units
1. Generation of relevant data, Stakeholders, and Timeliness 2.1. Include both qualitative and quantitative measures of capacity level within targeted institutions 2.2. Number (men and women and other vulnerable groups) 3.1. Use scale from 1 to 5: 5: Fully aware 4: Mostly aware 3: Partially aware 2: Partially not aware 1: Aware of neither predicted adverse impacts of climate change nor of appropriate responses 3.2. Use scale from 1 to 5: 5: All 4: Almost all 3: Half 2: Some 1: None 4.1. Summarize in an overall scale (1-5): 5: Highly responsive (All defined elements ) 4: Mostly responsive (Most defined elements) 3: Moderately responsive (Some defined elements) 2: Partially responsive (Lacks most elements) 1: Non responsive (Lacks all elements ) 4.2. Summarize in an overall scale (1-5): 5: Fully improved 4: Mostly Improved 3: Moderately improved 2: Somewhat improved 1: Not improved 5. Depends on the targeted natural asset: Biological (species): measure through changes in population numbers (dynamics, structure, etc.) Land: measure changes in hectares. Baseline data will be necessary to estimate the change. Supporting indicators baseline and target (as well as contextual information) are needed such as the following: Farmers adopting recommended technologies, Ha. of land improved, Average deforestation rate Etc. Use scale from 1 to 5. 5: Very effective (All elements are present) 4: Effective (Most elements are present) 3: Moderately effective (Some elements are present) 2: Partially effective (Most elements are not present) 1: Ineffective (No elements are present) 6.1. Summarize in an overall scale (1-5): 5: Very high improvement 4: High improvement 3: Moderate improvement 2: Limited improvement 1: No improvement 6.2. Household income by source of livelihood in project area (USD) prior and post project intervention 7. Summarize in an overall scale (1-5). 5: All (Fully integrated) 4: Most 3: Some 2: Most not integrated 1: None
Fund Output Indicator Units
1.1. Number, sector(s) and level(s) of projects or interventions in separate fields of monitoring plan 1.2. Number 2.1.1. Number of staff (male/female) of targeted institutions: a. Obtain baseline information: total number of staff from targeted institutions b. Define target 2.1.2. Number of staff (male/female) of targeted institutions: a. Obtain baseline information: total number of staff from targeted institutions b. Define target: needs to be defined by project proponents 2.2.1. Quantitative: Percentage (includes women – and other vulnerable groups – and men). Qualitative: Adequacy: include direct analysis of major areas; adequacy/effectiveness of systems or analysis of perceptions of populations and institutions. 2.2.2. Number (broken down by gender and, if possible, by vulnerable groups defined in the area of intervention) of people 3.1. Number and type (in separate columns) at local level. 3.2. Number 4.1. Number and type 4. 2. Number and type (entered in separate columns) 5. Number of interventions by type of natural asset and intervention 6.1. Number and type (in separate columns of monitoring plan) 6.2. Income sources per household; description of income source and number of households. 7.1. Number/Sector 7.2. Number; Effectiveness (see previous indicator) through enforcement level.

## Financial annex
Addressing Climate Change Impacts on Marginalized Agricultural Communities Living in the Mahaweli River Basin
Explanatory notes on variancies between planned and actual expenditures of outputs during the reporting period
ITEM / ACTIVITY / ACTION | ACTUAL EXPENDITURES (US$) | PLANNED EXPENDITURES (US$) | Difference | Reason for underspending
Component 01
Activity 1.1 Develop diversified home garden based agro forestry in Walapane,Lankapura and Medirigiriya DS to build household adaptive capacity to climate change | 270625.84 | 350000 | 79374.16 | Although the plans were there to conduct the field level programmes in wider scale, due to difficulties in gathering the most suitable partners as expected was a hindrance. Services of field level officers could not be obtained as expected due to rushed schedules of their own organizations.
Activity 1.2. Introduce and promote drought tolerant crop varities and agronomic practices to counter effects of rainfall variability | 32158.28 | 120000 | 87841.72 | Finalizing the lists of beneficieries took a long time and the availabilty of most suitable varieties or seeds could not be obtained on time.
Activity 1.3. Identify and promote climate- resilient alternate income sources among rural farm household dependent on rain-fed agriculture | 58863.75 | 420000 | 361136.25 | Although the trainings and meetings planned to establish self-started employee networks for livelihood development were conducted, integration of their recommendations could not be materialized at ground level.
Activity 1.4. Promote improved post harvest technologies as viable climate resilient livelihood sources for farm women | 3579.58 | 420000 | 416420.42 | Although Post harvest technology improvement programmes were coordinated and proposals were received the documentation part couldn’t be completed as per the procedures by the stakholder organization mandated for this activity
Activity 1.5. Build community assets and livelihood resources through cash-for-work to support climate risk reduction measures | 376765.9 | 460000 | 83234.1 | Most of the hard project componenets were planned to be completed under this activity but due to the lack of technical staff in line agencies the work couldn't be completed as expected.
Component 02
Activity 2.1. Train and mobilize officers at village, division and provincial level | 2394.69 | 120000 | 117605.31 | Lack of technical staff in stakholder organizations in preparing neccessary BOQs, estimates ect. Multi stage government approval procedures were not complete in expected speed.
Activity 2.2. Strengthen Farmer Organizations with information, training and equipment to implement adaptation strategies | 94042.22 | 150000 | 55957.78 | There are many sub-projects under this activity of which the majority is about rehabilitation or construction of minor irrigation schemes in different GN divisions (project target areas). Some GN divisions performed well while others still need to strengthen their capacity to carry out these activities. This led to the delays in achieving the targets. However, with more capacity and technical support being invested, the work will be expedited.
Activity 2.3. Pilot integrated watershed management models in micro watersheds to safeguard climate-sensitive livelihood assets such as land and water | 474185.93 | 580000 | 105814.07 | Stakeholder organization internal technical capacities were not enough to run the exercise in an expedited manner.
Activity 2.4. Risk Assessment and Adaptation Planning conducted with target communities | 0 | 54000 | 54000 | Although crop insurance schemes were mainly targeted within this, the protocols, mandatory requirements/scenarios that need to be cleared were huge and the crops introduced by the project itself was not enough in this regard.
Activity 2.5. Document and disseminate lessons of climate-resilient livelihood development and watershed management approaches and best practices | 11434.63 | 120000 | 108565.37 | Despite the face that documentation and a media campaign had been planned, it was challenging to carry out studies, draw lessons and best practices in order to document and disseminate information to the benefiting communities due to the fact that the project implementation experienced significant delays over the last years. With the new implementation arrangements (approved by the Adaptation Secretariat) whereby UNDP provides technical support in climate smart agriculture and climate resilient livelihoods, the implementation of these activities will be expedited.
Activity 2.6 Design and implement early warning systems for climate-induced risks of landslides and drought in Mahaweli Basin | 93392.7 | 150000 | 56607.3 | Part payment was only released as the organzation assigned to this task has not completed the field implementation and requested the payment
Execution cost | 73380.15 | 260000 | 186619.85 | Staff recruitments were schduled but couldn’t be realized as expected and the Office procurement needs to be fulfilled as per the procurement procedures only
Total | 1490823.67 | 3204000 | 1713176.33