## Overview
Project Performance Report (PPR)
| Period of Report (Dates) | 01/07/2016 - 30/06/2017
| Project Title: | TF 015041 - INCREASING CLIMATE RESILIENCE AND ENHANCING SUSTAINABLE LAND MANAGEMENT IN THE SOUTHWEST OF THE BUENOS AIRES PROVINCE
| Project Summary: | The Project Development Objective (PDO) is to contribute to reducing climate and man-made vulnerability of the agro-ecosystems in the Southwest of the Buenos Aires Province (SWBA) by increasing the adaptive capacity of key local institutions and actors and piloting and disseminating climate resilient and sustainable land management practices. Participatory planning processes were used to identify and are used to pilot concrete adaptation measures focusing on water, crops and livestock management to promote climate resilience. The Project aims to benefit farmers and families engaged in small and medium-sized agricultural-cattle production on dry lands within the direct and indirect intervention zones; the counties of Puan, Villarino and Patagones; and 9 further SWBA counties, respectively. Additionally, a wide range of current and potential partner organizations working on related aspects within the area and up to national level benefit from and contribute to a comprehensive set of capacity building and institutional strengthening measures. The continued, inter-sectoral and inter-institutional work and learning process, through which the Project evolves, aims at (1) creating an adequate political, social, and economic framework to facilitate adoption, sustainability, continuity, and further development of the piloted adaptation efforts; and (2) bolstering and fine-tuning adaptation measures identified and chosen through institutional and community-level participation and capacity building.
|  |  | Countries | Project Type: |  | GEF Focal Area: | GEF 4 Focal Areas | GEF 2 / 3 Operational Programme: | Overall Rating of the project in the evaluation by the project evaluator: | GEF-4 Focal Area Strategic Program: | GEF-3 Focal Area Strategic Program:
| Database Number: | ARG/MIE/Rural/2011/1 - P125804 | Afghanistan | FP | Yes | Biodiversity | 1 | 1 | U | BD-SP1-PA Financing | 1: Arid & semi-arid ecosystems
Implementing Entity (IE) [name]: |  | The World Bank | Albania | MSP | No | Climate Change Adaptation | 2 | 2 | S | BD-SP2-Marine PA | 2: Coastal, marine & freshwater ecosystems
| Type of IE: | MIE | Algeria | EA |  | Climate Change Mitigation | 3 | 3 | MU | BD-SP3-PA Networks | 3: Forest ecosystems
| Country(ies): | Argentina | Angola |  |  | International Waters | 5 | 5 | Good | BD-SP5-Markets | 13: Conservation and Sustainable Use of Biological Diversity Important to Agriculture
Relevant Geographic Points (i.e. cities, villages, bodies of water): |  | Counties of Patagones, Villarino, Puan - Buenos Aires Province, Argentina | Argentina |  |  | Multiple Focal Area |  |  |  | BD-SP7-Invasive Alien Species(IAS) | 6: Promoting the adoption of renewable energy by removing barriers and reducing implementation costs
[8 empty] | CC-SP2- Industrial EE | 8: Waterbody based operational program
| Project Milestones | [6 empty] | CC-SP3-RE,CC-SP4-Biomass | 9: Integrated Land and Water multiple focal area
| Milestone |  | Bahamas | [6 empty] | CC-SP5-Transport | 10: Contaminants based operational program
AFB Approval Date: |  | December, 2012
IE-AFB Agreement Signature Date: |  | 2013-02-25 | [6 empty] | CC-SP6-LULUCF | 12: Integrated Ecosystem Management
Start of Project/Programme: |  | June, 2015 (Inception Workshop) | [6 empty] | Cross cutting capacity building | 14: Persistent Organic Pollutants
Mid-term Review Date (if planned): |  | April, 2017
| Terminal Evaluation Date: | 2019-06-30
|  | List documents/ reports/ brochures / articles that have been prepared about the project. | Cyprus
|  | Brochure of the Project Description; Brochure on Resilience and Sustainable Land Management for the intervention area; Multi-proposal poster for teaching at local schools and capacity building for local agents, opinion leaders and farmers; chapter in the publication "Economics of Land Degradation and Improvement – A Global Assessment for Sustainable Development" edited by the Economics of Land Degradation Initiative of the UNCCD, available at http://link.springer.com/book/10.1007/978-3-319-19168-3, and 89 media-articles. During the reporting period, the Information and Early-Warning System (IEWS; SIAT for the Spanish acronym) developed and disseminated the first 3 quarterly Meteorological and Agricultural Outlook Reports that provide key data about the 6 previous months, forecasts for the 3 next months, and recommendations for good practices to protect productive activities. The SIAT reports are available e.g. at the following INTA website: http://inta.gob.ar/busqueda/p/buscar/SIAT/type/0__all | Czech Republic
List the Website address (URL) of project. |  |  | Democratic People's Republic of Korea
|  | http://ambiente.gob.ar/suelos/proyecto-aumentando-la-resiliencia-climatica-y-mejorando-el-manejo-sostenible-de-la-tierra-en-el-sudoeste-de-la-provincia-de-buenos-aires/ | Democratic Republic of the Congo
Denmark
| Project contacts: |  | Djibouti
National Project Manager/Coordinator |  |  | Dominica
| Name: | Director Jorge Heider - Argentina's Ministry of Environment and Sustainable Development (MAyDS) | Dominican Republic
| Email: | jheider@ambiente.gob.ar | Ecuador
| Date: | July, 2017 | Egypt
| Government DA |  | El Salvador
| Name: | Undersecretary Dolores Duverges - Argentina's Ministry of Environment and Sustainable Development | Equatoral Guinea
| Email: | dduverges@ambiente.gob.ar | Eritrea
| Date: | July, 2017 | Estonia
| Implementing Entity |  | Ethiopia
| Name: | Tuuli Bernardini, Environmental Specialist GEN04, Task Team Leader - The World Bank | Fiji
| Email: | tbernardini@worldbank.org | Finland
| Date: | July, 2017 | France
| Executing Agency |  | Gambia
| Name: | Coordinator Joaquin Etorena - Argentina's Ministry of Environment and Sustainable Development | Georgia
| Email: | jetorena@ambiente.gob.ar | Germany
| Date: | July, 2017 | Ghana
| Executing Agency |  | Greece
| Name: |  | Grenada
| Email: |  | Guatemala
| Date: |  | Guinea
| Executing Agency |  | Guinea Bissau
| Name: |  | Guyana
| Email: |  | Haiti
| Date: |  | Honduras
Hungary
Iceland
India
Indonesia
Iran (Islamic Republic of)
Iraq
Ireland
Israel
Italy
Jamaica
Japan
Jordan
Kazakhstan
Kenya
Kiribati
Kuwait
Kyrgyzstan
Lao People’s Democratic Republic
Latvia
Lebanon
Lesotho
Liberia
Libyan Arab Jamahiriya
Liechtenstein
Lithuania
Luxembourg
Madagascar
Malawi
Malaysia
Maldives
Mali
Malta
Marshall Islands
Mauritania
Mauritius
Mexico
Micronesia, Federated States of
Monaco
Mongolia
Montenegro
Morocco
Mozambique
Myanmar
Namibia
Nauru
Nepal
Netherlands
New Zealand
Nicaragua
Niger
Nigeria
Norway
Oman
Pakistan
Palau
Panama
Papua New Guinea
Paraguay
Peru
Philippines
Poland
Portugal
Qatar
Republic of Korea
Republic of Moldova
Romania
Russian Federation
Rwanda
Saint Kitts and Nevis
Saint Lucia
Saint Vincent and the Grenadines
Samoa
San Marino
Sao Tome and Principe
Saudi Arabia
Senegal
Serbia
Seychelles
Sierra Leone
Singapore
Slovakia
Slovenia
Solomon Islands
Somalia
South Africa
Spain
Sri Lanka
Sudan
Suriname
Swaziland
Sweden
Switzerland
Syrian Arab Republic
Tajikistan
Thailand
The former Yugoslav Republic of Macedonia
Timor-Leste
Togo
Tonga
Trinidad and Tobago
Tunisia
Turkey
Turkmenistan
Tuvalu
Uganda
Ukraine
United Arab Emirates
United Kingdom of Great Britain and Northern Ireland
United Republic of Tanzania
United States of America
Uruguay
Uzbekistan
Vanuatu
Venezuela, Bolivarian Republic of
Viet Nam
Yemen
Zambia
Zimbabwe

## FinancialData
Financial information: cumulative from project start to June 30, 2017
DISBURSEMENT OF AF GRANT FUNDS
How much of the total AF grant as noted in Project Document plus any project preparation grant has been spent to date?
Estimated cumulative total disbursement as of June 30, 2017 | 1384435
Add any comments on AF Grant Funds. (word limit=200) | As of June 30, 2017, USD 1,013,602.09 has been spent; USD 286,818 has been commited; and USD 884,435.88 has been documented to the WB.
EXPENDITURE DATA
List output and corresponding amount spent for the current reporting period | ITEM / ACTIVITY / ACTION | AMOUNT
| SUB-COMPONENT 1.1: Creating Institutional Tools for Climate Resilience | 15362.95
| 1- Information and early-warning system for droughts, land degradation and desertification control | 15362.95
| 2- Regional Consultative Observatory of Public Policies on Climate Change and Desertification to mainstream climate change adaptation | 0
| 3- Institutional capacity building program directed at local public officers | 0
| SUB-COMPONENT 1.2: Promoting Climate-smart Socio-cultural Approaches to Land Management | 37580.22
| 4- Training program on climate change and different adaptation options for disseminators | 26084.75
| 5- Training program for rural school teachers to mainstream environmental factors, climate change and approaches to climate resilience into the curriculum | 0
| 6- A gender-sensitive program to empower farmers and their families and strengthen their social role for sustainable development | 11495.47
| COMPONENT 2: Implementing Adaptation Measures in Productive Agroecosystem | 499143.11
| 7- Water Resources Management: Installation of microsystems for irrigation and rainwater harvesting | 121036.11
| 8- Crop Management: Implementation of crop rotation systems, diversification, time alteration of sowing, and organic agriculture in demonstration sites | 229281.64
| 9- Livestock and Pasture Management: Implementation of adaptation measures such as forage banks, silvopastorile systems, rangeland recovery and sustainable plot management | 148517.04
| 10- Participatory development of Good Agricultural Practices (GAPs) aimed at enhancing management plans for production and adoption of a voluntary code of climate resilient GAP. Based on results of further stakeholder consultations, identification of alternative livelihood options and ways to facilitate their adoption | 308.32
| COMPONENT 3: Applying Participatory Approach to Knowledge Management and Local Capacity Development for Adaptation to Climate Change | 40536.49
| 11- Combined consultation, coordination, training, and knowledge sharing at the local level in the three counties of direct Project intervention to develop and validate intervention proposals and work plans | 6909.02
| 12- Capacity building for indicator development and measurement plans, systems of continuous improvement, training for local application groups, and mutual knowledge sharing in terms of the proposed activities between and beyond the counties | 25828.73
| 13- Participatory development of progress information through development of periodic reports to make information available to all stakeholders | 244.29
| 14- Training and knowledge management with stakeholders through joint demonstrative field visits | 7554.45
| COMPONENT 4: Developing a Sustainability Strategy | 27226.43
| 15- A representative Working Committee for the Project’s intervention area comprised by the regional Observatory with institutional capacity to maintain the IEWS and committed to provide information to the national and provincial | 21191.27
| 16- A compilation and publication of standard-formatted set of evaluation and tracking tools (specific reports on key issues) | 2195.84
| 17- A compilation and review of domestic and international sources of finance to secure continuity of the key Project activities | 0
| 18- Knowledge sharing on progress evaluation with involved stakeholders and publication and dissemination of lessons learned | 0
| 19- Implementation of a program for dissemination and exchange of experiences from the local to the international | 3839.32
| Project Execution - Project Implementation Unit (PIU) | 77464.33
| Printing costs on communication material | 3865.71
| PIU salaries and expenses | 41367.97
| Other services | 29857.24
| Banking costs | 10065.02
| Miscelaneous expenses | 5381.69
| TOTAL | 697313.54
PLANNED EXPENDITURE SCHEDULE
List outputs planned and corresponding projected cost for the upcoming reporting period | ITEM / ACTIVITY / ACTION | PROJECTED COST | Est. Completion Date
| Sub-Component 1.1: Creating Institutional Tools for Climate Resilience | 332000
| 1- Information and early-warning system for droughts, land degradation and desertification control | 312000 | 2018-06-18
| 2- Regional Consultative Observatory of Public Policies on Climate Change and Desertification to mainstream climate change adaptation | 0 | 2018-06-18
| 3- Institutional capacity building program directed at local public officers | 20000 | 2018-06-18
| Sub-Component 1.2: Promoting Climate-smart Socio-cultural Approaches to Land Management | 84000
| 4- Training program on climate change and different adaptation options for disseminators | 30000 | 2018-06-18
| 5- Training program for rural school teachers to mainstream environmental factors, climate change and approaches to climate resilience into the curriculum | 22000 | 2018-06-01
| 6- A gender-sensitive program to empower farmers and their families and strengthen their social role for sustainable development | 32000 | 2018-06-01
| Component 2: Implementing Adaptation Measures in Productive Agroecosystem | 1472000
| 7- Water Resources Management: Installation of microsystems for irrigation and rainwater harvesting | 350000 | 2018-06-01
| 8- Crop Management: Implementation of crop rotation systems, diversification, time alteration of sowing, and organic agriculture in demonstration sites | 690000 | 2018-06-01
| 9- Livestock and Pasture Management: Implementation of adaptation measures such as forage banks, silvopastorile systems, rangeland recovery and sustainable plot management | 390000 | 2018-06-01
| 10- Participatory development of Good Agricultural Practices (GAPs) aimed at enhancing management plans for production and adoption of a voluntary code of climate resilient GAP. Based on results of further stakeholder consultations, identification of alternative livelihood options and ways to facilitate their adoption | 42000 | 2018-06-01
| Component: 3. Applying Participatory Approach to Knowledge Management and Local Capacity Development for Adaptation to Climate Change | 87000
| 11- Combined consultation, coordination, training, and knowledge sharing at the local level in the three counties of direct Project intervention to develop and validate intervention proposals and work plans | 25000 | 2018-06-18
| 12- Capacity building for indicator development and measurement plans, systems of continuous improvement, training for local application groups, and mutual knowledge sharing in terms of the proposed activities between and beyond the counties | 18000 | 2018-06-18
| 13- Participatory development of progress information through development of periodic reports to make information available to all stakeholders | 20000 | 2018-06-18
| 14- Training and knowledge management with stakeholders through joint demonstrative field visits | 24000 | 2018-06-01
| Component: 4. Developing a Sustainability Strategy | 80000
| 15- A representative Working Committee for the Project’s intervention area comprised by the regional Observatory with institutional capacity to maintain the IEWS and committed to provide information to the national and provincial | 22000 | 2018-06-18
| 16- A compilation and publication of standard-formatted set of evaluation and tracking tools (specific reports on key issues) | 18000 | 2018-06-18
| 17- A compilation and review of domestic and international sources of finance to secure continuity of the key Project activities | 18000 | 2018-06-18
| 18- Knowledge sharing on progress evaluation with involved stakeholders and publication and dissemination of lessons learned | 12000 | 2018-06-18
| 19- Implementation of a program for dissemination and exchange of experiences from the local to the international | 10000 | 2018-06-18
| TOTAL | 2169000
ACTUAL CO-FINANCING (If the MTR or TE have not been undertaken this reporting period, DO NOT report on actual co-financing.)
How much of the total co-financing as committed in the Project Document has actually been realized? | 33%
Estimated cumulative actual co-financing as verified during Mid-term Review (MTR) or Terminal Evaluation (TE). | USD 319,774 by the Ministry of Environment and Sustainable Development (MAyDS)
Add any comments on actual co-financing in particular any issues related to the realization of in-kind, grant, credits, loans, equity, non-grant instruments and other types of co-financing. (word limit=200) | Co-financing until June 30, 2017 includes in-kind, non-grant instruments and other types of co-financing for more than USD 1 million as follows: i) INTA staff time, transportation, use of laboratory and meteorological equipment, use of facilities, and conduction of studies and training; ii) UNS and CERZOS staff time, transportation, use of equipment and facilities, conduction of studies and use of the Naposta field; iii) SMN staff time, use of meteorological equipment and servers, and conduction of studies; iv) municipal governments of Patagones, Villarino and Puan staff time, meeting and workshop arrangements, and running of plant nurseries; v) Spegazzini Agriculture School staff time and field work; vi) farmers' time and expenses, use of fields and agroforestry products; vii) Ministry of Social Development staff time and transportation; viii) Vialidad Nacional staff time and transportation; ix) OPDS staff time, transportation, training and meetings.

## Procurement (hidden)
PROCUREMENT DATA
Please provide information for all contracts over $2,500 USD
Please provide the number of contracts under $2,500, signed during this reporting period: |  |  |  | 10
LIST OF CONTRACTS
List all contracts related to the project/program with signature dates
Contract Type | Agency / Contracted party | Contract Value/Amount (USD) (*) | Signature Date | Payment to Date | Remaining Balance
Consultants' services | Juan Corvalán 2016 | 13705.61 | 2016-04-29 | 13705.61 | 0 | The contract signature date is prior to the reporting period, but as the contract was not reflected in the previous report, it is reflected in this one.
Consultants' services | Andres Buono 2016 | 13133.04 | 2016-04-01 | 13133.04 | 0 | Idem.
Consultants' services | Adriana Freysselinard | 9476.31 | 2016-07-01 | 9476.31 | 0
Consultants' services | Pablo Sívori | 8755.36 | 2016-07-01 | 5439.45 | 3315.91
Consultants' services | Gaspes Ezequiel 2017 | 23464.34 | 2017-01-01 | 9740.37 | 13723.97
Consultants' services | Juan Corvalán 2017 | 21950.87 | 2017-01-01 | 9112.11 | 12838.76
Consultants' services | Anastasia Luciano 2017 | 15138.4 | 2017-01-01 | 6421.95 | 8716.45
Consultants' services | Testani Martin 2017 | 20436.66 | 2017-01-01 | 6786.83 | 13649.83
Consultants' services | Ricardo Rotsztein | 15958.23 | 2017-02-01 | 5958.96 | 9999.27
Consultants' services | Ana Corallo | 10218.33 | 2017-03-01 | 5141.99 | 5076.34
Consultants' services | Andres Buono 2017 | 14592.69 | 2017-03-31 | 14592.69 | 0
Consultants' services | Fernando Ianovsky | 15046.67 | 2017-04-28 | 1822.42 | 13224.25
Consultants' services | TNC Argentina | 108555.98 | 2016-09-16 | 52670.67 | 55885.31
Training, Travel and workshops | AMEMOP | 9018 | 2016-11-30 | 9103 | -85
Training, Travel and workshops | AMEMOP | 11615.63 | 2016-11-30 | 11725.13 | -109.5
Non-consulting services and works | Vilma Mariana Prieto | 3457.52 | 2016-09-19 | 3457.52 | 0
Non-consulting services and works | FUNES ENRIQUE ALFREDO | 3865.72 | 2016-06-10 | 3865.72 | 0 | Idem. La fecha es correcta. Finalmente se terminó de pagar el 30 de enero de 2017
Non-consulting services and works | JC ME MH Y RS BERARDI | 4536.32 | 2016-07-21 | 4536.32 | 0
Non-consulting services and works | JC ME MH Y RS BERARDI | 10853.18 | 2017-05-16 | 10853.18 | 0
Non-consulting services and works | PAGAVI | 3913.63 | 2017-06-07 | 3913.63 | 0
Non-consulting services and works | PAGAVI | 9154.84 | 2017-05-05 | 9154.84 | 0
Goods | Agro Luro SRL | 53821.66 | 2016-08-16 | 53821.66 | 0
Goods | Agropecuaria Agromax SA | 3018.62 | 2016-08-12 | 3018.62 | 0
Goods | Metalye Maquinarias | 7897.78 | 2016-08-17 | 7897.78 | 0
Goods | DEISA | 12974 | 2016-08-29 | 12974 | 0
Goods | El Pato Maquinarias | 11663 | 2016-08-29 | 11663 | 0
Goods | Instrumental Pasteur | 6419 | 2016-08-26 | 6419 | 0
Goods | Instrumentalia | 7843 | 2016-08-26 | 7843 | 0
Goods | Juber S.A. | 48109.46 | 2016-08-12 | 48109.46 | 0
Goods | Lasarte HNOS SRL | 5582 | 2016-08-26 | 5582 | 0 | Idem. AÑO CORREGIDO
Goods | PyR Argentina | 10572 | 2016-09-21 | 10572 | 0
Goods | Riegos Pigue | 28287.47 | 2016-10-18 | 28287.47 | 0
Goods | Sartorius | 8748.3 | 2016-08-26 | 8748.3 | 0
Goods | SURGENTE MOLINOS SA | 30877.79 | 2016-09-23 | 12036.44 | 18841.35
Goods | Wekume Agro Servicios SRL. | 93300.16 | 2017-03-23 | 93300.16 | 0
(*) Exchange rate: US Dolar, seller, Banco Nación Divisas, at date of contract signature
BIDS
List all bids for each contract signed with date of open call and winning bid | [5 empty] | "Incomplete lot offer" refers to the bidder in the corresponding line.
CONTRACT & Procurement Method | Submitted Bids | Bid Amount (USD)(*) | Winning Bid Amount (USD)(*) | Selection Justification for the Winner
Shopping PIRCMGS-61-CP-B: Purchase and installation of wire and a mill, Lot N°1, 20/10/2016 | Rurales Don Oscar | 7896 | Incomplete lot offer | Lowest price fulfilling technical requirements
| Agro Luro SRL | 68669
| El Fortín | 17928 | 17928
Shopping PIRCMGS-61-CP-B: Purchase and installation of wire and a mill, Lot N°2, 20/10/2016 | Rurales Don Oscar | 3913.24 | Incomplete lot offer | Lowest price fulfilling technical requirements
| Agro Luro SRL | 165897
| El Fortín | 12309 | 12309
Shopping PIRCMGS-61-CP-B: Purchase and installation of wire and a mill, Lot N°3, 20/10/2016 | Rurales Don Oscar | 1498 | Incomplete lot offer | Lowest price fulfilling technical requirements
| Agro Luro SRL | 52647
| El Fortín | 2954 | 2954
Shopping PIRCMGS-61-CP-B: Purchase and installation of wire and a mill, Lot N°4, 20/10/2016 | Rurales Don Oscar | 9240.45 | Incomplete lot offer | Lowest price fulfilling technical requirements
| Agro Luro SRL | 267845
| El Fortín | 26342 | 26342
Shopping PIRCMGS-61-CP-B: Purchase and installation of wire and a mill, Lot N°5, 20/10/2016 | Agro Luro SRL | 34402 |  | Lowest price fulfilling technical requirements
| El Fortín | 5473 | 5473
Shopping PIRCMGS-61-CP-B: Purchase and installation of wire and a mill, Lot N°6, 20/10/2016 | Rurales Don Oscar | 5810 | Incomplete lot offer | Lowest price fulfilling technical requirements
| Agro Luro SRL | 85573
| El Fortín | 12098 | 12098
Shopping PIRCMGS-61-CP-B: Purchase and installation of wire and a mill, Lot N°7, 20/10/2016 | Agro Luro SRL | 523446 |  | Lowest price fulfilling technical requirements
| El Fortín | 6196 | 6196
Shopping PIRCMGS-61-CP-B: Purchase and installation of wire and a mill, Lot N°8, 20/10/2016 | Agro Luro SRL | 5575 |  | Lowest price fulfilling technical requirements
| El Fortín | 1961 | 1961
Shopping PIRCMGS-61-CP-B: Purchase and installation of wire and a mill, Lot N°9, 23/09/2016 | Agro Luro SRL | 128286.81 |  | Lowest price fulfilling technical requirements
| El Fortín | 36337
| SURGENTE MOLINOS SA | 30877.79 | 12036.44
Shopping PIRCMGS 63 CP B: Purchase of Machinery, Lot N°1, 16/08/2016 | Agromáquinas Villalonga SRL | 57150 |  | Lowest price fulfilling technical requirements
| Agropecuaria Agromax SA | 74545.27
| Agro Mazzuchelli | 75796
| Agro Luro SRL | 53822 | 53821.66
Shopping PIRCMGS 63 CP B: Purchase of Machinery, Lot N°2, 18/08/2016 | Agromáquinas Villalonga SRL | 2034.04 | 2087.22 | Lowest price fulfilling technical requirements
| Agropecuaria Agromax SA | 4434
| Metalye Maquinarias | 2070
Shopping PIRCMGS 63 CP B: Purchase of Machinery, Lot N°3, 18/10/2016 | Metalye Maquinarias | 2961.78 | 2961.78 | Lowest price fulfilling technical requirements
| El Pato Maquinarias | 17834
Shopping PIRCMGS 63 CP B: Purchase of Machinery, Lot N°4, 17/08/2016 | Agropecuaria Agromax SA | 7489 |  | Lowest price fulfilling technical requirements
| Metalye Maquinarias | 4936 | 4858.93
| El Pato Maquinarias | 16561
Shopping PIRCMGS 63 CP B: Purchase of Machinery, Lot N°5, 24/08/2016 | Agromáquinas Villalonga SRL | 5078 |  | Lowest price fulfilling technical requirements
| Dolbi S.A. | 19185 | 18884.64
| Agropecuaria Agromax SA | 20701
| El Pato Maquinarias | 25287
Shopping PIRCMGS 69 CP B: Purchase of Irrigation Systems and Apiculture Materials, Lot N°1, 18/10/2016 | Wekume Agro Servicios SRL. | 11761 | 11407.69 | Lowest price fulfilling technical requirements
Shopping PIRCMGS 69 CP B: Purchase of Irrigation Systems and Apiculture Materials, Lot N°2 18/10/2016 | Riegos Pigue | 659.24 | 659.24 | Lowest price fulfilling technical requirements
| Wekume Agro Servicios SRL. | 1522.52
Shopping PIRCMGS 69 CP B: Purchase of Irrigation Systems and Apiculture Materials, Lot N°3, 21/09/2016 | Riegos Pigue | 25596.23 | 25596.23 | Lowest price fulfilling technical requirements
| Hidráulica Bahía | 26907
| Agro Luro SRL | 33121.02
| Wekume Agro Servicios SRL. | 32172.13
Shopping PIRCMGS 69 CP B: Purchase of Irrigation Systems and Apiculture Materials, Lot N°4, 21/09/2016 | Riegos Pigue | 12677.75 |  | Lowest price fulfilling technical requirements
| PyR Argentina | 10572 | 10572
| Calypso | 12140.88
| Nexo SRL | 11635
| Wekume Agro Servicios SRL. | 20480.6
Shopping PIRCMGS 69 CP B: Purchase of Irrigation Systems and Apiculture Materials, Lot N°5, 18/10/2016 | Agro Luro SRL | 23885.35 |  | Lowest price fulfilling technical requirements
| Wekume Agro Servicios SRL. | 10196.37 | 10068.51
Shopping PIRCMGS 69 CP B: Purchase of Irrigation Systems and Apiculture Materials, Lot N°6, 25/10/2016 | Agro Luro SRL | 955.41 |  | Lowest price fulfilling technical requirements
| Apilcutodo | 613.69
| Wekume Agro Servicios SRL. | 859.33 | 835.39
Shopping PIRCMGS 69 CP B: Purchase of Irrigation Systems and Apiculture Materials, Lot N°7, 21/09/2016 | Riegos Pigue | 2060.97 | 2032 | Lowest price fulfilling technical requirements
| Agro Luro SRL | 3757.96
| Wekume Agro Servicios SRL. | 3354.09
Shopping PIRCMGS-88-CP: Purchase of Seeds and Fertilizers, Lot N°1, 23/03/2017 | Wekume Agro Servicios SRL. | 1297.3 | 1297.3 | Lowest price fulfilling technical requirements
| El Galpón SRL | 14388.28
| Agro Luro SRL | 18692.97
Shopping PIRCMGS-88-CP: Purchase of Seeds and Fertilizers, Lot N°2, 23/03/2017 | Wekume Agro Servicios SRL. | 7750.13 | 7750.13 | Lowest price fulfilling technical requirements
| El Galpón SRL | 11625.19
| Agro Luro SRL | 10745.37
Shopping PIRCMGS-88-CP: Purchase of Seeds and Fertilizers, Lot N°3, 23/03/2017 | Wekume Agro Servicios SRL. | 6096.56 | 6096.56 | Lowest price fulfilling technical requirements
| El Galpón SRL | 5844.76
| Agro Luro SRL | 5606.28
Shopping PIRCMGS-88-CP: Purchase of Seeds and Fertilizers, Lot N°4, 23/03/2017 | Wekume Agro Servicios SRL. | 200.11 | 200.11 | Lowest price fulfilling technical requirements
| El Galpón SRL | 202.18
| Agro Luro SRL | 240.13
Shopping PIRCMGS-88-CP: Purchase of Seeds and Fertilizers, Lot N°5, 23/03/2017 | Wekume Agro Servicios SRL. | 949.62 | 949.62 | Lowest price fulfilling technical requirements
| El Galpón SRL | 1136.48
| Agro Luro SRL | 1035.21
Shopping PIRCMGS-88-CP: Purchase of Seeds and Fertilizers, Lot N°6, 23/03/2017 | Wekume Agro Servicios SRL. | 13192.06 | 13192.06 | Lowest price fulfilling technical requirements
| El Galpón SRL | 15549.27
| Agro Luro SRL | 15088.42
Shopping PIRCMGS-88-CP: Purchase of Seeds and Fertilizers, Lot N°7, 23/03/2017 | Wekume Agro Servicios SRL. | 9238.89 | 9238.89 | Lowest price fulfilling technical requirements
| El Galpón SRL | 11349.49
| Agro Luro SRL | 11814.13
Shopping PIRCMGS-88-CP: Purchase of Seeds and Fertilizers, Lot N°8, 23/03/2017 | Wekume Agro Servicios SRL. | 5705.38 | 5705.38 | Lowest price fulfilling technical requirements
| El Galpón SRL | 7064.72
| Agro Luro SRL | 6469.77
Shopping PIRCMGS-88-CP: Purchase of Seeds and Fertilizers, Lot N°9, 23/03/2017 | Wekume Agro Servicios SRL. | 3124.56 | 3124.56 | Lowest price fulfilling technical requirements
| El Galpón SRL | 4806.3
| Agro Luro SRL | 3749.47
Shopping PIRCMGS-88-CP: Purchase of Seeds and Fertilizers, Lot N°10, 23/03/2017 | Wekume Agro Servicios SRL. | 5489.42 | 5489.42 | Lowest price fulfilling technical requirements
| El Galpón SRL | 9067.34
| Agro Luro SRL | 6587.3
Shopping PIRCMGS-88-CP: Purchase of Seeds and Fertilizers, Lot N°11, 23/03/2017 | Wekume Agro Servicios SRL. | 7030.25 | 7030.25 | Lowest price fulfilling technical requirements
| El Galpón SRL | 13026.65
| Agro Luro SRL | 11377.98
Shopping PIRCMGS-88-CP: Purchase of Seeds and Fertilizers, Lot N°12, 23/03/2017 | Wekume Agro Servicios SRL. | 2291.34 | 2291.34 | Lowest price fulfilling technical requirements
| El Galpón SRL | 3905.7
| Agro Luro SRL | 2749.61
Shopping PIRCMGS-88-CP: Purchase of Seeds and Fertilizers, Lot N°13, 23/03/2017 | Wekume Agro Servicios SRL. | 3032.66 | 3032.66 | Lowest price fulfilling technical requirements
| El Galpón SRL | 4135.44
| Agro Luro SRL | 2966.49
Shopping PIRCMGS-88-CP: Purchase of Seeds and Fertilizers, Lot N°14, 23/03/2017 | Wekume Agro Servicios SRL. | 13325.32 | 13325.32 | Lowest price fulfilling technical requirements
| El Galpón SRL | 20321.11
| Agro Luro SRL | 18331.19
Shopping PIRCMGS-88-CP: Purchase of Seeds and Fertilizers, Lot N°15, 23/03/2017 | Wekume Agro Servicios SRL. | 5954.41 | 5954.41 | Lowest price fulfilling technical requirements
| El Galpón SRL | 8308.48
| Agro Luro SRL | 7145.29
Shopping PIRCMGS-88-CP: Purchase of Seeds and Fertilizers, Lot N°16, 23/03/2017 | Wekume Agro Servicios SRL. | 7615.06 | 7615.06 | Lowest price fulfilling technical requirements
| El Galpón SRL | 9854.78
| Agro Luro SRL | 9176.03
Shopping PIRCMGS-88-CP: Purchase of Seeds and Fertilizers, Lot N°17, 23/03/2017 | Wekume Agro Servicios SRL. | 716.15 | 716.15 | Lowest price fulfilling technical requirements
| El Galpón SRL | 727.34
| Agro Luro SRL | 859.38
Shopping PIRCMGS-88-CP: Purchase of Seeds and Fertilizers, Lot N°18, 23/03/2017 | Wekume Agro Servicios SRL. | 290.94 | 290.94 | Lowest price fulfilling technical requirements
| El Galpón SRL | 330.1
| Agro Luro SRL | 349.12
Shopping PIRCMGS-79-CP-B: Purchase of Chipper, Compressor, Post Hole Digger and Compost Remover, Lot N°1, 07/09/2016 | Agromax | 2222 |  | Lowest price fulfilling technical requirements
| Rumbo SRL | 581 | 510.91
| Molamaq | 745
| Casa Bernabé | 1026
Shopping PIRCMGS-79-CP-B: Purchase of Chipper, Compressor, Post Hole Digger and Compost Remover, Lot N°2, 07/09/2016 | Agromax | 3268 |  | Lowest price fulfilling technical requirements
| Rumbo SRL | 301
| Molamaq | 1503 | 1493.51
| Casa Bernabé | 1706
| Martín Seery | 1506
Shopping PIRCMGS-79-CP-B: Purchase of Chipper, Compressor, Post Hole Digger and Compost Remover, Lot N°3, 29/08/2016 | Samit | 34000 |  | Lowest price fulfilling technical requirements
| Rumbo SRL | 782
| DEISA | 12974 | 12643.31
Shopping PIRCMGS-79-CP-B: Purchase of Chipper, Compressor, Post Hole Digger and Compost Remover, Lot N°4, 29/08/2016 | Agromax | 15163 |  | Lowest price fulfilling technical requirements
| DEISA | 11699
| El Pato Maquinarias | 11663 | 11366.24
| Casa Bernabé | 16848
| Bio Nex | 25490
Shopping PIRCMGS-76-CP-B: Laboratory Equipment, Lot N°1, 26/08/2016 | Instrumentalia | 23904 |  | Lowest price fulfilling technical requirements
| Instrumentos del Sur S.A. | 12105 | 12041
| Proveeduría Médica | 13870
| Seasinglab | 22877
| Instrumental CIASA | 14560
Shopping PIRCMGS-76-CP-B: Laboratory Equipment, Lot N°2, 26/08/2016 | Instrumentalia | 8768 |  | Lowest price fulfilling technical requirements
| Instrumental Pasteur | 6419 | 6419
| Instrumentos del Sur S.A. | 9482
| Instrumentación Científica | 5558 | Does not satisfy technical evaluation
Shopping PIRCMGS-76-CP-B: Laboratory Equipment, Lot N°3, 26/08/2016 | Instrumentos del Sur S.A. | 7677 | 7737.16 | Lowest price fulfilling technical requirements
| Seasinglab | 10813
Shopping PIRCMGS-76-CP-B: Laboratory Equipment, Lot N°5, 30/08/2016 | Instrumentalia | 1039 | Does not satisfy technical evaluation | Lowest price fulfilling technical requirements
| Martinelli De Prieto | 973 | Does not satisfy technical evaluation
| Proveeduría Médica | 1162 | Does not satisfy technical evaluation
| Runco S.A. | 1901 | 1877
| Instrumental CIASA | 1292
Shopping PIRCMGS-76-CP-B: Laboratory Equipment, Lot N°6, 26/08/2016 | Instrumentalia | 3837 |  | Lowest price fulfilling technical requirements
| Instrumental Pasteur | 1688
| Instrumentos del Sur S.A. | 1843
| Instrumentación Científica | 552 | 552
| Proveeduría Médica | 4221
| Instrumental CIASA | 4481
Shopping PIRCMGS-76-CP-B: Laboratory Equipment, Lot N°7, 26/08/2016 | Instrumental Pasteur | 7274 |  | Lowest price fulfilling technical requirements
| Lasarte HNOS SRL | 5582 | 5545
| Seasinglab | 3418
Shopping PIRCMGS-76-CP-B: Laboratory Equipment, Lot N°9, 26/08/2016 | Instrumentalia | 5259 | 3787 | Lowest price fulfilling technical requirements
| Instrumentos del Sur S.A. | 3294
| Instrumentación Científica | 4990
Shopping PIRCMGS-76-CP-B: Laboratory Equipment, Lot N°10, 26/08/2016 | Instrumentalia | 14965 | 4056 | Lowest price fulfilling technical requirements
6867
| Instrumentos del Sur S.A. | 11354
| Instrumentación Científica | 10078
Shopping PIRCMGS-76-CP-B: Laboratory Equipment, Lot N°11, 26/08/2016 | Instrumental Pasteur | 7680 | Does not satisfy technical evaluation | Lowest price fulfilling technical requirements
| Instrumentación Científica | 5640 | Does not satisfy technical evaluation
| Seasinglab | 12237
| Sartorius | 8748.3 | 7675.47
Single Source PIRCMGS 83-CD: Purchase of Native Plants, Lot N°1, 17/11/2016 | Vivero Renovales | 2284.31 | 2284.31 | Direct contracting
Single Source PIRCMGS 83-CD: Purchase of Native Plants, Lot N°2, 17/11/2016 | Vivero Renovales | 388.89 | 388.89 | Direct contracting
Single Source PIRCMGS 83-CD: Purchase of Native Plants, Lot N°3, 17/11/2016 | Vivero Renovales | 1970.59 | 1970.59 | Direct contracting
Single Source PIRCMGS 83-CD: Purchase of Native Plants, Lot N°4, 17/11/2016 | Vivero Renovales | 4505.23 | 4505.23 | Direct contracting
(*) Exchange rate: US Dolar, seller, Banco Nación Divisas, at date of contract signature
Formulas:
Signature Date = +[Signature Date, row above]

## Risk Assesment
RISK ASSESMENT
IDENTIFIED RISKS
List all Risks identified in project preparation phase and what steps are being taken to mitigate them
Identified Risk | Current Status | Steps Taken to Mitigate Risk
Stakeholder Risk: The number of involved stakeholders (national and provincial government agencies and municipal authorities, farmers and communities, scientific institutions, and NGOs) may make swift decisionmaking difficult and slow down Project implementation. Incentives/direct benefits at community level might prove insufficient to convince people to adopt behavioral changes and new ways of cooperation in order to achieve longer-term objectives especially outside the key intervention zones. | This risk was rated as High at the PPP and continues the same. | Considering that the Project fundamentally builds upon participatory planning procedures, the number of involved stakeholders implies a great challenge for timely execution. Due to the participatory approach followed in the management of Project activities, similar to Community-Driven Development strategies, actions must be discussed, planned and carried out with stakeholders who don't usually count with prior training or experience on M&E procedures, environmental and social safeguards or procurement regulations; neither with introducing considerations of climate resilience in their productive activities. To deal with these challenges, the PIU has implemented a system aimed at pre-formatting the planning procedures, based on a site-specific template for planning the investments, including safeguards check-lists, indicators, planning schedules, and procurement guidelines. Besides of facilitating the dialogue with the beneficiaries and local counterparts, this system facilitates the progress assessment, exchange of experiences, continued evaluation and early implementation of corrective measures, as needed. It is worth mentioning that this procedure has also provided an important set of lessons learned that have been summarized by the PIU and shared with the stakeholders through workshops on project planning. The participatory process has contributed to local capacity development, which by itself is expected to constitute a lasting Project result (see Monitoring Arrangements in the Project Proposal/Assessment Document). Nonetheless, the approach has required great efforts in local capacity building through a number of workshops and field missions that sometimes challenge the intended execution schedules.
Capacity: Financial Management and Procurement may prove challenging for the PIU and certain administrative processes may delay Project execution. | This risk was rated Low and was increased to Moderate after the first year of Project implementation. | The fiduciary capacity risk has been addressed through enhanced inter and intra-institutional articulation. During the current reporting period, all the PIU staff has contributed to fiduciary management and the PIU has counted with fiduciary support from other areas of the MAyDS. In early May, 2017, the MAyDS contracted a new assistant for financial management with co-financing, and further help is being contracted for procurement.
Governance: Policy/political priorities across administrative levels (national, provincial, and municipal) could differ and/or change during Project implementation. Similarly, due to lack of synchronicity between political cycles and dynamics of ecosystem recovery, political counterparts may not prioritize Project-related cooperation. | This risk was rated Moderate and is now increased to High, particularly as the country has entered into a new electoral period. | Humid environmental conditions prevailed during three consecutive years since the Project started. A removal of a tax on wheat production was approved by the Government in 2016, which affected political commitment to the overall long-term Project objective. To counter this trend, activities on awareness-raising have been and are undertaken by the PIU jointly with the targeted municipal governments, as well as giving a new focus to local policies aimed at rangeland recovery and cattle-ranching support. Since the beginning of 2016, the PIU has worked on strenghtening the Project articulation with the key provincial governmental institutions, particularly OPDS, the Provincial Agency for Sustainable Development and the Ministry of Agroindustry. In May, 2016, this led to the participation of representatives of both provincial agencies in a training event organized by the Spanish Agency for International Development Cooperation (AECID) in Montevideo, and to organization of joint activities in the field. Since then, not only the PIU but also MAyDS have given efforts to involve OPDS more actively in Project activities and monitoring, yet with limited resuts. In December, 2016, the PIU/MAyDS organized a seminar on climate resilience with OPDS in La Plata, in which context high level meetings were hold between authorities of the two institutions. The highest municipal authorities of the involved counties also participated in the training activity developed in Montevideo, which resulted in the joint signature of an agreement for the creation of the Iberoamerican Network of Sustainable Development and Resilient Local Governments. Furthermore, the local governments started to implement plans on planting tree windbreaks on national, provincial and local routes, as well as plans on sustainable forage production.
Design: Changing climate conditions could affect the success of adaptation measures to be piloted during Project implementation; climate change may take a different form than anticipated (more or less severe and different in specific aspects such as impact on rainfall totals, regularity, intensity, etc., or to occur slowlier than anticipated). The chosen adaptive practices may prove less effective than anticipated in reducing impacts of climate variability and change to farmers; farmers might not wish to adopt the chosen adaptive practices due to lack of inputs, financing, or TA. | This risk was assessed as Moderate and is now increased to High. | The climate variability factor dominated by the El Niño Southern Oscillation (ENSO) is currently causing a humid cycle in the Project area, so the perception of risk and vulnerability that made key beneficiaries and stakeholders receptive to the Project proposals has weakened: the identified risk is currently materializing. One Project strategy to take advantage of the more humid conditions has been to support local public policies such as plans on sustainable forage production through the provision of seeds and other supplies and make cattle-rising (a more sustainable productive option for the Project area than the mainstream wheat production) more appealing to local farmers. The focus on participative Project planning is fortunately proving to be an adequate mean to mitigate this risk. Stakeholders in the field decide and plan the Project activities jointly with the PIU, so the actions to be implemented are based on strong ownership by the stakeholders. Considering that the Project works on a typically change-reluctant territory, participatory planning has been fundamental to ensure acceptance and continuity of the proposed measures. This approach implies a need for major investments in participatory planning workshops, mechanisms, field visits, etc. that all requiere time and sometimes delay expected implementation pace of the field activities. Since December, 2016 until the end of June, 2017, the Information and Early-Warning System (IEWS; SIAT for the Spanish acronym) developed and disseminated the first 3 quartely Meteorological and Agricultural Outlook Reports that provide key data about the 6 previous months, forecasts for the 3 next months, and recommendations for good practices to protect productive activities in the Project area. This contributes to critical awareness-rising amongst local farmers and other stakeholders and the subsequent risk reduction actions.
Social and Environmental: Moderate capacity for environmental and social management could negatively affect achievement of the PDO. The PIU has no earlier experience on environmental and social management under the World Bank safeguards. However, other divisions in the SAyDS (current MAyDS) have been implementing safeguard policies. | This Risk was rated Low, and continues the same. | The PIU staff was trained with WB specialists on environmental and social management under the Bank safeguards as the Project implementation got started. This led to the development of a checklist to be completed by local partners and controlled by specialized staff of the PIU/MAyDS when consolidating the guidelines for management of the specific intervention sites (SISs). Additionally, the PIU has received support from other WB related Projects executed by the Ministry of Agroindustry to take advantage of their experience on the implementation of social and environmental safeguard policies. Recently, the Project's mid-term review mission and field visits were used to review and discuss safeguards implementation in early April, 2017.
Delivery, Monitoring and Sustainability: In case the overall Project results proved insufficient to create expected behavioral changes across different stakeholder groups, or the planned communication and dissemination efforts would not succeed, the Project may fail to promote expected replications and scale-up operations. | This risk was rated Moderate and continues the same. | The Project design establishes participatory planning processes that sometimes delay expected execution pace in the field, yet work towards strengthening stakeholder commitment and engagement in the longer run. A monitoring process through indicators and local consultive workshops was developed during the first year of Project implementation as planned to help manage implementation processes and local queries. During the first 2 years of the Project implementation, different Sustainable Land Management practices and technologies have started implementation in the Specific Implementation Sites (SISs). To date, 2 SISs show visible results in improved soil structure and productivity, and the first steps to sistematize the respective case studies into recommendations of good practices will be taken in the months following the reporting period to disseminate and promote appropriation of the technologies and practices by other farmers, aiming to facilitate behavioural changes. On the other hand, promoting inter-institutional agreements e.g. on the IEWS and Forestry Plans aims to guarantee sustainability of Project guidelines which help, at the medium and long term, potential replication and scale-up efforts.
Critical Risks Affecting Progress (Not identified at project design)
Identify Risks with a 50% or > likelihood of affecting progress of project
Identified Risk | Current Status | Steps Taken to Mitigate Risk
The climate variability factor dominated by the El Niño Southern Oscillation (ENSO) is currently causing a humid cycle in the Project area, affecting the perception of risk and vulnerability that made key beneficiaries and stakeholders receptive to the Project Proposal. | 60% | The PIU is working to coordinate with broader county-policies linked to recovery of local ecosystems, such as plans on sustainable forage production and municipal road-side and urban afforestation. Said plans aim to widen the scale of the adaptation activities promoted by the Project, such as dune-fixation and wind-erosion control through afforestation. In line with this, awareness-raising and technical capacity building events have been undertaken jointly by the Project and municipal governments. Additionally, when designing Terms of Reference for studies on related issues, the PIU emphasizes cost-benefit analysis as well as the concept of opportunity cost of inaction in view of impacts of projected climate change in the Project area; concepts that have proved to draw farmers' attention.
Policies - Changes in the National Government at the end of 2015 resulted in the elimination of export taxes on wheat, making wheat production more attractive to farmers than it was at the time of the Project preparation. Productive alternatives to traditional wheat production promoted by the Project to prevent further soil erosion and thus contribution to increasing vulnerability to climate variability may lose attraction to farmers. | 60% | As mentioned above, the PIU is working to articulate with major county policies aimed at ecosystem recovery, such as the plans on sustainable forage production and afforestation in urban areas and road sides in order to widen the scale of the measures that increase climate resilience. First investments have been made to directly foster the local plans on sustainable forage production and to support development of nurseries for native tree species. Also, the initial investments were focused on specific practices that may show visible results in the short term in recovery of soil structure and productivity, aimed to motivate further farmers to produce forage that contributes to soil quality. To continue related work, the PIU/MAyDS has agreed with the local governments on the Project's participation in the major community fairs at the Project area to host stands and capacity-building events to boost shared work on related awareness-raising.
Recent budget cuts of key local counterparts, such as the Universities and the National Institute for Agricultural Technology (INTA), are causing unexpected needs that affect the local counterparts' structural ability to deliver agreed upon Project activities (e.g. lack of vehicles, fuel for machines, and salaries for technicians and other personnel). | 70% | The PIU is making extra efforts and using its potential for institutional networking to cope with the related challenges. For instance, some initiatives and activities are focused on the pilot SISs, different initiatives developed by the key partners specially in training are supported with Project resources to help them gain major results. The Project has also invested in increasing capacity of INTA's Soil Laboratory through which farmers get laboratory services in adequate conditions.
Institutional changes in OPDS and the Ministry of Agroindustry may impose limitations to future activities, in particuar as their overall involvement in Project activities has been limited during 2016 and 2017. | 70% | The PIU has developed direct and strong relationships with the targeted municipal governments in order to overcome the referred lack of active participation by the key provincial institutions. Since OPDS has not counted with any local office in the field or specialized staff in the region during the Project implementation period, the PIU has opted creating strong direct links with the municipal governments. Additionally, high-level meetings between representatives of the MAyDS and OPDS have been and are being conducted in order to strenghten the involvement of the provincial authorities in strategic Project activities.
Risk Measures: Were there any risk mitigation measures employed during the current reporting period? If so, were risks reduced? If not, why were these risks not reduced?
Add any comments relevant to risk mitigation (word limit = 500)
Diverse risk mitigation measures have been employed during the reporting period as described above. For example, strong involvement by the local authorities has been fostered to continue the momentum gained through their participation in the Climate Change Adaptation Training Program hold in Montevideo in May 2016, and they have continued motivated and engaged strongly in a number of Project activities after the signature of an Agreement for the creation of the Network for Iberoamerican Sustainable Development and Resilient Local Governments. Additionally, certain investments in the SISs, e.g. in seeds and farm equipment like paratil have been accelerated to keep farmers and other local stakeholders interested and engaged. This has been complemented with a stronger presence of the PIU and MAyDS in the Project intervention area. Meetings with the World Bank Task Team have also became more frequent during 2017 to monitor progress, anticipate issues and find solutions to implementation bottlenecks, including in fiduciary aspects. Further, innovative agreements involving additional federal organizations, such as the Ministry of Social Development and the National Roads Agency, as well as the involvement of the National Meteorological Service in the IEWS, have been promoted in order to guarantee sustainability of Project initiatives and foster the involvement of the local governments.

## Rating
RATING ON IMPLEMENTATION PROGRESS
For rating definitions please see bottom of page.
| Progress on Key Milestones |  | Expected Progress |  | Progress to Date | Rating
Project Manager/Coordinator: | PIU capacity and the overall Project governance structure/institutional arrangements and capacity |  | The Project governance structure/institutional arrangements are functional and the capacity sufficient to achieve the expected results. |  | During Project preparation, the WB carried out an assessment of the executing agency's fiduciary capacity that at the time was concentrated in a unit called "Program of Projects with External Financing, PPFE". Further, the overall organizational structure for implementing the Project and the interaction between the Project’s staff responsible for procurement, financial management (FM) and other areas and actors were reviewed. The PPFE was deemed satisfactorily equipped, staffed and experienced and a detailed action plan was prepared to address the related risks. However, once the Project became effective after a long effectiveness delay, the PPFE was no longer in place and the PIU needed to assume full responsibility of the Project's fiduciary aspects. This implied an important learning curve that added to the initial implementation delays. Currently, the thus far experience gained and lessons learnt, together with high motivation of the PIU staff and close collaboration with the WB Task Team is allowing satisfactory execution progress. OPDS, the Provincial Agency for Sustainable Development, was expected to advice on the main Project intervention lines and provide strategic and political leadership to the Project to secure effective coordination among environmental authorities at national and provincial level. The local staff to be hired to work on the Project in the intervention area were to be hosted in a small OPDS office that was in place during Project preparation, but was dismantled soon after the implementation started, due to political reasons, staff turnover and overall low capacity of OPDS. As a consequence, OPDS never became in charge of the local institutional relations or supervision of the field activities; it only participated in the major Project events in the territory. The situation was addressed during the Project mid-term review, yet changes amongst the OPDS authorities only recently opened a window of opportunity to discuss the situation and agree upon the way forward between MAyDS and OPDS overall and OPDS and the Project in particular. In all, the institutional arrangements used to implement the Project have resulted different than those originally intended and assessed. After the first disbursement of the Grant proceeds, the PIU was established in April 2015 under the MAyDS Directorate of Soil Conservation and it started to catch up with the implementation schedule. Since early 2016, after initial problems due to lack of experience and staff turnover, the PIU has achieved major advance in Project implementation. Today, it counts with technical, organizational and fiduciary capacity and is supported by MAyDS staff as necessary. Heavy work load implied by procurement and related logistics in the field remains the main challenge for the PIU, and the mid-term review agreed upon on contracting of two new fiduciary assistants, one with co-financing by MAyDS. The PIU has developed a solid working relation with the targeted municipal actors and coordinates with other related national and provincial institutions and programs with satisfactory results. By mid 2017, the thus far Project execution was audited by AGN, the National Supreme Audit Institution with satisfactory results. Despite, and partly due to the challenges faced with OPDS, the PIU/MAyDS has established excellent working relations with a number of key institutions at local, provincial and national level. In particular, fluent articulation is on-going with the National Meteorological Service, Southern National University, CERZOS and INTA in developing IEWS reports and related complementary work. There has also been good advance in articulating amongst other national and local governmental organizations, as in the case of innovative collaboration achieved with the Ministry of Social Development at the national level, the National Road Agency and the municipal government of Villarino in order to promote tree barriers along national roads to prevent wind erosion. | MS
| Execution of the Project activities according to the operational framework presented to the AF and the Annual Operating Plan |  | The overall implementation pace and results of the key indicators are on track |  | At the level of the PDO, the following outcomes have been achieved: PDO Indicator 1: Five (5) institutions reflect institution-specific adaptation needs in their budget/resources allocations to increase their capacity to address climate-related challenges: (i) Municipality of Villarino has created a Municipal Environmental Agency, is co-implementing with the National Ministry of Social Development and Roads Agency a road-side afforestation plan aimed at reducing wind erosion, and established a Municipal Nature Reserve (protected area); (ii) Municipality of Puan has allocated resources to strengthen the Bordenave tree nursery and established a Municipal Nature Reserve (protected area); (iii) Municipality of Patagones has re-launched a Municipal Plan on Sustainable Forage Production that aims at fixing soil and reducing wind erosion through increased topsoil coverage; (iv) National Ministry of Social Development is co-implementing with the Municipality of Villarino and National Roads Agency a road-side afforestation plan aimed at reducing wind erosion; and (v) National Roads Agency is co-implementing with the Municipality of Villarino and National Ministry of Social Development a road-side afforestation plan aimed at reducing wind erosion. This indicator aligns to the PDO outcome (ii) on increased adaptive capacity of key local institutions. The main part of the funding that has allowed the above results came from Component 2, yet taken the high-level of the result in terms of demonstrating changes at institutional level, all Project expenditure thus far can be claimed to have contributed to these results. The targeted result at the end of the Project implementation is 10 institutions. Beyond the achieved result, the work remaining to add 4 further institutions is well advanced, taken SMN, UNS, CERZOS-CONICET, and INTA that contribute to the IEWS are soon to formalize their commitment in its continued operation by signing the respective interinstitutional agreements. PDO Indicator 2: Two (2) Specific Intervention Sites (SISs) improved the soil structure and productivity. Nine (9) SISs maintained the productive agro-ecosystems to withstand conditions resulting from climate variability and change (2 in irrigation area; 4 in arid area; and in 3 research sites). For 9 of these SISs, a baseline has been developed to determine the soil conservation status and tendencies under specific management conditions, considering index-based FAO-LADA methods and field controls based on soil conservation techniques. The indicator aligns to the PDO outcome (i) on contribution to reduction of climate and man-made vulnerability of the agroecosystems in the Southwest of the Buenos Aires Province. The main funding that has allowed the above results came from Component 2, yet expenditures under Component 3 on implementing the participatory approach and knowledge management and capacity building activities have naturally contributed to the same. The indicator bases on a proxy index with hypothetical values from 0 to 24, assuming a total of 12 SISs as planned during the Project preparation. In said index, each SIS where the status of the agroecosystem improves adds 2 points; a SIS where it is maintained adds 1 point; and a SIS where the agroecosystem deteriorates adds 0 point. The targeted result at the end of the Project implementation is 10. At the MTR, two years after the Project Inception Workshop, the indicator value was 13, yet as clarified in the MTR Report, said value bases on visual observations by responsible PIU/MAyDS staff with relevant technical profile, given the follow-up study on the baseline results will be conducted at the end of 2018. PDO Indicator 3: A prototype Information and Early Warning System on climate change and desertification (IEWS) has been developed jointly with local research and extension institutions and the National Meteorological Service (SMN) to generate and disseminate relevant (Project-related) information on threats and hazards to farmers and other stakeholders on a timely basis. The first three (3) quarterly reports that include agro-meteorological information, productive forecasts and risk assessment on fires and wind-erosion, as well as land management and crop and animal management recommendations were compiled and disseminated during the reporting period through rural radios and local institutions, particularly the targeted Municipalities and the National Institute of Agricultural Technology (INTA), relevant public offices and websites, as well as social media, e.g. WhatsApp groups. The institutional arrangements (legal agreement and operational manual) have been developed and submitted for consideration and signature by the authorities of the four (4) institutions to sustain the IEWS operation beyond the Project closure. The indicator aligns to all the PDO outcomes at some level as farmers that adopt improved agricultural technology contribute to all of them. Directly, it aligns to the PDO outcomes (iii) on increased adaptive capacity of key local actors and (iv) on piloted climate resilient and sustainable land management practices. The funding that has allowed the above results came from Sub-Component 1.1. The indicator is a simple Yes/No indicator, the current result being “Yes”. Further on the results achieved until June 30, 2017 to justify the overall Satisfactory project rating, please see the attached MTR Report. | S
| Progress on Project activities that pave the way for sustainability, replication and scale-up of key Project activities |  | Progress achieved in implementing Component 4: Developing a Sustainability Strategy meets expectations at the current implementation stage |  | The activities conducted thus far include five (5) inter-institutional work fronts on policies/plans that aim to develop/replicate/scale-up results that transcend the Project implementation period: 1) The IEWS that currently focuses on improving the presentation and dissemination of the quartely Meteorological and Agricultural Outlook Reports and consolidating the institutional set-up (legal agreement and operational manual) by the four (4) institutions that constitute it; 2) Villarino Reforestation Plan that counts with innovative collaboration with the National Ministry of Social Development, National Roads Agency and MAyDS. The plan will scale-up the pilot supported by MAyDS, aimed at strengthening the local tree nursery in the short term, and reducing wind erosion in the long term. This example is expected to be replicated in other regions in Argentina; 3) Municipal plans on sustainable forage production to support recovery of degraded soil and natural pastures through use of perennial and nitrogen fixing species, in all three Municipalities (Patagones Villarino and Puan); 4) A preliminary dialogue within the Governmental Committee on Climate Change (GCCC), including elaboration of national adaptation plans, particularly on agroindustry, as well as sector plans and funding proposals for the Nationally Determined Contributions (NDCs); and 5) International funding, where at least two (2) projects have been developed and are in the pipeline for approval; one on sustainable land management in the Province of Buenos Aires that bases on project experience, and a GEF Project “Mainstreaming biodiversity conservation and sustainable land management (SLM) into development planning: making Environmental Land Use Planning (ELUP) operational in Argentina”. In line with the above description, activities have been developed jointly in partnership with different local and international institutions, aimed at improving local, provincial and national level technical and institutional capacity to sustain, replicate and scale-up the Project outcomes. The Project has also developed abundant communication materials; leaflets, pamphlets, posters, etc., and different Project activities have enjoyed good media coverage at the local and provincial level. As natural to the current implemenation stage, production of guidance material on key pieces of policy framework, piloted adaptation practices, and potential sources of financing to support continued efforts to promote climate resilience at different administrative levels to disseminate Project results has still been limited. A positive exception is a document that systematizes the municipal plans for sustainable forage production that has been prepared. | S
[5 empty] | Overall Rating | S
Please Provide the Name and Contact information of person(s) reponsible for completeling the Rating section
| Name: | Joaquin Etorena and Tuuli Bernardini
| Email: | jetorena@ambiente.gob.ar, tbernardini@worldbank.org
Please justify your rating. Outline the positive and negative progress made by the project since it started. Provide specific recommendations for next steps. . (word limit=500)
During the reporting period, the Project execution pace and the progress achieved is deemed overall satisfactory as presented above. After the completion of the initial participatory planning phase that involved key stakeholders and counterparts through consultative processes and joint planning procedures, execution of the planned field activities started and are advancing well. Together with the local stakeholders, the PIU has been able to address a number of particularly procurement related challenges. Some processes such as procurement of meteorological monitoring stations suffered a major delay, yet that was due to careful inter-institutional preparatory work that was invested in preparing the technical specifications, including participatory analysis and planning to determine the stations' optimal locations. For example in case of the IEWS, implementation first focused on convening the necessary partners and getting the system up and running; on showing results, and only then on confirming the supporting operational procedures and legal documents. Further, the Project has achieved innovative inter-institutional collaboration beyond the originally planned activities, particularly in terms of creation of a green employement program that plants wind barriers along different types of roads in the Project area, enjoying of keen interest and commitment by the National Ministry of Social Development. Overall, progress in the main outcomes included in the PDO is starting to reflect into the results indicators, yet the Project's results framework requires restructuring to improve the overall quality of the indicators and focus the Project monitoring on a reasonable number of key results.
| Progress on Key Milestones |  | Expected Progress |  | Progress to Date | Rating
Implementing Agency | Increase the development impact of the Project through improved results |  | Add value to Project execution by providing managerial, technical, fiduciary and operational assistance on aspects that could yield improved results at different levels. |  | As a development agency, the World Bank has an invested interest in assisting MAyDS as the Executing Agency in achieving the PDO on sustainable basis and maximizing the Project's development impact. For this purpose, the WB provides managerial, technical, fiduciary and operational assistance to improve Project results at different levels and across relevant sectors. The WB reviews the key Project documents such Annual Operational Plans, terms of reference, tecnical specifications, procurement plan and progress and fiduciary reports and provides strategic guidance and technical inputs to strenghten quality and reflect lessons learnt from similar operations/tasks across relevant WB portfolio. The WB has emphasized the importance of monitoring, reporting and disseminating of results, during the reporting period mainly across the Project beneficiaries and towards relevant WB projects under preparation, particularly the Argentina Integrated Management of Agricultural Risk project (P162316), as well as continued learning. The WB supports the PIU/MAyDS to provide reliable, objective, timely, and useful information on Project activities to guide their adaptive management. In line with this, the WB reviews the evidence gathered by the PIU to support the reported progress on achived results. It identifies and shares information on opportunities for relevant knowledge-sharing based on international experience. For example, the WB invited the PIU/MAyDS and other key Project stakeholders to remotely participate in a workshop on Drought Management, organized jointly by the WB and NASA, and shared a WB report on best practices in implementing Hazard Early Warning Systems. Throughout the Project implementation phase, the WB has offered MAyDS different opportunities to engage in sector dialogues that could lead to strengthening and/or scale-up of Project impacts and efficiency. For example, the WB has facilitated contact with relevant initiatives by the private sector and civil society, as well as collaboration with the National Ministry of Agroindustry that is preparing the referred new operation on integrated management of agricultural risk. During the reporting period, the WB carried out two implementation support missions and one technical mission, including two rounds of extensive field visits to evaluate Project execution status and performance in August 2016 and April 2017. The WB also carried our an internal mid-term review of the Project, including a peer review process by colleagues from other WB areas with relevant experience and know-how in the key topics for the Project success. Said review proved a valuable exercise that initiated continued technical exchange thereafter. In these occasions, the WB assessed the overall Project and PIU performance with particular attention to adequacy of the implementation arrangements. Additionally, the WB has provided implementation support on a continuous basis through technical meetings and continuous and flexible contact particularly since February 2017 as the task team leader changed from a HQ based to a Country Office based staff. Particularly, the WB and PIU/MAyDS discuss and address reasons for observed delays/deviations to identify the implied internal and external factors and the implications down the road in terms of the Project’s ability to meet the PDO. | S
| Increase the development impact of the Project through efficient execution and risk management |  | Identify, address and resolve implementation issues in a timely and efficiently manner. Achieve the expected results or adjust expectations that prove overly ambitious. Ensure smooth execution of resources and manage risks so that they don't hamper Project execution nor cause reputational risk to any stakeholder. |  | The WB focuses on early risk identification, including support to secure document and process quality in terms of procurement. In line with continued risk assessment, the WB reviews the relevance of the risk management measures and monitors and guides their implementation. During the reporting period, it has provided fiduciary support and oversight on a continuous basis, and particularly during the two implementation support missions. Including the internal mid-term review process prior to the April 2017 mid-term mission, the WB participated closely in assessing the Project's minor restructuring needs that focus on improving the results framework, which includes too many and a couple of not measurable indicators. On the other hand, the WB supported the PIU/MAyDS to revise and update the role of the OPDS in the Project design, including mediation to facilitate the inter-institutional dialogue. The MS rating in terms of timely and efficient implementation reflects the fact that the restructuring started to prove a longer process than expected, due to a myriad of factors. Overall, the WB has secured the Project's continued capacity to 1) implement the procurement plan; 2) follow the use of funds and present the expenditures to provide assurance that the donation proceeds are being used for their intended purposes, including the WB reviews to validate the eligibility of the activities proposed for Project financing and verify their economic justification. The WB reviews the terms of reference and technical specifications for contracts and provides no objections as determined in the procurement plan; and 3) record the transactions and balances and prepare reliable financial statements. The WB monitors procurement implementation and disbursements and recommends ways to ensure their smooth progress in line with the planned and periodically adjusted schedules. The WB prompts timely reception of and reviews the unaudited interim financial reports and the reports of the external audit. The WB also provides environmental and social safeguards support and oversight. | MS
| Increase the development impact of the Project through increased institutional development of the Executing Agency |  | Increase the PIU/MAyDS capacity to manage the Project based on international standards. |  | The WB has established a strong and frank partnerships with the PIU/MAyDS staff and other relevant stakeholders, using efficient communication through different channels for the dialogue to deal with Project implementation issues on a continuous basis, trying to expedite the overall Project execution. Consequently, the prevailing working environment allows prompt identification and addressing of issues. The WB provides technical support to the PIU/MAyDS to strengthen its capacity to manage and deliver Project activities following agreed technical specifications and quality standards and to address technical issues that arise during implementation. The WB takes advantage of its overall project portfolio not only with MAyDS but also with other institutions at national and provincial level to convey inter-institutional and cross-sectoral collaboration to harness synergies between various projects working on mutually relevant fronts, including with the National Ministry of Agroindustry and in terms of strengthening the meteorological observation network in the Province of Buenos Aires. | MS
| Ensure compliance with the Project's Legal Agreements |  | Achieve the Project development objectives in conformity with the Project’s Legal Agreements. |  | The WB monitors the Project implementation to achieve the PDO in conformity with the Project’s Legal Agreements and provides related support on an as-needed basis to secure due diligence e.g. in terms of compliance with the technical and financial reporting requirements, implementation of procurement rules, environmental and social risk management, and independent financial audit. | S
[5 empty] | Overall Rating | MS
Please Provide the Name and Contact information of person(s) reponsible for completeling the Rating section
| Name: | Tuuli Bernardini and Pablo Herrera
| Email: | tbernardini@worldbank.org, pherrera@worldbank.org
| Progress on Key Milestones |  | Expected Progress |  | Progress to Date | Rating
Other
Overall Rating
Please Provide the Name and Contact information of person(s) reponsible for completeling the Rating section
Name:
Email:
| Please justify your rating and address the following points: 1. Indicate trends, both positive and negative, in achievement of outcomes as per the project indicators. 2. Detail critical risks that have affected progress. 3. Outline response to MTR undertaken this reporting period. 4. Outline action plan to address projects with a rating of HU, U or MU. Please keep your input to 1200 words |  | The progress on key milestones has been rated MS-S basically because the operational and technical support provided by the WB has resulted in better Project execution and partial achievement of the result, in most cases in line with the targets expected for the Project year 2. The overall trend toward the achievement of the expected outcomes is positive, yet some of them fall short due the initial delays in starting the Project execution. The main identified risks have been mitigated to prevent major impacts on the Project execution, which improvement has reflected in the increase of the disbursement of the grant proceeds. Within the framework of the Project mid-term review, the WB pushed the PCU/MAyDS to address the issue of limited collaboration by OPDS, the Provincial Agency for Sustainable Development that was to assume a key role in Project execution at the provincial and local level. The issue has been mostly political, and once the PCU/MAyDS got the Project up and running through close collaboration with the key targeted institutions and the three beneficiary municipalities, a half-silent status quo with OPDS was deemed simply a fact of the prevailing institutional set-up. Despite the fact that the Project execution proceeded well also without active participation by OPDS, the situation caused tensions and simply didn't reflect the natural state of the institutional agendas. The main concern on simply leaving OPDS aside was deemed controversial to sustainability and scalability of key Project results. The Project mid-term review focused on analyzing the results framework as some of the overall too numerous indicators included in the same have resulted ill-formulated or simply too complex to measure, and some of the result targets too ambitious. The proposed adjustments in the Project's results framework are presented in the report of the mid-term evaluation. Overall, completing the Adaptation Fund requiered mid-term evaluation and the subsequent restructuring proposal have suffered an important delay for a myriad of reasons. The main challenges have been first closing of the necessary agreements on the restructuring substance between the participating Government agencies and mainly OPDS, where the responsible authorities changed in the middle of the discussions, and the work load imposed by two and differing sets of requirements and procedures for mid-term review/evaluation and restructuring.
Rating Definitions
|  |  | Highly Satisfactory (HS) | Project actions/activities planned for current reporting period are progressing on track or exceeding expectations to acheive all major outcomes/outputs for given reporting period, without major shortcomings. The project can be presented as “good practice”.
|  |  | Satisfactory (S) | Project actions/activities planned for current reporting period are progressing on track to achieve most of its major outcomes/outputs with only minor shortcomings.
|  |  | Marginally Satisfactory (MS) | Project actions/activities planned for current reporting period are progressing on track to achieve most major relevant outcomes/outputs, but with either significant shortcomings or modest overall relevance.
|  |  | Marginally Unsatisfactory (MU) | Project actions/activities planned for current reporting period are not progressing on track to achieve major outcomes/outputs with major shortcomings or is expected to achieve only some of its major outcomes/outputs.
|  |  | Unsatisfactory (U) | Project actions/activities planned for current reporting period are not progressing on track to achieve most of its major outcomes/outputs.
|  |  | Highly Unsatisfactory (U) | Project actions/activities planned for current reporting period are not on track and shows that it is failing to achieve, and is not expected to achieve, any of its outcomes/outputs.

## Project Indicators
PROJECT Indicators
Please provide all indicators being tracked for the project as outlined in the project document
Type of Indicator (indicators towards Objectives, Outcomes, etc…) |  |  |  |  | Comments
Type of Indicator | Indicator | Baseline | Progress since inception (30/06/2017) | Target for Project End (31/12/2018)
Outcome | Outcome 1 Targeted institutions that reflect institution-specific adaptation needs in their budget allocations to increase their capacity to address climate-related challenges (Number, Custom) | 0 | 5 | 10 | The five reported institutions are: 1. Municipality of Villarino has created a Municipal Environmental Agency, is co-implementing with the National Ministry of Social Development and Roads Agency a road-side afforestation plan aimed at reducing wind erosion, and established a Municipal Nature Reserve (protected area); 2. Municipality of Puan has allocated resources to strengthen the Bordenave tree nursery and established a Municipal Nature Reserve (protected area); 3. Municipality of Patagones has re-launched a Municipal Forage Production Plan that aims at fixing soil and reducing wind erosion through increased topsoil coverage; 4. National Ministry of Social Development is co-implementing with the Municipality of Villarino and National Roads Agency a road-side afforestation plan aimed at reducing wind erosion; and 5. National Roads Agency is co-implementing with the Municipality of Villarino and National Ministry of Social Development a road-side afforestation plan aimed at reducing wind erosion.
Outcome | Outcome 2 Productive agroecosystems in the pilot sites maintained or improved to withstand conditions resulting from climate variability and change (Number, Custom) | 0 | 13 | 10 | 2 Specific Intervention Sites (SISs) were improved to withstand conditions imposed by climate variability. They are located in Patagones and their improvement is related to the use of an equipment provided by the Project, called paratill, which lifts and bends subsoil to remove hardpans. It gently lifts the soil, allowing it to fracture along its natural planes of weakness and then settle back again. This loosening improves water infiltration and drainage, encourages root development, and allows for deeper fertilizer placement. The gentle lifting action leaves topsoil and subsoil layers intact, minimizes clods, and leaves valuable residue on the surface. 9 SISs were maintained to withstand conditions resulting from climate variability: - 2 of them are located in irrigated areas in Patagones and Villarino; - 4 are located in non-irrigated areas; 2 in Patagones, 1 in Puan, and 1 in Villarino; - 3 SISs are located in experimental fields; an agroecologic field in Bordenave, Campo Naposta of the National Southern University (UNS), and experimental plots managed by the Center of Renewable Natural Resources of the Semi-Arid Zone (CERZOS) in the same Campo Naposta.
Outcome | Outcome 3 Relevant threat and hazard information generated and disseminated to farmers and other stakeholders on a timely basis (Yes/No, Custom) | NO | YES | YES | The consortium of institutions that has constituted the basic structure of the Information and Early-Warning System (IEWS, locally known as "SIAT"), aimed at reducing climate-related vulnerability, during the reporting period produced, disclosed and disseminated 3 quarterly Meteorological and Agricultural Outlook Reports (Dec 2016 and Feb and June 2017) in the Project area, which includes agro-meteorological information, agricultural production forecasts, and risks related information on fires and wind erosion.
Output | Output 1: Targeted clients satisfied with agricultural services (percentage) (Percentage, Core) | 0% | 0% | 50% | The surveys to determine the degree of satisfaction among targeted beneficiaries that receive agricultural services are expected to be conducted after June 2017. The PIU has suggested that, in this context, "agricultural services" refers to the provision of the quarterly IEWS reports. Further, the PIU suggested that "percentage of targeted clients" means the percentage of the 440 people that were expected to participate in the 10 SISs (at a rate of 10 producers by SIS and an average of 4 family members by each producer, except the two experimental sites). Of these, 80% (352) are estimated to be male, and 20% (88) female. The satisfaction target was set at 50% (176 and 44, respectively).
| MALE (number) (Number, Core Supplement) | 0 | 0 | 176
| FEMALE (number) (Number, Core Supplement) | 0 | 0 | 44
Output | Output 2: Targeted clients- MALE (number) (Number, Core Supplement) | 0 | 154 | 352 | The accumulated number of male producers who have received (through WhatsApp), at least one of the IEWS reports produced by the responsible consortium is 154.
| Targeted clients- FEMALE (number) (Number, Core Supplement) | 0 | 19 | 88 | The accumulated number of female producers who have received (through WhatsApp), at least one of the IEWS reports produced by the responsible consortium 19.
Output | Output 3: Targeted local public employees trained (Percentage, Custom) | 0% | 58% | 60%
| MALE (percentage of the total males+females) (Percentage, Custom Breakdown) | 0% | 86% | NS | Out of the targeted public employees trained by the Project thus far, 86% are male.
| FEMALE (percentage of the total males+females) (Percentage, Custom Breakdown) | 0% | 14% | NS | Out of the targeted public employees trained by the Project thus far, 14% are female.
Output | Output 4: IEWS developed/operational through inter-institutional cooperation (Yes/No, Custom) | N | Y | Y | A prototype Information and Early Warning System on climate change and desertification (IEWS) has been developed jointly with local research and extension institutions (INTA / UNS / CERZOS / SMN) to generate and disseminate relevant Project-related information on threats and hazards to producers and other stakeholders on a timely basis. During the reporting period, the IEWS generated and disseminated the three first quarterly reports, including agro-meteorological information, agriculture production forecasts and risk related information on fires and wind erosion. The presentation of the reports was subject to improvement report by report, and they were disseminated through equally evolving channels; rural radios, local institutions (Municipalities, National Institute on Agricultural Technology, etc.) relevant public offices and websites, and social media (e.g. WhatsApp groups). Parallel to improving the operational aspects of the IEWS, the respective institutional arrangements have been discussed and established in paper to sustain the IEWS beyond the Project closure. A legal agreement and the operational arrangements have been drafted and submitted for consideration and signature of the authorities of the involved institutions. Related collaboration arrangements have also been broadened to include further agencies, e.g. CONAE, the national space agency.
Output | Output 5: Active participation of at least the key institutions of the Observatory (Yes/No, Custom) | N | N | Y | Based on the Project mid-term review, it was decided the respective output on a "Regional Consultative Observatory of Public Policies on Climate Change and Desertification", as originally foreseen, will be dropped out from the Project design: the consultancy that analyzed the optimal operational set-up of both the IEWS as the Observatory, concluded the relevant local institutions do not present the necessary interest/commitment for the Project to engage in establishing it. Overall, the Project has many demanding work fronts; it is considered necessary the efforts are concentrated as strategically and efficiently as possible.
Output | Output 6: Consulted people who report on modification(s) in their Project-related practices (Percentage, Custom) | 0% | 0% | 60% | During the Project mid-term review, the PIU suggested that one of the Project-related practices that could be changed by the targeted producers because of their participation in the Project would be the regular access to the information disseminated by the IEWS. However, the surveys needed to assess the evolution of this indicator have not been conducted yet, as the PIU has faced many difficulties when it comes to interpreting and using this indicator in a meaningful way. Per the WB Project Appraisal Document (PAD), the population targeted by this indicator refers to the 80,000 inhabitants of the three Municipalities where the Project works directly (Patagones, Puan and Villarino), most of which live in urban areas. However, the Project mostly works with rural producers from the vulnerable agro-ecosystems, which represent only a minor fraction (and probably not statistically representative) of the total population. Additionally, the PIU considers that measurable behavioral changes at that scale would require stronger inputs and longer implementation period than those considered under this Project. For these reasons, the PIU considers the indicator is not properly suited for this Project and proposed to restructure/dismiss it.
| MALE (percentage of total: male+female) (Percentage, Custom Breakdown) | 0% | 0% | NS
| FEMALE (percentage of total: male+female) (Percentage, Custom Breakdown) | 0% | 0% | NS
Output | Output 7: Client days of training provided (number) (Number, Core) | 0 | 41 | 64 | The days of client training provided until June 30, 2017 by the Project reflect 35 training days delivered on various Project-related topics e.g. on participatory project planning, incorporation of climate considerations in productive activities and early-warning systems. Further, the following events are counted: (i) a workshop on Economics of Land Degradation and spatial analysis conducted, as in-kind co-financing committed by MAyDS, through joint action of the PIU, IFPRI and the National University of Arturo Jauretche in Aug, 2014 in Buenos Aires; and the following training organized in Sept, 2015 in Medanos: (ii) a field visit and workshop with 35 farmers; (iii) a seminar on environmental law and relevant SIS-specific legislation on protection of native forest for municipal staff from the local Secretariats of Production and Economic Development; (iv) a workshop on M&E methods and validation of Project indicators; (v) a workshop on results-oriented project planning focusing on the SISs, conducted with participants from the key stakeholders and partners of the intervention area; and (vi) a two-day workshop on spatial evaluation of evapotranspiration, organized by the WB and NASA, with participation by key IEWS stakeholders in Sept, 2015 in Buenos Aires.
| FEMALE (number) (Number, Core Breakdown) | 0 | 34 | NS
Output | Output 8: Teacher training institutes within SWBA that cooperate with the Project and offer related training (Number, Custom) | 0 | 4 | 10 | The educative institutions that collaborate with the Project are the Southern National University (UNS), Agrarian School EESA N°1 "Carlos Spegazzini”, Agrarian School of Patagones, and National Technological University. Further, the General Directorate of Schools, District of Southwest of the Ministry of Education of the Province of Buenos Aires facilitates the Project’s provision of educative material to schools within the targeted Municipalities. During the Project mid-term review, the PIU/MAyDS suggested to revise/remove this indicator so as to focus Project implementation to more strategic areas.
Output | Output 9: Cultural and socio-productive activities carried out in the Project zone jointly with the municipal governments (fairs, exhibitions, etc.) (Number, Custom) | 0 | 8 | 28 | During the reporting period, the Project participated in Expo Villa Iris in Puan, National Garlic Festival in Villarino, and Festival of Patagonian Sovereignty in Patagones. Further, it organized a workshop on the National Forest Law and protection of native forests for municipal agents in Patagones.
Output | Output 10: FEMALES participating in cultural and socio-productive activities carried out in the Project zone jointly with the municipal governments (fairs, exhibitions, etc.) (Number, Custom Breakdown) | 0 | 19 | NS | The number of females corresponds to the four events where the Project participated during the current reporting period; sex-aggregation of the people that visited the Project booth during the earlier public events with loads of people was not conducted/registered.
| MALES participating in cultural and socio-productive activities carried out in the Project zone jointly with the municipal governments (fairs, exhibitions, etc.) (Number, Custom Breakdown) | 0 | 85 | NS | The number of males corresponds to the four events where the Project participated during the current reporting period; sex-aggregation of the people that visited the Project booth during the earlier public events with loads of people was not conducted/registered.
Output | Output 11: Clients who have adopted an improved agr. technology promoted by the project (Number, Core) | 0 | 1632 | 1400 | 408 producers participate in the implementation of the SISs and the municipal sustainable forage production and reforestation plans. Each producer represents an average family of 4 persons. "Improved agricultural technology adoption" is understood in terms of the "adoption" involving a process that comprises four stages: 1) Commitment: verified through the application letter of each ISI. 2) Implementation: verified in the field by means of physical investments, associated with the Project activities. 3) Management and evaluation: verified through interviews with producers and field visit. 4) Adoption: verified through interviews with producers and field visit. Within the scope of the Project implementation period, it needs to be noted that that monitoring the number of people who reach the referred stages will only be feasible in terms of the two first stages of the process. There will be a chance to see a trend toward potential adoption of the promoted technologies through verification related with the implementation and management stages, yet the remaining implementation period will be too short to verify reaching of the final adoption stage.
| FEMALE (Number, Core Breakdown) | 0 | 408 | 280 | 408 producers participate in the implementation of the SISs and the municipal sustainable forage production and reforestation plans. 39 of them are women, yet each producer family is considered to represent one woman.
Output | Output 12: Adaptation/sustainable land management (SLM) technologies identified/verified through local participatory consultations under the Project framework that are demonstrated within the GIAs (Number, Custom) | 0 | 41 IDENTIFIED | 12
|  |  | 12 IMPLEMENTED | 9 | The list of the implemented technologies: 1) Loosening of topsoil and deepening of soil profile by using paratill; 2) planting of perennial pastures to strengthen cattle raising; 3) inclusion of annual legumes in cattle raising management; 4) drip irrigation; 5) planning and implementation of crop rotation; 6) biologic pest management by means of strip cropping; 7) soil mapping; 8) land management zoning and mapping; 9) intercropping of legumes and perennial pastures for fodder; 10) consociated intercropping; 11) production of substrates through composting; and 12) breeding of native plants. Further, an experiment on simulating and evaluating drought impacts is on-going on a demonstrative field; it is not counted against the indicator as adoption of related lessons will still take a while.
Output | Output 13: Related articles/programs in the local media and political initiatives in the three municipal Councils of the directly targeted counties (Number, Custom) | 0 | 96 | 82
Output | Output 14: Related articles/programs in the local media in the three municipal Councils of the directly targeted counties (Number, Custom Breakdown) | 0 | 89 | 72
Output | Output 15: Related political initiatives in the three municipal Councils of the directly targeted counties (Number, Custom Breakdown) | 0 | 7 | 10
Output | Output 16: Workshops and other Knowledge Management events meet their targets in terms of participation of different stakeholder groups (Yes/No, Custom) | N | Y | Y | Beyond two workshops organized in Sept 2015 on the Project indicators and formulation of the SIS proposals with focus on objectives, in Dec 2016 the PIU organized a workshop to evaluate the Project advance until the date.
Output | Output 17: Targeted beneficiaries who have participated in related training and carry out their own means of M&E and continued improvement related to the measures they have adopted through participation in the Project (Percentage, Custom) | 0% | 0% | 70% | Thus far, this indicator has not been measured as the referred M&E processes have resulted to be more institutional than individual in nature. Yet the producers have received training on Project indicators and monitoring, it is more relevant to adjust the indicator to refer to the percentage of the local institutions that participate in the Project than the producers.
| FEMALE (Percentage, Custom Breakdown) | 0% | 0% | 70% | Consequently to the above comment, the disaggregation by gender is not valid when the indicator refers to institutions.
Output | Output 18: Assumed institutional commitments for the continuity and sustainability of the Project results per sector and activity (Number, Custom) | 0 | 9 | 1 per sector | The result reflects: 3 local governments (Municipios de Patagones, Villarino and Puan); 4 institutions participating in the IEWS (INTA, UNS, CERZOS and SMN); and 2 national organizations participating in the road-side afforestation plan in Villarino (Ministry of Social Development and Roads Agency)
Output | Output 19: Guidance material produced on critical pieces of policy framework, piloted adaptation practices, and potential sources of financing to support continued efforts to promote climate resiliency at differ (Yes/No, Custom) | N | Y | Y
NS = Not specified

## Lessons Learned
QUALITATIVE MEASURES and LESSONS LEARNED
Please complete the following section every reporting period
Implementation and Adaptive Management | Response
What implementation issues/lessons, either positive or negative, affected the progress? | Participatory planning processess during the first stages of project implementation are crucial as they foster commitment to the overall project objectives and activities. This is specially the case when considering that beneficiaries, as well as local counterparts and partners, are not used to environmental rationales nor do have experience in project execution. However, when stakeholders are as many as in case of the Project, the participatory processes become easily long-lasting and complex. In this sense, one lesson learned is that the very participatory planning should be visioned as an integral learning process that by itself is a Project objective, especially considering that it normally generates collateral benefits to the target groups such as fostering organizational skills. Otherwise, said important experience gained may remain invisible, or even appear as a bottleneck to efficient project execution. Participatory planning should be analyzed as an integral part of project execution and included in the cronogram. Another related key lesson has been the importance of standardizing the practices and documents applied to conduct the participative procedures, and doing so together with the stakeholders to secure their buy-in of the basic tools and prompt their adoption. It was necessary to undertake efforts to promote adaptation-readiness in the field and among the local partners: the PIU designed a two-hour basic course on adaptation, and also conducted a short training on the typical implementation issues, basics of the participatory planning approach, accounting, and monitoring and evaluation.
Were there any delays in implementation? If so, include any causes of delays. What measures have been taken to reduce delays? | During 2014, MAyDS faced changes of the national authorities that affected the intended PIU structure and introduced changes in internal procedures. This caused important delays in getting the Project operational, and the first disbursement only took place and the funds became available to the PIU in March 2015; almost a year later than planned. The PIU was established and fully operative in April/May 2015. Further, as the PIU needed to be set-up from a scratch, the Project start was affected due to the PIU lack of knowledge on the WB rules and procedures. These delays impacted the PIU ability to initate planning of Project activities that only started in June 2015, parallel to the local and presidential election campaigns in the intervention area and nationwide. This political momentum implied a further and not minor constraint to prompt Project execution, as political leadership and commitment to the Project had to be established in a context of severe uncertainty. At that momento, the PIU took two important decisions to accelerate the process and foster commitment: 1) it managed to solve the lack of accessible funds and specialized personnel through articulation with other institutions that counted with staff trained and experienced with the WB procedures and were willing to collaborate. This collaboration with relevant partners and other areas of the national Government that were already involved in mayor WB funded projects accelerated the work and processes until the PIU was fully operational; and 2) the PIU accelerated the participative planning processes through preparation and application of a set of standardized templates for their implementation and reporting while, at the same time, it conducted capacity-building activities for the key partners and local stakeholders.
Describe any changes undertaken to improve results on the ground or any changes made to project outputs (i.e. changes to project design) | As result of the Project's mid-term review, two outputs are proposed to be removed from the Project design as described under the Rating section and in the Mid-term Evaluation, to avoid dispersing the overall ambitious and challenging execution efforts too thin and, importantly, to areas that would most probably not yield the expected results; namely Output 1.1.3: Regional Consultative Observatory of Public Policies on Climate Change and Desertification and Output 1.2.2: Teacher training program for environmental education specifically designed for the zone. On the other hand, the Project has gained an interesting additional output, namely a Program for Social Inclusion through Work, executed in collaboration with the National Ministry of Social Development and the National Road Agency in the Municipality of Villarino. The program pioneers creation of green employment through a municipal tree nursery that produces seedlings to be planted along road sides and later, expectedly, field edges and other critical areas. The WB and PIU/MAyDS consider the referred changes as not material, based on the following justifications: During Project preparation, the Observatory (Output 1.1.3) was inspired by the then recently created National Observatory of Land Degradation and Desertification by SAyDS-CONICET. It was envisioned as a relevant tool to strengthen the implementation of the Development Plan of the Southwest of Buenos Aires Province (PDSO), and expected to “utilize the information generated by IEWS in the relevant decision-making processes”. The respective budget reservation was USD89,855 (2.5% of the AF grant). The respective output indicator is “Active participation of at least the key institutions of the Observatory”, whereas the key institutions were listed as UNS, municipalities, PDSO, NGOs, INTA (Ascasubi and Bordenave Experimental Agricultural Stations), CERZOS, and the National Observatory of Land Degradation and Desertification. Further, the indicator definition stated: “Their participation is considered active if at least 70% of them are present in meetings and agree on specific action plans for each institution for the following meetings.” Against said indicator, dropping the establishment of the Observatory is not considered an issue due to scarce demand/buy-in by the referred institutions and the fact that the PDSO implementation has been practically at halt during the implementation period. In practice, MAyDS, UNS, the Municipalities of Puan, Villarino and Patagones, INTA and CERZOS-CONICET participate actively in the IEWS, which is constantly strengthening its dissemination channels and, importantly, benefits of a leading participation by the National Meteorological Service (SMN) that was not contemplated during Project preparation. Based on all said factors, it is justified to say that the projected function of the Observatory is already being delivered by the IEWS as an interinstitutional framework, and by each of the contributing institutions within their overall sphere of action. Output 1.2.2 on a Teacher training program on environmental education specifically designed for the zone, with a budget reservation of USD123,633 (3.4% of the AF grant), was included in the Project design without sufficient assessment of the required procedures to insert new substance material into public teacher training programs. The respective output indicator is “Number of teacher training institutes within SWBA that cooperate with the Project and offer related training”, and the indicator was commented by saying that “there are 7 such institutes within the 3 counties that are direct beneficiaries of the Project”. The mid-term target was set to 6 and the final target to 10 institutions. Currently, the result is 4 institutions that collaborate with the Project: UNS, Agrarian School N°1 Carlos Spegazzini, Agrarian School of Patagones, and National Technological University. Further, the General Directorate of Schools, District of Southwest of the Ministry of Education of the Province of Buenos Aires facilitates the Project’s provision of educative material to schools within the targeted Municipalities. The Project has produced useful and popular pedagogical material used across schools and other public institutions in the SWBA, including elaboration and dissemination of a simplified, visual poster on climate change and SLM in favor of greater climate resilience. The Project has also organized/supported events like drawing competitions in local schools on Project-related topics. For example, in 2017 the topic of the competition was “My Footprint on the Ground 2017. Tree Our Refuge” (Mi Huella en el Suelo 2017. El Árbol Nuestro Refugio), and the Project produced related T-shirts and cloth bags. Despite these successful actions, as the indicator requires that the reported training institutes would offer related training, the final target of 10 institutes (still more specific “teacher training institutions within the SWBA”), is most probably not going to be achieved. During the MTR, the PIU/MAyDS suggested to drop Output 1.2.2 as it was deemed to fall out of the feasible Project scope, given introducing new curricular content within the public-school system requires completion of demanding administrative processes that take more time than the Project can invest in a minor output that would have been complementary but not critical to the expected Project results. Collaboration with local schools will in every case be continued through specific awareness-raising events. Regarding forthcoming actions at the MTR, the terms of reference were elaborated to produce a didactic table game adjustable to different age groups to explore the problematic of climate change and SLM. The Project will produce it for distribution to local schools, including an introductory workshop in each beneficiary Municipality.
How have gender considerations been taken into consideration during the reporting period? What have been the lessons learned as a consequence of inclusion of such considerations on project performance or impacts? | Gender considerations are transversal to the Project activities. In the Project area, women are overall well represented at the decision-making level within the participating institutions. In terms of the relevant producer profile, most of the Project's beneficiary farmers are elder males with small-scale farms, whose families live in the nearby villages. The Project addresses this producer profile focusing on generating motivation and fostering family-related activities e.g. in local producer fairs. As commented above, in Villarino the Project supports a major initiative to employ marginalized sectors of the local population through subsidized salaries. This initiative was coordinated in close collaboration with the Municipality and the National Ministry for Social Development and Road Agency, focused on setting-up worker cooperatives and building their capacity to foster the Project results in recovering forested areas within the Project area. Under this initiative, most of the direct beneficiaries are unemployed women and, indirectly, their children.
Please complete the following section at mid-term and project completion
Lessons for Adaptation | Response
Climate Resilience Measures
What have been the lessons learned, both positive and negative, in implementing climate adaptation measures that would be relevant to the design and implementation of future projects/programmes for enhanced resilience to climate change? | It is worthy of notice how, in the agriculture sector, there is often little difference between practices considered as climate resilience measures, and those of overall good agricultural practices. Particularly when working with producers and agroindustrial organizations that are not familiar with the concept of climate change, it is pertinent to consider a project's communication strategy in terms of maximum attractiveness and receptiveness by the targeted people. In case of the Project, it resulted helpful to develop both technical and non-technical information material and distribute it through focus groups since the early implementation stage. The participatory planning processes undertaken during the first year of the Project execution proved an excellent opportunity to create/strengthen awareness on the "climate-smartness" of the referred good practices as part of discussing and prioritizing the Project interventions proposed by the local technical organizations and producers. Through the participatory processes guided by two-way feedback provision, both the PIU and targeted stakeholders came up with improved climate adaptation measures as compared with the initial proposals. This was possible through a standardized "Field Planning Template", where the stakeholders stated objectives, expected goals and activities and presented them in an Action Plan with outputs, indicators, and an estimated budget for the list of the required goods and services. This way, the PIU analyzed and approved the proposals for the Specific Intervention Sites (SISs) and their Action Plans that applied rather consistent language on the proposed climate adaptation measures and included specificity on the necessary goods and services. Further, the process facilitated efficiency and synergies in terms of using the Project resources, as particular goods and services are shared between various SISs. See further lessons in the Mid-term Evaluation Report.
What is the potential for the climate resilience measures undertaken by the project/programme to be replicated and scaled up both within and outside the project area? | The potential for replication and scale-up of the Project activities is considered overall promising, as their direct benefits for producers and the work conducted by the participating technical institutions is already surfacing. There are, however, various work fronts that will require continued intra and inter-institutional engagement and effort to first showcase an appealing pilot case and, subsequently, generate replication and scale-up opportunities. This is particularly the case of the IEWS, Villarino Reforestation Plan, and municipal forage production plans. Currently, the WB facilitates the PIU/MAyDS to share and disseminate the Project work and lessons learnt across relevant WB operations that could engage in the expected replication and scale-up of the Project's pilot activities.
Concrete Adaptation Interventions
What have been the lessons learned, both positive and negative, in implementing concrete adaptation interventions that would be relevant to the design and implementation of future projects/programmes implementing concrete adaptation interventions? | Related with the earlier comment on the similarity of many agricultural good practices and practices that can be promoted particularly in name of increased climate resilience, the Project has proven that promotion of climate adaptation measures does not necessarily requiere a lot of innovation in terms of the subject matter. Rather, it requires 1) participatory approach that creates ownership of the project activities and harnesses the local know-how to a maximum, and 2) smart and integral communication and overall intervention strategies that motivate targeted stakeholder groups to adjust their productive approach to be more environmentally focused and oriented to longer-term sustainability instead of short-term gains; no minor targets indeed. Overall, it is critical to point out that the very concept of a climate adaptation project that would need to prove measurable results in the field after a couple of years of concreate action on the ground is a highly challenging and even a controversial concept: within the limited time period allowed for a standard project execution, proving a robust relationship between a good agricultural practice and its contribution to adaptation to climate variability and/or change is subject to unpredicted annual variation of the climatic conditions at the local level, and the very adoption of new productive approaches is a process that requires time. Interventions like planting of trees and improving soil quality won't yield their results in couple of years. Ideally, each project ought to identify and promptly implement at least one practice that shows difference in the soil structure and productivity within short, like the Project has been able to do with a paratill; an equipment that bends soil layers to loosen without clodding or destroying subsoil structures and shows rapid results in improved growth of pasture. Such practices should be rapidly sistematized and disseminated for a "contagious" impact; to boost interest in and motivation to actively engage with the project activities. A key lesson learnt in terms of the usefulness of an overall bottom-up implementation approach and inter-institutional/multistakeholder activities has been that starting concreate activities to operationalize and test the initial IEWS activities before elaborating and signing the formal agreement on the operation of the system proved useful for the related Project dynamics. The fact that each time improved Quarterly Forecast Reports were issued before launching the process of signing the inter-institutional agreement has allowed the champions from each institution a solid basis to formalize the commitments with their respective authorities, thus simplifying the formal approval process. The Project has proved to be rather complex as it covers a number of SISs and land management practice to pilot and assess; one lesson learnt is that, to promote more visible impacts, less but bigger interventions might yield better results. It is crucial that a project like this counts with capable personnel located in the field and working in permanent contact with the local authorities, technical institutions and beneficiaries. Such personnel bear a critical role in engaging stakeholders and building commitment and ownership, as well as in solving issues in an efficient manner, serving as a messanger between the local and central actors.
What is the potential for the concrete adaptation interventions undertaken by the project/programme to be replicated and scaled up both within and outside the project area? | As commented above, many of the adaptation interventions undertaken by the Project are rather straight-forward practices that even replicate practices implemented by earlier farmer generations but that were later replaced by more short-term productive strategies. Said practices are already proving directly benefitial for the participating producers and collaborative institutions. Said interventions can be easily replicated and scaled-up by the collaborative institutions, within and outside of the Project area where similar environmental and productive conditions prevail. There are other adaptation interventions like the IEWS, Villarino Reforestation Plan, and municipal forage production plans that are more complex to replicate and even scale-up, as they are innovative approaches that requiere strong buy-in, larger investments, and inter-institutional processes by the responsible agencies.
Community/National Impact
What would you consider to be the most successful aspects for the target communities? | As stated by producers, technicians and representatives of local governments in a M&E workshop conducted in December 2016 in Bahia Blanca, access to the Quartely Forecast Reports produced by the Project on the critical climatic, agronomical, and productive aspects at the local level has proved highly relevant for decision-making by producers and other relevant stakeholders in terms of delivery of local policies and initiatives. Simple practices with an analysis of their respective inputs and results in terms of production, soil productivity and resilience, which were easily understood by producers. For example, demonstation of a soil structure remediation practice that is being developed in Patagones, where differences in soil structure and productivity can be easily proven, and the respective analysis of the soil structure efficiently demonstrated, proved an attactive case study amongst the workshop participants on application of a specific technology.
What measures are/have been put in place to ensure sustainability of the project/program results? | The first direct initiative the Project delivered was an analysis and restructuring proposal for the existing programs that promote forage production in the beneficiary Municipalities. When successful, said program adjustments would provide scale and sustainability to some of the core adaptation measures promoted by the Project. Additionally, piloting an innovative tree plantation program combined with creation of green jobs to prevent soil degradation by wind and water at the local level in close collaboration with national and provincial government entities is expected to repercute in longer-term work by the same. For example, the National Ministry of Social Development is interested in elaborating a detailed case study of the pilot with the aim of its potential replication in other regions facing similar issues.
What measures are being/could have been put in place to improve project/program results? | Considering the complexity of the Project's results framework that includes almost 20 indicators, the PIU and WB used the mid-term review to review and adjust the framework to help focus the remaining Project implementation on the key results chains and align them better with the PDO.
Knowledge Management
How has existing information/data/knowledge been used to inform project development and implementation? What kinds of information/data/knowledge were used? | To deliver the participatory planning processes conducted during the first year of the Project execution, the PIU elaborated and applied a standardized "Field Planning Template” that facilitated capturing of specific information on each SIS, and was then reinforced by the study on their respective baseline. The information collected on the beneficiaries, local soil conditions and productive conditions, etc., was used to capture key aspects to be monitored during Project implementation and to present the results achieved at the end. A template was also elaborated to conduct monitoring and evaluation by the responsible agencies, through which each SIS reports advances on their site-specific activites using specific indicators and comparing them to the baseline data e.g. on the soil conditions.
If learning objectives have been established, have they been met? Please describe. | The Project's results framework includes a number of training-related indicators, yet no specific learning objectives have been established.
Describe any difficulties there have been in accessing or retrieving existing information (data or knowledge) that is relevant to the project. Please provide suggestions for improving access to the relevant data. | A baseline study has been developed, including a long list of indicators, some of them related to FAO/LADA methodology. However, it proved difficult to gather all the necessary information to fulfill such a standard, and it was necessary to simplify the list of indicators, focusing on the most relevant factors of the history of each SIS's agroecosystem and its productivity, beneficiaries and climate variability. For 9 of the 11 SISs, a baseline has been developed with specific indicators that reflect the main issues related to their respective objetives.
Has the identification of learning objectives contributed to the outcomes of the project? In what ways have they contributed? | N/A

## Results Tracker
Results Tracker for Adaptation Fund (AF) Projects
Goal: Assist developing-country Parties to the Kyoto Protocol that are particularly vulnerable to the adverse effects of climate change in meeting the costs of concrete adaptation projects and programmes in order to implement climate-resilient measures. Impact: Increased resiliency at the community, national, and regional levels to climate variability and change.
Important: Please read the following guidance document (also posted on the Adaptation Fund website) before entering your data
Link: http://www.adaptation-fund.org/sites/default/files/Results%20Framework%20and%20Baseline%20Guidance%20final.pdf
Adaptation Fund Strategic Results Framework
Project ID | BIRF TF15041
Implementing Entity | WORLD BANK
Type of implementing entity | MIE
Country | Argentina
Region | Latin America and Caribbean
Sector | Agriculture
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Impact: Increased resiliency at the community, national, and regional levels to climate variability and change | Core Indicator: No. of beneficiaries |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project
|  | Total | 0 | 408 | -408 | Total | 1400 | 350 | 1050 | Total | 1632 | 408 | 1224 | Total
|  | % of female beneficiaries |  | 9.6% | 9.6% | % of female beneficiaries | 20% |  |  | % of female beneficiaries | 25% | 9.6% | 25% | % of female beneficiaries
|  | % of Youth beneficiaries |  |  |  | % of Youth beneficiaries |  |  |  | % of Youth beneficiaries |  |  |  | % of Youth beneficiaries
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 1: Reduced exposure to climate-related hazards and threats | Indicator 1: Relevant threat and hazard information generated and disseminated to stakeholders on a timely basis | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness
|  | Total | 440 | Drought | 1: Ineffective | Total | 220 | Drought | 4: Effective | Total | 173 | Drought | 3: Moderately effective | Total
|  | % of female targeted | 20% |  |  | % of female targeted | 20% |  |  | % of female targeted | 12.34% |  |  | % of female targeted
Output 1.1 Risk and vulnerability assessments conducted and updated | Indicator 1.1: No. of projects/programmes that conduct and update risk and vulnerability assessments | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
Output 1.2 Targeted population groups covered by adequate risk reduction systems | Core Indicator 1.2: No. of Early Warning Systems | No. of adopted Early Warning Systems | Category targeted | Hazard | Drought | No. of adopted Early Warning Systems | Category targeted | Hazard | Drought | No. of adopted Early Warning Systems | Category targeted | Hazard | Drought | No. of adopted Early Warning Systems | Category targeted | Hazard
|  | 0 | 2: Monitoring and warning service | Geographical coverage | Local | 1 | 2: Monitoring and warning service | Geographical coverage | Local | 1 | 2: Monitoring and warning service | Geographical coverage | Local |  |  | Geographical coverage
|  |  |  | Number of municipalities |  |  |  | Number of municipalities | 3 |  |  | Number of municipalities | 3 |  |  | Number of municipalities
|  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 2: Strengthened institutional capacity to reduce risks associated with climate-induced socioeconomic and environmental losses | Indicator 2: Capacity of staff to respond to, and mitigate impacts of, climate-related events from targeted institutions increased | Number of staff targeted |  | Sector | Capacity level | Number of staff targeted |  | Sector | Capacity level | Number of staff targeted |  | Sector | Capacity level | Number of staff targeted |  | Sector | Capacity level
|  | Total |  |  |  | Total |  |  |  | Total |  |  |  | Total
|  | % of female targeted |  |  |  | % of female targeted |  |  |  | % of female targeted |  |  |  | % of female targeted
Output 2.1 Strengthened capacity of national and sub-national centres and networks to respond rapidly to extreme weather events | Indicator 2.1.1: No. of staff trained to respond to, and mitigate impacts of, climate-related events | Total staff trained | % of female staff trained | Type |  | Total staff trained | % of female staff trained | Type |  | Total staff trained | % of female staff trained | Type |  | Total staff trained | % of female staff trained | Type
|  | 0 | 0% | Public |  | 7 | 14.28% | Public |  | 7 | 14.28% | Public
| Indicator 2.1.2: No. of targeted institutions with increased capacity to minimize exposure to climate variability risks | Type | Scale | Sector | Capacity level | Type | Scale | Sector | Capacity level | Type | Scale | Sector | Capacity level | Type | Scale | Sector | Capacity level
|  | Public | Local | Agriculture | 2: Low capacity | Public | Local | Agriculture | 3: Medium capacity | Public | Local | Agriculture | 3: Medium capacity
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 3: Strengthened awareness and owernship of adaptation and climate risk reduction processes | Indicator 3.1: Increase in application of appropriate adaptation responses | Percentage of targeted population applying adaptation measures |  | Sector |  | Percentage of targeted population applying adaptation measures |  | Sector |  | Percentage of targeted population applying adaptation measures |  | Sector |  | Percentage of targeted population applying adaptation measures |  | Sector
Output 3: Targeted population groups participating in adaptation and risk reduction awareness activities | Indicator 3.1.1: Percentage of targeted population awareness of predicted adverse impacts of climate change, and of appropriate responses | No. of targeted beneficiaries | % of female participants targeted | Level of awareness |  | No. of targeted beneficiaries | % of female participants targeted | Level of awareness |  | No. of targeted beneficiaries | % of female participants targeted | Level of awareness |  | No. of targeted beneficiaries | % of female participants targeted | Level of awareness
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 4: Increased adaptive capacity within relevant development sector services and infrastructure assets | Indicator 4.1: Increased responsiveness of development sector services to evolving needs from changing and variable climate | Project/programme sector | Geographical scale | Response level |  | Project/programme sector | Geographical scale | Response level |  | Project/programme sector | Geographical scale | Response level |  | Project/programme sector | Geographical scale | Response level
| Core Indicator 4.2: Assets produced, developed, improved or strengthened | Sector | Targeted asset | Changes in asset (quantitative or qualitative) |  | Sector | Targeted asset | Changes in asset (quantitative or qualitative) |  | Sector | Targeted asset | Changes in asset (quantitative or qualitative) |  | Sector | Targeted asset | Changes in asset (quantitative or qualitative)
Output 4: Vulnerable development sector services and infrastructure assets strengthened in response to climate change impacts, including variability | Indicator 4.1.1: No. and type of development sector services to respond to new conditions resulting from climate variability and change | Number of services | Type |  | Sector | Number of services | Type |  | Sector | Number of services | Type |  | Sector | Number of services | Type |  | Sector
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 5: Increased ecosystem resilience in response to climate change and variability-induced stress | Indicator 5: Ecosystem services and natural resource assets maintained or improved under climate change and variability-induced stress | Natural resource improvement level |  | Sector | Type | Natural resource improvement level |  | Sector | Type | Natural resource improvement level |  | Sector | Type | Natural resource improvement level |  | Sector | Type
|  | 1: Ineffective |  | Agriculture | land | 4: Effective |  | Agriculture | land | 2: Partially effective |  | Agriculture | land
Output 5: Vulnerable ecosystem services and natural resource assets strengthned in response to climate change impacts, including variability | Core Indicator 5.1: Natural Assets protected or rehabilitated | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Baseline information |  |  |  | Targeted performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 6: Diversified and strengthened livelihoods and sources of income for vulnerable people in targeted areas | Indicator 6.1: Increase in households and communities having more secure access to livelihood assets | No. of targeted households | % of female headed households | Improvement level |  | No. of targeted households | % of female headed households | Improvement level |  | No. of targeted households | % of female headed households | Improvement level |  | No. of targeted households | % of female headed households | Improvement level
| Indicator 6.2: Increase in targeted population's sustained climate-resilient alternative livelihoods | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
|  | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
|  | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
|  | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
Output 6 Targeted individual and community livelihood strategies strengthened in relation to climate change impacts, including variability | Indicator 6.1.1: No. and type of adaptation assets created or strengthened in support of individual or community livelihood strategies | Number of Assets | Type of Assets | Sector | Adaptation strategy | Number of Assets | Type of Assets | Sector | Adaptation strategy | Number of Assets | Type of Assets | Sector | Adaptation strategy | Number of Assets | Type of Assets | Sector | Adaptation strategy
| Core Indicator 6.1.2: Increased income, or avoided decrease in income | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 7: Improved policies and regulations that promote and enforce resilience measures | Indicator 7: Climate change priorities are integrated into national development strategy | Integration level |  |  |  | Integration level |  |  |  | Integration level |  |  |  | Integration level
Output 7:Improved integration of climate-resilience strategies into country development plans | Indicator 7.1: No. of policies introduced or adjusted to address climate change risks | No. of Policies introduced or adjusted | Sector | Scale | Type | No. of Policies introduced or adjusted | Sector | Scale | Type | No. of Policies introduced or adjusted | Sector | Scale | Type | No. of Policies introduced or adjusted | Sector | Scale | Type
|  | 0 | Agriculture | Local | Public policy | 1 | Agriculture | Local | Public policy | 0 | Agriculture | Local | Public policy
| Indicator 7.2: No. of targeted development strategies with incorporated climate change priorities enforced | No. of Development strategies | Regulation |  | Effectiveness | No. of Development strategies | Regulation |  | Effectiveness | No. of Development strategies | Regulation |  | Effectiveness | No. of Development strategies | Regulation |  | Effectiveness
Glacier lake outburst flood
|  | Inland flooding | fr | biological assets |  | Company policy | 5: Fully enforced (All elements implemented)
|  | Salinization | Decrease | land |  | Communication & Information policy | 4: Enforced (Most elements implemented)
|  | Drought | Same | water areas |  | Defense policy | 3: Partially enforced (Some elements implemented)
|  | Wind |  | subsoil assets | increased adpative capacity | Domestic policy | 2: Partially not enforced (Most elements not implemented) |  | Agribusiness
|  | Coastal flooding |  | air | achieved | Economic policy | 1: Not enforced (No elements implemented) |  | Agricultural-related | Financial capital
|  | Storm surge | Please choose |  | enhanced level of protection | Education policy |  |  | Agriculture | Human capital
|  | Hurricane | Selected | [5 empty] | Aquaculture | Physical capital
|  |  | Not relevant |  |  | 5: All (Fully integrated) |  |  | Construction/repairing business | Social capital
[6 empty] | 4: Most |  |  | Cultivation | Natural capital
[6 empty] | 3: Some |  |  | Fishing | Personal capital
Select | 5: All | Select |  |  | Community | 2: Most not integrated |  | Other | Forestry | Adaptation strategies
1 | 4: Almost all | Private | Type | Yes | Multi-community | 1: None |  | Agriculture | Handicrafts
2 | 3: Half | Public | Scale | No | Departmental |  |  | Coastal management | Livestock production
3 | 2: Some | NGO | Sector |  | National |  |  | Disaster risk reduction | Manufacturing
4 | 1: None |  |  |  |  | 5: Very high improvement | Established | Food security | other
|  | National |  |  |  | 4: High improvement | Maintained | Health | Services
|  | Regional |  |  |  | 3: Moderate improvement | Improved | Urban development | Tourism-related
|  | Local |  |  |  | 2: Limited improvement |  | Water management | Trading
[6 empty] | 1: No improvement |  | Multi-sector
|  | 1 -generated information is irrelevant, and neither the stakeholders reached nor the timeframe managed were achieved | 1: No info transferred on time | 4: High capacity | 5: Fully aware | 5: Highly responsive (All defined elements ) | 5: Fully improved | Roads | 5: Very effective
Asia-Pacific | NIE | 2 -the existence of some challenge in any of the three aspects of the indicator (generation of dissemination, stakeholders reached or timeframe managed) | 2: Somewhat info transferred | 3: Medium capacity | 4: Mostly aware | 4: Mostly responsive (Most defined elements) | 4: Mostly Improved | Gov Buildings | 4: Effective
Latin America and Caribbean | RIE | 3 -relevant information is generated and disseminated to all identified stakeholders on timely basis | 3: Info transferred on time | 2: Low capacity | 3: Partially aware | 3: Moderately responsive (Some defined elements) | 3: Moderately improved | Causeways | 3: Moderately effective
Africa | MIE |  |  | 1: No capacity | 2: Partially not aware | 2: Partially responsive (Lacks most elements) | 2: Somewhat improved | Airports | 2: Partially effective
Eastern Europe |  |  |  |  | 1: Aware of neither | 1: Non responsive (Lacks all elements ) | 1: Not improved | Schools | 1: Ineffective
| ha protected | [6 empty] | Training Centres
| ha rehabilitated | [5 empty] | Monitoring/Forecasting capacity | Hospitals
Afghanistan, Islamic Rep. of | km protected | [5 empty] | Policy/regulatory reform | Drinking water systems
Angola | km rehabilitated | 1: Risk knowledge | 1: No plans conducted or updated |  |  |  | Capacity development | Other
Albania |  | 2: Monitoring and warning service | 2: Undertaking or updating of assessments in progress |  |  | Communication & Information policy | Sustainable forest management
Argentina |  | 3: Dissemination and communication | 3: Risk and vulnterability assessments completed or updated |  |  | Domestic policy | Strengthening infrastructure | 1: Health and Social Infrastructure (developed/improved)
Armenia | Forests | 4: Response capability |  |  |  | Economic policy | Supporting livelihoods | 2: Physical asset (produced/improved/strenghtened)
Antigua and Barbuda | Mangroves |  |  |  |  | Education policy | Mangrove reforestation
Azerbaijan | Coasts |  | From 0 to 0.5% |  |  | Energy policy | Coastal drainage and infrastructure
Burundi | Rangelands |  | From 0.5 to 1% |  |  | Environmental policy | Irrigation system
Benin | Cultivated land/Agricultural land |  | From 1% to 5% |  |  | Foreign policy | Community-based adaptation
Burkina Faso | Catchment area/Watershed/Aquifer |  | From 5% to 10% |  |  | Health policy | Erosion control
Bangladesh | Protected areas/National parks |  | From 10% to 20% |  |  | Housing policy | Soil water conservation
Bulgaria | Other |  | From 20% to 30% |  |  | Human resource policies | Microfinance
Bahrain |  |  | From 30% to 40% |  |  | Information policy | Special Program for women
Bahamas, The |  |  | From 40% to 50% |  |  | Macroeconomic policy | Livelihoods
Bosnia and Herzegovina |  |  | Above 50% |  |  | Monetary policy | Water storage
Belarus | [5 empty] | Population policy | ICT and information dissemination
Belize | [5 empty] | Private policy
Bolivia | [5 empty] | Public policy
Brazil | [5 empty] | Science policy
Barbados | [5 empty] | Social policy
Bhutan |  | 3- relevant information is generated and disseminated to all identified stakeholders on timely basis |  |  |  | Transportation policy
Botswana |  | describe |  |  |  | Urban policy
Central African Republic |  | 2- the existence of some challenge in any of the three aspects of the indicator |  |  |  | Water policy
Chile |  | describe |  |  |  | Other policy
China, People's Republic of |  | 1- generated information is irrelevant and neither the stakeholders reached nor the timeframe managed were achieved
Cote d'Ivoire |  | describe
Cameroon
Congo, Dem. Rep. of
Congo, Republic of
Cook Islands
Colombia
Comoros
Cape Verde
Costa Rica
Cuba
Czech Republic
Djibouti
Dominica
Dominican Republic
Algeria
Ecuador
Egypt
Eritrea
Estonia
Ethiopia
Fiji
Micronesia, Fed. States of
Gabon
Georgia
Ghana
Guinea
Gambia, The
Guinea-Bissau
Equatorial Guinea
Grenada
Guatemala
Guyana
Honduras
Croatia
Haiti
Hungary
Indonesia
India
Iran, Islamic Republic of
Jamaica
Jordan
Kazakhstan
Kenya
Kyrgyz Republic
Cambodia
Kiribati
Saint Kitts and Nevis
Korea, Republic of
Lao People's Democratic Republic
Lebanon
Liberia
Libya
Saint Lucia
Sri Lanka
Lesotho
Lithuania
Latvia
Morocco
Moldova
Madagascar
Maldives
Mexico
Marshall Islands
Macedonia, former Yugoslav Republic of
Mali
Malta
Myanmar
Montenegro
Mongolia
Mozambique
Mauritania
Mauritius
Malawi
Malaysia
Namibia
Niger
Nigeria
Nicaragua
Niue
Nepal
Nauru
Oman
Pakistan
Panama
Peru
Philippines
Palau
Papua New Guinea
Poland
Korea, Dem. People's Rep. of
Paraguay
Romania
Russian Federation
Rwanda
Saudi Arabia
Sudan
Senegal
Solomon Islands
Sierra Leone
El Salvador
San Marino
Serbia
Sao Tome and Principe
Suriname
Slovak Republic
Slovenia
Swaziland
Seychelles
Syrian Arab Republic
Chad
Togo
Thailand
Tajikistan
Turkmenistan
Tonga
Trinidad and Tobago
Tunisia
Turkey
Tuvalu
Tanzania
Uganda
Ukraine
Uruguay
Uzbekistan
Saint Vincent and the Grenadines
Venezuela
Vietnam
Vanuatu
Samoa
Yemen, Republic of
South Africa
Zambia
Zimbabwe
Timor-Leste

## Units for Indicators
Fund Outcome Indicator Units
1. Generation of relevant data, Stakeholders, and Timeliness 2.1. Include both qualitative and quantitative measures of capacity level within targeted institutions 2.2. Number (men and women and other vulnerable groups) 3.1. Use scale from 1 to 5: 5: Fully aware 4: Mostly aware 3: Partially aware 2: Partially not aware 1: Aware of neither predicted adverse impacts of climate change nor of appropriate responses 3.2. Use scale from 1 to 5: 5: All 4: Almost all 3: Half 2: Some 1: None 4.1. Summarize in an overall scale (1-5): 5: Highly responsive (All defined elements ) 4: Mostly responsive (Most defined elements) 3: Moderately responsive (Some defined elements) 2: Partially responsive (Lacks most elements) 1: Non responsive (Lacks all elements ) 4.2. Summarize in an overall scale (1-5): 5: Fully improved 4: Mostly Improved 3: Moderately improved 2: Somewhat improved 1: Not improved 5. Depends on the targeted natural asset: Biological (species): measure through changes in population numbers (dynamics, structure, etc.) Land: measure changes in hectares. Baseline data will be necessary to estimate the change. Supporting indicators baseline and target (as well as contextual information) are needed such as the following: Farmers adopting recommended technologies, Ha. of land improved, Average deforestation rate Etc. Use scale from 1 to 5. 5: Very effective (All elements are present) 4: Effective (Most elements are present) 3: Moderately effective (Some elements are present) 2: Partially effective (Most elements are not present) 1: Ineffective (No elements are present) 6.1. Summarize in an overall scale (1-5): 5: Very high improvement 4: High improvement 3: Moderate improvement 2: Limited improvement 1: No improvement 6.2. Household income by source of livelihood in project area (USD) prior and post project intervention 7. Summarize in an overall scale (1-5). 5: All (Fully integrated) 4: Most 3: Some 2: Most not integrated 1: None
Fund Output Indicator Units
1.1. Number, sector(s) and level(s) of projects or interventions in separate fields of monitoring plan 1.2. Number 2.1.1. Number of staff (male/female) of targeted institutions: a. Obtain baseline information: total number of staff from targeted institutions b. Define target 2.1.2. Number of staff (male/female) of targeted institutions: a. Obtain baseline information: total number of staff from targeted institutions b. Define target: needs to be defined by project proponents 2.2.1. Quantitative: Percentage (includes women – and other vulnerable groups – and men). Qualitative: Adequacy: include direct analysis of major areas; adequacy/effectiveness of systems or analysis of perceptions of populations and institutions. 2.2.2. Number (broken down by gender and, if possible, by vulnerable groups defined in the area of intervention) of people 3.1. Number and type (in separate columns) at local level. 3.2. Number 4.1. Number and type 4. 2. Number and type (entered in separate columns) 5. Number of interventions by type of natural asset and intervention 6.1. Number and type (in separate columns of monitoring plan) 6.2. Income sources per household; description of income source and number of households. 7.1. Number/Sector 7.2. Number; Effectiveness (see previous indicator) through enforcement level.