## Overview
Project Performance Report (PPR)
| Period of Report (Dates) | October 2014 - September 2015
| Project Title: | Enhancing the Adaptive Capacity and Increasing Resilience of Small-size Agricultural Producers of the Northeast of Argentina
| Project Summary: | The overall project objective is to increase the adaptive capacity and resilience of small-scale agriculture producers to the impacts of climate change and its variability, particularly those deriving from the increase in the intensity of hydro-meteorological events such as floods and droughts. The project has three components: 1) Improvement of the adaptive capacity to climate change and its variability of small-scale producers of North-eastern Argentina; 2) Strengthening of information, monitoring and climate information management systems; and 3) Generation of local and regional capabilities on the impact of climate change and its variability, and implementation of adaptation measures.
|  |  | Countries | Project Type: |  | GEF Focal Area: | GEF 4 Focal Areas | GEF 2 / 3 Operational Program: | Overall Rating of the project in the evaluation by the project evaluator: | GEF-4 Focal Area Strategic Program: | GEF-3 Focal Area Strategic Program:
| Database Number: |  | Afghanistan | FP | Yes | Biodiversity | 1 | 1 | U | BD-SP1-PA Financing | 1: Arid & semi-arid ecosystems
Implementing Entity (IE) [name]: |  | UCAR - Unit for Rural Change | Albania | MSP | No | Climate Change Adaptation | 2 | 2 | S | BD-SP2-Marine PA | 2: Coastal, marine & freshwater ecosystems
| Type of IE: | National Implementing Entity | Algeria | EA |  | Climate Change Mitigation | 3 | 3 | MU | BD-SP3-PA Networks | 3: Forest ecosystems
| Country(ies): | Argentina | Angola |  |  | International Waters | 5 | 5 | Good | BD-SP5-Markets | 13: Conservation and Sustainable Use of Biological Diversity Important to Agriculture
Relevant Geographic Points (i.e. cities, villages, bodies of water): |  | Provinces of Chaco, Santiago del Estero, Santa Fe and Corrientes. | Argentina |  |  | Multiple Focal Area |  |  |  | BD-SP7-Invasive Alien Species(IAS) | 6: Promoting the adoption of renewable energy by removing barriers and reducing implementation costs
[8 empty] | CC-SP2- Industrial EE | 8: Waterbody based operational program
| Project Milestones | [6 empty] | CC-SP3-RE,CC-SP4-Biomass | 9: Integrated Land and Water multiple focal area
| Milestone |  | Bahamas | [6 empty] | CC-SP5-Transport | 10: Contaminants based operational program
AFB Approval Date: |  | 2013-04-04
IE-AFB Agreement Signature Date: |  | 2013-04-16 | [6 empty] | CC-SP6-LULUCF | 12: Integrated Ecosystem Management
Start of Project/Program: |  | 2013-10-24 | [6 empty] | Cross cutting capacity building | 14: Persistent Organic Pollutants
Mid-term Review Date (if planned): |  | -
Terminal Evaluation Date: |  | -
|  | List documents/ reports/ brochures / articles that have been prepared about the project. | Cyprus
|  | NEWS: The first supervision mission from the Adaptation Fund is expected to arrive in November (institutional webpage of UCAR , 12/10/2015). http://www.ucar.gob.ar/index.php/novedades/noticias-ucar/1878-se-recibira-en-noviembre-a-la-primera-mision-de-supervision-del-fondo-de-adaptacion The Adaptation Fund project will display its activities in COP 21 (institutional webpage of UCAR , 07/10/2015). http://ucar.gob.ar/index.php/novedades/noticias-ucar/1869-el-proyecto-del-fondo-de-adaptacion-expondra-sus-actividades-en-la-cop-21 Signature of agreement for the integration of climate information networks (institutional webpage of UCAR , 27/09/2015). http://ucar.gob.ar/index.php/novedades/noticias-ucar/1848-se-firmo-un-acuerdo-para-la-integracion-de-redes-de-informacion-climatica Meeting of executing institutions of the Project for Adaptation to Climate Change in the town of San Javier, Santa Fe (institutional webpage of UCAR, 08/07/2015). http://ucar.gob.ar/index.php/novedades/noticias-ucar/1670-encuentro-de-organizaciones-en-torno-al-agua-y-al-cambio-climatico UCAR attended the workshop on climate funding for Latin America and the Caribbean (institutional webpage of UCAR, 14/04/2015). http://ucar.gob.ar/index.php/novedades/noticias-ucar/1387-la-ucar-participo-del-taller-de-financiamiento-climatico-para-america-latina-y-el-caribe The project consolidates its actions in the NEA [North-East region of Argentina] (institutional webpage of UCAR, 06/04/2015). http://ucar.gob.ar/index.php/novedades/noticias-ucar/1347-el-proyecto-adaptacion-y-resiliencia-ante-el-cambio-climatico-afianza-sus-acciones-en-el-nea Second Training on Climate Change aimed at technicians and professionals of the NEA (institutional webpage of UCAR, 10/12/2014). http://ucar.gob.ar/index.php/novedades/noticias-ucar/1038-chaco-se-realiza-segunda-capacitacion-en-cambio-climatico-a-tecnicos-y-profesionales Training in the use of hand augers to make access to water easier (institutional webpage of UCAR , 27/10/2014). http://ucar.gob.ar/index.php/novedades/noticias-ucar/889-jornada-en-pos-del-buen-uso-del-agua-en-la-agricultura-familiar | Czech Republic
REPORTS: - Monitoring Visit Report April 9 2015 -UCAR- - Feasibility study to develop a Pilot plan for risk management concerning family agricultural producers whose main activity is field horticulture. Report with main results – September 2015. – Scenario analysis concerning Climate Change and climate tendencies and their impact on crops, Report of September 2015 - Progress Report of the Project of Adaptation to Climate Change. La Brava as of 30/01/2015 - Report of hands-on course introducing rotating mechanical drilling techniques for the construction of shallow groundwater abstraction wells. Nov.2014 - Progress Report , Goya. February 2015 - Progress Report on the Project of Adaptation to Climate Change. Santa lucia - Nov. 2014 - REPORT: Training workshops: Construction of boreholes and cased wells for abstraction of groundwater. Drilling with hand augers and handcrafted screens . Groundwater georeferenced studies. Nov.2014 - Spreadsheets for the monitoring of project activities - Committee report on installation of automatized meteorological stations - 8/9/15 to 10/9/15
List the Website address (URL) of project. |  |  | Democratic People's Republic of Korea
|  | http://www.ucar.gob.ar/index.php/institucional/fondo-de-adaptacion-para-el-cambio-climatico | Democratic Republic of the Congo
Denmark
| Project contacts: |  | Djibouti
National Project Manager/Coordinator |  |  | Dominica
| Name: | Mario Nanclares | Dominican Republic
| Email: | mnanclares@prosap.gov.ar | Ecuador
| Date: |  | Egypt
| Government DA |  | El Salvador
| Name: | Lucas Di Pietro | Equatoral Guinea
| Email: | ldipietro@ambiente.gob.ar | Eritrea
| Date: |  | Estonia
| Implementing Entity |  | Ethiopia
| Name: | Mario Nanclares | Fiji
| Email: | mnanclares@prosap.gov.ar | Finland
| Date: |  | France
| Executing Agency |  | Gambia
| Name: | INTA - Diego Ramilo | Georgia
| Email: | ramilo.diegonicolas@inta.gob.ar | Germany
| Date: |  | Ghana
| Executing Agency |  | Greece
| Name: | ORA - Sandra Occhiuzzi | Grenada
| Email: | socchi@minagri.gob.ar | Guatemala
| Date: |  | Guinea
| Executing Agency |  | Guinea Bissau
| Name: | DCC - Nazareno Castillo | Guyana
| Email: | ncastillo@ambiente.gov.ar | Haiti
| Date: |  | Honduras
Hungary
Iceland
India
Indonesia
Iran (Islamic Republic of)
Iraq
Ireland
Israel
Italy
Jamaica
Japan
Jordan
Kazakhstan
Kenya
Kiribati
Kuwait
Kyrgyzstan
Lao People’s Democratic Republic
Latvia
Lebanon
Lesotho
Liberia
Libyan Arab Jamahiriya
Liechtenstein
Lithuania
Luxembourg
Madagascar
Malawi
Malaysia
Maldives
Mali
Malta
Marshall Islands
Mauritania
Mauritius
Mexico
Micronesia, Federated States of
Monaco
Mongolia
Montenegro
Morocco
Mozambique
Myanmar
Namibia
Nauru
Nepal
Netherlands
New Zealand
Nicaragua
Niger
Nigeria
Norway
Oman
Pakistan
Palau
Panama
Papua New Guinea
Paraguay
Peru
Philippines
Poland
Portugal
Qatar
Republic of Korea
Republic of Moldova
Romania
Russian Federation
Rwanda
Saint Kitts and Nevis
Saint Lucia
Saint Vincent and the Grenadines
Samoa
San Marino
Sao Tome and Principe
Saudi Arabia
Senegal
Serbia
Seychelles
Sierra Leone
Singapore
Slovakia
Slovenia
Solomon Islands
Somalia
South Africa
Spain
Sri Lanka
Sudan
Suriname
Swaziland
Sweden
Switzerland
Syrian Arab Republic
Tajikistan
Thailand
The former Yugoslav Republic of Macedonia
Timor-Leste
Togo
Tonga
Trinidad and Tobago
Tunisia
Turkey
Turkmenistan
Tuvalu
Uganda
Ukraine
United Arab Emirates
United Kingdom of Great Britain and Northern Ireland
United Republic of Tanzania
United States of America
Uruguay
Uzbekistan
Vanuatu
Venezuela, Bolivarian Republic of
Viet Nam
Yemen
Zambia
Zimbabwe

## FinancialData
Financial information: Cumulative from project start to September 30, 2014.
DISBURSEMENT OF AF GRANT FUNDS
How much of the total AF grant as noted in Project Document plus any project preparation grant has been spent to date?
Estimated cumulative total disbursement as of October 2014 | 1156742
Add any comments on AF Grant Funds. (word limit=200) | Funds from the first disbursement made by the Adaptation Fund continue to be used given that 2015 execution was slower than anticipated. The main reason for such delay is due to some issues with the application to the National Budget Office regarding the lending sums authorized for 2015, which adversely affected project execution. This matter is fully explained in the Risk Assessment, Rating and Lessons Learned sections.
EXPENDITURE DATA
List output and corresponding amount spent for the current reporting period | ITEM / ACTIVITY / ACTION |  | AMOUNT
| 1. Improvement of the adaptive capacity to climate change and its variability of small-scale agriculture producers of North-eastern Argentina. | 1.1 Implementation of improvements in the efficient use, catchment, harvesting, and storage of water in the areas of intervention. | 305351.862
|  | 1.2 Implementation of a system for the management and transfer of risks targeting small- and mid-scale agriculture producers. Development of two pilot tests in the region selected. | 2803.9314
|  | 1.3 Optimization practices of agricultural, farming, and forestry production management in each one of the areas of intervention. | 89775.4646
| 2. Strengthening of information, monitoring and climate information management systems. | 2.1 Integration and expansion of agro-hydro-meteorological networks within the project area. | 327212.3731
|  | 2.2 Development of an Early Warning and Decision-making system to assess and manage climate risks, including extreme events. | 20121.4182
| 3. Generation of local and regional capabilities on the impact of climate change and its variability, and implementation of adaptation measures. | 3.1 Development of training and communication modules on risk management and transfer targeted to government technical experts and small-scale agriculture producers. | 56522.6953
3.2 Training and capacity building targeted to municipal and provincial government units for hydro-meteorological management and monitoring, analysis of climate information, use of methodological tools and development of adaptation modules.
| 4. Project Cycle Management (Implementing Entity) |  | 7543.7252
| TOTAL |  | 809331.4698
PLANNED EXPENDITURE SCHEDULE
List outputs planned and corresponding projected cost for the upcoming reporting period | ITEM / ACTIVITY / ACTION |  | PROJECTED COST | Estimated Completion Date
| 1. Improvement of the adaptive capacity to climate change and its variability of small-scale agriculture producers of North-eastern Argentina. | 1.1 Implementation of improvements in the efficient use, catchment, harvesting, and storage of water in the areas of intervention. | 900000 | 2016-10-01
|  | 1.2 Implementation of a system for the management and transfer of risks targeting small- and mid-scale agriculture producers. Development of two pilot tests in the region selected. | 600000 | 2016-10-01
|  | 1.3 Optimization practices of agricultural, farming, and forestry production management in each one of the areas of intervention. | 400000 | 2016-10-01
| 2. Strengthening of information, monitoring and climate information management systems. | 2.1 Integration and expansion of agro-hydro-meteorological networks within the project area. | 325000 | 2016-10-01
|  | 2.2 Development of an Early Warning and Decision-making system to assess and manage climate risks, including extreme events. | 150000 | 2016-10-01
| 3. Generation of local and regional capabilities on the impact of climate change and its variability, and implementation of adaptation measures. | 3.1 Development of training and communication modules on risk management and transfer targeted to government technical experts and small-scale agriculture producers. | 100000 | 2016-10-01
|  | 3.2 Training and capacity building targeted to municipal and provincial government units for hydro-meteorological management and monitoring, analysis of climate information, use of methodological tools and development of adaptation modules. | 100000 | 2016-10-01
| 4. Project Cycle Management (Implementing Entity) |  | 95000 | 2016-10-01
| TOTAL |  | 2670000 | 2016-10-01
ACTUAL CO-FINANCING (If the MTR or TE have not been undertaken this reporting period, DO NOT report on actual co-financing.)
How much of the total co-financing as committed in the Project Document has actually been realized? | Not applicable
Estimated cumulative actual co-financing as verified during Mid-term Review (MTR) or Terminal Evaluation (TE).
Add any comments on actual co-financing in particular any issues related to the realization of in-kind, grant, credits, loans, equity, non-grant instruments and other types of co-financing. (word limit=200) | Not applicable

## Risk Assesment
RISK ASSESMENT
IDENTIFIED RISKS
List all Risks identified in project preparation phase and what steps are being taken to mitigate them
Identified Risk | Current Status | Steps Taken to Mitigate Risk
There is a risk that the decisions made and actions taken during the project may not be ratified by future administrations. | LOW | The various executing parties are perceived as highly committed when it comes to strengthening institutions so that practices become incorporated and learned on the long run by technicians and administrations. To such end, training and result dissemination meetings continue to be conducted for all those involved in the project.
Lack of transparency or political interference in the allocation of resources. | LOW | Ongoing monitoring: not observed so far. The articulation with various organizations allows deepening control and mutual accountability, which favors transparency and ensures resources are duly allocated.
Not all required stakeholders are likely to take part in the process with the capacity and commitment needed. Afterwards, some stakeholders may be reluctant to adopt the proposed measures. | LOW | "COMPONENT 1: During the period considered, in addition to the multiple theory/hands-on workshops of training conducted to strengthen the capabilities of family agricultural producers to develop adaptation strategies to climate change, a symposium was organized for technical and operation planning exchange in San Javier (Santa Fé). More than 70 representatives of INTA, UCAR, INTI and the Secretariat of Family Agriculture of the MAGyP took part in this symposium with the purpose of analyzing the different technologies proposed to family agricultural producers placing emphasis on the response by the focus groups in order to refit such technologies and also work strategies. Some of the technologies proposed were fought back but inter-institutional strategies are already being developed to diminish the risk at hand. COMPONENT 2: INTA is holding different meetings with provincial institutions to negotiate the signature of Agreements that allow the integration of information from the Agrometeorological Station Networks (Ministry of Production, Cereal Stock Market, etc.). The first has already been signed. The signature of agreements warrants the integration of information from the Networks to the Agrometeorological Information and Management System (S.I.G.A) INTA, involved in the current project”.
Staff turnover in the Project Implementing Unit. Local project counterparts could experience staff turnover that could delay project implementation. | LOW | No project component is conceived outside the relevant public organizational structures and activities are secured by institutional agreements. Thus, the continuity of the implementation is guaranteed despite potential changes. Nonetheless, there has been no staff turnover so far.
Lack of sufficient information to characterize the scope of the changes brought about by the overheating of the troposphere. | LOW | The project provides for the use of modern techniques for remote monitoring supplemented via a network of field stations and modelling tools to be used to reduce the risk.
Activities implemented are not found to be cost-effective. | LOW | Continuation of work focused on implementing adaptation strategies to long draughts, seeking to develop precast concrete-slab cisterns to catch and store rainwater, and drilling wells to access underground water. These works allow small-scale agriculture producers to have water available for human consumption and their production activities during critical water shortage periods. These production activities are mainly targeted to home consumption, leading to savings in their household economies and, in some cases, to surpluses that they can trade in local markets. Therefore, it could be affirmed that priority has primarily been given to fulfilling a fundamental right. Profitability improvement of the production activities developed will be a long-term secondary result but it is not deemed a priority in this first stage.
Natural hazards (flood, drought, storm surges, storms) hamper some efforts. | MEDIUM-HIGH | The occurrence of intense precipitation during the period considered has exceeded average values for the north of the provinces of Santa Fe, Corrientes and Chaco, and have caused flooding in Santa Lucía, La Brava, Goya and San Martín (Chaco). This situation has delayed the progress of works in the towns mentioned as well as geoelectric surveys conducted by INTI (INTA/INTI Agreement).
Climate variability. Changing climatic conditions could affect the success of particular adaptation measures to be piloted during the life of the project. | MEDIUM | Climate variability during the implementation of the project may affect the success of the activities planned. Such success depends on the full execution of the activities planned with the Office of Agricultural Risk and on the interpretation and availability of agrometeorological information provided by the new Nimbus Stations, which are undergoing construction and installation in the area covered by the project.
Delays in executing funding at the regional level. | MEDIUM | Coordination and articulation with the different executing parties of the project continued to improve the administrative flow paths and to generate greater understanding of the procedures inherent to UCAR regarding procurement. The time of processes was thus reduced and greater fluidity was achieved in the use of funds by adapting such mechanisms and generating capabilities that would allow to work in a more efficient manner.
The Argentine Government is not able to leverage sufficient financial resources for the sustainability of project actions. | LOW | Sustainability of the project actions continues to focus on articulation and institutional strengthening allowing to generate long-term agreements and installed capacity at the public administration. The agreement with provincial institutions in Argentina’s northeast region (Ministry of Production, Cereal Stock Market, etc.) and basically the institutional installed character of INTA's network of stations ensure the sustainability and continuing operation of the Network on the long run. The articulation with the program “Actions of training for work” of the National Ministry of Work and Social Security keeps going strong. Financial resources have been mobilized to train family agricultural producers who take part in the project in the trade of “building community systems for access to water in family agriculture” in the project areas. Presently, there are 7 applicable work trainings that involve 140 construction workers. The INTA and the National Ministry of Agriculture, Farming and Fishery (MAGyP) have multiple programs intended for Family Agriculture that supplement the actions of the project, generating synergy among the public policies for this sector. In this regard, the articulation with the Infrastructure and Agro-Industry Office for Family Agriculture of the Secretariat of Family Agriculture of the MAGyP has been strengthened by combining technical and financial capabilities to accomplish the objectives. The INTA and the INTI have signed an agreement of technical cooperation for activities leading to access to groundwater under the project of reference. Such articulation enhances the technical capabilities in the territories and provides sustainability to the works that are being implemented in the project’s area.
Critical Risks Affecting Progress (Not identified at project design)
Identify Risks with a 50% or > likelihood of affecting progress of project
Identified Risk | Current Status | Steps Taken to Mitigate Risk
INTA's local technical teams have little experience in extra-institutional funding management. | LOW | INTA received a more intense support in the learning of administrative procedures, both at a central and a local level. Also, a regional workshop was held mid July where, among other activities, local technicians were trained in terms of the administrative flow path of the Project, and in terms of how documents must be submitted for the accountability of travel expenses and purchase of goods and services (subject to the sum thereof). The experience acquired allowed to leave behind the “direct purchase” method for the procurement of services and instead centralize purchases at a regional level from the second half of year 2015. The bidding of purchases allows conducting public and private bids, which lowers prices - the larger the volume of purchases is- and also it improves transparency. Follow-up (meetings, phone calls, refitting of administrative flow paths) has been enhanced for each one of the project activities, from the drafting of each application till execution of each purchase order, thereby improving communication and articulation among different areas of UCAR, INTA and provider firms. The risk derived from these circumstances is being handled at the level of UCAR and INTA authorities for its solution.
Administrative procedures delay the execution of activities. | LOW | Huge efforts have been devoted within the UCAR to make the adaptation project visible so that the role of UCAR as national implementation entity may be clearly understood by the “back office”.
UCAR does not have a budget available for the INTA and the ORA to execute the activities planned for the second semester of 2015. | HIGH | (Also explained in section 'Lessons Learned') By the end of 2014, the budget of UCAR programs and projects was raised, which later gave rise to the opening of a line of credit to use throughout the year. Upon making such application, the execution of INTA and ORA was treated as non-budgetary. That is why lending was authorized only for UCAR execution. Processes to solve this situation: upon detecting such problem in February 2015, a letter was sent to the Ministry of Agriculture, Farming and Fishery, in order to request before the National Budget Office an increase in lending for Fuente 21. Such increase was dismissed. In April 2015, the request was filed once again. At last, in May 2015, after presenting the case before the National Park Administration (APN, in Spanish), owners of a donation which will not be executed in 2015, part of the funding was transferred. Such process is an Administrative Ruling in nature, which is pending approval. The Ministry of Economy must sign it before it can be referred to Presidency for the Chief of the Cabinet of Ministers to sign it. Also, a new increase was applied for in July this year for Fuente 21. It is in the original stage of the processing.
Risk Measures: Were there any risk mitigation measures employed during the current reporting period? If so, were risks reduced? If not, why were these risks not reduced?
Add any comments relevant to risk mitigation (word limit = 500)
Yes. Greater fluidity has been accomplished in the administrative flow path, which has brought about greater budget execution in the period considered in this report. We have managed to implement payment of traveling expenses as well with the possibility of advance payments, generating a larger amount of activities in the period.

## Rating
RATING ON IMPLEMENTATION PROGRESS
For rating definitions please see bottom of page.
|  | Progress on Key Milestones |  | Expected Progress |  | Progress to Date | Rating
| Project Manager/Coordinator: | Improvements in the use and productivity of water for small-scale agriculture producers. |  | Progress is estimated towards project completion. |  | Progress was made in drilling wells and retrofitting roofs. A substantial progress was made in terms of families assisted through retrofitted roofs, reaching 70% of the final goal. Meanwhile, progress made in the boring of wells reaches 20% and population assisted with the wells, 25% of the anticipated goal. No progress was made in the activities of community dams or multi-purpose water systems on account of two main reasons: on the one hand, the relative complexity of these types of works for INTA, institution which has just recently started working with access to water. Dams and multi-purpose systems require much more inter-institutional work added to substantial requirements regarding procedures of procurement and work services. Due to the lessons learned after developing boreholes and water wells, now there is a lot of confidence in promoting these works beginning next year. On the other hand, there is the already explained limitation of funds for the period. | S
|  | Reducing the variability in income inflow of small-scale agriculture producers, promoting their continuity in the activity and in rural settings. |  | Progress is estimated towards project completion. |  | Progress was made in studies to characterize exposure of family agricultural producers to climate risk referring to producers whose main activity is horticulture in the Provinces of Santa Fe, Corrientes and Chaco. In addition, the first meetings with companies were held that will enable to develop a Pilot Plan of risk management aimed at small horticultural producers. Once the risk coverage instrument should have been designed, the rest of the activities of the subcomponent shall proceed. For the next period, progress is expected to be made with the feasibility study for cereal, oilseed and cotton producers. No further progress has been made due to the already explained fund limitation on account of lack of lending. | MS
|  | Increase in agricultural production of small-scale agriculture producers and reduction of economic and social vulnerability in the face of climate change and its variability. |  | Progress is estimated towards project completion. |  | Slow progress is observed in the activities anticipated for the subcomponent. Progress was made in activities of technical assistance reaching 5% of the families planned, who grew pastures for the preparation of forage reserves. Also, progress was made in the installation of crop protection structures covering 6% of the anticipated final goal. No progress was made in other activities. The reasons for that are mainly two: one the one hand, very pertinent proposals could not follow through on account of lack of local providers with capacity to respond to their demand. INTA is considering alternatives to overcome this situation. On the other hand, the situation of lack of lending of this year fails to encourage any promotion of the proposals, so none others were submitted. | MU
|  | Improvement and enhancement of the capacity of monitoring and evaluating climate change and its variability. |  | Progress is estimated towards project completion. |  | NIMBUS II automatic stations keep on being procured and installed. 6 new automatic stations have been installed in this period. And other 8 simple stations have been converted to full meteorological stations. In addition, an agreement between institutions has been signed involving the Ministry of Production of Corrientes, the Cereal Stock Market of Entre Ríos (BOLSACER), Corrientes’ Association of Rice Planters (ACPA) and the INTA for the integration of meteorological networks in the province of Corrientes. | S
|  | Systematized basic information freely available for effective decision-making regarding adaptation of producers to adverse conditions, and for local and regional planning. |  | Progress is estimated towards project completion. |  | Little progress has been made in this subcomponent due to the already explained lack of funding. Progress was indeed made in the performance of studies analyzing impact of the El Niño and La Niña events on seasonal precipitation and on yields of major crops in Argentina northeastern region. This has allowed to develop recommendations as to optimal sowing dates. Progress is expected to be made with the following activities starting next period. | MU
|  | Municipal and provincial government units, educational settings, and producers with capabilities to generate appropriate adaptive interventions. |  | Progress is estimated towards project completion. |  | Training on Adaptation to Climate Change with a duration of 4 days was given in December. This training included a dedicated training on Gender issues, as an introduction for the training that is being planned for the next period. During the year, training relating to the activities executed in component 1 (drilling of wells, construction of cisterns, filters) and component 2 (use of climate information) has been given showing significant progress vis-à-vis the trained technical experts goal set. A meeting was also held with the project’s executing parties to analyze the progress of the activities, any future actions and to share the results obtained to that day. Such activities had very positive results in making the main results known and strengthening the institutions involved. A monthly newsletter about project activities is being prepared. It will be distributed starting October 2015, with the objective of increasing the knowledge of the activities of the project and thus its ownership, among the participants of the project, who are disperse in the territory. | S
[6 empty] | Overall Rating | MS
(
Please Provide the Name and Contact information of person(s) responsible for completing the Rating section(*)
|  | Name: | Mario Nanclares
|  | Email: | mnanclares@prosap.gov.ar
|  | Name: | Mariano Poledo
|  | Email: | mpoledo@prosap.gov.ar
(*) This section has been prepared by the NIE, the Project Coordination Unit and the Management Control Area in charge of the physical and financial supervision of the progress of the project.
Please justify your rating. Outline the positive and negative progress made by the project since it started. Provide specific recommendations for next steps. . (word limit=500)
The Project is rated as MS given that most of the activities anticipated do not show any substantial progress for the period. The main reason that prevented progress at a higher pace was a problem of budget availability. Due to an internal problem, by the end of 2014, when budgets are requested of the Ministry of Economy, that pertaining to INTA and to ORA was rated as “not budgetary” of the UCAR. This led to those budget authorization requests to be overlooked, which gave rise to a budgetary restriction during the year, which was made up for with funds transferred from other donations. The positive progress of the period are mostly related to greater fluidity in the project procurement and administrative procedures, as well as an improvement in the articulation and communication between the executing parties and the NIE for a successful implementation of the project. In this regard, the problems observed during the first year of implementation were overcome, and the mechanisms for equipment procurement as well as other administrative mechanisms, deemed to be slow and too bureaucratic, were adjusted during the period. As for the progress of the activities, during the period, the main progress was achieved in the activities of the subcomponent of Implementation of improvements in the efficient use, catchment, harvesting and storage of water, particularly regarding the retrofitting of roofs to catch and store water. The goal anticipated for this subcomponent is expected to have been even exceeded. Also, the activities of Integration and expansion of the agro/hidrometeorological networks for the NEA region have made significant progress attaining 80% of the goal anticipated as regards simple meteorological stations converted to full stations, and new 6 automatic stations were installed, which amounts to 40% of the final goal. This has been rated as very positive. Also, progress was made in the integration of networks through an inter-institutional agreement involving public and private actors, which makes the project more sustainable. As for the downside of the period, the project was adversely affected by the above mentioned budgetary restriction. Overall, this affected the progress of the different activities but mostly that regarding procurement and works
|  | Progress on Key Milestones |  | Expected Progress |  | Progress to Date | Rating
Implementing Agency**
Overall Rating
(**) The executing entities were not required to fill in this section as they are responsible for some subcomponents of the project but lack the overall view of it.
Please Provide the Name and Contact information of person(s) responsible for completing the Rating section
Name:
Email:
|  | Progress on Key Milestones |  | Expected Progress |  | Progress to Date | Rating
Other
Overall Rating
Please Provide the Name and Contact information of person(s) responsible for completing the Rating section
Name:
Email:
|  | Please justify your rating and address the following points: 1. Indicate trends, both positive and negative, in achievement of outcomes as per the project indicators. 2. Detail critical risks that have affected progress. 3. Outline response to MTR undertaken this reporting period. 4. Outline action plan to address projects with a rating of HU, U or MU. Please keep your input to 1200 words |  | The Project is rated as MS given that the activities of the period are moving forward at a steady pace although during the period the progress anticipated could not be made. As previously mentioned in different points of the report, the reasons for such delay were of budgetary and exceptional nature. That is why, it will not affect the execution of the next period and progress of the project is expected to improve significantly over the next year. Also, the delay of the period does not jeopardize the accomplishment of the results anticipated, which are estimated to be reached given the progress of processes and actions of the project surveyed so far. In this regard, the activities of component 1, which had already started, continued to move forward and 70% of the goal could be attained in terms of families assisted through well boring. The activities contribute to enhance the agricultural production and to reduce economic and social vulnerability of producers/families in which the project’s contribution (material, technical and human) is perceived as essential. Also, progress was made in the analyses necessary to develop the pilot plan of insurance. Thus, significant progress is expected to be made in such subcomponent over the next period. Component 2, on the other hand, has made progress in terms of installation of automatic stations and conversion of simple stations reaching a total of 14 stations. Also, progress was made in inter-institutional negotiations to integrate meteorological networks in Argentina’s northeast that will allow sustainability of actions on the long term. This way, even though the activities of component 2.2. Development of an Early Alert and Decision-Making integral system have shown no significant progress, work is being made in the prior actions required that will later allow to advance in the development of such information systems and their availability over an easy-to-access web platform. In terms of component 3, focus was placed during training of technicians on the use of climate information for risk management and sensitization on the need for inclusion of the Climate Change topic in day-to-day practices. Also, the first meeting was held that brought together 4 institutions and 71 technicians to discuss the progress of the project and to disseminate results, which had a very positive evaluation. This way, in terms of progress of training oriented to technicians, 93% of the final goal was attained. Training of producers is also moving forward, although at a lower pace than the rest of the activities of the component.
Rating Definitions
|  |  |  | Highly Satisfactory (HS) | Project actions/activities planned for current reporting period are progressing on track or exceeding expectations to achieve all major outcomes/outputs for given reporting period, without major shortcomings. The project can be presented as “good practice”.
|  |  |  | Satisfactory (S) | Project actions/activities planned for current reporting period are progressing on track to achieve most of its major outcomes/outputs with only minor shortcomings.
|  |  |  | Marginally Satisfactory (MS) | Project actions/activities planned for current reporting period are progressing on track to achieve most major relevant outcomes/outputs, but with either significant shortcomings or modest overall relevance.
|  |  |  | Marginally Unsatisfactory (MU) | Project actions/activities planned for current reporting period are not progressing on track to achieve major outcomes/outputs with major shortcomings or is expected to achieve only some of its major outcomes/outputs.
|  |  |  | Unsatisfactory (U) | Project actions/activities planned for current reporting period are not progressing on track to achieve most of its major outcomes/outputs.
|  |  |  | Highly Unsatisfactory (HU) | Project actions/activities planned for current reporting period are not on track and shows that it is failing to achieve, and is not expected to achieve, any of its outcomes/outputs.

## Project Indicators
PROJECT Indicators
Please provide all indicators being tracked for the project as outlined in the project document
Type of Indicator (indicators towards Objectives, Outcomes, etc…)
Type of Indicator | Indicator | Baseline | Progress since inception | Target for Project End | % Progress on the Ultimate Goal
Objective | Number of families vulnerable to the adverse effects of climate change and its variability. | No climate change adaptation measures have been implemented up to date. | Total: 263 Women: 38 Young: 46 | 4000 | 6.575%
Outcome | % of producers with enhanced capacities to respond to and act upon climate variability. | No installed capacity or infrastructure. |  | 20% | 0%
Outcome | % of beneficiaries that noted an improvement in agriculture productivity linked to water supply. | To be determined during project implementation. |  | 50% | 0%
Outcome | % of beneficiaries that noted better access to water supply for consumption and irrigation. | 1,000 families will benefit from the water supply works. |  | 80% | 0%
Activity | Number of wells drilled and targeted families to access underground water. | Up to date, there are no wells drilled in the targeted communities. | 27 | 138 | 19.57%
|  | Up to date, there are no wells for the targeted families in the area. | Total: 35 Women: 16 Young: 1 | 138 | 25.36%
Activity | Number of families with roofs retrofitted for rainwater catchment and cisterns (disaggregated by gender). | Up to date, there are no reservoirs or roofs retrofitted for rainwater catchment in the area of intervention. | Total: 189 Women: 20 Young: 44 | 266 | 71.05%
Activity | Number of community reservoirs built for small and large livestock. | 0 community reservoirs built in the targeted communities up to date. |  | 145 | 0%
|  | 0 families assisted. |  | 739 | 0%
Activity | Number of multipurpose water supply systems built. | There have been no initiatives to build multipurpose water supply systems. |  | 140 | 0%
Outcome | % of targeted population covered by adequate risk-transfer mechanisms (disaggregated by gender). | 0% families within the project area with access to insurance. |  | 15% | 0%
Outcome | % of beneficiaries of risk transfer instruments that perceive diminished risks from extreme events. | No families are covered by this instrument. The goal is to have 787 families as beneficiaries of the risk transfer pilot program. |  | 50% | 0%
Activity | Development of feasibility study (oleaginosas) | No study has been conducted up to date. |  | 1 | 0%
Activity | Development of feasibility study (horticultura) | No study has been conducted up to date. | 1 | 1 | 100%
Activity | Number of families included in the Pilot Programs (disaggregated by gender). | No insurance coverage. |  | 787 | 0%
Activity | Evaluation of Pilot Programs implemented. | 0 evaluation conducted. |  | 1% | 0%
Outcome | Number of small-scale producers having more secure (increased) access to livelihood assets. | 0,8% families within the project area have been assisted in various agricultural practices. |  | 10% | 0%
Outcome | % of beneficiaries that noticed an improvement in their food security due to project activities. | 1,000 families will benefit from technical assistance. |  | 50% | 0%
Outcome | % of beneficiaries that noticed an increase in their income due to project activities. | 1,000 families will benefit from technical assistance. |  | 30% | 0%
Outcome | % of beneficiaries that have enhanced their access to markets. | 1,000 families will benefit from technical assistance. |  | 30%
Activity | Number of indigenous families receiving technical assistance (disaggregated by gender). | 15 families with fruit and vegetable gardens with irrigation, and raising small animals. |  | 82 | 0%
Activity | Number of families assisted in the management and use of forage resources (disaggregated by gender). | 29 families assisted in the management and use of forage resources. | Total: 23 Women: 1 | 473 | 4.863%
Activity | Number of families assisted in the implementation of soil management techniques (disaggregated by gender). | 0 families assisted. |  | 119 | 0%
Activity | Number of families assisted by means of crop protection structures (disaggregated by gender). | 20 families assisted. | Total: 16 Women: 1 Young:1 | 272 | 5.882%
Activity | Number of families assisted by technology and improvement of facilities (disaggregated by gender). | 20 families assisted. |  | 109 | 0%
Outcome | Density increase of hydro-meteorological stations and pluviometers. | Very low density of monitoring-station coverage. |  | 20% | 0%
Activity | Number of automatic meteorological stations fully operative. | 8 monitoring stations linked to SMN and INTA monitoring networks, 35 automatic stations and 22 pluviometers in the project area. | 7 | 18 | 38.89%
Activity | Number of simple automatic stations fully converted into complete measuring stations. | 0 complete stations converted. | 8 | 10 | 80%
Activity | % of meteorological networks integrated. | 0% networks integrated. | 30 | 100% | 30%
Activity | % of Information Systems of local nodes fully operational. | 0% of Information Systems of local nodes operational. | 40 | 100% | 40%
Activity | % of online availability of the integrated information system. | 0% of online availability of the integrated information system. |  | 100% | 0%
Outcome | Number of government staff members/decision makers and producers using an early warning system and a climate knowledge platform as basis for decision taking. | The Early Warning System only partially covers the Provinces of Chaco and Santa Fe. |  | 25% | 0%
Activity | % of compilation and assessment of databases and georeferenced mapping in the area of intervention. | 0% compilation and assessment performed on existing databases and maps. |  | 100% | 0%
Activity | Number of tests performed. | 0 tests performed. |  | 3 | 0%
Activity | % of project area with risk maps. | 35% of project area with risk maps developed. |  | 70% | 0%
Activity | % of implementation of the soil moisture monitoring system. | 30% of project area with a monitoring system installed. |  | 60% | 0%
Activity | % of analysis developed of climate change scenarios and climate trends on crop production. | No available regional climate change scenarios or knowledge of the impact on crop production. | 85 | 100% | 85%
Activity | Development of an early warning system. | No hydrological monitoring system or vulnerability assessment at an appropriate scale or in place. |  | 1 | 0%
Activity | Development of an early warning system. | No integrated decision making system with a weather alert component in place. |  | 1 | 0%
Activity | % of development of the web platform. | 0% platform developed. |  | 100% | 0%
Outcome | % of staff and producers trained to implement measures to respond to, and mitigate impacts of, climate-related events (disaggregated by gender). | No training or capacity building activities done for the 4,000 families involved in project activities and 200 technical experts and government officials up to date. |  | 60% | 0%
Activity | % of targeted staff members and population trained in predicted adverse impacts of climate change and adequate responses. | No training or capacity building activities done for technical experts up to date (200 technical experts). | 74.5% | 80% | 93.12%
|  | No training or capacity building activities done for the targeted population up to date (4,000 beneficiaries). | 5.825% | 80% | 7.281%
Activity | Number of institutions trained in the use of an early warning system and related tools. | No training or capacity building activities done up to date. | 4 | 5 | 80%
Activity | Number of publications and meetings conducted for dissemination. | 3 publications during project preparation. | 5 | 8 | 62.5%
|  | No meetings held for dissemination. | 1 | 3 | 33.33%

## Lessons Learned
QUALITATIVE MEASURES and LESSONS LEARNED
Please complete the following section every reporting period
Implementation and Adaptive Management | Response
What implementation issues/lessons, either positive or negative, affected progress? | Progress was mainly affected in an adverse manner by the lack of available funds (see explanation below). This caused involuntary delays in the performance of the activities anticipated. On the side of positive lessons learned, the permanent articulation between the various executing parties and the NIE made it possible to move forward more fluidly in terms of project administration. Also, special emphasis was placed on articulating with other institutions in the territory including but not limited to local municipalities and other public institutions such as the INTI or ministries of production, which also brought to the table technical or financial resources, which allowed leveraging the project actions and achieving greater coverage and effect in the area of intervention. This also enables the sustainability of the actions in the long run.
Were there any delays in implementation? If so, include any causes of delays. What measures have been taken to reduce delays? | Indeed, there were delays in the implementation during the 2015 period due to problems of fund availability. By the end of 2014, the budget of UCAR programs and projects was raised, which later gave rise to the opening of a line of credit to use throughout the year. Upon making such application, the execution of INTA and ORA was treated as non-budgetary. That is why lending was authorized only for UCAR execution. Upon detecting such problem in February 2015, a letter was sent to the Ministry of Agriculture, Farming and Fishery, in order to request before the National Budget Office an increase in lending for Fuente 21. Such increase was dismissed. In April 2015, the request was filed once again. At last, in May 2015, after presenting the case before the National Park Administration (APN, in Spanish), owners of a donation which will not be executed in 2015, part of the funding was transferred. Such process is an Administrative Ruling in nature, which is pending approval. The Ministry of Economy must sign it before it can be referred to Presidency for the Chief of Cabinet of Ministers to sign it. Also, a new increase was applied for in July this year for Fuente 21. It is in the original stage of the processing.
Describe any changes undertaken to improve results on the ground or any changes made to project outputs (i.e. changes to project design) | One of the actions implemented to improve the results of the projects was the beginning of the on-site visits by project coordination (INTA and UCAR) to detect potential changes of design aimed at improving results. Also, an external consultant was hired to conduct a permanent follow-up in the territory and collect sensitive information for the improvement of the project’s inter-institutional management. In addition, an external consultant was hired to perform follow-up visits to the different locations where activities are being executed. Such consultant collects information on the problems and delays, and they also verify the actions performed and obtain information on gender issues and on how those intended as beneficiaries make the project their own or not. Such information is being processed and shall be soon available for its presentation and analysis. Work continued in the form of meetings between INTA and UCAR to overhaul the administrative flow path with the purpose of shortening terms for agreement performance, and advanced payment of traveling expenses to technicians in the project’s area could be maintained. All of the foregoing has led to improve project’s results. Also, the thorough follow-up has continued with INTA’s local technicians and providers awarded with the contracts/bids to ensure success of the scheduled goals. During the period considered, annual planning was performed with all coordinators of PRETs [Regional Projects with a Territorial Approach] of the INTA in the project’s area. Such consolidated information has been strategic for the preparation of the bidding documents for the purchase of materials so as to reduce administrative times for execution of the scheduled works.
How have gender considerations been taken into consideration during the reporting period? What have been the lessons learned as a consequence of inclusion of such considerations on project performance or impacts? | Specific training on gender was performed in December. A workshop was performed on “Sensitization and introduction to the topic of Climate Change Effects on gender gaps”. Such workshop had a methodology that included time for the development of theoretical contents and other times for participatory debates around topics. The purpose proposed was to question the effects of climate change using the gender transversal approach. Gender approach: What is gender? Difference between sex and gender, natural vs. culturally constructed; Sex-Gender system. What are and where do gender gaps stem from? Some tools to identify gender gaps; What effect does Climate Change pose over gender gap? The role of female technicians in gender-based Rural Development. A new training is planned for the next period, with the objective of addressing this perspective in greater depth.
Please complete the following section at mid-term and project completion (*)
Lessons for Adaptation | Response
Climate Resilience Measures
What have been the lessons learned, both positive and negative, in implementing climate adaptation measures that would be relevant to the design and implementation of future projects/programs for enhanced resilience to climate change? | -
What is the potential for the climate resilience measures undertaken by the project/program to be replicated and scaled up both within and outside the project area? | -
Concrete Adaptation Interventions
What have been the lessons learned, both positive and negative, in implementing concrete adaptation interventions that would be relevant to the design and implementation of future projects/program implementing concrete adaptation interventions? | -
What is the potential for the concrete adaptation interventions undertaken by the project/program to be replicated and scaled up both within and outside the project area? | -
Community/National Impact
What would you consider to be the most successful aspects for the target communities? | -
What measures are/have been put in place to ensure sustainability of the project/program results? | -
What measures are being/could have been put in place to improve project/program results? | -
Knowledge Management
How has existing information/data/knowledge been used to inform project development and implementation? What kinds of information/data/knowledge were used? | -
If learning objectives have been established, have they been met? Please describe. | -
Describe any difficulties there have been in accessing or retrieving existing information (data or knowledge) that is relevant to the project. Please provide suggestions for improving access to the relevant data. | -
Has the identification of learning objectives contributed to the outcomes of the project? In what ways have they contributed? | -
(*) To be completed following the mid term evaluation

## Results Tracker
Results Tracker for Adaptation Fund (AF) Projects
Goal: Assist developing-country Parties to the Kyoto Protocol that are particularly vulnerable to the adverse effects of climate change in meeting the costs of concrete adaptation projects and programmes in order to implement climate-resilient measures. Impact: Increased resiliency at the community, national, and regional levels to climate variability and change.
Important: Please read the following guidance document (also posted on the Adaptation Fund website) before entering your data
Link: http://www.adaptation-fund.org/sites/default/files/Results%20Framework%20and%20Baseline%20Guidance%20final.pdf
Adaptation Fund Strategic Results Framework
Project ID
Implementing Entity | Unidad para el Cambio Rural
Type of implementing entity | NIE
Country | Argentina
Region | Latin America and Caribbean
Sector | Multi-sector
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Impact: Increased resiliency at the community, national, and regional levels to climate variability and change | Core Indicator: No. of beneficiaries |  | Total (direct + indirect beneficiaries) (*) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project (*) |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project
|  | Total |  | 4000 |  | Total | 4000 | 4000 |  | Total |  |  |  | Total
|  | % of female beneficiaries |  | 20% |  | % of female beneficiaries | 20% | 20% |  | % of female beneficiaries |  |  |  | % of female beneficiaries
|  | % of Youth beneficiaries |  |  |  | % of Youth beneficiaries |  |  |  | % of Youth beneficiaries |  |  |  | % of Youth beneficiaries
(*) not yet estimated
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 2: Strengthened institutional capacity to reduce risks associated with climate-induced socioeconomic and environmental losses | Indicator 2: Capacity of staff to respond to, and mitigate impacts of, climate-related events from targeted institutions increased | Number of staff targeted |  | Sector | Capacity level | Number of staff targeted |  | Sector | Capacity level | Number of staff targeted |  | Sector | Capacity level | Number of staff targeted |  | Sector | Capacity level
|  | Total | 200 | Agriculture | 2: Low capacity | Total | 160 | Agriculture | 4: High capacity | Total |  |  |  | Total
|  | % of female targeted | 20% |  |  | % of female targeted | 20% |  |  | % of female targeted |  |  |  | % of female targeted
Output 2.1 Strengthened capacity of national and sub-national centres and networks to respond rapidly to extreme weather events | Indicator 2.1.1: No. of staff trained to respond to, and mitigate impacts of, climate-related events | Total staff trained | % of female staff trained | Type |  | Total staff trained | % of female staff trained | Type |  | Total staff trained | % of female staff trained | Type |  | Total staff trained | % of female staff trained | Type
|  |  |  | Public |  |  |  | Public
| Indicator 2.1.2: No. of targeted institutions with increased capacity to minimize exposure to climate variability risks | Type | Scale (*) | Sector | Capacity level | Type | Scale | Sector | Capacity level | Type | Scale | Sector | Capacity level | Type | Scale | Sector | Capacity level
|  | Public | National | Agriculture | 2: Low capacity | Public | National | Agriculture | 4: High capacity
(*) there are national and regional institutions targeted