## Overview
Project Performance Report (PPR)
Period of Report (Dates)
| Project Title: | Reducing vulnerability to climate change in North Western Rwanda through community based Adaptation
| Project Summary: | The Reducing Vulnerability to Climate Change in North West Rwanda through Community Based Adaptation (RV3CBA) Project is executed under Rwanda Natural Resources Authority (RNRA) and implemented by the Ministry of Natural Resources (MINIRENA). The main objective is to reduce vulnerability to flooding and rainfall variation through the promotion of climate resilient production and post harvest systems, supporting livelihood diversification and capacity building to scale up successful climate adaptation strategies in Nyabihu and Musanze Districts. To achieve this objective, the project implementation is focusing on the following main components:  Support for the transition from exploitive farming practices to sustainable alternative off-farm livelihoods;  Adaptation to climate change (rainfall intensity and duration) through integrated land and water management to support climate-resilient production and post-harvest systems;  Capacity building of local institutions to improve understanding of climate change impacts and scale up effective adaptation strategies at the local level.
|  |  | Countries | Project Type: |  | GEF Focal Area: | GEF 4 Focal Areas | GEF 2 / 3 Operational Programme: | Overall Rating of the project in the evaluation by the project evaluator: | GEF-4 Focal Area Strategic Program: | GEF-3 Focal Area Strategic Program:
| Database Number: | N/RW/1 | Afghanistan | FP | Yes | Biodiversity | 1 | 1 | U | BD-SP1-PA Financing | 1: Arid & semi-arid ecosystems
Implementing Entity (IE) [name]: |  | Ministry of Natural Resources( MINIRENA) | Albania | MSP | No | Climate Change Adaptation | 2 | 2 | S | BD-SP2-Marine PA | 2: Coastal, marine & freshwater ecosystems
| Type of IE: | National | Algeria | EA |  | Climate Change Mitigation | 3 | 3 | MU | BD-SP3-PA Networks | 3: Forest ecosystems
| Country(ies): | Rwanda | Angola |  |  | International Waters | 5 | 5 | Good | BD-SP5-Markets | 13: Conservation and Sustainable Use of Biological Diversity Important to Agriculture
Relevant Geographic Points (i.e. cities, villages, bodies of water): |  | Rwanda | Argentina |  |  | Multiple Focal Area |  |  |  | BD-SP7-Invasive Alien Species(IAS) | 6: Promoting the adoption of renewable energy by removing barriers and reducing implementation costs
[8 empty] | CC-SP2- Industrial EE | 8: Waterbody based operational program
| Project Milestones | [6 empty] | CC-SP3-RE,CC-SP4-Biomass | 9: Integrated Land and Water multiple focal area
| Milestone |  | Bahamas | [6 empty] | CC-SP5-Transport | 10: Contaminants based operational program
AFB Approval Date: |  | 2013-12-01
IE-AFB Agreement Signature Date: |  | 2013-11-01 | [6 empty] | CC-SP6-LULUCF | 12: Integrated Ecosystem Management
Start of Project/Programme: |  | 2014-06-01 | [6 empty] | Cross cutting capacity building | 14: Persistent Organic Pollutants
Mid-term Review Date (if planned): |  | 2016-01-01
| Terminal Evaluation Date: | 2017-09-01
|  | List documents/ reports/ brochures / articles that have been prepared about the project. | Cyprus
|  | Project reports have been done on quartely and annual basis. Project brochures have been developed and published in Kinyarwanda and English languages. Moreover, several articles have been published in local newspapers as well as on RV3CBA project website. | Czech Republic
List the Website address (URL) of project. |  |  | Democratic People's Republic of Korea
|  | www.rv3cba.rnra.rw | Democratic Republic of the Congo
Denmark
| Project contacts: |  | Djibouti
National Project Manager/Coordinator |  |  | Dominica
| Name: | NGABONZIZA Prime | Dominican Republic
| Email: | prime0467@yahoo.fr | Ecuador
| Date: |  | Egypt
| Government DA |  | El Salvador
| Name: | MUKARUBIBI Fatina | Equatoral Guinea
| Email: | fmukarubibi@minirena.gov.rw | Eritrea
| Date: |  | Estonia
| Implementing Entity |  | Ethiopia
| Name: | MUSABYIMANA Innocent | Fiji
| Email: | musasebin2000@yahoo.fr | Finland
| Date: |  | France
| Executing Agency |  | Gambia
| Name: | Dr. NKURUNZIZA Emmanuel | Georgia
| Email: | emmanuel.nkurunziza@rnra.rw | Germany
| Date: |  | Ghana
| Executing Agency |  | Greece
| Name: |  | Grenada
| Email: |  | Guatemala
| Date: |  | Guinea
| Executing Agency |  | Guinea Bissau
| Name: |  | Guyana
| Email: |  | Haiti
| Date: |  | Honduras
Hungary
Iceland
India
Indonesia
Iran (Islamic Republic of)
Iraq
Ireland
Israel
Italy
Jamaica
Japan
Jordan
Kazakhstan
Kenya
Kiribati
Kuwait
Kyrgyzstan
Lao People’s Democratic Republic
Latvia
Lebanon
Lesotho
Liberia
Libyan Arab Jamahiriya
Liechtenstein
Lithuania
Luxembourg
Madagascar
Malawi
Malaysia
Maldives
Mali
Malta
Marshall Islands
Mauritania
Mauritius
Mexico
Micronesia, Federated States of
Monaco
Mongolia
Montenegro
Morocco
Mozambique
Myanmar
Namibia
Nauru
Nepal
Netherlands
New Zealand
Nicaragua
Niger
Nigeria
Norway
Oman
Pakistan
Palau
Panama
Papua New Guinea
Paraguay
Peru
Philippines
Poland
Portugal
Qatar
Republic of Korea
Republic of Moldova
Romania
Russian Federation
Rwanda
Saint Kitts and Nevis
Saint Lucia
Saint Vincent and the Grenadines
Samoa
San Marino
Sao Tome and Principe
Saudi Arabia
Senegal
Serbia
Seychelles
Sierra Leone
Singapore
Slovakia
Slovenia
Solomon Islands
Somalia
South Africa
Spain
Sri Lanka
Sudan
Suriname
Swaziland
Sweden
Switzerland
Syrian Arab Republic
Tajikistan
Thailand
The former Yugoslav Republic of Macedonia
Timor-Leste
Togo
Tonga
Trinidad and Tobago
Tunisia
Turkey
Turkmenistan
Tuvalu
Uganda
Ukraine
United Arab Emirates
United Kingdom of Great Britain and Northern Ireland
United Republic of Tanzania
United States of America
Uruguay
Uzbekistan
Vanuatu
Venezuela, Bolivarian Republic of
Viet Nam
Yemen
Zambia
Zimbabwe

## FinancialData
Financial information: cumulative from project start to [insert date]
DISBURSEMENT OF AF GRANT FUNDS
How much of the total AF grant as noted in Project Document plus any project preparation grant has been spent to date?
Estimated cumulative total disbursement as of [December 2014] | 1300302
Add any comments on AF Grant Funds. (word limit=200) | Basing on the activities and budget planned in the project document,The Disbursement of funds was done reasonably. Though the planned budget was executed at 45,6% (Contracts not yet paid are not considered here), that was due to the fact that the project started its activities in june 2014 instead of January 2014 as expected, it means in the real sense a full year will end in june 2015. Moreover, when you look at the procurement data, most of the contracts with other parties were not yet fully paid in 2014, and yet it is a project engagement which has to be realised as soon as a service/work is delivered. Therefore, note that this reporting period is not a year but six months; reason why we have judged the disbursement to be reasonable.
EXPENDITURE DATA
List ouput and corresponding amount spent for the current reporting period | ITEM / ACTIVITY / ACTION | AMOUNT
FOR NEE
| Output 1.1: Community level mobilisation and climate adaptation plans developed and implemented. | 13510
| Output 1.2: Investment in integrated land and water management practices | 911004
| Output 1.3: Diversification and integration of crop and livestock production systems to minimise the impact of variable rainfall on rural livelihoods (agro-sylvopastoral systems etc.). | 2300
| Output 1.4 Introduction of climate-resilient crop/fodder varieties and agronomic practices (short season crops, seasonal pastures etc.). | 4100
| Output 1.5 Introduction of climate resilient post-harvest processing and storage systems for safe handling and storage of agricultural produce during extreme climate events (floods, rains). | 3000
| 2.1 Identification of viable alternative livelihood opportunities and constraints | 4500
| Output: 2.2 Development of Rural Development hubs within selected imidugudus to promote and facilitate sustainable, market-linked and diversified livelihoods | 2500
| Output 2.3 Resettlement of 200 households living in high-risk zones to Rural Development Hubs. | 1000
| Output 2.4 Increased investment in market development (infrastructure, transport, storage, market research etc.). | 6800
| Output 2.5 Increased investment in and access to renewable energy (Biogas plants, solar etc.) for enterprise development. | 0
| Output 3.1 Training of government technical staff on climate risk management and flood and landslide prevention measures for further scaling up. | 12200
| Output 3.2 Sharing project results and lessons learned and mainstreaming new approaches in local and national planning. | 2600
| Compensation of employees | 148577
| Office rent | 11064
| Computers and IT equipment | 4865
| Phone cards | 5674
| Supplies and services | 10770
| Other Expenses/Bank charges | 64
| TOTAL NEE | 1144528
FOR NIE
| Output1.1: Finance, Budget and Treasury management | 39746
| Output1.2: Project Performance Management | 53350
| Output 1.3: Programme Management Support | 54000
| Output 1.4: Information and Telecoms Support | 8678
| TOTAL NIE | 155774
| TOTAL NEE+NIE | 1300302
PLANNED EXPENDITURE SCHEDULE
List outputs planned and corresponding projected cost for the upcoming reporting period | ITEM / ACTIVITY / ACTION | PROJECTED COST | Est. Completion Date
| Output 1.1: Community level mobilisation and climate adaptation plans developed and implemented. | 108768 | 2016-06-30
| Output 1.2: Investment in integrated land and water management practices | 1823647 | 2016-06-30
| Output 1.3: Diversification and integration of crop and livestock production systems to minimise the impact of variable rainfall on rural livelihoods (agro-sylvopastoral systems etc.). | 64725 | 2016-06-30
| Output 1.4 Introduction of climate-resilient crop/fodder varieties and agronomic practices (short season crops, seasonal pastures etc.). | 7850 | 2016-06-30
| Output 1.5 Introduction of climate resilient post-harvest processing and storage systems for safe handling and storage of agricultural produce during extreme climate events (floods, rains). | 260596 | 2016-06-30
| 2.1 Identification of viable alternative livelihood opportunities and constraints | 11303 | 2016-06-30
| Output: 2.2 Development of Rural Development hubs within selected imidugudus to promote and facilitate sustainable, market-linked and diversified livelihoods | 422292 | 2016-06-30
| Output 2.3 Resettlement of 200 households living in high-risk zones to Rural Development Hubs. | 1704866 | 2016-06-30
| Output 2.4 Increased investment in market development (infrastructure, transport, storage, market research etc.). | 365777 | 2016-06-30
| Output 2.5 Increased investment in and access to renewable energy (Biogas plants, solar etc.) for enterprise development. | 30986 | 2016-06-30
| Output 3.1 Training of government technical staff on climate risk management and flood and landslide prevention measures for further scaling up. | 38933 | 2016-06-30
| Output 3.2 Sharing project results and lessons learned and mainstreaming new approaches in local and national planning. | 31744 | 2016-06-30
| TOTAL NEE | 4871487
| Output1.1: Finance, Budget and Treasury management | 43781 | 2016-06-30
| Output1.2: Project Performance Management | 77234 | 2016-06-30
| Output 1.3: Programme Management Support | 7803 | 2016-06-30
| Output 1.4: Information and Telecoms Support | 21843 | 2016-06-30
| Total NIE | 150661
| Total NEE+NIE | 5022148
ACTUAL CO-FINANCING (If the MTR or TE have not been undertaken this reporting period, DO NOT report on actual co-financing.)
How much of the total co-financing as committed in the Project Document has actually been realized?
Estimated cumulative actual co-financing as verified during Mid-term Review (MTR) or Terminal Evaluation (TE).
Add any comments on actual co-financing in particular any issues related to the realization of in-kind, grant, credits, loans, equity, non-grant instruments and other types of co-financing. (word limit=200)

## Risk Assesment
RISK ASSESMENT
IDENTIFIED RISKS
List all Risks identified in project preparation phase and what steps are being taken to mitigate them
Identified Risk | Current Status | Steps Taken to Mitigate Risk
1) Low awareness and acceptance of the need to tackle climate change among key practitioners limits the support for action on climate change within key sectors. | Medium | 62 Climate change resilient groups have been formed in the project intervention area in the aim of raising awareness; 169 existing cooperatives have also been identified with the aim of working with them in diferrent project activities. The project has conducted different meetings, workshops and trainings with various stakeholders on climate change issues. The Project team has also done consultations with other stakeholders in the area to know the best approach to raise awareness in the project intervention area.
2) District administrations lack the resources and capacity to engage fully with the project and integrate project outputs with development plans. | Low | The local government officials starting from the Mayors of Districts, Vice-Mayors, Executive secretaries of sectors, etc. are involved and committed to closely work with the project implementation unit by providing advices and support where necessary. some of the project activities are even include into the District performance contracts.
3) Climatic conditions (destructive rains and unpredictable seasons) hamper project interventions (planting etc.) and could affect adaptation measures being implemented and undermine confidence of local communities in adaptation measures promoted by the project. | Medium | The project is in process of recruiting a consultant to carry out a study to provide a long solution of mugogo low land. The Project has constructed preventive infrastructures like bench terraces, progressive terraces, protection of river banks and maintainance of Mugogo low land; we hope this will give solutions to this kind of risk.
4) Limited capacity of partner organisations to deliver project outputs. | Medium | The Project has conducted workshops and consultation meetings with different stakeholders in the intervention area to cope the best practices and build capacity. This exercise will be kept ongoing with the project progress.
5) Failure to create ownership of the project at the local level. | Low | The local leaders and community have shown their commitments in participating with the project and ensured their contribution in sustaining its activities. This was made possible by strong and continous mobilization done by the project team and community animators.
6) Price fluctuations which could a) affect the costs of implementation and lead to budgetary constraints b) affect costs and returns from enterprise development activities among project beneficiaries. | Low | The project will conduct a study on regional price fluctuations and the way they could affect the budget of implementation and costs and returns from enterprise development activities.
7) Delays in the disbursement of funds, procurement and Institutional inefficiencies (lengthy approval processes etc.) delay the resulting in delayed recruitment of project staff and hence project implementation. | Medium | To avoid the experienced procurement delays, the executing entity has decided to recruit a specific procurement officer of the project instead of the the procurement officer of RNRA to add on her permanent responsibilities the project tenders.
8) High costs and insufficient supply of electricity impedes livelihood diversification (Rwanda is expensive compared to other countries in the region at $0.24/kwh compared to Kenya’s $0.15/ kWh, Uganda’s $0.17/kwh, and Tanzania’s $0.05/kwh (EDPRS 2, 2013). | Medium | The project will conduct a study the project regional cost of electricity compared to other livelihood diversification source of energies.
9) Failure to adopt a holistic approach necessary for this type of project due to a lack of expertise within the project team or lead agency. | Low | The Project team is made by experienced specialists in different domains and consultations are done for technical advices. The project collaborate with other projects in the intervention area.
10) Lack of co-ordination with other climate change projects in Rwanda limits the capacity of implementing agency to learn from and build on the experiences of related projects. | Low | The PIU consults other similar projects for some activities when needed.
11) Weak capacity of coordination for concerned services in the optional choice of technical solutions and project planning. | Low | The project has experienced staff with coordination and technical skills.
12) Lack of transparency or political interference in allocation of project resources. | Low | To ensure transparency and accountability, the country has put in place financial management measures (like having the Project finance officer, the Project manager and the Chief budget manager).
13) Lack of capacity and commitment to project outcomes and resistance to adopting the proposed measures. | Medium | To avoid resistance from the project beneficiaries and other stakeholders in owning and implementating project activities, the PIU has formed climate resilient groups as mentioned in the project document ( 55groups which means 1 group per Cell in 8 sectors); the members of those groups are the first targeted project beneficiaries who got jobs in terracing and other activities that the project has started. from the climate resilient groups, members have elected their representatives (President, Vice President and Secretary) whom the PIU meet when nessecary into meetings and workshops for better communication with members of the groups. The Project has also organised election of 16 community animators ( 2/sector: Gender balance has been considered) whom works closely with the Project Implementation Unit and the Project beneficiaries for information sharing and sensitization. After all, The local government is fully involved as they are the ones who knows better the attittudes and behaviors of their citisens. Therefore, all the above mentioned organs helps to avoid resistance.
14) Staff turnover in the Project Implementing Unit may hamper progress. | Low | The governement of Rwanda has initiated the staff retention policy ( work advantages and improved working environment).
15) Local district administrations are unwilling to incorporate climate adaptation into district plans and budgets. | Low | The Project team works closely with the District administrations during the implementation to ensure the local ownership.
16) Conflicting interests among stakeholders with respect to land use (e.g. Crop Intensification Programme which is focussed on maximising agricultural production by promoting mono-cropping and the use of chemical inputs) and access to and use of natural resources hampers erosion control and other adaptation measures. | Low | The project started by raising awareness through community mobilization in the selected sites for terraces construction, where the PIU, NIE, NEE and Local leaders explained the bojectives of the project to the community, the importance of terraces and use of inputs in increasing the production, and assured them to be facilitated in this process ( construction of bench and progressive terraces and provision of organic manure); it was very fortunate that the community welcomed the project's initiatives and it was realised that they were aware of most of the information as these are included into government initiatives through EDPRS and Umurenge VUP. In addition to this, the project has organs that helps in addressing conficts during its implenentation ( National and Local Steering Committees, and the technical advisory group).
17) Loss of livelihood for resettled families. | Low | The project targeted beneficiaries are the first priority to work with the project in diferrent activities such as erosion control activities, and according to what is observed on the field; people are happy and satisfied with what they get from the project as wages. The project beneficiaries already linked with SACCOs are around 3613(2,204 women equivalent to 61%). The total amount of money injected directly in beneficiaries as wages is 143,959,000Rwf. The shares paid by beneficiaries in SACCOs are so far 14,726,000Frw. Regarding the construction of the model village, the Vulnerable families will be the priority to get employment and support.
18) Resistance to adoption of new livelihood for resettled households. | Low | Families to be resettled do not have where to live by then, so the sensitization was no difficult because they have had that they are going to get the first solution of being given a house which is a very great and important support for them. Together with the Local leaders, the PIU has explained them the importance of living into green model villages as they will have easy access to electicity, water, schools, and other necessary basic infrastructures. they have also been told about the new livelihoods rather than agriculture, and this sensitization shall continue even after having been resettled. the mitigation of this risk could not be difficult because resettlement has been a government initiative for long, and the community is aware for it since long.
19) Delayed compensation to land owners affected by resettlement programme. | Low | The valuation of land and properties has ended and the owners have agreed and signed the results of the valuation. The expropriation process is going to be done as early as possible.
20) Low awareness of benefits of resettlement results in community resistance. | Low | The project has invested in sensitisation and awareness building by explaining the benefits of resettlement to families to be resettled and those to be expropriated. For families to be expropriated, the project decided that nobody in the site will be expropriated and leave the site, because it would create another problem that the expropriated persons can go also into High risk zones. Therefore, a person living in the site will release only the non constructed land and remain with his/her house. A sub-standard house will be put on the standards of others by the project still. these explanations were welcomed without any objections.
21) Crop destruction during resettlement. | Low | During this reporting period, as constructions have not yet started there is no worry that crops will be destroyed; and once the constructions will start, the project will ensure that all crops are harvested before commencement of construction activities.
22) Refusal of some households to share their lands for construction of houses. | Low | Land owners have been sensitised and agreed to share their lands with others. This exercise was facilitated by Local authorities (District, Sector, Cell and Village). The rwandan expropriation law was the basis of explanations, and this law prevent that the land owners meets problems during this process. the land to be expropriated was valued, and their owners have signed to agree the value attributed their lands and properties.
23) Poor targeting of households for resettlement results in less vulnerable households being resettled. | Low | During the project preparation, the vulnerable HH to resettle have been identified in collaboration with Nyabihu district considering their level of vulnerability categorised by Ubudehe. The project will continue to ensure effective targeting of vulnerable households to resettle. .
24) New settlements do not make adequate provisions for human waste management. | Low | The consultancy company which will design and supervise the model green village will have to respect the terms of referrences and this article of waste management is included in the ToRs. it is in this regards that the Project will ensure proper management of human waste by connecting latrines to biogas digesters to provide a source of gas (for lighting and cooking) and fertiliser.
25) Poor management of solid waste in new settlements results in pollution and disease risk. | Low | The project intends to build a green model village with waste management principles (Rainwater harvesting tanks, biogas and waste management). After the design of the model village by the consulting company, the project will invite differrent stakeholders experts in resettlement for validation to avoid this risk ( the resettlement task forse will be involved, District, Rwanda Energy group/REG, WASAC, Ministry of Disaster Management/MDIMAR,...).
26) Continued unplanned settlement and unsustainable farming practices hinder progress. | Low | Project will build awareness on the effects of unplanned settlements and unsustainable farming practices and will introduce advocacy measures to promote the adoption of improved climate resilient farming practices.
27) Lack of incentives for local communities to participate and cooperate in interventions that do not yield immediate financial value or reduce incomes in the short term, but aim at longer-term resilience. This may reduce stakeholder engagement and participation. | Low | The project incorporates activities that yield immediate benefits for commuties in terms of skill development and income generation. The project started building awareness on these benefits. Also affected people got jobs during the project implementation.
28) Religious belief systems (e.g. 7th day Adventism which is prevalent in the project area) preclude certain income generating activities such as raising and eating rabbits, pigs or ducks. | Medium | Intensive consultations with local communities during preparation and implementation of the project.
29) Cultural views of women may impede their ability to take up some of the identified livelihood opportunities especially in construction (e.g. carpentry and bricklaying). | Medium | The project undertook awareness meetings to empower women for carrying out identified livelihoods opportunities including carpentry and bricklaying.
Critical Risks Affecting Progress (Not identified at project design)
Identify Risks with a 50% or > likelihood of affecting progress of project
Identified Risk | Current Status | Steps Taken to Mitigate Risk
transport means for project staff was the main challenge at the starting phase. | Low | the project staff managed to share one car hired for field works as they were waiting for the project car and moto cycles which were in tender process.
Approval of budget and activities delay at the executing agency instead of at the PIU level. | Low | the executing entity has allowed the Project coordination to authorise some activities like approval of travel clearances and sign the project correspondances(delegation of power, and the recruitement of the project procurement officer is in process.)
Heavy rain which sometimes destroyed the progress recorded and delay of activities | Low | this issue was particularly in mugogo low land but the project kept on maintaining the channels and caves. The project is also to conduct a study on long solution on mugogo low land.
Risk Measures: Were there any risk mitigation measures employed during the current reporting period? If so, were risks reduced? If not, why were these risks not reduced?
Add any comments relevant to risk mitigation (word limit = 500)
All identified risks have been managed, they all fall in the range of Low and Medium and the mitigation strategic solutions are promising.

## Rating
RATING ON IMPLEMENTATION PROGRESS
For rating definitions please see bottom of page.
| Progress on Key Milestones |  | Expected Progress |  | Progress to Date | Rating
Project Manager/Coordinator: | Output 1.1: Community level mobilisation and climate adaptation plans developed and implemented. |  | The project had the targets for this 1st output of assessing the climate change vulnerability and adaptive capacity to cope with climate change; and developping 8 Adaptation plans, it means one plan for each sector of the intervention area. Another target was to form and operationalise 55 community groups in the project area (1/sector); another purpose was also to train different stackeholders and beneficiaries for adaptation planning with the aim of raising awareness to climate change issues; the target for this activity was 1000Women/1000Men. |  | For the first indicator of this output, at the end of the year 2014 the consultacy contract of assessing the vulnerability and developping the adaptation plans was signed. The total members of Climate change resilient groups are 2,032 (composed by 43% of men over 57% of women) grouped into 50groups; and 12 groups are made by youth .Each group is made by 30 to 35 people; which means that the project formed many groups than expected. All expected meetings and workshops with community have been conducted. The total number of participants was 7,992 people (3,704 Male&4,288 Female). Community animators and project staff have been trained on financial literacy, cooperative management , forestry management, watersheds management, porst harvest and storage techniques and land management. They have also been explained their role in the project activities. | Satisfactory
| Output 1.2: Investment in integrated land and water management practices |  | This output has under it five indicators most of them related to watersheds management whereby; in year one (2014) 59 Ha bench terraces were planned to be constructed, 167 ha to be rehabilitated (progressive terraces and replanting agro forestry trees). other activities were related to Re-planting bamboo on river banks, Drainage works and to conduct a feasibity study for long term solution of Mugogo low land ( all these activities targeting to reduce the turbidity at 2% in 2014). |  | 180ha out of 167ha of progressive terraces, 107ha out of 59ha of bench terraces targeted were executed, and 25.5ha out of 15.5ha for Re-planting bamboo planned are already executed. About the studies, the Bids are still under evaluation due the fact that the project was launched late and the procurement rules with timeframe to be respected for each step of the process. | Satisfactory
| Output 1.3: Diversification and integration of crop and livestock production systems to minimise the impact of variable rainfall on rural livelihoods (agro-sylvopastoral systems etc.). |  | 1500HH adopting climate resilient farming practices disaggregated by type (e.g. agro-forestry, agro-sylvopastoral etc) were targeted in 2014. |  | This output has not achieved its targets due to the delay of project launch; only preliminary activies were done such as: A workshop on capacity building for agro forestry management has been conducted with project stakeholders(Community animators, district and sector forest officers and presidents of cooperatives ), The identification of existing cooperatives was done (130 cooperatives in Nyabihu, and 39 in Busogo/Musanze), and 12 Farmer field schools have been grouped in 6 sectors composed by 360 members. | Satisfactory
| Output 1.4 Introduction of climate-resilient crop/fodder varieties and agronomic practices (short season crops, seasonal pastures etc.). |  | 1500 HH adopting at least 1 new climate-resilient crop or fodder variety or agronomic practices (disaggregated by male/female headed HH) and 45 women and 30 men Participating in farmer field trials were the targets of this output. |  | Reviewing existing data(District report of season: 2013 A, 2013 B and 2014A)was done. 12 Farmer field schools have been grouped in 6 sectors composed by 360 members; other activities under this output will be done after the operationalisation of FFS groups in 2015. | Satisfactory
| Output 1.5 Introduction of climate resilient post-harvest processing and storage systems for safe handling and storage of agricultural produce during extreme climate events (floods, rains). |  | 8 post-harvest storage facilities used by > 700 HH, 40% increase on baseline of HH adding value by primary agro processing such as sorting, drying, threshing, grading, 20% increase on baseline of HH adding value through transformative agro processing such as milling, shelling, grinding or packaging and 200 Women and 200 men from target HH engaged in post- harvest livelihoods were the targets of this output. |  | A survey on existing post harvest processing and storage systems in 8 sectors has been done and found out that 4 post harvest storages exists but none of them is used due to the low production and sometimes due to resistance. To incease access to credit facilities; the project beneficiaries already linked with SACCOs are around 3613(2,204 women equivalent to 61%). The total amount of money injected directly in beneficiaries as wages is 143,959,000Rwf. The shares paid by beneficiaries in SACCOs are so far 14,726,000Frw. other activities under this output will be done in 2015 due to the same problem of limited time in 2014. | Satisfactory
| 2.1 Identification of viable alternative livelihood opportunities and constraints |  | 50 women and 50 men from target HH with a new source of income was the target. |  | To raise awarness of potential livelihood opportunities; SACCO managers, district cooperatives officers, community animators and cooperative representatives have been trained on saving and credit, financial literacy and self sufficiency and 3613 beneficiaries from self help groups (2,204 Women and 1409 Men) have been engaged as manpower. | Satisfactory
| Output: 2.2 Development of Rural Development hubs within selected imidugudus to promote and facilitate sustainable, market-linked and diversified livelihoods |  | 4000 women/ 4000 men from target HH in Self-help groups or co-operatives, 16/12 hrs and 700 women/ 500 men from target beneficiaries (women/men) in VSLAs were the targets under this output. |  | Considering that the project launch was done in june 2014, the acivities of this output targeted this year are expected to be completed before june 2015 as it will be a full year there will not be any delay. However, preliminary activities were done where, 3613 beneficiaries from self help groups (2,204 Women and 1409 Men) have opened accounts in SAACOs; The community enterprise development guidelines document has been developed and shared with TAG members for Advices and Capacity and needs assessment of 4 technical vocational training centers (VTC Kibihekane, MTC karago, DCD Abacu tubiteho Rwankeri, and Jenda craft center) have been done. | Satisfactory
| Output 2.3 Resettlement of 200 households living in high-risk zones to Rural Development Hubs. |  | Extreme poor 200HH from high risk zone resettled in houses constructed in safe zone in compliance with national standards. |  | This output of Resettlement was not completed in 2014 due the Laws governing expropriation in Rwanda which are complex with long procedures but targeting to avoid conflicts in this. Therefore, we expect that after expropriation the constructions will start and end in the right time. The valued land to be expropriated which will accommodate 200houses is completed. The land required is 14ha, 55a, 12ca and 44%. The owners of land and properties of kabyaza site are 121 people. The amount valued for land and properties is 111,338,947Rwf. The design of the model green village is in process. | Satisfactory
| Output 2.4 Increased investment in market development (infrastructure, transport, storage, market research etc.). |  | 20% of targeted HH selling produce through new markets, 60% of farmers bulking produce for market and selling collectively and using new market infrastructure. |  | The project has started by raising awareness but the real activies were postponed to 2015. | Satisfactory
| Output 2.5 Increased investment in access to renewable energy (Biogas plants, solar etc.) for enterprise development. |  | 1000HH using renewable source of energy for cooking and lighting and 16 co-operatives or self help groups accessing a concessional loan for a renewable energy source were the target of 2014. |  | The activites under this output are expected to start after the construction of the model green village. | Satisfactory
| Output 3.1 Training of government technical staff on climate risk management and flood and landslide prevention measures for further scaling up. |  | 150 stakeholders who have received gender sensitization training as part of climate risk management |  | 81 Persons from Local government, civil society, NGOs, JAF and other project stakeholders attended a workshop on sharing experience with RV3CBA Project. | Satisfactory
| Output 3.2 Sharing project results and lessons learned and mainstreaming new approaches in local and national planning. |  | Development of a Communication Strategy, Project Website, Knowledge management strategy, Participatory videos Media articles in newspapers, journals, newsletters, radio were the targets of this output in 2014. |  | Bidders to develop a communication strategy have already submitted their proposals and are being evaluated, The website has been developed, The ToRs of developing the knoweledge management strategy are ready in procurement office but not yet advertised, The video recording company tender is under evaluation. In addition, the FFs groups are still being formed within the project intervention area. So, participatory video will be viewed after the formation of the concerned FFs groups, The starting phase video is under development. - MTV Studio is shooting a starting phase video. RV3CBA Project activities and events on community climate change adaptation have been covered and reported on Radio Rwanda, RC Musanze and RTV. For example, RV3CBA official launch, Training of Community Animators, RV3CBA meeting with its Partners, Local Steering Committee meeting and National Steering Committee. Over 6 articles on climate adaptation messages have been published in local newspapers and websites. | Satisfactory
[5 empty] | Overall Rating | Satisfactory
Please Provide the Name and Contact information of person(s) reponsible for completeling the Rating section
| Name: | NGABONZIZA Prime
| Email: | prime0467@yahoo.fr
Please justify your rating. Outline the positive and negative progress made by the project since it started. Provide specific recommendations for next steps. . (word limit=500)
The Project implementation is on a good progress considering the targets and the time it has started, though it has met some challenges such as The delay of Development of adaptation plans for the intervention area caused by the delay of Procurement procedures. the project has also encountered a challenge in ressettlement activity due to the fact that this activity engages the intervention of various parties and a lot of procedures.
| Progress on Key Milestones |  | Expected Progress |  | Progress to Date | Rating
NIE | Output 1.1: Community level mobilisation and climate adaptation plans developed and implemented. |  | The project had the targets for this 1st output of assessing the climate change vulnerability and adaptive capacity to cope with climate change; and developping 8 Adaptation plans, it means one plan for each sector of the intervention area. Another target was to form and operationalise 55 community groups in the project area (1/sector); another purpose was also to train different stackeholders and beneficiaries for adaptation planning with the aim of raising awareness to climate change issues; the target for this activity was 1000Women/1000Men. |  | The total members of Climate change resilient groups are 2,032 (composed by 43% of men over 57% of women) grouped into 50groups; and 12 groups are made by youth .Each group is made by 30 to 35 people; which means that the project formed many groups than expected. At the end of the year 2014 the contract to carry out consultacy of assessing the vulnerability and developping the adaptation plans was signed. All expected meetings and workshops with community have been conducted. The total number of participants was 7,992 people (3,704 Male&4,288 Female). Community animators and project staff have been trained on financial literacy, cooperative management , forestry management, watersheds management, porst harvest and storage techniques and land management. They have also been explained their role in the project activities. | Satisfactory
| Output 1.2: Investment in integrated land and water management practices |  | This output has under it five indicators most of them related to watersheds management whereby; 59 Ha bench terraces were planned to be constructed, 167ha to be rehabilitated (progressive terraces and replanting agro forestry trees) in 2014. other activities were related to Re-planting bamboo on river banks, Drainage works and to conduct a feasibity study for long term solution of Mugogo low land ( all these activities targeting to reduce the turbidity at 2% in 2014). |  | 180ha out of 167ha of progressive terraces, 107ha out of 59ha of bench terraces targeted were constructed, and 25.5ha out of 15.5ha for Re-planted with bamboo. The feasibity study for long term solution of Mugogo low land is under evaluation . | Highly Satisfactory
| Output 1.3: Diversification and integration of crop and livestock production systems to minimise the impact of variable rainfall on rural livelihoods (agro-sylvopastoral systems etc.). |  | 1500HH adopting climate resilient farming practices disaggregated by type (e.g. agro-forestry, agro-sylvopastoral etc) were targeted in 2014. |  | A workshop on capacity building for agro forestry management has been conducted with project stakeholders(Community animators, district and sector forest officers and presidents of cooperatives ), The identification of existing cooperatives was done (130 cooperatives in Nyabihu, and 39 in Busogo/Musanze), and 12 Farmer field schools have been grouped in 6 sectors composed by 360 members. The actual milestone related to 1500 HH adopting climate resilient farming will be executed next year. | Satisfactory
| Output 1.4 Introduction of climate-resilient crop/fodder varieties and agronomic practices (short season crops, seasonal pastures etc.). |  | 1500 HH adopting at least 1 new climate-resilient crop or fodder variety or agronomic practices (disaggregated by male/female headed HH) and 45 women and 30 men Participating in farmer field trials were the targets of this output. |  | Existing data(District report of season: 2013 A, 2013 B and 2014A)were reviewed. 12 Farmer field schools have been grouped in 6 sectors composed by 360 members; other activities under this output will be done after the operationalisation of FFS groups in 2015. | Satisfactory
| Output 1.5 Introduction of climate resilient post-harvest processing and storage systems for safe handling and storage of agricultural produce during extreme climate events (floods, rains). |  | 8 post-harvest storage facilities used by > 700 HH, 40% increase on baseline of HH adding value by primary agro processing such as sorting, drying, threshing, grading, 20% increase on baseline of HH adding value through transformative agro processing such as milling, shelling, grinding or packaging and 200 Women and 200 men from target HH engaged in post- harvest livelihoods were the targets of this output. |  | A survey on existing post harvest processing and storage systems in 8 sectors has been done and found out that 4 post harvest storages exists but none of them is used due to the low production and sometimes due to resistance. To incease access to credit facilities; the project beneficiaries already linked with SACCOs are around 3613(2,204 women equivalent to 61%). The total amount of money injected directly in beneficiaries as wages is 143,959,000Rwf. The shares paid by beneficiaries in SACCOs are so far 14,726,000Frw. other activities under this output will be done in 2015 due to the same problem of limited time in 2014. | Satisfactory
| 2.1 Identification of viable alternative livelihood opportunities and constraints |  | 50 women and 50 men from target HH with a new source of income was the target. |  | SACCO managers, district cooperatives officers, community animators and cooperative representatives have been trained on saving and credit, financial literacy and self sufficiency and 3613 beneficiaries from self help groups (2,204 Women and 1409 Men) have been engaged as manpower. | Satisfactory
| Output: 2.2 Development of Rural Development hubs within selected imidugudus to promote and facilitate sustainable, market-linked and diversified livelihoods |  | 4000 women/ 4000 men from target HH in Self-help groups or co-operatives, 16/12 hrs and 700 women/ 500 men from target beneficiaries (women/men) in VSLAs were the targets under this output. |  | Preliminary activities were done where 3613 beneficiaries from self help groups (2,204 Women and 1409 Men) have opened accounts in SAACOs; The community enterprise development guidelines document has been developed and shared with Technical Advisory Group members for Advices and Capacity and needs assessment of 4 technical vocational training centers (Kibihekane, Karago, Abacu Tubiteho Rwankeri, and Jenda craft center) was carried out. | Satisfactory
| Output 2.3 Resettlement of 200 households living in high-risk zones to Rural Development Hubs. |  | Extreme poor 200HH from high risk zone resettled in houses constructed in safe zone in compliance with national standards. |  | The valued land to be expropriated which will accommodate 200 houses is completed. The land required is 14ha, 55a, 12ca and 44%. The owners of land and properties of kabyaza site are 121 people. The amount valued for land and properties is 111,338,947Rwf. The design of the model green village is in process. | Marginally Satisfactory
| Output 2.4 Increased investment in market development (infrastructure, transport, storage, market research etc.). |  | 20% of targeted HH selling produce through new markets, 60% of farmers bulking produce for market and selling collectively and using new market infrastructure. |  | 4 meetings were carried out with Local communities on entrerprise development | Marginally Satisfactory
| Output 2.5 Increased investment in access to renewable energy (Biogas plants, solar etc.) for enterprise development. |  | 1000HH using renewable source of energy for cooking and lighting and 16 co-operatives or self help groups accessing a concessional loan for a renewable energy source were the target of 2014. |  | The activites under this output are expected to start after the construction of the model green village. | Satisfactory
| Output 3.1 Training of government technical staff on climate risk management and flood and landslide prevention measures for further scaling up. |  | 150 stakeholders who have received gender sensitization training as part of climate risk management |  | The project launching was done in June 2014 and was attended by around 1230 participants from different institutions (Pubic Institutions, CBOs and Development Partners). 81 Persons from Local government, civil society, NGOs, JAF and other project stakeholders attended a workshop on sharing experience with RV3CBA Project. | Satisfactory
| Output 3.2 Sharing project results and lessons learned and mainstreaming new approaches in local and national planning. |  | Development of a Communication Strategy, Project Website, Knowledge management strategy, Participatory videos Media articles in newspapers, journals, newsletters, radio were the targets of this output in 2014. |  | Bidders to develop a communication strategy have already submitted their proposals and are being evaluated, The website has been developed, The ToRs of developing the knoweledge management strategy are ready in procurement office but not yet advertised, the video recording company tender is under evaluation. In addition, the FFs groups are still being formed within the project intervention area. So, participatory video will be viewed after the formation of the concerned FFs groups, The starting phase video is under development. - MTV Studio is shooting a starting phase video. RV3CBA Project activities and events on community climate change adaptation have been covered and reported on Radio Rwanda, RC Musanze and RTV. For example, RV3CBA official launch, Training of Community Animators, RV3CBA meeting with its Partners, Local Steering Committee meeting and National Steering Committee. Over 6 articles on climate adaptation messages have been published in local newspapers and websites. | Satisfactory
[5 empty] | Overall Rating | Satisfactory
Please Provide the Name and Contact information of person(s) reponsible for completeling the Rating section
| Name: | Innocent MUSABYIMANA
| Email: | musasebin2000@yahoo.fr
| Please justify your rating and address the following points: 1. Indicate trends, both positive and negative, in achievement of outcomes as per the project indicators. 2. Detail critical risks that have affected progress. 3. Outline response to MTR undertaken this reporting period. 4. Outline action plan to address projects with a rating of HU, U or MU. Please keep your input to 1200 words |  | The National Implementing Entity is happy with the Progress so far made by the Executing Entit. The key driving forces for these achievement are relying on high level political support from Hon. Minister of Natural Resources, the Director General of Rwanda Natural Resources Authority, the committed entire Project Implementation Unit and the Local Leaders. Also the current frameworks set by the Minitsry of Natural Resources especially having existing Memorandum of Understanding with Local Civil Society Organizations is promising since we can base on their existing skills and innovations to build on to sppeed up the project outputs. We can testify the project will keep the momentum of implementation since we have a strong commitment and cooperation with Local Leaders and local communities.
Rating Definitions
|  |  | Highly Satisfactory (HS) | Project actions/activities planned for current reporting period are progressing on track or exceeding expectations to acheive all major outcomes/outputs for given reporting period, without major shortcomings. The project can be presented as “good practice”.
|  |  | Satisfactory (S) | Project actions/activities planned for current reporting period are progressing on track to achieve most of its major outcomes/outputs with only minor shortcomings.
|  |  | Marginally Satisfactory (MS) | Project actions/activities planned for current reporting period are progressing on track to achieve most major relevant outcomes/outputs, but with either significant shortcomings or modest overall relevance.
|  |  | Marginally Unsatisfactory (MU) | Project actions/activities planned for current reporting period are not progressing on track to achieve major outcomes/outputs with major shortcomings or is expected to achieve only some of its major outcomes/outputs.
|  |  | Unsatisfactory (U) | Project actions/activities planned for current reporting period are not progressing on track to achieve most of its major outcomes/outputs.
|  |  | Highly Unsatisfactory (U) | Project actions/activities planned for current reporting period are not on track and shows that it is failing to achieve, and is not expected to achieve, any of its outcomes/outputs.

## Project Indicators
2
PROJECT Indicators
Please provide all indicators being tracked for the project as outlined in the project document
Type of Indicator (indicators towards Objectives, Outcomes, etc…)
Type of Indicator | Indicator | Baseline | Progress since inception | Target for Project End
Overall Objective | Consumption levels in target HH | Rwf 118,000 | The project is still in middle of its first year of implemention and usualy the impact of the project on this indicator is visible gradually with time. Its progress will be reported after conducting the project annual impact assessment and the mid- term evaluation (as it is highlighted in project document). | 50% increase on baseline
Overall Objective | Percentage of target population adopting risk reduction measures | 10% TBC in baseline | Climate change resilient groups created so far are 2,032 people (composed by 43% of men over 57% of women) grouped into 50groups; and 12 groups are made by youth and the total number of participants of meetings and workshops on climate change issues was 7,992 people (3,704 Male&4,288 Female); this shows the targeted population is adopting risk reduction measures at an acceptable rate. However, as the project is still in middle of its first year of implemention and usualy the impact of the project on this indicator is visible gradually with time. Its progress will be reported after conducting the project annual impact assessment and the mid- term evaluation (as it is highlighted in project document). | 60% practice at least 1 risk reduction measure.
Outcome 1. | Number of victims killed and houses destroyed by flooding and landslides. | In 2012, 13 people died, 598 households completely destroyed, 748 households partially destroyed | The project is still in middle of its first year of implemention and usualy the impact of the project on this indicator is visible gradually with time. Its progress will be reported in project annual impact assessment (as it is highlighted in project document). But since the project is working in its intervention area, we have not recorded any people died because climate change deasaster. | 30% decrease on baseline
Outcome 1. | Crop losses due to climate variability (potatoes, beans, maize, wheat, peas, tea, coffee, pyrethrum). | In 2012, 6114 ha of crop land destroyed. | The project is still in middle of its first year of implemention and usualy the impact of the project on this indicator is visible gradually with time. Its progress will be reported in project annual impact assessment (as it is highlighted in project document). Due to the project intervention activities mostly soil & water managent activities, the positive impact of the project is gradually visible as described in the rating template of this report. | 30% decrease
Output 1.1 | No. of community based adaptation plans being implemented. | 0 | At the end of the year 2014 the consultacy contract of assessing the vulnerability and developping the adaptation plans for 8 sectors of the project intervention area was signed and being executed. | 8Plans (1 for each sector)
Output 1.1 | No. of community groups formed and operationalised for adaptation planning. | 0 | 62 groups formed. The total members of Climate change resilient groups are 2,032 (composed by 43% of men over 57% of women) grouped into 50groups; and 12 groups are made by youth .Each group is made by 30 to 35 people; which means that the project formed many groups than expected. | 55 groups (one for each cell)
Output 1.1 | Participation of women/men from target HH in adaptation planning processes and mobilised to participate in project activities. | 0 | All expected meetings and workshops with community have been conducted. The total number of participants was 7,992 people (3,704 Male&4,288 Female). Community animators and project staff have been trained on financial literacy, cooperative management , forestry management, watersheds management, porst harvest and storage techniques and land management. They have also been explained their role in the project activities. | 4000 women/4000 men
Output 1.1 | Percentage of committee positions held by women/men from target HH in adaptation planning processes. | 0 | Meetings and workshops with volunteers committees have been conducted to raise awareness.This activity is regularly done by community animators . The focus is put on ownership of RV3CBA activities. | 50% women/50% men
Output1.2 | Hours per day (or year) women from target HH spend fetching water and collecting water. | 1 hour | Consultancy on rainwater harvesting installation is in procurement process. | 30 minutes
Output1.2 | Area (ha) rehabilitated with erosion control measures. | 0 | 180 ha progressive terraces and 107ha of bench terraces constructed | 500 Ha bench terraces constructed, 1000 ha rehabilitated (progressive terraces by replanting agro forestry trees).
Output1.2 | Number of water user groups managing ponds and rainwater harvesting tanks with management plans in place. | 0 | Ongoing training for local communities that will end up by formulating the water user goups in the next year of 2015 | 80
Output1.2 | No. target HH using harvested rainwater for domestic use and irrigation. | 0 | we are waiting the results of the consultancy before the installation of rain water harvesting. | 2000
Output1.2 | Change in turbidity of rivers. | High levels of turbidity in all rivers due to erosion | 25.5ha for Re-planting bamboo along rivers and 1000 check dams . As the project is still in middle of its first year of implemention, this indicator need more time to have impact in terms of reducing turbidity, it will be reported at mid-term of the project implementation. | 20% reduction
Output 1.3 | No of target HH adopting climate resilient farming practices disaggregated by type (e.g. agro-forestry, agro-sylvopastoral etc). | 0 | Due to the delay of project launch (02 June 2014); only preliminary activies were done such as: Workshops on capacity building for agro forestry management has been conducted with project stakeholders(Community animators, district and sector forest officers and presidents of cooperatives ),Identification of existing cooperatives (130 cooperatives in Nyabihu, and 39 in Busogo/Musanze). | 5000
Output 1.3 | Area of cultivated land (ha) under diversified cropping and integrated farming systems in target areas. | 0 | Due to the delay of project launch (02 June 2014); only 12 Farmer field schools are regulary conducted in 6 sectors i.e 2 farmer field school per sector and each farmer field school is compsed by 30 members. | 20%
Output 1.4 | Numbers of HH adopting at least 1 new climate-resilient crop or fodder variety or agronomic practices (disaggregated by male/female headed HH). | 0 | Reviewing existing data (District report of season: 2013 A, 2013 B and 2014A)was done. | 5000
Output 1.4 | Participation of women/men in farmer field trials. | 0 | This activity will be done the operationalisation of FFS groups. | 140 women/140 men
Output 1.5 | Number of post harvest storage systems established; number of HH using these. | 4 Storage established | The post harvest survey was done and realised that 4 storages are already established but not used due to low production. | 7 storage facilities used by > 700 HH
Output 1.5 | Percentage of target HH adding value by primary agro processing such as sorting, drying, threshing, grading. | 0 | The Activity was not yet started because we`re waiting for adaptation plan study, but taining on value chain has been done. To incease access to credit facilities; the project beneficiaries already linked with SACCOs are around 3613(2,204 women equivalent to 61%). The total amount of money injected directly in beneficiaries as wages is 143,959,000Rwf. The shares paid by beneficiaries in SACCOs are so far 14,726,000Frw. other activities under this output will be done in 2015 due to the same problem of limited time in 2014. | 40% increase on baseline
Output 1.5 | Percentage of target HH adding value through transformative agro processing such as milling, shelling, grinding or packaging | <5% HHs engaged in 2nd processing | Training on value chain has been done and 3407 people were linked with SACCOs amang them 2139 are women which is 63%. The total amount injected directly in beneficiaries as wages is 104,967,500frw. | 20% increase on baseline
Output 1.5 | No of women/men from target HH engaged in post- harvest livelihoods | 50Men/100Women | 81 representatives of beneficiaries have been trained on financial literacy and enterpreneurship. | 1000W/1000M
Outcome 2. | Share of target HH income from non-farm activities. | 12,4% | The project is still in middle of its first year of implemention and usualy the impact of the project on this indicator is visible gradually with time. Its progress will be reported in project annual impact assessment (as it is highlighted in project document). | 50%
Outcome 2. | No. of women/men from target HH adopting alternative livelihood. | TBD in baseline | The project is still in middle of its first year of implemention and usualy the impact of the project on this indicator is visible gradually with time. Its progress will be reported in project annual impact assessment (as it is highlighted in project document). | 50% increase on baseline
Output 2.1 | Number of women/men from target HH with a new source of income. | 0 | To raise awarness of potential livelihood opportunities; SACCO managers, district cooperatives officers, community animators and cooperative representatives have been trained on saving and credit, financial literacy and self sufficiency and 3613 beneficiaries from self help groups (2,204 Women and 1409 Men) have been engaged as manpower. | 4000 w/4000 men
Output 2.2 | % increase in annual HH income from diversified livelihoods (disaggregated by FHH/MHH). | 0 | Considering that the project launch was done in june 2014, the acivities of this output targeted this year are expected to be completed before june 2015 as it will be a full year there will not be any delay. However, preliminary activities were done where, 3613 beneficiaries from self help groups (2,204 Women and 1409 Men) have opened accounts in SAACOs; The community enterprise development guidelines document has been developed and shared with TAG members for Advices. | 30%
Output 2.2 | Number of women/men from target HH in Self-help groups or co-operatives. |  | 1612 people have been grouped into 50 self help groups (composed by 43% of men and 57% of women) | 4000W/4000M
Output 2.2 | Number of women/men from target HH graduating from vocational training schemes. | 0 | Capacity and needs assessment of 4 technical vocational training centers (VTC Kibihekane, MTC karago, DCD Abacu tubiteho Rwankeri, and Jenda craft center) have been done. | 50
Output 2.2 | No. of hours spent on domestic duties by women/men aged over 16 years. | 20/8 hrs | 3407 people are engaged in work force where the spent 6 hours at project activities; among them 2,139 are women which is 63%. | 16 (Women) /12 hrs (Man)
Output 2.2 | No. of FHH/MHH in receipt of small loans to start an enterprise. | 0 | This activity is planned in 2015. | 3000
Output 2.2 | No. of women’s associations/savings groups (comprising target HHs) investing in a new and profitable business opportunity. | 0 | This activity is planned in 2015. | 300
Output 2.2 | No. of target beneficiaries (women/men) in VSLAs | 0 | 1612 people have been grouped into 50 self help groups (composed by 43% of men and 57% of women) | 3500 w/ 3500 men
Output 2.3 | No. of extreme poor HH from high risk zone resettled in houses constructed in safe zone in compliance with national standards. | 0 | This output of Resettlement was not completed in 2014 due the Laws governing expropriation in Rwanda which are complex with long procedures. Therefore, we expect that after expropriation, the constructions will start and end in the right time. The value of land and properties to be expropriated which will accommodate 200houses is completed. The land required is 14ha, 55a, 12ca and 44%. The owners of land and properties to be compesated are 121 peoples. The amount valued for land and properties is 111,338,947Rwf. The design of the model green village is also competed. | 200
Output 2.4 | Percentage of targeted HH selling produce through new markets. | 0 | The PIU has started with mobilisation to raise awareness and it is planned in 2015. | 20%
Output 2.4 | Percentage of farmers bulking produce for market and selling collectively. | 0 | The PIU has started with mobilisation to raise awareness and it is planned in 2015. | 60%
Output 2.4 | No of target HH using new market infrastructure. | 0 | The PIU has started with mobilisation to raise awareness and it is planned in 2015. | 2000 HH
Output 2.5 | No. of HH using a renewable energy source for lighting or cooking. | 0 | This activity has not yet started because we`re waiting for adaptation plan study and construction of 200 houses for resettlement . | 1000
Output 2.5 | No. co-operatives or self help groups accessing a concessional loan for a renewable energy source. | 0 | The activites under this output are expected to start after the construction of the model green village. | 16
Outcome 3. | No. of sectors outside project area replicating community based adaptation approaches. | 0 | The project is still in middle of its first year of implemention and usualy the impact of the project on this indicator is visible gradually with time. Its progress will be reported in project annual impact assessment (as it is highlighted in project document) and the project mid-term (end of 2015). | 2
Outcome 3. | Gender sensitive climate adaptation approaches incorporated into X local and Y national planning documents. | No adaptation planning currently taking place | The progress will be reported in the project mid-term (end of 2015) after providing the impact assessment and evaluation results. | 5 local and 2 national level
Output 3.1 | Budgets and staffing dedicated to climate change adaptation through district development plans. | 0 | Community animators have been elected and will be facilitating the project implementation. | Integrated into 2 DDPs
Output 3.1 | No. of stakeholders who have received gender sensitisation training as part of climate risk management. | 0 | 150 representatives of self help groups and 81 people from local authorities and communty initiatives have been trained on Climate Change Management | 150
Output 3.2 | Number of environmental/climate change policy briefs written and communicated to key decision makers. | 0 | The activities under this indicator were not done because we were waiting for the communication strategy to be availed by the consultant. This will be implemented in 2015. | 8
Output 3.2 | No of farmers making cross visits or viewing participatory videos by other farmers. | 0 | FFs groups are still being formed within the project intervention area. Participatory video will be viewed after the formation of the concerned FFs groups, The starting phase video is under development. | 8000
Output 3.2 | No. of TV/radio broadcasts with key adaptation messages. | 0 | Project activities and events on community climate change adaptation have been covered and reported on Radio Rwanda, RC Musanze and Rwanda Televion (RTV). | 10 out of 16
Output 3.2 | No. of news reports in the local press and media that have covered climate adaptation initiatives. | 0 | Over 6 articles on climate adaptation messages have been published in local newspapers and websites and most of them are in KINYARWANDA Language as a big number of beneficiaries uses the local language. Examples: - Imvaho Nshya, “Musanze- Nyabihu: barasabwa kuba umusemburo w’iterambere” - The New times, “ Local leaders unveil project to mitigate climate change - Izuba Rirashe, “Musanze na Nyabihu mu rugamba rwo guhangana n’imihindagurike y’ikirere” - www.Igihe.com “MINIRENA yatangije umushinga ufasha abaturage guhangana n’imihindagurikire y’ibihe” - www.kigalitoday.com, “ Nyabihu: Hatangijwe umushinga wo guhangana n’imihindagurikire y’ibihe uzatwara miliyari 7” - www.minirena.gov.rw, “Gahunda y’ibikorwa by’Umushinga | 30
Output 3.2 | No. of potential donors/investors receiving the adaptation investment plan for North West Rwanda. | 0 | The activities under this indicator are expected to be done in 2015. | 10

## Lessons Learned
QUALITATIVE MEASURES and LESSONS LEARNED
Please complete the following section every reporting period
Implementation and Adaptive Management | Response
What implementation issues/lessons, either positive or negative, affected progress? | Transport means for project staff was the main challenge since we delayed to procure the Project vehicle and motocycles and heavy rain which sometimes destroyed land and water management infrastructures.
Were there any delays in implementation? If so, include any causes of delays. What measures have been taken to reduce delays? | Of course delays have been there because the project started on later date than expected. To reduce those delays like in land and water management activities whereby the Project decided to contract with Inkeragutabara as a Single source basing on MOU signed between MINIRENA and Inkeragutabara . This approach has been also appreciated by the Project Steering Committee and Rwanda Public Procurement Authority
Describe any changes undertaken to improve results on the ground or any changes made to project outputs (i.e. changes to project design) | Using existing frameworks ( Administrative entities and contract or Agreements signed through a competitive approach)
How have gender considerations been taken into consideration during the reporting period? What have been the lessons learned as a consequence of inclusion of such considerations on project performance or impacts? | The reported data is seggregated by gender basis.
Please complete the following section at mid-term and project completion
Lessons for Adaptation | Response
Climate Resilience Measures
What have been the lessons learned, both positive and negative, in implementing climate adaptation measures that would be relevant to the design and implementation of future projects/programmes for enhanced resilience to climate change?
What is the potential for the climate resilience measures undertaken by the project/programme to be replicated and scaled up both within and outside the project area?
Concrete Adaptation Interventions
What have been the lessons learned, both positive and negative, in implementing concrete adaptation interventions that would be relevant to the design and implementation of future projects/programmes implementing concrete adaptation interventions?
What is the potential for the concrete adaptation interventions undertaken by the project/programme to be replicated and scaled up both within and outside the project area?
Community/National Impact
What would you consider to be the most successful aspects for the target communities?
What measures are/have been put in place to ensure sustainability of the project/program results?
What measures are being/could have been put in place to improve project/program results?
Knowledge Management
How has existing information/data/knowledge been used to inform project development and implementation? What kinds of information/data/knowledge were used?
If learning objectives have been established, have they been met? Please describe.
Describe any difficulties there have been in accessing or retrieving existing information (data or knowledge) that is relevant to the project. Please provide suggestions for improving access to the relevant data.
Has the identification of learning objectives contributed to the outcomes of the project? In what ways have they contributed?

## Results Tracker
Results Tracker for Adaptation Fund (AF) Projects
Goal: Assist developing-country Parties to the Kyoto Protocol that are particularly vulnerable to the adverse effects of climate change in meeting the costs of concrete adaptation projects and programmes in order to implement climate-resilient measures. Impact: Increased resiliency at the community, national, and regional levels to climate variability and change.
Important: Please read the following Results Framework and Baseline Guidance (also posted on the Adaptation Fund website) before entering your data
Link: http://www.adaptation-fund.org/sites/default/files/Results%20Framework%20and%20Baseline%20Guidance%20final.pdf
Please select the relevant Fund level Outcome and Output indicators that allign with the project objectives and outcomes
OBJECTIVE 1
Fund Outcome | Please select from dropdown menu below | Fund Outcome Indicator | Please select from dropdown menu below | Target at project/programme approval (see Units in next sheet) | Baseline (see Units in next sheet) | Mid-term Results | Terminal Results
Outcome 1: Reduced exposure at national level to climate-related hazards and threats Outcome 2: Strengthened institutional capacity to reduce risks associated with climate-induced socioeconomic and environmental losses Outcome 3: Strengthened awareness and ownership of adaptation and climate risk reduction processes at local level Outcome 4: Increased adaptive capacity within relevant development and natural resource sectors Outcome 5: Increased ecosystem resilience in response to climate change and variability-induced stress Outcome 6: Diversified and strengthened livelihoods and sources of income for vulnerable people in targeted areas Outcome 7: Improved policies and regulations that promote and enforce resilience measures | 5 | 1. Relevant threat and hazard information generated and disseminated to stakeholders on a timely basis 2.1. No. and type of targeted institutions with increased capacity to minimize exposure to climate variability risks 2.2. Number of people with reduced risk to extreme weather events 3.1. Percentage of targeted population aware of predicted adverse impacts of climate change, and of appropriate responses 3.2. Modification in behavior of targeted population 4.1. Development sectors' services responsive to evolving needs from changing and variable climate 4.2. Physical infrastructure improved to withstand climate change and variability-induced stress 5. Ecosystem services and natural assets maintained or improved under climate change and variability-induced stress 6.1. Percentage of households and communities having more secure (increased) access to livelihood assets 6.2. Percentage of targeted population with sustained climate-resilient livelihoods 7. Climate change priorities are integrated into national development strategy | 5 | * 30% decrease on baseline * 30% decrease | * In 2012, 13 people died, 598 households completely destroyed, 748 households partially destroyed * In 2012, 6114 ha of crop land destroyed.
Fund Output | Please select from dropdown menu below | Fund Output Indicator | Please select from dropdown menu below | Target at project/programme approval | Baseline | Mid-term Results | Terminal Results
Output 1: Risk and vulnerability assessments conducted and updated at a national level Output 2.1: Strengthened capacity of national and regional centres and networks to respond rapidly to extreme weather events Output 2.2: Targeted population groups covered by adequate risk reduction systems Output 3: Targeted population groups participating in adaptation and risk reduction awareness activities Output 4: Vulnerable physical, natural, and social assets strengthened in response to climate change impacts, including variability Output 5: Vulnerable physical, natural, and social assets strengthened in response to climate change impacts, including variability Output 6: Targeted individual and community livelihood strategies strengthened in relation to climate change impacts, including variability Output 7: Improved integration of climate-resilience strategies into country development plans | 5 | 1.1. No. and type of projects that conduct and update risk and vulnerability assessments 1.2. Development of early warning systems 2.1.1. No. of staff trained to respond to, and mitigate impacts of, climate-related events 2.1.2. Capacity of staff to respond to, and mitigate impacts of, climate-related events from targeted institutions increased 2.2.1. Percentage of population covered by adequate risk-reduction systems 2.2.2. No. of people affected by climate variability 3.1 No. and type of risk reduction actions or strategies introduced at local level 3.2 No. of news outlets in the local press and media that have covered the topic 4.1. No. and type of health or social infrastructure developed or modified to respond to new conditions resulting from climate variability and change (by type) 4. 2. No. of physical assets strengthened or constructed to withstand conditions resulting from climate variability and change (by asset types) 5. No. and type of natural resource assets created, maintained or improved to withstand conditions resulting from climate variability and change (by type of assets) 6.1. No. and type of adaptation assets (physical as well as knowledge) created in support of individualor community-livelihood strategies 6.2. Type of income sources for households generated under climate change scenario 7.1. No., type, and sector of policies introduced or adjusted to address climate change risks 7.2. No. or targeted development strategies with incorporated climate change priorities enforced | 5 | * 8 Community Based Adaptation Plans (1 for each sector) *30 minutes spent by women for fetching water * 500 Ha bench terraces constructed, 1000 ha rehabilitated (progressive terraces by replanting agro forestry trees). *High levels of turbidity in all rivers due to erosion | * 0 * 1hour spent by women for fetching water * 0 * 20% reduction
OBJECTIVE 2
Fund Outcome | Please select from dropdown menu below | Fund Outcome Indicator | Please select from dropdown menu below | Target at project/programme approval (see Units in next sheet) | Baseline | Mid-term Results | Terminal Results
Outcome 1: Reduced exposure at national level to climate-related hazards and threats Outcome 2: Strengthened institutional capacity to reduce risks associated with climate-induced socioeconomic and environmental losses Outcome 3: Strengthened awareness and ownership of adaptation and climate risk reduction processes at local level Outcome 4: Increased adaptive capacity within relevant development and natural resource sectors Outcome 5: Increased ecosystem resilience in response to climate change and variability-induced stress Outcome 6: Diversified and strengthened livelihoods and sources of income for vulnerable people in targeted areas Outcome 7: Improved policies and regulations that promote and enforce resilience measures | 6 | 1. Relevant threat and hazard information generated and disseminated to stakeholders on a timely basis 2.1. No. and type of targeted institutions with increased capacity to minimize exposure to climate variability risks 2.2. Number of people with reduced risk to extreme weather events 3.1. Percentage of targeted population aware of predicted adverse impacts of climate change, and of appropriate responses 3.2. Modification in behavior of targeted population 4.1. Development sectors' services responsive to evolving needs from changing and variable climate 4.2. Physical infrastructure improved to withstand climate change and variability-induced stress 5. Ecosystem services and natural assets maintained or improved under climate change and variability-induced stress 6.1. Percentage of households and communities having more secure (increased) access to livelihood assets 6.2. Percentage of targeted population with sustained climate-resilient livelihoods 7. Climate change priorities are integrated into national development strategy | 6.1 | 50% share of targeted HH income from non-farm activities. | 12,4% share of targeted HH income from non-farm activities.
Fund Output | Please select from dropdown menu below | Fund Output Indicator | Please select from dropdown menu below | Target at project/programme approval | Baseline | Mid-term Results | Terminal Results
Output 1: Risk and vulnerability assessments conducted and updated at a national level Output 2.1: Strengthened capacity of national and regional centres and networks to respond rapidly to extreme weather events Output 2.2: Targeted population groups covered by adequate risk reduction systems Output 3: Targeted population groups participating in adaptation and risk reduction awareness activities Output 4: Vulnerable physical, natural, and social assets strengthened in response to climate change impacts, including variability Output 5: Vulnerable physical, natural, and social assets strengthened in response to climate change impacts, including variability Output 6: Targeted individual and community livelihood strategies strengthened in relation to climate change impacts, including variability Output 7: Improved integration of climate-resilience strategies into country development plans | 6 | 1.1. No. and type of projects that conduct and update risk and vulnerability assessments 1.2. Development of early warning systems 2.1.1. No. of staff trained to respond to, and mitigate impacts of, climate-related events 2.1.2. Capacity of staff to respond to, and mitigate impacts of, climate-related events from targeted institutions increased 2.2.1. Percentage of population covered by adequate risk-reduction systems 2.2.2. No. of people affected by climate variability 3.1 No. and type of risk reduction actions or strategies introduced at local level 3.2 No. of news outlets in the local press and media that have covered the topic 4.1. No. and type of health or social infrastructure developed or modified to respond to new conditions resulting from climate variability and change (by type) 4. 2. No. of physical assets strengthened or constructed to withstand conditions resulting from climate variability and change (by asset types) 5. No. and type of natural resource assets created, maintained or improved to withstand conditions resulting from climate variability and change (by type of assets) 6.1. No. and type of adaptation assets (physical as well as knowledge) created in support of individualor community-livelihood strategies 6.2. Type of income sources for households generated under climate change scenario 7.1. No., type, and sector of policies introduced or adjusted to address climate change risks 7.2. No. or targeted development strategies with incorporated climate change priorities enforced | 6 | 200 of extreme poor HH from high risk zone resettled in houses constructed in safe zone in compliance with national standards. * < 1,416,000 | 0 of extreme poor HH from high risk zone resettled in houses constructed in safe zone in compliance with national standards. * 30% increase in annual HH income from diversified livelihoods (disaggregated by FHH/MHH).
OBJECTIVE 3
Fund Outcome | Please select from dropdown menu below | Fund Outcome Indicator | Please select from dropdown menu below | Target at project/programme approval | Baseline | Mid-term Results | Terminal Results
Outcome 1: Reduced exposure at national level to climate-related hazards and threats Outcome 2: Strengthened institutional capacity to reduce risks associated with climate-induced socioeconomic and environmental losses Outcome 3: Strengthened awareness and ownership of adaptation and climate risk reduction processes at local level Outcome 4: Increased adaptive capacity within relevant development and natural resource sectors Outcome 5: Increased ecosystem resilience in response to climate change and variability-induced stress Outcome 6: Diversified and strengthened livelihoods and sources of income for vulnerable people in targeted areas Outcome 7: Improved policies and regulations that promote and enforce resilience measures | 2 | 1. Relevant threat and hazard information generated and disseminated to stakeholders on a timely basis 2.1. No. and type of targeted institutions with increased capacity to minimize exposure to climate variability risks 2.2. Number of people with reduced risk to extreme weather events 3.1. Percentage of targeted population aware of predicted adverse impacts of climate change, and of appropriate responses 3.2. Modification in behavior of targeted population 4.1. Development sectors' services responsive to evolving needs from changing and variable climate 4.2. Physical infrastructure improved to withstand climate change and variability-induced stress 5. Ecosystem services and natural assets maintained or improved under climate change and variability-induced stress 6.1. Percentage of households and communities having more secure (increased) access to livelihood assets 6.2. Percentage of targeted population with sustained climate-resilient livelihoods 7. Climate change priorities are integrated into national development strategy | 2.1 | 2 sectors outside project area replicating community based adaptation approaches. | 0
Fund Output | Please select from dropdown menu below | Fund Output Indicator | Please select from dropdown menu below | Target at project/programme approval | Baseline | Mid-term Results | Terminal Results
Output 1: Risk and vulnerability assessments conducted and updated at a national level Output 2.1: Strengthened capacity of national and regional centres and networks to respond rapidly to extreme weather events Output 2.2: Targeted population groups covered by adequate risk reduction systems Output 3: Targeted population groups participating in adaptation and risk reduction awareness activities Output 4: Vulnerable physical, natural, and social assets strengthened in response to climate change impacts, including variability Output 5: Vulnerable physical, natural, and social assets strengthened in response to climate change impacts, including variability Output 6: Targeted individual and community livelihood strategies strengthened in relation to climate change impacts, including variability Output 7: Improved integration of climate-resilience strategies into country development plans | 2.2 | 1.1. No. and type of projects that conduct and update risk and vulnerability assessments 1.2. Development of early warning systems 2.1.1. No. of staff trained to respond to, and mitigate impacts of, climate-related events 2.1.2. Capacity of staff to respond to, and mitigate impacts of, climate-related events from targeted institutions increased 2.2.1. Percentage of population covered by adequate risk-reduction systems 2.2.2. No. of people affected by climate variability 3.1 No. and type of risk reduction actions or strategies introduced at local level 3.2 No. of news outlets in the local press and media that have covered the topic 4.1. No. and type of health or social infrastructure developed or modified to respond to new conditions resulting from climate variability and change (by type) 4. 2. No. of physical assets strengthened or constructed to withstand conditions resulting from climate variability and change (by asset types) 5. No. and type of natural resource assets created, maintained or improved to withstand conditions resulting from climate variability and change (by type of assets) 6.1. No. and type of adaptation assets (physical as well as knowledge) created in support of individualor community-livelihood strategies 6.2. Type of income sources for households generated under climate change scenario 7.1. No., type, and sector of policies introduced or adjusted to address climate change risks 7.2. No. or targeted development strategies with incorporated climate change priorities enforced | 2.2.1 | 150 stakeholders received gender sensitisation training as part of climate risk management. | 0
OBJECTIVE 4
Fund Outcome | Please select from dropdown menu below | Fund Outcome Indicator | Please select from dropdown menu below | Target at project/programme approval | Baseline | Mid-term Results | Terminal Results
Outcome 1: Reduced exposure at national level to climate-related hazards and threats Outcome 2: Strengthened institutional capacity to reduce risks associated with climate-induced socioeconomic and environmental losses Outcome 3: Strengthened awareness and ownership of adaptation and climate risk reduction processes at local level Outcome 4: Increased adaptive capacity within relevant development and natural resource sectors Outcome 5: Increased ecosystem resilience in response to climate change and variability-induced stress Outcome 6: Diversified and strengthened livelihoods and sources of income for vulnerable people in targeted areas Outcome 7: Improved policies and regulations that promote and enforce resilience measures |  | 1. Relevant threat and hazard information generated and disseminated to stakeholders on a timely basis 2.1. No. and type of targeted institutions with increased capacity to minimize exposure to climate variability risks 2.2. Number of people with reduced risk to extreme weather events 3.1. Percentage of targeted population aware of predicted adverse impacts of climate change, and of appropriate responses 3.2. Modification in behavior of targeted population 4.1. Development sectors' services responsive to evolving needs from changing and variable climate 4.2. Physical infrastructure improved to withstand climate change and variability-induced stress 5. Ecosystem services and natural assets maintained or improved under climate change and variability-induced stress 6.1. Percentage of households and communities having more secure (increased) access to livelihood assets 6.2. Percentage of targeted population with sustained climate-resilient livelihoods 7. Climate change priorities are integrated into national development strategy
Fund Output | Please select from dropdown menu below | Fund Output Indicator | Please select from dropdown menu below | Target at project/programme approval | Baseline | Mid-term Results | Terminal Results
Output 1: Risk and vulnerability assessments conducted and updated at a national level Output 2.1: Strengthened capacity of national and regional centres and networks to respond rapidly to extreme weather events Output 2.2: Targeted population groups covered by adequate risk reduction systems Output 3: Targeted population groups participating in adaptation and risk reduction awareness activities Output 4: Vulnerable physical, natural, and social assets strengthened in response to climate change impacts, including variability Output 5: Vulnerable physical, natural, and social assets strengthened in response to climate change impacts, including variability Output 6: Targeted individual and community livelihood strategies strengthened in relation to climate change impacts, including variability Output 7: Improved integration of climate-resilience strategies into country development plans |  | 1.1. No. and type of projects that conduct and update risk and vulnerability assessments 1.2. Development of early warning systems 2.1.1. No. of staff trained to respond to, and mitigate impacts of, climate-related events 2.1.2. Capacity of staff to respond to, and mitigate impacts of, climate-related events from targeted institutions increased 2.2.1. Percentage of population covered by adequate risk-reduction systems 2.2.2. No. of people affected by climate variability 3.1 No. and type of risk reduction actions or strategies introduced at local level 3.2 No. of news outlets in the local press and media that have covered the topic 4.1. No. and type of health or social infrastructure developed or modified to respond to new conditions resulting from climate variability and change (by type) 4. 2. No. of physical assets strengthened or constructed to withstand conditions resulting from climate variability and change (by asset types) 5. No. and type of natural resource assets created, maintained or improved to withstand conditions resulting from climate variability and change (by type of assets) 6.1. No. and type of adaptation assets (physical as well as knowledge) created in support of individualor community-livelihood strategies 6.2. Type of income sources for households generated under climate change scenario 7.1. No., type, and sector of policies introduced or adjusted to address climate change risks 7.2. No. or targeted development strategies with incorporated climate change priorities enforced

## Units for Indicators
Fund Outcome Indicator Units
1. Generation of relevant data, Stakeholders, and Timeliness 2.1. Include both qualitative and quantitative measures of capacity level within targeted institutions 2.2. Number (men and women and other vulnerable groups) 3.1. Use scale from 1 to 5: 5: Fully aware 4: Mostly aware 3: Partially aware 2: Partially not aware 1: Aware of neither predicted adverse impacts of climate change nor of appropriate responses 3.2. Use scale from 1 to 5: 5: All 4: Almost all 3: Half 2: Some 1: None 4.1. Summarize in an overall scale (1-5): 5: Highly responsive (All defined elements ) 4: Mostly responsive (Most defined elements) 3: Moderately responsive (Some defined elements) 2: Partially responsive (Lacks most elements) 1: Non responsive (Lacks all elements ) 4.2. Summarize in an overall scale (1-5): 5: Fully improved 4: Mostly Improved 3: Moderately improved 2: Somewhat improved 1: Not improved 5. Depends on the targeted natural asset: Biological (species): measure through changes in population numbers (dynamics, structure, etc.) Land: measure changes in hectares. Baseline data will be necessary to estimate the change. Supporting indicators baseline and target (as well as contextual information) are needed such as the following: Farmers adopting recommended technologies, Ha. of land improved, Average deforestation rate Etc. Use scale from 1 to 5. 5: Very effective (All elements are present) 4: Effective (Most elements are present) 3: Moderately effective (Some elements are present) 2: Partially effective (Most elements are not present) 1: Ineffective (No elements are present) 6.1. Summarize in an overall scale (1-5): 5: Very high improvement 4: High improvement 3: Moderate improvement 2: Limited improvement 1: No improvement 6.2. Household income by source of livelihood in project area (USD) prior and post project intervention 7. Summarize in an overall scale (1-5). 5: All (Fully integrated) 4: Most 3: Some 2: Most not integrated 1: None
Fund Output Indicator Units
1.1. Number, sector(s) and level(s) of projects or interventions in separate fields of monitoring plan 1.2. Number 2.1.1. Number of staff (male/female) of targeted institutions: a. Obtain baseline information: total number of staff from targeted institutions b. Define target 2.1.2. Number of staff (male/female) of targeted institutions: a. Obtain baseline information: total number of staff from targeted institutions b. Define target: needs to be defined by project proponents 2.2.1. Quantitative: Percentage (includes women – and other vulnerable groups – and men). Qualitative: Adequacy: include direct analysis of major areas; adequacy/effectiveness of systems or analysis of perceptions of populations and institutions. 2.2.2. Number (broken down by gender and, if possible, by vulnerable groups defined in the area of intervention) of people 3.1. Number and type (in separate columns) at local level. 3.2. Number 4.1. Number and type 4. 2. Number and type (entered in separate columns) 5. Number of interventions by type of natural asset and intervention 6.1. Number and type (in separate columns of monitoring plan) 6.2. Income sources per household; description of income source and number of households. 7.1. Number/Sector 7.2. Number; Effectiveness (see previous indicator) through enforcement level.