## Overview
Project Performance Report (PPR)
| Period of Report (Dates) | June 2014 - June 2015
| Project Title: | Ecosystem-based Adaptation to Climate Change in Seychelles
| Project Summary: | The proposed project aims to reduce the vulnerability of the Seychelles to climate change, focusing on water scarcity and flooding. The climate change projections in the Seychelles show that rainfall will become irregular with much of the precipitation falling in sharp bursts, creating heavy flooding in the wet season, while imposing extended period of drought during the dry season. The lack of large water storage capacity and with the topography of the islands constraining such infrastructure, water supplies are heavily dependent on rainfall. Furthermore, the coastal zone is vulnerable to flooding as a consequence of rising sea surface levels, and increased storm surges from cyclonic activity in the Western Indian Ocean. The project will reduce these vulnerabilities by spearheading an ecosystem-based adaptation approach that will be applied to watershed and coastal rehabilitation on the 2 largest Islands to address water shortages and watershed and coastal flooding that have been accentuated by climate change.
|  |  | Countries | Project Type: |  | GEF Focal Area: | GEF 4 Focal Areas | GEF 2 / 3 Operational Programme: | Overall Rating of the project in the evaluation by the project evaluator: | GEF-4 Focal Area Strategic Program: | GEF-3 Focal Area Strategic Program:
| Database Number: | 4775 | Afghanistan | FP | Yes | Biodiversity | 1 | 1 | U | BD-SP1-PA Financing | 1: Arid & semi-arid ecosystems
Implementing Entity (IE) [name]: |  | UNDP | Albania | MSP | No | Climate Change Adaptation | 2 | 2 | S | BD-SP2-Marine PA | 2: Coastal, marine & freshwater ecosystems
| Type of IE: | Multilateral | Algeria | EA |  | Climate Change Mitigation | 3 | 3 | MU | BD-SP3-PA Networks | 3: Forest ecosystems
| Country(ies): | Seychelles | Angola |  |  | International Waters | 5 | 5 | Good | BD-SP5-Markets | 13: Conservation and Sustainable Use of Biological Diversity Important to Agriculture
Relevant Geographic Points (i.e. cities, villages, bodies of water): |  | Mare aux Cochons watershed, Mahe; Mt Plaisir watershed, Mahe; Baie Lazare watershed, Mahe; Caiman River watershed, Mahe; Fond B’Offay/Nouvelle Decouvert watershed, Praslin; North-east Point coastal ecosystem, Mahe; Anse Royale coastal ecosystem, Mahe | Argentina |  |  | Multiple Focal Area |  |  |  | BD-SP7-Invasive Alien Species(IAS) | 6: Promoting the adoption of renewable energy by removing barriers and reducing implementation costs
[8 empty] | CC-SP2- Industrial EE | 8: Waterbody based operational program
| Project Milestones | [6 empty] | CC-SP3-RE,CC-SP4-Biomass | 9: Integrated Land and Water multiple focal area
| Milestone |  | Bahamas | [6 empty] | CC-SP5-Transport | 10: Contaminants based operational program
AFB Approval Date: |  | 2014-02-13
IE-AFB Agreement Signature Date: |  | 2014-02-13 | [6 empty] | CC-SP6-LULUCF | 12: Integrated Ecosystem Management
Start of Project/Programme: |  | 2014-06-06 | [6 empty] | Cross cutting capacity building | 14: Persistent Organic Pollutants
Mid-term Review Date (if planned): |  | 2017
| Terminal Evaluation Date: | 2019
|  | List documents/ reports/ brochures / articles that have been prepared about the project. | Cyprus
|  | Reports: a) Inception report, b) Quarterly reports (Q4 2014, Q1 2015, Q2 2015) Brochures: a) Project brochure (summary of the project and its objectives), b) A specific brochure for the Baie-Lazare watershed committee and community, c) Watershed committee guide 'Our water Our Choice' Press articles: a) http://www.nation.sc/article.html?id=246190 - 23rd February 2015: Adapting water usage to address climate change impacts/ Seychelles Nation b) http://www.nation.sc/article.html?id=245748 - 17th June 2015: International World Day to Combat Desertification; Preserving our natural resources from drought/ Seychelles Nation c) http://www.nation.sc/article.html?id=246223 - 30th July 2015: Stakeholders follow training on soil salinity management/ Seychelles Nation & TODAY | Czech Republic
List the Website address (URL) of project. |  |  | Democratic People's Republic of Korea
|  | www.pcusey.sc and www.undp.org | Democratic Republic of the Congo
Denmark
| Project contacts: |  | Djibouti
National Project Manager/Coordinator |  |  | Dominica
| Name: | Betty Seraphine (Project Manager) | Dominican Republic
| Email: | b.seraphine@pcusey.sc | Ecuador
| Date: | 2015-07-01 | Egypt
| Government DA |  | El Salvador
| Name: | Wills Agricole | Equatoral Guinea
| Email: | w.agricole@env.gov.sc | Eritrea
| Date: | 2015-08-01 | Estonia
| Implementing Entity |  | Ethiopia
| Name: | Roland Alcindor | Fiji
| Email: | roland.alcindor@undp.org | Finland
| Date: | 2015-06-01 | France
| Executing Agency |  | Gambia
| Name: | Wills Agricole | Georgia
| Email: | w.agricole@env.gov.sc | Germany
| Date: | 2015-06-01 | Ghana
| Executing Agency |  | Greece
| Name: |  | Grenada
| Email: |  | Guatemala
| Date: |  | Guinea
| Executing Agency |  | Guinea Bissau
| Name: |  | Guyana
| Email: |  | Haiti
| Date: |  | Honduras
Hungary
Iceland
India
Indonesia
Iran (Islamic Republic of)
Iraq
Ireland
Israel
Italy
Jamaica
Japan
Jordan
Kazakhstan
Kenya
Kiribati
Kuwait
Kyrgyzstan
Lao People’s Democratic Republic
Latvia
Lebanon
Lesotho
Liberia
Libyan Arab Jamahiriya
Liechtenstein
Lithuania
Luxembourg
Madagascar
Malawi
Malaysia
Maldives
Mali
Malta
Marshall Islands
Mauritania
Mauritius
Mexico
Micronesia, Federated States of
Monaco
Mongolia
Montenegro
Morocco
Mozambique
Myanmar
Namibia
Nauru
Nepal
Netherlands
New Zealand
Nicaragua
Niger
Nigeria
Norway
Oman
Pakistan
Palau
Panama
Papua New Guinea
Paraguay
Peru
Philippines
Poland
Portugal
Qatar
Republic of Korea
Republic of Moldova
Romania
Russian Federation
Rwanda
Saint Kitts and Nevis
Saint Lucia
Saint Vincent and the Grenadines
Samoa
San Marino
Sao Tome and Principe
Saudi Arabia
Senegal
Serbia
Seychelles
Sierra Leone
Singapore
Slovakia
Slovenia
Solomon Islands
Somalia
South Africa
Spain
Sri Lanka
Sudan
Suriname
Swaziland
Sweden
Switzerland
Syrian Arab Republic
Tajikistan
Thailand
The former Yugoslav Republic of Macedonia
Timor-Leste
Togo
Tonga
Trinidad and Tobago
Tunisia
Turkey
Turkmenistan
Tuvalu
Uganda
Ukraine
United Arab Emirates
United Kingdom of Great Britain and Northern Ireland
United Republic of Tanzania
United States of America
Uruguay
Uzbekistan
Vanuatu
Venezuela, Bolivarian Republic of
Viet Nam
Yemen
Zambia
Zimbabwe

## FinancialData
Financial information: cumulative from project start to June 2015
DISBURSEMENT OF AF GRANT FUNDS
How much of the total AF grant as noted in Project Document plus any project preparation grant has been spent to date?
Estimated cumulative total disbursement as of June 2014 | 355701
Add any comments on AF Grant Funds. (word limit=200) | Expenditure is 50.6% of the budgeted amount for the reporting period. This is largely due to delays in start-up (spending commenced in Q4 2014) and delays in implementation of key activities up - which have now speeded up with the PIT fully in place from March 2015 and the new Project Manager hired from July 2015. The current period of low expenditure reflects a great deal of consultation in regard to the project interventions, with Government stakeholders (notably the utilities company)and also with the beneficiary communities, to obtain buy-in pror to interventions being initiated. Intervemtions on Government land have been cleared by the Government departments concerned, with MOUs under development (e.g. in the case of SNPA) but dicussion is still underway in regard to interventions on private land, which must be approved by the land owners.
INVESTMENT INCOME | 0
Amount of annual investment income generated from the Adaptation Fund’s grant
EXPENDITURE DATA
List ouput and corresponding amount spent for the current reporting period | ITEM / ACTIVITY / ACTION | AMOUNT
| Component 1 ECOSYSTEM-BASED ADAPTATION APPROACH TO ENHANCING FRESHWATER SECURITY AND FLOOD CONTROL IN MAHÉ AND PRASLIN UNDER CONDITIONS OF CLIMATE CHANGE Output 1.1 Management and rehabilitation of critical watersheds to enhance functional connectivity and the resilience of these areas to climate change and reduce water scarcity and watershed flooding (Mare aux Cochons, Mt Plaisar, Baie Lazare, Caiman, Praslin Fond B’Offay/Nouvelle Decouvert watershed management) Output 1.2 Small-scale water storage and detention facilities designed and constructed or rehabilitated in critical waterways for communities to benefit from enhanced ecosystem functioning by forests (Mare aux Cochons, Mt Plaisar, Baie Lazare, Caiman, Praslin Fond B’Offay/Nouvelle Decouvert watershed control structures) | 126690.71
| Component 2 ECOSYSTEM-BASED ADAPTATION APPROACHES ALONG THE SHORELINES OF THE GRANITIC ISLANDS REDUCE THE RISKS OF CLIMATE CHANGE INDUCED COASTAL FLOODING Output 2.1 Ecosystem-based measures for flood protection on an urban shoreline Output 2.2 Ecosystem-based measures for flood protection and mitigating salt water intrusion in an agricultural and tourism development area | 150940.21
| Component 3 ECOSYSTEM BASED ADAPTATION MAINSTREAMED INTO DEVELOPMENT PLANNING AND FINANCING Output 3.1 Policy and legal frameworks for watershed and coastal climate change adaptation Output 3.2 Capacity Development for Ecosystem Based Adaptation Methods Output 3.3 Lessons learned and Knowledge Dissemination | 7664.57
| Component 4 PROJECT MANAGEMENT (Note. Technical staff costs are mis-recorded under this component - should have been recorded in Atlas under the technical components.) | 70450
| TOTAL | 355745.49
PLANNED EXPENDITURE SCHEDULE
List outputs planned and corresponding projected cost for the upcoming reporting period | ITEM / ACTIVITY / ACTION | PROJECTED COST | Est. Completion Date
| Output 1.1: Mare aux Cochons: MOU with SNPA, ecosystem assessment, identification and start of invasive species management programme (long-term action), wetland rehabilitation (long-term action) | 60000 | 2016-06-01
| Output 1.1: Mont Plaisir: ecosystem assessment (key intervention areas), identification and start of invasive species management programme (long-term action) | 20000 | 2016-06-01
| Output 1.1: Baie Lazare: refocusing of actions into areas where land ownership issues can be addressed, identification and start of invasive species management programme (long-term action), design of wetland rehabilitation interventions (4 wetlands), assessing impacts of conflicts on water resourcesecosystem assessment (key intervention areas), identification and start of invasive species management programme (long-term action) | 60000 | 2016-06-01
| Output 1.1: Caiman watershed: ecosystem assessment (key intervention areas), identification and start of invasive species management programme (long-term action) | 30000 | 2016-06-01
| Output 1.1: Praslin: Upgrading and completion of tree nursery, start up of vegetation management and rehabilitation (red soils area) (2-year plan of action), mitigation of impacts of landslides on water resources | 80000 | 2016-06-01
| Output 1.2: Mare aux Cochons: renovation of downstream barrage, assessment of plans for water abstraction by utility company | 80000 | 2016-06-01
| Output 1.2: Mont Plaisir: Assessent of water quality, barrage renovation, assessment of potential for targeted awater harvesting | 20000 | 2016-06-01
| Output 1.2: Baie Lazare: Design of additional barrages, study to determine water source protection zone, study on pollution from agriculture | 50000 | 2016-04-01
| Output 1.2: Caiman watershed: renovation of downstream barrage, assessment of potential for further abstraction | 10000 | 2016-04-01
| Output 1.2: Praslin: Assessment of need for a new check dam as a response to fire risk | 44000 | 2016-02-01
| Cross cutting: Initiation of process of formulation of community based watershed management plans (long-term action), monitoring and evaluation plans | 100000 | 2016-06-01
| Cross cutting: Educaion and awareness materials | 11500 | 2016-06-01
| Cross-cutting: Training on site rehabilitation, monitoring and evaluation | 20000 | 2016-06-01
| Output 2.1: NE Point: biodiversity assessment of wetlands, environmental flow through wetlands, assessment of wetland rehabilitation potential. | 80000 | 2016-06-01
| Output 2.1: NE Point: coastal hydrographic studies, modelling, assessment of options for reconstruction of barrier reef and restoration | 100000 | 2016-06-01
| Output 2.2: Anse Royale: biodiversity assessment, integration of wetland management plan into previously development coastal management plan, environmental flows study | 90000 | 2016-06-01
| Output 2.2: Anse Royale: study of potential for shoreline rehabilitation | 85000 | 2016-06-01
| Output 3.1: Consultation regarding watershed management policy framework, resuscitation of Rivers Board | 13000 | 2016-02-01
| Output 3.2: Development of modules for training programmes to be delvered by UNISEY (initially forest rehabilitation and beach berm management) | 25000 | 2016-06-01
| Output 3.3: Communications strategy, experience exchanges | 10000 | 2016-03-01
| TOTAL | 848500
ACTUAL CO-FINANCING (If the MTR or TE have not been undertaken this reporting period, DO NOT report on actual co-financing.)
How much of the total co-financing as committed in the Project Document has actually been realized?
Estimated cumulative actual co-financing as verified during Mid-term Review (MTR) or Terminal Evaluation (TE).
Add any comments on actual co-financing in particular any issues related to the realization of in-kind, grant, credits, loans, equity, non-grant instruments and other types of co-financing. (word limit=200)

## Risk Assesment
RISK ASSESMENT
IDENTIFIED RISKS
List all Risks identified in project preparation phase and what steps are being taken to mitigate them
Identified Risk | Current Status | Steps Taken to Mitigate Risk
Policy makers prioritize economic benefits over sustainable and resilient ecosystems | Medium risk. | A project brochure has been developed to raise awareness about the project at the national level. The first watershed committee has been set up in the local district and is actively involved in promoting the importance of watershed management. The designated Authority and team are involved in the decision-making process of the project and will spearhead the development of the future policy.
Extreme natural disasters affect confidence of local community to adaptation measures | Medium risk. | The project has already initiated participatory processes for integrated watershed management at the community level. The first watershed committee has been set up in the Baie Lazare community and has taken ownership of the project activities even during various weather events. As the project invests in capacity building they become more confident to accept and implement adaptation measures.
Environmental impact of structures in watercourses and reefs | Medium risk. | Biodiversity assessments are being conducted for the marshes of Anse Royale and North-East Point. This is to allow for informed decision making for wetland management, to guide the development of a proposal for project interventions at these sites, and to be used as reference for an Environmental Impact Assessment of the proposed interventions.
Methods of ecosystem rehabilitation need better testing for hydrological impacts | Low risk. | The methods of ecosystem rehabilitation measures are being evaluated by both local and international experts prior to decision-making. The scientific community will be engaged to ensure that rehabilitation experiences are adjusted and refined to address hydrological variables, including informed understanding of forest cover change and watershed runoff and infiltration using various methods. Intensive discussion on the selection of appropriate methods and species, and the monitoring systems to assess performance will be included.
Adaptation measures increase inequity | Low risk. | The project promotes social inclusion. Gender equality is addressed in the project by ensuring equal opportunity for women and men to participate on local watershed committees, and by promoting gender balance in training programmes.
The cost of the proposed measures may be higher than expected. | Low/medium risk. | Estimating the cost of adaptation is a complex matter. Nevertheless the scale of intervention within the first reporting period has been within the budget.
Critical Risks Affecting Progress (Not identified at project design)
Identify Risks with a 50% or > likelihood of affecting progress of project
Identified Risk | Current Status | Steps Taken to Mitigate Risk
Private lands identified for potential forest rehabilitation within the catchhment areas may not be available if land owners refuse to approve the rehabilitation works or if it is unclear who owns the land (such as when the land is under probate) | Medium risk. There is a possibility that land may not be available for rehabilitation. | Baie Lazare: The project team has made several field visit to identify potential areas for rehabilitation and 13 hectares has been identified to date. Some of this land was formerly owned by a private individual who has gone bankrupt and his assets are in process of being seized. Until this process is complete and the land resold, the person to be approached to approve the rehabilitation work cannot be defined.
Risk Measures: Were there any risk mitigation measures employed during the current reporting period? If so, were risks reduced? If not, why were these risks not reduced?
Add any comments relevant to risk mitigation (word limit = 500)
The above mentioned risk was identified in July 2015 and mitigation will be reported on in the next PPR.

## Rating
RATING ON IMPLEMENTATION PROGRESS
For rating definitions please see bottom of page.
| Progress on Key Milestones |  | Expected Progress |  | Progress to Date | Rating
Project Manager/Coordinator: | Inception phase of the project completed |  | Inception was expected to take 3 months from the date of signature. This was delayed due to late recruitment of the project manager, but commenced ahead of the recruitment of the rest of the Project Implementation Team (PIT) |  | Inception commenced in September 2014 with the recruitment of the Project Manager. The Inception Workshop was held on 30th October 2014 in Victoria, Mahe. There were 31 participants including the UNDP TA for AF projects. The Inception Report was produced in November 2014. | S
Component 1: Ecosystem-based adaptation approach to enhancing freshwater security and flood control in Mahé and Praslin under conditions of climate change
| Output 1.1 Management and rehabilitation of critical watersheds to enhance functional connectivity and the resilience of these areas to climate change and reduce water scarcity and watershed flooding (Mare aux Cochons, Mt Plaisar, Baie Lazare, Caiman, Praslin Fond B’Offay/Nouvelle Decouvert watershed management) |  | Mare aux cochons, Mont Plaisir, Baie Lazare, Caiman watershed: planning and start of invasive species management programmes. Praslin: completion of nursery, start of vegetation management and replanting programme |  | Initial assessments of the five watershed areas have been conducted by project staff (required prior to planning of interventions). Mahe: TORs are under development for specific inventory work and definition of focus areas in Mont Plaisir and Caiman. Planning of interventions at Baie Lazare was held up with coarification fo land ownership issues, permissions are needed prior to interventions being planned. Interventions at Mare aux Cochons were delayed by a need to develop a MOU with SNPA (the area is a National Park and part is a World Heritage Site) and a need to obtain very specific technical advice on interventions. For this it was agreed to establish a Technical Advisory Group, and TORs have been developed. Praslin: An MOU has been prepared with the NGO TRASS for extension of their tree nursery, which will provide seed stock. TORs for the planting interventions have been prepared for advertisement. | MU
| Output 1.2 Small-scale water storage and detention facilities designed and constructed or rehabilitated in critical waterways for communities to benefit from enhanced ecosystem functioning by forests (Mare aux Cochons, Mt Plaisar, Baie Lazare, Caiman, Praslin Fond B’Offay/Nouvelle Decouvert watershed control structures) |  | Mare aux cochons, Mont Plaisir, Caiman watershed: assessment of needs for renovation of existing barrages. Baie Lazare: assessment of water conflict issues, planning for additional barrages. Praslin: assessment of need for new check dam |  | Discussions have been held with PUC concerning barrage renovations at the target sites, but PUC has been very slow to participate in field visits and to provide ideas and recommendations. At Baie Lazare a study of water demand has been carried out and extensve discussions held with the community concerning issues of concern, followed up with discussions with PUC over competing water uses, including cross-watershed abstraction. No interventions can yet be planned pending settlement of land ownership issues. Praslin: no progress as yet. | MU
| Cross-cutting issues |  | PIT fully in place. Watershed management committees in place. Initial awareness materials designed and printed. Training on priority issues commenced. |  | Advertisements and recruitment was conducted for four PIT staff, all of whom were in place by early 2015. The Community Engagement Specialist, once recruited, commended discussions for the establishment of waterhsed committees, working with the district administrations and other key local stakeholders. This proved a slow process and only one committee, Baire Lazare, was in place at end of reporting period. Some initial awareness materials were printed, some for general dissemination and some pecifically for the Baie Lazare committee. training commenced with short courses on plant identification and means of cleaning watercourses, which were applied at Baie Lazare to rivers overgrown by invasive alien plan species and/or choked with material including discarded waste. | MS
Component 2: Ecosystem-based adaptation approaches along the shorelines of the Granitic Islands reduce the risks of climate change induced coastal flooding
| Output 2.1 Ecosystem-based measures for flood protection on an urban shoreline (North-east Point) |  | Development of shoreline management plans, identificationof needs for wetland, reef and beach berm rehabilitation |  | A biodiversity assessment of the inland marsh has been planned and TORs developed, advertisement has commenced. Additional needs for studies on environmental flows and potential rehabilitation/reprofiling measures has been identified. These will need to be conducted as part of EIA prior to any interventions. TORs have been developed for a hydrographic study of the nearshore area and coral reefs, but it is apparent that some expertise does not exist in Seychelles and will have to be obtained through international consultancy. Initial research has been undertaken on e.g. means of rebuilding coral reefs in areas with strong nearshore currents. This will require specific modelling work. No work has yet been done on beach berm rehabilitation although the whole area will be properly mapped and assessed as part of the hydrographic surveys. | MU
| Output 2.2 Ecosystem-based measures for flood protection and mitigating salt water intrusion in an agricultural and tourism development area (Anse Royale) |  | Development of shoreline management plan taking into account the existing integrated coastal management plan, studies of wetland function, needs for shoreline rehabilitation and ecosystem-based measures to control saline intrusion |  | A biodiversity assessment of the inland marsh has been planned and TORs developed, advertisement has commenced. Discussions have been held with farmers and other donors on combining interventions to control salinity, this area also being targeted by other projects. | U
Component 3: Ecosystem based adaptation mainstreamed into development planning and financing
| Output 3.1: Policy and legal frameworks for watershed and coastal climate change adaptation |  | Analysis of institutional structures to identify policy gaps |  | This output is shared with at one other EBA project under implementation (funded by UNEP) and is also highlighted in an incoming EBA project (funded by EU). Discussions were held with the UNEP EBA project concerning how to coordinate activities in regard to this output. | MU
| Output 3.2 Capacity Development for Ecosystem Based Adaptation Methods |  | Capacity development for watershed committees |  | Only one watershed committee (Baie Lazare) is so far in place. Initial training programmes have been developed and some training in plant identification needed for clearing of invasive plant species has been carried out. A comprehensive training programme is in process of development by the PIT with inputs from the project Steering Committee. | MU
| Output 3.3 Lessons learned and Knowledge Dissemination |  | Development of a communications strategy |  | A strategy has not yet been developed. However, the project has proceeded with educational materials needed for dissemination of project intervenions (building local ownership) and in support of the first phase of the capacity building. A community survey was undertaken on 28th March and 4th April 2015 at Anse Royale and North East Point with the assistance of the University of Seychelles. Promotion of watershed management has been done through the use of the national media for publishing articles. Partnerships have been developed with the keyinstitutional partners, including PUC and SNPA. | MU
[5 empty] | Overall Rating | MU
Please Provide the Name and Contact information of person(s) reponsible for completeling the Rating section
| Name: | Betty Seraphine (Project Manager), Andrew Grieser Johns (Programme Coordinator)
| Email: | b.seraphine@pcusey.sc; a.grieserjohns@pcusey.sc
Please justify your rating. Outline the positive and negative progress made by the project since it started. Provide specific recommendations for next steps. . (word limit=500)
The project is overall rated (by the new PM and Programme Coordinator) as MU. This reflects the slow start to most activities and delays caused by early resignation of the first PM: the current PM was recruited at the beginning of July 2015. Handover by the first PM was unsatisfactory including no contribution to this PPR and no explanation for the long delays in initiating various activities. However, the PIT is fully in place and the staff are now working hard to catch up. Inception: The inception process was completed satisfactorily, if late. The inception report was prepared and uploaded to the project website. Component 1: The MU ratings reflect delays caused by a precuationary approach to designing interventions (including an identified need to seek external technical advice) and issues of land ownership that had to be resolved. Agreement has been obtained to work on Government land, pending MOUs with e.g. SNPA), and contacts are being forged with land under private ownership - so far with positive results except for a bankruptcy case where a new area has to be identified. Work will accelerate rapidly in the next year as TORs and contracts for the baseline ecological assessments and first 2 years of rehabilitation interventions are being prepared. Component 2: MU and U ratings reflect delays caused by long periods of discussion with the utilities company (PUC) without firm resolution on issues, in part through a lack of energy to resuscitate the Rivers Board which can make decisions. Field visits with PUC have taken place, however, and decisions are beginning to be made. The U rating for Anse Royale reflects a concerntration so far on NE Point, which is regarded as the higher priority, but it is realized that work at Anse Royale nees to pick up in the next year. Component 3: Delays here are in part due to a need to rationalize interventions with other EBA initiatives and in part due to slow movement with the two technical co ponents which would guide component 3, hence the further MU rating.TORs for major contracts in the next reporting period are being prepared. reflects has been a surge in the development of TORs, advertisement and recruitment of contractors since July such that progress in the next reporting period is expected to be considerably improved. Good relationships have also been built by the PIT with key stakeholders and with target communities, which will asist improved implementation progress in year 2. Next steps: A new project manager has been appointed at the end of this reporting period and instructed to a) continue to ensure clear scientific guidance to project interventions, especially in sensitive areas; b) check needs for EIAs for interventions and make sure the baseline information on biodiversity, environment, social needs, etc., is in place to inform the EIA and subsequent interventions, and c) move forward as fast as possible in sites such as the Praslin watersheds where intervention to rehabilitate the bare soils is easy to agree and rehabilitation techniques have already been thoroughly researched. A dialogue will continue to be held with the UNEP EBA project and incoming EU-funded GCCA+ to ensure complementarity of work - beyond the geographical separation that so far justifies having three quite similar projects in Seychelles.
| Progress on Key Milestones |  | Expected Progress |  | Progress to Date | Rating
Implementing Agency | The project start up was delayed significantly as the PM was only hired in September 2014 even if the Project was signed beginning of June 2014 between UNDP and the Ministry of Environment. The main factors which delayed start up was the time it takes for idenfitying a suitable candidate. Furthermore delays encountered during implementation wa due to the fact that the PM only lasted 8 months and the Programme Coordinating Unit had to launch the process to recruit a replacement. Changes at the level of the Ministry also implied that the National Project Director changed during the reporting period and the Personnel involved had to be briefed on the project all over again. Likewise, the oversight mechanism was not in place till September 2014 when UNDP had to initiate the revival of the National Climate Change Committee and establishment of a sub Committee to oversee the AEBA project implementation. Recruitment of the PIT took a long time before the team was in place. Given the capacity constraints, the milestones forseen in the first year of implementation could not be reached. However, with the team now in place, a number of activities have been launched and will be reported on in the next Report. Progress for the first year has been slow , but the foundatons are now established for increased implementation for the remainder of the project, provided there is no turnover in the PIT core team. |  | It was expected that by the end of year one of implementation, the following would have been achieved: 1. Starting the management and rehabilitation at the Mare aux Cochons River Watershed, as well for the caiman River, Praslin Fond Boffay and nouvelle decouverte watershed. These have been delayed as only one watershed committee has been set up. 2. Integrated Shoreline Management Plan has not been initiated. 3. The works for the Wetland Rehabilitation have only been tendered and have not been started at both selected sites. 4. Reef Rehabilitation and Beach Berm Enhancement cannot start until later in the project phase. 5. For output 2.2, the Integrated Shoreline Management Plan has not been initiated yet. 6. The Stream Channel, Wetland Rehabilitation and Shoreline Rehabilitation have not started for Anse Royale district. 7. Ecosystem Based Salinization Control Measures have been discussed with no particular interventions made at this point. Some of these activities could have been initiated in the first year by the first project manager but they experienced delayed for various reasons mentioned. |  | Given that actual implementation is for only 9 months, progress is marginall satisfactory when compared to other projects of similar magnitude and focus. The major obstacles is mobilisation of community elements to ensure buy-in, ownership and sustainability of the activities as it is very difficult in seychelles to mobilize communities and get their involvement in donor funded projects. However, with the recruitment of the Community Engagement Officer, this acruvity is now progressing satisfactorily in the 2 areas where the project has started the actifities. Community engagement however is a long term process that requires nurtuting if it is to be suatainable, and requires tangible results to maintai community interest. Speeding up some of the physical rehabilitation works in those areas will need to be enhanced over the next year of implementation. AS for the technical acrivities and training, this is ongoing satisfactorily and results will be reported upoj in the next Report as the first year has been devoted more to baseline work and preparation of materisl/modules which will now be rolled out in the various project sites/target beneficiaries/stakeholders. | MU | Can you please provide a more comprehensive reporting against the logframe and the workplan agreed in the inception workshop? Please see the examples. At least provide progress against the components
Overall Rating
Please Provide the Name and Contact information of person(s) reponsible for completeling the Rating section
| Name: | Roland Alcindor
| Email: | roland.alcindor@undp.org
| Progress on Key Milestones |  | Expected Progress |  | Progress to Date | Rating
Other
Overall Rating
Please Provide the Name and Contact information of person(s) reponsible for completeling the Rating section
Name:
Email:
| Please justify your rating and address the following points: 1. Indicate trends, both positive and negative, in achievement of outcomes as per the project indicators. 2. Detail critical risks that have affected progress. 3. Outline response to MTR undertaken this reporting period. 4. Outline action plan to address projects with a rating of HU, U or MU. Please keep your input to 1200 words |  | The project is tated Marginaally Unsatisfactory because progress has been slow and for all the reasons outlined above. Due to difficulties to start the project on time the implementation of the activities during this reporting period is below expectations. As indicated in the Project indicators, planned outputs for Year 1 has not been achieved. Critical risks: The newly identified risk that land most suitable for rehabilitation is under private ownership is critical only for Baie Lazare, as identified at this point. This is being addressed by identification of other potential areas, not optimally suitable for rehabilitation due to slope but where project interventions may be applied. The issue of land ownership and need to carefully expalin project objectoves and put MOUs into place, etc., has delayed project interventions during this period, but the project is now proceeding in all target sites. Action plan to address MU rating: 1) MOUs to be put into place to complete and formalize agreements with Government agencies for interventions on Government land, and with private land owners for interventions on their land (noting that all the areas identified for project interventions are no-development zones, even if privately owned). 2) Emphasis to be placed on awareness building and working with communities to try to provide an impetus in establishing of watershed communities (most community members are highly in favour of having such a committee but not willing to invest their own time in it). This needs to be a core area within the communications strategy and supported with capacity building as necessary - although it is noted that mtivation is really the key issue here. 3) Technical Advisory Group to be constituted to research and review scientific merit of interventions proposed in sensitive areas and ensure intervemtions are robust and not likely to adversely affect project indicators. Forest rehabilitation interventions are likely to focus more on replacing IAS in the understory than on removing large invasive trees, which would open up areas for more harmful IAS invasions. The question of how to address the cinnamon 'novel ecosystem' also has to be determined based in scientific inputs. 4) High levels of the MEECC will be engaged in putting some pressure on the utility company (PUC) to work with the project more effectively in deciding on barrage renovations (with EBA adjustments such as runs and steps to allow passage of eels and other fish that might migrate up and down the streams) and in resuscitating the Rivers Committee/Board, which they chair, as a decision making body for integrated watershed management planning (noting that at the moment there is a planning vacuum in this respect). 5) Additional technical advice to be sought on articial reef building using concrete structures as a base and subsequent coral restoration ain areas where there are strong currents that would make establishment of coral nurseries difficult. This will require engagement of offshore companies with enperience in modelling of todal flos, etc., and in establishing this type of structures. 6) Discussions will be held with technical experts at UNISEY to increase the project attention on shoreline EBA measures, and also in addressing soil salinity issues (in cooperation with other donors). 7) Close collaboraton and exploration of synergies beteen the three EBA projects need to be further explored. The three projects focus on interventions on Mahe and Praslin upper watersheds (this project), Praslin coastal areas (UNEP) and La Digue (EU) but need to be brought into closer synchrony in terms of advancing on EBA policy, capacity building at the national level, etc. |  |  |  | Roland please add justification for rating
Rating Definitions
|  |  | Highly Satisfactory (HS) | Project actions/activities planned for current reporting period are progressing on track or exceeding expectations to acheive all major outcomes/outputs for given reporting period, without major shortcomings. The project can be presented as “good practice”.
|  |  | Satisfactory (S) | Project actions/activities planned for current reporting period are progressing on track to achieve most of its major outcomes/outputs with only minor shortcomings.
|  |  | Marginally Satisfactory (MS) | Project actions/activities planned for current reporting period are progressing on track to achieve most major relevant outcomes/outputs, but with either significant shortcomings or modest overall relevance.
|  |  | Marginally Unsatisfactory (MU) | Project actions/activities planned for current reporting period are not progressing on track to achieve major outcomes/outputs with major shortcomings or is expected to achieve only some of its major outcomes/outputs.
|  |  | Unsatisfactory (U) | Project actions/activities planned for current reporting period are not progressing on track to achieve most of its major outcomes/outputs.
|  |  | Highly Unsatisfactory (U) | Project actions/activities planned for current reporting period are not on track and shows that it is failing to achieve, and is not expected to achieve, any of its outcomes/outputs.

## Project Indicators
PROJECT Indicators
Please provide all indicators being tracked for the project as outlined in the project document
Type of Indicator (indicators towards Objectives, Outcomes, etc…)
Type of Indicator | Indicator | Baseline | Progress since inception | Target for Project End
Project Objective | Ecosystem services and natural assets maintained or improved under climate change and variability-induced stress | Project watersheds and coastal areas are regularly subject to water shortages and flooding events | The water resources assessment has been completed in Baie Lazare and is ongoing for the other 4 catchment areas. A scientific assessment of the biodiversity in the marshes of Anse Royale and North-East Point have been conducted. A hydrodynamic survey is being carried out for the coastal zone. | Reduced water shortages and flooded area involving about 4,000 ha of watershed and coastal ecosystems
Project Objective | August mean daily discharge on two rivers (Mare aux Couchons & Baie Lazare) with increased base flows78 | Mare aux Couchons August Avg Mean Daily Discharge: 261.1 L/S Baie Lazare August Mean Daily Discharge: 33.4 L/S | The Mare-aux-Cochons flow weir is not in service since 2013 such that a current baseline is not available. A new structure has been approved and will be designed shortly to provide an updated baseline (or verify the older baselines). Data from Baie Lazare should be available from PUC but has not yet been obtained. As there have been no interventions from the project as yet the discharge rates are as per baselines. | Mare aux Cochons and Baie Lazare: Aug. baseline flows +20 – 30%
Project Objective | January mean daily discharge on two rivers with decreased flood flows | Mare aux Couchons January Avg Mean Daily Discharge: 595.4 L/S Baie Lazare January Mean Daily Discharge: 173.1 L/S | As above. | Mare aux Cochons and Baie Lazare: January baseline flows -20%
Component 1 | Number of water users with more reliable water supply | 10% of PUC water supply customers in project watersheds without fully reliable surface water supply | The baseline needs to be verified as the figure indicated by PUC is considerably higher, It has been agreed with PUC that the weir at Mare aux Cochons will be refurbished by the project to improve water storage. | 100% of PUC customers in target watersheds with more reliable water supply
Component 1 | Number of days per year water supply is not available at two sites: Baie Lazare and Mare aux Cochons | Number of days per year when stream flows at critical low: Baie Lazare: avg. 18 days Mare aux Cochons: avg. 75 days (2010 - 2011) | There are two dimensions to this indicator. First, in terms of storage capacity to ensure water supply to customers from the catchements, a weir is in place at Baie Lazare to store water during the rainy season. Hydrological studies are underway to determine how the storage capacity of the watershed may be improved and indications are that there is considerable scope for additional barrages and improvement of storage capacity within rehabilitated wetlands. At Mare aux Cochons similar studies are being designed to assess the capacity of the existing barrages and needs for renovation. Secondly, in terms of environmental services provided by the foreest in storing water, the natural storage capacity, studies are being designed and consultation is underway with the Technical Advisory Group to determine interventions that will build natural storage capacity over time (and not cause reductions in storage capacity over the stort term while large trees are removed and before newly planted trees are established, etc.). | 0 days of no water availability per year in project watersheds
Component 1 | Volume of raw water production from PUC facilities in project watersheds | Annual water production at: Mare aux Cochons: 614,336 KL Baie Lazare: 191,232 KL | No change is effected at this time as project interventions have not yet started. There has been no water shortage in 2015 due to a mild dry season. | Annual water production figures increase by 20%
Component 1 | Number of hectares of watersheds covered by site-based water management plans | 0 hectares | Watershed management plans have not yet been developed; project interventions so far have focussed on initial assessments and on developing watershed committees who will develop and own the management plans (1 of 5 watershed committees is now in place). | 3,000 ha of critical watersheds
Component 1 | Area of rehabilitated water provisioning and watershed flooding attenuation ecosystems | Total hectares of watershed with increased resilience to climate change: 0 Total area of watershed that has undergone total rehabilitation: 0 | Interventions not yet started. | Total hectares of watershed with increased resilience to climate change: 3000 ha Total area of forest that has undergone total rehabilitation: at least 60 ha
Component 1 | Active community watershed committees (with gender balance) | No watershed committees established | 1 watershed committee has been set up in the district of Baie Lazare and is actively involved in the management of their catchment area. It comprises of 13 members, of which 6 are female. | At least 4 watershed committees established with gender balance
Component 2 | Area of rehabilitated coastal ecosystems | # of tidal sluice gates installed: 0 | No interventions as yet. A baseline study of hydrographic conditions is on-going. | # of tidal sluice gates installed: 2 by end of project
|  | Little wave energy attenuation provided by reef (5% of the pre-1998 bleaching event reef size) | No interventions as yet. A baseline study of hydrographic conditions is on-going. | 150 m of artificial breakwater providing substrate for coral growth and wave energy attenuation and more than 10% of original reef area rehabilitated at NE Point
|  | Total hectares of wetlands rehabilitated to provide flood attenuation services: 0 ha | Baseline biodiversity and water flow studies are on-going to determine appropriate interventions. | Total hectares of wetlands rehabilitated to provide flood attenuation services: 17 ha
|  | Total km of rehabilitated beach berms providing a barrier for coastal floods: 0 km | No interventions as yet. | Total km of rehabilitated beach berms providing a barrier for coastal floods: 5 km
|  | Total hectares of mangroves, wetlands, fringing reef, beach berms and other ecosystems with increased resilience to climate change impacts: 0 | No interventions as yet. | Total hectares with increase resilience: 1,000 ha
Component 2 | Farm pond salinity levels reduced | Up to 6.0 ppt salinity levels in farm ponds during dry season | A training workshop on soil salinity assessment and management has been undertaken and the institutional capacity of the Seychelles Agricultural Agency has been built to train farmers how to adapt to soil salinity. Interventions to assist this process are being defined by SAA. | 70% less salinity levels in farm ponds during the dry season
Component 2 | Number of hectares of coastal ecosystems covered by Integrated Shoreline Management Plans | 0 hectares | No interventions as yet. | 1,000 ha of coastal ecosystems
Component 3 | Approved water management policy framework being implemented for watershed areas | No policy and financing framework | Requirements for revision of the legal framework have not yet been developed. Discussions have been held with PUC consultants and there is consensus on the need to develop a regulatory framework for water management in Seychelles. This will include re-defining the mandate of the Rivers Committee and potentially deferring a regulatory function from PUC to a new unit within MEECC. | Approved water management policy for watershed areas Core annual funding for local watershed management provided by tariffs and fees: $ 500,000
Component 3 | Capacity developed for EbA methods: Rivers Committee meet regularly. | No institutional mechanisms | The project team is encouraging the Rivers Committee to be reconstituted - this is being backed up by project steering committee but as yet there is no response from PUC who chair the RC.. | River Committee meets every quarter to discuss and address issues
| A National Watershed Monitoring System developed, applied and influences watershed management decisions | Little information available regarding functional connectivity, watershed integrity and water balance of watersheds | Educational materials are being developed by the project implementation team. | Institutionalised and operational watershed monitoring system ensures adaptive management of watershed systems.
| Technical standards established for watershed, tidal wetland, and beach and reef rehabilitation | Incomplete and ad hoc specifications for ecosystem rehabilitation | The project has proposed, and the Steering Committee has approved, the establishment of a Technical Advisory Group comprising scientific consultants based inside and outside of Seychelles who will assist with the development of technical standards. This group will be tasked with analysing conflicting opinions and making recommendations for rehabilitation actions, particularly in ecologically sensitive areas. | Technical standards are established and provide the basis for training
| Number of trainees by gender skilled in EbA methods | Few government or NGO staff experienced in watershed or wetland rehabilitation | Training programmes are being developed for stakeholders; a preliminaty programme has been reviewed by the Steering Committee and will be implemented from year 2. | 50 persons (gender balanced) trained in watershed, tidal wetland and beach and reef rehabilitation
Component 3 | Number of knowledge products on watershed and coastal ecosystem- based adaptation | Limited awareness of EbA methods related to watersheds and coastal ecosystems | A Watershed Committee Guide has been developed for local communities to assist in establishing and defining a role for local watershed committees. For Baie Lazare Watershed a brochure "Our Water, Our Choice" has been published and disseminated (1000 copies). An EbA brochure has been developed and published in English & Creole (1000 copies each). 200 t-Shirts with project message and logos and 500 caps have been produced and many distributed. | 10 knowledge products produced to assist awareness building

## Lessons Learned
QUALITATIVE MEASURES and LESSONS LEARNED
Please complete the following section every reporting period
Implementation and Adaptive Management | Response
What implementation issues/lessons, either positive or negative, affected progress? | Project implementation is at an early stage and little can be said at this point. It is clear, however, that a particular effort in working with partners and communities, and in starting out with a clear communications strategy, has been highly benficial in creating interest in the project and its activities. On the negative side, it is becoming clear that the local capacity to implement elements of the project is quite limited, and that there are quite few companies or NGOs that can take on major sub-contracts such as hydrographic surveys or forest rehabilitation. Whether this becomes a critical factor in slowing down implementation remains to be seen.
Were there any delays in implementation? If so, include any causes of delays. What measures have been taken to reduce delays? | There were severe delays in the project start up. Although the project document was signed in early June 2014, a project manager was not recruited until September, and the Inception Workshop was held on 30th October. Progress in the next 8 months was very slow, to some extent because of delays in recruiting other PIT members but also because the PM felt the need to engage in extensive discussion on the project approaches prior to implementing activities, such that the development of TORs for the first inputs were slow to materialize. While this helped in establishing good working relationships with partners, it meant that project interventions were mostly not started during this reporting period. The PM resigned in May and left in June, with a new manager (fortunately recruited very quickly) coming on board in July. However, the first manager departed without leaving much behind in terms of notes and without contributing to this PPR, such that documentation of progress in this reporting period has been rather incomplete. The new manager, who started work on 1st July, is experienced and is expected to bring a new dynamism to the project team that will quickly speed up the delivery of outputs.
Describe any changes undertaken to improve results on the ground or any changes made to project outputs (i.e. changes to project design) | There have been no specific changes made to date, although there has been discussion on the distribution and number of hectares of land to be rehabilitated per catchment. This may need to be modified further due to issues of ownership of the most suitable areas for rehabilitation. A further issue that needs to be addressed is the opinion of stakeholders expressed in the Inception Workshop that some indicators are unrealistic - rehabilitation of watersheds is a long term process and it may be many years before reforested areas begin to impact significantly on water flow, for example. The target of 60 ha rehabilitated is reachable, the question is more whether the extent of rehabilitation in the lifetime of the project will be sufficient to impact on the water regime. Concerning the 150m reconstructed breakwater proposed for north-east Point, there are complications resulting from the strong currents in this area, but these are being assessed and modelled to determine the best means of approaching coral reef restoration. The feasibility of different methods already researched in Seychelles will be assessed based on the modelling results.
How have gender considerations been taken into consideration during the reporting period? What have been the lessons learned as a consequence of inclusion of such considerations on project performance or impacts? | The PIT, which is itself gender balanced with two members, including the PM, being female, has paid particular attention to this aspect. Gender balance is required in, for example, local watershed committees - the first watershed committee established in Baie Lazare district has 13 members of whom 6 are female. The community engagement process is facilitated by the dynamism of the women, which can be more pronounced than among men.
Please complete the following section at mid-term and project completion
Lessons for Adaptation | Response
Climate Resilience Measures
What have been the lessons learned, both positive and negative, in implementing climate adaptation measures that would be relevant to the design and implementation of future projects/programmes for enhanced resilience to climate change?
What is the potential for the climate resilience measures undertaken by the project/programme to be replicated and scaled up both within and outside the project area?
Concrete Adaptation Interventions
What have been the lessons learned, both positive and negative, in implementing concrete adaptation interventions that would be relevant to the design and implementation of future projects/programmes implementing concrete adaptation interventions?
What is the potential for the concrete adaptation interventions undertaken by the project/programme to be replicated and scaled up both within and outside the project area?
Community/National Impact
What would you consider to be the most successful aspects for the target communities?
What measures are/have been put in place to ensure sustainability of the project/program results?
What measures are being/could have been put in place to improve project/program results?
Knowledge Management
How has existing information/data/knowledge been used to inform project development and implementation? What kinds of information/data/knowledge were used?
If learning objectives have been established, have they been met? Please describe.
Describe any difficulties there have been in accessing or retrieving existing information (data or knowledge) that is relevant to the project. Please provide suggestions for improving access to the relevant data.
Has the identification of learning objectives contributed to the outcomes of the project? In what ways have they contributed?

## Results Tracker
Results Tracker for Adaptation Fund (AF) Projects
Goal: Assist developing-country Parties to the Kyoto Protocol that are particularly vulnerable to the adverse effects of climate change in meeting the costs of concrete adaptation projects and programmes in order to implement climate-resilient measures. Impact: Increased resiliency at the community, national, and regional levels to climate variability and change.
Important: Please read the following guidance document (also posted on the Adaptation Fund website) before entering your data
Link: http://www.adaptation-fund.org/sites/default/files/Results%20Framework%20and%20Baseline%20Guidance%20final.pdf
Adaptation Fund Strategic Results Framework
Project ID | 89895
Implementing Entity | Ministry of Environment, Energy and Climate Change
Type of implementing entity | NIE
Country | Seychelles
Region | Africa
Sector | Water management
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Impact: Increased resiliency at the community, national, and regional levels to climate variability and change | Core Indicator: No. of beneficiaries Note: For this project the direct beneficiaries will be PUC customers and other water users in the target sites; indirect beneficiaries will be customers and users outside the target sites who either receive water piped or flowing from those sites, benefit from improved coastal defences at the target sites, etc. This information was cpllected in 2012 and presented in the Prodoc, but without the youth dimension. As 47% of the Seychelles population is youth (aged below 30), as per the Seychelles Youth Council, this is the figure used. |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project
|  | Total | 0 | 0 | 0 | Total | 89045 | 21545 | 67500 | Total |  |  |  | Total
|  | % of female beneficiaries | 50% | 50% | 50% | % of female beneficiaries | 50% | 50% | 50% | % of female beneficiaries |  |  |  | % of female beneficiaries
|  | % of Youth beneficiaries | 47% | 47% | 47% | % of Youth beneficiaries | 47% | 47% | 47% | % of Youth beneficiaries |  |  |  | % of Youth beneficiaries
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 1: Reduced exposure to climate-related hazards and threats | Indicator 1: Relevant threat and hazard information generated and disseminated to stakeholders on a timely basis | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness
|  | Total | 0 | Coastal flooding | 1: Ineffective | Total | 89045 | Coastal flooding | 4: Effective | Total |  |  |  | Total
|  | % of female targeted | 50% |  |  | % of female targeted | 50% |  |  | % of female targeted |  |  |  | % of female targeted
Output 1.1 Risk and vulnerability assessments conducted and updated | Indicator 1.1: No. of projects/programmes that conduct and update risk and vulnerability assessments Note: At baseline there is one project developing a vulnerability assessment, but this is not part of the AF project and neither is this to be followed up under the AF project. | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | 1 | Disaster risk reduction | National | 2: Undertaking or updating of assessments in progress | 1 | Disaster risk reduction | National | 3: Risk and vulnterability assessments completed or updated
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
Output 1.2 Targeted population groups covered by adequate risk reduction systems | Core Indicator 1.2: No. of Early Warning Systems Note: This is not a part of the current project as the project does not work directly with Departent of Risk and Disaster Management (DRDM) - which has other sources of funds. | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 2: Strengthened institutional capacity to reduce risks associated with climate-induced socioeconomic and environmental losses | Indicator 2: Capacity of staff to respond to, and mitigate impacts of, climate-related events from targeted institutions increased | Number of staff targeted |  | Sector | Capacity level | Number of staff targeted |  | Sector | Capacity level | Number of staff targeted |  | Sector | Capacity level | Number of staff targeted |  | Sector | Capacity level
|  | Total | 50 | Multi-sector | 1: No capacity | Total | 50 | Multi-sector | 4: High capacity | Total |  |  |  | Total
|  | % of female targeted | 50% |  |  | % of female targeted | 50% |  |  | % of female targeted |  |  |  | % of female targeted
Output 2.1 Strengthened capacity of national and sub-national centres and networks to respond rapidly to extreme weather events | Indicator 2.1.1: No. of staff trained to respond to, and mitigate impacts of, climate-related events | Total staff trained | % of female staff trained | Type |  | Total staff trained | % of female staff trained | Type |  | Total staff trained | % of female staff trained | Type |  | Total staff trained | % of female staff trained | Type
|  | 0 | 0% | Public |  | 50 | 50% | Public
| Indicator 2.1.2: No. of targeted institutions with increased capacity to minimize exposure to climate variability risks | Type | Scale | Sector | Capacity level | Type | Scale | Sector | Capacity level | Type | Scale | Sector | Capacity level | Type | Scale | Sector | Capacity level
|  | Public | National | Multi-sector | 1: No capacity | Public | National | Multi-sector | 3: Medium capacity
output 2.2 removed and associated fund indicator 2.2.2 recommendation to report against 2.1
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 3: Strengthened awareness and owernship of adaptation and climate risk reduction processes | Indicator 3.1: Increase in application of appropriate adaptation responses Note. Refers to direct beneficiaries calculated at 21,545 persons. | Percentage of targeted population applying adaptation measures |  | Sector |  | Percentage of targeted population applying adaptation measures |  | Sector |  | Percentage of targeted population applying adaptation measures |  | Sector |  | Percentage of targeted population applying adaptation measures |  | Sector
|  | 0% |  | Coastal management |  | 70 |  | Coastal management
Output 3: Targeted population groups participating in adaptation and risk reduction awareness activities | Indicator 3.1.1: Percentage in targeted population awareness of predicted adverse impacts of climate change, and of appropriate responses Note. Baseline knowledge survey not yet undertaken to verify. | No. of targeted beneficiaries | % of female participants targeted | Level of awareness |  | No. of targeted beneficiaries | % of female participants targeted | Level of awareness |  | No. of targeted beneficiaries | % of female participants targeted | Level of awareness |  | No. of targeted beneficiaries | % of female participants targeted | Level of awareness
|  | 21545 | 50% | 3: Partially aware |  | 21545 | 50% | 5: Fully aware
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Target performance at completion |  |  |  | Target performance at completion
Outcome 4: Increased adaptive capacity within relevant development sector services and infrastructure assets | Indicator 4.1: Increased responsiveness of development sector services to evolving needs from changing and variable climate | Project/programme sector | Geographical scale | Response level |  | Project/programme sector | Geographical scale | Response level |  | Project/programme sector | Geographical scale | Response level |  | Project/programme sector | Geographical scale | Response level
|  | Water management | National | 2: Partially responsive (Lacks most elements) |  | Water management | National | 4: Mostly responsive (Most defined elements)
| Core Indicator 4.2: Assets produced, developed, improved or strengthened | Sector | Targeted asset | Changes in asset (quantitative or qualitative) |  | Sector | Targeted asset | Changes in asset (quantitative or qualitative) |  | Sector | Targeted asset | Changes in asset (quantitative or qualitative) |  | Sector | Targeted asset | Changes in asset (quantitative or qualitative)
|  | Water management | 2: Physical asset (produced/improved/strenghtened) | 1: Not improved |  | Water management | 2: Physical asset (produced/improved/strenghtened) | 4: Mostly Improved
|  | Coastal management | 2: Physical asset (produced/improved/strenghtened) | 1: Not improved |  | Coastal management | 2: Physical asset (produced/improved/strenghtened) | 4: Mostly Improved
Output 4: Vulnerable development sector services and infrastructure assets strengthened in response to climate change impacts, including variability | Indicator 4.1.1: No. and type of development sector services to respond to new conditions resulting from climate variability and change | Number of services | Type |  | Sector | Number of services | Type |  | Sector | Number of services | Type |  | Sector | Number of services | Type |  | Sector
|  | 0 | National |  | Water management | 1 | National |  | Water management
|  | 0 | National |  | Coastal management | 1 | National |  | Coastal management
|  | 0 | Multi-community |  | Agriculture | 1 | Multi-community |  | Agriculture
indicator 4.1.2 removed we can only really change this to reporting 4.1.1
|  | Baseline information |  |  |  | Targeted performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 5: Increased ecosystem resilience in response to climate change and variability-induced stress | Indicator 5: Ecosystem services and natural resource assets maintained or improved under climate change and variability-induced stress | Natural resource improvement level |  | Sector | Type | Natural resource improvement level |  | Sector | Type | Natural resource improvement level |  | Sector | Type | Natural resource improvement level |  | Sector | Type
|  | 1: Ineffective |  | Multi-sector | land | 4: Effective |  | Multi-sector | land
Output 5: Vulnerable ecosystem services and natural resource assets strengthned in response to climate change impacts, including variability | Core Indicator 5.1: Natural Assets protected or rehabilitated Note. Baseline figures are set at 0 and refer to the areas targeted for rehabilitation by the project; some of these areas are nominally protected but this is ineffective. Nationally there are other areas that have been rehabilitated to varying degrees and levels of effectiveness. | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Forests |  | ha rehabilitated | 1: Ineffective | Forests | 650 | ha rehabilitated | 3: Moderately effective
|  | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Forests |  | ha rehabilitated | 1: Ineffective | Forests | 60 | ha rehabilitated | 5: Very effective
|  | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Coasts |  | km rehabilitated | 1: Ineffective | Coasts | 5 | km rehabilitated | 4: Effective
|  | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Other |  | ha rehabilitated | 1: Ineffective | Other | 17 | ha rehabilitated | 4: Effective
|  | Baseline information |  |  |  | Targeted performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 6: Diversified and strengthened livelihoods and sources of income for vulnerable people in targeted areas | Indicator 6.1: Increase in households and communities having more secure access to livelihood assets Note. Refers to farmng households. 55% of female headed households is as per national average reported in household surveys (but noting that in a hgh percentage of cases the respondent is female) | No. of targeted households | % of female headed households | Improvement level |  | No. of targeted households | % of female headed households | Improvement level |  | No. of targeted households | % of female headed households | Improvement level |  | No. of targeted households | % of female headed households | Improvement level
|  | 600 | 55% | 2: Limited improvement |  | 600 | 55% | 3: Moderate improvement
| Indicator 6.2: Increase in targeted population's sustained climate-resilient alternative livelihoods | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
|  | 600 | 55% |  | Agriculture | 600 | 55% | From 20% to 30% | Agricultural-related
|  | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
|  | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
|  | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
Output 6 Targeted individual and community livelihood strategies strengthened in relation to climate change impacts, including variability | Indicator 6.1.1: No. and type of adaptation assets created or strengthened in support of individual or community livelihood strategies | Number of Assets | Type of Assets | Sector | Adaptation strategy | Number of Assets | Type of Assets | Sector | Adaptation strategy | Number of Assets | Type of Assets | Sector | Adaptation strategy | Number of Assets | Type of Assets | Sector | Adaptation strategy
|  | 1 | Natural capital | Coastal management | Community-based adaptation | 1 | Natural capital | Coastal management | Community-based adaptation
| Core Indicator 6.1.2: Increased income, or avoided decrease in income | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 7: Improved policies and regulations that promote and enforce resilience measures | Indicator 7: Climate change priorities are integrated into national development strategy | Integration level |  |  |  | Integration level |  |  |  | Integration level |  |  |  | Integration level
|  | 3: Some |  |  |  | 4: Most
Output 7:Improved integration of climate-resilience strategies into country development plans | Indicator 7.1: No. of policies introduced or adjusted to address climate change risks Note. Watershed management policy framework | No. of Policies introduced or adjusted | Sector | Scale | Type | No. of Policies introduced or adjusted | Sector | Scale | Type | No. of Policies introduced or adjusted | Sector | Scale | Type | No. of Policies introduced or adjusted | Sector | Scale | Type
|  | 0 | Water management | National | Water policy | 1 | Water management | National | Water Policy
| Indicator 7.2: No. of targeted development strategies with incorporated climate change priorities enforced Note. Seychelles Sustainable Development Strategy | No. of Development strategies | Regulation |  | Effectiveness | No. of Development strategies | Regulation |  | Effectiveness | No. of Development strategies | Regulation |  | Effectiveness | No. of Development strategies | Regulation |  | Effectiveness
|  | 1 | 2: Partially not enforced (Most elements not implemented) |  | 1: Ineffective | 1 | 3: Partially enforced (Some elements implemented) |  | 3: Moderately effective
Glacier lake outburst flood
|  | Inland flooding | fr | biological assets |  | Company policy | 5: Fully enforced (All elements implemented)
|  | Salinization | Decrease | land |  | Communication & Information policy | 4: Enforced (Most elements implemented)
|  | Drought | Same | water areas |  | Defense policy | 3: Partially enforced (Some elements implemented)
|  | Wind |  | subsoil assets | increased adpative capacity | Domestic policy | 2: Partially not enforced (Most elements not implemented) |  | Agribusiness
|  | Coastal flooding |  | air | achieved | Economic policy | 1: Not enforced (No elements implemented) |  | Agricultural-related | Financial capital
|  | Storm surge | Please choose |  | enhanced level of protection | Education policy |  |  | Agriculture | Human capital
|  | Hurricane | Selected | [5 empty] | Aquaculture | Physical capital
|  |  | Not relevant |  |  | 5: All (Fully integrated) |  |  | Construction/repairing business | Social capital
[6 empty] | 4: Most |  |  | Cultivation | Natural capital
[6 empty] | 3: Some |  |  | Fishing | Personal capital
Select | 5: All | Select |  |  | Community | 2: Most not integrated |  | Other | Forestry | Adaptation strategies
1 | 4: Almost all | Private | Type | Yes | Multi-community | 1: None |  | Agriculture | Handicrafts
2 | 3: Half | Public | Scale | No | Departmental |  |  | Coastal management | Livestock production
3 | 2: Some | NGO | Sector |  | National |  |  | Disaster risk reduction | Manufacturing
4 | 1: None |  |  |  |  | 5: Very high improvement | Established | Food security | other
|  | National |  |  |  | 4: High improvement | Maintained | Health | Services
|  | Regional |  |  |  | 3: Moderate improvement | Improved | Urban development | Tourism-related
|  | Local |  |  |  | 2: Limited improvement |  | Water management | Trading
[6 empty] | 1: No improvement |  | Multi-sector
|  | 1 -generated information is irrelevant, and neither the stakeholders reached nor the timeframe managed were achieved | 1: No info transferred on time | 4: High capacity | 5: Fully aware | 5: Highly responsive (All defined elements ) | 5: Fully improved | Roads | 5: Very effective
Asia-Pacific | NIE | 2 -the existence of some challenge in any of the three aspects of the indicator (generation of dissemination, stakeholders reached or timeframe managed) | 2: Somewhat info transferred | 3: Medium capacity | 4: Mostly aware | 4: Mostly responsive (Most defined elements) | 4: Mostly Improved | Gov Buildings | 4: Effective
Latin America and Caribbean | RIE | 3 -relevant information is generated and disseminated to all identified stakeholders on timely basis | 3: Info transferred on time | 2: Low capacity | 3: Partially aware | 3: Moderately responsive (Some defined elements) | 3: Moderately improved | Causeways | 3: Moderately effective
Africa | MIE |  |  | 1: No capacity | 2: Partially not aware | 2: Partially responsive (Lacks most elements) | 2: Somewhat improved | Airports | 2: Partially effective
Eastern Europe |  |  |  |  | 1: Aware of neither | 1: Non responsive (Lacks all elements ) | 1: Not improved | Schools | 1: Ineffective
| ha protected | [6 empty] | Training Centres
| ha rehabilitated | [5 empty] | Monitoring/Forecasting capacity | Hospitals
Afghanistan, Islamic Rep. of | km protected | [5 empty] | Policy/regulatory reform | Drinking water systems
Angola | km rehabilitated | 1: Risk knowledge | 1: No plans conducted or updated |  |  |  | Capacity development | Other
Albania |  | 2: Monitoring and warning service | 2: Undertaking or updating of assessments in progress |  |  | Communication & Information policy | Sustainable forest management
Argentina |  | 3: Dissemination and communication | 3: Risk and vulnterability assessments completed or updated |  |  | Domestic policy | Strengthening infrastructure | 1: Health and Social Infrastructure (developed/improved)
Armenia | Forests | 4: Response capability |  |  |  | Economic policy | Supporting livelihoods | 2: Physical asset (produced/improved/strenghtened)
Antigua and Barbuda | Mangroves |  |  |  |  | Education policy | Mangrove reforestation
Azerbaijan | Coasts |  | From 0 to 0.5% |  |  | Energy policy | Coastal drainage and infrastructure
Burundi | Rangelands |  | From 0.5 to 1% |  |  | Environmental policy | Irrigation system
Benin | Cultivated land/Agricultural land |  | From 1% to 5% |  |  | Foreign policy | Community-based adaptation
Burkina Faso | Catchment area/Watershed/Aquifer |  | From 5% to 10% |  |  | Health policy | Erosion control
Bangladesh | Protected areas/National parks |  | From 10% to 20% |  |  | Housing policy | Soil water conservation
Bulgaria | Other |  | From 20% to 30% |  |  | Human resource policies | Microfinance
Bahrain |  |  | From 30% to 40% |  |  | Information policy | Special Program for women
Bahamas, The |  |  | From 40% to 50% |  |  | Macroeconomic policy | Livelihoods
Bosnia and Herzegovina |  |  | Above 50% |  |  | Monetary policy | Water storage
Belarus | [5 empty] | Population policy | ICT and information dissemination
Belize | [5 empty] | Private policy
Bolivia | [5 empty] | Public policy
Brazil | [5 empty] | Science policy
Barbados | [5 empty] | Social policy
Bhutan |  | 3- relevant information is generated and disseminated to all identified stakeholders on timely basis |  |  |  | Transportation policy
Botswana |  | describe |  |  |  | Urban policy
Central African Republic |  | 2- the existence of some challenge in any of the three aspects of the indicator |  |  |  | Water policy
Chile |  | describe |  |  |  | Other policy
China, People's Republic of |  | 1- generated information is irrelevant and neither the stakeholders reached nor the timeframe managed were achieved
Cote d'Ivoire |  | describe
Cameroon
Congo, Dem. Rep. of
Congo, Republic of
Cook Islands
Colombia
Comoros
Cape Verde
Costa Rica
Cuba
Czech Republic
Djibouti
Dominica
Dominican Republic
Algeria
Ecuador
Egypt
Eritrea
Estonia
Ethiopia
Fiji
Micronesia, Fed. States of
Gabon
Georgia
Ghana
Guinea
Gambia, The
Guinea-Bissau
Equatorial Guinea
Grenada
Guatemala
Guyana
Honduras
Croatia
Haiti
Hungary
Indonesia
India
Iran, Islamic Republic of
Jamaica
Jordan
Kazakhstan
Kenya
Kyrgyz Republic
Cambodia
Kiribati
Saint Kitts and Nevis
Korea, Republic of
Lao People's Democratic Republic
Lebanon
Liberia
Libya
Saint Lucia
Sri Lanka
Lesotho
Lithuania
Latvia
Morocco
Moldova
Madagascar
Maldives
Mexico
Marshall Islands
Macedonia, former Yugoslav Republic of
Mali
Malta
Myanmar
Montenegro
Mongolia
Mozambique
Mauritania
Mauritius
Malawi
Malaysia
Namibia
Niger
Nigeria
Nicaragua
Niue
Nepal
Nauru
Oman
Pakistan
Panama
Peru
Philippines
Palau
Papua New Guinea
Poland
Korea, Dem. People's Rep. of
Paraguay
Romania
Russian Federation
Rwanda
Saudi Arabia
Sudan
Senegal
Solomon Islands
Sierra Leone
El Salvador
San Marino
Serbia
Sao Tome and Principe
Suriname
Slovak Republic
Slovenia
Swaziland
Seychelles
Syrian Arab Republic
Chad
Togo
Thailand
Tajikistan
Turkmenistan
Tonga
Trinidad and Tobago
Tunisia
Turkey
Tuvalu
Tanzania
Uganda
Ukraine
Uruguay
Uzbekistan
Saint Vincent and the Grenadines
Venezuela
Vietnam
Vanuatu
Samoa
Yemen, Republic of
South Africa
Zambia
Zimbabwe
Timor-Leste

## Units for Indicators
Fund Outcome Indicator Units
1. Generation of relevant data, Stakeholders, and Timeliness 2.1. Include both qualitative and quantitative measures of capacity level within targeted institutions 2.2. Number (men and women and other vulnerable groups) 3.1. Use scale from 1 to 5: 5: Fully aware 4: Mostly aware 3: Partially aware 2: Partially not aware 1: Aware of neither predicted adverse impacts of climate change nor of appropriate responses 3.2. Use scale from 1 to 5: 5: All 4: Almost all 3: Half 2: Some 1: None 4.1. Summarize in an overall scale (1-5): 5: Highly responsive (All defined elements ) 4: Mostly responsive (Most defined elements) 3: Moderately responsive (Some defined elements) 2: Partially responsive (Lacks most elements) 1: Non responsive (Lacks all elements ) 4.2. Summarize in an overall scale (1-5): 5: Fully improved 4: Mostly Improved 3: Moderately improved 2: Somewhat improved 1: Not improved 5. Depends on the targeted natural asset: Biological (species): measure through changes in population numbers (dynamics, structure, etc.) Land: measure changes in hectares. Baseline data will be necessary to estimate the change. Supporting indicators baseline and target (as well as contextual information) are needed such as the following: Farmers adopting recommended technologies, Ha. of land improved, Average deforestation rate Etc. Use scale from 1 to 5. 5: Very effective (All elements are present) 4: Effective (Most elements are present) 3: Moderately effective (Some elements are present) 2: Partially effective (Most elements are not present) 1: Ineffective (No elements are present) 6.1. Summarize in an overall scale (1-5): 5: Very high improvement 4: High improvement 3: Moderate improvement 2: Limited improvement 1: No improvement 6.2. Household income by source of livelihood in project area (USD) prior and post project intervention 7. Summarize in an overall scale (1-5). 5: All (Fully integrated) 4: Most 3: Some 2: Most not integrated 1: None
Fund Output Indicator Units
1.1. Number, sector(s) and level(s) of projects or interventions in separate fields of monitoring plan 1.2. Number 2.1.1. Number of staff (male/female) of targeted institutions: a. Obtain baseline information: total number of staff from targeted institutions b. Define target 2.1.2. Number of staff (male/female) of targeted institutions: a. Obtain baseline information: total number of staff from targeted institutions b. Define target: needs to be defined by project proponents 2.2.1. Quantitative: Percentage (includes women – and other vulnerable groups – and men). Qualitative: Adequacy: include direct analysis of major areas; adequacy/effectiveness of systems or analysis of perceptions of populations and institutions. 2.2.2. Number (broken down by gender and, if possible, by vulnerable groups defined in the area of intervention) of people 3.1. Number and type (in separate columns) at local level. 3.2. Number 4.1. Number and type 4. 2. Number and type (entered in separate columns) 5. Number of interventions by type of natural asset and intervention 6.1. Number and type (in separate columns of monitoring plan) 6.2. Income sources per household; description of income source and number of households. 7.1. Number/Sector 7.2. Number; Effectiveness (see previous indicator) through enforcement level.