## Overview
Project Performance Report (PPR)
| Period of Report (Dates) | July 2015 - March 2016
| Project Title: | Ecosystem-based Adaptation to Climate Change in Seychelles
| Project Summary: | The proposed project aims to reduce the vulnerability of the Seychelles to climate change, focusing on water scarcity and flooding. The climate change projections in the Seychelles show that rainfall will become irregular with much of the precipitation falling in sharp bursts, creating heavy flooding in the wet season, while imposing extended period of drought during the dry season. The lack of large water storage capacity and with the topography of the islands constraining such infrastructure, water supplies are heavily dependent on rainfall. Furthermore, the coastal zone is vulnerable to flooding as a consequence of rising sea surface levels, and increased storm surges from cyclonic activity in the Western Indian Ocean. The project will reduce these vulnerabilities by spearheading an ecosystem-based adaptation approach that will be applied to watershed and coastal rehabilitation on the 2 largest Islands to address water shortages and watershed and coastal flooding that have been accentuated by climate change.
|  |  | Countries | Project Type: |  | GEF Focal Area: | GEF 4 Focal Areas | GEF 2 / 3 Operational Programme: | Overall Rating of the project in the evaluation by the project evaluator: | GEF-4 Focal Area Strategic Program:
| Database Number: | 4775 | Afghanistan | FP | Yes | Biodiversity | 1 | 1 | U | BD-SP1-PA Financing
Implementing Entity (IE) [name]: |  | UNDP | Albania | MSP | No | Climate Change Adaptation | 2 | 2 | S | BD-SP2-Marine PA
| Type of IE: | Multilateral | Algeria | EA |  | Climate Change Mitigation | 3 | 3 | MU | BD-SP3-PA Networks
| Country(ies): | Seychelles | Angola |  |  | International Waters | 5 | 5 | Good | BD-SP5-Markets
Relevant Geographic Points (i.e. cities, villages, bodies of water): |  | Mare aux Cochons watershed, Mahe; Mt Plaisir watershed, Mahe; Baie Lazare watershed, Mahe; Caiman River watershed, Mahe; Fond B’Offay/Nouvelle Decouvert watershed, Praslin; North-east Point coastal ecosystem, Mahe; Anse Royale coastal ecosystem, Mahe | Argentina |  |  | Multiple Focal Area |  |  |  | BD-SP7-Invasive Alien Species(IAS)
[8 empty] | CC-SP2- Industrial EE | 8: Waterbody based operational program
| Project Milestones | [6 empty] | CC-SP3-RE,CC-SP4-Biomass | 9: Integrated Land and Water multiple focal area
| Milestone |  | Bahamas | [6 empty] | CC-SP5-Transport
AFB Approval Date: |  | 2014-02-13
IE-AFB Agreement Signature Date: |  | 2014-02-13 | [6 empty] | CC-SP6-LULUCF | 12: Integrated Ecosystem Management
Start of Project/Programme: |  | 2014-06-06 | [6 empty] | Cross cutting capacity building | 14: Persistent Organic Pollutants
Mid-term Review Date (if planned): |  | 2017-07-17
| Terminal Evaluation Date: | 2019
|  | List documents/ reports/ brochures / articles that have been prepared about the project. | Cyprus
|  | Progress reports: a) Inception report, b) Quarterly reports (Q4 2014 to Q2 2016), c) PPR (June 2015) Technical reports: 1) Project brochure (summary of the project and its objectives), 2) A specific brochure for the Baie-Lazare watershed committee and community, 3) Watershed committee guide 'Our water Our Choice'. 4)Proposed methodology for forest rehabilitation has been prepared by one member of the Technical Working group. It is entitled "Evaluation of important elements of the ecosystem service of water-catchment areas in the Seychelles by (in a first phase) (I) estimating the vegetation quality, (II) the water quality, (III) the water flow, (IV) the human impact on the designated water-catchment areas". 5) "Draft Methods for Rehabilitation of Seychelles Forest" 6) Rapid Biodiversity Assessment of North East Point and Anse Royale Marshes 7) Assessment of Coastal Wetlands Environmental Flow at North East Point and Anse Royale Towards Wetlands Rehabilitation 8) Assessment of the Rehabilitation Potential of the Mont Plaisir River Catchment 9) Assessment of the Rehabilitation Potential of the Mont Caiman River Catchment Press articles: a) http://www.nation.sc/article.html?id=246190 - 23rd February 2015: Adapting water usage to address climate change impacts/ Seychelles Nation b) http://www.nation.sc/article.html?id=245748 - 17th June 2015: International World Day to Combat Desertification; Preserving our natural resources from drought/ Seychelles Nation c) http://www.nation.sc/article.html?id=246223 - 30th July 2015: Stakeholders follow training on soil salinity management/ Seychelles Nation & TODAY d) http://www.nation.sc/article.html?id=246190 - 27th July 2015: Our water, our choice’ - EbA project launches logo competition e) http://www.nation.sc/article.html?id=246795 - 17th September: Fermye Val d’Andorre pou netway lemonnn dan en fason f) http://www.nation.sc/article.html?id=248813 - 21st March 2016 : Environment stakeholders get skills in chainsaw use g) Sesel Sa Magazine Issue 9, Jan-Mar 2016: https://simplebooklet.com/seselsa15#page=61 & https://simplebooklet.com/seselsa15#page=62 - Deep Impact: Seychelles adapts to climate change before its too late | Czech Republic
List the Website address (URL) of project. |  | 4 | Democratic People's Republic of Korea
|  | www.pcusey.sc and www.undp.org | Democratic Republic of the Congo
Denmark
| Project contacts: |  | Djibouti
National Project Manager/Coordinator |  |  | Dominica
| Name: | Betty Seraphine (Project Manager) | Dominican Republic
| Email: | b.seraphine@pcusey.sc | Ecuador
| Date: | 2015-07-01 | Egypt
| Government DA |  | El Salvador
| Name: | Wills Agricole | Equatoral Guinea
| Email: | w.agricole@env.gov.sc | Eritrea
| Date: | 2015-08-01 | Estonia
| Implementing Entity |  | Ethiopia
| Name: | Roland Alcindor | Fiji
| Email: | roland.alcindor@undp.org | Finland
| Date: | 2015-06-01 | France
| Executing Agency |  | Gambia
| Name: | Wills Agricole | Georgia
| Email: | w.agricole@env.gov.sc | Germany
| Date: | 2015-06-01 | Ghana
| Executing Agency |  | Greece
| Name: |  | Grenada
| Email: |  | Guatemala
| Date: |  | Guinea
| Executing Agency |  | Guinea Bissau
| Name: |  | Guyana
| Email: |  | Haiti
| Date: |  | Honduras
Hungary
Iceland
India
Indonesia
Iran (Islamic Republic of)
Iraq
Ireland
Israel
Italy
Jamaica
Japan
Jordan
Kazakhstan
Kenya
Kiribati
Kuwait
Kyrgyzstan
Lao People’s Democratic Republic
Latvia
Lebanon
Lesotho
Liberia
Libyan Arab Jamahiriya
Liechtenstein
Lithuania
Luxembourg
Madagascar
Malawi
Malaysia
Maldives
Mali
Malta
Marshall Islands
Mauritania
Mauritius
Mexico
Micronesia, Federated States of
Monaco
Mongolia
Montenegro
Morocco
Mozambique
Myanmar
Namibia
Nauru
Nepal
Netherlands
New Zealand
Nicaragua
Niger
Nigeria
Norway
Oman
Pakistan
Palau
Panama
Papua New Guinea
Paraguay
Peru
Philippines
Poland
Portugal
Qatar
Republic of Korea
Republic of Moldova
Romania
Russian Federation
Rwanda
Saint Kitts and Nevis
Saint Lucia
Saint Vincent and the Grenadines
Samoa
San Marino
Sao Tome and Principe
Saudi Arabia
Senegal
Serbia
Seychelles
Sierra Leone
Singapore
Slovakia
Slovenia
Solomon Islands
Somalia
South Africa
Spain
Sri Lanka
Sudan
Suriname
Swaziland
Sweden
Switzerland
Syrian Arab Republic
Tajikistan
Thailand
The former Yugoslav Republic of Macedonia
Timor-Leste
Togo
Tonga
Trinidad and Tobago
Tunisia
Turkey
Turkmenistan
Tuvalu
Uganda
Ukraine
United Arab Emirates
United Kingdom of Great Britain and Northern Ireland
United Republic of Tanzania
United States of America
Uruguay
Uzbekistan
Vanuatu
Venezuela, Bolivarian Republic of
Viet Nam
Yemen
Zambia
Zimbabwe

## FinancialData
Financial information: March 31st 2016
DISBURSEMENT OF AF GRANT FUNDS
How much of the total AF grant as noted in Project Document plus any project preparation grant has been spent to date?
Estimated cumulative total disbursement as of March 2016 | 799999
Add any comments on AF Grant Funds. (word limit=200) | Expenditure during the current reporting period (July 2015 - March 2016) is $456,689, and cumulative expenditure at the end of March 2016 is $799,999, being 78.6% of the first tranche of funds received from AF. Balance of funds held at the end of March 2018 was $218,000, being sufficient for activities during Q2 2016 but requiring the completion of this PPR and request for the next funding tranche from Q3 2016. The project expenditure rate has accelerated since the last reporting period, despite a change in Project Manager in July 2015. The PIT is fully in place and operating efficiently, supported by a Technical Advisory Group to ensure interventions are well-designed with the best possibe technical and scientific justifications. Most activities are now fully planned and commencing implementation such that the number of activities and associted expenditure continues to rise. Remaining bottlenecks, such as the slower then expected establishment of watershed committees, are being addressed. The next tranche of funds is expected to be used within a one-year period as originally envisaged, being expended by end of March 2017.
INVESTMENT INCOME | 0
Amount of annual investment income generated from the Adaptation Fund’s grant
EXPENDITURE DATA
List ouput and corresponding amount spent for the current reporting period | ITEM / ACTIVITY / ACTION | AMOUNT
Component 1 ECOSYSTEM-BASED ADAPTATION APPROACH TO ENHANCING FRESHWATER SECURITY AND FLOOD CONTROL IN MAHÉ AND PRASLIN UNDER CONDITIONS OF CLIMATE CHANGE
| Output 1.1 Management and rehabilitation of critical watersheds to enhance functional connectivity and the resilience of these areas to climate change and reduce water scarcity and watershed flooding (Mare aux Cochons, Mt Plaisar, Baie Lazare, Caiman, Praslin Fond B’Offay/Nouvelle Decouvert watershed management) | 125543.57
| Output 1.2 Small-scale water storage and detention facilities designed and constructed or rehabilitated in critical waterways for communities to benefit from enhanced ecosystem functioning by forests (Mare aux Cochons, Mt Plaisar, Baie Lazare, Caiman, Praslin Fond B’Offay/Nouvelle Decouvert watershed control structures) | 101977.79
Component 2 ECOSYSTEM-BASED ADAPTATION APPROACHES ALONG THE SHORELINES OF THE GRANITIC ISLANDS REDUCE THE RISKS OF CLIMATE CHANGE INDUCED COASTAL FLOODING
| Output 2.1 Ecosystem-based measures for flood protection on an urban shoreline | 17181.45
| Output 2.2 Ecosystem-based measures for flood protection and mitigating salt water intrusion in an agricultural and tourism development area | 71734.29
Component 3 ECOSYSTEM BASED ADAPTATION MAINSTREAMED INTO DEVELOPMENT PLANNING AND FINANCING
| Output 3.1 Policy and legal frameworks for watershed and coastal climate change adaptation | 702.02
| Output 3.2 Capacity Development for Ecosystem Based Adaptation Methods | 6183.73
| Output 3.3 Lessons learned and Knowledge Dissemination | 59047.62
| Component 4 PROJECT MANAGEMENT | 74298.89
| TOTAL | 456669.36
PLANNED EXPENDITURE SCHEDULE
List outputs planned and corresponding projected cost for the upcoming reporting period | ITEM / ACTIVITY / ACTION | PROJECTED COST | Est. Completion Date
| Output 1.1: Mare aux Cochons: Invasive species management programme (long-term action), wetland rehabilitation (long-term action) | 70000 | 2017-03-01
| Output 1.1: Mont Plaisir: invasive species management programme (long-term action) | 10000 | 2017-03-01
| Output 1.1: Baie Lazare: invasive species management programme (long-term action), assessing impacts of conflicts on water resources, stakeholder consultations, study of impact and design for wetland rehabilitation and initiation of rehabilitation programme (4 wetlands) | 50000 | 2017-03-01
| Output 1.1: Caiman watershed: invasive species management programme (long-term action) | 50000 | 2017-03-01
| Output 1.1: Praslin: completion of work on the tree nursery, vegetation management and rehabilitation (red soils area), mitigation of impacts of landslides on water resources | 80000 | 2017-03-01
| Output 1.1: Training on site rehabilitation, equipment | 78000 | 2017-03-01
| Output 1.2: Mare aux Cochons: renovation of downstream barrage, assessment of impacts of water abstraction by utility company | 105000 | 2017-03-01
| Output 1.2: Mont Plaisir: barrage renovation, assessment of potential for targeted water harvesting | 15000 | 2016-12-16
| Output 1.2: Baie Lazare: construction of additional barrages, study to determine water source protection zone, study on pollution from agriculture | 114500 | 2017-03-01
| Output 1.2: Caiman watershed: renovation of downstream barrage, assessment of potential for further abstraction | 11500 | 2016-12-16
| Output 1.2: Praslin: installation of new check dams as a response to fire risk | 26000 | 2016-12-16
| Output 1.2: Engagement of community based watershed managementmanagement committees (long-term action), strategic water resources adaptation assessments, community-based watershed management plans, monitoring and evaluation | 110000 | 2017-03-01
| Output 1.2: Education and awareness materials | 10000 | 2016-12-16
| Output 2.1: NE Point: integrated shoreline management plan | 30000 | 2016-12-16
| Output 2.1: NE Point: hydrological study, wetland reprofiling | 48500 | 2016-12-16
| Output 2.1: NE Point: reef rehabilitation study and assessment of options for artificial reef structure | 100000 | 2017-03-01
| Output 2.1: Technical support, workshops and monitoring |  | 2017-03-17
| Output 2.2: Anse Royale: development of integrated shoreline management plan | 30000 | 2016-12-16
| Output 2.2: Anse Royale: study of wetland function, implementation of reprofiling | 46500 | 2016-12-16
| Output 2.2: Anse Royale: shoreline rehabilitation, installation of bollards and start of replanting (long-term action) | 25000 | 2017-03-17
| Output 2.2: Anse Royale: monitoring equipment for salaination control measures, development of efficient irrigation system for farmers (explore co-financing and alternative water supplies) | 7500 | 2016-12-16
| Output 2.2: Equiment for shoreline rehabilitation | 32000 | 2016-09-16
| Output 2.2: Awareness raising activities and materials | 9000 | 2017-03-17
| Output 2.2: Technical and office support | 29600 | 2017-03-17
| Output 3.1: Watershed policy: analysis of institutional structures, needs analysis, review of planning practces related to watersheds, identificatin of financing mechanisms | 13000 | 2016-12-16
| Output 3.1: Technical support to policy development | 16600 | 2017-03-17
| Output 3.2: Training programmes: modules development (to be delivered mostly by UNISEY) | 9800 | 2017-03-17
| Output 3.2: Institutional support to watershed committees, lessons learned, support for Rivers Committee | 30000 | 2017-03-17
| Output 3.3: Communications strategy: strategy development, materials, knowledge sharing | 30000 | 2017-03-17
| Output 3.3: Technical and office support | 36000 | 2017-03-17
| Output 4.1 Project management | 76500 | 2017-03-17 | NOTE:
| TOTAL | 1300000 |  | Balance at end March 2016 = $218,000
Advance request is $1,081,999
ACTUAL CO-FINANCING (If the MTR or TE have not been undertaken this reporting period, DO NOT report on actual co-financing.) |  |  |  | Expenditure next reporting period is 218,000 + 1,081,999 = $1,299,999
How much of the total co-financing as committed in the Project Document has actually been realized?
Estimated cumulative actual co-financing as verified during Mid-term Review (MTR) or Terminal Evaluation (TE).
Add any comments on actual co-financing in particular any issues related to the realization of in-kind, grant, credits, loans, equity, non-grant instruments and other types of co-financing. (word limit=200)

## Risk Assesment
RISK ASSESMENT
IDENTIFIED RISKS
List all Risks identified in project preparation phase and what steps are being taken to mitigate them
Identified Risk | Current Status | Steps Taken to Mitigate Risk
Policy makers prioritize economic benefits over sustainable and resilient ecosystems | Medium risk. | In a landmark decision handed down by the Chief Justice on January 12th 2016, a Government Land Use Plan was declared 'invalid' as the constraints imposed in relation to preservation of the fragile ecosystem in that area were deemed to infringe the rights of the owner to develop the land. This sets an unfortunate precedent and essentially supports developers to ignore ecological contraints or ecosystem resilience in proceeding with development projects. If this precedent is applied widely in fragile areas, large areas of which are under private ownership (even within gazetted Protected Areas) then this risk will become critical. Pursuant to the above is the further allocation of land in upper watersheds for very large residential developments, often for wealthy offshore clients. One such development under EIA process in the upper Mt Plaisir catchment (a project target area) would impact considerably on downstream forest and water supplies, although hopefully this point will be picked up by the EIA and duly acted upon. The project will monitor this. Another issue is that the Public Utilities Corporation (PUC) needs greater commitment to participatory catchment management . PUC is primarily concerned with supply and demand, lacks awareness on watershed management, and so far has not been very willing to engage with the project to understand the EbA approach. The issue of land ownership and community support are also important factors in this context. The project is addressing this through continued dialogue and development of a closer working relationshp with PUC, and bringing PUC into dialogue with communities through the Watershed Committees being established.
Extreme natural disasters affect confidence of local community to adaptation measures | Medium risk. | The project has initiated participatory processes for integrated watershed management at the community level, operating primarily through watershed committees. Understanding of the principles behind adaptation mesures - to adapt to climate risks - are being cmmunicated through intensive awareness raising activities. 2015 and early 2016 has seen some extreme climate events in Seychelles, incuding El Nino impacts on ocean currents and warming leading to a severe and widespread coral bleaching event in early 2016, and Cyclone Fantala in March 2016 (which forunately did not impact on the poulated inner islands) such that the real otential for climate shocks is in the forefront of public conciousness. The need to be serious about adaptation to CC is increasingly high on the political agenda and there is strong support for project actions.
Environmental impact of structures in watercourses and reefs | Medium risk. | Environmental impact assessment is a necessary part of project main interventions, including the development of new barrages and reef structures, all of which are preceeded by the appropriate biodiversity assessments beyond the level legally required for the EIAs. Regulations for EIA are being tightened up under the new Environmental Protection Act, expected to be approved in mid 2016, and this will hopefully limit the impacts of non-project developments in or close to target sites.
Methods of ecosystem rehabilitation need better testing for hydrological impacts | Low risk. | The project has taken specific advice on hydrological impacts, through its Technical Advisory Group. A working relationship with University of Seychelles has been established for the collection of baselne data to assess hydrological impacts in the Baie Lazae site. Similar assessments are being made in the Mare aux Cochons site using data collected by PUC or new data collected by consultants working on rehabilitation or design of new barrages, and these information will guide the design of interventions.
Adaptation measures increase inequity | Low risk. | The project promotes social inclusion. The community engagement specialist is in the process of establishing community associations in all target areas to ensure that community interests are represented, and indeed that the community engages in and advises on the design of adaptation interventions. So far the community engagement specialist has successfully set up two watershed committees on both Islands of Mahe and Praslin, so that the interests of the communities at the project sites are represented. Three more will be set up during the second half of 2016
The cost of the proposed measures may be higher than expected. | Low/medium risk. | Estimating the cost of adaptation is a complex matter. The scale of required interventions is in some cases quite major. For example, rebuilding the reef structure at NE Point will far exceed the financial resources of the project such that the project can only test an appropriate methodology, and co-financing needs to be sought for up-scaling. An agreement has been reached with the EU to provide US$1.3 million for additional coastal adaptation measures, but this financing will focus on replicating approaches on La Digue island. Additional adaptation finance is being sought through south-south cooperation projects.
Critical Risks Affecting Progress (Not identified at project design)
Identify Risks with a 50% or > likelihood of affecting progress of project
Identified Risk | Current Status | Steps Taken to Mitigate Risk
Private lands identified for potential forest rehabilitation within the catchment areas may not be available if land owners refuse to approve the rehabilitation works or if it is unclear who owns the land (such as when the land is under probate) | Retired | This risk was introduced in the 2015 PPR. Since that time, the project has identified additional sites at Baie Lazare Baie Lazare suitable for project rehabilitation actions, and this may be upscaled to sites currently under disputed ownership in the future when these ownership issues have been sresolved.
The legislative framework does not adequately support adaptation interventions | High risk | Introduced in the current PPR. Elaborating on the risk above 'Policy makers prioritize economic benefits over sustainable and resilient ecosystems' the current legislation does not provide the means to ensure that this does not happen. While there has been intent to develop and approve legislation that forms the enabling environment for certain interventions (Environmental Protection Act, Physical Planning Act, Land Use Plans for the target districts) the progress in agreement of these has been very slow, and it is evident that the Judiciary sees no legal basis in not approving development in sensitive area, and indeeed has heavily criticised the relevant Ministry for trying to impose rules that prioritise ecological concerns over the interests of developers. The absence of the clear legislative framework could potentially hamper the ability of the project to design integrated solutions for managemment of sensitive sites The Acts mentioned above are expected to be approved within 2016. Unfortunately, however, it appears that the new Acts have not yet been harmonized, especially concerning wetlands which are still not legislated under the EPA (they are legislated under the PPA) and in their current form may confuse the situation even further rather than resolving conflicts and discrepancies in the previous acts. Hopefully the Ministry working groups working to finalize the acts will undertake the harmonization before taking the acts to Cabinet.
Risk Measures: Were there any risk mitigation measures employed during the current reporting period? If so, were risks reduced? If not, why were these risks not reduced?
Add any comments relevant to risk mitigation (word limit = 500)
The finalization of the legislation is beyond project control, although the project (and other projects within the PCU) continue to provide inputs when requested. In target sites, the project will instigate rigorous EIAs and or support and work with other imapct assessment consultants to minimise the risks. However, if the EIA is not appropriately applied (or overruled) then this risk will be raised to critical. Government commitment to observing and applying results and conditions of EIAs will be necessary for the successful (sustainable) rehabilitation and management of the watershed areas and coastal rehabilitation.

## Rating
RATING ON IMPLEMENTATION PROGRESS
For rating definitions please see bottom of page.
| Progress on Key Milestones |  | Expected Progress |  | Progress to Date | Rating
Project Manager/Coordinator: | Inception phase Inception commenced in September 2014 with the recruitment of the Project Manager. The Inception Workshop was held on 30th October 2014 in Victoria, Mahe. There were 31 participants including the UNDP TA for AF projects. The Inception Report was produced in November 2014. |  | Complete |  | Complete | S
Component 1: Ecosystem-based adaptation approach to enhancing freshwater security and flood control in Mahé and Praslin under conditions of climate change
| Output 1.1 Management and rehabilitation of critical watersheds to enhance functional connectivity and the resilience of these areas to climate change and reduce water scarcity and watershed flooding (Mare aux Cochons, Mt Plaisar, Baie Lazare, Caiman, Praslin Fond B’Offay/Nouvelle Decouvert watershed management) |  | Conduct assessments of the five watershed areas. Start ivegetation and invasive species management programmes in the watershed areas. The completion of the Praslin nursery and the start of vegetation management and replanting programme on Praslin. |  | Mare aux Cochons watershed: A rapid survey of the Mare aux Cochons watershed area is underway, focusing on surveying the vegetation around the existing wetland (Zone A) and areas with potential for wetland creation (Zone B). In zone A, detailed surveys are being done using transects established perpendicular to the Mare aux Cochons valley. Each transect consists of nested plots corresponding to the different size classes: (1) a 20 m wide strip for trees with DBH >30 cm; (2) a 5 m wide strip for trees with DBH between 10 and 30 cm; (3) a 2 m wide strip for the herbaceous and shrub flora of the understorey plus for the regeneration of canopy trees. In zone B, the widely used 'Key biodiversity Area' method' is observed which allows identification of all areas of special conservation value, particularly wetland areas with a potential for improvement of water storage within the catchment area. Mont Plaisir watershed and Caiman Watershed: Assessments of the rehabilitation potential of the Mont Plaisir River catchment and Caiman River catchment has been completed. Consultants surveyed and mapped the rivers and all tributaries, identifying sources and other significant features such as wetlands and barrages. The locations and numbers of invasive tree species were mapped using GPS and numbered (including size classing of Albizia). Suitable areas for rehabilitation have been identified. There are currently c.10 small concrete and/or stone barrages creating small pools for private water collection and two locations in Mont Plaisir where PUC abstracts water. The Mont Plaisir residents have access to PUC water, but quite a lot of households also source their own water from the river and tributaries (thus avoiding PUC charges). The number of pipes sourcing water from the river could affect river flow at times of low flow during droughts. For Caiman, there are currently c.7 small concrete and/or stone barrages creating small pools for water sources; one for PUC and the other c.6 for private individuals. The Caiman residents do not have access to PUC water and they source and pipe their own. PUC plans to provide Caiman residents with treated water in the near future. . Baie Lazare Watershed: A new plot of Government land has been identified and allocated to the project for forest rehabilitation. This eliminates the risk arising from a land ownership issue identified in 2015. Minor works to prepare sites for rehabilitation has started. 6 locations have been identified to set up monitoring stations. Sign boards are being installed and Univeristy of Seychelles students are assisting with data collection. 100 ha of forest will be rehabilitated through the management of invasive trees and the implementation of soft engineering solutions and wetland enhancement in rivers to create more even flows. The mapping of the boundaries of the management area with GPS has been completed and 10 permanent monitoring transects have been identified for conducting research.Two students from the University of Zurich are assessing the ecosystem services of water catchment areas in the Seychelles, focusing on Baie Lazare and Mont Plaisir catchments. Their theses focus on the quality of the vegetation and human induced impacts on the water catchment area such as housing, water pollution, waste dumping, and land use. Fond B'Offay and Nouvelle Découverte Watershed: The local NGO TRASS has commenced forest rehabilitation actions. A team of workers has set up the nursery and started plant propagation. The first phase of the project targets 20 ha for rehabilitation, including 10 ha in the first year. 20 ha of exposed red soil was surveyed and delineated as suitable for rehabilitation to native forest. A draft rehabilitation plan is being circulated and TRASS has started experimental trials and with an aim to applying a semi-experimental approach to the rehabilitation to test methods to enhance establishment and growth rates. | S
| Output 1.2 Small-scale water storage and detention facilities designed and constructed or rehabilitated in critical waterways for communities to benefit from enhanced ecosystem functioning by forests (Mare aux Cochons, Mt Plaisar, Baie Lazare, Caiman, Praslin Fond B’Offay/Nouvelle Decouvert watershed control structures) |  | Conduct assessments of the 5 watersheds to identify existing barrages in need of repair or identify potential sites for constructing new water storage facilities. Conduct an assessment of water conflicts between water users in the Baie Lazare watershed area to assist in the management of the water resources in the future. Conduct preparations for feasibility studies to erect check dams in the project watersheds. |  | This work is contingent on discussion and agreement with PUC who have the mandate to manage water flows and install barrages. Discussions have been held with PUC concerning project interventions, particularly barrage renovations at the target sites, but PUC has been very slow to participate in field visits and to provide ideas and recommendations. This is a particular issue with the La Drisse intervention at Mare aux Cochons where specific inputs from PUC are needed, but are currently not forthcoming. Mare aux Cochons: After consulting PUC, the EBA project is supporting (co-financing) the renovation of the barrage at Port Launay. To further improve water storage capacity, the project is assessing the feasibility of installing a small check dam on the outflow from the La Drisse depession, with the dual role of a) creating an ecologically significant wetland in an area that is already seasonally flooded and b) improving the water storage capacity of the river flowing down to Port Launay and the mangroves adjacent to Constance Ephelia. Mont Plaisir / Caiman: The water resources assesment has been completed with mapping of areas to be rehabilitated and also indicating current pollution sources. Land ownership issues have slowed down the process for identifying work in the upper catchment at Caiman as there is currently an EIA underway for a large residential development which could result in potential conflict of use and/or pollution of the upper water sources. Baie Lazare: Water resources mapping has been completed in order to identify potential for additional water strage interventions. Six sites have been selected for potential development water storage areas and assicted wetlands, of which three have been prioritised. Detail topographic surveys have been undertaken for these three. The first site is proposed to be enhanced with a gabion rock dam to increase significantly in river storage; a biodiversity assesment has been conducted to determine potential ecological impacts. The gabion rock dam is currently under technical design and a tender document is being prepared, which will include a full EIA as required by law. In the same area, six sites have been identified for the estab;ishment of river stations for river flow monitoring, with periodic water quality testing being conducted by students from the University of Seychelles. Data is also being collected from a rainfall intensity recorder at the community center at Baie Lazare. A standard water storage tank has been designed and it is planned to build several of these in the watershed to provide raw water to farmers, who have been identified as the main water users from the target area. Praslin: A water resources assesment has been 80% completed with 26 potential sites for check dams identified and seven amarked as significant for potential interventions under the project. Discussion are on-going with SIF and SNPA to obtain approval for the intenventions, together with a fire fighting strategic plan since a main use of the water is for fighting wild fires. | S
Component 2: Ecosystem-based adaptation approaches along the shorelines of the Granitic Islands reduce the risks of climate change induced coastal flooding
| Output 2.1 Ecosystem-based measures for flood protection on an urban shoreline (North-east Point) |  | Conduct coastal studies on the North East Point shoreline to facilitate the drafting of an integrated shoreline management plan and to inform wetland and reef rehabilitation and beach berm enhancement. |  | Shoreline management planning is proceeding through stakeholder identification and consultation to gather historical data in an attempt to understand the shoreline dynamics of North East Point. The project is referencing past work undertaken in the area, which includes the JICA project of 2014 which funded sand nourishment on the eroded shoreline of North-East Point. Wetland rehabilitation: The biodiversity assessment of the wetland has been completed. A key finding is that there is a population of (endangered) terrapins inhabiting the marsh at the North East Point project site. Mapping of the wetland has been done. An increase of human activities around the marshes, such as earth cutting works on the hillside, construction works and the rapid invasion of the marshes by alien aquatic plant species such as the water lettuce Pistia stratiotes and water hyacinth Eichhornia crassipes have been identified. Innovative techniques should be applied to prevent salt water intrusion into the fresh water marsh, seen in the example of the V-Sump storm water discharge system. An assessment of coastal wetlands environmental flow at North East Point towards wetlands rehabilitation was conducted. Preliminary results divid the area into zones: Zone A is around 40 0m in length and does not have a continuous reef crest, Zone B is about 1800m in length and has a continuous reef crest. The absence of a reef crest in Zone A would seem to leave this area of coastline more exposed to wave action in comparison to Zone B where there is a well-developed reef crest with a steep depth gradient on its outer edge that can absorb a large amount of the wave energy followed by a wide intertidal zone with a shallow and constant depth. The large movements of sand observed accumulating and eroding in Zone A indicates that the lack of the reef crest in this section makes it a much more dynamic environment than in Zone B in terms of currents, wave action and sand transport. Hydrographic studies for reef and beach berm rehabilitation: An international company (eCoast) is conducting the coastal processes study for North East Point in collaboration with a local company, EcoSol. The key output is to identify and quantify the existing coastal process to determine how they affect sediment transport within the study site, and how these processes relate to climate change resilience strategies and to construct a modelling tool for the project. The consultants have conducted a site survey, wave gauges and current meters (Aquadopp wave/current profiler and current meter) have been deployed. Due to malfunction of the EcoSol's equipment, eCoast initially had only one set of data to process. The single point wave/current meter was redeployed as a result. eCoast has developed and set up numerical grids (using a combination of EcoSol survey data, nautical charts and online databases - SRTM and GEBCO in particular) and are running a preliminary wave propagation model (SWAN) for the deployment period. | S
| Output 2.2 Ecosystem-based measures for flood protection and mitigating salt water intrusion in an agricultural and tourism development area (Anse Royale) |  | Raise awareness about how relevant stakeholders can undertake ecosystem-based measures for flood protection and mitigating salt water intrusion in the agricultural coastal plains of Anse Royale. Conduct studies on the Anse Royale shoreline to facilitate the drafting of an integrated shoreline management plan to inform wetland and reef rehabilitation and beach berm enhancement. |  | A scientific assessment of the Anse Royale Marshes was conducted for informed decision making for wetland management, to guide the development of a proposal for project interventions at the project site. A new field inventory was undertaken and a map of the wetland habitat types was done for the site. 42 animal species were recorded at the Anse Royale wetlands, including several records of exotic invasive species as well as other flagship species. Wetland ecosystem diversity is high at Anse Royale, due to a larger water catchment area than North East Point, which results in the development of a small estuary landscape with tidal mangroves and tidal freshwaters. At Anse Royale, the most extensive area corresponds to the Non-tidal coastal plateau freshwater swamp, which is the area where most terrapins were caught. An assessment of the Coastal Wetlands Environmental Flow has been largely completed for Anse Royale, aimed towards wetlands rehabilitation. The findings indicate that in most of the valleys, the slopes are steep, streams are perennial and recharging the coastal aquifer in the plateau area. This aquifer is recharged directly from coastal wetlands surface at Sweet Escott and from behind the University of Seychelles premises which are fed directly by rivers. The shallow aquifer contains a thin freshwater level (2 to 8 meters), depending closely on rain cycles. over a brackish level that marks the beginning of the sea level. The shallow aquifer makes it vulnerable to salt water intrusion. The effect of this intrusion is especially apparent when water is pumped for irrigation during the seasons of low flow from the in-feeding Riviere Jumeau, Riviere Royale and the Sweet Escott Tributaries. The dynamic movement of water in these areas accelerates the rhythm of soil degradation in the coastal plain, which is compensated by a high renewal rate of water in the aquifer by watershed through the aforementioned rivers after heavy rains. The project team is working in collaboration with the Seychelles Agricultural Agency project and the IAEA to assist the farmers on the coastal plains of Anse Royale to adapt to salt water intrusion. A workshop was conducted by the SAA and IAEA with ICBA in January 2016 which established a joint collaboration between projects. The next step includes an education and awareness campaign to further educate the farmers and relevant stakeholders. The shoreline management planning process will proceed from stakeholder consultation. The process will pick up the previous Integrated Coastal Management Plan undertaken for Anse Royale district by a local NGO ,MCSS, through the former UNDP-GEF Mainstreaming Biodiversity project in Seychelles. Setting up a watershed committee and collaboration with the SAA and University of Seychelles are underway to help the identification of project interventions. A biodiversity assessment of the inland marsh has started. Discussions have been held with farmers and other donors on combining interventions to control salinity. This area is also being targeted by another adaptation project through South-South Corporation, an International Ecosystem Management Partnerships between GEF, Government of Seychelles and UNEP, piloted in Seychelles and 2 other countries. | S
Component 3: Ecosystem based adaptation mainstreamed into development planning and financing
| Output 3.1: Policy and legal frameworks for watershed and coastal climate change adaptation |  | Conduct an analysis of institutional structures to identify policy gaps. |  | The incoming EU-funded project has an institutional capacity building component supported through international technical assistance which will lead on the institutional analysis. At the policy and strategy level, the drafting of a Watershed Management Policy (likely to be led by this project) is pending the finalization of a Water Policy by the PUC and MEECC. MEECC has recently hired a Water Analyst with a main role in clarifying the policy environment for water sypply and demand. Consultants working for MWH Global (funded by the EIB) are providing advice on water demand management and drought risk mitigation to the PUC, aimed at identifying long term objectives for the water sector of Seychelles and an assured delivery of a sustainable water supply. Our project is contributiong to the circulated paper 'Towards a Water Policy' and the update of the 2011 Water Masterplan as part of the overall stakeholder consultation. This output is shared with at one other EBA project under implementation (funded by UNEP) and is also highlighted in an incoming EBA project (funded by EU). Discussions were held with the UNEP EBA project concerning how to coordinate activities in regard to this output. | S
| Output 3.2 Capacity Development for Ecosystem Based Adaptation Methods |  | Capacity development for watershed committees and other project stakeholders. |  | Two watershed committees out of five have now been set up. The already established Baie Lazare committee is actively involved in removal of invasive plant species in the community watershed and have developed a tree nursey to facilitate the provision of stock for forest rehabilitation in the area supplying water to their community. The members of the new Praslin Watershed Committee are being trained to become the community stewards of the water resources in the Nouvelle Decouverte and Fond Boffay watersheds. The Praslin community has also identified a site for future management. Plant identification training and the removal of alien invasive plant species have been conducted. A comprehensive training programme on forest management and the safe use of chainsaws has been completed, led by a LANTRA accredited international consultant; four Seychellois participant were trained as trainers and will be certified to support the rehabilitation works of the project. | S
| Output 3.3 Lessons learned and Knowledge Dissemination |  | Development of a communications strategy |  | A strategy has not yet been developed. The project has invested in a variety of education and awareness materials to raise awareness about the ecosystem based adaptation to climate change method. The communication strategy will be drafted once the programme analysis and audience analysis has been completed by the project team. A community survey was undertaken on 28th March and 4th April 2015 at Anse Royale and North East Point with the assistance of the University of Seychelles. Promotion of watershed management has been done through the use of the national media for publishing articles. Partnerships have been developed with the key institutional partners, including Public Utilities Corporation (PUC) and Seychelles National Parks Authrotity. 2000 project brochures were designed and printed. They have been disseminated to project stakeholders. 750 posters with messages to preserve our wetland and coastal ecosystems were designed by local project stakeholders. 200 T-shirts were designed and disseminated to children with a printed message to preserve our forest and wetland ecosystems on the back. 280 T-shirts and 1000 Caps were deisgned for adult project stakeholders and they were disseminated to the Praslin Watershed Committee, the Baie Lazare Watershed Committee including the general public. These were also used during national exhibitions to raise awareness about the EbA approach. 50 calendars and 50 diaries containing the project logos were manaufactured and distributed to stakeholders. Sign boards have been made for the different river monitoring stations at Baie Lazare. An exhibition was set up to commemorate World Water Day. The project produced 200 wrist band pen drives, 200 cotton bags, 300 plastic ball pens, 150 biodegradable water bottles, 100 umbrellas and shower timers with a print on message to use water sustainably. | S
[5 empty] | Overall Rating | S
Please Provide the Name and Contact information of person(s) reponsible for completeling the Rating section
| Name: | Betty Seraphine (Project Manager), Andrew Grieser Johns (Programme Coordinator)
| Email: | b.seraphine@pcusey.sc; a.grieserjohns@pcusey.sc
Please justify your rating. Outline the positive and negative progress made by the project since it started. Provide specific recommendations for next steps. . (word limit=500)
The Satisfactory rating given for this reporting period reflects substantial progress since the last reporting period. Two watershed Committeees have now been set up by the project, comprising the Baie Lazare Watershed Committee and the Praslin Watershed Committee. The communities have been actively involved in the project activities to date. Capacity building for community participation has started with a training on plant identification. The members of the Baie lazare Watershed Committee (the first established and most active thus far) have participated in a Clean-up the World campaign to remove invasive plant species and to plant native palms along the river following the training, and have set up a plant nursery. There is slow progress in establishing the other local management committees for watersheds and wetland areas, due to unwillingness of people to come forward and devote time to the community issues involved, but this is being addressed through the awareness activities and targeted actions by the project Community Engagement Specialist. Essential steps for forest rehabilitation work are being put into place. Four local persons underwent and intensive 2 week training in the safe use of chainsaws by a LANTRA accredited trainer from the UK. An interim methodology has been drafted which aims to reduce the non native trees in treatment areas without causing damage or disruption to the forest structure, and allowing the growth of existing native saplings without causing rapid growth of non-native species, which requires the safe use of chainsaws - and well as the deployment of other methods such as stem injection and ring-barking. Assessments of the rehabilitation potential of the Mont Plaisir Watershed river catchment and the Caiman Watershed river catchment were done, and surveys are underway at Mare aux Cochons. The project Technical Advisory Group has been active in discussing appropriate interventions and methodologies for rehabilitation in sensitive forest environments, and local and overseas Universities are contributing studnets and senor researchers to guide and help in collection and analysis of data required to record project progress against baselines (e.g. 6 hydrographic monitoring stations have been set up in the Baie Lazare watershed with data collection being conducted by University of Seychelles students). There remain differences of opinion in how to intervene in sensitive areas, and these are being filtered by the project Scientific and Technical Advisor, with an aim to ensure that interventions are scientifically based and follow in general the precautionary principle. Assessments are almost complete to guide project interventions in the North-east Point and Anse Royale coastal areas (coastal wetlands and offshore reef areas). Rapid biodiversity assessments of the inland marshes have been conducted, and assessments of coastal wetlands environmental flows at both North East Point and Anse Royale project sites. There have been some delays due to limited local capacity and only one local company being suitably qualified to conduct the assessment work - resulting in over-loading and delays in submitting the final reports. This is being addtressed, however, by partnering the company with international technical experts, which also assures quality of the resulting products. A coastal processes study is being conducted under such an international/local partnership at North East Point to identify and quantify the existing coastal process and how they affect sediment transport and thus relate to climate change resilience strategies. Partnerships are being created actively, such as a collaboration with the IAEA, ICBA and Seychelles Agricultural Agency to assist the farmers of Anse Royale to adapt to salt water intrusion. There has been slow progress in setting up strategic and legislative instruments to guide watershed management, but MEECC has recently employed a water analyst to complete the Water Policy, which will be a starting point for further development of legislation and wtershed management plans under that legislation. The Rivers Committee appears defunct pending creation of that policy environment. The project has meanwhile actively pursued an education and awareness raising agenda with many materials produced and distributed to raise awareness about the project's ecosystem-based approach to climate change.
| Progress on Key Milestones |  | Expected Progress |  | Progress to Date | Rating
Implementing Agency | Component 1: Ecosystem-based adaptation approach to enhancing freshwater security and flood control in Mahé and Praslin under conditions of climate change
| Output 1.1 Management and rehabilitation of critical watersheds to enhance functional connectivity and the resilience of these areas to climate change and reduce water scarcity and watershed flooding (Mare aux Cochons, Mt Plaisar, Baie Lazare, Caiman, Praslin Fond B’Offay/Nouvelle Decouvert watershed management) |  | It was expected by the end of June 2016, that Mare aux Cochons, Mont Plaisir, Baie Lazare, Caiman watershed: planning and start of invasive species management programmes. On Praslin: completion of nursery, start of vegetation management and replanting programme was expected to be ongoing. Specific Inventory works conducted by end of reporting period |  | The Project Implementation Team (PIT) has undertaken initial assessment of watershed areas in 5 regions in order to obtain baseline data prior to undertaking any planned interventions. Terms of reference for development for specific inventories have been prepared for specific areas while land issues have been clarified in Baie Lazare prior to undertaking any planned interventions. Some of the specific progress to date can be summarized below for the various intervention sites. Mare aux Cochons watershed: Ongoing surveys at this specific site are underway and it is focusing on assessing the existing vegetation and potential areas for creation of additional wetland using the KBA method. Mont Plaisir watershed and Caiman Watershed: Significant progress has been achieved with regards to completing the assessments for suitable rehabilitation sites and potential and invasive species control of the Mont Plaisir River catchment and Caiman River catchment areas. Close linkages and collaboration with the Public Utilities Corporation are ongoing as well as the communities who are tapping untreated water from the various sources. Baie Lazare Watershed: Work has started to rehabilitate an alternative site which has been identified as part of Government land and it resolved one of the land ownership issues which surfaced in 2015. Monitoring stations will be set up at 6 identified locations and a total of 100ha is expected to be rehabilitated. GIS mapping has been completed and 2 interns from university of Zurich are undertaking data collection and assessment of ecosystem services from human induced impacts on the water catchment areas. Fond B'Offay and Nouvelle Découverte Watershed: Forest rehabilitation is ongoing at the site with the engagement of the local NGO TRASS, with the aim of rehabilitating 20ha of land with native forest. Target of 10 ha in the first year is within reach. | S
| Output 1.2 Small-scale water storage and detention facilities designed and constructed or rehabilitated in critical waterways for communities to benefit from enhanced ecosystem functioning by forests (Mare aux Cochons, Mt Plaisar, Baie Lazare, Caiman, Praslin Fond B’Offay/Nouvelle Decouvert watershed control structures) |  | Conduct assessments of the 5 watersheds to identify existing barrages in need of repair or identify potential sites for constructing new water storage facilities. Conduct an assessment of water conflicts between water users in the Baie Lazare watershed area to assist in the management of the water resources in the future. Conduct preparations for feasibility studies to erect check dams in the project watersheds. Mare aux cochons, Mont Plaisir, Caiman watershed: assessment of needs for renovation of existing barrages completed Baie Lazare: assessment of water conflict issues, planning for additional barrages completed Praslin: assessment of need for new check dam completed |  | Discussions are ongoing with PUC regarding the various project interventions as any constructions along rivers and water catchments must be approved by the PUC. The PIT will maintain the ongoing discussions in particular for some specific sites where PUC is intending to build their own barrages and small reservoir. A coordinated effort and approach is required to ensure that the EBA is followed within project identified sites. In particular in the Mare au Cochons area where the PUC has announced construction of an additional reservoir. Progress to date includes the following: Mare au Cochons: feasibility studies are progressing to assess the possibility of constructing small barrages to improve water storage through co financing from EBA and PUC. Mont Plaisir / Caiman: Completion of water resource assessment and mapping of areas identified for rehabilitation as well as identification of polluting sources. Progress has been somewhat slow due to emerging land use issues which needs to be resolved in the future as it could potentially affect the project in the future from land based pollution if a proposed residential development goes ahead in the upper catchment area. Baie Lazare: progress to date include completion of water resources mapping and topographies surveys and site identifications for water monitoring stations as well as ongoing technical designs for small civil works to be undertaken. Data collection is ongoing which is strengthening the existing and ongoing collaboration with the University of Seychelles. Praslin: Completion of water resource assessment (80%) and identification of 26 potential sites for construction of small water dams. The Project team is in continued discussions with the Seychelles Island Foundation and the Seychelles National Parks Authority in order to obtain approval for interventions which falls within protected areas managed by these 2 institutions.
Component 2: Ecosystem-based adaptation approaches along the shorelines of the Granitic Islands reduce the risks of climate change induced coastal flooding
| Output 2.1 Ecosystem-based measures for flood protection on an urban shoreline (North-east Point) |  | Completion of coastal studies on North East Point Shoreline and drafted Integrated Shoreline Management Plan |  | To date progress is ongoing on the Shoreline management planning at North East Point site with several consultative meetings with the stakeholder to gather historical data in conjunction with a monitoring data being collected through scientific methods (hydrographic studies) by e-Coast and EcoSol to determine how sediment movements. Synergies are being built with past studies funded from another JICA project in the recent past which prescribed sand nourishment for the eroded shoreline. Wetland rehabilitation: The biodiversity assessment of the wetland and the coastal wetlands environmental flow has been completed and findings disseminated. Recommendations for protecting the marsh as well as reducing salt water intrusion will be implemented. | S
| Output 2.2 Ecosystem-based measures for flood protection and mitigating salt water intrusion in an agricultural and tourism development area (Anse Royale) |  | Raise awareness about how relevant stakeholders can undertake ecosystem-based measures for flood protection and mitigating salt water intrusion in the agricultural coastal plains of Anse Royale. Conduct studies on the Anse Royale shoreline to facilitate the drafting of an integrated shoreline management plan to inform wetland and reef rehabilitation and beach berm enhancement |  | Progress to date includes scientific assessment of the Anse Royale Marshes and completion of an inventory and wetland habitat maps for the site with corresponding animals species inventoried. Furthermore, progress has resulted in the completion of An assessment of the Coastal Wetlands Environmental Flow for the Anse Royale area to determine coastal aquifer recharge and salt water intrusion. Works are still ongoing by the project team in collaboration with the Seychelles Agricultural Agency and the IAEA to identify salt water intrusion ad recommend solutions for the farming community in the Anse Royale coastal plains. Education and awareness campaigns will be initiated in the coming months. For the shoreline management planning process , the project is building on previous work carried out under a GEF-funded project and will review the draft Integrated Coastal Management Plan prepared by the local NGO (Marine Conservation Society of Seychelles – MCSS). Project interventions will be identified and prioritized through consultative processes with the local stakeholders as well as setting up their watershed committee similar to other sites being supported under the EBA Project. Lessons learned from the experiences of the other more advances will be relevant for the Anse Royale area. The PIT is developing synergies with other ongoing EBA initiatives by UNEP and Government of Seychelles.
Component 3: Ecosystem based adaptation mainstreamed into development planning and financing
| Output 3.1: Policy and legal frameworks for watershed and coastal climate change adaptation |  | Conduct an analysis of institutional structures to identify policy gaps. |  | The EBA project continued to create the right linkages with other donor–funded projects where policy formulation is concerned. Climate adaptation policy is expected to be reviewed and developed under the EU GCCA+ Project on Adaptation in Seychelles, and tender for Component A of the project is already launched. Technical Assistance will be procured to review climate change adaptation policies and integration into national plans and policies as well as institutional capacity building of the key institutions responsible for implementation of climate adaptation policies. The EBA project sits on the various EBA Project committees and regular meetings are held to coordinate and exchange information on all adaptation projects ongoing in the country. Other policy work which has been initiated relates to the Watershed Management Policy which is pending finalizaton of the Water Policy by the Public Utilities Corporation and the Ministry of Environment, Energy and Climate Change. The Water Analyst has been bired by the Ministry and she is leading the review of the Water Policy at the level of the MEECC which is the parent ministry of the Public Utilities Corporation. In addition, the MEECC is recruiting under a different project (GEF Regional Project on Integrated Water Resources Management in SIDS) to undertake work on water governance and policy issues within the ministry in close link with the PUC. The EBA team is also a member of the PSC for this UNOPS/UNEP/UNDP implemented regional project and it is ensuring the right collaboration between the various projects. Ongoing discussions are held regularly between projects to ensure coordination of activities. | S
| Output 3.2 Capacity Development for Ecosystem Based Adaptation Methods |  | Capacity development for watershed committees and other project stakeholders. |  | Progress towards setting up the watershed committees is progressing. To date 40% of the committees (2 out of 5) have been established one on Mahe and the second on Praslin which was launched to coincide with World Water Day. The Baie Lazare Watershed committee which was set up first is already engaged with various activities under the project such as removal of invasive, setting up a tree nursery to provide enough trees for forest rehabilitation of water shed and water catchments. Exchanges were organised between the more advances Baie-Lazare Watershed Committee and that on Praslin when it was set up and the project is providing hands-on training to committee members on watershed stewardship and community champions as well and removal of alien invasive and safe use of tools for forest management.
| Output 3.3 Lessons learned and Knowledge Dissemination |  | Development of a communications strategy |  | To date the project has not yet produced the Communications Strategy but it has invested in numerous educational activities and information dissemination and awareness-raising. The Communication Strategy will be initiated during the Q2 2016 and will be available for the next reporting period. The project has developed materials and brochures/t-shirts a lot of which have been used during the various events such as lunching of Praslin Watershed Committee, World Water Day road show on Praslin, school competitions etc as mentioned by the PM assessment above. The communication strategy will be drafted once the programme analysis and audience analysis has been completed by the project team and it is part of the 2016 annual work plan (Jan to Dec 2016). Use of national media has been maintained during the reporting period with the production of a short TV documentary on the project which was aired on World Biodiversity day. The project is now geared to take part in the National Day Celebrations EXPO which will run from 29 to 29th June 2016.
Overall Rating
Please Provide the Name and Contact information of person(s) reponsible for completeling the Rating section
| Name: | Roland Alcindor
| Email: | roland.alcindor@undp.org
| Progress on Key Milestones |  | Expected Progress |  | Progress to Date | Rating
Other
Overall Rating
Please Provide the Name and Contact information of person(s) reponsible for completeling the Rating section
Name:
Email:
| Please justify your rating and address the following points: 1. Indicate trends, both positive and negative, in achievement of outcomes as per the project indicators. 2. Detail critical risks that have affected progress. 3. Outline response to MTR undertaken this reporting period. 4. Outline action plan to address projects with a rating of HU, U or MU. Please keep your input to 1200 words |  | The rating of Satisfactory is justified because the project has made significant progress compared to the first PPR produced last year. As can been seen from expenses/delivery on the various targets, the project is now on track. The establishment of a fully functional Project Implementation Team has been key as well as having on board an experienced Project Manager who is already well versed with the procedures of donor funded projects as well as the operational side of the Programme Coordinating Unit, has facilitated progress towards the various indicators. The experience of the PM and the team has resulted in dealing with a number of bottlenecks. Positive trends observed are the stability of the project team for some time now and it is expected that the current team will remain in place for the next reporting period. Furthermore, project activities have started on all project sites in various forms from studies to site rehabilitation plans and feasibility studies as well as setting up community groups (Watershed Community Groups) which is also positive. The various linkages with the other ongoing projects needs to be highlighted as it shows a good level of coordination as well as internal communications between the various agencies and institutions involved with ecosystem based adaptation and/or water sector issues in Seychelles. This cooperation is a key aspect which will ensure progress towards the objectives and create the appropriate synergies between the various interventions. Building on previous studies is also positive such as the North East Point coastal adaptation activities using JICA studies as it allows the EBA project to benefit from important data at no extra costs and already generated by other donor-funded projects. On the policy and regulatory side, the linkages with upcoming activities funded by the EU will allow the EBA to provide inputs into the wider concept of integrating climate adaptation concerns into development policy and planning and not focus solely on water sector adaptation. The policy work under the EBA will complement the national efforts and add greater value to the process. The project has been able to find workable solutions to address land ownership issues which at some point threatened to become a critical risk in some of the project sites. Whilst, the risk is not fully eliminated, as in one of the project site, residential development on private land still poses a risk of water pollution and contamination of water catchment, the issue of site selection at least was resolved during the reporting period. Some of the factors affecting progress to date have been noted such as finalisation of various policy documents by other agencies upon which the project team have little or no control over. However, the Programme Coordinating Unit has been pro-active and in engaging the Public Utilities Corporation which is the key partner upon which a number of decisions can affect the success of this project. The PPR is also reporting for only 9 months since the last one and hence the rating of satisfactory is justified as a number of initiatives will be completed during the last remaining 3 months of the workplan.
Rating Definitions
|  |  | Highly Satisfactory (HS) | Project actions/activities planned for current reporting period are progressing on track or exceeding expectations to acheive all major outcomes/outputs for given reporting period, without major shortcomings. The project can be presented as “good practice”.
|  |  | Satisfactory (S) | Project actions/activities planned for current reporting period are progressing on track to achieve most of its major outcomes/outputs with only minor shortcomings.
|  |  | Marginally Satisfactory (MS) | Project actions/activities planned for current reporting period are progressing on track to achieve most major relevant outcomes/outputs, but with either significant shortcomings or modest overall relevance.
|  |  | Marginally Unsatisfactory (MU) | Project actions/activities planned for current reporting period are not progressing on track to achieve major outcomes/outputs with major shortcomings or is expected to achieve only some of its major outcomes/outputs.
|  |  | Unsatisfactory (U) | Project actions/activities planned for current reporting period are not progressing on track to achieve most of its major outcomes/outputs.
|  |  | Highly Unsatisfactory (U) | Project actions/activities planned for current reporting period are not on track and shows that it is failing to achieve, and is not expected to achieve, any of its outcomes/outputs.

## Project Indicators
PROJECT Indicators
Please provide all indicators being tracked for the project as outlined in the project document
Type of Indicator (indicators towards Objectives, Outcomes, etc…)
Type of Indicator | Indicator | Baseline | Progress since inception | Target for Project End
Project Objective | Ecosystem services and natural assets maintained or improved under climate change and variability-induced stress | Project watersheds and coastal areas are regularly subject to water shortages and flooding events | At the landscape-level intervention the farmers in the Baie Lazare community are working to ensure their increased yields are not at the expense of the water provision services from the watershed. Farmers are being trained to make conscious choices to improve the forest water retention and flow, to maximise water provision services. | Reduced water shortages and flooded area involving about 4,000 ha of watershed and coastal ecosystems
| August mean daily discharge on two rivers (Mare aux Couchons & Baie Lazare) with increased base flows78 | Mare aux Couchons August Avg Mean Daily Discharge: 261.1 L/S Baie Lazare August Mean Daily Discharge: 33.4 L/S | Data are being collected at Baie Lazare by PUC and UNISEY, e.g. Baie Lazare August 2015 Mean Daily Discharge: 53.1 L/s (+60%); data collection at Mare aux Cochons is being led by PUC | Mare aux Cochons and Baie Lazare: Aug. baseline flows +20 – 30%
| January mean daily discharge on two rivers with decreased flood flows | Mare aux Couchons January Avg Mean Daily Discharge: 595.4 L/S Baie Lazare January Mean Daily Discharge: 173.1 L/S | Data are being collected at Baie Lazare by PUC and UNISEY, e.g. Baie Lazare Mean Daily Discharge for January 2016: 106.5 L/s (-62%); data collection at Mare aux Cochons is being led by PUC | Mare aux Cochons and Baie Lazare: January baseline flows -20%
Component 1 | Number of water users with more reliable water supply | 10% of PUC water supply customers in project watersheds without fully reliable surface water supply | Indicator not measured in this reporting period. Project surveys have noted that a considerable amount of people do not have access to PUC water in some watersheds (Caiman, Mont PLaisir, Praslin, Baie Lazare). As the indicator specifically targets PUC water supply customers, not wider water users, the project is debating whether or not to work on PUC data for water supply figures only. It has been agreed with PUC that the weir at Mare aux Cochons will be refurbished by the project to improve data collection for water and supply. | 100% of PUC customers in target watersheds with more reliable water supply
| Number of days per year water supply is not available at two sites: Baie Lazare and Mare aux Cochons | Number of days per year when stream flows at critical low: Baie Lazare: avg. 18 days Mare aux Cochons: avg. 75 days (2010 - 2011) | There was a reduction in the number of days where there was no water availability in the Baie Lazare project watershed in this reporting period (compared to previous years). | 0 days of no water availability per year in project watersheds
| Volume of raw water production from PUC facilities in project watersheds | Annual water production at: Mare aux Cochons: 614,336 KL Baie Lazare: 191,232 KL | The data was not provided by the Public Utilities Corporation (PUC) for this reporting period. The project team will measure this indicator in this quarter's progress report. | Annual water production figures increase by 20%
| Number of hectares of watersheds covered by site-based water management plans | 0 hectares | Watershed management plans have not yet been developed. The following hectares have been surveyed and mapped as potential areas that will be rehabilitated in future management plans: 160 ha for Caiman River watershed, 360 ha for Baie Lazare, 530ha for Mare-aux-Cochon, 34 ha for Fond B'Offay and Nouvelle Decouverte. In total, 1398 ha of watersheds has been mapped for direct project interventions. These will be the basis of the future management plans, which may also cover additional areas (e.g. areas managed by partners). | 3,000 ha of critical watersheds
| Area of rehabilitated water provisioning and watershed flooding attenuation ecosystems | Total hectares of watershed with increased resilience to climate change: 0 Total area of watershed that has undergone total rehabilitation: 0 | Baseline studies and minor works to prepare sites for rehabilitation in Baie Lazare have been started. The intervention will start in the second quarter of 2016; 445 ha will be addressed for this indicator in Baie Lazare. Areas to be addressed in other sites are yet to be determined. | Total hectares of watershed with increased resilience to climate change: 3000 ha Total area of forest that has undergone total rehabilitation: at least 60 ha
| Active community watershed committees (with gender balance) | No watershed committees established | Two watershed committees have been set up in the district of Baie Lazare and Praslin Island, and are actively involved in the management of their catchment area. There is gender balance in both, with the Chairperson of the Praslin Committee being a female. Currently, there are 13 members of the Baie lazare committee with 6 females and 7 males. The Praslin Watershed Committee comprise of 4 females and 4 males. | At least 4 watershed committees established with gender balance
Component 2 | Area of rehabilitated coastal ecosystems | # of tidal sluice gates installed: 0 | No tidal sluice gates have been installed yet. The preliminary findings from the assessments of coastal wetlands environmental flows report for both North East Point and Anse Royale will assist the project management team with making informed decisions for this indicator. Pilot sluice gates have been installed at a number of sites by relevant authorities over the last year, and it may be that Government will provide the finance needed for this engineering work. | # of tidal sluice gates installed: 2 by end of project
|  | Little wave energy attenuation provided by reef (5% of the pre-1998 bleaching event reef size) | The status of the reef structures at north east point have been assessed; results indicate that the reef crest is exposed to strong wave surge, breaking off larger coral colonies so branching corals tend to grow less and remain smaller. The project is identifying means to proceed with artificial reef structures. | 150 m of artificial breakwater providing substrate for coral growth and wave energy attenuation and more than 10% of original reef area rehabilitated at NE Point
|  | Total hectares of wetlands rehabilitated to provide flood attenuation services: 0 ha | 25 ha of wetlands will be rehabilitated through this project, which includes all the coastal wetland for both North East Point and Anse Royale. There has been no interventions yet as the project experienced delays in completing biodiversity assessments and environmental flow assessments of the wetlands. | Total hectares of wetlands rehabilitated to provide flood attenuation services: 17 ha
|  | Total km of rehabilitated beach berms providing a barrier for coastal floods: 0 km | 2.1 km of beach berm has been identified for rehabilitation at North East Point. There has been no interventions in this reporting period as the project has been focusing on watershed rehabilitation. | Total km of rehabilitated beach berms providing a barrier for coastal floods: 5 km
|  | Total hectares of mangroves, wetlands, fringing reef, beach berms and other ecosystems with increased resilience to climate change impacts: 0 | There has been no interventions yet as the project focuses on initial baseline assessments and conducts further scientific situation analyses of these 2 coastal sites. | Total hectares with increase resilience: 1,000 ha
| Farm pond salinity levels reduced | Up to 6.0 ppt salinity levels in farm ponds during dry season | ICBA is working with the SAA and the project to revise this project indicator, which has been found to be unrealistic. A joint workshop was undertaken to establish collaboration with the IAEA and ICBA and the Seychelles Agricultural Agency to review the situation of water and soil salinity challenges in the Seychelles. There was knowledge-sharing and lessons learnt to broaden and strengthen partnership to build on the various project results taking into account the government and farmers’ priority needs. | 70% less salinity levels in farm ponds during the dry season
| Number of hectares of coastal ecosystems covered by Integrated Shoreline Management Plans | 0 hectares | No interventions as yet. The Integrated Coastal Management Plan developed by the NGO MCSS under another UNDP project will inform the drafting of this management plan. Input from the SAA project with IAEA and ICBA is also being sought to inform the drafting of the Integrated Shoreline Management Plan for Anse Royale. | 1,000 ha of coastal ecosystems
Component 3 | Approved water management policy framework being implemented for watershed areas | No policy and financing framework | Discussions have been held with European Investment Bank and PUC consultants and there is consensus on the need to develop a regulatory framework for water management in Seychelles. This will thereafter facilitate the drafting of a watershed management policy. | Approved water management policy for watershed areas Core annual funding for local watershed management provided by tariffs and fees: $ 500,000
| Capacity developed for EbA methods: Rivers Committee meet regularly. | No institutional mechanisms | If the Rivers Committee is resuscitated, the project team will support it to meet on a quarterly basis to to discuss and address issues related to improving run-of-river barrages and water control structures, sustainably managing watercourses and promoting local stewardship of watersheds (issues that need to be discussed but which are stalled pending clarification of the policy environment). | River Committee meets every quarter to discuss and address issues
| A National Watershed Monitoring System developed, applied and influences watershed management decisions | Little information available regarding functional connectivity, watershed integrity and water balance of watersheds | 6 monitoring stations have been set up in Baie Lazare watershed to record the hydrological flow of in the rivers and streams and the quality paremeters data on the study areas. University of Seychelles students are collecting data regulalry for analyses. This is the start of the watershed monitoring programme for Baie Lazare, which will be extended to other project sites. | Institutionalised and operational watershed monitoring system ensures adaptive management of watershed systems.
| Technical standards established for watershed, tidal wetland, and beach and reef rehabilitation | Incomplete and ad hoc specifications for ecosystem rehabilitation | The project Technical Advisory Group has provided guidance through 4 scientific background papers concerning the promotion of ecosystem services of water catchment areas and forest in Seychelles. A UNISEY visiting Professor is actively guiding students to collect and analyse data to inform the project. University students are testing water quality in the Baie Lazare catchment area and measuring the water flow and water availability. 8 potential rehabilitation sites at Baie Lazare are being studied by 2 Masters students from ETH Zürich to assess vegetation quality and the impact of the anthropogenic activities in the catchment areas. | Technical standards are established and provide the basis for training.
| Number of trainees by gender skilled in EbA methods | Few government or NGO staff experienced in watershed or wetland rehabilitation | A total of 6 female and 7 male Watershed Committee members were trained in plant identification in September 2015. 13 female students from the University of Seychelles and 4 male students were trained in how to monitor stream flow in Baie Lazare rivers using the weirs. The students learnt how to measure the potential volume of water held within the small PUC barrages, and assessed the many factors affecting drainage at the site, in terms of soil, geology, slope dynamics, vegetation, landuse, rainfall, overland and through flow. 6 female Government staff and 9 male farmers were trained in soil and salinity management in a workshop organized by ICBA in 2015. Only 4 male participants were trained as trainers in the safe use of chainsaws for forest management due to limited positions available in the international LANTRA certificate course and no female applicants. | 50 persons (gender balanced) trained in watershed, tidal wetland and beach and reef rehabilitation.
| Number of knowledge products on watershed and coastal ecosystem- based adaptation | Limited awareness of EbA methods related to watersheds and coastal ecosystems | Specific knowledge products produced by the project thus far are: 1) Project brochure (summary of the project and its objectives), 2) A specific brochure for the Baie-Lazare watershed committee and community, 3) Watershed committee guide 'Our water Our Choice'. 4)Proposed methodology for forest rehabilitation has been prepared by one member of the Technical Working group. It is entitled "Evaluation of important elements of the ecosystem service of water-catchment areas in the Seychelles by (in a first phase) (I) estimating the vegetation quality, (II) the water quality, (III) the water flow, (IV) the human impact on the designated water-catchment areas". 5) Another paper has been prepared entitled "Draft Methods for Rehabilitation of Seychelles Forest". It is a paper proposing methods for Introduction and Objectives of Forest Rehabilitation in Seychelles, Methods for the Rehabillitation of Forest and operational procedures for rehabilitation. 6) Rapid Biodiversity Assessment of North East Point and Anse Royale Marshes 7) Assessment of Coastal Wetlands Environmental Flow at North East Point and Anse Royale Towards Wetlands Rehabilitation 8) Assessment of the Rehabilitation Potential of the Mont Plaisir River Catchment 9) Assessment of the Rehabilitation Potential of the Mont Caiman River Catchment | 10 knowledge products produced to assist awareness building

## Lessons Learned
QUALITATIVE MEASURES and LESSONS LEARNED
Please complete the following section every reporting period
Implementation and Adaptive Management | Response
What implementation issues/lessons, either positive or negative, affected progress? | Implementation is accelerating, but it is noted that the PIT needs to exert close monitoring and evaluation of activities undertaken by consultants to ensure timely delivery. Local capacities are quite limited such that advertised conusltncies attract few bidders, and usually the same ones - there is little competition among local firms such that the project has little choice in awarding contracts. Further, required expertise such as geotechnics and marine modelling is not available locally and has to be sourced regionally or internationally, although the project is trying to access this expertise through and in association with local firms to ensure integration of work and local capacity building as a spin-off of the project actions.
Were there any delays in implementation? If so, include any causes of delays. What measures have been taken to reduce delays? | There remains a delay in the rehabilitation work at Baie Lazare due to land ownership issues; while these are now largely solved the late start in activities means the delays are perpetuated. To make sure there are no further impacts resulting from e.g. a change of land ownership, the community enegagement specialist works in collaboration with the Land Registry Office to keep in touch with the land owners and to ensure that there are no conflicts with property rights. In the case of Mare aux Cochons the rehabilitation work is delayed by the sensitive nature of the site (as a National Park and key biodiversity area) which has required extensive consultation (still on-going) through the Technical Advisory Group to determine the types of interventions that may be applied without impacting on ecosystem processes and values.
Describe any changes undertaken to improve results on the ground or any changes made to project outputs (i.e. changes to project design) | No specific changes were made during this reporting period. There are some suggestions for revisions of indicators that will be clarified by the time of the mid-term review.
How have gender considerations been taken into consideration during the reporting period? What have been the lessons learned as a consequence of inclusion of such considerations on project performance or impacts? | The PIT, which is itself gender balanced with two members, including the PM, being female, has paid particular attention to this aspect. Gender balance is observed in both watershed committees so far established. The Praslin committee has a female chairperson with a total of 4 females and 4 males. The Baie Lazare committee has a male Chairperson and comprises 6 females and 7 males. The lesson learnt is that gender balance brings a broad-based stakeholder input and more successful outputs.
Please complete the following section at mid-term and project completion
Lessons for Adaptation | Response
Climate Resilience Measures
What have been the lessons learned, both positive and negative, in implementing climate adaptation measures that would be relevant to the design and implementation of future projects/programmes for enhanced resilience to climate change?
What is the potential for the climate resilience measures undertaken by the project/programme to be replicated and scaled up both within and outside the project area?
Concrete Adaptation Interventions
What have been the lessons learned, both positive and negative, in implementing concrete adaptation interventions that would be relevant to the design and implementation of future projects/programmes implementing concrete adaptation interventions?
What is the potential for the concrete adaptation interventions undertaken by the project/programme to be replicated and scaled up both within and outside the project area?
Community/National Impact
What would you consider to be the most successful aspects for the target communities?
What measures are/have been put in place to ensure sustainability of the project/program results?
What measures are being/could have been put in place to improve project/program results?
Knowledge Management
How has existing information/data/knowledge been used to inform project development and implementation? What kinds of information/data/knowledge were used?
If learning objectives have been established, have they been met? Please describe.
Describe any difficulties there have been in accessing or retrieving existing information (data or knowledge) that is relevant to the project. Please provide suggestions for improving access to the relevant data.
Has the identification of learning objectives contributed to the outcomes of the project? In what ways have they contributed?

## Results Tracker
Results Tracker for Adaptation Fund (AF) Projects
Goal: Assist developing-country Parties to the Kyoto Protocol that are particularly vulnerable to the adverse effects of climate change in meeting the costs of concrete adaptation projects and programmes in order to implement climate-resilient measures. Impact: Increased resiliency at the community, national, and regional levels to climate variability and change.
Important: Please read the following guidance document (also posted on the Adaptation Fund website) before entering your data
Link: http://www.adaptation-fund.org/sites/default/files/Results%20Framework%20and%20Baseline%20Guidance%20final.pdf
Adaptation Fund Strategic Results Framework
Project ID | 89895
Implementing Entity | Ministry of Environment, Energy and Climate Change
Type of implementing entity | NIE
Country | Seychelles
Region | Africa
Sector | Water management
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Impact: Increased resiliency at the community, national, and regional levels to climate variability and change | Core Indicator: No. of beneficiaries Note: For this project the direct beneficiaries will be PUC customers and other water users in the target sites; indirect beneficiaries will be customers and users outside the target sites who either receive water piped or flowing from those sites, benefit from improved coastal defences at the target sites, etc. This information was cpllected in 2012 and presented in the Prodoc, but without the youth dimension. As 47% of the Seychelles population is youth (aged below 30), as per the Seychelles Youth Council, this is the figure used. |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project
|  | Total | 0 | 0 | 0 | Total | 89045 | 21545 | 67500 | Total |  |  |  | Total
|  | % of female beneficiaries | 50% | 50% | 50% | % of female beneficiaries | 50% | 50% | 50% | % of female beneficiaries |  |  |  | % of female beneficiaries
|  | % of Youth beneficiaries | 47% | 47% | 47% | % of Youth beneficiaries | 47% | 47% | 47% | % of Youth beneficiaries |  |  |  | % of Youth beneficiaries
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 1: Reduced exposure to climate-related hazards and threats | Indicator 1: Relevant threat and hazard information generated and disseminated to stakeholders on a timely basis | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness
|  | Total | 0 | Coastal flooding | 1: Ineffective | Total | 89045 | Coastal flooding | 4: Effective | Total |  |  |  | Total
|  | % of female targeted | 50% |  |  | % of female targeted | 50% |  |  | % of female targeted |  |  |  | % of female targeted
Output 1.1 Risk and vulnerability assessments conducted and updated | Indicator 1.1: No. of projects/programmes that conduct and update risk and vulnerability assessments Note: At baseline there is one project developing a vulnerability assessment, but this is not part of the AF project and neither is this to be followed up under the AF project. | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | 1 | Disaster risk reduction | National | 2: Undertaking or updating of assessments in progress | 1 | Disaster risk reduction | National | 3: Risk and vulnterability assessments completed or updated
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
Output 1.2 Targeted population groups covered by adequate risk reduction systems | Core Indicator 1.2: No. of Early Warning Systems Note: This is not a part of the current project as the project does not work directly with Departent of Risk and Disaster Management (DRDM) - which has other sources of funds. | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 2: Strengthened institutional capacity to reduce risks associated with climate-induced socioeconomic and environmental losses | Indicator 2: Capacity of staff to respond to, and mitigate impacts of, climate-related events from targeted institutions increased | Number of staff targeted |  | Sector | Capacity level | Number of staff targeted |  | Sector | Capacity level | Number of staff targeted |  | Sector | Capacity level | Number of staff targeted |  | Sector | Capacity level
|  | Total | 50 | Multi-sector | 1: No capacity | Total | 50 | Multi-sector | 4: High capacity | Total |  |  |  | Total
|  | % of female targeted | 50% |  |  | % of female targeted | 50% |  |  | % of female targeted |  |  |  | % of female targeted
Output 2.1 Strengthened capacity of national and sub-national centres and networks to respond rapidly to extreme weather events | Indicator 2.1.1: No. of staff trained to respond to, and mitigate impacts of, climate-related events | Total staff trained | % of female staff trained | Type |  | Total staff trained | % of female staff trained | Type |  | Total staff trained | % of female staff trained | Type |  | Total staff trained | % of female staff trained | Type
|  | 0 | 0% | Public |  | 50 | 50% | Public
| Indicator 2.1.2: No. of targeted institutions with increased capacity to minimize exposure to climate variability risks | Type | Scale | Sector | Capacity level | Type | Scale | Sector | Capacity level | Type | Scale | Sector | Capacity level | Type | Scale | Sector | Capacity level
|  | Public | National | Multi-sector | 1: No capacity | Public | National | Multi-sector | 3: Medium capacity
output 2.2 removed and associated fund indicator 2.2.2 recommendation to report against 2.1
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 3: Strengthened awareness and owernship of adaptation and climate risk reduction processes | Indicator 3.1: Increase in application of appropriate adaptation responses Note. Refers to direct beneficiaries calculated at 21,545 persons. | Percentage of targeted population applying adaptation measures |  | Sector |  | Percentage of targeted population applying adaptation measures |  | Sector |  | Percentage of targeted population applying adaptation measures |  | Sector |  | Percentage of targeted population applying adaptation measures |  | Sector
|  | 0% |  | Coastal management |  | 70 |  | Coastal management
Output 3: Targeted population groups participating in adaptation and risk reduction awareness activities | Indicator 3.1.1: Percentage in targeted population awareness of predicted adverse impacts of climate change, and of appropriate responses Note. Baseline knowledge survey not yet undertaken to verify. | No. of targeted beneficiaries | % of female participants targeted | Level of awareness |  | No. of targeted beneficiaries | % of female participants targeted | Level of awareness |  | No. of targeted beneficiaries | % of female participants targeted | Level of awareness |  | No. of targeted beneficiaries | % of female participants targeted | Level of awareness
|  | 21545 | 50% | 3: Partially aware |  | 21545 | 50% | 5: Fully aware
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Target performance at completion |  |  |  | Target performance at completion
Outcome 4: Increased adaptive capacity within relevant development sector services and infrastructure assets | Indicator 4.1: Increased responsiveness of development sector services to evolving needs from changing and variable climate | Project/programme sector | Geographical scale | Response level |  | Project/programme sector | Geographical scale | Response level |  | Project/programme sector | Geographical scale | Response level |  | Project/programme sector | Geographical scale | Response level
|  | Water management | National | 2: Partially responsive (Lacks most elements) |  | Water management | National | 4: Mostly responsive (Most defined elements)
| Core Indicator 4.2: Assets produced, developed, improved or strengthened | Sector | Targeted asset | Changes in asset (quantitative or qualitative) |  | Sector | Targeted asset | Changes in asset (quantitative or qualitative) |  | Sector | Targeted asset | Changes in asset (quantitative or qualitative) |  | Sector | Targeted asset | Changes in asset (quantitative or qualitative)
|  | Water management | 2: Physical asset (produced/improved/strenghtened) | 1: Not improved |  | Water management | 2: Physical asset (produced/improved/strenghtened) | 4: Mostly Improved
|  | Coastal management | 2: Physical asset (produced/improved/strenghtened) | 1: Not improved |  | Coastal management | 2: Physical asset (produced/improved/strenghtened) | 4: Mostly Improved
Output 4: Vulnerable development sector services and infrastructure assets strengthened in response to climate change impacts, including variability | Indicator 4.1.1: No. and type of development sector services to respond to new conditions resulting from climate variability and change | Number of services | Type |  | Sector | Number of services | Type |  | Sector | Number of services | Type |  | Sector | Number of services | Type |  | Sector
|  | 0 | National |  | Water management | 1 | National |  | Water management
|  | 0 | National |  | Coastal management | 1 | National |  | Coastal management
|  | 0 | Multi-community |  | Agriculture | 1 | Multi-community |  | Agriculture
indicator 4.1.2 removed we can only really change this to reporting 4.1.1
|  | Baseline information |  |  |  | Targeted performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 5: Increased ecosystem resilience in response to climate change and variability-induced stress | Indicator 5: Ecosystem services and natural resource assets maintained or improved under climate change and variability-induced stress | Natural resource improvement level |  | Sector | Type | Natural resource improvement level |  | Sector | Type | Natural resource improvement level |  | Sector | Type | Natural resource improvement level |  | Sector | Type
|  | 1: Ineffective |  | Multi-sector | land | 4: Effective |  | Multi-sector | land
Output 5: Vulnerable ecosystem services and natural resource assets strengthned in response to climate change impacts, including variability | Core Indicator 5.1: Natural Assets protected or rehabilitated Note. Baseline figures are set at 0 and refer to the areas targeted for rehabilitation by the project; some of these areas are nominally protected but this is ineffective. Nationally there are other areas that have been rehabilitated to varying degrees and levels of effectiveness. | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Forests |  | ha rehabilitated | 1: Ineffective | Forests | 650 | ha rehabilitated | 3: Moderately effective
|  | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Forests |  | ha rehabilitated | 1: Ineffective | Forests | 60 | ha rehabilitated | 5: Very effective
|  | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Coasts |  | km rehabilitated | 1: Ineffective | Coasts | 5 | km rehabilitated | 4: Effective
|  | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Other |  | ha rehabilitated | 1: Ineffective | Other | 17 | ha rehabilitated | 4: Effective
|  | Baseline information |  |  |  | Targeted performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 6: Diversified and strengthened livelihoods and sources of income for vulnerable people in targeted areas | Indicator 6.1: Increase in households and communities having more secure access to livelihood assets Note. Refers to farmng households. 55% of female headed households is as per national average reported in household surveys (but noting that in a hgh percentage of cases the respondent is female) | No. of targeted households | % of female headed households | Improvement level |  | No. of targeted households | % of female headed households | Improvement level |  | No. of targeted households | % of female headed households | Improvement level |  | No. of targeted households | % of female headed households | Improvement level
|  | 600 | 55% | 2: Limited improvement |  | 600 | 55% | 3: Moderate improvement
| Indicator 6.2: Increase in targeted population's sustained climate-resilient alternative livelihoods | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
|  | 600 | 55% |  | Agriculture | 600 | 55% | From 20% to 30% | Agricultural-related
|  | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
|  | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
|  | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
Output 6 Targeted individual and community livelihood strategies strengthened in relation to climate change impacts, including variability | Indicator 6.1.1: No. and type of adaptation assets created or strengthened in support of individual or community livelihood strategies | Number of Assets | Type of Assets | Sector | Adaptation strategy | Number of Assets | Type of Assets | Sector | Adaptation strategy | Number of Assets | Type of Assets | Sector | Adaptation strategy | Number of Assets | Type of Assets | Sector | Adaptation strategy
|  | 1 | Natural capital | Coastal management | Community-based adaptation | 1 | Natural capital | Coastal management | Community-based adaptation
| Core Indicator 6.1.2: Increased income, or avoided decrease in income | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 7: Improved policies and regulations that promote and enforce resilience measures | Indicator 7: Climate change priorities are integrated into national development strategy | Integration level |  |  |  | Integration level |  |  |  | Integration level |  |  |  | Integration level
|  | 3: Some |  |  |  | 4: Most
Output 7:Improved integration of climate-resilience strategies into country development plans | Indicator 7.1: No. of policies introduced or adjusted to address climate change risks Note. Watershed management policy framework | No. of Policies introduced or adjusted | Sector | Scale | Type | No. of Policies introduced or adjusted | Sector | Scale | Type | No. of Policies introduced or adjusted | Sector | Scale | Type | No. of Policies introduced or adjusted | Sector | Scale | Type
|  | 0 | Water management | National | Water policy | 1 | Water management | National | Water Policy
| Indicator 7.2: No. of targeted development strategies with incorporated climate change priorities enforced Note. Seychelles Sustainable Development Strategy | No. of Development strategies | Regulation |  | Effectiveness | No. of Development strategies | Regulation |  | Effectiveness | No. of Development strategies | Regulation |  | Effectiveness | No. of Development strategies | Regulation |  | Effectiveness
|  | 1 | 2: Partially not enforced (Most elements not implemented) |  | 1: Ineffective | 1 | 3: Partially enforced (Some elements implemented) |  | 3: Moderately effective
Glacier lake outburst flood
|  | Inland flooding | fr | biological assets |  | Company policy | 5: Fully enforced (All elements implemented)
|  | Salinization | Decrease | land |  | Communication & Information policy | 4: Enforced (Most elements implemented)
|  | Drought | Same | water areas |  | Defense policy | 3: Partially enforced (Some elements implemented)
|  | Wind |  | subsoil assets | increased adpative capacity | Domestic policy | 2: Partially not enforced (Most elements not implemented) |  | Agribusiness
|  | Coastal flooding |  | air | achieved | Economic policy | 1: Not enforced (No elements implemented) |  | Agricultural-related | Financial capital
|  | Storm surge | Please choose |  | enhanced level of protection | Education policy |  |  | Agriculture | Human capital
|  | Hurricane | Selected | [5 empty] | Aquaculture | Physical capital
|  |  | Not relevant |  |  | 5: All (Fully integrated) |  |  | Construction/repairing business | Social capital
[6 empty] | 4: Most |  |  | Cultivation | Natural capital
[6 empty] | 3: Some |  |  | Fishing | Personal capital
Select | 5: All | Select |  |  | Community | 2: Most not integrated |  | Other | Forestry | Adaptation strategies
1 | 4: Almost all | Private | Type | Yes | Multi-community | 1: None |  | Agriculture | Handicrafts
2 | 3: Half | Public | Scale | No | Departmental |  |  | Coastal management | Livestock production
3 | 2: Some | NGO | Sector |  | National |  |  | Disaster risk reduction | Manufacturing
4 | 1: None |  |  |  |  | 5: Very high improvement | Established | Food security | other
|  | National |  |  |  | 4: High improvement | Maintained | Health | Services
|  | Regional |  |  |  | 3: Moderate improvement | Improved | Urban development | Tourism-related
|  | Local |  |  |  | 2: Limited improvement |  | Water management | Trading
[6 empty] | 1: No improvement |  | Multi-sector
|  | 1 -generated information is irrelevant, and neither the stakeholders reached nor the timeframe managed were achieved | 1: No info transferred on time | 4: High capacity | 5: Fully aware | 5: Highly responsive (All defined elements ) | 5: Fully improved | Roads | 5: Very effective
Asia-Pacific | NIE | 2 -the existence of some challenge in any of the three aspects of the indicator (generation of dissemination, stakeholders reached or timeframe managed) | 2: Somewhat info transferred | 3: Medium capacity | 4: Mostly aware | 4: Mostly responsive (Most defined elements) | 4: Mostly Improved | Gov Buildings | 4: Effective
Latin America and Caribbean | RIE | 3 -relevant information is generated and disseminated to all identified stakeholders on timely basis | 3: Info transferred on time | 2: Low capacity | 3: Partially aware | 3: Moderately responsive (Some defined elements) | 3: Moderately improved | Causeways | 3: Moderately effective
Africa | MIE |  |  | 1: No capacity | 2: Partially not aware | 2: Partially responsive (Lacks most elements) | 2: Somewhat improved | Airports | 2: Partially effective
Eastern Europe |  |  |  |  | 1: Aware of neither | 1: Non responsive (Lacks all elements ) | 1: Not improved | Schools | 1: Ineffective
| ha protected | [6 empty] | Training Centres
| ha rehabilitated | [5 empty] | Monitoring/Forecasting capacity | Hospitals
Afghanistan, Islamic Rep. of | km protected | [5 empty] | Policy/regulatory reform | Drinking water systems
Angola | km rehabilitated | 1: Risk knowledge | 1: No plans conducted or updated |  |  |  | Capacity development | Other
Albania |  | 2: Monitoring and warning service | 2: Undertaking or updating of assessments in progress |  |  | Communication & Information policy | Sustainable forest management
Argentina |  | 3: Dissemination and communication | 3: Risk and vulnterability assessments completed or updated |  |  | Domestic policy | Strengthening infrastructure | 1: Health and Social Infrastructure (developed/improved)
Armenia | Forests | 4: Response capability |  |  |  | Economic policy | Supporting livelihoods | 2: Physical asset (produced/improved/strenghtened)
Antigua and Barbuda | Mangroves |  |  |  |  | Education policy | Mangrove reforestation
Azerbaijan | Coasts |  | From 0 to 0.5% |  |  | Energy policy | Coastal drainage and infrastructure
Burundi | Rangelands |  | From 0.5 to 1% |  |  | Environmental policy | Irrigation system
Benin | Cultivated land/Agricultural land |  | From 1% to 5% |  |  | Foreign policy | Community-based adaptation
Burkina Faso | Catchment area/Watershed/Aquifer |  | From 5% to 10% |  |  | Health policy | Erosion control
Bangladesh | Protected areas/National parks |  | From 10% to 20% |  |  | Housing policy | Soil water conservation
Bulgaria | Other |  | From 20% to 30% |  |  | Human resource policies | Microfinance
Bahrain |  |  | From 30% to 40% |  |  | Information policy | Special Program for women
Bahamas, The |  |  | From 40% to 50% |  |  | Macroeconomic policy | Livelihoods
Bosnia and Herzegovina |  |  | Above 50% |  |  | Monetary policy | Water storage
Belarus | [5 empty] | Population policy | ICT and information dissemination
Belize | [5 empty] | Private policy
Bolivia | [5 empty] | Public policy
Brazil | [5 empty] | Science policy
Barbados | [5 empty] | Social policy
Bhutan |  | 3- relevant information is generated and disseminated to all identified stakeholders on timely basis |  |  |  | Transportation policy
Botswana |  | describe |  |  |  | Urban policy
Central African Republic |  | 2- the existence of some challenge in any of the three aspects of the indicator |  |  |  | Water policy
Chile |  | describe |  |  |  | Other policy
China, People's Republic of |  | 1- generated information is irrelevant and neither the stakeholders reached nor the timeframe managed were achieved
Cote d'Ivoire |  | describe
Cameroon
Congo, Dem. Rep. of
Congo, Republic of
Cook Islands
Colombia
Comoros
Cape Verde
Costa Rica
Cuba
Czech Republic
Djibouti
Dominica
Dominican Republic
Algeria
Ecuador
Egypt
Eritrea
Estonia
Ethiopia
Fiji
Micronesia, Fed. States of
Gabon
Georgia
Ghana
Guinea
Gambia, The
Guinea-Bissau
Equatorial Guinea
Grenada
Guatemala
Guyana
Honduras
Croatia
Haiti
Hungary
Indonesia
India
Iran, Islamic Republic of
Jamaica
Jordan
Kazakhstan
Kenya
Kyrgyz Republic
Cambodia
Kiribati
Saint Kitts and Nevis
Korea, Republic of
Lao People's Democratic Republic
Lebanon
Liberia
Libya
Saint Lucia
Sri Lanka
Lesotho
Lithuania
Latvia
Morocco
Moldova
Madagascar
Maldives
Mexico
Marshall Islands
Macedonia, former Yugoslav Republic of
Mali
Malta
Myanmar
Montenegro
Mongolia
Mozambique
Mauritania
Mauritius
Malawi
Malaysia
Namibia
Niger
Nigeria
Nicaragua
Niue
Nepal
Nauru
Oman
Pakistan
Panama
Peru
Philippines
Palau
Papua New Guinea
Poland
Korea, Dem. People's Rep. of
Paraguay
Romania
Russian Federation
Rwanda
Saudi Arabia
Sudan
Senegal
Solomon Islands
Sierra Leone
El Salvador
San Marino
Serbia
Sao Tome and Principe
Suriname
Slovak Republic
Slovenia
Swaziland
Seychelles
Syrian Arab Republic
Chad
Togo
Thailand
Tajikistan
Turkmenistan
Tonga
Trinidad and Tobago
Tunisia
Turkey
Tuvalu
Tanzania
Uganda
Ukraine
Uruguay
Uzbekistan
Saint Vincent and the Grenadines
Venezuela
Vietnam
Vanuatu
Samoa
Yemen, Republic of
South Africa
Zambia
Zimbabwe
Timor-Leste

## Units for Indicators
Fund Outcome Indicator Units
1. Generation of relevant data, Stakeholders, and Timeliness 2.1. Include both qualitative and quantitative measures of capacity level within targeted institutions 2.2. Number (men and women and other vulnerable groups) 3.1. Use scale from 1 to 5: 5: Fully aware 4: Mostly aware 3: Partially aware 2: Partially not aware 1: Aware of neither predicted adverse impacts of climate change nor of appropriate responses 3.2. Use scale from 1 to 5: 5: All 4: Almost all 3: Half 2: Some 1: None 4.1. Summarize in an overall scale (1-5): 5: Highly responsive (All defined elements ) 4: Mostly responsive (Most defined elements) 3: Moderately responsive (Some defined elements) 2: Partially responsive (Lacks most elements) 1: Non responsive (Lacks all elements ) 4.2. Summarize in an overall scale (1-5): 5: Fully improved 4: Mostly Improved 3: Moderately improved 2: Somewhat improved 1: Not improved 5. Depends on the targeted natural asset: Biological (species): measure through changes in population numbers (dynamics, structure, etc.) Land: measure changes in hectares. Baseline data will be necessary to estimate the change. Supporting indicators baseline and target (as well as contextual information) are needed such as the following: Farmers adopting recommended technologies, Ha. of land improved, Average deforestation rate Etc. Use scale from 1 to 5. 5: Very effective (All elements are present) 4: Effective (Most elements are present) 3: Moderately effective (Some elements are present) 2: Partially effective (Most elements are not present) 1: Ineffective (No elements are present) 6.1. Summarize in an overall scale (1-5): 5: Very high improvement 4: High improvement 3: Moderate improvement 2: Limited improvement 1: No improvement 6.2. Household income by source of livelihood in project area (USD) prior and post project intervention 7. Summarize in an overall scale (1-5). 5: All (Fully integrated) 4: Most 3: Some 2: Most not integrated 1: None
Fund Output Indicator Units
1.1. Number, sector(s) and level(s) of projects or interventions in separate fields of monitoring plan 1.2. Number 2.1.1. Number of staff (male/female) of targeted institutions: a. Obtain baseline information: total number of staff from targeted institutions b. Define target 2.1.2. Number of staff (male/female) of targeted institutions: a. Obtain baseline information: total number of staff from targeted institutions b. Define target: needs to be defined by project proponents 2.2.1. Quantitative: Percentage (includes women – and other vulnerable groups – and men). Qualitative: Adequacy: include direct analysis of major areas; adequacy/effectiveness of systems or analysis of perceptions of populations and institutions. 2.2.2. Number (broken down by gender and, if possible, by vulnerable groups defined in the area of intervention) of people 3.1. Number and type (in separate columns) at local level. 3.2. Number 4.1. Number and type 4. 2. Number and type (entered in separate columns) 5. Number of interventions by type of natural asset and intervention 6.1. Number and type (in separate columns of monitoring plan) 6.2. Income sources per household; description of income source and number of households. 7.1. Number/Sector 7.2. Number; Effectiveness (see previous indicator) through enforcement level.