## Overview
Project Performance Report (PPR)
| Period of Report (Dates) | 1st July 2016 - 31st July 2017
| Project Title: | Ecosystem-based Adaptation to Climate Change in Seychelles
| Project Summary: | The project aims to reduce the vulnerability of the Seychelles to climate change, focusing on water scarcity and flooding. The climate change projections in the Seychelles show that rainfall will become irregular with much of the precipitation falling in sharp bursts, creating heavy flooding in the wet season, while imposing extended period of drought during the dry season. The lack of large water storage capacity and with the topography of the islands constraining such infrastructure, water supplies are heavily dependent on rainfall. Furthermore, the coastal zone is vulnerable to flooding as a consequence of rising sea surface levels, and increased storm surges from cyclonic activity in the Western Indian Ocean. The project will reduce these vulnerabilities by spearheading an ecosystem-based adaptation approach that will be applied to watershed and coastal rehabilitation on the two largest Islands to address water shortages and watershed and coastal flooding that have been accentuated by climate change.
|  |  | Countries | Project Type: |  | GEF Focal Area: | GEF 4 Focal Areas | GEF 2 / 3 Operational Programme: | Overall Rating of the project in the evaluation by the project evaluator: | GEF-4 Focal Area Strategic Program:
| Database Number: | 4775 | Afghanistan | FP | Yes | Biodiversity | 1 | 1 | U | BD-SP1-PA Financing
Implementing Entity (IE) [name]: |  | UNDP | Albania | MSP | No | Climate Change Adaptation | 2 | 2 | S | BD-SP2-Marine PA
| Type of IE: | Multilateral | Algeria | EA |  | Climate Change Mitigation | 3 | 3 | MU | BD-SP3-PA Networks
| Country(ies): | Seychelles | Angola |  |  | International Waters | 5 | 5 | Good | BD-SP5-Markets
Relevant Geographic Points (i.e. cities, villages, bodies of water): |  | Mare aux Cochons watershed, Mahe; Mt Plaisir watershed, Mahe; Baie Lazare watershed, Mahe; Caiman River watershed, Mahe; Fond B’Offay/Nouvelle Decouvert watershed, Praslin; North-east Point coastal ecosystem, Mahe; Anse Royale coastal ecosystem, Mahe | Argentina |  |  | Multiple Focal Area |  |  |  | BD-SP7-Invasive Alien Species(IAS)
[8 empty] | CC-SP2- Industrial EE | 8: Waterbody based operational program
| Project Milestones | [6 empty] | CC-SP3-RE,CC-SP4-Biomass | 9: Integrated Land and Water multiple focal area
| Milestone |  | Bahamas | [6 empty] | CC-SP5-Transport
AFB Approval Date: |  | 2014-02-13
IE-AFB Agreement Signature Date: |  | 2014-02-13 | [6 empty] | CC-SP6-LULUCF | 12: Integrated Ecosystem Management
Start of Project/Programme: |  | 2014-06-06 | [6 empty] | Cross cutting capacity building | 14: Persistent Organic Pollutants
Mid-term Review Date (if planned): |  | 2017-10-01
| Terminal Evaluation Date: | 2020
|  | List documents/ reports/ brochures / articles that have been prepared about the project. | Cyprus
|  | Progress reports: - Quarterly reports (Q3 2016 to Q2 2017) Technical reports: - Assessment of the rehabilitation potential of forests in the Mare aux Cochons. (Senterre et al) - Mapping and reef assessment on the reef of North East Point. (Jude Bijoux) - Coastal Processes Study, North East point, Mahe Island, Seychelles. (eCoast Company): https://www.dropbox.com/s/nunlx9r6spx1spo/Seychelles_North_Point_Mahe_v6_reduced.pdf?dl=0 - Rapid Fauna Assessment of La Drisse potential wetland area (Rachel Bristol) - Rapid Flora Assessment of La Drisse potential wetland area (Charles Morel and Tara Padayachy) - Geotechnical and financial feasibility study of wetland creation in the "La Drisse" depression, in the Mare-aux-Cochons watershed (SCP) - Forest rehabilitation and assessment of important elements of the ecosystem services of the Val d’Endor watershed on the island of Mahé, Seychelles. (Karl Fleischmann et al). EBA project in collaboration with the University of Seychelles & the Federal Institute of Technology (ETH) Zürich - Status assessment and proposed management regime for Mare aux Cochons Ramsar site, Seychelles (Dirk Lamberts) UN in Seychelles Newsletter: • 4th Quarter Sept-Dec 2016- New course sets high standards for plant identification http://www.unicnairobi.org/wp-content/uploads/2017/02/UNSeychellesNewsletter_Sept-Dec2016.pdf • 1st Quarter Jan-April 2017 - Engaging Farming Community In Watershed Management http://www.unicnairobi.org/wp-content/uploads/2017/06/UNNewsletter_Seychelles_Jan-April2017.pdf SIDS Times Newsletter • February 2017 (Volume 2, Issue 1) – New Course Sets high stands for plant identification http://www.sids2014.org/index.php?page=view&type=2017&nr=44&template=978&menu=1601 Press articles: • 5-September- 2016 - What plant is that? New course sets high standard for plant identification http://www.nation.sc/article.html?id=250904 • 3-February- 2017 - World Wetlands Day - Exhibition showcases importance of wetlands http://www.nation.sc/article.html?id=25276 • 8-May-2017 - Engaging farming community in watershed management http://www.nation.sc/article.html?id=253967 | Czech Republic
List the Website address (URL) of project. |  | UN | Democratic People's Republic of Korea
|  | www.pcusey.sc and www.undp.org | Democratic Republic of the Congo
Denmark
| Project contacts: |  | Djibouti
National Project Manager/Coordinator |  |  | Dominica
| Name: | Betty Seraphine (Project Manager) | Dominican Republic
| Email: | b.seraphine@pcusey.sc | Ecuador
| Date: | 2017-06-16 | Egypt
| Government DA |  | El Salvador
| Name: | Wills Agricole | Equatoral Guinea
| Email: | w.agricole@env.gov.sc | Eritrea
| Date: | 30/6/2017 | Estonia
| Implementing Entity |  | Ethiopia
| Name: | Roland Alcindor | Fiji
| Email: | roland.alcindor@undp.org | Finland
| Date: | 2015-06-30 | France
| Executing Agency |  | Gambia
| Name: | Wills Agricole | Georgia
| Email: | w.agricole@env.gov.sc | Germany
| Date: | 30/06/2017 | Ghana
| Executing Agency |  | Greece
| Name: |  | Grenada
| Email: |  | Guatemala
| Date: |  | Guinea
| Executing Agency |  | Guinea Bissau
| Name: |  | Guyana
| Email: |  | Haiti
| Date: |  | Honduras
Hungary
Iceland
India
Indonesia
Iran (Islamic Republic of)
Iraq
Ireland
Israel
Italy
Jamaica
Japan
Jordan
Kazakhstan
Kenya
Kiribati
Kuwait
Kyrgyzstan
Lao People’s Democratic Republic
Latvia
Lebanon
Lesotho
Liberia
Libyan Arab Jamahiriya
Liechtenstein
Lithuania
Luxembourg
Madagascar
Malawi
Malaysia
Maldives
Mali
Malta
Marshall Islands
Mauritania
Mauritius
Mexico
Micronesia, Federated States of
Monaco
Mongolia
Montenegro
Morocco
Mozambique
Myanmar
Namibia
Nauru
Nepal
Netherlands
New Zealand
Nicaragua
Niger
Nigeria
Norway
Oman
Pakistan
Palau
Panama
Papua New Guinea
Paraguay
Peru
Philippines
Poland
Portugal
Qatar
Republic of Korea
Republic of Moldova
Romania
Russian Federation
Rwanda
Saint Kitts and Nevis
Saint Lucia
Saint Vincent and the Grenadines
Samoa
San Marino
Sao Tome and Principe
Saudi Arabia
Senegal
Serbia
Seychelles
Sierra Leone
Singapore
Slovakia
Slovenia
Solomon Islands
Somalia
South Africa
Spain
Sri Lanka
Sudan
Suriname
Swaziland
Sweden
Switzerland
Syrian Arab Republic
Tajikistan
Thailand
The former Yugoslav Republic of Macedonia
Timor-Leste
Togo
Tonga
Trinidad and Tobago
Tunisia
Turkey
Turkmenistan
Tuvalu
Uganda
Ukraine
United Arab Emirates
United Kingdom of Great Britain and Northern Ireland
United Republic of Tanzania
United States of America
Uruguay
Uzbekistan
Vanuatu
Venezuela, Bolivarian Republic of
Viet Nam
Yemen
Zambia
Zimbabwe

## FinancialData
Financial information: 01 April 2016 - 31 July 2017
DISBURSEMENT OF AF GRANT FUNDS
How much of the total AF grant as noted in Project Document plus any project preparation grant has been spent to date?
Estimated cumulative total disbursement as of March 2016 | 1822152
Add any comments on AF Grant Funds. (word limit=200) | The previous PPR reported expenditure up to 31 March 2016. The current financial reporting period extends from 01 April 2016 to 31 July 2017. Expenditure during the current reporting period is $1,022, 513; thus cumulative expenditure at the end of July 2017 is $1,822,1529. The balance of funds held at the end of July 2017 was $343,494 and is sufficient for activities for the remainder of Q3 2017. Most activities are now under implementation, with steady expenditure in all components. Some delays have been experienced in component 3, which have delayed expenditure, but these are now being resolved following endorsement of a national Water Policy in July 2017. With contiinued expansion and upscaling of activities, the next tranche of funds is expected to be used within a one-year period as originally envisaged, being expended by end of July 2018.
INVESTMENT INCOME | 0
Amount of annual investment income generated from the Adaptation Fund’s grant
EXPENDITURE DATA
List ouput and corresponding amount spent for the current reporting period | ITEM / ACTIVITY / ACTION | AMOUNT
| Component 1 ECOSYSTEM-BASED ADAPTATION APPROACH TO ENHANCING FRESHWATER SECURITY AND FLOOD CONTROL IN MAHÉ AND PRASLIN UNDER CONDITIONS OF CLIMATE CHANGE | 630895.85
| Output 1.1 Management and rehabilitation of critical watersheds to enhance functional connectivity and the resilience of these areas to climate change and reduce water scarcity and watershed flooding (Mare aux Cochons, Mt Plaisar, Baie Lazare, Caiman, Praslin Fond B’Offay/Nouvelle Decouvert watershed management) | 388269.34
| Output 1.2 Small-scale water storage and detention facilities designed and constructed or rehabilitated in critical waterways for communities to benefit from enhanced ecosystem functioning by forests (Mare aux Cochons, Mt Plaisar, Baie Lazare, Caiman, Praslin Fond B’Offay/Nouvelle Decouvert watershed control structures) | 242626.51
| Component 2 ECOSYSTEM-BASED ADAPTATION APPROACHES ALONG THE SHORELINES OF THE GRANITIC ISLANDS REDUCE THE RISKS OF CLIMATE CHANGE INDUCED COASTAL FLOODING | 139230.65
| Output 2.1 Ecosystem-based measures for flood protection on an urban shoreline | 79798.79
| Output 2.2 Ecosystem-based measures for flood protection and mitigating salt water intrusion in an agricultural and tourism development area | 59431.86
| Component 3 ECOSYSTEM BASED ADAPTATION MAINSTREAMED INTO DEVELOPMENT PLANNING AND FINANCING | 126589.09
| Output 3.1 Policy and legal frameworks for watershed and coastal climate change adaptation | 62854.1
| Output 3.2 Capacity Development for Ecosystem Based Adaptation Methods | 17897.91
| Output 3.3 Lessons learned and Knowledge Dissemination | 45837.08
| Component 4 Project Management | 125437.41
| TOTAL | 1022153
PLANNED EXPENDITURE SCHEDULE
List outputs planned and corresponding projected cost for the upcoming reporting period | ITEM / ACTIVITY / ACTION | PROJECTED COST | Est. Completion Date
| Output 1.1: Mare aux Cochons: Invasive species management programme (long-term action), wetland rehabilitation (long-term action) | 60000 | 2017-07-01
| Output 1.1: Mont Plaisir: invasive species management programme (long-term action) | 50000 | 2017-07-01
| Output 1.1: Baie Lazare: invasive species management programme (long-term action), assessing impacts of conflicts on water resources, stakeholder consultations, study of impact and design for wetland rehabilitation and initiation of rehabilitation programme (4 wetlands) | 50000 | 2017-07-01
| Output 1.1: Caiman watershed: invasive species management programme (long-term action) | 50000 | 2017-07-01
| Output 1.1: Praslin: completion of work on the tree nursery, vegetation management and rehabilitation (red soils area), mitigation of impacts of landslides on water resources | 80000 | 2017-07-01
| Output 1.1: Training on site rehabilitation with rehabilitation equipment | 78000 | 2017-07-01
| Output 1.2: Mare aux Cochons: renovation of downstream barrage, assessment of impacts of water abstraction by utility company | 105000 | 2017-07-01
| Output 1.2: Mont Plaisir: barrage renovation, assessment of potential for targeted water harvesting | 40000 | 2016-12-16
| Output 1.2: Baie Lazare: construction of additional barrages, study to determine water source protection zone, study on pollution from agriculture | 103500 | 2017-07-01
| Output 1.2: Caiman watershed: renovation of downstream barrage, assessment of potential for further abstraction | 40000 | 2016-12-16
| Output 1.2: Praslin: installation of new check dams as a response to fire risk | 50000 | 2016-12-16
| Output 1.2: Engagement of community based watershed management committees (long-term action), strategic water resources adaptation assessments, community-based watershed management plans, monitoring and evaluation | 110000 | 2017-07-01
| Output 1.2: Education and awareness materials | 40000 | 2016-12-16
| Output 2.1: NE Point: integrated shoreline management plan | 29000 | 2016-12-16
| Output 2.1: NE Point: hydrological study, wetland reprofiling | 43993 | 2016-12-16
| Output 2.1: NE Point: reef rehabilitation study and assessment of options for artificial reef structure | 100000 | 2017-03-01
| Output 2.1: Technical support, workshops and monitoring | 40000 | 2017-03-17
| Output 2.2: Anse Royale: development of integrated shoreline management plan | 30000 | 2016-12-16
| Output 2.2: Anse Royale: study of wetland function, implementation of reprofiling | 46500 | 2016-12-16
| Output 2.2: Anse Royale: shoreline rehabilitation, installation of bollards and start of replanting (long-term action) | 25000 | 2017-07-01
| Output 2.2: Anse Royale: monitoring equipment for salaination control measures, development of efficient irrigation system for farmers (explore co-financing and alternative water supplies) | 7500 | 2016-12-16
| Output 2.2: Equiment for shoreline rehabilitation | 32000 | 2016-09-16
| Output 2.2: Awareness raising activities and materials | 9000 | 2017-07-01
| Output 2.2: Technical and office support | 29600 | 2017-07-01
| Output 3.1: Watershed policy: analysis of institutional structures, needs analysis, review of planning practces related to watersheds, identificatin of financing mechanisms | 13000 | 2016-12-16
| Output 3.1: Technical support to policy development | 16600 | 2017-03-17
| Output 3.2: Training programmes: modules development (to be delivered mostly by UNISEY) | 9800 | 2017-07-01
| Output 3.2 Institutional Support for watershed committees | 30000 | 2017-07-01
| Output 3.3: Communications strategy: strategy development, materials, knowledge sharing | 30000 | 2017-07-01
| Output 3.3: Technical and office support | 36000 | 2017-07-01
| Output 4.1 Project management | 76500 | 2017-07-01 | Third tranch = $1,117,499
| TOTAL | 1460993 |  | Balance at end July 2017 = $343,494
ACTUAL CO-FINANCING (If the MTR or TE have not been undertaken this reporting period, DO NOT report on actual co-financing.)
How much of the total co-financing as committed in the Project Document has actually been realized?
Estimated cumulative actual co-financing as verified during Mid-term Review (MTR) or Terminal Evaluation (TE).
Add any comments on actual co-financing in particular any issues related to the realization of in-kind, grant, credits, loans, equity, non-grant instruments and other types of co-financing. (word limit=200)

## Procurement (hidden)
PROCUREMENT DATA
Please provide information for all contracts over $2,500 USD
Please provide the number of contracts under $2,500, signed during this reporting period: |  |  |  | 20
LIST OF CONTRACTS
List all contracts related to the project/program with signature dates
Contract Type | Agency / Contracted party | Contract Value/Amount (USD) | Signature Date | Payment to Date | Remaining Balance
Contractual services - individual (Project Manager) | Betty Seraphine | $26,933 (extension: one year) | 27th July 2016 (extension covering 1st July 2016 to 30th June 2017) | 26933 | 0
Contractual services - individual (Engineer - Hydrologist)) | Johan Esteban Mendez | $69,720 (extension: two years) | 23rd August 2016 (extension covering 15th August 2016 to 14th August 2018) | 30502.5 | 39217.5
Contractual services - individual (Community Engagement Specialist) (resigned 24th September 2016) | Betty Mondon | $18,200 (extension: one year) | 27th July 2016 (extension covering 1st February 2016 to 31st January 2017) | 11200 | $0.00 (contract terminated)
Contractual services - individual (Community Engagement Specialist) (new appointee) | Rajelle Barbe | $36,400 | 30th December 2016 (covering 1st January 2017 to 31st December 2018) | 8400 | 28000
Contractual services - individual (Scientific and Technical Advisor) | James Millett | $69,300 (extension: two years) | 14th February 2017 (covering period 1st March 2017 to 28th Februry 2019) | 14155 | 55145
Contractual services - individual (Driver) | Eldrick Adelaide | $14,445 (two years) | 24th August 2015 (covering period 24th August 2015 to 23rd August 2017) | 13055 | 1390
Contractual services - individual (Wetland clearing in Baie Lazare) | Unels Bristol | $3,703 | 4th August 2016 | $3,703 | $0.00
International consultant (Chainsaw training) | Matthew White | $22,567.36 | 22nd August 2016 | 22567 | 0
Contractual services - individual (Intern) | Stephanie Massy | $4,741 | 21st November 2016 | 4741 | 0
Contractual services - Individual (River re-profiling in Baie Lazare Station #1) | Pascal Octave - ProCleaning Agent | $3,926 | 16th November 2016 | 3926 | 0
Contractual services - Companies (Maintenance of invasive vegetation in the Monitoring Station #2 at Baie Lazare | Pascal Octave - ProCleaning Agent | $3,518 | 19th December 2016 | 3518 | 0
Contractual services - individual (Coral reef assessment at NEP) | Jude Bijoux | $22,500 | 21st December 2016 | 12800 | 9700
Contractual services - individual (Technical Advisory Group: support to forest rehabilitation) | Karl Fleischmann | $4,200 | 1st February 2017 | 4200 | 4200
Contractual services - Individual (Status Assessment and Proposed Management regime for Mare aux Cochons Ramsar site, Seychelles) | Dirk Lamberts | $9,970 | 27th February 2017 | 1994 | 7976
Contractual services - Individual (Forest Management in Praslin Catchment) | Serge Radegonde | $4,000 | 24th February 2017 | $4000 | $0.00
Contractual services - Individual (Forest Management in Praslin Catchment) | Bradley Agathine | $4,000 | 24th February 2017 | $4000 | $0.00
Contractual services - Individual (Forest Management in Praslin Catchment) | Steve Agricole | $4,000 | 24th February 2017 | $4000 | $0.00
Contractual services - Individual (Forest Management in Praslin Catchment) | Benny Moncherry | $4,000 | 24th February 2017 | $4000 | $0.00
Contractual services - Individual (Forest Management in Praslin Catchment) | Sylver Onezime | $4,000 | 24th February 2017 | $4000 | $0.00
Contractual services - Individual (Assisting community invovement in EBA Forest and Catchment rehabilitation) | Terence Vel | $3,000 | 3rd March 2017 | 3000 | 0
Contractual services - Individual (Forest Management in Baie Lazare Catchment) | Serge Radegonde | $3,911 | 12th April 2017 | 3911 | $0.00
Contractual services - Individual (Forest Management in Baie Lazare Catchment) | Bradley Agathine | $3,911 | 12th April 2017 | 3911 | $0.00
Contractual services - Companies (Creation of a gabion-filter structure for rock barrage) | Pro-Cleaning, Pascal Octave | $48,962 | 7th June 2017 | 14815 | 34147
Contractual services - Companies (provision of rocks for gabion) | BV and Sons, Brian Victor | $53,407 | 5th June 2017 | 17284 | 36123
Contractual services - Companies (wetland reprofiling at Baie Lazare) | BV and Sons, Brian Victor | $86,111 | 7th June 2017 | 14815 | 71296
Contractual services - individual (forest management Caiman) | Serge Radegonde and Bradley Agathine | $8,370 | 23rd June 2017 | $0.00 | $8,370.00
Contractual services - Companies (forest management at Baie Lazare) | Ecofix: Unels Bristol and Steve Agricole | $8,220 | 23rd June 2017 | 0 | 8220
BIDS
List all bids for each contact signed with date of open call and winning bid
CONTRACT & Procurement Method | Submitted Bids | Bid Amount (USD) | Winning Bid Amount (USD) | Selection Justification for the Winner
Wetland clearing in Baie Lazare, direct contact, August 2016 | Unels Bristol | 3703 | 3703 | Direct contracting of individual recently certified under project training scheme
Chainsaw training, amendment to previous contract (see last PPR), August 2016 | Matthew White | 22567 | 22567 | Extension to previous contract for the LANTRA certified trainer (addition to former TORs)
Internship, direct approach and approval by GOS, August 2016 | Stephanie Massy | 4741 | 4741 | Dircct contracting of individual formerly working in association with the project as a Volunteer while completed MSc degree
River re-profiling in Baie Lazare Station #1, direct contact, November 2016 | Pascal Octave - ProCleaning Agent | 3926 | 3926 | Direct contracting of individual living in area of operations
Maintenance of invasive vegetation in the Monitoring Station #2 at Baie Lazare, direct contact, December 2016 | Pascal Octave - ProCleaning Agent | 3518 | 3518 | Direct contracting of individual living in area of operations
Coral reef assessment at NEP, call for proposals, 21st October 2016 | Jude Bijoux | 22500 | 22500 | Sole bid. Judged by TEC as sufficient capacity to do the work.
Technical Advisory Group: support to forest rehabilitation, direct contact, from May 2016 | Karl Fleischmann | 4200 | 4200 | Direct contracting of Technical Advisory group member to provide specific inputs
Status Assessment and Proposed Management regime for Mare aux Cochons Ramsar site, international job advert, January 2016 | Dirk Lamberts | $9,970 | $9,970 | Technical evaluation of bids received through UNDP Jobs. 11 applications, 5 shortlisted (indicated opposite). Selection based on epxerience and competence (70%) and financial bid (30%)
| Guido Corno | no bid
| Paul Dubowy | 25782
| Richard Cuthbert | 13100
| Stephen Parr | 6550
Contractual services - Individual (Forest Management in Praslin Catchment), directr contracts, multiple individuals, 22nd Feburary 2017 | Serge Radegonde | 4000 | $4000 x 5 | Individual contracts awarded to staff who had undergone chainsaw training (see previous contract awarded to Matthew White). Contract amount based on daily rates and fixed by PCU.
| Bradley Agathine | 4000
| Steve Agricole | 4000
| Benny Moncherry | 4000
| Sylver Onezime | 4000
Contractual services - Individual (Assisting community invovement in EBA Forest and Catchment rehabilitation), direct contract, March 2017 | Terence Vel | $3,000 | 3000 | Direct contracting of individual working with UNISEY in the area of operations
Contractual services - Individual (Forest Management in Baie Lazare Catchment), direct contract, April 2017 | Serge Radegonde | 3911 | $3,911 x 2 | Individual contracts awarded to staff who had undergone chainsaw training (see previous contract awarded to Matthew White). Contract amount based on daily rates and fixed by PCU.
| Bradley Agathine | 3911
Contractual services - Companies (Creation of a gabion-filter structure for rock barrage), field capacity assessment followed by direct contract, June 2017 | Pro-Cleaning, Pascal Octave | 48962 | 48962 | Field assessment was undertaken of capacity of companies in the project area (human resources, suitable construction and transport equipment, etc.). As companies with sufficient reources existed within the targeted watershed community, it was considered appropriate for the contracts to be awarded there (cost effective). Individual contracts were based on the companies' particular areas of expertise.
Contractual services - Companies (provision of rocks for gabion), field cpcity assessment followed by direct contract, June 2017 | BV and Sons, Brian Victor | $53,407 | $53,407
Contractual services - Companies (wetland reprofiling at Baie Lazare), field cpacity assessment followed by direct contract, June 2017 | BV and Sons, Brian Victor | $86,111 | $86,111
Contractual services - individual (forest management Caiman), national consultancy, call for proposals, 29th May 2017 | Serge Radegonde and Bradley Agathine | $8,370 | 8370 | TEC found little to differentiate the teams as they were all trained at the same time by the same trainer (Matthew White). Contract award was on the basis of cheapest financial bid.
| Ecofix: Unels Bristol and Steve Agricole | 10031
Contractual services - Companies (forest management at Baie Lazare), call for proposals, 29th May 2017 | Ecofix: Unels Bristol and Steve Agricole | 8220 | 8220 | As above. TEC determined it was most effective to give the second award to the alternate team, although their bid was higher, as the contracts were to run simultaneously.
| Serge Radegonde and Bradley Agathine | 6741
Name of Contract , Procurement Method, if appicable Date of Call

## Risk Assesment
RISK ASSESMENT
IDENTIFIED RISKS
List all Risks identified in project preparation phase and what steps are being taken to mitigate them
Identified Risk | Current Status | Steps Taken to Mitigate Risk
Policy makers prioritize economic benefits over sustainable and resilient ecosystems | Medium risk | On a positive note, a paradigm shift in the legal framework of the Environment sector occurred during the current reporting period, with the drafting by environment policy makers of a Water Policy for the Seychelles. The Ministry of Environment, Energy and Climate Change spearheaded the process through an Integrated Water Resource Management (IWRM) donor-funded project, which worked closely with the current project and other stakeholders. The Water Policy was submitted to and approved by Cabinet Ministers in July 2017 and the drafting of the legislation will follow. At the systemic level, supporting the above, the EBA project is aiming to draft watershed management regulations with an applied EBA approach. On a less positive note, pressure for building land has caused Government to cancel a previous ban on constriuction above the 50 metre contour on Praslin and La Digue islands, thereby allowing for further development in lower watersheds on tbose islands. Pressure to allow similar construcions in lower watersheds on Mahe, including inside nominated protected areas (or shifting the boundary of the protected areas upars) is likely to grow. Government has committed to releasing 100s of additional land parcels over the next years. The Ministry of Habitat, Infrastructure and Land Transport (MHILT, formerly MLUH) is reviewing the Land Use Plans developed under a GEF project in 2013-14, but never approved, to consider these type of land issues but hopefully to regulate development to some degree. This LUP review exercice is opportune as the EBA project is collecting data to map the 5 water catchments and continues to strive for the preservation of watershed protected zones (with a strengthened legal framework under the Water Policy). The resort development in the upper watershed of Caiman catchment, one of the project areas, advanced to EIA stage but was halted by Government pending review. The project has met with the developers, but remains neutral and awaits the decision of Government concerning whether the project will proceed (in which case the project may assist in mitigatory actions identified by the EIA). | ```````````````````````````````````````````````````````````````````````````
Extreme natural disasters affect confidence of local community to adaptation measures | Medium risk. | Seychelles suffered the impacts of another El Nino event in 2016 with mass coral bleaching, as a result of the above-average ocean temperatures. A report was disseminated to stakeholders to raise awareness about the associated impacts on the reefs and potentially on livelihoods through loss of important fish breeding areas, etc. A further bleaching in early 2017 was narrowly averted by a sudden change in weather. Nonetheless, damage to coral reefs around Mahe and Praslin is extensive, with live coral losses up to 90%. Through training programs for watershed committees, the project has initiated participatory processes for integrated watershed management at the community level. The local community have better understood the fundamental principles of an EBA approach to managing the adverse effects of climate change. The adaptive management approach of the project has built their confidence in the efficacy of adaptation measures. This has so far focused primarily on addressing impacts of changing weather conditions in watersheds, but simil;ar committees need to be built and approac hes adopted to address EBA issues in coastal areas (noting that recent data collected by the project in regard to coastal proceeses at North-east Point have indicated a 10 cm rise in high tide levels over the last 20 years).
Environmental impact of structures in watercourses and reefs | Retired. | Regulations for EIA has been updated under the revised Environmental Protection Bill approved in September 2016. The revised legislation will more closely regulate the construction of intended structures in water sources, where necessary, in particular those that will require an environment impact assessment. In the project context, biodiveristy assessments are conducted in project areas prior to designing physical interventions such as wetland reprofiling and barrages. The project works in collaboration with partners and the community to determine appropriate structures to be built, as well as to help mitigate water pollution in areas affected by unforeseeen agricultural or residential development from neigbouring plots.
Methods of ecosystem rehabilitation need better testing for hydrological impacts | Low risk. | The project is working in collaboration with the University of Seychelles, using scientifically sound methods of rehabilitation for forests which are expected (on the basis of existing scientific knowledge and on-going testing) to have positive impacts on ecosystem services and water retention. The project is undertaking pilot forest and wetland rehabilitation projects to record, monitor and analyse hydrological data. Monitoring is supported by the university students, with particular analysis conducted on hydrological impacts, with expert knowledge provided by the project Technical Advisory Group.
Adaptation measures increase inequity | Low risk. | The project promotes social inclusion and equity. Four watershed committees have been set up for the project watershed sites. This ensures that community interests are represented, and that communities engage in decision-making in relation to adaptation interventions of the project. One more watershed committee will be set up during 2017. Adaptation measures implemented through forest and wetland rehabilitation under the project are designed to achieve sustainable management and to deliver multiple benefits for communities. The rehabilitation components of the project creates job opportunities through contractual services for the communities, encouraging them to participate in the rehabilitation and management of their water and forest resources.
The cost of the proposed measures may be higher than expected. | Low/medium risk. | Estimating the cost of adaptation is a complex matter. The scale of required interventions is in some cases quite major. Studies conducted by the project on the feasibility of building a check dam or water control structure in the Mare Aux Cochons watershed indicate that while a structure is economically feasible, and will have a major positive impact on water flows to communities in the catchments, the costs will far exceed the financial resources of the project. The geo-technical and financial feasibility studies conducted by the project act to advise the Government, through the Public Utilities Corporation and Seychelles National Parks Authority, to provide the required information to consider investment in constructing the barrage, if considered necessary. Similarly, a possible intervention at North East Point will be determined through further community consultation, following on from an assessment of the status of the reef flats (which revealed the reef flats to be highly degraded with very little structure to assist in dampening wave action). Mitigatory structures such as a breakwater to reduce sediment erosion will be considered at a later stage, but will require significant Government investment to be effective.
Critical Risks Affecting Progress (Not identified at project design)
Identify Risks with a 50% or > likelihood of affecting progress of project
Identified Risk | Current Status | Steps Taken to Mitigate Risk
Private lands identified for potential rehabilitation within the catchment areas may not be available if land owners refuse to approve the rehabilitation works or if it is unclear who owns the land. | Low Risk | This risk has been reactivated since the project has identified additional privately-owned sites in the Baie Lazare watershed suitable for both forest and wetland rehabilitation actions. The project team has met with various landowners to discuss the principles of the EBA approach of the project, to advocate the importance of rehabilitating forests on private land. Some landowners have subsequently granted authorisation for the restoration works while others have stated that their lands are planned for future development. Where permission is not given, the project has sought to identify adjacent Government land for restoration.
The legislative framework does not adequately support adaptation interventions | Medium Risk | A new Water Policy has been drafted for the Seychelles, to provide an appropriate legal, regulatory and institutional framework for the optimal integrated management of the country’s water resources. The policy gives the approach to be adopted by Government to ensure that water resources are protected, used, developed, conserved, managed and controlled through appropriate means, therby ensuring sustainable use of the resources. The policy statement also affirms that the responsible authorities will take appropriate measures to rehabilitate, sustainably manage and protect catchment forests. Through this policy, there is provision for forests to be rehabilitated where necessary and it advocates that catchment forests should be afforded legal protected status where feasible. The Policy now needs to be carried forward into Law, however, and there is as yet no indication of when this might occur or how much of the policy will be adopted as law and how it will be enforced. The revised Environmental Protection Act 2016 has still not been followed up with regulations, although these are in the process of being drafted. There is no movement on the Physical Planning Act (replacing the former Town and Country Planning Act) and the Land Use Plans that are central to the PPA remain under review.
River Committee not effective, lack of leadership and interest from PUC. | Medium Risk | The project hydrologist is a now a member on the Rivers Committee and works in collaboration with PUC to manage the rivers in the five project water catchments. The Integrated Water Resource Management (IWRM) project is proposing an external APEX body that would coordinate water resource management in Seychelles. PUC would retain its utilities function but would not be called upon to lead policy implementation or regulatory functions.
Risk Measures: Were there any risk mitigation measures employed during the current reporting period? If so, were risks reduced? If not, why were these risks not reduced?
Add any comments relevant to risk mitigation (word limit = 500)
A strengthened policy and legal framework for the water sector has been developed through the IWRM donor-funded project with the collaboration of this project and other stakeholders. The Water Policy has been approved by the Cabinet of Ministers and will be followed up during the next reporting period with supporting legislation. The EBA project had considerable input into the policy through participation in stakeholder forums to asist the drafting. The project will continue to assist in drafting the follow-up legislation, and also in collaborating with the Government to include protected water catchment zones in revised Land Use regulations, and in piloting community-led watershed management approaches. Combined, these measures are aimed at mitigating the ever-present risk of further development of watershed areas and coastal wetlands.

## Rating
RATING ON IMPLEMENTATION PROGRESS
For rating definitions please see bottom of page.
| Progress on Key Milestones |  | Expected Progress |  | Progress to Date | Rating
Project Manager/Coordinator: | Inception phase; Inception commenced in September 2014. The Inception Workshop was held on 30th October 2014. There were 31 participants including the UNDP TA for AF projects. The Inception Report was produced in November 2014. |  | Completed. |  | The inception worshop was completed and report was submitted. | S
Component 1: Ecosystem-based adaptation approach to enhancing freshwater security and flood control in Mahé and Praslin under conditions of climate change
| Output 1.1 Management and rehabilitation of critical watersheds to enhance functional connectivity and the resilience of these areas to climate change and reduce water scarcity and watershed flooding (Mare aux Cochons, Mt Plaisar, Baie Lazare, Caiman, Praslin Fond B’Offay/Nouvelle Decouvert watershed management) |  | Conduct assessments of the five watershed areas. Start vegetation and invasive species management programmes in the watershed areas. Complete development of the Praslin tree nursery and the start of vegetation management and replanting programme on Praslin. |  | Mare aux Cochons Watershed: A first report was submitted on the biodiversity assessment and rehabilitation potential of forests in the Mare aux Cochons catchment.The report concluded that there are remarkable flora with several irreplaceable sites for biodiversity in this watershed. Invasive species and potential rehabilitation sites were prioritized, and the consultants finalised mapping of stream networks and wetlands showing the gapsin exploration A second report on the status assessment and proposed management regime for Mare Aux Cochons Ramsar Site was conducted by another international consultant with the aim of informing decision-making for EbA intervention in that part of the watershed. The report included the identification of key biodiversity interest values of the site. Mont Plaisir and Caiman watersheds:The Mont Plaisir and Caiman watershed committees have been set up. The committee members have explored their watershed areas and are now involved in the decision making process. They have advocated the cleaning up of the area to promote the resilience of their water catchment. A public consultative meeting was held in the Caiman district to educate residents about the EBA methods in relation to climate change adaptation. A first phase forest rehabilitation will start in July to rehabilitate a parcel of 2.94 ha of forest in the Caiman catchment through the selective removal of invasive vegetation whilst leaving at least 80% of the canopy intact. The work will be implemented in accordance with the standard method devised under the EBA project. Fond B'Offay and Nouvelle Découverte Watershed: The local NGO TRASS is continuing forest rehabilitation on Praslin. The first phase of the project has a time frame of 2 years (2016-2017) and targets about 20 ha for rehabilitation, including 10 ha in the first year. However, following several trains of work involving different rehabilitation models, TRASS and the project agree that it may not be possible to achieve the targeted area of rehablitated forest, due to the current pace of reforestation in the very difficult terrain. There are limited workers on the ground and the nursery also has limited storage capacity, with space for seedlings for only 5 ha. Two teams of workers have been subcontracted to start the planting of native stocks in the strips that had been cleared from invasive species. Baie Lazare Watershed: Pilot forest rehabilitation in secondary forest by thinning invasive trees is well underway, with several work packages completed or on-going. The thinning required the careful removal of alien shrubs e.g. Coco plum and the removal of alien trees using methods that will not disrupt soil structures or damage native vegetation. Two phases of training in Chainsaw operation and forestry management, conducted by international LANTRA accredited experts, have facilitated the forest rehabilitation works in Baie Lazare and other catchments. | S
| Output 1.2 Small-scale water storage and detention facilities designed and constructed or rehabilitated in critical waterways for communities to benefit from enhanced ecosystem functioning by forests (Mare aux Cochons, Mt Plaisar, Baie Lazare, Caiman, Praslin Fond B’Offay/Nouvelle Decouvert watershed control structures) |  | Conduct assessments of the 5 watersheds to identify existing barrages in need of repair or identify potential sites for constructing new water storage facilities. Conduct an assessment of water conflicts between water users in the Baie Lazare watershed area to assist in the management of the water resources in the future. Conduct preparations for feasibility studies to erect check dams in the project watersheds. |  | Discussions are ongoing with the Public Utilities Corporation (PUC) regarding the various project interventions as PUC is required to approve any constructions along rivers and water catchments. Mare aux Cochons watershed: A geotechnical and financial feasibility study of a proposed wetland creation in the "La Drisse" area in the Mare aux Cochons watershed was conducted and a report was submitted to the Government and PUC to assess various scenarios in relation to the creatiion of the barrage. Rapid fauna and flora biodiversity assessments were conducted in the area to assist the Government to make informed decisions. Mont Plaisir / Caiman: Water resource assessment and mapping of areas identified for rehabilitation have been completed, as well as the identification of polluting sources. Progress has been somewhat slow due to emerging land use issues at the Caiman site which need to be resolved (a major resort development in the upper watershed was originally approved by Government but has since been halted). Baie Lazare: Progress to date include completion of water resources mapping and topographic surveys and site identification for water monitoring stations. Data collection is ongoing through a collaboration with the University of Seychelles. Praslin: Water resource assessment has been completed and 26 potential sites have been identified for construction of small water dams. | S
COMPONENT 2: Ecosystem-based adaptation approaches along the shorelines of the granitic islands reduce the risk of climate change induced coastal flooding
| Output 2.1 Ecosystem-based measures for flood protection on an urban shoreline (North-east Point) |  | Conduct coastal studies on the North East Point shoreline to facilitate the drafting of an integrated shoreline management plan and to inform wetland and reef rehabilitation and beach berm enhancement. |  | A report has been completed on coastal processes at North East Point. The key output of the study was to identify and quantify the existing coastal process and how they affect the current sediment transport within North East Point, and how these relate to climate change resilience strategies. Aquadopp current meters and wave recorders were deployed at two locations offshore from the beach during the North-west monsoon and South-east monsoon to capture the different wave climates. Based on long-term tide gauge data, local average high tides have risen by ~10 cm over the past 20 years. Numerical modelling was undertaken to characterise the physical coastal processes driven by waves, tides, wind and atmospheric pressure. The report also considers the effects of modifications to the reef environment on the bed shear stress. Based on the modelling, it can be seen that the northward direction of sediment transport from the reefs located south of North East Point has been eliminated owing to the changes between the 1978 and 2016 bathymetry. This suggests that areas of coral reef which were likely sources of sediment for the beaches of NE Point have been cut off and are no longer able to provide sediment to naturally re-nourish the beaches there. The primary findings are that the beach at North East Point undergo marked seasonal fluctuations on beach width. These variations are driven by monsoonal wind and wave conditions. In conclusion, local sea levels have steadily risen at rates greater than global averages with potentially significant coastal impacts. The project is now assessing means of addressing these potential impacts. As a first phase, an assessment of the coral reefs is underway and a study of the potential for reef rehabilitation will comemnce later in 2017. | S
| Output 2.2 Ecosystem-based measures for flood protection and mitigating salt water intrusion in an agricultural and tourism development area (Anse Royale) |  | Raise awareness about how relevant stakeholders can undertake ecosystem-based measures for flood protection and mitigating salt water intrusion in the agricultural coastal plains of Anse Royale. Conduct studies on the Anse Royale shoreline to facilitate the drafting of an integrated shoreline management plan to inform wetland and reef rehabilitation and beach berm enhancement. |  | The project works in collaboration with the Seychelles Agricultural Agency (SAA) and the United Nations IAEA to hold annual training workshops to build the capacity of local SAA staff in actions to reduce salinity intrusion in coastal farming areas. The project interventions include activities to monitor electrical conductivity driven by the sodium ion as a means of tracking salt intrusion. GIS licenses and GPS equipment were donated to the Seychelles Agricultural Agency to facilitate the mapping of the agricultural zone of the Anse Royale district. Spatial analysis of the data will be conducted in order to assess changes over time. Further training on how to operate the GIS license will be conducted in July 2017 . An international expert is currently in Seychelles to conduct field sampling with the SAA staff and EBA project for analysis of Isotopes 18O and 2H. The purpose is to assess the origin of salinity of the coastal plateau of Seychelles and strengthen the institutional capacity of the Agencies striving to reduce salinity. The use of stable isotope tracers is deemed an effective way in which we can confirm movement of seawater intrusion. This can confirm whether the salinity of the coastal irrigation system is due to seawater and how the intrusion is occurring, prpoviding baseline data to determine where and how to address the issue. | S
Component 3: Ecosystem based adaptation mainstreamed into development planning and financing
| Output 3.1: Policy and legal frameworks for watershed and coastal climate change adaptation |  | Conduct an analysis of institutional structures to identify policy gaps. |  | The policy and legal frameworks for watershed and coastal climate change adaptation are being developed through an ongoing process and combined effort of several IWRM/EBA projects in Seychelles. The national water policy wasn developed in early 2017 and was approved by the Cabinet of Ministers in early July 2017. This is a major milestone for the project. Watershed protection is recognized as an important aspect within the new policy for Seychelles. The drafting of the legislation for a new Water Act will include the mandate and the role of proposed river basin committees as well as the official delimitation through GIS mapping of watersheds. The existing watershed committees created under this project can serve as pilots to show the benefits of such an approach while the legislation is being developed. All laws pertaining to the protection of wetlands, forests, water catchents and coastal areas are being revised leading to the Water Act. | HS
| Output 3.2 Capacity Development for Ecosystem Based Adaptation Methods |  | Capacity development for watershed committees and other project stakeholders. |  | Two more Watershed Committees have been successfully set up during this reporting period, making a total of 4 committees operating in 4 watershed districts. These comprise the Baie Lazare Watershed Committee, Praslin Watershed Committee, Caiman Watershed committee and the Mont Plaisir Watershed Committee. A new commmunity engagement spcecialist has been recruited and is spearheading the coordination of these committees. A series of workshops commenced in May 2017 to develop the capacity of community members on these watershed committees. Good Governance training was organised for the watershed committees on 8 July 2017 based on effective good governance and development of advocacy skills for a positive change in the communities. A plant identification training was conducted during 18-29 July 2016 and a guide booklet was prepared to facilitate the delivery of the training. A foundation course was also delivered to support the implementation of the forest rehabilitation programme. Further training was conducted on management of non-native vegetation. The project team and key stakeholders attended a training workshop on computer-based assessment of forest light climates at the University of Seychelles: participants learnt that forest light plays a crucial role with regards to the susceptibility of environments to invasion by alien plant species and about the correlation between high levels of forest light and enhanced plant invasions. The project purchased a 360-degree fish-eye lens and camera to be used by the University in continued assessment of the forest light climate to demonstrate the effect of vegetation rehabilitation in the project target sites (extending post-project). | HS
| Output 3.3 Lessons learned and Knowledge Dissemination |  | Development of a communications strategy and dissemination of project initial results |  | A strategic community engagement action plan was produced by the communication engagement specialist to actively engage the community in the project. The findings of an research study by two university intern students have been disseminated to key partners and stakeholders. The research focused on two important perspectives for characterizing and evaluating a water catchment area: aspects of the vegetation characterized and evaluated in the forest system and the human activities impacting water provision and retention. The thesis provides a baseline for a more sustainable management of the Baie Lazare water catchment area and has informed the drafting of a report on the assessment of the ecosystem services and vegetation rehabilitation in the Baie Lazare watershed. The next steps are to develop an appropriate vegetation rehabilitation programme, design an action plan to improve the ecosystem services of the water catchment, mitigate the problems regarding human impacts and water quality and availability by assigning responsibilities and concrete action to stakeholders and communities, and, finally, monitor the outcomes and revise present aspects of research according to the achievements. This serves as a model for other catchments and is a key element of the communications approach. | S
S
Please Provide the Name and Contact information of person(s) reponsible for completeling the Rating section
| Name: | Betty Seraphine (Project Manager), Andrew Grieser Johns (Programme Coordinator)
| Email: | b.seraphine@pcusey.sc; a.grieserjohns@pcusey.sc
Please justify your rating. Outline the positive and negative progress made by the project since it started. Provide specific recommendations for next steps. . (word limit=500)
The Satisfactory rating maintained for this reporting period reflects significant progress achieved by the EBA project. The project has achieved two key milestones. Firstly, four watershed committees with gender balance are now in place. This has been faciliated with the recruitment of a new Community Engagement Specialist who has brought new dynamism to the community engagement process. The four committees are actively involved in the project as they learn how to become stewards of their water resources. The project has further developed their capacity by training them in good governance and how to develop advocacy skills as community-based organisations. Several trainings have been conducted to strengthen the institutional and individual capacity. Secondly, the project collaborated with other IWRM and EBA projects in the development of a national water policy approved in early July 2017 by the Cabinet of Ministers. The development of the legal framework is ongoing and the drafting of the legislation for a new Water Act will be the next step. The watershed committees established by the project are a key element in piloting devolved watershed management approaches under the new Policy and Act. A memorandum of understanding was signed between the MEECC and the University of Seychelles to facilitate long-term collaboration with this project and with MEECC post-project. The project benefits from collaboration with Professor Karl Fleischman who has designed a scientific methodology for piloting forest rehabilitation in Seychelles, together with the University of Seychelles, ETZ Zurich and the project technical advisor. This MOU will enable the University to coordinate follow-up assessments, monitoring of the watershed vegetation in the pilot Baie Lazare watershed, the regular testing of the water quality through 10 quality parameters and the regular monitoring of the water-flow (much of the monitoring performed by students of the University). In addition, the project benefited from a drone-assisted vegetation monitoring of 10 intensive monitoring plots selected in 2016 provided as cofinancing by Save our Seas Foundation. This will offer an additional baseline for assessing post-rehabilitation vegetation changes and facilitate forest monitoring. All of these actions are building towards long-term (post-project) monitoring of rehabilitation success, which is of course a longer-term process than a project lifetime. An abstract paper and poster were prepared by the project technical advisor in collaboration with Professor Fleischman and an intern student and have been delivered at an Island Invasive Species Conference in Scotland, giving the project international exposure. In terms of capacity building, the project has held a series of training courses in Plant Identification Course for Forest rehabilitation, and in forestry management and chainsaw operation (delivered by professional LANTRA trainers) which has increased the number of Seychellois workers able to undertake responsible forestry operations. These private sector workers are now bidding for and being awarded contracts under the project to support the rehabilitation programme of the project. Several biodiversity assessments have been conducted and reported by the project which demonstrate the use of scientific data, local knowledge and social science information to assist the project team and implementing agencies in making informed decisions about EBA approaches to be applied in watersheds and coastal areas.
| Progress on Key Milestones |  | Expected Progress |  | Progress to Date | Rating
Implementing Agency | Component 1: Ecosystem-based adaptation approach to enhancing freshwater security and flood control in Mahé and Praslin under conditions of climate change
| Output 1.1 Management and rehabilitation of critical watersheds to enhance functional connectivity and the resilience of these areas to climate change and reduce water scarcity and watershed flooding (Mare aux Cochons, Mt Plaisar, Baie Lazare, Caiman, Praslin Fond B’Offay/Nouvelle Decouvert watershed management) |  | It was expected by the end of June 2017, that Mare aux Cochons, Mont Plaisir, Baie Lazare, Caiman watershed: planning and start of invasive species management programmes. On Praslin: completion of nursery, start of vegetation management and replanting programme was expected to be ongoing. Specific Inventory works conducted by end of reporting period |  | There has been much progress in the management and rehabilitation of the 4 watersheds, comprising of Baie-Lazare and Praslin, with recent activities being conducted in the Caiman and Mont Plaisir watersheds. The project has developed a number of partnerships through this initiative, with a Memorandum of Understanding signed between the Ministry of Environment and the University of Seychelles. This collaboration allows the university students to participate in the data collection, analysis and interpretation for the project, especially in relation to flow monitoring of the rivers. The project team continues with both forest rehabilitation and is privileged to have Dr. Karl Fleischman working in association with the project to apply a sound, scientific methodology to pilot forest rehabilitation in the Baie Lazare watershed. Successful implementation could offer potential replication in the other watersheds. A Memorandum of Understanding has been signed between the Ministry of Environment and the NGO TRASS to undertake forest rehabilitation in Nouvelle D'ecouverte and F'ond Boffay in the Praslin watershed. The main limitations are mainly logistical difficulties encountered due to distance between islands- however the project team applies adaptive management and ensure activities are carried out as feasible to mitigate any potential risks or delays to project implementation. | S
| Output 1.2 Small-scale water storage and detention facilities designed and constructed or rehabilitated in critical waterways for communities to benefit from enhanced ecosystem functioning by forests (Mare aux Cochons, Mt Plaisir, Baie Lazare, Caiman, Praslin Fond B’Offay/Nouvelle Decouvert watershed control structures) |  | Conduct assessments of the 5 watersheds to identify existing barrages in need of repair or identify potential sites for constructing new water storage facilities. Conduct an assessment of water conflicts between water users in the Baie Lazare watershed area to assist in the management of the water resources in the future. Conduct preparations for feasibility studies to erect check dams in the project watersheds. Mare aux cochons, Mont Plaisir, Caiman watershed: assessment of needs for renovation of existing barrages completed Baie Lazare: assessment of water conflict issues, planning for additional barrages completed Praslin: assessment of need for new check dam completed |  | Several small-scale water storage and retention structures are being constructed or enhanced in the Baie Lazare watershed, which is being used as a pilot district for the project. A v-notch weir and barrage is being constructed using gabions at the largest upland wetland in the Baie-Lazare watershed. Permissions were sought from the Government and biodiversity assessments were conducted prior to the commencement of the work. Wetland enhancement have been done in several locations in Baie-Lazare and will be replicated in other watersheds. Several water river monitoring stations have been set up by the project and the project hydrologist is working with university students to do his monitoring and evaluation, and compilation of data sets to measure the indicators.
Component 2: Ecosystem-based adaptation approaches along the shorelines of the Granitic Islands reduce the risks of climate change induced coastal flooding
| Output 2.1 Ecosystem-based measures for flood protection on an urban shoreline (North-east Point) |  | Completion of coastal studies on North East Point Shoreline and drafted Integrated Shoreline Management Plan |  | The expert studies from the eCoast company on the Coastal Processes for north East Point has been completed and the numerical model has been undertaken. The resarch findings gives a wider understanding of the impacts of sea level rise and the sand dynamics at North East Point and how this can affect the community. Interaction with the district authority and district council is ongoing. The project team has displayed good collaboration with the community in all 4 watersheds that have currently benefitted from an existing watershed committee. The Government district authorities are playing active roles in raising awareness and building the capacity of stakeholders to adopt acosystem-based adaptation measures are applied for flood control. | S
| Output 2.2 Ecosystem-based measures for flood protection and mitigating salt water intrusion in an agricultural and tourism development area (Anse Royale) |  | Raise awareness about how relevant stakeholders can undertake ecosystem-based measures for flood protection and mitigating salt water intrusion in the agricultural coastal plains of Anse Royale. Conduct studies on the Anse Royale shoreline to facilitate the drafting of an integrated shoreline management plan to inform wetland and reef rehabilitation and beach berm enhancement |  | The collaboration with Seychelles Agricultural Agency (SAA) and IAEA is ongoing. The project donated equipment and GIS license to facilitate the works of the Agency in asssiting the project to reduce farm pond salinity on the coastal agricutlural plains of Anse Royale. The project is mandated to collaborate with local institutions and partners to develop the institutional capacity of government and communities to address rehabilitation needs. One of the aim is to manage the ecosystems to ensure their resilience is a critical barrier to advancing ecosystem based approaches to climate change risk management. Several training workshops have been conducted with the SAA and GIS equipment have been donated by the project to ensure that the capacity of the institution is further developed to assist the project in achieving the reduction of soil and water salinity in the coastal plains of Anse Royale. The project is also promoting to implement concrete ecosystem-based adaptation measures to deliver saltwater intrusion protection and mitigation at Anse Royale.
Component 3: Ecosystem based adaptation mainstreamed into development planning and financing
| Output 3.1: Policy and legal frameworks for watershed and coastal climate change adaptation |  | The drafting, submission and approval of a water management policy for watershed areas. |  | The Policy frameworks for watershed and coastal climate change adaptation has been developed and the development of the legal framework is an ongoing process. The national water policy has been developed and approved by the Cabinet Ministers early July 2017. This target for the project has been partly attained. The policy development was coordinated by an IWRM project working in partnership with the EBA project. Watershed protection is recognized as an important aspect of the new policy for Seychelles. The drafting of the legislation for a new Water Act will include the mandate and the role of proposed river basin committees as well as the official delimitation, GIS mapping of watersheds. The existing watershed committees created under the Adaptation Fund project can serve as pilots for now to show the benefits of such an approach while the legislation is being developed. All laws pertaining to the protection of wetlands, forests, water catchents and coastal areas are being revised in the Seychelles. The environemnt Protection Bill was finalised and approved. | S
| Output 3.2 Capacity Development for Ecosystem Based Adaptation Methods |  | Capacity development for watershed committees and other project stakeholders. |  | Continuous training and support were provided for the watershed committees. The committee members benefit from capacity-building activities organised by the project to equip and empower them to manage their water catchments. The most recent workshop was undertaken on Good governance to teach them how to develop a set of skills that will enable them to become active players in the stewardship of their water resources. The project is ensuring that they develop effective advocacy skills so that the communities residing in the project watersheds can play a role in decision-making and promote inclusiveness in the development of the legal framework. The intern students sent by the University of Seychelles assist the project by conducting research and monitoring. This provides an opportunity for knowledge sharing and capacity-building in collaboration with University of Seychelles.
| Output 3.3 Lessons learned and Knowledge Dissemination |  | Development of a communications strategy |  | The communication strategy was developed by the Community Engagement Specialist. The project has learnt many valuable lessons in particular when handling private land owners and private contractors. The risks associated with community and public engagement has to be mitigated and eliminated through adaptive management.
S
Please Provide the Name and Contact information of person(s) reponsible for completeling the Rating section
| Name: | Roland Alcindor
| Email: | roland.alcindor@undp.org
| Progress on Key Milestones |  | Expected Progress |  | Progress to Date | Rating
Other | Component 1: Ecosystem-based adaptation approach to enhancing freshwater security and flood control in Mahé and Praslin under conditions of climate change. |  |  |  | A Memorandum of Understanding was signed between the University of Seychelles and the EBA Project. Professor Karl Fleischman developed a scientific methodology to inform the forest rehabilitation component of the project in collaboration with the project technician and the University of ETH Zurich. An assessment of the ecosystem service and vegetation rehabilitation of the Baie Lazare watershed was conducted in collaboration with the University of Seychelles and University of ETH Zürich of Switzerland. Ten permanent vegetation-monitoring sites were established in the Baie Lazare watershed as part of the Ecosystem based Adaptation Project (EbA) on the vegetation rehabilitation of watersheds on Mahé. The survey aimed in a first phase at providing a quotable, repeatable baseline for the vegetation rehabilitation and a methodology for the post-rehabilitation monitoring (quality assurance) in the Baie Lazare water catchment Some parameters were set as important tools for the actual vegetation rehabilitation and for the assessment of post-rehabilitation changes. These included 1. the prominence and importance (species dominance based on the DBH stem area in m2/ha) of a particular tree species at landscape level, 2. (II) the tree density, (III) indicators for biodiversity at stand level, (IV) indices for forest succession by comparing PVs (landscape level) and abundance (stand level) of adult trees versus juveniles (i.e. juveniles likely to become adults in a next fertile tree generation), (V) quantifiable and repeatable (!) protection values of a forest site, along with vegetation quality indices as performed at the Tea Tavern Glacis and at Val d’Endor 2016, (VI) invasion patterns and the magnitude of the invasiveness of a particular plant species in a particular area.
| Component 2: Ecosystem-based adaptation approaches along the shorelines of the Granitic Islands reduce the risks of climate change induced coastal flooding. |  |  |  | The project acknowledges that coastal ecosystems have an important role to play in climate change resilience and the project has conducted several studies. A coastal processes study was completed by the eCoast company and the research findings have been commmunicated ot the Government. Another report was conducted at North East point to check the status of the reef in relation to its role in ecosystem based adaptation on the coast. This is inline with component 2, the Ecosystem based measures for flood protection on an urban shoreline. Further to this, for the south of Mahe, the project is engaging in many activities to help the local fermers adapt to the changes in the climatic conditions affecting coastal agricultural activities. This has included several workshops undertaken by the Government partner Seychelles Agricultural Agency, which is an institution that had already been combatting saltwater intrusion and soil salinity before the project started.
| Component 3: Ecosyetem based Adaptation mainstreamed into development planning and financing |  |  |  | The project is on track with developing a policy and gal framework for a water policy in Seychelles. The Cabinet of ministers approved the Water Policy that was submitted early July and the milestone achievement. It reflects a paradigm shift in policy-maker's strategy to preserve the physical environment and natural resources of the country, as we leanr to adpat to the changes in the climate. The drafting of the legislation will be done in collaboration with the IWRM project and the watershed regulations will be discussed.
Overall Rating
Please Provide the Name and Contact information of person(s) reponsible for completeling the Rating section
| Name: | Wills Agricole, PS Emergy and Climate Change / National Project Director
| Email: | w.agricole@meteo.gov.sc
| Please justify your rating and address the following points: 1. Indicate trends, both positive and negative, in achievement of outcomes as per the project indicators. 2. Detail critical risks that have affected progress. 3. Outline response to MTR undertaken this reporting period. 4. Outline action plan to address projects with a rating of HU, U or MU. Please keep your input to 1200 words |  | The rating of Satisfactory is justified because the project has kept the momentum in achieving significant progress from the PPR produced last year. As can been seen from expenses/delivery on the various targets, the project is on track. The establishment of a more experience community engagement specialist has facilitated progress towards the community-based indicators, and the project has even achieved one target for the establishment of 4 local watershed committees. Positive trends observed are the increasing number of trainings delivered and sound research being conducted by the project to pilot rehabilitation in the various water catchments allocated as project sites. The project hydrologist attended a conference on community-based adaptation in Kampala, Uganda in June 2017 for knowledge-sharing with other regional countries undertaking similar inititatives and climate change adaptatio projects. Furthermore, project activities have progressed on all project sites in various forms from wetland rehabilitation involving the community to applied science in the forest rehabilitation component. The various linkages with other ongoing projects needs to be highlighted as it shows a good level of coordination as well as internal communications between the various institutions involved with ecosystem based adaptation and/or water sector issues in Seychelles. This is clearly demonstrated in the collaboration with the Integrated Water Resource Management (IWRM) project coordinated by the Ministry of Environment, Energy and Climate Change. The rating of satisfactory is justified as several initiatives have been completed during this last reporting period.
Rating Definitions
|  |  | Highly Satisfactory (HS) | Project actions/activities planned for current reporting period are progressing on track or exceeding expectations to acheive all major outcomes/outputs for given reporting period, without major shortcomings. The project can be presented as “good practice”.
|  |  | Satisfactory (S) | Project actions/activities planned for current reporting period are progressing on track to achieve most of its major outcomes/outputs with only minor shortcomings.
|  |  | Marginally Satisfactory (MS) | Project actions/activities planned for current reporting period are progressing on track to achieve most major relevant outcomes/outputs, but with either significant shortcomings or modest overall relevance.
|  |  | Marginally Unsatisfactory (MU) | Project actions/activities planned for current reporting period are not progressing on track to achieve major outcomes/outputs with major shortcomings or is expected to achieve only some of its major outcomes/outputs.
|  |  | Unsatisfactory (U) | Project actions/activities planned for current reporting period are not progressing on track to achieve most of its major outcomes/outputs.
|  |  | Highly Unsatisfactory (U) | Project actions/activities planned for current reporting period are not on track and shows that it is failing to achieve, and is not expected to achieve, any of its outcomes/outputs.

## Project Indicators
PROJECT Indicators
Please provide all indicators being tracked for the project as outlined in the project document
Type of Indicator (indicators towards Objectives, Outcomes, etc…)
Type of Indicator | Indicator | Baseline | Progress since inception | Target for Project End
Project Objective | Ecosystem services and natural assets maintained or improved under climate change and variability-induced stress | Project watersheds and coastal areas are regularly subject to water shortages and flooding events | Various phases of forest rehabilitation have started in the watersheds to facilitate the progressive restoration and capacity of degraded forest-land to deliver forest services to the communities. The activites undertaken as part of the wetland enhancement program are improving the water quality and flow in the upland wetlands of the targeted watersheds. For Praslin the project tree nursery was completed on time and on budget. Supplementary funding for the project nursery was provided by Government of Japan, and a parallel nursery effort is provided by SNPA as co-financing. Rehabilitation work by TRASS is underway. Tree tubes and other equipment have been sent to Praslin to facilitate growth of planted out saplings. Two teams of field workers and additional forestry operators are working to clear invasive vegetation to facilitate the rehabilitation works being conducted. | Reduced water shortages and flooded area involving about 4,000 ha of watershed and coastal ecosystems
| August mean daily discharge on two rivers (Mare aux Cochons & Baie Lazare) with increased base flows 78 | Mare aux Cochons August Avg Mean Daily Discharge: 261.1 L/S Baie Lazare August Mean Daily Discharge: 33.4 L/S | Baie Lazare August 2016 Mean Daily Discharge: 11.3 L/s (+60%). Data collection at Mare aux Cochons is being led by PUC. | Mare aux Cochons and Baie Lazare: Aug. baseline flows +20 – 30%
| January mean daily discharge on two rivers with decreased flood flows | Mare aux Cochons January Avg Mean Daily Discharge: 595.4 L/S Baie Lazare January Mean Daily Discharge: 173.1 L/S | Mare aux Cochons: no data. Baie Lazare: Mean Daily Discharge for January 2016: 106.5 L/s (-62%). The monitoring equipment maintained by the Public Utilities Corporation has been malfunctioning since December 2016 and only empirical data are available since then. | Mare aux Cochons and Baie Lazare: January baseline flows -20%
Component 1 | Number of water users with more reliable water supply | 10% of PUC water supply customers in project watersheds without fully reliable surface water supply | At this early phase in the wetland rehabilitation works it is not possible to measure the indicator as the project team are currently undertaking wetland enhancement programmes in various catchment areas. This indicator specifically targets PUC water supply customers, not wider water users, therefore the project is still debating whether or not to work on PUC data for water supply figures only. This will be addressed in the MTR. One constraint is that PUC is not refurbishing their weir at Mare aux Cochons to improve data collection for water supply. | 100% of PUC customers in target watersheds with more reliable water supply
| Number of days per year water supply is not available at two sites: Baie Lazare and Mare aux Cochons | Number of days per year when stream flows at critical low: Baie Lazare: avg. 18 days Mare aux Cochons: avg. 75 days (2010 - 2011) | There were 11 days where there was no water availability in the Baie Lazare project watershed in this reporting period. No shortage of water has been reported from Mare-aux-Cochons. However, refurbishment of the La Gogue dam from mid-2017 will likely cause many days of water shortage in north Mahe which will skew the data from Mare aux Cochons for the two years during which the dam height is to be raised. | 0 days of no water availability per year in project watersheds
| Volume of raw water production from PUC facilities in project watersheds. | Annual water production at: Mare aux Cochons: 614,336 KL Baie Lazare: 191,232 KL | Mare-aux-Cochons: 1,372,860 KL total for 2016 ; Baie Lazare: 243,343 KL total for 2016. | Annual water production figures increase by 20%
| Number of hectares of watersheds covered by site-based water management plans. | 0 hectares | Watershed management plans have not yet been developed. Now that the waterhed committees have been set up in four watersheds, the stakeholder and community engagement will facilitate the development of the management plans (under the umbrella of the new Water Policy, giving the plans a legal footing and also acting as pilots for such plans to be developed in other areas of Seychelles). A detailed reseach driven methodology has been developed for forest rehabilitation in collaboration with the University of Seychelles and this has informed detailed forest rehabilitation plans. These plans have been implemented on a series of pilot sites in Baie Lazare where permant transects are established to measure forest response in treated and untreated sites. About 20 ha have been rehabilitated in Baie Lazare and work tendered for Caiman catchment. A further c.8 ha on Praslin has been rehabilitated through planting of line-tracks being cut in non native fire prone vegetation. | 3,000 ha of critical watersheds
| Area of rehabilitated water provisioning and watershed flooding attenuation ecosystems. | Total hectares of watershed with increased resilience to climate change: 0 Total area of watershed that has undergone total rehabilitation: 0 | Project work is on-going over serval 100s of ha of forest watershed on Mahe and Praslin, although it is too early to provide monitoring results showing increased resilience to climate change. River profiling and wetland rehabilitation works are ongoing in Baie Lazare for water provising and flood attenuation (total rehabilitation) on 47 hectares in the upper watershed. | Total hectares of watershed with increased resilience to climate change: 3000 ha Total area of forest that has undergone total rehabilitation: at least 60 ha
| Active community watershed committees (with gender balance). | No watershed committees established | Four watershed committees have been set up so far, achieving the project target. These comprise Baie Lazare, Mont Plaisir, Caiman and Praslin watersheds. All four committees are committed to preserving and managing their water catchments. There is gender balance on all four committees, with the Chairperson of the Praslin and Mont Plaisir Watershed Committees being female. Currently, there are 13 members of the Baie Lazare Watershed committee with 6 females and 7 males. The Praslin Watershed Committee comprise of 5 females and 5 males. The Caiman Watershed commitee comprise of 6 females and 8 males and the Mont Plaisir watershed committee is composed of 10 females and 3 males. A fifth committee will be set up by the next reporting period for a key watershed within the Mare aux Cochons watershed (the area is very large and comprises several doistinct watersheds). To commemorate World Water Day, the Baie Lazare watershed committee collaborated with their district primary school to set up an exhibition to raise awareness about the EbA approach to climate change. The chairperson of the committee lead a group of children on an educational visit around the water catchment. The Praslin watershed commmittee collaborated with various partners to clear a path in the catchment forest leading to an upland wetland that can be beneficial for fire fighting on Praslin. | At least 4 watershed committees established with gender balance
Component 2 | Area of rehabilitated coastal ecosystems | # of tidal sluice gates installed: 0 | No tidal sluice gates have been installed yet. It has been decided that the installation of these will come after the complete coastal wetland reprofiling phases to ensure there are adequate designs. | # of tidal sluice gates installed: 2 by end of project
|  | Little wave energy attenuation provided by reef (5% of the pre-1998 bleaching event reef size) | The status of the reef structures at North east point hs been assessed; results indicate that the reef crest is exposed to strong wave surge, breaking off larger coral colonies such that branching corals tend to grow less and remain smaller. The project is identifying means to proceed with artificial reef structures. | 150 m of artificial breakwater providing substrate for coral growth and wave energy attenuation and more than 10% of original reef area rehabilitated at NE Point
|  | Total hectares of wetlands rehabilitated to provide flood attenuation services: 0 ha | Tenders have been issued for 15.3 hectares of coastal wetland to be cleared from invasive plant species and cleaned from wastes to increase resilience and prepare for further rehabilatation works in the Anse Royale coastal areas. This work will commence on August 2017. | Total hectares of wetlands rehabilitated to provide flood attenuation services: 17 ha
|  | Total km of rehabilitated beach berms providing a barrier for coastal floods: 0 km | 2.1 km of beach berm has been identified for rehabilitation at North East Point. Interventions will be based on the community choices after presentation of the project's report and recommendations, including presentation of possible scenarios. This will take place in August or September 2017. | Total km of rehabilitated beach berms providing a barrier for coastal floods: 5 km
|  | Total hectares of mangroves, wetlands, fringing reef, beach berms and other ecosystems with increased resilience to climate change impacts: 0 | The total hectares with increased resilience cannot yet be measured at North East Point coastal area. Mapping and status assessment of the coral reef ecosystem at North East Point is on-going to inform decision-making on the relevant interventions. The first phase of wetland rehabilitation has been tendered at Anse Royale (above) but it is not feasbile to report on the increased resilience of the wetland in this repoting period. | Total hectares with increase resilience: 1,000 ha
| Farm pond salinity levels reduced | Up to 6.0 ppt salinity levels in farm ponds during dry season | There is ongoing collaboration between the Seychelles Agricultural Agency and the EBA project to reduce the impact of salinity on agriculture. GIS licenss and GPS equipment were donated to the Agency to facilitate the mapping of the agricultural zone of Anse Royale to determine where salinity levels are rising and where interventions are needed. Spatial Analysis of the data will be used to design interventions. This is a collaboration between several agencies and other EBA projects. | 70% less salinity levels in farm ponds during the dry season
| Number of hectares of coastal ecosystems covered by Integrated Shoreline Management Plans | 0 hectares | An integrated shoreline management plan for Anse Royale has not been revised as yet (updated from the former ICZM plan). The drafting of the revised plan will be facilitated through the various rehabilitation programmes and community involvement. | 1,000 ha of coastal ecosystems
Component 3 | Approved water management policy framework being implemented for watershed areas | No policy and financing framework | A water management policy framework has been developed. Following stakeholder consultation and collaboration led by an Integrated Water Resource Management (IWRM) project, a water policy was submitted adn approved by the the Cabinet of Ministers in July 2017. Watershed management will be regulated through drafting of legislation that will follow, based in the Policy. The Environment Protection Bill 2016 has been approved, which also provides background to watershed management. Land use plans for Seychelles' main islands are being revised, but these provide the basic regulatory framework for the protection of water catchments in Seychelles. | Approved water management policy for watershed areas Core annual funding for local watershed management provided by tariffs and fees: $ 500,000
| Capacity developed for EbA methods: Rivers Committee meet regularly. | No institutional mechanisms | The Rivers Committee has been reactivated through the appointment of an officer in the Public Utilities Corporation. The committee has met once this reporting period; the project hydrologist is a member of the committee. | River Committee meets every quarter to discuss and address issues
| A National Watershed Monitoring System developed, applied and influences watershed management decisions | Little information available regarding functional connectivity, watershed integrity and water balance of watersheds | A national monitoring system has not yet been developed, but a system is in place for Baie Lazare watershed (acting as a pilot for possible adoption at a wider level). There are 10 forest monitoring plots where sound scientific research is being conducted to monitor change in the forest canopy over time. Methodologies and rehabilitation guidelines have been developed by professor Fleischman of the University of Seychelles. The project hydrologist and a cohort of University of Seychelles students continues to conduct regular monitoring at 6 river monitoring stations to collect rainfall datasets in the Baie Lazare watershed. Water quality data were collected for June and July 2016 (being repeated in 2017) testing for several key water quality indicators. These data provide baseline information to identify trends or changes in water quality. The regular monitoring helps investigations into problems such as point- or nonpoint-source pollution and nutrient enrichment. | Institutionalised and operational watershed monitoring system ensures adaptive management of watershed systems.
| Technical standards established for watershed, tidal wetland, and beach and reef rehabilitation | Incomplete and ad hoc specifications for ecosystem rehabilitation | Six permanent water-sampling points at Val d’Endor in Baie Lazare watershed have been regularly visited by students of the Environmental Science Department of University of Seychelles to collect water samples and monitor the water discharge (water flow) (above). A scientific methodology has been developed to set technical standards for forest rehabilitation and monitoring (above). Protection values of the vegetation are being determined in each watershed to give an orientation on vegetation quality of a particular forest site. The e-Coast experts have conducted a coastal processes study for North East Point coastline to identify and quantify the existing coastal processes and how they affect sediment transport within the site, and how these processes relate to climate change resilience strategies. | Technical standards are established and provide the basis for training.
| Number of trainees by gender skilled in EbA methods | Few government or NGO staff experienced in watershed or wetland rehabilitation | A total of 6 female and 7 male Watershed Committee members were trained in plant identification in September 2015. 13 female students from the University of Seychelles and 4 male students were trained in how to monitor stream flow in Baie Lazare rivers. The students learnt how to measure the potential volume of water held within the small PUC barrages, and assessed the many factors affecting drainage at the site, in terms of soil, geology, slope dynamics, vegetation, landuse, rainfall, overland and through-flow. 6 female Government staff and 9 male farmers were trained in soil and salinity management. Ten male participants underwent intensive training held on Mahe in forestry management work, including safe use of chainsaws, through an international LANTRA certificate course. A second less-intensive course for a further 10 participants, including 1 female trainee, was undertaken on Praslin. | 50 persons (gender balanced) trained in watershed, tidal wetland and beach and reef rehabilitation.
| Number of knowledge products on watershed and coastal ecosystem- based adaptation | Limited awareness of EbA methods related to watersheds and coastal ecosystems | Subsequent to the last reporting period, the project technical advisor has prepared an abstract paper in collaboration with the University of Seychelles, which was presented at an Island Invasive Conference held in Scotland in May 2017. The paper focuses on the understanding of light climate, vegetation monitoring and how this has informed initial rehabilitation. Management recommendations have been made based on the methodology devised that will be important to reconsider during the project mid-term review. | 10 knowledge products produced to assist awareness building

## Lessons Learned
QUALITATIVE MEASURES and LESSONS LEARNED
Please complete the following section every reporting period
Implementation and Adaptive Management | Response
What implementation issues / lessons, either positive or negative, affected progress? | The forest rehabilitation methodology designed at the Baie Lazare site has benefitted from considerable scientific inputs and debate. A number of techniques have been applied to monitoring, including the use of fish-eye lenses and analytical software to assess the forest light climate, and drones to overfly and record the canopy from the air. Early results have been presented at a Scientific Conference in July 2017 for additional feedback. These inputs have significantly assisted progress while making the work scientifically defensible and relevant on the wider international stage. The results of the Coastal processes study and the findings from the mapping and assessment of the North East Point coral reef system have provided information relevant at national level concerning the delayed impacts of land reclaimation schemes. They also provide the basis for the project to further consult the community and lead to informed decision-making cobcerning how to apply coastal adaptation measures in the face of rapidly increasing tidal surges.
Were there any delays in implementation? If so, include any causes of delays. What measures have been taken to reduce delays? | While the forest ehabilitation approaches on Mahe proceeded on schedule (variants of understory thinning) the forest rehabilitation program being undertaken by the NGO TRASS on Praslin was subject to considerable delays (this was focussed on replanting of degraded red soils). TRASS originally relied on volunteer assistance for replanting, and had difficulty in obtaining full time volunteers as the planting was more complicateda and demanding than anticipated. TRASS then proceeded to recruitment of field contractors, sub-contracting two teams of field contractors to clear strips of invasive plant species to allow for planting out of the native stocks from their nursery. This proceeded extremely slowly in difficult terrain. The project brought in a trained team from Mahe to assist, but in general the progress remained relatively slow in terms of achieving the area targeted by the project for rehabilitation. TRASS is now suggesting a revision of their contract to reduce the forest rehabilitation target from 20 hectares to 10 hectares. This will be analysed further during the mid-term review. An issue affecting monitoring is that the Public Utilities Corporation has still not provided the data needed to measure the indicators. Further, they have not fixed or replaced a malfunctioning water level sensor device at Baie Lazare which is used to estimate real-time river flow measurements and thus provides information vital to measuring project success. The project will address this by purchasing or co-financing new equipment.
Describe any changes undertaken to improve results on the ground or any changes made to project outputs (i.e. changes to project design) | Scientific research on the forest rehabilitation methodology being conducted by the project, in collaboration with the University of Seychelles and ETH Zurich has helped to refine the methods and improved results. The ongoing collaboration aims at providing a quotable and repeatable baseline for a watershed forest rehabilitation and the application of a methodology for the post-rehabilitation monitoring of the Baie Lazare watershed, with 10 representative permanent monitoring sites established, that will extend post-project under the auspices of the University of Seychelles.
How have gender considerations been taken into consideration during the reporting period? What have been the lessons learned as a consequence of inclusion of such considerations on project performance or impacts? | Gender balance is observed in all four watershed committees so far established. Two of the committees have female chairpersons and this ascertains gender equality and inclusiveness in the management of the water catchments. Both female and male members are actively involved in project activities and the result is a more enriched approach to watershed management.
Please complete the following section at mid-term and project completion
Lessons for Adaptation | Response
Climate Resilience Measures
What have been the lessons learned, both positive and negative, in implementing climate adaptation measures that would be relevant to the design and implementation of future projects/programmes for enhanced resilience to climate change?
What is the potential for the climate resilience measures undertaken by the project/programme to be replicated and scaled up both within and outside the project area?
Concrete Adaptation Interventions
What have been the lessons learned, both positive and negative, in implementing concrete adaptation interventions that would be relevant to the design and implementation of future projects/programmes implementing concrete adaptation interventions?
What is the potential for the concrete adaptation interventions undertaken by the project/programme to be replicated and scaled up both within and outside the project area?
Community/National Impact
What would you consider to be the most successful aspects for the target communities?
What measures are/have been put in place to ensure sustainability of the project/program results?
What measures are being/could have been put in place to improve project/program results?
Knowledge Management
How has existing information/data/knowledge been used to inform project development and implementation? What kinds of information/data/knowledge were used?
If learning objectives have been established, have they been met? Please describe.
Describe any difficulties there have been in accessing or retrieving existing information (data or knowledge) that is relevant to the project. Please provide suggestions for improving access to the relevant data.
Has the identification of learning objectives contributed to the outcomes of the project? In what ways have they contributed?

## Results Tracker
Results Tracker for Adaptation Fund (AF) Projects
Goal: Assist developing-country Parties to the Kyoto Protocol that are particularly vulnerable to the adverse effects of climate change in meeting the costs of concrete adaptation projects and programmes in order to implement climate-resilient measures. Impact: Increased resiliency at the community, national, and regional levels to climate variability and change.
Important: Please read the following guidance document (also posted on the Adaptation Fund website) before entering your data
Link: http://www.adaptation-fund.org/sites/default/files/Results%20Framework%20and%20Baseline%20Guidance%20final.pdf
Adaptation Fund Strategic Results Framework
Project ID | 89895
Implementing Entity | Ministry of Environment, Energy and Climate Change
Type of implementing entity | NIE
Country | Seychelles
Region | Africa
Sector | Water management
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Impact: Increased resiliency at the community, national, and regional levels to climate variability and change | Core Indicator: No. of beneficiaries Note: For this project the direct beneficiaries will be PUC customers and other water users in the target sites; indirect beneficiaries will be customers and users outside the target sites who either receive water piped or flowing from those sites, benefit from improved coastal defences at the target sites, etc. This information was cpllected in 2012 and presented in the Prodoc, but without the youth dimension. As 47% of the Seychelles population is youth (aged below 30), as per the Seychelles Youth Council, this is the figure used. |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project
|  | Total | 0 | 0 | 0 | Total | 89045 | 21545 | 67500 | Total |  |  |  | Total
|  | % of female beneficiaries | 50% | 50% | 50% | % of female beneficiaries | 50% | 50% | 50% | % of female beneficiaries |  |  |  | % of female beneficiaries
|  | % of Youth beneficiaries | 47% | 47% | 47% | % of Youth beneficiaries | 47% | 47% | 47% | % of Youth beneficiaries |  |  |  | % of Youth beneficiaries
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 1: Reduced exposure to climate-related hazards and threats | Indicator 1: Relevant threat and hazard information generated and disseminated to stakeholders on a timely basis | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness
|  | Total | 0 | Coastal flooding | 1: Ineffective | Total | 89045 | Coastal flooding | 4: Effective | Total |  |  |  | Total
|  | % of female targeted | 50% |  |  | % of female targeted | 50% |  |  | % of female targeted |  |  |  | % of female targeted
Output 1.1 Risk and vulnerability assessments conducted and updated | Indicator 1.1: No. of projects/programmes that conduct and update risk and vulnerability assessments Note: At baseline there is one project developing a vulnerability assessment, but this is not part of the AF project and neither is this to be followed up under the AF project. | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | 1 | Disaster risk reduction | National | 2: Undertaking or updating of assessments in progress | 1 | Disaster risk reduction | National | 3: Risk and vulnterability assessments completed or updated
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
Output 1.2 Targeted population groups covered by adequate risk reduction systems | Core Indicator 1.2: No. of Early Warning Systems Note: This is not a part of the current project as the project does not work directly with Departent of Risk and Disaster Management (DRDM) - which has other sources of funds. | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 2: Strengthened institutional capacity to reduce risks associated with climate-induced socioeconomic and environmental losses | Indicator 2: Capacity of staff to respond to, and mitigate impacts of, climate-related events from targeted institutions increased | Number of staff targeted |  | Sector | Capacity level | Number of staff targeted |  | Sector | Capacity level | Number of staff targeted |  | Sector | Capacity level | Number of staff targeted |  | Sector | Capacity level
|  | Total | 50 | Multi-sector | 1: No capacity | Total | 50 | Multi-sector | 4: High capacity | Total |  |  |  | Total
|  | % of female targeted | 50% |  |  | % of female targeted | 50% |  |  | % of female targeted |  |  |  | % of female targeted
Output 2.1 Strengthened capacity of national and sub-national centres and networks to respond rapidly to extreme weather events | Indicator 2.1.1: No. of staff trained to respond to, and mitigate impacts of, climate-related events | Total staff trained | % of female staff trained | Type |  | Total staff trained | % of female staff trained | Type |  | Total staff trained | % of female staff trained | Type |  | Total staff trained | % of female staff trained | Type
|  | 0 | 0% | Public |  | 50 | 50% | Public
| Indicator 2.1.2: No. of targeted institutions with increased capacity to minimize exposure to climate variability risks | Type | Scale | Sector | Capacity level | Type | Scale | Sector | Capacity level | Type | Scale | Sector | Capacity level | Type | Scale | Sector | Capacity level
|  | Public | National | Multi-sector | 1: No capacity | Public | National | Multi-sector | 3: Medium capacity
output 2.2 removed and associated fund indicator 2.2.2 recommendation to report against 2.1
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 3: Strengthened awareness and owernship of adaptation and climate risk reduction processes | Indicator 3.1: Increase in application of appropriate adaptation responses Note. Refers to direct beneficiaries calculated at 21,545 persons. | Percentage of targeted population applying adaptation measures |  | Sector |  | Percentage of targeted population applying adaptation measures |  | Sector |  | Percentage of targeted population applying adaptation measures |  | Sector |  | Percentage of targeted population applying adaptation measures |  | Sector
|  | 0% |  | Coastal management |  | 70 |  | Coastal management
Output 3: Targeted population groups participating in adaptation and risk reduction awareness activities | Indicator 3.1.1: Percentage in targeted population awareness of predicted adverse impacts of climate change, and of appropriate responses Note. Baseline knowledge survey not yet undertaken to verify. | No. of targeted beneficiaries | % of female participants targeted | Level of awareness |  | No. of targeted beneficiaries | % of female participants targeted | Level of awareness |  | No. of targeted beneficiaries | % of female participants targeted | Level of awareness |  | No. of targeted beneficiaries | % of female participants targeted | Level of awareness
|  | 21545 | 50% | 3: Partially aware |  | 21545 | 50% | 5: Fully aware
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Target performance at completion |  |  |  | Target performance at completion
Outcome 4: Increased adaptive capacity within relevant development sector services and infrastructure assets | Indicator 4.1: Increased responsiveness of development sector services to evolving needs from changing and variable climate | Project/programme sector | Geographical scale | Response level |  | Project/programme sector | Geographical scale | Response level |  | Project/programme sector | Geographical scale | Response level |  | Project/programme sector | Geographical scale | Response level
|  | Water management | National | 2: Partially responsive (Lacks most elements) |  | Water management | National | 4: Mostly responsive (Most defined elements)
| Core Indicator 4.2: Assets produced, developed, improved or strengthened | Sector | Targeted asset | Changes in asset (quantitative or qualitative) |  | Sector | Targeted asset | Changes in asset (quantitative or qualitative) |  | Sector | Targeted asset | Changes in asset (quantitative or qualitative) |  | Sector | Targeted asset | Changes in asset (quantitative or qualitative)
|  | Water management | 2: Physical asset (produced/improved/strenghtened) | 1: Not improved |  | Water management | 2: Physical asset (produced/improved/strenghtened) | 4: Mostly Improved
|  | Coastal management | 2: Physical asset (produced/improved/strenghtened) | 1: Not improved |  | Coastal management | 2: Physical asset (produced/improved/strenghtened) | 4: Mostly Improved
Output 4: Vulnerable development sector services and infrastructure assets strengthened in response to climate change impacts, including variability | Indicator 4.1.1: No. and type of development sector services to respond to new conditions resulting from climate variability and change | Number of services | Type |  | Sector | Number of services | Type |  | Sector | Number of services | Type |  | Sector | Number of services | Type |  | Sector
|  | 0 | National |  | Water management | 1 | National |  | Water management
|  | 0 | National |  | Coastal management | 1 | National |  | Coastal management
|  | 0 | Multi-community |  | Agriculture | 1 | Multi-community |  | Agriculture
indicator 4.1.2 removed we can only really change this to reporting 4.1.1
|  | Baseline information |  |  |  | Targeted performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 5: Increased ecosystem resilience in response to climate change and variability-induced stress | Indicator 5: Ecosystem services and natural resource assets maintained or improved under climate change and variability-induced stress | Natural resource improvement level |  | Sector | Type | Natural resource improvement level |  | Sector | Type | Natural resource improvement level |  | Sector | Type | Natural resource improvement level |  | Sector | Type
|  | 1: Ineffective |  | Multi-sector | land | 4: Effective |  | Multi-sector | land
Output 5: Vulnerable ecosystem services and natural resource assets strengthned in response to climate change impacts, including variability | Core Indicator 5.1: Natural Assets protected or rehabilitated Note. Baseline figures are set at 0 and refer to the areas targeted for rehabilitation by the project; some of these areas are nominally protected but this is ineffective. Nationally there are other areas that have been rehabilitated to varying degrees and levels of effectiveness. | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Forests |  | ha rehabilitated | 1: Ineffective | Forests | 650 | ha rehabilitated | 3: Moderately effective
|  | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Forests |  | ha rehabilitated | 1: Ineffective | Forests | 60 | ha rehabilitated | 5: Very effective
|  | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Coasts |  | km rehabilitated | 1: Ineffective | Coasts | 5 | km rehabilitated | 4: Effective
|  | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Other |  | ha rehabilitated | 1: Ineffective | Other | 17 | ha rehabilitated | 4: Effective
|  | Baseline information |  |  |  | Targeted performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 6: Diversified and strengthened livelihoods and sources of income for vulnerable people in targeted areas | Indicator 6.1: Increase in households and communities having more secure access to livelihood assets Note. Refers to farming households. 55% of female headed households is as per national average reported in household surveys (but noting that in a hgh percentage of cases the respondent is female) | No. of targeted households | % of female headed households | Improvement level |  | No. of targeted households | % of female headed households | Improvement level |  | No. of targeted households | % of female headed households | Improvement level |  | No. of targeted households | % of female headed households | Improvement level
|  | 600 | 55% | 2: Limited improvement |  | 600 | 55% | 3: Moderate improvement
| Indicator 6.2: Increase in targeted population's sustained climate-resilient alternative livelihoods | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
|  | 600 | 55% |  | Agriculture | 600 | 55% | From 20% to 30% | Agricultural-related
|  | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
|  | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
|  | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
Output 6 Targeted individual and community livelihood strategies strengthened in relation to climate change impacts, including variability | Indicator 6.1.1: No. and type of adaptation assets created or strengthened in support of individual or community livelihood strategies | Number of Assets | Type of Assets | Sector | Adaptation strategy | Number of Assets | Type of Assets | Sector | Adaptation strategy | Number of Assets | Type of Assets | Sector | Adaptation strategy | Number of Assets | Type of Assets | Sector | Adaptation strategy
|  | 1 | Natural capital | Coastal management | Community-based adaptation | 1 | Natural capital | Coastal management | Community-based adaptation
| Core Indicator 6.1.2: Increased income, or avoided decrease in income | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 7: Improved policies and regulations that promote and enforce resilience measures | Indicator 7: Climate change priorities are integrated into national development strategy | Integration level |  |  |  | Integration level |  |  |  | Integration level |  |  |  | Integration level
|  | 3: Some |  |  |  | 4: Most
Output 7:Improved integration of climate-resilience strategies into country development plans | Indicator 7.1: No. of policies introduced or adjusted to address climate change risks Note. Watershed management policy framework | No. of Policies introduced or adjusted | Sector | Scale | Type | No. of Policies introduced or adjusted | Sector | Scale | Type | No. of Policies introduced or adjusted | Sector | Scale | Type | No. of Policies introduced or adjusted | Sector | Scale | Type
|  | 0 | Water management | National | Water policy | 1 | Water management | National | Water Policy
| Indicator 7.2: No. of targeted development strategies with incorporated climate change priorities enforced Note. Seychelles Sustainable Development Strategy | No. of Development strategies | Regulation |  | Effectiveness | No. of Development strategies | Regulation |  | Effectiveness | No. of Development strategies | Regulation |  | Effectiveness | No. of Development strategies | Regulation |  | Effectiveness
|  | 1 | 2: Partially not enforced (Most elements not implemented) |  | 1: Ineffective | 1 | 3: Partially enforced (Some elements implemented) |  | 3: Moderately effective
Glacier lake outburst flood
|  | Inland flooding | fr | biological assets |  | Company policy | 5: Fully enforced (All elements implemented)
|  | Salinization | Decrease | land |  | Communication & Information policy | 4: Enforced (Most elements implemented)
|  | Drought | Same | water areas |  | Defense policy | 3: Partially enforced (Some elements implemented)
|  | Wind |  | subsoil assets | increased adpative capacity | Domestic policy | 2: Partially not enforced (Most elements not implemented) |  | Agribusiness
|  | Coastal flooding |  | air | achieved | Economic policy | 1: Not enforced (No elements implemented) |  | Agricultural-related | Financial capital
|  | Storm surge | Please choose |  | enhanced level of protection | Education policy |  |  | Agriculture | Human capital
|  | Hurricane | Selected | [5 empty] | Aquaculture | Physical capital
|  |  | Not relevant |  |  | 5: All (Fully integrated) |  |  | Construction/repairing business | Social capital
[6 empty] | 4: Most |  |  | Cultivation | Natural capital
[6 empty] | 3: Some |  |  | Fishing | Personal capital
Select | 5: All | Select |  |  | Community | 2: Most not integrated |  | Other | Forestry | Adaptation strategies
1 | 4: Almost all | Private | Type | Yes | Multi-community | 1: None |  | Agriculture | Handicrafts
2 | 3: Half | Public | Scale | No | Departmental |  |  | Coastal management | Livestock production
3 | 2: Some | NGO | Sector |  | National |  |  | Disaster risk reduction | Manufacturing
4 | 1: None |  |  |  |  | 5: Very high improvement | Established | Food security | other
|  | National |  |  |  | 4: High improvement | Maintained | Health | Services
|  | Regional |  |  |  | 3: Moderate improvement | Improved | Urban development | Tourism-related
|  | Local |  |  |  | 2: Limited improvement |  | Water management | Trading
[6 empty] | 1: No improvement |  | Multi-sector
|  | 1 -generated information is irrelevant, and neither the stakeholders reached nor the timeframe managed were achieved | 1: No info transferred on time | 4: High capacity | 5: Fully aware | 5: Highly responsive (All defined elements ) | 5: Fully improved | Roads | 5: Very effective
Asia-Pacific | NIE | 2 -the existence of some challenge in any of the three aspects of the indicator (generation of dissemination, stakeholders reached or timeframe managed) | 2: Somewhat info transferred | 3: Medium capacity | 4: Mostly aware | 4: Mostly responsive (Most defined elements) | 4: Mostly Improved | Gov Buildings | 4: Effective
Latin America and Caribbean | RIE | 3 -relevant information is generated and disseminated to all identified stakeholders on timely basis | 3: Info transferred on time | 2: Low capacity | 3: Partially aware | 3: Moderately responsive (Some defined elements) | 3: Moderately improved | Causeways | 3: Moderately effective
Africa | MIE |  |  | 1: No capacity | 2: Partially not aware | 2: Partially responsive (Lacks most elements) | 2: Somewhat improved | Airports | 2: Partially effective
Eastern Europe |  |  |  |  | 1: Aware of neither | 1: Non responsive (Lacks all elements ) | 1: Not improved | Schools | 1: Ineffective
| ha protected | [6 empty] | Training Centres
| ha rehabilitated | [5 empty] | Monitoring/Forecasting capacity | Hospitals
Afghanistan, Islamic Rep. of | km protected | [5 empty] | Policy/regulatory reform | Drinking water systems
Angola | km rehabilitated | 1: Risk knowledge | 1: No plans conducted or updated |  |  |  | Capacity development | Other
Albania |  | 2: Monitoring and warning service | 2: Undertaking or updating of assessments in progress |  |  | Communication & Information policy | Sustainable forest management
Argentina |  | 3: Dissemination and communication | 3: Risk and vulnterability assessments completed or updated |  |  | Domestic policy | Strengthening infrastructure | 1: Health and Social Infrastructure (developed/improved)
Armenia | Forests | 4: Response capability |  |  |  | Economic policy | Supporting livelihoods | 2: Physical asset (produced/improved/strenghtened)
Antigua and Barbuda | Mangroves |  |  |  |  | Education policy | Mangrove reforestation
Azerbaijan | Coasts |  | From 0 to 0.5% |  |  | Energy policy | Coastal drainage and infrastructure
Burundi | Rangelands |  | From 0.5 to 1% |  |  | Environmental policy | Irrigation system
Benin | Cultivated land/Agricultural land |  | From 1% to 5% |  |  | Foreign policy | Community-based adaptation
Burkina Faso | Catchment area/Watershed/Aquifer |  | From 5% to 10% |  |  | Health policy | Erosion control
Bangladesh | Protected areas/National parks |  | From 10% to 20% |  |  | Housing policy | Soil water conservation
Bulgaria | Other |  | From 20% to 30% |  |  | Human resource policies | Microfinance
Bahrain |  |  | From 30% to 40% |  |  | Information policy | Special Program for women
Bahamas, The |  |  | From 40% to 50% |  |  | Macroeconomic policy | Livelihoods
Bosnia and Herzegovina |  |  | Above 50% |  |  | Monetary policy | Water storage
Belarus | [5 empty] | Population policy | ICT and information dissemination
Belize | [5 empty] | Private policy
Bolivia | [5 empty] | Public policy
Brazil | [5 empty] | Science policy
Barbados | [5 empty] | Social policy
Bhutan |  | 3- relevant information is generated and disseminated to all identified stakeholders on timely basis |  |  |  | Transportation policy
Botswana |  | describe |  |  |  | Urban policy
Central African Republic |  | 2- the existence of some challenge in any of the three aspects of the indicator |  |  |  | Water policy
Chile |  | describe |  |  |  | Other policy
China, People's Republic of |  | 1- generated information is irrelevant and neither the stakeholders reached nor the timeframe managed were achieved
Cote d'Ivoire |  | describe
Cameroon
Congo, Dem. Rep. of
Congo, Republic of
Cook Islands
Colombia
Comoros
Cape Verde
Costa Rica
Cuba
Czech Republic
Djibouti
Dominica
Dominican Republic
Algeria
Ecuador
Egypt
Eritrea
Estonia
Ethiopia
Fiji
Micronesia, Fed. States of
Gabon
Georgia
Ghana
Guinea
Gambia, The
Guinea-Bissau
Equatorial Guinea
Grenada
Guatemala
Guyana
Honduras
Croatia
Haiti
Hungary
Indonesia
India
Iran, Islamic Republic of
Jamaica
Jordan
Kazakhstan
Kenya
Kyrgyz Republic
Cambodia
Kiribati
Saint Kitts and Nevis
Korea, Republic of
Lao People's Democratic Republic
Lebanon
Liberia
Libya
Saint Lucia
Sri Lanka
Lesotho
Lithuania
Latvia
Morocco
Moldova
Madagascar
Maldives
Mexico
Marshall Islands
Macedonia, former Yugoslav Republic of
Mali
Malta
Myanmar
Montenegro
Mongolia
Mozambique
Mauritania
Mauritius
Malawi
Malaysia
Namibia
Niger
Nigeria
Nicaragua
Niue
Nepal
Nauru
Oman
Pakistan
Panama
Peru
Philippines
Palau
Papua New Guinea
Poland
Korea, Dem. People's Rep. of
Paraguay
Romania
Russian Federation
Rwanda
Saudi Arabia
Sudan
Senegal
Solomon Islands
Sierra Leone
El Salvador
San Marino
Serbia
Sao Tome and Principe
Suriname
Slovak Republic
Slovenia
Swaziland
Seychelles
Syrian Arab Republic
Chad
Togo
Thailand
Tajikistan
Turkmenistan
Tonga
Trinidad and Tobago
Tunisia
Turkey
Tuvalu
Tanzania
Uganda
Ukraine
Uruguay
Uzbekistan
Saint Vincent and the Grenadines
Venezuela
Vietnam
Vanuatu
Samoa
Yemen, Republic of
South Africa
Zambia
Zimbabwe
Timor-Leste

## Units for Indicators
Fund Outcome Indicator Units
1. Generation of relevant data, Stakeholders, and Timeliness 2.1. Include both qualitative and quantitative measures of capacity level within targeted institutions 2.2. Number (men and women and other vulnerable groups) 3.1. Use scale from 1 to 5: 5: Fully aware 4: Mostly aware 3: Partially aware 2: Partially not aware 1: Aware of neither predicted adverse impacts of climate change nor of appropriate responses 3.2. Use scale from 1 to 5: 5: All 4: Almost all 3: Half 2: Some 1: None 4.1. Summarize in an overall scale (1-5): 5: Highly responsive (All defined elements ) 4: Mostly responsive (Most defined elements) 3: Moderately responsive (Some defined elements) 2: Partially responsive (Lacks most elements) 1: Non responsive (Lacks all elements ) 4.2. Summarize in an overall scale (1-5): 5: Fully improved 4: Mostly Improved 3: Moderately improved 2: Somewhat improved 1: Not improved 5. Depends on the targeted natural asset: Biological (species): measure through changes in population numbers (dynamics, structure, etc.) Land: measure changes in hectares. Baseline data will be necessary to estimate the change. Supporting indicators baseline and target (as well as contextual information) are needed such as the following: Farmers adopting recommended technologies, Ha. of land improved, Average deforestation rate Etc. Use scale from 1 to 5. 5: Very effective (All elements are present) 4: Effective (Most elements are present) 3: Moderately effective (Some elements are present) 2: Partially effective (Most elements are not present) 1: Ineffective (No elements are present) 6.1. Summarize in an overall scale (1-5): 5: Very high improvement 4: High improvement 3: Moderate improvement 2: Limited improvement 1: No improvement 6.2. Household income by source of livelihood in project area (USD) prior and post project intervention 7. Summarize in an overall scale (1-5). 5: All (Fully integrated) 4: Most 3: Some 2: Most not integrated 1: None
Fund Output Indicator Units
1.1. Number, sector(s) and level(s) of projects or interventions in separate fields of monitoring plan 1.2. Number 2.1.1. Number of staff (male/female) of targeted institutions: a. Obtain baseline information: total number of staff from targeted institutions b. Define target 2.1.2. Number of staff (male/female) of targeted institutions: a. Obtain baseline information: total number of staff from targeted institutions b. Define target: needs to be defined by project proponents 2.2.1. Quantitative: Percentage (includes women – and other vulnerable groups – and men). Qualitative: Adequacy: include direct analysis of major areas; adequacy/effectiveness of systems or analysis of perceptions of populations and institutions. 2.2.2. Number (broken down by gender and, if possible, by vulnerable groups defined in the area of intervention) of people 3.1. Number and type (in separate columns) at local level. 3.2. Number 4.1. Number and type 4. 2. Number and type (entered in separate columns) 5. Number of interventions by type of natural asset and intervention 6.1. Number and type (in separate columns of monitoring plan) 6.2. Income sources per household; description of income source and number of households. 7.1. Number/Sector 7.2. Number; Effectiveness (see previous indicator) through enforcement level.