## Overview
Project Performance Report (PPR)
| Period of Report (Dates) | Aug 2014 - 31 Mar 2016
| Project Title: | ADDRESSING CLIMATE CHANGE RISKS ON WATER RESOURCES AND FOOD SECURITY IN THE DRY ZONE OF MYANMAR
| Project Summary: | Myanmar’s Dry Zone is one of the few areas in this region where food security for survival is still a real issue and the linkage of “bad weather” and poverty is immediate and dire. In 2009, a drought triggered 50-70% drop in rice and 80-90% drop in sesame and sunflower harvest – some of the key crops grown in the region. To strike a balance of investments on urgent adaptation needs and greater coverage of beneficiaries, this project combines targeted interventions for resilient livelihood actions and rehabilitation of community ecosystem assets such as forests and watersheds.
|  |  | Countries | Project Type: |  | GEF Focal Area: | GEF 4 Focal Areas | GEF 2 / 3 Operational Programme: | Overall Rating of the project in the evaluation by the project evaluator: | GEF-4 Focal Area Strategic Program: | GEF-3 Focal Area Strategic Program:
| Database Number: | PIMS 4703 | Afghanistan | FP | Yes | Biodiversity | 1 | 1 | U | BD-SP1-PA Financing | 1: Arid & semi-arid ecosystems
Implementing Entity (IE) [name]: |  | United Nations Development Programme | Albania | MSP | No | Climate Change Adaptation | 2 | 2 | S | BD-SP2-Marine PA | 2: Coastal, marine & freshwater ecosystems
| Type of IE: | MIE | Algeria | EA |  | Climate Change Mitigation | 3 | 3 | MU | BD-SP3-PA Networks | 3: Forest ecosystems
| Country(ies): | Myanmar | Angola |  |  | International Waters | 5 | 5 | Good | BD-SP5-Markets | 13: Conservation and Sustainable Use of Biological Diversity Important to Agriculture
Relevant Geographic Points (i.e. cities, villages, bodies of water): |  | Five townships (Shwebo, Moneywa, Myingyan, Nyaung Oo and Chauk) in Myanmar's Dry Zone | Argentina |  |  | Multiple Focal Area |  |  |  | BD-SP7-Invasive Alien Species(IAS) | 6: Promoting the adoption of renewable energy by removing barriers and reducing implementation costs
[8 empty] | CC-SP2- Industrial EE | 8: Waterbody based operational program
| Project Milestones | [6 empty] | CC-SP3-RE,CC-SP4-Biomass | 9: Integrated Land and Water multiple focal area
| Milestone |  | Bahamas | [6 empty] | CC-SP5-Transport | 10: Contaminants based operational program
AFB Approval Date: |  | 2014-03-11
IE-AFB Agreement Signature Date: |  | 2014-03-26 | [6 empty] | CC-SP6-LULUCF | 12: Integrated Ecosystem Management
Start of Project/Programme: |  | 2014-08-06 | [6 empty] | Cross cutting capacity building | 14: Persistent Organic Pollutants
Mid-term Review Date (if planned): |  | 2017-02-17
| Terminal Evaluation Date: | 2019-02-17
|  | List documents/ reports/ brochures / articles that have been prepared about the project. | Cyprus
|  | 1. Project Brochure - UNDP Adaptation Fund Project - Addressing Climate Change Risks on Water and Food Security in the Dry Zone of Myanmar 2. Report of the launching ceremony of the project 3. Communication Strategy of the AF Project 4. Greening the Dry Zone: Conserving land while improving water acces and food security in Myanmar (photo essay published on ALM page) 5. Summary Report of the Target Villages selection process 6. Inception Report 7. Minutes of the 1st Project Steering Committee meeting 8. Capacity Assessment of NGOs/CSOs 9. Monitoring and Evaluation Framework for the AF project | Czech Republic
List the Website address (URL) of project. |  |  | Democratic People's Republic of Korea
|  | http://www.undp-alm.org/projects/af-myanmar | Democratic Republic of the Congo
Denmark
| Project contacts: |  | Djibouti
National Project Manager/Coordinator |  |  | Dominica
| Name: | Mr. Myint Wai | Dominican Republic
| Email: | myint.wai@undp.org | Ecuador
| Date: | 2016-06-23 | Egypt
| Government DA |  | El Salvador
| Name: |  | Equatoral Guinea
| Email: |  | Eritrea
| Date: |  | Estonia
| Implementing Entity |  | Ethiopia
| Name: | Ms. Lat Lat Aye; Mr. Yusuke Taishi; | Fiji
| Email: | lat.lat.aye@undp.org; yusuke.taishi@undp.org; | Finland
| Date: | 2016-06-23 | France
| Executing Agency |  | Gambia
| Name: |  | Georgia
| Email: |  | Germany
| Date: |  | Ghana
| Executing Agency |  | Greece
| Name: |  | Grenada
| Email: |  | Guatemala
| Date: |  | Guinea
| Executing Agency |  | Guinea Bissau
| Name: |  | Guyana
| Email: |  | Haiti
| Date: |  | Honduras
Hungary
Iceland
India
Indonesia
Iran (Islamic Republic of)
Iraq
Ireland
Israel
Italy
Jamaica
Japan
Jordan
Kazakhstan
Kenya
Kiribati
Kuwait
Kyrgyzstan
Lao People’s Democratic Republic
Latvia
Lebanon
Lesotho
Liberia
Libyan Arab Jamahiriya
Liechtenstein
Lithuania
Luxembourg
Madagascar
Malawi
Malaysia
Maldives
Mali
Malta
Marshall Islands
Mauritania
Mauritius
Mexico
Micronesia, Federated States of
Monaco
Mongolia
Montenegro
Morocco
Mozambique
Myanmar
Namibia
Nauru
Nepal
Netherlands
New Zealand
Nicaragua
Niger
Nigeria
Norway
Oman
Pakistan
Palau
Panama
Papua New Guinea
Paraguay
Peru
Philippines
Poland
Portugal
Qatar
Republic of Korea
Republic of Moldova
Romania
Russian Federation
Rwanda
Saint Kitts and Nevis
Saint Lucia
Saint Vincent and the Grenadines
Samoa
San Marino
Sao Tome and Principe
Saudi Arabia
Senegal
Serbia
Seychelles
Sierra Leone
Singapore
Slovakia
Slovenia
Solomon Islands
Somalia
South Africa
Spain
Sri Lanka
Sudan
Suriname
Swaziland
Sweden
Switzerland
Syrian Arab Republic
Tajikistan
Thailand
The former Yugoslav Republic of Macedonia
Timor-Leste
Togo
Tonga
Trinidad and Tobago
Tunisia
Turkey
Turkmenistan
Tuvalu
Uganda
Ukraine
United Arab Emirates
United Kingdom of Great Britain and Northern Ireland
United Republic of Tanzania
United States of America
Uruguay
Uzbekistan
Vanuatu
Venezuela, Bolivarian Republic of
Viet Nam
Yemen
Zambia
Zimbabwe

## FinancialData
Financial information: cumulative from project start to 31 March 2016
DISBURSEMENT OF AF GRANT FUNDS
How much of the total AF grant as noted in Project Document plus any project preparation grant has been spent to date?
Estimated cumulative total disbursement as of [31 March 2016] | 447418
Add any comments on AF Grant Funds. (word limit=200) | At the end of Q1/2016, the project had disbursed US$ 447,418 out of the first tranche allocation of US$ 2,101,675 (representing 21.29% delivery rate). Most of the expenditure in 2014 and 2015 were made under UNDP co-financing. The planned expenditure schedule given below also reflects the planned activities from April to December of the 2016 annual work plan.
INVESTMENT INCOME | N/A
Amount of annual investment income generated from the Adaptation Fund’s grant
EXPENDITURE DATA
List ouput and corresponding amount spent for the current reporting period | ITEM / ACTIVITY / ACTION | AMOUNT
| Output1.1: Water Capture and Storage Capacity in 280 Villages enhanced to ensure imporved access to fresh water supply during dry periods | 112122.226
| Output1.2: 6141 hectares of micro-watersheds are protected and rehabilitated through Farmer-Managed Natural Regeneration (FMNR) to increase natural water retention and reduce erosion | 81812.8036
| Output1.3: Community-based agro-foresty plots are established on 3,983 hectares of private and communal lands to conserve soil and water | 62326.3704
| Output2.1: Drought-resilient farming methods introuduced to farmers to enhance the resilience of subsistence agriculture in the Dry Zone | 48843.5844
| Output2.2: Resilient post-harvest processing and storage systems intoruduced to reduce climate-induced post-harvest losses(droughts, rain and floods) | 23800.0222
| Output2.3: Diversified livestock production systems are introudced in 6,300 households to buffer the effects of drought on rural livelihoods | 43315.0434
| Output3.1: Climate hazard maps and risk scenarios are developed in each Township to support community-based climate risk managemetn and preparedness planning | 17484.0506
| Output3.2: Local level climate and disaster risk management framework strengthened for timely and effective communication of climate risk and early warning information | 26850.3494
| Project Execution Cost | 30863.05
| TOTAL | 447417.5
PLANNED EXPENDITURE SCHEDULE
List outputs planned and corresponding projected cost for the upcoming reporting period | ITEM / ACTIVITY / ACTION | PROJECTED COST | Est. Completion Date
| Output1.1: Water Capture and Storage Capacity in 280 Villages enhanced to ensure imporved access to fresh water supply during dry periods | 278078.63 | 2016-12-31
| Output1.2: 6141 hectares of micro-watersheds are protected and rehabilitated through Farmer-Managed Natural Regeneration (FMNR) to increase natural water retention and reduce erosion | 286238.36 | 2016-12-31
| Output1.3: Community-based agro-foresty plots are established on 3,983 hectares of private and communal lands to conserve soil and water | 224246.99 | 2016-12-31
| Output2.1: Drought-resilient farming methods introuduced to farmers to enhance the resilience of subsistence agriculture in the Dry Zone | 249247.68 | 2016-12-31
| Output2.2:Resilient post-harvest processing and storage systems intoruduced to reduce climate-induced post-harvest losses(droughts, rain and floods) | 226073.61 | 2016-12-31
| Output2.3: Diversified livestock production systems are introudced in 6,300 households to buffer the effects of drought on rural livelihoods | 181674.88 | 2016-12-31
| Output3.1: Climate hazard maps and risk scenarios are developed in each Township to support community-based climate risk managemetn and preparedness planning | 93666.43 | 2016-12-31
| Output3.2: Local level climate and disaster risk management framework strengthened for timely and effective communication of climate risk and early warning information | 59871.99 | 2016-12-31
| Project Execution Cost | 15014.08 | 2016-12-31
| TOTAL | 1614112.65
ACTUAL CO-FINANCING (If the MTR or TE have not been undertaken this reporting period, DO NOT report on actual co-financing.)
How much of the total co-financing as committed in the Project Document has actually been realized? | 172983.52
Estimated cumulative actual co-financing as verified during Mid-term Review (MTR) or Terminal Evaluation (TE).
Add any comments on actual co-financing in particular any issues related to the realization of in-kind, grant, credits, loans, equity, non-grant instruments and other types of co-financing. (word limit=200)

## Risk Assesment
RISK ASSESMENT
IDENTIFIED RISKS
List all Risks identified in project preparation phase and what steps are being taken to mitigate them
Identified Risk | Current Status | Steps Taken to Mitigate Risk
Non-climate drivers undermine adaptation efforts under this project. | Impact: 4 Probability: 1 | The original risk mitigation approach remains relevant. That is, the project will promote an integrated view of vulnerability in which the mitigation of climate-related drivers of vulnerability can be coupled with economic benefits. This integrated, ecosystem-based view of resilience, which is based on community-based participatory planning, will be able to hold non-climatic drivers such as over-grazing, deforestation and unsustainable agricultural practices in check. From this perspective, many adaptation actions that are implemented or planned to be implemented in the project, have been designed to address the local community needs for economic and social empowerment.
Extreme weather events during the project lifetime undermine confidence of local communities in adaptation measures promoted by the project. | Impact: 3 Probability: 3 | By design, the project integrates Outputs which focus on disaster risk and early warning communication, which enable basic preparedness planning. Currently, activities under Outcome 3 are ongoing to design a mobile application system that would establish a new method of disseminating early warning information, in addition to the existing word-of-mouth communications.
Adaptation measures increase inequity in communities. | Impact: 3 Probability: 1 | The selection of project target villages have been done in consultation with the beneficiaries and based on a set of selection criteria, including - observed temperature extremes, frequency of drought per year, impacts of climatic parameters on food security and potential to access ground and surface water resources. The project has also collected baseline information on beneficiaries and developed a database to monitor and ensure that the project supports the most vulnerable and marginalized communities.
Technical capacity of township and village stakeholders restricts broad community engagement. | Impact: 3 Probability: 3 | During the inception phase of the project, the project team conducted stakeholder consultations in each of the project townships on project objectives, outcomes, priorities and local needs to enhance better understanding of the project. Township authorities and local communities have expressed willingness to work together to achieve the objectives of the project.
Political and social instability and lack of government engagement | Impact:3 Probability:1 | While this risk continues to be valid, the likelihood of this risk materializing has gone down since this project was under design 3 years ago. The project steering committee includes representaives from the Government and key decisions in the project are jointly made by the Government of Myanmar and UNDP. So far, lack of Government engagement is not at all an issue.
Critical Risks Affecting Progress (Not identified at project design)
Identify Risks with a 50% or > likelihood of affecting progress of project
Identified Risk | Current Status | Steps Taken to Mitigate Risk
Risk Measures: Were there any risk mitigation measures employed during the current reporting period? If so, were risks reduced? If not, why were these risks not reduced?
Add any comments relevant to risk mitigation (word limit = 500)
During the reporting period, the project team has instituted a system of monthly project coordination meetings with the counterpart agency (Dry Zone Greening Department). This has enabled the project team to clarify issues and address implementation bottlenecks with the government, thereby reducing risk assocated with lack of governmentr engagement.

## Rating
RATING ON IMPLEMENTATION PROGRESS
For rating definitions please see bottom of page.
| Progress on Key Milestones |  | Expected Progress |  | Progress to Date | Rating
Project Manager/Coordinator: | Output 1.1: Identify specific locations in target villages for the following adaptation interventions: canals for water diversion; small-scale pumping systems; communal water tanks; tube wells; pound reserviors; and soil storage dams |  | Target villages selected based on a set of slection criteria and adaptation interventions identified for targetted villages |  | Secondary baseline data on agriculture, livestock, forestry, soil and water conservation have been collected. Target villages (280) have been identified in consultation with the government. | MS
| Output 1.1: Village level management scheme formulated which includes the roles and responsibilities of VWUG and distribution agreement across (vulnerable) households |  | Draft village level water management schemes guidelines, as well as water distribution agreements developed |  | The project team has discussed the need for guidelines and SOPs for Village Water User Groups with Water Resources Utilization Department and Department of Rural Development and they have welcomed our inputs in this regard. The work on guidelines and SOPs is already planned as an input from the project | MU
| Output 1.1: At least 50% of women's participation is encouraged to the workshops on water storage and capture interventions and participation monitored |  | At least 35% participation of women achieved in workshops on water storage and capture interventions |  | A monitoring and evaluation framework for the project has been drafted which takes into account the need to record gender disaggregated data during implementation. In addition, the database maintained by the project has recorded beneficiery information so as to assist in monitoring during implementation. | MU
| Output 1.1: Contribution of labour from women and/or landless improverished households is facilitated |  | Contributoin of labour from women and/or landless impoverished households facilitated and encouraged |  | All the TORs developed for the implementation of project activities by NGOs/CSOs have specifically outlined the need to engage landless and impoverished households for and labour-related activities | MS
| Output 1.1: Production of a report on the success and challenges of micro-scale water infrastructure |  | No progress expected in the 1st year of project implementation |  | No progress | MS
| Output 1.2: Finalize village-wise intervention type and size based on the level of denudation, ongoing surface runoff and topography |  | Target villages selected based on a set of slection criteria and adaptation interventions identified for targetted villages |  | During the design of the TOR for watershed and forestry interventions, tentative areas along with the type and size of interventions have been pre-identified in discussion with the forestry department and the Dry Zone Greening Department. These will be confirmed again, once the implementing partner has been deputed on the ground. | MU
| Output 1.2: At least 50% of women's participation is encouraged to the workshops on wtareshed rehabilitation programmes and participation monitored |  | At least 35% participation of women achieved in workshops on water storage and capture interventions |  | A monitoring and evaluation framework for the project has been drafted which takes into account the need to record gender disaggregated data during implementation. In addition, the database maintained by the project has recorded beneficiery information so as to assist in monitoring during implementation. | MU
| Output 1.2: Roles and responsibilities of women are clearly identified in the community management plan |  | No progress expected in the 1st year of project implementation |  | No progress | MS
| Output 1.2: Production of a report on the success and challenges of community forest management plan |  | No progress expected in the 1st year of project implementation |  | No progress | MS
| Output 1.2: Initial 30-year lease permission sought and granted for successfully managed community forests |  | No progress expected in the 1st year of project implementation |  | The team has discussed modalities of securing 30 year lease for community forestry management with the Forestry Department and this has been incorporated in the implementation guidelines prepared for the implementing partner | MS
| Output 1.3: Initial call for participation will target primarily women; at minimum 50% of the members should be women |  | At least 35% participation of women achieved in workshops on water storage and capture interventions |  | No progress | MU
| Output 1.3: Information collected on ongoing agro-forestry practices will be gender disaggregated |  | Information collected on ongoing agro-forestry practices is gender-disaggregated |  | A draft template on the inventory of agro-forestry practices is in place and conisders collection of gender-disaggregated data | MS
| Output 1.3: 1,700 hectares of homestead gardening in 110 villages established |  | Implementation of the activity iniitated with the deployment of implementing parner with a specifi TOR |  | The TOR for the engagement of implementing partner for this activity is ready and call for proposals will be sent out soon | MU
| Output 1.3: 3,400 hectares of farm boundary planting in 100 villages established |  | Implementation of the activity iniitated with the deployment of implementing parner with a specifi TOR |  | The TOR for the engagement of implementing partner for this activity is ready and call for proposals will be sent out soon | MU
| Output 1.3: Participants of the monitoring visits encourage women's participation |  | Monitoring visits to project sites will include women participants so as to ensure gender considerations in activities |  | No progress | MU
| Output 1.3: Production of a report on the success and challenges of community forestry management plan |  | No progress expected in the 1st year of project implementation |  | No progress | MS
| Output 2.1: Organize a technical workshop to consolidate existing domestic and international knowledge on drought resistant crop varieties and seed banks inviting technical agencies such as Myanmar Agriculture Services, University of Agriculture, Department of Agriculture Research |  | Technical workshop to consolidate existing domestic and international knowledge on drought resistant crop varieties and seed banks inviting technical agencies such as Myanmar Agriculture Services, University of Agriculture, Department of Agriculture Research conducted |  | The TOR for this work package has been designed and include this activity as a key deliverable and it is included in the implementation guidelines | MU
| Output 2.2: Quantative assessment of current post-harvest processes undertaken and reported |  | Quantative assessment of current post-harvest processes drafted |  | This activity is planned as part of the TOR on the promotion of climate resilient agriculture practices in the Dry Zone of Myanmar | MU
| Output 2.2: Production of an assessment report on current post-harvest processes |  | No progress expected in the 1st year of project implementation |  | No progress | MS
| Output 2.2: Formulate a cost-sharing and maintenance plan in each village for the use of the thresher |  | Cost-sharing and maintenance plan in each village for the use of the thresher drafted |  | The procurement of threshers has been initiated. The work on the drafting of guidelines on cost-sharing and use of threshers is part of the TOR on promotion of climate resilient agriculture practices in the Dry Zone of Myanmar (which is ready for call for proposals) | MS
| Output 2.2: Women's participation in post-harvest trainings encouraged and gender-disaggregated participation record will be produced |  | No progress expected in the 1st year of project implementation |  | A monitoring and evaluation framework for the project has been drafted which takes into account the need to record gender disaggregated data during implementation. In addition, the database maintained by the project has recorded beneficiery information so as to assist in monitoring during implementation. | MS
| Output 2.2: Production of assessment reports on the effectiveness of harvest storage facilities and post-harvest handling techniques |  | No progress expected in the 1st year of project implementation |  | This activity is planned as part of the TOR on the promotion of climate resilient agriculture practices in the Dry Zone of Myanmar | MS
| Output 2.3: Atleast 50% of the participants of the training on livestock production systems should be women. Gender disaggregated participants list will be produced |  | Atleast 35% of the participants of the training on livestock production systems are women |  | A monitoring and evaluation framework for the project has been drafted which takes into account the need to record gender disaggregated data during implementation. In addition, the database maintained by the project has recorded beneficiery information so as to assist in monitoring during implementation. | MU
| Output 2.3: Production of an assessment report on the effectiveness of diversified livestock production systems |  | No progress expected in the 1st year of project implementation |  | No progress | MS
| Output 3.1: Vulnerability assessment in townships will look at gender-differentiated vulnerability to climate risks |  | Vulnerability assessment in townships consider gender-differentiated vulnerability to climate risks |  | The TOR for the work on vulnerability assessments in townships are designed to be participatory in nature and women's participation will be considered during the process | MU
| Output 3.2: Seasonal agriculture bulletins produced |  | No progress expected in the 1st year of project implementation |  | Discussions ongoing with DMH and RIMES to replicate/upscale ongoing pilot agro-advisory system in Nyaung U and Monywa townships. | MU
| Output 3.2: CBDRM committee will have women representatives and they will be assigned specific roles and responsibilities |  | CBDRM committees have women representatives with specific roles and responsibilities |  | The review and update of the CBDRM manual for Myanmar is being initiated.CBDRM committees have yet to be formed. This will likely take place only in 2017 | MU
[5 empty] | Overall Rating | MU
Please Provide the Name and Contact information of person(s) reponsible for completeling the Rating section
| Name: | Myint Wai
| Email: | myint.wai@undp.org
Please justify your rating. Outline the positive and negative progress made by the project since it started. Provide specific recommendations for next steps. . (word limit=500)
During the reporting period, much time was spent on mobilizing the project, including recruitment of key project personnel and setting up project office (renovation and construction) in the Dry Zone Greening Department in Mandalay. The 4 Sector Specialists and Project Assistant were recruited in Dec 2014. The position of Monitoring and Evaluation Specialist is still vacant owing to limited expertise in the local market and capacity of potential candidates. The position has been readvertized three times and it is expected to be filled in the 2nd quarter of 2016. The Technical Specialist was recruited in 2nd quarter of 2015 (joined in April 2015) and the National Project Manager in the 3rd quarter of 2015 (joined in Aug 2015). After a delay of almost 3 months, the inception workshop was held in Aug 2015. The 1st Project Steering Committee meeting was held in Dec 2015, where the annual work plan for 2016 was approved. The Project Steering Committe meeting was postponed twice. The 1st Technical Advisory Group meeting for the project was held only in February 2016. The delay was mainly due to the availability of government members of the Project Steering Committee. While very few milestones have been met since the start of the project, it must be acknowledged that the Government and UNDP placed a lot of emphasis on laying the foundation for effective implementation in the following years to come. Setting the conditions for effective implementation was considered critical as this Adaptation Fund project is one of the very first large-scale donor assisted projects that involve the Government, after the transition to democracy in Myanmar. For this reason, this project is defining pathways and setting benchmarks in many ways for other donor projects that follow. Also this meant that many things in project implementation were new not only to the Government but also to UNDP Country Office. For example, the project team spent nearly three months to complete the selection of project target villages. This process took particularly long because the vulnerability of each of the 280 villages were verified through a ranking exercise involving a consultative process at local level - to mitigate the future risk of, for example, elite capture and unnecessary political interference. Baseline data were collected in parallel, resulting in the establishment of a database which will be used for supporting project implementation and M&E. The project team has also developed implementation guidelines and Terms of Reference for the delivery of activities under NGO/CSO engagement modality. The NGO/CSO assessment process took some time due to the long procedure of engaging NGOs/CSOs and new experience to the CO. A project communication strategy and monitoring and evaluation framework has also been developed and this will ensure effective monitoring of project during implementation. It should also be noted that there were miscommunications about focal counterpart agency with Dry Zone Greening Department in the early phase of project implementation, which led to the additional need of organizing consultations and added delays to the project timeline. The communication between UNDP and the DZGD and constructinve partnership has been improving over time. The 2015 floods that impacted most part of the country and the general elections in November 2015, as well as the subsequent change in government also affected progress to a certain extent. Moving forward, the project team is now set for accelerating field implementation. With the completion of the NGO/CSO engagement process, the terms of reference for the different work packages undert the project has been finalized for call for proposals from potential implementing partners. The project team has also instituted a system of monthly project coordination meeting with the counterpart government agency and implementation isses and bottlenecks are being addressed through this forum
| Progress on Key Milestones |  | Expected Progress |  | Progress to Date | Rating
Implementing Agency | Output 1.1: Identify specific locations in target villages for the following adaptation interventions: canals for water diversion; small-scale pumping systems; communal water tanks; tube wells; pound reserviors; and soil storage dams |  | Target villages selected based on a set of slection criteria and adaptation interventions identified for targetted villages |  | Secondary baseline data on agriculture, livestock, forestry, soil and water conservation have been collected. Target villages (280) have been identified in consultation with the government. | MS
| Output 1.1: Village level management scheme formulated which includes the roles and responsibilities of VWUG and distribution agreement across (vulnerable) households |  | Draft village level water management schemes guidelines, as well as water distribution agreements developed |  | The project team has discussed the need for guidelines and SOPs for Village Water User Groups with Water Resources Utilization Department and Department of Rural Development and they have welcomed our inputs in this regard. The work on guidelines and SOPs is already planned as an input from the project | MU
| Output 1.1: At least 50% of women's participation is encouraged to the workshops on water storage and capture interventions and participation monitored |  | At least 35% participation of women achieved in workshops on water storage and capture interventions |  | A monitoring and evaluation framework for the project has been drafted which takes into account the need to record gender disaggregated data during implementation. In addition, the database maintained by the project has recorded beneficiery information so as to assist in monitoring during implementation. | MU
| Output 1.1: Contribution of labour from women and/or landless improverished households is facilitated |  | Contributoin of labour from women and/or landless impoverished households facilitated and encouraged |  | All the TORs developed for the implementation of project activities by NGOs/CSOs have specifically outlined the need to engage landless and impoverished households for and labour-related activities | MS
| Output 1.1: Production of a report on the success and challenges of micro-scale water infrastructure |  | No progress expected in the 1st year of project implementation |  | No progress | MS
| Output 1.2: Finalize village-wise intervention type and size based on the level of denudation, ongoing surface runoff and topography |  | Target villages selected based on a set of slection criteria and adaptation interventions identified for targetted villages |  | During the design of the TOR for watershed and forestry interventions, tentative areas along with the type and size of interventions have been pre-identified in discussion with the forestry department and the Dry Zone Greening Department. These will be confirmed again, once the implementing partner has been deputed on the ground. | MU
| Output 1.2: Atleast 50% of women's participation is encouraged to the workshops on wtareshed rehabilitation programmes and participation monitored |  | At least 35% participation of women achieved in workshops on water storage and capture interventions |  | A monitoring and evaluation framework for the project has been drafted which takes into account the need to record gender disaggregated data during implementation. In addition, the database maintained by the project has recorded beneficiery information so as to assist in monitoring during implementation. | MU
| Output 1.2: Roles and responsibilities of women are clearly identified in the community management plan |  | No progress expected in the 1st year of project implementation |  | No progress | MS
| Output 1.2: Production of a report on the success and challenges of community forest management plan |  | No progress expected in the 1st year of project implementation |  | No progress | MS
| Output 1.2: Initial 30-year lease permission sought and granted for successfully managed community forests |  | No progress expected in the 1st year of project implementation |  | The team has discussed modalities of securing 30 year lease for community forestry management with the Forestry Department and this has been incorporated in the implementation guidelines prepared for the implementing partner. | MS
| Output 1.3: Initial call for participation will target primarily women; at minimum 50% of the members should be women |  | At least 35% participation of women achieved in workshops on water storage and capture interventions |  | No progress | MU
| Output 1.3: Information collected on ongoing agro-forestry practices will be gender disaggregated |  | Information collected on ongoing agro-forestry practices is gender-disaggregated |  | A draft template on the inventory of agro-forestry practices is in place and conisders collection of gender-disaggregated data. | MS
| Output 1.3: 1,700 hectares of homestead gardening in 76 villages established |  | Implementation of the activity iniitated with the deployment of implementing parner with a specifi TOR |  | The TOR for the engagement of implementing partner for this activity is ready and call for proposals will be sent out soon. | MU
| Output 1.3: 1500 hectares of farm boundary planting in 95 villages established |  | Implementation of the activity iniitated with the deployment of implementing parner with a specifi TOR |  | The TOR for the engagement of implementing partner for this activity is ready and call for proposals will be sent out soon. | MU
| Output 1.3: Participants of the monitoring visits encourage women's participation |  | Monitoring visits to project sites will include women participants so as to ensure gender considerations in activities |  | No progress | MU
| Output 1.3: Production of a report on the success and challenges of community forestry management plan |  | No progress expected in the 1st year of project implementation |  | No progress | MS
| Output 2.1: Organize a technical workshop to consolidate existing domestic and international knowledge on drought resistant crop varieties and seed banks inviting technical agencies such as Department of Agriculture, University of Agriculture, Department of Agriculture Research |  | Technical workshop to consolidate existing domestic and international knowledge on drought resistant crop varieties and seed banks inviting technical agencies such as Myanmar Agriculture Services, University of Agriculture, Department of Agriculture Research conducted |  | The TOR for this work package has been designed and include this activity as a key deliverable and it is included in the implementation guidelines. | MU
| Output 2.2: Quantative assessment of current post-harvest processes undertaken and reported |  | Quantative assessment of current post-harvest processes drafted |  | This activity is planned as part of the TOR on the promotion of climate resilient agriculture practices in the Dry Zone of Myanmar. | MU
| Output 2.2: Production of an assessment report on current post-harvest processes |  | No progress expected in the 1st year of project implementation |  | No progress | MS
| Output 2.2: Formulate a cost-sharing and maintenance plan in each village for the use of the thresher |  | Cost-sharing and maintenance plan in each village for the use of the thresher drafted |  | The procurement of threshers has been initiated. The work on the drafting of guidelines on cost-sharing and use of threshers is part of the TOR on promotion of climate resilient agriculture practices in the Dry Zone of Myanmar (which is ready for call for proposals). | MS
| Output 2.2: Women's participation in post-harvest trainings encouraged and gender-disaggregated participation record will be produced |  | No progress expected in the 1st year of project implementation |  | A monitoring and evaluation framework for the project has been drafted which takes into account the need to record gender disaggregated data during implementation. In addition, the database maintained by the project has recorded beneficiery information so as to assist in monitoring during implementation. | MS
| Output 2.2: Production of assessment reports on the effectiveness of harvest storage facilities and post-harvest handling techniques |  | No progress expected in the 1st year of project implementation |  | This activity is planned as part of the TOR on the promotion of climate resilient agriculture practices in the Dry Zone of Myanmar. | MS
| Output 2.3: Atleast 50% of the participants of the training on livestock production systems should be women. Gender disaggregated participants list will be produced |  | Atleast 35% of the participants of the training on livestock production systems are women |  | A monitoring and evaluation framework for the project has been drafted which takes into account the need to record gender disaggregated data during implementation. In addition, the database maintained by the project has recorded beneficiery information so as to assist in monitoring during implementation. | MU
| Output 2.3: Production of an assessment report on the effectiveness of diversified livestock production systems |  | No progress expected in the 1st year of project implementation |  | No progress | MS
| Output 3.1: Vulnerability assessment in townships will look at gender-differentiated vulnerability to climate risks |  | Vulnerability assessment in townships consider gender-differentiated vulnerability to climate risks |  | The TOR for the work on vulnerability assessments in townships are designed to be participatory in nature and women's participation will be considered during the process. | MU
| Output 3.2: Seasonal agriculture bulletins produced |  | No progress expected in the 1st year of project implementation |  | Discussions ongoing with DMH and RIMES to replicate/upscale ongoing pilot agro-advisory system in Nyaung U and Monywa townships. | MU
| Output 3.2: CBDRM committee will have women representatives and they will be assigned specific roles and responsibilities |  | CBDRM committees have women representatives with specific roles and responsibilities |  | The review and update of the CBDRM manual for Myanmar is being initiated.CBDRM committees have yet to be formed. This will likely take place only in 2017. | MU
[5 empty] | Overall Rating | MU
Please Provide the Name and Contact information of person(s) reponsible for completeling the Rating section
| Name: | Lat Lat Aye
| Email: | lat.lat.aye@undp.org
| Progress on Key Milestones |  | Expected Progress |  | Progress to Date | Rating
Other
Overall Rating
Please Provide the Name and Contact information of person(s) reponsible for completeling the Rating section
Name:
Email:
| Please justify your rating and address the following points: 1. Indicate trends, both positive and negative, in achievement of outcomes as per the project indicators. 2. Detail critical risks that have affected progress. 3. Outline response to MTR undertaken this reporting period. 4. Outline action plan to address projects with a rating of HU, U or MU. Please keep your input to 1200 words |  | By nature, the project needed a lot of preparatory work, including development of M&E plan, selection of beneficiary villages, base-line data and information collection, covering 280 villages across 5 townships located in different states/regions. The project team was able to accomplich these preparatory activities in the reporting period. Consultations with multi-government agencies, coordination at Regional, district and township levels and convening the Project Steering Committee (PSC) and Technical Working Group (TWG) took more time than expected. The project is the first Adaptation Fund project with a considerable volume of work on the ground and involves more than 5 government sectoral departments with limited knowledge and practices of participation and coordination with multi-stakeholders for adaptation initiatives. In addition, the 6-month period for transition to the new government after the election in October 2015, had partly impacted on delay of the project activities since the participation and responses from the government departments were delayed in convening PSC and TWG meetings. The project needs to procure a large volume of goods and services (seedlings, threshers, etc.). UNDP needs to ensure the procurement process is systematic. It takes some time in processing and selection of capable suppliers, NGOs, CSOs as responsible parties. Since much of the preparatory work has been completed in this reporting period, it is expected to deliver the project activities and meet the project targets as planned in the next reporting period.
Rating Definitions
|  |  | Highly Satisfactory (HS) | Project actions/activities planned for current reporting period are progressing on track or exceeding expectations to acheive all major outcomes/outputs for given reporting period, without major shortcomings. The project can be presented as “good practice”.
|  |  | Satisfactory (S) | Project actions/activities planned for current reporting period are progressing on track to achieve most of its major outcomes/outputs with only minor shortcomings.
|  |  | Marginally Satisfactory (MS) | Project actions/activities planned for current reporting period are progressing on track to achieve most major relevant outcomes/outputs, but with either significant shortcomings or modest overall relevance.
|  |  | Marginally Unsatisfactory (MU) | Project actions/activities planned for current reporting period are not progressing on track to achieve major outcomes/outputs with major shortcomings or is expected to achieve only some of its major outcomes/outputs.
|  |  | Unsatisfactory (U) | Project actions/activities planned for current reporting period are not progressing on track to achieve most of its major outcomes/outputs.
|  |  | Highly Unsatisfactory (U) | Project actions/activities planned for current reporting period are not on track and shows that it is failing to achieve, and is not expected to achieve, any of its outcomes/outputs.

## Project Indicators
PROJECT Indicators
Please provide all indicators being tracked for the project as outlined in the project document
Type of Indicator (indicators towards Objectives, Outcomes, etc…)
Type of Indicator | Indicator | Baseline | Progress since inception | Target for Project End
Objective | % of households in target site implementing climate change adaptation livelihood measures introduced by the project | Current agricultural and livestock rearing practices among subsistence farmers are based on historical climatic conditions and trends and are unsuited to increased drought conditions that are becoming increasingly frequent in the Dry Zone in Myanmar | Project activities and associated TORs for implementation have been designed with the objective of benefiting mainly the landless and impoverished households | By the end of the project, at least 61% of impoverished farming households or the landless, equivalent to approximately 17,850 households (11,500 agriculture and 6,300 livestock) benefit from and implement climate-resilient agriculture or livestock practices
| % of Dry Zone hoseholds using climate risk information to adjust their livelihood behavior | Currently climate risk information on sudden onset of disasters is delivered only to those houses with TV/radio and yet the level of interpretation and response is low. The outreach and understanding of information on slow onset of disasters are even lower. | The project is currently exploring options with DMH and RIMES to produce and communicate climate information in the form of agro-advisories so that farmers are able to plan ahead and adapt to the changing climate | At least 50% of all households in target location (based on random sampling), equivalent to 25,000 households, report that they have changed their livelihood behaviour based on climate risk information produced by the project
| % of Dry Zone households with access to early warning information on sudden onset of disasters | Currently climate risk information on sudden onset of disasters is delivered only to those houses with TV/radio and yet the level of interpretation and response is low. The outreach and understanding of information on slow onset of disasters are even lower. | The project is currently exploring options with DMH and RRD to employ communication tools - such as SMS and social media applications. UNDP has been requested by RRD to suport this initiative, which is part of the 100 days plan of the RRD | At least 75% of all households in target location, equivalent to 38,000, receive early warning in a timely manner.
Outcome 1 | Outcome Indicator 1: % of Dry Zone farmers reporting increased freshwater availability during dry periods | 74% of households in project targeted townships area currently face shortages of fresh water supply for domestic and agricultural use | The project has planned activities such as micro-watershed and natural forest conservation, homestead and farm boundary plantation and capacity building and demonstration of soil and eater conservation activities to ensure freshwater supply for drinking and agriculture | At least 60% of households facing water shortages in 280 villages in the five project targeted townships report increased freshwater availability during dry periods
| 1.1. Additional community-based freshwater supply and storage infrastructure put in place in drought-prone villages | 0 additional freshwater supply and/or storage infrastructure in drought-prone villages to account for climate change-induced increases in drought | The recruitment of a technical firm to assess the needs and feasibility of small-scale water infrastructure in specific drught-prone locations is underway. This will result in the preparation of TOR and design of small-scale water infrastructure to be put in place in 2017 | 45 canals for water diversion constructed, 70 small-scale water pumping systems installed, 56 communal water tanks (500 galoons) incl. pipes installed, 40 shallow tube wells constructed, 150 communal ponds rehabilitated or constructed, 10 deep tube wells (new and repaired/renovated), 1,156 ha of land covered with soil and water conservation techniques, Trainings on water infrastructure, soil & water conservation, operation and management, Water Usage Groups formed with by laws
| 1.2. Hectares of watershed area protected through community-based afforestation, reforestation and regeneration practices | 1,500 ha of natural forest conservation and community based reforestation practices in the critical watershed area in the project area | A detail TOR with BoQ and implementation guidelines have been prepared by an international expert. The TOR is ready to be advertized | 3,913 ha of natural forest conservation, 1,458 ha of community forest establishment including (# of community forest management plan) 770 ha of tree planting activities on public land, Micro-watersheds (661ha) Road-side planting (35.5ha) Religous compounds (32.2ha) Schools (38.5ha) Clinics (2.8ha)
| 1.3. Hectares of land covered by systematic new agroforestry plantations | 160 ha of traditional agro-forestry home garden and 430 ha of farm boundary plantations currently exist in 280 villages in five targeted townships | A detail TOR with BoQ and implementation guideline have been prepared by an international expert. The TOR is ready to be advertized | 1,000 ha of homestead gardening/agro-forestry plots established in 76 villages, 1,500 ha of farm boundary plantations in 95 villages
Outcome 2 | Outcome Indicator 2: Number of climate-resilient agricultural and livestock practices demonstrated and adopted to support adaptation of marginal farmers and landless households | Agricultural and livestock practices and extension services in the Dry Zone pay only limited attention to climate change risks. | Climate-resilient agriculture and livestock activities under the project have been packaged in a way that specifically benefit marginal farmers and landless households | By the end of the project, at least 6 discrete agricultural adaptation and diversified livestock rearing practices are demonstrated including resilient varieties, on-farm water management techniques, soil management practices, planting techniques, post-harvest processing, and diversified livestock breeds.
| 2.1.1. Number of Dry Zone farmers exposed to and involved in climate resilient farming techniques | In project target villages, farmers have (not been exposed) only limited exposure to climate-resilient farming techniques | A project database with details on beneficiery households disaggregated by land holding has been established so that efficacy of capacity building interventions can be monitored during implementation | By the end of the project, at least 11,550 (11,200 farmers plus 350 others) households, extension workers and CSO/NGO members in the target townships are trained on climate-resilient farming methods. Trainings on (#/hhs/m-f): Climate resilient farming methods Water smart practices (AWD) Tanahka intercropping Fruit tree drip irrigation Organic farming and vermiculture
| 2.1.2. Accessibility to drought-resilient seed varieties | Only (five) limited seed (banks) sourcess are available in the target townships (one per each township) | Discussion held with Department of Agriculture, Department of Agriculture Research and Yezin Agriculture University in sourcing drought-resilient seed varieties, which in turn will be multiplied and distributed to additional households within the project area | At least 140 villages produce climate-resilient seed varities, Trainings on climate-resilient seed multiplication.
| 2.1.3. Number of project and non-project community members participating in exchange visits and demonstration plots | Currently there is no initiatives in the Dry Zone promoting cross exchange between Townships of practical knowledge on climate resilient farming techniques | The planned interventions on promotion of climate-resilient agriculture practices includes exchange visit of farmers to learn from each others' experience | At least 20% of community participants in exchange visits and farmers field demonstrations are from non-project target villages, Farmer field schools on climate change, At least 50 participatory demonstration plots on climate-resilient agricultural practices are established
| 2.2. % of households who report reduced harvest losses due to improved post-harvest processing and storage | Only few households (farmers) apply improved post-harvest processing techniques | To reduce post harvest losses, the project plans to provide rice and multi-crop threshers, the procurement of which is underway. In addition, the project will also provide post-harvest storage facilities based on needs of the beneficieries | 80% of target households (9,240 of 11,550) report reduced post-harvest losses through the use of improved processing and storage technology, 20 rice threshers and 120 multi-crop threshers, Establishment of thresher groups (140), Trainings and participatory assessments of post harvest loss, Elevated storage systems (36)
| 2.3. Number of landless and marginal households with increased diversity of livestock assets | Majority of impoverished farmers (either landless or those with less than 2.5 hectares of land) in the Dry Zone have zero or small number of livestock: 65% have no livestock and 35% own some livestock | The project has already planned to deliver improved varieties of dought-resilient livestock species and to do this the project will employ the livestock banking system that is being implemented currently | By the end of the project, at least 6,300 marginal and landless households have increased the diversity of livestock assets. Diversity in types: Cattle Sheep Goat Pig Poultry Climate-resistant/improved breeds
Outcome 3 | Outcome Indicator 3-1: % of Dry Zone households using climate risk information to adjust their livelihood behavior | Currently climate risk information on sudden onset of disasters is delivered only to those houses with TV/radio and yet the level of interpretation and response is low. The outreach and understanding of information on slow onset of disasters are even lower. | The project is currently exploring options with DMH and RIMES to produce and communicate climate information in the form of agro-advisories so that farmers are able to plan ahead and adapt to the changing climate | At least 50% of all households in target location (based on random sampling), equivalent to 25,000 households, report that they have changed their livelihood behaviour based on climate risk information produced by the project
| Outcome Indicator 3-2: % of Dry Zone households with access to early warning information on sudden onset of disasters | Currently climate risk information on sudden onset of disasters is delivered only to those houses with TV/radio and yet the level of interpretation and response is low. The outreach and understanding of information on slow onset of disasters are even lower. | The project is currently exploring options with DMH and RRD to employ communication tools - such as SMS and social media applications. UNDP has been requested by RRD to suport this initiative, which is part of the 100 days plan of the RRD | At least 90% of all households in target location, equivalent to 45,600, receive early warning in a timely manner.
| 3.1. Number of climate risk maps, vulnerability assessments and scenarios in active use by township authorities, NGOs and CBOs to improve planning decisions and prioritize investment actions | No climate risk maps, vulnerability assessments and scenarios in active use by township authorities, NGOs and CBOs to improve planning decisions and prioritize investment actions | The terms of reference for the work on vulnerability assessment and mapping is ready and will be advertized soon | Climate hazard maps, vulnerability assessments and risk scenarios are available in each township
| 3.2.1. Number of local institutions that issue regular warning and forecasting communications to community-based organisations and vulnerable households | Currently, no such information is available except weekly/mothly forecats boradcasted over TV/radio | The recruitemnt of a consultant for the review and update of CBDRM manual is ongoing. The establishment of CBDRM committees will be done in 2017. | 70 community based disaster risk management (CBDRM) committees are formed to relay climate early warning information from the Township DPC, 5 Climate Risk Information sub-committees established within the Township Disaster Preparedness Committee
| 3.2.2. The number of climate related information materials produced to assist Dry Zone farmers to adjust their livelihood behavior | Not available | The project is currently exploring options with DMH and RIMES to produce and communicate climate information in the form of agro-advisories so that farmers are able to plan ahead and adapt to the changing climate | At least six agro-meteorological bulletins; two early warning and disaster response bulletins/posters; four guidance notes on resilient agricultural/livestock practices produced

## Lessons Learned
QUALITATIVE MEASURES and LESSONS LEARNED
Please complete the following section every reporting period
Implementation and Adaptive Management | Response
What implementation issues/lessons, either positive or negative, affected progress? | The implementation of the project has been slow due to challenges in mobilizing the project and delays in organizing the inception workshop (29 Aug 2015), project steering committee meeting (9 Dec 2015) and the first technical advisory group meeting (18 Feb 2016). As this is one of the first projects of its kind that the Myanmar is implementing, there is no prior experience and benchmarks. Also given the political context in Myanmar, there is also limited understanding of the roles and responsibilities in project management - on the part of the government. The recruitment of key project personnel - Technical Specialist (April 2015) and National Project Manager (Aug 2015) took place only after all other support staff were recruited (Dec 2014). It would have been more strategic for the project to recruit the National Project Manager and the Technical Specialist before recruitment of support staff. The Monitoring and Evaluation Specialist position is still vacant due to challenges in finding qualified candidates. This is a critical project position and in the absence of a full time staff, existing staff have had to fill in the gap. The identification of project target villages took some time as it involved stakeholder consultataions at the local level - which also involved bureaucratic government procedures in seeking permissions to conduct these consultations. Ideally, this process should have have been conducted right after the design of the project or in the initial stages of project implementation or even during the design of the project. The delay in project implementation is also because the NGO/CSO assessment process which took some time due to the lengthy procedure of engaging NGOs/CSOs,as well as due to the fact that there has been no prior experience in the UNDP Country Office on this matter. This issue should have been clarified before the actual implementation of the project or during the initial stages in 2014. In addition, staff capacity in the project team is also a concern. There were issues regarding designation of focal government counterpart for the project, but this has been clarified now. There is a need to clarify the roles and rsponsibilities of government counterparts in project management and implementation. This is being continuously addressed through various forums such as the technical advisory group and monthly project ocordination meetings. Overall, this is a complex project with multiple government partners and with the objective of serving a large geographical area (50,000 households in 280 villages under 5 townships in 3 regions of Myanmar's dry zone) through engagement of NGOs/CSOs as delivery partners. Given the political context of Myanmar, it would have been useful if implementation modalities were thought through well before the actual implementation of the project.
Were there any delays in implementation? If so, include any causes of delays. What measures have been taken to reduce delays? | Yes, the overall implementation is estimated to be behind schedule by approximately 10-11 months. However, despite initial delays in holding the inception workshop and the 1st project steering committee meeting, the project team was able to complete the process of identification of 280 target villages and collect baseline data for the target areas. A project database has been established, which will assist the project team to monitor progress and assess results during and after implementation. The project communication startegy and monitoring and evaluation frameowrk has also been drafted to support communication of project results/impacts and to ensure adequate monitoring and oversight of project activities during implementation. Initially, there was unclarity regarding the focal government agency. But the Dry Zone Greening Department is now officially designated as the counterpart agency and the project has institutionalize monthly project coordination meetings with the government counterpart agency. The forum is being used currently to address implementation challenges and bottlenecks and the arrangement is working well. Despite the lengthy procedures, the NGO/CSO capacity assessment process has been completed and a roster of NGOs/CSOs has been established. The project team now has to package the activities together and call for proposals from potential NGOs/CSOs for implementaiton. Once implementation starts on the ground, the project team will need to ensure proper monitoring and oversight of field activities so as to ensure achievement of project results. The project staff have also undergone a procurement training in February 2015 with the support of UNDP procurement team. This has enhanced staff understanding on UNDP procurement procedures. Other issues such as staff performance management and work planning are being continuouly addressed through day to day mentoring and coaching by the Technical Specialist.
Describe any changes undertaken to improve results on the ground or any changes made to project outputs (i.e. changes to project design) | There has been no change on the project outputs
How have gender considerations been taken into consideration during the reporting period? What have been the lessons learned as a consequence of inclusion of such considerations on project performance or impacts? | The stakeholder consultation meetings and project target village selection process have considered equal participation of men and women. As women headed households are one of the key beneficieries of the project, the project team will continue to provide the necessary thrust and encourage equal participation of men and women in project activities.
Please complete the following section at mid-term and project completion
Lessons for Adaptation | Response
Climate Resilience Measures
What have been the lessons learned, both positive and negative, in implementing climate adaptation measures that would be relevant to the design and implementation of future projects/programmes for enhanced resilience to climate change? | N/A
What is the potential for the climate resilience measures undertaken by the project/programme to be replicated and scaled up both within and outside the project area? | N/A
Concrete Adaptation Interventions
What have been the lessons learned, both positive and negative, in implementing concrete adaptation interventions that would be relevant to the design and implementation of future projects/programmes implementing concrete adaptation interventions? | N/A
What is the potential for the concrete adaptation interventions undertaken by the project/programme to be replicated and scaled up both within and outside the project area? | N/A
Community/National Impact
What would you consider to be the most successful aspects for the target communities? | N/A
What measures are/have been put in place to ensure sustainability of the project/program results? | N/A
What measures are being/could have been put in place to improve project/program results? | N/A
Knowledge Management
How has existing information/data/knowledge been used to inform project development and implementation? What kinds of information/data/knowledge were used? | N/A
If learning objectives have been established, have they been met? Please describe. | N/A
Describe any difficulties there have been in accessing or retrieving existing information (data or knowledge) that is relevant to the project. Please provide suggestions for improving access to the relevant data. | N/A
Has the identification of learning objectives contributed to the outcomes of the project? In what ways have they contributed? | N/A

## Results Tracker
Results Tracker for Adaptation Fund (AF) Projects
Goal: Assist developing-country Parties to the Kyoto Protocol that are particularly vulnerable to the adverse effects of climate change in meeting the costs of concrete adaptation projects and programmes in order to implement climate-resilient measures. Impact: Increased resiliency at the community, national, and regional levels to climate variability and change.
Important: Please read the following guidance document (also posted on the Adaptation Fund website) before entering your data
Link: http://www.adaptation-fund.org/sites/default/files/Results%20Framework%20and%20Baseline%20Guidance%20final.pdf
Adaptation Fund Strategic Results Framework
Project ID | PIMS 4703
Implementing Entity | United Nations Development Programme
Type of implementing entity | MIE
Country | Myanmar
Region | Five townships (Shwebo, Moneywa, Myin Chan, Nyaung Oo and Chauk) in Myanmar's Dry Zone
Sector | Multi-sector
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Impact: Increased resiliency at the community, national, and regional levels to climate variability and change | Core Indicator: No. of beneficiaries |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project
|  | Total | 0 | 0 | 0 | Total |  | 229155 | 1200 | Total |  |  |  | Total
|  | % of female beneficiaries |  | 0% |  | % of female beneficiaries |  | 53% |  | % of female beneficiaries |  |  |  | % of female beneficiaries
|  | % of Youth beneficiaries |  |  |  | % of Youth beneficiaries |  |  |  | % of Youth beneficiaries |  |  |  | % of Youth beneficiaries
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 1: Reduced exposure to climate-related hazards and threats | Indicator 1: Relevant threat and hazard information generated and disseminated to stakeholders on a timely basis | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness
|  | Total | 229155 | Drought | 1: Ineffective | Total | 229155 | Drought | 4: Effective | Total |  |  |  | Total
|  | % of female targeted | 53% |  |  | % of female targeted | 53% |  |  | % of female targeted |  |  |  | % of female targeted
Output 1.1 Risk and vulnerability assessments conducted and updated | Indicator 1.1: No. of projects/programmes that conduct and update risk and vulnerability assessments | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | 0 | Multi-sector | Local | 1: No plans conducted or updated | 1 | Multi-sector | Local | 3: Risk and vulnterability assessments completed or updated
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
Output 1.2 Targeted population groups covered by adequate risk reduction systems | Core Indicator 1.2: No. of Early Warning Systems | No. of adopted Early Warning Systems | Category targeted | Hazard | Drought | No. of adopted Early Warning Systems | Category targeted | Hazard | Drought | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  | 0 | 2: Monitoring and warning service | Geographical coverage | Local | 1 | 2: Monitoring and warning service | Geographical coverage | Local |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities | 5 |  |  | Number of municipalities | 5 |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 2: Strengthened institutional capacity to reduce risks associated with climate-induced socioeconomic and environmental losses | Indicator 2: Capacity of staff to respond to, and mitigate impacts of, climate-related events from targeted institutions increased | Number of staff targeted |  | Sector | Capacity level | Number of staff targeted |  | Sector | Capacity level | Number of staff targeted |  | Sector | Capacity level | Number of staff targeted |  | Sector | Capacity level
|  | Total |  |  |  | Total |  |  |  | Total |  |  |  | Total
|  | % of female targeted |  |  |  | % of female targeted |  |  |  | % of female targeted |  |  |  | % of female targeted
Output 2.1 Strengthened capacity of national and sub-national centres and networks to respond rapidly to extreme weather events | Indicator 2.1.1: No. of staff trained to respond to, and mitigate impacts of, climate-related events | Total staff trained | % of female staff trained | Type |  | Total staff trained | % of female staff trained | Type |  | Total staff trained | % of female staff trained | Type |  | Total staff trained | % of female staff trained | Type
| Indicator 2.1.2: No. of targeted institutions with increased capacity to minimize exposure to climate variability risks | Type | Scale | Sector | Capacity level | Type | Scale | Sector | Capacity level | Type | Scale | Sector | Capacity level | Type | Scale | Sector | Capacity level
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 3: Strengthened awareness and owernship of adaptation and climate risk reduction processes | Indicator 3.1: Increase in application of appropriate adaptation responses | Percentage of targeted population applying adaptation measures |  | Sector |  | Percentage of targeted population applying adaptation measures |  | Sector |  | Percentage of targeted population applying adaptation measures |  | Sector |  | Percentage of targeted population applying adaptation measures |  | Sector
|  | 0% |  | Multi-sector |  | 61% |  | Multi-sector
Output 3: Targeted population groups participating in adaptation and risk reduction awareness activities | Indicator 3.1.1: Percentage in targeted population awareness of predicted adverse impacts of climate change, and of appropriate responses | No. of targeted beneficiaries | % of female participants targeted | Level of awareness |  | No. of targeted beneficiaries | % of female participants targeted | Level of awareness |  | No. of targeted beneficiaries | % of female participants targeted | Level of awareness |  | No. of targeted beneficiaries | % of female participants targeted | Level of awareness
|  | 0 | 0% | 2: Partially not aware |  | 24498 | 43% | 4: Mostly aware
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 4: Increased adaptive capacity within relevant development sector services and infrastructure assets | Indicator 4.1: Increased responsiveness of development sector services to evolving needs from changing and variable climate | Project/programme sector | Geographical scale | Response level |  | Project/programme sector | Geographical scale | Response level |  | Project/programme sector | Geographical scale | Response level |  | Project/programme sector | Geographical scale | Response level
|  | Water management | Local | 2: Partially responsive (Lacks most elements) |  | Water management | Local | 4: Mostly responsive (Most defined elements)
| Core Indicator 4.2: Assets produced, developed, improved or strengthened | Sector | Targeted asset | Changes in asset (quantitative or qualitative) |  | Sector | Targeted asset | Changes in asset (quantitative or qualitative) |  | Sector | Targeted asset | Changes in asset (quantitative or qualitative) |  | Sector | Targeted asset | Changes in asset (quantitative or qualitative)
|  | Water management | 2: Physical asset (produced/improved/strenghtened) | 2: Somewhat improved |  | Water management | 2: Physical asset (produced/improved/strenghtened) | 4: Mostly Improved
Output 4: Vulnerable development sector services and infrastructure assets strengthened in response to climate change impacts, including variability | Indicator 4.1.1: No. and type of development sector services to respond to new conditions resulting from climate variability and change | Number of services | Type |  | Sector | Number of services | Type |  | Sector | Number of services | Type |  | Sector | Number of services | Type |  | Sector
|  | 0 | Community |  | Water management | 45 | Community |  | Water management
|  | 0 | Community |  | Water management | 70 | Community |  | Water management
|  | 0 | Community |  | Water management | 56 | Community |  | Water management
|  | 0 | Community |  | Water management | 150 | Community |  | Water management
|  | 0 | Community |  | Water management | 50 | Community |  | Water management
|  | 0 | Community |  | Water management | 1156 | Community |  | Water management
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at Completion
Outcome 5: Increased ecosystem resilience in response to climate change and variability-induced stress | Indicator 5: Ecosystem services and natural resource assets maintained or improved under climate change and variability-induced stress | Natural resource improvement level |  | Sector | Type | Natural resource improvement level |  | Sector | Type | Natural resource improvement level |  | Sector | Type | Natural resource improvement level |  | Sector | Type
|  | 2: Partially effective |  | Agriculture | land | 3: Moderately effective |  | Agriculture | land
Output 5: Vulnerable ecosystem services and natural resource assets strengthned in response to climate change impacts, including variability | Core Indicator 5.1: Natural Assets protected or rehabilitated | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Catchment area/Watershed/Aquifer | 1500 | ha protected | 2: Partially effective | Catchment area/Watershed/Aquifer | 6141 | ha protected | 4: Effective
|  | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Forests | 160 | ha protected | 2: Partially effective | Forests | 2483 | ha protected | 4: Effective
|  | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Forests | 430 | ha protected | 2: Partially effective | Forests | 1500 | ha protected | 4: Effective
|  | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Baseline information |  |  |  | Targeted performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 6: Diversified and strengthened livelihoods and sources of income for vulnerable people in targeted areas | Indicator 6.1: Increase in households and communities having more secure access to livelihood assets | No. of targeted households | % of female headed households | Improvement level |  | No. of targeted households | % of female headed households | Improvement level |  | No. of targeted households | % of female headed households | Improvement level |  | No. of targeted households | % of female headed households | Improvement level
| Indicator 6.2: Increase in targeted population's sustained climate-resilient alternative livelihoods | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
|  | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
|  | 0 | 53% | From 10% to 20% | Livestock production | 6300 | 53% | From 10% to 20% | Livestock production
|  | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
|  | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
Output 6 Targeted individual and community livelihood strategies strengthened in relation to climate change impacts, including variability | Indicator 6.1.1: No. and type of adaptation assets created or strengthened in support of individual or community livelihood strategies | Number of Assets | Type of Assets | Sector | Adaptation strategy | Number of Assets | Type of Assets | Sector | Adaptation strategy | Number of Assets | Type of Assets | Sector | Adaptation strategy | Number of Assets | Type of Assets | Sector | Adaptation strategy
| Core Indicator 6.1.2: Increased income, or avoided decrease in income | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
0
|  | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | 6300 | Livestock production |  | 0 | 6300 | Livestock production |  | 100
|  | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 7: Improved policies and regulations that promote and enforce resilience measures | Indicator 7: Climate change priorities are integrated into national development strategy | Integration level |  |  |  | Integration level |  |  |  | Integration level |  |  |  | Integration level
Output 7:Improved integration of climate-resilience strategies into country development plans | Indicator 7.1: No. of policies introduced or adjusted to address climate change risks | No. of Policies introduced or adjusted | Sector | Scale | Type | No. of Policies introduced or adjusted | Sector | Scale | Type | No. of Policies introduced or adjusted | Sector | Scale | Type | No. of Policies introduced or adjusted | Sector | Scale | Type
| Indicator 7.2: No. of targeted development strategies with incorporated climate change priorities enforced | No. of Development strategies | Regulation |  | Effectiveness | No. of Development strategies | Regulation |  | Effectiveness | No. of Development strategies | Regulation |  | Effectiveness | No. of Development strategies | Regulation |  | Effectiveness
Glacier lake outburst flood
|  | Inland flooding | fr | biological assets |  | Company policy | 5: Fully enforced (All elements implemented)
|  | Salinization | Decrease | land |  | Communication & Information policy | 4: Enforced (Most elements implemented)
|  | Drought | Same | water areas |  | Defense policy | 3: Partially enforced (Some elements implemented)
|  | Wind |  | subsoil assets | increased adpative capacity | Domestic policy | 2: Partially not enforced (Most elements not implemented) |  | Agribusiness
|  | Coastal flooding |  | air | achieved | Economic policy | 1: Not enforced (No elements implemented) |  | Agricultural-related | Financial capital
|  | Storm surge | Please choose |  | enhanced level of protection | Education policy |  |  | Agriculture | Human capital
|  | Hurricane | Selected | [5 empty] | Aquaculture | Physical capital
|  |  | Not relevant |  |  | 5: All (Fully integrated) |  |  | Construction/repairing business | Social capital
[6 empty] | 4: Most |  |  | Cultivation | Natural capital
[6 empty] | 3: Some |  |  | Fishing | Personal capital
Select | 5: All | Select |  |  | Community | 2: Most not integrated |  | Other | Forestry | Adaptation strategies
1 | 4: Almost all | Private | Type | Yes | Multi-community | 1: None |  | Agriculture | Handicrafts
2 | 3: Half | Public | Scale | No | Departmental |  |  | Coastal management | Livestock production
3 | 2: Some | NGO | Sector |  | National |  |  | Disaster risk reduction | Manufacturing
4 | 1: None |  |  |  |  | 5: Very high improvement | Established | Food security | other
|  | National |  |  |  | 4: High improvement | Maintained | Health | Services
|  | Regional |  |  |  | 3: Moderate improvement | Improved | Urban development | Tourism-related
|  | Local |  |  |  | 2: Limited improvement |  | Water management | Trading
[6 empty] | 1: No improvement |  | Multi-sector
|  | 1 -generated information is irrelevant, and neither the stakeholders reached nor the timeframe managed were achieved | 1: No info transferred on time | 4: High capacity | 5: Fully aware | 5: Highly responsive (All defined elements ) | 5: Fully improved | Roads | 5: Very effective
Asia-Pacific | NIE | 2 -the existence of some challenge in any of the three aspects of the indicator (generation of dissemination, stakeholders reached or timeframe managed) | 2: Somewhat info transferred | 3: Medium capacity | 4: Mostly aware | 4: Mostly responsive (Most defined elements) | 4: Mostly Improved | Gov Buildings | 4: Effective
Latin America and Caribbean | RIE | 3 -relevant information is generated and disseminated to all identified stakeholders on timely basis | 3: Info transferred on time | 2: Low capacity | 3: Partially aware | 3: Moderately responsive (Some defined elements) | 3: Moderately improved | Causeways | 3: Moderately effective
Africa | MIE |  |  | 1: No capacity | 2: Partially not aware | 2: Partially responsive (Lacks most elements) | 2: Somewhat improved | Airports | 2: Partially effective
Eastern Europe |  |  |  |  | 1: Aware of neither | 1: Non responsive (Lacks all elements ) | 1: Not improved | Schools | 1: Ineffective
| ha protected | [6 empty] | Training Centres
| ha rehabilitated | [5 empty] | Monitoring/Forecasting capacity | Hospitals
Afghanistan, Islamic Rep. of | km protected | [5 empty] | Policy/regulatory reform | Drinking water systems
Angola | km rehabilitated | 1: Risk knowledge | 1: No plans conducted or updated |  |  |  | Capacity development | Other
Albania |  | 2: Monitoring and warning service | 2: Undertaking or updating of assessments in progress |  |  | Communication & Information policy | Sustainable forest management
Argentina |  | 3: Dissemination and communication | 3: Risk and vulnterability assessments completed or updated |  |  | Domestic policy | Strengthening infrastructure | 1: Health and Social Infrastructure (developed/improved)
Armenia | Forests | 4: Response capability |  |  |  | Economic policy | Supporting livelihoods | 2: Physical asset (produced/improved/strenghtened)
Antigua and Barbuda | Mangroves |  |  |  |  | Education policy | Mangrove reforestation
Azerbaijan | Coasts |  | From 0 to 0.5% |  |  | Energy policy | Coastal drainage and infrastructure
Burundi | Rangelands |  | From 0.5 to 1% |  |  | Environmental policy | Irrigation system
Benin | Cultivated land/Agricultural land |  | From 1% to 5% |  |  | Foreign policy | Community-based adaptation
Burkina Faso | Catchment area/Watershed/Aquifer |  | From 5% to 10% |  |  | Health policy | Erosion control
Bangladesh | Protected areas/National parks |  | From 10% to 20% |  |  | Housing policy | Soil water conservation
Bulgaria | Other |  | From 20% to 30% |  |  | Human resource policies | Microfinance
Bahrain |  |  | From 30% to 40% |  |  | Information policy | Special Program for women
Bahamas, The |  |  | From 40% to 50% |  |  | Macroeconomic policy | Livelihoods
Bosnia and Herzegovina |  |  | Above 50% |  |  | Monetary policy | Water storage
Belarus | [5 empty] | Population policy | ICT and information dissemination
Belize | [5 empty] | Private policy
Bolivia | [5 empty] | Public policy
Brazil | [5 empty] | Science policy
Barbados | [5 empty] | Social policy
Bhutan |  | 3- relevant information is generated and disseminated to all identified stakeholders on timely basis |  |  |  | Transportation policy
Botswana |  | describe |  |  |  | Urban policy
Central African Republic |  | 2- the existence of some challenge in any of the three aspects of the indicator |  |  |  | Water policy
Chile |  | describe |  |  |  | Other policy
China, People's Republic of |  | 1- generated information is irrelevant and neither the stakeholders reached nor the timeframe managed were achieved
Cote d'Ivoire |  | describe
Cameroon
Congo, Dem. Rep. of
Congo, Republic of
Cook Islands
Colombia
Comoros
Cape Verde
Costa Rica
Cuba
Czech Republic
Djibouti
Dominica
Dominican Republic
Algeria
Ecuador
Egypt
Eritrea
Estonia
Ethiopia
Fiji
Micronesia, Fed. States of
Gabon
Georgia
Ghana
Guinea
Gambia, The
Guinea-Bissau
Equatorial Guinea
Grenada
Guatemala
Guyana
Honduras
Croatia
Haiti
Hungary
Indonesia
India
Iran, Islamic Republic of
Jamaica
Jordan
Kazakhstan
Kenya
Kyrgyz Republic
Cambodia
Kiribati
Saint Kitts and Nevis
Korea, Republic of
Lao People's Democratic Republic
Lebanon
Liberia
Libya
Saint Lucia
Sri Lanka
Lesotho
Lithuania
Latvia
Morocco
Moldova
Madagascar
Maldives
Mexico
Marshall Islands
Macedonia, former Yugoslav Republic of
Mali
Malta
Myanmar
Montenegro
Mongolia
Mozambique
Mauritania
Mauritius
Malawi
Malaysia
Namibia
Niger
Nigeria
Nicaragua
Niue
Nepal
Nauru
Oman
Pakistan
Panama
Peru
Philippines
Palau
Papua New Guinea
Poland
Korea, Dem. People's Rep. of
Paraguay
Romania
Russian Federation
Rwanda
Saudi Arabia
Sudan
Senegal
Solomon Islands
Sierra Leone
El Salvador
San Marino
Serbia
Sao Tome and Principe
Suriname
Slovak Republic
Slovenia
Swaziland
Seychelles
Syrian Arab Republic
Chad
Togo
Thailand
Tajikistan
Turkmenistan
Tonga
Trinidad and Tobago
Tunisia
Turkey
Tuvalu
Tanzania
Uganda
Ukraine
Uruguay
Uzbekistan
Saint Vincent and the Grenadines
Venezuela
Vietnam
Vanuatu
Samoa
Yemen, Republic of
South Africa
Zambia
Zimbabwe
Timor-Leste
Note on G41: Hans van Noord: Townships i.e.
Note on F63: Hans van Noord: Combination of agriculture and livestock sectors
Note on H63: Hans van Noord: ProDoc states 75% 24498/40162 = 61%
Note on H65: Hans van Noord: 11550 agri, 6300 livestock, 6648 agroforestry and homestead gardening (based on 2.5 ha cut off)
Note on I65: UNDP: 97835(female)/229155(total) based on 2.5 ha cut off
Note on L67: Hans van Noord: template has mistake: indicated Target at completion instead at Mid-term
Note on P67: Hans van Noord: Should be "Performance at completion"instead of "Target at completion"
Note on H78: Hans van Noord: 45 small canals 70 small scale water pumps 56 communal water tanks 150 communal ponds rehabilitated or constructed 10 deep tube wells 1156 ha land covered with soil and water conservation techniques 40 shallow tube wells
Note on H79: Hans van Noord: small pumps
Note on H80: Hans van Noord: storage tanks
Note on H81: Hans van Noord: ponds
Note on H82: Hans van Noord: 40 shallow and 10 deep wells
Note on H83: Hans van Noord: Ha of watershed management area
Note on H85: Hans van Noord: Template has mistake: instead of baseline this should read "Target at completion"
Note on L85: Hans van Noord: Mistake in header: should read "Performance at mid-term" instead of "baseline"
Note on P85: Hans van Noord: Replaced "Baseline Information" title
Note on F87: Hans van Noord: In fact it is Forestry and Agroforestry or watershed management
Note on G87: Hans van Noord: In fact combination of vegetation cover increase to enhance soil- and water conservation
Note on E89: Hans van Noord: 1500ha of natural forest conservation and community based reforesation practices in critical watershed areas and 160ha agrofestry and 430ha of farm boundary plantations
Note on I89: Hans van Noord: Summation of: 3913 of NFC 1458 of CF, and 770 of tree planting on public land
Note on I92: Hans van Noord: 1000 homestead gardening 20ha demo plots 2ha silvopasture development 3 tree-intercropping 1458ha Taungya crop
Note on I95: Hans van Noord: Farm boundary plantation

## Units for Indicators
Fund Outcome Indicator Units
1. Generation of relevant data, Stakeholders, and Timeliness 2.1. Include both qualitative and quantitative measures of capacity level within targeted institutions 2.2. Number (men and women and other vulnerable groups) 3.1. Use scale from 1 to 5: 5: Fully aware 4: Mostly aware 3: Partially aware 2: Partially not aware 1: Aware of neither predicted adverse impacts of climate change nor of appropriate responses 3.2. Use scale from 1 to 5: 5: All 4: Almost all 3: Half 2: Some 1: None 4.1. Summarize in an overall scale (1-5): 5: Highly responsive (All defined elements ) 4: Mostly responsive (Most defined elements) 3: Moderately responsive (Some defined elements) 2: Partially responsive (Lacks most elements) 1: Non responsive (Lacks all elements ) 4.2. Summarize in an overall scale (1-5): 5: Fully improved 4: Mostly Improved 3: Moderately improved 2: Somewhat improved 1: Not improved 5. Depends on the targeted natural asset: Biological (species): measure through changes in population numbers (dynamics, structure, etc.) Land: measure changes in hectares. Baseline data will be necessary to estimate the change. Supporting indicators baseline and target (as well as contextual information) are needed such as the following: Farmers adopting recommended technologies, Ha. of land improved, Average deforestation rate Etc. Use scale from 1 to 5. 5: Very effective (All elements are present) 4: Effective (Most elements are present) 3: Moderately effective (Some elements are present) 2: Partially effective (Most elements are not present) 1: Ineffective (No elements are present) 6.1. Summarize in an overall scale (1-5): 5: Very high improvement 4: High improvement 3: Moderate improvement 2: Limited improvement 1: No improvement 6.2. Household income by source of livelihood in project area (USD) prior and post project intervention 7. Summarize in an overall scale (1-5). 5: All (Fully integrated) 4: Most 3: Some 2: Most not integrated 1: None
Fund Output Indicator Units
1.1. Number, sector(s) and level(s) of projects or interventions in separate fields of monitoring plan 1.2. Number 2.1.1. Number of staff (male/female) of targeted institutions: a. Obtain baseline information: total number of staff from targeted institutions b. Define target 2.1.2. Number of staff (male/female) of targeted institutions: a. Obtain baseline information: total number of staff from targeted institutions b. Define target: needs to be defined by project proponents 2.2.1. Quantitative: Percentage (includes women – and other vulnerable groups – and men). Qualitative: Adequacy: include direct analysis of major areas; adequacy/effectiveness of systems or analysis of perceptions of populations and institutions. 2.2.2. Number (broken down by gender and, if possible, by vulnerable groups defined in the area of intervention) of people 3.1. Number and type (in separate columns) at local level. 3.2. Number 4.1. Number and type 4. 2. Number and type (entered in separate columns) 5. Number of interventions by type of natural asset and intervention 6.1. Number and type (in separate columns of monitoring plan) 6.2. Income sources per household; description of income source and number of households. 7.1. Number/Sector 7.2. Number; Effectiveness (see previous indicator) through enforcement level.