## Overview
Project Performance Report (PPR)
| Period of Report (Dates) | 1 April 2017 - 31 December 2017
| Project Title: | ADDRESSING CLIMATE CHANGE RISKS ON WATER RESOURCES AND FOOD SECURITY IN THE DRY ZONE OF MYANMAR
| Project Summary: | Myanmar’s Dry Zone is one of the few areas in this region where food security for survival is still a real issue and the linkage of “bad weather” and poverty is immediate and dire. In 2009, a drought triggered 50-70% drop in rice and 80-90% drop in sesame and sunflower harvest – some of the key crops grown in the region. To strike a balance of investments on urgent adaptation needs and greater coverage of beneficiaries, this project combines targeted interventions for resilient livelihood actions and rehabilitation of community ecosystem assets such as forests and watersheds. The main objective of the project is to reduce vulnerability of farmers in Myanmar’s Dry Zone to increasing drought and rainfall variability, and enhance their capacity to plan for and respond to future impacts of Climate Change on food security. The project components relate to three main Outcomes of 1) Continuous freshwater availability is ensured during the dry seasons in 280 villages in the Dry Zone; 2) Climate-resilient agricultural and livestock practices enhanced in Myanmar’s Dry Zone; and 3)Timeliness and quality of climate risk information disseminated to Dry Zone farmers enhanced through use of shortterm weather forecasts, medium-term seasonal forecasts, and longerterm climate scenario planning, which are composed of lower-level Outputs to achieve them.
| Database Number: | PIMS 4703
Implementing Entity (IE) [name]: |  | United Nations Development Programme
| Type of IE: | MIE
| Country(ies): | Myanmar
Relevant Geographic Points (i.e. cities, villages, bodies of water): |  | Five townships (Shwebo, Monywa, Myingyan, Nyaung Oo and Chauk) in Myanmar's Dry Zone
Project Milestones
Milestone
AFB Approval Date: |  | 2014-03-11
IE-AFB Agreement Signature Date: |  | 2014-03-26
Start of Project/Programme: |  | 2015-02-17
Mid-term Review Date (if planned): |  | January 29,2018
| Terminal Evaluation Date: | 2019-02-17
List documents/ reports/ brochures / articles that have been prepared about the project.
In addition to the list submitted in the 1st PPR and 2nd PPR, the following is a list of documents prepared during the reporting period: 1. Second Interim Report on Soil and Water Conservation Activities 2. Report on Joint Survival Counting of Rehabilitation/reforestation areas 3. Report on Farm Boundary Plantation Programme 4. Report on Public Land Tree Plantation Programme 5. Report on Capacity Building Programme on Watershed and Forestry Management 6. Report on Establishment of Agro-forestry Systems in the Dry Zone of Myanmar 7. Public Consultation Report on Identification of Rehabilitation/reforestation Area 8. Repot of Seedlings delivery by Dry Zone Greening Department in 2017 9. Completion Report - Training on Climate Resilient Farming Methods - 2017 10. Completion Report - Training on Climate Adaptation and Water Saving Technology (Alternative Wet and Dry (AWD) practices in Paddy Cultivation - 2017 11. Completion Report - Training on Perennial Tree (Thanakha) Plantation - 2017 12. Completion Report - Training on Establishment of Perennial Fruit Trees - 2017 13. Completion Report - Training on Farmer-managed Seed Multiplication Programme - 2017 14. Completion Report - Training on Participatory On-Farm Demonstration of Climate-Resilient Agriculture Practices - 2017 15. Completion Report - Training on Farmer Field School Concepts and Methodology on Climate Resilient Dry land Farming - 2017 16. Completion Report - Training on Drip Irrigation Technology - 2017 17. Progress Report - Implementation of Drip Irrigation Demonstration - 2017 18. Progress Report - Provision of Post-harvest Seed Storage Facilities - 2017 19. Report on participatory varietal selection of rice varieties in Shwebo Township - 2017 20. Report on Refresher Training on Climate Change Resilient Diversified Livestock Rearing Practices 21. Progress Reoprt - Provision/Delivery of Climate Resileint Livestock 22. Report on Livestock Banking System 23. Report - National Training on Climate/Weather Forecast Translation and Application 24. Report - Regional Training on Climate/Weather Forecast Translation and Application 25. Guidelines for Testing Climate Information Flow 26. Risk Assessment Report: Enhancing Capacities for Climate Risk Management in Myanmar’s Dry Zone through Climate Information and Services 27. Climate Hazard Maps for 5 Townships (Flood, Drought, Earthquake) 28. Inception Report on Community-Based Disaster Risk Management 29. Baseline Report: Impact Assessment – Addressing Climate Change Risks on Water Resources and Food Security in the Dry Zone of Myanmar 30. Mid-term Evaluation Report 31. Project Story - "Measuring Progress: Adapting to Climate Change in the Dry Zone of Myanmar (http://www.mm.undp.org/content/myanmar/en/home/presscenter/pressreleases/2017/12/20/measuring-progress-adapting-to-climate-change-in-the-dry-zone-of-myanmar.html) 32. The Rice Elections (http://www.mm.undp.org/content/myanmar/en/home/ourwork/environmentandenergy/successstories/The_Rice_Elections.html)
List the Website address (URL) of project.
http://www.undp-alm.org/projects/af-myanmar
Project contacts:
National Project Manager/Coordinator
| Name: | Mr. Myint Wai
| Email: | myint.wai@undp.org
Date:
Government DA
Name:
Email:
Date:
Implementing Entity
| Name: | Mr.Biplove Choudhary ; Mr. Yusuke Taishi; Mr. Karma Lodey Rapten
| Email: | biplove.choudhary@undp.org; yusuke.taishi@undp.org; karma.rapten@undp.org
Date:
Executing Agency
Name:
Email:
Date:
Executing Agency
Name:
Email:
Date:
Executing Agency
Name:
Email:
Date:

## Financial Data
Financial information: cumulative from project start to 31 December 2017
DISBURSEMENT OF AF GRANT FUNDS
How much of the total AF grant as noted in Project Document plus any project preparation grant has been spent to date?
Estimated cumulative total disbursement as of [31 Dec 2017] | 4492613
Add any comments on AF Grant Funds. (word limit=200) | By the end of 2017, the project had disbursed US$ 4,492,613 out of the fist,second and third tranche allocation of US$ 6,454,076 (representing 69.60% delivery rate). The planned expenditure schedule given below also reflects the planned activities from 1st April 2017 to 31 December 2017.
INVESTMENT INCOME | 26,827.65 (2017); 67,597.27 (project start to date)
Amount of annual investment income generated from the Adaptation Fund’s grant
EXPENDITURE DATA
List ouput and corresponding amount spent for the current reporting period | ITEM / ACTIVITY / ACTION | AMOUNT
| Output1.1: Water Capture and Storage Capacity in 280 Villages enhanced to ensure imporved access to fresh water supply during dry periods | 185585.99
| Output1.2: 6141 hectares of micro-watersheds are protected and rehabilitated through Farmer-Managed Natural Regeneration (FMNR) to increase natural water retention and reduce erosion | 306886.37
| Output1.3: Community-based agro-foresty plots are established on 3,983 hectares of private and communal lands to conserve soil and water | 205229.01
| Output2.1: Drought-resilient farming methods introuduced to farmers to enhance the resilience of subsistence agriculture in the Dry Zone | 217936.55
| Output2.2: Resilient post-harvest processing and storage systems intoruduced to reduce climate-induced post-harvest losses(droughts, rain and floods) | 52199.67
| Output2.3: Diversified livestock production systems are introudced in 6,300 households to buffer the effects of drought on rural livelihoods | 428300.18
| Output3.1: Climate hazard maps and risk scenarios are developed in each Township to support community-based climate risk management and preparedness planning | 129630.9
| Output3.2: Local level climate and disaster risk management framework strengthened for timely and effective communication of climate risk and early warning information | 198718.91
| Project Execution Cost | 19998.5
| TOTAL | 1744486.08
PLANNED EXPENDITURE SCHEDULE
List outputs planned and corresponding projected cost for the upcoming reporting period | ITEM / ACTIVITY / ACTION | PROJECTED COST | Est. Completion Date
| Output1.1: Water Capture and Storage Capacity in 280 Villages enhanced to ensure imporved access to fresh water supply during dry periods | 908300.14 | 2019-02-16
| Output1.2: 6141 hectares of micro-watersheds are protected and rehabilitated through Farmer-Managed Natural Regeneration (FMNR) to increase natural water retention and reduce erosion | 588069.21 | 2019-02-16
| Output1.3: Community-based agro-foresty plots are established on 3,983 hectares of private and communal lands to conserve soil and water | 464518.77 | 2019-02-16
| Output2.1: Drought-resilient farming methods introuduced to farmers to enhance the resilience of subsistence agriculture in the Dry Zone | 192147.67 | 2019-02-16
| Output2.2:Resilient post-harvest processing and storage systems intoruduced to reduce climate-induced post-harvest losses(droughts, rain and floods) | 187146.67 | 2019-02-16
| Output2.3: Diversified livestock production systems are introudced in 6,300 households to buffer the effects of drought on rural livelihoods | 76473 | 2019-02-16
| Output3.1: Climate hazard maps and risk scenarios are developed in each Township to support community-based climate risk management and preparedness planning | 43554.23 | 2019-02-16
| Output3.2: Local level climate and disaster risk management framework strengthened for timely and effective communication of climate risk and early warning information | 249392.5 | 2019-02-16
| Project Execution Cost | 87209.5 | 2019-02-16
| TOTAL | 2796811.69
ACTUAL CO-FINANCING (If the MTR or TE have not been undertaken this reporting period, DO NOT report on actual co-financing.)
How much of the total co-financing as committed in the Project Document has actually been realized? | 399681.25
Estimated cumulative actual co-financing as verified during Mid-term Review (MTR) or Terminal Evaluation (TE). | 399681
Add any comments on actual co-financing in particular any issues related to the realization of in-kind, grant, credits, loans, equity, non-grant instruments and other types of co-financing. (word limit=200) | The only cash co-financing is from UNDP (US$ 624,998) and as of reporting date, UNDP has made a cumulative co-financing contribution of US$ 399,681. The remaining UNDP co-financing is allocated in 2018 and 2019. The government is providing in-kind contribution - the exact value of which will be determined during the terminal evaluation of the project

## Procurement (hidden)
PROCUREMENT DATA
Please provide information for all contracts over $2,500 USD
Please provide the number of contracts under $2,500, signed during this reporting period: |  |  |  |  | 0
LIST OF CONTRACTS
List all contracts related to the project/program with signature dates
Contract Type | Agency / Contracted party | Contract Value/Amount (USD) | Signature Date | Payment to Date | Remaining Balance | Remark
Service Contract (Project Staff) | Yan Naing Tun | 19573.08 | 2014-12-10 | 19573.08 | 0
Service Contract (Project Staff) | Myint Zaw | 19573.08 | 2014-12-15 | 19573.08 | 0
Service Contract (Project Staff) | Khin Maung Htay | 17246.16 | 2014-12-15 | 17246.16 | 0
Service Contract (Project Staff) | Khin Maung Lwin | 19573.08 | 2014-12-24 | 19573.08 | 0
Dispatch PO: Procurement of Goods | Toyota Gibraltar Stockholdings (TGS) Ltd (12-Aug-2015) | 38232.19 | 2015-08-27 | 38232.19 | 0
Service Contract (Project Staff) | Yan Naing Tun | 19573.08 | 2015-11-25 | 19573.08 | 0
Service Contract (Project Staff) | Myint Zaw | 19573.08 | 2015-11-30 | 19573.08 | 0
Service Contract (Project Staff) | Khin Maung Htay | 17246.16 | 2015-11-30 | 17246.16 | 0
Service Contract (Project Staff) | Khin Maung Lwin | 19573.08 | 2015-11-30 | 19573.08 | 0
Service for Individual Contractor | Hans Van Noord | 28690 | 2015-12-18 | 28690 | 0
Service for Individual Contractor | Jose Miguel Ruiz Verona | 24471.95 | 2016-01-15 | 24471.95 | 0
Service for Individual Contractor | Mr.Hari Krishna Nibanupudi | 22900 | 2016-05-25 | 22900 | 0
Dispatch PO: Procurment of Services | Chalk& Slate | 3395.12 | 2016-07-20 | 3395.12 | 0
Contract for Professional Services-National | Myanmar Survey Research Company Limited | 84673 | 2016-08-02 | 42335 | 42338
Responsible Party Agreement | Aung Zay Yar Social Compassioners Association, Shwebo ("CSO") | 50000 | 2016-08-03 | 50000 | 0
Responsible Party Agreement | Community Development Association ("CSO") | 699662 | 2016-08-03 | 664677 | 34985
Responsible Party Agreement | Farm Business Development Technical Group ("CSO") | 631424 | 2016-08-04 | 410424 | 221000
Contract for Professional Services-International | Hydroconseil | 188994 | 2016-08-09 | 113396 | 75598
Service Contract (Project Staff) | Van Lal Ruat Pwee Yee | 10848.391 | 2016-08-18 | 10848.391 | 0
Contract for Professional Services-International | Regional Integrated Multi-Hazard Early Warning System (RIMES) for Afro-Asian Region | 214843 | 2016-08-23 | 214843 | 0
Dispatch PO: Procurement of Goods | Aung Than Wai | 179215.39 | 2016-09-27 | 179215.39 | 0
Letter of Agreement | Dry Zone Greening Department | 702976 | 2016-10-03 | 377573 | 325403
Contract for Professional Services -National | Community Development Action | 271248.641 | 2016-10-05 | 132686.58 | 104624.4755
Contract for Professional Services-National | Network Activites Group | 760574.49 | 2016-10-21 | 329822.83 | 325960.4967
Contract for Professional Services-International | CESVI | 839967 | 2016-11-15 | 629973 | 209994
Service Contract (Project Staff) | Yan Naing Tun | 21835.38 | 2016-12-10 | 21835.38 | 0
Service Contract (Project Staff) | Myint Zaw | 21835.38 | 2016-12-15 | 21835.38 | 0
Service Contract (Project Staff) | Khin Maung Lwin | 9786.54 | 2016-12-12 | 9786.54 | 0
Service Contract (Project Staff) | Khin Maung Htay | 2584.606 | 2016-12-19 | 2584.606 | 0
Service Contract (Project Staff) | Kyaw Zin Aung Soe | 23645.22 | 2017-05-03 | 15311.02 | 8334.2
Service Contract (Project Staff) | Khin Maung Lwin | 12048.84 | 2017-06-24 | 12048.84 | 0
Service Contract (Project Staff) | Van Lal Ruat Pwee Yee | 9303.2 | 2017-08-18 | 9303.2 | 0
Contract for Professional Services-International | Regional Integrated Multi-Hazard Early Warning System (RIMES) for Afro-Asian Region | 198985 | 2017-08-17 | 69644 | 129341
Dispatch PO: Procurment of Services | Chalk& Slate | 4468.86 | 2017-08-08 | 4468.86 | 0
Procurement Contract (Invitation to Bid) ITB | Win Top Engineering & General Services Co,Ltd (Package A) | 301212 | 2017-12-19 | 45348.11 | 255863.89
Procurement Contract (Invitation to Bid) ITB | Well Done Engineering Co,Ltd (Package B) | 148268.47 | 2017-11-27 | 22158.8 | 126109.67
Procurement Contract (Invitation to Bid) ITB | Well Done Engineering Co,Ltd (Package C) | 152799.17 | 2017-11-27 | 22835.92 | 129963.25
Service Contract (Project Staff) | Yan Naing Tun | 25002.6 | 2017-12-10 | 0 | 25002.6
Service Contract (Project Staff) | Myint Zaw | 25002.6 | 2017-12-15 | 0 | 25002.6
Service Contract (Project Staff) | Khin Maung Lwin | 25002.6 | 2017-12-24 | 0 | 25002.6
BIDS
List all bids for each contact signed with date of open call and winning bid
CONTRACT & Procurement Method | Submitted Bids | Bid Amount (USD) | Date of Open Call | Winning Bid Amount (USD) | Selection Justification for the Winner
Toyota Gilbraltar Stockholdings (TGS)Ltd, Comparison for Project Vehicle Procurement (Dispatched PO: 27-Aug-2015) | Toyota Gibraltar Stockholdings (TGS) Ltd (12-Aug-2015) | 38232.19 | 2015-08-11 | 38232.19 | Toyota Gibraltar Stockholdings offered a more competetive rate with a longer warranty period
| UNOPS(UNWEBBUY) (20-Aug-2015) | 40598.84
Sedona Hotel Mandalay RFQ on 25 Jan 2015 | Sedona Hotel Mandalay | 2695 | 2015-01-25 | 2695 | Sedona Hotel was the only vendor who submitted the bid. The other hotels of similar standard were all booked for other events on the day and Sedona Hotel was the only one available
Dispatch PO contract & Competetive bidding process - Request for Proposal | Chalk and Slate | 3589.7 | 2016-06-24 | 3589.7 | Chalk and Slate offered a more competetive bid after a combined scoring methond (techncal and financial) was employed.
| Xtage | 39700
Contract for Professional Services-National & Competetive bidding process - Request for Proposal | Mekong Economics | 89303 | 2016-06-16 | 84673 | Myanmar Survey Research Company Limited (MSR) offered the most competetive bid (both technically and financially)
| Asian Consulting Engineer Pvt Ltd (ACE) | 134600
| Myanmar Survey Research Company Limited (MSR) | 84673
Responsible Party Agreement & NGO/CSO engagement process | Aung Zay Yar Social Compassioners' Association | 50000 | 2016-06-20 | 50000 | The offer to bid was made through the NGO/CSO engagement modality. The NGOs/CSOs listed in the NGO/CSO roster was re-assessed against the TOR and scope of work, following which a collaborative advantage analysis was conducted by an inter-disciplinary panel. The panel recommended Aung Zay Yar for the assignment based on their comparative advantage and technical capacity.
Responsible Party Agreement & NGO/CSO engagement process | Community DevelopmentAssociation (CDAssociation) | 699662 | 2016-06-20 | 699662 | This assignment was awarded through the NGO/CSO engagement modality. The NGOs/CSOs listed in the NGO/CSO roster was re-assessed against the TOR and scope of work, following which a collaborative advantage analysis was conducted by an inter-disciplinary panel. Bids were invited from shortlisted NGOs/CSOs and the most competetive offer was made by Community Development Association (CDAssociation).
| Swanyee Development Foundration | 1223686
Responsible Party Agreement & NGO/CSO engagement process | Farm Business Development Technical Group (FBD) | 631424 | 2016-06-20 | 631424 | This assignment was awarded through the NGO/CSO engagement modality. The NGOs/CSOs listed in the NGO/CSO roster was re-assessed against the TOR and scope of work, following which a collaborative advantage analysis was conducted by an inter-disciplinary panel. Bids were invited from two shortlisted NGOs/CSOs - out of which only one (Farm Business Development Technical Group) responded. The bid submitted by Farm Business Development Group was found to be competetive and within the estimated budget.
Contract for Professional Services -International & Competetive bidding process - Request for Proposal | Hydroconseil | 188994 | 2016-06-02 | 188994 | Hydroconseil offered the most competetive bid, which was determined through an evaluation process which consisted of a combined scoring method taking into consideration their technical and financial proposals.
| Cowater International Inc. (CWI) | 1205037
| International Centre for Environmental Management (ICEM) | 272744
| Myanmar Marketing Research and Development Co. Ltd. (MMRD) | 314053
Contract for Professional Services-International & Competetive bidding process - Request for Proposal | International Centre for Environmental Management | 299792 | 2016-06-22 | 214843 | RIMES offered the most competetive bid, which was determined through an evaluation process which consisted of a combined scoring method taking into consideration both technical and financial proposals.
| Oikologica | 664992
| Ramboll Environ | 284646
| Regional Integrated Multihazard Early Warning System | 214843
| ACTED | 802041
Dispatch PO contract & Invitation to Bid (ITB) | Aung Than Wai Industries | 178295 | 2016-06-23 | 178295 | Aung Than Wai offered the most competetive bid which was determined through an evaluation process which consisted of a combined scoring method considering both the technical and financial proposal. Aung Than Wai Industries is a local manufacturer is easily accessible for after-sales services.
| Bellstone | 389134
| Guru Nanak | 345300
Contract for Professional Services-National & Competetive bidding process - Request for Proposal | Community Development Action (CDAction) | 271248.641 | 2016-07-26 | 271248.641 | Out of the 3 bids submitted, only Community Development Action (CDAction) qualified the technical evaluation round. CD Action also offered a competetive financial proposal which was well within the estimated budget.
Contract for Professional Services-National & Competetive bidding process - Request for Proposal | Network Activities Group (NAG) | 760574.48 | 2016-07-08 | 760574.48 | Network Activities Group (NAG) offered the most competetive bid, which was determined through an evaluation process which consisted of a combined scoring method taking into consideration both technical and financial proposals proposals.
| International Center for Research for Agroforestry (ICRAF) | 4658273.42
Contract for Professional Services-International & Competetive bidding process - Request for Proposal | Cesvi Fondazione (Onlus) | 839967 | 2016-07-27 | 839967 | CESVI was the only technically qualified bid. The other bid submitted by Professional Research and Consultancy (PRC) was rejected in the technical round. The financial proposal of CESVI was found competetive and within the budget limit and therefore the offer was made to CSEVI.
Contract for Professional Services-International & Competetive bidding process - Request for Proposal | Action Aid Myanmar | 1146069 | 2017-05-05 |  | Among the 3 technically qualified firms, RIMES offered the most competetive financial bid - which was determined through an evaluation process consisting of a combined scoring method taking into consideration both technical and financial proposals.
| Karuna Mission Social Solidarity/CORDAID | 898980 |  | 198985
| Regional Integrated Multihazard Early Warning System | 198985
Dispatch PO contract - Direct contracting | Chalk and Slate | 4468.86 | 2017-07-17 | 4468.86 | Based on past engagement/performance in the development of the application, as well as referring to evaluation for previous services provided by Chalk & Slate, approval for direct contracting was sought to engage Chalk and Slate for upgrading of DAN mobile application
Invitation to Bid (ITB) | Puritas | 2015096.67 | 2017-06-29 |  | Bids from 3 firms - Puritas, WINTOP and Geomechanical Services (GMS) were qualified technically. Wintop offered the lowest bid, following which the project entered into a negotiation with WINTOP. After negotiation, WINTOP offered a rate of US$ 301,212.
| WIN TOP Engineering and General Services Co., Ltd. | 1115604.87 |  | 301212
| Geomechanical Services - GMS | 1853248.32
Invitation to Bid (ITB) | Well Done Engineering Co., Ltd. | 148268.47 | 2017-06-29 |  | Bids from 4 firms - Puritas, WIN TOP, Well Done and Geomechanical Services (GMS) were accepted as technically qualified. The financial proposal of Well Done was was found to be most competetive and in line with the internal cost estimates prepared by the project
| Puritas | 526414 |  | 148268.47
| WIN TOP Engineering and General Services Co., Ltd. | 921179.12
| Geomechanical Services - GMS | 922824.13
Invitation to Bid (ITB) | Well Done Engineering Co., Ltd. | 152799.17 | 2017-06-29 |  | Bids from 4 firms - Puritas, High Development Construction, Well Done and Geomechanical Services (GMS) were accepted as technically qualified. The financial proposal of Well Done was found to be most competetive and in line with the internal cost estimates prepared by the project
| Puritas | 499288.92 |  | 152799.17
| High Development Construction | 207671.86
| Geomechanical Services - GMS | 958432.02

## Risk Assesment
RISK ASSESMENT
IDENTIFIED RISKS
List all Risks identified in project preparation phase and what steps are being taken to mitigate them
Identified Risk | Current Status | Steps Taken to Mitigate Risk
Non-climate drivers undermine adaptation efforts under this project. | [Medium] The risk still remains valid. | The original risk mitigation approach remains relevant. That is, the project will promote an integrated view of vulnerability in which the mitigation of climate-related drivers of vulnerability can be coupled with economic benefits. This integrated, ecosystem-based view of resilience, which is based on community-based participatory planning, will be able to hold non-climatic drivers such as over-grazing, deforestation and unsustainable agricultural practices in check. From this perspective, adaptation actions that are implemented or planned to be implemented in the project are designed to address local community needs for economic and social empowerment.
Extreme weather events during the project lifetime undermine confidence of local communities in adaptation measures promoted by the project. | [Medium] The risk still remains valid. | By design, the project integrates outputs which focus on disaster risk and early warning communication, which enable basic preparedness planning. Under Outcome 3 of the project has supported Relief and Resettlement Department to develop a mobile application - Disaster Alert Notification, which is a new method of disseminating early warning information, in addition to the existing word-of-mouth communications. In addition, the project also supported the Department of Hydrology and Meteoreology in developing a mobile application - DMH-SESAME - which provides 3-day, 10-day, monthly and seasonal forecasts for end users, including implementing partners, government agencies, and communities. The project also developed the enhanced version of SESAME mobile application in Myanmar language and the DAN mobile application is also upgraded to include additional features such as custom sound notification; links to the Myanmar Disaster Losses and Damages Database; integration of audio clips that will enable visually impaired and illiterate people to use the application.
Adaptation measures increase inequity in communities. | [Medium] The risk still remains valid. | The selection of project target villages have been done in consultation with the beneficiaries and based on a set of selection criteria, including - observed temperature extremes, frequency of drought per year, impacts of climatic parameters on food security and potential to access ground and surface water resources. The project has also collected baseline information on beneficiaries and developed a database to monitor and ensure that the project supports the most vulnerable and marginalized communities. The project prioritizes interventions on mainly landless, marginal and women-headed households. For specific sectoral interventions, the project also conducts needs assessments and identifies beneficiaries based on the overall project criteria of prioritizing landless and marginal farmers. In addition, a monitoring and evaluation framework has been developed to ensure that project delivers intended results and target intended beneficiaries.
Technical capacity of township and village stakeholders restricts broad community engagement. | [Medium] The risk still remains valid. | During the inception phase of the project, the project team conducted stakeholder consultations in each of the project townships on project objectives, outcomes, priorities and local needs to enhance better understanding of the project. Township authorities and local communities have expressed willingness to work together to achieve the objectives of the project. The implementation of project activities are done through a consultative process engaging township level relevant sector and all community members that have a stake in the project.
Political and social instability and lack of government engagement | [Medium] The risk still remains valid. | While this risk continues to be valid, the likelihood of this risk materializing has gone down since this project was under design 3 years ago. The project steering committee includes representatives from the Government and key decisions in the project are jointly made by the Government of Myanmar and UNDP. The Technical Advisory Group meets every quarter and the Project Steering Committee meets bi-annually to review progress and make course corrections. So far, lack of Government engagement is not a major issue.
Critical Risks Affecting Progress (Not identified at project design)
Identify Risks with a 50% or > likelihood of affecting progress of project
Identified Risk | Current Status | Steps Taken to Mitigate Risk
Lack of clarity in land acquisition for project interventions, in particular for forestry and watershed management activities | [High] This risk has emerged as the project started assessing and identifying areas for reforestation and rehabilitation activities. Any delay in securing approval will result in implementation delays | In consultation with the Dry Zone Greening Department and Forestry Department, the Project has submitted applicaiton for use of land for rehabilitation/reforestation activities to the respectve township General Administration Department after securing endorsement from communities and local land management committees. UNDP Country Director met with the Minister of Natural Resources and Environmental Conservation on 10 Nov 2017 to discuss issue of land availability for rehabilitation/reforestation activities and the Minister committed to support the project is securing permission from the Chief Ministers of the 3 regions. The issue of land availability was also discussed in the TAG meeting held on 8 Dec 2017 and PSC meeting held on 20 Dec 2017, where the intial findings of the Mid-Term Evaluation (which identified land availability for rehabilitation and reforestation activities as a critical risk). As agreed by the PSC, UNDP and Dry Zone Greening Department approached the Ministry of Natural Resources and Environmental Conservation on 29 Dec 2017 to seek support in securing approval for land to implement rehabilitation/reforestation activities under the project. The Permanent Secretary of the Ministry of Natural Resources and Environmental Conservation committed to assist the project in securind land for rehabilitation/reforestation activities by the end of Jan 2018. It is likely that the issue will be resolved in 2018.
Risk Measures: Were there any risk mitigation measures employed during the current reporting period? If so, were risks reduced? If not, why were these risks not reduced?
Add any comments relevant to risk mitigation (word limit = 500)
As reported in previous PPRs, the monthly project coordination meetings with the counterpart agency (Dry Zone Greening Department) and quarterly review and coordination meetings with implementing partners continue to provide a useful platform to resolve issues and address implementation bottlenecks. The one-day joint monitoring visits combined with the quarterly TAG meetings (held in the 5 project townships on a rotational basis) have provided TAG members the opportunity to observe activities in the field and provide inputs/suggestions for improvement, as well as avoid potential risks in the future. As proposed by the PSC, the project is also providing bi-annual updates (progress reports and presentation) on project implementation to the Minister of MONREC and Chief Ministers of Sagaing, Mandalay and Magwe regions. These meetings provide opportunity for the project to showcase results/impacts, as well as request support of senior government functionaries in addressing issues and challenges. In addition, as proposed by the Mid-Term Evaluation, the project will also provide progress reports to the Regional Directors of key Departments who have a stake in the project. All of the above have contributed to enhanced partnership and ensured smooth implementation of the project.

## Rating
RATING ON IMPLEMENTATION PROGRESS
For rating definitions please see bottom of page.
| Progress on Key Milestones |  | Expected Progress |  | Progress to Date | Rating
Project Manager/Coordinator: | Output 1.1: Identify specific locations in target villages for the following adaptation interventions: canals for water diversion; small-scale pumping systems; communal water tanks; tube wells; pound reservois; and soil storage dams |  | Field verification of identified locations for soil and water conservation activities conducted towards end Dec 2017 for implementation of activities in 2018; Verificaiton of prioritized locations for water infrastructure investments in target villages |  | A field assessment/survey was conducted at start of project to identify needs and prioritize locations for soil and water conservation activities and water retention ponds. Similarly, a rapid needs assessment for small-scale water infrastructure was completed with a priority ranking of sites/locations for project investment. The assessment was presented to relevant government departments (Dry Zone Greenign Department/Department of Agriculture, Department of Rural Development/Irrigation and Water Utilization Management Department) for endorsement, as well as to ensure alignment with government plans and initiatives. Site verification for soil and water conservation activities, as well as renovation of water retention ponds were conducted in Dec to prepare for implementation in 2018. The locations for small-scale water infrastructure were also verified during the reporting period, since there was considerable gap between needs assessment and actual implementation. The verificaiton process resulted in some changes in needs and location of infrastructure. | HS
| Output 1.1: Village level management scheme formulated which includes the roles and responsibilities of VWUG and distribution agreement across (vulnerable) households |  | Develop standard operating procedures (SOP) for water user groups who have received small-sclae water infrastructure (deep tube well, shallow tube well, water retention ponds, etc) |  | Standard operating procedures for the water user group was developed in Shwebo, where the project invested in the renovation of Kin Tat irrigation canal. The SOPs for water user groups for other investments under the project could not be developed in 2017, as the recruitment of implementing partner for installation of small-scale water infrastructure was delayed. The SOPs will be develpoed in 2018 and include importants elements such as cost-sharing and user fees for the use and management of infrastructure for long-term sustainability. | MS
| Output 1.1: At least 50% of women's participation is encouraged to the workshops on water storage and capture interventions and participation monitored |  | At least 35% participation of women achieved in workshops on water storage and capture interventions |  | Concerted efforts are being made to enhance women's participation in trainings and implementation of activities in the field by adjusting timing of participation in these activities and avoiding conflicts with field/household work. Soil and water conservation trainings were conducted for 304 participant (293 male and 11 female). Awareness rasining and training for water user groups will be conducted in 2018 and the results will be reported in the next PPR. The soil conservation field day actitivities recorded 17% participation by women (40 out of a total 230 people). | MU
| Output 1.1: Contribution of labour from women and/or landless improverished households is facilitated |  | Contribution of labour from women and/or landless impoverished households facilitated and encouraged |  | Implementing partners are specifically instructed to include women and landless households while engaing labour for project activities. Overall, 43% of the 1,853 labourers involved in soil conservation activities; 45% of 1,678 labourers involved in pond renovation activities and 36% of 1,214 labourers involved in run on/ run off water diversion canal activities were women. | S
| Output 1.1: Production of a report on the success and challenges of micro-scale water infrastructure |  | No progress expected during the reporting period |  | No progress. This activity will be carried out towards the end of project implementation. In addition, the Mid Term Evaluation has recommended that an assessment be conducted to gauge the effectivessness and quality of water retention ponds already provided through the project. This assessment will be carreid out in early 2018. | N/A
| Output 1.2: Finalize village-wise intervention type and size based on the level of denudation, ongoing surface runoff and topography |  | Target villages already selected based on a set of selection criteria and adaptation interventions identified for targetted villages Sites for intervention in 2018 are verified through field surveys and public consultations. |  | Township level and village level consultation conducted to verify and validate land use for reforestation/rehabilitation activities and target locations were identified together with GIS maps at the begining of project implementation. In addition, based on annual work plan targets, the sites for rehabilitation/reforestation in 2018 was verified through field surveys and public consultations towards the end of Dec. | S
| Output 1.2: At least 50% of women's participation is encouraged to the workshops on watershed rehabilitation programmes and participation monitored |  | At least 35% participation of women achieved in workshops on watershed rehabilitation programmes and results documented |  | Efforts are being made to enhance women's participation in trainings and implementation of activities in the field by adjusting timing of participation in these activities and avoiding conflicts with field/household work.10% of the 593 participants in watershed rehabilitation programmes were women. Female participation in watershed rehabilitation programmes are generally low due to the physical nature of practical trainings and field activities and men tend to take up these roles. | MU
| Output 1.2: Roles and responsibilities of women are clearly identified in the community management plan |  | Forest management plans have been prepared and the roles and responsibilities of women are being considered in the management plans |  | The management plan temaplate prescribed by Forest Deptt. do not specifically mention differentiated roles of men and women. However, the project will ensure a specific clause in the managemet plans encouraging participation of women at all levels. Women are included as members of community forestry user groups and are encouraged to take leadership position - such as chiarman, secretary and treasurer, etc. | MU
| Output 1.2: Production of a report on the success and challenges of community forest management plan |  | No progress expected during the reporting period |  | No progress. This activity will be carried out towards the end of project implementation in end 2018 or early 2019. However, lessons are being continuously captured and integrated into implementation of activities in the field. | N/A
| Output 1.2: Initial 30-year lease permission sought and granted for successfully managed community forests |  | Identify and demarcate land available for community forestry practices and apply for community forestry certificates from the forest department. |  | One community forestry group (Ma Au village) in Shwebo Township has received community forestry certificate from the forest department. Community forestry certificates for user groups in other locations have been delayed due to absence of "no objection letter" for land use. As per recommendations of Mid Term Evaluation, "no objection letters" are being secured from the respective townships. The issuance of community forestry certificates will be pursued once the "no objection letters" have been received because this is a pre-requisite for community forestry certificates. | MS
| Output 1.3: Initial call for participation will target primarily women; at minimum 50% of the members should be women |  | No progress expected during the reporting period |  | During the initial discussions at village and township levels on land identification and verification for watershed rehabilitation programmes, a large number of women have participated, accounting for about 36% of total participants | N/A
| Output 1.3: Information collected on ongoing agro-forestry practices will be gender disaggregated |  | Gender disaggregated data collection is being considered for the inventory of on-going agro forestry practices. |  | As of date, 62 Agro-forestry groups (homestead gardening) have been established, with 488 members - out of which 143 are women (29%). The inventory report will be updated in May 2018 and final figures will be available in the next PPR reporting period | S
| Output 1.3: 1,000 hectares of homestead gardening in 76 villages established |  | 397 ha of hometead gardening in 97 villages accomplished |  | 600 ha of homesteads have been established so far in 159 villages (cumulative total), and 169,060 fruit tree saplings were distributed to beneficiaries | HS
| Output 1.3: 1,500 hectares of farm boundary planting in 95 villages established |  | 650 ha of farm boundary plantation accomplished |  | 710 ha of farm boundary plantation accomplished in 124 villages and a total of 254,336 seedlings have been planted. Communities have been engaged in plantation on a cash-for-work programme and the responsibility of managing plantation rests with the respective communities, which in turn will ensure sustainability of project interventions. | HS
| Output 1.3: Participants of the monitoring visits encourage women's participation |  | Monitoring visits to project sites include women participants so as to ensure gender considerations in project activities |  | The project has conducted one exchange visit and 1 women out of total 45 people participated in the exchange visit of community members for agroforestry knowledge exchange | U
| Output 1.3: Production of a report on the success and challenges of community forestry management plan |  | No progress expected during the reporting period |  | No progress. This activity will be carried out towards the end of project implementation | N/A
| Output 2.1: Organize a technical workshop to consolidate existing domestic and international knowledge on drought resistant crop varieties and seed banks inviting technical agencies such as Myanmar Agriculture Services, University of Agriculture, Department of Agriculture Research |  | Engage Department of Agricultre Research and Yezin Agriculture University to idenity drough-resistant varieties of crops and seeds for propagation by communities |  | The project conducted participatory varietal selection on rice which provided farmers opportunity to evaluate suitable drought-resilient rice varieties and identify locally preferred, high yield, and locally-acceptable rice varieties under high temperature and drought conditions in Ta Ga Nan Village, Shwebo township through farmers’ participation and technical collaboration of Yezin Agricultural University. Technical report was prepared and presented to the TAG, where it was well-received. The TAG recommended similar collaboration in future too. | S
| Output 2.2: Quantative assessment of current post-harvest processes undertaken and reported |  | No progress expected during the reporting period |  | The post-harvest assessment was completed in the beginning of 2017 and reported in the previous PPR | N/A
| Output 2.2: Production of an assessment report on current post-harvest processes |  | No progress expected during the reporting period |  | The assessment report was produced in the beginning of 2017 and distributed to related government departments. | N/A
| Output 2.2: Formulate a cost-sharing and maintenance plan in each village for the use of the thresher |  | Standard Operating Procedures for thresher User Group formulated. Operations and Maintenance manual developed. |  | Standard Operatingf Procedures for thresher user groups formulated and handed over to thresher user groups. Trainings on operation and maintenance of threshers imparted to all 127 thresher user groups | S
| Output 2.2: Women's participation in post-harvest trainings encouraged and gender-disaggregated participation record will be produced |  | Gender disaggregated data collected and reported on post-harvest training activities |  | 17 % of women participated in post-harvest trainings (51 women out of total 299 participants) | MU
| Output 2.2: Production of assessment reports on the effectiveness of harvest storage facilities and post-harvest handling techniques |  | No progress expected during the reporting period |  | No progress. This activity will be carried out towards the end of project implementation | N/A
| Output 2.3: Atleast 50% of the participants of the training on livestock production systems should be women. Gender disaggregated participants list will be produced |  | At least 35% of the participants of the training on livestock production systems are women |  | 33% of participants were woman in ToT trainings on climate resilient livestock production conducted for Livestock Breeding and Veterinary Department staff (9 females out of total 27 staff). 47% of participants were women in community level trainings on climate resilient livestock production conducted in 141 village tracts (2,599 women out of 5,558 participants) 33 % of participants were women in refresher tranings conducted at 62 cluster villages (399 female out of a total 1,204 participants). | S
| Output 2.3: Production of an assessment report on the effectiveness of diversified livestock production systems |  | No progress expected during the reporting period |  | No progress. This activity will be carried out towards the end of project implementation | N/A
| Output 3.1: Vulnerability assessment in townships will look at gender-differentiated vulnerability to climate risks |  | No progress expected during the reporting period |  | The risk assessment report was completed during the previous reporting period and gender concerns were included in the risk/vulnerability mapping exercise. Female population at village tracts was used as one of the indicators of social vulnerability, together with population under 18, and population density. | N/A
| Output 3.2: Seasonal agriculture bulletins produced |  | Seasonal agro-met bulletin produced on a regular basis |  | 295 agromet bulletins produced (i.e. 6 bulletins per month per township (5 days forecast)); DMH-SESAME mobile application produced which provides 3 days and 10 days forecasts (temp, rainfall, humidity, potential evapo-transpiration, spell and soil moisture) | HS
| Output 3.2: CBDRM committee will have women representatives and they will be assigned specific roles and responsibilities |  | Ensure women's representation in CBDRM Committee and specify their roles and responsibilities |  | 75 Village Disaster Management Teams have been formed with 22% women's representation. The roles and responsibilities of the members of the committe are yet to be specified. This will be done in 2018. | S
[5 empty] | Overall Rating | S
Please Provide the Name and Contact information of person(s) reponsible for completeling the Rating section
| Name: | Myint Wai
| Email: | myint.wai@undp.org
Please justify your rating. Outline the positive and negative progress made by the project since it started. Provide specific recommendations for next steps. . (word limit=500)
During the reporting period, overall progress of the project is rated as satisfactory. One of the key milestones - Mid Term Evaluation (MTE) of the project was conducted. The MTE provided an overall satisfactory rating for the project. Except for some minor issues under outcome 1, the MTE noted that the project was delivering satisfactory results. The initial findings of MTE was presented to both the Technical Working Group (TAG) and the Project Steering Committee (PSC). One of the key recommendations of the MTE was to review and reduce some of the project targets and instead provide more emphasis on enhancing quality of project deliverables, especially those related to watershed rehabilitation/reforestation and renovation/construction of water retention ponds. As per directives of PSC, the project team organized a bilateral meeting with the main counterpart - Dry Zone Greening Department to outline a proposal for adjustment of targets and enhancement of quality. An extra-ordinary TAG and an extra-ordinary PSC meeting will be organized in Jan 2018 to consider the recommendations. One of the challenges encountered was the availability of land for watershed rehabilitation/reforestation, where lack of clarity about the process for securing approval for land use caused slight delays in implementation. The issue was raised at both TAG and PSC levels, and elevated to the level of the Minister of Natural Resources and Environmental Conservation. The Minister agreed to discuss the issue with Ministry of Home Affairs and secure permission for land use within the first quarter of 2018. Activities related to promotion of climate-resilient agriculture, including delivering drought-tolerant crop varieties, promoting climate-resilient farming methods, improvement of post-harvest measures and technology, have provided clear benefits to beneficiaries, who are mostly marginal farmers. Moving forward, the key focus will be to disseminate these practices beyond the demonstration area, as well as to non-project villages for long-term sustainability. The component on promotion of climate-resilient livestock practices has been very successful and well-received by beneficiaries, who are mostly landless households. The support has enabled poor households to generate additional income from livestock resources, as well as provide income buffer during times of distress. However, there remain some risks in the capacity of Livestock Farmer Groups, especially in the areas of diseases control and management and the management of the livestock banking system. In the remaining period, the project will provide refresher trainings to communities/groups on climate-resilient livestock management practices. In the area of climate risk infromation management, the project has made important contributions - such as climate risk assessment and hazard mapping, development of weather forecasting and early warning tools (SESAME and Disaster Alert Notification). The project has benefited from the active support of Department of Meteorology and Hydrology (DMH). However, much remains to be done in terms of disseminating and application of these tools through awareness, advocacy and trainings. The project is working closely with DMH and Department of Agriculture (DOA) and integrating forecast translation and interpretation into extension services provided through DOA extension agents at the village level. Despite the particular circumstances of the project – many different activities across many locations and difficulties in collaboration with some parts of government, management of the project has been generally effective. The project team has adopted a robust monitoring and reporting mechanism and have communicated success stories, as relevant through online social media platform.
| Progress on Key Milestones |  | Expected Progress |  | Progress to Date | Rating
Implementing Agency | Output 1.1: Identify specific locations in target villages for the following adaptation interventions: canals for water diversion; small-scale pumping systems; communal water tanks; tube wells; pound reservois; and soil storage dams |  | Field verification of identified locations for soil and water conservation activities conducted towards end Dec 2017 for implementation of activities in 2018; Verificaiton of prioritized locations for water infrastructure investments in target villages |  | A field assessment/survey was conducted at start of project to identify needs and prioritize locations for soil and water conservation activities and water retention ponds. Similarly, a rapid needs assessment for small-scale water infrastructure was completed with a priority ranking of sites/locations for project investment. The assessment was presented to relevant government departments (Dry Zone Greenign Department/Department of Agriculture, Department of Rural Development/Irrigation and Water Utilization Management Department) for endorsement, as well as to ensure alignment with government plans and initiatives. Site verification for soil and water conservation activities, as well as renovation of water retention ponds were conducted in Dec to prepare for implementation in 2018. The locations for small-scale water infrastructure were also verified during the reporting period, since there was considerable gap between needs assessment and actual implementation. The verificaiton process resulted in some changes in needs and location of infrastructure. | HS
| Output 1.1: Village level management scheme formulated which includes the roles and responsibilities of VWUG and distribution agreement across (vulnerable) households |  | Develop standard operating procedures (SOP) for water user groups who have received small-sclae water infrastructure (deep tube well, shallow tube well, water retention ponds, etc) |  | Standard operating procedures for the water user group was developed in Shwebo, where the project invested in the renovation of Kin Tat irrigation canal. The SOPs for water user groups for other investments under the project could not be developed in 2017, as the recruitment of implementing partner for installation of small-scale water infrastructure was delayed. The SOPs will be develpoed in 2018 and include importants elements such as cost-sharing and user fees for the use and management of infrastructure for long-term sustainability. | MS
| Output 1.1: At least 50% of women's participation is encouraged to the workshops on water storage and capture interventions and participation monitored |  | At least 35% participation of women achieved in workshops on water storage and capture interventions |  | Concerted efforts are being made to enhance women's participation in trainings and implementation of activities in the field by adjusting timing of participation in these activities and avoiding conflicts with field/household work. Soil and water conservation trainings were conducted for 304 participant (293 male and 11 female). Awareness rasining and training for water user groups will be conducted in 2018 and the results will be reported in the next PPR. The soil conservation field day actitivities recorded 17% participation by women (40 out of a total 230 people). | MU
| Output 1.1: Contribution of labour from women and/or landless improverished households is facilitated |  | Contribution of labour from women and/or landless impoverished households facilitated and encouraged |  | Implementing partners are specifically instructed to include women and landless households while engaing labour for project activities. Overall, 43% of the 1,853 labourers involved in soil conservation activities; 45% of 1,678 labourers involved in pond renovation activities and 36% of 1,214 labourers involved in run on/ run off water diversion canal activities were women. | S
| Output 1.1: Production of a report on the success and challenges of micro-scale water infrastructure |  | No progress expected during the reporting period |  | No progress. This activity will be carried out towards the end of project implementation. In addition, the Mid Term Evaluation has recommended that an assessment be conducted to gauge the effectivessness and quality of water retention ponds already provided through the project. This assessment will be carreid out in early 2018. | N/A
| Output 1.2: Finalize village-wise intervention type and size based on the level of denudation, ongoing surface runoff and topography |  | Target villages already selected based on a set of slection criteria and adaptation interventions identified for targetted villages Sites for intervention in 2018 are verified through field surveys and public consultations. |  | Township level and village level consultation conducted to verify and validate land use for reforestation/rehabilitation activities and target locations were identified together with GIS maps at the begining of project implementation. In addition, based on annual work plan targets, the sites for rehabilitation/reforestation in 2018 was verified through field surveys and public consultations towards the end of Dec. | S
| Output 1.2: At least 50% of women's participation is encouraged to the workshops on watershed rehabilitation programmes and participation monitored |  | At least 35% participation of women achieved in workshops on watershed rehabilitation programmes and results documented |  | Efforts are being made to enhance women's participation in trainings and implementation of activities in the field by adjusting timing of participation in these activities and avoiding conflicts with field/household work.10% of the 593 participants in watershed rehabilitation programmes were women. Female participation in watershed rehabilitation programmes are generally low due to the physical nature of practical trainings and field activities and men tend to take up these roles. | MU
| Output 1.2: Roles and responsibilities of women are clearly identified in the community management plan |  | Forest management plans have been prepared and the roles and responsibilities of women are being considered in the management plans |  | The management plan temaplate prescribed by Forest Deptt. do not specifically mention differentiated roles of men and women. However, the project will ensure a specific clause in the managemet plans encouraging participation of women at all levels. Women are included as members of community forestry user groups and are encouraged to take leadership position - such as chiarman, secretary and treasurer, etc. | MU
| Output 1.2: Production of a report on the success and challenges of community forest management plan |  | No progress expected during the reporting period |  | No progress. This activity will be carried out towards the end of project implementation in end 2018 or early 2019. However, lessons are being continuously captured and integrated into implementation of activities in the field. | N/A
| Output 1.2: Initial 30-year lease permission sought and granted for successfully managed community forests |  | Identify and demarcate land available for community forestry practices and apply for community forestry certificates from the forest department. |  | One community forestry group (Ma Au village) in Shwebo Township has received community forestry certificate from the forest department. Community forestry certificates for user groups in other locations have been delayed due to absence of "no objection letter" for land use. As per recommendations of Mid Term Evaluation, "no objection letters" are being secured from the respective townships. The issuance of community forestry certificates will be pursued once the "no objection letters" have been received because this is a pre-requisite for community forestry certificates. | MS
| Output 1.3: Initial call for participation will target primarily women; at minimum 50% of the members should be women |  | No progress expected during the reporting period |  | During the initial discussions at village and township levels on land identification and verification for watershed rehabilitation programmes, a large number of women have participated, accounting for about 36% of total participants | N/A
| Output 1.3: Information collected on ongoing agro-forestry practices will be gender disaggregated |  | Gender disaggregated data collection is being considered for the inventory of on-going agro forestry practices. |  | As of date, 62 Agro-forestry groups (homestead gardening) have been established, with 488 members - out of which 143 are women (29%). The inventory report will be updated in May 2018 and final figures will be available in the next PPR reporting period | S
| Output 1.3: 1,000 hectares of homestead gardening in 76 villages established |  | 397 ha of hometead gardening in 97 villages accomplished |  | 600 ha of homesteads have been established so far in 159 villages (cumulative total), and 169,060 fruit tree saplings were distributed to beneficiaries | HS
| Output 1.3: 1,500 hectares of farm boundary planting in 95 villages established |  | 650 ha of farm boundary plantation accomplished |  | 710 ha of farm boundary plantation accomplished in 124 villages and a total of 254,336 seedlings have been planted. Communities have been engaged in plantation on a cash-for-work programme and the responsibility of managing plantation rests with the respective communities, which in turn will ensure sustainability of project interventions. | HS
| Output 1.3: Participants of the monitoring visits encourage women's participation |  | Monitoring visits to project sites include women participants so as to ensure gender considerations in project activities |  | The project has conducted one exchange visit and 1 women out of total 45 people participated in the exchange visit of community members for agroforestry knowledge exchange | U
| Output 1.3: Production of a report on the success and challenges of community forestry management plan |  | No progress expected during the reporting period |  | No progress. This activity will be carried out towards the end of project implementation | N/A
| Output 2.1: Organize a technical workshop to consolidate existing domestic and international knowledge on drought resistant crop varieties and seed banks inviting technical agencies such as Myanmar Agriculture Services, University of Agriculture, Department of Agriculture Research |  | Engage Department of Agricultre Research and Yezin Agriculture University to idenity drough-resistant varieties of crops and seeds for propagation by communities |  | The project conducted participatory varietal selection on rice which provided farmers opportunity to evaluate suitable drought-resilient rice varieties and identify locally preferred, high yield, and locally-acceptable rice varieties under high temperature and drought conditions in Ta Ga Nan Village, Shwebo township through farmers’ participation and technical collaboration of Yezin Agricultural University. Technical report was prepared and presented to the TAG, where it was well-received. The TAG recommended similar collaboration in future too. | S
| Output 2.2: Quantative assessment of current post-harvest processes undertaken and reported |  | No progress expected during the reporting period |  | The post-harvest assessment was completed in the beginning of 2017 and reported in the previous PPR | N/A
| Output 2.2: Production of an assessment report on current post-harvest processes |  | No progress expected during the reporting period |  | The assessment report was produced in the beginning of 2017 and distributed to related government departments. | N/A
| Output 2.2: Formulate a cost-sharing and maintenance plan in each village for the use of the thresher |  | Standard Operating Procedures for thresher User Group formulated. Operations and Maintenance manual developed. |  | Standard Operatingf Procedures for thresher user groups formulated and handed over to thresher user groups. Trainings on operation and maintenance of threshers imparted to all 127 thresher user groups | S
| Output 2.2: Women's participation in post-harvest trainings encouraged and gender-disaggregated participation record will be produced |  | Gender disaggregated data collected and reported on post-harvest training activities |  | 17 % of women participated in post-harvest trainings (51 women out of total 299 participants) | MU
| Output 2.2: Production of assessment reports on the effectiveness of harvest storage facilities and post-harvest handling techniques |  | No progress expected during the reporting period |  | No progress. This activity will be carried out towards the end of project implementation | N/A
| Output 2.3: Atleast 50% of the participants of the training on livestock production systems should be women. Gender disaggregated participants list will be produced |  | At least 35% of the participants of the training on livestock production systems are women |  | 33% of participants were woman in ToT trainings on climate resilient livestock production conducted for Livestock Breeding and Veterinary Department staff (9 females out of total 27 staff). 47% of participants were women in community level trainings on climate resilient livestock production conducted in 141 village tracts (2,599 women out of 5,558 participants) 33 % of participants were women in refresher tranings conducted at 62 cluster villages (399 female out of a total 1,204 participants). | S
| Output 2.3: Production of an assessment report on the effectiveness of diversified livestock production systems |  | No progress expected during the reporting period |  | No progress. This activity will be carried out towards the end of project implementation | N/A
| Output 3.1: Vulnerability assessment in townships will look at gender-differentiated vulnerability to climate risks |  | No progress expected during the reporting period |  | The risk assessment report was completed during the previous reporting period and gender concerns were included in the risk/vulnerability mapping exercise. Female population at village tracts was used as one of the indicators of social vulnerability, together with population under 18, and population density. | N/A
| Output 3.2: Seasonal agriculture bulletins produced |  | Seasonal agro-met bulletin produced on a regular basis |  | 295 agromet bulletins produced (i.e. 6 bulletins per month per township (5 days forecast)); DMH-SESAME mobile application produced which provides 3 days and 10 days forecasts (temp, rainfall, humidity, potential evapo-transpiration, spell and soil moisture) | HS
| Output 3.2: CBDRM committee will have women representatives and they will be assigned specific roles and responsibilities |  | Ensure women's representation in CBDRM Committee and specify their roles and responsibilities |  | 75 Village Disaster Management Teams have been formed with 22% women's representation. The roles and responsibilities of the members of the committe are yet to be specified. This will be done in 2018. | S
[5 empty] | Overall Rating | S
Please Provide the Name and Contact information of person(s) reponsible for completeling the Rating section
| Name: | Biplove Choudhary
| Email: | biplove.choudhary@undp.org
| Please justify your rating and address the following points: 1. Indicate trends, both positive and negative, in achievement of outcomes as per the project indicators. 2. Detail critical risks that have affected progress. 3. Outline response to MTR undertaken this reporting period. 4. Outline action plan to address projects with a rating of HU, U or MU. Please keep your input to 1200 words |  | The project is on track to meet intended outcomes as per the project indicators. The overall progress so far is satisfactory despite minor issues/challenges - as reported in the Mid Term Evaluation (MTE). The project has made important contributions in enhancing capacities of communities and government functionaries, mainly in the areas of promoting climate-resilient agriculture and livestock practices, as well as in climate risk information management and dissemination to dry zone farming communities. As noted by the MTE mission, there were minor issues under outcome 1 of the project, where delays were encountered due to lack of clarity on procedures for land use for watershed rehabilitation/reforestation, as well as due to delays in procurement pertaining to engagement of partners for the installation of small-scale water infrastructure. The project team is taking the recommendations of the MTE seriously and have already started actions for course-correction. The Project Steering Committee has directed the project team to conduct a detailed analysis of targets and budgets and propose corrective measures - towards increasing efficiency and enhancing quality of deliverables. The outcome on promotion of climate-resilient agriculture and livestock practices has benefitted dry zone communities immensely and there is clear evidence of good results in the field, as noted in the MTE. During the remaining period, the project will provide additional emphasis on dissemination and replication of these practices beyond demonstration areas to project and non-project areas to ensure long-term sustainability of important asset built by the project. The collaboration of the Department of Agriculture and Livestock Breeding and Veterinary Department have been useful. Similarly, for the outcome on climate risk information management and dissemination, the project has made important contributions, especially in building capacity of government officials in the Department of Meteorology and Hydrology and Department of Agriculture in strengthening weather forecasting and early warning systems. The tools developed under this outcome will enable informed planning and investment decisions about appropriate risk reduction measures. The collaboration from DMH and DOA has been good and these departments have taken proactive, leadership role during implementation. The project will now have to focus more on dissemination of the tools and systems developed under this outcome - so that they benefit farming communities. A critical risk that has emerged is the difficulty in acquiring land for watershed rehabilitation/reforestation programme. This has caused slight delays in implementation and the project team has had to invest considerable time in processing approval with the government. The project steering committee has considered this risk, and measures are being taken to resolve the issue, including seeking intervention of the Ministry of Natural Resources and Environmental Conservation. The Ministry is currently trying to resolve the issue and coordinating with other arms of the government to secure permission for land use. This issue will most likely be resolved in the first quarter of 2018. While the MTE mission is completed, the report is still being finalized. The project has already started preparing the draft management responses for MTE recommendations. One of the significant recommendation of the MTE is to adjust project targets and budget under outcome 1 and enhance quality of deliverables for watershed rehabilitation/reforestation and renovation of water retention ponds. In response to this recommendation, the project is already conducting a detail analysis of the targets and budget under outcome 1 and a proposal for revision of targets and budget will be submitted to the Project Steering Committee in early 2018. One of the challenges in project implementation is ensuring women's participation and in meeting gender equality targets. While the situation has improved compared to the last reporting period, more efforts are required to meet the target. The project will have to provide additional focus on women's participation in project activities and ensure gender disaggregated reporting from implementing partners. Moving forward, an important aspect for the project is to ensure quality of outputs of the implementing partners and enhance joint monitoring activities in the field with government counterparts. It is also important for the project team to ensure that government counterparts and local communities are fully engaged during implementation, so as to ensure sustainability of project activities.
| Progress on Key Milestones |  | Expected Progress |  | Progress to Date | Rating
Other
Overall Rating
Please Provide the Name and Contact information of person(s) reponsible for completeling the Rating section
Name:
Email:
Please justify your rating and address the following points: 1. Indicate trends, both positive and negative, in achievement of outcomes as per the project indicators. 2. Detail critical risks that have affected progress. 3. Outline response to MTR undertaken this reporting period. 4. Outline action plan to address projects with a rating of HU, U or MU. Please keep your input to 1200 words
Rating Definitions
|  |  | Highly Satisfactory (HS) | Project actions/activities planned for current reporting period are progressing on track or exceeding expectations to acheive all major outcomes/outputs for given reporting period, without major shortcomings. The project can be presented as “good practice”.
|  |  | Satisfactory (S) | Project actions/activities planned for current reporting period are progressing on track to achieve most of its major outcomes/outputs with only minor shortcomings.
|  |  | Marginally Satisfactory (MS) | Project actions/activities planned for current reporting period are progressing on track to achieve most major relevant outcomes/outputs, but with either significant shortcomings or modest overall relevance.
|  |  | Marginally Unsatisfactory (MU) | Project actions/activities planned for current reporting period are not progressing on track to achieve major outcomes/outputs with major shortcomings or is expected to achieve only some of its major outcomes/outputs.
|  |  | Unsatisfactory (U) | Project actions/activities planned for current reporting period are not progressing on track to achieve most of its major outcomes/outputs.
|  |  | Highly Unsatisfactory (U) | Project actions/activities planned for current reporting period are not on track and shows that it is failing to achieve, and is not expected to achieve, any of its outcomes/outputs.
Note on D8: Biplove Choudhary: Pond?
Note on D23: Biplove Choudhary: this is the same as output 1.2??
Note on F81: Biplove Choudhary: Please include a section on sustainability

## Project Indicators
PROJECT Indicators
Please provide all indicators being tracked for the project as outlined in the project document
Type of Indicator (indicators towards Objectives, Outcomes, etc…)
Type of Indicator | Indicator | Baseline | Progress since inception | Target for Project End
Objective | % of households in target site implementing climate change adaptation livelihood measures introduced by the project | Current agricultural and livestock rearing practices among subsistence farmers are based on historical climatic conditions and trends and are unsuited to increased drought conditions that are becoming increasingly frequent in the Dry Zone in Myanmar | 73% impoverished farming households (equivalent to 29,671) benefit from climate-resilient agriculture and livestock and agroforestry interventions (8,019 HH in Agriculture sector, 4041 HH in livestock sector and 17,611 HH homestead gardening) | By the end of the project, at least 61% of impoverished farming households or the landless, equivalent to approximately 24,498 households (11,550 agriculture, 6,648 agroforestry/homestead gardening and 6,300 livestock) benefit from and implement climate-resilient agriculture or livestock practices
| % of Dry Zone hoseholds using climate risk information to adjust their livelihood behavior | Currently climate risk information on sudden onset of disasters is delivered only to those houses with TV/radio and yet the level of interpretation and response is low. The outreach and understanding of information on slow onset of disasters are even lower. | Data not available right now. This will be available after the impact survey in 2018/19 | At least 50% of all households in target location (based on random sampling), equivalent to 25,000 households, report that they have changed their livelihood behaviour based on climate risk information produced by the project
| % of Dry Zone households with access to early warning information on sudden onset of disasters | Currently climate risk information on sudden onset of disasters is delivered only to those houses with TV/radio and yet the level of interpretation and response is low. The outreach and understanding of information on slow onset of disasters are even lower. | Data not available right now. This will be available after the impact survey in 2018/19 | At least 75% of all households in target location, equivalent to 38,000, receive early warning in a timely manner.
Outcome 1 | Outcome Indicator 1: % of Dry Zone farmers reporting increased freshwater availability during dry periods | 74% of households in project targeted townships area currently face shortages of fresh water supply for domestic and agricultural use | 13,371 HH have received water supply for domestic and agricultural use. | At least 60% of households facing water shortages in 280 villages in the five project targeted townships report increased freshwater availability during dry periods
| 1.1. Additional community-based freshwater supply and storage infrastructure put in place in drought-prone villages | 0 additional freshwater supply and/or storage infrastructure in drought-prone villages to account for climate change-induced increases in drought | *45 run off/flush water diversion canals renovated to collect water and divert into village water retention ponds increasing access to water for drinking, domestic use and irrigation *75 communal water retention ponds rehabilitated. *Soil and water conservation measures applied on 852 hectares of land *304 HH trained on soil and water conservation techniques | 45 canals for water diversion constructed, 70 small-scale water pumping systems installed, 56 communal water tanks (500 galoons) incl. pipes installed, 40 shallow tube wells constructed, 150 communal ponds rehabilitated or constructed, 10 deep tube wells (new and repaired/renovated), 1,156 ha of land covered with soil and water conservation techniques, Trainings on water infrastructure, soil & water conservation, operation and management, Water Usage Groups formed with by laws
| 1.2. Hectares of watershed area protected through community-based afforestation, reforestation and regeneration practices | 1,500 ha of natural forest conservation and community based reforestation practices in the critical watershed area in the project area | In total : 4,008 ha of land are protected and rehabilitated.  2,625 Ha of natural forest conservation accomplished  843 Ha of Community Forest established  540 Ha of tree planting activities on public land accomplished | 3,913 ha of natural forest conservation, 1,458 ha of community forest establishment including (# of community forest management plan) 770 ha of tree planting activities on public land, 661 ha of Micro-watersheds, 35.5 ha of Road-side planting, 32.2 ha of planting in religous compounds 38.5 ha in Schools and 2.8 ha in clinics
| 1.3. Hectares of land covered by systematic new agroforestry plantations | 160 ha of traditional agro-forestry home garden and 430 ha of farm boundary plantations currently exist in 280 villages in five targeted townships | In total: 1,378 ha of land covered by systematic agroforestry plantations  600 Ha of Homestead gardening/ agro-forestry  710 Ha of farm boundary plantation  13 Ha of Demo plots established  55 Ha of Gap plantation | 1,000 ha of homestead gardening/agro-forestry plots established in 76 villages, 1,500 ha of farm boundary plantations in 95 villages
Outcome 2 | Outcome Indicator 2: Number of climate-resilient agricultural and livestock practices demonstrated and adopted to support adaptation of marginal farmers and landless households | Agricultural and livestock practices and extension services in the Dry Zone pay only limited attention to climate change risks. | Project demonstrated at least 6 discrete agricultural adaptation measures - such as climate resilient farming method, Alternative Wet and Dry Technology and drip irrigation demonstration (on-farm water management techniques), establishment of perennial trees and demonstration plots (soil managment techniques), farmer-managed seed multiplication and participatory varietal selection, post-harvest processing techniques and promoting diversified livestock production system and breeds. | By the end of the project, at least 6 discrete agricultural adaptation and diversified livestock rearing practices are demonstrated including resilient varieties, on-farm water management techniques, soil management practices, planting techniques, post-harvest processing, and diversified livestock breeds.
| 2.1.1. Number of Dry Zone farmers exposed to and involved in climate resilient farming techniques | In project target villages, farmers have only limited exposure to climate-resilient farming techniques | Overall 8,019 HH (direct and indirect beneficiaries and extension workers) have been trained on climate-resilient crop production system. - 3,011 HH received training on climate resilient farming methods - CC vulnerability and impacts on agriculture, water and soil conservation techniques, climate-resilient seed conservation techniques, integrated pest management, fertilizer application, post-harvest and pre-harvest crop management systems, etc (male = 2,239 and female = 772) - 377 HH received training on Water Smart Practices (AWD) - (male = 260 and female = 117) - 70 HH received training on establishment of perennial trees (thanaka) - (male = 56 and female = 14) - 190 HH received training on establishment of perennial trees (fruit trees) - (male = 141 and female = 49) - 128 HH received training on establishment of drip irrigation system (male = 116 and female = 12) - 1,764 HH received training on organic farming and verminculture (male = 1,391 and female = 373) | By the end of the project, at least 11,550 (11,200 farmers plus 350 others) households, extension workers and CSO/NGO members in the target townships are trained on climate-resilient farming methods. Trainings on (#/hhs/m-f): - Climate resilient farming methods - Water smart practices (AWD) - Thanahka intercropping - Fruit tree drip irrigation - Organic farming and vermiculture
| 2.1.2. Accessibility to drought-resilient seed varieties | Only limited seed sourcess are available in the target townships | Overall 8,019 HH (direct and indirect beneficiaries and extension workers) have been trained on climate-resilient crop production system. 89 villages were trained on climate-resilient seed multiplication techniques. The remaining villages will be implemented in 2018. - 985 HH received training on climate-resilient seed multiplication (male = 767 and female = 218) | At least 140 villages produce climate-resilient seed varities - Trainings on climate-resilient seed multiplication (# hhs/m-f)
| 2.1.3. Number of project and non-project community members participating in exchange visits and demonstration plots | Currently there is no initiatives in the Dry Zone promoting cross exchange between Townships of practical knowledge on climate resilient farming techniques | Overall 8,019 HH (direct and indirect beneficiaries and extension workers) have been trained on climate-resilient crop production system. Community participants from non-project villages will be engaged in the exchange visit programme in 2018. 146 HH participated in farmer field schools (male = 103 and female = 43) 180 participatory demonstration plots on climate-resilient agricultural practices established (1,348 HH received training on participatory demo plots and participatory varietal selection) | At least 20% of community participants in exchange visits and farmers field demonstrations are from non-project target villages Farmer field schools on climate change (# hhs/m-f) At least 50 participatory demonstration plots on climate-resilient agricultural practices are established
| 2.2. % of households who report reduced harvest losses due to improved post-harvest processing and storage | Only few households apply improved post-harvest processing techniques | 8,913 HH have experienced reduced post-harvest losses through use of improved processing and storage technology. - 20 rice threshers and 107 multi-crop threshers have been provided. - 127 thresher user groups in 5 project townships established -299 HH received training on participatory assessment of post harvest loss. - 36 seed storage system have been installed to introduce community-managed crop handling and storage facilities and to avoid crop loss, which benefited 795 HH in total (male = 656 and female = 139) | 80% of target households (9,240 of 11,550) report reduced post-harvest losses through the use of improved processing and storage technology - 20 rice threshers and 120 multi-crop threshers - Establishment of thresher groups (140) - Trainings and participatory assessments of post harvest loss - Elevated storage systems (36)
| 2.3. Number of landless and marginal households with increased diversity of livestock assets | Majority of impoverished farmers (either landless or those with less than 2.5 hectares of land) in the Dry Zone have zero or small number of livestock: 65% have no livestock and 35% own some livestock | During the reporting period, 3,948 marginal and landless households have increased livestock assets (3,200 first-in-line beneficiaries and 748 second-in-line beneficiaries consisting mostly marginal and landless households) 113 demonstrations (mostly small breeder farms of goat, local chicken and pig cross breeds) for 113 landless and marginal farmer households are established. Demonstration activities include 12 local chicken for commercial breeding, 4 semi-broiler for cross breeding, 40 goat breeder farm, 37 DYL cross breeding and 20 pasture demonstartion plot (Napier grass plantation). Demonstration plots support in increased diversity of livestock assets and keeping the resilient breeds at the communities. | By the end of the project, at least 6,300 marginal and landless households have increased the diversity of livestock assets. Diversity in types: - Cattle - Sheep - Goat - Pig - Poultry Climate-resistant/improved breeds
Outcome 3 | Outcome Indicator 3-1: % of Dry Zone households using climate risk information to adjust their livelihood behavior | Currently climate risk information on sudden onset of disasters is delivered only to those houses with TV/radio and yet the level of interpretation and response is low. The outreach and understanding of information on slow onset of disasters are even lower. | Data not available right now. This will be available after the impact survey in 2018/19 | At least 50% of all households in target location (based on random sampling), equivalent to 25,000 households, report that they have changed their livelihood behaviour based on climate risk information produced by the project
| Outcome Indicator 3-2: % of Dry Zone households with access to early warning information on sudden onset of disasters | Currently climate risk information on sudden onset of disasters is delivered only to those houses with TV/radio and yet the level of interpretation and response is low. The outreach and understanding of information on slow onset of disasters are even lower. | Data not available right now. This will be available after the impact survey in 2018/19 | At least 75% of all households in target location, equivalent to 38,000, receive early warning in a timely manner.
| 3.1. Number of climate risk maps, vulnerability assessments and scenarios in active use by township authorities, NGOs and CBOs to improve planning decisions and prioritize investment actions | No climate risk maps, vulnerability assessments and scenarios in active use by township authorities, NGOs and CBOs to improve planning decisions and prioritize investment actions | Climate profiles and risk scenarios for 5 project townships completed; Participatory risk assessment in 144 village tracts of 5 project townships conducted. Climate hazard maps for 5 Project townships have been developed which are Drought map, Flood map and Earthquake map. | Climate hazard maps, vulnerability assessments and risk scenarios are available in each township
| 3.2.1. Number of local institutions that issue regular warning and forecasting communications to community-based organisations and vulnerable households | Currently, no such information is available except weekly/mothly forecats boradcasted over TV/radio | 75 Village Disaster Management Teams have been formed with 22% women's representation and 5 Climate Risk Informaiton Sub-Committees have been formed in the 5 project townships. | 70 community based disaster risk management (CBDRM) committees are formed to relay climate early warning information from the Township DPC. 5 Climate Risk Information sub-committees established within the Township Disaster Preparedness Committee
| 3.2.2. The number of climate related information materials produced to assist Dry Zone farmers to adjust their livelihood behavior | Not available | 295 Agromet bulletins produced; DMH-SESAME mobile application produced and translated into Myanmar language - which provides 3 days and 10 days weather forecasts (temp, rainfall, humidity, PET, spell and soil moisture) | At least six agro-meteorological bulletins; two early warning and disaster response bulletins/posters; four guidance notes on resilient agricultural/livestock practices produced

## Lessons Learned
QUALITATIVE MEASURES and LESSONS LEARNED
Please complete the following section every reporting period
Implementation and Adaptive Management | Response
What implementation issues/lessons, either positive or negative, affected progress? | The vast geographical coverage of the project (50,000 households in 280 villages of 5 townships across 3 regions) posed several challenges in coordinating, implementing and monitoring project activities. For instance securing approval for land for rehabilitation/reforestation activities was extremely challenging and time-consuming given that locations are spread out across several villages in the 5 project townships. Added to this is the difficulty in maintenance and monitoring of rehabilitated/reforested areas, due to distance and remote locations. The project has discussed these concerns with the counterpart department, as well as with the TAG and PSC members, and it has been agreed that in 2018, rehabilitation/reforestation activities will be implemented in larger areas in fewer locations with more emphasis on quality and survival of plantations. Due to the very ambitious project targets, quality of some project deliverables have suffered. As pointed out in the Mid Term Evaluation, the project standard cost norms for rehabilitation/reforestation activities and renovation of water retention ponds are much lower than similar activities with government. As a result, the PSC has agreed to lower the targets for watershed rehabilitation/reforestation and renovation/construction of water retention ponds and allocated additional resources to enhance quality of deliverables. The investments on water resources have proven very impactful for the communities, as there is acute shortage of water in the dry zone - for both domestic and agirculture use. The engagement and participation of communities in water infrastrcture related support has been very positive. The communities that have had major domestic water supply projects previously (with the help of international NGOs) present a model for future communities and staged investment in water system using community funds generated from water use fees. There were high community participation and willingness to pay when pond renovation activities are implemented. As noted in the Mid Term Evaluation,the project has leveraged as much as 50% cash contributions from some of these communities. The application of user fees is something that is being applied for the management of other project assets - so as to make project investments more sustainable in the long-run. A close working relationship with relevant departments at the township level and the high level of outreach and stakeholder consultation served to expand the project activities smoothly and resulted in good participation from the government departments especially under outcome 2 and outcome 3. In some instances, such as promotion of climate resilient agriculture and livestock practices and climate risk information dissemination, concerned departments took leadership role in implementing activities. The collaboration with the Department of Meteorology and Hydrology has been exceptional and data sourced from the department has allowed the project to generate much-needed weather forecasts, which in turn is disseminated to the farmers. The system of having regular dialogues with project counterparts/partners continue to be immensely beneficial in addressing implementation issues. The monthly project coordination meetings with the counterpart agency (Dry Zone Greening Department) has helped the project in building trust and confidence, in addition to addressing implementation challenges and bottlenecks. The quarterly project coordination meetings with partners is yet another mechanism employed by the project which has ensured better coordination and alignment of project activities. The arrangement to convene Technical Advisory Group (TAG) meetings in the 5 project townships (on a rotational basis) is very useful as this provides opportunities for TAG members and local government stakeholders to witness progress of project activities first hand and provide technical inputs and advise to implementing partners. The PSC has met on a six-monthly schedule, reflecting a high level of attention paid by the Government to the project. The project database compiled during the iniital phase of project implementation has been a useful resource for planning interventions throughout. The project prioritizes interventions on mainly landless, marginal and women-headed households in order to achieve the objectives of reducing vulnerability and enhancing adaptive capacity of households to address climate-related food security issues. The database developed by the project consist of beneficiary details (household head, livelihood source, land holding etc.). For specific sectoral interventions, the project also conducts needs assessments and identifies beneficiaries based on the overall project criteria of prioritizing landless and marginal farmers. All these ensured that most project assistance has been channeled to the most-needy and marginalized population. The agricultural activities including drought-tolerant crop varieties, inter-cropping and other farming methods, threshing equipment, improved seed storage and multiplication have provided clear benefits to the participating farmers. The demonstration plots have generated considerable farmer interest. Participating farmers express a high level of satisfaction and commitment to the improved seed varieties and inter-crop farming. In addition, new threshing equipment and seed storage facilities are greatly appreciated given the high rate of post-harvest losses of 50% and higher, as per the post-harvest assessment report published by the project. For the remaining period, the project will need to focus more on replication of these initiatives in other project and non-project villages The high turn-over of government staff and limitation of internal communication and sharing of information within government organizations and between levels of government contributed to lack of awareness of the project. The project has at least ten counterpart departments at various levels and despite the strong field activity coordination efforts, there are still gaps in information flow within the government system. The project has made efforts to provide progress reports to stakeholders, whenever requested.
Were there any delays in implementation? If so, include any causes of delays. What measures have been taken to reduce delays? | The installation/construction of small-scale water infrastructure was delayed significantly owing to a non-responsive RFP process in the first round of bidding. The bid had to be re-advertized as an ITB in the second round. The entire process took some time and caused delays in implementation. In the second round of procurement process, the ITB was re-designed in 3 lots with the help of UNDP Regional Office in Bangkok. The procurement process resulted in the selection of two competent firms for the 3 lots and implementation started only in Dec 2017. Field activities related to this component will be completed in Aug 2018. The lack of clarity in the land approval process for rehabilitation/reforestation activities posed significant challenges to the project team and implementing partner. This caused delays in field activities - as the project had to invest time in securing approval at different levels. Approval from communities and village development committees have been secured. As recommended by General Administration Department (GAD), site verification has been conducted by respective township level committees, but GADs responded that they are unable to grant approval since they are not authorized to grant approval. The project elevated the matter to the Project Steering Committee as well as approached the respective Regional Chief Ministers for assistance, and then to the Minister, Ministry of Natural Resources and Environmental Conservation. The issue was discussed again at the PSC meeting held on 20 Dec 2017, where it was agreed that the project will process for "no objection letter" from the respective GADs and continue with rehabilitation/reforestation activities based on the "no objection letter." The main counterpart Dry Zone Greening Department has committed to provide support in securing the "no objection letter" from the respective GADs of 5 townships.
Describe any changes undertaken to improve results on the ground or any changes made to project outputs (i.e. changes to project design) | Under Output 1.1 - the targets on new/renovation of 10 deep tube wells and 40 shallow tube wells were changed to 12 deep tube well and 20 shallow tube wells as per findings of the assessment report for small-scale water infrastructure needs. The amount saved from reduction of target for shallow tube well has been used to fund the 2 additional deep tube wells. The decision to change the targets was made by the 4th Project Steering Committee meeting held on 30 June 2017. There is however, no change in the output statement. As per recommendations of the Mid Term Evaluation, the project is expecting further changes in targets under output 1.1, 1.2 and 1.3. The recommendations of the MTE will be deliberated in the special sessions of TAG and PSC in Jan 2018 and the resulting changes will be reported in the next PPR.
How have gender considerations been taken into consideration during the reporting period? What have been the lessons learned as a consequence of inclusion of such considerations on project performance or impacts? | Gender considerations have been included in all field activities such as participation in workshops, meetings and prioritization exercises, farmers' group formation, selection of laborers for project activities, beneficiary selection for livestock distribution and training activities. While women's participation in trainings and user groups (eg. thresher user groups) have been encouraging, their participation in field activities (labour inputs) have been low because of the physical nature of participation. The project has accorded priority to women-headed households in its livestock distribution programme and there is clear evidence that women are benefitting from project interventions. The project has placed emphasis on the need for implementing partners to report gender disaggregated data in all its reporting (monthly and quarterly) mechanisms. This data is carefully recorded and the impacts of results will be monitored from time to time. The project reports gender-related stories from the field and publishes it from time to time through UNDP Intranet site and UNDP facebook page. The MTE mission noted that the project is making a visible effort to ensure women are a significant part of the project. For instance, the consultation meeting on village selection recorded 28% participation by women; the livestock rapid needs assessment and beneficiary selection in 253 villages recorded 35% participation of women; 20% of livestock farmer committee members are women. In the training activities conducted under the project so far, 38% of the participants are female (4,327 out of 11,415).
Please complete the following section at mid-term and project completion
Lessons for Adaptation | Response
Climate Resilience Measures
What have been the lessons learned, both positive and negative, in implementing climate adaptation measures that would be relevant to the design and implementation of future projects/programmes for enhanced resilience to climate change? | The assumption that land would be readily available for rehabilitation/reforestation and watershed treatments was over-estimated, as reflected in the complicated approval processes and delays that have occurred. A considerable amount of time was spent in identifying sites and seeking endorsements of concerned authorities. These issues could have been sorted at the design stage to avoid creeping into precious implementation time. Similarly, the identification of target villages in the 5 project townships took some time and this activity could have been implemented during the design stage. The expectation that women would be major participants in the project was also over-estimated, although various adjustments are being made to respond to this issue. Given the context of Myanmar, there are several underlying issues related to gender equality, most of which is beyond the scope of the project. While efforts are being made to encourage women's participation in project activities, it will not be possible to see actual impacts during the life of the project. The ambitious targets (especially under watershed rehabilitation/reforestation) resulted in spreading out resources too thinly. This has led to a situation where budget for rehabilitation/reforestation prgramme are much lower than government norms and this affected quality of the plantation. Availability of land and acquisition of land is a real issue in the context of Myanmar. The lack of clarity in procedures caused delays in implementation and resulted in considerable staff time spent on processing approvals/endorsements and consultations, etc. The availability of land also posed constraints to the project, in terms of implementing activities in a coherent manner. For instance, watershed conservation activities could have been implemented nearby water retention ponds, but at most locations this was not possible since land was not available. The effectiveness of enhanced weather forecasts and early warning system should consider not only access to but also use of the forecasts in farming, planting and maintenance decisions. In the remaining period, the project will accord more emphasis on use of forecast and early warning information for decision-making in day-to-day agriculture practices. The multi-sectoral nature, as well as the large geographical coverage of the project posed several challenges, especially in terms of sequencing/planning a diverse range of activities being implemented by several implementing partners. A more sectoral focus (eg. promoting climate-resilience in agriculture) within a smaller geographical area would have produced better results/impacts. While there is general understanding of the negative impacts of climate change among farming communities in the dry zone, adaptation measures need to be simple, well-understood and inexpensive for demonstration and replication. Most marginal farmers are unable to replicate adaptation measures that involve costly interventions.
What is the potential for the climate resilience measures undertaken by the project/programme to be replicated and scaled up both within and outside the project area? | There are some evidence of replication and upscaling of some of the project activities. However, this will be better assessed towards the end of the project. At this stage of implementation, communities are still in the process of understanding the costs and benefits of these interventions and it will take some to fully capture results in terms of replication and up-scaling. The farmer field school and exchange programme adopted in the project has been useful in disseminating climate resilient measures both within and outside the project area.
Readiness Interventions (Applicable only to NIEs that received one or more readiness grants)
What have been the lessons learned, both positive and negative, in accessing and implementing climate finance readiness support that would be relevant to the preparation, design and implementation of future concrete adaptation projects/programmes? | N/A
How have the outputs (such as manuals, guidelines, procedures or the experience from providing peer support, etc) from employing readiness grants been used to inform institutional capacity needs, gender issues, and environmental and social aspects in developing and implementing concrete projects/programmes for enhanced resilience to climate change? | N/A
Concrete Adaptation Interventions
What have been the lessons learned, both positive and negative, in implementing concrete adaptation interventions that would be relevant to the design and implementation of future projects/programmes implementing concrete adaptation interventions? | The project interventions are relatively small-scale and spread out thinly - due to the diverse nature of activities and large geographical focus (280 villages in 5 townships under 3 regions) of the project. The dispersed locations limit the potential to demonstrate the combined effects of multiple adaptation measures on households, communities, and landscapes. The availability of water during dry periods is the most pressing issue in the dry zone. In most project locations, the only practical way to ensure secure access to freshwater throughout the year is to retain water in communal ponds during the monsoon season and use it throughout the year. Ideally, effective adaptation actions should be to minimize the water loss by, for example, placing lining under the water to reduce seepage. However, during the project design, a conscious decision was made to spread out adaptation benefits to wider populations at the cost of delivering greater resilience building benefits to smaller populations. A proper analysis of cost-effectiveness of various options during the project design would have ensured most efficient and effective use of finite resources. Possible options that should be in such an analysis include the conventional silt removal (currently employed in the project in many locations); placement of lining underneath the water; and other ecosystem-based measures to substitute or complement direct retention expansion measures. The seasonal nature of some adaptation measures (eg. watershed rehabilitation/reforestation) poses challenges in implementing the project in a coherent manner. Availability of land and land acquisition process late in the year caused rushed decisions in plantation preparations and planting after the start of the rainy season lead to low survival of seedlings and poor-quality plantations. The agro-forestry interventions should focus on larger sites to model and showcase demonstrations of introducing trees into cropping and inter-cropping systems and alternatively introducing cover crops into existing tree farms. Due to land availability issues and the ambitious targets, the project had to resort to demonstration of agro-forestry practices in smaller farm areas The delivery of drought resilient livestock species to marginal farmers was well-received and proved to be the most beneficial intervention. The returns on investment on livestock is realized within a span of about 4 - 8 months and this in turn provides additional income for households, as well as provides a buffer during extreme events and disasters. However, the community-managed livestock banking system needs to be backed by institutional strengthening and capacity building activities, as well as monitored closely to ensure long-term sustainability and continuity. The inter-cropping systems and other agronomic climate change adaptation measures have had good impacts on people's perception on climate-resilient farming practices. A robust strategy to disseminate and expand their use by other farmers is a must for better replication and upscaling of these interventions.
What is the potential for the concrete adaptation interventions undertaken by the project/programme to be replicated and scaled up both within and outside the project area? | The inter-cropping systems and other agronomic climate change adaptation measures have had good results on the two or three demonstration plots in each village where they have been tested. These climate change adaptation measures have high potential for replication but significant additional support to expand their use by other farmers is needed in the form of information and advice and the possible expansion of the farmer field school approach to dissemination of the new methods. The introduction of new drought-resistant crops, more diversified cropping systems and the measures to reduce post-harvest losses, and livestock raising by marginal farmers are the most successful interventions so far. These interventions involve simple technologies and approaches that have potential to be scaled up, both within the project villages (i.e beyond demonstration plots) and to other areas of the dry zone. Due to the acute shortage of water for drinking and domestic use, the improvement in enhancing water supply is greatly appreciated by communities. In most instances, communities have willingly contributed co-financing for interventions on water retention/capture. Any visible and effective measures to enhance water supply is likely to be replicated and up-scaled in the future. The advance tools in weather forecasting and early warning (weather forecasts, crop advisories and disaster alert notification) have been significant and may provide important extension assistance in future agriculture practices.
Community/National Impact
What would you consider to be the most successful aspects for the target communities? | The most successful aspects for the target communities have been the following: - Provision of small-scale water infrastructure, which in turn has ensured water availability during dry periods. The interventions that ensured additional water for irrigation have greatly benefitted communities in terms of increased production and generated additional income for marginal farmers. - The introduction of new drought-resistant crops, more diversified cropping systems and the measures to reduce post-harvest losses are also very successful. These interventions involve simple technologies and approaches and the potential to be scaled up and replicated is high. - The provision of drought-resilient livestock species has also been very successful and well-received by communities. Livestock rearing has meant diversified income base, which provides a buffer during extreme events and disasters.
What measures are/have been put in place to ensure sustainability of the project/program results? | The project has, right from the start, ensured community participation and capacity building to manage new assets/systems (eg. seed storage facility, livestock banking system, crop thresher user groups, water user groups, etc), which will be a key to long term sustainability of project interventions. The engagement of government counterparts in annual work planning and implementation is a key aspect of project management. This has ensured that project activities are implementation as per government plans and programmes and in accordance with government standards and norms. The climate risk information management system developed under the project has ensured leadership role by Department of Meteorology and Hydrology (DMH) and integrated project activities with DMH activities. The weather forecasts, including agro-advisories and early warning system generated through project assistance have been fully integrated into government systems/extension programs. The weather forecast and agro-advisory system is owned and operated by the DMH. The Disaster Alert Notification (application) is owned and operated by the Department of Disaster Management. The project has also conducted risk/vulnerability mapping and risk mapping in a participatory manner engaging government staff so as to build local capacity. The project is also in the process of preparing a sustainability plan and exit strategy for each of the outcomes under the project, as per directives of the 6th Project Steering Committee meeting held on 5 Feb 2018.
What measures are being/could have been put in place to improve project/program results? | Considering the time taken during the initial stage of implementation, preparatory activities such as identification of project target villages and identfication of watershed rehabilitation/reforestation areas could have been agreed with the government and stakeholders during the design phase. A considerable amount of implementation time was spent on managing these activities. The initial design specifications and cost estimates from 2012 should have been updated at inception phase based on site circumstances in the project locations. Doing this would have provided a more realistic basis for planning project interventions and processing procurement/contractual actions under the project. Alongside this, the project could have exercised some flexibility in adjustment of targets, providing more focus on quality rather than on meeting targets. This issue has been highlighted by the MTE and as such, targets for some indicators have been reduced to enhance quality of project deliverables. The project has put in place a robust monitoring and reporting system whereby stakeholders and counterparts are informed of project progress/results on a regular basis. The quarterly Technical Advisory Group meetings are being held in the 5 project townships on a rotational basis. This arrangement provides members of the Technical Advisory Group the opportunity to jointly monitor project activities with the project team. In addition, the project has also diligently catered to all ad hoc requests for project progress from individual government departments, in an effort to enhance visibility of the project. A project database and a monitoring and evaluation framework has been put in place and project results are being monitored continuously as per the framework. The project is also in the process of preparing a sustainability plan and exit strategy for each of the outcomes under the project, as per directives of the 6th Project Steering Committee meeting held on 5 Feb 2018. This will ensure proper consolidation of field activities and ensure continuity of project activities after project closure.
Knowledge Management
How has existing information/data/knowledge been used to inform project development and implementation? What kinds of information/data/knowledge were used? | The project maintains a dynamic record of all information related to project implementation, including back to office reports, minutes of meetings, monthly and quarterly reports, annual project performance review report, as well as deliverables/reports under each of the project outputs. Project Steering Committee meetings are held bi-annually and Technical Advisory Group meetings are held on a quarterly basis where project progress is reviewed and challenges/bottlenecks discussed. The project team facilitates and organizes consultation with sectoral departments and local administration to inform them on important milestones and present assessments, reports for their inputs and ideas from time to time. Updates are also being provided to the Chief Ministers of the 3 regions and the Minister, Ministry of Natural Resources and Environmental Conservation on a bi-annual basis. Data on project results are updated/recorded by the M&E Officer on a quarterly basis. Lessons from project implementation are captured on a regular basis and recorded. Articles, press releases and photo stories and best practices from the field are compiled and published on UNDP internet site and facebook page, as well as on other online sites, thereby enhancing the visibility of the project. A record of photos from project implementation is maintained in the project photo library and shared during important events, such as World Environment Day, International Day for Disaster Risk Reduction, etc. Lessons (both positive and negative) from the project are being shared internally within UNDP and incorporated into other projects that are being developed and implemented. In addition, project lessons are also shared with project formulation missions from other development partners, as well as in events organized by development partners working on similar topics. A case study on the development of mobile application for weather forecasting and early warning system was recently submitted in response to a call from World Bank/GFDRR – to be featured as a global best practice on climate risk management at local level.
If learning objectives have been established, have they been met? Please describe. | The arrangement to organize Technical Working Group meetings in project township was instituted with the objective of promoting learning and sharing experience among government counterparts, implementing partners and UNDP project team. The joint monitoring during the Technical Working Group meeting provides space for cross-learning and providing technical advice/inputs based on local knowledge and experience. The quarterly project review and coordination meetings with implementing partners provides a platform for cross-learning and exchange of ideas, including for integration of project activities in the different sectors/outputs of the project. This platform has also been used to review progress of project activities and resolve issues/bottlenecks confronting the project. The project team has also proactively trained personnel of implementing partners on aspects such as reporting, monitoring, annual work planning, etc and over the course of project implementation, there has been a marked improvement in these areas. Closer to the closure of the project, a project lessons learning workshop will be organized to capture and record lessons from the project, which can provide inputs and inform implementation of projects in the future. The engagement of government counterparts in project implementation, in monitoring project activities, as well as in community trainings and workshops has resulted in increased capacity of government officials at the local level. The community trainings have been mostly delivered through engagement of technical staff form government departments as resource persons. The delivery of project through engagement of local NGO/CSO partners have also contributed to capacity development of the institutions, as well as local staff involved in project implementation. The engagement of community in management of important project assets has also lead to increased knowledge and capacity of community groups, which in turn will ensure long-term sustainability of project activities.
Describe any difficulties there have been in accessing or retrieving existing information (data or knowledge) that is relevant to the project. Please provide suggestions for improving access to the relevant data. | There have been no major issues with regard to accessing information relevant to the project. Most of the resources necessary for the project are available within the UN system and the government. However, there were minor hiccups in accessing certain information from government due to the lengthy official procedures required for accessing data and information. The importance of close partnership and collaboration with concerned government agencies in project implementation cannot be undermined.
Has the identification of learning objectives contributed to the outcomes of the project? In what ways have they contributed? | Yes, to a large extent, the identification of learning objectives have contributed to the outcomes of the project. The key beneficiaries in this regard are the various community groups that have been established to manage important project assets (eg. crop threshers, livestock banking system, small-scale water infrastructure, crop and seed storage facilities, etc). The learning objectives have been fulfilled through numerous trainings provided on operations, maintenance and use of project assets for the longer-term. Local government officials have also benefitted from numerous trainings that have been identified by the stakeholders themselves in the initial stages of project implementation. These trainings are delivered through the implementing partners and where possible through engagement of specific subject-area experts in the relevant technical areas. The project has also contributed to enhanced capacity of NGO/CSO implementing partners. This has been useful, especially considering the nascent NGO/CSO community in Myanmar and the limited experience and exposure of personnel of implementing partners
Note on D16: Biplove Choudhary: Please modify the language for limited flexibility

## Results Tracker
Results Tracker for Adaptation Fund (AF) Projects
Goal: Assist developing-country Parties to the Kyoto Protocol that are particularly vulnerable to the adverse effects of climate change in meeting the costs of concrete adaptation projects and programmes in order to implement climate-resilient measures. Impact: Increased resiliency at the community, national, and regional levels to climate variability and change.
Important: Please read the following guidance document (also posted on the Adaptation Fund website) before entering your data
Link: http://www.adaptation-fund.org/sites/default/files/Results%20Framework%20and%20Baseline%20Guidance%20final.pdf
Adaptation Fund Strategic Results Framework
Project ID | PIMS 4703
Implementing Entity | United Nations Development Programme
Type of implementing entity | MIE
Country | Myanmar
Region | Asia-Pacific
Sector | Multi-sector
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Impact: Increased resiliency at the community, national, and regional levels to climate variability and change | Core Indicator: No. of beneficiaries |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project
|  | Total | 0 | 0 | 0 | Total |  | 229155 | 2800 | Total |  | 146890 | 0 | Total
|  | % of female beneficiaries | 0% | 0% | 0% | % of female beneficiaries |  | 53% |  | % of female beneficiaries |  | 47% |  | % of female beneficiaries
|  | % of Youth beneficiaries |  |  |  | % of Youth beneficiaries |  |  |  | % of Youth beneficiaries |  |  |  | % of Youth beneficiaries
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 1: Reduced exposure to climate-related hazards and threats | Indicator 1: Relevant threat and hazard information generated and disseminated to stakeholders on a timely basis | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness
|  | Total | 229155 | Drought | 1: Ineffective | Total | 229155 | Drought | 4: Effective | Total | 0 | Drought | 2: Partially effective | Total
|  | % of female targeted | 53% |  |  | % of female targeted | 53% |  |  | % of female targeted | 0% |  |  | % of female targeted
Output 1.1 Risk and vulnerability assessments conducted and updated | Indicator 1.1: No. of projects/programmes that conduct and update risk and vulnerability assessments | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | 0 | Multi-sector | Local | 1: No plans conducted or updated | 1 | Multi-sector | Local | 3: Risk and vulnterability assessments completed or updated | 1 | Multi-sector | Local | 3: Risk and vulnterability assessments completed or updated
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
Output 1.2 Targeted population groups covered by adequate risk reduction systems | Core Indicator 1.2: No. of Early Warning Systems | No. of adopted Early Warning Systems | Category targeted | Hazard | Drought | No. of adopted Early Warning Systems | Category targeted | Hazard | Drought | No. of adopted Early Warning Systems | Category targeted | Hazard | Drought | No. of adopted Early Warning Systems | Category targeted | Hazard
|  | 0 | 2: Monitoring and warning service | Geographical coverage | Local | 1 | 2: Monitoring and warning service | Geographical coverage | Local | 1 | 2: Monitoring and warning service | Geographical coverage | Local |  |  | Geographical coverage
|  |  |  | Number of municipalities | 5 |  |  | Number of municipalities | 5 |  |  | Number of municipalities | 5 |  |  | Number of municipalities
|  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 2: Strengthened institutional capacity to reduce risks associated with climate-induced socioeconomic and environmental losses | Indicator 2: Capacity of staff to respond to, and mitigate impacts of, climate-related events from targeted institutions increased | Number of staff targeted |  | Sector | Capacity level | Number of staff targeted |  | Sector | Capacity level | Number of staff targeted |  | Sector | Capacity level | Number of staff targeted |  | Sector | Capacity level
|  | Total |  |  |  | Total |  |  |  | Total |  |  |  | Total
|  | % of female targeted |  |  |  | % of female targeted |  |  |  | % of female targeted |  |  |  | % of female targeted
Output 2.1 Strengthened capacity of national and sub-national centres and networks to respond rapidly to extreme weather events | Indicator 2.1.1: No. of staff trained to respond to, and mitigate impacts of, climate-related events | Total staff trained | % of female staff trained | Type |  | Total staff trained | % of female staff trained | Type |  | Total staff trained | % of female staff trained | Type |  | Total staff trained | % of female staff trained | Type
| Indicator 2.1.2: No. of targeted institutions with increased capacity to minimize exposure to climate variability risks | Type | Scale | Sector | Capacity level | Type | Scale | Sector | Capacity level | Type | Scale | Sector | Capacity level | Type | Scale | Sector | Capacity level
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 3: Strengthened awareness and owernship of adaptation and climate risk reduction processes | Indicator 3.1: Increase in application of appropriate adaptation responses | Percentage of targeted population applying adaptation measures |  | Sector |  | Percentage of targeted population applying adaptation measures |  | Sector |  | Percentage of targeted population applying adaptation measures |  | Sector |  | Percentage of targeted population applying adaptation measures |  | Sector
|  | 0% |  | Multi-sector |  | 61% |  | Multi-sector |  | 73% |  | Multi-sector
Output 3: Targeted population groups participating in adaptation and risk reduction awareness activities | Indicator 3.1.1: Percentage of targeted population awareness of predicted adverse impacts of climate change, and of appropriate responses | No. of targeted beneficiaries | % of female participants targeted | Level of awareness |  | No. of targeted beneficiaries | % of female participants targeted | Level of awareness |  | No. of targeted beneficiaries | % of female participants targeted | Level of awareness |  | No. of targeted beneficiaries | % of female participants targeted | Level of awareness
|  | 0 | 0% | 2: Partially not aware |  | 24498 | 43% | 4: Mostly aware |  | 29671 | 21% | 3: Partially aware
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Target performance at completion
Outcome 4: Increased adaptive capacity within relevant development sector services and infrastructure assets | Indicator 4.1: Increased responsiveness of development sector services to evolving needs from changing and variable climate | Project/programme sector | Geographical scale | Response level |  | Project/programme sector | Geographical scale | Response level |  | Project/programme sector | Geographical scale | Response level |  | Project/programme sector | Geographical scale | Response level
|  | Water management | Local | 2: Partially responsive (Lacks most elements) |  | Water management | Local | 4: Mostly responsive (Most defined elements) |  | Water management | Local | 3: Moderately responsive (Some defined elements)
| Core Indicator 4.2: Assets produced, developed, improved or strengthened | Sector | Targeted asset | Changes in asset (quantitative or qualitative) |  | Sector | Targeted asset | Changes in asset (quantitative or qualitative) |  | Sector | Targeted asset | Changes in asset (quantitative or qualitative) |  | Sector | Targeted asset | Changes in asset (quantitative or qualitative)
|  | Water management | 2: Physical asset (produced/improved/strenghtened) | 2: Somewhat improved |  | Water management | 2: Physical asset (produced/improved/strenghtened) | 4: Mostly Improved |  | Water management | 2: Physical asset (produced/improved/strenghtened) | 3: Moderately improved
Output 4: Vulnerable development sector services and infrastructure assets strengthened in response to climate change impacts, including variability | Indicator 4.1.1: No. and type of development sector services to respond to new conditions resulting from climate variability and change | Number of services | Type |  | Sector | Number of services | Type |  | Sector | Number of services | Type |  | Sector | Number of services | Type |  | Sector
|  | 0 | Community |  | Water management | 45 | Community |  | Water management | 45 | Community |  | Water management
|  | 0 | Community |  | Water management | 70 | Community |  | Water management | 0 | Community |  | Water management
|  | 0 | Community |  | Water management | 56 | Community |  | Water management | 0 | Community |  | Water management
|  | 0 | Community |  | Water management | 150 | Community |  | Water management | 75 | Community |  | Water management
|  | 0 | Community |  | Water management | 50 | Community |  | Water management | 0 | Community |  | Water management
|  | 0 | Community |  | Water management | 1156 | Community |  | Water management | 852 | Community |  | Water management
|  | Baseline information |  |  |  | Baseline information |  |  |  | Performance at mid-term |  |  |  | Target performance at completion
Outcome 5: Increased ecosystem resilience in response to climate change and variability-induced stress | Indicator 5: Ecosystem services and natural resource assets maintained or improved under climate change and variability-induced stress | Natural resource improvement level |  | Sector | Type | Natural resource improvement level |  | Sector | Type | Natural resource improvement level |  | Sector | Type | Natural resource improvement level |  | Sector | Type
|  | 2: Partially effective |  | Other | land | 3: Moderately effective |  | Other | land | 2: Partially effective |  | Other | land
Output 5: Vulnerable ecosystem services and natural resource assets strengthned in response to climate change impacts, including variability | Core Indicator 5.1: Natural Assets protected or rehabilitated | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Catchment area/Watershed/Aquifer | 1500 | ha protected | 2: Partially effective | Catchment area/Watershed/Aquifer | 6141 | ha protected | 4: Effective | Catchment area/Watershed/Aquifer | 4008 | ha protected | 3: Moderately effective
|  | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Forests | 160 | ha protected | 2: Partially effective | Forests | 2483 | ha protected | 4: Effective | Forests | 668 | ha protected | 3: Moderately effective
|  | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | forests | 430 | ha protected | 2: Partially effective | Forests | 1500 | ha protected | 4: Effective | Forests | 710 | ha protected | 3: Moderately effective
|  | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Baseline information |  |  |  | Targeted performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 6: Diversified and strengthened livelihoods and sources of income for vulnerable people in targeted areas | Indicator 6.1: Increase in households and communities having more secure access to livelihood assets | No. of targeted households | % of female headed households | Improvement level |  | No. of targeted households | % of female headed households | Improvement level |  | No. of targeted households | % of female headed households | Improvement level |  | No. of targeted households | % of female headed households | Improvement level
| Indicator 6.2: Increase in targeted population's sustained climate-resilient alternative livelihoods | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
|  | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
|  | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
|  | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
Output 6 Targeted individual and community livelihood strategies strengthened in relation to climate change impacts, including variability | Indicator 6.1.1: No. and type of adaptation assets created or strengthened in support of individual or community livelihood strategies | Number of Assets | Type of Assets | Sector | Adaptation strategy | Number of Assets | Type of Assets | Sector | Adaptation strategy | Number of Assets | Type of Assets | Sector | Adaptation strategy | Number of Assets | Type of Assets | Sector | Adaptation strategy
| Core Indicator 6.1.2: Increased income, or avoided decrease in income | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 7: Improved policies and regulations that promote and enforce resilience measures | Indicator 7: Climate change priorities are integrated into national development strategy | Integration level |  |  |  | Integration level |  |  |  | Integration level |  |  |  | Integration level
Output 7:Improved integration of climate-resilience strategies into country development plans | Indicator 7.1: No. of policies introduced or adjusted to address climate change risks | No. of Policies introduced or adjusted | Sector | Scale | Type | No. of Policies introduced or adjusted | Sector | Scale | Type | No. of Policies introduced or adjusted | Sector | Scale | Type | No. of Policies introduced or adjusted | Sector | Scale | Type
| Indicator 7.2: No. of targeted development strategies with incorporated climate change priorities enforced | No. of Development strategies | Regulation |  | Effectiveness | No. of Development strategies | Regulation |  | Effectiveness | No. of Development strategies | Regulation |  | Effectiveness | No. of Development strategies | Regulation |  | Effectiveness
Glacier lake outburst flood
|  | Inland flooding | fr | biological assets |  | Company policy | 5: Fully enforced (All elements implemented)
|  | Salinization | Decrease | land |  | Communication & Information policy | 4: Enforced (Most elements implemented)
|  | Drought | Same | water areas |  | Defense policy | 3: Partially enforced (Some elements implemented)
|  | Wind |  | subsoil assets | increased adpative capacity | Domestic policy | 2: Partially not enforced (Most elements not implemented) |  | Agribusiness
|  | Coastal flooding |  | air | achieved | Economic policy | 1: Not enforced (No elements implemented) |  | Agricultural-related | Financial capital
|  | Storm surge | Please choose |  | enhanced level of protection | Education policy |  |  | Agriculture | Human capital
|  | Hurricane | Selected | [5 empty] | Aquaculture | Physical capital
|  |  | Not relevant |  |  | 5: All (Fully integrated) |  |  | Construction/repairing business | Social capital
[6 empty] | 4: Most |  |  | Cultivation | Natural capital
[6 empty] | 3: Some |  |  | Fishing | Personal capital
Select | 5: All | Select |  |  | Community | 2: Most not integrated |  | Other | Forestry | Adaptation strategies
1 | 4: Almost all | Private | Type | Yes | Multi-community | 1: None |  | Agriculture | Handicrafts
2 | 3: Half | Public | Scale | No | Departmental |  |  | Coastal management | Livestock production
3 | 2: Some | NGO | Sector |  | National |  |  | Disaster risk reduction | Manufacturing
4 | 1: None |  |  |  |  | 5: Very high improvement | Established | Food security | other
|  | National |  |  |  | 4: High improvement | Maintained | Health | Services
|  | Regional |  |  |  | 3: Moderate improvement | Improved | Urban development | Tourism-related
|  | Local |  |  |  | 2: Limited improvement |  | Water management | Trading
[6 empty] | 1: No improvement |  | Multi-sector
|  | 1 -generated information is irrelevant, and neither the stakeholders reached nor the timeframe managed were achieved | 1: No info transferred on time | 4: High capacity | 5: Fully aware | 5: Highly responsive (All defined elements ) | 5: Fully improved | Roads | 5: Very effective
Asia-Pacific | NIE | 2 -the existence of some challenge in any of the three aspects of the indicator (generation of dissemination, stakeholders reached or timeframe managed) | 2: Somewhat info transferred | 3: Medium capacity | 4: Mostly aware | 4: Mostly responsive (Most defined elements) | 4: Mostly Improved | Gov Buildings | 4: Effective
Latin America and Caribbean | RIE | 3 -relevant information is generated and disseminated to all identified stakeholders on timely basis | 3: Info transferred on time | 2: Low capacity | 3: Partially aware | 3: Moderately responsive (Some defined elements) | 3: Moderately improved | Causeways | 3: Moderately effective
Africa | MIE |  |  | 1: No capacity | 2: Partially not aware | 2: Partially responsive (Lacks most elements) | 2: Somewhat improved | Airports | 2: Partially effective
Eastern Europe |  |  |  |  | 1: Aware of neither | 1: Non responsive (Lacks all elements ) | 1: Not improved | Schools | 1: Ineffective
| ha protected | [6 empty] | Training Centres
| ha rehabilitated | [5 empty] | Monitoring/Forecasting capacity | Hospitals
Afghanistan, Islamic Rep. of | km protected | [5 empty] | Policy/regulatory reform | Drinking water systems
Angola | km rehabilitated | 1: Risk knowledge | 1: No plans conducted or updated |  |  |  | Capacity development | Other
Albania |  | 2: Monitoring and warning service | 2: Undertaking or updating of assessments in progress |  |  | Communication & Information policy | Sustainable forest management
Argentina |  | 3: Dissemination and communication | 3: Risk and vulnterability assessments completed or updated |  |  | Domestic policy | Strengthening infrastructure | 1: Health and Social Infrastructure (developed/improved)
Armenia | Forests | 4: Response capability |  |  |  | Economic policy | Supporting livelihoods | 2: Physical asset (produced/improved/strenghtened)
Antigua and Barbuda | Mangroves |  |  |  |  | Education policy | Mangrove reforestation
Azerbaijan | Coasts |  | From 0 to 0.5% |  |  | Energy policy | Coastal drainage and infrastructure
Burundi | Rangelands |  | From 0.5 to 1% |  |  | Environmental policy | Irrigation system
Benin | Cultivated land/Agricultural land |  | From 1% to 5% |  |  | Foreign policy | Community-based adaptation
Burkina Faso | Catchment area/Watershed/Aquifer |  | From 5% to 10% |  |  | Health policy | Erosion control
Bangladesh | Protected areas/National parks |  | From 10% to 20% |  |  | Housing policy | Soil water conservation
Bulgaria | Other |  | From 20% to 30% |  |  | Human resource policies | Microfinance
Bahrain |  |  | From 30% to 40% |  |  | Information policy | Special Program for women
Bahamas, The |  |  | From 40% to 50% |  |  | Macroeconomic policy | Livelihoods
Bosnia and Herzegovina |  |  | Above 50% |  |  | Monetary policy | Water storage
Belarus | [5 empty] | Population policy | ICT and information dissemination
Belize | [5 empty] | Private policy
Bolivia | [5 empty] | Public policy
Brazil | [5 empty] | Science policy
Barbados | [5 empty] | Social policy
Bhutan |  | 3- relevant information is generated and disseminated to all identified stakeholders on timely basis |  |  |  | Transportation policy
Botswana |  | describe |  |  |  | Urban policy
Central African Republic |  | 2- the existence of some challenge in any of the three aspects of the indicator |  |  |  | Water policy
Chile |  | describe |  |  |  | Other policy
China, People's Republic of |  | 1- generated information is irrelevant and neither the stakeholders reached nor the timeframe managed were achieved
Cote d'Ivoire |  | describe
Cameroon
Congo, Dem. Rep. of
Congo, Republic of
Cook Islands
Colombia
Comoros
Cape Verde
Costa Rica
Cuba
Czech Republic
Djibouti
Dominica
Dominican Republic
Algeria
Ecuador
Egypt
Eritrea
Estonia
Ethiopia
Fiji
Micronesia, Fed. States of
Gabon
Georgia
Ghana
Guinea
Gambia, The
Guinea-Bissau
Equatorial Guinea
Grenada
Guatemala
Guyana
Honduras
Croatia
Haiti
Hungary
Indonesia
India
Iran, Islamic Republic of
Jamaica
Jordan
Kazakhstan
Kenya
Kyrgyz Republic
Cambodia
Kiribati
Saint Kitts and Nevis
Korea, Republic of
Lao People's Democratic Republic
Lebanon
Liberia
Libya
Saint Lucia
Sri Lanka
Lesotho
Lithuania
Latvia
Morocco
Moldova
Madagascar
Maldives
Mexico
Marshall Islands
Macedonia, former Yugoslav Republic of
Mali
Malta
Myanmar
Montenegro
Mongolia
Mozambique
Mauritania
Mauritius
Malawi
Malaysia
Namibia
Niger
Nigeria
Nicaragua
Niue
Nepal
Nauru
Oman
Pakistan
Panama
Peru
Philippines
Palau
Papua New Guinea
Poland
Korea, Dem. People's Rep. of
Paraguay
Romania
Russian Federation
Rwanda
Saudi Arabia
Sudan
Senegal
Solomon Islands
Sierra Leone
El Salvador
San Marino
Serbia
Sao Tome and Principe
Suriname
Slovak Republic
Slovenia
Swaziland
Seychelles
Syrian Arab Republic
Chad
Togo
Thailand
Tajikistan
Turkmenistan
Tonga
Trinidad and Tobago
Tunisia
Turkey
Tuvalu
Tanzania
Uganda
Ukraine
Uruguay
Uzbekistan
Saint Vincent and the Grenadines
Venezuela
Vietnam
Vanuatu
Samoa
Yemen, Republic of
South Africa
Zambia
Zimbabwe
Timor-Leste
Note on N21: Microsoft Office User: The outcome indicators in the Result Framework are primarily designed for post-project impact assessment and the indicators do not assist progress monitoring. This data can be presented at the terminal phase, after the end line impact survey is conducted.
Note on M27: The outcome indicators in the Result Framework are primarily designed for post-project impact assessment and the indicators do not assist progress monitoring. This data can be presented only during the terminal stage of the project, after the end line impact survey is conducted
Note on N27: In addition to drought hazard maps, flood and earthquake hazard maps were also produced.
Note on H78: Microsoft Office User: 45 small canals 70 small scale water pumps 56 communal water tanks 150 communal ponds rehabilitated or constructed 10 deep tube wells 1156 ha land covered with soil and water conservation techniques 40 shallow tube wells
Note on E89: 1500ha of natural forest conservation and community based reforesation practices in critical watershed areas
Note on I89: Summation of: 3913 of NFC 1458 of CF, and 770 of tree planting on public land
Note on E92: 160ha agrofestry establishement
Note on I92: 1000 homestead gardening 20ha demo plots 2ha silvopasture development 3 tree-intercropping 1458ha Taungya crop
Note on E95: 430ha of farm boundary plantations
Note on I95: Farm boundary plantation

## Units for Indicators
Fund Outcome Indicator Units
1. Generation of relevant data, Stakeholders, and Timeliness 2.1. Include both qualitative and quantitative measures of capacity level within targeted institutions 2.2. Number (men and women and other vulnerable groups) 3.1. Use scale from 1 to 5: 5: Fully aware 4: Mostly aware 3: Partially aware 2: Partially not aware 1: Aware of neither predicted adverse impacts of climate change nor of appropriate responses 3.2. Use scale from 1 to 5: 5: All 4: Almost all 3: Half 2: Some 1: None 4.1. Summarize in an overall scale (1-5): 5: Highly responsive (All defined elements ) 4: Mostly responsive (Most defined elements) 3: Moderately responsive (Some defined elements) 2: Partially responsive (Lacks most elements) 1: Non responsive (Lacks all elements ) 4.2. Summarize in an overall scale (1-5): 5: Fully improved 4: Mostly Improved 3: Moderately improved 2: Somewhat improved 1: Not improved 5. Depends on the targeted natural asset: Biological (species): measure through changes in population numbers (dynamics, structure, etc.) Land: measure changes in hectares. Baseline data will be necessary to estimate the change. Supporting indicators baseline and target (as well as contextual information) are needed such as the following: Farmers adopting recommended technologies, Ha. of land improved, Average deforestation rate Etc. Use scale from 1 to 5. 5: Very effective (All elements are present) 4: Effective (Most elements are present) 3: Moderately effective (Some elements are present) 2: Partially effective (Most elements are not present) 1: Ineffective (No elements are present) 6.1. Summarize in an overall scale (1-5): 5: Very high improvement 4: High improvement 3: Moderate improvement 2: Limited improvement 1: No improvement 6.2. Household income by source of livelihood in project area (USD) prior and post project intervention 7. Summarize in an overall scale (1-5). 5: All (Fully integrated) 4: Most 3: Some 2: Most not integrated 1: None
Fund Output Indicator Units
1.1. Number, sector(s) and level(s) of projects or interventions in separate fields of monitoring plan 1.2. Number 2.1.1. Number of staff (male/female) of targeted institutions: a. Obtain baseline information: total number of staff from targeted institutions b. Define target 2.1.2. Number of staff (male/female) of targeted institutions: a. Obtain baseline information: total number of staff from targeted institutions b. Define target: needs to be defined by project proponents 2.2.1. Quantitative: Percentage (includes women – and other vulnerable groups – and men). Qualitative: Adequacy: include direct analysis of major areas; adequacy/effectiveness of systems or analysis of perceptions of populations and institutions. 2.2.2. Number (broken down by gender and, if possible, by vulnerable groups defined in the area of intervention) of people 3.1. Number and type (in separate columns) at local level. 3.2. Number 4.1. Number and type 4. 2. Number and type (entered in separate columns) 5. Number of interventions by type of natural asset and intervention 6.1. Number and type (in separate columns of monitoring plan) 6.2. Income sources per household; description of income source and number of households. 7.1. Number/Sector 7.2. Number; Effectiveness (see previous indicator) through enforcement level.