## Overview
Project Performance Report (PPR)
| Period of Report (Dates) | 01 Apr 2016 - 31 Mar 2017
| Project Title: | ADDRESSING CLIMATE CHANGE RISKS ON WATER RESOURCES AND FOOD SECURITY IN THE DRY ZONE OF MYANMAR
| Project Summary: | Myanmar’s Dry Zone is one of the few areas in this region where food security for survival is still a real issue and the linkage of “bad weather” and poverty is immediate and dire. In 2009, a drought triggered 50-70% drop in rice and 80-90% drop in sesame and sunflower harvest – some of the key crops grown in the region. To strike a balance of investments on urgent adaptation needs and greater coverage of beneficiaries, this project combines targeted interventions for resilient livelihood actions and rehabilitation of community ecosystem assets such as forests and watersheds.
|  |  | Countries | Project Type: |  | GEF Focal Area: | GEF 4 Focal Areas | GEF 2 / 3 Operational Programme: | Overall Rating of the project in the evaluation by the project evaluator: | GEF-4 Focal Area Strategic Program: | GEF-3 Focal Area Strategic Program:
| Database Number: | PIMS 4703 | Afghanistan | FP | Yes | Biodiversity | 1 | 1 | U | BD-SP1-PA Financing | 1: Arid & semi-arid ecosystems
Implementing Entity (IE) [name]: |  | United Nations Development Programme | Albania | MSP | No | Climate Change Adaptation | 2 | 2 | S | BD-SP2-Marine PA | 2: Coastal, marine & freshwater ecosystems
| Type of IE: | MIE | Algeria | EA |  | Climate Change Mitigation | 3 | 3 | MU | BD-SP3-PA Networks | 3: Forest ecosystems
| Country(ies): | Myanmar | Angola |  |  | International Waters | 5 | 5 | Good | BD-SP5-Markets | 13: Conservation and Sustainable Use of Biological Diversity Important to Agriculture
Relevant Geographic Points (i.e. cities, villages, bodies of water): |  | Five townships (Shwebo, Moneywa, Myingyan, Nyaung Oo and Chauk) in Myanmar's Dry Zone | Argentina |  |  | Multiple Focal Area |  |  |  | BD-SP7-Invasive Alien Species(IAS) | 6: Promoting the adoption of renewable energy by removing barriers and reducing implementation costs
[8 empty] | CC-SP2- Industrial EE | 8: Waterbody based operational program
| Project Milestones | [6 empty] | CC-SP3-RE,CC-SP4-Biomass | 9: Integrated Land and Water multiple focal area
| Milestone |  | Bahamas | [6 empty] | CC-SP5-Transport | 10: Contaminants based operational program
AFB Approval Date: |  | 2014-03-11
IE-AFB Agreement Signature Date: |  | 2014-03-26 | [6 empty] | CC-SP6-LULUCF | 12: Integrated Ecosystem Management
Start of Project/Programme: |  | 2014-08-06 | [6 empty] | Cross cutting capacity building | 14: Persistent Organic Pollutants
Mid-term Review Date (if planned): |  | 2017-10-09
| Terminal Evaluation Date: | 2019-02-17
|  | List documents/ reports/ brochures / articles that have been prepared about the project. | Cyprus
|  | In addition to the list submitted in the 1st PPR, the following is a list of documents prepared during the reporting period: 1. Completion Report: Renovation of Kin Tat Irrigation Canal in Shwebo 2. Rapid Needs Assessment: Assessment, Identification & Monitoring of Small-Scale Water Infrastructure Needs for Drinking and Irrigation Water in the Dry Zone of Myanmar. 3. Field Survey Report: Soil and Water Conservation Activities under the AF Project. 4. Training Manual for Soil and Water Conservation Activities 5. Interim Report on Soil and Water Conservation Activities in the dry zone, March 2017 6. Participatory Rural Appraisal and Training Need Assessment Report for Promotion of Climate Resilient Agriculture practices in the Dry Zone of Myanmar 7. User Guide for Thresher User Groups 8. Participatory post-harvest assessment report 9. Final report of the delivery of Threshers to Thresher User Groups 10. Training Report: Operation and Maintenance of Threshers 11. Training manual on “Farmer-managed Seed Multiplication Training” 12. Livestock rapid need assessment report 13. Completion Report: Training of Trainers for climate change resilient livestock rearing practices in dry zone. 14. Completion Report: Community trainings on climate resilient diversified livestock rearing practices. 15. Training Report: Training of Trainers on Community Based Disaster Risk Management 16. Community Based Disaster Risk Management manual and tools 17. Climate Analysis: variabilities, extremes, trends, projections and associated risks, Central Dry ZOne of Myanmar. 18. Summary Report: Presentation of CLimate Profiles for Monywa and Nyaung U townships in the Central dry zone of Myanmar. 19. Assessment of climate risk information flow in the dry zone of Myanmar - capacities, gaps and user requirements. 20. Vulnerability and rick assessment guide book. 21. Special agro-climatic bulletins for the 5 project townships 22. Standard operating procedure for information/risk dissemination 23. Baseline Report: Impact Assesment - Addressing Climate Change Risks on Water Resources and Food Security in the Dry Zone of Myanmar. 24. Baseline video documentary of the project 25. News Article - Responding to disasters before they happen: Trainings build resilience in Myanmar’s Dry Zone 26. Photo Essay - Supporting Shwebo farmers improve Water Access and Food Security in Myanmar 27. UNDP Myanmar Facebook post on Distribution of Threshers to project beneficiaries 28. News Article - Disaster Alert Notification Application to Improve Myanmar’s Preparedness 29. DAN (Disaster Alert Notification) - Mobile Application 30. DMH-SESAME (Specialized Expert System for Agro-Meteorological Early warning | Czech Republic
List the Website address (URL) of project. |  |  | Democratic People's Republic of Korea
|  | http://www.undp-alm.org/projects/af-myanmar | Democratic Republic of the Congo
Denmark
| Project contacts: |  | Djibouti
National Project Manager/Coordinator |  |  | Dominica
| Name: | Mr. Myint Wai | Dominican Republic
| Email: | myint.wai@undp.org | Ecuador
| Date: |  | Egypt
| Government DA |  | El Salvador
| Name: |  | Equatoral Guinea
| Email: |  | Eritrea
| Date: |  | Estonia
| Implementing Entity |  | Ethiopia
| Name: | Ms. Lat Lat Aye; Mr. Yusuke Taishi; Mr. Karma Lodey Rapten | Fiji
| Email: | lat.lat.aye@undp.org; yusuke.taishi@undp.org; karma.rapten@undp.org | Finland
| Date: |  | France
| Executing Agency |  | Gambia
| Name: |  | Georgia
| Email: |  | Germany
| Date: |  | Ghana
| Executing Agency |  | Greece
| Name: |  | Grenada
| Email: |  | Guatemala
| Date: |  | Guinea
| Executing Agency |  | Guinea Bissau
| Name: |  | Guyana
| Email: |  | Haiti
| Date: |  | Honduras
Hungary
Iceland
India
Indonesia
Iran (Islamic Republic of)
Iraq
Ireland
Israel
Italy
Jamaica
Japan
Jordan
Kazakhstan
Kenya
Kiribati
Kuwait
Kyrgyzstan
Lao People’s Democratic Republic
Latvia
Lebanon
Lesotho
Liberia
Libyan Arab Jamahiriya
Liechtenstein
Lithuania
Luxembourg
Madagascar
Malawi
Malaysia
Maldives
Mali
Malta
Marshall Islands
Mauritania
Mauritius
Mexico
Micronesia, Federated States of
Monaco
Mongolia
Montenegro
Morocco
Mozambique
Myanmar
Namibia
Nauru
Nepal
Netherlands
New Zealand
Nicaragua
Niger
Nigeria
Norway
Oman
Pakistan
Palau
Panama
Papua New Guinea
Paraguay
Peru
Philippines
Poland
Portugal
Qatar
Republic of Korea
Republic of Moldova
Romania
Russian Federation
Rwanda
Saint Kitts and Nevis
Saint Lucia
Saint Vincent and the Grenadines
Samoa
San Marino
Sao Tome and Principe
Saudi Arabia
Senegal
Serbia
Seychelles
Sierra Leone
Singapore
Slovakia
Slovenia
Solomon Islands
Somalia
South Africa
Spain
Sri Lanka
Sudan
Suriname
Swaziland
Sweden
Switzerland
Syrian Arab Republic
Tajikistan
Thailand
The former Yugoslav Republic of Macedonia
Timor-Leste
Togo
Tonga
Trinidad and Tobago
Tunisia
Turkey
Turkmenistan
Tuvalu
Uganda
Ukraine
United Arab Emirates
United Kingdom of Great Britain and Northern Ireland
United Republic of Tanzania
United States of America
Uruguay
Uzbekistan
Vanuatu
Venezuela, Bolivarian Republic of
Viet Nam
Yemen
Zambia
Zimbabwe

## FinancialData
Financial information: cumulative from project start to 31 March 2017
DISBURSEMENT OF AF GRANT FUNDS
How much of the total AF grant as noted in Project Document plus any project preparation grant has been spent to date?
Estimated cumulative total disbursement as of [31 March 2017] | 2748127
Add any comments on AF Grant Funds. (word limit=200) | As of Q1/2017, the project had disbursed US$ 2,748,127 out of the fist & second tranche allocation of US$ 4,386,378 (representing 62.65% delivery rate). The planned expenditure schedule given below also reflects the planned activities from April to December from the 2017 annual work plan.
INVESTMENT INCOME | N/A
Amount of annual investment income generated from the Adaptation Fund’s grant
EXPENDITURE DATA
List ouput and corresponding amount spent for the current reporting period | ITEM / ACTIVITY / ACTION | AMOUNT
| Output1.1: Water Capture and Storage Capacity in 280 Villages enhanced to ensure imporved access to fresh water supply during dry periods | 562987.83
| Output1.2: 6141 hectares of micro-watersheds are protected and rehabilitated through Farmer-Managed Natural Regeneration (FMNR) to increase natural water retention and reduce erosion | 370734.55
| Output1.3: Community-based agro-foresty plots are established on 3,983 hectares of private and communal lands to conserve soil and water | 190479.91
| Output2.1: Drought-resilient farming methods introuduced to farmers to enhance the resilience of subsistence agriculture in the Dry Zone | 456921.69
| Output2.2: Resilient post-harvest processing and storage systems intoruduced to reduce climate-induced post-harvest losses(droughts, rain and floods) | 239493.87
| Output2.3: Diversified livestock production systems are introudced in 6,300 households to buffer the effects of drought on rural livelihoods | 337394.78
| Output3.1: Climate hazard maps and risk scenarios are developed in each Township to support community-based climate risk management and preparedness planning | 51622.98
| Output3.2: Local level climate and disaster risk management framework strengthened for timely and effective communication of climate risk and early warning information | 61452.24
| Project Execution Cost | 29621.89
| TOTAL | 2300709.74
PLANNED EXPENDITURE SCHEDULE
List outputs planned and corresponding projected cost for the upcoming reporting period | ITEM / ACTIVITY / ACTION | PROJECTED COST | Est. Completion Date
| Output1.1: Water Capture and Storage Capacity in 280 Villages enhanced to ensure imporved access to fresh water supply during dry periods | 627476.21 | 2017-12-31
| Output1.2: 6141 hectares of micro-watersheds are protected and rehabilitated through Farmer-Managed Natural Regeneration (FMNR) to increase natural water retention and reduce erosion | 349511.79 | 2017-12-31
| Output1.3: Community-based agro-foresty plots are established on 3,983 hectares of private and communal lands to conserve soil and water | 222062.66 | 2017-12-31
| Output2.1: Drought-resilient farming methods introuduced to farmers to enhance the resilience of subsistence agriculture in the Dry Zone | 221068.85 | 2017-12-31
| Output2.2:Resilient post-harvest processing and storage systems intoruduced to reduce climate-induced post-harvest losses(droughts, rain and floods) | 51849.69 | 2017-12-31
| Output2.3: Diversified livestock production systems are introudced in 6,300 households to buffer the effects of drought on rural livelihoods | 430554.95 | 2017-12-31
| Output3.1: Climate hazard maps and risk scenarios are developed in each Township to support community-based climate risk management and preparedness planning | 132783.62 | 2017-12-31
| Output3.2: Local level climate and disaster risk management framework strengthened for timely and effective communication of climate risk and early warning information | 171149.67 | 2017-12-31
| Project Execution Cost | 10773.94 | 2017-12-31
| TOTAL | 2217231.38
ACTUAL CO-FINANCING (If the MTR or TE have not been undertaken this reporting period, DO NOT report on actual co-financing.)
How much of the total co-financing as committed in the Project Document has actually been realized? | 324736.76
Estimated cumulative actual co-financing as verified during Mid-term Review (MTR) or Terminal Evaluation (TE).
Add any comments on actual co-financing in particular any issues related to the realization of in-kind, grant, credits, loans, equity, non-grant instruments and other types of co-financing. (word limit=200)

## Risk Assesment
RISK ASSESMENT
IDENTIFIED RISKS
List all Risks identified in project preparation phase and what steps are being taken to mitigate them
Identified Risk | Current Status | Steps Taken to Mitigate Risk
Non-climate drivers undermine adaptation efforts under this project. | [Medium] The risk still remains valid. | The original risk mitigation approach remains relevant. That is, the project will promote an integrated view of vulnerability in which the mitigation of climate-related drivers of vulnerability can be coupled with economic benefits. This integrated, ecosystem-based view of resilience, which is based on community-based participatory planning, will be able to hold non-climatic drivers such as over-grazing, deforestation and unsustainable agricultural practices in check. From this perspective, adaptation actions that are implemented or planned to be implemented in the project are designed to address local community needs for economic and social empowerment.
Extreme weather events during the project lifetime undermine confidence of local communities in adaptation measures promoted by the project. | [Medium] The risk still remains valid. | So far there is noBy design, the project integrates outputs which focus on disaster risk and early warning communication, which enable basic preparedness planning. Under Outcome 3 of the project has supported Relief and Resettlement Department to develop a mobile application - Disaster Alert Notification, which is a new method of disseminating early warning information, in addition to the existing word-of-mouth communications. In addition, the project also supported the Department of Hydrology and Metereology in developing a mobile application - DMH-SESAME - which provides 3-day, 10-day, monthly and seasonal forecasts for end users, including implementing partners, government agencies, and communities.
Adaptation measures increase inequity in communities. | [Medium] The risk still remains valid. | The selection of project target villages have been done in consultation with the beneficiaries and based on a set of selection criteria, including - observed temperature extremes, frequency of drought per year, impacts of climatic parameters on food security and potential to access ground and surface water resources. The project has also collected baseline information on beneficiaries and developed a database to monitor and ensure that the project supports the most vulnerable and marginalized communities.
Technical capacity of township and village stakeholders restricts broad community engagement. | [Medium] The risk still remains valid. | During the inception phase of the project, the project team conducted stakeholder consultations in each of the project townships on project objectives, outcomes, priorities and local needs to enhance better understanding of the project. Township authorities and local communities have expressed willingness to work together to achieve the objectives of the project.
Political and social instability and lack of government engagement | [Medium] The risk still remains valid. | While this risk continues to be valid, the likelihood of this risk materializing has gone down since this project was under design 3 years ago. The project steering committee includes representaives from the Government and key decisions in the project are jointly made by the Government of Myanmar and UNDP. So far, lack of Government engagement is not at all an issue.
Critical Risks Affecting Progress (Not identified at project design)
Identify Risks with a 50% or > likelihood of affecting progress of project
Identified Risk | Current Status | Steps Taken to Mitigate Risk
Lack of clarity in land acquisition for project interventions, in particular for forestry and watershed management activities | [High] This risk has emerged as the project started assessing and identifying areas for reforestation and rehabilitation activities. Any delay in securing approval will result in implementation delays | In consultation with the Dry Zone Greening Department and Forestry Department, the Project is seeking approval for land acquisition starting from - communities and local land management committees. Following this process, endorsements are being sought from General Administration Departments of respective townships. Finally, the Dry Zone Greening Department and Forestry Department will be informed on the complete process for their record. This process is taking longer than expected and is likely to hamper progress.
Risk Measures: Were there any risk mitigation measures employed during the current reporting period? If so, were risks reduced? If not, why were these risks not reduced?
Add any comments relevant to risk mitigation (word limit = 500)
As reported in the previous PPR, the monthly project coordination meetings with the counterpart agency (Dry Zone Greening Department) has helped solve issues and address implementation bottlenecks. In addition, the project has also instituted a quarterly coordination meeting with implementing partners to ensure alignment of activities under the different components of the project, as well as to avoid duplication of efforts and promote cross-practice learning and exchange of best practices across the different work packages that are currently under implementation. The project has also instituted a system of sharing/presenting any kind of assessments and appraisals undertaken under the project to specific government departments/stakeholders - so as to incorporate their comments/suggestions and to share findings and recommendation of these processes.

## Rating
RATING ON IMPLEMENTATION PROGRESS
For rating definitions please see bottom of page.
| Progress on Key Milestones |  | Expected Progress |  | Progress to Date | Rating
Project Manager/Coordinator: | Output 1.1: Identify specific locations in target villages for the following adaptation interventions: canals for water diversion; small-scale pumping systems; communal water tanks; tube wells; pound reservois; and soil storage dams |  | Rapid needs assessment for small-scale water infrastructure in the project townships conducted and documented |  | A rapid needs assessment for small-scale water infrastructure was completed with a priority ranking of sites/locations for project investment. The assessment was presented to relevant government departments (Dry Zone Greenign Department/Department of Agriculture, Department of Rural Development/Irrigation and Water Utilization Management Department) for endorsement, as well as to ensure alignment with government plans and initiatives | HS
| Output 1.1: Village level management scheme formulated which includes the roles and responsibilities of VWUG and distribution agreement across (vulnerable) households |  | Develop standard operating procedures (SOP) for water user groups. |  | This standard operating procedures for the water user group in Shwebo, where the project invested in the renovation of Kin Tat irrigation canal was developed. The SOPs for water user groups for other investments under the project will be developed towards the end of 2017, as the activity on installation of small-scale water infrastructure has been delayed due to lack of competetive bidders during procurement process. | MS
| Output 1.1: At least 50% of women's participation is encouraged to the workshops on water storage and capture interventions and participation monitored |  | At least 35% participation of women achieved in workshops on water storage and capture interventions |  | Despite efforts to enhance women's participation in trainings, the result is not very positive. During the reporting period soil and water conservation trainings were conducted for 304 participant, where 293 were males and only 11 were females. | U
| Output 1.1: Contribution of labour from women and/or landless improverished households is facilitated |  | Contribution of labour from women and/or landless impoverished households facilitated and encouraged |  | Implementing partner is specifically instructed to include women and landless households while engaing labour for project activities. Project activities on the ground have not yet started during reporting period. The project M&E Officer is monitoring this on a regular basis | MS
| Output 1.1: Production of a report on the success and challenges of micro-scale water infrastructure |  | No progress expected during the reporting period |  | No progress. This activity will be carried out towards the end of project implementation | N/A
| Output 1.2: Finalize village-wise intervention type and size based on the level of denudation, ongoing surface runoff and topography |  | Target villages selected based on a set of slection criteria and adaptation interventions identified for targetted villages |  | Township level and village level consultation conducted to verify and validate land use for reforestation/rehabilitation activities. The process of soliciting endorsement from community groups, local government and line departments is taking longer than expected. This is expected to be completed by first week of July 2017 | U
| Output 1.2: At least 50% of women's participation is encouraged to the workshops on watershed rehabilitation programmes and participation monitored |  | At least 35% participation of women achieved in workshops on watershed rehabilitation programmes and results documented |  | There has been very few trainings conducted so far on watershed rehabilitation. Once activities commence, gender disaggregated data will be gathered and reported | U
| Output 1.2: Roles and responsibilities of women are clearly identified in the community management plan |  | No progress expected during the reporting period |  | No progress. This will be ensured during the formulation of the management plans in Q2 and Q3 of 2017 | N/A
| Output 1.2: Production of a report on the success and challenges of community forest management plan |  | No progress expected during the reporting period |  | No progress. This activity will be carried out towards the end of project implementation in end 2018 or early 2019 | N/A
| Output 1.2: Initial 30-year lease permission sought and granted for successfully managed community forests |  | Identify and demarcate land available for community forestry practices and seek endorsement from stakeholders |  | The process of land identification and verification is ongoing. This has taken longer than expected due to the unclear process of seeking endorsement. The project is currently seeking endorsement of local land management committees, township authorities and line departments. The process is expected to be complete by first week of July 2017 | MU
| Output 1.3: Initial call for participation will target primarily women; at minimum 50% of the members should be women |  | At least 35% participation of women achieved |  | During the initial discussions at village and township levels on land identification and verification for watershed rehabilitation programmes, a large number of women have participated, accounting for about 36% of total participants | HS
| Output 1.3: Information collected on ongoing agro-forestry practices will be gender disaggregated |  | No progress expected during the reporting period |  | A draft template on the inventory of agro-forestry practices is in place and considers collection of gender-disaggregated data. This activity will be completed in 2018 | N/A
| Output 1.3: 1,700 hectares of homestead gardening in 110 villages established |  | Initiate distribution/plantation of fruit tree saplings in homesteads in select project villages |  | During the reporting period, 203 ha of homesteads have been planted in 62 villages, where 56,655 fruit tree saplings were distributed to beneficiaries | MS
| Output 1.3: 3,400 hectares of farm boundary planting in 100 villages established |  | Initiate plantation in farm boundaries in select project villages |  | Plantation of farm boundaries accomplished in 28 villages on 223 ha of land area with distribution/plantation of 82,682 seedlings | MS
| Output 1.3: Participants of the monitoring visits encourage women's participation |  | Monitoring visits to project sites include women participants so as to ensure gender considerations in project activities |  | During the reporting period, 3 joint (UNDP, Govt) monitoring visits were conducted in which 19% participants were women. | MS
| Output 1.3: Production of a report on the success and challenges of community forestry management plan |  | No progress expected during the reporting period |  | No progress. This activity will be carried out towards the end of project implementation | N/A
| Output 2.1: Organize a technical workshop to consolidate existing domestic and international knowledge on drought resistant crop varieties and seed banks inviting technical agencies such as Myanmar Agriculture Services, University of Agriculture, Department of Agriculture Research |  | No progress expected during the reporting period |  | The project has conducted a participatory rural appraisal and training need assessment for promotion of climate resilient agriculture practices. This activity is planned towards end 2017 | N/A
| Output 2.2: Quantative assessment of current post-harvest processes undertaken and reported |  | Post-harvest assessment conducted in project townships |  | The post-harvest assessment has been completed | S
| Output 2.2: Production of an assessment report on current post-harvest processes |  | Post harvest assessment report produced |  | The assessment report was produced and distributed to related government departments. | HS
| Output 2.2: Formulate a cost-sharing and maintenance plan in each village for the use of the thresher |  | Standard Operating Procedures for thresher User Group formulated. Operations and Maintenance manual developed. |  | Standard Operatingf Procedures for thresher user groups formulated and handed over to thresher user groups. Trainings on operation and maintenance of threshers imparted to all 127 thresher user groups | S
| Output 2.2: Women's participation in post-harvest trainings encouraged and gender-disaggregated participation record will be produced |  | No progress expected during the reporting period |  | No progress. Once the training is conducted, gender disaggregated data will be gathered and reported | N/A
| Output 2.2: Production of assessment reports on the effectiveness of harvest storage facilities and post-harvest handling techniques |  | No progress expected during the reporting period |  | No progress. This activity will be carried out towards the end of project implementation | N/A
| Output 2.3: Atleast 50% of the participants of the training on livestock production systems should be women. Gender disaggregated participants list will be produced |  | At least 35% of the participants of the training on livestock production systems are women |  | ToT trainings on climate resilient livestock production conducted for 27 Livestock Breeding and Veterinary Department staff (9 females = 33%). Community level trainings on climate resilient livestock production conducted in 141 village tracts where 5,558 participants attended (2599 woman = 47%) | S
| Output 2.3: Production of an assessment report on the effectiveness of diversified livestock production systems |  | No progress expected during the reporting period |  | No progress. This activity will be carried out towards the end of project implementation | N/A
| Output 3.1: Vulnerability assessment in townships will look at gender-differentiated vulnerability to climate risks |  | Vulnerability assessment conducted considering gender-differentiated vulnerability to climate risks |  | ToT training on Participatory vulnerability/risk assessment training was attended by 49 government staff (38 females = 78%). The training participants were engaged in participatory risk assessment in 144 village tracts and gender considerations were a part of the assessment process | S
| Output 3.2: Seasonal agriculture bulletins produced |  | Seasonal agro-met bulletin produced on a regular basis |  | 55 Agromet bulletins produced; DMH-SESAME mobile application produced which provides 3 days and 10 days forecasts (temp, rainfall, humidity, PET, spell and soil moisture) | S
| Output 3.2: CBDRM committee will have women representatives and they will be assigned specific roles and responsibilities |  | develop TOR and RFP for the recruitment of an Implementing partner |  | TOR and request for proposal developed for the engagement of an implementing partner to implement CBDRM activities in 70 villages under 5 project townships | S
[5 empty] | Overall Rating | S
Please Provide the Name and Contact information of person(s) reponsible for completeling the Rating section
| Name: | Myint Wai
| Email: | myint.wai@undp.org
Please justify your rating. Outline the positive and negative progress made by the project since it started. Provide specific recommendations for next steps. . (word limit=500)
During the reporting period, several procurement actions were undertaken, including pre-bid/ pre-proposal meetings and technical evaluation of proposals for the different work packages under the project. A total of 9 contractual agreements were signed with implementing partners who are now engaged in delivering project activities under the various components of the project. In addition, the project procured 127 crop threshers through an Invitation to Bid process, as well as signed a Letter of Agreement with Dry Zone Greening Department for the supply of seedlings for plantation activities. The project also recruited individual consultants to - (i) review and update CBDRM manual and tools and (ii) develop a mobile application for disaster alert. With the completion of major procurement actions by 3rd quarter of 2016, focus is now accorded to implementation oversight, monitoring and contractual management through proper planning of field monitoring visits, alignment of project activities within different project components as well as with government and development partners’ initiatives in the Dry Zone of Myanmar. The project has instituted a system of quarterly project coordination meetings with implementing partners to ensure alignment of the different work streams under the project, address implementation challenges and bottlenecks and to also provide space for knowledge-sharing and learning from each other. The Monitoring and Evaluation Framework for the project was approved by the PSC in August 2016 and a Monitoring and Evaluation Officer was recruited in August 2016. The Project Steering Committee meetings are held on a bi-annual basis (in June and Dec) and continues to provide overall guidance and oversight. The Technical Advisory Group meets every quarter to provide technical guidance and support to the project team. The arrangement to have TAG meetings on a rotational basis in project townships has provided a platform for TAG members/government partners to observe progress of project activities on the ground and provide technical inputs to implementing partners, as well as learn and capture lessons from field implementation. Overall, the progress of project activities are satisfactory, considering the short time available for actual implementation in 2016. The project is begining to show some good results. Since this project is a new initiative on the ground, there are apparent issues/challenges relating to implementation. The Project Team is trying its best to ensure proper coordination and engage all relevant stakeholders in its work. In particular, key government counterparts are consulted at every stage of implementation and their views and concerns are considered in planning and implementing project activities. Moving forward, the project team recognizes the importance of maintaining a healthy relationship with stakeholders and implementing partners. The Project Team is committed to doing this through dialogue and creating space for learning and knowledge-sharing.
| Progress on Key Milestones |  | Expected Progress |  | Progress to Date | Rating
Implementing Agency | Output 1.1: Identify specific locations in target villages for the following adaptation interventions: canals for water diversion; small-scale pumping systems; communal water tanks; tube wells; pound reserviors; and soil storage dams |  | Rapid needs assessment on small-scale water infrastructure needs in the project townships conducted and documented |  | A rapid needs assessment of small-scale water infrastructure needs was completed with a priority ranking of sites/locations for project investment. The assessment was presented to relevant government departments for endorsement, as well as to ensure alignment with government plans and initiatives | HS
| Output 1.1: Village level management scheme formulated which includes the roles and responsibilities of VWUG and distribution agreement across (vulnerable) households |  | Develop standard operations procedures for water user groups. |  | This standard operating procedures for the water user group in Shwebo, where the project invested in the renovation of Kin Tat irrigation canal was developed. The SOPs for water user groups for other investments under the project will be developed towards the end of 2017, as the activity on installation of small-scale water infrastructure has been delayed due to lack of competetive bidders during procurement process. | MS
| Output 1.1: At least 50% of women's participation is encouraged to the workshops on water storage and capture interventions and participation monitored |  | At least 35% participation of women achieved in workshops on water storage and capture interventions |  | Despite repeated efforts to enhance women's participation in trainings, the result is not very positive. During the reporting period soil and water conservation trainings were conducted for 304 participant, where 293 were males and only 11 were females. | U
| Output 1.1: Contribution of labour from women and/or landless improverished households is facilitated |  | Contributoin of labour from women and/or landless impoverished households facilitated and encouraged |  | Implementing partners are specifically instructed to include women and landless households while engaing labour for project activities. The project M&E Officer is monitoring this on a regular basis | MS
| Output 1.1: Production of a report on the success and challenges of micro-scale water infrastructure |  | No progress expected during the reporting period |  | No progress. This activity will be carried out towards the end of project implementation | N/A
| Output 1.2: Finalize village-wise intervention type and size based on the level of denudation, ongoing surface runoff and topography |  | Target villages selected based on a set of slection criteria and adaptation interventions identified for targetted villages |  | Township level and village level consultation conducted to verify and validate land use for reforestation/rehabilitation activities. The process of soliciting endorsement from community groups, local government and line departments is taking longer than expected | MS
| Output 1.2: Atleast 50% of women's participation is encouraged to the workshops on wtareshed rehabilitation programmes and participation monitored |  | At least 35% participation of women achieved in workshops on watershed rehabilitation programmes and results documented |  | There has been very few trainings conducted so far on watershed rehabilitation. Once activities commence, gender disaggregated data will be gathered and reported | U
| Output 1.2: Roles and responsibilities of women are clearly identified in the community management plan |  | No progress expected during the reporting period |  | No progress. This will be ensured during the formulation of the management plans | N/A
| Output 1.2: Production of a report on the success and challenges of community forest management plan |  | No progress expected during the reporting period |  | No progress. This activity will be carried out towards the end of project implementation | N/A
| Output 1.2: Initial 30-year lease permission sought and granted for successfully managed community forests |  | Identify and demarcate land available for community forestry practices and seek endorsement from stakeholders |  | The process of land identification and verification is ongoing. This has taken longer than expected due to the unclear process of seeking endorsement. The project is currently seeking endorsement of local land management committees, township authorities and line departments | MU
| Output 1.3: Initial call for participation will target primarily women; at minimum 50% of the members should be women |  | At least 35% participation of women achieved |  | During the initial discussions at village and township levels on land identification and verification for watershed rehabilitation programmes, a large number of women have participated, accounting for about 36% of total participants | HS
| Output 1.3: Information collected on ongoing agro-forestry practices will be gender disaggregated |  | No progress expected during the reporting period |  | A draft template on the inventory of agro-forestry practices is in place and conisders collection of gender-disaggregated data. This activity will be completed in 2018 | N/A
| Output 1.3: 1,700 hectares of homestead gardening in 76 villages established |  | Initiate distribution/plantation of fruit tree saplings in homesteads in select project villages |  | During the reporting period, 203 ha of homesteads have been planted in 62 villages, where 56,655 fruit tree saplings were distributed to beneficiaries | MS
| Output 1.3: 1500 hectares of farm boundary planting in 95 villages established |  | Initiate plantation in farm boundaries in select project villages |  | Plantation of farm boundaries accomplished in 28 villages on 223 ha of land area with distribution/plantation of 82,682 seedlings | MS
| Output 1.3: Participants of the monitoring visits encourage women's participation |  | Monitoring visits to project sites include women participants so as to ensure gender considerations in project activities |  | During the reporting period, 3 joint (UNDP, Govt) monitoring visits were conducted in which 19% participants were women. | MS
| Output 1.3: Production of a report on the success and challenges of community forestry management plan |  | No progress expected during the reporting period |  | No progress. This activity will be carried out towards the end of project implementation | N/A
| Output 2.1: Organize a technical workshop to consolidate existing domestic and international knowledge on drought resistant crop varieties and seed banks inviting technical agencies such as Department of Agriculture, University of Agriculture, Department of Agriculture Research |  | No progress expected during the reporting period |  | The project has conducted a participatory rural appraisal and training need assessment for promotion of climate resilient agriculture practices. This activity is planned towards end 2017 | N/A
| Output 2.2: Quantative assessment of current post-harvest processes undertaken and reported |  | Post-harvest assessment conducted in project townships |  | The post-harvest assessment has been completed | S
| Output 2.2: Production of an assessment report on current post-harvest processes |  | Post harvest assessment report produced |  | The assessment report was produced and distributed to related government departments. | HS
| Output 2.2: Formulate a cost-sharing and maintenance plan in each village for the use of the thresher |  | Standard Operating Procedures for thresher User Group formulated. Operations and Maintenance manual developed. |  | Standard Operatingf Procedures for thresher user groups formulated and handed over to thresher user groups. Trainings on operation and maintenance of threshers imparted to all 127 thresher user groups | S
| Output 2.2: Women's participation in post-harvest trainings encouraged and gender-disaggregated participation record will be produced |  | No progress expected during the reporting period |  | No progress. Once the training is conducted, gender disaggregated data will be gathered and reported | N/A
| Output 2.2: Production of assessment reports on the effectiveness of harvest storage facilities and post-harvest handling techniques |  | No progress expected during the reporting period |  | No progress. This activity will be carried out towards the end of project implementation | N/A
| Output 2.3: Atleast 50% of the participants of the training on livestock production systems should be women. Gender disaggregated participants list will be produced |  | Atleast 35% of the participants of the training on livestock production systems are women |  | ToT trainings on climate resilient livestock production conducted for 27 Livestock Breeding and Veterinary Department staff (9 females = 33%). Community level trainings on climate resilient livestock production conducted in 141 village tracts where 5,558 participants attended (2599 woman = 47%) | S
| Output 2.3: Production of an assessment report on the effectiveness of diversified livestock production systems |  | No progress expected during the reporting period |  | No progress. This activity will be carried out towards the end of project implementation | N/A
| Output 3.1: Vulnerability assessment in townships will look at gender-differentiated vulnerability to climate risks |  | Vulnerability assessment conducted considering gender-differentiated vulnerability to climate risks |  | ToT training on Participatory vulnerability/risk assessment training was attended by 49 government staff (38 females = 78%). The training participants were engaged in participatory risk assessment in 144 village tracts and gender considerations were a part of the assessment process | S
| Output 3.2: Seasonal agriculture bulletins produced |  | Seasonal agro-met bulletin produced on a regular basis |  | 55 Agromet bulletins produced; DMH-SESAME mobile application produced which provides 3 days and 10 days forecasts (temp, rainfall, humidity, PET, spell and soil moisture) | S
| Output 3.2: CBDRM committee will have women representatives and they will be assigned specific roles and responsibilities |  | develop TOR and RFP for the recruitment of an Implementing partner |  | TOR and request for proposal developed for the engagement of an implementing partner to implement CBDRM activities in 70 villages under 5 project townships | S
[5 empty] | Overall Rating | S
Please Provide the Name and Contact information of person(s) reponsible for completeling the Rating section
| Name: | Lat Lat Aye
| Email: | lat.lat.aye@undp.org
| Progress on Key Milestones |  | Expected Progress |  | Progress to Date | Rating
Other
Overall Rating
Please Provide the Name and Contact information of person(s) reponsible for completeling the Rating section
Name:
Email:
| Please justify your rating and address the following points: 1. Indicate trends, both positive and negative, in achievement of outcomes as per the project indicators. 2. Detail critical risks that have affected progress. 3. Outline response to MTR undertaken this reporting period. 4. Outline action plan to address projects with a rating of HU, U or MU. Please keep your input to 1200 words |  | During the reporting period, the progress of project implemenetaiton is satisfactory. In some areas/output, project made very good progress and deserve highly satisfactory rating, such as progress made in agriculture product post harvesting support. Significant improvement of the partnership and working relationship with the main government counterpart (DZGD) has been witnessed. The project has established a fairly robust implementation and monitoring arrangement, including monthly project coordination meeting with DZGD, quarterly project review and coordination meetings with the implementing partners, quarterly meetings of the Technical Advisory Group, and bi-annual Project Steering Committee meetings. With the technical inputs and guidance received from partners and government agencies through this forum, the project is able to ensure smooth implementation of activities on the ground. The project may also wish to explore how it can disseminate results/best practicies beyond the scope of the project - both internally and externally, including providing updates on project progress at the Union Government level. There is a need to undertake concreate measures to improve gender equality in all project activities to achieve targets of “women” participation and contribution under key outputs. Stronger alignment with climate risks and climate change adaptation measures are needed in all project activities and support. The project needs to ensure synergies across the different work streams under the project. In particular, the work under outcome 3 of the project needs to be integrated into the work of the other two outcomes of the project. Moving forward, the project team will have to ensure quality of outputs of the implementing partners and enhance joint monitoring activities in the field with government counterparts. It is also important for the project team to ensure that government counterparts and local communities are fully engaged during implementation, so as to ensure sustainability of project activities.
Rating Definitions
|  |  | Highly Satisfactory (HS) | Project actions/activities planned for current reporting period are progressing on track or exceeding expectations to acheive all major outcomes/outputs for given reporting period, without major shortcomings. The project can be presented as “good practice”.
|  |  | Satisfactory (S) | Project actions/activities planned for current reporting period are progressing on track to achieve most of its major outcomes/outputs with only minor shortcomings.
|  |  | Marginally Satisfactory (MS) | Project actions/activities planned for current reporting period are progressing on track to achieve most major relevant outcomes/outputs, but with either significant shortcomings or modest overall relevance.
|  |  | Marginally Unsatisfactory (MU) | Project actions/activities planned for current reporting period are not progressing on track to achieve major outcomes/outputs with major shortcomings or is expected to achieve only some of its major outcomes/outputs.
|  |  | Unsatisfactory (U) | Project actions/activities planned for current reporting period are not progressing on track to achieve most of its major outcomes/outputs.
|  |  | Highly Unsatisfactory (HU) | Project actions/activities planned for current reporting period are not on track and shows that it is failing to achieve, and is not expected to achieve, any of its outcomes/outputs.

## Project Indicators
PROJECT Indicators
Please provide all indicators being tracked for the project as outlined in the project document
Type of Indicator (indicators towards Objectives, Outcomes, etc…)
Type of Indicator | Indicator | Baseline | Progress since inception | Target for Project End
Objective | % of households in target site implementing climate change adaptation livelihood measures introduced by the project | Current agricultural and livestock rearing practices among subsistence farmers are based on historical climatic conditions and trends and are unsuited to increased drought conditions that are becoming increasingly frequent in the Dry Zone in Myanmar | approximately 21 % of impoversished farming households or landless have benefitted from climate resilient agriculture and livestock practices | By the end of the project, at least 61% of impoverished farming households or the landless, equivalent to approximately 24,498 households (11,550 agriculture, 6,648 agroforestry/homestead gardening and 6,300 livestock) benefit from and implement climate-resilient agriculture or livestock practices
| % of Dry Zone hoseholds using climate risk information to adjust their livelihood behavior | Currently climate risk information on sudden onset of disasters is delivered only to those houses with TV/radio and yet the level of interpretation and response is low. The outreach and understanding of information on slow onset of disasters are even lower. | data not available right now. This will be available after the impact survey in 2018/19 | At least 50% of all households in target location (based on random sampling), equivalent to 25,000 households, report that they have changed their livelihood behaviour based on climate risk information produced by the project
| % of Dry Zone households with access to early warning information on sudden onset of disasters | Currently climate risk information on sudden onset of disasters is delivered only to those houses with TV/radio and yet the level of interpretation and response is low. The outreach and understanding of information on slow onset of disasters are even lower. | data not available right now. This will be available after the impact survey in 2018/19 | At least 75% of all households in target location, equivalent to 38,000, receive early warning in a timely manner.
Outcome 1 | Outcome Indicator 1: % of Dry Zone farmers reporting increased freshwater availability during dry periods | 74% of households in project targeted townships area currently face shortages of fresh water supply for domestic and agricultural use | data not available right now. This will be available after the impact survey in 2018/19 | At least 60% of households facing water shortages in 280 villages in the five project targeted townships report increased freshwater availability during dry periods
| 1.1. Additional community-based freshwater supply and storage infrastructure put in place in drought-prone villages | 0 additional freshwater supply and/or storage infrastructure in drought-prone villages to account for climate change-induced increases in drought | 1 diversion canal renovated in Shwebo township benefitting 10,944 households with a population of 56,152 and covering a land area of 1,141 ha; 49 communal ponds rehabilitated in 49 villages benefitting 10,196 hh and a total population of 42,781; Soil and water conservation measures adopted in 5 project townships covering 504 ha of land; Training on soil & water conservation techniques conducted at 8 locations in 5 project townships (304 trainees - 280 trainees from community and 24 trainees from 3 government departments) | 45 canals for water diversion constructed, 70 small-scale water pumping systems installed, 56 communal water tanks (500 galoons) incl. pipes installed, 40 shallow tube wells constructed, 150 communal ponds rehabilitated or constructed, 10 deep tube wells (new and repaired/renovated), 1,156 ha of land covered with soil and water conservation techniques, Trainings on water infrastructure, soil & water conservation, operation and management, Water Usage Groups formed with by laws
| 1.2. Hectares of watershed area protected through community-based afforestation, reforestation and regeneration practices | 1,500 ha of natural forest conservation and community based reforestation practices in the critical watershed area in the project area | Afforestation/reforestation of natural forest and community forest areas will commence in 2017 co-inciding with the monsoon; 138.75 hectares of tree planting activities on public land has been accomplished during the reporting period | 3,913 ha of natural forest conservation, 1,458 ha of community forest establishment including (# of community forest management plan) 770 ha of tree planting activities on public land, Micro-watersheds (661ha) Road-side planting (35.5ha) Religous compounds (32.2ha) Schools (38.5ha) Clinics (2.8ha)
| 1.3. Hectares of land covered by systematic new agroforestry plantations | 160 ha of traditional agro-forestry home garden and 430 ha of farm boundary plantations currently exist in 280 villages in five targeted townships | 203.3 ha of homestead gardening/agroforestry plots established in 62 villages; 85.08 ha of farm boundary plantation in 44 villages completed | 1,000 ha of homestead gardening/agro-forestry plots established in 76 villages, 1,500 ha of farm boundary plantations in 95 villages
Outcome 2 | Outcome Indicator 2: Number of climate-resilient agricultural and livestock practices demonstrated and adopted to support adaptation of marginal farmers and landless households | Agricultural and livestock practices and extension services in the Dry Zone pay only limited attention to climate change risks. | 1 discrete agriculture adaptation practice demonstrated (minimizing post harvest loss through utilization of crop threshers) during the reporting period. Diversified livestock rearing practices under imeplemntation in the 5 project townships | By the end of the project, at least 6 discrete agricultural adaptation and diversified livestock rearing practices are demonstrated including resilient varieties, on-farm water management techniques, soil management practices, planting techniques, post-harvest processing, and diversified livestock breeds.
| 2.1.1. Number of Dry Zone farmers exposed to and involved in climate resilient farming techniques | In project target villages, farmers have (not been exposed) only limited exposure to climate-resilient farming techniques | Not yet started during the reporting time. Activities were planned during the reporting period for implementaiton in 2017 | By the end of the project, at least 11,550 (11,200 farmers plus 350 others) households, extension workers and CSO/NGO members in the target townships are trained on climate-resilient farming methods. Trainings on (#/hhs/m-f): - Climate resilient farming methods - Water smart practices (AWD) - Tanahka intercropping - Fruit tree drip irrigation - Organic farming and vermiculture
| 2.1.2. Accessibility to drought-resilient seed varieties | Only (five) limited seed (banks) sourcess are available in the target townships (one per each township) | Not yet started during the reporting period. Activities were planned during the reporting period for implementaiton in 2017 | At least 140 villages produce climate-resilient seed varities; trainings on climate-resilient seed multiplication.
| 2.1.3. Number of project and non-project community members participating in exchange visits and demonstration plots | Currently there is no initiatives in the Dry Zone promoting cross exchange between Townships of practical knowledge on climate resilient farming techniques | Not yet started during the reporting period.Activities were planned during the reporting period for implementaiton in 2017 | At least 20% of community participants in exchange visits and farmers field demonstrations are from non-project target villages, Farmer field schools on climate change, At least 50 participatory demonstration plots on climate-resilient agricultural practices are established
| 2.2. % of households who report reduced harvest losses due to improved post-harvest processing and storage | Only few households (farmers) apply improved post-harvest processing techniques | 127 thresher user groups in 5 project townships established (107 multi-crop threshers and 20 rice threshers). The threshers benefit 7,226 hh (107 multi-crop thresher user groups benefitting 6,196 hh and 20 rice thresher user groups benefiting 1,030 hh) | 80% of target households (9,240 of 11,550) report reduced post-harvest losses through the use of improved processing and storage technology; 20 rice threshers and 120 multi-crop threshers; Establishment of thresher groups (140); Trainings and participatory assessments of post harvest loss; Elevated storage systems (36)
| 2.3. Number of landless and marginal households with increased diversity of livestock assets | Majority of impoverished farmers (either landless or those with less than 2.5 hectares of land) in the Dry Zone have zero or small number of livestock: 65% have no livestock and 35% own some livestock | 1,354 landless households have received 5,209 livestock species in 133 villages (1,866 local chickens for 152 households, 450 layer chickens for 30 households, 1,576 piglets for 788 households and 1,317 sheep/goat for 384 households; TOT trainings on climate-resilient livestock practices conducted for 27 LBVD staff (18 male, 9 female); community level trainings conducted covering 5,558 people (2959 male and 2599 female) in 141 village tracks | By the end of the project, at least 6,300 marginal and landless households have increased the diversity of livestock assets. Diversity in types: Cattle Sheep Goat Pig Poultry Climate-resistant/improved breeds
Outcome 3 | Outcome Indicator 3-1: % of Dry Zone households using climate risk information to adjust their livelihood behavior | Currently climate risk information on sudden onset of disasters is delivered only to those houses with TV/radio and yet the level of interpretation and response is low. The outreach and understanding of information on slow onset of disasters are even lower. | Data not available right now. This will be available after the impact survey in 2018/19 | At least 50% of all households in target location (based on random sampling), equivalent to 25,000 households, report that they have changed their livelihood behaviour based on climate risk information produced by the project
| Outcome Indicator 3-2: % of Dry Zone households with access to early warning information on sudden onset of disasters | Currently climate risk information on sudden onset of disasters is delivered only to those houses with TV/radio and yet the level of interpretation and response is low. The outreach and understanding of information on slow onset of disasters are even lower. | Data not available right now. This will be available after the impact survey in 2018/19 | At least 75% of all households in target location, equivalent to 38,000, receive early warning in a timely manner.
| 3.1. Number of climate risk maps, vulnerability assessments and scenarios in active use by township authorities, NGOs and CBOs to improve planning decisions and prioritize investment actions | No climate risk maps, vulnerability assessments and scenarios in active use by township authorities, NGOs and CBOs to improve planning decisions and prioritize investment actions | Climate profiles and risk scenarios for 5 project townships completed; participatory risk assessment in 144 village tracts of 5 project townships conducted. The data is being analyzed and risk maps will bne produced shortly. | Climate hazard maps, vulnerability assessments and risk scenarios are available in each township
| 3.2.1. Number of local institutions that issue regular warning and forecasting communications to community-based organisations and vulnerable households | Currently, no such information is available except weekly/mothly forecats boradcasted over TV/radio | The TOR and RFP for this assignment is under preparation and activities are expected to commence in the 2nd half of 2017 | 70 community based disaster risk management (CBDRM) committees are formed to relay climate early warning information from the Township DPC, 5 Climate Risk Information sub-committees established within the Township Disaster Preparedness Committee
| 3.2.2. The number of climate related information materials produced to assist Dry Zone farmers to adjust their livelihood behavior | Not available | 55 Agromet bulletins produced; DMH-SESAME mobile application produced which provides 3 days and 10 days forecasts (temp, rainfall, humidity, PET, spell and soil moisture) | At least six agro-meteorological bulletins; two early warning and disaster response bulletins/posters; four guidance notes on resilient agricultural/livestock practices produced

## Lessons Learned
QUALITATIVE MEASURES and LESSONS LEARNED
Please complete the following section every reporting period
Implementation and Adaptive Management | Response
What implementation issues/lessons, either positive or negative, affected progress? | While the efficiency of procurement process has improved since the last reporting period, it continues to be a cause of delay in the project implementation. Given the nascent NGO/CSO community in Myanmar, there are not many qualified/competent NGOs/CSOs that can assist the implementation of the project. Therefore the Project chose to deliver project activities through a mix of partners selected through either the NGO/CSO engagement process or through competetive procurement process. This approach has been useful for the project and perhaps it can be applied to future projects implemented by UNDP and other development partners. The system of having regular dialogues with project counterparts/partners has proven to be immensely beneficial in addressing implementation issues. The monthly project coordination meetings with the counterpart agency (Dry Zone Greening Department) has helped the project in building trust and confidence, in addition to addressing implementation challenges and bottlenecks. The quarterly project coordination meetings with partners is yet another mechcniasm employed by the project - which has ensured better coordination and alignment of project activities. In addition this forum has also created space for cross-practice learning and sharing of information. The project has also engaged stakeholder agencies in specific project activities to solicit inputs and advice (eg. sectoral assessment, capacity needs assessment and presentation of outputs related to specific sectors). This has ensured ownership of project activities by stakeholders and alignment of project activities with ongoing government initiatives. The arrangement to convene Technical Advisory Group (TAG) meetings in the 5 project townships (on a rotational basis) is very useful as this provides opportunities for TAG members and local government stakeholders to witness progress of project activities first hand and provide technical inputs and advise to implementing partners. This arrangement also provide opportunities for learning and knowledge-sharing among the various project stakeholders. The efficacy of the TAG could be further enhanced by ensuring continuity/consistency in participation in quarterly meetings and monitoring visits and ensuring that information is shared within the respective stakeholder agencies. The seasonal nature of some project activities (eg. reforestation/watershed rehabilitation and livestock distribution) posed challenges in terms of planning and timing of activities. The project will need to make certain adjustments in 2017 and ensure that annual targets are met. The project continues to face issues related to staff turn-over and recruitment of project personnel. During the reporting period one of the project staff (Environment Conservation and Forestry Specialist) resigned and the post remained vacant for almost three months. Until the M&E officer was recruited in August 2016, the M&E functions were taken up by other staff, in addition to their regular responsibilities. With the endorsement of the M&E Framework and the M&E Officer on board now, the project is well-positioned to deliver results. Given the location of project office in Mandalay, we foresee that staff attrition will continue to be an issue. The project therefore recognizes the need to keep staff happy and meanigfully engaged in their work. The time taken to acquire land for reforestation/rehabilitation activities has also hampered progress. The project has had to go through a tedious process of seeking endorsement from all concerned. It would have helped, if areas for reforestation/rehabilitation were identified and agreed with all concerned before the start of the project.
Were there any delays in implementation? If so, include any causes of delays. What measures have been taken to reduce delays? | As noted in the last PPR, the project is estimated to be behind schedule by approximately 10-11 months. During the reporting period, some delays were encountered due to issues related to procurement and timing of field activities - which are highlighted in the previous section. In order to keep up with annual targets, the project will ensure annual targets are achieved through adjustment of annual targets in the following years. The project has also benefitted through support and expert advice provided by procurement advisors in the Bangkok Regional Hub. In 2017 and beyond, the project will continue to use the services of colleagues in Bangkok through their engagement in review of TORs and ex-ante review of request for proposals. This will minimize back and forth communication on clarification and significantly reduce delays in the procurement process. The identification, verification and endorsement of land areas for reforestation and watershed rehabilitation has taken a long time, thereby affecting progress. The project recognizes land issues are sensitive and therefore has considered a comprehensive approach in seeking approval for land. During the reporting period, the project has conducted village level and township level consultations with communities and local government officials to identify and verify land for plantation activities. Endorsement for land will be sought from land management committess, both at the village level as well as the township level. Final endorsement will then be sought from the General Administration Department at township level, as well as from the Department of Forestry and Dry Zone Greening Department.
Describe any changes undertaken to improve results on the ground or any changes made to project outputs (i.e. changes to project design) | There has been no change in the project outputs
How have gender considerations been taken into consideration during the reporting period? What have been the lessons learned as a consequence of inclusion of such considerations on project performance or impacts? | Gender considerations have been highlighted in all project activities such as prioritization exercises, water user group formation, selection of labourers for project activities, beneficiary selection for livestock distribution and training activities. While women's participation in trainings and user groups (eg. thresher user groups) have been encouraging, their participation in project activiites (labout inputs) have been low. The project has accorded priority to women-headed households in its livestock distribution programme. The results of this initiative will be visible in the not so distant future. The project has placed emphasis on the need for implementing partners to report gender disaggregated data in all its reporting (monthly and quarterly) mechanisms. This data is carefully recorded and the impacts of results will be monitored from time to time. The project will also report gender-related stories from the field and upload it on the country office website.
Please complete the following section at mid-term and project completion
Lessons for Adaptation | Response
Climate Resilience Measures
What have been the lessons learned, both positive and negative, in implementing climate adaptation measures that would be relevant to the design and implementation of future projects/programmes for enhanced resilience to climate change? | N/A
What is the potential for the climate resilience measures undertaken by the project/programme to be replicated and scaled up both within and outside the project area? | N/A
Concrete Adaptation Interventions
What have been the lessons learned, both positive and negative, in implementing concrete adaptation interventions that would be relevant to the design and implementation of future projects/programmes implementing concrete adaptation interventions? | N/A
What is the potential for the concrete adaptation interventions undertaken by the project/programme to be replicated and scaled up both within and outside the project area? | N/A
Community/National Impact
What would you consider to be the most successful aspects for the target communities? | N/A
What measures are/have been put in place to ensure sustainability of the project/program results? | N/A
What measures are being/could have been put in place to improve project/program results? | N/A
Knowledge Management
How has existing information/data/knowledge been used to inform project development and implementation? What kinds of information/data/knowledge were used? | N/A
If learning objectives have been established, have they been met? Please describe. | N/A
Describe any difficulties there have been in accessing or retrieving existing information (data or knowledge) that is relevant to the project. Please provide suggestions for improving access to the relevant data. | N/A
Has the identification of learning objectives contributed to the outcomes of the project? In what ways have they contributed? | N/A

## Results Tracker
Results Tracker for Adaptation Fund (AF) Projects
Goal: Assist developing-country Parties to the Kyoto Protocol that are particularly vulnerable to the adverse effects of climate change in meeting the costs of concrete adaptation projects and programmes in order to implement climate-resilient measures. Impact: Increased resiliency at the community, national, and regional levels to climate variability and change.
Important: Please read the following guidance document (also posted on the Adaptation Fund website) before entering your data
Link: http://www.adaptation-fund.org/sites/default/files/Results%20Framework%20and%20Baseline%20Guidance%20final.pdf
Adaptation Fund Strategic Results Framework
Project ID | PIMS 4703
Implementing Entity | United Nations Development Programme
Type of implementing entity | MIE
Country | Myanmar
Region | Five townships (Shwebo, Moneywa, Myin Chan, Nyaung Oo and Chauk) in Myanmar's Dry Zone
Sector | Multi-sector
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Impact: Increased resiliency at the community, national, and regional levels to climate variability and change | Core Indicator: No. of beneficiaries |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project
|  | Total | 0 | 0 | 0 | Total |  | 229155 | 2800 | Total |  |  |  | Total
|  | % of female beneficiaries |  | 0% |  | % of female beneficiaries |  | 53% |  | % of female beneficiaries |  |  |  | % of female beneficiaries
|  | % of Youth beneficiaries |  |  |  | % of Youth beneficiaries |  |  |  | % of Youth beneficiaries |  |  |  | % of Youth beneficiaries
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 1: Reduced exposure to climate-related hazards and threats | Indicator 1: Relevant threat and hazard information generated and disseminated to stakeholders on a timely basis | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness
|  | Total | 229155 | Drought | 1: Ineffective | Total | 229155 | Drought | 4: Effective | Total |  |  |  | Total
|  | % of female targeted | 53% |  |  | % of female targeted | 53% |  |  | % of female targeted |  |  |  | % of female targeted
Output 1.1 Risk and vulnerability assessments conducted and updated | Indicator 1.1: No. of projects/programmes that conduct and update risk and vulnerability assessments | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | 0 | Multi-sector | Local | 1: No plans conducted or updated | 1 | Multi-sector | Local | 3: Risk and vulnterability assessments completed or updated
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
Output 1.2 Targeted population groups covered by adequate risk reduction systems | Core Indicator 1.2: No. of Early Warning Systems | No. of adopted Early Warning Systems | Category targeted | Hazard | Drought | No. of adopted Early Warning Systems | Category targeted | Hazard | Drought | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  | 0 | 2: Monitoring and warning service | Geographical coverage | Local | 1 | 2: Monitoring and warning service | Geographical coverage | Local |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities | 5 |  |  | Number of municipalities | 5 |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 2: Strengthened institutional capacity to reduce risks associated with climate-induced socioeconomic and environmental losses | Indicator 2: Capacity of staff to respond to, and mitigate impacts of, climate-related events from targeted institutions increased | Number of staff targeted |  | Sector | Capacity level | Number of staff targeted |  | Sector | Capacity level | Number of staff targeted |  | Sector | Capacity level | Number of staff targeted |  | Sector | Capacity level
|  | Total |  |  |  | Total |  |  |  | Total |  |  |  | Total
|  | % of female targeted |  |  |  | % of female targeted |  |  |  | % of female targeted |  |  |  | % of female targeted
Output 2.1 Strengthened capacity of national and sub-national centres and networks to respond rapidly to extreme weather events | Indicator 2.1.1: No. of staff trained to respond to, and mitigate impacts of, climate-related events | Total staff trained | % of female staff trained | Type |  | Total staff trained | % of female staff trained | Type |  | Total staff trained | % of female staff trained | Type |  | Total staff trained | % of female staff trained | Type
| Indicator 2.1.2: No. of targeted institutions with increased capacity to minimize exposure to climate variability risks | Type | Scale | Sector | Capacity level | Type | Scale | Sector | Capacity level | Type | Scale | Sector | Capacity level | Type | Scale | Sector | Capacity level
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 3: Strengthened awareness and owernship of adaptation and climate risk reduction processes | Indicator 3.1: Increase in application of appropriate adaptation responses | Percentage of targeted population applying adaptation measures |  | Sector |  | Percentage of targeted population applying adaptation measures |  | Sector |  | Percentage of targeted population applying adaptation measures |  | Sector |  | Percentage of targeted population applying adaptation measures |  | Sector
|  | 0% |  | Multi-sector |  | 61% |  | Multi-sector
Output 3: Targeted population groups participating in adaptation and risk reduction awareness activities | Indicator 3.1.1: Percentage in targeted population awareness of predicted adverse impacts of climate change, and of appropriate responses | No. of targeted beneficiaries | % of female participants targeted | Level of awareness |  | No. of targeted beneficiaries | % of female participants targeted | Level of awareness |  | No. of targeted beneficiaries | % of female participants targeted | Level of awareness |  | No. of targeted beneficiaries | % of female participants targeted | Level of awareness
|  | 0 | 0% | 2: Partially not aware |  | 24498 | 43% | 4: Mostly aware
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 4: Increased adaptive capacity within relevant development sector services and infrastructure assets | Indicator 4.1: Increased responsiveness of development sector services to evolving needs from changing and variable climate | Project/programme sector | Geographical scale | Response level |  | Project/programme sector | Geographical scale | Response level |  | Project/programme sector | Geographical scale | Response level |  | Project/programme sector | Geographical scale | Response level
|  | Water management | Local | 2: Partially responsive (Lacks most elements) |  | Water management | Local | 4: Mostly responsive (Most defined elements)
| Core Indicator 4.2: Assets produced, developed, improved or strengthened | Sector | Targeted asset | Changes in asset (quantitative or qualitative) |  | Sector | Targeted asset | Changes in asset (quantitative or qualitative) |  | Sector | Targeted asset | Changes in asset (quantitative or qualitative) |  | Sector | Targeted asset | Changes in asset (quantitative or qualitative)
|  | Water management | 2: Physical asset (produced/improved/strenghtened) | 2: Somewhat improved |  | Water management | 2: Physical asset (produced/improved/strenghtened) | 4: Mostly Improved
Output 4: Vulnerable development sector services and infrastructure assets strengthened in response to climate change impacts, including variability | Indicator 4.1.1: No. and type of development sector services to respond to new conditions resulting from climate variability and change | Number of services | Type |  | Sector | Number of services | Type |  | Sector | Number of services | Type |  | Sector | Number of services | Type |  | Sector
|  | 0 | Community |  | Water management | 45 | Community |  | Water management
|  | 0 | Community |  | Water management | 70 | Community |  | Water management
|  | 0 | Community |  | Water management | 56 | Community |  | Water management
|  | 0 | Community |  | Water management | 150 | Community |  | Water management
|  | 0 | Community |  | Water management | 50 | Community |  | Water management
|  | 0 | Community |  | Water management | 1156 | Community |  | Water management
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at Completion
Outcome 5: Increased ecosystem resilience in response to climate change and variability-induced stress | Indicator 5: Ecosystem services and natural resource assets maintained or improved under climate change and variability-induced stress | Natural resource improvement level |  | Sector | Type | Natural resource improvement level |  | Sector | Type | Natural resource improvement level |  | Sector | Type | Natural resource improvement level |  | Sector | Type
|  | 2: Partially effective |  | Agriculture | land | 3: Moderately effective |  | Agriculture | land
Output 5: Vulnerable ecosystem services and natural resource assets strengthned in response to climate change impacts, including variability | Core Indicator 5.1: Natural Assets protected or rehabilitated | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Catchment area/Watershed/Aquifer | 1500 | ha protected | 2: Partially effective | Catchment area/Watershed/Aquifer | 6141 | ha protected | 4: Effective
|  | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Forests | 160 | ha protected | 2: Partially effective | Forests | 2483 | ha protected | 4: Effective
|  | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Forests | 430 | ha protected | 2: Partially effective | Forests | 1500 | ha protected | 4: Effective
|  | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Baseline information |  |  |  | Targeted performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 6: Diversified and strengthened livelihoods and sources of income for vulnerable people in targeted areas | Indicator 6.1: Increase in households and communities having more secure access to livelihood assets | No. of targeted households | % of female headed households | Improvement level |  | No. of targeted households | % of female headed households | Improvement level |  | No. of targeted households | % of female headed households | Improvement level |  | No. of targeted households | % of female headed households | Improvement level
| Indicator 6.2: Increase in targeted population's sustained climate-resilient alternative livelihoods | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
|  | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
|  | 0 | 53% | From 10% to 20% | Livestock production | 6300 | 53% | From 10% to 20% | Livestock production
|  | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
|  | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
Output 6 Targeted individual and community livelihood strategies strengthened in relation to climate change impacts, including variability | Indicator 6.1.1: No. and type of adaptation assets created or strengthened in support of individual or community livelihood strategies | Number of Assets | Type of Assets | Sector | Adaptation strategy | Number of Assets | Type of Assets | Sector | Adaptation strategy | Number of Assets | Type of Assets | Sector | Adaptation strategy | Number of Assets | Type of Assets | Sector | Adaptation strategy
| Core Indicator 6.1.2: Increased income, or avoided decrease in income | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
0
|  | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | 6300 | Livestock production |  | 0 | 6300 | Livestock production |  | 100
|  | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 7: Improved policies and regulations that promote and enforce resilience measures | Indicator 7: Climate change priorities are integrated into national development strategy | Integration level |  |  |  | Integration level |  |  |  | Integration level |  |  |  | Integration level
Output 7:Improved integration of climate-resilience strategies into country development plans | Indicator 7.1: No. of policies introduced or adjusted to address climate change risks | No. of Policies introduced or adjusted | Sector | Scale | Type | No. of Policies introduced or adjusted | Sector | Scale | Type | No. of Policies introduced or adjusted | Sector | Scale | Type | No. of Policies introduced or adjusted | Sector | Scale | Type
| Indicator 7.2: No. of targeted development strategies with incorporated climate change priorities enforced | No. of Development strategies | Regulation |  | Effectiveness | No. of Development strategies | Regulation |  | Effectiveness | No. of Development strategies | Regulation |  | Effectiveness | No. of Development strategies | Regulation |  | Effectiveness
Glacier lake outburst flood
|  | Inland flooding | fr | biological assets |  | Company policy | 5: Fully enforced (All elements implemented)
|  | Salinization | Decrease | land |  | Communication & Information policy | 4: Enforced (Most elements implemented)
|  | Drought | Same | water areas |  | Defense policy | 3: Partially enforced (Some elements implemented)
|  | Wind |  | subsoil assets | increased adpative capacity | Domestic policy | 2: Partially not enforced (Most elements not implemented) |  | Agribusiness
|  | Coastal flooding |  | air | achieved | Economic policy | 1: Not enforced (No elements implemented) |  | Agricultural-related | Financial capital
|  | Storm surge | Please choose |  | enhanced level of protection | Education policy |  |  | Agriculture | Human capital
|  | Hurricane | Selected | [5 empty] | Aquaculture | Physical capital
|  |  | Not relevant |  |  | 5: All (Fully integrated) |  |  | Construction/repairing business | Social capital
[6 empty] | 4: Most |  |  | Cultivation | Natural capital
[6 empty] | 3: Some |  |  | Fishing | Personal capital
Select | 5: All | Select |  |  | Community | 2: Most not integrated |  | Other | Forestry | Adaptation strategies
1 | 4: Almost all | Private | Type | Yes | Multi-community | 1: None |  | Agriculture | Handicrafts
2 | 3: Half | Public | Scale | No | Departmental |  |  | Coastal management | Livestock production
3 | 2: Some | NGO | Sector |  | National |  |  | Disaster risk reduction | Manufacturing
4 | 1: None |  |  |  |  | 5: Very high improvement | Established | Food security | other
|  | National |  |  |  | 4: High improvement | Maintained | Health | Services
|  | Regional |  |  |  | 3: Moderate improvement | Improved | Urban development | Tourism-related
|  | Local |  |  |  | 2: Limited improvement |  | Water management | Trading
[6 empty] | 1: No improvement |  | Multi-sector
|  | 1 -generated information is irrelevant, and neither the stakeholders reached nor the timeframe managed were achieved | 1: No info transferred on time | 4: High capacity | 5: Fully aware | 5: Highly responsive (All defined elements ) | 5: Fully improved | Roads | 5: Very effective
Asia-Pacific | NIE | 2 -the existence of some challenge in any of the three aspects of the indicator (generation of dissemination, stakeholders reached or timeframe managed) | 2: Somewhat info transferred | 3: Medium capacity | 4: Mostly aware | 4: Mostly responsive (Most defined elements) | 4: Mostly Improved | Gov Buildings | 4: Effective
Latin America and Caribbean | RIE | 3 -relevant information is generated and disseminated to all identified stakeholders on timely basis | 3: Info transferred on time | 2: Low capacity | 3: Partially aware | 3: Moderately responsive (Some defined elements) | 3: Moderately improved | Causeways | 3: Moderately effective
Africa | MIE |  |  | 1: No capacity | 2: Partially not aware | 2: Partially responsive (Lacks most elements) | 2: Somewhat improved | Airports | 2: Partially effective
Eastern Europe |  |  |  |  | 1: Aware of neither | 1: Non responsive (Lacks all elements ) | 1: Not improved | Schools | 1: Ineffective
| ha protected | [6 empty] | Training Centres
| ha rehabilitated | [5 empty] | Monitoring/Forecasting capacity | Hospitals
Afghanistan, Islamic Rep. of | km protected | [5 empty] | Policy/regulatory reform | Drinking water systems
Angola | km rehabilitated | 1: Risk knowledge | 1: No plans conducted or updated |  |  |  | Capacity development | Other
Albania |  | 2: Monitoring and warning service | 2: Undertaking or updating of assessments in progress |  |  | Communication & Information policy | Sustainable forest management
Argentina |  | 3: Dissemination and communication | 3: Risk and vulnterability assessments completed or updated |  |  | Domestic policy | Strengthening infrastructure | 1: Health and Social Infrastructure (developed/improved)
Armenia | Forests | 4: Response capability |  |  |  | Economic policy | Supporting livelihoods | 2: Physical asset (produced/improved/strenghtened)
Antigua and Barbuda | Mangroves |  |  |  |  | Education policy | Mangrove reforestation
Azerbaijan | Coasts |  | From 0 to 0.5% |  |  | Energy policy | Coastal drainage and infrastructure
Burundi | Rangelands |  | From 0.5 to 1% |  |  | Environmental policy | Irrigation system
Benin | Cultivated land/Agricultural land |  | From 1% to 5% |  |  | Foreign policy | Community-based adaptation
Burkina Faso | Catchment area/Watershed/Aquifer |  | From 5% to 10% |  |  | Health policy | Erosion control
Bangladesh | Protected areas/National parks |  | From 10% to 20% |  |  | Housing policy | Soil water conservation
Bulgaria | Other |  | From 20% to 30% |  |  | Human resource policies | Microfinance
Bahrain |  |  | From 30% to 40% |  |  | Information policy | Special Program for women
Bahamas, The |  |  | From 40% to 50% |  |  | Macroeconomic policy | Livelihoods
Bosnia and Herzegovina |  |  | Above 50% |  |  | Monetary policy | Water storage
Belarus | [5 empty] | Population policy | ICT and information dissemination
Belize | [5 empty] | Private policy
Bolivia | [5 empty] | Public policy
Brazil | [5 empty] | Science policy
Barbados | [5 empty] | Social policy
Bhutan |  | 3- relevant information is generated and disseminated to all identified stakeholders on timely basis |  |  |  | Transportation policy
Botswana |  | describe |  |  |  | Urban policy
Central African Republic |  | 2- the existence of some challenge in any of the three aspects of the indicator |  |  |  | Water policy
Chile |  | describe |  |  |  | Other policy
China, People's Republic of |  | 1- generated information is irrelevant and neither the stakeholders reached nor the timeframe managed were achieved
Cote d'Ivoire |  | describe
Cameroon
Congo, Dem. Rep. of
Congo, Republic of
Cook Islands
Colombia
Comoros
Cape Verde
Costa Rica
Cuba
Czech Republic
Djibouti
Dominica
Dominican Republic
Algeria
Ecuador
Egypt
Eritrea
Estonia
Ethiopia
Fiji
Micronesia, Fed. States of
Gabon
Georgia
Ghana
Guinea
Gambia, The
Guinea-Bissau
Equatorial Guinea
Grenada
Guatemala
Guyana
Honduras
Croatia
Haiti
Hungary
Indonesia
India
Iran, Islamic Republic of
Jamaica
Jordan
Kazakhstan
Kenya
Kyrgyz Republic
Cambodia
Kiribati
Saint Kitts and Nevis
Korea, Republic of
Lao People's Democratic Republic
Lebanon
Liberia
Libya
Saint Lucia
Sri Lanka
Lesotho
Lithuania
Latvia
Morocco
Moldova
Madagascar
Maldives
Mexico
Marshall Islands
Macedonia, former Yugoslav Republic of
Mali
Malta
Myanmar
Montenegro
Mongolia
Mozambique
Mauritania
Mauritius
Malawi
Malaysia
Namibia
Niger
Nigeria
Nicaragua
Niue
Nepal
Nauru
Oman
Pakistan
Panama
Peru
Philippines
Palau
Papua New Guinea
Poland
Korea, Dem. People's Rep. of
Paraguay
Romania
Russian Federation
Rwanda
Saudi Arabia
Sudan
Senegal
Solomon Islands
Sierra Leone
El Salvador
San Marino
Serbia
Sao Tome and Principe
Suriname
Slovak Republic
Slovenia
Swaziland
Seychelles
Syrian Arab Republic
Chad
Togo
Thailand
Tajikistan
Turkmenistan
Tonga
Trinidad and Tobago
Tunisia
Turkey
Tuvalu
Tanzania
Uganda
Ukraine
Uruguay
Uzbekistan
Saint Vincent and the Grenadines
Venezuela
Vietnam
Vanuatu
Samoa
Yemen, Republic of
South Africa
Zambia
Zimbabwe
Timor-Leste
Note on G41: Hans van Noord: Townships i.e.
Note on F63: Hans van Noord: Combination of agriculture and livestock sectors
Note on H63: Hans van Noord: ProDoc states 75% 24498/40162 = 61%
Note on H65: Hans van Noord: 11550 agri, 6300 livestock, 6648 agroforestry and homestead gardening (based on 2.5 ha cut off)
Note on I65: UNDP: 97835(female)/229155(total) based on 2.5 ha cut off
Note on L67: Hans van Noord: template has mistake: indicated Target at completion instead at Mid-term
Note on P67: Hans van Noord: Should be "Performance at completion"instead of "Target at completion"
Note on H78: Hans van Noord: 45 small canals 70 small scale water pumps 56 communal water tanks 150 communal ponds rehabilitated or constructed 10 deep tube wells 1156 ha land covered with soil and water conservation techniques 40 shallow tube wells
Note on H79: Hans van Noord: small pumps
Note on H80: Hans van Noord: storage tanks
Note on H81: Hans van Noord: ponds
Note on H82: Hans van Noord: 40 shallow and 10 deep wells
Note on H83: Hans van Noord: Ha of watershed management area
Note on H85: Hans van Noord: Template has mistake: instead of baseline this should read "Target at completion"
Note on L85: Hans van Noord: Mistake in header: should read "Performance at mid-term" instead of "baseline"
Note on P85: Hans van Noord: Replaced "Baseline Information" title
Note on F87: Hans van Noord: In fact it is Forestry and Agroforestry or watershed management
Note on G87: Hans van Noord: In fact combination of vegetation cover increase to enhance soil- and water conservation
Note on E89: Hans van Noord: 1500ha of natural forest conservation and community based reforesation practices in critical watershed areas and 160ha agrofestry and 430ha of farm boundary plantations
Note on I89: Hans van Noord: Summation of: 3913 of NFC 1458 of CF, and 770 of tree planting on public land
Note on I92: Hans van Noord: 1000 homestead gardening 20ha demo plots 2ha silvopasture development 3 tree-intercropping 1458ha Taungya crop
Note on I95: Hans van Noord: Farm boundary plantation

## Units for Indicators
Fund Outcome Indicator Units
1. Generation of relevant data, Stakeholders, and Timeliness 2.1. Include both qualitative and quantitative measures of capacity level within targeted institutions 2.2. Number (men and women and other vulnerable groups) 3.1. Use scale from 1 to 5: 5: Fully aware 4: Mostly aware 3: Partially aware 2: Partially not aware 1: Aware of neither predicted adverse impacts of climate change nor of appropriate responses 3.2. Use scale from 1 to 5: 5: All 4: Almost all 3: Half 2: Some 1: None 4.1. Summarize in an overall scale (1-5): 5: Highly responsive (All defined elements ) 4: Mostly responsive (Most defined elements) 3: Moderately responsive (Some defined elements) 2: Partially responsive (Lacks most elements) 1: Non responsive (Lacks all elements ) 4.2. Summarize in an overall scale (1-5): 5: Fully improved 4: Mostly Improved 3: Moderately improved 2: Somewhat improved 1: Not improved 5. Depends on the targeted natural asset: Biological (species): measure through changes in population numbers (dynamics, structure, etc.) Land: measure changes in hectares. Baseline data will be necessary to estimate the change. Supporting indicators baseline and target (as well as contextual information) are needed such as the following: Farmers adopting recommended technologies, Ha. of land improved, Average deforestation rate Etc. Use scale from 1 to 5. 5: Very effective (All elements are present) 4: Effective (Most elements are present) 3: Moderately effective (Some elements are present) 2: Partially effective (Most elements are not present) 1: Ineffective (No elements are present) 6.1. Summarize in an overall scale (1-5): 5: Very high improvement 4: High improvement 3: Moderate improvement 2: Limited improvement 1: No improvement 6.2. Household income by source of livelihood in project area (USD) prior and post project intervention 7. Summarize in an overall scale (1-5). 5: All (Fully integrated) 4: Most 3: Some 2: Most not integrated 1: None
Fund Output Indicator Units
1.1. Number, sector(s) and level(s) of projects or interventions in separate fields of monitoring plan 1.2. Number 2.1.1. Number of staff (male/female) of targeted institutions: a. Obtain baseline information: total number of staff from targeted institutions b. Define target 2.1.2. Number of staff (male/female) of targeted institutions: a. Obtain baseline information: total number of staff from targeted institutions b. Define target: needs to be defined by project proponents 2.2.1. Quantitative: Percentage (includes women – and other vulnerable groups – and men). Qualitative: Adequacy: include direct analysis of major areas; adequacy/effectiveness of systems or analysis of perceptions of populations and institutions. 2.2.2. Number (broken down by gender and, if possible, by vulnerable groups defined in the area of intervention) of people 3.1. Number and type (in separate columns) at local level. 3.2. Number 4.1. Number and type 4. 2. Number and type (entered in separate columns) 5. Number of interventions by type of natural asset and intervention 6.1. Number and type (in separate columns of monitoring plan) 6.2. Income sources per household; description of income source and number of households. 7.1. Number/Sector 7.2. Number; Effectiveness (see previous indicator) through enforcement level.