## Overview
Project Performance Report (PPR)
| Period of Report (Dates) | 26 May 2015 - 25 May 2017
| Project Title: | Developing climate resilience of farming communities in the drought prone parts of Uzbekistan
| Project Summary: | The project objective is to develop climate resilience of farming and pastoral communities in the drought prone parts of Uzbekistan, specifically Karakalpakstan. The project will help the central, regional and local governments and vulnerable farmers and pastoralists to withstand the current and future impacts of climate change: aridification and projected drying of this region that places serious strains on water availability resulting in a decline in land productivity. The project is comprised of four main components: (i) institutional capacity and mechanisms for drought risk management and early warning; (ii) climate resilient agricultural and pastoral production systems; (iii) landscape level approach to adaptation to climate change risks of increased aridity; (iv) knowledge management and awareness raising.
|  |  | Countries | Project Type: |  | GEF Focal Area: | GEF 4 Focal Areas | GEF 2 / 3 Operational Programme: | Overall Rating of the project in the evaluation by the project evaluator: | GEF-4 Focal Area Strategic Program: | GEF-3 Focal Area Strategic Program:
| Database Number: | PIMS 5002 | Afghanistan | FP | Yes | Biodiversity | 1 | 1 | U | BD-SP1-PA Financing | 1: Arid & semi-arid ecosystems
Implementing Entity (IE) [name]: |  | United Nations Development Programme | Albania | MSP | No | Climate Change Adaptation | 2 | 2 | S | BD-SP2-Marine PA | 2: Coastal, marine & freshwater ecosystems
| Type of IE: | MIE | Algeria | EA |  | Climate Change Mitigation | 3 | 3 | MU | BD-SP3-PA Networks | 3: Forest ecosystems
| Country(ies): | Uzbekistan | Angola |  |  | International Waters | 5 | 5 | Good | BD-SP5-Markets | 13: Conservation and Sustainable Use of Biological Diversity Important to Agriculture
Relevant Geographic Points (i.e. cities, villages, bodies of water): |  | Karakalpakstan, including Muynak, Kegeyli, Takhtakupir, Chimbay, and Kanlykol districts | Argentina |  |  | Multiple Focal Area |  |  |  | BD-SP7-Invasive Alien Species(IAS) | 6: Promoting the adoption of renewable energy by removing barriers and reducing implementation costs
[8 empty] | CC-SP2- Industrial EE | 8: Waterbody based operational program
| Project Milestones | [6 empty] | CC-SP3-RE,CC-SP4-Biomass | 9: Integrated Land and Water multiple focal area
| Milestone |  | Bahamas | [6 empty] | CC-SP5-Transport | 10: Contaminants based operational program
AFB Approval Date: |  | 2014-02-10
IE-AFB Agreement Signature Date: |  | 2014-03-07 | [6 empty] | CC-SP6-LULUCF | 12: Integrated Ecosystem Management
Start of Project/Programme: |  | 2014-05-26 | [6 empty] | Cross cutting capacity building | 14: Persistent Organic Pollutants
Mid-term Review Date (if planned): |  | 2017-10-31
| Terminal Evaluation Date: | 2020-02-01
|  | List documents/ reports/ brochures / articles that have been prepared about the project. | Cyprus
|  | Multi-Year Work Plan and Budget Schedule Quarterly Reports and Annual Report in Atlas Minutes of Project Board meetings Press Releases in mass media Concept of agro-conservation and water saving technologies, methods and approaches can be implemented at project pilot sites Comprehensive Concept and detailed Action Plans to implementing landscape adaptation measures for each of five pilot sites Project communication strategy Quarterly informational bulletins issued in 2015 and 2016 Manual on how to develop hothouses and greenhouses in Karakalpakstan Manual "Salt tolerant plants for crop diversification in Karakalpakstan" Manual on growing vegetables in greenhouses in north part of Karakalpakstan Recommendations on use of glauconit mineral as natural fertilizer in agriculture at arid lands Project Brief Article about project in national mass media, see at http://pv.uz/ekologiya/28884 ; http://www.uz.undp.org/content/uzbekistan/en/home/presscenter/pressreleases/2017/04/14/development-of-the-aral-sea-region--priority-area-of-cooperation/; http://un.uz/eng/news/display/203 | Czech Republic
List the Website address (URL) of project. |  |  | Democratic People's Republic of Korea
|  | http://af.climatechange.uz/index.php/ru/ | Democratic Republic of the Congo
Denmark
| Project contacts: |  | Djibouti
National Project Manager/Coordinator |  |  | Dominica
| Name: | Mr. Aleksandr Merkushkin | Dominican Republic
| Email: | aleksandr.merkushkin@undp.org | Ecuador
| Date: | 2014-09-14 | Egypt
| Government DA |  | El Salvador
| Name: | Prof. Viktor Chub, General Director of Uzhydromet | Equatoral Guinea
| Email: | uzhymet@meteo.uz | Eritrea
| Date: | 2011-04-12 | Estonia
| Implementing Entity |  | Ethiopia
| Name: | Ms Natasha Olofinskaya; Ms. Rano Baykhanova | Fiji
| Email: | nataly.olofinskaya@undp.org; rano.baykhanova@undp.org | Finland
| Date: | 2014-05-01 | France
| Executing Agency |  | Gambia
| Name: | Prof. Viktor Chub, General Director of Uzhydromet | Georgia
| Email: | uzhymet@meteo.uz | Germany
| Date: | 2014-09-04 | Ghana
| Executing Agency |  | Greece
| Name: | Ms. Malika Nazarova, Deputy Head of Department on Pollutions Monitoring, Uzhydromet | Grenada
| Email: | uzhymet@meteo.uz | Guatemala
| Date: | 2014-09-15 | Guinea
| Executing Agency |  | Guinea Bissau
| Name: | Ms. Natalya Agaltseva, Deputy Head of Department on Pollutions Monitoring, Uzhydromet | Guyana
| Email: | natalya.agaltseva@gmail.com | Haiti
| Date: | 2015-10-10 | Honduras
Hungary
Iceland
India
Indonesia
Iran (Islamic Republic of)
Iraq
Ireland
Israel
Italy
Jamaica
Japan
Jordan
Kazakhstan
Kenya
Kiribati
Kuwait
Kyrgyzstan
Lao People’s Democratic Republic
Latvia
Lebanon
Lesotho
Liberia
Libyan Arab Jamahiriya
Liechtenstein
Lithuania
Luxembourg
Madagascar
Malawi
Malaysia
Maldives
Mali
Malta
Marshall Islands
Mauritania
Mauritius
Mexico
Micronesia, Federated States of
Monaco
Mongolia
Montenegro
Morocco
Mozambique
Myanmar
Namibia
Nauru
Nepal
Netherlands
New Zealand
Nicaragua
Niger
Nigeria
Norway
Oman
Pakistan
Palau
Panama
Papua New Guinea
Paraguay
Peru
Philippines
Poland
Portugal
Qatar
Republic of Korea
Republic of Moldova
Romania
Russian Federation
Rwanda
Saint Kitts and Nevis
Saint Lucia
Saint Vincent and the Grenadines
Samoa
San Marino
Sao Tome and Principe
Saudi Arabia
Senegal
Serbia
Seychelles
Sierra Leone
Singapore
Slovakia
Slovenia
Solomon Islands
Somalia
South Africa
Spain
Sri Lanka
Sudan
Suriname
Swaziland
Sweden
Switzerland
Syrian Arab Republic
Tajikistan
Thailand
The former Yugoslav Republic of Macedonia
Timor-Leste
Togo
Tonga
Trinidad and Tobago
Tunisia
Turkey
Turkmenistan
Tuvalu
Uganda
Ukraine
United Arab Emirates
United Kingdom of Great Britain and Northern Ireland
United Republic of Tanzania
United States of America
Uruguay
Uzbekistan
Vanuatu
Venezuela, Bolivarian Republic of
Viet Nam
Yemen
Zambia
Zimbabwe

## Risk Assesment
RISK ASSESMENT
IDENTIFIED RISKS
List all Risks identified in project preparation phase and what steps are being taken to mitigate them
Identified Risk | Current Status | Steps Taken to Mitigate Risk
1. Reluctance of farmers or pastoralists to depart from over-irrigation and overutilization of inputs approach towards climate resilient conservation agriculture | Low | The risk was mitigated through number of knowledge sharing and best practice demonstration events conducted by the project. At least 160 farmers (20% of women) attended the three field hands-on workshops, within which they familiarized with land laser leveling demonstrations/trainings conducted at 500 ha of lands located in the project pilot districts (Kanlikul, Chimbay and Takhtakupir). Agro conservation and water saving practices were piloted at two project pilot districts (Kegeili and Chimbay). 247 farmers and householders (205 women) raised their awareness about agro conservation and water saving technologies applicable at local level through workshops conducted at four project pilot districts (Kegeili, Chimbay, Takhtakupir and Kankikul). 100 stakeholders (10% of women) of line ministries, Committee of Women and farmers attended two thematic demo workshops and increased their understanding about annual project targets and results achieved. Members of local communities in two project pilot districts (Muynak and Takhtakupir) familiarized with piloting sand stabilization and pasture reclamation at 80 ha of lands. 132 representatives (51% of women) of local communities learned about landscape adaptation measures that can increase their resilience to droughts and other climate change impacts through two series of field workshops held in three project pilot districts (Muynak, Takhtakupir and Kanlikul).
2. Repeated drought | High | The Dought Early Warning System (DEWS) previously designed for run-off forming zones and applicable for different river basins was upgraded for downstream of Amudarya river. Currently, early warning about low water availability or drought can be issued for the regions located at the downstream of Amudarya with lead-time of 3 months. Upgraded DEWS provides quantitative and qualitative water availability assessments published in the project's quarterly bulletins that are targeted at central and regional government decision-makers, farmers and householders. Thus, the given risk was reduced during the reporting period and it is expected to be further reduced during the next reporting period due to wider dissemination of DEWS products among end-users in the project pilot districts in Karakalpakstan.
3. Low level of cooperation between executing institutions | Low | Within the two demo workshops, a high level meeting (at sub-national level) was conducted to strengthen partnership with and ownership of all stakeholders involved in implementation of the project activities in Karakalpakstan. Meeting was chaired by the Chairman and Deputy Chair of the Council of Ministers of Republic of Karakalpakstan. Moreover, the two Inter-Agency Working Groups (national and sub-national levels) established by the particular government resolutions to strengthen coordination and cooperation of all national partners involved in the Adaptation Project were supplemented with five initiative groups (each group includes 5-7 persons representing the rural communities) in each project pilot district. Those are aimed at strengthening the interaction between the national and sub-national executing agencies, and therefore significantly reduce the risk.
Critical Risks Affecting Progress (Not identified at project design)
Identify Risks with a 50% or > likelihood of affecting progress of project
Identified Risk | Current Status | Steps Taken to Mitigate Risk
Risk Measures: Were there any risk mitigation measures employed during the current reporting period? If so, were risks reduced? If not, why were these risks not reduced?
Add any comments relevant to risk mitigation (word limit = 500)

## FinancialData
Financial information: cumulative from project start to 25 May 2017
DISBURSEMENT OF AF GRANT FUNDS
How much of the total AF grant as noted in Project Document plus any project preparation grant has been spent to date?
Estimated cumulative total disbursement as of 25 May 2017 | 1194026
Add any comments on AF Grant Funds. (word limit=200) | Since the beginning of the project, US$1,194,026 AF grants have been received through two tranches: first tranche of US$164,863.00 and the second one of US$1,029,163.00. Since the project start in 2014, cumulative disbursed funds totaled to US$876,103.63. For the reporting period from 26 May 2015 to 25 May 2017, the disbursed amount is US$731,051.40 (US$19,810.77 from the first tranche and US$711,240.63 the from second tranche) and committed funds of the second tranche are US$241,875.04. In total, disbursed and committed funds of the second tranche (US$953,115.67), since October 2015 to May 2017, represent 93%. Disbursement of AF grants during the current reporting period was experienced with delays due to the late receipt of the second tranche (3 months delayed) and delay of pre-commissioned works provided by some of the international vendors (MOTOROLA SOLUTION).
INVESTMENT INCOME
Amount of annual investment income generated from the Adaptation Fund’s grant
EXPENDITURE DATA
List ouput and corresponding amount spent for the current reporting period | ITEM / ACTIVITY / ACTION | AMOUNT
| 1.1 Upgraded observation and monitoring infrastructure (e.g. 2 Doppler water meters, automatization of 8 meteo stations) for effective data receiving and transmission | 370801.44
1.2. Multi-modules platform for integration of data flow from hydro-meteorological observation network to end users
1.3. Drought early warning mechanisms (indicators, gauges, warning distribution mechanisms etc.) to minimize impacts of droughts in place and functional
1.4. Science-based extension services for subsistence dekhan farmers established to assist in farm-based climate risk management, including sub-district, community level Climate Field School/Extension (CFS/E) for direct outreach to farmers and localized training in adaptation practices
| 2.1. 40,000 Dekhkan farmers have adopted climate resilient conservation agriculture practices (e.g. low till, mixed cropping, fodder production, and residue crop soil covering adopted measures adopted at 80,000 ha of dekhkan farms) | 84423.35
2.2. 40,000 Dekhan farmers have adopted water saving irrigation practices (e.g. land leveling, well management, furrow and drip irrigation systems adopted at 80,000 ha dekhkan farms to improve farm-level drainage and minimize salinization)
2.3. 40% of targeted dekhan farmers have established horticulture greenhouses on 20,000 ha of farms to minimize impacts of droughts on farm production
2.4. Legal and regulatory framework put in place to support well tested farm-based adaptation measures for replication and upscale
| 3.1. Local saksaul and tamarix plantations deliver sand stabilization and soil desalinization function for 1,042,094 ha of farm and adjacent farmlands, based on wind models and comprehensive landscape rehabilitation and management plan | 33800.11
3.2. Community management scheme for planting and maintenance established as community employment scheme for landscape level adaptation
3.3. Cooperative management for landscape rehabilitation and management established to enhance community control and ownership arrangements
| 4.1. Inventory of all tested agronomic and water saving measures to map out successful practices | 85503.97
4.2. Analysis and lessons learned for climate resilient agricultural and pastoral production systems in arid lands documented and disseminated through printed and web-based publications
4.3. Quarterly farm and pasture land demonstration meetings with participation of national, local authorities, media and communities delivered
| 5. Project management | 156522.53
| TOTAL | 731051.4
PLANNED EXPENDITURE SCHEDULE
List outputs planned and corresponding projected cost for the upcoming reporting period | ITEM / ACTIVITY / ACTION | PROJECTED COST | Est. Completion Date
| 1.1 Upgraded observation and monitoring infrastructure (e.g. 2 Doppler water meters, automatization of 8 meteo stations) for effective data receiving and transmission | 43404.9722 | 2018-05-01
| 1.2. Multi-module platform for integration of data flow from hydro-meteorological observation network to end users | 86047.8066 | 2018-05-01
| 1.3. Drought early warning mechanisms (indicators, gauges, warning distribution mechanisms etc.) to minimize impacts of droughts in place and functional | 49579.9267 | 2018-05-01
| 1.4. Science-based extension services for subsistence dekhan farmers established to assist in farm-based climate risk management, including sub-district, community level Climate Field School/Extension (CFS/E) for direct outreach to farmers and localized training in adaptation practices | 55316.4471 | 2018-05-01
| 2.1. 40,000 Dekhkan farmers have adopted climate resilient conservation agriculture practices (e.g. low till, mixed cropping, fodder production, and residue crop soil covering adopted measures adopted at 80,000 ha of dekhkan farms) | 346861.2034 | 2018-05-01
| 2.2. 40,000 Dekhan farmers have adopted water saving irrigation practices (e.g. land leveling, well management, furrow and drip irrigation systems adopted at 80,000 ha dekhkan farms to improve farm-level drainage and minimize salinization) | 122310.8108 | 2018-05-01
| 2.3. 40% of targeted dekhan farmers have established horticulture greenhouses on 20,000 ha of farms to minimize impacts of droughts on farm production | 256094.6625 | 2018-05-01
| 2.4. Legal and regulatory framework put in place to support well tested farm-based adaptation measures for replication and upscale | 16646.1531 | 2018-05-01
| 3.1. Local saksaul and tamarix plantations deliver sand stabilization and soil desalinization function for 1,042,094 ha of farm and adjacent farmlands, based on wind models and comprehensive landscape rehabilitation and management plan | 509894.3352 | 2018-05-01
| 3.2. Community management scheme for planting and maintenance established as community employment scheme for landscape level adaptation | 51218.9325 | 2018-05-01
| 3.3. Cooperative management for landscape rehabilitation and management established to enhance community control and ownership arrangements | 51218.9325 | 2018-05-01
| 4.1. Inventory of all tested agronomic and water saving measures to map out successful practices | 8771.7544 | 2018-05-01
| 4.2. Analysis and lessons learned for climate resilient agricultural and pastoral production systems in arid lands documented and disseminated through printed and web-based publications | 10243.7865 | 2018-05-01
| 4.3. Quarterly farm and pasture land demonstration meetings with participation of national, local authorities, media and communities delivered | 8195.0292 | 2018-05-01
| 5. Project management | 77280.62 | 2018-05-01
| TOTAL | 1693085.3727
ACTUAL CO-FINANCING (If the MTR or TE have not been undertaken this reporting period, DO NOT report on actual co-financing.)
How much of the total co-financing as committed in the Project Document has actually been realized? | From the committed UNDP's cofinancing (USD200,000), $ 56,414.10 was used to cover the costs associated with direct project support services such as assistance to procurement and recruitment.
Estimated cumulative actual co-financing as verified during Mid-term Review (MTR) or Terminal Evaluation (TE).
Add any comments on actual co-financing in particular any issues related to the realization of in-kind, grant, credits, loans, equity, non-grant instruments and other types of co-financing. (word limit=200)
Note on F36: aleksandr.merkushkin: 6 months PM salary included
Note on F40: aleksandr.merkushkin: Yearly salary of NFC included
Note on F44: aleksandr.merkushkin: Specilalist on landscape adptation (SC7) yearly salary included. Project Assistant (SC6, Duty Station Nukus) 10 months salary included
Note on F50: aleksandr.merkushkin: PM 6 months salary, Project Assistant salary,two drivers salaries and miscellaneous expenses included

## Rating
RATING ON IMPLEMENTATION PROGRESS
For rating definitions please see bottom of page.
| Progress on Key Milestones |  | Expected Progress |  | Progress to Date | Rating
Project Manager/Coordinator: | Doppler water meters and 8 automated meteorological stations installed (Outcome 1) |  | 8 automated meteo stations and 2 new Doppler water meters installed and commissioned. |  | The network of 10 meteorological stations in Karakalpakstan have been autamated and functional. Two Doppler water discharge meters procured and installed in two key water gauge stations (Tuyamuyun and Kipchak). | HS
| At least 40,000 km2 of the Karakalpakstan region covered by automated hydro-meteorological observation network (Outcome 1) |  | At least 8 national experts trained for maintenance of automated weather stations network. |  | 40 local specialists (35% of women) trained on installation, maintenance and operation of the meteorological equipment, and 10 (20% of women) local specialists trained on use the water measuring equipment. | HS
| Season ahead forecasts and 2 weeks ahead temperature forecasts for effective warnings are practiced (Outcome 1) |  | Drought early warning mechanisms elaborated and its locations identified. At least 8 hardware components for maintenance of automated weather stations identified and procured |  | Existing mechanisms of Drought Early Warning System (DEWS) located in Uzhydromet and at Drought Monitoring Center were upgraded and adapted to Amudarya downstream condition. DEWS provides both quantitative and qualitative water availability assessment for Amudarya specific cross-sections with lead time of 3 months. Validity of the assessments varies from 70 to 100% | HS
| At least 40% of Dekhkan farmers and pastoralists of Karakalpak region are served by science-based extension (Outcome 1) |  | At least 5,000 (at least 20% of women) stakeholders targeted by science-based extension services and trained within trainings and workshops. |  | Two Extension Service Centers established and operationalized. 5,963 (20 % of women) representatives of local communities in the projetc's pilot districts (in Kegeili, Kanlikul, Chimbay, Takhtakupir and Muynak districts) are aware on set of climate change adaptation services available and innovative agro conservation and water saving practices. | S
| At least 3 Field School/Extension established and delivered training in adaptation practices to farmers and pastoralists (Outcome 1) |  | Concept of establishing science-based extension services for subsistence dekhan farmers developed |  | Concept of establishing science-based extension services for subsistence dekhan farmers developed and is implemented by 2 Extension Service Centers established. 93 potential employees of Extension Service Centers to be further established in 3 pilot districts trained. | S
| At least 20% of targeted Dekhkan beneficiaries are female (Outcome 1) |  | At least 15,000 stakeholders and end-users (50% of women) are aware of the automated hydro-meteorological observation network |  | 15,000 stakeholders in Karakalpakstan and overall in Uzbekistan, and 1,500 direct end-users (20%) in 5 pilot districts were informed about the automated hydro-meteorological observation network through demo-workshops, quarterly bulletins, web-resources and wide mass media coverage (TV and radio broadcasting, and press) | S
| At least 40,000 Dekhan farmers have adopted climate resilient conservation agriculture practices by end of the project (Output 2.1) |  | At least 5,000 stakeholders (30% of women) provided with printing and publications associated with the climate resilient conservation agriculture practices |  | 5,963 (20 % of women) representatives of local communities from five pilot districts (in Kegeili, Kanlikul, Chimbay, Takhtakupir and Muynak districts) provided with 4 publications, 4 informative quarterly bulletins on agro conservation and water saving practices and crop diversification options within 15 workshops, meetings, through Extension Service Centers and round table, 2 press-conferences. | S
| At least 40,000 Dekhan farmers have adopted water saving irrigation practices by end of the project (Output 2.2) |  | At least 5,000 stakeholders (30% of women) trained in application of land leveling, furrow, siphon and drip irrigation systems |  | 217 (24% of women) farmers in 4 project's pilots (Kegeili, Kanlikul, Chimbay and Takhtakupir ) trained through 4 field trainings on adaptation practice including water saving irrigation practices | MS
| Female lead horticulture greenhouses established by mid of 2016 (Outcome 2) |  | At least 500 units of horticulture greenhouse equipment procured; and at least 16,000 households (50% of women) provided with printing and publications associated with the horticulture greenhouse best practices; and female lead horticulture greenhouses established |  | Documentation to procure 500 units of horticulture greenhouse equipment developed based on the identified types and designs of greenhouses applicable to climate conditions of northern areas of Karkalpakstan. 500 potential owners (20% of female) identified based on their social and gender profile. 400 beneficiaries were provided with Informational Guidance to developing greenhouse and hot house business in Karakalpakstan and Recommendations on indoor vegetables growing for Northern Districts of Karakalpakstan published in Karakalpak, Uzbek and Russian. | MS
| Laws on agricultural practices and water management amended and integrate conservation agriculture and water saving techniques by end of 2016 |  | Gaps in existing legal and regulatory framework and required improvements to support well tested farm-based adaptation measures identified. At least 500 stakeholders (30% of women) provided with expertise and technical assistance in development/improvement of legal and regulatory framework to support well tested farm-based adaptation measures for replication and upscale |  | Study conducted to identify gaps in legal regulatory to supporting the promotion of well-tested farm-based adaptation measures that can be replicated and up-scaled, and recommendations on how the gaps can be filled up as well as proposed actions can be integrated into the existing regulations developed. | S
| By end of the project, over 70,000 ha of arid land of Karakalpakstan is covered with saksaul and tamarix plantations and deliver sand stabilization and soil desalinization function (Outcome 3) |  | Technical assistance in best practices on development of management plan for sand stabilization and soil desalinization and comprehensive landscape rehabilitation provided at least 5,000 ha of lands. At least 10,000 of local saksaul and tamarix plantings procured and planted at fields, and at least 8 survey equipment to monitor sand stabilization and soil desalinization based on wind models and comprehensive landscape rehabilitation procured. |  | The most problematic areas with poor or no vegetation coverage at 5 project pilot districts were identified with use of data derived from TERRA MODIS platform as a prerequisite to quantify yearly demand for saplings (approx. 70 mln). Sand stabilization and pastures reclamation works were initiated at over 80 ha of the two most exposed to land degradation/desertification pilot districts (Muynak and Takhtakupir) as a test prior initiation works over 1,000 ha. | MS
| At least 20,000 people organized in at least 10 cooperatives at the khokimiyat and makhalla levels and participate in sand stabilization plantation scheme (Outcome 3) |  | At least one community management scheme for planting and maintenance as community employment scheme for landscape level adaptation developed. At least 10,000 stakeholders (50% of women) trained in community management for planting and maintenance for landscape level adaptation. |  | A concept on establishing the cooperative management scheme for implementation of the required landscape adaptation measures developed. Three hands-on workshops on landscape adaptation measures/approaches and their implementation were conducted at three pilot districts (Muynak, Takhtakupir and Kanlikul), at which 132 members of local communities (51% of women) attended. Sand stabilization and soil moisture saving works were initiated at 2 the most vulnerable pilot districts (Muynak and Takhtakupir) based on cooperative management approaches piloting at 80 ha (30 ha for sand stabilization and 50 ha for pasture reclamation) was implemented by 2 local forestry farms. | MS
| At least 10 community organizations (at least 5 female groups and village organizations) at khokimiyat and makhalla level have clear mandates, institutional capacities and skills and manage saksaul and tamarix plantations by end of 2019 (Outcome 3) |  | At least 10,000 stakeholders (30% of women) provided with the printing and publications associated with the cooperative management system for landscape rehabilitation and management to enhance community control and ownership, and trained in its application |  | 5,963 (20 % of women) representatives of local communities from five project's pilots (in Kegeili, Kanlikul, Chimbay, Takhtakupir and Muynak districts) provided with 2 recommendations, 4 informative quarterly bulletins on cooperative management system for landscape rehabilitation and management to enhance community control and ownership within 15 workshops, meetings, through Extension Service Centers and round table, 2 press-conferences. | S
| At least two sets of lessons learned bulletins produced and covered successful climate resilient agronomic and water saving measures (Outcome 4) |  | At least 3 lessons learned for climate resilient agricultural and pastoral production systems in arid lands from stakeholders through providing them with technical assistance in analysis and documentation of those lessons learned |  | The lessons focused on DEWS, agro conservation and water saving practices, and landscape adaptation measures are captured and formulated to be finalized and documented by the end of 2017 | MS
| At least 5 farmland demonstration meetings covered by the local and national media for adaptation advocacy (Outcome 4) |  | At least 2 farm and pasture land demonstration meetings conducted with participation of national, local authorities, media and communities, and associated printing and publications produced and disseminated |  | 15 demonstration meetings and workshops (535 people; 26% of female) on climate change adaptation and resilience and targeted at local communities conducted. Information on the events posted at newspapers and web-resources, and broadcasted via national and regional radio and TV. | HS
[5 empty] | Overall Rating | S
Please Provide the Name and Contact information of person(s) responsible for completing the Rating section
| Name: | Aleksandr Merkushkin
| Email: | aleksandr.merkushkin@undp.org
Please justify your rating. Outline the positive and negative progress made by the project since it started. Provide specific recommendations for next steps. . (word limit=500)
The overall rating is Satisfactory. For the reporting time period the project's staff was able to speed up some of the major project activities that were significantly lagging behind. There are a few milestones that could be particularly highlighted : - - completion of the installation of 10 automated meteo-stations in Karakalpakstan; - adaptation of drought early warning system in the lower Amudarya delta; - overall concept on agro conservation and water saving practices and action plans for each of 5 pilot regions developed and are under implementation; - 80 mechanics and farmers from 5 pilot districts trained on land laser levelling (covered 160 ha) with use of 7 sets of laser leveling equipment provided within field hands-on workshops conducted; - preparatory agro conservation and water saving works done at over 30 ha in two pilot districts; - terrotories most exposed to desertification identified using remote sensing data (TERRA-MODIS, NDVI); - 211 beneficiaries (82 women or 39%) familiarized with sand stabilization, pasture reclamation and forest belt planting though 5 thematic workshops; - encroaching sand stabilization works are underway and cover 30 ha in Muynak pilot region; - pastures reclamation activity are underway and cover over 50 ha in Takhtakupir district - the project communication strategy developed and is being implemented; - 2 Extension Service Centers established; - 963 direct beneficiaries (245 or 25% women) and up to 5,000 indirect beneficiaries (20% women) raised their awareness and increased knowledge through dissemination of information and sharing knowledge within 13 thematic workshops covered all 5 pilot districts; - 4 thematic publications (use of greenhouses, techniques of growing vegetables in arid lands, use of glaukonit as natural fertilizer) and 3 quarterly project’s bulletins developed on Karakalpak, Uzbek and Russian and widely distributed; - project’s web site developed and operational at the common platform: http://climatechange.uz/ (shared with CRM and GCF Readiness projects) under Uzhydromet: http://af.climatechange.uz At the same time, in the second half of 2016 certain lack of coherence of project activities and inconsistent follow-up were observed. In this regard, systematic and coherent planning of the project and efficient planning of procurement works by duly taking into account complexity and seasonality factors of certain project activities and procurement works should be ensured .
| Progress on Key Milestones |  | Expected Progress |  | Progress to Date | Rating
Implementing Agency | Doppler water meters and 8 automated meteorological stations installed (Outcome 1) |  | 8 automated meteo stations and 2 new Doppler water meters installed and commissioned. |  | The network of 10 meteorological stations in Karakalpakstan have been autamated and functional. Two Doppler water discharge meters procured and installed in two key water gauge stations (Tuyamuyun and Kipchak). | S
| At least 40,000 km2 of the Karakalpakstan region covered by automated hydro-meteorological observation network (Outcome 1) |  | At least 8 national experts trained for maintenance of automated weather stations network. |  | 40 local specialists (35% of women) trained on installation, maintenance and operation of the meteorological equipment, and 10 (20% of women) local specialists trained on use the water measuring equipment. | S
| Season ahead forecasts and 2 weeks ahead temperature forecasts for effective warnings are practiced (Outcome 1) |  | Drought early warning mechanisms elaborated and its locations identified. At least 8 hardware components for maintenance of automated weather stations identified and procured |  | Existing mechanisms of Drought Early Warning System (DEWS) located in Uzhydromet and at Drought Monitoring Center were upgraded and adapted to Amudarya downstream condition. DEWS provides both quantitative and qualitative water availability assessment for Amudarya specific cross-sections with lead time of 3 months. Validity of the assessments varies from 70 to 100% | HS
| At least 40% of Dekhkan farmers and pastoralists of Karakalpak region are served by science-based extension (Outcome 1) |  | At least 5,000 (at least 20% of women) stakeholders targeted by science-based extension services trained within trainings and workshops. |  | Two Extension Service Centers established and operationalized. 5,963 (20 % of women) representatives of local communities in the projetc's pilot districts (in Kegeili, Kanlikul, Chimbay, Takhtakupir and Muynak districts) are aware on set of climate change adaptation services available and innovative agro conservation and water saving practices. | HS
| At least 3 Field School/Extension established and delivered training in adaptation practices to farmers and pastoralists (Outcome 1) |  | Concept of establishing science-based extension services for subsistence dekhan farmers developed |  | Concept of establishing science-based extension services for subsistence dekhan farmers developed and is implemented by 2 Extension Service Centers established. 93 potential employees of Extension Service Centers to be further established in 3 pilot districts trained. | S
| At least 20% of targeted Dekhkan beneficiaries are female (Outcome 1) |  | At least 15,000 stakeholders and end-users (50% of women) are aware of the automated hydro-meteorological observation network |  | 15,000 stakeholders in Karakalpakstan and overall in Uzbekistan, and 1,500 direct end-users (20%) in 5 pilot districts were informed about the automated hydro-meteorological observation network through demo-workshops, quarterly bulletins, web-resources and wide mass media coverage (TV and radio broadcasting, and press) | S
| At least 40,000 Dekhan farmers have adopted climate resilient conservation agriculture practices by end of the project (Output 2.1) |  | At least 5,000 stakeholders (30% of women) provided with printing and publications associated with the climate resilient conservation agriculture practices |  | 5,963 (20 % of women) representatives of local communities from five pilot districts (in Kegeili, Kanlikul, Chimbay, Takhtakupir and Muynak districts) provided with 4 publications, 4 informative quarterly bulletins on agro conservation and water saving practices and crop diversification options within 15 workshops, meetings, through Extension Service Centers and round table, 2 press-conferences. | HS
| At least 40,000 Dekhan farmers have adopted water saving irrigation practices by end of the project (Output 2.2) |  | At least 5,000 stakeholders (30% of women) trained in application of land leveling, furrow, siphon and drip irrigation systems |  | 217 (24% of women) farmers in 4 project's pilots (Kegeili, Kanlikul, Chimbay and Takhtakupir ) trained through 4 field trainings on adaptation practice including water saving irrigation practices | MS
| Female lead horticulture greenhouses established by mid of 2016 (Outcome 2) |  | At least 500 units of horticulture greenhouse equipment procured; and at least 16,000 households (50% of women) provided with printing and publications associated with the horticulture greenhouse best practices; and female lead horticulture greenhouses established |  | Documentation to procure 500 units of horticulture greenhouse equipment developed based on the identified types and designs of greenhouses applicable to climate conditions of northern areas of Karkalpakstan. 500 potential owners (20% of female) identified based on their social and gender profile. 400 beneficiaries were provided with Informational Guidance to developing greenhouse and hot house business in Karakalpakstan and Recommendations on indoor vegetables growing for Northern Districts of Karakalpakstan published in Karakalpak, Uzbek and Russian. | MS
| Laws on agricultural practices and water management amended and integrate conservation agriculture and water saving techniques by end of 2016 |  | Gaps in existing legal and regulatory framework and required improvements to support well tested farm-based adaptation measures identified. At least 500 stakeholders (30% of women) provided with expertise and technical assistance in development/improvement of legal and regulatory framework to support well tested farm-based adaptation measures for replication and upscale. |  | Study conducted to identify gaps in legal regulatory to supporting the promotion of well-tested farm-based adaptation measures that can be replicated and up-scaled, and recommendations on how the gaps can be filled up as well as proposed actions can be integrated into the existing regulations developed. | MS
| By end of the project, over 70,000 ha of arid land of Karakalpakstan is covered with saksaul and tamarix plantations and deliver sand stabilization and soil desalinization function (Outcome 3) |  | Technical assistance in best practices on development of management plan for sand stabilization and soil desalinization and comprehensive landscape rehabilitation provided at least 5,000 ha of lands. At least 10,000 of local saksaul and tamarix plantings procured and planted at fields, and at least 8 survey equipment to monitor sand stabilization and soil desalinization based on wind models and comprehensive landscape rehabilitation procured |  | The most problematic areas with poor or no vegetation coverage at 5 project pilot districts were identified with use of data derived from TERRA MODIS platform as a prerequisite to quantify yearly demand for saplings (approx. 70 mln). Sand stabilization and pastures reclamation works were initiated at over 80 ha of the two most exposed to land degradation/desertification pilot districts (Muynak and Takhtakupir) as a test prior initiation works over 1,000 ha. | MS
| At least 20,000 people organized in at least 10 cooperatives at the khokimiyat and makhalla levels and participate in sand stabilization plantation scheme (Outcome 3) |  | At least one community management scheme for planting and maintenance as community employment scheme for landscape level adaptation developed. At least 10,000 stakeholders (50% of women) trained in community management for planting and maintenance for landscape level adaptation. |  | A concept on establishing the cooperative management scheme for implementation of the required landscape adaptation measures developed. Three hands-on workshops on landscape adaptation measures/approaches and their implementation were conducted at three pilot districts (Muynak, Takhtakupir and Kanlikul), at which 132 members of local communities (51% of women) attended. Sand stabilization and soil moisture saving works were initiated at 2 the most vulnerable pilot districts (Muynak and Takhtakupir) based on cooperative management approaches piloting at 80 ha (30 ha for sand stabilization and 50 ha for pasture reclamation) was implemented by 2 local forestry farms. | MU
| At least 10 community organizations (at least 5 female groups and village organizations) at khokimiyat and makhalla level have clear mandates, institutional capacities and skills and manage saksaul and tamarix plantations by end of 2019 (Outcome 3) |  | At least 10,000 stakeholders (30% of women) provided with the printing and publications associated with the cooperative management system for landscape rehabilitation and management to enhance community control and ownership, and trained in its application |  | 5,963 (20 % of women) representatives of local communities from five project's pilots (in Kegeili, Kanlikul, Chimbay, Takhtakupir and Muynak districts) provided with 2 recommendations, 4 informative quarterly bulletins on cooperative management system for landscape rehabilitation and management to enhance community control and ownership within 15 workshops, meetings, through Extension Service Centers and round table, 2 press-conferences. | S
| At least two sets of lessons learned bulletins produced and covered successful climate resilient agronomic and water saving measures (Outcome 4) |  | At least 3 lessons learned for climate resilient agricultural and pastoral production systems in arid lands from stakeholders through providing them with provided with technical assistance in analysis and documentation of those lessons learned |  | The lessons focused on DEWS, agro conservation and water saving practices, and landscape adaptation measures are captured and formulated to be finalized and documented by the end of 2017 | S
| At least 5 farmland demonstration meetings covered by the local and national media for adaptation advocacy (Outcome 4) |  | At least 2 farm and pasture land demonstration meetings conducted with participation of national, local authorities, media and communities, and associated printing and publications produced and disseminated |  | 15 demonstration meetings and workshops (535 people; 26% of female) on climate change adaptation and resilience and targeted at local communities conducted. Information on the events posted at newspapers and web-resources, and broadcasted via national and regional radio and TV. | S
[5 empty] | Overall Rating | S
Please Provide the Name and Contact information of person(s) responsible for completing the Rating section
| Name: | Ms Natasha Olofinskaya; Ms. Rano Baykhanova
| Email: | nataly.olofinskaya@undp.org; rano.baykhanova@undp.org
| Progress on Key Milestones |  | Expected Progress |  | Progress to Date | Rating
Other | Doppler water meters and 8 automated meteorological stations installed (Outcome 1) |  | 8 automated meteo stations and 2 new Doppler water meters installed and commissioned. |  | The network of 10 meteorological stations in Karakalpakstan have been autamated and functional. Two Doppler water discharge meters procured and installed in two key water gauge stations (Tuyamuyun and Kipchak). | S
| At least 40,000 km2 of the Karakalpakstan region covered by automated hydro-meteorological observation network (Outcome 1) |  | At least 8 national experts trained for maintenance of automated weather stations network. |  | 40 local specialists (35% of women) trained on installation, maintenance and operation of the meteorological equipment, and 10 (20% of women) local specialists trained on use the water measuring equipment. | S
| Season ahead forecasts and 2 weeks ahead temperature forecasts for effective warnings are practiced (Outcome 1) |  | Drought early warning mechanisms elaborated and its locations identified. At least 8 hardware components for maintenance of automated weather stations identified and procured |  | Existing mechanisms of Drought Early Warning System (DEWS) located in Uzhydromet and at Drought Monitoring Center were upgraded and adapted to Amudarya downstream condition. DEWS provides both quantitative and qualitative water availability assessment for Amudarya specific cross-sections with lead time of 3 months. Validity of the assessments varies from 70 to 100% | S
| At least 40% of Dekhkan farmers and pastoralists of Karakalpak region are served by science-based extension (Outcome 1) |  | At least 5,000 (at least 20% of women) stakeholders targeted by science-based extension services trained within trainings and workshops. |  | Two Extension Service Centers established and operationalized. 5,963 (20 % of women) representatives of local communities in the projetc's pilot districts (in Kegeili, Kanlikul, Chimbay, Takhtakupir and Muynak districts) are aware on set of climate change adaptation services available and innovative agro conservation and water saving practices. | S
| At least 3 Field School/Extension established and delivered training in adaptation practices to farmers and pastoralists (Outcome 1) |  | Concept of establishing science-based extension services for subsistence dekhan farmers developed |  | Concept of establishing science-based extension services for subsistence dekhan farmers developed and is implemented by 2 Extension Service Centers established. 93 potential employees of Extension Service Centers to be further established in 3 pilot districts trained. | S
| At least 20% of targeted Dekhkan beneficiaries are female (Outcome 1) |  | At least 15,000 stakeholders and end-users (50% of women) are aware of the automated hydro-meteorological observation network |  | 15,000 stakeholders in Karakalpakstan and overall in Uzbekistan, and 1,500 direct end-users (20%) in 5 pilot districts were informed about the automated hydro-meteorological observation network through demo-workshops, quarterly bulletins, web-resources and wide mass media coverage (TV and radio broadcasting, and press) | MS
| At least 40,000 Dekhan farmers have adopted climate resilient conservation agriculture practices by end of the project (Output 2.1) |  | At least 5,000 stakeholders (30% of women) provided with printing and publications associated with the climate resilient conservation agriculture practices |  | 5,963 (20 % of women) representatives of local communities from five pilot districts (in Kegeili, Kanlikul, Chimbay, Takhtakupir and Muynak districts) provided with 4 publications, 4 informative quarterly bulletins on agro conservation and water saving practices and crop diversification options within 15 workshops, meetings, through Extension Service Centers and round table, 2 press-conferences. | S
| At least 40,000 Dekhan farmers have adopted water saving irrigation practices by end of the project (Output 2.2) |  | At least 5,000 stakeholders (30% of women) trained in application of land leveling, furrow, siphon and drip irrigation systems |  | 217 (24% of women) farmers in 4 project's pilots (Kegeili, Kanlikul, Chimbay and Takhtakupir ) trained through 4 field trainings on adaptation practice including water saving irrigation practices | MS
| Female lead horticulture greenhouses established by mid of 2016 (Outcome 2) |  | At least 500 units of horticulture greenhouse equipment procured; and at least 16,000 households (50% of women) provided with printing and publications associated with the horticulture greenhouse best practices; and female lead horticulture greenhouses established |  | Documentation to procure 500 units of horticulture greenhouse equipment developed based on the identified types and designs of greenhouses applicable to climate conditions of northern areas of Karkalpakstan. 500 potential owners (20% of female) identified based on their social and gender profile. 400 beneficiaries were provided with Informational Guidance to developing greenhouse and hot house business in Karakalpakstan and Recommendations on indoor vegetables growing for Northern Districts of Karakalpakstan published in Karakalpak, Uzbek and Russian. | MS
| Laws on agricultural practices and water management amended and integrate conservation agriculture and water saving techniques by end of 2016 |  | Gaps in existing legal and regulatory framework and required improvements to support well tested farm-based adaptation measures identified. At least 500 stakeholders (30% of women) provided with expertise and technical assistance in development/improvement of legal and regulatory framework to support well tested farm-based adaptation measures for replication and upscale. |  | Study conducted to identify gaps in legal regulatory to supporting the promotion of well-tested farm-based adaptation measures that can be replicated and up-scaled, and recommendations on how the gaps can be filled up as well as proposed actions can be integrated into the existing regulations developed. | S
| By end of the project, over 70,000 ha of arid land of Karakalpakstan is covered with saksaul and tamarix plantations and deliver sand stabilization and soil desalinization function (Outcome 3) |  | Technical assistance in best practices on development of management plan for sand stabilization and soil desalinization and comprehensive landscape rehabilitation provided at least 5,000 ha of lands. At least 10,000 of local saksaul and tamarix plantings procured and planted at fields, and at least 8 survey equipment to monitor sand stabilization and soil desalinization based on wind models and comprehensive landscape rehabilitation procured. |  | The most problematic areas with poor or no vegetation coverage at 5 project pilot districts were identified with use of data derived from TERRA MODIS platform as a prerequisite to quantify yearly demand for saplings (approx. 70 mln). Sand stabilization and pastures reclamation works were initiated at over 80 ha of the two most exposed to land degradation/desertification pilot districts (Muynak and Takhtakupir) as a test prior initiation works over 1,000 ha. | MS
| At least 20,000 people organized in at least 10 cooperatives at the khokimiyat and makhalla levels and participate in sand stabilization plantation scheme (Outcome 3) |  | At least one community management scheme for planting and maintenance as community employment scheme for landscape level adaptation developed. At least 10,000 stakeholders (50% of women) trained in community management for planting and maintenance for landscape level adaptation. |  | A concept on establishing the cooperative management scheme for implementation of the required landscape adaptation measures developed. Three hands-on workshops on landscape adaptation measures/approaches and their implementation were conducted at three pilot districts (Muynak, Takhtakupir and Kanlikul), at which 132 members of local communities (51% of women) attended. Sand stabilization and soil moisture saving works were initiated at 2 the most vulnerable pilot districts (Muynak and Takhtakupir) based on cooperative management approaches piloting at 80 ha (30 ha for sand stabilization and 50 ha for pasture reclamation) was implemented by 2 local forestry farms. | MS
| At least 10 community organizations (at least 5 female groups and village organizations) at khokimiyat and makhalla level have clear mandates, institutional capacities and skills and manage saksaul and tamarix plantations by end of 2019 (Outcome 3) |  | At least 10,000 stakeholders (30% of women) provided with the printing and publications associated with the cooperative management system for landscape rehabilitation and management to enhance community control and ownership, and trained in its application |  | 5,963 (20 % of women) representatives of local communities from five project's pilots (in Kegeili, Kanlikul, Chimbay, Takhtakupir and Muynak districts) provided with 2 recommendations, 4 informative quarterly bulletins on cooperative management system for landscape rehabilitation and management to enhance community control and ownership within 15 workshops, meetings, through Extension Service Centers and round table, 2 press-conferences. | MS
| At least two sets of lessons learned bulletins produced and covered successful climate resilient agronomic and water saving measures (Outcome 4) |  | At least 3 lessons learned for climate resilient agricultural and pastoral production systems in arid lands from stakeholders through providing them with provided with technical assistance in analysis and documentation of those lessons learned |  | The lessons focused on DEWS, agro conservation and water saving practices, and landscape adaptation measures are captured and formulated to be finalized and documented by the end of 2017 | S
| At least 5 farmland demonstration meetings covered by the local and national media for adaptation advocacy (Outcome 4) |  | At least 2 farm and pasture land demonstration meetings conducted with participation of national, local authorities, media and communities, and associated printing and publications produced and disseminated |  | 15 demonstration meetings and workshops (535 people; 26% of female) on climate change adaptation and resilience and targeted at local communities conducted. Information on the events posted at newspapers and web-resources, and broadcasted via national and regional radio and TV. | S
[5 empty] | Overall Rating | S
| Name: | Prof. Victor Chub, National Project Coordinator of Adaptation Project in Uzbekistan
| Email: | Uzhymet@meteo.uz
| Please justify your rating and address the following points: 1. Indicate trends, both positive and negative, in achievement of outcomes as per the project indicators. 2. Detail critical risks that have affected progress. 3. Outline response to MTR undertaken this reporting period. 4. Outline action plan to address projects with a rating of HU, U or MU. Please keep your input to 1200 words |  | The overall rating is Satisfactory. The project is going on to perform good managerial and operational abilities . Spite the certain lack of coherence of project activities and inconsistent follow-up observed it fulfilled a number of essentials outputs and achieved results being following the project's key milestones like: - completion of the installation of 10 automated meteo-stations in Karakalpakstan; - adaptation of drought early warning system in the lower Amudarya delta; - 80 mechanics and farmers from 5 pilot districts trained on land laser levelling (covered 160 ha) with use of 7 sets of laser leveling equipment provided within field hands-on workshops conducted; - 211 beneficiaries (82 women of 39%) familiarized with sand stabilization, pasture reclamation and forest belt planting though 5 thematic workshops; - encroaching sand stabilization works are underway and cover 30 ha in Muynak pilot region; - pastures reclamation activity are underway and cover over 50 ha in Takhtakupir district - the project communication strategy developed and is being implemented; - 2 Extension Service Centers established; - 963 direct beneficiaries (245 or 25% women) and up to 5,000 indirect beneficiaries (20% women) raised their awareness and increased knowledge through dissemination of information and sharing knowledge within 13 thematic workshops covered all 5 pilot districts. The systematic and well balanced planning of the project thematic activities and efficient planning of procurement works by duly taking into account their complexity and seasonality factors should be ensured to make project implementation more seamless and tangible.
Rating Definitions
|  |  | Highly Satisfactory (HS) | Project actions/activities planned for current reporting period are progressing on track or exceeding expectations to acheive all major outcomes/outputs for given reporting period, without major shortcomings. The project can be presented as “good practice”.
|  |  | Satisfactory (S) | Project actions/activities planned for current reporting period are progressing on track to achieve most of its major outcomes/outputs with only minor shortcomings.
|  |  | Marginally Satisfactory (MS) | Project actions/activities planned for current reporting period are progressing on track to achieve most major relevant outcomes/outputs, but with either significant shortcomings or modest overall relevance.
|  |  | Marginally Unsatisfactory (MU) | Project actions/activities planned for current reporting period are not progressing on track to achieve major outcomes/outputs with major shortcomings or is expected to achieve only some of its major outcomes/outputs.
|  |  | Unsatisfactory (U) | Project actions/activities planned for current reporting period are not progressing on track to achieve most of its major outcomes/outputs.
|  |  | Highly Unsatisfactory (U) | Project actions/activities planned for current reporting period are not on track and shows that it is failing to achieve, and is not expected to achieve, any of its outcomes/outputs.

## Project Indicators
PROJECT Indicators
Please provide all indicators being tracked for the project as outlined in the project document
Type of Indicator (indicators towards Objectives, Outcomes, etc…)
Type of Indicator | Indicator | Baseline | Progress since inception | Target for Project End
Outcome 1 | Indicator 1.1.1: Number of automated met stations for field data collection and transmission | Currently, there is no automated hydro-meteorological stations in Karakalpakstan | 10 meteorological stations automatized and commissioned. 2 Doppler water discharge meters installed on 2 key water gauge stations (Tuyamuyn and Kipchak). | 8 automated hydro-meteorological stations and 2 Doppler water meters installed
| Indicator 1.2.1: Coverage of hydro-meteorological observation network on km2 | Currently, there is no spatial coverage of automated hydro-meteorological observation network | 10 meteorological stations (instead of initially planned 8 meteo stations) automatized and are operational in testing mode. They represent the whole hydro-meteorological observation network of the Republic of Karakalpakstan, and therefore will cover as minimum 40,000 km2 of the region | At least 40,000 km2 of the Karakalpakstan region covered by automated hydro-meteorological observation network
| Indicator 1.3.1: Lead time for drought early warning | Currently, drought early warning does not exists | Existing mechanisms of Drought Early Warning System (DEWS) located in Uzhydromet and at Drought Monitoring Center were upgraded and adapted to Amudarya downstream condition. DEWS provides both quantitative and qualitative water availability assessment for Amudarya specific cross-sections with warning lead time of 3 months. Validity of the assessments varies from 70 to 100% | Seasonal and biweekly
| Indicator 1.4.1: % Dekhkan farmers (% female Dekhkan farmers) receiving extension services to introduce farm-based climate risk management measures | Uzbekistan does not yet have a science-based extension system in place | At least 15% of the project beneficiaries (farmers, dekhans, households and rural communities) can receive the required consultancy services from 2 Extension Service Centers established (Hub in Nukus, i.e. capital of Karakalpakstan, and in Kegely pilot district). As of today, 5,963 (20 % of women) representatives of local communities from five project's pilots (in Kegeili, Kanlikul, Chimbay, Takhtakupir and Muynak districts) received information on climate change adaptation services available and innovative agro conservation and water saving practices through those 2 Extension Service facilities. | At least 40% of Dekhkan farmers and pastoralists of Karakalpakstan region served by science-based extension
| Indicator 1.4.2: # of Field School/Extension delivering training in adaptation practices to farmers and pastoralists. | Currently, no Field School/Extension outlets exist in Karakalpakstan | 2 Extension Service Centers established (Hub in Nukus, i.e. capital of Karakalpakstan, and in Kegely pilot district) conducted field trainings on best adaptation practices, e.g. by land laser leveling technique that were attended by 217 (24% of women) farmers from project pilot districts. | At least 3 Field School/Extension established to deliver training in adaptation practices to farmers and pastoralists by the fourth year (2017)
Outcome 2 | Indicator 2.1.1: # of dekhkan farmers adopted conservation agriculture practices (e.g. low till, mixed cropping, fodder production, and residue crop soil) | It is estimated that 7-10% of farmers practice climate resilient conservation agriculture practices | 5,963 (20 % of women) representatives of local communities from five project's pilots (in Kegeili, Kanlikul, Chimbay, Takhtakupir and Muynak districts) provided with 4 publications, 4 project's informative quarterly bulletins on agro conservation and water saving practices and crop diversification options within 15 workshops, meetings, through Extension Service Centers and round table, 2 press-conferences. | At least 40,000 Dekhan farmers have adopted climate resilient conservation agriculture practices
| Indicator 2.2.1: # of dekhkan farmers adopted water saving irrigation practices (e.g. land levelling, furrow and drip irrigation systems) | It is estimated that 3-5% of farmers practice water saving practices | 217 (24% of women) farmers in 4 project's pilots (Kegeili, Kanlikul, Chimbay and Takhtakupir ) trained through 4 field trainings on adaptation practice including water saving irrigation practices | At least 40,000 Dekhan farmers have adopted water saving irrigation practices
| Indicator 2.3.1: Number of female led horticulture greenhouses established | In Karakalpakstan, currently no horticulture greenhouses are led by women farmers (This is currently being verified as part of inception phase activities) | 100 female candidates (20% of 500 beneficiaries) identified based on their social and gender profile to be recipients of greenhouse equipment. Types and designs of greenhouses applicable to climate conditions of northern areas of Karkalpakstan identified. Documentation to procure 500 units of horticulture greenhouse equipment developed. | At least five woman-led horticulture greenhouses established by end of second year (out of 12 greenhouses that will be delivered in the project)
| Indicator 2.4.1: # of legal acts and regulations enacted to support well tested farm-based adaptation measures. | Legal acts and regulations that exist do not provide conditions that facilitate take-up of farm-based adaptation | Gaps in legal regulatory to supporting the promotion of well-tested farm-based adaptation measures that can be replicated and up-scaled identified and recommendations on their integration into the existing regulations formulated | At least three laws/regulations on agricultural practices and water management amended and integrated regulations on the adoption of conservation agriculture and water saving techniques and technologies on the farms by end of the third year
Outcome 3 | Indicator 3.1.1: # of ha with saksaul and tamarix plantations to deliver sand stabilization and soil desalinization function. | There have been only sporadic and largely unsuccessful attempts of sand stabilization | The most problematic areas with poor or no vegetation coverage at 5 project pilot districts were identified with use of data derived from TERRA MODIS platform as a prerequisite to quantify yearly demand for saplings (approx. 70 mln). Sand stabilization and pastures reclamation works were initiated at over 80 ha of the two most exposed to land degradation/desertification pilot districts (Muynak and Takhtakupir) as a test prior initiation works over 1,000 ha. | Over 70,000 ha of arid land of Karakalpakstan is covered with saksaul and tamarix plantations and deliver sand stabilization and soil desalinization function
| Indicator 3.2.1: # of Dekhkan farmer and pastoral community members involved in landscape level adaptation measures (e.g. saksaul and tamarix planting) through local employment programme. | Currently, there is no systemic engagement of dekhan farmers and pastoral community for landscape land management | 132 members of local communities (51% of women) were trained within 3 hands-on workshops on landscape adaptation measures/approaches and their implementation conducted at 3 pilot districts (Muynak, Takhtakupir and Kanlikul). Sand stabilization and soil moisture saving works were initiated at 2 the most vulnerable pilot districts (Muynak and Takhtakupir) based on cooperative management approaches piloting at 80 ha (30 ha for sand stabilization and 50 ha for pasture reclamation) being implemented by 2 local communities jointly with 2 local forestry farms. | At least 20,000 people organized in at least 10 cooperatives at the khokimiyat and makhalla levels and participate in sand stabilization plantation scheme
| Indicator 3.3.1: # of cooperatives established at Khokimiyat and Makhalla levels for community management of sand stabilising plantations. | Cooperatives are a new mechanism that has not been tested in the country, and hence, there is currently none. | A concept on establishing the cooperative management scheme for implementation of the required landscape adaptation measures developed. Moreover, 5,963 (20% of women) representatives of local communities from five project's pilots (in Kegeili, Kanlikul, Chimbay, Takhtakupir and Muynak districts) provided with 2 recommendations, 4 project's informative quarterly bulletins on cooperative management system for landscape rehabilitation and management to enhance community control and ownership within 15 workshops, meetings, through Extension Service Centers and round table, 2 press-conferences. | At least 10 community organizations (at least 5 female groups and village organizations) at khokimiyat and makhalla level have clear mandates, institutional capacities and skills and manage saksaul and tamarix plantations by end of the fourth year
Outcome 4 | Indicator 4.1.1: # of documented good practices of agronomic and water saving measures. | None | 5 good practices were selected and documented in project publications: greenhouses and indoor growing of vegetables, improving water content in soils, salt tolerant plants growing in arid lands, seeds and sapling growing in nurseries, etc. | At least two sets of bulletins published including information about results of inventory of all tested agronomic and water saving measures and successful practices mapped out
| Indicator 4.2.1: # of lessons learned bulletins disseminated through printed and web-based media. | None | The lessons focused on DEWS, agro conservation and water saving practices, and landscape adaptation measures are captured and formulated to be finalized and documented by the end of 2017 | At least two sets of lessons learned bulletins produced covering successful climate resilient agronomic and water saving measures
| Indicator 4.3.1: # of farm and pasture land demonstration meetings covered by media and attended by national and local authorities | None | 15 demonstration meetings and workshops (535 people; 26% of female) on climate change adaptation and resilience and targeted at local communities conducted. Information on the events posted at newspapers and web-resources, and broadcasted via national and regional radio and TV. | At least 5 farmland demonstration meetings covered by the local and national media for adaptation advocacy

## Lessons Learned
QUALITATIVE MEASURES and LESSONS LEARNED
Please complete the following section every reporting period
Implementation and Adaptive Management | Response
What implementation issues/lessons, either positive or negative, affected progress? | Commitment and ownership of project activities by all beneficiaries are crucial for achieving progress and success in project implementation. Late approval and disbursement of the 2nd tranche. Turnover of project staff resulted in periodic capacity depletion. Insufficient engagement of project team in the field works in Karakalpakstan with regards to components 2 and 3.
Were there any delays in implementation? If so, include any causes of delays. What measures have been taken to reduce delays? | Activities of seasonal nature should be planned with ample lead time with considering and ensuring timely and duly delivery of all required inputs.
Describe any changes undertaken to improve results on the ground or any changes made to project outputs (i.e. changes to project design) | Given the launch of the Joint Programme in 2016, changes in project management structure to apply programmatic and integrated approach to project activities implementation by the Adaptation project and the UN Joint Programme (Phase II) in the Aral See region (Karakalpakstan, including at least 2 common pilot districts).
How have gender considerations been taken into consideration during the reporting period? What have been the lessons learned as a consequence of inclusion of such considerations on project performance or impacts? | 100 female candidates (20% of 500 beneficiaries) were identified based on their social and gender profile to be recipients of greenhouse equipment. The project is collecting gender-disaggregated data and information; considering gender mainstreaming in all project activities and project reporting with providing relevant evidence.
Please complete the following section at mid-term and project completion
Lessons for Adaptation | Response
Climate Resilience Measures
What have been the lessons learned, both positive and negative, in implementing climate adaptation measures that would be relevant to the design and implementation of future projects/programmes for enhanced resilience to climate change? | Design of the project should be done in clear language that is understandable by various stakeholders (decision makers, local authorities and local communities). It shall be built on relevant studies and reflect the corresponding lessons learned. Project activities focused on adaptation measures to be implemented at the spot shall consider the seasonal aspects and to be integrated into the existing planning, institutional, financial and organizational processes and procedures. Room should be provided for piloting innovative solutions having potential for dissemination beyond the project implementation cycle with ensuring the national ownership.
What is the potential for the climate resilience measures undertaken by the project/programme to be replicated and scaled up both within and outside the project area? | Products of the Drought Early Warning System have substantial potential for mitigation of drought or low water availability impacts. Agro conservation and water saving measures demonstrated and proved to be effective and efficient will result in greater resource saving and income generation.
Concrete Adaptation Interventions
What have been the lessons learned, both positive and negative, in implementing concrete adaptation interventions that would be relevant to the design and implementation of future projects/programmes implementing concrete adaptation interventions? | Any intervention should be well-balanced in terms of its affordability and ambition. Adaptation interventions are both convincing and promising, giving clear understanding of the nature of and timeframe for the adaptation measure benefits.
What is the potential for the concrete adaptation interventions undertaken by the project/programme to be replicated and scaled up both within and outside the project area? | The well-teased and proven agro-conservation and water saving technologies and best practices have a significant potential for replication and scaling-up within the project implementation cycle and beyond as those are highly demanded by rural stakeholders given the increasing aridity of climate and water stress in this region as well as due to their result in reducing/avoiding potential monetary losses and potential for income generation, strengthening food security and health improving benefits.
Community/National Impact
What would you consider to be the most successful aspects for the target communities? | Rural communities involvement in landscape level adaptation measures (e.g. saksaul and tamarix planting) through local employment programme is the most complicated activity to be implemented within the project course but if it succeeds, important environment and social benefits as well as their greater resilience to climate change will be achieved
What measures are/have been put in place to ensure sustainability of the project/program results? | Greater engagement and stronger ownership of all stakeholders, including local authorities and self-government shall be strengthened within all project activities using various approaches and tools (demo meetings, project Boards, round tables, meetings, discussions and consultations)
What measures are being/could have been put in place to improve project/program results? | Programmatic and integrated approach was applied to project activities implementation through joining efforts of the Adaptation project and the UN Joint Programme (Phase II) in the Aral See region (Karakalpakstan, including at least 2 common pilot districts) given the launch of the Joint Programme in 2016. This allows to cover bigger number of beneficiaries in this region with combining and integrating the adaptation and development activities.
Knowledge Management
How has existing information/data/knowledge been used to inform project development and implementation? What kinds of information/data/knowledge were used? | Technical specifications for automated hydrometeorological equipment were developed as being based on historical meteorological and hydrological data. Adaptation of Drought Early Warning System to Amudarya downstream conditions was provided with help of historical measured data series of precipitation and air temperature. Most problematic territories with poor or no vegetation were identified by GIS technologies with MODIS remote sense data (NDVI) used.
If learning objectives have been established, have they been met? Please describe. | Outlining and establishment of the project's learning objectives are formulated in the project's communication strategy that was developed in 2016.
Describe any difficulties there have been in accessing or retrieving existing information (data or knowledge) that is relevant to the project. Please provide suggestions for improving access to the relevant data. | Project was faced some difficulties with accessing the social and economic data related to local communities or farming as such statistics is poor or not available. Local communities and farmers are driven by sporadically planning, and therefore have no knowledge or interest in collecting the data that might help with the planning based on cost-benefit analysis. One of the project's objective is to change the mind of the targeted groups and convince in efficiency of advantages of the long-term planning based on cost-benefit analysis.
Has the identification of learning objectives contributed to the outcomes of the project? In what ways have they contributed? | Learning of relevance and potential impacts related to seasonal aspects of adaptation activities (agro-conservation, land laser levelling, landscape adaptation activities) to be implemented in rural areas resulted in more focused and better planning and implementation of project activities in pilot districts to achieve the expected outputs and outcomes

## Results Tracker
Results Tracker for Adaptation Fund (AF) Projects
Goal: Assist developing-country Parties to the Kyoto Protocol that are particularly vulnerable to the adverse effects of climate change in meeting the costs of concrete adaptation projects and programmes in order to implement climate-resilient measures. Impact: Increased resiliency at the community, national, and regional levels to climate variability and change.
Important: Please read the following guidance document (also posted on the Adaptation Fund website) before entering your data
Link: http://www.adaptation-fund.org/sites/default/files/Results%20Framework%20and%20Baseline%20Guidance%20final.pdf
Adaptation Fund Strategic Results Framework
Project ID | 82613
Implementing Entity | UNDP
Type of implementing entity | MIE
Country | Uzbekistan
Region | Eastern Europe
Sector | Agriculture
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Impact: Increased resiliency at the community, national, and regional levels to climate variability and change | Core Indicator: No. of beneficiaries |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project
|  | Total | 0 | 0 | 0 | Total | 40000 | 20000 | 20000 | Total | 5963 | 963 | 5000 | Total
|  | % of female beneficiaries | 0% | 0% | 0% | % of female beneficiaries | 20% | 20% | 20% | % of female beneficiaries | 20% | 25% | 20% | % of female beneficiaries
|  | % of Youth beneficiaries |  |  |  | % of Youth beneficiaries |  |  |  | % of Youth beneficiaries |  |  |  | % of Youth beneficiaries
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 1: Reduced exposure to climate-related hazards and threats | Indicator 1: Relevant threat and hazard information generated and disseminated to stakeholders on a timely basis | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness
|  | Total | 0 | Drought | 1: Ineffective | Total | 10000 | Drought | 4: Effective | Total | 400 | Drought | 2: Partially effective | Total
|  | % of female targeted | 0% |  |  | % of female targeted | 20% |  |  | % of female targeted | 20% |  |  | % of female targeted
Output 1.1 Risk and vulnerability assessments conducted and updated | Indicator 1.1: No. of projects/programmes that conduct and update risk and vulnerability assessments | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
2
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
Output 1.2 Targeted population groups covered by adequate risk reduction systems | Core Indicator 1.2: No. of Early Warning Systems | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard | Drought | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  | 0 |  | Geographical coverage |  | 1 | 3: Dissemination and communication | Geographical coverage | Regional | 1 | 3: Dissemination and communication | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities |  |  |  | Number of municipalities | 3 |  |  | Number of municipalities | 1 |  |  | Number of municipalities
|  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 2: Strengthened institutional capacity to reduce risks associated with climate-induced socioeconomic and environmental losses | Indicator 2: Capacity of staff to respond to, and mitigate impacts of, climate-related events from targeted institutions increased | Number of staff targeted |  | Sector | Capacity level | Number of staff targeted |  | Sector | Capacity level | Number of staff targeted |  | Sector | Capacity level | Number of staff targeted |  | Sector | Capacity level
|  | Total | 0 |  |  | Total | 50 | Agriculture | 3: Medium capacity | Total | 20 | Agriculture | 3: Medium capacity | Total
|  | % of female targeted |  |  |  | % of female targeted | 20% |  |  | % of female targeted | 20% |  |  | % of female targeted
Output 2.1 Strengthened capacity of national and sub-national centres and networks to respond rapidly to extreme weather events | Indicator 2.1.1: No. of staff trained to respond to, and mitigate impacts of, climate-related events | Total staff trained | % of female staff trained | Type |  | Total staff trained | % of female staff trained | Type |  | Total staff trained | % of female staff trained | Type |  | Total staff trained | % of female staff trained | Type
|  | 0 |  |  |  | 50 | 20% | Public |  | 20 | 20% | Public
| Indicator 2.1.2: No. of targeted institutions with increased capacity to minimize exposure to climate variability risks | Type | Scale | Sector | Capacity level | Type | Scale | Sector | Capacity level | Type | Scale | Sector | Capacity level | Type | Scale | Sector | Capacity level
[6 empty] | Public | Local | Agriculture | 3: Medium capacity | Public | Local | Agriculture | 2: Low capacity
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 3: Strengthened awareness and owernship of adaptation and climate risk reduction processes | Indicator 3.1: Increase in application of appropriate adaptation responses | Percentage of targeted population applying adaptation measures |  | Sector |  | Percentage of targeted population applying adaptation measures |  | Sector |  | Percentage of targeted population applying adaptation measures |  | Sector |  | Percentage of targeted population applying adaptation measures |  | Sector
|  | 0% |  | Agriculture |  | 100 |  | Agriculture |  | 15 |  | Agriculture
Output 3: Targeted population groups participating in adaptation and risk reduction awareness activities | Indicator 3.1.1: Percentage of targeted population awareness of predicted adverse impacts of climate change, and of appropriate responses | No. of targeted beneficiaries | % of female participants targeted | Level of awareness |  | No. of targeted beneficiaries | % of female participants targeted | Level of awareness |  | No. of targeted beneficiaries | % of female participants targeted | Level of awareness |  | No. of targeted beneficiaries | % of female participants targeted | Level of awareness
|  | 0 | 0% | 1: Aware of neither |  | 40000 | 20% | 4: Mostly aware |  | 5963 | 20% | 3: Partially aware
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Target performance at completion |  |  |  | Performance at completion
Outcome 4: Increased adaptive capacity within relevant development sector services and infrastructure assets | Indicator 4.1: Increased responsiveness of development sector services to evolving needs from changing and variable climate | Project/programme sector | Geographical scale | Response level |  | Project/programme sector | Geographical scale | Response level |  | Project/programme sector | Geographical scale | Response level |  | Project/programme sector | Geographical scale | Response level
|  | Agriculture | Local | 2: Partially responsive (Lacks most elements) |  | Agriculture | Regional | 3: Moderately responsive (Some defined elements) |  | Agriculture | Local | 2: Partially responsive (Lacks most elements)
| Core Indicator 4.2: Assets produced, developed, improved or strengthened | Sector | Targeted asset | Changes in asset (quantitative or qualitative) |  | Sector | Targeted asset | Changes in asset (quantitative or qualitative) |  | Sector | Targeted asset | Changes in asset (quantitative or qualitative) |  | Sector | Targeted asset | Changes in asset (quantitative or qualitative)
|  | Agriculture | 2: Physical asset (produced/improved/strenghtened) | 2: Somewhat improved |  | Agriculture | 2: Physical asset (produced/improved/strengthened) | 3: Moderately improved |  | Agriculture | 2: Physical asset (produced/improved/strengthened) | 2: Somewhat improved
|  | Water management | 2: Physical asset (produced/improved/strenghtened) | 2: Somewhat improved |  | Water management | 2: Physical asset (produced/improved/strengthened) | 3: Moderately improved |  | Water management | 2: Physical asset (produced/improved/strengthened) | 2: Somewhat improved
|  | Disaster risk reduction | 2: Physical asset (produced/improved/strenghtened) | 1: Not improved |  | Disaster risk reduction | 2: Physical asset (produced/improved/strenghtened) | 3: Moderately improved |  | Disaster risk reduction | 1: Health and Social Infrastructure (developed/improved) | 2: Somewhat improved
Output 4: Vulnerable development sector services and infrastructure assets strengthened in response to climate change impacts, including variability | Indicator 4.1.1: No. and type of development sector services to respond to new conditions resulting from climate variability and change | Number of services | Type |  | Sector | Number of services | Type |  | Sector | Number of services | Type |  | Sector | Number of services | Type |  | Sector
|  | 0 | Multi-community |  | Agriculture | 7 | Multi-community |  | Agriculture | 5 | Community |  | Agriculture
|  | 0 | Multi-community |  | Water management | 5 | Multi-community |  | Water management | 3 | Community |  | Water management
|  | 0 | Multi-community |  | Disaster risk reduction | 3 | Multi-community |  | Disaster risk reduction | 1 | Community |  | Disaster risk reduction
|  | Baseline information |  |  |  | Targeted performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 5: Increased ecosystem resilience in response to climate change and variability-induced stress | Indicator 5: Ecosystem services and natural resource assets maintained or improved under climate change and variability-induced stress | Natural resource improvement level |  | Sector | Type | Natural resource improvement level |  | Sector | Type | Natural resource improvement level |  | Sector | Type | Natural resource improvement level |  | Sector | Type
|  | 2: Partially effective |  | Agriculture | land | 2: Partially effective |  | Agriculture | land | 2: Partially effective |  | Agriculture | land
Output 5: Vulnerable ecosystem services and natural resource assets strengthned in response to climate change impacts, including variability | Core Indicator 5.1: Natural Assets protected or rehabilitated | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Forests |  | ha rehabilitated | 1: Ineffective | Forests | 70000 | ha rehabilitated | 3: Moderately effective | Forests | 80 | ha rehabilitated | 2: Partially effective
|  | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Cultivated land/Agricultural land |  | ha protected | 1: Ineffective | Cultivated land/Agricultural land | 20000 | ha protected | 4: Effective | Cultivated land/Agricultural land | 28 | ha protected | 2: Partially effective
|  | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Baseline information |  |  |  | Targeted performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 6: Diversified and strengthened livelihoods and sources of income for vulnerable people in targeted areas | Indicator 6.1: Increase in households and communities having more secure access to livelihood assets | No. of targeted households | % of female headed households | Improvement level |  | No. of targeted households | % of female headed households | Improvement level |  | No. of targeted households | % of female headed households | Improvement level |  | No. of targeted households | % of female headed households | Improvement level
|  | 16000 | 20% | 1: No improvement |  | 16000 | 20% | 4: High improvement |  | 1490 | 20% | 2: Limited improvement
| Indicator 6.2: Increase in targeted population's sustained climate-resilient alternative livelihoods | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
|  | 0 | 0% | From 0 to 0.5% | Agribusiness | 16000 | 20% | From 10% to 20% | Agribusiness | 1490 | 20% | From 1% to 5% | Agribusiness
|  | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
|  | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
|  | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
Output 6 Targeted individual and community livelihood strategies strengthened in relation to climate change impacts, including variability | Indicator 6.1.1: No. and type of adaptation assets created or strengthened in support of individual or community livelihood strategies | Number of Assets | Type of Assets | Sector | Adaptation strategy | Number of Assets | Type of Assets | Sector | Adaptation strategy | Number of Assets | Type of Assets | Sector | Adaptation strategy | Number of Assets | Type of Assets | Sector | Adaptation strategy
|  | 0 | Physical capital | Agriculture | Community-based adaptation | 595 | Physical capital | Agriculture | Community-based adaptation | 7 | Physical capital | Agriculture | Community-based adaptation
| Core Indicator 6.1.2: Increased income, or avoided decrease in income | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 7: Improved policies and regulations that promote and enforce resilience measures | Indicator 7: Climate change priorities are integrated into national development strategy | Integration level |  |  |  | Integration level |  |  |  | Integration level |  |  |  | Integration level
|  | 1: None |  |  |  | 3: Some |  |  |  | 2: Most not integrated
Output 7:Improved integration of climate-resilience strategies into country development plans | Indicator 7.1: No. of policies introduced or adjusted to address climate change risks | No. of Policies introduced or adjusted | Sector | Scale | Type | No. of Policies introduced or adjusted | Sector | Scale | Type | No. of Policies introduced or adjusted | Sector | Scale | Type | No. of Policies introduced or adjusted | Sector | Scale | Type
|  | 0 | Agriculture | Regional | Public policy | 3 | Agriculture | Regional | Public policy | 0 | Agriculture | Regional | Public policy
| Indicator 7.2: No. of targeted development strategies with incorporated climate change priorities enforced | No. of Development strategies | Regulation |  | Effectiveness | No. of Development strategies | Regulation |  | Effectiveness | No. of Development strategies | Regulation |  | Effectiveness | No. of Development strategies | Regulation |  | Effectiveness
|  | 0 | 1: Not enforced (No elements implemented) |  | 1: Ineffective | 1 | 3: Partially enforced (Some elements implemented) |  | 3: Moderately effective | 1 | 2: Partially not enforced (Most elements not implemented) |  | 2: Partially effective
Glacier lake outburst flood
|  | Inland flooding | fr | biological assets |  | Company policy | 5: Fully enforced (All elements implemented)
|  | Salinization | Decrease | land |  | Communication & Information policy | 4: Enforced (Most elements implemented)
|  | Drought | Same | water areas |  | Defense policy | 3: Partially enforced (Some elements implemented)
|  | Wind |  | subsoil assets | increased adpative capacity | Domestic policy | 2: Partially not enforced (Most elements not implemented) |  | Agribusiness
|  | Coastal flooding |  | air | achieved | Economic policy | 1: Not enforced (No elements implemented) |  | Agricultural-related | Financial capital
|  | Storm surge | Please choose |  | enhanced level of protection | Education policy |  |  | Agriculture | Human capital
|  | Hurricane | Selected | [5 empty] | Aquaculture | Physical capital
|  |  | Not relevant |  |  | 5: All (Fully integrated) |  |  | Construction/repairing business | Social capital
[6 empty] | 4: Most |  |  | Cultivation | Natural capital
[6 empty] | 3: Some |  |  | Fishing | Personal capital
Select | 5: All | Select |  |  | Community | 2: Most not integrated |  | Other | Forestry | Adaptation strategies
1 | 4: Almost all | Private | Type | Yes | Multi-community | 1: None |  | Agriculture | Handicrafts
2 | 3: Half | Public | Scale | No | Departmental |  |  | Coastal management | Livestock production
3 | 2: Some | NGO | Sector |  | National |  |  | Disaster risk reduction | Manufacturing
4 | 1: None |  |  |  |  | 5: Very high improvement | Established | Food security | other
|  | National |  |  |  | 4: High improvement | Maintained | Health | Services
|  | Regional |  |  |  | 3: Moderate improvement | Improved | Urban development | Tourism-related
|  | Local |  |  |  | 2: Limited improvement |  | Water management | Trading
[6 empty] | 1: No improvement |  | Multi-sector
|  | 1 -generated information is irrelevant, and neither the stakeholders reached nor the timeframe managed were achieved | 1: No info transferred on time | 4: High capacity | 5: Fully aware | 5: Highly responsive (All defined elements ) | 5: Fully improved | Roads | 5: Very effective
Asia-Pacific | NIE | 2 -the existence of some challenge in any of the three aspects of the indicator (generation of dissemination, stakeholders reached or timeframe managed) | 2: Somewhat info transferred | 3: Medium capacity | 4: Mostly aware | 4: Mostly responsive (Most defined elements) | 4: Mostly Improved | Gov Buildings | 4: Effective
Latin America and Caribbean | RIE | 3 -relevant information is generated and disseminated to all identified stakeholders on timely basis | 3: Info transferred on time | 2: Low capacity | 3: Partially aware | 3: Moderately responsive (Some defined elements) | 3: Moderately improved | Causeways | 3: Moderately effective
Africa | MIE |  |  | 1: No capacity | 2: Partially not aware | 2: Partially responsive (Lacks most elements) | 2: Somewhat improved | Airports | 2: Partially effective
Eastern Europe |  |  |  |  | 1: Aware of neither | 1: Non responsive (Lacks all elements ) | 1: Not improved | Schools | 1: Ineffective
| ha protected | [6 empty] | Training Centres
| ha rehabilitated | [5 empty] | Monitoring/Forecasting capacity | Hospitals
Afghanistan, Islamic Rep. of | km protected | [5 empty] | Policy/regulatory reform | Drinking water systems
Angola | km rehabilitated | 1: Risk knowledge | 1: No plans conducted or updated |  |  |  | Capacity development | Other
Albania |  | 2: Monitoring and warning service | 2: Undertaking or updating of assessments in progress |  |  | Communication & Information policy | Sustainable forest management
Argentina |  | 3: Dissemination and communication | 3: Risk and vulnterability assessments completed or updated |  |  | Domestic policy | Strengthening infrastructure | 1: Health and Social Infrastructure (developed/improved)
Armenia | Forests | 4: Response capability |  |  |  | Economic policy | Supporting livelihoods | 2: Physical asset (produced/improved/strenghtened)
Antigua and Barbuda | Mangroves |  |  |  |  | Education policy | Mangrove reforestation
Azerbaijan | Coasts |  | From 0 to 0.5% |  |  | Energy policy | Coastal drainage and infrastructure
Burundi | Rangelands |  | From 0.5 to 1% |  |  | Environmental policy | Irrigation system
Benin | Cultivated land/Agricultural land |  | From 1% to 5% |  |  | Foreign policy | Community-based adaptation
Burkina Faso | Catchment area/Watershed/Aquifer |  | From 5% to 10% |  |  | Health policy | Erosion control
Bangladesh | Protected areas/National parks |  | From 10% to 20% |  |  | Housing policy | Soil water conservation
Bulgaria | Other |  | From 20% to 30% |  |  | Human resource policies | Microfinance
Bahrain |  |  | From 30% to 40% |  |  | Information policy | Special Program for women
Bahamas, The |  |  | From 40% to 50% |  |  | Macroeconomic policy | Livelihoods
Bosnia and Herzegovina |  |  | Above 50% |  |  | Monetary policy | Water storage
Belarus | [5 empty] | Population policy | ICT and information dissemination
Belize | [5 empty] | Private policy
Bolivia | [5 empty] | Public policy
Brazil | [5 empty] | Science policy
Barbados | [5 empty] | Social policy
Bhutan |  | 3- relevant information is generated and disseminated to all identified stakeholders on timely basis |  |  |  | Transportation policy
Botswana |  | describe |  |  |  | Urban policy
Central African Republic |  | 2- the existence of some challenge in any of the three aspects of the indicator |  |  |  | Water policy
Chile |  | describe |  |  |  | Other policy
China, People's Republic of |  | 1- generated information is irrelevant and neither the stakeholders reached nor the timeframe managed were achieved
Cote d'Ivoire |  | describe
Cameroon
Congo, Dem. Rep. of
Congo, Republic of
Cook Islands
Colombia
Comoros
Cape Verde
Costa Rica
Cuba
Czech Republic
Djibouti
Dominica
Dominican Republic
Algeria
Ecuador
Egypt
Eritrea
Estonia
Ethiopia
Fiji
Micronesia, Fed. States of
Gabon
Georgia
Ghana
Guinea
Gambia, The
Guinea-Bissau
Equatorial Guinea
Grenada
Guatemala
Guyana
Honduras
Croatia
Haiti
Hungary
Indonesia
India
Iran, Islamic Republic of
Jamaica
Jordan
Kazakhstan
Kenya
Kyrgyz Republic
Cambodia
Kiribati
Saint Kitts and Nevis
Korea, Republic of
Lao People's Democratic Republic
Lebanon
Liberia
Libya
Saint Lucia
Sri Lanka
Lesotho
Lithuania
Latvia
Morocco
Moldova
Madagascar
Maldives
Mexico
Marshall Islands
Macedonia, former Yugoslav Republic of
Mali
Malta
Myanmar
Montenegro
Mongolia
Mozambique
Mauritania
Mauritius
Malawi
Malaysia
Namibia
Niger
Nigeria
Nicaragua
Niue
Nepal
Nauru
Oman
Pakistan
Panama
Peru
Philippines
Palau
Papua New Guinea
Poland
Korea, Dem. People's Rep. of
Paraguay
Romania
Russian Federation
Rwanda
Saudi Arabia
Sudan
Senegal
Solomon Islands
Sierra Leone
El Salvador
San Marino
Serbia
Sao Tome and Principe
Suriname
Slovak Republic
Slovenia
Swaziland
Seychelles
Syrian Arab Republic
Chad
Togo
Thailand
Tajikistan
Turkmenistan
Tonga
Trinidad and Tobago
Tunisia
Turkey
Tuvalu
Tanzania
Uganda
Ukraine
Uruguay
Uzbekistan
Saint Vincent and the Grenadines
Venezuela
Vietnam
Vanuatu
Samoa
Yemen, Republic of
South Africa
Zambia
Zimbabwe
Timor-Leste

## Units for Indicators
Fund Outcome Indicator Units
1. Generation of relevant data, Stakeholders, and Timeliness 2.1. Include both qualitative and quantitative measures of capacity level within targeted institutions 2.2. Number (men and women and other vulnerable groups) 3.1. Use scale from 1 to 5: 5: Fully aware 4: Mostly aware 3: Partially aware 2: Partially not aware 1: Aware of neither predicted adverse impacts of climate change nor of appropriate responses 3.2. Use scale from 1 to 5: 5: All 4: Almost all 3: Half 2: Some 1: None 4.1. Summarize in an overall scale (1-5): 5: Highly responsive (All defined elements ) 4: Mostly responsive (Most defined elements) 3: Moderately responsive (Some defined elements) 2: Partially responsive (Lacks most elements) 1: Non responsive (Lacks all elements ) 4.2. Summarize in an overall scale (1-5): 5: Fully improved 4: Mostly Improved 3: Moderately improved 2: Somewhat improved 1: Not improved 5. Depends on the targeted natural asset: Biological (species): measure through changes in population numbers (dynamics, structure, etc.) Land: measure changes in hectares. Baseline data will be necessary to estimate the change. Supporting indicators baseline and target (as well as contextual information) are needed such as the following: Farmers adopting recommended technologies, Ha. of land improved, Average deforestation rate Etc. Use scale from 1 to 5. 5: Very effective (All elements are present) 4: Effective (Most elements are present) 3: Moderately effective (Some elements are present) 2: Partially effective (Most elements are not present) 1: Ineffective (No elements are present) 6.1. Summarize in an overall scale (1-5): 5: Very high improvement 4: High improvement 3: Moderate improvement 2: Limited improvement 1: No improvement 6.2. Household income by source of livelihood in project area (USD) prior and post project intervention 7. Summarize in an overall scale (1-5). 5: All (Fully integrated) 4: Most 3: Some 2: Most not integrated 1: None
Fund Output Indicator Units
1.1. Number, sector(s) and level(s) of projects or interventions in separate fields of monitoring plan 1.2. Number 2.1.1. Number of staff (male/female) of targeted institutions: a. Obtain baseline information: total number of staff from targeted institutions b. Define target 2.1.2. Number of staff (male/female) of targeted institutions: a. Obtain baseline information: total number of staff from targeted institutions b. Define target: needs to be defined by project proponents 2.2.1. Quantitative: Percentage (includes women – and other vulnerable groups – and men). Qualitative: Adequacy: include direct analysis of major areas; adequacy/effectiveness of systems or analysis of perceptions of populations and institutions. 2.2.2. Number (broken down by gender and, if possible, by vulnerable groups defined in the area of intervention) of people 3.1. Number and type (in separate columns) at local level. 3.2. Number 4.1. Number and type 4. 2. Number and type (entered in separate columns) 5. Number of interventions by type of natural asset and intervention 6.1. Number and type (in separate columns of monitoring plan) 6.2. Income sources per household; description of income source and number of households. 7.1. Number/Sector 7.2. Number; Effectiveness (see previous indicator) through enforcement level.