## Overview
Project Performance Report (PPR)
| Period of Report (Dates) | 25 May 2017 - 02 October 2018
| Project Title: | Developing climate resilience of farming communities in the drought prone parts of Uzbekistan
| Project Summary: | The project objective is to develop climate resilience of farming and pastoral communities in the drought prone parts of Uzbekistan, specifically Karakalpakstan. The project will help the central, regional and local governments and vulnerable farmers and pastoralists to withstand the current and future impacts of climate change: aridification and projected drying of this region that places serious strains on water availability resulting in a decline in land productivity. The project is comprised of four main components: (i) institutional capacity and mechanisms for drought risk management and early warning; (ii) climate resilient agricultural and pastoral production systems; (iii) landscape level approach to adaptation to climate change risks of increased aridity; (iv) knowledge management and awareness raising.
|  |  | Countries | Project Type: |  | GEF Focal Area: | GEF 4 Focal Areas | GEF 2 / 3 Operational Programme: | Overall Rating of the project in the evaluation by the project evaluator: | GEF-4 Focal Area Strategic Program: | GEF-3 Focal Area Strategic Program:
| Database Number: | PIMS 5002 | Afghanistan | FP | Yes | Biodiversity | 1 | 1 | U | BD-SP1-PA Financing | 1: Arid & semi-arid ecosystems
Implementing Entity (IE) [name]: |  | United Nations Development Programme | Albania | MSP | No | Climate Change Adaptation | 2 | 2 | S | BD-SP2-Marine PA | 2: Coastal, marine & freshwater ecosystems
| Type of IE: | MIE | Algeria | EA |  | Climate Change Mitigation | 3 | 3 | MU | BD-SP3-PA Networks | 3: Forest ecosystems
| Country(ies): | Uzbekistan | Angola |  |  | International Waters | 5 | 5 | Good | BD-SP5-Markets | 13: Conservation and Sustainable Use of Biological Diversity Important to Agriculture
Relevant Geographic Points (i.e. cities, villages, bodies of water): |  | Karakalpakstan, including Muynak, Kegeyli, Takhtakupir, Chimbay, and Kanlykol districts | Argentina |  |  | Multiple Focal Area |  |  |  | BD-SP7-Invasive Alien Species(IAS) | 6: Promoting the adoption of renewable energy by removing barriers and reducing implementation costs
[8 empty] | CC-SP2- Industrial EE | 8: Waterbody based operational program
| Project Milestones | [6 empty] | CC-SP3-RE,CC-SP4-Biomass | 9: Integrated Land and Water multiple focal area
| Milestone |  | Bahamas | [6 empty] | CC-SP5-Transport | 10: Contaminants based operational program
AFB Approval Date: |  | 2014-02-10
IE-AFB Agreement Signature Date: |  | 2014-03-07 | [6 empty] | CC-SP6-LULUCF | 12: Integrated Ecosystem Management
Start of Project/Programme: |  | 2014-05-26 | [6 empty] | Cross cutting capacity building | 14: Persistent Organic Pollutants
Mid-term Review Date (if planned): |  | 2017-10-31
| Terminal Evaluation Date: | 2020-02-01
|  | List documents/ reports/ brochures / articles that have been prepared about the project. | Cyprus
|  | Multi-Year Work Plan and Budget Schedule Quarterly Reports and Annual Report in Atlas Minutes of Project Board meetings Press Releases in mass media Project's Thematic and Knowlegde Products (Executive Summary), iss.1 Project Brief Article about project in national mass media, see at Year 2017 http://www.agriculture.uz/.php?/news/read/336 http://www.uz.undp.org/contt/uzbekistan//home/presscter/pressreleases/2017/07/28/farmers-of-the-republic-of-karakalpakstan-are-invited-to-the-lan/ http://uzdaily.com/articles-id-40599.htm http://af.climatechange.uz/index.php//news/170-training-on-operational-forecasts-of-water-contt-in-the-lower-reaches-of-the-amudarya-river-was-conducted-in-uzhidromet.html www.uz.undp.org http://www.uz.undp.org/contt/uzbekistan//home/presscter/pressreleases/2017/10/14/un-residt-coordinator-visited-karakalpakstan/ http://af.climatechange.uz/index.php//news/169-innovative-approaches-to-provision-of-soil-moisture-storage-were-prested-in-nukus.html Year 2018 http://www.uz.undp.org/contt/uzbekistan//home/presscter/articles/2018/05/29/taming-the-amudaryas-waters.html http://af.climatechange.uz/index.php//news/168-local-communities-will-be-involved-in-implemting-adaptation-measures-at-the-landscape-level-in-karakalpakstan.html https://www.youtube.com/watch?v=aLVvFaWHPc0&feature=youtu.be http://af.climatechange.uz/index.php//news/201-adaptation-measures-at-the-landscape-level-were-prested-to-the-future-agrarians-of-karakalpakstan.html http://www.uz.undp.org/contt/uzbekistan//home/presscter/articles/2018/05/29/taming-the-amudaryas-waters/ | Czech Republic
List the Website address (URL) of project. |  |  | Democratic People's Republic of Korea
|  | http://af.climatechange.uz/index.php/en/ | Democratic Republic of the Congo
Denmark
| Project contacts: |  | Djibouti
National Project Manager/Coordinator |  |  | Dominica
| Name: | Mr. Aleksandr Merkushkin | Dominican Republic
| Email: | aleksandr.merkushkin@undp.org | Ecuador
| Date: | 2014-09-14 | Egypt
| Government DA |  | El Salvador
| Name: | Mr. Bakhriddin Nishonov, First Deputy of General Director of Uzhydromet | Equatoral Guinea
| Email: | uzhymet@meteo.uz | Eritrea
| Date: | 2018-04-12 | Estonia
| Implementing Entity |  | Ethiopia
| Name: | Ms. Natasha Olofinskaya; Ms. Rano Baykhanova | Fiji
| Email: | nataly.olofinskaya@undp.org; rano.baykhanova@undp.org | Finland
| Date: | 2014-05-01 | France
| Executing Agency |  | Gambia
| Name: | Mr. Bakhriddin Nishonov, First Deputy of General Director of Uzhydromet | Georgia
| Email: | uzhymet@meteo.uz | Germany
| Date: | 2018-04-12 | Ghana
| Executing Agency |  | Greece
| Name: | Ms. Malika Nazarova, Deputy Head of Department on Pollutions Monitoring, Uzhydromet | Grenada
| Email: | uzhymet@meteo.uz | Guatemala
| Date: | 2014-09-15 | Guinea
| Executing Agency |  | Guinea Bissau
| Name: | Ms. Natalya Agaltseva, Deputy Head of Department on Pollutions Monitoring, Uzhydromet | Guyana
| Email: | natalya.agaltseva@gmail.com | Haiti
| Date: | 2015-10-10 | Honduras
Hungary
Iceland
India
Indonesia
Iran (Islamic Republic of)
Iraq
Ireland
Israel
Italy
Jamaica
Japan
Jordan
Kazakhstan
Kenya
Kiribati
Kuwait
Kyrgyzstan
Lao People’s Democratic Republic
Latvia
Lebanon
Lesotho
Liberia
Libyan Arab Jamahiriya
Liechtenstein
Lithuania
Luxembourg
Madagascar
Malawi
Malaysia
Maldives
Mali
Malta
Marshall Islands
Mauritania
Mauritius
Mexico
Micronesia, Federated States of
Monaco
Mongolia
Montenegro
Morocco
Mozambique
Myanmar
Namibia
Nauru
Nepal
Netherlands
New Zealand
Nicaragua
Niger
Nigeria
Norway
Oman
Pakistan
Palau
Panama
Papua New Guinea
Paraguay
Peru
Philippines
Poland
Portugal
Qatar
Republic of Korea
Republic of Moldova
Romania
Russian Federation
Rwanda
Saint Kitts and Nevis
Saint Lucia
Saint Vincent and the Grenadines
Samoa
San Marino
Sao Tome and Principe
Saudi Arabia
Senegal
Serbia
Seychelles
Sierra Leone
Singapore
Slovakia
Slovenia
Solomon Islands
Somalia
South Africa
Spain
Sri Lanka
Sudan
Suriname
Swaziland
Sweden
Switzerland
Syrian Arab Republic
Tajikistan
Thailand
The former Yugoslav Republic of Macedonia
Timor-Leste
Togo
Tonga
Trinidad and Tobago
Tunisia
Turkey
Turkmenistan
Tuvalu
Uganda
Ukraine
United Arab Emirates
United Kingdom of Great Britain and Northern Ireland
United Republic of Tanzania
United States of America
Uruguay
Uzbekistan
Vanuatu
Venezuela, Bolivarian Republic of
Viet Nam
Yemen
Zambia
Zimbabwe

## FinancialData
Financial information: cumulative from project start to 02 October 2018
DISBURSEMENT OF AF GRANT FUNDS
How much of the total AF grant as noted in Project Document plus any project preparation grant has been spent to date?
Estimated cumulative total disbursement as of 02 October 2018 | 1636156
Add any comments on AF Grant Funds. (word limit=200) | Since the beginning of the project, US$2,569,189 AF grants have been received through three tranches: first tranche of US$164,863.00, the second one of US$1,029,163.00 and the third tranche of $1,375,163.00 . Since the project start in 2014, cumulative disbursed funds totaled to US$2,356,371.29 as of 02 October 2018. For the reporting period from 25 May 2017 to 02 October 2018, the disbursed amount is US$742,154.13 (US$300,023.7 from the second tranche and US$442,130.43 the from third tranche) and committed funds of the second tranche is US$10,529.94 and committed funds of the third tranche is US$709,684.92. In total, disbursed and committed funds of the third tranche (US$1,151,815.35), since October 2017 to October 2018, represent 84%.
INVESTMENT INCOME | 12395.62
Amount of annual investment income generated from the Adaptation Fund’s grant
EXPENDITURE DATA
List ouput and corresponding amount spent for the current reporting period | ITEM / ACTIVITY / ACTION | AMOUNT
| 1.1 Upgraded observation and monitoring infrastructure (e.g. 2 Doppler water meters, automatization of 8 meteo stations) for effective data receiving and transmission | 270462.12
1.2. Multi-modules platform for integration of data flow from hydro-meteorological observation network to end users
1.3. Drought early warning mechanisms (indicators, gauges, warning distribution mechanisms etc.) to minimize impacts of droughts in place and functional
1.4. Science-based extension services for subsistence dekhan farmers established to assist in farm-based climate risk management, including sub-district, community level Climate Field School/Extension (CFS/E) for direct outreach to farmers and localized training in adaptation practices
| 2.1. 40,000 Dekhkan farmers have adopted climate resilient conservation agriculture practices (e.g. low till, mixed cropping, fodder production, and residue crop soil covering adopted measures adopted at 80,000 ha of dekhkan farms) | 141800
2.2. 40,000 Dekhan farmers have adopted water saving irrigation practices (e.g. land leveling, well management, furrow and drip irrigation systems adopted at 80,000 ha dekhkan farms to improve farm-level drainage and minimize salinization)
2.3. 40% of targeted dekhan farmers have established horticulture greenhouses on 20,000 ha of farms to minimize impacts of droughts on farm production
2.4. Legal and regulatory framework put in place to support well tested farm-based adaptation measures for replication and upscale
| 3.1. Local saksaul and tamarix plantations deliver sand stabilization and soil desalinization function for 1,042,094 ha of farm and adjacent farmlands, based on wind models and comprehensive landscape rehabilitation and management plan | 140939.01
3.2. Community management scheme for planting and maintenance established as community employment scheme for landscape level adaptation
3.3. Cooperative management for landscape rehabilitation and management established to enhance community control and ownership arrangements
| 4.1. Inventory of all tested agronomic and water saving measures to map out successful practices | 78350
4.2. Analysis and lessons learned for climate resilient agricultural and pastoral production systems in arid lands documented and disseminated through printed and web-based publications
4.3. Quarterly farm and pasture land demonstration meetings with participation of national, local authorities, media and communities delivered
| 5. Project management | 110603
| TOTAL | 742154.13
PLANNED EXPENDITURE SCHEDULE
List outputs planned and corresponding projected cost for the upcoming reporting period | ITEM / ACTIVITY / ACTION | PROJECTED COST | Est. Completion Date
| 1.1 Upgraded observation and monitoring infrastructure (e.g. 2 Doppler water meters, automatization of 8 meteo stations) for effective data receiving and transmission | 64505.9017 | 2019-09-25
| 1.2. Multi-modules platform for integration of data flow from hydro-meteorological observation network to end users | 118018.8049 | 2019-09-25
| 1.3. Drought early warning mechanisms (indicators, gauges, warning distribution mechanisms etc.) to minimize impacts of droughts in place and functional | 94921.8133 | 2019-09-25
| 1.4. Science-based extension services for subsistence dekhan farmers established to assist in farm-based climate risk management, including sub-district, community level Climate Field School/Extension (CFS/E) for direct outreach to farmers and localized training in adaptation practices | 38787.3529 | 2019-09-25
| 2.1. 40,000 Dekhkan farmers have adopted climate resilient conservation agriculture practices (e.g. low till, mixed cropping, fodder production, and residue crop soil covering adopted measures adopted at 80,000 ha of dekhkan farms) | 143064.9096 | 2019-09-25
| 2.2. 40,000 Dekhan farmers have adopted water saving irrigation practices (e.g. land leveling, well management, furrow and drip irrigation systems adopted at 80,000 ha dekhkan farms to improve farm-level drainage and minimize salinization) | 230290.6494 | 2019-09-25
| 2.3. 40% of targeted dekhan farmers have established horticulture greenhouses on 20,000 ha of farms to minimize impacts of droughts on farm production | 173763.4427 | 2019-09-25
| 2.4. Legal and regulatory framework put in place to support well tested farm-based adaptation measures for replication and upscale | 17542.0189 | 2019-09-25
| 3.1. Local saksaul and tamarix plantations deliver sand stabilization and soil desalinization function for 1,042,094 ha of farm and adjacent farmlands, based on wind models and comprehensive landscape rehabilitation and management plan | 386898.9722 | 2019-09-25
| 3.2. Community management scheme for planting and maintenance established as community employment scheme for landscape level adaptation | 51164.2218 | 2019-09-25
| 3.3. Cooperative management for landscape rehabilitation and management established to enhance community control and ownership arrangements | 329249.0762 | 2019-09-25
| 4.1. Inventory of all tested agronomic and water saving measures to map out successful practices | 9550.6547 | 2019-09-25
| 4.2. Analysis and lessons learned for climate resilient agricultural and pastoral production systems in arid lands documented and disseminated through printed and web-based publications | 13936.1595 | 2019-09-25
| 4.3. Quarterly farm and pasture land demonstration meetings with participation of national, local authorities, media and communities delivered | 15022.7901 | 2019-09-25
| 5. Project management | 38261.0923 | 2019-09-25
| TOTAL | 1724977.86
ACTUAL CO-FINANCING (If the MTR or TE have not been undertaken this reporting period, DO NOT report on actual co-financing.)
How much of the total co-financing as committed in the Project Document has actually been realized? | From the committed UNDP's cofinancing (USD200,000), $110,147.9 (55%) was used to cover the costs associated with direct project support services such as assistance to procurement, recruitment, payment and admin services.
Estimated cumulative actual co-financing as verified during Mid-term Review (MTR) or Terminal Evaluation (TE). | 80647
Add any comments on actual co-financing in particular any issues related to the realization of in-kind, grant, credits, loans, equity, non-grant instruments and other types of co-financing. (word limit=200) | The MTR of the Project was conducted in September-November 2017. The financial data was taken as of 30 Sep 2017 which makes 40% of 200,000 USD (UNDP cofinancing commitment).

## Risk Assesment
RISK ASSESMENT
IDENTIFIED RISKS
List all Risks identified in project preparation phase and what steps are being taken to mitigate them
Identified Risk | Current Status | Steps Taken to Mitigate Risk
1. Reluctance of farmers or pastoralists to depart from over-irrigation and overutilization of inputs approach towards climate resilient conservation agriculture | Low | The risk was mitigated through number of knowledge sharing and best practice demonstration events conducted by the project. At least 3,395 farmers and householders (18% of women) attended the 18 field hands-on workshops and Field Schools, within which they familiarized with low water availability warning approaches (Drought Early Warning Facility) to planning the responses through water saving measures and sustainable land management frameworks. 2,292 (15% of women) stakeholders provided with technical assistance and trained in use of land laser leveling (944), irrigated water saving practices (1,348) in 4 projects pilot districts (Kegeili, Kanlikul, Chimbay and Takhtakupir) through 2 field trainings, by 4 Field Schools and 3 Extension Service Centers established. Laser leveling is used over 1390 ha. MoU between UNDP and State Committee of Forestry of Republic of Uzbekistan was signed that built up a frame for solid cooperation aimed to 3000 ha afforested by Local Forestry Organizations with technical and methodological support from side of UNDP. 43522 (30% of females) pastoralists from 10 communities with leadership based on cooperative management established in 4 project pilot districts (Kegeily, Kanlikul, Chimbay and Takhtakupir) are involved in implementation of works aimed at pasture reclamation to increase their productivity and to establish new pastures on 15307 ha.
2. Repeated drought | High | The Drought Early Warning System (DEWS) previously designed for run-off forming zones and applicable for different river basins was adapted for downstream of Amudarya river. 69 specialists (19% of females) of National Hydrometeorological Service were trained on DEWS use and on use of its products (quantitative and qualitative warnings of water availability). Currently, early warning about low water availability or drought can be issued for the regions located at the downstream of Amudarya with lead-time of 3 months. The concept of multi-modules information platform lately developed gives technical solution for integration of all hydrometeorological and climate data and information including DEWS products to be timely delivered to the end users. Beside DEWS products published in the project's quarterly bulletins that are targeted at central and regional government decision-makers, farmers and householders this reduced risk during the reporting period and it is expected to be further reduced during the next reporting period due to wider dissemination of DEWS products among end-users in the project pilot districts in Karakalpakstan.
3. Low level of cooperation between executing institutions | Low | Within the working of the Inter Agency Working Group, a meetings of Commission on Selection of the Potential Project Beneficiaries held, during the signing of MoU between UNDP and State Committee of Forestry of Republic of Uzbekistan, Project Board meetings and domo workshops the strengthened partnership with and ownership of all stakeholders involved in implementation of the project activities in Karakalpakstan were demonstrated. Moreover, the two Inter-Agency Working Groups (national and sub-national levels) established by the particular government resolutions to strengthen coordination and cooperation of all national partners involved in the Adaptation Project were supplemented with five initiative groups (each group includes 5-7 persons representing the rural communities) in each project pilot district. Those are aimed at strengthening the interaction between the national and sub-national executing agencies, and therefore significantly reduce the risk given.
Critical Risks Affecting Progress (Not identified at project design)
Identify Risks with a 50% or > likelihood of affecting progress of project
Identified Risk | Current Status | Steps Taken to Mitigate Risk
1. A change in political support for promoting and integrating adaptation measures into the agricultural sector | Low | The current political trends in promoting and mainstreaming adaptation measures are regularly tracked and analysed by the project. Recommendations on improvement of the existing legislative framework to facilitate mainstreaming of the climate change adaptation in the national policy agenda have been formulated and are a part of draft Food Security Law. This has significantly reduced the risk.
2. Insufficient capacity development and practical know-how within key state institutions and local authorities by the end of the project to allow sustainability of project achievements | Medium | The applied adaptation measures catalogue and Project Informational Strategy have been developed by the project. Development of Project Outreach Model is underway. Availability of the Catalogue as well as development of Project Informational Strategy and Project Outreach Model would enable familiarization of the key government agencies and institutions with best adaptation practices that contribute to sustainability of project achievements and reduction of the risk.
3. Implement legislative changes in a timely manner that are required to develop an adequate enabling environment for the promotion and use of adaptation measures | Low | The project analyzes the policy trends in promoting and mainstreaming adaptation measures on regular basis. Two Inter-Agency Working Groups (IAWG) on national and sub-national levels are consisted of representatives of the line ministries (Economy, Finance, Agriculture, Water Resources) that are aware about dynamically changing legislative framework to capture emerging opportunities related to promotion and application of adaptation measures. Interaction between the project and IAWGs establish sound enabling environment for piloting and demonstration of implementation of adaptation measures, which significantly reduces the risk.
Risk Measures: Were there any risk mitigation measures employed during the current reporting period? If so, were risks reduced? If not, why were these risks not reduced?
Add any comments relevant to risk mitigation (word limit = 500)
Recommendations on improvement of the existing legislative framework to facilitate mainstreaming of the climate change adaptation in the national policy agenda have been formulated and are a part of draft Food Security Law. This has significantly reduced the risk of change in political support for promoting and integrating adaptation measures into the agricultural sector.

## Rating
RATING ON IMPLEMENTATION PROGRESS
For rating definitions please see bottom of page.
| Progress on Key Milestones |  | Expected Progress |  | Progress to Date | Rating
Project Manager/Coordinator: | Doppler water meters and 8 automated meteorological stations installed (Outcome 1) |  | Data flow from 2 new Doppler water meters and 8 automated meteorological stations integrated for end-users |  | The concept of multi-modules informational platform (with technical specifications for all required equipment and software) to integrate data flow from the automated meteorological network and two water gauge stations equipped with new Doppler water discharge meters developed. | S
| At least 40,000 km2 of the Karakalpakstan region covered by automated hydro-meteorological observation network (Outcome 1) |  | At least 15,000 stakeholders and end-users (50% of women) are aware of the automated hydro-meteorological observation network |  | 40,000 km2 of the region is now covered with the observation network. 1,510 stakeholders (10% of women) are aware of the automated hydro-meteorological observation network through publication "Economic Feasibility Evaluation for installation of the automatic hydrometeorological equipment for modernization of the observational network in the Republic of Karakalpakstan" developed and published by the project, project's informational bulletins, 5 workshops and 1 press conference. CO UNDP has concluded MOU with national TV company at Karakalpakstan to broadcasting project activities including animated film on advantage of the automated hydrometeorological observation network for massive audience (15000 stakeholder or even more). | MS
| Season ahead forecasts and 2 weeks ahead temperature forecasts for effective warnings are practiced (Outcome 1) |  | At least 10,000 stakeholder (at least 20% of women) of early warning mechanisms trained in their use |  | 94 specialists (20% of females) of Uzhydromet and lime ministies were trained on use of DEWS its products (quantitative and qualitative values in warnings of water availability). 1,050 (20% of women) stakeholders were provided with drought early warnings through project informational bulletin. Early warnings about water resources deficiency and/or drought have been issued for the regions located at the downstream of Amudarya river with the lead-time of 3 months with warnings validity 70-100%. | MS
| At least 40% of Dekhkan farmers and pastoralists of Karakalpak region are served by science-based extension (Outcome 1) |  | At least 5,000 (at least 20% of women) stakeholders targeted by science-based extension services and trained within trainings and workshops. |  | 6248 (10% of 51,208 as the total number of Dekhkan farmers and pastoralists in 5 project pilot districts in Karakalpakstan), of which 15% are women) representatives of local communities are trained or consulted on available and innovative agro conservation and water saving practices by 3 Extension Services Centers. | S
| At least 3 Field School/Extension established and delivered training in adaptation practices to farmers and pastoralists (Outcome 1) |  | At least 3 Field School/Extension established to deliver training in adaptation practices to farmers and pastoralists |  | 3 Extension Services Centers established at Nukus Branch of Tashkent State Rural University in Nukus; Agricultural College in Kegeily district and LLC "Agrotech Service" in Kanlikul along with 4 Field Schools delivered trainings on: 1) Water saving practices applicable to low water availability periods (in all 5 project piloting districts in July 2018; 2) Sustainable land management approaches (in Kegeily and Chimbay districts in March 2018); 3) Land laser leveling applications (Kegeily, Kanlikul, Chimbay and Takhtakupir in August 2018); 4) Water saving practices (jointly with Ministry of Water Resources, in Chimbay and Takhtakupir districts in August 2018). | S
| At least 20% of targeted Dekhkan beneficiaries are female (Outcome 1) |  | At least 15,000 stakeholders and end-users (50% of women) are aware of the automated hydro-meteorological observation network. At least 10,000 stakeholder (at least 20% of women) of early warning mechanisms trained in their use. At least 5,000 (at least 20% of women) stakeholders targeted by science-based extension services and trained within trainings and workshops. |  | 1510 (10% of women) stakeholders are aware of the automated hydro-meteorological observation network through publication "Economic Feasibility Evaluation for installation of the automatic hydrometeorological equipment for modernization of the observational network in the Republic of Karakalpakstan" developed and published by the project, project's informational bulletins, 5 workshops and 1 press conference. In total 1,144 (20% of females) of Uzhydromet and line ministries specialists were trained on use of DEWS and its products, and other stakeholders were provided with drought early warnings through project informational bulletin. 5,165 (15 % of women) representatives of stakeholders were targeted by science-based extension services and trained within trainings and workshops. | MS
| At least 40,000 Dekhan farmers have adopted climate resilient conservation agriculture practices by end of the project (Output 2.1) |  | Technical assistance in best practices and application of low till, mixed cropping, fodder production, and residue crop soil provided to at least 20,000 stakeholders (at least 30% of women) |  | 3120 (15% of women) stakeholders provided with technical assistance in application of zero tillage (713), mulching (389), pan breaking (219), bio-protection of crops (619), fodder production with help of hydroponic equipment (371), improvement of land fertility (809) in 5 project pilot districts through 4 Field Schools, 5 hands-on workshops and by 3 Extension Service Center established. | MS
| At least 40,000 Dekhan farmers have adopted water saving irrigation practices by end of the project (Output 2.2) |  | Technical assistance in best practices and application of land leveling, furrow, siphon and drip irrigation systems provided to 20,000 stakeholders (at least 25% of women) |  | 2,292 (15% of women) stakeholders provided with technical assistance and trained in use of land laser leveling (944), irrigated water saving practices (1,348) in 4 projects pilot districts (Kegeili, Kanlikul, Chimbay and Takhtakupir) through 2 field trainings, by 4 Field Schools and 3 Extension Service Centers established. | MS
| Female lead horticulture greenhouses established by mid of 2016 (Outcome 2) |  | 16,000 households (at least 50% of women) provided with expertise and technical assistance in establishing horticulture greenhouses |  | 1,594 (20% of women) beneficiaries were provided with Informational Guidance on development of greenhouse and hotbeds in Karakalpakstan and recommendations on indoor vegetables growing in Northern Districts of Karakalpakstan.
| Laws on agricultural practices and water management amended and integrate conservation agriculture and water saving techniques by end of 2016 |  | At least 500 stakeholders (30% of women) provided with printing and publications associated with the best practices on legal and regulatory framework to support well tested farm-based adaptation measures for replication and upscale |  | 103 stakeholders (12% are women) provided with handouts and informational module "Recommendations on ensuring scaling up and expansion of the science-based and well-proven adaptation measures in agriculture" through 4 working meetings and workshops. | MS
| By end of the project, over 70,000 ha of arid land of Karakalpakstan is covered with saksaul and tamarix plantations and deliver sand stabilization and soil desalinization function (Outcome 3) |  | At least 10,000 stakeholders (at least 20% of women) provided with expertise and technical assistance in local saksaul and tamarix plantations deliver for sand stabilization and soil desalinization based on wind models and landscape rehabilitation management plan |  | 2,700 representatives (20% are women) of local communities learned about landscape adaptation measures that can increase their resilience to droughts and other climate change impacts through 3 series of field workshops conducted in all 5 project pilot districts. | MS
| At least 20,000 people organized in at least 10 cooperatives at the khokimiyat and makhalla levels and participate in sand stabilization plantation scheme (Outcome 3) |  | 20,000 stakeholders (50% of women) provided with expertise and technical assistance in development of community management scheme for planting and maintenance as community employment scheme for landscape level adaptation |  | 2253 stakeholders (15% are women) experienced and assisted in development of community management scheme for landscape level adaptation through 5 hands-on workshops on landscape adaptation measures/approaches and their implementation conducted in all 5 project pilot districts. 10 communities with leadership based on cooperative management were established in 5 project pilot districts and joined 43,522 (30% are females) pastoralists to implement works aimed at pasture reclamation to increase their productivity and to establish 15,307 ha of new pasture lands. | MS
| At least 10 community organizations (at least 5 female groups and village organizations) at khokimiyat and makhalla level have clear mandates, institutional capacities and skills and manage saksaul and tamarix plantations by end of 2019 (Outcome 3) |  | At least one cooperative management system for landscape rehabilitation and management established by national sub-contractors |  | 10 communities with leadership based on cooperative management established by local communities in 4 project pilot districts (Kegeily, Kanlikul, Chimbay and Takhtakupir) that are joined 43,522 (32% are females) pastoralists to implement works aimed at pasture reclamation to increase their productivity and to establish 15,507 ha of new pasture lands. | S
| At least two sets of lessons learned bulletins produced and covered successful climate resilient agronomic and water saving measures (Outcome 4) |  | At least 3 lessons learned for climate resilient agricultural and pastoral production systems in arid lands from stakeholders through providing them with technical assistance in analysis and documentation of those lessons learned |  | 5 lessons focused on agro conservation and water saving practices and landscape adaptation measures: 1) Land laser leveling as resources and water saving technology (learned from farmers in Chimbay, Kunlikul and Kegeily districts); 2) Pan breaking and crop rotation, as the crops and land fertility increasing applications (learned form farmers in Chimbay and Kegeily districts; 3) Use of bio-stimulating and environment friendly substances for crops protection and their production increase (learned from framers and households in Kanlikul and Kegeily districts); 4) Use of water giving diversified modes, as water saving applications, during low water availability or droughts (learned from farmers in Kegeily and Chimbay districts); 5) Growing arboreal and fodder seedlings in nurseries, as a measure of increased desert plants germination (learned from foresters in Muynak, Chimbay and Takhtakupir regions). | S
| At least 5 farmland demonstration meetings covered by the local and national media for adaptation advocacy (Outcome 4) |  | At least 3 farm and pasture land demonstration meetings with participation of national, local authorities, media and communities, and associated printing and publications produced and disseminated |  | 21 demonstration meetings and workshops (4440 people; with 18% of female) on climate change adaptation and on increasing climate change resilience of the targeted local communities conducted. Information on the events posted at newspapers and web-resources, and broadcasted via national and regional radio and TV. | HS
[5 empty] | Overall Rating | MS
Please Provide the Name and Contact information of person(s) reponsible for completeling the Rating section
| Name: | Aleksandr Merkushkin
| Email: | aleksandr.merkushkin@undp.org
Please justify your rating. Outline the positive and negative progress made by the project since it started. Provide specific recommendations for next steps. . (word limit=500)
The overall rating is Marginally Satisfactory. Project is making progress. It has passed MTE, which main conclusions and recommendations are well noted and have been reflected in Management Response to MTE. The overal rating by MTE for Outcomes 1 and 4 is Satisfactory and for Outcomes 2 and 3 is Moderately Satisfactory . The most of recommendations made are partially completed. During the reporting period, project was able to speed up implementation of some major project activities, which were significantly lagging behind. There are a few milestones that confirm a progress: • 10 automated meteo-stations installed in Karakalpakstan upgraded with 5 new sensors (pyranometers). 40 specialists/observers have been trained on operation and maintenance measuring and communication equipment; •In total 1,119 (20% of females) of Uzhydromet specialists were trained on use of DEWS and its products, and other stakeholders were provided with drought early warnings through project informational bulletin; • Concept of multi-modules information platform developed includes technical solution for integration of all hydrometeorological and climate data/information, including DEWS products, that are to be timely delivered to the end users; • 3 Extension Services Centers are operational. 5,225 ( 10% of 51,208 total Dekhkan farmers and pastoralists of project piloting districts) (15 % of women) representatives of local communities were trained or consulted on available and innovative agro conservation and water saving practices by established Extension Services Centers in Kegeily, Kanlikul , Chimbay and Tahktakupir project's pilot districts; • 4 Field Schools have trained 1,272 (19% females) farmers, householders and pastoralists on: 1) Water saving practices applied to low water availability seasons; 2) Sustainable land management approaches; 3) Land laser leveling applications; 4) Water saving practices (jointly with Ministry of Water Resources); • 2,749 (15% of women) stakeholders provided with technical assistance in application of zero tillage (713), mulching (389), pan breaking (219), bio-protection of crops (619), improvement of land fertility (809) in 5 project pilot districts through 4 Field Schools, 5 hands-on workshops and by 3 Extension Service Center established.. • Recommendations on narrowing gaps in legal regulatory to support promotion of well-tested farm-based adaptation measures that can be replicated and up-scaled developed and are part of draft of Food Security Law; • MoU signed between UNDP and State Committee of Forestry of Republic of Uzbekistan to establish framework for cooperation and aims at afforestation of 3,000 ha of lands by Local Forestry Farms with technical and methodological support to be provided by UNDP; • 696 representatives (20% of women) of local communities learned about landscape adaptation measures that can increase their resilience to droughts and other climate change impacts; • 9 communities with leadership based on cooperative management established at 4 project pilot districts (Kegeily, Kanlikul, Chimbay and Takhtakupir), which have joined 40,250 (38% of females) pastoralists to implement works aimed at pasture reclamation to increase their productivity and establish new pastures. • 18 demonstration meetings and workshops (3,395 people; with 18% of female) on climate change adaptation and on increasing climate change resilience of the targeted local communities conducted. Information on the events posted at newspapers and web-resources, and broadcasted via national and regional radio and TV.
| Progress on Key Milestones |  | Expected Progress |  | Progress to Date | Rating
Implementing Agency | Doppler water meters and 8 automated meteorological stations installed (Outcome 1) |  | Data flow from 2 new Doppler water meters and 8 automated meteorological stations integrated for end-users |  | The concept of multi-modules informational platform (with technical specifications for all required equipment and software) to integrate data flow from the automated meteorological network and two water gauge stations equipped with new Doppler water discharge meters developed. | S
| At least 40,000 km2 of the Karakalpakstan region covered by automated hydro-meteorological observation network (Outcome 1) |  | At least 15,000 stakeholders and end-users (50% of women) are aware of the automated hydro-meteorological observation network |  | 40,000 km2 of the region is now covered with the observation network. 1,510 stakeholders (10% of women) are aware of the automated hydro-meteorological observation network through publication "Economic Feasibility Evaluation for installation of the automatic hydrometeorological equipment for modernization of the observational network in the Republic of Karakalpakstan" developed and published by the project, project's informational bulletins, 5 workshops and 1 press conference. CO UNDP has concluded MOU with national TV company at Karakalpakstan to broadcasting project activities including animated film on advantage of the automated hydrometeorological observation network for massive audience (15000 stakeholder or even more). | MS
| Season ahead forecasts and 2 weeks ahead temperature forecasts for effective warnings are practiced (Outcome 1) |  | At least 10,000 stakeholder (at least 20% of women) of early warning mechanisms trained in their use |  | 94 specialists (20% of females) of Uzhydromet and lime ministies were trained on use of DEWS its products (quantitative and qualitative values in warnings of water availability). 1,050 (20% of women) stakeholders were provided with drought early warnings through project informational bulletin. Early warnings about water resources deficiency and/or drought have been issued for the regions located at the downstream of Amudarya river with the lead-time of 3 months with warnings validity 70-100%. | MS
| At least 40% of Dekhkan farmers and pastoralists of Karakalpak region are served by science-based extension (Outcome 1) |  | At least 5,000 (at least 20% of women) stakeholders targeted by science-based extension services and trained within trainings and workshops. |  | 6248 (10% of 51,208 as the total number of Dekhkan farmers and pastoralists in 5 project pilot districts in Karakalpakstan), of which 15% are women) representatives of local communities are trained or consulted on available and innovative agro conservation and water saving practices by 3 Extension Services Centers. | S
| At least 3 Field School/Extension established and delivered training in adaptation practices to farmers and pastoralists (Outcome 1) |  | At least 3 Field School/Extension established to deliver training in adaptation practices to farmers and pastoralists |  | 3 Extension Services Centers established at Nukus Branch of Tashkent State Rural University in Nukus; Agricultural College in Kegeily district and LLC "Agrotech Service" in Kanlikul along with 4 Field Schools delivered trainings on: 1) Water saving practices applicable to low water availability periods (in all 5 project piloting districts in July 2018; 2) Sustainable land management approaches (in Kegeily and Chimbay districts in March 2018); 3) Land laser leveling applications (Kegeily, Kanlikul, Chimbay and Takhtakupir in August 2018); 4) Water saving practices (jointly with Ministry of Water Resources, in Chimbay and Takhtakupir districts in August 2018). | S
| At least 20% of targeted Dekhkan beneficiaries are female (Outcome 1) |  | At least 15,000 stakeholders and end-users (50% of women) are aware of the automated hydro-meteorological observation network. At least 10,000 stakeholder (at least 20% of women) of early warning mechanisms trained in their use. At least 5,000 (at least 20% of women) stakeholders targeted by science-based extension services and trained within trainings and workshops. |  | 1510 (10% of women) stakeholders are aware of the automated hydro-meteorological observation network through publication "Economic Feasibility Evaluation for installation of the automatic hydrometeorological equipment for modernization of the observational network in the Republic of Karakalpakstan" developed and published by the project, project's informational bulletins, 5 workshops and 1 press conference. In total 1,144 (20% of females) of Uzhydromet and line ministries specialists were trained on use of DEWS and its products, and other stakeholders were provided with drought early warnings through project informational bulletin. 5,165 (15 % of women) representatives of stakeholders were targeted by science-based extension services and trained within trainings and workshops. | MS
| At least 40,000 Dekhan farmers have adopted climate resilient conservation agriculture practices by end of the project (Output 2.1) |  | Technical assistance in best practices and application of low till, mixed cropping, fodder production, and residue crop soil provided to at least 20,000 stakeholders (at least 30% of women) |  | 3120 (15% of women) stakeholders provided with technical assistance in application of zero tillage (713), mulching (389), pan breaking (219), bio-protection of crops (619), fodder production with help of hydroponic equipment (371), improvement of land fertility (809) in 5 project pilot districts through 4 Field Schools, 5 hands-on workshops and by 3 Extension Service Center established. | MS
| At least 40,000 Dekhan farmers have adopted water saving irrigation practices by end of the project (Output 2.2) |  | Technical assistance in best practices and application of land leveling, furrow, siphon and drip irrigation systems provided to 20,000 stakeholders (at least 25% of women) |  | 2,292 (15% of women) stakeholders provided with technical assistance and trained in use of land laser leveling (944), irrigated water saving practices (1,348) in 4 projects pilot districts (Kegeili, Kanlikul, Chimbay and Takhtakupir) through 2 field trainings, by 4 Field Schools and 3 Extension Service Centers established. | MS
| Female lead horticulture greenhouses established by mid of 2016 (Outcome 2) |  | 16,000 households (at least 50% of women) provided with expertise and technical assistance in establishing horticulture greenhouses |  | 1,594 (20% of women) beneficiaries were provided with Informational Guidance on development of greenhouse and hotbeds in Karakalpakstan and recommendations on indoor vegetables growing in Northern Districts of Karakalpakstan. | MS
| Laws on agricultural practices and water management amended and integrate conservation agriculture and water saving techniques by end of 2016 |  | At least 500 stakeholders (30% of women) provided with printing and publications associated with the best practices on legal and regulatory framework to support well tested farm-based adaptation measures for replication and upscale |  | 103 stakeholders (12% are women) provided with handouts and informational module "Recommendations on ensuring scaling up and expansion of the science-based and well-proven adaptation measures in agriculture" through 4 working meetings and workshops. | MS
| By end of the project, over 70,000 ha of arid land of Karakalpakstan is covered with saksaul and tamarix plantations and deliver sand stabilization and soil desalinization function (Outcome 3) |  | At least 10,000 stakeholders (at least 20% of women) provided with expertise and technical assistance in local saksaul and tamarix plantations deliver for sand stabilization and soil desalinization based on wind models and landscape rehabilitation management plan |  | 2,700 representatives (20% are women) of local communities learned about landscape adaptation measures that can increase their resilience to droughts and other climate change impacts through 3 series of field workshops conducted in all 5 project pilot districts. | MS
| At least 20,000 people organized in at least 10 cooperatives at the khokimiyat and makhalla levels and participate in sand stabilization plantation scheme (Outcome 3) |  | 20,000 stakeholders (50% of women) provided with expertise and technical assistance in development of community management scheme for planting and maintenance as community employment scheme for landscape level adaptation |  | 2253 stakeholders (15% are women) experienced and assisted in development of community management scheme for landscape level adaptation through 5 hands-on workshops on landscape adaptation measures/approaches and their implementation conducted in all 5 project pilot districts. 10 communities with leadership based on cooperative management were established in 5 project pilot districts and joined 43,522 (30% are females) pastoralists to implement works aimed at pasture reclamation to increase their productivity and to establish 15,307 ha of new pasture lands. | MS
| At least 10 community organizations (at least 5 female groups and village organizations) at khokimiyat and makhalla level have clear mandates, institutional capacities and skills and manage saksaul and tamarix plantations by end of 2019 (Outcome 3) |  | At least one cooperative management system for landscape rehabilitation and management established by national sub-contractors |  | 10 communities with leadership based on cooperative management established by local communities in 4 project pilot districts (Kegeily, Kanlikul, Chimbay and Takhtakupir) that are joined 43,522 (32% are females) pastoralists to implement works aimed at pasture reclamation to increase their productivity and to establish 15,507 ha of new pasture lands. | HS
| At least two sets of lessons learned bulletins produced and covered successful climate resilient agronomic and water saving measures (Outcome 4) |  | At least 3 lessons learned for climate resilient agricultural and pastoral production systems in arid lands from stakeholders through providing them with technical assistance in analysis and documentation of those lessons learned |  | 5 lessons focused on agro conservation and water saving practices and landscape adaptation measures: 1) Land laser leveling as resources and water saving technology (learned from farmers in Chimbay, Kunlikul and Kegeily districts); 2) Pan breaking and crop rotation, as the crops and land fertility increasing applications (learned form farmers in Chimbay and Kegeily districts; 3) Use of bio-stimulating and environment friendly substances for crops protection and their production increase (learned from framers and households in Kanlikul and Kegeily districts); 4) Use of water giving diversified modes, as water saving applications, during low water availability or droughts (learned from farmers in Kegeily and Chimbay districts); 5) Growing arboreal and fodder seedlings in nurseries, as a measure of increased desert plants germination (learned from foresters in Muynak, Chimbay and Takhtakupir regions). | HS
| At least 5 farmland demonstration meetings covered by the local and national media for adaptation advocacy (Outcome 4) |  | At least 3 farm and pasture land demonstration meetings with participation of national, local authorities, media and communities, and associated printing and publications produced and disseminated |  | 21 demonstration meetings and workshops (4440 people; with 18% of female) on climate change adaptation and on increasing climate change resilience of the targeted local communities conducted. Information on the events posted at newspapers and web-resources, and broadcasted via national and regional radio and TV. | HS
[5 empty] | Overall Rating | MS
Please Provide the Name and Contact information of person(s) reponsible for completeling the Rating section
| Name: | Ms Natasha Olofinskaya; Ms. Rano Baykhanova
| Email: | nataly.olofinskaya@undp.org; rano.baykhanova@undp.org
| Progress on Key Milestones |  | Expected Progress |  | Progress to Date | Rating
Other | Doppler water meters and 8 automated meteorological stations installed (Outcome 1) |  | Data flow from 2 new Doppler water meters and 8 automated meteorological stations integrated for end-users |  | The concept of multi-modules informational platform (with technical specifications for all required equipment and software) to integrate data flow from the automated meteorological network and two water gauge stations equipped with new Doppler water discharge meters developed. | S
| At least 40,000 km2 of the Karakalpakstan region covered by automated hydro-meteorological observation network (Outcome 1) |  | At least 15,000 stakeholders and end-users (50% of women) are aware of the automated hydro-meteorological observation network |  | 40,000 km2 of the region is now covered with the observation network. 1,510 stakeholders (10% of women) are aware of the automated hydro-meteorological observation network through publication "Economic Feasibility Evaluation for installation of the automatic hydrometeorological equipment for modernization of the observational network in the Republic of Karakalpakstan" developed and published by the project, project's informational bulletins, 5 workshops and 1 press conference. CO UNDP has concluded MOU with national TV company at Karakalpakstan to broadcasting project activities including animated film on advantage of the automated hydrometeorological observation network for massive audience (15000 stakeholder or even more). | MS
| Season ahead forecasts and 2 weeks ahead temperature forecasts for effective warnings are practiced (Outcome 1) |  | At least 10,000 stakeholder (at least 20% of women) of early warning mechanisms trained in their use |  | 94 specialists (20% of females) of Uzhydromet and lime ministies were trained on use of DEWS its products (quantitative and qualitative values in warnings of water availability). 1,050 (20% of women) stakeholders were provided with drought early warnings through project informational bulletin. Early warnings about water resources deficiency and/or drought have been issued for the regions located at the downstream of Amudarya river with the lead-time of 3 months with warnings validity 70-100%. | MS
| At least 40% of Dekhkan farmers and pastoralists of Karakalpak region are served by science-based extension (Outcome 1) |  | At least 5,000 (at least 20% of women) stakeholders targeted by science-based extension services and trained within trainings and workshops. |  | 6248 (10% of 51,208 as the total number of Dekhkan farmers and pastoralists in 5 project pilot districts in Karakalpakstan), of which 15% are women) representatives of local communities are trained or consulted on available and innovative agro conservation and water saving practices by 3 Extension Services Centers. | S
| At least 3 Field School/Extension established and delivered training in adaptation practices to farmers and pastoralists (Outcome 1) |  | At least 3 Field School/Extension established to deliver training in adaptation practices to farmers and pastoralists |  | 3 Extension Services Centers established at Nukus Branch of Tashkent State Rural University in Nukus; Agricultural College in Kegeily district and LLC "Agrotech Service" in Kanlikul along with 4 Field Schools delivered trainings on: 1) Water saving practices applicable to low water availability periods (in all 5 project piloting districts in July 2018; 2) Sustainable land management approaches (in Kegeily and Chimbay districts in March 2018); 3) Land laser leveling applications (Kegeily, Kanlikul, Chimbay and Takhtakupir in August 2018); 4) Water saving practices (jointly with Ministry of Water Resources, in Chimbay and Takhtakupir districts in August 2018). | S
| At least 20% of targeted Dekhkan beneficiaries are female (Outcome 1) |  | At least 15,000 stakeholders and end-users (50% of women) are aware of the automated hydro-meteorological observation network. At least 10,000 stakeholder (at least 20% of women) of early warning mechanisms trained in their use. At least 5,000 (at least 20% of women) stakeholders targeted by science-based extension services and trained within trainings and workshops. |  | 1510 (10% of women) stakeholders are aware of the automated hydro-meteorological observation network through publication "Economic Feasibility Evaluation for installation of the automatic hydrometeorological equipment for modernization of the observational network in the Republic of Karakalpakstan" developed and published by the project, project's informational bulletins, 5 workshops and 1 press conference. In total 1,144 (20% of females) of Uzhydromet and line ministries specialists were trained on use of DEWS and its products, and other stakeholders were provided with drought early warnings through project informational bulletin. 5,165 (15 % of women) representatives of stakeholders were targeted by science-based extension services and trained within trainings and workshops. | MS
| At least 40,000 Dekhan farmers have adopted climate resilient conservation agriculture practices by end of the project (Output 2.1) |  | Technical assistance in best practices and application of low till, mixed cropping, fodder production, and residue crop soil provided to at least 20,000 stakeholders (at least 30% of women) |  | 3120 (15% of women) stakeholders provided with technical assistance in application of zero tillage (713), mulching (389), pan breaking (219), bio-protection of crops (619), fodder production with help of hydroponic equipment (371), improvement of land fertility (809) in 5 project pilot districts through 4 Field Schools, 5 hands-on workshops and by 3 Extension Service Center established. | MS
| At least 40,000 Dekhan farmers have adopted water saving irrigation practices by end of the project (Output 2.2) |  | Technical assistance in best practices and application of land leveling, furrow, siphon and drip irrigation systems provided to 20,000 stakeholders (at least 25% of women) |  | 2,292 (15% of women) stakeholders provided with technical assistance and trained in use of land laser leveling (944), irrigated water saving practices (1,348) in 4 projects pilot districts (Kegeili, Kanlikul, Chimbay and Takhtakupir) through 2 field trainings, by 4 Field Schools and 3 Extension Service Centers established. | MS
| Female lead horticulture greenhouses established by mid of 2016 (Outcome 2) |  | 16,000 households (at least 50% of women) provided with expertise and technical assistance in establishing horticulture greenhouses |  | 1,594 (20% of women) beneficiaries were provided with Informational Guidance on development of greenhouse and hotbeds in Karakalpakstan and recommendations on indoor vegetables growing in Northern Districts of Karakalpakstan. | MS
| Laws on agricultural practices and water management amended and integrate conservation agriculture and water saving techniques by end of 2016 |  | At least 500 stakeholders (30% of women) provided with printing and publications associated with the best practices on legal and regulatory framework to support well tested farm-based adaptation measures for replication and upscale |  | 103 stakeholders (12% are women) provided with handouts and informational module "Recommendations on ensuring scaling up and expansion of the science-based and well-proven adaptation measures in agriculture" through 4 working meetings and workshops. | MS
| By end of the project, over 70,000 ha of arid land of Karakalpakstan is covered with saksaul and tamarix plantations and deliver sand stabilization and soil desalinization function (Outcome 3) |  | At least 10,000 stakeholders (at least 20% of women) provided with expertise and technical assistance in local saksaul and tamarix plantations deliver for sand stabilization and soil desalinization based on wind models and landscape rehabilitation management plan |  | 2,700 representatives (20% are women) of local communities learned about landscape adaptation measures that can increase their resilience to droughts and other climate change impacts through 3 series of field workshops conducted in all 5 project pilot districts. | MS
| At least 20,000 people organized in at least 10 cooperatives at the khokimiyat and makhalla levels and participate in sand stabilization plantation scheme (Outcome 3) |  | 20,000 stakeholders (50% of women) provided with expertise and technical assistance in development of community management scheme for planting and maintenance as community employment scheme for landscape level adaptation |  | 2253 stakeholders (15% are women) experienced and assisted in development of community management scheme for landscape level adaptation through 5 hands-on workshops on landscape adaptation measures/approaches and their implementation conducted in all 5 project pilot districts. 10 communities with leadership based on cooperative management were established in 5 project pilot districts and joined 43,522 (30% are females) pastoralists to implement works aimed at pasture reclamation to increase their productivity and to establish 15,307 ha of new pasture lands. | MS
| At least 10 community organizations (at least 5 female groups and village organizations) at khokimiyat and makhalla level have clear mandates, institutional capacities and skills and manage saksaul and tamarix plantations by end of 2019 (Outcome 3) |  | At least one cooperative management system for landscape rehabilitation and management established by national sub-contractors |  | 10 communities with leadership based on cooperative management established by local communities in 4 project pilot districts (Kegeily, Kanlikul, Chimbay and Takhtakupir) that are joined 43,522 (32% are females) pastoralists to implement works aimed at pasture reclamation to increase their productivity and to establish 15,507 ha of new pasture lands. | S
| At least two sets of lessons learned bulletins produced and covered successful climate resilient agronomic and water saving measures (Outcome 4) |  | At least 3 lessons learned for climate resilient agricultural and pastoral production systems in arid lands from stakeholders through providing them with technical assistance in analysis and documentation of those lessons learned |  | 5 lessons focused on agro conservation and water saving practices and landscape adaptation measures: 1) Land laser leveling as resources and water saving technology (learned from farmers in Chimbay, Kunlikul and Kegeily districts); 2) Pan breaking and crop rotation, as the crops and land fertility increasing applications (learned form farmers in Chimbay and Kegeily districts; 3) Use of bio-stimulating and environment friendly substances for crops protection and their production increase (learned from framers and households in Kanlikul and Kegeily districts); 4) Use of water giving diversified modes, as water saving applications, during low water availability or droughts (learned from farmers in Kegeily and Chimbay districts); 5) Growing arboreal and fodder seedlings in nurseries, as a measure of increased desert plants germination (learned from foresters in Muynak, Chimbay and Takhtakupir regions). | S
| At least 5 farmland demonstration meetings covered by the local and national media for adaptation advocacy (Outcome 4) |  | At least 3 farm and pasture land demonstration meetings with participation of national, local authorities, media and communities, and associated printing and publications produced and disseminated |  | 21 demonstration meetings and workshops (4440 people; with 18% of female) on climate change adaptation and on increasing climate change resilience of the targeted local communities conducted. Information on the events posted at newspapers and web-resources, and broadcasted via national and regional radio and TV. | S
[5 empty] | Overall Rating | MS
Please Provide the Name and Contact information of person(s) reponsible for completeling the Rating section
| Name: | Mr.Bakhriddin Nishonov, First Deputy of General Director of Uzhydromet, National Project Coordinator of Adaptation Project
| Email: | Uzhymet@meteo.uz
| Please justify your rating and address the following points: 1. Indicate trends, both positive and negative, in achievement of outcomes as per the project indicators. 2. Detail critical risks that have affected progress. 3. Outline response to MTR undertaken this reporting period. 4. Outline action plan to address projects with a rating of HU, U or MU. Please keep your input to 1200 words |  | The overall rating is Marginally Satisfactory. The project demonstrates good budget delivery and budget efficient utilization within Activity 1 and 4 where targets identified for the project are high likely achievable. However, the project is still experiencing with significant lagging in targets achievement within Activity 2 and 3, and thus shall put more efforts on balance the budget utilization for those activities through more preventive planning and speeding up the implementation of the procurement, training and outreach framework. The lagging is significant and partially was caused by second tranche delayed that it turn caused even longer delay due to seasonal nature of agriculture works planned by the project. The project has passed MTE. The recommendations made should be addressed to let the project pace be more balanced and even. One of recommendation says: "It is recommended to extend the project until the AF grant will be expended". NIA requests the project's time extension from AF in accordance with AF regulations and rules. Most of MTE recommendations are partially completed.
Rating Definitions
|  |  | Highly Satisfactory (HS) | Project actions/activities planned for current reporting period are progressing on track or exceeding expectations to acheive all major outcomes/outputs for given reporting period, without major shortcomings. The project can be presented as “good practice”.
|  |  | Satisfactory (S) | Project actions/activities planned for current reporting period are progressing on track to achieve most of its major outcomes/outputs with only minor shortcomings.
|  |  | Marginally Satisfactory (MS) | Project actions/activities planned for current reporting period are progressing on track to achieve most major relevant outcomes/outputs, but with either significant shortcomings or modest overall relevance.
|  |  | Marginally Unsatisfactory (MU) | Project actions/activities planned for current reporting period are not progressing on track to achieve major outcomes/outputs with major shortcomings or is expected to achieve only some of its major outcomes/outputs.
|  |  | Unsatisfactory (U) | Project actions/activities planned for current reporting period are not progressing on track to achieve most of its major outcomes/outputs.
|  |  | Highly Unsatisfactory (U) | Project actions/activities planned for current reporting period are not on track and shows that it is failing to achieve, and is not expected to achieve, any of its outcomes/outputs.

## Project Indicators
PROJECT Indicators
Please provide all indicators being tracked for the project as outlined in the project document
Type of Indicator (indicators towards Objectives, Outcomes, etc…)
Type of Indicator | Indicator | Baseline | Progress since inception | Target for Project End
| Indicator 1.1.1: Number of automated met stations for field data collection and transmission | Currently, there is no automated hydro-meteorological stations in Karakalpakstan | 10 automated meteo-stations in Karakalpakstan upgraded with 5 new sensors (pyranometers). 40 specialists/observers trained on operation and maintenance of measuring and communication equipment. | 8 automated hydro-meteorological stations and 2 Doppler water meters installed
| Indicator 1.2.1: Coverage of hydro-meteorological observation network on km2 | Currently, there is no spatial coverage of automated hydro-meteorological observation network | 40,000 km2 of spatial coverage by the automated meteteorological observation ensured. | At least 40,000 km2 of the Karakalpakstan region covered by automated hydro-meteorological observation network
| Indicator 1.3.1: Lead time for drought early warning | Currently, drought early warning does not exists | 3 months lead time for early drought warnings for vegetation period ensured by Drought Early Warning System (DEWS) adapted to Amudarya river downstream conditions. Early warnings' are available for 10 day periods and monthly with validity of the warnings varies from 70 to 100%. | Seasonal and biweekly
| Indicator 1.4.1: % Dekhkan farmers (% female Dekhkan farmers) receiving extension services to introduce farm-based climate risk management measures | Uzbekistan does not yet have a science-based extension system in place | At least 12% (6248 of 51,208 as the total number of Dekhkan farmers and pastoralists in 5 project pilot districts in Karakalpakstan) of farms, dekhans and households (15% are female) from 5 project pilot districts received information about climate change adaptation related services (available innovative agro conservation and water saving practices) from 3 Extension Services Centers established, Field Schools and hands-on workshops. | At least 40% of Dekhkan farmers and pastoralists of Karakalpakstan region served by science-based extension
| Indicator 1.4.2: # of Field School/Extension delivering training in adaptation practices to farmers and pastoralists. | Currently, no Field School/Extension outlets exist in Karakalpakstan | 3 Extension Services Centers established at Nukus Branch of Tashkent State Rural University in Nukus; Agricultural College in Kegeily district and LLC "Agrotech Service" in Kanlikul district along with 4 Field Schools delivered trainings on: 1) Water saving practices applicable to low water availability periods (in all 5 project piloting districts in July 2018); 2) Sustainable land management approaches (in Kegeily and Chimbay districts in March 2018); 3) Land laser leveling applications (Kegeily, Kanlikul, Chimbay and Takhtakupir districts in August 2018); 4) Water saving practices (jointly with Ministry of Water Resources, in Chimbay and Takhtakupir districts in August 2018), 5) Study visit on fodder production with help of hydroponic equipment in October 2018. Overall, 6248 (15% are females) farmers, householders and pastoralists were trained. | At least 3 Field School/Extension established to deliver training in adaptation practices to farmers and pastoralists by the fourth year (2017)
| Indicator 2.1.1: # of dekhkan farmers adopted conservation agriculture practices (e.g. low till, mixed cropping, fodder production, and residue crop soil) | It is estimated that 7-10% of farmers practice climate resilient conservation agriculture practices | 3120 (15% of women) stakeholders provided with technical assistance in application of zero tillage (713), mulching (389), pan breaking (219), bio-protection of crops (619), fodder production with help of hydroponic equipment (371), improvement of land fertility (809) in 5 project pilot districts through 4 Field Schools, 5 hands-on workshops and by 3 Extension Service Center established. | At least 40,000 Dekhan farmers have adopted climate resilient conservation agriculture practices
| Indicator 2.2.1: # of dekhkan farmers adopted water saving irrigation practices (e.g. land levelling, furrow and drip irrigation systems) | It is estimated that 3-5% of farmers practice water saving practices | 2,292 (15% of women) stakeholders provided with technical assistance and trained in use of land laser leveling (944), irrigated water saving practices (1,348) in 4 projects pilot districts (Kegeili, Kanlikul, Chimbay and Takhtakupir) through 2 field trainings, by 4 Field Schools and 3 Extension Service Centers established. Laser leveling is used over 1390 ha. 1,594 (20% of women) beneficiaries provided with Informational Guidance on development of greenhouse and hotbeds in Karakalpakstan and recommendations on indoor vegetables growing in project pilot districts in the Northern Karakalpakstan. | At least 40,000 Dekhan farmers have adopted water saving irrigation practices
| Indicator 2.3.1: Number of female led horticulture greenhouses established | In Karakalpakstan, currently no horticulture greenhouses are led by women farmers (This is currently being verified as part of inception phase activities) | 106 female candidates (21% of 512 beneficiaries) identified based on their social and gender profile to be recipients of greenhouse equipment. 1,594 (20% of women) beneficiaries were provided with Informational Guidance on development of greenhouse and hotbeds in Karakalpakstan and recommendations on indoor vegetables growing in the Northern Karakalpakstan.. | At least five woman-led horticulture greenhouses established by end of second year (out of 12 greenhouses that will be delivered in the project)
| Indicator 2.4.1: # of legal acts and regulations enacted to support well tested farm-based adaptation measures. | Legal acts and regulations that exist do not provide conditions that facilitate take-up of farm-based adaptation | Draft Food Security Law reflects the recommendation related to supporting promotion of well-tested farm-based adaptation measures that can be replicated and up-scaled developed by the project. | At least three laws/regulations on agricultural practices and water management amended and integrated regulations on the adoption of conservation agriculture and water saving techniques and technologies on the farms by end of the third year
| Indicator 3.1.1: # of ha with saksaul and tamarix plantations to deliver sand stabilization and soil desalinization function. | There have been only sporadic and largely unsuccessful attempts of sand stabilization | 3,000 ha of desert/degraded lands are committed by Local Forestry Farms to be afforested, with technical and methodological support provided by project (UNDP) in accordance with MoU signed between UNDP and State Committee of Forestry of Uzbekistan. | Over 70,000 ha of arid land of Karakalpakstan is covered with saksaul and tamarix plantations and deliver sand stabilization and soil desalinization function
| Indicator 3.2.1: # of Dekhkan farmer and pastoral community members involved in landscape level adaptation measures (e.g. saksaul and tamarix planting) through local employment programme. | Currently, there is no systemic engagement of dekhan farmers and pastoral community for landscape land management | 43,522 (30% are females) pastoralists from 10 communities with leadership based on cooperative management established in 4 project pilot districts (Kegeily, Kanlikul, Chimbay and Takhtakupir) are involved in implementation of works aimed at pasture reclamation to increase their productivity and to establish new pastures at 15307 ha. | At least 20,000 people organized in at least 10 cooperatives at the khokimiyat and makhalla levels and participate in sand stabilization plantation scheme
| Indicator 3.3.1: # of cooperatives established at Khokimiyat and Makhalla levels for community management of sand stabilizing plantations. | Cooperatives are a new mechanism that has not been tested in the country, and hence, there is currently none. | 10 community-based cooperatives established in 5 project pilot districts and they are joined 43,522 (30% are females) pastoralists to implement works aimed at pastures reclamation to increase their productivity and to establish new pastures at 15,307 ha. | At least 10 community organizations (at least 5 female groups and village organizations) at khokimiyat and makhalla level have clear mandates, institutional capacities and skills and manage saksaul and tamarix plantations by end of the fourth year
| Indicator 4.1.1: # of documented good practices of agronomic and water saving measures. | None | 5 good practices were selected and documented in project publications: 1) greenhouses and indoor growing of vegetables, 2) improving water content in soils, 3) growing salt tolerant plants in arid lands, 4) seeds and sapling growing in nurseries, 5) the most effective water and land use options for low water availability condition | At least two sets of bulletins published including information about results of inventory of all tested agronomic and water saving measures and successful practices mapped out
| Indicator 4.2.1: # of lessons learned bulletins disseminated through printed and web-based media. | None | 5 lessons focused on agro conservation and water saving practices and landscape adaptation measures captured and documented in 3 project publications. | At least two sets of lessons learned bulletins produced covering successful climate resilient agronomic and water saving measures
| Indicator 4.3.1: # of farm and pasture land demonstration meetings covered by media and attended by national and local authorities | None | 21 demonstration meetings and workshops (4440 people; with 18% of female) on climate change adaptation and on increasing climate change resilience of the targeted local communities conducted. Information on the events posted at newspapers and web-resources, and broadcasted via national and regional radio and TV. | At least 5 farmland demonstration meetings covered by the local and national media for adaptation advocacy

## Lessons Learned
QUALITATIVE MEASURES and LESSONS LEARNED
Please complete the following section every reporting period
Implementation and Adaptive Management | Response
What implementation issues/lessons, either positive or negative, affected progress? | Project strategy is complex with lack of clarity and logic to understand how planned activities will reach the expected results and particularly the targets. The outputs, in most cases, identified as deliverables with, in some cases, targets embedded in the output statements. With ambitious targets and the current context of the agriculture sector in Uzbekistan, it is difficult to know how results from project supported activities will reach these targets. The project document does not provide a useful “blue print” for the project team to guide the implementation of the project.
Were there any delays in implementation? If so, include any causes of delays. What measures have been taken to reduce delays? | The implementation of the project progresses is uneven. Project is making progress and it has 2.5 more years of implementation left. Good progress is made under outcome 1 and 4 and it is anticipated that it will meet its targets under these two outcomes. However, regarding outcome 2 & 3, the targets are ambitious and their achievement is seriously delayed. To reduced the delays, the project shall speed up demonstration of adaptation measures and piloting an “outreach model” targeting farmers, dekhan farmers and small plot owners to promote and scale up climate change adaptation measures.
Describe any changes undertaken to improve results on the ground or any changes made to project outputs (i.e. changes to project design) | The management structure needs to be adapted to be more present in the Karakalpakstan region. This management change has been discussed at the project board level and a decision was made at the December 2016 meeting and is being implemented since January 2017.
How have gender considerations been taken into consideration during the reporting period? What have been the lessons learned as a consequence of inclusion of such considerations on project performance or impacts? | Gender considerations were not adequately included in the project design, and there is no specific sections that discuss gender aspects. Project team reports gender disaggregated data in its mid-year and annual reporting as well as in PPRs. The only one indicator is singularly targeting women: “Number of female lead horticulture greenhouses established” but no quantitative target is set for this indicator. Considering that the project is targeting different groups of farmers (commercial farmers, dekhan farmers and small plot owners), project will conducts gender analysis in the pilot areas to better understand gender roles and gender issues in farming and pastoral communities.
Please complete the following section at mid-term and project completion
Lessons for Adaptation | Response
Climate Resilience Measures
What have been the lessons learned, both positive and negative, in implementing climate adaptation measures that would be relevant to the design and implementation of future projects/programmes for enhanced resilience to climate change? | The project is making good progress under outcome 1, which is contributing to strengthen the capacity of Uzhydromet by investing in better equipment to collect weather data and also by supporting the organization in developing weather forecast and models to assess climate change impacts. However, these services do not generate economic and social value unless users benefit from the information provided. A feasibility study may be needed to assess the user needs related to weather information and to assess the potential bottlenecks that may exist to make this information readily available, such as public access to this type of information.
What is the potential for the climate resilience measures undertaken by the project/programme to be replicated and scaled up both within and outside the project area? | Develop an extended “outreach model”– an extension service – that will be piloted with the support of the project in collaboration with the relevant national, regional and local institutions in the five pilot districts has potential for further replication and scaled up within and outside the project area. Setting up a sustainable extension service as a link between policy and legislation decision-makers and farmers (practitioners) but it is also as a mechanism to increase the efficiency of farms while adapting to climate change and increase the standard of living of farming and pastoral communities in Karakalpakstan and overall in Uzbekistan.
Readiness Interventions (Applicable only to NIEs that received one or more readiness grants)
What have been the lessons learned, both positive and negative, in accessing and implementing climate finance readiness support that would be relevant to the preparation, design and implementation of future concrete adaptation projects/programmes? | N/A
How have the outputs (such as manuals, guidelines, procedures or the experience from providing peer support, etc.) from employing readiness grants been used to inform institutional capacity needs, gender issues, and environmental and social aspects in developing and implementing concrete projects/programmes for enhanced resilience to climate change? | N/A
Concrete Adaptation Interventions
What have been the lessons learned, both positive and negative, in implementing concrete adaptation interventions that would be relevant to the design and implementation of future projects/programmes implementing concrete adaptation interventions? | The project is making good progress under outcome 1, which is contributing to strengthen the capacity of Uzhydromet by investing in better equipment to collect weather data and also by supporting the organization in developing weather forecast and models to assess climate change impacts. As per the World Meteorological Organization, investments in this area bring socio-economic benefits; all economic studies have consistently concluded with benefit-cost ratios greater than one. However, these services do not generate economic and social value unless users benefit from decisions as a result of the information provided. To optimize the investments made in this area, it is recommended that the project focuses in making weather information and forecast and climate change models available to farming and pastoral communities (users). A feasibility study may be needed to assess the user needs related to weather information and to assess the potential bottlenecks that may exist to make this information readily available, such as public access to this type of information.
What is the potential for the concrete adaptation interventions undertaken by the project/programme to be replicated and scaled up both within and outside the project area? | Potential replication and scaling up of those services is with integration of achievements within government funded institutions such as Uzhydromet, Ministry of Agriculture, Ministry of Water Resources, local administration, and Council of Farmers, dekhan farms and rural households. The physical infrastructure financed with AF funds, together with the development of capacity for the use of this equipment and the interpretation of data, and complemented by Extension Services provided both in the project area and nationwide will further promote public awareness of the value of weather information and of climate trends and timely adaptation to corresponding impacts.
Community/National Impact
What would you consider to be the most successful aspects for the target communities? | Rural communities involvement in landscape level adaptation measures (e.g. saksaul and tamarix planting) through local employment programme is the most complicated activity to be implemented within the project course but if it succeeds, important environment and social benefits as well as their greater resilience to climate change will be achieved
What measures are/have been put in place to ensure sustainability of the project/program results? | Greater engagement and stronger ownership of all stakeholders, including local authorities and self-government strengthened within all project activities using various approaches and tools (demo meetings, project Boards, round tables, meetings, discussions and consultations)
What measures are being/could have been put in place to improve project/program results? | 1.Programmatic and integrated approach was applied to project activities implementation through joining efforts of the Adaptation project and the UN Joint Programme (Phase II) in the Aral See region (Karakalpakstan, including at least 2 common pilot districts) given the launch of the Joint Programme in 2016. This allows to cover bigger number of beneficiaries in this region with combining and integrating the adaptation and development activities. 2. Development of an extended “outreach model”– an extension service version; and piloting it in collaboration with the relevant national, regional and local institutions in the five pilot districts. 3. Development of recommendations on promotion the most applicable best practices to rural communities
Knowledge Management
How has existing information/data/knowledge been used to inform project development and implementation? What kinds of information/data/knowledge were used? | Knowledge management have been at the forefront of the implementation of the project. It is implemented through three (3) outputs: 4.1: Inventory of all tested agronomic and water saving measures to map out successful practices; 4.2: Analysis and lessons learned for climate resilient agricultural and pastoral production systems in arid lands documented and disseminated through printed and web-based publications; and 4.3: Quarterly farm and pasture land demonstration meetings with participation of national, local authorities, media and communities delivered. Moreover, five best practices were selected, documented and published.
If learning objectives have been established, have they been met? Please describe. | Outlining and establishment of the project's learning objectives are formulated in the project's communication strategy developed in 2016.
Describe any difficulties there have been in accessing or retrieving existing information (data or knowledge) that is relevant to the project. Please provide suggestions for improving access to the relevant data. | Project was faced some difficulties with accessing the social and economic data related to local communities or farming as such statistics is poor or not available. Local communities and farmers are driven by sporadically planning, and therefore they have no knowledge or interest in collecting the data that might help with the planning based on cost-benefit analysis. One of the project's objective is to change the mindset of the targeted groups and convince them in advantages of the long-term planning based on cost-benefit analysis.
Has the identification of learning objectives contributed to the outcomes of the project? In what ways have they contributed? | Learning objectives are an integral part of the project Information Project Strategy developed to facilitate achievement of the targets set and ensuring project outcomes' sustainability beyond the project implementation cycle. Objectives contributed to equipping tools and methods to collect, structure, package and disseminate knowledge on climate change adaptation measures adjusted to the Karakalpakstan region. This provides the project team with instruments to manage knowledge and communicate with stakeholders and beneficiaries.

## Results Tracker
Results Tracker for Adaptation Fund (AF) Projects
Goal: Assist developing-country Parties to the Kyoto Protocol that are particularly vulnerable to the adverse effects of climate change in meeting the costs of concrete adaptation projects and programmes in order to implement climate-resilient measures. Impact: Increased resiliency at the community, national, and regional levels to climate variability and change.
Important: Please read the following guidance document (also posted on the Adaptation Fund website) before entering your data
Link: http://www.adaptation-fund.org/sites/default/files/Results%20Framework%20and%20Baseline%20Guidance%20final.pdf
Adaptation Fund Strategic Results Framework
Project ID | 82613
Implementing Entity | UNDP
Type of implementing entity | MIE
Country | Uzbekistan
Region | Eastern Europe
Sector | Agriculture
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Impact: Increased resiliency at the community, national, and regional levels to climate variability and change | Core Indicator: No. of beneficiaries |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project
|  | Total | 0 | 0 | 0 | Total | 40000 | 20000 | 20000 | Total | 15822 | 5401 | 10421 | Total
|  | % of female beneficiaries | 0% | 0% | 0% | % of female beneficiaries | 20% | 20% | 20% | % of female beneficiaries | 15% | 10% | 18% | % of female beneficiaries
|  | % of Youth beneficiaries |  |  |  | % of Youth beneficiaries |  |  |  | % of Youth beneficiaries |  |  |  | % of Youth beneficiaries
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 1: Reduced exposure to climate-related hazards and threats | Indicator 1: Relevant threat and hazard information generated and disseminated to stakeholders on a timely basis | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness
|  | Total | 0 | Drought | 1: Ineffective | Total | 10000 | Drought | 4: Effective | Total | 1050 | Drought | 2: Partially effective | Total
|  | % of female targeted | 0% |  |  | % of female targeted | 20% |  |  | % of female targeted | 20% |  |  | % of female targeted
Output 1.1 Risk and vulnerability assessments conducted and updated | Indicator 1.1: No. of projects/programmes that conduct and update risk and vulnerability assessments | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | 0 | Agriculture | Local | 1: No plans conducted or updated | 1 | Agriculture | Local | 3: Risk and vulnterability assessments completed or updated | 0 | Agriculture | Local | 1: No plans conducted or updated
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
Output 1.2 Targeted population groups covered by adequate risk reduction systems | Core Indicator 1.2: No. of Early Warning Systems | No. of adopted Early Warning Systems | Category targeted | Hazard | Drought | No. of adopted Early Warning Systems | Category targeted | Hazard | Drought | No. of adopted Early Warning Systems | Category targeted | Hazard | Drought | No. of adopted Early Warning Systems | Category targeted | Hazard
|  | 0 | 2: Monitoring and warning service | Geographical coverage | Regional | 1 | 2: Monitoring and warning service | Geographical coverage | Regional | 1 | 2: Monitoring and warning service | Geographical coverage | Local |  |  | Geographical coverage
|  |  |  | Number of municipalities | 0 |  |  | Number of municipalities | 3 |  |  | Number of municipalities | 1 |  |  | Number of municipalities
|  | No. of adopted Early Warning Systems | Category targeted | Hazard | Drought | No. of adopted Early Warning Systems | Category targeted | Hazard | Drought | No. of adopted Early Warning Systems | Category targeted | Hazard | Drought | No. of adopted Early Warning Systems | Category targeted | Hazard
|  | 0 | 3: Dissemination and communication | Geographical coverage | Regional | 1 | 3: Dissemination and communication | Geographical coverage | Regional | 0 | 3: Dissemination and communication | Geographical coverage | Regional |  |  | Geographical coverage
|  |  |  | Number of municipalities | 0 |  |  | Number of municipalities | 3 |  |  | Number of municipalities | 0 |  |  | Number of municipalities
|  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 2: Strengthened institutional capacity to reduce risks associated with climate-induced socioeconomic and environmental losses | Indicator 2: Capacity of staff to respond to, and mitigate impacts of, climate-related events from targeted institutions increased | Number of staff targeted |  | Sector | Capacity level | Number of staff targeted |  | Sector | Capacity level | Number of staff targeted |  | Sector | Capacity level | Number of staff targeted |  | Sector | Capacity level
|  | Total | 0 | Agriculture | 2: Low capacity | Total | 200 | Agriculture | 3: Medium capacity | Total | 91 | Agriculture | 3: Medium capacity | Total
|  | % of female targeted | 0% |  |  | % of female targeted | 20% |  |  | % of female targeted | 20% |  |  | % of female targeted
Output 2.1 Strengthened capacity of national and sub-national centres and networks to respond rapidly to extreme weather events | Indicator 2.1.1: No. of staff trained to respond to, and mitigate impacts of, climate-related events | Total staff trained | % of female staff trained | Type |  | Total staff trained | % of female staff trained | Type |  | Total staff trained | % of female staff trained | Type |  | Total staff trained | % of female staff trained | Type
|  | 0 | 0% | Public |  | 200 | 20% | Public |  | 91 | 20% | Public
| Indicator 2.1.2: No. of targeted institutions with increased capacity to minimize exposure to climate variability risks | Type | Scale | Sector | Capacity level | Type | Scale | Sector | Capacity level | Type | Scale | Sector | Capacity level | Type | Scale | Sector | Capacity level
|  | Public | Regional | Agriculture | 2: Low capacity | Public | Local | Agriculture | 3: Medium capacity | Public | Local | Agriculture | 2: Low capacity
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 3: Strengthened awareness and owernship of adaptation and climate risk reduction processes | Indicator 3.1: Increase in application of appropriate adaptation responses | Percentage of targeted population applying adaptation measures |  | Sector |  | Percentage of targeted population applying adaptation measures |  | Sector |  | Percentage of targeted population applying adaptation measures |  | Sector |  | Percentage of targeted population applying adaptation measures |  | Sector
|  | 0% |  | Agriculture |  | 100 |  | Agriculture |  | 10 |  | Agriculture
Output 3: Targeted population groups participating in adaptation and risk reduction awareness activities | Indicator 3.1.1: Percentage of targeted population awareness of predicted adverse impacts of climate change, and of appropriate responses | No. of targeted beneficiaries | % of female participants targeted | Level of awareness |  | No. of targeted beneficiaries | % of female participants targeted | Level of awareness |  | No. of targeted beneficiaries | % of female participants targeted | Level of awareness |  | No. of targeted beneficiaries | % of female participants targeted | Level of awareness
|  | 0 | 0% | 1: Aware of neither |  | 40000 | 20% | 4: Mostly aware |  | 5225 | 15% | 3: Partially aware
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Target performance at completion |  |  |  | Performance at completion
Outcome 4: Increased adaptive capacity within relevant development sector services and infrastructure assets | Indicator 4.1: Increased responsiveness of development sector services to evolving needs from changing and variable climate | Project/programme sector | Geographical scale | Response level |  | Project/programme sector | Geographical scale | Response level |  | Project/programme sector | Geographical scale | Response level |  | Project/programme sector | Geographical scale | Response level
|  | Agriculture | Local | 2: Partially responsive (Lacks most elements) |  | Agriculture | Regional | 3: Moderately responsive (Some defined elements) |  | Agriculture | Local | 2: Partially responsive (Lacks most elements)
| Core Indicator 4.2: Assets produced, developed, improved or strengthened | Sector | Targeted asset | Changes in asset (quantitative or qualitative) |  | Sector | Targeted asset | Changes in asset (quantitative or qualitative) |  | Sector | Targeted asset | Changes in asset (quantitative or qualitative) |  | Sector | Targeted asset | Changes in asset (quantitative or qualitative)
|  | Agriculture | 2: Physical asset (produced/improved/strenghtened) | 2: Somewhat improved |  | Agriculture | 2: Physical asset (produced/improved/strengthened) | 3: Moderately improved |  | Agriculture | 2: Physical asset (produced/improved/strengthened) | 2: Somewhat improved
|  | Water management | 2: Physical asset (produced/improved/strenghtened) | 2: Somewhat improved |  | Water management | 2: Physical asset (produced/improved/strengthened) | 3: Moderately improved |  | Water management | 2: Physical asset (produced/improved/strengthened) | 2: Somewhat improved
|  | Disaster risk reduction | 2: Physical asset (produced/improved/strenghtened) | 1: Not improved |  | Disaster risk reduction | 2: Physical asset (produced/improved/strenghtened) | 3: Moderately improved |  | Disaster risk reduction | 1: Health and Social Infrastructure (developed/improved) | 2: Somewhat improved
Output 4: Vulnerable development sector services and infrastructure assets strengthened in response to climate change impacts, including variability | Indicator 4.1.1: No. and type of development sector services to respond to new conditions resulting from climate variability and change | Number of services | Type |  | Sector | Number of services | Type |  | Sector | Number of services | Type |  | Sector | Number of services | Type |  | Sector
|  | 0 | Multi-community |  | Agriculture | 7 | Multi-community |  | Agriculture | 5 | Community |  | Agriculture
|  | 0 | Multi-community |  | Water management | 5 | Multi-community |  | Water management | 3 | Community |  | Water management
|  | 0 | Multi-community |  | Disaster risk reduction | 3 | Multi-community |  | Disaster risk reduction | 1 | Community |  | Disaster risk reduction
|  | Baseline information |  |  |  | Targeted performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 5: Increased ecosystem resilience in response to climate change and variability-induced stress | Indicator 5: Ecosystem services and natural resource assets maintained or improved under climate change and variability-induced stress | Natural resource improvement level |  | Sector | Type | Natural resource improvement level |  | Sector | Type | Natural resource improvement level |  | Sector | Type | Natural resource improvement level |  | Sector | Type
|  | 2: Partially effective |  | Agriculture | land | 2: Partially effective |  | Agriculture | land | 2: Partially effective |  | Agriculture | land
Output 5: Vulnerable ecosystem services and natural resource assets strengthned in response to climate change impacts, including variability | Core Indicator 5.1: Natural Assets protected or rehabilitated | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Forests |  | ha rehabilitated | 1: Ineffective | Forests | 70000 | ha rehabilitated | 3: Moderately effective | Forests | 3000 | ha rehabilitated | 2: Partially effective
|  | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Cultivated land/Agricultural land |  | ha protected | 1: Ineffective | Cultivated land/Agricultural land | 20000 | ha protected | 4: Effective | Cultivated land/Agricultural land | 1390 | ha protected | 2: Partially effective
|  | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Baseline information |  |  |  | Targeted performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 6: Diversified and strengthened livelihoods and sources of income for vulnerable people in targeted areas | Indicator 6.1: Increase in households and communities having more secure access to livelihood assets | No. of targeted households | % of female headed households | Improvement level |  | No. of targeted households | % of female headed households | Improvement level |  | No. of targeted households | % of female headed households | Improvement level |  | No. of targeted households | % of female headed households | Improvement level
|  | 16000 | 20% | 1: No improvement |  | 16000 | 20% | 4: High improvement |  | 145 | 15% | 2: Limited improvement
| Indicator 6.2: Increase in targeted population's sustained climate-resilient alternative livelihoods | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
|  | 0 | 0% | From 0 to 0.5% | Agribusiness | 16000 | 20% | From 10% to 20% | Agribusiness | 145 | 15% | From 1% to 5% | Agribusiness
|  | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
|  | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
|  | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
Output 6 Targeted individual and community livelihood strategies strengthened in relation to climate change impacts, including variability | Indicator 6.1.1: No. and type of adaptation assets created or strengthened in support of individual or community livelihood strategies | Number of Assets | Type of Assets | Sector | Adaptation strategy | Number of Assets | Type of Assets | Sector | Adaptation strategy | Number of Assets | Type of Assets | Sector | Adaptation strategy | Number of Assets | Type of Assets | Sector | Adaptation strategy
|  | 0 | Physical capital | Agriculture | Community-based adaptation | 595 | Physical capital | Agriculture | Community-based adaptation | 50 | Physical capital | Multi-sector | Community-based adaptation
| Core Indicator 6.1.2: Increased income, or avoided decrease in income | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 7: Improved policies and regulations that promote and enforce resilience measures | Indicator 7: Climate change priorities are integrated into national development strategy | Integration level |  |  |  | Integration level |  |  |  | Integration level |  |  |  | Integration level
|  | 1: None |  |  |  | 3: Some |  |  |  | 3: Some
Output 7:Improved integration of climate-resilience strategies into country development plans | Indicator 7.1: No. of policies introduced or adjusted to address climate change risks | No. of Policies introduced or adjusted | Sector | Scale | Type | No. of Policies introduced or adjusted | Sector | Scale | Type | No. of Policies introduced or adjusted | Sector | Scale | Type | No. of Policies introduced or adjusted | Sector | Scale | Type
|  | 0 | Agriculture | Regional | Public policy | 3 | Agriculture | Regional | Public policy | 1 | Agriculture | Regional | Public policy
| Indicator 7.2: No. of targeted development strategies with incorporated climate change priorities enforced | No. of Development strategies | Regulation |  | Effectiveness | No. of Development strategies | Regulation |  | Effectiveness | No. of Development strategies | Regulation |  | Effectiveness | No. of Development strategies | Regulation |  | Effectiveness
|  | 0 | 1: Not enforced (No elements implemented) |  | 1: Ineffective | 1 | 3: Partially enforced (Some elements implemented) |  | 3: Moderately effective | 1 | 2: Partially not enforced (Most elements not implemented) |  | 2: Partially effective
Glacier lake outburst flood
|  | Inland flooding | fr | biological assets |  | Company policy | 5: Fully enforced (All elements implemented)
|  | Salinization | Decrease | land |  | Communication & Information policy | 4: Enforced (Most elements implemented)
|  | Drought | Same | water areas |  | Defense policy | 3: Partially enforced (Some elements implemented)
|  | Wind |  | subsoil assets | increased adpative capacity | Domestic policy | 2: Partially not enforced (Most elements not implemented) |  | Agribusiness
|  | Coastal flooding |  | air | achieved | Economic policy | 1: Not enforced (No elements implemented) |  | Agricultural-related | Financial capital
|  | Storm surge | Please choose |  | enhanced level of protection | Education policy |  |  | Agriculture | Human capital
|  | Hurricane | Selected | [5 empty] | Aquaculture | Physical capital
|  |  | Not relevant |  |  | 5: All (Fully integrated) |  |  | Construction/repairing business | Social capital
[6 empty] | 4: Most |  |  | Cultivation | Natural capital
[6 empty] | 3: Some |  |  | Fishing | Personal capital
Select | 5: All | Select |  |  | Community | 2: Most not integrated |  | Other | Forestry | Adaptation strategies
1 | 4: Almost all | Private | Type | Yes | Multi-community | 1: None |  | Agriculture | Handicrafts
2 | 3: Half | Public | Scale | No | Departmental |  |  | Coastal management | Livestock production
3 | 2: Some | NGO | Sector |  | National |  |  | Disaster risk reduction | Manufacturing
4 | 1: None |  |  |  |  | 5: Very high improvement | Established | Food security | other
|  | National |  |  |  | 4: High improvement | Maintained | Health | Services
|  | Regional |  |  |  | 3: Moderate improvement | Improved | Urban development | Tourism-related
|  | Local |  |  |  | 2: Limited improvement |  | Water management | Trading
[6 empty] | 1: No improvement |  | Multi-sector
|  | 1 -generated information is irrelevant, and neither the stakeholders reached nor the timeframe managed were achieved | 1: No info transferred on time | 4: High capacity | 5: Fully aware | 5: Highly responsive (All defined elements ) | 5: Fully improved | Roads | 5: Very effective
Asia-Pacific | NIE | 2 -the existence of some challenge in any of the three aspects of the indicator (generation of dissemination, stakeholders reached or timeframe managed) | 2: Somewhat info transferred | 3: Medium capacity | 4: Mostly aware | 4: Mostly responsive (Most defined elements) | 4: Mostly Improved | Gov Buildings | 4: Effective
Latin America and Caribbean | RIE | 3 -relevant information is generated and disseminated to all identified stakeholders on timely basis | 3: Info transferred on time | 2: Low capacity | 3: Partially aware | 3: Moderately responsive (Some defined elements) | 3: Moderately improved | Causeways | 3: Moderately effective
Africa | MIE |  |  | 1: No capacity | 2: Partially not aware | 2: Partially responsive (Lacks most elements) | 2: Somewhat improved | Airports | 2: Partially effective
Eastern Europe |  |  |  |  | 1: Aware of neither | 1: Non responsive (Lacks all elements ) | 1: Not improved | Schools | 1: Ineffective
| ha protected | [6 empty] | Training Centres
| ha rehabilitated | [5 empty] | Monitoring/Forecasting capacity | Hospitals
Afghanistan, Islamic Rep. of | km protected | [5 empty] | Policy/regulatory reform | Drinking water systems
Angola | km rehabilitated | 1: Risk knowledge | 1: No plans conducted or updated |  |  |  | Capacity development | Other
Albania |  | 2: Monitoring and warning service | 2: Undertaking or updating of assessments in progress |  |  | Communication & Information policy | Sustainable forest management
Argentina |  | 3: Dissemination and communication | 3: Risk and vulnterability assessments completed or updated |  |  | Domestic policy | Strengthening infrastructure | 1: Health and Social Infrastructure (developed/improved)
Armenia | Forests | 4: Response capability |  |  |  | Economic policy | Supporting livelihoods | 2: Physical asset (produced/improved/strenghtened)
Antigua and Barbuda | Mangroves |  |  |  |  | Education policy | Mangrove reforestation
Azerbaijan | Coasts |  | From 0 to 0.5% |  |  | Energy policy | Coastal drainage and infrastructure
Burundi | Rangelands |  | From 0.5 to 1% |  |  | Environmental policy | Irrigation system
Benin | Cultivated land/Agricultural land |  | From 1% to 5% |  |  | Foreign policy | Community-based adaptation
Burkina Faso | Catchment area/Watershed/Aquifer |  | From 5% to 10% |  |  | Health policy | Erosion control
Bangladesh | Protected areas/National parks |  | From 10% to 20% |  |  | Housing policy | Soil water conservation
Bulgaria | Other |  | From 20% to 30% |  |  | Human resource policies | Microfinance
Bahrain |  |  | From 30% to 40% |  |  | Information policy | Special Program for women
Bahamas, The |  |  | From 40% to 50% |  |  | Macroeconomic policy | Livelihoods
Bosnia and Herzegovina |  |  | Above 50% |  |  | Monetary policy | Water storage
Belarus | [5 empty] | Population policy | ICT and information dissemination
Belize | [5 empty] | Private policy
Bolivia | [5 empty] | Public policy
Brazil | [5 empty] | Science policy
Barbados | [5 empty] | Social policy
Bhutan |  | 3- relevant information is generated and disseminated to all identified stakeholders on timely basis |  |  |  | Transportation policy
Botswana |  | describe |  |  |  | Urban policy
Central African Republic |  | 2- the existence of some challenge in any of the three aspects of the indicator |  |  |  | Water policy
Chile |  | describe |  |  |  | Other policy
China, People's Republic of |  | 1- generated information is irrelevant and neither the stakeholders reached nor the timeframe managed were achieved
Cote d'Ivoire |  | describe
Cameroon
Congo, Dem. Rep. of
Congo, Republic of
Cook Islands
Colombia
Comoros
Cape Verde
Costa Rica
Cuba
Czech Republic
Djibouti
Dominica
Dominican Republic
Algeria
Ecuador
Egypt
Eritrea
Estonia
Ethiopia
Fiji
Micronesia, Fed. States of
Gabon
Georgia
Ghana
Guinea
Gambia, The
Guinea-Bissau
Equatorial Guinea
Grenada
Guatemala
Guyana
Honduras
Croatia
Haiti
Hungary
Indonesia
India
Iran, Islamic Republic of
Jamaica
Jordan
Kazakhstan
Kenya
Kyrgyz Republic
Cambodia
Kiribati
Saint Kitts and Nevis
Korea, Republic of
Lao People's Democratic Republic
Lebanon
Liberia
Libya
Saint Lucia
Sri Lanka
Lesotho
Lithuania
Latvia
Morocco
Moldova
Madagascar
Maldives
Mexico
Marshall Islands
Macedonia, former Yugoslav Republic of
Mali
Malta
Myanmar
Montenegro
Mongolia
Mozambique
Mauritania
Mauritius
Malawi
Malaysia
Namibia
Niger
Nigeria
Nicaragua
Niue
Nepal
Nauru
Oman
Pakistan
Panama
Peru
Philippines
Palau
Papua New Guinea
Poland
Korea, Dem. People's Rep. of
Paraguay
Romania
Russian Federation
Rwanda
Saudi Arabia
Sudan
Senegal
Solomon Islands
Sierra Leone
El Salvador
San Marino
Serbia
Sao Tome and Principe
Suriname
Slovak Republic
Slovenia
Swaziland
Seychelles
Syrian Arab Republic
Chad
Togo
Thailand
Tajikistan
Turkmenistan
Tonga
Trinidad and Tobago
Tunisia
Turkey
Tuvalu
Tanzania
Uganda
Ukraine
Uruguay
Uzbekistan
Saint Vincent and the Grenadines
Venezuela
Vietnam
Vanuatu
Samoa
Yemen, Republic of
South Africa
Zambia
Zimbabwe
Timor-Leste

## Units for Indicators
Fund Outcome Indicator Units
1. Generation of relevant data, Stakeholders, and Timeliness 2.1. Include both qualitative and quantitative measures of capacity level within targeted institutions 2.2. Number (men and women and other vulnerable groups) 3.1. Use scale from 1 to 5: 5: Fully aware 4: Mostly aware 3: Partially aware 2: Partially not aware 1: Aware of neither predicted adverse impacts of climate change nor of appropriate responses 3.2. Use scale from 1 to 5: 5: All 4: Almost all 3: Half 2: Some 1: None 4.1. Summarize in an overall scale (1-5): 5: Highly responsive (All defined elements ) 4: Mostly responsive (Most defined elements) 3: Moderately responsive (Some defined elements) 2: Partially responsive (Lacks most elements) 1: Non responsive (Lacks all elements ) 4.2. Summarize in an overall scale (1-5): 5: Fully improved 4: Mostly Improved 3: Moderately improved 2: Somewhat improved 1: Not improved 5. Depends on the targeted natural asset: Biological (species): measure through changes in population numbers (dynamics, structure, etc.) Land: measure changes in hectares. Baseline data will be necessary to estimate the change. Supporting indicators baseline and target (as well as contextual information) are needed such as the following: Farmers adopting recommended technologies, Ha. of land improved, Average deforestation rate Etc. Use scale from 1 to 5. 5: Very effective (All elements are present) 4: Effective (Most elements are present) 3: Moderately effective (Some elements are present) 2: Partially effective (Most elements are not present) 1: Ineffective (No elements are present) 6.1. Summarize in an overall scale (1-5): 5: Very high improvement 4: High improvement 3: Moderate improvement 2: Limited improvement 1: No improvement 6.2. Household income by source of livelihood in project area (USD) prior and post project intervention 7. Summarize in an overall scale (1-5). 5: All (Fully integrated) 4: Most 3: Some 2: Most not integrated 1: None
Fund Output Indicator Units
1.1. Number, sector(s) and level(s) of projects or interventions in separate fields of monitoring plan 1.2. Number 2.1.1. Number of staff (male/female) of targeted institutions: a. Obtain baseline information: total number of staff from targeted institutions b. Define target 2.1.2. Number of staff (male/female) of targeted institutions: a. Obtain baseline information: total number of staff from targeted institutions b. Define target: needs to be defined by project proponents 2.2.1. Quantitative: Percentage (includes women – and other vulnerable groups – and men). Qualitative: Adequacy: include direct analysis of major areas; adequacy/effectiveness of systems or analysis of perceptions of populations and institutions. 2.2.2. Number (broken down by gender and, if possible, by vulnerable groups defined in the area of intervention) of people 3.1. Number and type (in separate columns) at local level. 3.2. Number 4.1. Number and type 4. 2. Number and type (entered in separate columns) 5. Number of interventions by type of natural asset and intervention 6.1. Number and type (in separate columns of monitoring plan) 6.2. Income sources per household; description of income source and number of households. 7.1. Number/Sector 7.2. Number; Effectiveness (see previous indicator) through enforcement level.