## Overview
Project Performance Report (PPR)
| Period of Report (Dates) | March 2015 - March 2016
| Project Title: | Belize Marine Conservation and Climate Adaptation Project (MCCAP)
| Project Summary: | The Belize Marine Conservation and Climate Adaptation Project (MCCAP) is a five year project implemented by the World Bank and funded by the Adaptation Fund grant in the amount of US$ 5.53 million and US$ 1.78 million in-kind contribution by the Government of Belize. The objective of MCCAP is to implement priority ecosystem-based marine conservation and climate adaptation measures to strengthen the climate resilience of the Belize Barrier Reef System. Specifically, the Project will support: (1) improvement of the coral reef protection regime including an expansion and enforcement of the MPAs and replenishment (no-take) zones in strategic locations to build climate resilience; (2) promote sustainable alternative livelihoods and income diversification for affected users of the reef, and (3) build local capacity and raising awareness regarding the importance of the overall health of the reef ecosystem to its climate resilience and, consequently the community welfare as well as the growth prospect of the country's economy. The proposed adaptation, conservation, and restoration activities of the Belize Barrier Reef System have socio-economic significance, providing and opportunity for maintaining and potentially increasing the income level and marine resources available dor an estimated 203,000 people living in the coastal areas of Belize. The Project will build capacity for local communities, which are directly affected by the climate impacts, to act as champions of the marine managed areas and of the resources upon which they depend.
|  | The main components are: (1) Improving the Protection Regime of marine and coastal ecosystem (AF resources: USD 2 million; in-kind contribution by the Government of Belize and NGOs USD 0.415 million). (2) Promotion of viable and sustainable alternative livelihoods for afftected users of the reef (AF resources: USD 2.45 million; in-kind contributions from GOB and NGOs USD 0.368 million). (3) Raising awareness, building local capacity, and disseminating information (AF resources: USD 0.56 million). | [9 empty] | ,
|  |  | Countries | Project Type: |  | GEF Focal Area: | GEF 4 Focal Areas | GEF 2 / 3 Operational Programme: | Overall Rating of the project in the evaluation by the project evaluator: | GEF-4 Focal Area Strategic Program: | GEF-3 Focal Area Strategic Program:
| Database Number: | P131408 | Afghanistan | FP | Yes | Biodiversity | 1 | 1 | U | BD-SP1-PA Financing | 1: Arid & semi-arid ecosystems
Implementing Entity (IE) [name]: |  | World Bank | Albania | MSP | No | Climate Change Adaptation | 2 | 2 | S | BD-SP2-Marine PA | 2: Coastal, marine & freshwater ecosystems
| Type of IE: | Multilateral | Algeria | EA |  | Climate Change Mitigation | 3 | 3 | MU | BD-SP3-PA Networks | 3: Forest ecosystems
| Country(ies): | Belize | Angola |  |  | International Waters | 5 | 5 | Good | BD-SP5-Markets | 13: Conservation and Sustainable Use of Biological Diversity Important to Agriculture
Relevant Geographic Points (i.e. cities, villages, bodies of water): |  | Marine Protected Areas - Corozal Bay Wildlife Sanctuary (CBWS), Turneffe Atoll Marine Reserve (TAMR), and South Water Caye Marine Reserve (SWCMR). Fishing communities - Consejo, Corozal, Copper Bank, Chunox, Sarteneja, Belize City, Dangriga, Hopkins, Sittee River, Riversdale, Seine Bight, Placencia | Argentina |  |  | Multiple Focal Area |  |  |  | BD-SP7-Invasive Alien Species(IAS) | 6: Promoting the adoption of renewable energy by removing barriers and reducing implementation costs
[8 empty] | CC-SP2- Industrial EE | 8: Waterbody based operational program
| Project Milestones | [6 empty] | CC-SP3-RE,CC-SP4-Biomass | 9: Integrated Land and Water multiple focal area
| Milestone |  | Bahamas | [6 empty] | CC-SP5-Transport | 10: Contaminants based operational program
AFB Approval Date: |  | 2014-08-18
IE-AFB Agreement Signature Date: |  | 2014-08-26 | [6 empty] | CC-SP6-LULUCF | 12: Integrated Ecosystem Management
Start of Project/Programme: |  | 3/17/2015 (Inception workshop) | [6 empty] | Cross cutting capacity building | 14: Persistent Organic Pollutants
Mid-term Review Date (if planned): |  | 2017-09-25
| Terminal Evaluation Date: | 2020-03-31
|  | List documents/ reports/ brochures / articles that have been prepared about the project. | Cyprus
Reports
(1) MCCAP project inception workshop report (2015)
(2) Flyer with general information on MCCAP;
(3) Project Operations Manual - Revised May 2015
(4) Annual Operational Plan and Procurement Plan (2015/2016)
Safeguard documents (5) Environmental Management Framework (6) Indigenous Peoples’ Plan (7) Resettlement Process Framework
Technical Documents
(8) Draft Comprehensive Fisheries Enforcement and Training Manual (2015);
(9) Integrated Enforcement and Prosecution Training Outline (2015);
(10) CZMAI Water Quality monitoring programme protocol manual (2015);
(11) CZMAI coastal and marine data centre aerial survey report (2016);
(12) Press Releases - CHANNEL 7 NEWS http://www.7newsbelize.com/sstory.php?nid=31905 Getting the Climate Change Message Out To The Community posted (March 17, 2015)
(13) KAP Survey: Inception Report v 1.1 (Sept 2015)
(14) KAP Survey: Survey Protocol and Instruments (December 2015)
(15) Report on the sustainable livelihood forum (2016)
(16) Fish guide (2016)
|  | (17) Quarterly and Annual Progress Reports | Czech Republic
List the Website address (URL) of project. |  |  | Democratic People's Republic of Korea
|  | TBD | Democratic Republic of the Congo
Denmark
| Project contacts: |  | Djibouti
National Project Manager/Coordinator |  | MCCAP | Dominica
| Name: | Sandra Grant | Dominican Republic
| Email: | pc.mccap@ffsd.gov.bz | Ecuador
| Date: | 2015-03-03 | Egypt
| Government DA | Fisheries Department | El Salvador
| Name: | Beverly Wade | Equatoral Guinea
| Email: | fa@ffsd.gov.bz | Eritrea
| Date: |  | Estonia
| Government DA | Coastal Zone Management Authority and Institute (CZMAI) | Ethiopia
| Name: | Chantalle Clarke-Samuels | Fiji
| Email: | ceo@coastalzone. | Finland
| Date: |  | France
| Government DA | Forest Department | Gambia
| Name: | Wilber Sabido | Georgia
| Email: | cfo@forest.gov.bz | Germany
| Date: |  | Ghana
| NIE | PACT | Greece
| Name: | Dennisia Francisco | Grenada
| Email: | ed@pactbelize.org | Guatemala
| Date: |  | Guinea
| MIE | World Bank
| Name: | Enos Esikuri (Team Leader)
| Email: | eesikuri@worldbank.org
Date:
| Executing Agency | Ministry of Agriculture, Fisheries, Forestry, the Environment and Sustainable Development (MAFFESD) | Guinea Bissau
| Name: | Jose Alpuche | Guyana
| Email: | ceo@agriculture.gov.bz | Haiti
| Date: | 2015-11-06 | Honduras
Hungary
Iceland
India
Indonesia
Iran (Islamic Republic of)
Iraq
Ireland
Israel
Italy
Jamaica
Japan
Jordan
Kazakhstan
Kenya
Kiribati
Kuwait
Kyrgyzstan
Lao People’s Democratic Republic
Latvia
Lebanon
Lesotho
Liberia
Libyan Arab Jamahiriya
Liechtenstein
Lithuania
Luxembourg
Madagascar
Malawi
Malaysia
Maldives
Mali
Malta
Marshall Islands
Mauritania
Mauritius
Mexico
Micronesia, Federated States of
Monaco
Mongolia
Montenegro
Morocco
Mozambique
Myanmar
Namibia
Nauru
Nepal
Netherlands
New Zealand
Nicaragua
Niger
Nigeria
Norway
Oman
Pakistan
Palau
Panama
Papua New Guinea
Paraguay
Peru
Philippines
Poland
Portugal
Qatar
Republic of Korea
Republic of Moldova
Romania
Russian Federation
Rwanda
Saint Kitts and Nevis
Saint Lucia
Saint Vincent and the Grenadines
Samoa
San Marino
Sao Tome and Principe
Saudi Arabia
Senegal
Serbia
Seychelles
Sierra Leone
Singapore
Slovakia
Slovenia
Solomon Islands
Somalia
South Africa
Spain
Sri Lanka
Sudan
Suriname
Swaziland
Sweden
Switzerland
Syrian Arab Republic
Tajikistan
Thailand
The former Yugoslav Republic of Macedonia
Timor-Leste
Togo
Tonga
Trinidad and Tobago
Tunisia
Turkey
Turkmenistan
Tuvalu
Uganda
Ukraine
United Arab Emirates
United Kingdom of Great Britain and Northern Ireland
United Republic of Tanzania
United States of America
Uruguay
Uzbekistan
Vanuatu
Venezuela, Bolivarian Republic of
Viet Nam
Yemen
Zambia
Zimbabwe

## FinancialData
Financial information: cumulative from project start to March 2, 2016
DISBURSEMENT OF AF GRANT FUNDS
How much of the total AF grant as noted in Project Document plus any project preparation grant has been spent to date?
Estimated cumulative total disbursement as of March 2, 2016 | 370244.87
Add any comments on AF Grant Funds. (word limit=200) | The PACT Board of Directors approved retroactive financing for MCCAP of US140,000.00 in April, 2014 – ref: Minutes of Negotiations of January 21, 2015 – signed by Mrs. Yvonne Hyde (CEO Ministry of Finance and Economic Development) and Mr. Enos Esikuri (Senior Environmental Specialist and Task Team Leader of the World Bank Group). These funds were credited to the PACT/MCCAP operational account at the Belize Bank LTD account no. 645 1 1 19079 in April, 2015.
The total budget, based on the Annual Operations Plan 2015/2016 budget is USD1,437,370.00. The first withdrawal of Project funds USD 500,000 was credited to the Designated Account (DA) No. 311091 at the Central Bank of Belize on 24th September 2015. PACT applied for refund of retroactive finance of USD140,000.00 from the World Bank.
The new audit period for MCCAP will be for the period April 1, 2015 to March 31, 2016, and the due date for the audit report will be July 31, 2016. Since, the project is a Grant, only the Grant monies for the MCCAP project disbursed to PACT from the World Bank will be audited.
Project expenditure for the interim period March 3, 2015 - March 2, 2016 (reported on the accrual basis of accounting) amounts to US $ 370,244.87
INVESTMENT INCOME | 0
Amount of annual investment income generated from the Adaptation Fund’s grant
EXPENDITURE DATA
List ouput and corresponding amount spent for the current reporting period | ITEM / ACTIVITY / ACTION | AMOUNT (USD)
Component 1 - USD 170,851.23
| 1.1 Spatially map and analyse target MPAs for realignment or expansion | 6290.33
| 1.2 Verify spatial mapping via ground-truthing | 0
| 1.3 Mapping of proposed revised zoning scheme prepared for feedback | 0
| 1.4 Consultations carried out with communities and stakeholders to obtain feedback on the revised zoning | 0
| 1.5 Consultation feedback and baseline data compiled and incorporated into zoning map | 0
| 1.6 Final revised map incorporated into the existing management plan for target MPAs and management plans textually adjusted to reflect zoning adjustment | 0
| 1.7 Target MPAs demarcated with buoys and signage as per the new boundaries | 0
| 1.8 Enhancement of enforcement and monitoring of selected MPAs, including replenishment zones | 135413.6
| 1.9 Biological monitoring of strategic and control sites | 8617.56
| 1.10 Management effectiveness assessments using tracking tools | 0
| 1.11 Ground-truthing to identify reefs suitable for nurseries set-up | 0
| 1.12 Establishment of coral nurseries | 0
| 1.13 Out-planting in selected reefs | 0
| 1.14 Rolling out of the over-arching PA legislation | 0
| 1.15 Initial support to the PA administration structure | 0
| 1.16 Revision of mangrove regulations | 6993.5
| 1.17 Revision of the CZM Act | 0
| 1.18 Implementation of an Integrated Coastal Zone Management Plan | 13536.25
Component 2 - USD 46,440.54
| 2.1 Communtiy needs assessment workshops | 5772.63
| 2.2 Participatory sub-project planning workshop | 0
| 2.3 Development of business plans | 0
| 2.4 Marketing support for business venture | 0
| 2.5 Training in business development | 0
| 2.6 Training in marketable skills | 0
| 2.7 Sub-grants for initial capital investment to support the startup of business venture | 40667.91
Component 3 - USD 51,744.32
| 3.1 Development and implementation of KAP survey (including instrument, field data collection, analysis, presentation of findings | 51395
| 3.2 Development of BCC strategy and action plan | 0
| 3.3 Implementation of BCC strategy and action plan | 0
| 3.4 Updates of project activities (via quarterly electronic and print newsletters) | 349.32
| 3.5 Web-based platform | 0
| 3.6 Best practice forum | 0
| 3.7 Learning events, leadership development, training | 0
| 3.8 Strategic planning for the network | 0
Project execution cost (PIU/NIE) - USD 101,208.79
| Coordination and management | 50018.43
| Overheads and administration | 18301.82
| Monitoring and Evalution | 2888.54
| Fudiciary management | 30000
| SUB-TOTAL | 370244.89
Contracts awarded, finalizing procurement process
| 2 vehicles | 80693.2
| Computers, laptops | 33034.17
| SUB-TOTAL | 113727.37
PLANNED EXPENDITURE SCHEDULE
List outputs planned and corresponding projected cost for the upcoming reporting period | ITEM / ACTIVITY / ACTION | PROJECTED COST | Est. Completion Date
Component 1: Improving the protection regime of marine and coastal ecosystems
| 1.1 Spatially map and analyse target MPAs for realignment or expansion | 0 | Completed
| 1.2 Verify spatial mapping via ground-truthing | 20000
| 1.3 Mapping of proposed revised zoning scheme prepared for feedback | 0
| 1.4 Consultations carried out with communities and stakeholders to obtain feedback on the revised zoning | 30000 | 2016-06-01
| 1.5 Consultations feedback and baseline data complied and incorporated into zoning map | 15000 | 2016-06-01
| 1.6 Final revised map incorporated into the existing management plan for target MPAs and management plans textually adjusted to reflect zoning adjustments | 45000 | 2016-09-01
| 1.7 Target MPAs demarcated with buoys and signage as per the new boundaries | 130000 | 2016-12-01
| 1.8 Enhancement of enforcement and monitoring of selected MPAs, including replenishment zones | 50000 | 2017-03-01
| 1.9 Biological and water quality monitoring of strategic and control sites within selected MPAs | 20000 | 2017-03-01
| 1.10 Management effectiveness assessments using tracking tools | 17775 | 2017-02-01
| 1.11 Ground-truthing to identify reefs suitable for nurseries set-up | 40000 | 2017-02-01
| 1.12 Establishment of coral nurseries | 60000 | 2017-03-01
| 1.13 Out-planting in selected reefs | 75000 | 2017-03-01
| 1.14 Rolling out of the over-arching PA legislation | 0
| 1.15 Initial support to the PA administration structure | 0
| 1.16 Revision of mangrove regulations | 25000 | 2016-09-01
| 1.17 Revision of the CZM Act | 90000 | 2016-09-01
| 1.18 Implementation of an integrated Coastal Zone Management Plan | 100000 | 2017-03-01
Component 2: Promotion of viable and sustainable alternative livelihoods for affected users of the reef
| 2.1 Community needs assessment | 19000 | 2017-03-01
| 2.2 Participatory sub-project planning workshop | 22000 | 2017-03-01
| 2.3 Development of business plans | 33000 | 2017-03-01
| 2.4 Marketing support for business venture | 36000 | 2017-03-01
| 2.5 Training in business development | 10000 | 2017-03-01
| 2.6 Training in marketable skills | 10000 | 2017-03-01
| 2.7 Sub-grants for initial capital investment to support the startup of business venture | 600000 | 2017-03-01
Component 3: Raising awareness, building local capacity and dissemination of information
| 3.1 Development and implementation of KAP survey (including instrument, field data collection, analysis, presentation of findings | 0 | Completed
| 3.2 Development of a BCC Strategy and Action Plan | 25000 | 2016-06-01
| 3.3 Implementation of a BCC strategy and action plan | 45000 | 2016-09-01
| 3.4 Updates of project activities | 6800 | 2017-03-01
| 3.5 Website platform | 4500 | 2016-06-01
| 3.6 Best practice forum | 17500 | 2017-03-01
| 3.7 Learning events, leadership development, training | 75000 | 2016-12-01
| 3.8 Strategic planning for the network | 15000 | 2016-12-01
Project execution cost (PIU/NIE)
| Coordination and management | 57535 | 2017-03-01
| Overheads and administration | 20170 | 2017-03-01
| Monitoring and Evalution | 4500 | 2017-03-01
| Fudiciary management | 40000 | 2017-03-01
| TOTAL | 1758780
ACTUAL CO-FINANCING (If the MTR or TE have not been undertaken this reporting period, DO NOT report on actual co-financing.)
How much of the total co-financing as committed in the Project Document has actually been realized? | Co-financing is not applicable to this programme
Estimated cumulative actual co-financing as verified during Mid-term Review (MTR) or Terminal Evaluation (TE).
Add any comments on actual co-financing in particular any issues related to the realization of in-kind, grant, credits, loans, equity, non-grant instruments and other types of co-financing. (word limit=200)

## Risk Assesment
RISK ASSESMENT
IDENTIFIED RISKS
List all Risks identified in project preparation phase and what steps are being taken to mitigate them
Identified Risk | Current Status | Steps Taken to Mitigate Risk
1. Project Stakeholder Risks
1.1 Some stakeholders (local communities, land owners, and/or NGOs) may not support the proposed activities (e.g., the proposed expansion of MPAs). | Low | Consultations with local communities, Co-managers, and regulator agencies continued under the implementation phase. Project Implementing Agency Group (PIAG)/Project Implementing Unit (PIU) staff and Fisheries Department staff visited all 12 communities to build awareness of the project and start the discussion on potential livelihood activities. MCCAP consults and collaborate with organizations at multiple levels:
Regional level: (1) The Caribbean Community Climate Change Centre (CCCCC) - on climate change related issues, mainly training (MCCAP staff and line Ministries), climate change clubs in Secondary schools. (2) Caribbean Regional Fisheries Mechanism (CRFM) - fisheries and enforcement related issues. (3) Caribbean Network of Fisherfolk Organizations (CNFO) - issues related to fishermen
National Level: (1) Government Organizations - Fisheries, Coastal Zone Management Authority & Institute, Agriculture, Tourism, National Climate Change Office, Environment, Forest. (2) Non-government Organizations - Belize Federation of Fishers, Belize Fishermen Cooperative Association, Sarteneja Allience for Conservation and Development, The Nature Conservancy, Southern Environemental Association, Turneffe Atoll Sustainability Association, Wildlife Conservation Society, Fragments of Hope, Belize Audubon Society, OCEANA, Belize Red Cross, Pan American Development Foundation, National Protected Area System Secretariat.
Community level: (1) Target communities - Consejo, Corozal Town, Copper Bank, Chunox, Sarteneja, Belize City, Dangriga, Hopkins, Sittee River, Riversdale, Seine Bight, and Placencia. (2) Community Groups - Copper Bank Fishermen Association (FA), Chunox FA, Sarteneja FA, Sarteneja Homestay Group, Sarteneja Tilapia Growers and Development Association, Sarteneja United FA, Belize City Central FA, Wabufu FA, Hopkins FA, Placencia Producers Group.
Projects: (1) Belize Enterprise for Sustainable Technology (BEST)/Japan Social Development Fund grant), Conservation of Marine Resources in Central America (MARFund/German kfw project) and Management and Protection of key Biodiversity Areas in Belize Project (KBA/GEF)
The results of the KAP survey will provide information on knowledge of community and fishers on the Project and climate change. Based on these results the PIAG will organize an appropriately scaled awareness raising campaign to increase the understanding of sub-project activities and the inclusion of sound environmental and social safeguards including climate proofing sub-projects.
2. Operating Environment Risks
2.1 Future Governments may not support the goals, targets and commitments of the Project | Low | Continuous updating on Project activities and expected results is communicated to new members/employee of regulator organizations, co-managers, fishers, etc. Since the General Election November 4, the PIAG spent time updating new members of the TAC and PSC. MCCAP information documents are sent to interested parties, background justifications documents are prepared and distributed (as requested), one-on-one meetings are held to update committee members. Continuous information sharing and networking is required to ensure support for the Project.
2.2 The Government does not meet certain policy and regulatory commitments (e.g., restrictions on ability to de-reserve, additionality commitment, etc.) in accordance to mutually agreed targets (UE, UNDP-GEF, WB-GEF) as in the past projects (e.g., GEF project) | Low | The Government's commitment has been confirmed at the Ministerial level through on-going efforts to improve regulatory and institutional framework of MPAs and coastal zones.
3. Executing Entity Risks (including FM & OR Risks)
3.1 The Executing Entity selected for the Adaptation Fund Project is not equipped with enough capacity to manage the financial transactions and to implement the climate adaptation measures in the future. | Medium - Low | Training PACT and MCCAP staff - Project Coordinator (MCCAP) and Procurement Officer (PACT) trained at the World Bank Caribbean Project Implementation Workshop in Dominican Republic, June 8-11, 2015 in Safeguards and Procument procedures
World Bank supervision and mentoring - The World Bank provides the much needed technical and financial capacity building required for the initial stage of project implementation. Specifically to staff at MCCAP and PACT in the areas of project management, procurement, financial management, disbursement, etc., and the process of preparing technical and procurement documents. Main support comes from the Team Leader Mr. Enos Esikuri - visited Belize/the Project twice last year (March and September 2015) including numerous phone calls to provide technical guidance. (2) Sylvia Michele Diez - technical support almost daily, including follow up on the review process of approving technical and financial documents at the WB. (3) Yingwei Wu - procurement Specialist, reviewed MCCAP procurement plan twice in Belize and provided guidance on the drafting of procurment plans and the utility of it. (4) David I - Financial Specialist, reviewed MCCAP budget/finances once in Belize and provided PACT with the support needed to effectively execute the financial aspects of the project.
Before the Project effectiveness, the World Bank provided retroactive financing of USD 140,000 to enhance the capacity of the PIAG with technical and administrative staff.
PACT was recently accredited by the Adaptation Fund as the National Implementing Entity (NIE) for Belize and is therefore equipped with the requisite personnel and experience to oversee the execution of the project.
3.2 The governance structure, operational guidelines and other institutional policies of the PACT are altered over time and do not conform to the adequate standards | Low | PACT is a statutory Body established by the Protected Areas Conservation Trust Act, No. 15 of 1995 and governed by a Board of Directors. Its jurisdiction is expressly set out in the Act, therefore, makes switching, sharing or evasion of responsibility more difficult.
3.3 Fraud and corruption occur after the proposed Project is completed | Low | MCCAP established internal control system set out in the Operations Manual for MCCAP - revised May 2015, to systematically review expenditures to ensure they are in-line with work plans and the objectives of the project.
MAFFESD does the following: (1) Implementing Entity (Forest, Fisheries, CZMAI) submits budget and workplan to PIAG. (2) Implementing Entity forward request for purchase of goods and services to PIAG. (3) Project Coordinator (PC) ensures that request is consistent with project budget and workplan. (4) PC forwards purchase order request signed appropriately with proper support documents to PACT.
PACT does the following: (1) Ensures expenditures are in compliance with budget and supporting documentation is adequate. (2) Prepares purchase order/payment with authorized signatures. (3) Process payment based on invoices from vendors and attached source documents. (4) Reports irregularities to the PSC for immediate action.
Implementing Entity conducts activity/action and provide technical reports to support expenditure
The Technical Advisory Committee (TAC) and Project Steering Committee (PSC) meets every two months and three months respectively to review technical and financial activities
4. Project Risks
4.1 Program of climate change adaptation measures is too ambitious | Low | The activity build upon or scale up on-going efforts in the country and are complemented by the programmes under the Bank's Country Partnership Strategy
4.2 Downstream conservtion and climate adaptation activities will create social and environmental concerns | Medium - Low | The operational manual of the Project mandates that all activities supported by the Project comply with safeguard policies of the World Bank
4.3 Other donor's programme overlaps with the proposed activities | Low | Donor coordination is done by the PIAG, MAFFESD, and PACT
4.4 Alternative livelhoods activities may not be implemented or may be poorly implemented | Medium - Low | The first year was spent understanding the targetted communities within the context of the Process Framework, IPP and EMF. Additional information was captured in the Knowledge, Attitude and Practice (KAP) survey to understand their knowledge of and importance of the Marine conservation, climate change, and the impact of MPA restriction. Previous attempts have been unsuccessful at changing attitudes and behaviour towards fishing, but we hope by targetting older fishers to adopt a new livelihood activities, diverting youths from fishing to other livelihood options, and encouraging women to engage in economic activities the Project will be able to restore livelihoods and change economic portfolio of households.
In Belize, the success rate of programs with one of the core objectives being to encourage targeted beneficiaries to engage in alternative economic activities has been abysmal. This low success rate results in most programs failing to achieve their objectives. The Alternative Livelihood Forum (January 2016) stimulated an open problem solving discussion on improving the success rate of the adaptation of sustainable alternative livelihoods by targeted beneficiaries. With participants from NGOs, Government organizations, financial institutions, the forum identified opportunities, barrier/challenges and recommendations to improve to sustainable diversify the economic activities of programme beneficiaries.
A review of past and current projects that offered sustainable livelihoods options, such as Belize Rural Development Project, Toledo Institute for Development and Environment, BEST, etc. The lessons learnt were particularly noted and will be applied as required.
In view of the above, the PIAG formed synergies with the Agriculture Department and Ministry of Tourism to apply best practice livelihood activities that has been tried and proven by these departments and to get community by-in for these processes. The PIAG will look at the overall enabling environment for successful livelihood sub-projects and not only support the economic activity, but also provide training, capacity building, market studies, etc., as required. The PIAG will also provide the network needed with the relevant government departments to ensure the livelihood activity is sustainable. Part of the sub-project concept note assessment is to determine the type of help communities/groups need to develop and executed successful livelihood project, and provide the assistance needed within the scope of the Project.
Critical Risks Affecting Progress (Not identified at project design)
Identify Risks with a 50% or > likelihood of affecting progress of project
Identified Risk | Current Status | Steps Taken to Mitigate Risk
Belize's vulnerability to natural hazards, capacity and resource limitations could constrain sustainability of the project achievements. Even if the Project succeeds in removing the local stressors, it may not be enough for the reef’s survival in the face of climate change | Medium-low | The Bank continues to assess the resource issue and mitigate it with efforts to support the Government seeking additional resources for continued activities.
The PIAG is not able to manage the procurement process in a timely way. | Low | PACT has staff trained to administer and monitor the procurement process to properly spend donor grant funds. Procurement process reviews by the WB are conducted periodically.
Risk Measures: Were there any risk mitigation measures employed during the current reporting period? If so, were risks reduced? If not, why were these risks not reduced?
Add any comments relevant to risk mitigation (word limit = 500)
A number of risk mitigation measures were employed during the current reportng period (as stated above). Thus far the Project has been able to reduce the risks and kept project activities going by working closely with line ministries and other government departments. In many cases, line ministries do the work required or assist the Project with Administrative work/use of vehicles etc. This arrangement has reduced potential risks for the Project.

## Rating
RATING ON IMPLEMENTATION PROGRESS
For rating definitions please see bottom of page.
| Progress on Key Milestones |  | Expected Progress |  | Progress to Date | Rating
Project Manager/Coordinator: | Project Inception Phase Completed |  | Project Launch and Inception Workshop |  | The Belize Marine Conservation and Climate Adaptation Project was launched at the Best Western Belize Biltmore Plaza Hotel on March 17, 2015. Presenters included Ms. Beverly Wade, Fisheries Administrator; Mrs. Adele Catzim-Sanchez, former Chief Executive Officer (CEO) in the Ministry of Forestry, Fisheries, and Sustainable Development; Mr. Enos E. Esikuri, Senior Environmental Specialist and Task Team Leader, GENDR, World Bank; Mr. Vincent Gillett, CEO Coastal Zone Management Authority and Institute; and Mr. Eleodoro Martinez, Chairman of the Belize Fishermen Federation and Chairman of the Chunox Fishermen Association. | HS
Over 43 participants participated, namely, representatives from Fishermen Organizations/Associations (Chunox, Sarteneja, Belize City, Stann Creek, Belize Fishermen Federation), Fishermen Cooperatives (Northern, National), the NGO community (World Wildlife Fund (WWF), Wildlife Conservation Society (WCS), OCEANA, The Nature Conservancy (TNC), Turneffe Atoll Sustainability Association (TASA), Belize Audubon Society (BAS)), partner organizations (PACT, Forest, National Protected Area System, Coastal Zone Management Authority and Institute), the media (Press Office, Reporter, Channel 7, Channel 5), and staff of the Fisheries Department and the Ministry of Forestry, Fisheries and Sustainable Development.
| Establishment and Activation of Governance Structure |  | Project Implemention Unit, Project Steering Committee and Technical Advisory Committees established and functional |  | The Technical Advisory Committee (TAC) and Project Steering Committees (PSC) were convened following the Launch of the Project. The TAC has 13 members and 2 ex-officio observers, and the PSC has 7 members and 3 ex-officio observers. Bothe committees meet every two or three months respectively. To date the PIAG convened 4 meetings each. These committees were established to provide technical oversight, guidance and support for project implementation. | HS
The Project Implementing Agency Group (PIAG)/ Project Implementing Unit (PIU) is housed at the Fisheries Department and headed by the Project Coordinator and assisted by the Senior Technical Officer and Administrative Assistant. The PIAG is responsible for all aspects of the day-to-day management of the project, including planning, budgeting, technical coordination, implementation supervision, monitoring and evaluation (M&E), and ensuring compliance with World Bank's safeguards and regulations of Belize. The PACT retains procurement and the financial management of MCCAP as well as for project monitoring and reporting responsibilities to the World Bank. Implementation of MCCAP by PACT is carried out under the oversight and guidance of the PSC. The organizational structure of the Project Implementing Agency Group is shown at Figure 1 below
| Project implementation |  | Operating documents finalized |  | Preparation of the Annual Operational Plan (AOP) for the fiscal year 2015/2016 involved consultation with key stakeholders and MPAs co-managers, collaboration with key projects with similar interests, community meetings, focus group meetings which culminated with a Planning Workshop on June 3, 2015 with 23 key stakeholders. The AOP was approved by the TAC, PSC, and the World Bank (No objection 9 September 2015). The corresponding Procurement Plan 2015/16 was also approved (World Bank no-objection 24 August 2015). | HS
[5 empty] | Overall Rating | HS
Please Provide the Name and Contact information of person(s) reponsible for completeling the Rating section
| Name: | Sandra Grant
| Email: | pc.mccap@ffsd.gov.bz
| Progress on Key Milestones |  | Expected Progress |  | Progress to Date | Rating
| 1.1 Spatially map and analyse target MPAs for realignment or expansion |  | Stakeholder consultations completed |  | First meetings in a series of consultations with reserve managers, fishers and key stakeholders were successfully held to discuss MPA expansion and Replenishment Zone. The meetings were conducted in the northern communities (Corozal, Sarteneja, Copper Bank, and Chunox), Belize City, and southern communities (Dangriga, Hopkins, Placencia, Seine Bight) to discuss MPA expansion and replenishment zones for CBWS, TAMR, and SWCMR. Over 190 fishers, NGO community, Co-managers participated in the first consultation. Procurement process on-going to contract GIS consultant. | S
| 1.2 Verify spatial mapping via ground-truthing |  | Ground-truthing completed |  | Action delayed. Awaiting the completion of the second rounds of consultations. | MS
| 1.3 Mapping of proposed revised zoning scheme prepared for feedback |  | No action required in year 1
| 1.4 Consultations carried out with communities and stakeholders to obtain feedback on the revised zoning |  | No action required in year 1
| 1.5 Consultation feedback and baseline data compiled and incorporated into zoning map |  | No action required in year 1
| 1.6 Final revised map incorporated into the existing management plan for target MPAs and management plans textually adjusted to reflect zoning adjustment |  | No action required in year 1
| 1.7 Target MPAs demarcated with buoys and signage as per the new boundaries |  | No action required in year 1
| 1.8 Enhancement of enforcement and monitoring of selected MPAs, including replenishment zones |  | Enforcement fleet improved |  | Repaired five patrol boats, purchased 2 vessels (28 feet each) including engines and trailers | HS
|  |  | Patrols increased |  | Increased patrols in TAMR, CBWS, SWCMR by providing monthly allocation of fuel and accommodation and transportation for enforcement officers. Supporting joint patrols between Fisheries Department, Forest Department, Coast Guard, and Customs in high risk areas. | HS
|  |  | Capacity building |  | Conducted a 5 days training with 21 participants from Coast Guard, Fisheries Department Marine Reserve and Conservation Compliance Unit, and Co-managers (Belize Audubon Society, Turneffe Atoll Sustainability Association, Southern Environmental Association) in fisheries enforcement, prosecution, small craft handling, engine maintenance, and Spatial Monitoring and Reporting Tool (SMART) a new enforcement software. A Draft Comprehensive Enforcement Training Manual was developed as a training guide for Enforcement Officers. The Manual will be finalized and circulated to the various partner/agencies. | HS
|  |  | Enforcement equipment provided |  | Enforcement equipment - Purchase computer, laptop, and tablets to support national roll out of the SMART enforcement system, which will be used to gather data on infractions at sea in the 3 targeted Marine Protected Areas. | S
| 1.9 Biological monitoring of strategic and control sites |  | Biological monitoring within Marine Reserves initiated |  | Supported biological data collection activities at SWCMR to conduct fishery independent study of lobster catch rates of traps in replenishment zones and fishing area. The data will complement fishery depend activities where fishers will be given log-books to record catch and effort data | S
| 1.10 Management effectiveness assessments using tracking tools |  | No action required in year 1
| 1.11 Ground-truthing to identify reefs suitable for nurseries set-up |  | Initial activities started |  | Single Source Selection of Fragments of Hope approved by the Bank; Terms of Reference approved by TAC, PSC, and Bank, Procurement process ongoing to finalize contract. | MU
| 1.12 Establishment of coral nurseries |  | At least 1 coral nursery established |  | Activity delayed by procurement process | U
| 1.13 Out-planting in selected reefs |  | No action in year 1
| 1.14 Rolling out of the over-arching PA legislation |  | No action required in year 1
| 1.15 Initial support to the PA administration structure |  | No action required in year 1
| 1.16 Revision of mangrove regulations |  | Mangrove regulations drafted |  | Consultancy to review and revise the Forest (Protection of Mangroves) Regulations 2014 - Terms of Reference was reviewed and approved by the TAC, PSC and WB; Procurement process ongoing. | S
First meeting with stakeholders was conducted to review (i) the status of the Mangrove Regulations, (ii) the draft Mangrove Regulations, and (iii) the Solicitor General's comments on the Mangrove Regulations. Based on the outcome of the meeting, the Forest Department will draft a Terms of Reference to review, update, and finalize the mangrove regulations. MCCAP will also collaborate with the Key Biodiversity Areas Project (KBA) in ensuring that the Forest Act (being updated by KBA) and the Mangrove Regulation (updated by MCCAP) are consistent.
| 1.17 Revision of the CZM Act |  | CZM Act drafted |  | Consultancy to conduct a review and revision of the Belize Coastal Zone Management Act and Regulation - Terms of Reference was reviewed and approved by TAC, PSC and WB. Procurement process ongoing. | S
| 1.18 Implementation of an Integrated Coastal Zone Management Plan |  | Water Quality personnel and lab equipment in place |  | Developed a Water Quality Monitoring (WQM) protocol which will be discussed with other relevant agencies. Purchased a vehicle, 30 ft vessel with engines and trailer, and computer and laptop to assist in WQM. Sourcing lab equipment for the WQM programme. Procurement process to hire 1 boat captain and 1 WQM Laboratory Technician ongoing. | S
|  |  | Inventory of development sites for Ambergris Caye, Central and Caye Caulker completed |  | Aerial survey of seascape and landscape for Ambergris Caye, Central and Caye Caulker was conducted. The purpose of the inventory was to establish a spatial and temporal baseline for human use of coastal and marine resources in tandem with the implementation of the Belize Integrated Coastal Zone Management (ICZM) Plan. The MCCAP Project will equip CZMAI with tools that will assist in compilation and analysis to track health of the coastal systems and the strengthening of coastal outreach. The inventory will serve as an important tool for monitoring and assessing compliance with the ICZM Plan, and establishing a baseline aerial survey of seascape and landscape database for Ambergris Caye, Central and Caye Caulker. The output will be an updated imagery of the three planning regions. Received 1,575 geo-referenced aerilal photographs. Digitizing aerial imagery to assess % change in human use activities with Ambergris Caye, Central and Caye Caulker. | HS
| 2.1 Communtiy needs assessment workshops |  | Community needs assessment completed in the 12 targetted communities |  | Conducted community needs assessment workshops in 12 targeted fishing communities with over 150 stakeholders. Facilitated numerous meetings with Co-managers, government agencies, etc. | S
Agriculture based sub-projects - The PIAG organized two meeting with the Agriculture Department. The first was a tour with fishers at the Agriculture Department Central Farm establishment where fishers and extension officers viewed and discussed agriculture activities (tilapia farming, chicken rearing, pig rearing, vegetable/backyard farming), possible alternative livelihood options. The tour included 30 people: 15 fishermen (from Belize City, Sarteneja, Chunox, Copper Bank, Hopkins, and Dangriga); 11 Agriculture Extension/Research Officers (from Cayo, Stann Creek, and Corozal), 2 PACT, and 1 MCCAP. The second activity was a meeting with senior management of the Agriculture Department, including the Chief Agriculture Officer, to discuss collaboration between MCCAP and the Department. The Agriculture Department: (a) agreed to support MCCAP, in-particularly the 12 targeted coastal communities by scoping these communities to identify potentially sustainable alternative livelihood activities which could be introduced to communities; and (b) identified Extension Officers what will work with coastal communities to mentor agriculture-based alternative livelihood options.
Tourism based sub-projects - The PIAG met with representatives from the Ministry of tourism to discuss possible synergies and implement modalities for the implementation of tourism related projects. It was noted that it would be difficult to develop viable alternative livelihood tourism based options in northern communities because there was no tourism destination in the area. Both parties agreed that it might be best to first develop a tourism destination plan for the northern belt which would include the training required, potential destinations and infrastructure development.
Fisheries based sub-projects - The PIAG discussed with the Fisheries Department the need for research and development to support alternative fishing activities related to none targeted species such as seaweed, crab, and deepslope fishing.
| 2.2 Participatory sub-project planning workshops |  | At least 3 concept notes completed |  | Completed 1 of 3 concept notes. Assisted Chunox St. Viator Vocational High School to draft concept note. The PSC approved recommendation to provide the school with the necessary Service provider to develop a full proposal including a business plan. | MS
[5 empty] | University of Belize assisting Chunox Fishermen Association, Belize Central Fishermen Association, and the Belize Federation of fishers to develop concept notes and proposals. | MS
|  |  | Dialogue and networking |  | Organized a sustainable livelihoods forum, a meeting with organizations responsible for implementing sustainable livelihoods project to discuss the success rates of their development/ intervention programme and share lessons learnt. The forum provided MCCAP the opportunity to review its programme and apply recommendations. | S
| 2.3 Development of business plans |  | Two business plans developed |  | None requested | N/A
| 2.4 Marketing support for business venture |  | One marketing support given |  | None requested | N/A
| 2.5 Training in business development |  | No action required in year 1
| 2.6 Training in marketable skills |  | No action required in year 1
| 2.7 Sub-grants for initial capital investment to support the startup of business venture |  | One sub-project funded |  | None requested | N/A
| 3.1 Development and implementation of KAP survey (including instrument, field data collection, analysis, presentation of findings |  | KAP survey completed |  | Belize Environmental Technologies (BET) was contracted to conduct a Knowledge, Attitude, and Behaviour Practice Survey. BET engaged with key stakeholders working in the target communities. The first deliverable (inception report) outlining the methodology was submitted and approved by the TAC and PSC. They employed a combination of quantitative and qualitative techniques to undertake the survey. The KAP survey has 3 main elements: (1) a probability sample of households representative at the village/community level based on the 2010 Household and Population Census. A total of 2,100 households were sampled. (2) A probability sample of 10% random sample of registered fisherfolks based on the Fisheries Department 2015 Database of fishers. (3) a purposeful sample of key policy actors in the fisheries sector (regulators, managers and co-managers of MPAs) was invited to participate in an online component of the survey. The Second deliverable (Survey Instrument) was completed, approved and piloted. A stakeholder meeting was convened to validate and finalize the survey instrument. Training of surveyors was completed and data colection and entry has been completed. The report is currently being finalized. | HS
A number of core activities await data input from the KAP survey report. The report will - (1) be used to update some baseline data in the Results Framework; (2) determine the level of training (e.g., climate change) to be provided by the Project; and (3) assist in the development of the Behavioural Change Campaign strategy.
| 3.2 Development of BCC strategy and action plan |  | No action required in year 1
| 3.3 Implementation of BCC strategy and action plan |  | No action required in year 1
| 3.4 Updates of project activities (via quarterly electronic and print newsletters) |  | Reports completed in a timely fashion |  | Quarterly and yearly reports completed. To improve the image of the Project a branding exercise was undertaken and completed. | HS
| 3.5 Web-based platform |  | No action required in year 1
| 3.6 Best practice forum |  | No action required in year 1
| 3.7 Learning events, leadership development, training |  | Training events increased |  | MCCAP will partner with the Caribbean Community Climate Change Centre and the National Climate Change Office to develop a training curriculum for community members, targeted government organization (Fisheries Department, Forest Department, CZMAI), and teachers involved in MCCAP supported climate change clubs in schools. | MU
| 3.8 Strategic planning for the network |  | No action required in year 1
[5 empty] | Overall Rating | S
Please Provide the Name and Contact information of person(s) reponsible for completeling the Rating section
| Name: | Sandra Grant
| Email: | pc.mccap@ffsd.gov.bz; linegrant@gmail.com
Please justify your rating. Outline the positive and negative progress made by the project since it started. Provide specific recommendations for next steps. . (word limit=500)
Activities undertaken by MCCAP is satisfactory to date. The PIAG/PIU office was opened in March 2013, and MCCAP became Effective in July of that same year. Thus far we have been able to finalize the Project Operations Manual, Annual Operational Plan and Procurement Plan 2015/16, and produced technical, workshop, safeguards, and training reports. The Project is behind in actual expenditure, about 14% to date; however the commitment is 58%. The procurement process (from drafting service Terms of Reference/goods specification list to signing the contract) is taking more time than envisioned. There has been delays in obtaining three quotations/bids (some companies are charging a fee for quotations), poor responses to call for EOI/bids, review process by TAC and PSC members which requires time for approval of documents, and availability of evaluation committee to meet. The PIAG has also not been able to fill all positions to effectively get the work done. The Senior Technical Officer was contracted in September 2015 but resigned effective February 29, 2016. The position of Administrative Assistant has not been filled. With all the limitations, the PIAG pushes to implement activities with the help of the targeted Government Departments (Fisheries, Forest, and Coastal Zone Management Authority and Institute) and PACT (Finance and Procurement Officers).
| Progress on Key Milestones |  | Expected Progress |  | Progress to Date | Rating
Implementing Agency | 1.1 Spatially map and analyse target MPAs for realignment or expansion |  | First stakeholder consultation completed |  | First meetings in a series of consultations with reserve managers, fishers and key stakeholders were successfully held to discuss MPA expansion and Replenishment Zone. The meetings were conducted in the northern communities (Corozal, Sarteneja, Copper Bank, and Chunox), Belize City, and southern communities (Dangriga, Hopkins, Placencia, Seine Bight) to discuss MPA expansion and replenishment zones for CBWS, TAMR, and SWCMR. Over 190 fishers, NGO community, Co-managers participated in the first consultation. | S
| 1.2 Verify spatial mapping via ground-truthing |  | Ground-truthing completed |  | On October 27, 2015, the Bank reviewed and provided technical no-objection to the Consultancy on "Realignment of boundaries and creation of new zones for the targeted Marine Protected Areas". The groundtruthing will aid verification of the image data (maps and remote sensing data) to real features on the ground. The groundtruthing is scheduled to be completed after the second rounds of consultations to incorporate more feedback from stakeholders. | MS
| 1.3 Mapping of proposed revised zoning scheme prepared for feedback |  | No action required in year 1
| 1.4 Consultations carried out with communities and stakeholders to obtain feedback on the revised zoning |  | No action required in year 1
| 1.5 Consultation feedback and baseline data compiled and incorporated into zoning map |  | No action required in year 1
| 1.6 Final revised map incorporated into the existing management plan for target MPAs and management plans textually adjusted to reflect zoning adjustment |  | No action required in year 1
| 1.7 Target MPAs demarcated with buoys and signage as per the new boundaries |  | No action required in year 1
| 1.8 Enhancement of enforcement and monitoring of selected MPAs, including replenishment zones |  | Enforcement fleet improved |  | Strenghtening surveillance and enforcement are critical components of the MPA management system, and the project has successfully repaired five patrol boats, purchased 2 vessels (28 feet each), along with engines and trailers. | HS
|  |  | Patrols increased |  | The project has given the resources and tools for effective management of the MPA. Resources included monthly allocation of fuel and accommodation and transportation for enforcement officers in TAMR, CBWS, SWCMR by providing monthly allocation of fuel and accommodation and transportation for enforcement officers. Close collaboration between Fisheries Department, Forest Department, Coast Guard, and Customs are essential to support patrols in high risk areas. | HS
|  |  | Capacity building |  | Capacity building is essential for the effective management of MPAs. An enforcement training workshop, including 21 participants, with key enforcement entities (Coast Guard, Fisheries Department Marine Reserve and Conservation Compliance Unit, and Co-managers (Belize Audubon Society, Turneffe Atoll Sustainability Association, Southern Environmental Association), was successfully conducted on key areas including fisheries enforcement, prosecution, small craft handling, engine maintenance, and Spatial Monitoring and Reporting Tool (SMART) a new enforcement software. A Draft Comprehensive Enforcement Training Manual was developed as a training guide for Enforcement Officers. The Manual will be finalized and circulated to the various partner/agencies. | HS
|  |  | Enforcement equipment provided |  | Necessary equipment were purchased to support the implementation of the Spatial Monitoring and Reporting Tool (SMART) enforcement system. The SMART is an improved tool for measuring, evaluating and improving the effectiveness of conservation areas which will be used by the project to gather data on illegal activities. | S
| 1.9 Biological monitoring of strategic and control sites |  | Biological monitoring within Marine Reserves initiated |  | Biological data collection has started at the SWCMR to support studies in the targetted MPAs. Equipment for biological monitoring was purchased (wooden lobster traps). The data collected will be integrated in a database system for analysis and will serve to improve the management strategy in the replenishment zones. | S
| 1.10 Management effectiveness assessments using tracking tools |  | No action required in year 1
| 1.11 Ground-truthing to identify reefs suitable for nurseries set-up |  | Initial activities started |  | On September 3, 2015, the Bank reviewed and provided no-objection for Single Source Selection of the firm Fragments of Hope Ltd., Belize, for the "Consultancy to repopulate reefs within replenishment zones of Turneffe Atoll Marine Reserve and South Water Caye Marine Reserve with temperature resilient coral varieties". The project is in the process of contracting Fragments of Hope, Ltd., to expand the reef restoration activities in TAMR and SWCMR, and by extension to expand the reef restoration programme in Belize. | MU
| 1.12 Establishment of coral nurseries |  | At least 1 coral nursery established |  | The project has experienced delays on the procurement process, but will advance implementation with expedited procurement measures. | U
| 1.13 Out-planting in selected reefs |  | No action required in year 1
| 1.14 Rolling out of the over-arching PA legislation |  | No action required in year 1
| 1.15 Initial support to the PA administration structure |  | No action required in year 1
| 1.16 Revision of mangrove regulations |  | Mangrove regulations drafted |  | On February 18, 2016, the Bank reviewed and provided technical no-objection to the Consultancy to review and revise the Forest (Protection of Mangroves) Regulations 2014. Consultation with stakeholders was conducted to review the Mangrove Regulations and to integrate the Solicitor General's comments. Under the mandate of the Forest Department, the project will support efforts to finalize the draft revised mangrove regulations to enable added protection for mangroves. The project will collaborate with the Key Biodiversity Areas Project (KBA) in ensuring that the Forest Act (being updated by KBA Project), will be reflected in the Mangrove Regulation (updated by MCCAP). The Procurement process is ongoing. | S
| 1.17 Revision of the CZM Act |  | CZM Act drafted |  | On October 27, 2015, the Bank reviewed and provided technical no objection to the Consultancy to conduct a review and revision of the Belize Coastal Zone Management Act and Regulation. Procurement process is ongoing. | S
| 1.18 Implementation of an Integrated Coastal Zone Management Plan |  | Water Quality personnel and lab equipment in place |  | On October 27, 2015, the Bank reviewed and provided technical no objection to the TORs for Boat Captain/Water Quality Assistant and Environmental Lab Technician. Hiring for the two positions are ongoing. A Water Quality Monitoring protocol was developed and will be discussed with other relevant agencies. On November 9, 2016 the Bank reviewed and provided technical no objection to the bid document on the Supply and Delivery of 3 Vessels. | S
|  |  | Inventory of development sites for ambergris Caye, Central and Caye Caulker completed |  | The inventory establishes a spatial and temporal baseline for human use of coastal and marine resources in tandem with the implementation of the Belize Integrated Coastal Zone Management (ICZM) Plan. Aerial survey of seascape and landscape for Ambergris Caye, Central and Caye Caulker were successfully conducted, and are now being digitized to assess changes in human use activities in those areas. | HS
| 2.1 Communtiy needs assessment workshops |  | Community needs assessment completed in the 12 targetted communities |  | A series of communities needs assessment workshops were successfully conducted with the 12 targeted communities, over 150 fishers and community leaders participated. A diverse set of ideas for potential livelihoods were expressed by fishers. The PIAG successfully established collaboration with the Agriculture Department for technical support on agriculture-related livelihood options. A tour (30 people) with fishers and agriculture representatives at the Agriculture Department Central Farm establishment was delivered to discuss possible agriculture options. This collaboration is critical for the success of the agriculture-based alternative livelihoods. PIAG also established collaboration with Ministry of Tourism for possible tourism-related projects; and engaged the Fisheries Department in supporting potential fishing activities related to non-targeted species such as seaweed, crab and deep slope fishing. | HS
| 2.2 Participatory sub-project planning workshops |  | At least 3 concept notes completed |  | Of the 3 concept notes, one was completed. With assistance of the Agriculture Department the project supported Chunox St. Viator Vocational High School to draft concept note. The concept was later approved by the PSC. The PIAG will assist the school to develop a full proposal including a business plan. | MS
|  |  | Dialogue and networking |  | On January 21, 2016, MCCAP organized a sustainable livelihoods forum to better understand the opportunities and challenges of implementing livelihood projects. Participants discussed the success rates of the programmes and shared lessons learned. Recommendations from the forum, were applied to MCCAP. | S
| 2.3 Development of business plans |  | Two business plans developed |  | One business plans has been approved by the PSC. | MS
| 2.4 Marketing support for business venture |  | One marketing support given |  | Action will be taken as soon as proposals are prepared and approved by PSC. | N/A
| 2.5 Training in business development |  | No action required in year 1
| 2.6 Training in marketable skills |  | No action required in year 1
| 2.7 Sub-grants for initial capital investment to support the startup of business venture |  | One sub-project funded |  | Action will be taken as soon as proposals are prepared and approved by PSC. | N/A
| 3.1 Development and implementation of KAP survey (including instrument, field data collection, analysis, presentation of findings |  | KAP survey completed |  | A number of products were delivered under this activity: 1) An initial stakeholder meeting was conducted in target communities to discuss survey; 2) preparation of Inception report (Sept 30); 3) Survey instrument and protocol (Dec 7); Instrument validation workshop (Nov 27); Training of surveyors (Dec 10); and Pilot & Data collection (Dec 14). The report is currently being finalized. This work has been conducted by the Belize Environmental Technologies (BET). The survey data will be used as a baseline data in the results framework; determine the level of training to be provided by the project; and assist in the development of the Behavioural Change Campaign strategy. | HS
| 3.2 Development of BCC strategy and action plan |  | No action required in year 1
| 3.3 Implementation of BCC strategy and action plan |  | No action required in year 1
| 3.4 Updates of project activities (via quarterly electronic and print newsletters) |  | Reports completed in a timely fashion |  | The project has produced quarterly and the yearly report in a timely manner. To improve the image of the Project, a branding exercise has been completed. The new logo shows “the interconnectedness of the social and ecological systems and their ability to adapt and change”. | HS
| 3.5 Web-based platform |  | No action required in year 1
| 3.6 Best practice forum |  | No action required in year 1
| 3.7 Learning events, leadership development, training |  | Training events increased |  | Training opportunities will be developed jointly with the Caribbean Community Climate Change Centre and the National Climate Change Office to develop a training curriculum for community members, targeted government organization, and climate change clubs in schools directly involved in MCCAP (Fisheries Department, Forest Department, CZMAI). | MU
| 3.8 Strategic planning for the network |  | No action required in year 1
[5 empty] | Overall Rating | S
Please Provide the Name and Contact information of person(s) reponsible for completeling the Rating section
| Name: | Enos Esikuri/Sylvia Michele Diez
| Email: | eesikuri@worldbank.org/sdiez@worldbank.org
| Progress on Key Milestones |  | Expected Progress |  | Progress to Date | Rating
Other
Overall Rating
Please Provide the Name and Contact information of person(s) reponsible for completeling the Rating section
Name:
Email:
| Please justify your rating and address the following points: 1. Indicate trends, both positive and negative, in achievement of outcomes as per the project indicators. 2. Detail critical risks that have affected progress. 3. Outline response to MTR undertaken this reporting period. 4. Outline action plan to address projects with a rating of HU, U or MU. Please keep your input to 1200 words |  | Overall, the project is progressing well towards the achievement of its outcomes. After the inception workshop (March 17, 2015), the project has moved into full implementation and is delivering effectively for most of the activities. Implementation is expected to be intensified in the coming year, and looks promising in delivering on its targets. Some of the challenges/risks identified such as procurement processes are considered of inception phase, and will be reduced with additional training, awareness and broad stakeholder outreach. In the first year, the PIU spent considerable time and effort to meet with relevant stakeholders to discuss synergies and reduce duplication of activities
Despite changes in government, this Project continues with high visibility and relevance in the national context. On November 4, 2015 Belizeans went to the polls to elect a new government. While the United Democratic Party retained the government, there were a number of changes, including a new Minister for Agriculture, Fisheries, Forestry, the Environment and Sustainable Development. The changes in Ministers/CEOs also means changes in members of the Project Steering Committee (PSC). Hence, the Project Implementing Unit has been meeting regularly with the new CEO to update on activities of MCCAP including procurement. Given the recent management changes, the WBG team will continue to provide close guidance especially with regard to fiduciary issues through regular communication and increased proactivity.
In its first year, the project can be considered satisfactory. Some highlights for this period are summarized below:
- Marking the initiation of the Project by the Adaptation Fund, a Project Inception Workshop was held on March 17, 2015 at the Belize Best Western Biltmore Plaza in Belize City. The workshop was well attended by over 43 participants including Government officials (Fisheries Department and the Ministry of Forestry, Fisheries and Sustainable Development), NGO community, private sector, partner organizations, and community beneficiaries, with full coverage of the media (Press Office, radio, newspaper, and television). Several outputs of the event were prepared (comprehensive summary report on the workshop, brochure, meeting attendance, MCCAP presentation, Press Release, photos and media reports) and submitted by the Bank to the Adaptation Fund on March 20, 2015.
-MCCAP was approved by the Bank's Board of Directors on March 3, 2015. The Grant Agreement was signed by the Minister of Finance on June 3, 2015; the Subsidiary Agreement was given the no-objection by the Bank on May 20, 2015; the Project Operational Manual was finalized and given no-objection by the Bank on May 18, 2015, and the Annual Operating Plan was cleared by the Bank on September 9, 2015. A General Procurement Notice for the Project was advertised on April 27, 2015 (Belize newspapers, website-PACT, WB).
-The institutional arrangements for the Project Implementation Unit (PIU) are in place and operational including the Project Implementation Agency Group (PIAG), Project Steering Committee (PSC), and Technical Advisory Committee (TAC). As part of the PIU, a Project Coordinator was hired on March 10, 2015. The Coordinator is a highly committed and motivated person, with excellent technical skills, and has greatly contributed to effective implementation of the project in this first year. There were some delays in the recruitment of the Sr. Technical Officer, who performed functions for a few months until his resignation. A new Sr. Technical Officer will be hired in the coming weeks. To strengthen the capacity of the PIU, the PIU staff participated in the Caribbean Project Implementation Workshop held in the Dominican Republic on June 8-11, 2015. The workshop focused on project implementation aspects including financial management, procurement, safeguards, disbursement, monitoring and evaluation.
-Component 1: Several Terms of References (TORs) were prepared for the activities aiming to improve the Protection Regime of Marine and Coastal Ecosystems. Some of the key deliverables include a Comprehensive Enforcement Training Manual, Water Quality Monitoring Protocol, and other workshop reports. Meetings with stakeholders were conducted to review the draft Mangrove Regulations. In addition, a meeting with reserve managers and key stakeholders was held to discuss MPA expansion and Replenishment Zone. Subsequent meetings were conducted in the northern communities (Corozal, Sarteneja, Copper Bank, and Chunox) and Belize City to discuss MPA expansion and replenishment zones for CBWS, TAMR, and SWCMR. An aerial survey of seascape and landscape for Ambergris Caye, Central and Caye Caulker was conducted to establish a spatial and temporal baseline for human use of coastal and marine resources in tandem with the implementation of the Belize Integrated Coastal Zone Management (ICZM) Plan.
-Component 2: The project was successful in setting up a broad stakeholder engagement process with several communities and Ministries, and creating initial awareness on project related aspects. Several community consultation meetings took place to introduce MCCAP and discuss viable alternative livelihood activities. With the assistance of the Fisheries Department, the PIU held project consultation meetings with the following communities: Corozal, Sarteneja, Chunnox, Belize City, Dangriga Town, Hopkins, Riversdale, Seine Bight and Placencia. The PIU also organized meetings with the Agriculture Department, Ministry of Tourism, and Fisheries Department to collaborate in the development of alternative livelihood projects, and discuss possible synergies. On January 21, 2016, MCCAP organized a sustainable livelihoods forum to better understand the opportunities and challenges of implementing livelihood projects.
-Component 3: On the 31st August, Belize Environmental Technologies (BET) was contracted to conduct the Knowledge, Attitude, and Behavioural Practice (KAP) survey, as part of the Raising Awareness and Building Local Capacity component. A number of products were delivered under this activity, including a an initial stakeholder meeting in target communities to discuss survey, Inception report, Survey instrument and protocol; instrument validation workshop, training of surveyors , and Pilot & Data collection. The report is currently being finalized. This work has been conducted by the Belize Environmental Technologies (BET). The survey data will be used as a baseline data in the results framework; determine the level of training to be provided by the project; and assist in the development of the Behavioral Change Campaign strategy. To improve the image of the Project, a branding exercise has been completed.
Rating Definitions
|  |  | Highly Satisfactory (HS) | Project actions/activities planned for current reporting period are progressing on track or exceeding expectations to acheive all major outcomes/outputs for given reporting period, without major shortcomings. The project can be presented as “good practice”.
|  |  | Satisfactory (S) | Project actions/activities planned for current reporting period are progressing on track to achieve most of its major outcomes/outputs with only minor shortcomings.
|  |  | Marginally Satisfactory (MS) | Project actions/activities planned for current reporting period are progressing on track to achieve most major relevant outcomes/outputs, but with either significant shortcomings or modest overall relevance.
|  |  | Marginally Unsatisfactory (MU) | Project actions/activities planned for current reporting period are not progressing on track to achieve major outcomes/outputs with major shortcomings or is expected to achieve only some of its major outcomes/outputs.
|  |  | Unsatisfactory (U) | Project actions/activities planned for current reporting period are not progressing on track to achieve most of its major outcomes/outputs.
|  |  | Highly Unsatisfactory (U) | Project actions/activities planned for current reporting period are not on track and shows that it is failing to achieve, and is not expected to achieve, any of its outcomes/outputs.

## Project Indicators
PROJECT Indicators
Please provide all indicators being tracked for the project as outlined in the project document
Type of Indicator (indicators towards Objectives, Outcomes, etc…)
Type of Indicator | Indicator | Baseline | Progress since inception | Target for Project End
Project Objective Indicator | Marine Protected Areas (MPA) coverage increased to 20.2% and areas declared as marine Replenishment Zones (RZ) increased to at least 3.1% of the Belize's territorial sea as identified in the NPASP, by the third year of the project. (Component 1) | MPAs share 13% of marine ecosystem habitats as identified by NPASP | 13% | 20.2%
|  | Marine RZs share approximately 2% of marine ecosystem habitats as identified in the NPASP | 2% | 3%
| Coastal zone managed effectively through implementation of Coastal Zone Management Plan, measured by coastline under protection and no net loss of mangroves (Component 1) | ICZM Plan available for implementation in Dec 2012 allowing for the 386 km of Belize’s coastline under better management. | 386 km | 386 km
|  | National mangrove status in 2012 is 74,480 hectares | 74,480 hectares | 74,480 hectares
| Project beneficiaries who have adopted alternative livelihoods and reduced dependency on traditional fishing for household income (at least 2,500 people), of which 30% are women (Component 2) | To be confirmed by the KAP survey | 0% fishers | 45% fishers
|  |  | 0% women | 30% women
| Awareness raising campaigns and dissemination of project information and project supported investments reach 100% and change attitude of 75% of intended beneficiaries (Component 3) | The value of marine conservation and impacts of climate change are not understood well among local people | 0% people with enhanced understanding; | 100% people with enhanced understanding;
|  |  | 0% people with changed attitude | 75% people with changed attitude
Project Outcome Indicators | The target MPAs are effectively managed as recorded by the Management Effectiveness Tracking Tool; | Management effectiveness score as recorded by Management Effectiveness Tracking Tool (Note: 1 to 4 – lowest to highest score)
|  | SWCMR - 2009 score of 2.65 of 4; | SWCMR - 2.65 of 4; | SWCMR – score of 3.5 of 4;
|  | CBWS - 2009 score 2.16 of 4; | CBWS - 2.17 of 4; | CBWS - score of 3.5 of 4;
|  | TAMR - nil | TAMR - nil | TAMR - score of 3.5 of 4
| Infractions of rules and regulations in the target MPAs and RZs reduced by 75% | % reduction in infractions of MPA/RZ rules and regulations based on arrests made at the MPAs in 2011-2012 |  | 75%
|  | Turneffe Atoll SPAG MRs - 13 arrest (2011) | Turneffe Atoll - 39 arrests (2014)
|  | SWCMR: 26 arrests (2011) | SWCMR - 17 arrests (2014)
|  | Turneffe Atoll SPAG MRs - 2 arrest (2012) | CBWS - 0 arrests (2014)
SWCMR - 23 arrests (up to September 2012)
| At least 3 restored coral sites, with resilient varieties grown in coral nurseries, within TAMR and SWCMR by the end of the project (with each site measuring 300 m2) | 0 coral sites restored | 0 | 6
| 75% of coastal developments adhering to the development guidelines set by the ICZM Plan | Baseline data being collected from the coastal mapping inventory | 0% | 75%
| Mangrove clearance infractions reduced by 100% (that is, infractions of the revised mangrove regulations) | TBD | 0% | 100%
| Alternative livelihoods subprojects elaborated and financed with 30% of beneficiaries being women | 0 business plans financed; | 0 business plans financed | 20 business plans financed;
|  | 0% of female beneficiaries | 0% of female beneficiaries | 30% of female beneficiaries
| Persons participating in training based on training needs assessment (at least 30% of trainees are women) | 0 number of persons; | 21 persons | 2000 persons;
|  | 0% of female trainees | 5% of female trainees | 30% of females trainees
| Behavioural change communication (BCC) campaigns conducted at all the target fishing communities (Chunox, Copper Bank, Sarteneja, Belize City, Dangriga, Hopkins, Placencia, Sittee River, Riversdale and Seine Bight) and reach 100% of fishers | The extent of the behavioural change communication campaign will depend on the outcome of the KAP survey (number of target communities, number of fishermen) | 0 targetted community | 12 targetted communities
|  |  | 0 fishers | TBD
| Strategic planning workshops with fishers association and three fisher cooperatives | Fishermen association and cooperatives do not have strategic plans | 2 planning workshops | 24 planning workshops
|  |  | 0 strategic plans | 8 strategic plans

## Lessons Learned
QUALITATIVE MEASURES and LESSONS LEARNED
Please complete the following section every reporting period
Implementation and Adaptive Management | Response
What implementation issues/lessons, either positive or negative, affected progress? | Collaboration/consultation requires significant time and investment with key partners (government agencies, NGOs, donor organizations, and community members). The first six months of Project implementation, the PIAG spent considerable time and effort to meet with relevant stakeholders to discuss synergies and reduce duplication of activities.
Balancing Project requirements/expectations with local realities. Community wants assistance on their terms, the project had to spend a lot of time explaining the process and activities to be funded as set out in the Project documents.
Staff of line Ministries directly involved in MCCAP activities are actively involved in implementation. Project activities increase time and counterpart funding which some Departments do not have. Hence, some expectations from the Project had to be reduced, while not affecting quality outcomes or the objectives.
Were there any delays in implementation? If so, include any causes of delays. What measures have been taken to reduce delays? | No. The implementation of activities started even before effectiveness utilizing retroactive financing, and it is progressing well. To expedite some of the processes, such as the identification of Firms/Individual Consultants, the PIAG established a Consultant database and asked firms/individual to register. Once an Advert/TOR is published the same information is emailed directly to firms/individuals. This has significantly improved the selection process.
Contract requiring review/comments/approval from TAC and PSC before payment needs to be properly managed in terms of time allocation for the review/comments/approval. Delays in reviews/comments/approval will delay the execution process. The PIAG established a 5 working days time period for comments/no-objection.
Describe any changes undertaken to improve results on the ground or any changes made to project outputs (i.e. changes to project design) | The capacity to manage sub-project activities at the community level is limited, and will impact the success of sub-projects. Results from other alternative livelihood projects have not been sustainable. The PIAG reviewed the lessons learnt and successes of other projects, then convened a sustainable livelihoods forum to discuss some of the challenges. The PIAG hopes to use the outcome to make changes to project outputs/project design as required.
How have gender considerations been taken into consideration during the reporting period? What have been the lessons learned as a consequence of inclusion of such considerations on project performance or impacts? | Several community consultations took place and for some of them half of the participation was by women.
Please complete the following section at mid-term and project completion
Lessons for Adaptation | Response
Climate Resilience Measures
What have been the lessons learned, both positive and negative, in implementing climate adaptation measures that would be relevant to the design and implementation of future projects/programmes for enhanced resilience to climate change?
What is the potential for the climate resilience measures undertaken by the project/programme to be replicated and scaled up both within and outside the project area?
Concrete Adaptation Interventions
What have been the lessons learned, both positive and negative, in implementing concrete adaptation interventions that would be relevant to the design and implementation of future projects/programmes implementing concrete adaptation interventions?
What is the potential for the concrete adaptation interventions undertaken by the project/programme to be replicated and scaled up both within and outside the project area?
Community/National Impact
What would you consider to be the most successful aspects for the target communities?
What measures are/have been put in place to ensure sustainability of the project/program results?
What measures are being/could have been put in place to improve project/program results?
Knowledge Management
How has existing information/data/knowledge been used to inform project development and implementation? What kinds of information/data/knowledge were used?
If learning objectives have been established, have they been met? Please describe.
Describe any difficulties there have been in accessing or retrieving existing information (data or knowledge) that is relevant to the project. Please provide suggestions for improving access to the relevant data.
Has the identification of learning objectives contributed to the outcomes of the project? In what ways have they contributed?

## Results Tracker (2)
Results Tracker for Adaptation Fund (AF) Projects
Goal: Assist developing-country Parties to the Kyoto Protocol that are particularly vulnerable to the adverse effects of climate change in meeting the costs of concrete adaptation projects and programmes in order to implement climate-resilient measures. Impact: Increased resiliency at the community, national, and regional levels to climate variability and change.
Important: Please read the following guidance document (also posted on the Adaptation Fund website) before entering your data
Link: http://www.adaptation-fund.org/sites/default/files/Results%20Framework%20and%20Baseline%20Guidance%20final.pdf
Adaptation Fund Strategic Results Framework
Project ID | P131408
Implementing Entity | PACT and the World Bank
Type of implementing entity | NIE
Country | Belize
Region | Latin America and Caribbean
Sector | Coastal management
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Impact: Increased resiliency at the community, national, and regional levels to climate variability and change | Core Indicator: No. of beneficiaries |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project
|  | Total | 0 | 0 | 0 | Total | 66792 | 2500 | 8825 | Total |  |  |  | Total
|  | % of female beneficiaries | 0% | 0% | 0% | % of female beneficiaries | 48% | 30% | 30% | % of female beneficiaries |  |  |  | % of female beneficiaries
|  | % of Youth beneficiaries | 0% | 0% | 0% | % of Youth beneficiaries | 40% | 40% | 40% | % of Youth beneficiaries |  |  |  | % of Youth beneficiaries
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 1: Reduced exposure to climate-related hazards and threats | Indicator 1: Relevant threat and hazard information generated and disseminated to stakeholders on a timely basis | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness
|  | Total |  |  |  | Total |  |  |  | Total |  |  |  | Total
|  | % of female targeted |  |  |  | % of female targeted |  |  |  | % of female targeted |  |  |  | % of female targeted
Output 1.1 Risk and vulnerability assessments conducted and updated | Indicator 1.1: No. of projects/programmes that conduct and update risk and vulnerability assessments | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
Output 1.2 Targeted population groups covered by adequate risk reduction systems | Core Indicator 1.2: No. of Early Warning Systems | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 2: Strengthened institutional capacity to reduce risks associated with climate-induced socioeconomic and environmental losses | Indicator 2: Capacity of staff to respond to, and mitigate impacts of, climate-related events from targeted institutions increased | Number of staff targeted |  | Sector | Capacity level | Number of staff targeted |  | Sector | Capacity level | Number of staff targeted |  | Sector | Capacity level | Number of staff targeted |  | Sector | Capacity level
|  | Total |  |  |  | Total |  |  |  | Total |  |  |  | Total
|  | % of female targeted |  |  |  | % of female targeted |  |  |  | % of female targeted |  |  |  | % of female targeted
Output 2.1 Strengthened capacity of national and sub-national centres and networks to respond rapidly to extreme weather events | Indicator 2.1.1: No. of staff trained to respond to, and mitigate impacts of, climate-related events | Total staff trained | % of female staff trained | Type |  | Total staff trained | % of female staff trained | Type |  | Total staff trained | % of female staff trained | Type |  | Total staff trained | % of female staff trained | Type
| Indicator 2.1.2: No. of targeted institutions with increased capacity to minimize exposure to climate variability risks | Type | Scale | Sector | Capacity level | Type | Scale | Sector | Capacity level | Type | Scale | Sector | Capacity level | Type | Scale | Sector | Capacity level
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 3: Strengthened awareness and owernship of adaptation and climate risk reduction processes | Indicator 3.1: Increase in application of appropriate adaptation responses | Percentage of targeted population applying adaptation measures |  | Sector |  | Percentage of targeted population applying adaptation measures |  | Sector |  | Percentage of targeted population applying adaptation measures |  | Sector |  | Percentage of targeted population applying adaptation measures |  | Sector
|  | 0% |  | Coastal management |  | 50% |  | Coastal management
Output 3: Targeted population groups participating in adaptation and risk reduction awareness activities | Indicator 3.1.1: Percentage in targeted population awareness of predicted adverse impacts of climate change, and of appropriate responses | No. of targeted beneficiaries | % of female participants targeted | Level of awareness |  | No. of targeted beneficiaries | % of female participants targeted | Level of awareness |  | No. of targeted beneficiaries | % of female participants targeted | Level of awareness |  | No. of targeted beneficiaries | % of female participants targeted | Level of awareness
|  | 0 | 0% | 1: Aware of neither |  | 2500 | 30% | 4: Mostly aware
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Target performance at completion |  |  |  | Target performance at completion
Outcome 4: Increased adaptive capacity within relevant development sector services and infrastructure assets | Indicator 4.1: Increased responsiveness of development sector services to evolving needs from changing and variable climate | Project/programme sector | Geographical scale | Response level |  | Project/programme sector | Geographical scale | Response level |  | Project/programme sector | Geographical scale | Response level |  | Project/programme sector | Geographical scale | Response level
| Core Indicator 4.2: Assets produced, developed, improved or strengthened | Sector | Targeted asset | Changes in asset (quantitative or qualitative) |  | Sector | Targeted asset | Changes in asset (quantitative or qualitative) |  | Sector | Targeted asset | Changes in asset (quantitative or qualitative) |  | Sector | Targeted asset | Changes in asset (quantitative or qualitative)
Output 4: Vulnerable development sector services and infrastructure assets strengthened in response to climate change impacts, including variability | Indicator 4.1.1: No. and type of development sector services to respond to new conditions resulting from climate variability and change | Number of services | Type |  | Sector | Number of services | Type |  | Sector | Number of services | Type |  | Sector | Number of services | Type |  | Sector
|  | Baseline information |  |  |  | Baseline information |  |  |  | Baseline information |  |  |  | Baseline information
Outcome 5: Increased ecosystem resilience in response to climate change and variability-induced stress | Indicator 5: Ecosystem services and natural resource assets maintained or improved under climate change and variability-induced stress | Natural resource improvement level |  | Sector | Type | Natural resource improvement level |  | Sector | Type | Natural resource improvement level |  | Sector | Type | Natural resource improvement level |  | Sector | Type
|  | 2: Partially effective |  | Coastal management | water areas | 4: Effective |  | Coastal management | water areas
Output 5: Vulnerable ecosystem services and natural resource assets strengthned in response to climate change impacts, including variability | Core Indicator 5.1: Natural Assets protected or rehabilitated | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Mangroves | 74480 | ha protected | 2: Partially effective | Mangroves | 74480 | ha protected | 4: Effective
|  | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Protected areas/National parks | 248810 | ha protected | 3: Moderately effective | Protected areas/National parks | 386612 | ha protected | 5: Very effective
|  | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Coasts | 386 | km protected | 2: Partially effective | Coasts | 386 | km protected | 4: Effective
|  | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Baseline information |  |  |  | Targeted performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 6: Diversified and strengthened livelihoods and sources of income for vulnerable people in targeted areas | Indicator 6.1: Increase in households and communities having more secure access to livelihood assets | No. of targeted households | % of female headed households | Improvement level |  | No. of targeted households | % of female headed households | Improvement level |  | No. of targeted households | % of female headed households | Improvement level |  | No. of targeted households | % of female headed households | Improvement level
|  | 0 | 0% | 1: No improvement |  | 2500 | 26% | 4: High improvement
| Indicator 6.2: Increase in targeted population's sustained climate-resilient alternative livelihoods | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
|  | 0 | 0% | From 0.5 to 1% | Agricultural-related | 600 | 5% | From 1% to 5% | Agricultural-related
|  | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
|  | 0 | 0% | From 0.5 to 1% | Tourism-related | 500 | 5% | From 1% to 5% | Tourism-related
|  | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
|  | 0 | 0% | From 0.5 to 1% | Fishing | 500 | 10% | From 1% to 5% | Fishing
|  | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
|  | 0 | 0% | From 0.5 to 1% | Livestock production | 400 | 5% | From 1% to 5% | Livestock production
Output 6 Targeted individual and community livelihood strategies strengthened in relation to climate change impacts, including variability | Indicator 6.1.1: No. and type of adaptation assets created or strengthened in support of individual or community livelihood strategies | Number of Assets | Type of Assets | Sector | Adaptation strategy | Number of Assets | Type of Assets | Sector | Adaptation strategy | Number of Assets | Type of Assets | Sector | Adaptation strategy | Number of Assets | Type of Assets | Sector | Adaptation strategy
|  | 0 | Financial capital | Coastal management | Supporting livelihoods | 6 | Financial capital | Coastal management | Supporting livelihoods
| Core Indicator 6.1.2: Increased income, or avoided decrease in income | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | 0 | Agricultural-related |  | 0 | 66792 | Agricultural-related |  | 4176.74
|  | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | 0 | Tourism-related |  | 0 | 66792 | Tourism-related |  | 6873.27
|  | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | 0 | Fishing |  | 0 | 66792 | Fishing |  | 8000
|  | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | 0 | Livestock production |  | 0 | 66792 | Livestock production |  | 4176.74
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 7: Improved policies and regulations that promote and enforce resilience measures | Indicator 7: Climate change priorities are integrated into national development strategy | Integration level |  |  |  | Integration level |  |  |  | Integration level |  |  |  | Integration level
|  | 2: Most not integrated |  |  |  | 4: Most
Output 7:Improved integration of climate-resilience strategies into country development plans | Indicator 7.1: No. of policies introduced or adjusted to address climate change risks | No. of Policies introduced or adjusted | Sector | Scale | Type | No. of Policies introduced or adjusted | Sector | Scale | Type | No. of Policies introduced or adjusted | Sector | Scale | Type | No. of Policies introduced or adjusted | Sector | Scale | Type
|  | 0 | Coastal management | National | Public policy | 5 | Coastal management | National | Public policy
| Indicator 7.2: No. of targeted development strategies with incorporated climate change priorities enforced | No. of Development strategies | Regulation |  | Effectiveness | No. of Development strategies | Regulation |  | Effectiveness | No. of Development strategies | Regulation |  | Effectiveness | No. of Development strategies | Regulation |  | Effectiveness
|  | 0 | 2: Partially not enforced (Most elements not implemented) |  | 1: Ineffective | 2 | 4: Enforced (Most elements implemented) |  | 4: Effective
Glacier lake outburst flood
|  | Inland flooding | fr | biological assets |  | Company policy | 5: Fully enforced (All elements implemented)
|  | Salinization | Decrease | land |  | Communication & Information policy | 4: Enforced (Most elements implemented)
|  | Drought | Same | water areas |  | Defense policy | 3: Partially enforced (Some elements implemented)
|  | Wind |  | subsoil assets | increased adpative capacity | Domestic policy | 2: Partially not enforced (Most elements not implemented) |  | Agribusiness
|  | Coastal flooding |  | air | achieved | Economic policy | 1: Not enforced (No elements implemented) |  | Agricultural-related | Financial capital
|  | Storm surge | Please choose |  | enhanced level of protection | Education policy |  |  | Agriculture | Human capital
|  | Hurricane | Selected | [5 empty] | Aquaculture | Physical capital
|  |  | Not relevant |  |  | 5: All (Fully integrated) |  |  | Construction/repairing business | Social capital
[6 empty] | 4: Most |  |  | Cultivation | Natural capital
[6 empty] | 3: Some |  |  | Fishing | Personal capital
Select | 5: All | Select |  |  | Community | 2: Most not integrated |  | Other | Forestry | Adaptation strategies
1 | 4: Almost all | Private | Type | Yes | Multi-community | 1: None |  | Agriculture | Handicrafts
2 | 3: Half | Public | Scale | No | Departmental |  |  | Coastal management | Livestock production
3 | 2: Some | NGO | Sector |  | National |  |  | Disaster risk reduction | Manufacturing
4 | 1: None |  |  |  |  | 5: Very high improvement | Established | Food security | other
|  | National |  |  |  | 4: High improvement | Maintained | Health | Services
|  | Regional |  |  |  | 3: Moderate improvement | Improved | Urban development | Tourism-related
|  | Local |  |  |  | 2: Limited improvement |  | Water management | Trading
[6 empty] | 1: No improvement |  | Multi-sector
|  | 1 -generated information is irrelevant, and neither the stakeholders reached nor the timeframe managed were achieved | 1: No info transferred on time | 4: High capacity | 5: Fully aware | 5: Highly responsive (All defined elements ) | 5: Fully improved | Roads | 5: Very effective
Asia-Pacific | NIE | 2 -the existence of some challenge in any of the three aspects of the indicator (generation of dissemination, stakeholders reached or timeframe managed) | 2: Somewhat info transferred | 3: Medium capacity | 4: Mostly aware | 4: Mostly responsive (Most defined elements) | 4: Mostly Improved | Gov Buildings | 4: Effective
Latin America and Caribbean | RIE | 3 -relevant information is generated and disseminated to all identified stakeholders on timely basis | 3: Info transferred on time | 2: Low capacity | 3: Partially aware | 3: Moderately responsive (Some defined elements) | 3: Moderately improved | Causeways | 3: Moderately effective
Africa | MIE |  |  | 1: No capacity | 2: Partially not aware | 2: Partially responsive (Lacks most elements) | 2: Somewhat improved | Airports | 2: Partially effective
Eastern Europe |  |  |  |  | 1: Aware of neither | 1: Non responsive (Lacks all elements ) | 1: Not improved | Schools | 1: Ineffective
| ha protected | [6 empty] | Training Centres
| ha rehabilitated | [5 empty] | Monitoring/Forecasting capacity | Hospitals
Afghanistan, Islamic Rep. of | km protected | [5 empty] | Policy/regulatory reform | Drinking water systems
Angola | km rehabilitated | 1: Risk knowledge | 1: No plans conducted or updated |  |  |  | Capacity development | Other
Albania |  | 2: Monitoring and warning service | 2: Undertaking or updating of assessments in progress |  |  | Communication & Information policy | Sustainable forest management
Argentina |  | 3: Dissemination and communication | 3: Risk and vulnterability assessments completed or updated |  |  | Domestic policy | Strengthening infrastructure | 1: Health and Social Infrastructure (developed/improved)
Armenia | Forests | 4: Response capability |  |  |  | Economic policy | Supporting livelihoods | 2: Physical asset (produced/improved/strenghtened)
Antigua and Barbuda | Mangroves |  |  |  |  | Education policy | Mangrove reforestation
Azerbaijan | Coasts |  | From 0 to 0.5% |  |  | Energy policy | Coastal drainage and infrastructure
Burundi | Rangelands |  | From 0.5 to 1% |  |  | Environmental policy | Irrigation system
Benin | Cultivated land/Agricultural land |  | From 1% to 5% |  |  | Foreign policy | Community-based adaptation
Burkina Faso | Catchment area/Watershed/Aquifer |  | From 5% to 10% |  |  | Health policy | Erosion control
Bangladesh | Protected areas/National parks |  | From 10% to 20% |  |  | Housing policy | Soil water conservation
Bulgaria | Other |  | From 20% to 30% |  |  | Human resource policies | Microfinance
Bahrain |  |  | From 30% to 40% |  |  | Information policy | Special Program for women
Bahamas, The |  |  | From 40% to 50% |  |  | Macroeconomic policy | Livelihoods
Bosnia and Herzegovina |  |  | Above 50% |  |  | Monetary policy | Water storage
Belarus | [5 empty] | Population policy | ICT and information dissemination
Belize | [5 empty] | Private policy
Bolivia | [5 empty] | Public policy
Brazil | [5 empty] | Science policy
Barbados | [5 empty] | Social policy
Bhutan |  | 3- relevant information is generated and disseminated to all identified stakeholders on timely basis |  |  |  | Transportation policy
Botswana |  | describe |  |  |  | Urban policy
Central African Republic |  | 2- the existence of some challenge in any of the three aspects of the indicator |  |  |  | Water policy
Chile |  | describe |  |  |  | Other policy
China, People's Republic of |  | 1- generated information is irrelevant and neither the stakeholders reached nor the timeframe managed were achieved
Cote d'Ivoire |  | describe
Cameroon
Congo, Dem. Rep. of
Congo, Republic of
Cook Islands
Colombia
Comoros
Cape Verde
Costa Rica
Cuba
Czech Republic
Djibouti
Dominica
Dominican Republic
Algeria
Ecuador
Egypt
Eritrea
Estonia
Ethiopia
Fiji
Micronesia, Fed. States of
Gabon
Georgia
Ghana
Guinea
Gambia, The
Guinea-Bissau
Equatorial Guinea
Grenada
Guatemala
Guyana
Honduras
Croatia
Haiti
Hungary
Indonesia
India
Iran, Islamic Republic of
Jamaica
Jordan
Kazakhstan
Kenya
Kyrgyz Republic
Cambodia
Kiribati
Saint Kitts and Nevis
Korea, Republic of
Lao People's Democratic Republic
Lebanon
Liberia
Libya
Saint Lucia
Sri Lanka
Lesotho
Lithuania
Latvia
Morocco
Moldova
Madagascar
Maldives
Mexico
Marshall Islands
Macedonia, former Yugoslav Republic of
Mali
Malta
Myanmar
Montenegro
Mongolia
Mozambique
Mauritania
Mauritius
Malawi
Malaysia
Namibia
Niger
Nigeria
Nicaragua
Niue
Nepal
Nauru
Oman
Pakistan
Panama
Peru
Philippines
Palau
Papua New Guinea
Poland
Korea, Dem. People's Rep. of
Paraguay
Romania
Russian Federation
Rwanda
Saudi Arabia
Sudan
Senegal
Solomon Islands
Sierra Leone
El Salvador
San Marino
Serbia
Sao Tome and Principe
Suriname
Slovak Republic
Slovenia
Swaziland
Seychelles
Syrian Arab Republic
Chad
Togo
Thailand
Tajikistan
Turkmenistan
Tonga
Trinidad and Tobago
Tunisia
Turkey
Tuvalu
Tanzania
Uganda
Ukraine
Uruguay
Uzbekistan
Saint Vincent and the Grenadines
Venezuela
Vietnam
Vanuatu
Samoa
Yemen, Republic of
South Africa
Zambia
Zimbabwe
Timor-Leste

## Units for Indicators
Fund Outcome Indicator Units
1. Generation of relevant data, Stakeholders, and Timeliness 2.1. Include both qualitative and quantitative measures of capacity level within targeted institutions 2.2. Number (men and women and other vulnerable groups) 3.1. Use scale from 1 to 5: 5: Fully aware 4: Mostly aware 3: Partially aware 2: Partially not aware 1: Aware of neither predicted adverse impacts of climate change nor of appropriate responses 3.2. Use scale from 1 to 5: 5: All 4: Almost all 3: Half 2: Some 1: None 4.1. Summarize in an overall scale (1-5): 5: Highly responsive (All defined elements ) 4: Mostly responsive (Most defined elements) 3: Moderately responsive (Some defined elements) 2: Partially responsive (Lacks most elements) 1: Non responsive (Lacks all elements ) 4.2. Summarize in an overall scale (1-5): 5: Fully improved 4: Mostly Improved 3: Moderately improved 2: Somewhat improved 1: Not improved 5. Depends on the targeted natural asset: Biological (species): measure through changes in population numbers (dynamics, structure, etc.) Land: measure changes in hectares. Baseline data will be necessary to estimate the change. Supporting indicators baseline and target (as well as contextual information) are needed such as the following: Farmers adopting recommended technologies, Ha. of land improved, Average deforestation rate Etc. Use scale from 1 to 5. 5: Very effective (All elements are present) 4: Effective (Most elements are present) 3: Moderately effective (Some elements are present) 2: Partially effective (Most elements are not present) 1: Ineffective (No elements are present) 6.1. Summarize in an overall scale (1-5): 5: Very high improvement 4: High improvement 3: Moderate improvement 2: Limited improvement 1: No improvement 6.2. Household income by source of livelihood in project area (USD) prior and post project intervention 7. Summarize in an overall scale (1-5). 5: All (Fully integrated) 4: Most 3: Some 2: Most not integrated 1: None
Fund Output Indicator Units
1.1. Number, sector(s) and level(s) of projects or interventions in separate fields of monitoring plan 1.2. Number 2.1.1. Number of staff (male/female) of targeted institutions: a. Obtain baseline information: total number of staff from targeted institutions b. Define target 2.1.2. Number of staff (male/female) of targeted institutions: a. Obtain baseline information: total number of staff from targeted institutions b. Define target: needs to be defined by project proponents 2.2.1. Quantitative: Percentage (includes women – and other vulnerable groups – and men). Qualitative: Adequacy: include direct analysis of major areas; adequacy/effectiveness of systems or analysis of perceptions of populations and institutions. 2.2.2. Number (broken down by gender and, if possible, by vulnerable groups defined in the area of intervention) of people 3.1. Number and type (in separate columns) at local level. 3.2. Number 4.1. Number and type 4. 2. Number and type (entered in separate columns) 5. Number of interventions by type of natural asset and intervention 6.1. Number and type (in separate columns of monitoring plan) 6.2. Income sources per household; description of income source and number of households. 7.1. Number/Sector 7.2. Number; Effectiveness (see previous indicator) through enforcement level.